|  |
| --- |
| **JDAI County Committee Work Plan 2022** |
| **Goal 1: Reduce the number of low-risk youth entering DYS detention** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Adopt the Cambridge Safety Net program in Lowell | Find a host agency for the program | In 2020 the average age at Detention Admission in Middlesex County was 16 | Reduction in the number of youths that appear in Lowell CourtIncreased number of youths receiving Diversion in Middlesex County. | Limited resourcesAvailability of fundingNo sustainability plans.  | Within the next 6 months |
| Operationalize the DYS Diversion Project learning lab led by NFI. | Present Diversion to key referral sources (Judges, court clerk, police, DA’s office), key stakeholders (JDAI committee meeting), community partners. |  | An increase in the number of youths of color receiving accessing diversion. | Receiving referrals from all stakeholders.Availability of mental health services for youths. | Ongoing (multi-year process) |
| **Goal 2: Reduce the length of stay of youth in detention** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Decrease the number of DCF involved youth from entering detention. | Reinstate DIY Subcommittee Develop DIY subcommittee goals | **DCF Involvement in 2020:**Cambridge:55.6%Framingham:84.6%Lowell:55%Waltham:14.3% | A reduction in the ALOS for DIY | Difficulty finding appropriate placements for DIYDIY tend to be high needs low risk | Ongoing  |
| **Goal 3: Reduce ethnic and racial disparity for youth in the juvenile justice system** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Increase knowledge and awareness of the role bias in decision making. Decrease the number of youths of color in detention | Host series of Racial Justice training for Diversion referrersTrain facilitators from Middlesex to administer JDAI Race Equity trainings | **Race 2020****Cambridge:**Black: 55.6Hispanic:22.2White: 22.2**Lowell:**Black: 44.4Hispanic: 44.4White: 11.1 | Increase the number of youths of color accessing diversion.Decrease the number of youths of color entering detention from Middlesex County. | Educating county members on the importance of continuing the work of JDAI. Overall detention numbers have decreased, however the rates at which youth of color are entering detention has increase.  | Ongoing  |
| **Goal 4: Replicate JDAI with fidelity at the local level** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Increase the number of JDAI Middlesex County participantsIncrease committee members knowledge of the JDAI 8 core strategies | Conduct “Flash trainings” on each of the 8 JDAI Core Strategies as a refresher for existing members and as a learning tool for new members. | New members have joined the JDAI Middlesex County Committee | Members increased knowledge of the JDAI 8 core strategies.Members begin to use 8 core strategies in their daily work. | Members consistency in attending meetings | Twice per year |