## Workplan2014
Priority: Establish Council priority areas and tasks for 2014.
Desired Outcome: Successfully fulfill Implementation Council charge and council member priorities.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
1 | Develop 2014 Workplan | Hear priority areas for Council input from MassHealth. | 2014-02-01 | 2014-03-01 | Implementation Council members & Priorities Workgroup | X
2 |  | Gather feedback from all Council members on Council priorities for the coming year. | 2014-02-01 | 2014-03-01 | Chair and Council staff | X
3 |  | Establish a working group to develop a workplan based on Council priorities. | 2014-02-01 | 2014-04-01 | Chair and Workgroup members | X
4 |  | Develop an initial budget to present to MassHealth to complete the immediate activities in the workplan. | 2014-05-01 | 2014-06-01 | Chair and Workgroup members
5 |  | Seek Council approval of 2014 Workplan at May 2014 Implementation Council meeting. | 2014-04-01 | 2014-05-01 | Implementation Council Members
6 |  | Review and revise workplan on quarterly basis. | 2014-08-14 | 2015-06-01 | Implementation Council Members
7 |  | Determine Implementation Council member interest and willingness to participate in workplan activities and ongoing Council activities. If needed, determine process for adding new Council members. | 2014-10-14 | 2014-11-15 | Implementation Council Members
Priority: Provide input on auto-assignment and broader roll-out
Desired Outcome: MassHealth uses data and indicators recommended by Implementation Council to inform and shape future rounds of auto-assignment.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
8 | Recommend indicators to measure success of auto-assignment roll out and preparedness for future phases of auto-assignment. | Hear from MassHealth about the current indicators or criteria used for determining One Care plan capacity for auto-assignment enrollments. | 2014-04-14 | 2014-06-01 | Implementation Council and MassHealth
9 |  | Review EIP Survey data to determine the effectiveness of MassHealth notices and informational documents in reaching enrollees and providing them with the information needed to make enrollment decisions. | 2014-05-15 | 2015-04-01 | EIP Work Group
10 |  | Establish indicators to measure plan and provider competency with working with One Care eligible populations, including complying with the ADA; identify data source. | 2014-05-01 | 2014-09-01 | Implementation Council Members and Quality Work Group (continuation of EIP)
11 |  | Establish indicators to measure plan and provider capacity; identify data source. | 2014-05-01 | 2014-09-01 | Implementation Council Members and Quality Work Group (continuation of EIP)
12 |  | Determine how auto-assignment is effecting homeless populations by collecting anecdotal data and identifying additional data sources. | 2014-07-01 | 2014-09-14 | Implementation Council Members
13 |  | Determine how auto-assignment is effecting non-English speaking and English as a Second Language populations, including Latinos and Deaf individuals. | 2014-09-01 | 2015-03-01 | Implementation Council members and Quality Work Group (continuation of EIP)
14 |  | Recommend interventions to address identified issues. | 2014-07-01 | Ongoing | Implementation Council Members and Quality Work Group (continuation of EIP)
Priority: Participate in decision-making regarding the development and implementation of the IL-LTSS Coordinator.
Desired Outcome: Members experience better access to LTSS under One Care with the assistance of competent and accessible IL-LTSS Coordinators.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
15 | Ensure success of the IL-LTSS Coordinator role. | Participate in IL-LTSS Coordinator Stakeholder Group and provide regular updates to the Council on IL-LTSS Coordinator rollout and barriers. | 2014-03-14 | Ongoing | Implementation Council Representatives
16 |  | Invite stakeholders, including consumers and IL-LTSS Coordinators, to provide anecdotal evidence of the IL-LTSS Coordinator roll out at a Council meeting and to submit information via email. | 2014-07-01 | 2015-06-01 | Implementation Council members and stakeholders
17 |  | Review data collected by MassHealth around enrollee LTSS needs and use of the IL-LTSS Coordinator and develop recommendations about how to increase access to use of the IL-LTSS Coordinator. | 2014-06-01 | 2015-06-01 | Implementation Council members and stakeholders
18 |  | Develop indicators to measure consumer experience with IL-LTSS Coordinators. | 2014-06-01 | 2014-09-01 | EIP Work Group
Priority: Monitor the overall performance of the Demonstration, including the ability of plans to meet the unmet needs on One Care enrollees.
Desired Outcome: Implementation Council is used as an active workgroup to hear concerns regarding the roll out of One Care and address issues raised throughout the demonstration.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
19 | Ensure consumers have user-friendly access to information on One Care online. | Provide feedback to MassHealth on Council member experiences reviewing the user-friendliness of the One Care plan websites and affiliated sites (i.e. the MassHealth One Care website, Ombudsman site, and website with SHINE information). | 2014-05-01 | 2014-06-15 | Implementation Council members
20 | Request updates from One Care plans, One Care Ombudsman and SHINE. | Determine additional topics for One Care plan quarterly updates beginning in May 2014. Example topics include: financing, and successes and challenges. | 2014-04-01 | 2015-05-01 | Council members, plans, and MassHealth
21 |  | Hear updates from One Care plans on topics determined by the Council. | 2014-05-01 | 2015-06-01
22 |  | Hear updates from One Care Ombudsman on semi-annual basis on topics determined by the Council. | 2014-04-14 | 2015-01-01 | Implementation Council members
23 |  | Hear updates from SHINE on semi-annual basis on topics determined by the Council. | 2014-04-01 | 2015-06-01 | Implementation Council members
24 | Collaborate with SHINE to ensure consumers have access to necessary information from SHINE Counselors and are aware of SHINE as a resource. | Hear an overview of the SHINE program to understand what information is available to SHINE counselors. | 2014-04-01 | 2014-04-01 | Implementation Council members and SHINE | X
25 |  | Determine how best to partner with SHINE on outreach efforts made to hard to reach and minority populations. Provide recommendations, including data collection elements, if applicable. | 2014-04-01 | 2014-09-15 | Implementation Council members and SHINE
26 | Measure effect of One Care financing on utilization of services. | Determine what data on service utilization, quality, and ADA compliance, including communication access, will be available from MassHealth and on what timeline. | 2014-04-14 | 2014-06-01 | Implementation Council members and MassHealth
27 |  | Determine what data elements should be considered when monitoring the program and access to services. Examples include: use of acute hospital, psychiatric hospital, PCA, Day hab, home modifications, certified peer specialists, transportation. | 2014-06-14 | 2014-09-01 | Implementation Council members
28 |  | Develop or recommend mechanism for measuring medical and LTSS quality of services and utilization of service by One Care plans over time. | 2015-01-01 | 2015-06-01 | Implementation Council members
29 | Promote awareness of role of Recovery Learning Communities and the Peer Specialist role in One Care and on Care Teams. | Determine the extent of the use of Recovery Learning Communities and Certified Peer Specialists on One Care care teams. | 2014-08-01 | 2014-10-01 | Implementation Council members and MassHealth
30 |  | Provide recommendations to MassHealth on how to best promote awareness of Certified Peer Specialists and increase access to the role. | 2014-09-01 | 2014-11-01 | Implementation Council members
31 | One Care enrollees have opportunity to self-identify sexual orientation and gender identity during the comprehensive assessment. | Continue to work with MassHealth to develop recommended mechanisms for One Care plans to offer enrollees the opportunity to self-identify gender identity and sexual orientation during the comprehensive assessment process. | 2014-06-01 | 2014-08-01 | MassHealth and Implementation Council members.
Priority: Provide input on outreach strategy to underserved populations.
Desired Outcome: Information about One Care is provided in an accessible and culturally competent way and reaches all target populations throughout the state.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
32 | Enhance One Care outreach efforts to broad and diverse populations. | Participate in outreach events with partner organizations targeting hard to reach and under-resourced populations. | 2014-05-14 | Ongoing | Implementation Council members
33 |  | Host a tele-town hall with One Care stakeholders to provide information on the program and to hear from stakeholders about their One Care experiences and questions. | 2014-06-01 | 2014-11-01 | Implementation Council members
34 |  | Hold semi-annual public hearings in different areas of the state to provide information on One Care and to hear from stakeholders about their One Care experiences and concerns. Activities could include tele-town hall component or could occur in conjunction with outreach efforts. | 2014-09-14 | Ongoing | Implementation Council members
35 | Build a cohort of the CHW workforce who are informed of and engaged in One Care. | Connect with Community Health Worker (CHW) representatives to provide information on One Care and learn how CHWs fit into One Care service delivery and outreach. | 2014-01-14 | Ongoing | Implementation Council members
36 |  | Enhance relationships between CHWs, ILCs and RLCs. Ex. Host forum that identifies next steps and measurable outcomes, develop 2-3 pilots. | 2014-08-01 | TBD | Implementation Council members
Priority: Provide input on provider outreach and education/training
Desired Outcome: Providers throughout the state are informed about One Care and can appropriately answer questions of their clients in regards to the program.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
37 | Ensure providers are receiving adequate and appropriate information to develop financial, and other internal systems necessary to adequately serve enrollees | Seek feedback from providers on MassHealth and One Care plan trainings. | 2014-06-01 | 2015-03-01 | Implementation Council members and Provider Strategy Work Group
38 |  | Seek input from providers on current concerns regarding One Care (Ex. Focus groups or survey of providers.) | 2014-08-01 | 2014-09-01 | Implementation Council members and Provider Strategy Work Group
39 |  | Provide input on provider outreach strategy and activities informed by feedback received directly from providers and consumers. | 2014-09-01 | 2014-02-15 | Implementation Council members and Provider Strategy Work Group
Priority: Provide recommendations on enrollee privacy.
Desired Outcome: One Care enrollee privacy and confidentiality is maintained through adequate programmatic mechanisms developed and implemented by One Care plans.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
40 | Ensure enrollee privacy is protected. | Determine what individual One Care plans are doing to ensure privacy and confidentiality. | 2014-08-01 | 2014-10-01 | Implementation Council members, MassHealth and One Care plans
41 |  | Provide guidance on what data should be collected to measure how well One Care plans are protecting enrollee privacy. Ex. Collect consumer feedback. | 2014-08-01 | 2014-11-01 | Implementation Council members
42 |  | Determine how consumers perceive maintenance of privacy and confidentially by One Care plans | 2014-09-01 | 2014-12-01 | Quality Workgroup
Priority: Provide recommendations on independent monitoring and participate in ongoing quality monitoring and Early Indicators Project.
Desired Outcome: Council member and community input further improves implementation and quality monitoring within One Care.
# | Major Objectives | Key Tasks | Start Date | Due Date | Responsible Party | Complete
43 | Ensure Implementation Council fulfillment of charge of playing a key role in monitoring access to health care. | Recommend a mechanism for the continuation of the Early Indicators Project workgroup, or similar workgroup, to track access to services and experiences of enrollees beyond the initial roll out of One Care. | 2014-04-01 | 2014-06-01 | Implementation Council members
44 |  | Hear from MassHealth regarding the quality process and timeline; form a workgroup consistent with the timeline. | 2014-05-01 | 2014-06-14 | Implementation Council members and MassHealth

## GanttChart
Implementation Council Workplan Gantt Chart |  |  |  | Full Council |  |  | EIP/Quality |  |  | Other |  |  | Priorities Workgroup
# | Obj. | Key Tasks | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01
1 | Develop 2014 Workplan | Hear priority areas for Council input from MassHealth. | bar: 2014-02-01
2 |  | Gather feedback from all Council members on Council priorities for the coming year. | bar: 2014-02-01
3 |  | Establish a working group to develop a workplan based on Council priorities. | bar: 2014-02-01 to 2014-03-01
4 |  | Develop a budget to present to MassHealth to complete the activities in the workplan. | bar: 2014-05-01 to 2014-06-01
5 |  | Seek Council approval of 2014 Workplan at May 2014 Implementation Council meeting. | bar: 2014-04-01
6 |  | Review and revise workplan on quarterly basis. | bar: 2014-08-01; 2014-11-01; 2015-02-01; 2015-05-01
7 |  | Determine Implementation Council member interest and willingness to participate in workplan activities and ongoing Council activities. If needed, determine process for adding new Council members. | bar: 2014-10-01
8 | Auto-assignment indicators | Hear from MassHealth about the current indicators or criteria used for determining One Care plan capacity for auto-assignment enrollments. | bar: 2014-04-01 to 2014-05-01
9 |  | Review EIP Survey data to determine the effectiveness of MassHealth notices and informational documents in reaching enrollees and providing them with the information needed to make enrollment decisions | bar: 2014-05-01 to 2015-03-01
10 |  | Establish indicators to measure plan and provider competency with working with One Care eligible populations, including complying with the ADA; identify data source. | bar: 2014-05-01 to 2014-08-01
11 |  | Establish indicators to measure plan and provider capacity; identify data source. | bar: 2014-05-01 to 2014-08-01
12 |  | Determine how auto-assignment is effecting homeless populations by collecting anecdotal data and identifying additional data sources. | bar: 2014-07-01 to 2014-08-01
13 |  | Determine how auto-assignment is effecting non-English speaking and English as a Second Language populations, including Latinos and Deaf individuals. | bar: 2014-09-01 to 2015-02-01
14 |  | Recommend interventions to address identified issues. | bar: 2014-07-01 to 2015-06-01
15 | Success of IL-LTSS Coordinator | Participate in IL-LTSS Coordinator Stakeholder Group and provide regular updates to the Council on IL-LTSS Coordinator rollout and barriers. (2 Council reps identified) | bar: 2014-03-01 to 2015-06-01
16 |  | Invite stakeholders, including consumers and IL-LTSS Coordinators, to provide anecdotal evidence of the IL-LTSS Coordinator roll out at a Council meeting and to submit information via email. | bar: 2014-07-01; 2014-10-01; 2015-01-01; 2015-04-01
17 |  | Review data collected by MassHealth around enrollee LTSS needs and use of the IL-LTSS Coordinator and develop recommendations about how to increase access to use of the IL-LTSS Coordinator. | bar: 2014-06-01 to 2015-06-01
18 |  | Develop indicators to measure consumer experience with IL-LTSS Coordinators. | bar: 2014-06-01 to 2014-08-01
19 | Online | Provide feedback to MassHealth on Council member experiences reviewing the user-friendliness of the One Care plan websites and affiliated sites (i.e. the MassHealth One Care website, Ombudsman site, and website with SHINE information). | bar: 2014-05-01
20 | Request updates | Determine additional topics for One Care plan quarterly updates beginning in May 2014. Example topics include: financing, and successes and challenges. | bar: 2014-04-01; 2014-07-01; 2014-10-01; 2015-01-01; 2015-04-01
21 |  | Hear updates from One Care plans on topics determined by the Council. | bar: 2014-05-01; 2014-08-01; 2014-11-01; 2015-02-01; 2015-05-01
22 |  | Hear updates from One Care Ombudsman on semi-annual basis on topics determined by the Council. | bar: 2014-03-01; 2014-09-01; 2015-03-01
23 |  | Hear update from SHINE on semi-annual basis. | bar: 2014-04-01; 2014-10-01; 2015-04-01
24 | SHINE Collaboration | Hear an overview of the SHINE program to understand what information is available to SHINE counselors. | bar: 2014-04-01
25 |  | Determine how best to partner with SHINE on outreach efforts made to hard to reach and minority populations. Provide recommendations, including data collection elements, if applicable. | bar: 2014-04-01 to 2014-08-01
26 | Service Utilization | Determine what data on service utilization, quality, and ADA compliance will be available from MassHealth and on what timeline. | bar: 2014-04-01 to 2014-05-01
27 |  | Determine what data elements should be considered when monitoring the program and access to services. Examples include: use of acute hospital, psychiatric hospital, PCA, Day hab, home modifications, certified peer specialists, transportation. | bar: 2014-06-01 to 2014-08-01
28 |  | Develop or recommend mechanism for measuring medical and LTSS quality of services and utilization of service by One Care plans over time. | bar: 2015-01-01 to 2015-06-01
29 | Use of Peers | Determine the extent of the use of Certified Peer Specialists on One Care care teams. | bar: 2014-08-01 to 2014-09-01
30 |  | Provide recommendations to MassHealth on how to best promote awareness of Certified Peer Specialists and increase access to the role. | bar: 2014-09-01 to 2014-10-01
31 | LGBT | Continue to work with MassHealth to develop recommended mechanisms for One Care plans to offer enrollees the opportunity to self-identify gender identity and sexual orientation during the comprehensive assessment process. | bar: 2014-06-01 to 2014-07-01
32 | Outreach | Participate in outreach events with partner organizations targeting hard to reach and under-resourced populations. | bar: 2014-05-01 to 2015-06-01
33 |  | Host a tele-town hall with One Care stakeholders to provide information on the program and to hear from stakeholders about their One Care experiences and questions. | bar: 2014-06-01 to 2014-10-01
34 |  | Hold semi-annual public hearings in different areas of the state to provide information on One Care and to hear from stakeholders about their One Care experiences and concerns. Activities could include tele-town hall component or could occur in conjunction with outreach efforts. | bar: 2014-09-01; 2015-03-01
35 | CHWs | Connect with Community Health Worker (CHW) representatives to provide information on One Care and learn how CHWs fit into One Care service delivery and outreach.
36 |  | Enhance relationships between CHWs, ILCs and RLCs. Ex. Host forum that identifies next steps and measurable outcomes, develop 2-3 pilots. | bar: 2014-08-01
37 | Provider Education | Seek feedback from providers on MassHealth and One Care plan trainings. (Provider Strategy Workgroup) | bar: 2014-06-01 to 2015-02-01
38 |  | Seek input from providers on current concerns regarding One Care Ex. Focus groups or survey of providers. (Provider Strategy Workgroup) | bar: 2014-08-01
39 |  | Provide input on provider outreach strategy and activities informed by feedback received directly from providers and consumers. (Provider Strategy Workgroup) | bar: 2014-09-01 to 2015-01-01
40 | Privacy | Determine what individual One Care plans are doing to ensure privacy and confidentiality. | bar: 2014-08-01 to 2014-09-01
41 |  | Provide guidance on what data should be collected to measure how well One Care plans are protecting enrollee privacy. Ex. Collect consumer feedback. | bar: 2014-08-01 to 2014-10-01
42 |  | Determine how consumers perceive maintenance of privacy and confidentially by One Care plans | bar: 2014-09-01 to 2014-11-01
43 | IC Charge | Recommend a mechanism for the continuation of the Early Indicators Project workgroup, or similar workgroup, to track access to services and experiences of enrollees beyond the initial roll out of One Care. | bar: 2014-04-01 to 2014-05-01
44 |  | Hear from MassHealth regarding the quality process and timeline; form a workgroup consistent with the timeline. | bar: 2014-05-01