## Slide 1: 2015-2016 Implementation Council Work Plan
Overview and Discussion on Leadership

## Slide 2: Overview
2015-2016 Implementation Council Work Plan includes:
  4 goal areas
  15 objectives
Activities will be completed by Council members
Identified partners will be invited to participate
  Coordination needed to ensure MassHealth and One Care plan participation

## Slide 3: GANTT Chart
Objective/Month | Sept15 | Oct 15 | Nov15 | Dec 15 | Jan 16 | Feb 16 | Mar 16 | Apr 16 | May 16 | June 16 | July 16 | Aug 16 | Sept 16 | Oct 16 | Nov 16 | Dec 16
Goal 1: Identify and, when possible, address challenges experienced by One Care stakeholders and promote successes that can be implemented by MassHealth, the One Care Plans, and One Care Ombudsman. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 Work with One Care Plan Representatives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.2 Hear form the One Care Ombudsman |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.3 Identify challenges and successes from Stakeholder perspective |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Goal 2: One Care enrollees have access to covered services as needed, including medical, behavioral health, and LTSS services, and essential social services such as housing and employment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.1 Collaborate on LTS-C role |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.2 Support FTC exit and transition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.3 Promote One Case Sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.4 Promote care for homeless enrollees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.5 Educate One Care plans and providers on Recovery model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.6 Work with MassHealth on Encounter Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: GANTT Chart cont.
Objective/Month | Sept15 | Oct15 | Nov15 | Dec15 | Jan 16 | Feb16 | Mar 16 | Apr 16 | May 16 | June 16 | July 16 | Aug 16 | Sept 16 | Oct 16 | Nov 16 | Dec 16
Goal 3: One Care enrollees will receive high quality care. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.1 Promote integration of primary care & behavioral health |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.2 Tools to compare One Care plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Goal 4: Public education and outreach activities will reach all potential One Care enrollees and providers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.1 Outreach strategies for reaching diverse communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.2 Tele-Town Hall |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.3 Recruiting providers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.4 Translation of material |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Proposed Leadership Structure
  Each goal area (4) has a leadership team
  Each objective (15) has an Implementation Council point person
  All Council members can provide input, assist with activities, and join workgroups

## Slide 6: Leadership Teams
Goal 1
  Jeff Keilson, Olivia Richard, David Matteodo
Goal 2
  Dale Mitchell, Dennis Heaphy, Bruce Bird, Joe Finn, Bob Rousseau, Howard Trachtman, Olivia Richard
Goal 3
  Bruce Bird, Bob Rousseau, Howard Trachtman, Dennis Heaphy
Goal 4
  Florette Willis, Jeff Keilson, Dennis Heaphy, Suzann Bedrosian

## Slide 7: Leadership Team Roles
Plan for how the Council will accomplish objectives
Determine resource needs
  Partners (ie. MassHealth, One Care plans, other)
  Staff support
  Other
Ensure timing of activities is appropriate
  Aligns with project need
  Considers potential resource constraints
    Partner availability and competing priorities
Report back to Council on progress

## Slide 8: Objective Point Person Roles
Review and refine activities and timeline
Provide leadership to accomplish tasks
Work with Council staff to:
  Plan accessible meetings
  Develop meeting materials
  Develop deliverables

## Slide 9: Next Steps
Approval of Work Plan
Meeting of Leadership Teams
Finalization of:
  Work plan timeline
  Participants
  Partners