## Sheet1
DMH Project #2019-117 Security Upgrades for Hadley Building
BD-19-1022-DMH08-8210C-39572
Question # | Created Date | User Created | Question Subject | Question | Answer
1 | 2019-05-16 | Francis DellaFera/Advance Security Integration, | Bid BD-19-1022-DMH08-8210C-39572_Security101 RFI#1 | 1) Is there a certificate/verification available that states the facility is asbestos free? 2) The scope of work states eight (8) cameras but the diagram shows Nine (9). What is the correct count. 3) The scope of work states twelve (12) doors but the tour indicated there are thirteen (13) doors. What is the correct count? Please provide a door list of exact locations. 4) The cameras are specified as either 4MpX Dome or 8MpX 180 degree Dome cameras. Are there particular brands that are preferred? 5) For the recorder ? is there a particular Video Management Software (VMS) that is preferred? What is the retention time period for the video cameras? 6) How large are the two monitors? One in IT? One at Security? 7) Is there a request for additional work station viewing of the video system? If so, how many? Will this be software only applied on an existing PC? 8) What are the hours that work can be conducted? 9) What, if any, are the restrictions in performing work in the facility? 10) During the tour the IT closets at the basement level and 2nd floor were shown. Can the installer use these locations to home run the equipment to and then network between the IT closets? 11) Are wireless access control locks permitted in the response? 12) What is the expected warranty period of the systems? 13) What is the training to be conducted on the systems? | 1) The Building is not asbestos containing material (ACM) free. The old steam pipe chases contain asbestos. However, there is no work contemplated in the pipe chases. 2) Please see attached revised figure. 3) Please see the revised figure. 4) The cameras must be not be on the list of manufacturers or an OEM of any manufacturer that are restricted which by law cannot be sold to US government entities. Any camera manufacturers must be compliant with US laws and regulations. 5) The NVR and Viewstation solution required is manufactured by IronVIDEO and the access control server is manufactured by IronAC. No subsitutions for the NVR, Viewstations or Access Control server will be allowed. 6) The monitors must be a minimum size of 23". 7) There will need to be a IronPC viewing station for the PD security desk and a IronPC viewing station at the head end location. No substitutions will be allowed. The system will not be connected to or accessed on the business LAN. 8) Normal business hours. Contractor will have to coordinate schedule and work with Hadley administration. 11) Wireless access control products are not permitted. 12) Minimum warranty is 1 year. 13) Administrators and Operators will need to be trained as to the functions needed to be performed on the systems
2 | 2019-05-20 | Paul Ziemba/Setronics Corp | Access Control Software | Does the software for the access control have to be DSX or can it be equal? | The access control software must be DSX running on a IronAC access control server. No substitutions will be allowed.
3 | 2019-05-20 | Paul Ziemba/Setronics Corp | Access Control doors | Can you supply a diagram showing door numbers and locations? | Please the attached revised figure.
4 | 2019-05-20 | Paul Ziemba/Setronics Corp | Access Control doors | Do you want all doors to be full access doors with read in capability, or are some doors to ONLY be monitored for "door open"? | Please the attached revised figure.
5 | 2019-05-20 | Paul Ziemba/Setronics Corp | Hazardous Materials | Are there any asbestos or hazardous materials in the building to be aware of? | The Building is not asbestos containing material (ACM) free. The old steam pipe chases contain asbestos. However, there is no work contemplated in the pipe chases.
6 | 2019-05-20 | Paul Ziemba/Setronics Corp | IDF | Can you indicate where and on what floor the IDFs are? | The system will be placed in the in the first floor ICF room (Room 101) as indicated on the revised figure.
7 | 2019-05-20 | Paul Ziemba/Setronics Corp | Access credentials | How many access credentials (cards, fobs, etc) do you want to be supplied in the bid or is this to be separate? | Minimum of 200 cards. Schlage 9520.
8 | 2019-05-20 | Paul Ziemba/Setronics Corp | Surveillance Cameras | The supplied drawing shows 9 camera locations, but the narrative calls for 8. How many cameras do you actually want? | Please the attached revised figure. We are requesting a total of nine cameras
9 | 2019-05-20 | Paul Ziemba/Setronics Corp | License Plate camera | At the walkthrough, a camera capable of picking up license plates at the main entrance was discussed. do you want that to be part of this bid? | The cameras need to be as what was specified in the documentation.
10 | 2019-05-20 | Paul Ziemba/Setronics Corp | Surveillance Cameras | The bid says to "supply and install la new monitor for the Security station in the main lobby." If the security officer already has a PC and monitor connected to the network, this may best be accomplished using the existing hardware with a software client loaded onto that PC. Would you like to do that rather than add a separate "monitor only" connected to the NVR in the IT room? | There will need to be a IronPC viewing station for the PD security desk and a IronPC viewing station at the head end location. No substitutions will be allowed.
11 | 2019-05-21 | Will Bissonnette/Sullivan and McLaughlin | TAA Compliance for all Video Surveillance Cameras | Do the cameras all have to be TAA Compliant? | Yes
12 | 2019-05-21 | Paul Ziemba/Setronics Corp | Access Control | Do you want the readers to be readers only, or readers with pin pad? | The readers required are the Schlage AptiQ MT15 readers.
13 | 2019-05-22 | Ben Jacobellis/Electronic Security and Control Systems Inc | Drawings and Specs | Will an updated drawing package be made available based on information from the walk thru? I.E; door quantities and locations | Please the attached revised figure.
14 | 2019-05-22 | Greg Hussey/SIGNET Electronic Systems, Inc. | Access Control | Can a detailed drawing showing all access control door locations be provided? | Please the attached revised figure.
15 | 2019-05-22 | Greg Hussey/SIGNET Electronic Systems, Inc. | Video | Please verify camera count. | Please the attached revised figure.
16 | 2019-05-22 | Greg Hussey/SIGNET Electronic Systems, Inc. | Video | Is there a specific CCTV system that is required? | The NVR and Viewstation solution required is manufactured by IronVIDEO and the access control server is manufactured by IronAC. No subsitutions for the NVR, Viewstations or Access Control server will be allowed. 6) The monitors must be a minimum size of 23". 7) There will need to be a IronPC viewing station for the PD security desk and a IronPC viewing station at the head end location. No substitutions will be allowed.
17 | 2019-05-22 | Greg Hussey/SIGNET Electronic Systems, Inc. | Access Control | How many client computers are necessary, who is responsible for providing these? | 2 IronVIDEO Viewstations. No substitutions will be allowed.
18 | 2019-05-22 | Greg Hussey/SIGNET Electronic Systems, Inc. | Video | How many days of recorded video is required to keep? | The IronVIDEO NVR will have 24 TB raw storage. No substitutions will be allowed.
19 | 2019-05-23 | Will Bissonnette/Sullivan and McLaughlin | Quantity inconsistencies between spec and drawings | There is a quantity discrepancy between the specs and the drawings, which document do we follow? | Please the attached revised figure.