## Sheet1
Annual Plan Date Calculator and Event Record for AP Preparation by LHAs
Annual Plan Year: | 2021 | <--Enter LHA's next FY.
LHA Fiscal Year End: | 2020-09-30 | <--Enter LHA's next FYE
Recommended Hearing Month: | June
Public Hearing Date: |  | <--Enter hearing date.
Description | Recommended Date | Actual Dates
Take AP training session | March
Complete CIP Preparation | 2020-04-02
Gather information for AP | 2020-03-31
Complete AP Draft | 2020-04-14
Post draft AP and hearing notice (46 days before hearing date). See note below. | 2020-04-16
Review draft AP with LTOs | 2020-05-18
Hold public hearing | 2020-06-01
Revise CIP for new projects or other changes if needed. | 2020-06-29
Revise AP and obtain Board approval | 2020-07-02
Submit to DHCD (Date Due) | 2020-07-31
DHCD review | August - September
Formulas:
Recommended Date = [Recommended Date, row below]-14
Recommended Date = MIN(+[Recommended Date, row above]+28,C17)
REQUIREMENT FOR POSTING HEARING NOTICE:
760 CMR 4.16(6)(b) requires that the public hearing be advertised on the LHA website, in public postings, and by contacting LTOs at least 45 calendar days before the hearing.
REQUIREMENT FOR POSTING DRAFT ANNUAL PLAN:
760 CMR 6.09(3)(h) requires that the draft Annual Plan be posted on the LHA website with a copy in the LHA office and distributed to each LTO 30 business days before the hearing. To simplify date calculations, DHCD is requiring that the draft be posted 46 calendar days before the hearing, which will always meet the 30 business days requirement. For posting on the LHA website it is sufficient to post a link to the CIMS public portal (https://tinyurl.com/LHA-MA-AnnualPlan) rather than posting the pdf file.

## Sheet2 (hidden)
FYE
2020-03-31
2020-06-30
2020-09-30
2020-12-31