## BDI-3 Implementation Timeline

|  |  |  |  |
| --- | --- | --- | --- |
| NOW (May) | T-6-8 mos (May-July) | After RFR (May-July) | T-6-8 (May-June) |
| Prepare EICS: Allow input for BDI-3 scores | EIS Programs receive BDI-3 kits and materials | 1-2 people per program opportunity to be trained | Share policy changes; program director webinar; highlight changes and timeline; MDS changes and expectations |

|  |  |  |
| --- | --- | --- |
| T-12 weeks (August-Sept) | T-8 weeks (October) | T-3 days (end of December) |
| Set up MDS EI Division creates new BDI-3 web platform; EIS administrators train on new web platform | Training for established evaluators; include training for EICS users | Release changes into EICS |

Go Time: January 6, 2025