The Commonwealth of Massachusetts

Executive Office of Health and Human Services

Department of Public Health

250 Washington Street, Boston, MA 02108-4619

MAURA T. HEALEY

Governor

KIMBERLEY DRISCOLL

Lieutenant Governor

KATHLEEN E. WALSH

Secretary

MARGRET R. COOKE

Commissioner

Tel: 617-624-6000

www.mass.gov/dph

April 10, 2023

Mr. Stewart A. Karger

Administrator

Belmont Manor

34 Agassiz Avenue

Belmont, MA 02478

Dear Mr. Karger:

I am writing regarding your request for an extension on DoN Project# 19090415-LE. The original project approval date was April 23, 2020; however, the construction project has been delayed, originally because of the COVID-19 pandemic and the de-stabilization of occupancy and staffing as well as the extremely high cost of construction. Staffing levels have stabilized, and operations are nearing pre­ pandemic levels. Based on this delay, the Determination of Need Program is granting an extension through May 1, 2026.

We request that you send an email to DPH.DON@MassMail.MA.US  when you have met the following milestones:

- When you have selected a contractor.

- When you commence with construction.

- Provide a construction update during the first week of December,2025.

- When the construction project is completed.

Sincerely,

[signature on file]

Dennis Renaud

Director, Determination of Need

Program Massachusetts

Department of Public Health