## Cover
Project Title
Utilize project Images - provide additional information relevant to BIM Execution
Project Name:
Project Number:
Contract Number:
Place Logos and Team Company Names

## Introduction
INTRODUCTION
DCAMM requires a project specific BIM Execution Plan (BIMxP). The BIMxP template documents project information, roles and responsibilities, the tools and communication protocols to be used on the project. Additionally, the template facilitates the identification of BIM specific Lean Conditions of Satisfaction (CoS) that are aligned to BIM Uses. This activity is part of the larger lean value mapping exercise defining overall project Conditions of Satisfaction.
The BIMxP will be a living document, accessible, referenced, and updated by the project team BIM Manager throughout the project. It is part of the final deliverables of the project.
Goal of the BIMxP: The goal of the BIMxP is to align project and BIM CoS goals with BIM Uses, and then determine the most effective BIM development strategy for efficient modeling, decision support and Lean project execution.
Participants: The project team, the prime BIM Manager and BIM team members, the DCAMM project manager (PM), and other project stakeholders. Lean facilitator as needed.
BIMxP TABS and CONTENTS:
ROLE DEFINITIONS - DCAMM has defined roles in BIM-based projects. The scope of the project will determine which of the roles are required on a project. Not all roles are required for all projects, however there should always be a BIM Manager for the prime or architect of record and a BIM Manager for the constructor. Additional model coordinators may manage the various discipline models on a project.
INTRODUCTION & DATA STANDARDS - Project standards, definitions and abbreviations used in projects and the pull down menus in the BIMxP. This section provides the team standards for the project.
SECTION 1. PROJECT INFORMATION - Project Information, BIM Execution Plan Approval Signatures, and Contacts
This section provides project name, number, contacts. Project Names and Numbers will be supplied by DCAMM. Any additional information considered relevant by the PM may be added in this section.
SECTION 2. COLLABORATION PROCEDURES - Meetings, Activities, IT Infrastructure, & Model Submissions
This section provides the strategic and technical procedures for project BIM collaboration. This includes the model strategy and sharing procedures, model infrastructure, and model submissions. This information is the primary responsibility of the BIM Manager in conjunction with the Discipline BIM coordinators.
The Model Submission is a jointly defined (DCAMM and the project BIM Manager) time table for model submissions to DCAMM for project review. There are three mandatory model submissions during a project, Criteria Definition Model, Design Intent Model Handover, and the Final Submission of the As-Built and Record Model. Other project specific model reviews and deliveries may be documented in this section.
SECTION 3 - BIM CONDITIONS of SATISFACTION (CoS)
The DCAMM PM or a Lean Facilitator will work with the team and stakeholders to define the project Conditions of Satisfaction. Aligned to these project goals will be BIM specific CoS and BIM actions for execution on the project. This alignment from overall project goals to specific BIM modeling defines the value stream and the Lean BIM process for a project. The prime BIM Manager participates in the CoS meeting and use Section 3 to identify the BIM CoS and activities that add value to the project.
The identification of a BIM CoS automatically selects a corresponding BIM Use in Section four. This gives the team a basis for BIM Use discussion and final selection of the BIM Uses to be executed on the project.
SECTION 4. - BIM USE MATRIX - Determine BIM uses on the project
The BIM Uses are divided into broad project categories. Not all BIM Uses are applicable to a project. The team will review the automatically identified BIM Uses and rank the priority and final selection.
BIM Use Categories:
| 1. Existing Conditions Modeling | 5. Design, Constructability Reviews
| 2. Design Systems Authoring | 6. Documentation and Specifications
| 3. Analysis and Reporting | 7. Commissioning and Handover
| 4. Sustainability, LEED, Energy Analysis | 8. Facilities & Operations
SECTION 5 - MODEL PROGRESSION - Model Progression, BIM Use Execution, Responsible Parties, and LOD
The Model Progression Worksheet documents the roles and responsibilities, model development, BIM Use execution, and the LOD of model elements. The LOD is a tracking mechanism for DCAMM. The LOD for elements will be defined at the beginning of each phase and support the highest requirements of the BIM uses to be executed during that phase. At the end of the phase the DCAMM DTIG manager will review the LOD development and BIM Use execution to determine model progress and adherence to schedule.
SECTION 6 (two tabs)- CLASH DETECTION MATRIX - Clash Detection Matrix and Report Results
The Clash Detection Matrix and the Results Report are two tabs in this file. These are to be used to document clash detection and resolution activities. A description and help animation is available in the DCAMM BIM Guide.
ABBREVIATIONS & LOD - Pull-Down Menus
DCAMM facility and project abbreviations, and other industry abbreviations are used throughout the BIMxP in pull down menus to identify discipline models, roles and responsibilities, and LOD designation. LOD descriptions from AGC and other industry standard abbreviations are included in Data Standards section of the introduction. A duplicate legend for roles and discipline models is included in Section 5.
SECTION 7. This section contains the tables for the pull-down menus. Do not change these tables.

## Definitions
AGC/LOD, OmniClass, and Data Standards Use in BIMxP
The following Data Standards are used or referenced in the DCAMM BIMxP. Additional information about each standard can be found on the following websites: www.omniclass.org, AGC LOD https://bimforum.org/lod. Additional Data Requirements for BIM Uses and FM are located within the DCAMM BIM Guide.
Construction Specification Institute - OmniClass, UniFormat
Tables Numbers and General Purpose - DCAMM will transition to OmniClass over several years. The list of tables and their use in project phases is provided as a reference for team discussion. Currently DCAMM uses Table 31-Phases and Table 13 Spaces by Function, and CSI UniFormat 2010 in the Model and Element Progression Worksheet.
OmniClass Phase Definitions: Used in the Model Progression Matrix
OmniClass & Traditional Phase Name | Description of Phase
Inception Phase (Planning & Program) | Establish the project vision and means to satisfy the client's requirements, site selection, planning, timeline, budget.
Conceptualization Phase (Schematic) | Identify and study the major design concepts, programmatic options, performance, and basic project element considerations.
Criteria Definition Phase (DD & Analysis) | Create and refine schematic design - substructure, shell, interiors, equipment, services, equipment and furnishings, special construction, demolition, building site work - fully establish project spatial and element criteria as the Basis of Design.
Design Phase (DD) | Project team satisfies project Basis of Design with technical solutions, analysis, evaluates alternatives, and completes initial documentation - Drawings and specified Work Results
Coordination Phase (CD) | Bridges design effort with implementation by integrating constructability and feasibility of the design in order to further develop spaces, elements, products, and materials for procurement and execution of the Work irrespective of the method of delivery
Implementation Phase (Construct) | implement the coordinated design through construction planning, prefabrication, and field execution characterized by constructor 'means and methods,' and Basis of Construction strategies, controlled by quality assurance and control protocols.
Handover Phase (Commissioning) | Evaluate completed work through commissioning activities, ensure design/performance criteria are met, conformance to applicable codes and standards. Transfer project knowledge from design/construction team to the Owner/facility management team
Operations Phase (Facilities Management) | Owner or designated agent occupies, uses, manages and maintains facility. May include partial or whole facility renovation, assessment, repair, reconditioning or remodeling activities.
Closure Phase (Re-Purpose & Demolition) | Includes facility closure, preparation for unknown future use, demolition in whole or part, foreclosure, sale, or dispensation initiated by the decision that the facility no longer meets the needs of the Owner and cannot be feasibly reconfigured for continued use by that Owner.
LEVEL of DEVELOPMENT -Associated General Contractors (AGC)
The Level of Development (LOD) Specification is a reference that enables practitioners in the AEC Industry to specify and articulate with a high level of clarity the content and reliability of Building Information Models (BIMs) at various stages in the design and construction process. AGC LOD https://bimforum.org/lod.
LOD Definitions
LOD 100 | The Model Element may be graphically represented in the Model with a symbol or other generic representation, but does not satisfy the requirements for LOD 200. Information related to the Model Element (i.e. cost per square foot, tonnage of HVAC, etc.) can be derived from other Model Elements.
LOD 200 | The Model Element is graphically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element.
LOD 300 | The Model Element is graphically represented within the Model as a specific system, object or assembly in terms of quantity, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element.
LOD 350 | The Model Element is graphically represented within the Model as a specific system, object or assembly in terms of quantity, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element.
LOD 400 | The Model Element is graphically represented within the Model as a specific system, object or assembly in terms of size, shape, location, quantity, and orientation with detailing, fabrication, assembly, and installation information. Non-graphic information may also be attached to the Model Element.
LOD 500 | The Model Element is a field verified representation in terms of size, shape, location, quantity, and orientation. Non-graphic information may also be attached to the Model Elements.
ABBREVIATIONS - Used in DCAMM Projects
Instructions |  | Owner | O | Architecture | A | Geotechnical | B | Equipment | Q
The supplied abbreviations shall be used in the BIMxP Sections and in the BIM model. The abbreviations appear again in Section 5. Model Progression as a legend for the pull-down menus for Discipline Model assignment and Responsible Parties. |  | Project Mgr. | PM | Structural | S | Civil | C | Tel/Com | T
|  | Con Mgr. | CM | Mechanical | M | Survey/Mapping | V | Electrical | E
|  | Operations | Op | Plumbing | P | Landscape | L | Fire Prot. Eng. | F
|  | Hazardous | Hz | Interiors | I | Contractor/Shop Draw | Z | Commissioning | Cx
|  | DCAMM BIM Mgr. | BMr | Tenant | Tr | Specialty Consultant | SC | Sub-Con/Shop | SB
*(H,V,A,S) Horizontal, Vertical, Aviation, Seaport/Bridge -added to PM for division designation if needed

## 1. Project Info & Contacts
SECTION 1. PROJECT INFORMATION
Project Name: | [10 empty] | Proj. No .
Address: | [10 empty] | Bldg. No.
City: |  |  |  |  | ST |  | ZIP |  |  |  | Location
Contract Type: | D | Proj. Start: | 8 | 20 | 2015 | Construct. Start: |  | 12 | 20 | 2015 | 2014
|  | Handover: | 12 | 20 | 2015 | Completion Date: |  | 12 | 20 | 2015 | 2014
Project Description:
Document Authority
This project plan has been agreed to by the representatives of the project team as listed and with the authority of their parent companies to accept this document as the Agreed BIM Execution Plan.
Signature/Firm |  |  | Signature/Firm | [7 empty] | Signature/Firm
Signature/Firm |  |  | Signature/Firm | [7 empty] | Signature/Firm
Project Contacts
In a BIM based project there are many people that develop BIM information or are responsible for tasks that rely upon BIM data. Each Discipline Model should have a single responsible person for BIM development and quality.
Title | Contact Name |  |  | Firm/Organization |  |  |  | Email |  |  |  | Phone
Owner Team
Proj. Mgr.
DCAMM BIM Mgr.
Program Mgr.
Commissioning
Client
Client Rep
Design Team
Proj. Prin. Arch.
Proj. Mgr.
Design BIM Mgr.
Interiors
Food Service
Engineers
Structural Eng.
HVAC Eng.
Electrical Eng.
Plumbing Eng.
Fire Protection
Communications
Civil Eng.
Landscape
Transportation
Construction Team
PM
Principal
VDC BIM Mgr
Estimation
Schedule
Mechanical
Sheet Metal
Plumbing
Electrical
Fire
Steel
Curtain Wall
As-Built Data
Const. Layout
Laser Scanning
Survey
BIM/IT (Resources and Consultants)
Software Support
Software Support
Software Support
Software Support
Software Support
VDC Environment
Data Validation
Note on C5: Abbreviations: C-Construction D-Design P-Procurement S-Study F-Facilities Mgt

## 2. Collaboration Procedures
SECTION 2. COLLABORATION PROCEDURES (Meetings, Activities, IT Infrastructure) & Model Submissions
Project Name: | [5 empty] | Project No.
Team will provide relevant collaboration strategies, procedures, and model requirements to insure consistent and clear communication, model development, sharing, and delivery. The BIM Manager is responsible for initial model set-up and standards as defined by the DCAMM BIM Guide and project need.
2.1 COLLABORATION STRATEGY
Provide relevant strategy including communication methods, document management, software and file exchange
2.2 MEETINGS
Meeting Type |  | Proj Stage | Frequency |  | Participant Teams |  |  |  | Location
Conference A
Conference S Conditions o f Satisfaction
BIM Reviews
BIM Execution Reviews
3D Coordination
FM Space Review
Constructability
Clash Avoidance (Template)
Coordination
Other
2.3 MODEL SHARING and EXCHANGE SCHEDULE
This section is for team use. It is the schedule for work in progress (WIP) model uploads for federation, BIM use execution.
Model Information Exchange (Ex.) | File Sender | File Receiver | Frequency | Start Date | Model File | Model Software | Native File | File Exchange Type
2.4 TECHNOLOGY INFRASTRUCTURE
Provide the software, version, model type (Analysis included), user, and exchanges for the software used on the project
SOFTWARE APPLICATIONS and USE
Software |  | Version | Model Type File Type | Model Author | Model Name |  |  |  | Model Size Max.
COLLABORATION SITE for MODEL FEDERATION, COLLABORATION, and FILE EXCHANGE
DCAMM requires the project prime either design or construction to provide a collaboration site for model coordination, file and document management during project phases. This accessible and secure site is the location for current model files, coordination files, and fully coordinated submittal files. Each BIM coordination team member will store and obtain data from this location per an agreed upon schedule. Project team members are to upload updated copies of their files, provide notification, and make collaboration comments and annotations as often as necessary to maintain project schedule.
The project prime BIM Manager will establish accessibility, and manage training for team members for efficient use of the environment. Provide name, email, phone for responsible parties
DESIGN PHASE COLLABORATION PLATFORM
Platform Address
User Access & Support
Platform Structure Management
Platform Training
Additional
CONSTRUCTION PHASE COLLABORATION PLATFORM
Platform Address
User Access & Support
Platform Structure Management
Platform Training
Additional
2.5 Model Submission Schedule
Criteria Definition Phase Model (Traditional 30% Milestone)
Federated Discipline Models |  | Model Use |  | Author |  | Receiving Party |  | Date
Design (Intent)Phase Model (60%)
Federated Discipline Models |  | Model Use |  | Author |  | Receiving Party |  | Date
Coordination Phase Model - Construction Handover (100%)
Federated Models |  | Model Use |  | Author |  | Receiving Party |  | Date
As-Built (Navisworks) | [7 empty] | Date
Record Model (Revit with As-Built Updates) | [7 empty] | Date

## 3. Cond.of Satisfaction
SECTION 3. | BIM CONDITIONS of STATISFACTION (CoS)
CoS address the desired process, decision, and project outcomes. They address the expected quality of services and products to achieve the CoS. BIM Use should enable and support desired project outcomes. BIMTEAM DIRECTIONS: Identify applicable Project Level CoS that utilize BIM. Set the priority (PR) using the pull down menu 1-High 3-Low or Blank - not required for the project. The CoS are aligned to appropriate BIM Uses on the BIM Uses Worksheet.
Categories for BIM Conditions of Satisfaction |  | CoS No. | PRIORITY | BIM-based Actions Supporting the Conditions of Satisfaction | [8 empty] | Responsible ← Parties
Collect and use accurate information supporting project design options, and processes. |  | 1.1 | 1 | Project Site Modeling -Also Infrastructure | [8 empty] | A
|  | 1.2 |  | Model the context for the project (project area surrounding project site)
|  | 1.3 | 3 | Utilize scanning technology to develop existing conditions model | [8 empty] | C | B
|  | 1.4 |  | Capture accurate building interiors modeled to an LOD required for project
|  | 1.5 |  | Identify and document environmental site conditions
|  | 1.6 |  | Model campus or multi-building facility for Master Planning
Model building systems for design options, program compliance and performance |  | 2.1 |  | Create model for architecture
|  | 2.2 |  | Develop space, circulation & program model
|  | 2.3 |  | Create model for structural design
|  | 2.4 |  | Create model supporting efficient sustainable mechanical systems
|  | 2.5 |  | Design model for plumbing and fire protection systems
|  | 2.6 |  | Design model for electrical and alarm
|  | 2.7 |  | Design ergonomic and flexible interior spaces
|  | 2.8 |  | Tenant Build out - Food Service, Ticketing, Retail, Hospitality
Utilize industry tools to verify design performance, cost, code compliance & usefulness |  | 3.1 |  | Develop and verify space model to stakeholder program needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs | Verify program compliance with stakeholder needs
|  | 3.2 |  | Develop design options to maximize program, sustainability and performance | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design | Develop design options to maximize final design
|  | 3.3 |  | Verify design, code compliance through model checking | Verify design code compliance | Verify design code compliance | Verify design code compliance | Verify design code compliance | Verify design code compliance | Verify design code compliance | Verify design code compliance | Verify design code compliance
|  | 3.4 |  | Reduce errors through model coordination (clash coordination) | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation | Reduce errors in design and documentation
|  | 3.5 |  | Verify performance of building structural systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems | Verify performance of building systems
|  | 3.6 |  | Model mechanical maintenance space for client approval | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance | Design mechanical space for efficient maintenance
|  | 3.7 |  | Develop programmatic budget based upon accurate program model | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project | Develop programmatic budget based upon accurate project definition and program - ON Budget project
|  | 3.8 |  | Streamline estimating process using model quantities | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model | Streamline estimating process using model
Develop sustainable design meeting LEED requirements |  | 4.1 |  | Maximize energy efficiency through design, daylight, and sun analysis, | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects
|  | 4.2 |  | Utilize rapid energy studies of existing buildings to increase energy efficiency | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects | Utilize industry tools to visualize energy, sun affects
|  | 4.3 |  | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency | Utilize industry tools to analyze MEP performance and efficiency
|  | 4.4 |  | Attain LEED accreditation goals | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation | Attain LEED accredidation
|  | 4.5 |  | Develop energy efficient ergonomic lighting
Maximize team coordination and collaboration |  | 5.1 |  | Maximize communication and constructability with BIM based reviews
|  | 5.2 |  | Digital prototyping and construction simulation for design review
|  | 5.3 |  | 4D project schedule building phasing
|  | 5.4 |  | Provide a safe, well utilized construction site
|  | 5.5 |  | Build to model - use model for field construction layouts
|  | 5.6 |  | Utilize laser scanning to document new construction
|  | 5.7 |  | Pre-fabrication of building components to reduce costs, improve quality
|  | 5.8 |  | Building systems analysis throughout project
Produce accurate and well coordinated documentation |  | 6.1 |  | Derive coordinated construction drawings, 3D views, and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model | Derive construction drawings and schedules from model
|  | 6.2 |  | Maximize coordination between A/E and shop fabrication modeler | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors | Maximize communication between design intent and shop fabrication to reduce waste and errors
|  | 6.3 |  | Provide highly accurate As-Built (Record) models and data for handover A/E
|  | 6.4 |  | Provide data per DCAMM requirements and normalize across model
|  | 6.5 |  | As-Built CAD Drawings
Commission the project for occupancy and the model for useful handover data |  | 7.1 |  | Virtual Handover utilize model prior to building handover for commissioning | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout | Provide highly accurate As-Built models and data for handover and closeout
|  | 7.2 |  | Provide asset and equipment data per COBie requirements | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS | Utilize BIM in operations - integrate systems - Link to CMMS, IWMS
|  | 7.3 |  | Model support for Commissioning | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover | Commission model and equipment data for facility handover
|  | 7.4 |  | Building information required for facility start-up after disaster | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance | Provide cost effective analysis of existing buildings performance
|  | 7.5 |  | BIM Server Handover | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team | Team will plan and execute a smooth transition of project data to owner team
Maximize technology and data for facilities management |  | 8.1 |  | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes | Streamline assessment processes
|  | 8.2 |  | Maintain accurate space information and use | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information
|  | 8.3 |  | Maintain accurate security information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information | Maintain accurate space information
|  | 8.4 |  | CMMS and CAFM integration |  | 8.2 | Move Management | 8.2 | Move Management
|  | 8.5 |  | Resiliency planning
|  | 8.6 |  | Building System Automation (BSA) Integration
Add Additional Condition |  | 9.1
9.2
9.3
9.4
9.5
Add Additional Condition |  | 10.1
10.2
10.3
10.4
10.5
Add Additional Condition |  | 11.1
11.2
11.3
11.4
11.5

## 4. BIM Use Matrix
SECTION 4 BIM Use
Directions: The goal of BIM Use is to align the Conditions of Satisfaction (CoS) defined in Section 3, with corresponding BIM Uses to support the project. According to the CoS priority number (left of the page from Section 3) the team will determine the final BIM Uses for the project. From a Lean perspective, aligning BIM Uses to CoS priorities maximizes model usefulness, model progression for decision support, and reduces over or under modeling. BIM Uses: For additional descriptions and requirements for a BIM Use see the DCAMM BIM Guide Appendix A.
About LOD: The LOD number at the right of the page, gives the LOD range for the BIM Use however, LOD is carried by the model objects and elements. See the DCAMM BIM Guide.
CoS Priority | Final BIM Use (FBU) | BIM Use No. | BIM USE NAME |  |  |  |  | BIM USE GENERAL DESCRIPTION | General LOD
|  | 1 | EXISTING CONDITIONS |  |  |  |  | See Appendix A - DCAMM BIM Guide for Additional Requirements | LOD
1 |  | 1.1 | BIM Project Site Modeling – Also Infrastructure Modeling | 1.1 | Programmatic Model | 1.1 | Programmatic Model | The project site modeled to an LOD 200 geometry showing topography, relevant surfaces, access, site utilities, major plantings to be protected, historically significant or environmentally sensitive areas | 100 200
0 |  | 1.2 | Surrounding Site Modeling | 1.2 | BIM Project Site Modeling – Also Infrastructure Modeling | 1.2 | BIM Project Site Modeling – Also Infrastructure Modeling | Provides additional land modeling or imagery providing the larger context for the project site. May be used with existing site conditions model and Existing Building Model/s. Also used for Way-Finding and Traffic pattern modeling. | 100 300
3 | Y | 1.3 | Laser Scanning - Existing Conditions | 1.3 | Surrounding Site Modeling | 1.3 | Surrounding Site Modeling | Laser scanning for building exterior or interior (project scope dependent). Laser scanning post processed into a BIM or hybrid file - BIM with point cloud as reference - Data determined by SOW | 100 300
0 |  | 1.4 | Existing Conditions- Building Interior | 1.4 | Existing Conditions- Laser Scanning | 1.4 | Existing Conditions- Laser Scanning | Existing buildings may be simple Massings, blocking/stacking models, photogrammetric models, or laser scan accurate BIMs per DCAMM and project needs. Existing buildings carry meta-data- (Building Name, Bldg. Number, Current Use, Built Date, Occupancy State, Square Footage, Est. Value-Condition Metric- TBD) | 300
0 |  | 1.5 | Geo-technical, Environmental | 1.5 | Existing Conditions Modeling – Building Interior | 1.5 | Existing Conditions Modeling – Building Interior | A geo-technical site model may be appropriate for environmentally sensitive sites. Identify site specific information and issues impacting project. These may include soil borings, protected land sites (wet-lands, marshes, animal habitats) topographical barriers, brown field, utilities | 200 300
0 |  | 1.6 | Site Modeling-Horizontal Construction | 1.6 | Geo-technical, Environmental | 1.6 | Geo-technical, Environmental | Model of horizontal structures for as-built/existing conditions or new construction. May be combination of scanning modeling, may be GIS and BIM | 200 350
CoS | FBU | 2 | DESIGN & BUILDING SYSTEM AUTHORING |  |  |  |  | LOD 200-300 | LOD
0 |  | 2.1 | Architectural Model | 2.1 | Architectural Model – LOD 200-300 | 2.1 | Architectural Model – LOD 200-300 | Progressive modeling of architectural elements supporting design options (100-200) through to Design Intent model(LOD 300) - Actual element modeling to include but not limited to information needed for construction documentation and trade collaboration. | 300
0 |  | 2.2 | Space & Circulation Requirements Modeling | 2.2 | Space & Circulation Requirements Modeling | 2.2 | Space & Circulation Requirements Modeling | Model of spaces and circulation meeting program requirements, identification of functional space use, OmniClass Table 13, code, and space allocation. | 300
0 |  | 2.3 | Structural Model | 2.3 | Structural Model | 2.3 | Structural Model | Discipline Model, the structural system of an existing or proposed design to LOD 300 for analysis and handover to contractor for detailing LOD 350. | 300
0 |  | 2.4 | HVAC Mechanical Systems | 2.4 | HVAC Mechanical Systems | 2.4 | HVAC Mechanical Systems | Discipline Model, the HVAC, mechanical systems are modeled to (LOD 300) to support coordination, construction documentation, and handover to contractor for fabrication (shop) drawings) | 200 300
0 |  | 2.5 | Plumbing & Fire Protection | 2.5 | Plumbing & Fire Protection | 2.5 | Plumbing & Fire Protection | Discipline Model - Plumbing, pipes, and vertical chases modeled to support coordination and construction documentation. | 200 300
0 |  | 2.6 | Electrical, Alarm Systems | 2.6 | Electrical, Alarm Systems | 2.6 | Electrical, Alarm Systems | As separate discipline models, the primary components of the electrical, lighting, alarm systems and building automation systems (BAS) controls. | 200 300
0 |  | 2.7 | Interiors | 2.7 | Interiors | 2.7 | Interiors | Modeling of interior design options, materials and finishes, details, furniture, fixtures, casework, equipment (FFE) furniture systems, signage and way finding, support for lighting power locations, LEED and Daylighting. Renderings may be required as part of project requirements. Integration of 3D views in Construction documentation, supports coordination, QTO and decision support. | 300 400
0 |  | 2.8 | Tenant Build Out (Food Service, Retail, Ticketing) | 2.8 | Tenant Build Out | 2.8 | Tenant Build Out | Tenant’s representative to determine the space, scope, and requirements for tenant documentation, including BIM. Model to support, construction documentation, all required disciplines, QTO, and coordination. | 300 400
CoS | FBU | 3 | ANALYSIS & REPORTING | [5 empty] | LOD
0 |  | 3.1 | Area & Space, Program Validation (SPV) – Testing Space & Circulation Modeling | 3.1 | Space Program Validation (SPV) – Testing Space & Circulation Modeling | 3.1 | Space Program Validation (SPV) – Testing Space & Circulation Modeling | The BIM file, specifically spaces and bounding elements, including floors and stories, is saved and analyzed using model checking software. Attention is given to the file format required by the checking software, and its applied rules. A report of deviations to be reviewed and addressed by the design team is generated. | NA
0 |  | 3.2 | Design Options - Set-based Design | 3.2 | Design Options | 3.2 | Design Options | Set based design involves rapid modeling and analysis within multi-disciplinary teams to explore multiple design alternatives up-front, allowing for trade-offs for integrated systems with competing requirements. Team process develops multiple design options and develop better data for decision to meet the Conditions of Satisfaction | 100 300
0 |  | 3.3 | Model Checking Program Compliance (Checking) | 3.3 | Model Checking Code Compliance (Checking) | 3.3 | Model Checking Code Compliance (Checking) | Model Checking using a rules-based application that automates model review for modeling quality, design and some code conformance, and data development. | 200 300
0 |  | 3.4 | Clash Avoidance and Detection | 3.4 | Clash Avoidance and Detection | 3.4 | Clash Avoidance and Detection | Discipline and Federated models are reviewed for physical interferences on a regular basis. Design Intent model is reviewed with clashes resolved and documented. | 300
0 |  | 3.5 | Structural Analysis | 3.5 | Structural Analysis | 3.5 | Structural Analysis | Model based analysis of structural design to determine fitness for purpose and design. | 300
0 |  | 3.6 | Mechanical/ Equipment Maintenance Clearance Space Modeling | 3.6 | Mechanical/ Equipment Maintenance Space Modeling | 3.6 | Mechanical/ Equipment Maintenance Space Modeling | This modeling supports FM review of major equipment and elements requiring access or maintenance space. Space is modeled as a translucent area, clearly named to prevent QTO conflict. Consideration should be given to typical maintenance cycles and continuity of operations so that adjacent equipment can be serviced at the same time. | 200 300
0 |  | 3.7 | Budgetary Cost Model |  |  |  |  | Budgetary Cost uses BIM spaces, major building elements with historic square foot costing data, project type, region, and construction type, to calculate budgetary estimates. Used as a decision basis in design options review and selection | 100 300
0 |  | 3.8 | Quantity Take-Off and Detailed Estimating |  |  |  |  | Progressive quantity take-off by building system, use of UniFormat and OmniClass | 200-350
CoS | FBU | 4 | SUSTAINABILITY, LEED & ENERGY |  |  |  |  | BIM Use Description | LOD
0 |  | 4.1 | Energy Modeling, Daylight, Sun Studies | 4.1 | New/Existing Construction - Energy Modeling, Sun Studies | 4.1 | New/Existing Construction - Energy Modeling, Sun Studies | BIM is analyzed to improve day lighting in design, to understand sun shading needs and the balance between daylight and artificial lights to support space usefulness | 200 300
0 |  | 4.2 | Rapid Energy Modeling- Existing Buildings | 4.2 | Existing Buildings - Rapid Energy Modeling | 4.2 | Existing Buildings - Rapid Energy Modeling | Rapid Energy Modeling (REM) is a streamlined process for simplified simulation that quickly and with minimal data from existing building conditions develops an energy analysis. Retro-Commissioning | 200
0 |  | 4.3 | Mechanical Analysis | 4.3 | Mechanical Analysis | 4.3 | Mechanical Analysis | Virtual testing and balancing of the design model to support sustainable building systems design and analysis | 200 300
0 |  | 4.4 | LEED Credit Certification Reporting | 4.4 | LEED Credit Certification Reporting | 4.4 | LEED Credit Certification Reporting | Models, elements and objects, and specs can be reported and quantified supporting LEED certification | 300
0 |  | 4.5 | Lighting Analysis | 4.5 | Budgetary Costing Model (LOD-200) | 4.5 | Budgetary Costing Model (LOD-200) | Utilize BIM architecture and interiors models with data required by lighting analysis software to image the lighting performance of a space. This analysis is used to support building performance. | 200 300
0 |  | 4.6 | Systems Analysis- Retrofitting |  |  |  |  | Develop a model to support existing conditions and energy analysis for retro-fitting and upgrading building systems. | 300-400
CoS | FBU | 5 | DESIGN,CONSTRUCTABILITY, COORDINATION REVIEWS | [5 empty] | LOD
0 |  | 5.1 | BIM Based Reviews – Project Lifecycle | 5.1 | BIM Based Reviews – Project Lifecycle | 5.1 | BIM Based Reviews – Project Lifecycle | Design teams and constructors will utilize live model manipulation, visualization, digital mock-ups, saved views and other electronic graphics to support problem solving and decision support. | 200 300
0 |  | 5.2 | Digital Detail & Mock-Ups | 5.3 | Digital Detail & Mock-Ups | 5.3 | Digital Detail & Mock-Ups | Detailed digital constructs of design elements supporting communication, collaboration, constructability and estimating. | 300 400
0 |  | 5.3 | Scheduling - 4D BIM for Project Schedule, Phasing | 5.4 | Scheduling - 4D BIM for Project Schedule, Phasing | 5.4 | Scheduling - 4D BIM for Project Schedule, Phasing | Coordination model supporting 4D schedule, Look-ahead, and phasing | 200 300
0 |  | 5.4 | Site Logistics and Safety (ICRA) | 5.5 | Site Logistics | 5.5 | Site Logistics | Model is used to show construction site asset layouts, relationships to traffic, public walkways, and coordination of materials, movement of workers, and equipment. | 200 300
0 |  | 5.5 | In Field Construction Lay-Out | 5.6 | In Field Construction Lay-Out | 5.6 | In Field Construction Lay-Out | Model dimensions used for field lay-out using laser equipment for accuracy | 300
0 |  | 5.6 | Laser Scanning-Construction Phase |  |  |  |  | Laser scanning to produce a point cloud of as-built conditions | NA
0 |  | 5.7 | Pre-Fabrication of Building Components |  |  |  |  | Integrated design intent and shop models for construction. Clash detection for final coordination -Use of the model and specific building components with a focus on visualizing and simulating the logistics of their placement in a new or existing building. Use of Design Intent and Shop Model | 300
0 |  | 5.8 | Analyze Systems Throughout Project Options |  |  |  |  | Continuous refinement and analysis of the performance of building systems through progressive refinement of system specification. | 200 400
CoS | FBU | 6 | DOCUMENTATION, DWGS, SPECS | [5 empty] | LOD
0 |  | 6.1 | Construction Drawing Production |  |  |  |  | Construction Documents (CDs), details, and schedules are derived from the fully coordinated Design Intent model. Views are automatically generated in the BIM file by the authoring software. | 300 400
0 |  | 6.2 | Shop Model and Drawing Coordination, Submittals | 6.2 | Shop Drawing Coordination | 6.2 | Shop Drawing Coordination | Detailed shop drawings for fabrication and construction are derived from the discipline specific design intent BIMs | 350
0 |  | 6.3 | As-Built Model | 6.3 | Pre-Fabrication of Building Components | 6.3 | Pre-Fabrication of Building Components | The As-Built BIM is the Navisworks file that has been developed throughout the design, shop modeling, and construction processes. It incorporates all spatial relationship changes and other alterations that have occurred up to the point where the Owner takes possession of the facility | 350 400
0 |  | 6.4 | Data Normalization |  |  |  |  | The BIM Manager will work with the team to assure that data standards are adhered to throughout the discipline models and model development. The standards are defined in the DCAMM BIM Guide and agreed upon within the BIMxP. | NA
0 |  | 6.5 | As-Built CAD Drawings |  |  |  |  | Should as-built CAD files be required at project handover, the contractor shall provide the updated As-Built drawings in AutoCAD format.
CoS | FBU | 7 | COMMISSIONING & HANDOVER | [5 empty] | LOD
0 |  | 7.1 | Virtual Handover - Record Model Commissioning | 7.1 | Record Model (As-Built) | 7.1 | Record Model (As-Built) | The Record model is the updated Design Intent model to be used for facilities management - The FM model is a stewardship model created by combining and normalizing multiple project models into the larger facility model. | 400
0 |  | 7.2 | COBie Data Set | 7.3 | COBie Data Set | 7.3 | COBie Data Set | The project team at each stage will populate the model with COBie data | 300 400
0 |  | 7.3 | Commissioning | 7.4 | Retro-Commissioning | 7.4 | Retro-Commissioning | Commissioning is a systematic process of verifying that all building systems perform interactively according to the design intent and the owner’s operational needs. Review Commissioning in DCAMM BIM Guide | 300 400
0 |  | 7.4 | Model Data Supporting Disaster Planning (Resiliency) |  |  |  |  | Critical systems data integrated into model supporting data turnover to CMMS and modeling for disaster planning | 400 300
0 |  | 7.5 | Model for Maintenance Training | 7.5 | BIM Server Turnover | 7.5 | BIM Server Turnover | Develop views, animations, presentations showing major equipment spaces, commissioning data and other relevant information to support pre-occupation and during commissioning training for facility staff. | NA
CoS | FBU | 8 | FACILITIES MANAGEMENT | [5 empty] | LOD
0 |  | 8.1 | Assessment Models |  |  |  |  | Use of a baseline FM model to support space, equipment, building systems, and facility condition assessments. Assessment objects or attribute information will be collected. DCAMM commissioning dataset shall be used. | 300
0 |  | 8.2 | Space Planning - Move Management | 8.1 | Assessment Model | 8.1 | Assessment Model | A model shall be used to assist in Move Management. Furniture and IT equipment shall be specified per room as required by FM. Spatial information shall include detailed room properties, validated against the Owner's Program Requirements. Report on departmental or functional spaces. Develop demolition model, for new design. | 200 400
0 |  | 8.3 | Security | 8.2 | Move Management | 8.2 | Move Management | In model identify secure and public spaces. Develop line-of-site views for security review. Provide circulation paths if required for project. | NA
0 |  | 8.4 | CMMS and CAFM Integration | 8.3 | Security | 8.3 | Security | Computerized Maintenance Management Systems (CMMS) and Computer Aided Facility Management (CAFM) applications shall be populated from BIM (via COBie) with as-built information. BIM shall be linked to CMMS/CAFM to allow for maintaining current as-built information. Maximo system | 200 400
0 |  | 8.5 | Resiliency Modeling |  |  |  |  | BIM simulations for resilient design development. Resilient design features, life safety equipment and systems shall be modeled according to the project requirements. | 200 400
0 |  | 8.6 | Building System Automation BSA Integration |  |  |  |  | It is a goal of DCAMM to utilize BIM to support Building Automation System integration. BIM will be an intelligent visual aid to accessing BAS data and building performance. | NA
CoS | FBU | 9 | ADDITIONAL PROJECT SPECIFIC USES
0 |  | 9.1
0 |  | 9.2
0 |  | 9.3
0 |  | 9.4
0 |  | 9.5
CoS | FBU | 10 | ADDITIONAL PROJECT SPECIFIC USES
0 |  | 10.1
0 |  | 10.2
0 |  | 10.3
0 |  | 10.4
0 |  | 10.5
CoS | FBU | 11 | ADDITIONAL PROJECT SPECIFIC USES
0 |  | 11.1
0 |  | 11.2
0 |  | 11.3
0 |  | 11.4
0 |  | 11.5

## 5. Model Progression Matrix
SECTION 5 MODEL & ELEMENT DEVELOPMENT SCHEDULE WORKSHEET | [13 empty] | DIRECTIONS for USE | [12 empty] | DISCIPLINE and RESPONSIBLE PARTIES ABBREVIATIONS
Project Name | [7 empty] | Project No. | [5 empty] | The top section of this Model Progression Worksheet schedules when a BIM Use is executed, the roles and responsibilities, and the start and end dates for completion. | [12 empty] | These abbreviations are used in the pull-down menus
Updates |  |  | Notes |  |  | Updates |  | Notes | [18 empty] | Responsible Parties R/P
[14 empty] | The Execute Column determines whether the BIM Use will be completed. | [12 empty] | Architecture |  |  | A | Geotechnical |  |  | B | Equipment |  |  |  | Q | Tenant |  |  | TR
[14 empty] | The pale orange columns are the required model submissions and the minimum LOD for the submission when an element is present in the model. This is to be reviewed for each project. | [12 empty] | Structural |  |  | S | Civil |  |  | C | Tele-Communications |  |  |  | T | Specialty Consultant |  |  | SC
[27 empty] | Mechanical |  |  | M | Survey/Mapping |  |  | V | Electrical |  |  |  | E | Sub Cont./Shop Dwg |  |  | SB
[14 empty] | The lower section defines the model elements LOD through the phases. Black and dark grey blocks show higher level (less detail) classifications acceptable in the earlier phases | [12 empty] | Plumbing |  |  | P | Landscape |  |  | L | Fire Protection Eng. |  |  |  | F | Owner |  |  | O
[27 empty] | Interiors |  |  | I | Contractor/Shop Dwg |  |  | Z | Commissioning |  |  |  | Cx
Project BIM Uses | [5 empty] | Execute | Conceptualization |  |  |  |  | Criteria Definition |  |  |  |  | Criteria Definition | Design |  |  |  |  | Design Intent Model | Coordination | [5 empty] | Shop Model Review | Implementation |  |  |  |  | As-Built | Handover | [5 empty] | Record Model
No | BIM Use Number and Name (From BIM Use Matrix) Identify Phase | [5 empty] | Start |  | Resp. Parties | End |  | Start |  | Resp. Parties | End |  |  | Start |  | Resp. Parties | End |  |  | Start |  | Resp. Parties |  | End |  |  | Start |  | Resp. Parties | End |  |  | Start |  | Resp. Parties |  | End
1 | Laser Scan Existing Bldg | [5 empty] | 12 | 2014 |  | 12 | 2014 | 12 | 2014 |  |  |  |  | 12 | 2014 |  | 12 | 2014 |  | 12 | 2014 |  |  | 12 | 2014 |  | 12 | 2014 |  | 12 | 2014 |  | 12 | 2014 |  |  | 12 | 2014
2
3
4
5 | [6 empty] | 2 | 2015
6
7
8
9
10
11
PHASES (OmniClass Table 31) | [6 empty] | Conceptualization |  |  |  |  | Criteria Definition |  |  |  |  | Criteria Model Minimum LOD | Design Development |  |  |  |  | Design Intent Minimum LOD | Coordination | [5 empty] | Shop Model Review Min. LOD | Implementation |  |  |  |  | As-Built Min. LOD | Handover | [5 empty] | Record Model Min. LOD
MILESTONES (Traditional Phases) | [6 empty] | Planning |  |  |  |  | Schematic Design | [5 empty] | Design Development | [5 empty] | Shop Dwg/Fabrication | [6 empty] | Construction | [5 empty] | Operations
CSI UniFormat II (2010) & OmniClass - Assign Model Elements to Discipline Model ↓ |  |  |  |  | Discipline Model Owner |  | LOD Start | R/P | Notes Add Comment |  | LOD End | LOD Start | R/P | Notes |  | LOD End |  | LOD Start | R/P | Notes |  | LOD End |  | LOD Start | R/P | Notes |  |  | LOD End |  | LOD Start | R/P | Notes |  | LOD End |  | LOD Start | R/P | Notes |  |  | LOD End
Functional Spaces (OmniClass Table 13) | [6 empty] | 100 | A |  |  | 100 | 100 | A |  |  |  | 200 | [5 empty] | 300 | 100 | A |  |  |  | 100 | 350 | [5 empty] | 400 | [6 empty] | 350
(Add spaces as required from Table 13) | [16 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | SUBSTRUCTURE | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | Foundations | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | 10 | Standard Foundations | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | 10 | .10 | Wall Foundations (Shallow Foundations) | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | 10 | .30 | Column Foundations | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | 20 | Special Foundations | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 10 | 20 | .80 | Grade Beams | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 20 | Subgrade Enclosures | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 20 | 10 | Walls for Subgrade Enclosures | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 40 | Slabs-on-Grade | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 40 | 10 | Standard Slabs-on-Grade | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
A | 40 | 20 | Structural Slabs-on-Grade | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | SHELL | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 10 | Superstructure | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 10 | 10 | Floor Construction | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 10 | 10 | .10 | Floor Structural Frame | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 10 | 10 | .20 | Floor Decks, Slabs, and Toppings | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | Exterior Vertical Enclosures | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | Exterior Walls | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | 0.1 | Exterior Wall Veneer | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | 0.2 | Exterior Wall Construction | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | 0.3 | Exterior Wall Interior Skin | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | 0.5 | Parapets | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 10 | 0.6 | Equipment Screens | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 20 | Exterior Windows | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 20 | .10 | Exterior Operating Windows | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 20 | .20 | Exterior Fixed Windows | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 20 | .30 | Exterior Window Wall | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 20 | .50 | Exterior Special Function Windows | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | Exterior Doors & Grilles | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .10 | Exterior Entrance Doors | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .20 | Exterior Utility Doors | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .30 | Exterior Oversize Doors | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .40 | Ext Special Function Doors | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .60 | Exterior Grilles | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .70 | Exterior Gates | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 50 | .90 | Exterior Doors Supplementary Components | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 70 | Exterior Louvers and Vents | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 70 | .10 | Exterior Louvers | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 70 | .50 | Exterior Vents | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | Exterior Wall Appurtenances | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | .10 | Exterior Fixed Grilles and Screens | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | .30 | Exterior Opening Protection Devices | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | .50 | Exterior Balcony Walls and Railings | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | .70 | Exterior Fabrications | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 80 | .80 | Bird Control Devices | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 20 | 90 | Exterior Wall Specialties | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | Exterior Horizontal Enclosures | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 10 | Roofing | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 10 | .10 | Steep Slope Roofing | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 10 | .50 | Low Slope Roofing | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 10 | .70 | Canopy Roofing | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 10 | .90 | Roofing Supplementary Components | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 20 | Roof Appurtenances | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 20 | .10 | Roof Accessories | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 20 | .30 | Roof Specialties | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 20 | .70 | Rainwater Management | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 40 | Traffic Bearing Horizontal Enclosures | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 40 | .10 | Traffic Bearing Coatings | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 40 | .30 | Horizontal Waterproofing Membrane | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 40 | .50 | Wear Surfaces | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 40 | .90 | Horizontal Enclosure Supplementary Components | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 60 | Horizontal Openings | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 60 | .10 | Roof Windows and Skylights | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 60 | .50 | Vents and Hatches | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 60 | .90 | Horizontal Opening Supplementary Comp. | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 80 | Overhead Exterior Enclosures | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 80 | .10 | Exterior Ceilings | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 80 | .20 | Exterior Soffits | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
B | 30 | 80 | .30 | Exterior Bulkheads | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | INTERIORS | [15 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | Interior Construction | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | Interior Partitions | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .10 | Interior Fixed Partitions | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .20 | Interior Glazed Partitions | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .40 | Interior Demountable Partitions | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .50 | Interior Operable Partitions | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .70 | Interior Screens | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 10 | .90 | Interior Partitions Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 20 | Interior Windows | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 20 | .10 | Interior Operating Windows | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 20 | .20 | Interior Fixed Windows | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 20 | .50 | Interior Special Function Windows | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 20 | .90 | Interior Window Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | Interior Doors | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .10 | Interior Swinging Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .20 | Interior Entrance Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .25 | Interior Siding Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .30 | Interior Folding Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .40 | Interior Coiling Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .50 | Interior Panel Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .70 | Interior Special Function Doors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .80 | Interior Access Doors and Panels | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 30 | .90 | Interior Door Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 40 | Interior Grilles and Gates | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 40 | .10 | Interior Grilles | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 40 | .50 | Interior Gates | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 60 | Raised Floor Construction | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 60 | .10 | Access Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 60 | .30 | Platform / Stage Floors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | Suspended Ceiling Construction | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | .10 | Acoustical Suspended Ceilings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | .20 | Suspended Plaster and Gypsum Board Ceilings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | .50 | Specialty Suspended Ceilings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | .70 | Special Function Suspended Ceilings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 70 | .90 | Ceiling Suspension Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | Interior Specialties | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .10 | Interior Railings and Handrails | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .15 | Interior Louvers | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .20 | Information Specialties | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .25 | Compartments and Cubicles | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .30 | Service Walls | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .35 | Wall and Door Protection | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .40 | Toilet, Bath and Laundry Accessories | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .45 | Interior Gas Lighting | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .50 | Fireplaces and Stoves | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .60 | Safety Specialties | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .70 | Storage Specialties | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 10 | 90 | .90 | Other Interior Specialties | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | Interior Finishes | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | Wall Finishes | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .10 | Tile Wall Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .20 | Wall Paneling | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .30 | Wall Coverings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .35 | Wall Carpeting | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .50 | Stone Facing | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .60 | Special Wall Surfacing | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .70 | Wall Painting and Coating | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .80 | Acoustical Wall Treatment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 10 | .90 | Wall Finish Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 20 | Interior Fabrications | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | Flooring | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .10 | Flooring Treatment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .20 | Tile Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .30 | Specialty Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .40 | Masonry Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .45 | Wood Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .50 | Resilient Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .60 | Terrazzo Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .70 | Fluid-Applied Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .75 | Carpeting | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .80 | Athletic Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .85 | Entrance Flooring | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 30 | .90 | Flooring Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | Stair Finishes | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .20 | Tile Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .40 | Masonry Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .45 | Wood Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .50 | Resilient Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .60 | Terrazzo Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 40 | .75 | Carpeted Stair Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | Ceiling Finishes | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | .10 | Plaster and Gypsum Board Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | .20 | Ceiling Paneling | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | .70 | Ceiling Painting and Coating | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | .80 | Acoustical Ceiling Treatment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 50 | .90 | Ceiling Finish Supplementary Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 90 | Interior Finish Schedules | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
C | 20 | 90 | .10 | Plaster and GypBd Finish | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | SERVICES | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | Conveying | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | Vertical Conveying Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | .10 | Elevators | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | .20 | Lifts | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | .30 | Escalators | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | .50 | Dumbwaiters | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 10 | .60 | Moving Ramps | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 30 | Horizontal Conveying Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 30 | .10 | Moving Walks | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 30 | .30 | Turntables | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 30 | .50 | Passenger Loading Bridges | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 30 | .70 | People Movers | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | Material Handling | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .10 | Cranes | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .20 | Hoists | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .30 | Derricks | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .40 | Conveyors | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .50 | Baggage Handling Equipment | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .60 | Chutes | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 50 | .70 | Pneumatic Tube Systems | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | Operable Access Sys | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | .10 | Suspended Scaffolding | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | .20 | Rope Climbers | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | .30 | Elevating Platforms | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | .40 | Powered Scaffolding | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 10 | 80 | .50 | Building Envelope Access | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | Plumbing | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | Domestic Water Distribution | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | .10 | Facility Potable Water Storage Tanks | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | .20 | Domestic Water Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | .40 | Domestic Water Piping | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | .60 | Plumbing Fixtures | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 10 | .90 | Domestic Water Distribution Sup Comp | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 20 | Sanitary Drainage | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 20 | .10 | Sanitary Sewerage Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 20 | .30 | Sanitary Sewerage Piping | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 20 | .90 | Sanitary Drainage Sup Components | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | Building Support Plumbing Systems | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | .10 | Stormwater Drainage Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | .20 | Stormwater Drainage Piping | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | .30 | Facility Stormwater Drains | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | .60 | Gray Water Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 30 | .90 | Building Sup Plumbing System Sup Comp | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 50 | General Service Compressed Air | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | Process Support Plumbing Systems | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .10 | Compressed-Air Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .20 | Vacuum Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .30 | Gas Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .40 | Chemical-Waste Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .50 | Processed Water Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 20 | 60 | .90 | Process Support Plumbing Sys Supplementary Comp | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | HVAC | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 10 | Facility Fuel Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 10 | .10 | Fuel Piping | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 10 | .30 | Fuel Pumps | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 10 | .50 | Fuel Storage Tanks | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 20 | Heating Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 20 | .10 | Heat Generation | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 20 | .30 | Thermal Heat Storage | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 20 | .70 | Decentralized Heating Equipment | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 20 | .90 | Heating Sys Sup Comp | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | Cooling Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | .10 | Central Cooling | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | .30 | Evaporative Air-Cooling | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | .50 | Thermal Cooling Storage | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | .70 | Decentralized Cooling | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 30 | .90 | Cooling Sys Sup Comp | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 50 | Facility HVAC Distribution System | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 50 | .10 | Facility Hydronic Distribution | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 50 | .30 | Facility Steam Distribution | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 50 | .50 | HVAC Air Distribution | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 50 | .90 | Facility HVAC Dist. Sys Sup Components | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | Ventilation | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .10 | Supply Air | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .20 | Return Air | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .30 | Exhaust Air | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .40 | Outside Air | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .60 | Air-to-Air Energy Recovery | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .70 | HVAC Air Cleaning | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 60 | .90 | Ventilation Sup Comp | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 70 | Special Purpose HVAC Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 30 | 70 | .10 | Snow Melting | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | Fire Protection | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 10 | Fire Suppression | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 10 | .10 | Water-Based Fire-Suppression | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 10 | .50 | Fire-Extinguishing | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 10 | .90 | Fire Suppression Sup Comp | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 30 | Fire Protection Specialties | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 30 | .10 | Fire Protection Cabinets | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 30 | .30 | Fire Extinguishers | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 30 | .50 | Breathing Air Replenishment Systems | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 40 | 30 | .70 | Fire Extinguisher Accessories | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | Electrical | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | Facility Power Generation | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | .10 | Packaged Generator Assemblies | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | .20 | Battery Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | .30 | Photovoltaic Collectors | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | .40 | Fuel Cells | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 10 | .70 | Transfer Switches | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 20 | Electrical Service and Distribution | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 20 | .10 | Electrical Serv. Entrance | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 20 | .30 | Power Distribution | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 20 | .70 | Facility Grounding | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 30 | General Purpose Electrical Power | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 30 | .10 | Branch Wiring System | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 30 | .50 | Wiring Devices | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 40 | Lighting | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 40 | .10 | Lighting Control | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 40 | .20 | Branch Wiring for Lighting | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 40 | .50 | Lighting Fixtures | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 80 | Misc. Electrical Systems | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 80 | .10 | Lighting Protection | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 50 | 80 | .70 | Transient Volt. Suppression | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | Communications | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | 10 | Data Communications | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | 20 | Voice Communications | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | 30 | Audio-Video Communication | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | 60 | Distributed Communications and Monitoring | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 60 | 90 | Communications Sup. Components | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | Elect Safety and Security | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | 10 | Access Control and Intrusion Detection | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | 30 | Electronic Surveillance | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | 50 | Detection and Alarm | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | 70 | Electronic Monitoring and Control | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 70 | 90 | Electronic Safety and Security Supplementary Components | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 80 | Integrated Automation | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
D | 80 | 10 | Integrated Automation Facility Controls | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | EQUIPMENT & FURNISHINGS | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | Equipment | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 10 | Vehicle and Pedestrian Equipment | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 10 | .10 | Vehicle Servicing Equipment | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 10 | .30 | Interior Parking Control Equipment | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 10 | .50 | Loading Dock Equipment | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 10 | .70 | Interior Ped Control Equip | [12 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | Commercial Equipment | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .10 | Mercantile and Service Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .20 | Vault Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .25 | Teller and Service Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .30 | Refrigerated Display Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .35 | Commercial Laundry and Dry Cleaning Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .40 | Maintenance Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .50 | Hospitality Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .55 | Unit Kitchens | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .60 | Photo Processing Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .70 | Postal, Packaging and Shipping Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .75 | Office Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 30 | .80 | Foodservice Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | Institutional Equipment | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | .10 | Educ. and Scientific Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | .20 | Healthcare Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | .40 | Religious Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | .60 | Security Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 40 | .70 | Detention Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 60 | Residential Equipment | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 60 | .10 | Residential Appliances | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 60 | .50 | Residential Stairs | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 60 | .70 | Residential Ceiling Fans | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 70 | Entertainment and Recreational Equipment | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 70 | .10 | Theater and Stage Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 70 | .20 | Musical Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 70 | .50 | Athletic Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 70 | .60 | Recreational Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 90 | Other Equipment | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 90 | .10 | Solid Waste Handling Equip | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 90 | .30 | Agricultural Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 90 | .40 | Horticultural Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 10 | 90 | .60 | Decontamination Equipment | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | Furnishings | [14 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | Fixed Furnishings | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | .10 | Fixed Art | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | .20 | Window Treatments | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | .30 | Casework | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | .70 | Fixed Multiple Seating | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 10 | .90 | Other Fixed Furnishings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | Movable Furnishings | [13 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | .10 | Movable Art | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | .30 | Furniture | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | .40 | Accessories | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | .60 | Movable Multiple Seating | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
E | 20 | 50 | .90 | Other Movable Furnishings | [12 empty] | 100 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | SPECIAL CONSTRUCTION & DEMOLITION | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | Special Construction | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 10 | Integrated Construction | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 20 | Special Structures | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 30 | Special Function Construction | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 50 | Special Facility Components | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 60 | Athletic and Recreational Special Construction | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 10 | 80 | Special Instrumentation | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 20 | Facility Remediation | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 20 | 10 | Hazardous Materials Remediation | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 30 | Demolition | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 30 | 10 | Structure Demolition | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 30 | 30 | Selective Demolition | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
F | 30 | 50 | Structure Moving | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | BUILDING SITEWORK | [15 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | Site Preparation | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | 10 | Site Clearing | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | 20 | Site Elements Demolition | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | 30 | Site Element Relocations | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | 50 | Site Remediation | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 10 | 70 | Site Earthwork | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | Site Improvements | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 10 | Roadways | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 20 | Parking Lots | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 30 | Pedestrian Plazas and Walkways | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 40 | Airfields | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 50 | Athletic, Recreational, and Playfield Areas | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 60 | Site Development | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 20 | 80 | Landscaping | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | Liquid and Gas Site Utilities | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 10 | Water Utilities | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 20 | Sanitary Sewerage Utilities | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 30 | Storm Drainage Utilities | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 50 | Site Energy Distribution | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 60 | Site Fuel Distribution | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 30 | 90 | Liquid and Gas Site Utilities Supplementary Components | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 40 | Electrical Site Improvements | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 40 | 10 | Site Electric Distribution Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 40 | 50 | Site Lighting | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 50 | Site Communications | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 50 | 10 | Site Communications Systems | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 90 | Miscellaneous Site Const | [14 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
G | 90 | 10 | Tunnels | [13 empty] | 200 | [5 empty] | 300 | [6 empty] | 350 | [5 empty] | 400 | [6 empty] | 350
Note on A28: Study and SpaceModeling: If space modeling insert spaces by function and appropriate LOD for project
Note on H69: MPA: Some elements may be transferred to another discipline model over time. Ex. From arch to structural
Note on X69: Admin-DED: 200 - Model Element is graphically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element.

## 6. LVL G (DATE) Clash Det
PROJECT - Clash Detection Matrix (ZONE) | [9 empty] | See BIM Guide for Instructions
Date: DATE
Trade | Arch | Struc | PL | EL | MD | MP | FP | TD | Arch Cores | Arch Shell
Arch | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | 0
Struc | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | 0
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
[9 empty] | NC | NC | 0 | bar: Date: DATE Trade to Date: DATE TD
Arch Cores | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | 0
Arch Shell | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY:
| NC = | Not Checked
Filling in cells above grey cells automatically fills in the corresponding cells below the grey cells
[5 empty] | Previous file |  | HOLD
Batch |  | Previous | New | Active (Carry Over) | Resolved | HTML Report | VP Report
Arch vs PL
Arch vs EL
Arch vs MD
Arch vs MP
Arch vs FP
Struc vs PL |  | 0 | 0 | 0 | 0
Struc vs EL |  | 0 | 0 | 0 | 0
Struc vs MD |  | 0 | 0 | 0 | 0
Struc vs MP |  | 0 | 0 | 0 | 0
Struc vs FP |  | 0 | 0 | 0 | 0
Struc vs TD
PL vs EL |  | 0 | 0 | 0 | 0
PL vs MD |  | 0 | 0 | 0 | 0
PL vs MP |  | 0 | 0 | 0 | 0
PL vs FP |  | 0 | 0 | 0 | 0
PL vs TD
PL vs Arch Core
PL vs Arch Shell
EL vs MD |  | 0 | 0 | 0 | 0
EL vs MP |  | 0 | 0 | 0 | 0
EL vs FP |  | 0 | 0 | 0 | 0
EL VS TD
EL vs Arch Core
EL vs Arch Shell
MD vs MP |  | 0 | 0 | 0 | 0
MD vs FP |  | 0 | 0 | 0 | 0
MD vs TD
MD vs Arch Core
MD vs Arch Shell
MP vs FP |  | 0 | 0 | 0 | 0
MP vs TD
MP vs Arch Core
MP vs Arch Shell
FP vs TD
FP vs Arch Core
FP vs Arch Shell
TD vs Arch Core
TD vs Arch Shell

## 6. Level G Results Chart
Animation
Level UG Clash Results
DATE
S vs P | NC
S vs E | NC
S vs MD | NC
S vs MP | NC
S vs FP | NC
P vs E | NC
P vs MD | NC
P vs MP | NC
P vs FP | NC
E vs MD | NC
E vs MP | NC
E vs FP | NC
MD vs MP | NC
MD vs FP | NC
MP vs FP | NC

## 7. Lookup Tables
LookUp Tables | These tables control the pull-down menus. Do not modify.
Architecture | A | Yes | Y | Construction | C | Education | 1 | 1 | 2014
Structural | S | No | N | Design | D | Justice | 2 | 2 | 2015
Mechanical | M | Option | O | Procurement | P | Renovation | 3 | 3 | 2016
Plumbing | P |  |  | Studies/Services | S | New Construction | 4 | 4 | 2017
Interiors | I |  |  | Facilities Mgt. | F | Study | 5 | 5 | 2018
Geotechnical | B | [5 empty] | 6 | 6 | 2019
Civil | C | [5 empty] | 7 | 7 | 2020
Survey/Mapping | V | [5 empty] | 8 | 8 | 2021
Landscape | L | [5 empty] | 9 | 9 | 2022
Contractor/Shop Draw | Z | [5 empty] | 10 | 10 | 2023
Equipment | Q | [5 empty] | 11 | 11 | 2024
Tel/Communications | T | [5 empty] | 12 | 12 | 2025
Electrical | E | [6 empty] | 13 | 2026
Fire Protection Engineer | F | [6 empty] | 14 | 2027
Commissioning | Cx | [6 empty] | 15 | 2028
Tenant | TR | [6 empty] | 16 | 2029
Specialty Consultant | SC | [6 empty] | 17 | 2030
Sub Cont/Shop Dwg | SB | [6 empty] | 18
Owner | O | [6 empty] | 19
20
21
22
23
24
25
26
27
28
29
30
31