|  |
| --- |
| **JDAI Bristol County Committee Work Plan 2022** |
| **Goal 1: Reduce the number of low-risk youth entering DYS detention** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Reduce the number of youth entering detention by recruiting people in positions who can make a difference at key decision-making points | Training/ Engagement Subcommittee will conduct outreach to identify a second co-chair and additional stakeholders to join the committee | Lower level of engagement is apparent at meetings | Attendance at meetings by:* Judge
* Probation
* ADAs
* Police
* Schools
 | -Concern that committee does not achieve results-Scheduling  | Within the next 6 months |
| Reduce the number of youth entering detention by interrupting the DCF🡪 Delinquency pipeline | DIY Subcommittee to develop multi-disciplinary team meeting/case conferencing model for youth involved with DCF that are charged with a delinquency | 38% of youth entering detention in Bristol County in 2021 were DCF involved at time of entry-need more information about type/extent of DCF involvement  | DCF youth will receive additional support/services and not be arraigned on charges/detained as a result of developed meeting process | Making sure all stakeholders are at the table and are aware of the process | Ongoing (multi-year process) |
| **Goal 2: Reduce the length of stay of youth in detention** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Reduce the length of stay for youth in detention who are held because they are awaiting DCF placement | DIY Subcommittee will monitor and discuss the needs of youth held because they are awaiting placement | -Some youth are held on low bail amounts with release to DCF only-Dually involved youth have longer average lengths of stay compared to other youth: in 2021 ALOS for DCF involved youth is 26.6 days, ALOS for non DCF is 21.4 days | Average length of stay for DIY youth is reduced | Lack of DCF placements | Ongoing  |
| **Goal 3: Reduce ethnic and racial disparity for youth in the juvenile justice system** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Reduce the number of youth of color coming into detention/ being arraigned through education of decision makers | Training subcommittee:-Race Equity listening tours in small groups to help stakeholders internalize work, understand over-representation-dangers of detention training? | DYS data showing over-representation of BIPOC youth entering detention in Bristol County: 31.4% of youth entering DYS in 2021 identify as Black (make up 7.6% of total county population), 28.6% entering are White (80.2% of pop), 25.7% entering are Latinx (4.72% of pop) | Over-representation will decrease | Ensuring that we offer new and engaging trainings  | Ongoing throughout the year |
| **Goal 4: Replicate JDAI with fidelity at the local level** |
| **What are the results we want to achieve?** | **What activities will get us to those results?** | **What is the baseline data? What data sources are we using/do we need?** | **How will success be measured? (What are the positive youth outcomes associated with the goal?)** | **What challenges might we anticipate to getting results?** | **Timeframe** |
| Listen to youth voices and include youth in decision making | Committee will actively include members of JDAI Youth Committee | Youth currently don’t have ability to participate in JDAI or committee initiatives  | Youth will attend JDAI meetings, consult on initiatives | Difficult time engaging youth because of movement in and out of detention | Ongoing once JDAI launches committee |