## Metrics
FY21 EOTSS Project Performance Metrics (As of XX/XX/XX)
1. Program/Project Information | [8 empty] | 1.1. Program Status
Agency/Secretariat |  | EOTSS | [6 empty] | As of Date | Current Month | Prior Month 1 | Prior Month 2
Program Code: | [8 empty] | Scope | On Track | On Track | On Track
Program Name: | [8 empty] | Milestones | On Track | On Track | On Track
Executive Sponsor |  | <name> | [6 empty] | Budget | On Track | On Track | On Track
Project Manager |  | <name> | [6 empty] | Schedule | On Track | On Track | On Track
Start Date |  | <date>
End Date |  | <date>
1.2. Project Assessment : <describe>
2. Current Fiscal Year Objectives and Current Fiscal Year Plan Performance
Change Control and Schedule Overview |  |  |  |  | Completion Date |  | %
# | Milestone Description |  |  |  | Planned | Forecasted | Complete |  | Status | Comments
1 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
2 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
3 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
4 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
5 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
6 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
7 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
8 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
9 | Milestone TBD |  |  |  | <date> | <date> | 0% |  | On Track | <comments>
3. Current Fiscal Year Financial Performance
FY21 Spend Estimate |  |  |  |  | FY Quarterly Spend Analysis (Cash out the door)
FY21 Budget |  |  | 0 |  |  |  | Q1 | Q2 | Q3 | Q4 | A/P |  | FY21 Total
Committed Spend |  | 0 |  |  | Vendors |  | 0 | 0 | 0 | 0 | 0 |  | 0
Forecast, Not Committed |  | 0 |  |  | Staff Aug |  | 0 | 0 | 0 | 0 | 0 |  | 0
Reserve |  | 0 |  |  | Other (1-time pymts, etc.) |  | 0 | 0 | 0 | 0 | 0 |  | 0
FY21 Spend Est |  |  | 0 |  | Total Spend |  | 0 | 0 | 0 | 0 | 0 |  | 0
Variance |  |  | 0
[5 empty] | FY21-FY26 Spend Est |  | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | Total
[5 empty] | BondCap |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Project Risks and Project Issues
Date | Risk |  |  |  |  | Mitigation Activity | [6 empty] | Status
<Date> | Risk 1 |  |  |  |  | Mitigation 1 | [6 empty] | Off Track
<Date> | Risk 2 |  |  |  |  | Mitigation 2 | [6 empty] | On Track
<Date> | Risk 3 |  |  |  |  | Mitigation 3 | [6 empty] | Not Started
<Date> | Risk 4 |  |  |  |  | Mitigation 4 | [6 empty] | At Risk
<Date> | Risk 5 |  |  |  |  | Mitigation 5 | [6 empty] | Complete
5. Executive Attention
Assistance Required: <describe assistance such as subject matter expertise, contingency funding or other types of assistance>
6a. Transition to Operations/Benefits Realization
<Explain how completed project/milestones will transition to Operations and intended benefits will be confirmed>
6b. Capital-to-Operating Spend Implications by Year
|  | Operating Spend |  | FY21 | FY22 | FY23 | FY24 | FY25 |  | Comments
|  | Increases or new Op spend |  | 0 | 0 | 0 | 0 | 0 |  | <comments>
|  | Decreases/Elimination to Op spend |  | 0 | 0 | 0 | 0 | 0 |  | <comments>
|  |  |  | 0 | 0 | 0 | 0 | 0 |  | <comments>
Executive Office of Technology Services and Security Office of Capital Planning

## Guidance
FY21 EOTSS Project Performance Metrics
See ISA Section 8
Monthly Status Reporting (Dashboard):
The Seller (Project Sponsor/SCIO) shall submit to EOTSS, on a monthly basis, project performance metrics that will be sufficient to derive a project status representation to date. Performance metrics to be reported on are (but are not limited to) the following:
1 | Project Assessment – Clear and succinct summary stating the overall state/status of the project and its likely outcomes. The Project Assessment should address 3 areas: 1.) the state of the project as of a particular moment in time; 2.) a brief statement of where the project expects to be in the next 1-3 months and 3.) a concise statement which describes the outlook of the major objectives of the project throughout the project’s life.
2 | Current Fiscal Year Objectives – The Current Fiscal Year Objectives should reflect what was documented in the most current Capital Investment Plan (CIP) submission. Additionally, any objectives that were added to the project scope during the course of the current fiscal year should also be captured and tracked in the Work Breakdown Structure of the project plan and schedule.
Current Fiscal Year Plan Performance – This metric references the cumulative total number of tasks planned to start and finish each month as compared to the cumulative total number of tasks that actually started and finished.
Change Control – The intent of the Change Control metric is to display, in an easy-to-read format, the changes to the project’s schedule and/or budget as it relates to the project’s defined fiscal year objectives.
Schedule Overview – The Schedule Overview depicts the percent complete for each project objective and major phase (Initiation, Planning, Execution, & Closure) of the project.
3 | Current Fiscal Year Financial Performance – The Current Fiscal Year Financial Performance metric summarizes the project’s financial activity with respect to the approved capital budget, forecasted spend plan, commitments, and expenditures for the current fiscal year. Moreover, this metric should also factor in total estimated project cost over the life of the project.
4 | Project Risks – The Project Risks list is used to provide management with the highest level and most critical risks impacting the project. The top risks should be taken directly from the project’s risks log.
Project Issues – The Project Issues list is used to provide management with the highest level and most critical issues impacting the project. The top issues should be taken directly from the project’s issues log.
5 | Executive Attention – Very clear synopsis of any issues the team feels needs immediate executive support or action on, or to give an executive clear warning of a major concern or action of the team.
6a | Transition to Operations/Benefits Realization – Please outline how completed projects/milestones will transition to Operations and how the intended benefits will be confirmed.
6b | Capital-to-Operating Spend Implications by Year – Please provide the FY21-FY25 impact on operating spend. Also, please provide the total annual impact for items that are projected to either increase or decrease operating funding to inform timely decision making.
The Buyer (EOTSS) may communicate the status on any capital project, derived from monthly performance metrics, both internally and externally as a means of transparency. Additional and/or more frequent and detailed reporting may be required as it is deemed necessary to oversee the project.
Additional guidance
1.1 | 1.1. Program Status: Intends to capture a heatmap view of project status by Scope, Milestones, Budget and Schedule. Select a status from the drop down menu. Status rating guidance as follows:
On Track | Project is on- track, any and all obstacles to success are known and being managed effectively
At Risk | Project is at risk of not achieving FY21 objectives. Risk / Issues have been identified and remendation action are focused on getting project back on- track
Off Track | Project is projected to be off-track for FY21. This may indicate current and/or future issues pose a likely threat to not achieving FY21 project objectives
Not Started | Project not started. Note, if the project was supposed to start and is delayed 3 months this may require an off-track rating
Complete | Project is completed
3 | FY21 Budget, Qtrly Spend Analysis, and FY21-FY26 Spend Est: –
a. FY21 Spend Est - Intended to capture how much of FY21 Spend Est is a) committed, b) forecasted, but not committed or c) reserve (not yet forecasted)
b. FY21 Quarterly Spend Analysis - The quarterly cash flow analysis will provide a view into spend (cash outflow) by quarter that will aid the A&F allotment process
c. FY21-FY26 Spend Est - FY21 should auto populate when you complete the FY21 Spend Est section. Please project FY22-26 spend estimates

## Due dates and Quarterly Reviews
FY21 EOTSS Project Performance Metrics
Due dates and quarterly review
EOTSS Capital Planning will meet with the SCIO quarterly to review project progress.
The completed Report should be emailed to Kevin Ennis and Tim Driscoll no later than the due dates below for inclusion in the consolidated EOTSS Capital Report.
Month | Report due date | Quarterly Review (week of)
Sept | 2020-10-09 | 2020-10-12 | FY21 project kick-off
Oct | 2020-11-06
Nov | 2020-12-11
Dec | 2020-01-08 | 2021-01-11 | link to FY22 Planning cycle
Jan | 2020-02-12
Feb | 2020-03-12
Mar | 2020-04-09 | 2021-04-12 | link to Projects in Excess of $250K exercise
Apr | 2020-05-07
May | 2020-06-11
Jun | 2020-07-09 | 2021-07-12 | Year end Progress Review

## Lookups (hidden)
Project Status
Blue | Complete
Green | On Track
Yellow | At Risk
Red | Off Track
Grey | Not Started