## Bid Doc Review
PREPARATION OF BID DOCUMENTS FOR CONTRACTOR PROCURMENT-MGL c. 149 over $150,000 ECC
Project #: |  |  | DOCUMENT FOR DELEGATION TRAINING | Date
Project Title: |  |  |  | Project Manager
Director/Deputy
Project Location: |  |  |  | Procurement Type | c149
Advertisement Date
Filed Sub-Bid Date
Designer: |  |  |  | GC Bid Date
Yes | No | General Requirements |  |  | Comments
Documents Necessary for a Project project to be Advertised:
Designer's Cost Estimate (Completed within 12 months of bidding)
List of Filed Sub-Bid Categories and required Paragraph E sub-sub bids
Project Drawings - Stamped & Sealed
Project Specifications with Professional Seals Page Stamped & Sealed
Prime Contractor DCAMM Certification Category (28 to select from)
Advertising Required in COMMBUYS, NEWSPAPER of general circulation, CENTRAL REGISTER (must be submitted to Central Register by Tuesdays by 4:00 pm to appear in the Central Register on the following Wednesday (8 days later), and AGENCY WEBSITE.
Yes | No | Specification Review |  |  | Comments
Table of Contents/Professional Seals Page
Verify professional seals page has been stamped and signed
Verify that all Specifications Sections are listed in Table of Contents and are included in sequential order in specification(s)
All Filed Sub-bid sections are identified with an asterisk (*) and footer reads * Indicates Filed Sub-Bid Required.
All sub-sections of Filed Sub-bids (Chapter 149) are identified with (Part of Work of Section XXXXXX, Filed Sub-bid)
"Unit Prices" Section 012200 and "Alternates" 012300, if not used, should appear in the Table of Contents and labeled “(Not Used)”
General
Verify the following:
All Notes to Designers, including any contained in double parentheses have been removed.
There is an "END OF SECTION" at the end of each spec section.
All spec sections for 149 read and Mass. State Project # and Project Title in upper right header.
All filed sub-bids and their subsections are properly numbered and identified.
Cross referencing in filed sub-bid specification sections are accurate.
Cross reference sub-subs listed in Paragraph E work with filed sub listed in specification
List of drawings included in the summary section of the specification is consistent with the index on the actual plans.
All sections listed in specification are included as part of the specification.
All specifications for materials list a minimum of three different products followed by the word "or equal" Only exception is proprietary specification which must be requested in writing with justification and approved by the Deputy Commissioner for Design and Construction. Approved proprietary specifications must still include "or equal" after the product reference.
Section 011000 – Summary Section
Paragraph 1.3 - Review project information/Scope of Work for accuracy and completeness.
Paragraph 1.4 - Insert “Submit questions to (add name of person responsible for procurement)"
Paragraph 1.5 - Insert “Category of Work” for Prime Contractor.(28 Prime Contractor DCAMM Certification Categories to Choose From)
Project time of operations comply with end user requirements.
Drawings list matches that on the Drawing Cover Sheet or Title Sheet.
Section 012200 - Unit Prices
Filed Sub-bid Unit Price work and General Bid Unit Price work is referenced in the Unit Price section of the specification (012200) and the Unit Price section cross references each applicable section of the specification. Unit Price Sheet “SAMPLES” (with “SAMPLE watermark) are included at the end of all sections that include unit prices.
Unit Price descriptions should be clear and concise, with no ambiguities to the actual scope.
The GC Unit Price work is referenced in the Unit Price section and that it is cross referenced with the description of the affected Section(s). Unit Price Sheets are made part of the Bid Forms (pages 2a, 2b2c…Etc.) with A "SAMPLE" watermark. Same for Sub-bid Unit Price Sections
Section 012300 - Alternates
Alternates are numbered in order of preference.
Alternates are listed as an Add or Deduct Alternate.
Alternate section references each applicable section of the specifications affected and the alternate description appears in each of those sections.
Alternate description and associated alternate number on the specifications matches those on the Contract Drawings.
Confirm cost estimate summary includes estimated costs for all alternates.
Filed Sub-bid Sections:
Sub-subs Paragraph 1.1 C insert “None” if there are no sub-subs (do not remove this paragraph). List Class of Work and reference Paragraph or Section # if any. (Sub-subs must be at least $25,000)
Reference Drawings Paragraph 1.1 D – Should read “Filed Sub-bid.” Replace “((When issuing for bidding, insert a list of the drawings applicable to the work of this section, including drawing number and title.))” with the list of drawings for each section.
Yes | No | Drawing Review |  |  | Comments
General
Drawings are stamped and signed by the appropriate discipline.
All dates on Drawings and Specifications match.
Project number and name are on all sheets.
Drawings are in correct sequential order.
Any numbering shown on the drawings is consistent.
Comments
Instructions to Bidders
Chapter 149 - Contract Cover Page and Instructions to Bidders
Pages 1-3 completed
Project number & name on contract cover page & Instructions to Bidders match plans & specs
Appropriate "Category of Work" has been selected
Project description matches project scope (this will appear in the Legal Ad)
Insert MBE/WBE goals-Custom Project Specific Goals Must be set by DCAMM Compliance Office
All Filed Sub-Bid categories are included and match those of the specifications and are properly labeled and numerical order
Insert Bid Dates and if applicable, Pre-bid/Site Visit Information
Chapter 149 - Owner - Contractor Agreement, Payment and Performance Bonds (Assembled by Assigned Attorney)
Insert Project Information
Article 1 - Insert Scope of work that has been tailored to project
Article 2 - Project Completion number of days has been inserted
Article 7 - MBE/WBE goals set for Project by DCAMM Compliance have been inserted
Article 8 - Liquidated Damages has been inserted. Insert "NONE", if not applicable
*NOTE ON ADDENDA
Language contained in an addendum should make reference to adding, deleting and/or replacing of a specific Section #/Paragraph #