## Sheet1
FY 2024 BoS CoC NOFO Response Timeline |  |  |  | 08.14.24
Item | Dates in bold are required by the NOFO | Who Responsible | Done | Comments
Complete
In progress
MA CoC NOFA on CommBUYS | 05.30.24 | Karen | X | Request new project applicants
NOFO Released | 07.31.24 | HUD | X
Applications available in e-snaps; instructions available at HUD website | In progress | HUD |  | CoC Program Competition ¦ HUD.gov / U.S. Department of Housing and Urban Development (HUD)
NOFO Kickoff meeting | 08.12.24 | HLC Team
Collaborative Application assignments made | 08.12.24 | Karen
Review NOFO webinar | 08.13.24 | Interested parties |  | FY24 CoC Program Competition Webinar link
Meeting to review NOFO changes from previous years, what is new, CoC-required tasks, discuss reallocations proposed (if any), new projects, DV projects and the Ranking and Review Tool. | 08.14.24 | Interested parties
Renewal Applications assigned to HLC Team | 08.16.24 | Karen
Applications in e-snaps ready for subrecipients | 08.19.24 | HLC Team
Web Posting of Competition Deadline; screen shot | 08.19.24 | Desiree |  | HUD requires 30 days before the competition submission deadline
Request for Concept Papers | 08.20.24 | Karen
Concept Papers due | 09.03.24 | Interested parties
CoC Application input due to Karen | 09.06.24 | HLC Team
Draft Project Applications due in esnaps | 09.13.24 | Project applicants |  | These will be reviewed by HLC staff
Review applications | Ongoing as applications are submitted through final project application | HLC Team
Ranking and Review Groups created | 09.23.24 | Karen and Kelly
Final project applications and all attachments due in esnaps | 09.27.24 | Project applicants
All Applications received by CoC | 09.27.24 | Project applicants and HLC team |  | HUD requires 30 days before submission which falls on a weekend this year
Training for Ranking and Review Groups | 10.01.24 | Karen and Kelly
Ranking and Review Groups review applications | 10.02-10.08.24 | Groups
Final project scores submitted to Karen | 10.09.24 | Review Group Leads
Project Evaluation Committee Meets to decide on ranking reccomendations to present to the Advisory Board | 10.10.24 | Project Evaluation Committee, HLC Team
Advisory Board meets to review priority list options and vote on final priority listing | 10.11.24 | Advisory Board |  | Votes on all projects accepted, rejected, or reduced.
All applications notified of acceptance or rejection by CoC | 10.15.24 | Karen |  | HUD requires 15 days before submission deadline
Public Notification of acceptance, rejection or reduction of project applications, and ranking position in the Priority Listing in writing | 10.15.24 | Karen and Desiree |  | HUD requires 15 days before submission deadline
Collaborative Application draft ready for last review before Chris T. | 10.16.24 | Team
Final Review of Consolidated Application | 10.22.24 | Chris T. |  | Will be sent to Chris by 10.16.24
Full NOFA response available on CoC webpage and partner websites for public review | 10.24.24 | Desiree and CoC members |  | HUD requires 2 days before submission deadline
Final Consolidated Application, Priority Listings and Project Applications with additional comments from public | 10.28.24 | Karen
NOFO submitted | 10.28.24 | Karen
NOFO responses due | 10.30.24