## Sheet 1 - Master
Example - Incentive / Disincentive Worksheet
2012-10-10 | DRAFT
MassDOT - Highway Division |  |  |  | Sheet 1 - Master
Boston Construction Section Office
Milestone No. 4 Incentive/Disincentive Worksheet for: (See separate worksheet for Milestone No. 2)
Project No. _________ - Project Description _______________________________________________________
1. MassDOT - Highway Division 6-26-12 ProjINFO Estimated Total Construction Cost = $246,376,400. Use 25% of this amount for the MS____ & 75% for MS#2 Incentive/Disincentive calculations. | [7 empty] | 61594100
2. Project length = 4.2 miles (from I-95 & Rt. 113 @ the south end to I-95 Exit 60 @ the north end.) See Step #9C below.
3. Maximum Incentive Payment @:
5% of Total Estimated Project Cost (FHWA-recommended cap) = |  |  |  | 61594100 | X | 0.05 | = | 3079705
4. Original Milestone #4 - North End Roadway Opening Duration in Calendar Days per Rev'd. Standard WB006 - Base Case (5, 8-hr. days/wk.) from revised NTP of March 12, 2013 NTP = |  |  | 436 | 14.5333 | MO | 1.1945 | YR
5. Original Milestone #4 Completion Date = |  |  | 2014-05-21
6. Revised Milestone #4 - North End Roadway Opening Duration in Calendar Days per Compressed WB007 - Accelerated Case (6, 10 hr. days/wk.) from revised NTP of March 12, 2013 NTP = |  |  | 417 | 13.9 | MO | 1.1425 | YR
7. Revised Milestone #4 Completion Date = |  |  | 2014-05-02
8. Maximum Potential Time Savings from WB006 to WB007 = |  |  | 19 | 19 |  | >>> Calendar Days for Milestone #4. (The left # is calculated using the two durations above. The right # is a double-check using the two dates.)
9. Daily Road User Costs = DRUC = (Dollar Value of Drivers' Time per Hour) X (Number of Vehicles per Hour) X (Delay Time in Hours) X (Number of Work Hours per Day)
DRUC = $16,507.86 = $24.67/HR X 2,373 VPH X 0.011749 HRS of Delay Time X Work Hours per Day of 24 based on:
16507.8606 | = | 24.6707 | X | 2373 | X | 0.011749 | X | 24
A. Dollar Value of Drivers' Time per Hour: $24.67 per hour of general purpose vehicle driver’s travel time is based on a 2014 forecast using Consumer Price Index (CPI) History Table-adjusted average 1999 median earnings for the towns of Salisbury, Amesbury, Newburyport and West Newbury, which are the project towns, plus one town on either side of them. This method is similar to the one used for the FHWA-approved 1998 CA/T Hourly Road User Costs Determination. See Sheet 2 - Median Earnings tab below.
Use: | 24.6707
B. Number of Vehicles per Hour = 2,373 Vehicles per Hour. This is the hourly average for a 24 hour period based on the AADT @ Station #5087 (I-95 in Salisbury @ Amesbury Town Line) of 55,289 provided by Kristen Torrance - PB Traffic Engineer. Per Highway Capacity Manual, a lane-width reduction from 12 ft. to 11 ft. results in a 3% loss of capacity, which results in a 3% increase in volume = 2,304 X 1.03 = 2,373 VPH.
Use: | 2373 | VPH
C. Delay Time in Hours: Add'l. time required to travel the project length of 4.2 miles (from Step #2 above) at a planned speed reduction of 65 MPH to 55 MPH. 4.2 Miles / 65 MPH = 0.064615 HRS. 4.2 Miles / 55 MPH = 0.076364 HRS. 0.076364 - 0.064615 = 0.011749 Hours of Delay Time Per Vehicle. See #9B above for effect of lane-width reduction from 12' TO 11'.
Use: | 0.011749
D. Number of Work Hours per Day or the number of hours the detour, lane reduction, lane width reduction and/or speed reduction is in effect. A combination of a speed reduction and a lane-width reduction is in effect for 24 Hours per Day.
Use: | 24 | HOURS
10. MassDOT - Highway Division Construction Engineering Inspection Costs = $3,500 per Day (If actual costs are unavailable, use Liquidated Damages amount from MassDOT - Highway Division 06-15-2012 Supplemental Specifications to the 1988 English Standard Specifications for Highways and Bridges, Subsection 8.11 for projects with an estimated value of over $15M.)
Use: | 3500 | per Day
11. Incentive/Disincentive Daily Amount = $16,507.86 (from Step #9) + $3,500 (from Step #10) = $20,007.86, say, $20,000.
16507.8606 | + | 3500 | = | 20007.8606 |  | Say, = |  | 20000
15. Max. Potential Time Savings Based Upon 5% of Contract Value =
3079705 | divided by | 20000 | = | 153.9853 |  | Calendar Days
153.9853 | X | 20000 | = | 3079705 |  | NG - equals allowable $, but is greater than allowable duration.
19 | X | 20000 | = | 380000 |  | OK - less than allowable $ & equals allowable duration. Use 19 CDs.
16. Maximum Total Incentive Payment @ 5% of Total Contract Value = | [7 empty] | 380000 | (from Step #15)
17. Incentive Time Limit @ 5% of Total Contract Value in Calendar Days = | [7 empty] | 19 | (from Step #15)

## Sheet 2 - Median Earnings
2012-07-05 | Sheet 2 - Median Earnings
Project No. 601096 - Amesbury / Newburyport / Salisbury - I-95 over the Merrimack River & Evans Place Bridge (Whittier Bridge) Replacement - D/B ABP Mega-Project
9. Daily Road User Costs = DRUC = (Dollar Value of Driver’s Time per HR) X (Peak VPH) X (Delay Time in HRS) X (No. of Work HRS per Day)
Town | Median Earnings | 1999 - Hrly.
Salisbury | 29620 | 14.2404
Amesbury | 30612 | 14.7173
Newburyport | 36027 | 17.3207 |  | CPI - Adjustment
West Newbury | 40011 | 19.2361
Average | 34067.5 | 16.3786 | 1.034 | 16.9355 | 2000
|  |  | 1.028 | 17.4097 | 2001
|  |  | 1.016 | 17.6882 | 2002
|  |  | 1.023 | 18.0951 | 2003
|  |  | 1.027 | 18.5836 | 2004
|  |  | 1.034 | 19.2155 | 2005
|  |  | 1.032 | 19.8304 | 2006
|  |  | 1.028 | 20.3856 | 2007
|  |  | 1.038 | 21.1603 | 2008
|  |  | 0.9847 | 20.8365 | 2009
|  |  | 1.016 | 21.1699 | 2010
|  |  | 1.039 | 21.9955 | 2011 | Estimated based on actual CPI thru Nov. 2011.
|  |  | 1.039 | 22.8533 | 2012 | Assumed
|  |  | 1.039 | 23.7446 | 2013 | Assumed
| Project duration = 2012 - 2016. |  | 1.039 | 24.6707 | 2014 | Assumed
| Use mid-point = 2014. |  | 1.039 | 25.6328 | 2015 | Assumed
|  |  | 1.039 | 26.6325 | 2016 | Assumed