# Consultants Estimating Manual

Commonwealth of Massachusetts

D i v i s i o n	o f	C a p i t a l	A s s e t	M a n a g e m e n t

###### Issue Date February 2006

Table of Contents

Introduction 								1

1 Estimating Overview 							2

1.1  Types of Estimates							2

1.1.1  Preliminary Estimates						2

1.1.2  Square Foot Estimates and Cubic Foot Estimates			2

1.1.3  Measured Estimates						3

1.1.4  Final Estimates							3

1.1.5 Unit Price Estimating						3

1.1.6  Schedule of Rates						4

1.2  Building Design/Construct Phases Estimate Types			4

1.3  Estimating Formats							5

1.4  Estimate Type and Accuracy					5

1.5  Historical Databases						5

1.6  Forms/References							5

1.6.1  BNI								5

1.6.2  R.S. Means							6

1.6.3  Engineering News Review (ENR)					6

2  Developing an Estimate						7

2.1  Estimate Components						7

2.2  TPC Components							7

2.2.1 Construction Costs						7

2.2.2 Non-construction Costs (“Soft” or “Budget” Costs)	9

2.2.3  Planning the Work						9

2.2.4  Quantities							9

2.2.5  Unit Pricing							10

2.2.6  Bid Schedule							10

2.2.7  Construction Schedule						10

2.2.8  Estimate Notes							10

2.2.9  Project Narrative							10

2.2.10  Filed Sub-Bid Work						12

2.2.11  Estimating Contingencies					12

2.2.12  Overhead							13

2.2.13  Profit								13

3  Space Estimates							14

3.1  Database Space Measures						14

3.2  Building Floor Area Measurements					15

3.2.1  The Standard ASTM E1836-98					15

3.2.2  DCAM Space Model for Administrative Building			15

3.2.3  Summing the Tabular Model					16

3.3  Space Cost Analysis Sample Sheet					18

4  Phase Cost Estimates							19

4.1  Cost Estimate Submissions						19

4.2  Study Cost Estimate						19

4.2.1 Preliminary Study Cost Planning					19

4.2.2  Estimator Final Study Cost Estimate Deliverables			22

4.2.3  Estimate Date and Shelf-Life					22

4.2.4  Space Measurement						23

4.2.5  Estimator Participation						23

4.2.6  MEP Estimates and Allowances					25

4.3  Schematic Design Cost Estimate					27

4.3.1 Preliminary Schematic Cost Planning				27

4.3.2  Estimator Deliverables						27

4.3.3  Cost Estimate Inclusions						27

4.3.4  Estimate Date and Shelf-Life					28

4.3.5  Space Measurement						28

4.3.6  Estimator Processes						28

4.4  Design Development Cost Estimate					30

4.4.1  Estimator Deliverables						30

4.4.2  Cost Estimate Inclusions						30

4.4.3  Estimate Date and Shelf-Life					30

4.4.4  Space Measurement						30

4.4.5  Cost Estimator Participation					31

4.5  Construction Document Cost Estimate				32

4.5.1 Estimator Deliverables						32

4.5.2  Cost Estimates Inclusions						32

4.5.3  Estimate Date and Shelf-Life					33

4.5.4  Space Measurement						33

4.5.5  Cost Estimator Participation					33

5  Inclusions/Exclusions							35

5.1  Basis for Pricing							35

5.1.1  Additional Items and Allowances					36

5.1.2  Included General Conditions and Markups				36

5.1.3  Contingency Allowances Inclusions				36

5.2  Specific Inclusions and Exclusions					37

5.2.1  Items not included in a typical estimate are:			37

5.2.2  Items that May Affect Typical Estimates				38

5.2.3  Job Overhead Activities (Structuring Estimates Insert)		38

6 Escalation								39

6.1  Escalation Provisions and Calculations				39

6.1.1  Escalation Indices							39

6.1.2  Industry Trends and Projected Escalation Rates			39

6.1.3  Explaining the Escalation Contingency				39

6.2  Estimate Shelf Life							39

6.3  DCAM Escalation Index Table					40

7  Special Estimates							41

7.1  RFPs								41

7.2  Peer Review							41

7.3  Change Orders							41

7.4  ADA/MAAB Work							41

8  Electronic Formats							42

8.1  DCAM Uniformat II Elemental Entry				42

8.2  General Conditions							45

8.3  Space Measurement						46

9  Appendix–Reference Documents List					48

Appendix A1 – Checklist for UNIFORMAT II Estimates			49

Appendix A2 – Checklist for General Conditions			57

Appendix A3 – Checklist for Submissions				60

Appendix A4 – Sample Uniformat Structured Narrative 
(for Preliminary Design)						61

Appendix A5 – DCAM Estimate Summary Sheet			63

Appendix B – CSI Division Numbers and Titles				74

Appendix C – CSI Detailed Divisions					75

Appendix D – ASTM STANDARD E1557 UNIFORMAT II		80

Appendix E – Building Floor Area Measurements			84

Appendix F — Bibliography						85

Appendix G — Acronyms						86

Appendix H — Glossary						89

Index		 							94

# Introduction

The Division of Capital Asset Management’s (DCAM) Office of Planning, Design and Construction (OPDC) is responsible for the cost throughout all phases of state building projects, from project initiation and Study to final Design and Construction. Architectural and engineering firms that prepare building studies, and develop final design and construction documents, will submit Cost Estimates and participate in cost control activities for each phase.

Rigorous Cost Management is essential throughout each project’s planning, design, and construction phase. This Consultants Estimating Manual contains forms and guidelines based on industry standards to enable consistency for DCAM Designers and Consultants in the Cost Management of OPDC projects. Once an initial budget has been established, DCAM will constantly monitor the project budget by employing a series of increasingly precise cost estimating techniques, matching the development of the project design through each phase.

Submission formats and processes represent industry standard practices as they apply to DCAM projects.

The reference section includes a list of acronyms, a glossary and all relevant formats. An index is located at the end of the document, and hyperlinks have been provided throughout the electronic version. Intended to be a “Living Document,” this manual will undergo periodic updates as procedures change. Naturally, comments from DCAM Consultants are always welcome.

1

## Types of Estimates

### Preliminary Estimates

Estimating Overview

Preliminary Estimates are employed in the early planning phases of a proposed project to match client needs, assessed programmatic requirements, and budget constraints in order to establish project scope and quality expectations. Estimate comparisons at this stage are utilized in evaluating the feasibility of strategic alternatives being considered to satisfy current and projected space requirements (e.g., new construction versus renovation, or lease space). Initial estimates may be by Program Unit (e.g., hospital bed) or equivalent order of magnitude accuracy.

### Square Foot Estimates and Cubic Foot Estimates

DCAM has developed models for buildings using elemental SF (Square Foot) rates and actively uses this method to balance program needs, specification levels, and budget/time constraints in both Study and Schematic Design phases. Based on historical data, SF Estimates and CF (Cubic Foot) Estimates are methods commonly used to develop preliminary budgets. They are effective in preparing more accurate estimates as the design is developed enough to allow for measurement and calculation of floor areas and volumes of the proposed spaces. Several historical databases support this method of estimating, and provide regularly updated unit costs ($/SF and $/CF). Many large estimating firms and professional organizations maintain their own databases, including DCAM.

Estimates made using this method need to allow for adjustments and additions for regional cost indices, local labor market rates, and interpolation between cost tables. Further adjustments may be made to account for other unique aspects of the design, such as special site conditions or design features being planned. In addition, when developed in UNIFORMAT II™, the estimate can provide overall SF or CF costs for major elements, along with build-out costs of different space types. This structure allows for relative ease in determining the impact that changes will have on the program.

### Measured Estimates

Measured Estimates are developed after proceeding with the preferred solution during the latter part of the Study Phase. These estimates maintain accountability for initial budget projections, and are used as a means of evaluating competing alternative construction assemblies, systems and materials. These estimates may be used in project Workshops, at decision points, and as part of the formal submissions to DCAM at the conclusion of each phase. As the design progresses, the estimating contingency can be reduced.

### Final Estimates

At the completion of Design Development and during Construction Documentation, a complete pre-bid estimate can be prepared using Unit Price Estimates as described below. The estimate is organized in the same format required of bidders, usually the CSI MasterFormat™, including separate estimates and bids for Filed Sub-Bids under MGL 149. This estimate allows for a comparison of the final estimate with the bids received and may aid in any contract negotiations. The estimating contingency should be reduced to zero. In addition, a final UNIFORMAT II™ format document is prepared from the same detailed information to provide continuity and comparison with previous phase estimates. Data are also used to update the DCAM cost database, providing elemental rates to be used in planning subsequent projects.

### Unit Price Estimating

The entire project is divided into small discrete work items, and a “unit price” is established for each item. The unit price is then multiplied by the required quantity to find the cost for the work item. All costs are summed to obtain the total Estimated Construction Cost. For example, the cost to erect a masonry wall can be accurately determined by finding the number of bricks required and estimating all costs related to delivering, storing, staging, cutting, installing, and cleaning the brick, along with related units of accessories, such as, reinforcing ties, weep-holes, flashings, etc. Unit Pricing Estimating within the CSI MasterFormat™ is the most accurate means of ascertaining costs based on materials and labor content.

### Schedule of Rates

A project may contain significant quantities of repetitive elements, without the exact amounts being defined. In this instance DCAM may issue the Bid documents as a partial or complete Schedule of Rates contract. A list of items and projected quantities is provided, leaving the bidder the opportunity to provide a rate for each item. The Schedule of Rates submitted by the successful bidder is used as the basis for the final contract measure of each item.

Estimators are required to submit estimated rates for items defined within a Schedule of Rates contract. The rates may be built up from system components if necessary to accommodate a nonstandard format. Items listed in a Schedule of Rates may be contract specific and not follow standard CSF or Uniformat structure.

## Building Design/Construct Phases Estimate Types

The phases used by DCAM are:	Estimate or Cost Category:

- Capital Budgeting	1.  Program Unit/Order of Magnitude

- Study	2.  SF/CF & Cost Modeling

- Schematic Design	3.  Uniformat Elemental 1,2

- Design Development	4. Uniformat Elemental 2,33 and CSI Masterformat

- Construction Drawings

& Bid Documentation	5.  Uniformat 3 and CSI Masterformat

- Procurement	6.  CSI Bids and Proposals

- Construction	7.  Schedule of Rates

After Practical Completion:	Additional Cost Categories:

- Project Close Out and Settlements	8.  Variations & Settlements

- Life Cycle Maintenance Period	9.  Life Cycle Costs

## Estimating Formats

The two most commonly used Unit Price formats are CSI MasterFormat 2004™, which provides a 31-division master list of numbers and titles for arranging products and activities; and ASTM UNIFORMAT II™, which hierarchically groups building elements into 12 “systems based” levels. MasterFormat™ is widely used within the design and construction industry, and is the usual format for construction specifications and most private-sector project-based cost estimating activity. Government and other large institutions also utilize UNIFORMAT II™ for building systems research and building economics analysis, in addition to cost estimating.

## Estimate Type and Accuracy

| Estimate Category | Budget | Study | SD | DD | CD | Bid | Const | Close |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Order of Magnitude (Functional Unit Measure) | √ |  |  |  |  |  |  |  |
| SF and CF Rates | √ | √ |  |  |  |  |  |  |
| Elemental Rates Level 1 |  | √ | √ |  |  |  |  |  |
| Elemental Rates Level 2 |  |  | √ | √ |  |  |  |  |
| Elemental Rates Level 3 |  |  |  | √ | √ |  |  |  |
| CSI Item List and Rates |  |  |  |  | √ | √ | √ | √ |
| Schedule of Rates |  |  |  |  |  | √ | √ | √ |
| Final Account |  |  |  |  |  |  |  | √ |

## Historical Databases

There are several historical databases available that provide current values for estimating costs of the various units of project work. The databases are compiled from records of actual project costs, and are published in the form of books, CDs and computer-based extranets.

## Forms/References

### BNI

BNI is a popular publisher of cost estimating guides in the U.S.

### R.S. Means

This is the most used and quoted source, with 25 different guides and unit prices for over 20,000 building components. This publisher also offers books on Unit Rate estimates and detailed application to project assessment.

    - Engineering News Record (ENR)

Engineering News Review magazine publishes monthly updates to major materials and labor costs, plus an historical index with regional modifiers.

2

## Estimate Components

Developing an Estimate

Back-up detailed estimating data may be in any format. As long as the items or work are properly grouped by level 3 account numbers, estimating detail work-ups below level 3 need not be identified by UNIFORMAT account numbers. To ensure that all components of an estimate are allowed for, the following points need to be considered.

- Regardless of format or type, every estimate can be rolled up to provide Total Project Cost (TPC).

- Standard contracts consider only ECC (Estimated Construction Cost) with additional “soft costs” added separately as margins or actual estimated amounts.

- Projects delivered using an RFP, Design-Build, or CM At Risk, have some or all of the “soft costs” built into the estimate, mingling ECC and soft cost components.

- Cost Estimators are required to ensure that all project estimate components and contingency markups are included or specifically noted as being allowed for by others. To ensure that all cost components making up the ECC and TCP are allowed for, DCAM recommends estimates be prepared by specialist cost estimating or consulting firms.

## TPC Components

### Construction Costs

      - Elemental: Sections A through G plus General Conditions

      - CSI: Sections 1 through 49 plus General Conditions

      - Insurances, Escalation, Contractors, Overhead and Profit

### Non-construction Costs (“Soft” or “Budget” Costs)

      - Feasibility Study with supporting studies and reports

      - Design Fees and Specialist Consultants

      - Site acquisition

      - Permits, Certifications and legal fees

      - Community allowances, utility or other relocations

      - Project administration and overhead (which may include CM fees)

      - FFE (furniture, fixtures and equipment)

      - Commissioning, relocation and startup costs

      - Financing and insurance costs through to startup

      - Development fees

### Planning the Work

It is important to thoroughly understand the project scope of work and the biddability and constructability aspects of the project being estimated. The Cost Estimator must thoroughly review drawings, specifications and other references to formulate a construction sequence and duration. A site visit for all Consultants is recommended to relate the physical characteristics of the project to the available design parameters and details. Developing a construction sequence as soon as possible is necessary for creating a formalized sequence, to be used throughout the entire cost estimating process as a checklist of construction requirements.

### Quantities

The Cost Estimator is responsible for the accuracy of quantity take-offs from drawings and specifications prepared by the Architect or other Consultants.

      - The quantity take-off is an important part of the estimate and should be based on all available design data. All quantities should be shown in standard units of measure.

      - The detail in which the quantities are prepared for each task is dependent on the Development Phase of the design. Quantity calculations and unit build-ups beyond design detail may be necessary to determine a reasonable price to complete the overall scope of work for the Cost Estimate. Project notes may be added to explain the basis for the quantity calculations, or allowances that have been determined by cost estimating judgment and will be updated as the design progresses.

### Unit Pricing

As a general rule, approximately 80 percent of the direct costs of a project are represented by only 20 percent of the estimated work items. Therefore the greatest estimating efforts are concentrated on these elements. The unit rates for each of these items are carefully analyzed and developed as the summation of all direct and indirect costs that will likely be incurred by an experienced and well-equipped Contractor.

When cost data is based on previously completed projects, the Cost Estimator must use judgment to adjust for project conditions to include overhead and price level data adjustments for inflation.

For small and easily identified work noted in the drawings and included in the estimate, lump sum bid items may be used. The cost of the lump sum item should be based on cost data related to the item’s total direct and indirect costs.

### Bid Schedule

The bid schedule is part of the procurement package and is included with the solicitation for bids. The estimate must show the unit prices, quantities, extension of unit prices, lump sum items, and costs consistent with the schedule provided with the Bid Documents.

### Construction Schedule

The Designer and Consultant Team will prepare a construction schedule to support the estimate that is consistent with the plans and specifications for completion of the work. It may be in the form of a GANTT chart or a PERT diagram, but it must identify the sequence and duration of the tasks upon which the Cost Estimate is developed.

### Estimate Notes

“Notes” are any explanations necessary to support the development of cost for individual items in the Cost Estimate. This descriptive information covers areas such as manufacturers quotes, overtime requirements, and material availability. These should be entered as notes to the appropriate detail level of the Cost Estimate.

### Project Narrative

The narrative defines the parameters upon which the Cost Estimate has been prepared to support the project scope and schedule. It describes the project requirements that must be performed in sufficient detail to give a clear understanding of the scope of work including length, width, height, and slope of primary features the following: special problems that will be encountered in performing the work; site conditions affecting the work, and the reasons for unusually high or low allowances.

Project Narratives are expected to follow the Uniformat II code structure through each Design Phase estimate. Initially, very broad level narratives are provided, increasing in detail as the design is developed. A partial sample of an early stage Uniformat structured Narrative is shown in Appendix A4.

At Construction Documentation and Design Development, the Project Narrative is replaced by the specification that is typically structured in detailed CSI format.

### Filed Sub-Bid Work

      - MGL 149 requires that specific trades be performed by filed sub-bids be procured by DCAM independently from the General Contractor bid.

      - The list of trades determined by MGL 149 is shown in Appendix C. For a detailed cross-reference of the work to be included against the CSI item classification, see the DCAM Standard Specification document.

      - Where a CSI bid is required at Design Development or Construction Document Phase, the work to be performed under filed sub-bids shall be identified separately in the estimate.

      - The successful low bid amount for each filed sub-bid Contractor is included as a direct lump sum cost to the General Contractor. This amount includes the Subcontractor’s costs for direct labor, materials and supplies, equipment, second tier subcontracts, and charges for overhead and profit.

      - The General Contractor is deemed to add his margins for General Conditions, Overhead and Profit, and any other loadings to the filed sub-bid contract amounts.

      - The Cost Estimator may utilize quotes for the expected filed sub-bid work in preparing the estimate or to verify the reasonableness of independently estimated subcontract work. Subcontractor quotes will be treated as proprietary information and should only be revealed to those who have a need to know.

### Estimating Contingencies

To develop appropriate contingency allowances, the Estimator must identify the uncertainty associated with an item of work or task, forecast the risk/cost relationship, and assign a value to this task that will limit the cost risk to an acceptable degree of confidence. Consideration must be given to the details available at each stage of planning, design, or construction for which a Cost Estimate is being prepared.

The following estimating contingency loadings represent an initial guide for the ECC at each phase. The Cost Estimator and Designers must assess the appropriate percentages for each project.

| Project Phase | Restoration | New Construction |
| --- | --- | --- |
| Study Phase | 20% | 15% |
| Schematic Design Phase | 15% | 10% |
| Design Development Phase | 10% | 5% |
| Construction Documents Phase | 0% | 0% |

The table provides a guide for estimating contingency development and is not intended to restrict or limit contingencies to these values. If the overall estimating contingency value developed through a detailed analysis as described above exceeds these guidelines, the Designer and DCAM Project Manager should consider further investigation of existing conditions and sufficient development of the design to reduce the uncertainty level.

### Overhead

Overhead costs are those costs that cannot be attributed to a single task of construction work. Costs that can be applied to a particular item or work should be considered a direct cost to that item and not be included in overhead costs.

The overhead costs are customarily divided into two categories:

      - General Conditions, including all Job Overhead, General Site Costs and Field Office Overhead. When estimating items costed over the entire duration of construction, the Cost Estimator should utilize the job schedule.

      - OH&P (Home Office Overhead), covering Overhead, Administrative costs, and Profit. OH&P expenses are those incurred by the Contractor in the overall management of business.

The Cost Estimator must be sure that costs are not duplicated between the two categories. Specific considerations must be evaluated for each project. The Cost Estimator must use considerable care and judgment in estimating overhead costs. For the source of pricing, the Cost Estimator must rely on judgment, historical data, and current labor market conditions to establish overhead costs.

The application of a previously determined overhead rate may be used for early design stages, but it is not an accurate or reliable method of forecasting costs. Overhead will vary from project to project and may even vary from month to month within any given project. Job overhead items for the General Contractor should be estimated in detail for all activities at Construction Documents Phase. Detailing of overhead costs for subcontract work is recommended when the impact of these costs is significant.

### Profit

Profit is shown as a percentage loading and provides the Contractor with an incentive to perform the work as efficiently as possible. The Cost Estimator must use previous historical data to provide a suitable industry profit loading, modified by an in-depth understanding of marketing conditions likely to impact the current project.

3

## Database Space Measures

Space Estimates

The Designer will provide the Estimator with a space analysis listing the program areas provided for in the concept design, the support areas, and the gross areas. The Designer should strive for high space efficiency that may result in a building with less gross area than the estimated maximum gross area provided by DCAM as the basis for the project.

DCAM will use the space and program areas at each phase as a basis for assessing and cost modeling the building to ensure program and cost budgets are met. During each phase, the Estimator is expected to provide cost information support for the Designer.

| Space Measures/ Phase | Budget | Study | SD | DD | CD | Bid | Const |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Functional Unit Measure (Accommodation) | √ |  |  |  |  |  |  |
| Program Area Measures | √ | √ | √ |  |  |  |  |
| Program Area Factors |  | √ | √ |  |  |  |  |
| Building Area Factors |  | √ | √ |  |  |  |  |
| Program Area Detailed Measures |  |  | √ | √ | √ |  |  |
| Building Area Detailed Measures |  |  |  | √ | √ | √ | √ |
| Building Performance Measures |  |  |  | √ | √ | √ | √ |

## Building Floor Area Measurements

### The Standard ASTM E1836-98

DCAM uses the ASTM E1836-98, “Standard Classification for Building Floor Area Measurements,” as a basis for preparation of program areas and support areas to make up the total Gross Floor Area of the project. DCAM’s model groups program areas according to the type and nature of the project. The Designer is to liaise with the DCAM Program Manager to establish the appropriate project space measures in each case.

### DCAM Space Model for Administrative Building

The table below illustrates a typical space model configuration for an administrative building. Sections A and B are specific to the building function. Sections D, E and F are common to all buildings. Note that Section C, “Assignable Area Loadings,” is only applied at preliminary Study Phase, when standardized program areas are utilized to assess the project scope.

A - Assignable Area A1 – Enclosed Office Areas Direct Functions A2 – Open Plan Work Station Areas A3 – Mission Specific Purpose Areas

B - Assignable Area B1 – Conference or Meeting Rooms Indirect Functions B2 – Restricted Area Service Rooms B3 – Support Rooms and Wet Areas B4 – Tenant Storage, Workshops, Docks

C - Assignable Area C1 – Prestige Level Loading Loadings C2 – Occupancy Type Loading C3 – Construction Class Loading C4 – Jurisdiction Loading

D - Net Useable Area D1 – Secondary Circulation Components D2 – Columns D3 – Partitions and Removable Walls

E - Gross Interior Area E1 – Mechanical and Electrical Components E1-1 - Mechanical Areas E1-2 - Electrical Areas E1-3 - Telecommunications Areas E1-4 - Vertical Penetrations and Chases E2 – Primary Circulation and Access E2-1 - Primary Circulation E2-2 - Stairwells E2-3 - Elevators E2-4 - Escalators E2-5 - Non-Assigned Public Areas E3 – Facility Common Services E3-1 - Toilet Areas E3-2 - Facility Maintenance Areas E3-3 - Facility Management Areas

F - Gross Exterior Area F1 – External Walls and Projections Components F2 – Attached External Walkways

### Summing the Tabular Model

The diagram below demonstrates how the tabular model shown in Section 3.2.2 is to be summed to match the Gross Floor Area at each phase. The accuracy of measurement is indicated below.

A	B	C	D	E

| Study – Preliminary | SF | SF | % loading | combined % |  |
| --- | --- | --- | --- | --- | --- |
| Study – Preferred Scheme | SF | SF | N/A | combined % |  |
| Schematic Design | SF | SF | N/A | SF | % |
| Design Detail | SF | SF | N/A | SF | SF |
| Construction Documents | SF | SF | N/A | SF | SF |

| 19650 |  |
| --- | --- |
| 4489 2695 500 7724 4242 | 4,489 |
|  | 675 |
|  | 1,373 |
|  | 647 |
|  | 121 |
|  | 379 |
|  | 7,677 |
|  | 47 |
|  | 0 |
|  | 2,637 |
|  | 1,605 |

## Space Cost Analysis Sample Sheet

Below is a spreadsheet model for an academic building with program adjustment and automatic cost revision calculation. In this example, detailed program areas shown in shaded cells can be adjusted by the user. Total building GFA and project cost are updated and displayed.

| SF TOTALS | REVISED PROGRAM |
| --- | --- |
| 46,878 | $12,554,738 |

ACADEMIC BUILDING PROGRAM

| Total GFA PROGRAM AREAS |  | 27228 | 27228 |
| --- | --- | --- | --- |
| Instructional/Studios | Course A | 14171 | 2,011 |
|  | Course B |  | 1,202 |
|  | Course C |  | 1,000 |
|  | Course D |  | 1,216 |
|  | Lecture/Presentation |  | 606 |
|  | Course E |  | 800 |
|  | Graduate |  | 4,137 |
|  | Undergraduate |  | 3,199 |
| Workshops/Laboratories | Course A | 6627 | 250 |
|  | Course B |  | 812 |
|  | Course C |  | 1,001 |
|  | Course D-1 |  | 1,057 |
|  | Course D-2 |  | 1,156 |
|  | Course D-3 |  | 1,548 |
|  | Course E |  | 803 |
| Faculty & Staff Space | Studios | 2821 | 2,346 |
|  | Offices |  | 475 |
| Storage | Course A | 1843 | 196 |
|  | Course B |  | 238 |
|  | Course D-1 |  | 208 |
|  | Course D-2 |  | 754 |
|  | Lecture/Presentation |  | 113 |
|  | General |  | 334 |
| Entry | Lobby/stair | 1766 | 1,766 |
| SERVICE AREAS | S/F SUBTOTAL |  |  |
| MEP basement | Basement |  |  |
| Fixed Services | Common Toilets |  |  |
|  | Stairs & Lobbies |  |  |
|  | Elevators |  |  |
| Fixed Facilities | Kitchen/Lounge |  |  |
|  | Lounge/wash areas |  |  |
| Corridors | Main |  |  |
|  | Entries |  |  |
|  | Exit Stairs |  |  |
| Walls & Columns | External @ 6% |  |  |
|  | Internal@ 3% |  |  |

4

## Cost Estimate Submissions

Phase Cost Estimates

During each phase, DCAM may require one or more estimate types to be formally submitted. In order to ensure the Project remains within budget at each Phase, the Designer and his team are expected to participate in Cost Modeling and Value Engineering activities as part of their Contract.

Itemized deliverables and activities for each Phase are listed in this section. Most phases have more than one format for submission. Designers and their Consultants, therefore, must plan their estimates to use the appropriate types and formats for each submission.

## Study Cost Estimate

### Preliminary Study Cost Planning

During the first half of the Study Phase, the Designer may consider various possible schemes. Higher-level estimates (see Sections 1.1.1 and 1.1.2) may be required to support initial cost planning and comparisons.

Designers may use historical square foot rates for these early estimates in accordance with the guidelines below. Generalized total rates from comparable projects should not be used to support a specific scheme without adjustments as outlined herein.

###### General Square Foot Rates

        - Each scheme presented as a plan or footprint with a defined envelope (number of floors) is to be supported by an expanded square foot rate estimate as shown in Section 4.2.1.3.

        - Estimated square foot rates are to be supported by a comparison of rates from similar projects completed in the last five years. Specific square foot rates are expected for the major mechanical services as shown in Section 4.2.1.3 and validated by both the MEP Consultant and the Cost Estimator.

###### Modifications to Standard Rates per Square Foot

Consideration should be given to the following building form factors weighed against comparable projects used to build the square foot rate:

        - External wall ratio and complexity to square foot area

        - Size scale (larger or smaller) than rates for comparable facilities

        - Structural outline, foundations and proposed systems against buildings

        - Configuration limitations in the design that may lead to an increase in standard mechanical cost allowances

(A full discussion of modification to square foot rates can be found in: “Square Foot & Assemblies Estimating Methods,” Third Edition, by RS Means.)

###### Lump Sum Allowances

Lump sum allowances are expected for site-specific items that are not included in the standardized overall construction rate. A typical list is below:

        - Site works, including general preparation, landscaping, profile restoration, required services

        - Cost allowance for site slope or access that will increase the standard SF rates

        - Parking area costs calculated at per-space costs, plus allowance for access control

        - Roadway modifications required by local authorities

        - Demolition of existing buildings and site cleaning for construction

        - Wetland provisions or restitution costs

        - Allowance for compliance with Massachusetts Historical Society requirements

        - Diversion of services around the proposed building footprint

        - Allowance for rectification of ADA or MAAB noncompliance items, in which the project scope does not specifically cover this work

        - Provision of additional services to the new buildings, including work done by utility companies

        - Legal or acquisition cost premium for the chosen site

        - Need for temporary accommodation, additional time, etc., for the chosen site

###### Uniformat Level 1 Breakdown for Preliminary SF Estimates

| Total Program Area |  |  | 30,000 | GFA 48,000 | Raw Rate/ SF $266 | Est. Cost | % of ECC | One-Line Specification or Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Multiplier |  |  | 1.60 |  |  |  |  |  |
| A | Substructure |  |  | 48,000 | $20.00 | $960,000 | 8% | Part basement level and standard footings |
| B | Shell |  |  | 48,000 | $65.00 | $3,120,000 | 26% | Steel frame with masonry cladding |
| C | Interiors |  |  | 48,000 | $35.00 | $1,680,000 | 14% | Metal/GWB partitions, standard finish |
| D | Services (not included below) |  |  | 48,00 0 | $2.00 | $96,000 | 1% | Includes communication & security |
| D10 |  | Conveying |  | 48,000 | $2.00 | $96,000 | 1% | One elevator with three stops |
| D20 |  | Plumbing |  | 48,000 | $10.00 | $480,000 | 4% | Standard quality systems |
| D30 |  | HVAC |  | 48,000 | $40.00 | $1,920,000 | 16% | Above average ventilation requirements |
| D40 |  | Fire Protection |  | 48,000 | $4.00 | $192,000 | 2% | Full building system |
| D50 |  | Electrical |  | 48,000 | $22.00 | $1,056,000 | 9% | Standard quality systems |
| E | Fittings & Fixed Equipment Special Construction & Demolition |  |  | 48,00 0 | $3.00 | $144,000 | 1% | Custom casework throughout |
| F |  |  |  | 48,00 0 | $2.00 | $96,000 | 1% | Existing 10,000 SF building |
| G | Building Site Work (not included below) |  |  | 48,00 0 | $0.00 | $0 | 0% |  |
| G10 |  | Site Preparation |  |  |  | $50,000 | 0% | Removal of carpark |
| G20 |  | Site Improvements |  |  |  | $100,000 | 1% | Landscaping allowance |
| G30 |  | Mechanical Utilities |  |  |  | $200,000 | 2% | Relocation of major services lines |
| G40 |  | Electrical Utilities |  |  |  | $100,000 | 1% | Relocation of distribution feeders |
| Z | General Conditions and Markups |  |  |  |  | $1,543,500 | 15% | Standard |
| Subtotal ECC Before Contingencies |  |  |  |  |  | $11,833,500 |  |  |
| Contingencies |  |  |  |  |  |  |  |  |
| Estimating Contingency |  |  |  |  | $1,183,350 |  | 10% | Standard for this level estimate |
| Phasing and Temporary Work |  |  |  |  | $650,843 |  | 5% | Phased occupancy allowance |
| Escalation Contingency |  |  |  |  | $1,093,415 |  | 8% | Midpoint construction end '06 |
| Total ECC with contingencies |  |  |  |  | $14,761,108 |  |  |  |
| Total Rate/SF with contingencies |  |  |  |  | $308 |  |  |  |

### Estimator Final Study Cost Estimate Deliverables

The Cost Estimate shall be developed using the Uniformat II Elemental Classification to as much detail as the preliminary drawings and specifications permit. Designers and Estimators are referred to ASTM Document E1557-97 (NISTIR 6389) for a detailed description of Uniformat II elements and components.

The Cost Estimate shall include:

- Cost Estimates for all work of the design scheme to elements at Level 3 of Uniformat II Classification, Sections A through G inclusive. The total for each element shall be built up from individual cost items as prepared by the Estimator. Each cost item shall be self sufficient in description and quantities; no direct reference to the drawings should be used to understand the pricing applied. Any detailed unit rate or custom item cost build-up shall be provided as backup.

- Cost Estimates for General Conditions of Contract, Contractor’s Overhead and Profit, Insurances, Bonds and all other items included in the Bid Documentation Package.

- Estimating Contingency and Escalation Contingency per Section 5.1.3.

- Gross Floor Areas and Net Floor Areas for the design scheme measured in accordance with DCAM’s ASTM pro forma.

- Unit Rates for Cost Elements derived from the itemized estimate for the GFA and NFA values.

- Unit User Cost as designated by the DCAM Project Manager.

### Estimate Date and Shelf-Life

The Estimate shall be current at the date of Document Submission, and include amounts (based on percentage adjustment) for Estimating Contingency and Escalation per Section 5.1.

### Space Measurement

At the conclusion of the Study Phase, all program and non-program building areas are to be accurately measured and summed correctly to the building GFA. For support and non-program areas, grossing factors or percentages may be defined if the design is not sufficiently developed to allow proper area measurement. Specific building performance measures may also be required as directed by the DCAM Project Manager.

Where the final Study submission includes a Preferred Solution of a specific building footprint and envelope, use of a single grossing factor based on program area is not sufficient. The non-program areas defined by DCAM must be estimated separately using percentages or direct area measurements.

For a list of typical DCAM elements derived from ASTM 1836-98, see Section 3, Space Estimates. The Designer will liaise with the DCAM Program manager to establish the grouping of program areas that make up the total project program.

Use of grossing factors or percentages for any of the specified ASTM elements is not acceptable.

Specific building performance measures may also be required as directed by the DCAM Project Manager. For ASTM elements and sample DCAM input sheets, see Section 8.3, Space Measurement.

### Estimator Participation

The Estimator will be involved in the preparation of Preliminary Estimates per Section 4.2.1 and Final Study Cost Estimates per Section 4.2.2. During the Study Phase, the Cost Estimator in the Study Consultant’s team is expected to participate in at least the following activities:

| Activity |  | Cost Estimator Participation |
| --- | --- | --- |
| 1 | Attendance at the “B” Conference Kick Off | Understand user agency quality needs, the site and existing building conditions; scope of the project; and provide concept level cost information during the conference. |
| 2 | Preliminary high-cost planning comparable data, order of magnitude estimates, existing conditions survey and scope development. | Develop and support cost modeling for Designer to allow high-level comparisons between alternative building footprints, story structure, layouts, site locations and major construction systems. |
| 3 | Attendance at Progress and Global Workshops to advise on cost matters for each proposed scheme until the preferred scheme is selected. | Provide cost modeling as above to allow cost comparison between alternative schemes, and to provide costing for requirements established during workshops. |
| 4 | Assisting the Designer to develop the preferred scheme layout and specification | Provide cost measurement for all the building elements and components of the Preferred Scheme. This includes consideration of site related costs, life-cycle alternative costs, and any other external factors affecting total project cost. Substantiate any earlier cost assumptions. |
| 5 | Submittal Preparation | Formally prepare in Uniformat II format the estimate breakdown in detail for the preferred scheme, as specified for both printed and electronic submittals. |
| 6 | Certification Package | Revise and update the Estimate in the presentation format needed for the Certification Package. |

### MEP Estimates and Allowances

Specific square foot rates or lump sum allowances are expected for major mechanical services as shown:

| Mechanical and Electrical Services |  | Uniformat II Level 3 |  | Pricing Measure |
| --- | --- | --- | --- | --- |
| D10 | Conveying | D1010 | Elevators and Lifts | LS as applicable |
|  |  | D1020 | Escalators | LS as applicable |
|  |  | D1030 | Other Conveying systems | LS as applicable |
| D20 | Plumbing | D2010 | Plumbing Fixtures | LS or include with D2020 SF rate |
|  |  | D2020 | Domestic Water Distribution | SF rate |
|  |  | D2030 | Sanitary Waste | SF rate or include with D2020 SF rate |
|  |  | D2040 | Rain Water Drainage | SF rate or LS |
|  |  | D2090 | Other Plumbing Systems | LS as applicable |
| D30 | HVAC | D3010-D3030 | Energy Supply and Generating Systems | LS or included in D3040-D3050 |
|  |  | D3040-D3050 | Distribution Systems, Terminal and Package Units | SF rate |
|  |  | D3060- | Controls, Instrumentation and | Included in D3040- |
|  |  | D3070 | Systems Testing | D3050 SF rate |
|  |  | D3090 | Other HVAC systems | LS allowance for venting or other |
| D40 | Fire Protection | D4010 | Sprinklers | SF rate |
|  |  | D4020 | Standpipes | LS or include with D4010 SF rate |
|  |  | D4030-D4090 | Fire Protection Specialties and other Fire Protection Systems | LS as applicable |
| D50 | Electrical | D5010 | Electrical Service and Distribution | SF rate |
|  |  | D5020 | Lighting and Branch Wiring | SF rate |
|  |  | D5030 | Communications & Security | SF rate |
|  |  | D5040 | Other Electrical Systems | LS as applicable |

## Schematic Design Cost Estimate

### Preliminary Schematic Cost Planning

For some projects the Designer may need to develop further alternative designs beyond the preferred solution accepted for Study Certification. An evaluation and selection process is again used to choose the most suitable design option.

For Design options developed in this manner during the Schematic Phase, high-level estimates are prepared in the same framework as for the Study Phase.

Often during the Schematic Phase, budget issues subsequent to the original Study—particularly due to the escalation impact—cause the need for a scheme redesign. The Designer has to redesign to stay within a specific nominated budget. Close attention must be paid to providing timely and comparable data to support cost modeling.

For directives on the content and level of detail for estimates and the participation expected from the Cost Estimators, see Section 4.2.1.

### Estimator Deliverables

The Cost Estimate shall be developed using the Uniformat II Elemental Classification to as much detail as the schematic drawings and specifications permit. Designers and Estimators are referred to ASTM Document E1557-97 (NISTIR 6389) for a detailed description of Uniformat II elements and components.

### Cost Estimate Inclusions

The following components and sections shall e included in the Cost Estimate submission:

- Estimates for all building work of the design scheme to at least Level 2 of Uniformat II Classification, Sections A through G inclusive, complete with a single line outline specification description for each item. The detailed unit rate or item cost buildup shall be provided as backup in each case

- Estimates for General Conditions of Contract, Contractor’s Overhead and Profit, Insurances, Bonds and all other items included in the Bid Documentation Package

- GFA and NFA measurements for the design scheme measured in accordance with DCAM’s ASTM pro forma

- Unit Rates for Cost Elements shall be derived for the GFA and NFA values

- Unit User Cost as designated by the DCAM Project Manager

- Reconciliation with the Gross Floor Area and Net Floor Areas determined at the Study Phase, including explanation of significant variances

- Reconciliation with the Uniformat II Cost Estimate done at Study Phase, including explanation of any significant variances, including Unit User Cost

### Estimate Date and Shelf-Life

The Estimate shall be current at the date of Document Submission, and include amounts (based on percentage adjustment) for Estimating Contingency and Escalation Contingency per Section 5.1.

For updating estimates for submission after specific time periods, see Section 6.2, Estimate Shelf Life for DCAM requirements.

### Space Measurement

At the conclusion of this phase, all program and non-program building areas are to be accurately measured and summed to match the building GFA.

- The Designer will liaise with the DCAM Project Manager to establish the grouping of program areas that make up the total project program.

- For support and non-program areas, if the design is not sufficiently developed to allow actual area measurement, grossing factors may be defined and allocated to functions.

- For a list of typical DCAM elements derived from ASTM 1836-98, see Section 3, Space Estimates.

- Specific building performance measures may also be required as directed by the DCAM Project Manager.

### Estimator Processes

| Activity |  | Cost Estimator Participation |
| --- | --- | --- |
| 1 | Design Iterations following Study Review and the Global Workshop | Develop and support Cost Modeling for the Designer to allow cost comparisons between alternative building footprints, story structure, layouts, site locations and major construction systems. |
| 2 | Attendance at regular Progress Workshop meetings to advise on cost matters for each proposed scheme, until the Preferred scheme is selected | Provide Cost Support for the Designer as above to allow cost comparison between alternative detail schemes and costing for requirements established from Workshops. |
| 3 | Assisting the Designer develop the Design layout and specifications | Develop Cost Measurement for all building elements and components of the Design. This includes consideration of site related costs, life cycle alternative costs, and any other external factors affecting total project cost. Substantiate any earlier cost assumptions at this time. |
| 4 | Submittal Preparation at 60% completion and at final submission | Document in Uniformat II format, the estimate breakdown in detail as specified in both printed and electronic submittals. Integrate costs from other specialist Consultants. Provide appropriate contingencies. |

## Design Development Cost Estimate

### Estimator Deliverables

The Cost Estimate shall be developed using the Uniformat II Elemental Classification to Level 3 as the drawings and specifications are developed. Designers and Estimators are referred to ASTM Document E1557-97 (NISTIR 6389) for a detailed description of Uniformat II elements and components.

### Cost Estimate Inclusions

- Cost Estimates for all work of the design scheme to Level 3 of Uniformat II Classification, Sections A through G inclusive, complete with a single line outline specification description for each item. The detailed unit rate or item cost buildup, shall be provided as backup in each case

- The same estimate shall also be prepared in are CSI MasterFormat 2004™ format, with particular attention to the estimates for each of the Trade Bid packages under MGL 149

- Cost Estimates for General Conditions of Contract, Contractor’s Overhead and Profit, Insurances, Bonds and all other items included in the Bid Documentation Package

- GFAs and NFAs for the design scheme measured in accordance with DCAM’s ASTM pro forma

- Unit Rates for Cost Elements shall be derived for the GFA and NFA values

- Unit User Cost as designated by the DCAM Project Manager

- Reconciliation with the Uniformat II Cost Estimate done at Schematic Phase, including an explanation of any significant variances

### Estimate Date and Shelf-Life

The Estimate shall be current at the date of Document Submission, and include amounts (based on percentage adjustment) for Estimating Contingency and Escalation Contingency per Section 5.1.

For DCAM requirements on updating estimates for submission after specific time periods, see Section 6.2, Estimate Shelf Life.

### Space Measurement

At the conclusion of this phase, all program and non-program building areas are to be accurately measured and correctly summed to match the building GFA. Use of grossing factors or percentage loadings for any of the specified ASTM elements is not acceptable.

For the list of typical DCAM elements derived from ASTM E1836-98, see Section 3, Space Estimates.

Specific building performance measures may also be required as directed by the DCAM Project Manager.

### Cost Estimator Participation

During the entire Design Development Phase, cost verification and, if necessary, Value Engineering will be required to ensure that the design as developed remain within the Project Budget. The Cost Estimator in the Designer’s team is expected to participate in at least the following activities:

| Activity |  | Cost Estimator Participation |
| --- | --- | --- |
| 1 | Attendance at regular Design Workshop meetings to advise on cost matters for each element or section of work | Provide cost data and advice to the Designer and other Consultants for an accurate indication of the cost of each designed element and major specification item. |
| 2 | Attendance at Design Workshop meetings to advise on cost matters for LEED and Life Cycle costs | Provide cost data and advice related to Life Cycle cost analysis, LEED evaluation, and specialist costs. |
| 3 | Assisting the Designer achieve the required cost budget within design and specification requirements, including scheduling needs | Provide Value Engineering of specific elements within the total estimate budget for construction and all specialist Consultants, and the impact of the detailed construction work schedule on the total cost picture. |
| 4 | Estimate Review in accordance with Appendix 3A and Final Submittal Preparation | Formally document in Uniformat II and CSI MasterFormat 2004™ the complete estimate breakdown in detail as specified for both printed and electronic submittals. Integrate costs from other specialist Consultants. Provide allowances where appropriate, including Escalation in accordance with Section 6. |

## Construction Document Cost Estimate

### Estimator Deliverables

As the final drawings and specifications are developed the Cost Estimate shall use the Uniformat II Elemental Classification to Level 3 and provide it for review at 60% completion of Construction Documents. Designers and Estimators are referred to ASTM Document E1557-97 (NISTIR 6389) for a detailed description of Uniformat II elements and components.

A second and final Cost Estimate shall be prepared at 100% Drawing Complete as part of the final Bid Document submission. This estimate shall be in both Uniformat II Elemental Classification, and in CSI Masterformat, cross referenced to the Uniformat II. Both estimates shall be of the same total and percentage allowances for OH&P, and any further allowances for escalation or other contingencies.

For final submission the estimator shall complete Summary Estimate DCAM Form “Appendix K” of the “C11 Bid Package,” which includes the filed sub-bids breakdown sheet. For the format of “Appendix K,” see Appendix A5.

### Cost Estimates Inclusions

- Cost Estimates for all work of the design scheme to Level 3 of Uniformat II Classification, Sections A through G inclusive, complete with a single line outline specification description for each item. The detailed unit rate or item cost buildup shall be provided as backup in each case.

- Cost Estimates for General Conditions of Contract, Contractor’s Overhead and Profit, Insurances, Bonds and all other items included in the Bid Documentation Package.

- The same estimated costs and sum totaled structured in CSI MasterFormat 2004™, including the value of work of each of the filed sub-bid trades listed under MGL 149.

- GFA and NFA measurement for the design scheme, in accordance with DCAM’s ASTM pro forma.

- Unit Rates shall be derived for the GFA and NFA values for both Uniformat II and Masterformat CSI formats.

- Reconciliation with the Gross Floor Area and Net Floor Areas determined at the Design Development Phase, including explanation of significant variances.

- Reconciliation with the Uniformat II Cost Estimate done at Design Development Phase, including explanation of any significant variances.

### Estimate Date and Shelf-Life

The Final Estimate shall be current at the date of Document Submission, and include amounts (based on percentage adjustment) for Escalation Contingency per Section 5.1.

For updating estimates for submission after specific time periods, see Section 6.2, Estimate Shelf Life for DCAM requirements.

### Space Measurement

At the conclusion of this phase, all program and non-program areas are to be accurately measured and summed correctly to match the building GFA. Any differences with areas derived at Design Development Phase are to be reconciled.

For the list of typical DCAM elements derived from ASTM E1836-98, see Section 3, Space Estimates.

### Cost Estimator Participation

During the entire Construction Documentation Phase, cost verification and if necessary Value Engineering will be required to ensure that the design as developed remain within the Project Budget. The Cost Estimator in the Designer’s team is expected to participate in at least the following activities:

| Activity |  | Cost Estimator Participation |
| --- | --- | --- |
| 1 | Attendance at regular Design Workshop meetings to advise on cost matters for each element or section of work | Cost data and advice to the Designer and other Consultants to provide an accurate indication of the cost of each designed element and major specification item. |
| 2 | Attendance at Design Workshop meetings to advise on cost matters for LEED and Life Cycle costs | Cost data and advice related to Life Cycle cost analysis, LEED evaluation, and specialist costs |
| 3 | Assisting the Designer achieve the required cost budget within design and specification requirements, including scheduling needs | Value Engineering of specific elements within the total estimate budget for construction and all specialist Consultants, and the impact of the detailed construction work schedule on the total cost picture. |
| 4 | Estimate Review in accordance with Appendix 3A and Final Submittal Preparation | Formally document in CSI MasterFormat 2004™ the complete estimate breakdown in detail for both printed and electronic submittals. Integrate all costs from other specialist Consultants and external works to be included in the contract. The final estimate is to be prepared also in Uniformat II format as previously detailed. |
| 5 | Bid Reconciliation | Provide Cost Estimate support to the Designer as required by DCAM in his evaluation of the Bid. |

5

## Basis for Pricing

Inclusions/Exclusions

Each estimate should reflect the fair construction value for the construction of the project and should not be a prediction of low bid. DCAM’s target for the estimate is the second to lowest bid if three or more bids are received. The following must be considered:

- Pricing assumes a procurement process with competitive bidding for every portion of the construction work, and assumes a minimum of three bids, including each filed sub-bidder.

- The basis of procurement should be noted. This may be competitive bidding under MGL Ch. 149, or using CM/GMP procurement. Any general markups or allowances for the procurement type should be identified.

- Subcontractor’s markups should be included in each line item unit price. Markups cover the cost of field overhead, home office overhead and Subcontractor’s profit.

- General Contractor’s general conditions cost may be calculated on a monthly basis or a percentage at early design phases. The basis for this cost should be noted. General Contractor’s overhead and fees should be based on a percentage of the total direct (trade) costs plus general conditions. The Contractor’s permits, bond and insurances may be included or noted separately.

- Unless identified specifically, the cost of such items as shift premiums, and allowances for temporary occupancy permits, police details or street/sidewalk permits are deemed to be included in item rates.

- The Estimating Contingency should be identified (a percentage to cover cost increases that will occur during design elaboration or unforeseen design issues). As the design develops, the estimating contingency is to be reduced, and is eliminated at the final Construction Document estimate.

- Construction Contingencies should be excluded in the estimate.

### Additional Items and Allowances

Detailed estimates are expected for site-specific items that are not included in the standardized overall construction rate. A typical list is below:

      - Site works including general preparation, landscaping, profile restoration, required services

      - Cost allowance for site slope or access which will add extra to standard SF rates

      - Parking area costs calculated at per-space costs, plus allowance for access control

      - Roadway modifications required by local authorities

      - Demolition of existing buildings and site cleaning for construction

      - Wetland provisions or restitution costs

      - Allowance for compliance with Massachusetts Historical Society requirements or time impact

      - Diversion of services around the proposed footprint

      - Provision of additional services to the new buildings, including work done by utility companies.

      - Legal or acquisition cost premium for the chosen site

      - Need for temporary accommodation, additional time, etc. for the chosen site.

### Included General Conditions and Markups

Percentage based or calculated allowances are expected for the General Contractor’s additions to the work items described in the Uniformat II system. These are to be taken in accordance with normal industry standards and added to the subtotal of all work described with Uniformat II items, shown on a line by line increment as follows:

      - General Conditions of the Contract

      - Fees and Permits

      - General Contractor’s Overhead and Profit

A subtotal is expected at this stage to give the current value of the project’s ECC.

### Contingency Allowances Inclusions

Percentage based or calculated allowances are expected on a line-by-line basis as below, to provide the total ECC estimated to the mid-point of the projected construction period.

      - Estimating Contingency

An allowance is a percentage of the total ECC for the detailed development of the design to CD level, including all details and specifications not complete at the time of estimate. This contingency specifically excludes changes due to design scope changes.

      - Phasing and Temporary Work

An allowance is a percentage or calculated additional cost for the execution of the project in particulars outside of a standard, fully available site to the Contractor. This will include additional costs for split phases, provision of temporary works outside those reasonably expected to build the works, provision of services to relocate and return the building users, provision of temporary accommodation for the users, and the provision of additional supervision or security to work in an occupied environment.

      - Escalation Contingency

An allowance is a compounded percentage to bring all estimated costs to the projected mid-point of the construction project. The percentage used is expected to be derived from current industry publications and recent estimates, and does not rely on extrapolation of previously published annual figures. The projected project design and construction time must be estimated for this purpose.

The total project ECC is to be summed to include these line items.

## Specific Inclusions and Exclusions

    - Items Not Included in a Typical Estimate

      - Land acquisition, feasibility, and financing costs

      - All professional fees and insurance

      - Site or existing conditions surveys investigations costs, including determining subsoil conditions

      - Items identified in the design as Not In Contract (NIC)

      - Owner supplied and/or installed items (e.g., draperies, furniture and equipment)

      - Tel/data, security and AV networks, equipment or software (unless identified otherwise)

      - Rock Excavation; special foundations (unless indicated by design engineers)

      - Hazardous materials investigations and abatement

      - Utility company back charges, including work required off-site

      - Work to City streets and sidewalks (except as noted in this estimate)

      - Construction or occupancy phasing or off hours’ work (except as noted in this estimate)

      - Owners Construction Contingency for scope changes

### Items that May Affect Typical Estimates

      - Modifications to the scope of work subsequent to the preparation of this estimate

      - Unforeseen subsurface conditions

      - Special requirements for site access, off-hour work or phasing activities

      - Restrictive technical specifications, excessive contract or non-competitive bid conditions

      - Sole source specifications for materials or products

      - Bid approvals delayed beyond the anticipated project schedule

### Job Overhead Activities (Structuring Estimates Insert)

Job overhead costs are those costs at the project site that occur specifically as a result of a particular project. Some examples of job overhead costs are:

- Job supervision and office personnel

- Engineering and shop drawings

- Site security

- Temporary facilities, project office

- Temporary utilities

- Preparatory work and laboratory testing

- Transportation vehicles

- Supplies and maintenance facilities

- Temporary protections and OSHA requirements

- Telephone and communications

- Permits and licenses

- Insurance (project coverage)

- Schedules & reports

- Quality control

- Cleanup

- Taxes

- Equipment costs not chargeable to a specific task

6

## Escalation Provisions and Calculations

### Escalation Indices

Escalation

Estimators are expected to be familiar with the major industry escalation indices, such as the following:

      - R.S. Means

      - BSI

      - Engineering News Review

### Industry Trends and Projected Escalation Rates

Estimators are expected to be current with industry trends and projected escalation rates. They may use data from both publications and their own expertise and experience to derive an appropriate escalation contingency percentage to reach midpoint of project construction.

### Explaining the Escalation Contingency

A brief explanation of the derivation of the escalation contingency is expected. Short-term or abnormal market pressures should be noted.

## Estimate Shelf Life

Due to current levels of market volatility, DCAM will require that all submitted Estimates will need to be reviewed as follows, when the date of submission is not concurrent with the date of estimate preparation:

| Project ECC | Under $5M | $5M or over |
| --- | --- | --- |
| Under 3 months | Apply Escalation percentage (if any) | Apply Escalation percentage (if any) |
| 3 – 6 months | Apply Escalation percentage | Apply Escalation percentage |
| Over 6 months | Apply Escalation percentage | Rate review of all items |
| Over 12 months | Rate and Peer Review of whole estimate | Independent Estimate and reconciliation with original |

## DCAM Escalation Index Table

DCAM has developed a provisional level table with averaged escalation factors as a starting point for initial estimates and analysis of earlier benchmark projects. This table is provided for this purpose, and Estimators are expected to provide and justify future projections for their submitted estimates.

(The escalation table below was effective as of June 2005, and is used solely as an example. Estimators will need to verify current rates for each new project.)

| % Change | Year 2000 |  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.02 | 2000 | 1.00 | 1.02 | 1.04 | 1.06 | 1.17 | 1.25 | 1.31 | 1.38 |
| 1.02 | 2001 |  | 1.00 | 1.02 | 1.04 | 1.14 | 1.22 | 1.29 | 1.35 |
| 1.02 | 2002 |  |  | 1.00 | 1.02 | 1.12 | 1.20 | 1.26 | 1.32 |
| 1.02 | 2003 |  |  |  | 1.00 | 1.10 | 1.18 | 1.24 | 1.30 |
| 1.10 | 2004 |  |  |  |  | 1.00 | 1.07 | 1.12 | 1.18 |
| 1.07 | 2005 |  |  |  |  |  | 1.00 | 1.05 | 1.10 |
| 1.05 | 2006 |  |  |  |  |  |  | 1.00 | 1.05 |
| 1.05 | 2007 |  |  |  |  |  |  |  | 1.00 |

| 7 | Special Estimates |
| --- | --- |
| 7.1 | RFPs |
|  | Reserved |
| 7.2 | Peer Review |
|  | Reserved |
| 7.3 | Change Orders |
|  | Reserved |
| 7.4 | ADA/MAAB Work |
|  | Reserved |

8

## DCAM Uniformat II Elemental Entry

Electronic Formats

ELEMENTAL COST ITEM ENTRY

Project Number: Project Phase: Estimator Initials: Estimating Contract Id: Estimate Date:

Level 1 total

$0

$0

$0

$0

Level 2 total

Level 3 total Database Entry

INSTRUCTIONS TO ESTIMATOR

    - This spreadsheet is to enter elemental cost information for DCAM projects using Uniformat II structure and standard elements.

    - Cost data may be entered at Levels 1, 2 or 3 according to Project Phase and Estimating Contract requirements.

    - Cost data at any level may be entered as a lump sum per element or entered as a elemental quantity and unit rate. Entry of (quantity x rate) takes precedence over a lump sum entry. Zero out quantity or rate to enter a lump sum.

    - Cost data entry may be made at any level. However, entry at a lower level will always take precedence over entry at the next higher level. Therefore, relevant lower level elements must be cleared of values to input higher level data.

    - Each hierarchy and sub-hierarchy of elements is independent, so that data entry may be made at different elemental levels for different elemental groups. It is the Estimator's responsibility to ensure that the total of all elemental costs at each level matches through the whole project when the estimate is complete. The spreadsheet will automatically add each element hierarchy upwards to level 1. To balance the totals at each level, an “unassigned” element group is provided as group “U” which is to be used to balance the totals at each level. This is necessary if not all elemental groups have costs detailed down to level 3. A fully broken down cost table to level through for all groups will not need to use “U” values.

    - Each estimating contract will specify the level of estimate accuracy required and if qty x rate is required.

    - A field is provided for each element for comments or specifications, to be used for non-standard rates or costs.

    - Data may only be entered into yellow-framed fields, on the sheets for Level 1, Level 2 and Level 3, also this front sheet.

    - Not every element will be necessary for each project—leave unused elements blank and do not try to delete them.

    - Do not alter the formatting, row or column count, or add or delete columns in this spreadsheet.

    - Project number will be provided by DCAM as an integer number for the Cost Database. Leave blank if not assigned.

    - Data entry must be done using or loading the yellow cells only of the worksheet “Entry_all_levels.” The worksheet “Database” will show the totals that are formatted to load directly into DCAM’s database.

    - Entry of line items making up each Uniformat Level 3 element is not required.

## General Conditions

GENERAL CONDITIONS COST ITEM ENTRY

Project Number: Project Phase: Estimator Initials: Estimating Contract Id: Estimate Date:

Level 0 total

$0

$0

$0

Level 1 total

Level 1 total

$0

Database Entry

INSTRUCTIONS TO ESTIMATOR

    - This spreadsheet is to enter General Conditions cost information for DCAM projects using standard codes.

    - General data may be entered at Level 1 or 2 according to Project Phase and Estimating Contract requirements.

    - General cost data may be entered at Level 0 as one lump sum, at Level 1 as major divisions, or Level 2 as detailed.

    - General cost item entry at a lower level will always take precedence over entry at the next higher level. Therefore, hierarchical lower level items must be set to 0 to allow input of higher-level data.

    - Each hierarchy and sub-hierarchy of items is independent, so that data entry may be made at a different level for different groups. The Estimator is responsible for ensuring that the total of all general costs at each level matches through the whole project when the estimate is complete. The spreadsheet will automatically add each hierarchy upwards to level 0. To balance the totals at each level, an “unassigned” item group is provided as “90,” to be used to balance the totals at each level. This is necessary as not all item groups have costs detailed down to level 2 for each estimate. When the spreadsheet is correct, all values above in blue cells will be the same.

    - Each estimating contract will specify the level of estimate accuracy required for each phase.

    - A field is provided for each general item for explanatory comments (not available for this version).

    - Data may only be entered into yellow-framed fields, on the Master or Display sheet, and also identification information onto this Summary sheet.

    - Not every item will be necessary for each project - leave unused items blank and do not try to delete them.

    - Do not alter the formatting, row or column count, or add or delete columns in this spreadsheet. Resizing columns for convenience is acceptable.

    - Project number will be provided by DCAM as an integer number for the Cost Database. If not available, leave blank.

- Data entry must be done using or loading the yellow cells only of the worksheet “Display” or “Master.” The worksheet “Database” will show the totals, which are formatted to load directly into DCAM’s database.

- Entry of detail of unit buildup for each DCAM entry item is not required.

## Space Measurement

    - The template provides for entry of program areas, one sheet for each phase.

    - At Program and Design Development, non-program areas can be entered as percentages (using grossing factors) to cumulatively add to the total GFA.

    - At Design Development, it is expected that all building areas will be dimensioned and the entire space can be added as individual areas to sum to the GFA.

    - Data entry must be done using or loading the yellow cells only of the worksheet “Program”, “Schematic” or “DesignDevt.” The worksheet “Summary” and “Graphics_3” will show and display the totals.

    - (reserved)

| 9 |  | Appendix–Reference Documents List |
| --- | --- | --- |
| A | A1— A5 |  |
|  | ■ | UNIFORMAT II Estimates |
|  | ■ | General Conditions |
|  | ■ | Submissions |
|  | ■ | To be inserted |
|  | ■ | DCAM Estimate Summary Sheet |
| B | NIST Uniformat II, Level-3 Element |  |
| C | CSI Division Numbers and Titles |  |
| D | CSI Detailed Divisions |  |
| E | ASTM STANDARD E1557 UNIFORMAT II |  |
| F | ASTM–Measurement of Buildings |  |

# Appendix A1 – Checklist for UNIFORMAT II Estimates

#### CHECKLIST FOR PREPARING AN ESTIMATE	06.04.03

Project/Location:	 Date:

#### SUBSTRUCTURE

A10 Foundations

A1010 Standard Foundations

Reinforced Concrete	 Masonry	 Other

Soil Conditions	 Bearing cap.	 Frost Depth

Grade Wall Type:	 Concrete	 Masonry A1020 Special Foundations

Unusual Subsurface Conditions

Piling:  Concrete	 Steel		 Caissons	 Mat	 Other	 Depth of Piling:		ft

A1030 Slab on Grade

Structural	 Non-Structural Thickness		in

A20 Basement Construction

A2010 Basement Excavation

Water Problems		 Depth	 ft

A2020 Basement Walls

Reinforced Concrete	 Brick	 Other

Waterproofing	 Damp proofing

#### SHELL

B10 Superstructure

B1010 Floor Construction

B1020 Roof Construction

Type:	 Cast-in-place	 Pre-Cast Concrete		 Steel	 Composite Wood	 Other

Load Bearing Walls	 Other

| Fireproofing: | Columns | Beams | Other |
| --- | --- | --- | --- |
| Stairs: | Metal | Concrete | Special |

Liveload: Floor	lbs/sf Roof	lbs/sf Typical Bay Size			Other

B20 Exterior Enclosure

B2010 Exterior Walls

Brick	 Concrete Block	 Cast-in-place Concrete	 Pre-Cast Concrete

Stone	 Metal Panels	 Wood Siding	 Other B2020 Exterior Windows

Windows	 Curtain Wall: Type

| Frames: | Aluminum | Wood | Plastic | Steel |
| --- | --- | --- | --- | --- |
| Glazing: | Sheet | Float/plate | Solar | Other |
| Single | Double | Clear | Reflective |  |
| B2030 Exterior Doors |  |  |  |  |
| Wood | Metal | Glass |  |  |
| Special Entrance |  | Single (%) |  |  |

Vestibule (%) 		Revolving (%)

Overhead (%)

B30 Roofing

B3010 Roof Coverings

Built-up	 Fluid Applied	 Elastic Sheet	 Composite Shingles

Sheet Metal	 Other

Color:	  Light	 Dark B3020 Roof Openings

Skylights	 Access Hatches

B3090 Other Roofing

Type:	FIat	Pitched

Insulation:	Rigid	Lightweight

Thickness	"U" Factor	 Other

#### INTERIORS

C10 Interior Construction

C1010 Partitions

Masonry (%) 	Stud (%)	Glazed (%)

Demountable (%)	Folding/sliding (%)	Other

Toilet Partitions: Type

C1020 Interior Doors

Door Frames:	 Wood	Metal

Doors:  Wood (%)		Metal (%)		  Glass (%)	 Other (%)

C1030 Fittings

Hardware:	 Brass	 Chrome	 Other	 Washroom Accessories: Type		 	Other

C20 Stairs

C2010 Stair Construction C2020 Stair Finishes

C30 Interior Finishes

C3010 Wall Finishes

Walls: Plaster (%)	Drywall (%)	Tile (%)

Paint (%)	Wall Covering (%)	Spec. Ctgs. (%)

Other (%)

C3020 Floor Finishes

Floors: Resilient (%)	Carpet (%)	Tile & Terr.(%)

Concrete Finish (%)	Wood (%)	Raised Fir(%)

Other (%)

C3030 Ceiling Finishes

Ceilings: Suspended (%)	Applied (%)	Unfinished (%)

Plaster (%)	Drywall (%)	Integrated (%)

Acoustical: Unrated (%)	Rated (%)	Other

#### SERVICES

D10 Conveying

D 1010 Elevators & Lifts

Elevators:		Type	 No.	 Speed/Cap	 LO/ea.	 Type	No.	Speed/Cap	LO/ea.

Elevators:	 No.	Width	Cap	 Lifts:	Type	 No.	 Other

D1020 Escalators & Moving Walks D1090 Other Conveying Systems

D20 Plumbing

D2010 Plumbing Fixtures

Fixtures: Standard: No.	Special No.

D2020 Domestic Water Distribution

Domestic Hot Water Heaters: Type	Capacity

D2030 Sanitary Waste D2040 Rain Water Drainage

Roof Drains: Drains per roof	sf   Interior	 Exterior

D2090 Other Plumbing Systems

Drinking Fountains	No.

D30 HVAC

D3010 Energy Supply

Energy Recovery	Controls	No. of Zones

D3020 Heat Generating Systems

Heating Capacity	mbh	Type

D3030 Cooling Generating Systems

Ventilation Req's	cfm Air Conditioning	(%) Cooling Capacity	 tons Type		  Cooling Tower: Type		 Location

D3040 Distribution Systems

Air Distribution	cfm  Type

D3050 Terminal & Package Systems D3060 Controls & Instrumentation D3070 Systems Testing & Balancing

D3090 Other HVAC Systems & Equipment

Equipment Load	w/sf	People Load

D40 Fire Protection

D4010 Sprinklers

Hazard Type: Light	(%) Ordinary	(%)	Extra	(%) Type

D4020 Standpipes

Extinguishers	 Special

D4030 Fire Protection Services D4090 Other Fire Protection Systems

Water Storage: Capacity	gals Location

D50 Electrical

D5010 Electrical Service and Distribution

KVA Demand 				 Primary Voltage	  Connected watts/sf			 amps	  Transformers: Utility		 Owners	 Voltage: Main distribution	V Secondary Distribution

Bus duct    Motor Control Center

D5020 Lighting & Branch Wiring

Under floor duct	 Raised Floor	 Raceway	 Undercarpet

Intensity (in fc) 		Watts/sf for Lighting

Receptacles	 HVAC

Elevators	 Spare	 Connected Motor hp

| Type: | Fluorescent | Incandescent | HPS |  |
| --- | --- | --- | --- | --- |
|  | Metal Halide | Mercury Vapor |  | Other |

D5030 Communications & Security

PA/Sound	 TV  Telephone	 Lighting Security

D5040 Specials Mechanical Systems

Special Piping: Type	 Special Systems: Dust & Fume Collection			 Other: Type/Quantity

D5090 Other Electrical Systems

Electric Heating	Fire alarm	Clock

#### EQUIPMENT & FURNITURE

E10 Equipment

E1010 Commercial Equipment E1020 Institutional Equipment

E20 Furnishings

E2010 Fixed Furnishings

Loading Dock: Equipment	 Other

E2020 Movable Furnishings

Artwork: Type

E2090 Other Furnishings

Window Treatment: Type/size	 Seating: Type

#### SPECIAL CONSTRUCTION & DEMOLITION

F10 Special Construction F1010 Special Structures F1020 Integrated Construction

F1030 Special Construction Systems

Vaults: Type/Size:	  Other

F1040 Special Facilities

F1050 Special Controls and Administration

| F20 Selective Building Demolition |  |
| --- | --- |
| F2010 Building Elements Demolition |  |
| F2020 Hazardous Components Abatement |  |
| G BUILDING SITE |  |
| G1010 Site Preparation |  |
| G1010 Site Clearing |  |
| Borrow (quantity) | Dispose (quantity) |
| G1020 Site Demolition |  |
| Demolition Amount | Clearing Amount |
| G1030 Site Earthwork |  |
| Retaining Walls (length) ) | Paved/Plaza Area (size) |
| G1040 Hazardous Waste Remediation |  |
| G20 Site Improvements |  |
| G2010 Roadways |  |
| Roads: Size/Type | Fences: Length |

| Cost Estimating Manual | OPDC |
| --- | --- |
| G2020 Parking Lots |  |
| Parking Lots: Size/Type | No. Cars |
| G2030 Pedestrian Paving |  |
| G2040 Site Development |  |
| G2050 Landscaping |  |
| Landscaping: Seeding Area | Ground Cover: Area |
| Trees: Number | Planters: Number |
| Other |  |
| G30 Site Mechanical Utilities |  |
| G3010 Water Supply |  |

Water: Size/Length	Irrigation: Size/Type	 G3020 Sanitary Sewer

Sanitary Sewer: Size/Type	 Process & acid waste system: Size/Type

Combined Drainage & Sewer System: Size/Length

G3030 Storm Sewer

Storm drainage: Size/Type

G3040 Heating Distribution

Heating System: Size/Type

G3050 Cooling Distribution G3060 Fuel Distribution

Natural Gas: Size/length	Other Gas System	 G3090 Other Site Mechanical Utilities

G40 Site Electrical Utilities

G4010 Electrical Distribution

Overhead Power: Size/Type	 Underground Power: Size/type

G4020 Site Lighting

Exterior Lighting: Type/Area

G4030 Site Communications & Security

Snow melting system: Size/Type

G4090 Other Site Electrical Utilities

Snow melting system: Size/Type

G90 Other Site Construction

G1090 Service and Pedestrian Tunnels G9090 Other Site Systems & Equipment

# Appendix A2 – Checklist for General Conditions

| General Item | Level | Description | √ |
| --- | --- | --- | --- |
| 00 | 0 | Entire General Items summed |  |
| 01 | 1 | Bonds payable |  |
| 0101 | 2 | Bonds payable |  |
| 02 | 1 | Fees payable |  |
| 0201 | 2 | Fees payable |  |
| 03 | 1 | Allowances |  |
| 0301 | 2 | City/Town Remediation |  |
| 0302 | 2 | Value Engineering Upgrades |  |
| 0303 | 2 | Base Building Signage |  |
| 0304 | 2 | Tenant Signage |  |
| 0305 | 2 | Furniture |  |
| 0306 | 2 | Dedicated Circuits (UPS, etc.) |  |
| 0307 | 2 | Security System |  |
| 0308 | 2 | Telecommunications |  |
| 0309 | 2 | Other |  |
| 04 | 1 | Coordination (Proj Mgt) |  |
| 0401 | 2 | Project Managers |  |
| 0402 | 2 | Expeditor |  |
| 0403 | 2 | EEO Coordinator |  |
| 0404 | 2 | Construction Executives |  |
| 0405 | 2 | General Superintendent |  |
| 0406 | 2 | Superintendent |  |
| 0407 | 2 | Assistant Superintendent |  |
| 0408 | 2 | MEP Coordinator |  |
| 0409 | 2 | Clerical |  |
| 0410 | 2 | Safety Officer |  |
| 0411 | 2 | Miscellaneous Laborer |  |
| 0412 | 2 | Accountant |  |
| 0413 | 2 | Legal |  |
| 0414 | 2 | Payroll Taxes, Benefits, Ins. |  |
| 0415 | 2 | Pre-construction Services |  |
| 0416 | 2 | Mobilization/Demobilization |  |
| 0417 | 2 | Other Coordination |  |
| 05 | 1 | Cutting and Patching |  |
| 0501 | 2 | General Cutting and Patching |  |
| 06 | 1 | Scheduling |  |
| 0601 | 2 | Schedule of Values |  |
| 0602 | 2 | CPM Scheduling |  |
| 0603 | 2 | Progress Reports |  |

| General Item | Level | Description | √ |
| --- | --- | --- | --- |
| 0604 | 2 | Estimating |  |
| 0605 | 2 | Other Scheduling |  |
| 07 | 1 | Submittals |  |
| 0701 | 2 | Shop Dwgs, Prod. Data, Samples |  |
| 0702 | 2 | Printing and Mailing Service |  |
| 0703 | 2 | Other Submittals |  |
| 08 | 1 | Construction Photos |  |
| 0801 | 2 | Ground Level Photographs |  |
| 0802 | 2 | Aerial Photographs |  |
| 0803 | 2 | Other Photographs |  |
| 09 | 1 | Quality Control |  |
| 0901 | 2 | Field Engineering |  |
| 0902 | 2 | Engineering Supplies |  |
| 0903 | 2 | Other Engineering |  |
| 10 | 1 | Field Inspection, Testing |  |
| 1001 | 2 | Certified Testing Services |  |
| 1002 | 2 | LSP |  |
| 1003 | 2 | Other Testing |  |
| 11 | 1 | Temporary Facilities, Utl |  |
| 1101 | 2 | Temporary Electric |  |
| 1102 | 2 | Winter Conditions, Temp. Heat |  |
| 1103 | 2 | Temporary Telephone |  |
| 1104 | 2 | Temporary Water |  |
| 1105 | 2 | Temporary Toilets |  |
| 1106 | 2 | Temporary Sewer |  |
| 1107 | 2 | Protection and Safety |  |
| 1108 | 2 | Rubbish Chute |  |
| 1109 | 2 | Dumpsters |  |
| 1110 | 2 | Temporary Enclosures |  |
| 1111 | 2 | Stairs, Ladders, Ramps etc. |  |
| 1112 | 2 | Temporary Fence and Barricades |  |
| 1113 | 2 | Snow Removal |  |
| 1114 | 2 | Water Control |  |
| 1115 | 2 | Project Identification |  |
| 1116 | 2 | Staging |  |
| 1117 | 2 | Field Offices – GC |  |
| 1118 | 2 | Office Equipment – GC |  |
| 1119 | 2 | Field Office – DCAM |  |
| 1120 | 2 | Office Equipment – DCAM |  |
| 1121 | 2 | Vehicles and Parking |  |
| 1122 | 2 | Emergencies |  |
| 1123 | 2 | Dust Mitigation |  |
| 1124 | 2 | Noise Control |  |

| General Item | Level | Description | √ |
| --- | --- | --- | --- |
| 1125 | 2 | Pollution Control |  |
| 1126 | 2 | Cleaning During Construction |  |
| 1127 | 2 | Security Guard Service |  |
| 1128 | 2 | Police Services |  |
| 1129 | 2 | Electric Company Backcharge |  |
| 1130 | 2 | Gas Company Backcharge |  |
| 1131 | 2 | Other Temporary Services |  |
| 12 | 1 | Material, Products, Equipment |  |
| 1201 | 2 | Material, Products Equipment |  |
| 13 | 1 | Project Closeout |  |
| 1301 | 2 | Final Cleaning |  |
| 1302 | 2 | Glass |  |
| 1303 | 2 | Record & As-Built Drawings |  |
| 1304 | 2 | Operations & Mainten. Manuals |  |
| 1305 | 2 | Instructions |  |
| 1306 | 2 | Requirements & Submittals |  |
| 1307 | 2 | Guarantees & Warranties |  |
| 1308 | 2 | Other Project Closeout |  |
| 1309 | 2 | Legal Handover Procedures |  |

# Appendix A3 – Checklist for Submissions

  - Validate rates to be current immediately before any submission date.

  - Ensure filed sub-bid work is accurately identified and separable for bid comparison.

  - Review all lump sum allowances provided in the Estimate and ensure that any work that has been subsequently designed in detail has been priced out in detail.

  - For CSI estimates, all Subcontractor margins are included with their particular trade.

  - Complete review of the final specification to ensure consistency with the Estimate.

  - Complete review of the exact scope of works as specified for the Bid.

  - Validate that the size of the final design (GFA) is consistent with the Estimate.

  - Validate that the Construction Period is consistent with the Estimate.

  - Validate the Escalation Rate to be applied with DCAM prior to final submission.

Appendix A4 – Sample Uniformat Structured Narrative (for

Preliminary Design)

| A10 | Foundations |  |
| --- | --- | --- |
| A1010 | Standard Foundations | Standard continuous perimeter foundation Isolated interior footings for columns |
| A1030 | Slab on Grade | 6” slab on grade, with gravel base, rigid insulation, barrier |
| B10 | Superstructure |  |
| B1010 | Floor construction | Metal deck on steel bar joists |
| B1020 | Roof Construction | Metal deck on bar joists |
| B20 | Exterior Enclosure |  |
| B2010 | Exterior Walls | Brick veneer on galvanized metal stud backup wall systems, 20% of wall area to be 1” insulated curtain walling |
| B2020 | Exterior windows | Aluminum double glazed windows other than curtain walling area |
| B2030 | Exterior doors | Entry doors: Narrow stile aluminum glass doors Other doors: Hollow metal in welded steel frames |
| B30 | Roofing |  |
| B3010 | Roof coverings | Modified bitumen on flat roofing |
| B3020 | Roof openings | Smoke hatch where required, access hatch with ship’s ladder |
| C10 | Interior Construction |  |
| C1010 | Partitions | Skim coat on blueboard on metal studs; CMU to core only |
| C1020 | Interior doors | Typical 3’x7’ solid core wood, clear finish, in welded steel frames |
| C1030 | Fittings |  |
| C20 | Stairs |  |
| C2010 | Stair construction | Steel pan on channel stringers |
| C2020 | Stair finishes | Sealed concrete |
| C30 | Interior Finishes |  |

| C3010 | Wall finishes | Offices, conference areas: Painted skim coat on blueboard, vinyl base Toilet rooms: full height ceramic tile on wet walls, painted GWB elsewhere. |
| --- | --- | --- |
| C3020 | Floor finishes | Offices, conference areas: Carpet Toilet rooms: Ceramic Tile Kitchens and labs: VCT |
| C3030 | Ceiling finishes | Suspended acoustical tile in small rooms and offices, exposed structure in open office areas |
| D10 | Conveying | Two stop fully accessible passenger elevator |
| D20 | Plumbing | Copper distribution system, gas HWS, cast iron sanitary waste |
| D30 | HVAC | Fully distributed VAV system; 150 ton water-cooled rooftop chiller; gas fired water boiler; 48000CFM air handling unit |
| D40 | Fire Protection | Standard sprinkler system throughout, one 4” standpipe. |
| D50 | Electrical | Service, board panel and feeder, 2000 amps. Standard office lighting and power distribution. Fire detection system and control center. Conduit for telco and data systems. |
| E10 | Equipment | Kitchen stove and wash equipment; gym equipment in 400 sqft training room |
| E20 | Furnishings | Custom display cabinets, 50’ in total length; vertical venetian blinds to all external windows. |
| G10 | Site Preparation | Site area 1 acre to be stripped and reduced to levels. Existing single story timber dwelling approximately 4000 SF to be demolished. |
| G20 | Site Improvements | Car parking for 100 cars, unsecured, lined and lighted. Trees, shrubs, lawn and hydraulic watering system. Rainwater underground dispersion tank to suit area. Two roadway entry ramps |
| G30 | Site Mechanical Services | Storm sewer 24” connection, sanitary sewer 10” connection, water supply 4” connection, gas connection, all at street area. Diversion of sanitary sewer and provision of manholes. |
| G40 | Site Electrical Services | Electrical underground conduit and cabling, with manhole. Duct bank for teleco cabling. Exterior lighting to car park. |
| Z10 | General Conditions | No site access restrictions or normal working hours restrictions. No existing tenant requirements. Site security at standard level. |

# Appendix A5 – DCAM Estimate Summary Sheet

“APPENDIX K”

DCAM ESTIMATE SUMMARY SHEET

MASS. STATE PROJECT NO. 	 CONTRACT NO.

TITLE AND LOCATION OF PROJECT

DESIGNER	ESTIMATOR	DATE SUBMITTED

CONSTRUCTION DURATION	ANTICIPATED BID DATE

BASE BID	ALTERNATES

1	2	3

- SITE COST	$

- BUILDING COST	$

- ESTIMATED BID COST

(INCLUDE OVERHEAD AND PROFIT)	$

- ITEM 1 WORK OF GENERAL CONTRACTOR	$

- ITEM 2 WORK OF FILED SUB-BIDS -- TOTALED	$

- GROSS SQ. FT. AREA OF BUILDING	$

- GROSS SQ. FT. COST OF BUILDING	$

- NET SQ. FT. AREA OF BUILDING	$

- ET TO GROSS SQ. FOOTAGE		 %

- UNIT USER COST (PUPIL, BED)	$

- GENERAL CONTRACTOR'S OVERHEAD AND PROFIT $

[Note to Designer: If alternates are used, line numbers 3,4,5 & 11 shall be filled in for each alternate.]

“APPENDIX K” (continued)

| BASE BID |  |
| --- | --- |
| MASONRY | $ |
| MISC. & ORN. IRON | $ |
| WPFG., DAMP. & CAULKING | $ |
| ROOFING & FLASHING | $ |
| METAL WINDOWS | $ |
| GLASS & GLAZING | $ |
| LATHING & PLASTERING | $ |
| TILE | $ |
| TERRAZZO | $ |
| ACOUSTICAL TILE | $ |
| MARBLE | $ |
| RESILIENT FLOORS | $ |
| PAINTING | $ |
| ELEVATORS | $ |
| FIRE PROTECTION | $ |
| PLUMBING | $ |
| HVAC | $ |
| ELECTRICAL WORK | $ |
| TOTAL OF ITEM 2 WORK | $ |

FIELD SUB-BIDS BY SECTION

04101

05101

07101

07201

08501,

08801

09201

09301

09401

09501

09601

09701

09901

14201

15301

15401

15501

16101

ALTERNATES

1	2	3

$ 	$	 $

| BREAK-OUT OF SUB-SUB-BIDS |  |
| --- | --- |
| PLUMBING: INSULATION | $ |
| (OTHER) | $ |
| HVAC: TEMPERATURE CONTROLS | $ |
| SHEET METAL | $ |
| INSULATION | $ |
| BALANCING | $ |
| ELECTRICAL: -- SYSTEM | $ |
| (OTHER) | $ |

Appendix B – NIST Uniformat II, Level-3 Element

(Inclusions & Exclusions)

The following lists show what items are included and excluded at Level 3 in the 1997 version of the ASTM Standard Classification for Building Elements and Related Sitework. Note that the listings of inclusions and exclusions are not intended to be an exhaustive listing. Rather, they provide a general outline of what to expect in each element consistent with the selection criteria outlined in section 2.2. Exclusions are listed to help users find items quickly. For example, a user might place exterior load bearing walls under B2010 Exterior Walls or B1010 Floor Construction. UNIFORMAT II puts them under B2010 Exterior Walls based on technical judgment and current practice. Putting under B1010 Floor Construction a cross-reference to B2010 Exterior Walls directs the person who looks first under Floor Construction to the appropriate element, Exterior Walls.

Description of Building Elements

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
| A 10 Foundations | A 1010 Standard Foundations | - wall & column foundations - foundation walls up to level of top of slab on grade | - general excavation to reduce levels (see section G 1030, Site Earthwork) - excavation for basements (see section |
|  |  | - pile caps | A 2010, Basement Excavation) |
|  |  | - backfill & compaction | - basement walls (see section A 2020, |
|  |  | - footings & bases | Basement Walls) |
|  |  | - perimeter insulation | - under-slab drainage and insulation |
|  |  | - perimeter drainage | (see section A 1030, Slab on Grade) |
|  |  | - anchor plates |  |
|  |  | - dewatering |  |
|  | A 1020 Special Foundations | - piling - caissons - underpinning | - pile caps (see section A 1010, Standard Foundations) - rock excavation (unless associated |
|  |  | - dewatering | with Special Foundations) (see |
|  |  | - raft foundations | section A 1010, Standard Foundations |
|  |  |  | & section A 2010, Basement |
|  |  |  | Excavation) - grade beams |
|  |  |  | - any other special foundation |
|  |  |  | conditions |
|  | A 1030 Slab on Grade | - standard - structural - inclined slabs on grade - trenches - pits - bases | - applied floor finishes (see section C 3020, Floor Finishes) - hardeners & sealers to the slab (see section C 3020, Floor Finishes) |
|  |  | - under-slab drainage - under-slab insulation |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
| A 20 | A 2010 | - additional excavation required | - general grading to reduce levels over |
| Basement | Basement | for construction of basement | site (see section G 1030, Site |
| Construction | Excavation | - backfill & compaction | Earthwork) |
|  |  | - excavation support system |  |
|  | A 2020 Basement Walls | - basement wall construction - moisture protection | - walls above grade that enclose basements - (see section B 2010, Exterior Walls) |
|  |  |  | - perimeter drainage (see section A |
|  |  |  | 1010, |
|  |  |  | - Standard Foundations) |
| B 10 Super-structure | B 1010 Floor Construction | - floor structural frame - interior structural walls | - exterior load bearing walls (see section B 2010, Exterior Walls) - floor slabs & decks |
|  |  |  | - inclined & stepped floors - expansion & contraction joints |
|  |  |  | - balcony construction |
|  |  |  | - suspended ramps - exterior stairs and fire escapes |
|  |  |  | - other floor construction (e.g., |
|  |  |  | catwalks, space frames, etc.) - applied & suspended ceiling & floor |
|  |  |  | finishes (see section C 3020, Floor |
|  |  |  | Finishes & section C 3030, Ceiling Finishes) |
|  |  |  | - stair construction (see section C 2010, |
|  |  |  | Stair Construction) - balcony walls & railings (see section |
|  |  |  | B 2010, Exterior Walls) |
|  | B 1020 Roof Construction | - roof structural frame - structural interior walls supporting roof - roof decks, slabs & sheathing | - roof coverings (see section B 3010, Roof Coverings) - skylights & roof openings (see section B 3020 Openings) |
|  |  | - canopies - other roof construction | - stair construction (see section C 2010, Stair Construction) |
| B 20 | B 2010 | - Includes | - Excludes |
| Enclosure | Exterior Walls | - exterior wall construction with facing | - applied finishes to interior faces of - exterior walls (see section C 3010, |
|  |  | - materials, exterior applied | Wall Finishes) |
|  |  | finishes, | - columns and beams in exterior walls |
|  |  | - back-up construction, framing, | (see section B 10, Superstructure) |
|  |  | wallboard, - parapets, insulation & vapor | - Venetian blinds (see section E 20, Furnishings) |
|  |  | retarders, | - other interior sun control devices (see |
|  |  | - sheathing, wallboard - exterior load-bearing wall | section E 20, Furnishings) - roof eaves and eaves soffits (see |
|  |  | construction - exterior louvers & screens | section B 3010, Roof Coverings) - glazed curtain walls (see section B |
|  |  | - exterior sun control devices | 2020, Windows) |
|  |  | - balcony walls & railings - exterior soffits |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | B 2020 Exterior Windows | - windows - storefronts - curtain walls | - window treatments (see section E 20, Furnishings) |
|  |  | - exterior painting of windows - wall opening elements such as lintels, sills, flashings, etc. |  |
|  | B 2030 Exterior Doors | - personnel doors - revolving doors - overhead doors |  |
|  |  | - other doors (e.g., hanger doors, blast-resistant doors, etc.) |  |
| B 30 Roofing | B 3010 Roof Coverings | - roofing membranes - traffic coatings - waterproof membranes below paving - expansion joints - vapor retarder - roof & deck insulation | - roof openings (see section B 3020, Roof Openings) - roof drains (see section D 2040, Rain Water Drainage) - parapets (see section B 2010, Exterior Walls) |
|  |  | - roof fill |  |
|  |  | - flashings & trim - gutters & downspouts - eaves & eaves soffits |  |
|  | B 3020 | - skylights | - powered & ducted ventilators (see |
|  | Roof | - area glazing | section D 3040, Distribution Systems) |
|  | Openings | - roof hatches |  |
|  |  | - gravity roof ventilators |  |
|  |  | - smoke vents |  |
| C 10 Interior Construction | C 1010 Partitions Includes | - fixed partitions - demountable partitions - retractable & movable partitions - operable partitions - interior balustrades & screens - interior window & storefronts - Though not in standard, C1010 includes field constructed toilet | - stair balustrades (see section C 2010, Stair Construction) - interior load bearing & shear walls (see section B 10, Superstructure) - applied wall finishes (see section C 3010, Wall Finishes) - Fabricated toilet partitions ( see section C1030, Fittings) |
|  |  | partitions |  |
|  | C 1020 Interior Doors | - standard swinging doors - glazed doors - sliding & folding doors - fire doors - other doors | - vault doors (see section E 10, Equipment) - operable partitions (see section C 1010, Partitions) |
|  |  | - door frames |  |
|  |  | - door hardware |  |
|  |  | - door opening elements - door painting & staining - hatches & access doors |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | C 1030 Fittings | - chalk & tack boards - identifying devices - lockers - toilet & bath accessories - storage shelving | - equipment (see section E 10, Equipment) - furniture (see section E 20, Furnishings) - special construction (see section F |
|  |  | - handrails & ornamental metals - fabricated toilet partitions | 10,Special Construction) - fire extinguishers (see section D |
|  |  | - fabricated compartments and cubicles | 4030, Fire Protection Specialties) - manufactured case work (see section |
|  |  | - closet specialties | E 20, Furnishings) |
| C 20 Stairs | C 2010 Stair | - Includes | - Excludes |
|  | Construction | - stair treads, risers and landings - handrails and balustrades | - steps in structural slabs (see section B 1010, Floor Construction) |
|  | C 2020 Stair | - finishes to treads, risers, |  |
|  | Finishes | landings & soffits |  |
|  |  | - finishes to handrails & |  |
|  |  | balustrades |  |
| C 30 Interior Finishes | C 3010 Wall Finishes | - concrete wall finishes - wall plastering - wallboard - tile & terrazzo | - wallboard integral to interior walls & - partitions (see section C 1010, Partitions, B2010, Exterior walls) |
|  |  | - painting - wall-coverings - acoustic wall treatment |  |
|  |  | - other coatings & finishings |  |
|  | C 3020 Floor Finishes | - floor toppings and traffic membranes - hardeners & sealers | - stair finishes (see section C 2020, Stair Finishes) |
|  |  | - tile, terrazzo, wood & resilient |  |
|  |  | flooring - carpeting - masonry & stone flooring - other flooring (e.g., conductive, armored) - painting & staining - access pedestal flooring |  |
|  | C 3030 | - exposed concrete finishes | - finishes to stair soffits (see section |
|  | Ceiling Finishes | - plaster ceiling finishes - wallboard ceiling finishes | C2020, Stair Finishes) - finishes to exterior soffits (see section |
|  |  | - acoustic ceiling tiles & panels | B 2010, Exterior Walls) |
|  |  | - painting & staining |  |
|  |  | - metal strip ceilings |  |
|  |  | - other ceilings |  |
|  |  | - all suspended systems |  |
| D 10 Conveying | D 1010 Elevators and Lifts | - passenger elevators - freight elevators - people lifts | - elevator pits (see section A 1030, Slab on Grade) |
|  |  | - wheel chair lifts |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | D 1020 | - escalators |  |
|  | Escalators | - moving walks |  |
|  | and Moving |  |  |
|  | Walks |  |  |
|  | D 1090 Other | - hoist & cranes |  |
|  | Conveying Systems | - conveyors - dumbwaiters - pneumatic tube systems - linen, trash & mail chutes |  |
|  |  | - turntables |  |
|  |  | - operable scaffolding - transportation systems (for example baggage handling and aircraft loading systems) |  |
| D 20 | D 2010 | - Includes | - Excludes |
| Plumbing | Plumbing Fixtures | - water closets - urinals - lavatories - sinks - showers - bathtubs - drinking fountains - bidets | - domestic hot water heaters (see section D 2020, Domestic Water) - hose bibbs (see section D 2020, Domestic Water) - other equipment (see section D 2090,Other Plumbing Systems) |
|  | D 2020 | - pipes & fittings | - plumbing fixtures (see section D |
|  | Domestic | - valves, hydrants & hose bibbs | 2010,Plumbing Fixtures) |
|  | Water | - water heaters |  |
|  | Distribution | - domestic water supply |  |
|  |  | equipment |  |
|  |  | - insulation |  |
|  | D 2030 | - waste pipe & fittings |  |
|  | Sanitary | - vent pipe & fittings |  |
|  | Waste | - floor drains |  |
|  |  | - sanitary waste equipment |  |
|  |  | - insulation |  |
|  | D 2040 Rain | - pipe & fittings | - gutters & downspouts (see section |
|  | Water | - roof drains | B3010, Roof Coverings) |
|  | Drainage | - insulation |  |
|  | D 2090 Other | - other piping systems |  |
|  | Plumbing | - gas distribution |  |
|  | Systems | - acid waste systems |  |
|  |  | - pool equipment |  |
|  |  | - fountain piping systems & |  |
|  |  | devices |  |
| D 30 HVAC | D 3010 Energy Supply | - oil, gas, & coal supply - steam, hot & chilled water supply | - electrical energy supply systems (see section D 5090, Other Electrical Systems, and section D 5010, Service |
|  |  | - solar energy supply | & Distribution) |
|  |  | - wind energy supply |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | D 3020 Heat Generating Systems | - boilers, including electric - piping and fittings adjacent to boilers - primary pumps - auxiliary equipment - equipment & piping insulation | - electric space unit heaters & baseboard, fuel-fired unit heaters, furnaces (see section D 3050, Terminal & Package Units) - controls & instrumentation (see section D 3060, Controls & Instrumentation) |
|  | D 3030 Cooling Generating Systems | - chillers - cooling towers & evaporative coolers - condensing units - piping & fittings - primary pumps - direct expansion systems - equipment & piping insulation | - secondary chilled water pumps (see section D 3040, Distribution Systems) - distribution piping (see section D 3040,Distribution Systems) - controls & instrumentation (see section D3060, Controls & Instrumentation) |
|  | D 3040 Distribution Systems | - supply & return air systems, including air-handling units with coils (electric included) - filters, ductwork, & associated devices such as VAV boxes, - duct heaters, induction units & grilles - ventilation & exhaust systems - steam, hot water, glycol & chilled water distribution - associated terminal devices including convectors - fan-coil units, & induction units, but not water & steam unit heaters - heat recovery equipment - auxiliary equipment such as secondary pumps - heat exchangers, sound attenuation, & vibration isolation - piping, duct, & equipment insulation | - electric, gas, or oil fired unit heaters (see Section D 3050, Terminal & Package Units) - furnaces (gas or oil) (see section D 3050,Terminal & Package Units) - floor, ceiling, & rooftop package units(see section D 3050, Terminal & Package Units) - controls & instrumentation (see section D3060, Controls & Instrumentation) |
|  | D 3050 Terminal and Package Units | - electric baseboard - electric or fossil fuel fired unit heaters, - unit ventilators, & radiant heaters - window or through-the-wall air - conditioners, with or without heating of any type | - piping & accessories (see section D 3040,Distribution Systems) - hydronic or steam convectors, fan-coil units (see section D 3040, Distribution Systems) - cooling towers, remote air-cooled condensers, - evaporative coolers (see section D3030, Cooling Generation Systems) |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | D 3050 Terminal and Package Units | - reverse-cycle, water- or air-cooled, - terminal heat pumps - wall sleeves where required | - air-handling units with only hydronic heating or steam coils (see section D 3040, Distribution Systems) - air-handling units with chilled water |
|  |  | - electric or fossil fuel fired air- | or direct expansion cooling coils (see |
|  |  | handling units or furnaces - self-contained, air- or water- | section D 3040, Distribution Systems) |
|  |  | cooled, |  |
|  |  | - floor, ceiling, & rooftop air |  |
|  |  | conditioners, & heat pumps - ductwork and accessories, |  |
|  |  | including flue stacks - factory-integrated controls |  |
|  | D 3060 Controls and Instrument-ation | - heating generating systems - cooling generating systems - heating/cooling air handling units - exhaust & ventilating systems - terminal devices | - factory-installed controls, when an integral part of terminal & package units (see section D 3050, Terminal & Package Units) |
|  |  | - energy monitoring & control - building automation systems |  |
|  | D 3070 | - Includes |  |
|  | Systems | - piping systems testing & |  |
|  | Testing and | balancing |  |
|  | Balancing | - air systems testing & balancing |  |
|  | D3090 Other HVAC | - special cooling systems and devices |  |
|  | Systems and Equipment | - special humidity control - dust and fume collectors - air curtains |  |
|  |  | - air purifiers - paint spray booth ventilation |  |
|  |  | systems - general construction items associated with mechanical |  |
|  |  | systems |  |
| D 40 Fire Protection | D 4010 Sprinklers | - water supply equipment - piping valves & fittings |  |
|  |  | - sprinkler heads & release |  |
|  |  | devices |  |
|  | D 4020 | - water supply equipment |  |
|  | Standpipes | - piping valves & fittings |  |
|  |  | - cabinets & hoses |  |
|  | D 4030 Fire | - fire extinguishers |  |
|  | Protection | - fire extinguisher cabinets |  |
|  | Specialties |  |  |
|  | D 4090 Other | - carbon dioxide systems |  |
|  | Fire | - clean agent systems |  |
|  | Protection | - foam generating systems |  |
|  | Systems | - dry chemical systems |  |
|  |  | - exhaust hood systems |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
| D 50 Electrical | D 5010 Electrical Service and Distribution | - primary transformers - secondary transformers - main switchboard - interior distribution transformers - branch circuit panels - enclosed circuit breakers | - outdoor transformers (see section G 4010,Electrical Distribution) - emergency power (see section D 5090,Other Electrical Systems) - branch wiring (see section D 5020,Lighting & Branch Wiring) |
|  |  | - motor control centers |  |
|  |  | - conduit and wiring to circuit panels |  |
|  | D 5020 Lighting and Branch Wiring | - branch wiring & devices for lighting fixtures - lighting fixtures - branch wiring for devices & equipment - connections | - under-floor raceways (see section D 5090,Other Electrical Systems) - exterior site lighting (see section G 4020,Site Lighting) |
|  |  | - devices |  |
|  |  | - exterior building lighting |  |
|  | D 5030 Communicati ons and Security | - fire alarm systems | - other electrical systems (see section D5090, Other Electrical Systems) - call systems - telephone systems - local area networks |
|  |  |  | - public address & music systems - intercommunication systems & |
|  |  |  | paging - clock & program systems |
|  |  |  | - television systems |
|  |  |  | - security systems |
|  | D 5090 Other | - emergency generators | - electric baseboard (see section D |
|  | Electrical | - UPS | 3050,Terminal & Package Units) |
|  | Systems | - emergency lighting systems - power factor correction | - electric coils & duct heaters (see section D 3040, Distribution Systems) |
|  |  | - lightning & grounding | - building automation & energy |
|  |  | protection systems | monitoring systems (see section D |
|  |  | - raceway systems | 3060, Controls & Instrumentation) |
|  |  | - power generation systems | - communications & security systems |
|  |  |  | (see section D 5030, |
|  |  |  | Communications & Security) |
| E 10 Equipment | E 1010 Commercial Equipment | - security and vault equipment - teller and service equipment - registration equipment |  |
|  |  | - checkroom equipment |  |
|  |  | - mercantile equipment |  |
|  |  | - commercial laundry and dry |  |
|  |  | cleaning equipment |  |
|  |  | - vending equipment |  |
|  |  | - office equipment |  |

| General | Specific | Inclusions | Exclusions |
| --- | --- | --- | --- |
|  | E 1020 | - ecclesiastical equipment |  |
|  | Institutional | - library equipment |  |
|  | Equipment | - theater and stage equipment - instrumental equipment |  |
|  |  | - audio-visual equipment |  |
|  |  | - detention equipment |  |
|  |  | - laboratory equipment |  |
|  |  | - medical equipment |  |
|  |  | - mortuary equipment |  |
|  | E 1030 | - vehicular service equipment |  |
|  | Vehicular | - parking control equipment |  |
|  | Equipment | - loading dock equipment |  |
|  | E 1090 Other Equipment | - maintenance equipment - solid waste handling equipment - food service equipment - residential equipment - unit kitchens |  |
|  |  | - darkroom equipment - athletic, recreational, and |  |
|  |  | therapeutic equipment - planetarium equipment - observatory equipment - agricultural equipment |  |
| E 20 | E 2010 Fixed | - fixed artwork |  |
| Furnishings | Furnishings | - fixed casework - window treatment |  |
|  |  | - fixed floor grilles and mats - fixed multiple seating - fixed interior landscaping |  |
|  | E 2020 | - Includes |  |
|  | Movable | - movable artwork |  |
|  | Furnishings | - furniture and accessories - movable rugs and mats - movable multiple seating - movable interior landscaping |  |
| F 10 Special | F 1010 Special | - air-supported structures |  |
| Construction | Structures | - pre-engineered structures |  |
|  |  | - other special structures |  |

# Appendix B – CSI Division Numbers and Titles

(Copyright © The Construction Specifications Institute and Construction Specifications Canada, 2004.)

CSI Division Numbers and Titles

##### Procurement and Contracting Requirements Group Division 00 Procurement and Contracting Requirements

##### General Requirements Subgroup

Division 01 General Requirements

Division 02 Existing Conditions Division 03 Concrete

Division 04 Masonry

Division 05 Metals

Division 06 Wood, Plastics & Composites Division 07 Thermal & Moisture

Protection Division 08 Openings

Division 09 Finishes

Division 10 Specialties

Division 11 Equipment

Division 12 Furnishings Division 13 Special Construction

Division 14 Conveying Equipment Division 15 Reserved

Division 16 Reserved

Division 17 Reserved

Division 18 Reserved

Division 19 Reserved

##### Facility Services Subgroup

Division 20 Reserved Division 21 Fire Suppression Division 22 Plumbing

Division 23 Heating, Ventilating & Air

Conditioning Division 24 Reserved

Division 25 Integrated Automation Division 26 Electrical

Division 27 Communications

Division 28 Electronic Safety & Security Division 29 Reserved

##### Site and Infrastructure Subgroup

Division 30 Reserved

Division 31 Earthwork

Division 32 Exterior Improvements Division 33 Utilities

Division 34 Transportation Division 35 Waterway & Marine

Construction Division 36 Reserved

Division 37 Reserved

Division 38 Reserved

Division 39 Reserved

##### Process Equipment Subgroup

Division 40 Process Integration Division 41 Material Processing &

Handling Equipment Division 42 Process Heating, Cooling &

Drying Equipment Division 43 Process Gas & Liquid

Handling, Purification & Storage Equipment

Division 44 Pollution Control Equipment Division 45 Industry Specific

Manufacturing Equipment Division 46 Reserved

Division 47 Reserved

Division 48 Electrical Power Generation Division 49 Reserved

# Appendix C – CSI Detailed Divisions

CSI MasterFormat 2004 Structure

- Groups, Subgroups, and Division— the highest levels of organization:

  - Quantity of divisions increased from 16 to 34 active divisions (plus 16 reserved for expansion).

  - For continuity, Divisions 03 through 14 (building construction work) remain basically the same.

  - New divisions allow more flexibility for specifying civil, process, and other engineering work.

- Section Numbers and Titles:

  - Numbers generally have three pairs of numbers (6 digits, each pair defining a level of specificity.

  - An optional fourth pair of numbers (Level 4) is used for when greater specificity is required.

  - Additional numbers and letters can be added (Level 5) for user-assigned numbers.

  - Spaces between pairs are optional and should be made with word processing “hard space” function.

  - Titles are work results when practical: “Painting” not “Paints,” “Lighting” not “Luminaries.”

| Scope (Old Terms) | Levels | MF 1995 | MF 2004 |
| --- | --- | --- | --- |
| Division | Level 1 | 11234 | 11 22 33 |
| Broad Scope | Level 2 | 11234 | 11 22 33 |
| Medium Scope | Level 3 | 11234 | 11 22 33 |
| Narrow Scope (If Needed) | Level 4 | 11234 | 11 22 33.44 |
| User Defined (If Needed | Level 5 | Not Used | 11 22 33.4455ABC |

- Unassigned Numbers: Unassigned numbers can be user defined. Divisions should not be used.

CSI Detailed Divisions

DIVISION OF CAPITAL ASSET MANAGEMENT THE COMMONWEALTH OF MASSACHUSETTS STANDARD SPECIFICATIONS

Designers and Cost Estimators are referred to the above DCAM publication for a comprehensive listing of the classification of work according to CSI MasterFormat 2004™. These detailed estimates are only required at the end of Design Development and during Construction Documents phases.

Particular attention should be paid to the breakup of the Estimate for each Filed Sub Bid under MGL

149. Clauses for this breakup are identified in this index with an * where applicable. Some clauses are included with others for the purpose of MGL 149 and these are noted. The exact scope for work in each clause is described in detail in each section of the DCAM manual.

The Estimator must also take account of the General Provisions specification (Summary Section 011000) for any project specific or unusual conditions and requirements which may influence the estimate.

DETAILED CSI BREAKDOWN SECTIONS FOR SPECIFICATION AND ESTIMATE DIVISION 01 - GENERAL REQUIREMENTS

Section 011000	 Summary Section 012200	Unit Prices Section 012300	Alternates

Section 013100	 Project Management, Coordination and Commissioning Section 013200	Construction Progress Documentation

Section 013300 Submittal Procedures Section 014000 Quality Requirements Section 014200  References

Section 014325	Testing Agency Services

Section 015000	Temporary Facilities and Controls Section 015716	Temporary Pest Control

Section 016000	Product Requirements

Section 017419	Construction Waste Management and Disposal Section 017700	Contract Closeout

Section 018113	Sustainable Design Requirements DIVISION 02 - EXISTING CONDITIONS

Section 023000	Subsurface Investigation Section 024100	 Demolition

DIVISION 03 - CONCRETE

Section 033000	Cast-In-Place Concrete DIVISION 04 - MASONRY

Section 040001 *	Masonry Work

Section 042000	Unit Masonry (part of 040001 FSB) Section 044200	Exterior Stone Cladding

DIVISION 05 - METALS

Section 050001 *	Miscellaneous and Ornamental Iron Section 051200	Structural Steel Framing

Section 052100	Steel Joist Framing Section 053100	Steel Decking

Section 054000	Cold-Formed Metal Framing

Section 055000	Metal Fabrications (part of 050001 FSB) Section 055100	 Metal Stairs (part of 050001 FSB)

DIVISION 06 - WOOD, PLASTICS AND COMPOSITES

Section 061000	Rough Carpentry Section 061600	Sheathing

Section 064023	Interior Architectural Woodwork DIVISION 07 - THERMAL AND MOISTURE PROTECTION

Section 070001 *	Waterproofing, Damp-proofing and Caulking Section 070002 *	Roofing and Flashing

Section 071113

Section 071326

Section 071413

Section 071613

Section 071616

Section 072100

Section 072713

Section 074213

Section 075216

Section 075323

Section 075400

Section 076200

Section 077200

Section 078100

Section 078413

Section 078446

Section 079200

Section 079500

Bituminous Damp-proofing (part of 070001 FSB)

Self-Adhering Sheet Waterproofing (part of 070001 FSB)

Hot Fluid-Applied Rubberized Asphalt Waterproofing (part of 070001 FSB) Polymer Modified Cement Waterproofing (part of 070001 FSB)

Crystalline Waterproofing (part of 070001 FSB) Thermal Insulation

Modified Bituminous Sheet Air Barriers (part of 070001 FSB) Metal Wall Panels

SBS Modified Bituminous Membrane Roofing (part of 070002 FSB) EPDM Roofing (part of 070002 FSB)

Thermoplastic Membrane Roofing (part of 070002 FSB) Sheet Metal Flashing and Trim (part of 070002 FSB) Roof Accessories

Applied Fireproofing Penetration Firestopping Fire-Resistive Joint Systems

Joint Sealants (part of 070001 FSB) Expansion Control

DIVISION 08 - OPENINGS

Section 080001 *	 Metal Windows Section 080002 *	Glass and Glazing

Section 081113

Section 081416

Section 083323

Section 083326

Section 083613

Section 084113

Section 084413

Section 085113

Section 085200

Section 086300

Section 087100

Section 088000

Section 089000

Hollow Metal Doors and Frames Flush Wood Doors

Overhead Coiling Doors Overhead Coiling Grilles Sectional Doors

Aluminum-Framed Entrances and Storefronts Glazed Aluminum Curtain Walls

Aluminum Windows (part of 080001 FSB) Wood Windows

Metal-Framed Skylights Door Hardware

Glazing (part of 080002 FSB) Louvers and Vents

DIVISION 09 - FINISHES

Section 090001 *	Lathing and Plastering Section 090002 *	 Tile

Section 090003 *	Acoustical Tile Section 090004 *	 Marble

Section 090005 *	Resilient Floors Section 090006 *	Terrazzo Section 090007 *	 Painting

Section 092116	Gypsum Board Assemblies

Section 092117	Gypsum Board Shaft Wall Assemblies

Section 092400	Portland Cement Plastering (part of 090001 FSB) Section 093000	 Tiling (part of 090002 FSB)

Section 095113	Acoustical Panel Ceilings (part of 090003 FSB) Section 096340	 Stone Flooring

Section 096519	Resilient Tile Flooring (part of 090005 FSB) Section 096600	 Terrazzo Flooring (part of 090006 FSB) Section 096816	Sheet Carpeting

Section 097510	Marble Facing (part of 090004 FSB) Section 099000	Painting and Coating (part of 090007 FSB)

DIVISION 10 - SPECIALTIES

Section 101100	Visual Display Surfaces Section 101400	 Signage

Section 102113	 Toilet Compartments Section 102213	 Wire Mesh Partitions Section 102226	 Operable Partitions Section 102813	Toilet Accessories Section 104400	Fire-Protection Specialties Section 105113	 Metal Lockers

DIVISION 11 - EQUIPMENT

Section 113100	Appliances

Section 114000	Foodservice Equipment Section 115213	Projection Screens

DIVISION 12 - FURNISHINGS

Section 122213	 Horizontal Louver Blinds Section 124813	Entrance Floor Mats and Frames

DIVISION 14 - CONVEYING EQUIPMENT

Section 140001 *	Elevators

Section 142400	Hydraulic Elevators (part of 140001 FSB) Section 144200	Wheelchair Lifts (part of 140001 FSB)

DIVISION 21 - FIRE SUPPRESSION

Section 210001 *	Fire Protection DIVISION 22 - PLUMBING

Section 220001 *	Plumbing

DIVISION 23 - HEATING VENTILATING AND AIR CONDITIONING

Section 230001 *	Heating, Ventilating and Air-Conditioning DIVISION 26 - ELECTRICAL

Section 260001 *	Electrical Work DIVISION 31 - EARTHWORK

Section 311000	Site Clearing Section 312000	 Earth Moving

Section 312500	Erosion and Sedimentation Controls

# Appendix D – ASTM STANDARD E1557 UNIFORMAT II

ASTM E1557, UNIFORMAT II, defines a standard classification for building elements and related sitework. The classification was the direct responsibility of Subcommittee E-06.81 on Building Economics.

DCAM Elemental Estimates are to be submitted in accordance with the structure below, except that the whole of the Major Group Elements are to be summed before margins and allowances are added in accordance with instructions in this document. DCAM does not require Sitework Elements to be separated.

ASTM UNIFORMAT II Standard Classification for Building Elements E1557-97

98.07.29

| Level 1 Major Group Elements | Level 2 Group Elements | Level 3 Elements |
| --- | --- | --- |
| A. SUBSTRUCTURE | A10 Foundations | A1010 Standard Foundations A1020 Special Foundations A1030 Slab on Grade |
|  | A20 Basement Construction | A2010 Basement Excavation A2020 Basement Walls |
| B. SHELL | B10 Superstructure | B1010 Floor Construction B1020 Roof Construction |
|  | B20 Exterior Enclosure * | B2010 Exterior Walls B2020 Exterior Windows B2030 Exterior Doors |
|  | B30 Roofing | B3010 Roof Coverings B3020 Roof Openings |
| C. INTERIORS | C10 Interior Construction | C1010 Partitions C1020 Interior Doors C1030 Fittings * |
|  | C20 Stairs * | C2010 Stair Construction C2020 Stair Finishes |
|  | C30 Interior Finishes | C3010 Wall Finishes C3020 Floor Finishes C3030 Ceiling Finishes |
| D. SERVICES | D10 Conveying * | D1010 Elevators & Lifts * D1020 Escalators & Moving Walks D1090 Other Conveying Systems * |
|  | D20 Plumbing | D2010 Plumbing Fixtures D2020 Domestic Water Distribution D2030 Sanitary Waste D2040 Rain Water Drainage D2090 Other Plumbing Systems * |

ASTM UNIFORMAT II Standard Classification for Building Related Sitework E1557-97

98.07.29

| Level 1 | Level 2 | Level 3 |
| --- | --- | --- |
| Major Group | Group Elements | Elements |
| Elements |  |  |
| G. BUILDING | G10 Site Preparation | G1010 Site Clearing |
| SITEWORK |  | G1020 Site Demolition and Relocations |
|  |  | G1030 Site Earthwork |
|  |  | G1040 Hazardous Waste Remediation |
|  | G20 Site Improvements | G2010 Roadways G2020 Parking Lots |
|  |  | G2030 Pedestrian Paving G2040 Site Development G2050 Landscaping |
|  | G30 Site Mechanical Utilities * | G3010 Water Supply * G3020 Sanitary Sewer G3030 Storm Sewer |
|  |  | G3040 Heating Distribution G3050 Cooling Distribution G3060 Fuel Distribution |
|  |  | G3090 Other Site Mechanical Utilities * |
|  | G40 Site Electrical | G4010 Electrical Distribution |
|  | Utilities | G4020 Site Lighting * |
|  |  | G4030 Site Communications & Security * |
|  |  | G4090 Other Site Electrical Utilities * |
|  | G90 Other Site | G9010 Service and Pedestrian Tunnels* |
|  | Construction * | G9090 Other Site Systems * |

| Level 1 | Level 2 | Level 3 |
| --- | --- | --- |
| Major Group | Group | Elements |
| Elements | Elements |  |
| * Changes to previous E1557-96 Standard | D30 HVAC | D3010 Energy Supply D3020 Heat Generating Systems D3030 Cooling Generating Systems D3040 Distribution Systems D3050 Terminal & Package Units D3060 Controls and Instrumentation |
|  |  | D3070 Systems Testing & Balancing * D3090 Other HVAC Systems & Equipment * |
|  | D40 Fire Protection | D4010 Sprinklers * D4020 Standpipes * D4030 Fire Protection Specialties D4090 Other Fire Protection Systems * |
|  | D50 Electrical | D5010 Electrical Service & Distribution |
|  |  | D5020 Lighting & Branch Wiring D5030 Communication & Security * D5090 Other Electrical Systems * |
| E. EQUIPMENT & FURNISHINGS | E10 Equipment | E1010 Commercial Equipment E1020 Institutional Equipment E1030 Vehicular Equipment E1090 Other Equipment * |
|  | E20 Furnishings | E2010 Fixed Furnishings |
|  |  | E2020 Movable Furnishings |
| F. SPECIAL CONSTRUCTION & DEMOLITION | F10 Special Construction | F1010 Special Structures F1020 Integrated Construction F1030 Special Construction Systems |
|  |  | F1040 Special Facilities F1050 Special Controls and Instrumentation |
|  | F20 Selective | F2010 Building Elements Demolition |
|  | Building Demolition | F2020 Hazardous Components Abatement |

# Appendix E –	Building Floor Area Measurements

# Appendix F — Bibliography

ASTM Standard E1557 UNIFORMAT II

ASTM–Measurement of Buildings BNI

CSI Master Format

GSA

DCAM Designers Procedures Manual DCAM Project Management Manual DCAM Standard Specifications

NIST Uniformat II, Level-3 Element

R.S. Means

# Appendix G — Acronyms

ADA	Americans with Disabilities Act

| AMP | Affirmative Market Program |
| --- | --- |
| ANF | (Executive Office for) Administration and Finance |
| APSA/PSAA | Account information |
| CAMIS | Capital Asset Management Information System |
| CF | Cubic Foot |
| CCR | Clarification Change Request |
| CM | Construction Manager |
| DCAF | DCAM Commissioner Approval Form |
| DCAM | Division of Capital Asset Management |
| DPS | Department of Public Safety |
| DSB | Designer Selection Board |
| ECC | Estimated Construction Cost |
| FFE | Furniture, Fixtures and Equipment |
| FPE | Facility Performance Evaluations |
| GFA | Gross Floor Area |
| GMP | Guaranteed Maximum Price |
| HEFA | Health and Education Finance Authority (Federal Government) |
| IPC | Information Processing Center |
| ISA | Interagency Service Agreement |
| LEED | Leadership in Energy and Environmental Design program. |
| MAAB | Massachusetts Architectural Access Board |
| MADEP | Massachusetts Department of Environmental Protection |
| MBE | Minority Business Enterprise |
| MEPA | The Massachusetts Environmental Policy Act |

| MGL | Massachusetts General Law |
| --- | --- |
| MOU | Memorandum of Understanding |
| MSA | Master Services Agreement |
| NFA | Net Floor Area |
| NOI | Notice of Intent |
| OFA | Office of Finance and Administration |
| OFM | Office of Facilities Maintenance |
| OGC | Office of the General Counsel |
| OH&P | Home Office Overhead |
| OPDC | Office of Planning, Design and Construction |
| OSD | Operational Services Division |
| P-3 | Primavera Version 3 Scheduling Software |
| PCO | Potential Change Order |
| PMAS | Project Management and Accounting System |
| PMT | Procurement Management Team |
| PNF | Project Notification Form |
| PV | Payment Voucher form |
| QRS | Quick Response Survey |
| RE | Resident Engineer |
| RFI | Request for Information |
| RFP | Request for Proposal |
| RFQ | Request for Qualifications |
| RFR | Request for Response |
| ROF | Reservation of Funds |
| SF | Square Foot |
| SRC | State Records Center |

TPC	Total Project Cost

WBE	Women’s Business Enterprise

# Appendix H — Glossary

| 801 CMR 21 | Regulations for procuring a good or service. |
| --- | --- |
| Appropriations | Funds made available through acts of the state legislature, which |
|  | stipulate the use of funds. |
| As-Built Drawings | Drawings of the project based on information provided by the |
|  | Contractor. |
| CAMIS | The database for: building and component conditions; systems and |
|  | equipment; the cost and priority for repairing deficiencies; performing |
|  | preventative maintenance tasks; and site and location information. |
| Capital Spending | The plan, submitted by DCAM and approved by ANF, that lists projects |
| Plan | and their associated spending projections. |
| CF Estimate | Construction Estimate expressed as a cost rate in $ per CF of floor area |
|  | of the building. |
| Change Orders | These are issued to initiate changes to the project during construction. |
| Client Agencies | The agencies for which DCAM provides projects and services. These |
|  | include agencies in the Executive Branch, Higher Education, the |
|  | Judiciary and counties. |
| Commissioning | The process of ensuring that the project’s design intent has been met at |
|  | the conclusion of Construction. |
| Construction | Construction Industry Contractor, or consulting firm, engaged by DCAM |
| Manager | to manage projects using “CM at Risk” procurement as defined in MGL |
|  | 193. |
| Commissioning | The person who works with the Designer to establish the standards a |
| Agent | project must meet and to develop testing procedures that will measure |
|  | whether the standards are achieved. |
| Comm-Pass | The state’s electronic procurement system. |
| Compliance Office | The office charged with ensuring that Contract provisions relative to |
| in OGC | MBE/WBE participation, minority workforce and prevailing wages are |
|  | met. |
| Construction | Certification that the state construction project followed the Designer’s |
| Control Affidavits | documents and the Massachusetts State Building code. |
| Construction | Formal stages for bidding, contract award, construction and project |
| Phase | completion as defined in DCAM’s Designers Procedures Manual. |
| DCAF | The DCAM Commissioner Approval Form describes a project, estimates |
|  | costs associated with each major phase, identifies the funding source and |
|  | forecasts project spending by fiscal year. It also indicates the Fixed Asset |

Design Fees

Design Phase Direct Payments

Estimated Construction Cost

Emergency Waiver

Estimated Construction Cost

Facility Performance Evaluations

Filed Sub-Bids

Fixed Asset Database

Forms Library

General Contractor

Global Workshops

Horizontal Construction/ Chapt. 30 Projects

House Doctors

ID number.

The fees payable to the Designer under contract for preparation of the scheme through all Design Phases, for providing Specialist Sub-consultant services, and management during the Construction Phase.

Formal stages of design work through the project life-cycle as defined in DCAM’s Designers Procedures Manual.

Filed sub-bidders, approved MBEs/WBEs or entities previously approved by DCAM for the specific project can request direct payments; they are processed through OGC.

The estimated cost of all work described in the Construction Documents that is included in the Bid Package and contract.

Sets aside certain provisions of the public procurement laws to allow for expedited procurement to correct situations that pose an imminent threat to the health and safety of people or property. It is authorized by OGC.

The estimated cost to construct a project. Does not include related project development costs.

Conducted within several years after occupancy, these may result in guidelines for building types, revisions to standard specifications, changes to project management procedures, and considerations for planning and design.

Subcontractor work to be performed by filed sub-bidders when the cost in any 17 statutorily defined categories of work is estimated to exceed

$20,000.

Tracks improvements to state assets to allow for accurate reporting by the State Comptroller

OPDC project documents are located in one of two central repositories – in PMAS or on OPDC’s dedicated electronic directory. These forms should be used as the basis for project-generated correspondence.

Performs work on both new construction and building repair projects.

These ensure DCAM staff members and, as requested, other parties with specific subject-matter expertise have an opportunity to comment on the project during the Design Phase.

Covers such construction as site work or roadways, very similar to other DCAM-administered projects without requiring designer selection through the DSB, filed sub-bids or Contractor certification.

Engineering/architectural firms hired by DCAM to assist in support of ongoing new construction/major renovation projects or in smaller repair or renovation projects.

IPC, Information Processing Centers

Kickoff Meeting LEED

Lessons Learned Database

Liquidated Damages

Massets

Master Oversight Form

Monthly Oversight Form

Monthly Progress Workshops

MSA, Master Services Agreement

Notice to Proceed

OFA

OH&P

OPDC Manager

Owner-Contractor Agreement

Partnering Meeting

Plan Holders List PMAS

Central receiving areas in OPDC for boxes for mail, distribution (including copying), travel reimbursements, vacation requests and other general needs.

This meeting helps to establish points of contact, set expectations and review the project requirements.

The US Green Buildings Council’s Leadership in Energy and Environmental Design program.

Established by DCAM, it is an internal communication system, including a database, for disseminating knowledge/experiences.

Damages incurred as a result of delays in completing the work.

A Geographic Information System that contains information on all land and buildings in a mapping program.

A form completed at the beginning and end of the transferred projects by Client Agencies to provide summary project information to OPDC.

Forms provided during the implementation of the transferred projects that Client Agencies use to report project progress.

Provides for timely decisions on Design Phase items, ensures that project goals are met, and keeps the project on schedule.

This is developed between a number of environmental consulting and geotechnical engineering firms and DCAM. OPDC Environmental staff provides and administer these contracts.

Official written notice to Contractors from DCAM authorizing work to begin as of the date specified therein.

Office of Finance and Administration

Home Office Overhead covers Overhead, Administrative costs, and Profit.

The Program Manager or Project Manager that is the lead on a project at a particular point in the job.

Boilerplate component of Construction Contracts.

Construction Phase kick-off meeting at which all parties meet to agree on project goals and objectives.

A list of individuals that request and receive bid packages, including plans and specifications; it is maintained in the Bid Room.

DCAM’s Project Management and Accounting System. A web-based database used by DCAM and the Designer to store and access all project

related information.

PNF

Preliminary Estimate

Program Manager

Project Manager Project Number

Project Oversight Checklist

Project Team

Punch List PV

Quick Response Surveys

Record Drawings

RE, Resident Engineer

Retainage

ROF (Reservation of Funds)

A Project Notification Form submitted to the Massachusetts Historical Commission.

Also known as Budget Estimates, these are prepared prior to any conceptual design or site selection. The basis for measurement and pricing is the client’s requirements and previous historical cost information.

The Lead in the Study Phase of projects. After the Design Contract has been executed, the lead of the project may be transferred to a Project Manager with architectural, engineering or construction experience.

However, it is not unusual for the Program Manager to become the Project Manager.

The Project Lead after the Design Contract has been executed.

An intelligent number that denotes the Client Agency, the current fiscal year, a sequential assignment, the contract type and project phase.

A list provided to Client Agencies to which project control and supervision is delegated. It identifies major procurement elements and activities. The Deputy Director completes the Checklist during or immediately following a site visit to check on the status of the project.

A Project Team is comprised of Program Managers, Project Engineers, Energy Team staff, Project Managers and Deputy Directors; a Resident Engineer is part of the Project Team during the Construction Phase.

A list of items still outstanding when a project is 99% complete.

A state-issued Payment Voucher Form on which all Consultants, Contractors or Suppliers must submit payment requests.

These are intended to capture feedback about building performance so that necessary adjustments can be made within the warranty period for systems and materials.

Drawings prepared by the Designer upon completion of a Construction project, based on As-Built Drawings provided by the General Contractor.

The RE is DCAM’s on-site project representative during Construction.

Percentage of project construction cost that is held by DCAM until the project is completed.

Form to secure approval to fund non-contractor services associated with a project. (Changes to Contractor services are authorized via Change Orders.)

Schedule of Values

SF Estimate

Study Certification

Study Certification Checklist

Substantial Completion

Sustainable Design Checklist

Total Project Cost

Transfer Project/Delegation

Use/Occupancy Certificate

Serves as the basis for monthly payment requests

Construction Estimate expressed as a cost rate in $ per SF of floor area of the building.

Certification validates the Study as corresponding to the current needs of the agency and its long-term capital facilities development plan. The certificate identifies the funding source for the project.

This goes to the Client Agency that is seeking delegation of the Study Phase of a project to ensure the Study contains the necessary information for certification.

The point in a project when less than one (1) percent of the contract value, including Change Orders, remains to be finished and all work associated with health, welfare and building function is complete.

Indicates the measures considered and included in the Study and in the Design.

The ECC plus all soft costs, management costs, and other service costs making up the total cost of a project to DCAM.

The process by which the DCAM Commissioner may delegate control and supervision of building projects up to $1 million to Client Agencies for implementation.

Certifies the project or portions of the project are determined safe to occupy per the building code.

# Index

ASTM 5, 15, 22, 23, 27, 28, 30, 32, 33, 48,

65, 80, 82, 85

Change Order	87

Construction Contingencies	35

Construction Costs	7

Construction Documentation	3, 11, 33

Cost Management	1

Cost Modeling	4, 19, 28

CSI MasterFormat 3, 5, 30, 31, 32, 33, 75,

76

Cubic Foot Estimates	2

CF	2, 3, 4, 5, 86, 89

Design Development 3, 4, 11, 12, 30, 31,

32, 33, 46, 76

Design Workshop	31, 33

Electronic Formats	42

escalation	27, 32, 39, 40

Escalation Contingency 22, 28, 30, 33, 37,

39

Escalation Index Table	40

Estimate Shelf Life	28, 30, 33, 39

Estimated Construction Cost	3, 7, 86, 90

Estimating Contingencies	12

Estimating Contingency	22, 28, 30, 35, 37

Estimator Participation	23, 28, 31, 33

FFE	9, 86

Filed Sub-Bid	12

Final Estimates	3

for General Conditions 12, 22, 27, 30, 32, 57

General Conditions 7, 8, 13, 21, 36, 45, 48,

62

Life Cycle Costs	4

Massachusetts General Law

149	3, 12, 30, 32, 35, 76

Measured Estimates	3

Non-construction Costs	9

Overhead and Profit 8, 12, 22, 27, 30, 32, 36

Phasing	22, 37

Preliminary Estimates	2, 23

Quantity	9, 53, 75

Reservation of Funds	87

Schedule of Rates	4, 5

Schematic Design	2, 4, 12, 16, 27

soft costs	7, 93

Square Foot Estimates	2

SF 2, 3, 4, 5, 16, 18, 20, 21, 22, 25, 36,

62, 87, 93

Square Foot Rates	19

Standard Rates	See Square Foot Rates Study Phase 3, 12, 15, 19, 23, 27, 28, 92, 93

Study 1, 2, 3, 4, 5, 9, 12, 14, 15, 16, 19,

22, 23, 27, 28, 92, 93

Total Project Cost	7, 88, 93 UNIFORMAT II

Uniformat 4, 10, 21, 22, 24, 25, 27, 28,

29, 30, 31, 32, 33, 36, 42, 43, 48, 61,

65, 85

UNIFORMAT 3, 5, 7, 48, 49, 65, 80, 82,

85

UNIFORMAT II™	3, 5

Unit Price Estimates	3

Value Engineering	19, 31, 33, 57

Workshops	3, 15, 18, 24, 28, 90, 91