## Sched 6-8-06
DCS FY09 Quality Assurance Review Schedule
Operator | Notification Letter Due | Questionaire due to DCS office | Date Notification Letter E-Mailed | Start Date of Review | Program End Date for Review | Fiscal End Date for Review | Fiscal Staff | Program Staff | Report Due to Field | Operator Response Due | Staff Resp. for Ltr. & Rpt
New Bedford | 2009-01-02 | 2009-01-23 | 2009-01-02 | 2009-02-02 | 2009-02-13 | 2009-02-13 | Carrie P | Kathy W | 2009-03-16 | 2009-04-16 | P
Franklin/Hampshire | 2009-01-02 | 2009-01-23 | 2009-01-02 | 2009-02-02 | 2009-02-13 | 2009-02-13 | Mike R | Judy B | 2009-03-16 | 2009-04-16 | P
North Central | 2009-01-02 | 2009-01-23 | 2009-01-02 | 2009-02-02 | 2009-02-13 | 2009-02-13 | Michael W | Eleanor/Linda K. | 2009-03-16 | 2009-04-16 | P
Cape & Islands | 2009-04-17 | 2009-05-08 | 2009-04-17 | 2009-05-18 | 2009-05-29 | 2009-05-29 | Michael W | Judy B | 2009-06-29 | 2009-07-30 | F
North Shore | 2009-04-17 | 2009-05-08 | 2009-04-17 | 2009-05-18 | 2009-05-29 | 2009-05-29 | Bruce S | Linda K | 2009-06-29 | 2009-07-30 | F
Lower Merrimack | 2009-04-17 | 2009-05-08 | 2009-04-17 | 2009-05-18 | 2009-05-29 | 2009-05-29 | Mike R. | Eleanor W | 2009-06-29 | 2009-07-30 | F
Berkshire | 2009-04-17 | 2009-05-08 | 2009-04-17 | 2009-05-18 | 2009-05-29 | 2009-05-29 | Carrie P | Kathy W | 2009-06-29 | 2009-07-30 | F
Central Mass | 2009-07-03 | 2009-07-24 | 2009-07-03 | 2009-08-03 | 2009-08-14 | 2009-08-14 | Bruce S | Judy B | 2009-09-14 | 2009-10-15 | P
Bristol | 2009-07-17 | 2009-08-07 | 2009-07-17 | 2009-08-17 | 2009-08-28 | 2009-08-28 | Michael W | Kathy W | 2009-09-28 | 2009-10-29 | P
Lowell | 2009-08-21 | 2009-09-11 | 2009-08-21 | 2009-09-21 | 2009-10-02 | 2009-10-02 | Bruce S | Linda K | 2009-11-02 | 2009-12-03 | F
South Coastal | 2009-08-21 | 2009-09-11 | 2009-08-21 | 2009-09-21 | 2009-10-02 | 2009-10-02 | Michael W | Judy B | 2009-11-02 | 2009-12-03 | F
Brockton | 2009-08-21 | 2009-09-11 | 2009-08-21 | 2009-09-21 | 2009-10-02 | 2009-10-02 | Carrie P | Eleanor | 2009-11-02 | 2009-12-03 | F
Hampden | 2009-08-21 | 2009-09-11 | 2009-08-21 | 2009-09-21 | 2009-10-02 | 2009-10-02 | Mike R | Kathy W | 2009-11-02 | 2009-12-03 | F
Boston Pic | 2009-09-18 | 2009-10-09 | 2009-09-18 | 2009-10-19 | 2009-10-30 | 2009-10-30 | Mike R | N/A | 2009-11-30 | 2009-12-31 | F
EDIC | 2009-09-18 | 2009-10-09 | 2009-09-18 | 2009-10-19 | 2009-10-30 | 2009-10-30 | Bruce S | Linda K | 2009-11-30 | 2009-12-31 | P
Metro North | 2009-09-18 | 2009-10-09 | 2009-09-18 | 2009-10-19 | 2009-10-30 | 2009-10-30 | Michael W | Kathy W. | 2009-11-30 | 2009-12-31 | P
Metro South West | 2009-09-18 | 2009-10-09 | 2009-09-18 | 2009-10-19 | 2009-10-30 | 2009-10-30 | Carrie P | Eleanor | 2009-11-30 | 2009-12-31 | P
Note - P or F in the last column indicates that the Program or Fiscal staff person is responsible for the notification letter, questionnaire, & report distribution
Note: The areas highlighted in "yellow" have been completed.
Formulas:
Notification Letter Due = [Start Date of Review]-31
Questionaire due to DCS office = [Notification Letter Due]+21
Date Notification Letter E-Mailed = [Notification Letter Due]
Program End Date for Review = [Start Date of Review]+11
Fiscal End Date for Review = [Program End Date for Review]
Fiscal End Date for Review = +[Program End Date for Review]
Report Due to Field = [Program End Date for Review]+31
Report Due to Field = [Fiscal End Date for Review]+31
Operator Response Due = [Report Due to Field]+31