## Sched 6-8-06
DCS FY10 Quality Assurance Review Schedule
Operator | Notification Letter Due | Questionaire due to DCS office | Date Notification Letter E-Mailed | Start Date of Review | Program End Date for Review | Fiscal End Date for Review | Fiscal Staff | Prgm. Staff | WIBStaff | Report Due to Field | Operator Response Due | Staff Resp. for Ltr. & Rpt
New Bedford | 2010-01-01 | 2010-01-22 | 2010-01-01 | 2010-02-01 | 2010-02-19 | 2010-02-19 | Carrie P | Kathy W | Team | 2010-03-22 | 2010-04-22 | P
F/H | 2010-01-01 | 2010-01-22 | 2010-01-01 | 2010-02-01 | 2010-02-19 | 2010-02-19 | Rosetta | Eleanor | Team | 2010-03-22 | 2010-04-22 | P
North Central | 2010-01-01 | 2010-01-22 | 2010-01-01 | 2010-02-01 | 2010-02-19 | 2010-02-19 | Michael W | Linda K. | Team | 2010-03-22 | 2010-04-22 | P
North Shore | 2010-02-05 | 2010-02-26 | 2010-02-05 | 2010-03-08 | 2010-03-26 | 2010-03-26 | Bruce S | Linda K | Newbie 1 | 2010-04-26 | 2010-05-27 | F
L. Merrimack | 2010-02-05 | 2010-02-26 | 2010-02-05 | 2010-03-08 | 2010-03-26 | 2010-03-26 | Rosetta | Judy B | Cheryl | 2010-04-26 | 2010-05-27 | F
Berkshire | 2010-02-05 | 2010-02-26 | 2010-02-05 | 2010-03-08 | 2010-03-26 | 2010-03-26 | Carrie P | Kathy W | Kathy M | 2010-04-26 | 2010-05-27 | F
South Coastal | 2010-03-12 | 2010-04-02 | 2010-03-12 | 2010-04-12 | 2010-04-30 | 2010-04-30 | Michael W | Judy B | Newbie 2 | 2010-05-31 | 2010-07-01 | P
*Lowell | 2010-03-12 | 2010-04-02 | 2010-03-12 | 2010-04-12 | 2010-04-30 | 2010-04-30 | Bruce S | Linda K | Cheryl | 2010-05-31 | 2010-07-01 | P
*Brockton | 2010-03-12 | 2010-04-02 | 2010-03-12 | 2010-04-12 | 2010-04-30 | 2010-04-30 | Carrie P | Eleanor | Kathy M | 2010-05-31 | 2010-07-01 | P
*Hampden | 2010-03-12 | 2010-04-02 | 2010-03-12 | 2010-04-12 | 2010-04-30 | 2010-04-30 | Rosetta | Kathy W | Newbie 1 | 2010-05-31 | 2010-07-01 | P
*Metro North | 2010-04-16 | 2010-05-07 | 2010-04-16 | 2010-05-17 | 2010-06-04 | 2010-06-04 | Michael W | Kathy W | Newbie 2 | 2010-07-05 | 2010-08-05 | F
*Central Mass | 2010-04-16 | 2010-05-07 | 2010-04-16 | 2010-05-17 | 2010-06-04 | 2010-06-04 | Bruce S | Judy B | Kathy M | 2010-07-05 | 2010-08-05 | F
*Bristol | 2010-04-16 | 2010-05-07 | 2010-04-16 | 2010-05-17 | 2010-06-04 | 2010-06-04 | Rosetta | Eleanor | Newbie 1 | 2010-07-05 | 2010-08-05 | F
*Boston Pic | 2010-05-21 | 2010-06-11 | 2010-05-21 | 2010-06-21 | 2010-07-09 | 2010-07-09 | Carrie P | N/A | Newbie 2 | 2010-08-09 | 2010-09-09 | W
*EDIC | 2010-05-21 | 2010-06-11 | 2010-05-21 | 2010-06-21 | 2010-07-09 | 2010-07-09 | Bruce S | Linda K | N/A | 2010-08-09 | 2010-09-09 | W
Cape & Islands | 2010-05-21 | 2010-06-11 | 2010-05-21 | 2010-06-21 | 2010-07-09 | 2010-07-09 | Michael W | Judy B | Cheryl | 2010-08-09 | 2010-09-09 | P
*Metro S/West | 2010-05-21 | 2010-06-11 | 2010-05-21 | 2010-06-21 | 2010-07-09 | 2010-07-09 | Rosetta | Eleanor | Newbie 1 | 2010-08-09 | 2010-09-09 | P
Note - P or F or W in the last column indicates that the Program, Fiscal, or WIB staff person is responsible for the notification letter, questionnaire, & report distribution
Note - Team listed in the WIB Staff column indicates 2 staff members
Formulas:
Notification Letter Due = [Start Date of Review]-31
Questionaire due to DCS office = [Notification Letter Due]+21
Date Notification Letter E-Mailed = [Notification Letter Due]
Program End Date for Review = [Start Date of Review]+18
Fiscal End Date for Review = [Program End Date for Review]
Fiscal End Date for Review = +[Program End Date for Review]
Report Due to Field = [Program End Date for Review]+31
Report Due to Field = [Fiscal End Date for Review]+31
Operator Response Due = [Report Due to Field]+31