## Sched FY13
DCS FY'14 Program Quality Assurance Systems Certification Review Schedule
Operator | Notification Letter Due | Questionaire due to DCS office | Date Notification Letter E-Mailed | Date Entrance Meeting | Start Date of Review | Program End Date for Review | Program Staff | Report Due to Field | Operator Response Due
New Bedford | 2014-04-04 | 2014-04-25 | 2014-04-04 | 2014-05-02 | 2014-05-05 | 2014-05-09 | Judy | 2014-06-09 | 2014-07-10
F/H | 2014-05-16 | 2014-06-06 | 2014-05-16 | 2014-06-13 | 2014-06-16 | 2014-06-20 | Judy | 2014-07-21 | 2014-08-21
N. Central | 2014-05-23 | 2014-06-13 | 2014-05-23 | 2014-06-20 | 2014-06-23 | 2014-06-27 | Mike | 2014-07-28 | 2014-08-28
MSW | 2014-06-13 | 2014-07-04 | 2014-06-13 | 2014-07-11 | 2014-07-14 | 2014-07-18 | Julie | 2014-08-18 | 2014-09-18
Berkshire | 2014-07-04 | 2014-07-25 | 2014-07-04 | 2014-08-01 | 2014-08-04 | 2014-08-08 | Mike | 2014-09-08 | 2014-10-09
Brockton | 2014-07-11 | 2014-08-01 | 2014-07-11 | 2014-08-08 | 2014-08-11 | 2014-08-15 | Judy | 2014-09-15 | 2014-10-16
Lowell | 2014-07-11 | 2014-08-01 | 2014-07-11 | 2014-08-08 | 2014-08-11 | 2014-08-15 | Julie | 2014-09-15 | 2014-10-16
S. Shore | 2014-08-08 | 2014-08-29 | 2014-08-08 | 2014-09-05 | 2014-09-08 | 2014-09-12 | Judy | 2014-10-13 | 2014-11-13
EDIC | 2014-08-15 | 2014-09-05 | 2014-08-15 | 2014-09-12 | 2014-09-15 | 2014-09-19 | Mike | 2014-10-20 | 2014-11-20
Bristol | 2014-08-15 | 2014-09-05 | 2014-08-15 | 2014-09-12 | 2014-09-15 | 2014-09-19 | Julie | 2014-10-20 | 2014-11-20
Metro North | 2014-09-05 | 2014-09-26 | 2014-09-05 | 2014-10-03 | 2014-10-06 | 2014-10-10 | Judy | 2014-11-10 | 2014-12-11
Cape/Islands | 2014-09-05 | 2014-09-26 | 2014-09-05 | 2014-10-03 | 2014-10-06 | 2014-10-10 | Mike | 2014-11-10 | 2014-12-11
Hampden | 2014-09-05 | 2014-09-26 | 2014-09-05 | 2014-10-03 | 2014-10-06 | 2014-10-10 | Julie | 2014-11-10 | 2014-12-11
N. Shore | 2014-09-19 | 2014-10-10 | 2014-09-19 | 2014-10-17 | 2014-10-20 | 2014-10-24 | Judy | 2014-11-24 | 2014-12-25
Merrimack | 2014-10-03 | 2014-10-24 | 2014-10-03 | 2014-10-31 | 2014-11-03 | 2014-11-07 | Mike | 2014-12-08 | 2015-01-08
Central | 2014-10-03 | 2014-10-24 | 2014-10-03 | 2014-10-31 | 2014-11-03 | 2014-11-07 | Julie | 2014-12-08 | 2015-01-08
*Schedule is subject to change
Formulas:
Notification Letter Due = [Start Date of Review]-31
Questionaire due to DCS office = [Notification Letter Due]+21
Date Notification Letter E-Mailed = [Notification Letter Due]
Date Entrance Meeting = [Start Date of Review]-3
Program End Date for Review = [Start Date of Review]+4
Report Due to Field = [Program End Date for Review]+31
Operator Response Due = [Report Due to Field]+31