## Sheet1
MDCS FY' 21 FMO Fiscal Systems Review Schedule
Operator | Notification Letter Due | Questionnaire due to DCS office | Date Notification Letter E-Mailed | Start Date of Review | Fiscal End Date for Review | Fiscal Staff | Report Due to Field | Operator Response Due
ABCD | -31 | -10 |  |  | 1900-01-03 | Rosetta | 1900-02-03 | 1900-03-06
Berkshire | 2021-02-26 | 2021-03-19 |  | 2021-03-29 | 2021-04-02 | Carrie | 2021-05-03 | 2021-06-03
Bristol | 2021-02-05 | 2021-02-26 |  | 2021-03-08 | 2021-03-12 | Rosetta | 2021-04-12 | 2021-05-13
Brockton | 2020-12-11 | 2021-01-01 |  | 2021-01-11 | 2021-01-15 | Carrie | 2021-02-15 | 2021-03-18
Cape/Islands | 2021-05-21 | 2021-06-11 |  | 2021-06-21 | 2021-06-25 | Milly Ruiz | 2021-07-26 | 2021-08-26
Central | 2021-01-29 | 2021-02-19 |  | 2021-03-01 | 2021-03-05 | Carrie | 2021-04-05 | 2021-05-06
*CommCorp | -31 | -10 |  |  | 1900-01-03 | Rosetta | 1900-02-03 | 1900-03-06
EDIC | 2021-05-07 | 2021-05-28 |  | 2021-06-07 | 2021-06-11 | Jack K | 2021-07-12 | 2021-08-12
F/H | 2021-04-23 | 2021-05-14 |  | 2021-05-24 | 2021-05-28 | Carrie | 2021-06-28 | 2021-07-29
Hampden | 2021-03-26 | 2021-04-16 |  | 2021-04-26 | 2021-04-30 | Carrie | 2021-05-31 | 2021-07-01
Lowell | 2021-04-09 | 2021-04-30 |  | 2021-05-10 | 2021-05-14 | Jack K | 2021-06-14 | 2021-07-15
Merrimack | 2020-12-25 | 2021-01-15 |  | 2021-01-25 | 2021-01-29 | Jack K | 2021-03-01 | 2021-04-01
Metro North | 2020-10-30 | 2020-11-20 |  | 2020-11-30 | 2020-12-04 | Rosetta | 2021-01-04 | 2021-02-04
MSW | 2020-12-25 | 2021-01-15 |  | 2021-01-25 | 2021-01-29 | Rosetta | 2021-03-01 | 2021-04-01
N. Central | 2021-02-19 | 2021-03-12 |  | 2021-03-22 | 2021-03-26 | Milly Ruiz | 2021-04-26 | 2021-05-27
N. Shore | 2020-10-30 | 2020-11-20 |  | 2020-11-30 | 2020-12-04 | Jack K | 2021-01-04 | 2021-02-04
New Bedford | 2020-11-13 | 2020-12-04 |  | 2020-12-14 | 2020-12-18 | Rosetta | 2021-01-18 | 2021-02-18
South Shore | 2021-01-29 | 2021-02-19 |  | 2021-03-01 | 2021-03-05 | Jack K | 2021-04-05 | 2021-05-06
The WorkPlace NB | -31 | -10 |  |  | 1900-01-03 | Rosetta | 1900-02-03 | 1900-03-06
Notes: Dates are subject to change.
Formulas:
Notification Letter Due = [Start Date of Review]-31
Questionnaire due to DCS office = [Start Date of Review]-10
Fiscal End Date for Review = [Start Date of Review]+4
Report Due to Field = [Fiscal End Date for Review]+31
Operator Response Due = [Report Due to Field]+31