## Backlog Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
BACKLOG DOUBLE POLE SUMMARY REPORT
Reporting Period: April 30, 2014 to November 1, 2014
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | POLE OWNER 2 | BACKLOG DOUBLE POLE SUMMARY
|  |  |  | TOTAL BACKLOG DOUBLE POLES | REMAINING BACKLOG DOUBLE POLES | REMOVED BACKLOG DOUBLE POLES | % BACKLOG DOUBLE POLES REMOVED
|  |  |  | 0 | 0 | 0 | 100% | TOTALS
ASHBY | JO | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 0 | 0 | 100%
FITCHBURG | JO | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 0 | 0 | 100%
FITCHBURG | SO | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0 | 100%
LUNENBURG | JO | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 0 | 0 | 100%
SHIRLEY | JO | VERIZON | FITCHBURG GAS AND ELECTRIC | 0 | 0 | 0 | 100%
TOWNSEND | JO | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 0 | 0 | 100%
TOWNSEND | SO | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0 | 100%
NOTES: The Summary Reports in Attachment A provide all backlog and double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
NOTES: The Summary Reports in Attachment A provide all backlog and new double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
The following Column Definitions apply to this Summary Report:
CITY OR TOWN |  |  |  | City or town in which backlog double poles are located.
POLE OWNERSHIP TYPE |  |  |  | "JO" or "SO" to indicate joint or sole pole ownership.
POLE OWNER 1 |  |  |  | Sole owner or first joint owner.
POLE OWNER 2 |  |  |  | Second joint owner (where JO).
TOTAL BACKLOG DOUBLE POLES |  |  |  | Initial total of backlog double poles as of January 31, 2004.
REMAINING BACKLOG DOUBLE POLES |  |  |  | Backlog double poles remaining at end of reporting period.
REMOVED BACKLOG DOUBLE POLES |  |  |  | Total backlog double poles removed by end of reporting period.
% BACKLOG DOUBLE POLES REMOVED |  |  |  | Percent of total backlog double poles removed by end of reporting period.

## New Pole Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
NEW DOUBLE POLE SUMMARY REPORT
Reporting Period: April 30, 2014 to November 1, 2014
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | POLE OWNER 2 | NEW DOUBLE POLES SUMMARY
|  |  |  | NEW DOUBLE POLES AT START | NEW DOUBLE POLES ADDED | NEW DOUBLE POLES REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS | NEW DOUBLE POLES REMAINING AT END
|  |  |  | 68 | 102 | 19 | 130 | 151 | TOTALS
ASHBY | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 37 | 33 | 0 | 64 | 70
ASHBY | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 1 | 0 | 1 | 1
FITCHBURG | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 17 | 28 | 2 | 30 | 43
FITCHBURG | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0 | 0 | 0
LUNENBURG | Joint Owned | VERIZON | FITCHBURG GAS AND ELECTRIC | 2 | 20 | 17 | 5 | 5
LUNENBURG | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0 | 0 | 0
SHIRLEY | Joint Owned | VERIZON | FITCHBURG GAS AND ELECTRIC | 0 | 0 | 0 | 0 | 0
TOWNSEND | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 11 | 17 | 0 | 26 | 28
TOWNSEND | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 1 | 3 | 0 | 4 | 4
NOTES: The Summary Reports in Attachment A provide all backlog and double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
The following Column Definitions apply to this Summary Report:
CITY OR TOWN |  |  |  | City or town in which new double poles are located.
POLE OWNERSHIP TYPE |  |  |  | "JO" or "SO" to indicate joint or sole pole ownership.
POLE OWNER 1 |  |  |  | Sole owner or first joint owner.
POLE OWNER 2 |  |  |  | Second joint owner (where JO).
NEW DOUBLE POLES AT START |  |  |  | New double poles at start of reporting period.
NEW DOUBLE POLES ADDED |  |  |  | New double poles added during the reporting period.
NEW DOUBLE POLES REMOVED |  |  |  | New double poles removed during the reporting period.
NEW DOUBLE POLES REMAINING > 90 DAYS |  |  |  | New double poles remaining at end of the reporting period that exceed 90 days.
NEW DOUBLE POLES REMAINING AT END |  |  |  | New double poles remaining at end of the reporting period.

## Statistical Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
COMBINED SUMMARY REPORT FOR BACKLOG AND NEW DOUBLE POLES
Reporting Period: April 30, 2014 to November 1, 2014
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | POLE OWNER 2 | REMAINING POLES
|  |  |  | REMAINING BACKLOG POLES | NEW DOUBLE POLES REMAINING AT END | TOTAL POLES REMAINING (BACKLOG AND NEW DOUBLE POLES)
|  |  |  | 0 | 151 | 151 | TOTALS
ASHBY | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 70 | 70
ASHBY | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 1 | 1
FITCHBURG | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 43 | 43
FITCHBURG | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0
LUNENBURG | Joint Owned | VERIZON | FITCHBURG GAS AND ELECTRIC | 0 | 5 | 5
LUNENBURG | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 0 | 0
SHIRLEY | Joint Owned | VERIZON | FITCHBURG GAS AND ELECTRIC | 0 | 0 | 0
TOWNSEND | Joint Owned | FITCHBURG GAS AND ELECTRIC | VERIZON | 0 | 28 | 28
TOWNSEND | Sole Owned | FITCHBURG GAS AND ELECTRIC |  | 0 | 4 | 4

## Backlog Detail
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
BACKLOG DOUBLE POLE PROGRESS REPORT
Reporting Period: April 30, 2014 to November 1, 2014
CITY OR TOWN | POLE LOCATION (STREET) | PLM ID | TELEPHONE COMPANY POLE NUMBER | ELECTRIC COMPANY POLE NUMBER | POLE OWNER 1 | POLE OWNER 2 | DATE INSTALLED | DATE REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS (YES/NO) | BALL IN COURT

## New Pole Detail
ATTACHMENOT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
NEW POLE PROGRESS REPORT
Reporting Period: April 30, 2014 to November 1, 2014
CITY OR TOWN | POLE LOCATION (STREET) | PLM ID | TELEPHONE COMPANY POLE NUMBER | ELECTRIC COMPANY POLE NUMBER | POLE OWNER 1 | POLE OWNER 2 | DATE INSTALLED | DATE REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS (YES/NO) | BALL IN COURT
ASHBY | ALLEN RD | 395829 | 11.5 | 12 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-13 |  | YES | COMCAST
ASHBY | ALLEN RD | 395832 | 11 | 11 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-13 |  | YES | COMCAST
ASHBY | ALLEN RD | 398553 | 7 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-07 |  | YES | COMCAST
ASHBY | ALLEN RD | 409367 | 6 | 6 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-07 |  | YES | COMCAST
ASHBY | ALLEN RD | 409370 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-12 |  | YES | COMCAST
ASHBY | ALLEN RD | 409371 | 17 | 17 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-13 |  | YES | COMCAST
ASHBY | COUNTY RD | 395835 | 11 | 5 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-14 |  | YES | COMCAST
ASHBY | COUNTY RD | 410227 | 40 | 26 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-07 |  | YES | COMCAST
ASHBY | CROCKER RD | 398555 |  | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-14 |  | YES | COMCAST
ASHBY | DAVIS RD | 303128 | 24 | 25 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-14 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | DAVIS RD | 395825 | 12-2 | 12-2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-04-29 |  | YES | COMCAST
ASHBY | DEER BAY RD | 410221 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-21 |  | YES | COMCAST
ASHBY | ERICKSON RD | 409394 | 2 | 58 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-17 |  | YES | COMCAST
ASHBY | FITCHBURG STATE RD | 273940 | 249 | 67 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-15 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | FITCHBURG STATE RD | 395759 | 221 | 39 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-15 |  | YES | COMCAST
ASHBY | FITCHBURG STATE RD | 409372 | 222 | 40 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-15 |  | YES | COMCAST
ASHBY | FITCHBURG STATE RD | 409373 | 234 | 52 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-15 |  | YES | COMCAST
ASHBY | FOSTER RD | 410620 | 9 | 34 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-12 |  | YES | COMCAST
ASHBY | FOSTER RD | 412170 | 2 | 27 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-29 |  | YES | COMCAST
ASHBY | FOSTER RD | 414274 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-12 |  | YES | COMCAST
ASHBY | FROST RD | 409391 | 15 | 15 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-15 |  | YES | COMCAST
ASHBY | FROST RD | 409393 | 8 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-15 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 308653 | 383 | 115 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-04-10 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | GREENVILLE RD | 409374 | 258 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-16 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | GREENVILLE RD | 409375 | 277 | 22 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-05-16 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 409377 | 385 | 117 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-06-10 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 409378 | 382 | 114 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-06-11 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 409379 | 345 | 78 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-07 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 410220 | 294 | 30 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-06-10 |  | YES | COMCAST
ASHBY | GREENVILLE RD | 419402 | 314 | 50 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-06 |  | NO | COMCAST
ASHBY | GREENVILLE RD | 419404 | 316 | 52 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-03 |  | NO | COMCAST
ASHBY | GREENVILLE RD | 419406 | 317 | 53 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-03 |  | NO | COMCAST
ASHBY | GREENVILLE RD | 419408 | 318 | 54 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-03 |  | NO | COMCAST
ASHBY | GREENVILLE RD | 419409 | 319 | 55 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-06 |  | NO | COMCAST
ASHBY | GREENVILLE RD | 428142 | 315 | 51 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-11-03 |  | NO | COMCAST
ASHBY | HARRIS RD | 409382 | 4 | 4 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-07 |  | YES | COMCAST
ASHBY | HARRIS RD | 409383 | 5 | 5 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-15 |  | YES | COMCAST
ASHBY | HEYWOOD RD | 409396 | 8 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-17 |  | YES | COMCAST
ASHBY | INGERSON RD | 338650 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-18 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | JEWETT HILL RD | 334799 | 25 | 22 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-02-14 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | JEWETT HILL RD | 337448 | 23 | 20 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-02-14 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | JONES HILL RD | 337447 | 32 | 31 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-02-19 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | LOG CABIN RD | 339543 | 3 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-25 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | LOG CABIN RD | 347957 | 2 | 2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-19 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | LOG CABIN RD | 347961 | 5-1 | 5-51 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-01 |  | YES | COMCAST
ASHBY | MAIN ST | 273944 | 12 | 64 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-15 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | MAIN ST | 359898 | 2 | 52 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-09-24 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | MASON RD | 305179 | 25 | 24 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-21 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | MASON RD | 307381 | 17 | 47 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-03-28 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | MASON RD | 347958 | 3 | 4 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-19 |  | YES | COMCAST
ASHBY | MAYO RD | 286362 | 11 | 14 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2011-04-26 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | MAYO RD | 360130 | 3 | 5 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-09-25 |  | YES | COMCAST
ASHBY | NEW IPSWICH RD | 340640 | 99 | 87 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-02-20 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | NEW IPSWICH RD | 340653 | 60-1 | 53-1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-09 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | OLD NORTHFIELD RD | 338774 | 23 | 23 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-27 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | PILLSBURY RD | 360131 | 6 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-09-19 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | PIPER RD | 359893 | 50-1 | 64-1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-09-06 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | RICHARDSON RD | 273947 | 83 | 25 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-15 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | RICHARDSON RD | 347959 | 26 | 57 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-19 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | SPRINGHILL RD RD | 337446 | 20 | 15 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-12 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | TAYLOR RD | 340642 | 9 | 9 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-18 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | TAYLOR RD | 347955 | 8 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-18 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | TOWNSEND RD | 273950 | 3 | 2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-15 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | TURNPIKE RD | 340649 | 25 | 65 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-01 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | TURNPIKE RD | 370155 | 11 | 51 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-09-18 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | WARES RD | 289843 | 7 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2011-06-23 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | WEST STATE RD | 340651 | 41 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-04-08 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | WHEELER RD | 311080 | 23 | 13 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-05-02 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | WHITNEY RD | 338651 | 14 | 14 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-14 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | WHITNEY RD | 338652 | 10 | 10 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-03-14 |  | YES | FITCHBURG GAS AND ELECTRIC
ASHBY | FOSTER RD | 409412 |  | 42 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-15 |  | YES | COMCAST
FITCHBURG | ACADEMY ST | 371698 | 8 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-07-24 |  | YES | COMCAST
FITCHBURG | ASHBURNHAM HILL RD | 412800 | 50 | 51 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
FITCHBURG | ASHBY ST RD | 320682 | 154 | 5306 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-09-12 |  | YES | FITCHBURG GAS AND ELECTRIC
FITCHBURG | BERRY ST | 391953 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-18 |  | YES | COMCAST
FITCHBURG | BOUTELLE ST | 263105 | 4 | 390 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-04-22 |  | YES | FITCHBURG GAS AND ELECTRIC
FITCHBURG | BOUTELLE ST | 392310 | 2 | 2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-24 |  | YES | COMCAST
FITCHBURG | BOUTELLE ST | 392311 | 9 | 9 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-24 |  | YES | COMCAST
FITCHBURG | BOUTELLE ST | 417110 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-29 |  | NO | COMCAST
FITCHBURG | CASWELL RD | 409397 | 14 | 14 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-21 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 409401 | 13 | 13 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-22 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 411906 | 2 | 2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-24 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 411908 | 5 | 5 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-28 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 411909 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412167 | 8 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412168 | 9 | 9 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-23 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412313 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412314 | 7 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-23 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412315 | 15 | 15 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-21 |  | YES | COMCAST
FITCHBURG | CASWELL RD | 412316 | 16 | 16 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-22 |  | YES | COMCAST
FITCHBURG | HANCOCK ST | 273889 | 6 | 2110 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-12 |  | YES | FITCHBURG GAS AND ELECTRIC
FITCHBURG | HAWES ST | 419401 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-10-02 |  | NO | COMCAST
FITCHBURG | LAWRENCE ST | 428146 | 7 | 6 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-11-07 |  | NO | COMCAST
FITCHBURG | LAWTON AVE | 412802 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-08 |  | NO | COMCAST
FITCHBURG | LINWOOD ST | 391956 | 2 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-27 |  | YES | COMCAST
FITCHBURG | LUNENBURG ST | 392317 | 36-1 | 39-1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-27 |  | YES | COMCAST
FITCHBURG | MONTROSE ST | 412803 | 14 | 4626 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-08 |  | NO | COMCAST
FITCHBURG | MT VERNON ST | 366248 | 7 | 8 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-10-29 |  | YES | COMCAST
FITCHBURG | MT VERNON ST | 366254 | 6 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2013-10-29 |  | YES | COMCAST
FITCHBURG | PACIFIC ST | 417350 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-30 |  | NO | COMCAST
FITCHBURG | REDMAN PL | 391952 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-04-01 |  | YES | COMCAST
FITCHBURG | ROBINSON ST | 392313 | 1 | 1 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-18 |  | YES | COMCAST
FITCHBURG | TOWNSEND ST | 392299 | 6 | 6 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-24 |  | YES | COMCAST
FITCHBURG | WENDALL RD | 412169 | 4 | 2 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-18 |  | YES | COMCAST
FITCHBURG | WINTER ST | 391944 | 13 | 13 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-25 |  | YES | COMCAST
FITCHBURG | WINTER ST | 391951 | 14 | 14 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-03-27 |  | YES | COMCAST
FITCHBURG | WINTER ST | 411910 | 6 | 6 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-19 |  | YES | COMCAST
LUNENBURG | FLORENCE ST ST | 407225 | 2 | 2 | VERIZON | FITCHBURG GAS AND ELECTRIC | 2014-07-16 |  | YES | FITCHBURG GAS AND ELECTRIC
LUNENBURG | GRAHAM ST | 407216 | 7 | 4 | VERIZON | FITCHBURG GAS AND ELECTRIC | 2014-07-15 |  | YES | FITCHBURG GAS AND ELECTRIC
LUNENBURG | GRAHAM ST | 407221 | 6 | 5 | VERIZON | FITCHBURG GAS AND ELECTRIC | 2014-07-15 |  | YES | FITCHBURG GAS AND ELECTRIC
LUNENBURG | MASSACHUSETTS AVE | 357743 | 8-1 | 8-1 | VERIZON | FITCHBURG GAS AND ELECTRIC | 2011-02-01 |  | YES | FITCHBURG GAS AND ELECTRIC
LUNENBURG | PLEASENT ST | 382787 | 9 | 29 | VERIZON | FITCHBURG GAS AND ELECTRIC | 2014-04-09 |  | YES | COMCAST
TOWNSEND | ADAMS RD | 309963 | 29 | 29 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-03-06 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | BARKER HILL RD | 410224 | 47 | 45 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-11 |  | YES | COMCAST
TOWNSEND | BLOOD RD | 302410 | 5 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-07 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | BROOKLINE ST | 308645 | 17 | 25 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-04-09 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | DAVIS RD | 308652 | 28 | 29 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-04-10 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | EDWARD RD | 305175 | 6 | 16 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-27 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | EDWARD RD | 305176 | 10 | 11 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-27 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | EDWARD RD | 409402 | 9 | 10 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-31 |  | YES | COMCAST
TOWNSEND | HAYNES RD | 128152 | 15 | 1661 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2006-05-11 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | HAYNES RD | 128157 | 16 | 1662 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2006-05-11 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | LUNENBURG RD | 410647 | 73 | 15 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-07-31 |  | YES | COMCAST
TOWNSEND | MAIN ST | 273928 | 1/2 | 126 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2010-10-15 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409405 | 20 | 142 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-04 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409407 | 42 | 164 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-04 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409408 | 44 | 166 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-04 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409684 | 79 | 200 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-05 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409685 | 47 | 169 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-04 |  | YES | COMCAST
TOWNSEND | MAIN ST | 409686 | 108 | 229 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-06 |  | YES | COMCAST
TOWNSEND | MAIN ST | 410607 | 102 | 223 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-05 |  | YES | COMCAST
TOWNSEND | MAIN ST | 410608 | 128 | 247 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-06 |  | YES | COMCAST
TOWNSEND | MAPLE ST | 216599 | 7 | 7 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2008-08-01 |  | YES | COMCAST
TOWNSEND | NORTH END RD | 410225 | 70 | 22 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-12 |  | YES | COMCAST
TOWNSEND | SAUNA ROW RD | 413062 | 4 | 6 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-08 |  | NO | COMCAST
TOWNSEND | SCHOOL ST | 413164 | 3 | 3 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
TOWNSEND | VINTON POND RD | 410222 | 35 | 28 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-07 |  | YES | COMCAST
TOWNSEND | W ELM ST | 413163 | 43 | 44 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-09-08 |  | NO | COMCAST
TOWNSEND | WORCESTER RD | 302164 | 5 | 5 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2012-02-06 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | WORCESTER RD | 410226 | 4 | 4 | FITCHBURG GAS AND ELECTRIC | VERIZON | 2014-08-14 |  | YES | COMCAST
TOWNSEND | HAYNES RD | 410223 |  | 20-1 | FITCHBURG GAS AND ELECTRIC |  | 2014-08-07 |  | YES | COMCAST
TOWNSEND | MAPLEWOOD DR | 348995 |  | 26 | FITCHBURG GAS AND ELECTRIC |  | 2013-04-29 |  | YES | FITCHBURG GAS AND ELECTRIC
TOWNSEND | SYCAMORE DR | 409410 |  | 2 | FITCHBURG GAS AND ELECTRIC |  | 2014-07-30 |  | YES | COMCAST
TOWNSEND | SYCAMORE DR | 409411 |  | 5 | FITCHBURG GAS AND ELECTRIC |  | 2014-07-30 |  | YES | COMCAST