## Backlog Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
BACKLOG DOUBLE POLE SUMMARY REPORT
Reporting Period: April 30, 2021 to November 1, 2021
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | POLE OWNER 2 | BACKLOG DOUBLE POLE SUMMARY
|  |  |  | TOTAL BACKLOG DOUBLE POLES | REMAINING BACKLOG DOUBLE POLES | REMOVED BACKLOG DOUBLE POLES | % BACKLOG DOUBLE POLES REMOVED
|  |  |  | 418 | 0 | 418 | 100% | TOTALS
Ashby | JO | Fitchburg Gas and Electric | Verizon | 114 | 0 | 114 | 100%
Ashby | JO | Verizon | Fitchburg Gas and Electric | 1 | 0 | 1 | 100%
Fitchburg | SO | Fitchburg Gas and Electric |  | 7 | 0 | 7 | 100%
Fitchburg | JO | Fitchburg Gas and Electric | Verizon | 74 | 0 | 74 | 100%
Fitchburg | JO | Verizon | Fitchburg Gas and Electric | 92 | 0 | 92 | 100%
Leominster | JO | Verizon | Fitchburg Gas and Electric | 1 | 0 | 1 | 100%
Lunenburg | JO | Fitchburg Gas and Electric | Verizon | 1 | 0 | 1 | 100%
Lunenburg | JO | Verizon | Fitchburg Gas and Electric | 36 | 0 | 36 | 100%
Shirley | JO | Verizon | Fitchburg Gas and Electric | 1 | 0 | 1 | 100%
Townsend | JO | Fitchburg Gas and Electric | Verizon | 67 | 0 | 67 | 100%
Townsend | SO | Fitchburg Gas and Electric |  | 2 | 0 | 2 | 100%
Townsend | JO | Verizon | Fitchburg Gas and Electric | 22 | 0 | 22 | 100%
NOTES: The Summary Reports in Attachment A provide all backlog and double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
NOTES: The Summary Reports in Attachment A provide all backlog and new double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
The following Column Definitions apply to this Summary Report:
CITY OR TOWN |  |  |  | City or town in which backlog double poles are located.
POLE OWNERSHIP TYPE |  |  |  | "JO" or "SO" to indicate joint or sole pole ownership.
POLE OWNER 1 |  |  |  | Sole owner or first joint owner.
POLE OWNER 2 |  |  |  | Second joint owner (where JO).
TOTAL BACKLOG DOUBLE POLES |  |  |  | Initial total of backlog double poles as of January 31, 2004.
REMAINING BACKLOG DOUBLE POLES |  |  |  | Backlog double poles remaining at end of reporting period.
REMOVED BACKLOG DOUBLE POLES |  |  |  | Total backlog double poles removed by end of reporting period.
% BACKLOG DOUBLE POLES REMOVED |  |  |  | Percent of total backlog double poles removed by end of reporting period.

## New Pole Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
NEW DOUBLE POLE SUMMARY REPORT
Reporting Period: April 30, 2021 to November 1, 2021
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | NEW DOUBLE POLES SUMMARY
|  |  | NEW DOUBLE POLES AT START | NEW DOUBLE POLES ADDED | NEW DOUBLE POLES REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS | NEW DOUBLE POLES REMAINING AT END
|  |  | 353 | 121 | 121 | 290 | 353 | TOTALS
Ashby | SO | Fitchburg Gas and Electric | 2 | 4 | 0 | 4 | 6
Fitchburg | SO | Fitchburg Gas and Electric | 267 | 91 | 68 | 255 | 290
Leominster | SO | Fitchburg Gas and Electric | 0 | 0 | 0 | 0 | 0
Lunenburg | SO | Fitchburg Gas and Electric | 74 | 16 | 53 | 21 | 37
Townsend | SO | Fitchburg Gas and Electric | 10 | 10 | 0 | 10 | 20
NOTES: The Summary Reports in Attachment A provide all backlog and double poles recorded in the Pole Lifecycle Management (PLM) database. Backlog double poles are those with a set date on or before January 31, 2004, and new double poles are those with a set date after January 31, 2004. Municipal electric companies that are sole and joint pole owners are included in these Reports.
The following Column Definitions apply to this Summary Report:
CITY OR TOWN |  |  | City or town in which new double poles are located.
POLE OWNERSHIP TYPE |  |  | "JO" or "SO" to indicate joint or sole pole ownership.
POLE OWNER 1 |  |  | Sole owner or first joint owner.
POLE OWNER 2 |  |  | Second joint owner (where JO).
NEW DOUBLE POLES AT START |  |  | New double poles at start of reporting period.
NEW DOUBLE POLES ADDED |  |  | New double poles added during the reporting period.
NEW DOUBLE POLES REMOVED |  |  | New double poles removed during the reporting period.
NEW DOUBLE POLES REMAINING > 90 DAYS |  |  | New double poles remaining at end of the reporting period that exceed 90 days.
NEW DOUBLE POLES REMAINING AT END |  |  | New double poles remaining at end of the reporting period.

## Statistical Summary
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
COMBINED SUMMARY REPORT FOR BACKLOG AND NEW DOUBLE POLES
Reporting Period: April 30, 2021 to November 1, 2021
CITY OR TOWN | POLE OWNERSHIP TYPE | POLE OWNER 1 | REMAINING POLES
|  |  | REMAINING BACKLOG POLES | NEW DOUBLE POLES REMAINING AT END | TOTAL POLES REMAINING (BACKLOG AND NEW DOUBLE POLES)
|  |  | 0 | 353 | 353 | TOTALS
Ashby | SO | Fitchburg Gas and Electric | 0 | 6 | 6
Fitchburg | SO | Fitchburg Gas and Electric | 0 | 290 | 290
Leominster | SO | Fitchburg Gas and Electric | 0 | 0 | 0
Lunenburg | SO | Fitchburg Gas and Electric | 0 | 37 | 37
Townsend | SO | Fitchburg Gas and Electric | 0 | 20 | 20

## Backlog Detail
ATTACHMENT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
BACKLOG DOUBLE POLE PROGRESS REPORT
Reporting Period: April 30, 2021 to November 1, 2021
CITY OR TOWN | POLE LOCATION (STREET) | PLM ID | TELEPHONE COMPANY POLE NUMBER | ELECTRIC COMPANY POLE NUMBER | POLE OWNER 1 | POLE OWNER 2 | DATE INSTALLED | DATE REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS (YES/NO) | BALL IN COURT

## New Pole Detail
ATTACHMENOT A
D.T.E. 03-87 DOUBLE POLE STATUS GRID
NEW POLE PROGRESS REPORT
Reporting Period: April 30, 2021 to November 1, 2021
CITY OR TOWN | POLE LOCATION (STREET) | NJUNS ID | TELEPHONE COMPANY POLE NUMBER | ELECTRIC COMPANY POLE NUMBER | POLE OWNER 1 | DATE INSTALLED | DATE REMOVED | NEW DOUBLE POLES REMAINING > 90 DAYS (YES/NO) | BALL IN COURT
Ashby | HILLSIDE DR | 4730183 |  | 4 | Fitchburg Gas and Electric | 2021-06-18 | 2021-07-01 | No | Fitchburg Gas and Electric
Ashby | JONES HILL RD | 4698622 | 10 | 10 | Fitchburg Gas and Electric | 2021-05-19 |  | Yes | Comcast Massachusetts
Ashby | MAIN ST | 4119317 | 51 | 39 | Fitchburg Gas and Electric | 2019-12-01 |  | Yes | Fitchburg Gas and Electric
Ashby | MAIN ST | 4662091 | 6 | 57 | Fitchburg Gas and Electric | 2021-03-31 |  | Yes | Comcast Massachusetts
Ashby | Main St | 4818252 | 35 | 87 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Ashby | PILLSBURY RD | 4698563 | 28 | 28 | Fitchburg Gas and Electric | 2021-05-19 |  | Yes | Comcast Massachusetts
Fitchburg | Allen Place | 4469137 |  | 1 | Fitchburg Gas and Electric | 2020-10-26 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | ALMOUNT RD | 4662098 | 5 | 5 | Fitchburg Gas and Electric | 2021-04-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ALMOUNT RD | 4662134 | 7 | 7 | Fitchburg Gas and Electric | 2021-04-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ALMOUNT TERRACE | 4612064 | 1 | 1 | Fitchburg Gas and Electric | 2021-03-03 |  | Yes | Verizon Massachusetts
Fitchburg | Amiott St | 4818308 | 1 | 1 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | APPLETON CIRCLE | 4657973 | 11 | 11 | Fitchburg Gas and Electric | 2021-03-24 |  | Yes | Verizon Massachusetts
Fitchburg | APPLETON CIRCLE | 4657990 | 6 | 6 | Fitchburg Gas and Electric | 2021-03-24 |  | Yes | Verizon Massachusetts
Fitchburg | APPLETON CIRCLE | 4657980 | 7 | 7 | Fitchburg Gas and Electric | 2021-03-24 |  | Yes | Verizon Massachusetts
Fitchburg | ASHBURNHAM ST | 4690904 | 12.5 | 13 | Fitchburg Gas and Electric | 2021-04-13 |  | Yes | Verizon Massachusetts
Fitchburg | ASHBURNHAM ST | 4690926 | 25 | 26 | Fitchburg Gas and Electric | 2021-05-04 |  | Yes | Verizon Massachusetts
Fitchburg | ASHBURNHAM ST | 4690941 | 39 | 40 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Verizon Massachusetts
Fitchburg | ASHBURNHAM ST | 4690956 |  | 62-1 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ASHBURNHAM ST | 4691043 | 69 | 69 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Verizon Massachusetts
Fitchburg | BAGLEY AVE | 4552380 | 1 | 1 | Fitchburg Gas and Electric | 2021-01-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | BAMFORD AVE | 4498861 | 1 | 1 | Fitchburg Gas and Electric | 2020-10-07 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | BAMFORD AVE | 4498882 | 2 | 2 | Fitchburg Gas and Electric | 2020-10-07 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | BEECH ST | 4609409 | 14 | 12-1 | Fitchburg Gas and Electric | 2021-02-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | BEECH ST | 4796165 |  | 18-1 | Fitchburg Gas and Electric | 2019-10-30 |  | Yes | Fitchburg Gas and Electric
Fitchburg | BEECH ST | 4600212 | 26 | 20-2 | Fitchburg Gas and Electric | 2021-02-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Bel Air Dr | 4612088 | 7 | 7 | Fitchburg Gas and Electric | 2021-02-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | BEL AIR DR | 4618742 | 9 | 9 | Fitchburg Gas and Electric | 2021-03-09 |  | Yes | Fitchburg Gas and Electric
Fitchburg | BOUTELLE ST | 4450908 | 24 | 24 | Fitchburg Gas and Electric | 2020-09-29 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | BRIGHAM ST | 4527367 | 1 | 1 | Fitchburg Gas and Electric | 2020-11-03 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | Brigham St | 4485027 | 4 | 4 | Fitchburg Gas and Electric | 2020-11-03 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | CALDWELL ST | 4424325 | 5 | 5 | Fitchburg Gas and Electric | 2020-09-04 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | CASCADE ST | 4812223 | 3 | 3 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Verizon Massachusetts
Fitchburg | CENTRAL AVE EXT | 4691066 | 10 | 10 | Fitchburg Gas and Electric | 2021-04-21 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CENTRAL AVE EXT | 4691077 | 12 | 12 | Fitchburg Gas and Electric | 2021-04-22 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CENTRAL AVE EXT | 4691090 | 13 | 13 | Fitchburg Gas and Electric | 2021-04-21 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CENTRAL AVE EXT | 4731199 | 3 | 3 | Fitchburg Gas and Electric | 2021-04-21 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CENTRAL AVE EXT | 4691059 | 4 | 4 | Fitchburg Gas and Electric | 2021-04-22 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CHABOT DR | 4618745 | 1 | 1 | Fitchburg Gas and Electric | 2021-03-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CLARENDON ST | 4796218 | 3 | 3 | Fitchburg Gas and Electric | 2021-07-26 |  | Yes | Comcast Massachusetts
Fitchburg | CLARENDON ST | 4505126 | 34 | 35 | Fitchburg Gas and Electric | 2020-11-05 |  | Yes | Verizon Massachusetts
Fitchburg | CLARENDON ST | 4505133 | 36 | 37 | Fitchburg Gas and Electric | 2020-11-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CLEGHORN ST | 4758908 | 12 | 8 | Fitchburg Gas and Electric | 2021-07-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | CLEGHORN ST | 4758954 | 13 | 9 | Fitchburg Gas and Electric | 2021-06-30 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Cliff St | 4485038 | 1 | 1 | Fitchburg Gas and Electric | 2020-10-21 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | COOLIDGE AVE | 3330370 |  | 1 | Fitchburg Gas and Electric | 2017-10-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | COTTAGE ST | 4678646 | 4 | 4 | Fitchburg Gas and Electric | 2021-04-21 |  | Yes | Verizon Massachusetts
Fitchburg | COTTAGE ST | 4796266 |  | 5-1 | Fitchburg Gas and Electric | 2021-04-26 |  | Yes | Fitchburg Gas and Electric
Fitchburg | COTTAGE ST | 4678710 |  | 6-51 | Fitchburg Gas and Electric | 2021-04-26 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | DANIELS ST | 4612096 | 14 | 21 | Fitchburg Gas and Electric | 2021-02-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DANIELS ST | 4547035 |  | 35-51 | Fitchburg Gas and Electric | 2020-12-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DANIELS ST | 4561802 |  | 37-52 | Fitchburg Gas and Electric | 2020-12-02 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | DANIELS ST | 4547046 |  | 37-52 | Fitchburg Gas and Electric | 2020-12-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DANIELS ST | 4600240 | 1.5 | 8 | Fitchburg Gas and Electric | 2021-02-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DELISLE ST | 4505147 | 6 | 5 | Fitchburg Gas and Electric | 2020-10-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DEPOT ST | 4658001 | 12 | 12 | Fitchburg Gas and Electric | 2021-03-23 |  | Yes | Fitchburg Gas and Electric
Fitchburg | DEPOT ST | 4660840 | 15 | 15 | Fitchburg Gas and Electric | 2021-03-18 |  | Yes | Verizon Massachusetts
Fitchburg | Douglas Ave | 4458092 | 2-1 | 1 | Fitchburg Gas and Electric | 2020-10-06 |  | Yes | Fitchburg Gas and Electric
Fitchburg | EATON ST | 4884172 | 12 | 11 | Fitchburg Gas and Electric | 2021-04-13 |  | Yes | Comcast Massachusetts
Fitchburg | EDWARD ST | 4527594 | 1 | 1 | Fitchburg Gas and Electric | 2020-11-16 |  | Yes | Fitchburg Gas and Electric
Fitchburg | EDWARD ST | 4527577 | 7 | 7 | Fitchburg Gas and Electric | 2020-10-21 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ELECTRIC AVE | 4820342 | 5 | 40 | Fitchburg Gas and Electric | 2021-09-02 |  | No | Verizon Massachusetts
Fitchburg | ELECTRIC AVE | 4820168 | 4 | 41 | Fitchburg Gas and Electric | 2021-09-02 |  | No | Comcast Massachusetts
Fitchburg | ELECTRIC AVE | 4622413 | 1 | 44 | Fitchburg Gas and Electric | 2020-12-03 |  | Yes | Verizon Massachusetts
Fitchburg | ELECTRIC AVE | 4555804 | 22 | 5 | Fitchburg Gas and Electric | 2020-12-03 |  | Yes | Verizon Massachusetts
Fitchburg | ELLIS ST | 4552357 | 16 | 18 | Fitchburg Gas and Electric | 2020-11-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ELLIS ST | 4416594 | 6 | 7 | Fitchburg Gas and Electric | 2020-08-31 |  | Yes | Verizon Massachusetts
Fitchburg | ELLIS ST | 4416666 | 7 | 8 | Fitchburg Gas and Electric | 2020-08-31 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | EUREKA ST | 4768899 | 1 | 1 | Fitchburg Gas and Electric | 2021-05-04 |  | Yes | Verizon Massachusetts
Fitchburg | EUREKA ST | 4711034 | 2 | 2 | Fitchburg Gas and Electric | 2021-05-12 |  | Yes | Verizon Massachusetts
Fitchburg | EXETER ST | 4825689 | 13 | 13 | Fitchburg Gas and Electric | 2021-03-17 |  | Yes | Verizon Massachusetts
Fitchburg | FAIRMOUNT ST | 4660854 | 39 | 36 | Fitchburg Gas and Electric | 2021-03-31 |  | Yes | Mass Technology Collaborative
Fitchburg | FAIRVIEW ST | 4660874 | 10 | 10 | Fitchburg Gas and Electric | 2021-04-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FAIRVIEW ST | 4818246 | 7 | 7 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Fitchburg | FAIRVIEW ST | 4737759 | 7 | 7 | Fitchburg Gas and Electric | 2021-04-08 |  | Yes | Verizon Massachusetts
Fitchburg | FAIRVIEW ST | 4731212 | 8 | 8 | Fitchburg Gas and Electric | 2021-04-08 |  | Yes | Verizon Massachusetts
Fitchburg | FARMER AVE | 4768904 | 1 | 1 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Verizon Massachusetts
Fitchburg | FARMER AVE | 4818301 | 2 | 2 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | FEDERAL ST | 4485062 | 4 | 4 | Fitchburg Gas and Electric | 2020-10-22 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FIFTH MASS TPKE | 4731218 | 5 | 19 | Fitchburg Gas and Electric | 2021-05-13 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FIFTH MASS TPKE | 4731224 | 2 | 22 | Fitchburg Gas and Electric | 2021-05-13 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FIFTH MASS TPKE | 4731261 | 26 | 49 | Fitchburg Gas and Electric | 2021-05-13 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Fisher Rd | 4325662 | 4 | 1 | Fitchburg Gas and Electric | 2020-02-10 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | Fisher Rd | 4325701 | 5 | 2 | Fitchburg Gas and Electric | 2020-02-10 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | FISHER RD | 3985501 | 10 | 47 | Fitchburg Gas and Electric | 2019-02-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Forest Park | 4448230 | 5 | 5 | Fitchburg Gas and Electric | 2020-10-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Forest Street | 4448239 | 6 | 4 | Fitchburg Gas and Electric | 2020-10-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FRANKLIN RD | 4612108 | 3 | 14 | Fitchburg Gas and Electric | 2021-02-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FRANKLIN RD | 4660911 | 9 | 20 | Fitchburg Gas and Electric | 2021-03-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | FRANKLIN RD | 4643333 | 14 | 25 | Fitchburg Gas and Electric | 2021-03-25 |  | Yes | Verizon Massachusetts
Fitchburg | Franklin Rd | 4751266 | 15 | 26 | Fitchburg Gas and Electric | 2021-05-12 |  | Yes | Verizon Massachusetts
Fitchburg | FRANKLIN RD | 4643314 | 17 | 28 | Fitchburg Gas and Electric | 2021-03-17 |  | Yes | Verizon Massachusetts
Fitchburg | FRANKLIN RD | 4643281 | 24 | 35 | Fitchburg Gas and Electric | 2021-03-22 |  | Yes | Verizon Massachusetts
Fitchburg | FRANKLIN RD | 4643346 | 30 | 41 | Fitchburg Gas and Electric | 2021-03-25 |  | Yes | Verizon Massachusetts
Fitchburg | FRANKLIN RD | 4450871 | 9 | 80 | Fitchburg Gas and Electric | 2020-09-24 |  | Yes | Verizon Massachusetts
Fitchburg | FREDETTE ST | 4623936 | 1 | 1 | Fitchburg Gas and Electric | 2021-03-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | GLORIA AVE | 4622428 | 5 | 5 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | GRANITE ST | 4505157 | 2 | 2 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | GRANITE ST | 4495284 | 5 | 5 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | GRANITE ST | 4495312 | 7 | 7 | Fitchburg Gas and Electric | 2020-11-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | GRANITE ST | 4495299 | 8 | 8 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | GRANITE ST | 4495319 | 9 | 9 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | HANNINGAN CT | 4817711 | 1 | 1 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Fitchburg | HAZEL ST | 4561862 | 3 | 3 | Fitchburg Gas and Electric | 2020-10-22 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HAZEL ST | 4559255 | 6 | 6 | Fitchburg Gas and Electric | 2021-01-21 |  | Yes | Non-participating 3rd Party Attacher - Massachusetts
Fitchburg | HAZEL ST | 4559258 | 7 | 7 | Fitchburg Gas and Electric | 2021-01-21 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HAZEL ST | 4559262 | 9 | 9 | Fitchburg Gas and Electric | 2021-01-20 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HEYWOOD ST | 4036801 | 8 | 10 | Fitchburg Gas and Electric | 2019-09-06 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HEYWOOD ST | 4060385 | 9 | 11 | Fitchburg Gas and Electric | 2019-09-19 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | HEYWOOD ST | 4070156 | 1 | 3 | Fitchburg Gas and Electric | 2019-10-09 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | HEYWOOD ST | 4551564 | 2 | 4 | Fitchburg Gas and Electric | 2020-10-28 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | HIGHVIEW ST | 4731274 | 3 | 3 | Fitchburg Gas and Electric | 2021-04-13 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HIGHVIEW ST | 4731282 | 6 | 6 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HIGHVIEW ST | 4660940 | 9 | 9 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HOLLYWOOD ST | 4622471 | 16 | 16 | Fitchburg Gas and Electric | 2021-03-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HOLLYWOOD ST | 4622478 | 18 | 18 | Fitchburg Gas and Electric | 2021-03-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HOLLYWOOD ST | 4622505 | 19 | 19 | Fitchburg Gas and Electric | 2021-03-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HOLLYWOOD ST | 4618751 | 3 | 3 | Fitchburg Gas and Electric | 2021-03-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HOLLYWOOD ST | 4618833 | 5 | 5 | Fitchburg Gas and Electric | 2021-03-01 |  | Yes | Verizon Massachusetts
Fitchburg | HOLLYWOOD ST | 4622455 | 6 | 6 | Fitchburg Gas and Electric | 2021-03-01 |  | Yes | Verizon Massachusetts
Fitchburg | HOLLYWOOD ST | 4622464 | 8 | 8 | Fitchburg Gas and Electric | 2021-03-01 |  | Yes | Verizon Massachusetts
Fitchburg | HOPE ST | 4647675 | 6 | 6 | Fitchburg Gas and Electric | 2021-03-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | HURD ST | 4818169 | 12 | 12 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | HURON ST | 4825721 | 4 | 4 | Fitchburg Gas and Electric | 2021-08-25 |  | No | Verizon Massachusetts
Fitchburg | INDUSTRIAL RD | 4554617 | 1 | 1 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | INDUSTRIAL RD | 4554635 | 2 | 2 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Comcast Massachusetts
Fitchburg | INDUSTRIAL RD | 4554644 | 3 | 3 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Comcast Massachusetts
Fitchburg | INDUSTRIAL RD | 4554654 | 4 | 4 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Verizon Massachusetts
Fitchburg | INDUSTRIAL RD | 4554666 | 5 | 5 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Verizon Massachusetts
Fitchburg | INDUSTRIAL RD | 4554680 | 6 | 6 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | INDUSTRIAL RD | 4554691 | 7 | 7 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | INDUSTRIAL RD | 4554700 | 9 | 9 | Fitchburg Gas and Electric | 2020-06-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | INSTITUTE ST | 4731469 | 3 | 3 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | INSTITUTE ST | 4731481 | 5 | 5 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Verizon Massachusetts
Fitchburg | JANET ST | 4485090 | 43-1 | 1 | Fitchburg Gas and Electric | 2020-10-21 |  | Yes | Verizon Massachusetts
Fitchburg | Kennedy Ave | 4464359 |  | 1 | Fitchburg Gas and Electric | 2020-10-20 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | KIMBALL RD | 4769095 | 1 | 1 | Fitchburg Gas and Electric | 2021-04-12 |  | Yes | Verizon Massachusetts
Fitchburg | KIMBALL RD | 4769150 | 10 | 10 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KIMBALL RD | 4662325 | 4 | 4 | Fitchburg Gas and Electric | 2021-04-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KIMBALL RD | 4769117 | 6 | 6 | Fitchburg Gas and Electric | 2021-04-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KIMBALL ST | 4555864 |  | 15 | Fitchburg Gas and Electric | 2021-01-18 |  | Yes | Comcast Massachusetts
Fitchburg | KIMBALL ST | 4625151 |  | 41 | Fitchburg Gas and Electric | 2021-02-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KING PL | 4825729 | 1 | 1 | Fitchburg Gas and Electric | 2021-03-25 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KING ST | 4250159 | 14 | 4 | Fitchburg Gas and Electric | 2020-02-20 |  | Yes | Fitchburg Gas and Electric
Fitchburg | KLONDIKE AVE | 4331949 | 10 | 10 | Fitchburg Gas and Electric | 2020-02-07 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LAUREL ST | 4551576 | 10 | 10 | Fitchburg Gas and Electric | 2020-11-25 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | LAUREL ST | 4505161 | 16 | 16 | Fitchburg Gas and Electric | 2020-11-20 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | LAUREL ST | 4485072 | 18 | 18 | Fitchburg Gas and Electric | 2020-10-24 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | LAUREL ST | 4505179 |  | 19 | Fitchburg Gas and Electric | 2020-10-21 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | LEIGHTON ST | 4801748 | 1 | 1 | Fitchburg Gas and Electric | 2021-05-03 |  | Yes | Verizon Massachusetts
Fitchburg | LEIGHTON ST | 4758803 | 110.5 | 12 | Fitchburg Gas and Electric | 2021-04-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LEIGHTON ST | 4661219 | 17 | 18 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LEIGHTON ST | 4825642 |  | 21 | Fitchburg Gas and Electric | 2021-09-08 |  | No | Fitchburg Gas and Electric
Fitchburg | LEROY ST | 4647815 | 2 | 2 | Fitchburg Gas and Electric | 2021-04-09 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LEROY ST | 4647767 | 3 | 3 | Fitchburg Gas and Electric | 2021-03-31 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LEROY ST | 4647732 | 5 | 5 | Fitchburg Gas and Electric | 2021-03-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LEYTE RD | 4055389 | 2 | 2 | Fitchburg Gas and Electric | 2019-09-23 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LIONEL AVE | 4622529 | 4 | 4 | Fitchburg Gas and Electric | 2021-03-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | LOVISA ST | 4505199 | 2 | 2 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | LOVISA ST | 4505209 | 3 | 3 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | LOVISA ST | 4505220 | 5 | 5 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | LYNN ST | 4801806 | 1 | 1 | Fitchburg Gas and Electric | 2021-08-09 |  | No | Verizon Massachusetts
Fitchburg | Madison St | 4818325 | 17 | 17 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | MADISON ST | 4559264 | 36 | 35 | Fitchburg Gas and Electric | 2020-12-02 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MARSHALL RD | 4345386 | 24 | 1 | Fitchburg Gas and Electric | 2020-02-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MARSHALL RD | 4825425 | 44 | 37 | Fitchburg Gas and Electric | 2021-09-08 |  | No | Fitchburg Gas and Electric
Fitchburg | Marshall Rd | 4818382 | 45 | 38 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Fitchburg | Marshall Rd | 4818334 | 46 | 39 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | MAYLAND ST | 4662118 | 5 | 5 | Fitchburg Gas and Electric | 2021-04-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MCDONALD AVE | 4662324 | 1 | 1 | Fitchburg Gas and Electric | 2021-03-16 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MCDONALD AVE | 4643301 | 2 | 2 | Fitchburg Gas and Electric | 2021-03-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MIAMI ST | 4618848 | 4 | 4 | Fitchburg Gas and Electric | 2021-03-09 |  | Yes | Verizon Massachusetts
Fitchburg | MILK ST | 4612118 | 14 | 14 | Fitchburg Gas and Electric | 2021-03-02 |  | Yes | Verizon Massachusetts
Fitchburg | Milk Street | 4448248 | 27 | 28 | Fitchburg Gas and Electric | 2020-08-25 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | Mount Elam Rd | 4816815 |  | 11 | Fitchburg Gas and Electric | 2021-08-31 | 2021-09-09 | No | Fitchburg Gas and Electric
Fitchburg | MT ELAM RD | 4485386 | 22 | 18 | Fitchburg Gas and Electric | 2020-10-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MT ELAM RD | 4485366 | 5 | 5 | Fitchburg Gas and Electric | 2020-10-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MT ELAM RD | 4555883 | 63 | 57 | Fitchburg Gas and Electric | 2020-10-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | MT ELAM RD | 4551595 | 76 | 70 | Fitchburg Gas and Electric | 2020-10-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | NASHUA ST | 4543606 | 9 | 9 | Fitchburg Gas and Electric | 2020-11-18 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | NEWTON ST | 4609372 | 7 | 3 | Fitchburg Gas and Electric | 2021-02-09 |  | Yes | Verizon Massachusetts
Fitchburg | NEWTONVILLE AVE | 4547008 | 1 | 1 | Fitchburg Gas and Electric | 2020-12-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | NORFOLK ST | 4612133 |  | 4-51 | Fitchburg Gas and Electric | 2021-02-18 |  | Yes | Fitchburg Gas and Electric
Fitchburg | NORMANDY RD | 4818471 | 3 | 3 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | NORMANDY RD | 4818331 | 4 | 4 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | OAK HILL LANE | 4758971 |  | 1-1 | Fitchburg Gas and Electric | 2021-04-13 |  | Yes | Fitchburg Gas and Electric
Fitchburg | OAK HILL RD | 4546971 | 30 | 21 | Fitchburg Gas and Electric | 2020-11-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | OAK HILL RD | 4546947 | 32 | 23 | Fitchburg Gas and Electric | 2020-11-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | OAK HILL RD | 4546920 | 36 | 27 | Fitchburg Gas and Electric | 2020-11-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | OAK HILL RD | 4647693 |  | 63 | Fitchburg Gas and Electric | 2021-03-16 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | OAK HILL RD | 4647712 | 94 | 85 | Fitchburg Gas and Electric | 2021-03-18 |  | Yes | Verizon Massachusetts
Fitchburg | OAKLAND ST | 4622556 | 2 | 2 | Fitchburg Gas and Electric | 2019-10-18 |  | Yes | Verizon Massachusetts
Fitchburg | OLD PRINCETON RD | 4731570 | 9 | 4 | Fitchburg Gas and Electric | 2021-05-17 |  | Yes | Fitchburg Gas and Electric
Fitchburg | OLIN DR | 4586905 |  | 2 | Fitchburg Gas and Electric | 2021-01-28 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | PALMER RD | 4731654 | 2 | 2 | Fitchburg Gas and Electric | 2021-05-18 |  | Yes | Verizon Massachusetts
Fitchburg | PALMER RD | 4731740 | 4 | 4 | Fitchburg Gas and Electric | 2021-05-18 |  | Yes | Comcast Massachusetts
Fitchburg | PARKER ST | 4618861 | 2 | 2 | Fitchburg Gas and Electric | 2021-03-09 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PARKER ST | 4618870 | 3 | 3 | Fitchburg Gas and Electric | 2021-03-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PARKER ST | 4618918 | 5 | 5 | Fitchburg Gas and Electric | 2021-03-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PAYSON ST | 4551617 | 5 | 5 | Fitchburg Gas and Electric | 2020-11-30 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PAYSON ST | 4546992 | 8 | 8 | Fitchburg Gas and Electric | 2020-11-30 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | Pearl St | 4818387 | 19 | 19 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | Pearl St | 4818340 | 25 | 25 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | Pearl St | 4818344 | 33 | 33 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | Pearl St | 4818407 | 34 | 34 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | Pearl St | 4818353 | 37 | 37 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Fitchburg | PEARL ST | 4324532 |  | 46 | Fitchburg Gas and Electric | 2020-02-08 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | PEARL ST | 4324542 | 45-1 | 47 | Fitchburg Gas and Electric | 2020-02-08 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | Pearl St | 4327655 |  | 49 | Fitchburg Gas and Electric | 2020-02-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PIERCE AVE | 4585914 | 1 | 1 | Fitchburg Gas and Electric | 2021-01-26 |  | Yes | Verizon Massachusetts
Fitchburg | PIERCE AVE | 4588914 | 22 | 8 | Fitchburg Gas and Electric | 2021-01-21 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | PLEASANTVIEW AVE | 4678776 | 2 | 2 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PLYMOUTH ST | 4678826 | 2 | 2 | Fitchburg Gas and Electric | 2021-04-07 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PRATT RD | 4705999 |  | 26-3 | Fitchburg Gas and Electric | 2021-05-17 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PRATT ST | 4600287 | 3 | 16 | Fitchburg Gas and Electric | 2021-02-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PRATT ST | 4825671 | 4 | 24 | Fitchburg Gas and Electric | 2021-09-08 |  | No | Fitchburg Gas and Electric
Fitchburg | PRATT ST | 4613700 | 5 | 5 | Fitchburg Gas and Electric | 2021-03-05 |  | Yes | Verizon Massachusetts
Fitchburg | PRINCETON RD | 4769261 |  | 3-51 | Fitchburg Gas and Electric | 2021-05-17 |  | Yes | Fitchburg Gas and Electric
Fitchburg | PROVIDENCE ST | 4613715 | 1 | 1 | Fitchburg Gas and Electric | 2021-02-18 |  | Yes | Verizon Massachusetts
Fitchburg | RALEIGH AVE | 4527375 | 1 | 1 | Fitchburg Gas and Electric | 2020-11-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | REINGOLD AVE | 4555898 | 15 | 6 | Fitchburg Gas and Electric | 2020-11-30 |  | Yes | Fitchburg Gas and Electric
Fitchburg | REINGOLD AVE | 4543639 | 21 | 7 | Fitchburg Gas and Electric | 2020-11-30 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RICHARDSON RD | 3985241 | 6 | 6 | Fitchburg Gas and Electric | 2019-02-27 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | RICHARDSON RD | 3985277 | 7 | 7 | Fitchburg Gas and Electric | 2019-02-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RICHARDSON RD | 3985284 | 8 | 8 | Fitchburg Gas and Electric | 2019-02-27 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812408 | P7 | 14 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812414 | 8 | 15 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812419 | 9 | 16 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812423 | 10 | 17 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812426 | 11 | 18 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812428 | 12 | 19 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812429 | 13 | 20 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812432 | 14 | 21 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812435 | 15 | 22 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Verizon Massachusetts
Fitchburg | Rindge Rd | 4812438 | 16 | 23 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Verizon Massachusetts
Fitchburg | Rindge Rd | 4812443 | 17 | 24 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812446 | 19 | 25 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812447 | 20 | 26 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812454 | 21 | 27 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812457 | 22 | 28 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Rindge Rd | 4812460 | 24 | 29 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Verizon Massachusetts
Fitchburg | Rindge Rd | 4812463 | 25 | 30 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Verizon Massachusetts
Fitchburg | Rindge Rd | 4812467 | 26 | 31 | Fitchburg Gas and Electric | 2021-05-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4722246 |  | 30-2 | Fitchburg Gas and Electric | 2021-05-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4722254 |  | 34-1 | Fitchburg Gas and Electric | 2021-04-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4722264 |  | 40 | Fitchburg Gas and Electric | 2021-04-08 | 2021-06-22 | No | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4722271 |  | 44 | Fitchburg Gas and Electric | 2021-04-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4450896 |  | 46 | Fitchburg Gas and Electric | 2020-09-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4102379 |  | 49 | Fitchburg Gas and Electric | 2019-10-10 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4314020 |  | 49 | Fitchburg Gas and Electric | 2020-05-10 | 2021-05-19 | No | Fitchburg Gas and Electric
Fitchburg | RIVER ST | 4722277 |  | 49-1 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RODIMAN AVE | 4527438 | 13 | 13 | Fitchburg Gas and Electric | 2020-12-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RODIMAN AVE | 4527433 | 7 | 7 | Fitchburg Gas and Electric | 2020-11-24 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | ROLLSTONE RD | 4737873 | 92 | 34 | Fitchburg Gas and Electric | 2021-06-24 |  | Yes | Verizon Massachusetts
Fitchburg | ROLLSTONE ST | 4543684 | 12 | 14-51 | Fitchburg Gas and Electric | 2020-12-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ROLLSTONE ST | 4731331 | 20 | 21 | Fitchburg Gas and Electric | 2021-06-23 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ROLLSTONE ST | 4647835 | 84-1 | 21-51 | Fitchburg Gas and Electric | 2021-04-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ROLLSTONE ST | 4555912 | 37 | 38 | Fitchburg Gas and Electric | 2020-12-03 |  | Yes | Verizon Massachusetts
Fitchburg | ROLLSTONE ST | 4555932 | 47 | 49 | Fitchburg Gas and Electric | 2020-12-03 |  | Yes | Verizon Massachusetts
Fitchburg | RONALD ST | 4618938 | 3 | 3 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | RONALD ST | 4618959 | 4 | 4 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ROOSEVELT ST | 4722478 | 3 | 3 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ROOSEVELT ST | 4722491 | 6 | 6 | Fitchburg Gas and Electric | 2021-04-28 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SALEM ST | 4551715 |  | 1 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SALEM ST | 4551749 | 3 | 3 | Fitchburg Gas and Electric | 2020-11-18 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SAMUEL ST | 4812488 | 1 | 1 | Fitchburg Gas and Electric | 2021-08-09 |  | No | Verizon Massachusetts
Fitchburg | Second St | 4371484 | 2 | 2 | Fitchburg Gas and Electric | 2020-05-19 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | Second St | 4371499 | 3 | 3 | Fitchburg Gas and Electric | 2020-05-19 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SENECA ST | 4812499 | 5 | 5 | Fitchburg Gas and Electric | 2021-08-05 |  | No | Fitchburg Gas and Electric
Fitchburg | SENNA RD | 4759094 | 2 | 2 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Verizon Massachusetts
Fitchburg | SENNA RD | 4662065 | 6 | 6 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SENNA RD | 4662345 | 7 | 7 | Fitchburg Gas and Electric | 2021-04-14 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4609395 | 11 | 19 | Fitchburg Gas and Electric | 2021-02-18 |  | Yes | Verizon Massachusetts
Fitchburg | SHEA ST | 4618972 |  | 20-1 | Fitchburg Gas and Electric | 2021-03-08 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4618994 | 18 | 25 | Fitchburg Gas and Electric | 2021-03-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619009 | 20 | 28 | Fitchburg Gas and Electric | 2021-03-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619014 | 22 | 30 | Fitchburg Gas and Electric | 2021-03-08 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619025 | 22-1 | 30-1 | Fitchburg Gas and Electric | 2021-03-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619050 | 26 | 34 | Fitchburg Gas and Electric | 2021-03-08 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619075 | 28 | 36 | Fitchburg Gas and Electric | 2021-03-09 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHEA ST | 4619040 | 29 | 37 | Fitchburg Gas and Electric | 2021-03-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHELDON RD | 4812505 | 33 | 33 | Fitchburg Gas and Electric | 2021-04-20 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHELDON RD | 4884200 | 40 | 40 | Fitchburg Gas and Electric | 2021-04-20 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SHELDON RD | 4812516 | 40 | 40-53 | Fitchburg Gas and Electric | 2021-04-20 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4609385 |  | 11 | Fitchburg Gas and Electric | 2020-11-05 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4543749 |  | 1-2 | Fitchburg Gas and Electric | 2020-12-02 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4543738 |  | 1-3 | Fitchburg Gas and Electric | 2020-11-04 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | South St | 4809683 |  | 32 | Fitchburg Gas and Electric | 2021-08-26 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4738015 |  | 36 | Fitchburg Gas and Electric | 2021-06-25 | 2021-07-08 | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4586936 | 49.5-1 | 61-51 | Fitchburg Gas and Electric | 2021-02-04 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4818389 |  | 82 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Fitchburg | SOUTH ST | 4555945 | 9 | 9 | Fitchburg Gas and Electric | 2020-11-05 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SPRAGUE ST | 4678901 |  | 1 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ST ANDREW ST | 4551669 | 7 | 7 | Fitchburg Gas and Electric | 2020-11-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ST CAMILLE ST | 4662339 | 18 | 2 | Fitchburg Gas and Electric | 2021-04-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ST JOSEPH AVE | 4613725 | 19 | 16 | Fitchburg Gas and Electric | 2021-02-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ST JOSEPH AVE | 4803056 |  | 5 | Fitchburg Gas and Electric | 2021-07-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | ST MARTIN ST | 4588822 |  | 6 | Fitchburg Gas and Electric | 2021-01-26 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | ST MARTIN ST | 4588814 |  | 7 | Fitchburg Gas and Electric | 2021-01-28 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | ST MARTIN ST | 4600305 | 8 | 8 | Fitchburg Gas and Electric | 2021-01-26 |  | Yes | Fitchburg Gas and Electric
Fitchburg | STEVENS RD | 4554708 |  | 1 | Fitchburg Gas and Electric | 2020-06-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | STICKNEY RD | 4678931 | 20 | 20 | Fitchburg Gas and Electric | 2021-04-19 |  | Yes | Fitchburg Gas and Electric
Fitchburg | STICKNEY RD | 4678914 | 21 | 21 | Fitchburg Gas and Electric | 2021-04-19 |  | Yes | Fitchburg Gas and Electric
Fitchburg | STICKNEY RD | 4678983 | 24 | 24 | Fitchburg Gas and Electric | 2021-04-19 |  | Yes | Fitchburg Gas and Electric
Fitchburg | STICKNEY RD | 4678994 | 25 | 25 | Fitchburg Gas and Electric | 2021-04-19 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SUNRISE AVE | 4731757 | 3 | 3 | Fitchburg Gas and Electric | 2021-05-03 |  | Yes | Fitchburg Gas and Electric
Fitchburg | SWAN AVE | 4485413 | 1 | 1 | Fitchburg Gas and Electric | 2020-10-31 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SWAN AVE | 4558188 | 2 | 2 | Fitchburg Gas and Electric | 2020-10-31 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | SWAN AVE | 4527570 | 3 | 3 | Fitchburg Gas and Electric | 2020-11-04 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | TEMPLE ST | 4812529 | 4 | 4 | Fitchburg Gas and Electric | 2021-04-27 |  | Yes | Fitchburg Gas and Electric
Fitchburg | THERESA ST | 4623947 | 23 | 13 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | THERESA ST | 4623957 | 24 | 14 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | THERESA ST | 4647611 | 33 | 24 | Fitchburg Gas and Electric | 2021-03-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | TOWNSEND ST | 4358093 | 45 | 35 | Fitchburg Gas and Electric | 2020-04-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | VALDALIA AVE | 4527443 | 5 | 5 | Fitchburg Gas and Electric | 2020-12-01 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | Valley St | 4382500 | 3 | 3 | Fitchburg Gas and Electric | 2020-04-29 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | Valley St | 4393524 | 8 | 8 | Fitchburg Gas and Electric | 2020-03-31 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | VERNON COURT | 4735518 | 1 | 1 | Fitchburg Gas and Electric | 2021-05-12 |  | Yes | Fitchburg Gas and Electric
Fitchburg | VERNON ST | 4691562 | 3 | 3 | Fitchburg Gas and Electric | 2021-05-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | VERNON ST | 4731797 | 5 | 5 | Fitchburg Gas and Electric | 2021-05-05 | 2021-09-01 | No | Fitchburg Gas and Electric
Fitchburg | WACHUSETT ST | 4711048 | 7 | 7 | Fitchburg Gas and Electric | 2021-05-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WALLACE RD | 4314037 |  | 14 | Fitchburg Gas and Electric | 2020-05-10 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | Wallace Rd | 4818418 |  | 8 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Fitchburg | WALLACE RD | 4731803 |  | 9 | Fitchburg Gas and Electric | 2021-05-04 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WALNUT ST | 4547004 | 12 | 12 | Fitchburg Gas and Electric | 2020-12-01 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WALTON ST | 4551695 |  | 1 | Fitchburg Gas and Electric | 2020-11-17 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WALTON ST | 4552391 |  | 23 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WALTON ST | 4495413 | 3 | 4 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WALTON ST | 4495472 | 4 | 6 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WALTON ST | 4495448 | 4.5 | 7 | Fitchburg Gas and Electric | 2020-11-17 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WANOOSNOC RD | 4283169 | 17 | 17 | Fitchburg Gas and Electric | 2020-04-29 | 2021-05-14 | No | Fitchburg Gas and Electric
Fitchburg | WANOOSNOC RD | 4283203 | 26 | 26 | Fitchburg Gas and Electric | 2020-04-20 | 2021-05-13 | No | Fitchburg Gas and Electric
Fitchburg | WANOOSNOC RD | 4826864 | 33 | 32 | Fitchburg Gas and Electric | 2021-09-09 |  | No | Fibertech Networks (Crown Castle)
Fitchburg | WANOOSNOC RD | 4826724 | 32 | 33 | Fitchburg Gas and Electric | 2021-09-09 |  | No | Fibertech Networks (Crown Castle)
Fitchburg | WANOOSNOC RD | 4600328 | 37 | 36 | Fitchburg Gas and Electric | 2021-02-08 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | WARD ST | 4722322 | 5 | 5 | Fitchburg Gas and Electric | 2021-05-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WARD ST | 4732163 | 6 | 6 | Fitchburg Gas and Electric | 2021-05-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WARNER AVE | 4722503 | 6 | 6 | Fitchburg Gas and Electric | 2021-05-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WARREN ST | 3424410 | 10 | 10 | Fitchburg Gas and Electric | 2018-02-12 |  | Yes | Comcast Massachusetts
Fitchburg | Water St | 4435560 | 36 | 14 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | Water St | 4434783 | 27 | 3 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | Water St | 4434814 | 27.5 | 4 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | Water St | 4434821 | 28 | 5 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | Water St | 4434922 | 28-1 | 5-1 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fitchburg Gas and Electric
Fitchburg | Water St | 4435505 | 29 | 6 | Fitchburg Gas and Electric | 2020-07-25 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | Water St | 4435546 | 31 | 8 | Fitchburg Gas and Electric | 2020-09-16 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | WEST ST | 3278899 | 57 | 10 | Verizon Massachusetts | 2019-03-15 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 4732195 | 42 | 41 | Fitchburg Gas and Electric | 2021-05-03 |  | Yes | Verizon Massachusetts
Fitchburg | WESTMINSTER HILL RD | 4812541 | 53 | 53 | Fitchburg Gas and Electric | 2021-07-24 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 4769282 | 60 | 58 | Fitchburg Gas and Electric | 2021-05-18 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 4732690 | 60 | 60 | Fitchburg Gas and Electric | 2021-04-29 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 3278871 | 76 | 73 | Verizon Massachusetts | 2019-03-18 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 4732699 | 99 | 95 | Fitchburg Gas and Electric | 2021-05-05 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER HILL RD | 4759150 | 100 | 96 | Fitchburg Gas and Electric | 2021-05-06 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER ST | 4826669 | 74 | 2 | Fitchburg Gas and Electric | 2021-09-09 |  | No | Fibertech Networks (Crown Castle)
Fitchburg | WESTMINSTER ST | 4711054 | 23 | 23 | Fitchburg Gas and Electric | 2021-05-06 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | WESTMINSTER ST | 4711073 |  | 28-2-2 | Fitchburg Gas and Electric | 2021-05-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER ST | 4691105 |  | 33 | Fitchburg Gas and Electric | 2021-05-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER ST | 4711132 |  | 41 | Fitchburg Gas and Electric | 2021-05-10 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER ST | 4711118 |  | 44-51 | Fitchburg Gas and Electric | 2021-05-11 |  | Yes | Fitchburg Gas and Electric
Fitchburg | WESTMINSTER ST | 4554513 | 56 | 76 | Fitchburg Gas and Electric | 2020-06-05 |  | Yes | Fibertech Networks (Crown Castle)
Fitchburg | WILLIAM ST | 4820286 | 3 | 3 | Fitchburg Gas and Electric | 2021-09-02 |  | No | Verizon Massachusetts
Fitchburg | WILLIAMS ST | 4555955 | 5 | 5 | Fitchburg Gas and Electric | 2020-11-16 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WILSON ST | 4812546 | 2-1 | 2-1 | Fitchburg Gas and Electric | 2021-08-04 |  | No | Fitchburg Gas and Electric
Fitchburg | WINCH ST | 4485423 | 1 | 1 | Fitchburg Gas and Electric | 2020-10-29 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WINCH ST | 4485431 | 3 | 3 | Fitchburg Gas and Electric | 2020-10-29 | 2021-05-12 | No | Fitchburg Gas and Electric
Fitchburg | WORCESTER ST | 4609422 | 3 | 3 | Fitchburg Gas and Electric | 2021-02-04 | 2021-09-01 | No | Fitchburg Gas and Electric
Lunenburg | Asplund Dr | 4435576 | 1 | 1 | Fitchburg Gas and Electric | 2020-09-24 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | Boucher Rd | 4835876 |  | 7 | Fitchburg Gas and Electric | 2021-09-17 |  | No | Verizon Massachusetts
Lunenburg | Chase Rd | 4448083 | 12-1 | 12-1 | Fitchburg Gas and Electric | 2020-08-26 | 2021-05-25 | No | Fitchburg Gas and Electric
Lunenburg | Electric Ave | 4812201 | 14 | 14 | Fitchburg Gas and Electric | 2021-04-01 |  | Yes | Verizon Massachusetts
Lunenburg | ELM ST | 4605615 |  | 13 | Fitchburg Gas and Electric | 2021-02-27 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | ELM ST | 4022602 | 9 | 7 | Fitchburg Gas and Electric | 2019-07-07 | 2021-05-25 | No | Fitchburg Gas and Electric
Lunenburg | FLAT HILL RD | 4470779 | 25 | 12 | Fitchburg Gas and Electric | 2020-09-23 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | FLAT HILL RD | 4470788 | 27 | 14 | Fitchburg Gas and Electric | 2020-09-23 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | FLAT HILL RD | 4472229 | 31 | 18 | Fitchburg Gas and Electric | 2020-09-23 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | FLAT HILL RD | 4466361 | 33 | 20 | Fitchburg Gas and Electric | 2020-09-22 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | FLAT HILL RD | 4818257 | 33 | 20 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | FLAT HILL RD | 4466363 | 34 | 21 | Fitchburg Gas and Electric | 2020-09-22 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Flat Hill Rd | 4818263 | 13 | 27 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | FLAT HILL RD | 4466354 | 52 | 38 | Fitchburg Gas and Electric | 2020-09-21 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Flat Hill Rd | 4463480 | 65 | 50 | Fitchburg Gas and Electric | 2020-09-21 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Flat Hill Rd | 4463522 | 65 | 51 | Fitchburg Gas and Electric | 2020-09-21 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Flat Hill Rd | 4463536 | 66 | 52 | Fitchburg Gas and Electric | 2020-09-21 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | Flat Hill Rd | 4463578 | 67 | 53 | Fitchburg Gas and Electric | 2020-09-21 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | FLYNN RD | 4818286 | 2 | 2 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Lunenburg | FLYNN RD | 4559239 | 8 | 8 | Fitchburg Gas and Electric | 2021-01-25 |  | Yes | Verizon Massachusetts
Lunenburg | ISLAND RD | 4060640 | 7 | 7 | Fitchburg Gas and Electric | 2019-10-02 |  | Yes | Fitchburg Gas and Electric
Lunenburg | KILBURN ST | 4551832 | 21 | 3 | Fitchburg Gas and Electric | 2020-01-13 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | LANCASTER AVE | 4827183 | 1 | 173 | Fitchburg Gas and Electric | 2021-09-09 |  | No | Fitchburg Gas and Electric
Lunenburg | LANCASTER AVE | 4818129 | 23 | 25 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Lunenburg | LANCASTER AVE | 4818184 | 28 | 30 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | LANCASTER AVE | 4414748 | 52 | 50 | Fitchburg Gas and Electric | 2020-05-21 |  | Yes | Fitchburg Gas and Electric
Lunenburg | LEOMINSTER RD | 4485455 | 50 | 38 | Fitchburg Gas and Electric | 2018-10-31 |  | Yes | Comcast Massachusetts
Lunenburg | LEOMINSTER SHIRLEY RD | 4818392 | 86 | 10 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | LEOMINSTER SHIRLEY RD | 4818343 | 19 | 43 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Lunenburg | LEOMINSTER SHIRLEY RD | 3680311 |  | 5 | Fitchburg Gas and Electric | 2018-09-07 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | LEOMINSTER SHIRLEY RD | 3668142 | 85 | 9 | Fitchburg Gas and Electric | 2018-09-05 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | leominster-shirley rd | 2538354 | 27-1 | 35-51 | Fitchburg Gas and Electric | 2015-01-01 |  | Yes | Fitchburg Gas and Electric
Lunenburg | MASS AVE | 4010078 | 115 | 119 | Fitchburg Gas and Electric | 2019-07-31 |  | Yes | Lunenburg Fire Department
Lunenburg | mass ave | 2535951 | 151 | 151 | Fitchburg Gas and Electric | 2015-01-01 | 2021-05-17 | No | Fitchburg Gas and Electric
Lunenburg | MASS AVE | 4014267 | 82-2 | 83 | Fitchburg Gas and Electric | 2019-07-31 |  | Yes | Verizon Massachusetts
Lunenburg | MASS AVE | 4055557 | 86 | 86 | Fitchburg Gas and Electric | 2019-09-22 |  | Yes | Fitchburg Gas and Electric
Lunenburg | Massachusetts Ave | 4448108 | 101-1 | 101-51 | Fitchburg Gas and Electric | 2020-09-22 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | Massachusetts Ave | 4448117 | 101-2 | 101-52 | Fitchburg Gas and Electric | 2020-09-22 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | Massachusetts Ave | 3102136 | 113 | 117 | Fitchburg Gas and Electric | 2016-06-12 |  | Yes | Mass Technology Collaborative
Lunenburg | Massachusetts Ave | 4448096 | 133-4 | 137-54 | Fitchburg Gas and Electric | 2020-08-25 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | MASSACHUSETTS AVE | 4818458 | 155 | 155 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Lunenburg | MASSACHUSETTS AVE | 4818434 | 78 | 78 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | New West Townsend Rd | 4779193 | 106 | 44 | Fitchburg Gas and Electric | 2021-08-01 | 2021-08-10 | No | Fitchburg Gas and Electric
Lunenburg | NORTHFIELD RD | 4324568 | 1 | 103 | Fitchburg Gas and Electric | 2020-02-10 | 2021-05-25 | No | Fitchburg Gas and Electric
Lunenburg | NORTHFIELD RD | 4324573 | 2 | 104 | Fitchburg Gas and Electric | 2020-02-10 | 2021-05-25 | No | Fitchburg Gas and Electric
Lunenburg | NORTHFIELD RD | 4324580 | 3 | 105 | Fitchburg Gas and Electric | 2020-02-10 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | NORTHFIELD RD | 4817769 |  | 83 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Lunenburg | Northfield Rd | 4818277 |  | 83-3 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Fitchburg Gas and Electric
Lunenburg | Northfield Rd | 4818290 | 2195-1 | 83-51 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Lunenburg | NORTHFIELD RD | 4397420 |  | 83-52 | Fitchburg Gas and Electric | 2020-08-03 | 2021-10-11 | No | Fitchburg Gas and Electric
Lunenburg | NORTHFIELD RD | 2507774 | 2212 | T-2212 , E-96 | Verizon Massachusetts | 2020-03-15 |  | Yes | Fitchburg Gas and Electric
Lunenburg | Page St | 4329262 | 18 | 18 | Fitchburg Gas and Electric | 2020-06-06 | 2021-06-01 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464018 | 1 | 71 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464030 | 2 | 72 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464037 | 4 | 74 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464039 | 5 | 75 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464068 | 9 | 79 | Fitchburg Gas and Electric | 2020-08-10 |  | Yes | Verizon Massachusetts
Lunenburg | Page St | 4464075 | 10 | 80 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464084 | 11 | 81 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464099 | 12 | 82 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464183 | 13 | 83 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464198 | 15 | 85 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Page St | 4464230 | 16 | 86 | Fitchburg Gas and Electric | 2020-08-10 | 2021-05-20 | No | Fitchburg Gas and Electric
Lunenburg | Reservoir Rd | 4419201 | 96 | 103 | Fitchburg Gas and Electric | 2020-09-11 |  | Yes | Fitchburg Gas and Electric
Lunenburg | RESERVOIR RD | 3600684 |  | 70-2-1 | Fitchburg Gas and Electric | 2018-06-25 |  | Yes | Fitchburg Gas and Electric
Lunenburg | Reservoir Rd | 4417913 | 71 | 74 | Fitchburg Gas and Electric | 2020-09-11 |  | Yes | Fitchburg Gas and Electric
Lunenburg | Reservoir Rd | 4418380 | 83 | 90 | Fitchburg Gas and Electric | 2020-09-11 | 2021-05-21 | No | Fitchburg Gas and Electric
Lunenburg | RESERVOIR RD | 4819485 | 95 | 95 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Lunenburg | SOUTH ROW RD | 4495266 | 9 | 20 | Fitchburg Gas and Electric | 2020-11-12 | 2021-05-25 | No | Fitchburg Gas and Electric
Lunenburg | SOUTH ROW RD | 4495277 | 48 | 28 | Fitchburg Gas and Electric | 2020-11-12 |  | Yes | Comcast Massachusetts
Lunenburg | SOUTH ROW RD | 4495285 | 51 | 31 | Fitchburg Gas and Electric | 2020-11-12 |  | Yes | Comcast Massachusetts
Lunenburg | SOUTH ROW RD | 4495291 | 10 | 43 | Fitchburg Gas and Electric | 2020-11-12 |  | Yes | Verizon Massachusetts
Lunenburg | SOUTH ROW RD | 4495298 |  | 50 | Fitchburg Gas and Electric | 2020-11-12 |  | Yes | Fitchburg Gas and Electric
Lunenburg | SUNSET LN/HARRIS AVE | 3480939 |  | 4 | Fitchburg Gas and Electric | 2018-03-01 |  | Yes | Fitchburg Gas and Electric
Lunenburg | TOWNSEND HARBOR RD | 4663866 | 19 | 49 | Fitchburg Gas and Electric | 2021-04-23 |  | Yes | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102463 |  | 13 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4314031 |  | 13 | Fitchburg Gas and Electric | 2020-05-10 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102523 |  | 14 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102543 |  | 15 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102552 |  | 16 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102562 |  | 17 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102571 |  | 18 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102581 |  | 19 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102587 |  | 20 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102601 |  | 21 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102871 |  | 22 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102925 |  | 23 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102931 |  | 24 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WALLACE RD | 4102937 |  | 25 | Fitchburg Gas and Electric | 2019-09-12 | 2021-05-12 | No | Fitchburg Gas and Electric
Lunenburg | WHALOM RD | 3476347 | 12 | 47 | Fitchburg Gas and Electric | 2018-03-23 |  | Yes | Fitchburg Gas and Electric
Lunenburg | WHALOM RD | 4397452 | 61 | 5 | Fitchburg Gas and Electric | 2020-08-03 | 2021-06-01 | No | Fitchburg Gas and Electric
Townsend | BAILEY RD | 4819500 | 4 | 4 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Townsend | DUDLEY RD | 4070211 | 15 | 16 | Fitchburg Gas and Electric | 2019-10-08 |  | Yes | Townsend Fire Department
Townsend | FITCHBURG RD | 4827075 |  | 26 | Fitchburg Gas and Electric | 2021-09-09 |  | No | Comcast Massachusetts
Townsend | FITCHBURG RD | 4817720 | 52 | 94 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Townsend | GILCHRIST RD | 4819569 | 13 | 13 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Townsend | LUNENBURG RD | 4711140 | 72-1 | 14-51 | Fitchburg Gas and Electric | 2020-05-07 |  | Yes | Comcast Massachusetts
Townsend | LUNENBURG RD | 4819580 | 81 | 24 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Townsend | Lunenburg Rd | 4361464 | 88 | 31 | Fitchburg Gas and Electric | 2020-07-01 |  | Yes | Fitchburg Gas and Electric
Townsend | MAIN ST | 4680312 |  | 170 | Fitchburg Gas and Electric | 2021-05-07 | 2021-09-01 | No | Fitchburg Gas and Electric
Townsend | MAIN ST | 3420432 | 78 | 199 | Fitchburg Gas and Electric | 2018-02-02 |  | Yes | Townsend Fire Department
Townsend | MAIN ST | 4005413 | 98 | 219 | Fitchburg Gas and Electric | 2019-08-05 |  | Yes | Townsend Fire Department
Townsend | MAIN ST | 4005722 |  | 224 | Fitchburg Gas and Electric | 2019-08-05 |  | Yes | Townsend Fire Department
Townsend | MASON RD | 4543583 | 17 | 8 | Fitchburg Gas and Electric | 2021-01-15 |  | Yes | Comcast Massachusetts
Townsend | NORTH END RD | 4588906 | 74 | 31 | Fitchburg Gas and Electric | 2021-02-11 |  | Yes | Comcast Massachusetts
Townsend | NORTH END RD | 4588892 | 83 | 40 | Fitchburg Gas and Electric | 2021-02-11 |  | Yes | Comcast Massachusetts
Townsend | North End Rd | 4818185 | 6 | 5 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Comcast Massachusetts
Townsend | NORTH END RD | 4817603 | 98 | 55 | Fitchburg Gas and Electric | 2021-09-01 |  | No | Verizon Massachusetts
Townsend | OAK ST | 4178183 | 2 | 2 | Fitchburg Gas and Electric | 2020-02-01 |  | Yes | Fitchburg Gas and Electric
Townsend | TURNER RD | 4798673 | 1 | 1 | Fitchburg Gas and Electric | 2021-07-27 | 2021-08-26 | No | Fitchburg Gas and Electric
Townsend | TURNER RD | 4798692 | 25 | 24 | Fitchburg Gas and Electric | 2021-08-17 |  | No | Fitchburg Gas and Electric