## Notes and Resources
Workbook Overview |  |  | Questions and feedback: email kschultz@synapse-energy.com
Last updated:
2024-12-10
Purpose
This workbook is intended to be a central location for keeping track of dates for GMAC and related activities.
It is intended to contain the master list of dates, which will be kept updated and can be referenced to update other summaries/ materials, such as the GMAC website.
Calendar tab
This tab displays key meetings and processes for the GMAC and related actvities
Users can toggle between Weekly, Monthly, or Quarterly views by selecting a drop-down in cell C2.
Resources
Useful Links |  | [Under development]
GMAC website
LTSPP website
DPU file room
Docket numbers |  | [under development]
| Number | Description

## Calendar
NOTE: DO NOT DRAG FORMULAS DOWN; FORMULAS ARE NOT THE SAME FOR ALL ROWS
View Selection >> | Weekly
|  |  |  | 2024 |  |  |  |  | 2025 | [51 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028 | [51 empty] | 2029
|  |  |  | 2024-12-02 | [8 empty] | 2025-02-03 |  |  |  | 2025-03-03 |  |  |  |  | 2025-04-07 |  |  |  | 2025-05-05 |  |  |  | 2025-06-02 |  |  |  |  | 2025-07-07 |  |  |  | 2025-08-04 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-06 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 | [8 empty] | 2026-02-02 |  |  |  | 2026-03-02 |  |  |  |  | 2026-04-06 |  |  |  | 2026-05-04 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  |  | 2026-12-07 | [7 empty] | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  |  | 2027-06-07 |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  |  | 2027-09-06 |  |  |  | 2027-10-04 |  |  |  | 2027-11-01 |  |  |  |  | 2027-12-06 | [8 empty] | 2028-02-07 |  |  |  | 2028-03-06 |  |  |  | 2028-04-03 |  |  |  | 2028-05-01 |  |  |  |  | 2028-06-05 |  |  |  | 2028-07-03 |  |  |  |  | 2028-08-07 |  |  |  | 2028-09-04 |  |  |  | 2028-10-02 |  |  |  |  | 2028-11-06 |  |  |  | 2028-12-04
| START DATE | END DATE | time axis 2024-12-02 to 2029-01-29
|  |  | Description | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029
GMAC | 2024-10-22 | 2026-01-07 | bar: 2024-12-02 to 2026-01-05
2025 planning | 2024-10-22 | 2025-01-10 | bar: 2024-12-02 to 2025-01-06
GMAC Meetings | Monthly | Monthly | GMAC meetings 3rd Wednesday of every month | bar: 2024-12-16; 2025-01-27; 2025-02-24; 2025-03-24; 2025-04-28; 2025-05-26; 2025-06-23; 2025-07-28; 2025-08-25; 2025-09-15; 2025-10-27; 2026-01-05
Dec 2024 Meeting | 2024-12-17 | 2024-12-17 | GMAC meeting | bar: 2024-12-16
Jan 2025 meeting | 2025-01-29 | 2025-01-29 | Cost recovery | bar: 2025-01-27
Feb 2025 meeting | 2025-02-26 | 2025-02-26 | Reporting: existing reports, ESMP metrics | bar: 2025-02-24
March 2025 meeting | 2025-03-26 | 2025-03-26 | Reporting: ESMP metrics, biannual report content | bar: 2025-03-24
April 2025 meeting | 2025-04-30 | 2025-04-30 | System Reliability and Resilience | bar: 2025-04-28
May 2025 meeting | 2025-05-28 | 2025-05-28 | Proactive Grid Planning (LTSPP Updates) | bar: 2025-05-26
June 2025 meeting | 2025-06-25 | 2025-06-25 | Integrated Energy Planning | bar: 2025-06-23
July 2025 meeting | 2025-07-30 | 2025-07-30 | Equity in Grid Planning | bar: 2025-07-28
Aug 2025 meeting | 2025-08-27 | 2025-08-27 | GMAC meeting - date is placeholder - discussion topic tbd | bar: 2025-08-25
Sept 2025 meeting | 2025-09-16 | 2025-09-16 | NOTE this is a Tuesday - discussion topic tbd | bar: 2025-09-15
Oct 2025 meeting | 2025-10-29 | 2025-10-29 | GMAC meeting - date is placeholder - discussion topic tbd | bar: 2025-10-27
Nov 2025 meeting |  |  | Skip/TBD?
Dec 2025 meeting | 2025-12-03 | 2025-12-03 | GMAC meeting - date is placeholder - discussion topic tbd
Jan 2026 meeting | 2026-01-07 | 2026-01-07 | GMAC meeting - date is placeholder - discussion topic tbd | bar: 2026-01-05
Excom Meetings | Bi-monthly | Bi-monthly | ExCom meetings on Thursdays 9:30-10:30 every other motnh | bar: 2025-02-24; 2025-04-21; 2025-06-02; 2025-08-11; 2025-10-06; 2025-12-15
Feb 2025 meeting | 2025-02-26 | 2025-02-26 | bar: 2025-02-24
April 2025 meeting | 2025-04-24 | 2025-04-24 | bar: 2025-04-21
June 2025 meeting | 2025-06-05 | 2025-06-05 | bar: 2025-06-02
Aug 2025 meeting | 2025-08-14 | 2025-08-14 | bar: 2025-08-11
Oct 2025 meeting | 2025-10-09 | 2025-10-09 | bar: 2025-10-06
Dec 2025 meeting | 2025-12-18 | 2025-12-18 | bar: 2025-12-15
EWG meetings | Quarterly | Quarterly | Placeholder dates Equity Working Group meetings are 1.5 hours quarterly | bar: 2025-02-03; 2025-03-31; 2025-07-07; 2025-09-29
Feb 2025 meeting | 2025-02-07 | 2025-02-07 | Dates are placeholders | bar: 2025-02-03
April 2025 meeting | 2025-04-04 | 2025-04-04 | Dates are placeholders | bar: 2025-03-31
July 2025 meeting | 2025-07-11 | 2025-07-11 | Dates are placeholders | bar: 2025-07-07
Oct 2025 meeting | 2025-10-03 | 2025-10-03 | Dates are placeholders | bar: 2025-09-29
GMAC Technical Sessions | 2025-06-01 | 2025-11-01 | GMAC technical sessions | bar: 2025-05-26; 2025-10-27
Technical session 1 | 2025-06-01 | 2025-06-01 | Topic TBD -Dates are placeholders | bar: 2025-05-26
Technical session 2 | 2025-11-01 | 2025-11-01 | Topic TBD -Dates are placeholders | bar: 2025-10-27
Interim ESMP Mechanism | 2024-12-18 | 2025-03-14 | ESMP Phase II Proceeding (Cost recovery) | bar: 2024-12-16 to 2025-03-10
EDC Proposals due | 2024-12-18 | 2024-12-18 | EDC proposals for ESMP mechanism tariff and supporting documentation and testimony due | bar: 2024-12-16
Questions for technical session due | 2025-01-14 | 2025-01-14 | Technical session questions final participation lists due | bar: 2025-01-13
Technical sessions | 2025-01-21 | 2025-01-24 | Sesssions cover both interim ESMP mechanism and reporting/metrics | bar: 2025-01-20
Intervenor testimony due | 2025-01-28 | 2025-01-28 | Intervenor pre-filed testimony on interim cost recovery issues due | bar: 2025-01-27
Discovery on intervenor testimony | 2025-01-28 | 2025-02-13 | bar: 2025-01-27 to 2025-02-10
Deadline to request evidentiary hearing | 2025-02-28 | 2025-02-28 | Deadline to request evidentiary hearing(s) and anticipated time needed for cross-examination, if applicable | bar: 2025-02-24
Discovery log and exhibit list due | 2025-03-04 | 2025-03-04 | Updated discovery log and Phase II exhibit list from each company due | bar: 2025-03-03
Evidentiary hearing | 2025-03-11 | 2025-03-14 | Dates reserved for virtual evidentiary hearing(s), if needed | bar: 2025-03-10
Briefs due | TBD | TBD | Briefing dates TBD
ESMP Phase II (Mertrics & Reporting) | 2025-01-14 | 2025-05-15 | bar: 2025-01-13 to 2025-05-12
EDC proposals due | 2025-03-18 | 2025-03-18 | The Companies shall confer and jointly propose initial ESMP metrics and reporting templates for the September 2025 and March 2026 biannual reports consistent with the Department’s directives | bar: 2025-03-17
Intervenor comments and proposed metrics due | 2025-04-17 | 2025-04-17 | bar: 2025-04-14
EDC reply comments due | 2025-05-15 | 2025-05-15 | bar: 2025-05-12
Questions for technical session due | 2025-01-14 | 2025-01-14 | bar: 2025-01-13
Technical sessions | 2025-01-21 | 2025-01-24 | Sesssions cover both interim ESMP mechanism and reporting/metrics | bar: 2025-01-20
LTSPP | 2024-10-01 | 2025-04-04 | Long-Term System Planning Program | bar: 2024-12-02 to 2025-03-31
LTSPP Process | 2024-10-01 | 2025-03-01 | DPU ordered EDCs to organize a 6-month process starting October 2024 (see ESMP Final Order) | bar: 2024-12-02 to 2025-02-24
October meeting 1 | 2024-10-08 | 2024-10-08
October meeting 2 | 2024-10-22 | 2024-10-22
WG Report due to DPU | 2025-04-04 | 2025-04-04 | bar: 2025-03-31
Current ESMPs | 2025-09-10 | 2026-03-31 | D.P.U. 24-10/D.P.U. 24-11/D.P.U. 24-12 | bar: 2025-09-08 to 2026-03-30
ESMP Term | 2025-07-01 | 2030-06-30 | First 5-year ESMP term | bar: 2025-06-30 to 2029-01-22
Biannnual ESMP report due | 2025-09-30 | 2025-09-30 | First EDC biannual report due to DPU | bar: 2025-09-29
Biannnual ESMP report due | 2026-03-31 | 2026-03-31 | Second EDC biannual report due to DPU | bar: 2026-03-30
EDC informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-09-10 | 2025-09-10 | bar: 2025-09-08
Intervenor informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-10-08 | 2025-10-08
Reply comments due | 2025-11-05 | 2025-11-05 | bar: 2025-11-03
CESAG | 2024-11-01 | 2030-01-01 | Community Engagement Stakeholder Advisory Group | bar: 2024-12-02 to 2029-01-22
Placeholder | 2024-11-01 | 2030-01-01 | Placeholder | bar: 2024-12-02 to 2029-01-22
Next ESMPs | 2028-07-14 | 2029-02-12 | Five-year term starting July 1, 2030 | bar: 2028-07-10 to 2029-01-22
Draft plans submitted to GMAC | 2029-02-12 | 2029-02-12
GMAC develops recommendations | 2029-02-12 | 2029-02-12
Final plans filed with DPU | 2028-07-14 | 2028-07-14 | bar: 2028-07-10
Other | 2025-03-01 | 2025-04-01 | bar: 2025-02-24 to 2025-03-31
ARR filed with DPU | 2025-03-31 | 2025-03-31 | Annual reliabilility reports (Filled annually March 31) | bar: 2025-03-31
Service Quality filed with DPU | 2025-03-01 | 2025-03-01 | bar: 2025-02-24
Climate Compliance Plans filed with DPU | 2025-04-01 | 2025-04-01 | D.P.U. 20-80-B
Formulas:
TBD = MIN([TBD, row below]:C54)
TBD = MAX([TBD, row below]:D54)