## Notes and Resources
Workbook Overview |  |  | Questions and feedback: email kschultz@synapse-energy.com
Last updated:
2025-02-24
Purpose
This workbook is intended to be a central location for keeping track of dates for GMAC and related activities.
It is intended to contain the master list of dates, which will be kept updated and can be referenced to update other summaries/ materials, such as the GMAC website.
Calendar tab
This tab displays key meetings and processes for the GMAC and related actvities
Users can toggle between Weekly, Monthly, or Quarterly views by selecting a drop-down in cell C2.
Resources
Useful Links
| GMAC website | Grid Modernization Advisory Council (GMAC) ¦ Mass.gov
| LTSPP website | Proposed LTSPP Meeting Schedule
| DPU file room | ByNumber
Docket numbers
| Number | Description
| 24-10 | Eversource ESMP
| 24-11 | National Grid ESMP
| 24-12 | Unitil ESMP

## Calendar
NOTE: DO NOT DRAG FORMULAS DOWN; FORMULAS ARE NOT THE SAME FOR ALL ROWS
View Selection >> | Weekly
|  |  |  | 2025 | [44 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028 | [51 empty] | 2029
|  |  |  | Q2 | 2025-03-03 |  |  |  |  | 2025-04-07 |  |  |  | 2025-05-05 |  |  |  | 2025-06-02 |  |  |  |  | 2025-07-07 |  |  |  | 2025-08-04 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-06 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 | [8 empty] | 2026-02-02 |  |  |  | 2026-03-02 |  |  |  |  | 2026-04-06 |  |  |  | 2026-05-04 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  |  | 2026-12-07 | [7 empty] | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  |  | 2027-06-07 |  |  |  | 2027-07-05 |  |  |  | 2027-08-02 |  |  |  |  | 2027-09-06 |  |  |  | 2027-10-04 |  |  |  | 2027-11-01 |  |  |  |  | 2027-12-06 | [8 empty] | 2028-02-07 |  |  |  | 2028-03-06 |  |  |  | 2028-04-03 |  |  |  | 2028-05-01 |  |  |  |  | 2028-06-05 |  |  |  | 2028-07-03 |  |  |  |  | 2028-08-07 |  |  |  | 2028-09-04 |  |  |  | 2028-10-02 |  |  |  |  | 2028-11-06 |  |  |  | 2028-12-04 | [8 empty] | 2029-02-05 |  |  |  | 2029-03-05 |  |  |  | 2029-04-02
| START DATE | END DATE | time axis 2025-02-24 to 2029-04-23
|  |  | Description | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029
GMAC | 2025-02-27 | 2026-01-08 | bar: 2025-02-24 to 2026-01-05
placeholder
GMAC Meetings | Monthly | Monthly | GMAC meetings 4th Thursday of every month 1-3PM | bar: 2025-02-24; 2025-03-24; 2025-04-28; 2025-05-26; 2025-06-23; 2025-07-28; 2025-08-25; 2025-09-15; 2025-10-27; 2025-12-01; 2026-01-05
Feb 2025 meeting | 2025-02-27 | 2025-02-27 | Reporting: existing reports, ESMP metrics | bar: 2025-02-24
March 2025 meeting | 2025-03-27 | 2025-03-27 | Reporting: ESMP metrics, biannual report content | bar: 2025-03-24
April 2025 meeting | 2025-05-01 | 2025-05-01 | System Reliability | bar: 2025-04-28
May 2025 meeting | 2025-05-29 | 2025-05-29 | Proactive Grid Planning (LTSPP Updates) | bar: 2025-05-26
June 2025 meeting | 2025-06-29 | 2025-06-29 | Integrated Energy Planning (NPA) | bar: 2025-06-23
July 2025 meeting | 2025-07-31 | 2025-07-31 | Equity in Grid Planning | bar: 2025-07-28
Aug 2025 meeting | 2025-08-28 | 2025-08-28 | System Resilience | bar: 2025-08-25
Sept 2025 meeting | 2025-09-18 | 2025-09-18 | Strategic Planning/ Biannual reports | bar: 2025-09-15
Oct 2025 meeting | 2025-10-30 | 2025-10-30 | Integrated Energy Planning (CCP) | bar: 2025-10-27
Nov 2025 meeting | None |  | Skip
Dec 2025 meeting | 2025-12-04 | 2025-12-04 | Topic TBD | bar: 2025-12-01
Jan 2026 meeting | 2026-01-08 | 2026-01-08 | Topic TBD | bar: 2026-01-05
Excom Meetings | Bi-monthly | Bi-monthly | ExCom meetings on Thursdays 9:30-10:30 every other month | bar: 2025-04-21; 2025-06-02; 2025-08-11; 2025-10-06; 2025-12-15
April 2025 meeting | 2025-04-24 | 2025-04-24 | bar: 2025-04-21
June 2025 meeting | 2025-06-05 | 2025-06-05 | bar: 2025-06-02
Aug 2025 meeting | 2025-08-14 | 2025-08-14 | bar: 2025-08-11
Oct 2025 meeting | 2025-10-09 | 2025-10-09 | bar: 2025-10-06
Dec 2025 meeting | 2025-12-18 | 2025-12-18 | bar: 2025-12-15
EWG meetings | Quarterly | Quarterly | EWG meetings 10-11:30 AM | bar: 2025-03-24; 2025-07-07; 2025-10-06
March 2025 meeting | 2025-03-28 | 2025-03-28 | bar: 2025-03-24
July 2025 meeting | 2025-07-11 | 2025-07-11 | bar: 2025-07-07
Oct 2025 meeting | 2025-10-10 | 2025-10-10 | bar: 2025-10-06
GMAC Stakeholder Sessions | 2025-07-19 | 2025-11-01 | GMAC stakeholder sessions | bar: 2025-07-14; 2025-10-27
Stakeholder Session #1 | 2025-07-19 | 2025-07-19 | TENTATIVE. 100 Cambridge St. 9-12PM. | bar: 2025-07-14
Stakeholder Session #2 | 2025-11-01 | 2025-11-01 | Topic TBD -Dates are placeholders | bar: 2025-10-27
ESMP Phase II (Interim ESMP Mechanism) | 2025-02-28 | 2025-03-13 | ESMP Phase II Proceeding (Cost recovery) | bar: 2025-02-24 to 2025-03-10
Deadline to request evidentiary hearing | 2025-02-28 | 2025-02-28 | Deadline to request evidentiary hearing(s) and anticipated time needed for cross-examination, if applicable | bar: 2025-02-24
Discovery log and exhibit list due | 2025-03-04 | 2025-03-04 | Updated discovery log and Phase II exhibit list from each company due | bar: 2025-03-03
Evidentiary hearing | 2025-03-12 | 2025-03-13 | bar: 2025-03-10
Briefs due | TBD | TBD | Briefing dates TBD
ESMP Phase II (Mertrics & Reporting) | 2025-03-18 | 2025-05-15 | ESMP Phase II (Mertrics & Reporting) | bar: 2025-03-17 to 2025-05-12
EDC proposals due | 2025-03-18 | 2025-03-18 | The Companies shall confer and jointly propose initial ESMP metrics and reporting templates for the September 2025 and March 2026 biannual reports consistent with the Department’s directives | bar: 2025-03-17
Intervenor comments and proposed metrics due | 2025-04-17 | 2025-04-17 | bar: 2025-04-14
EDC reply comments due | 2025-05-15 | 2025-05-15 | bar: 2025-05-12
Long-Term System Planning Process (LTSPP) | 2025-01-01 | 2025-04-04 | Long-Term System Planning Program | bar: 2025-02-24 to 2025-03-31
Stakeholder Meetings | Bi-weekly | Bi-weekly | Every other Tuesday 10am-12pm | bar: 2025-02-24; 2025-03-10; 2025-03-24
February meeting 2 | 2025-02-25 | 2025-02-25 | bar: 2025-02-24
March meeting 1 | 2025-03-11 | 2025-03-11 | bar: 2025-03-10
March meeting 2 | 2025-03-25 | 2025-03-25 | bar: 2025-03-24
EDCs provide draft LTSPP Framework | 2025-01-01 | 2025-01-14
Interim status report due to DPU | 2025-02-03 | 2025-02-03
EDC Final Report due to DPU | 2025-04-04 | 2025-04-04 | bar: 2025-03-31
Current ESMPs | 2025-09-10 | 2026-03-31 | D.P.U. 24-10/D.P.U. 24-11/D.P.U. 24-12 | bar: 2025-09-08 to 2026-03-30
ESMP Term | 2025-07-01 | 2030-06-30 | First 5-year ESMP term | bar: 2025-06-30 to 2029-04-16
Biannnual ESMP report due | 2025-09-30 | 2025-09-30 | First EDC biannual report due to DPU | bar: 2025-09-29
Biannnual ESMP report due | 2026-03-31 | 2026-03-31 | Second EDC biannual report due to DPU | bar: 2026-03-30
EDC informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-09-10 | 2025-09-10 | bar: 2025-09-08
Intervenor informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-10-08 | 2025-10-08
Reply comments due | 2025-11-05 | 2025-11-05 | bar: 2025-11-03
CESAG | 2024-11-01 | 2030-01-01 | Community Engagement Stakeholder Advisory Group | bar: 2025-02-24 to 2029-04-16
Placeholder | 2024-11-01 | 2030-01-01 | Placeholder | bar: 2025-02-24 to 2029-04-16
Next ESMPs | 2028-07-14 | 2029-02-12 | Five-year term starting July 1, 2030 | bar: 2028-07-10 to 2029-02-12
Draft plans submitted to GMAC | 2029-02-12 | 2029-02-12 | bar: 2029-02-12
GMAC develops recommendations | 2029-02-12 | 2029-02-12 | bar: 2029-02-12
Final plans filed with DPU | 2028-07-14 | 2028-07-14 | bar: 2028-07-10
Other | 2025-03-01 | 2025-04-01 | bar: 2025-02-24 to 2025-03-31
ARR filed with DPU | 2025-03-31 | 2025-03-31 | Annual reliabilility reports (Filled annually March 31) | bar: 2025-03-31
Service Quality filed with DPU | 2025-03-01 | 2025-03-01 | bar: 2025-02-24
Climate Compliance Plans filed with DPU | 2025-04-01 | 2025-04-01 | D.P.U. 20-80-B
Formulas:
TBD = MIN([TBD, row below]:C43)
TBD = MAX([TBD, row below]:D43)