## Sched FY11
DCS FY12 Quality Assurance Review Schedule
Operator | Notification Letter Due | Questionaire due to DCS office | Date Notification Letter E-Mailed | Start Date of Review | Program End Date for Review | Fiscal End Date for Review | Fiscal Staff | Prgm. Staff | WIBStaff | Report Due to Field | Operator Response Due | Staff Resp. for Ltr. & Rpt
Bristol | 2012-03-02 | 2012-03-23 | 2012-03-02 | 2012-04-02 | 2012-04-06 | 2012-04-06 | Carrie P | Judy B | Tom W. | 2012-05-07 | 2012-06-07 | F
New Bedford | 2012-03-09 | 2012-03-30 | 2012-03-09 | 2012-04-09 | 2012-04-13 | 2012-04-13 | Rosetta | Judy B | Deborah | 2012-05-14 | 2012-06-14 | F
Hampden | 2012-04-06 | 2012-04-27 | 2012-04-06 | 2012-05-07 | 2012-05-11 | 2012-05-11 | N/A | Judy B |  | 2012-06-11 | 2012-07-12 | P
Lowell | 2012-04-13 | 2012-05-04 | 2012-04-13 | 2012-05-14 | 2012-05-18 | 2012-05-18 | N/A | Judy B |  | 2012-06-18 | 2012-07-19 | P
N. Central | 2012-05-04 | 2012-05-25 | 2012-05-04 | 2012-06-04 | 2012-06-08 | 2012-06-08 | Carrie P | Judy B | Tom W. | 2012-07-09 | 2012-08-09 | P
N. Central | 2012-05-11 | 2012-06-01 | 2012-05-11 | 2012-06-11 | 2012-06-15 | 2012-06-15 |  |  |  | 2012-07-16 | 2012-08-16 | F
Hampden | 2012-06-08 | 2012-06-29 | 2012-06-08 | 2012-07-09 | 2012-07-13 | 2012-07-13 | Carrie P | NA |  | 2012-08-13 | 2012-09-13 | F
F/H | 2012-06-08 | 2012-06-29 | 2012-06-08 | 2012-07-09 | 2012-07-13 | 2012-07-13 | Rosetta | Judy B | Cheryl | 2012-08-13 | 2012-09-13 | P
S. Shore | 2012-06-15 | 2012-07-06 | 2012-06-15 | 2012-07-16 | 2012-07-20 | 2012-07-20 | N/A | Judy B |  | 2012-08-20 | 2012-09-20 | P
Lowell | 2012-06-22 | 2012-07-13 | 2012-06-22 | 2012-07-23 | 2012-07-27 | 2012-07-27 | Michael W | N/A | Cheryl | 2012-08-27 | 2012-09-27 | F
Boston Pic | 2012-06-22 | 2012-07-13 | 2012-06-22 | 2012-07-23 | 2012-07-27 | 2012-07-27 | Rosetta | N/A | Kathy M | 2012-08-27 | 2012-09-27 | F
Merrimack | 2012-07-06 | 2012-07-27 | 2012-07-06 | 2012-08-06 | 2012-08-10 | 2012-08-10 | Carrie P | Judy B | Kathy M | 2012-09-10 | 2012-10-11 | F
Brockton | 2012-07-13 | 2012-08-03 | 2012-07-13 | 2012-08-13 | 2012-08-17 | 2012-08-17 | Rosetta | Judy B | Deborah | 2012-09-17 | 2012-10-18 | F
Berkshire | 2012-07-20 | 2012-08-10 | 2012-07-20 | 2012-08-20 | 2012-08-24 | 2012-08-24 | Michael W | Judy B | Deborah | 2012-09-24 | 2012-10-25 | F
MSW | 2012-08-10 | 2012-08-31 | 2012-08-10 | 2012-09-10 | 2012-09-14 | 2012-09-14 | Rosetta | Judy B | Deborah | 2012-10-15 | 2012-11-15 | P
S. Shore | 2012-08-10 | 2012-08-31 | 2012-08-10 | 2012-09-10 | 2012-09-14 | 2012-09-14 | Carrie P | N/A | Tom W. | 2012-10-15 | 2012-11-15 | P
Central | 2012-08-17 | 2012-09-07 | 2012-08-17 | 2012-09-17 | 2012-09-21 | 2012-09-21 | Michael W | Judy B | N/A | 2012-10-22 | 2012-11-22 | P
Metro North | 2012-08-31 | 2012-09-21 | 2012-08-31 | 2012-10-01 | 2012-10-05 | 2012-10-05 | Rosetta | Judy B | Deborah | 2012-11-05 | 2012-12-06 | F
Cape/Islands | 2012-09-14 | 2012-10-05 | 2012-09-14 | 2012-10-15 | 2012-10-19 | 2012-10-19 | Carrie P | Judy B | Kathy M | 2012-11-19 | 2012-12-20 | F
N. Shore | 2012-09-21 | 2012-10-12 | 2012-09-21 | 2012-10-22 | 2012-10-26 | 2012-10-26 | Michael W | Judy B | Tom W. | 2012-11-26 | 2012-12-27 | F
EDIC | 2012-10-05 | 2012-10-26 | 2012-10-05 | 2012-11-05 | 2012-11-09 | 2012-11-09 | Michael W | Judy B | Cheryl | 2012-12-10 | 2013-01-10 | P
Note- Area in Blue indicate Fiscal & Program will be at separate timeframes due to other scheduling conflict.
Note- Area in Orange indicate a change in dates.
]
Formulas:
Notification Letter Due = [Start Date of Review]-31
Questionaire due to DCS office = [Notification Letter Due]+21
Date Notification Letter E-Mailed = [Notification Letter Due]
Program End Date for Review = [Start Date of Review]+4
Fiscal End Date for Review = [Program End Date for Review]
Fiscal End Date for Review = +[Program End Date for Review]
Report Due to Field = [Program End Date for Review]+31
Report Due to Field = [Fiscal End Date for Review]+31
Operator Response Due = [Report Due to Field]+31