1

2

Progress to date . . .

To date,  93% of the action items, announced by Governor Baker on June 22, 2016, are either  in progress or completed. A

few highlights include:

Prevention:

•     In March 2016, we implemented a first in the nation 7-day limit on opioid prescriptions to limit first time exposure to opioids.

•	We created three  public  awareness campaigns – State Without Stigma, Stop Addiction, and promotion of the Good Samaritan Law – to reduce stigma  and raise awareness.

•     We worked with medical schools,  dental schools,  advanced practice nursing (APRN) programs and professional organizations,

physician assistant programs, the Massachusetts Association of Physician Assistants, the Massachusetts League  of Community Health Centers, and all affiliated community health centers  to implement a set of core competencies related to the prevention and management of prescription drug misuse for medical professionals.

Intervention:

•     We launched a completely new and improved Prescription Monitoring Program on August 22, 2016.

•	We improved data  collection  and  the timeliness of releasing data  about  the impact opioids are having on our communities, issuing a quarterly report.

Treatment:

•     Since January of 2015, we have added 455 substance use treatment beds to the system.

•     In April 2016, we ended the practice of sending women who are civilly committed because of the risk they pose to themselves or others,

as a result  of a substance use disorder, to MCI-Framingham.

Recovery:

•     As of September 1, 2016, 83 Sober Homes have been certified by the Massachusetts Association of Sober Houses.

2

3

Prevention Initiatives

Public Awareness

•    Create  a public  awareness campaign focused on reframing addiction as a medical disease

•    Foster public-private partnerships to leverage public  awareness activities

•    Promote drug take-back days

•    Partner with a chain pharmacy to pilot a drug-take-back program in the Commonwealth

Education – Parents and Students

•    Educate parents, students, and faculty  about  the risks of opioid use and misuse during mandatory athletic  meetings

•    Provide state funding for evidence-based opioid prevention programs in schools

•    Develop targeted educational materials for parents about  the risks of opioid use and  misuse

Prescriber Practices

•	Mandate prescriber education as a condition of licensure by working with boards of registration to enforce  continuing education requirements related to: effective pain management; identification of patients at high risk for a SUD; and counseling patients on the side effects, addictive nature, and proper storage and disposal of prescription medications

•    Appoint an addiction specialist to the Board of Registration in Medicine, Board of Registration in Nursing, Board of Registration of

Physician Assistants, and Board of Registration in Dentistry

•    Appoint members to the drug formulary commission and  commence the first meeting prior  to August 1

•	Outreach to prenatal and postpartum care providers to increase training about  screening, intervention, and care for women with a substance use disorder (SUD)

•    Increase  and improve educational offerings about  safe prescribing practices by engaging in private-public partnerships

•	Encourage the American College of Graduate Medical  Education to adopt requirements for pain management and  substance use disorder education for all medical and residency programs, through a partnership with federal leaders

complete         in progress          not in progress

3

4

Intervention Initiatives

Prescription Monitoring Program

•    Improve the prescription monitoring program (PMP)

•    Ensure data  compatibility of the PMP with  other  states, Memorandum of understanding with other states required

•    Require PMP data  to be submitted within 24 hours by pharmacies, Legislation required

Data

•    Require timely  reporting of overdose death data  to the public

•    Amend Department of Public Health regulations to require that emergency medical service providers report opioid overdose data

•	Utilize overdose reports to identify geographical hot spots for targeted intervention and alert law enforcement, public  health entities, community coalitions, and the public

Other Intervention Action Items

•    Develop and distribute educational materials for prescribers to increase co-prescribing of naloxone with opioid prescriptions

•    Implement a training program about  neonatal abstinence syndrome and  addiction for Department of Children and  Families’  staff

•    Promote the Good Samaritan law

•	Amend the civil commitment statute, section 12 of chapter 123 of the General Laws, to allow for the involuntary transport and assessment of an individual with a substance use disorder (SUD), Legislation required

•    Improve affordability of naloxone through bulk purchasing, Legislation required

complete         in progress         not in progress

4

5

Treatment Initiatives

MassHealth

•    Develop a statewide database of available treatment services,  accessible  by phone and  internet

•    Expand mobile emergency service programs to support individuals with a substance use disorder (SUD) in crisis

•    Provide case management services  to MassHealth fee-for-service members who have a SUD

•	Remove  fail-first requirements for medication-assisted treatment and ensure naltrexone is categorized as a pharmacy benefit  within all MassHealth plans

•    Review SUD treatment prior  authorization policies across MassHealth to ensure consistency and remove barriers to treatment

•    Enroll uninsured patients receiving acute treatment services  or clinical stabilization services  in MassHealth or other  insurance

Department of Public Health

•	(Pilot) Create  walk-in access to a trained clinician  in community-based outpatient provider settings who can provide an emergent/urgent addiction assessment and direct  referral to the appropriate level of care

•    (Pilot) Make recovery coaches  available in emergency departments and hot spots

•    Increase  the number of office-based opioid treatment programs in community health centers

•    Integrate medication-assisted treatment into the clinical stabilization services  (CSS) care setting

•    Add  100 new treatment beds by July 2016 and expand access to patient navigators

complete         in progress         not in progress

5

6

Treatment Initiatives

Department of Corrections

•    Bulk purchase opioid agonist and naltrexone therapies for correctional facilities

•    Improve SUD treatment services  for men and women committed under section 35 of chapter 123 of the General Laws:

•    Transfer women from the correctional facility at MCI-Framingham to a new facility run by the Executive Office of Health and

Human Services (EOHHS)

•	Develop a feasibility plan to transfer responsibility for the Massachusetts Alcohol and  Substance Abuse  Center at Bridgewater to EOHHS, Legislation required

•    Increase  treatment beds and ensure a continuum of care for patients who are civilly committed under section  35

Division of Insurance

•    Review existing  Division of Insurance bulletins regarding parity oversight and enforcement

•    Issue guidance on the implementation of the substance use disorder recovery law before October  1, 2015

Group Insurance Commission

•    Ensure that all Group Insurance Commission (GIC) plans  provide coverage for naltrexone, naloxone, buprenorphine, and methadone

•    Review GIC insurance plans,  removing fail-first policies and  prior  authorization protocols that may impede access to treatment

Partnering with Federal Leaders

•    Change Drug  Enforcement Agency  (DEA) rules to permit medical residents to prescribe buprenorphine under an institutional DEA

registration number, through a partnership with federal leaders

•	Change federal  law and regulations to increase access to buprenorphine by: increasing the cap - the number of patients a physician can treat with buprenorphine - or removing it entirely; and permitting nurse practitioners and physician assistants to prescribe buprenorphine, through a partnership with federal leaders

complete         in progress         not in progress

6

7

Recovery Support Initiatives

Department of Public Health

•Enforce and strengthen the requirement that all licensed addiction treatment programs accept patients who are on methadone or buprenorphine medication

•Implement a process to certify alcohol and drug-free housing to increase accountability and  credibility

•Establish revised rates for residential recovery homes,  effective July 1, 2015

•Leverage community coalitions to address the opioid epidemic

•Open  Recovery  High  School in Worcester

Executive Office  of Health and Human Services

•    Create  a consistent public  behavioral health policy through a review of all DPH and  DMH licensing regulations for outpatient

primary care clinics, outpatient mental health clinics, and BSAS programs removing all barriers to integration

•    Ensure MassHealth coverage is reinstated on an accelerated basis for individuals upon release  from incarceration

•    Establish a single point  of accountability for addiction and  recovery policy within the Executive Office of Health and Human

Services

•    Amend the composition of the Interagency Council  on Substance Abuse,  Legislation required

•    Report  publicly on the progress and challenges of implementing the working group’s recommendations

•    Increase  federal  support for substance use prevention, intervention, treatment, and recovery efforts uniquely tailored for our

Veterans, through a partnership with federal leaders

complete          in progress         not in progress

7

8

Budget and Legislation

•	Supplemental Budget (Ch. 119 of the Acts of 2015): Appropriated $27.8 million  to curb the opioid epidemic ($3 M to expand SUD treatment for MassHealth members, $5.8 M to support the opening of the Women’s  Recovery  from Addictions Program at Taunton State Hospital, $14 M to support treatment of individuals in a residential recovery setting,  $5 M to support SUD prevention efforts).

•	FY 2016 Budget (Ch. 46 of the Acts of 2015): Appropriated $134 million  for substance use treatment, prevention, intervention, and recovery efforts. Included a strong investment in developing new clinical stabilization beds, funded a public  awareness campaign about  the Good  Samaritan Law, invested in community coalitions, invested in

improving access to medication assisted treatment, and authorized a bulk purchase trust  fund  to support the purchase of Narcan by first responders in our cities and towns.

•	Criminalizing Fentanyl Trafficking  (Ch. 136 of the Acts of 2015): Mandates that trafficking fentanyl is a felony and institutes mandatory minimums on the charge.

•	Ended the practice of civilly committing women under Section  35 to MCI-Framingham  (Ch. 8 of the Acts of 2016): Eliminates the possibility that women can be committed to MCI-Framingham under Section 35 of Chapter 123 of the General Laws. Ensures that women with  a substance use disorder who are civilly committed  will now receive substance use treatment at an appropriate facility.

•	STEP Act (Ch. 52 of the Acts of 2016): limits a first-time opioid prescription to seven  days; requires practitioners to check the PMP before prescribing opioids; requires student prevention education training during concussion safety training for athletes; increases prescriber education requirements; expands Good  Samaritan protections by shielding individuals administering Narcan to a person during an opiate  overdose from civil liability;  and requires a substance use disorder evaluation for individuals presenting in the emergency room  because of an apparent opiate  overdose.

•	FY 2017 Budget (Ch. 133 of the Acts of 2016): Appropriated $173 million  for substance use treatment, prevention, intervention, and recovery efforts.  Including a $24 million  increase  ,over FY 16 GAA, in support for residential recovery beds, continued support for 19 community coalitions, support for 32 office based  opioid treatment programs,

41 outpatient treatment programs, and 10 recovery support centers.

8

Public Awareness Campaigns and Improved Treatment Locator Services

Launched 3 public awareness campaigns:

•    Stop Addiction in its Tracks, providing information on

how to prevent and identify opioid misuse and where

to go for help  http://www.mass.gov/eohhs/gov/departments/dph/stop-

addiction/

•    #StateWithoutStigMA, changing the way we think

about, talk about and treat people with addiction

http://www.mass.gov/eohhs/gov/departments/dph/stop-addiction/state-without- stigma/

•    MakeTheRightCall, to improve public awareness about

the Good Samaritan Law

http://www.mass.gov/eohhs/gov/departments/dph/programs/substance- abuse/make-the-right-call-public-information-campaign.html

450,000

400,000

350,000

300,000

250,000

200,000

150,000

18,329

264,123

Make the Right Call unique web hits

Stop Addiction unique web hits

#StateWithoutStigMA

unique web hits

Helpline calls

Improved Treatment Locator Services, including:

•   BSAS Helpline, (800) 327-5050

•   The MBPH treatment locator

http://www.mabhaccess.com/

100,000

50,000

0

96,650

31,363

10

New PMP System: MassPAT

•	The new Massachusetts Prescription Awareness Tool (MassPAT): provides an enhanced user experience; improves data collection and timeliness; expand interstate connectivity; and allows for integration with electronic medical records systems.

•   Response times to query prescription data is significantly reduced to 1.7 seconds.

•	To date, MassPAT can send and receive prescription data from RI, CT, VT, VA, GA, NY, AZ, CO, ID, and TX.

•	Massachusetts pharmacies are required to report data within 24-hours or no later than the next business day.

•   80% of individuals who were registered on the old system have registered for

MassPAT.

Summary of Treatment Service Expansion for Psychiatric

and Substance Use Services in the Commonwealth

(As of September 1, 2016)

| Program Type | Total Operational Licensed Capacity as of January 1, 2015 | Total Operational Licensed Capacity as of January 1, 2016 | Total Operational Licensed Capacity as of September 1, 2016 | Change Since January 1, 2015 |
| --- | --- | --- | --- | --- |
| DPH Acute Treatment Services (ATS) (level 4.0 & 3.7), Adult | 846 beds | 902 beds | 953 beds | 107 beds |
| DPH Clinical Stabilization Services (CSS) | 297 beds | 340 beds | 454 beds | 157 beds |
| DPH Transitional Support Services (TSS) | 339 beds | 312 beds | 342 beds | 3 beds |
| DPH Adult Residential Recovery | 2300 beds | 2375 beds | 2,405 beds | 105 beds |
| DPH Youth Stabilization Beds | 48 beds | 48 beds | 48 beds |  |
| DPH Second Offender Residential | 58 beds | 58 beds | 58 beds |  |
| DPH Adolescent / Transitional Youth Residential Beds | 144 beds | 111 beds | 86 beds | -40 beds* |
| DPH Family Residential | 110 families | 110 families | 110 families |  |
| DMH Adult Psychiatric | 1782 beds | 1854 beds | 1,904 beds | 122 beds |
| DMH Geriatric Psychiatric | 399 beds | 399 beds | 453 beds | 54 beds |
| DMH Adolescent & Child Psychiatric | 252 beds | 266 beds | 266 beds | 14 beds |
| Section 35 Men's Beds | 258 beds | 308 beds | 308 beds | 50 beds |
| Section 35 Women's Beds | 90 beds | 90 beds | 163 beds | 73 beds |
| DPH Outpatient Treatment Program (OTP) - Medication Assisted Treatment (MAT) Programs (Methadone) | 39 programs | 41 programs | 41 programs | 2 programs |
| DPH Outpatient Counseling and Outpatient Detox Programs | 190 programs | 190 programs | 192 programs | 2 programs |
| DPH Office-Based Outpatient Treatment (OBOT) (buprenorphine) – MAT Sites funded by DPH | 14 programs | 17 programs | 30 programs | 16 programs |
| Sober Homes Certified by the Mass Association of Sober Houses | 0 | 0 | 83 homes 1,082 beds | 83 homes 1,082 beds |
| * DPH has awarded contracts to providers to add 60 new beds across 4 programs, these beds are not included in this number |  |  |  |  |

12

Opioid-Related Deaths, Unintentional / Undetermined, (Massachusetts 2000-2015)

Source: DPH.  http://www.mass.gov/eohhs/docs/dph/quality/drugcontrol/county-level-pmp/data-brief-overdose-deaths-may-2016.pdf

In 2015, 57% of opioid-related deaths with toxicology screen  tested positive for fentanyl. During the first six months of 2016, that number rose to 66%

Opioid-related Deaths, All Intents by Month

Massachusetts Residents: January 2015 - June 2016

200

180

Number of deaths

160

140         17

120                       19

100

80

Confirmed        Estimated

Opioid-Related Deaths by Month

11                                       18

156

46         95

150       171

60       135       119       140

40

20

0

107       111        97        100       122       120       124       126        97

136

108

82

20          2

January                      March                         May                           July                      September               November                  January                      March                         May

2015                                                                                                                                                     2016

754

565

Opioid-Related Deaths with a Positive

Toxicology Screen for Fentanyl

Negative for fentanyl

289

150

January 2015 – December 2015

Positive for fentanyl

January 2016 – June 2016

13

Using predictive modeling techniques and multiple data  sources,  DPH is able to estimate opioid-related deaths month-to-month with  minimal delay in reporting, http://www.mass.gov/eohhs/docs/dph/quality/drugcontrol/county-level-pmp/data-brief-overdose-deaths-may-2016.pdf

13

Unintentional Opioid-related Overdose Deaths vs. Motor Vehicle-related Injury  Deaths, (Massachusetts 2000-2015)

Unintentional Opioid-related Overdose          Motor  Vehicle-related Injury

1,800

1,600

1,659

Number of Deaths

1,400

1,200

1,000

800

600

493

200

338

315

14

0

2000    2001    2002    2003    2004    2005    2006    2007    2008    2009    2010    2011    2012    2013    2014    2015

Source: DPH. Note: 2015 motor  vehicle data  and 2014/2015 overdose data  are based  on DPH estimates

15

State Spending to Support Substance Use Prevention, Treatment, Intervention, and Recovery Efforts has increased steadily over the past six fiscal years

| Agency | FY12 GAA | FY13 GAA | FY14 GAA | FY15 GAA | FY16 GAA & Supp Budget | FY17 Projected |
| --- | --- | --- | --- | --- | --- | --- |
| Department of Public Health | $83,110,802 | $85,464,595 | $92,258,094 | $101,877,333 | $136,321,803² | $143,695,567 |
| Department of Mental Health |  |  |  |  | $3,500,000³ | $13,212,701 |
| MassHealth Substance Abuse Disorders Services (including Methadone) | $150,243,844¹ | $145,943,598¹ | $158,797,616¹ | $185,329,771¹ | * |  |
| Medication Assisted Treatment (e.g. Buprenorphine, Naltrexone) | $21,827,729¹ | $29,947,101¹ | $24,586,518¹ | $20,536,840¹ | * |  |
| Health Policy Commission |  |  |  |  | $600,000 |  |
| Attorney General's Office |  |  |  |  |  | $1,000,000 |
| Department of Correction |  |  | $10,521,022 | $11,909,800 | $13,326,130 | $13,326,130 |
| District Attorney's Association |  |  |  | $500,000 | $500,000 | $495,000 |
| Massachusetts State Police |  |  |  |  |  | $1,200,000 |

*MassHealth’s finalized claims data  will be available in November 2016

¹ Denotes actual  spending

² The FY16 GAA appropriated $119,487,403 to DPH; the Supplemental Budget  (Ch. 119 of the Acts of 2015) appropriated $16,834,400

³ The Supplemental Budget  (Ch.119 of the Acts of 2015) appropriated $5.8M to DMH to support the opening of the Women’s  Recovery  from Addictions

Program (WRAP) at Taunton State Hospital

The FY16 GAA appropriated $500,000 to DESE; the Supplemental Budget  (Ch. 119 of the Acts of 2015) appropriated $3.8M to DESE

Emergency Medical  Services (EMS) Naloxone Statistics

(2013-2015)

12,000

10,000

8,000

6,000

4,000

2,000

0

7,002

10,720

12,982

Incidents in which naloxone was administered more

than once

Incidents in which naloxone was administered once

administrations

16

2013                       2014                       2015

Source: DPH data

Opioid Overdose Deaths by Demographic

(2015)

Unintentional/undetermined opioid-related deaths by gender, 2015

1,500

1,000

500

400

300

Unintentional/undetermined opioid-related deaths by age, 2015

437

350

302

Unintentional/undetermined opioid-related deaths by race, 2015

1,400   1,162

1,200

1,000

800

600

500

0

Male        Female

200

100

0

142

1

132

15

400

200

0

63     6    125   23

17

Source: DPH.  http://www.mass.gov/eohhs/docs/dph/quality/drugcontrol/county-level-pmp/opioid-demographic-may-2016.pdf

17

18

Opioid-related Inpatient Hospital Admissions by Demographic

(2014)

Source: HPC analysis, CHIA Data

18

Opioid-Related Deaths in Massachusetts by Category of Insurance

(2013-2015)

2%  2%            10%

12%

50%

2013

9%

1%

14%

1% 0%

15%

2015

12%

4%        1%

14%

Commercial Insurance

Medicare

Medicare + HSN

Medicare + MassHealth (Duals)

1% 1%           11%

2014

13%

6%

1%

13%

53%

2015

MassHealth & CommCare

Health Safety Net Other Public* Unknown/Uninsured

19

53%

Source: DPH, MassHealth, and  CHIA data

Number of Substance-Exposed Newborns (SEN) Reports to DCF (March 2014 to July 2016)

260

240

244

246

225

232   235

228

180

160

133

200

169

151

184

220

214

206

195

174

201

181

Total

SEN Reports

Screen-In

Total

120

132

20

100

| 2014 2015 2016 |  |
| --- | --- |
| January February March April May June July August September October November December | 177 232 |
|  | 203 197 |
|  | 133 208 235 |
|  | 142 207 213 |
|  | 157 208 199 |
|  | 159 193 228 |
|  | 168 230 201 |
|  | 206 236 |
|  | 244 246 |
|  | 219 221 |
|  | 160 225 |
|  | 200 211 |

Source: DCF data

Medication-Assisted Treatment Re-Entry  Initiative (MATRI)

in the Correctional System

(January 2015 – June 2016)

94 participants received pre-release Vivitrol injection

61 received first post- release  injection  + 3 more remained

engaged in treatment

47 received a second post-release injection

21

•	Provides pre-release treatment and post-release referral for inmates with alcohol or opioid use disorder at participating sites in the Department of Correction (DOC)

•   Offers inmates a pre-release injection  of Vivitrol  and connects inmates to

community-based clinics for aftercare treatment

•   Vivitrol  shot provided at no cost to the Commonwealth

Source: DOC data