## Slide 1: One Care Implementation Council 2017-2018 Workplan
October 10, 2017

## Slide 2: AREA OF FOCUS 1. Communication Access
Action Step #1
  Identify members for work group by October 13

## Slide 3: AREA OF FOCUS 1. Communication Access
Action Step #2
  Create measurable goal(s) by November 6

## Slide 4: AREA OF FOCUS 1. Communication Access
Action Step #3
  By October 24, identify available data sources

## Slide 5: AREA OF FOCUS 1. Communication Access
Action Step #4
By October13, request IC be on agenda of Tufts, CCA, and the Provider Council to learn:
  how it ensures services are accessible to OC members who are deaf/ hard of hearing, blind/visually impaired, non-verbal, or with literacy challenges
  whether they have experts in communication access or a point person that assures people get what they need

## Slide 6: AREA OF FOCUS 2. Quality of Care
Action Step #1
Identify IC members for workgroup by November 6

## Slide 7: AREA OF FOCUS 2. Quality of Care
Action Step #2
Create measurable goal(s) by November 13

## Slide 8: AREA OF FOCUS 2. Quality of Care
Action Step #3
  Conduct virtual and in-person listening sessions with One Care members and providers; ask Plans to advertise events in Nov-Dec

## Slide 9: AREA OF FOCUS 2. Quality of Care
Action Step #4
Schedule a virtual town hall “listening session” to hear from members with lived experience about One Care services and quality (first week in December)

## Slide 10: AREA OF FOCUS 2. Quality of Care
Action Step #5
  By October 24, collect available data and determine whether it is in an accessible format

## Slide 11: AREA OF FOCUS 2. Quality of Care
Action Step #6
  By early October, request IC be on agenda of Tufts and CCA to learn how plans select, procure, contract with vendors (people giving services/medical supplies) and to generate plan strategies and proposals to apply value-based purchasing strategies to service providers including DME providers

## Slide 12: AREA OF FOCUS 2. Quality of Care
Action Step #7
In November, connect with stakeholders who are working on quality measures

## Slide 13: AREA OF FOCUS 2. Quality of Care
Action Step #8
Host presentations by long-term services/support coordinators (LTSCs) and certified peer specialists (CPSs) to inform the IC

## Slide 14: AREA OF FOCUS 3. Sustainability of One Care
Action Step #1
  Identify IC members for workgroup by October 13

## Slide 15: AREA OF FOCUS 3. Sustainability of One Care
Action Step #2
  Identify and analyze existing data on plan performance by November 13

## Slide 16: AREA OF FOCUS 3. Sustainability of One Care
Action Step #3
  Determine what additional information is needed, if any, by November 17

## Slide 17: AREA OF FOCUS 3. Sustainability of One Care
Action Step #4
  Create measurable goal(s) by November 17

## Slide 18: AREA OF FOCUS 3. Sustainability of One Care
Action Step #5
  Identify 1 or 2 specific focus areas or topics for data review (e.g. homelessness) by November 17

## Slide 19
Questions and Discussion