## Tracking Sheet
Company Name | City/Town | Facility ID (if any) | ZIP Code | Design Capacity (kW) | Fuel Type (PV, Wind, etc) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Begun | Date Review of Screens Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/Standard / Complex Project** | Construction Timeline Commitment (Workdays) | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Status | Date of Info Request | Private/Gov't | Net Metered? (Y/N)
Company Name | Town | ID | ZipCode | Size kw | Fuel Source Type | Circuit | Date Appl Received | Date Appl Deemed | Total Time Lapsed in Appl Stage | Customer Time Lapsed | Utility Time Lapsed | Date Review of Screens Begun | Date Review of Screens Completed | Total Time Lapsed in Scrn Review Stage | Customer Time Lapsed in Scrn Review Stage | Utility Time Lapsed in Scrn Review Stage | Date Suppl Review Began | Date Suppl Review Complete | Tot Time lapsed for SR | Cust Time Lapsed in SR | Utility time Lapsed in the SR | Date Standard Process Rev Began | Date Standard Process Rev complete | Tot Time lapsed for Standard Rev | Cust Time Lapsed in Standard Rev | Utility time Lapsed in Standard Rev | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed for the IS | Cust Time Lapsed for the IS | Utility Time Lapsed in the IS | Date Detail Study Began | Date Detail Study Completed | Total Time Lapsed for DS | Cust Time Lapsed for DS | Utility Time Lapsed for DS | Date Agreement Sent to Cust | Date ISA & Payment Received | Estimated In-Service Date | System modification required? | Type of Review2 | Construction Commitment Date | Date Const Began | Date Const Completed | Total Const Time Lapsed | Cust Time Lapsed Const | Utility Time Lapsed Const | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Current Process Stage | Date of Info Request | Private/Gov't | Netmetering | Retirement Date
NSTAR | Sandwich | 557 | 2542 | 1500 | Wind | 4-81A-81A | 2009-01-12 | 2009-01-12 | 0 | 8 | 0 | 2009-02-18 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-24 | 2009-06-24 |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2009-12-22 | Online |  | Private | N
NSTAR | Falmouth | 744 | 2540 | 1545 | Wind | 4-98A-98A | 2009-01-15 | 2009-01-15 | 0 |  | 0 | 2009-01-15 | 2009-03-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-04-29 | [7 empty] | 0 |  | 0 |  |  | 2010-03-23 | Online |  |  | Y
NSTAR | Edgartown | 863 | 2539 | 68 | Wind | 4-75-75 | 2009-01-05 | 2009-05-14 | #VALUE! | 70 | #VALUE! | 2009-05-14 | 2009-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2008-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-14 |  | 2009-08-13 | Online |  | Private | Y
NSTAR | Woburn | 945 | 1801 | 95 | PV | 375-H11 | 2009-10-15 | 2009-10-15 | 0 |  | 0 | 2008-10-15 | 2008-10-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2008-11-13 | [7 empty] | 0 |  | 0 | 2009-02-11 |  | 2009-02-11 | Online |  |  | Y
NSTAR | Woods Hole | 990 | 2543 | 10 | Wind | 4-91-434 | 2009-02-17 | 2009-02-17 | 0 |  | 0 | 2009-02-17 | 2009-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-03-03 | [7 empty] | 0 |  | 0 | 2009-04-30 |  | 2009-05-07 | Online |  |  | Y
NSTAR | Canton | 1083 | 2021 | 39 | PV | 470-H7 | 2009-01-06 | 2009-01-13 | #VALUE! | 4 | #VALUE! | 2009-01-13 | 2009-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-01-12 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Waltham | 1084 | 2454 | 1200 | Diesel | 386-1356 | 2009-01-28 | 2009-02-25 | #VALUE! | 19 | #VALUE! | 2009-02-25 | 2009-04-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-07 |  | 2009-07-07 | Online |  | Private | N
NSTAR | Waltham | 1144 | 2451 | 235 | PV | 450-H7 | 2009-02-09 | 2009-02-19 | #VALUE! | 7 | #VALUE! | 2009-02-19 | 2009-03-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-03-30 |  | 2009-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-04-23 |  | 2009-04-09 | Online |  |  | N
NSTAR | Sharon | 1167 | 2067 | 20 | PV | 146-H7 | 2009-02-10 | 2010-07-08 | #VALUE! | 366 | #VALUE! | 2010-07-08 | 2010-08-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-17 |  | 2009-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Gov't | Y
NSTAR | Chelsea | 1171 | 2150 | 44 | PV | 488-H3 | 2009-02-11 | 2009-04-29 | #VALUE! | 54 | #VALUE! | 2009-04-29 | 2009-05-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-27 |  | 2009-03-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-02 |  | 2009-07-02 | Online |  | Private | Y
NSTAR | West Tisbury | 1172 | 2575 | 5 | Wind | 4-97-222 | 2009-02-17 | 2009-03-16 | #VALUE! |  | #VALUE! | 2017-10-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-05-27 | 2009-05-27 | [6 empty] | 0 |  | 0 |  |  | 2009-07-08 | Online
NSTAR | Orleans | 1176 | 2662 | 10 | Wind | 4-95B-600 | 2009-02-17 | 2010-05-12 | #VALUE! | 320 | #VALUE! | 2010-05-12 | 2010-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2009-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Brewster | 1177 | 2631 | 10 | Wind | 4-89B-89B | 2009-02-25 | 2009-02-26 | #VALUE! | 0 | #VALUE! | 2009-02-26 | 2009-04-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-07-09 | Online |  | Private | N
NSTAR | Hyannis | 1187 | 2601 | 105 | Natural Gas | 4-80B-80B | 2009-02-25 | 2009-02-26 | #VALUE! | 0 | #VALUE! | 2009-03-04 | 2009-04-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-30 |  | 2009-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2010-07-21 | Online |  | Private | N
NSTAR | Falmouth | 1189 | 2536 | 1650 | Wind | 4-98A-98A | 2009-03-10 | 2009-03-10 | 0 | 0 | 0 | 2009-03-10 | 2009-04-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-21 | Online |  | Private | N
NSTAR | Roxbury | 1198 | 2109 | 35 | PV | 323-05 | 2009-03-15 | 2009-04-02 | #VALUE! | 11 | #VALUE! | 2017-11-03 | 2009-05-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-05 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-20 | Online |  | Gov't | Y
NSTAR | Somerville | 1203 | 2143 | 48 | PV | 250-1N81H1 | 2009-03-15 | 2009-03-18 | #VALUE! | 0 | #VALUE! | 2009-03-19 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Winthrop | 1204 | 2152 | 1200 | Wind | TRM-PTC | 2009-03-20 | 2009-03-23 | #VALUE! | 0 | #VALUE! | 2009-03-24 | 2009-04-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-06 |  | 2009-05-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-06-18 | Online |  | Gov't | N
NSTAR | Norfolk | 1219 | 2056 | 95 | PV | 146-H2 | 2009-03-24 | 2009-03-30 | #VALUE! | 3 | #VALUE! | 2009-03-30 | 2009-04-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-06-23 | Online |  | Private | Y
NSTAR | Somerville | 1226 | 2144 | 85 | Natural Gas | 250-1N81H1 | 2009-03-30 | 2009-11-02 | #VALUE! | 152 | #VALUE! | 2009-11-02 | 2009-11-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-16 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-08 | Online |  | Private | N
NSTAR | Weston | 1234 | 2493 | 95 | PV | 282-H10 | 2009-04-06 | 2009-05-05 | #VALUE! | 20 | #VALUE! | 2009-05-05 | 2009-06-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-23 |  | 2009-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-11-20 | Online |  | Private | N
NSTAR | Plymouth | 1240 | 2360 | 1670 | Wind | 3-71-71 | 2009-04-08 | 2009-04-16 | #VALUE! | 4 | #VALUE! | 2009-04-16 | 2009-05-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2012-11-08 | Online |  | Private | N
NSTAR | Woburn | 1245 | 1801 | 26 | PV | 375-H6 | 2009-04-08 | 2009-04-16 | #VALUE! | 4 | #VALUE! | 2009-04-16 | 2009-05-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-26 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2009-09-03 | Online |  | Private | Y
NSTAR | Woburn | 1246 | 1801 | 30 | PV | 375-H6 | 2009-04-13 | 2009-04-17 | #VALUE! | 1 | #VALUE! | 2009-04-22 | 2009-06-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-04 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2009-12-22 | Online |  | Gov't | N
NSTAR | Walpole | 1248 | 2081 | 75 | PV | 146-H4 | 2009-04-10 | 2009-05-05 | #VALUE! | 10 | #VALUE! | 2009-05-05 | 2009-06-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 1252 | 2360 | 750 | Wind | 3-71-937 | 2009-04-17 | 2009-04-22 | #VALUE! | 0 | #VALUE! | 2009-04-22 | 2009-05-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-18 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-08-05 | Online |  | Private | Y
NSTAR | Osterville | 1253 | 2655 | 52 | PV | 4-80A-490 | 2009-04-21 | 2009-04-29 | #VALUE! | 4 | #VALUE! | 2009-04-30 | 2009-05-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-05 |  | 2009-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2008-07-30 |  | 2009-07-30 | Online |  | Gov't | N
NSTAR | Chelsea | 1265 | 2150 | 60 | PV | 488-H6 | 2009-04-29 | 2009-06-09 | #VALUE! | 27 | #VALUE! | 2009-06-15 | 2009-07-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-11-30 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | West Barnstable | 1272 | 2668 | 600 | Wind | 4-82-516 | 2009-05-07 | 2009-06-08 | #VALUE! | 22 | #VALUE! | 2009-06-08 | 2009-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-14 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-15 |  | 2011-02-16 | Online |  | Gov't | N
NSTAR | Milton | 1277 | 2186 | 75 | Natural Gas | 496-H2 | 2009-05-14 | 2009-06-18 | #VALUE! | 24 | #VALUE! | 2009-06-18 | 2009-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-15 | Online |  | Private | Y
NSTAR | Dorchester | 1283 | 2124 | 45 | PV | 496-H8 | 2009-05-21 | 2009-05-28 | #VALUE! | 1 | #VALUE! | 2009-05-29 | 2009-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-09-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-30 |  | 2009-12-30 | Online |  | Private | N
NSTAR | Cambridge | 1289 | 2139 | 75 | PV | 817-02 | 2009-05-19 | 2009-06-04 | #VALUE! | 5 | #VALUE! | 2009-06-05 | 2011-10-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-24 |  | 2009-12-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 1290 | 2360 | 750 | Wind | 3-14-911 | 2009-05-26 | 2009-06-02 | #VALUE! | 2 | #VALUE! | 2009-06-02 | 2009-06-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-29 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-09-17 | Online |  | Private | N
NSTAR | Marshfield | 1293 | 2050 | 135 | PV | 3-25-908 | 2009-05-28 | 2009-06-01 | #VALUE! | 1 | #VALUE! | 2009-06-02 | 2009-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-06 |  | 2009-08-06 | Online |  | Private | Y
NSTAR | Hyannis | 1294 | 2601 | 27 | PV | 4-63-521 | 2009-05-29 | 2009-06-02 | #VALUE! | 0 | #VALUE! | 2009-06-03 | 2009-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-10-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-02-04 | Online |  | Private | N
NSTAR | Framingham | 1297 | 1701 | 100 | PV | 433-H4 | 2009-06-10 | 2009-06-11 | #VALUE! | 1 | #VALUE! | 2009-06-11 | 2009-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online |  | Private | Y
NSTAR | New Bedford | 1303 | 2740 | 44 | PV | 2-103-103 | 2009-06-18 | 2009-09-10 | #VALUE! | 60 | #VALUE! | 2009-09-10 | 2009-10-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-31 |  | 2009-12-31 | Online |  | Gov't | N
NSTAR | Framingham | 1316 | 1701 | 75 | PV | 274-H4 | 2009-06-23 | 2009-07-01 | #VALUE! | 6 | #VALUE! | 2009-07-02 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-06-23 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Jamaica Plain | 1330 | 2130 | 150 | Natural Gas | 284-1360H2 | 2009-06-23 | 2009-06-25 | #VALUE! | 2 | #VALUE! | 2009-06-25 | 2009-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-11-24 | Online |  | Private | Y
NSTAR | Edgartown | 1335 | 2539 | 5 | Wind | 4-75-75 | 2009-06-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hopkinton | 1337 | 1748 | 2000 | Other | 126-H1 | 2009-06-29 | 2009-06-30 | #VALUE! | 1 | #VALUE! | 2009-06-30 | 2009-07-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online |  | Private | Y
NSTAR | Bellingham | 1344 | 2019 | 75 | PV | 65-H4 | 2009-06-30 | 2009-07-01 | #VALUE! | 1 | #VALUE! | 2009-07-01 | 2009-07-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-08 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-10-15 | Online |  | Private | N
NSTAR | Hopkinton | 1346 | 1748 | 177 | PV | 65-H7 | 2009-06-30 | 2009-06-30 | 0 | 0 | 0 | 2009-07-01 | 2009-08-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-13 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-10-08 | Online |  | Private | N
NSTAR | Hopkinton | 1347 | 1748 | 82 | PV | 65-H7 | 2009-07-03 | 2009-07-07 | #VALUE! | 0 | #VALUE! | 2009-07-08 | 2009-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-23 |  | 2009-09-23 | Online |  | Private | N
NSTAR | Bedford | 1353 | 1730 | 142 | PV | 512-1399H | 2009-07-22 | 2009-07-22 | 0 | 0 | 0 | 2009-07-30 | 2009-09-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-01-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online |  | Private | Y
NSTAR | Arlington | 1380 | 2474 | 52 | PV | 320-H7 | 2009-07-24 | 2009-07-30 | #VALUE! | 3 | #VALUE! | 2009-07-30 | 2009-08-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-26 |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Brighton | 1383 | 2135 | 58 | PV | 329-H5 | 2009-07-24 | 2009-07-30 | #VALUE! | 3 | #VALUE! | 2009-07-30 | 2009-08-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Brighton | 1384 | 2135 | 16 | PV | 329-H5 | 2009-07-23 | 2009-07-29 | #VALUE! | 0 | #VALUE! | 2009-07-29 | 2009-08-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-18 |  | 2009-07-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1386 | 2131 | 30 | PV | 496-H3 | 2009-07-14 | 2009-08-13 | #VALUE! | 10 | #VALUE! | 2009-08-13 | 2009-09-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-16 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2010-01-07 |  | 2010-01-07 | Online |  | Private | N
NSTAR | Dedham | 1388 | 2026 | 400 | Natural Gas | 20-H5 | 2009-07-13 | 2009-08-06 | #VALUE! | 4 | #VALUE! | 2009-08-06 | 2009-09-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-02 |  | 2009-10-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online |  | Private | N
NSTAR | Dedham | 1390 | 2026 | 75 | PV | 20-H5 | 2009-06-19 | 2009-08-03 | #VALUE! | 0 | #VALUE! | 2009-08-03 | 2009-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-02-28 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 1393 | 2360 | 1670 | Wind | 3-89-926 | 2009-08-07 | 2009-12-17 | #VALUE! | 93 | #VALUE! | 2009-12-18 | 2010-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-04 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-10 |  |  | Withdrawn |  | Gov't | N
NSTAR | Weston | 1400 | 2493 | 200 | Hydro | 282-H8 | 2009-08-07 | 2010-01-15 | #VALUE! | 114 | #VALUE! | 2010-01-15 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-05-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Milton | 1401 | 2186 | 2000 | Wind | 496-H7 | 2009-08-10 | 2009-10-14 | #VALUE! | 47 | #VALUE! | 2009-10-14 | 2009-11-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-05 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-03-02 | Online |  | Private | Y
NSTAR | Orleans | 1402 | 2653 | 85 | PV | 4-94A-632 | 2009-08-17 | 2009-08-24 | #VALUE! | 3 | #VALUE! | 2009-08-25 | 2009-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-08-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-12-17 | Online |  | Private | Y
NSTAR | Oak Bluffs | 1413 | 2557 | 39 | PV | 4-99-221 | 2009-08-25 | 2010-03-30 | #VALUE! | 153 | #VALUE! | 2010-03-30 | 2011-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-12 |  | 2011-04-15 | Online |  | Private | Y
NSTAR | Bedford | 1426 | 1730 | 75 | Natural Gas | 533-H7 | 2009-09-08 | 2009-09-16 | #VALUE! | 5 | #VALUE! | 2009-09-16 | 2009-12-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-09 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-23 | Online |  | Private | N
NSTAR | Watertown | 1435 | 2472 | 500 | PV | 467-H9 | 2009-09-08 | 2009-10-30 | #VALUE! | 37 | #VALUE! | 2009-10-30 | 2009-12-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting App Fee and/or Further Info |  | Private | N
NSTAR | Newton | 1436 | 2467 | 400 | Natural Gas | 467-H14 | 2009-09-08 | 2010-03-01 | #VALUE! | 123 | #VALUE! | 2010-03-01 | 2010-04-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-26 |  | 2010-05-26 | Online |  | Gov't | Y
NSTAR | Cambridge | 1437 | 2139 | 30 | PV | 814-14 | 2009-09-15 | 2009-09-28 | #VALUE! | 9 | #VALUE! | 2009-09-28 | 2010-10-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-12 |  | 2010-03-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-26 | Online |  | Private | N
NSTAR | Dorchester | 1440 | 2122 | 1240 | PV | 466-1482H1 | 2009-09-25 | 2009-09-30 | #VALUE! | 2 | #VALUE! | 2009-09-30 | 2009-10-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-23 |  | 2009-09-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2012-01-17 | Online |  |  | N
NSTAR | Bourne | 1450 | 2534 | 100 | PV | 4-78-409 | 2009-10-06 | 2009-10-09 | #VALUE! | 0 | #VALUE! | 2009-10-09 | 2009-10-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-11-09 | Online |  | Gov't | Y
NSTAR | Acton | 1464 | 1720 | 95 | PV | 416-H2 | 2009-10-06 | 2009-10-09 | #VALUE! | 0 | #VALUE! | 2009-10-09 | 2009-12-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2009-06-22 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-25 |  | 2010-02-25 | Online |  | Private | Y
NSTAR | Falmouth | 1465 | 2536 | 67 | PV | 4-80B-523 | 2009-10-06 | 2009-10-23 | #VALUE! | 10 | #VALUE! | 2009-10-23 | 2009-11-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-21 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-04 | Online |  | Gov't | N
NSTAR | Acton | 1466 | 1720 | 190 | PV | 416-H2 | 2009-10-09 | 2009-10-15 | #VALUE! | 2 | #VALUE! | 2009-10-15 | 2009-11-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-10 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-14 |  | 2010-01-14 | Online |  | Private | Y
NSTAR | Woburn | 1468 | 1801 | 101 | PV | 375-H11 | 2009-10-09 | 2009-10-23 | #VALUE! | 7 | #VALUE! | 2009-10-23 | 2009-11-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2009-10-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-16 | Online |  | Private | Y
NSTAR | Framingham | 1469 | 1702 | 20 | PV | 2404 | 2009-10-13 | 2009-10-23 | #VALUE! | 7 | #VALUE! | 2009-10-23 | 2009-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-11-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-02 |  | 2010-06-02 | Online |  | Private | N
NSTAR | Dartmouth | 1470 | 2747 | 95 | PV | 2-532-532 | 2009-10-16 | 2009-10-23 | #VALUE! | 1 | #VALUE! | 2009-10-23 | 2009-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-03 |  | 2009-11-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-20 |  | 2010-06-02 | Online |  | Private | Y
NSTAR | Woburn | 1483 | 1801 | 45 | PV | 375-H6 | 2009-10-21 | 2009-10-27 | #VALUE! | 3 | #VALUE! | 2009-10-27 | 2009-12-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2010-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-11 |  | 2012-02-06 | Online |  | Gov't | Y
NSTAR | Boston | 1484 | 2110 | 30 | PV | 528-129H | 2009-10-21 | 2009-11-09 | #VALUE! | 11 | #VALUE! | 2009-11-10 | 2009-12-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-11-06 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-18 |  | 2010-02-18 | Online |  | Private | Y
NSTAR | Dennisport | 1485 | 2639 | 33 | PV | 4-92B-583 | 2009-10-29 | 2009-11-03 | #VALUE! | 3 | #VALUE! | 2009-11-03 | 2009-11-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2011-04-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Bourne | 1491 | 2532 | 600 | Wind | 4-86-402 | 2009-10-30 | 2009-12-04 | #VALUE! | 24 | #VALUE! | 2009-12-07 | 2010-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  |  | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2011-01-31 | Private | N
NSTAR | Boston | 1494 | 2127 | 7200 | Natural Gas | 515-193H | 2009-11-03 | 2009-11-10 | #VALUE! | 5 | #VALUE! | 2009-11-10 | 2009-11-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-04 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-02 |  | 2010-02-02 | Online |  | Private | N
NSTAR | Lexington | 1495 | 2421 | 150 | Natural Gas | 3401 | 2009-11-05 | 2009-11-17 | #VALUE! | 8 | #VALUE! | 2009-11-17 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | n/a | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Boston | 1498 | 2118 | 6600 | Natural Gas | 376-90 | 2009-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Plymouth | 1500 | 2360 | 1650 | Wind | 3-89-926 | 2009-11-10 | 2009-11-12 | #VALUE! | 2 | #VALUE! | 2009-11-12 | 2009-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-21 |  |  | Withdrawn |  | Private | N
NSTAR | Cambridge | 1503 | 2138 | 66 | PV | 827-31 | 2009-11-13 | 2009-11-20 | #VALUE! | 4 | #VALUE! | 2009-11-20 | 2010-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2010-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-16 | Online |  | Private | N
NSTAR | Somerville | 1505 | 2143 | 75 | Natural Gas | 250-1N81H1 | 2009-11-13 | 2009-11-17 | #VALUE! | 1 | #VALUE! | 2009-11-17 | 2009-12-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-11-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-11 |  | 2010-02-11 | Online |  | Private | Y
NSTAR | East Falmouth | 1506 | 2536 | 40 | PV | 4-98A-98A | 2009-11-16 | 2009-11-17 | #VALUE! | 0 | #VALUE! | 2009-11-17 | 2009-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-07-07 | Online |  | Private | N
NSTAR | Waltham | 1507 | 2154 | 60 | Natural Gas | 33-H2 | 2009-11-16 | 2009-11-19 | #VALUE! | 2 | #VALUE! | 2009-11-19 | 2009-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-04 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online |  | Gov't | Y
NSTAR | Eastham | 1508 | 2642 | 80 | PV | 4-94B-646 | 2009-11-13 | 2009-11-17 | #VALUE! | 0 | #VALUE! | 2009-12-03 | 2009-12-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-24 |  | 2010-02-24 | Online |  | Private | Y
NSTAR | Waltham | 1509 | 2453 | 272 | PV | 282-H8 | 2009-10-16 | 2009-11-17 | #VALUE! | 0 | #VALUE! | 2009-11-24 | 2009-12-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online |  | Private | N
NSTAR | Jamaica Plain | 1510 | 2130 | 75 | Natural Gas | 350-H2 | 2009-10-16 | 2009-11-18 | #VALUE! | 0 | #VALUE! | 2009-11-19 | 2009-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-02-01 | Online |  | Private | Y
NSTAR | Newton | 1511 | 2459 | 36 | PV | 467-H5 | 2009-10-18 | 2009-11-18 | #VALUE! | 0 | #VALUE! | 2009-12-03 | 2010-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-06 |  | 2010-05-06 | Online |  | Private | Y
NSTAR | Somerville | 1512 | 2145 | 198 | PV | 250-1N81H1 | 2009-11-17 | 2009-11-23 | #VALUE! | 2 | #VALUE! | 2009-11-24 | 2009-12-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online |  | Private | N
NSTAR | Needham | 1513 | 1730 | 75 | Natural Gas | 148-H1 | 2009-11-19 | 2009-11-19 | 0 | 0 | 0 | 2009-11-20 | 2009-12-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2010-01-28 | Online |  | Private | Y
NSTAR | Westport | 1514 | 2790 | 34 | PV | 2-523-523 | 2009-11-20 | 2009-12-03 | #VALUE! | 9 | #VALUE! | 2009-12-03 | 2010-01-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-02 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-13 |  | 2010-05-13 | Online |  | Private | Y
NSTAR | Dedham | 1516 | 2026 | 167 | PV | 13-H1 | 2009-11-25 | 2009-11-27 | #VALUE! | 0 | #VALUE! | 2009-12-03 | 2010-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-12-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-07-22 |  | 2010-07-22 | Online |  | Gov't | Y
NSTAR | Brewster | 1520 | 2631 | 101 | PV | 4-89B-573 | 2009-11-25 | 2009-11-27 | #VALUE! | 0 | #VALUE! | 2009-12-03 | 2009-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online |  | Gov't | Y
NSTAR | Eastham | 1521 | 2642 | 101 | PV | 4-94A-648 | 2009-11-25 | 2009-11-27 | #VALUE! | 0 | #VALUE! | 2009-12-03 | 2010-01-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-16 |  | 2010-07-16 | Online |  | Gov't | Y
NSTAR | Brewster | 1522 | 2631 | 101 | PV | 4-89B-573 | 2009-12-03 | 2009-12-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | East Falmouth | 1526 | 2540 | 20 | PV | 4-98A-98A | 2009-12-02 | 2009-12-15 | #VALUE! | 9 | #VALUE! | 2009-12-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Wellfleet | 1527 | 2667 | 1650 | Wind | 4-94B-653 | 2009-11-30 | 2009-12-17 | #VALUE! | 6 | #VALUE! | 2009-12-18 | 2010-01-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-05 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Kingston | 1531 | 2364 | 100 | Wind | 3-17-913 | 2009-12-16 | 2010-01-18 | #VALUE! | 22 | #VALUE! | 2010-01-18 | 2010-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-22 |  | 2009-12-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-07 |  | 2010-04-07 | Online |  | Private | Y
NSTAR | Framingham | 1534 | 1702 | 63 | PV | 240-H4 | 2009-12-16 | 2009-12-22 | #VALUE! | 2 | #VALUE! | 2009-12-23 | 2010-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-11 |  | 2010-03-11 | Online |  | Private | Y
NSTAR | Dartmouth | 1535 | 2748 | 32 | PV | 2-532-532 | 2009-12-17 | 2010-01-12 | #VALUE! | 16 | #VALUE! | 2010-01-12 | 2010-02-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-12 |  | 2010-02-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-03-25 | Online |  | Gov't | N
NSTAR | Medway | 1536 | 2053 | 134 | PV | 65-H5 | 2009-12-17 | 2010-01-05 | #VALUE! | 11 | #VALUE! | 2010-01-05 | 2010-01-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-04-08 | Online |  | Private | Y
NSTAR | Plymouth | 1537 | 2360 | 30 | PV | 3-73-938 | 2009-12-22 | 2010-10-19 | #VALUE! | 215 | #VALUE! | 2010-10-19 | 2010-10-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-10-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | South Dartmouth | 1541 | 2748 | 750 | Wind | 2-528-528 | 2010-01-04 | 2010-01-07 | #VALUE! | 1 | #VALUE! | 2010-01-07 | 2010-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2010-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2010-04-01 | Online |  | Private | Y
NSTAR | Cambridge | 1544 | 2141 | 29 | PV | 811-37 | 2010-01-05 | 2010-06-30 | #VALUE! | 123 | #VALUE! | 2010-06-30 | 2010-09-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-06-01 |  | 2011-06-01 | Online |  | Gov't | N
NSTAR | Hyannis | 1545 | 2601 | 200 | Wind | 4-80B-523 | 2010-01-05 | 2010-01-12 | #VALUE! | 2 | #VALUE! | 2010-01-12 | 2010-02-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-10 |  | 2010-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-26 |  | 2011-04-28 | Online |  | Private | N
NSTAR | Dorchester | 1546 | 2125 | 75 | Natural Gas | 483-08 | 2010-01-06 | 2010-01-27 | #VALUE! | 12 | #VALUE! | 2010-01-27 | 2010-04-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-09 | Online |  | Private | N
NSTAR | Plymouth | 1547 | 2360 | 250 | PV | 3-13-943 | 2010-01-06 | 2010-03-03 | #VALUE! | 37 | #VALUE! | 2010-03-03 | 2010-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  | 2010-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-22 |  | 2012-03-30 | Online |  | Private | Y
NSTAR | New Bedford | 1548 | 2740 | 39 | PV | 2-38-38 | 2010-01-08 | 2010-02-01 | #VALUE! | 12 | #VALUE! | 2010-02-01 | 2010-03-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-02-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-04-21 | Online |  | Private | Y
NSTAR | Bourne | 1550 | 2532 | 27 | PV | 4-81A-81A | 2010-01-11 | 2010-01-27 | #VALUE! | 9 | #VALUE! | 2010-01-27 | 2010-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-05 |  | 2010-05-05 | Online |  | Private | N
NSTAR | Boston | 1554 | 2122 | 170 | PV | 106-H4 | 2010-01-08 | 2010-01-28 | #VALUE! | 12 | #VALUE! | 2010-01-28 | 2010-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-31 |  | 2010-03-31 | Online |  | Gov't | N
NSTAR | Bourne | 1555 | 2532 | 28 | PV | 3-88-923 | 2010-01-15 | 2010-06-10 | #VALUE! | 103 | #VALUE! | 2010-06-18 | 2010-07-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | South Dartmouth | 1559 | 2748 | 3340 | Wind | 2-531-531 | 2010-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2010-01-22 | Online |  | Private | Y
NSTAR | Bourne | 1562 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bourne | 1563 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bourne | 1564 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bourne | 1565 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-29 | 2010-02-02 | #VALUE! | 0 | #VALUE! | 2010-02-02 | 2010-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-02-22 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dennis | 1569 | 2660 | 150 | PV | 4-92B-92B | 2010-02-01 | 2010-02-04 | #VALUE! | 1 | #VALUE! | 2010-02-04 | 2010-03-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-15 |  | 2010-07-15 | Online |  | Gov't | Y
NSTAR | Harwich | 1571 | 2645 | 104 | PV | 4-95A-95A | 2010-02-01 | 2010-02-04 | #VALUE! | 1 | #VALUE! | 2010-02-04 | 2010-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-22 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-14 | Online |  | Gov't | Y
NSTAR | Bourne | 1572 | 2532 | 143 | PV | 4-86-402 | 2010-02-04 | 2010-02-12 | #VALUE! | 6 | #VALUE! | 2010-02-16 | 2010-03-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-29 |  | 2010-04-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online |  | Private | Y
NSTAR | Canton | 1573 | 2021 | 155 | PV | 470-H10 | 2010-02-04 | 2010-02-25 | #VALUE! | 15 | #VALUE! | 2010-02-25 | 2010-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-14 |  | 2010-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Response and/or Cost Estimates from Eng | 2011-05-09 | Private | Y
NSTAR | Charlestown | 1574 | 2129 | 555 | Diesel | 10-H1 | 2010-02-16 | 2010-02-17 | #VALUE! | 1 | #VALUE! | 2010-02-17 | 2010-03-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-04-12 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online |  | Gov't | Y
NSTAR | Ashland | 1580 | 1721 | 21 | PV | 274-1429H1 | 2010-02-11 | 2010-02-24 | #VALUE! | 5 | #VALUE! | 2010-02-25 | 2010-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | N
NSTAR | Boston | 1581 | 2128 | 200 | PV | 592-70H | 2010-02-18 | 2010-02-23 | #VALUE! | 3 | #VALUE! | 2010-02-24 | 2010-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online |  | Gov't | Y
NSTAR | Watertown | 1582 | 2472 | 28 | PV | 467-H8 | 2010-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bourne | 1583 | 2532 | 1500 | Wind | 3-88-923 | 2010-03-01 | 2010-03-02 | #VALUE! | 1 | #VALUE! | 2010-03-03 | 2010-03-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-29 |  |  | Withdrawn |  | Gov't | Y
NSTAR | Fairhaven | 1585 | 2719 | 85 | PV | 2-221-221 | 2010-03-01 | 2010-03-08 | #VALUE! | 4 | #VALUE! | 2010-08-02 | 2010-08-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Wareham | 1587 | 2571 | 4398 | PV | 3-83-83 | 2010-03-03 | 2010-03-08 | #VALUE! | 3 | #VALUE! | 2010-03-08 | 2011-04-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-01-28 | Withdrawn |  | Private | Y
NSTAR | Framingham | 1588 | 1702 | 60 | Natural Gas | 2401 | 2010-03-12 | 2010-03-24 | #VALUE! | 8 | #VALUE! | 2010-03-25 | 2010-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-10 |  | 2010-06-10 | Online |  | Private | Y
NSTAR | Walpole | 1589 | 2081 | 104 | PV | 146-H6 | 2010-03-12 | 2010-03-26 | #VALUE! | 10 | #VALUE! | 2010-03-26 | 2010-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-14 | Online |  | Private | Y
NSTAR | Woburn | 1590 | 1801 | 30 | PV | 375-H9 | 2010-03-19 | 2010-03-23 | #VALUE! | 2 | #VALUE! | 2010-03-24 | 2010-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2010-05-03 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-05 |  | 2010-08-05 | Online |  | Private | Y
NSTAR | Hyannis | 1591 | 2601 | 259 | PV | 4-84B-524 | 2010-03-22 | 2010-03-24 | #VALUE! | 2 | #VALUE! | 2010-07-30 | 2010-10-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-03-09 |  | 2010-08-05 | Online |  | Private | Y
NSTAR | New Bedford | 1592 | 2740 | 1600 | PV | 4-107-107 | 2010-03-22 | 2010-03-31 | #VALUE! | 7 | #VALUE! | 2010-03-31 | 2010-07-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-04-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | North Dartmouth | 1593 | 2747 | 1500 | PV | 2-541-541 | 2010-03-23 | 2010-03-26 | #VALUE! | 3 | #VALUE! | 2010-03-26 | 2010-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-10 |  | 2010-03-26 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-09 |  |  |  |  | Private | Y
NSTAR | Falmouth | 1594 | 2536 | 50 | PV | 4-76-437 | 2010-03-25 | 2010-04-01 | #VALUE! | 5 | #VALUE! | 2010-04-01 | 2010-05-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2010-05-30 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2012-02-14 | Online |  | Gov't | Y
NSTAR | Falmouth | 1595 | 2540 | 1650 | Wind | 4-98A-98A | 2010-03-29 | 2010-04-01 | #VALUE! | 3 | #VALUE! | 2010-04-01 | 2010-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-14 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-15 |  | 2012-02-14 | Online |  | Private | N
NSTAR | Needham | 1596 | 2494 | 78 | PV | 292-H10 | 2010-03-31 | 2010-04-01 | #VALUE! | 1 | #VALUE! | 2010-04-01 | 2010-05-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-12 |  | 2010-05-21 | No | STD |  |  |  | 0 | 0 | 0 | 2010-10-15 |  | 2010-10-15 | Online |  | Private | Y
NSTAR | Mashpee | 1597 | 2649 | 141 | PV | 4-88-453 | 2010-04-02 | 2010-04-09 | #VALUE! | 5 | #VALUE! | 2010-04-09 | 2010-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-30 |  | 2010-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2010-07-21 |  | 2010-07-21 | Online |  | Private | Y
NSTAR | Sandwich | 1598 | 2537 | 29 | PV | 4-87A-471 | 2010-04-09 | 2010-04-16 | #VALUE! | 5 | #VALUE! | 2010-04-20 | 2010-05-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-27 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-12-16 | Online |  | Gov't | N
NSTAR | Milton | 1600 | 2186 | 60 | PV | 362-02 | 2010-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Hyannis | 1601 | 2601 | 48 | PV | 4-80B-80B | 2010-04-21 | 2010-04-21 | 0 | 0 | 0 | 2010-05-18 | 2010-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-07 |  | 2010-10-07 | Online |  | Private | Y
NSTAR | Hyannis | 1602 | 2601 | 60 | PV | 4-80B-80B | 2010-04-21 | 2010-05-18 | #VALUE! | 19 | #VALUE! | 2010-05-18 | 2010-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online |  | Private | Y
NSTAR | Hyannis | 1603 | 2601 | 40 | PV | 4-84B-524 | 2010-04-21 | 2010-05-05 | #VALUE! | 10 | #VALUE! | 2010-05-05 | 2010-06-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
NSTAR | Somerville | 1604 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | #VALUE! | 10 | #VALUE! | 2010-05-05 | 2010-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-30 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
NSTAR | Somerville | 1605 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | #VALUE! | 10 | #VALUE! | 2010-05-05 | 2010-06-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
NSTAR | Somerville | 1606 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-06-07 | #VALUE! | 33 | #VALUE! | 2010-06-07 | 2010-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online |  | Gov't | N
NSTAR | Dorchester | 1608 | 2121 | 36 | PV | 143-151H1 | 2010-04-21 | 2010-06-07 | #VALUE! | 33 | #VALUE! | 2010-06-07 | 2010-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online |  | Gov't | Y
NSTAR | Dorchester | 1609 | 2122 | 45 | PV | 466-1481H1 | 2010-04-23 | 2010-05-17 | #VALUE! | 16 | #VALUE! | 2010-05-18 | 2010-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-10 | Online |  | Gov't | Y
NSTAR | Watertown | 1610 | 2472 | 34 | PV | 467-H9 | 2010-04-23 | 2010-05-24 | #VALUE! | 21 | #VALUE! | 2010-05-25 | 2010-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-09 |  | 2010-08-09 | Online |  | Gov't | Y
NSTAR | Newton | 1611 | 2460 | 30 | PV | 17-H1 | 2010-04-23 | 2010-05-10 | #VALUE! | 11 | #VALUE! | 2010-08-26 | 2010-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-14 |  | 2010-05-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-20 |  | 2010-10-22 | Online |  | Private | Y
NSTAR | Hopkinton | 1612 | 1748 | 29 | PV | 126-H1 | 2010-04-26 | 2010-05-11 | #VALUE! | 11 | #VALUE! | 2010-05-12 | 2010-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-22 | Online |  | Private | Y
NSTAR | Mashpee | 1613 | 2649 | 192 | PV | 4-88-453 | 2010-04-28 | 2010-05-03 | #VALUE! | 3 | #VALUE! | 2010-05-03 | 2010-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-07-16 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-08 |  | 2011-03-08 | Online |  | Gov't | N
NSTAR | Freetown | 1614 | 2717 | 82 | PV | 2-102-102 | 2010-04-28 | 2010-05-03 | #VALUE! | 3 | #VALUE! | 2010-05-03 | 2010-07-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-22 |  | 2011-03-25 | Online |  | Gov't | Y
NSTAR | Bourne | 1615 | 2532 | 50 | Wind | 4-79-79 | 2010-04-29 | 2010-05-10 | #VALUE! | 7 | #VALUE! | 2010-05-12 | 2010-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-05-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-29 |  | 2010-09-29 | Online |  | Gov't | Y
NSTAR | Boston | 1616 | 2126 | 11 | PV | 496-H8 | 2010-04-30 | 2010-05-12 | #VALUE! | 8 | #VALUE! | 2010-05-12 | 2010-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-05-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-26 |  | 2011-05-09 | Online |  | Gov't | Y
NSTAR | Hyannis | 1617 | 2601 | 14 | PV | 4-63-905 | 2010-05-03 | 2010-05-12 | #VALUE! | 7 | #VALUE! | 2010-05-12 | 2010-06-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online |  | Gov't | Y
NSTAR | Barnstable | 1618 | 2601 | 131 | PV | 4-80B-514 | 2010-05-04 | 2010-06-08 | #VALUE! | 25 | #VALUE! | 2010-06-08 | 2010-08-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
NSTAR | Westport | 1619 | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | #VALUE! | 25 | #VALUE! | 2010-06-08 | 2010-08-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
NSTAR | Westport | 1620 | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | #VALUE! | 25 | #VALUE! | 2010-06-08 | 2010-08-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
NSTAR | Westport | 1621 | 2790 | 10 | Wind | 2-523-523 | 2010-05-07 | 2011-10-03 | #VALUE! | 366 | #VALUE! | 2011-10-03 | 2011-11-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-08-28 | 2013-08-28 | 2013-09-19 | Online |  | Gov't | N
NSTAR | Dartmouth | 1622 | 2747 | 2150 | Natural Gas | 2-525-525 | 2010-05-07 | 2010-05-11 | #VALUE! | 2 | #VALUE! | 2010-05-12 | 2010-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-23 |  | 2010-11-23 | Online |  | Gov't | N
NSTAR | Boston | 1623 | 2119 | 242 | PV | 106-H4 | 2010-05-12 | 2010-05-25 | #VALUE! | 9 | #VALUE! | 2010-05-25 | 2010-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-09 |  | 2010-09-09 | Online |  | Private | Y
NSTAR | Holliston | 1624 | 1746 | 50 | PV | 274-H3 | 2010-05-17 | 2010-05-26 | #VALUE! | 7 | #VALUE! | 2010-05-26 | 2010-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2011-02-24 | Online |  | Private | Y
NSTAR | Hyannis | 1625 | 2601 | 25 | PV | 4-80B-523 | 2010-05-18 | 2010-05-25 | #VALUE! | 5 | #VALUE! | 2010-05-25 | 2010-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online |  | Private | Y
NSTAR | West Roxbury | 1626 | 2132 | 37 | PV | 374-04 | 2010-05-21 | 2010-05-25 | #VALUE! | 2 | #VALUE! | 2010-05-25 | 2010-06-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-07-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-08-13 | Online |  | Private | Y
NSTAR | Yarmouth | 1627 | 2664 | 183 | PV | 4-64-558 | 2010-05-24 | 2010-05-26 | #VALUE! | 2 | #VALUE! | 2010-05-27 | 2010-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-05-04 | Online |  | Private | N
NSTAR | Boston | 1628 | 2118 | 177 | PV | 323-02 | 2010-05-27 | 2010-06-01 | #VALUE! | 3 | #VALUE! | 2010-06-01 | 2010-07-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-03 | Online |  | Private | Y
NSTAR | Cambridge | 1629 | 2142 | 75 | Natural Gas | 875-1N35B | 2010-05-27 | 2010-06-02 | #VALUE! | 4 | #VALUE! | 2010-06-02 | 2010-07-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-08 |  | 2010-09-02 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-18 |  | 2010-11-18 | Online |  | Private | Y
NSTAR | Brighton | 1630 | 2135 | 75 | Natural Gas | 329-H7 | 2010-06-01 | 2010-06-03 | #VALUE! | 2 | #VALUE! | 2010-06-03 | 2010-07-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-06-21 | Online |  | Private | Y
NSTAR | Cambridge | 1631 | 2142 | 85 | Natural Gas | 875-1N39A | 2010-06-01 | 2010-06-04 | #VALUE! | 3 | #VALUE! | 2010-06-04 | 2010-07-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-07 | Online |  | Private | Y
NSTAR | New Bedford | 1632 | 2744 | 177 | PV | 2-6-17 | 2010-06-04 | 2010-07-26 | #VALUE! | 36 | #VALUE! | 2010-08-26 | 2010-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-03-01 | Online |  | Gov't | Y
NSTAR | Cambridge | 1633 | 2140 | 41 | PV | 826-28 | 2010-06-09 | 2010-06-18 | #VALUE! | 6 | #VALUE! | 2010-06-18 | 2010-07-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-30 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-14 |  | 2010-12-14 | Online |  | Gov't | Y
NSTAR | Acton | 1634 | 1720 | 60 | PV | 416-H4 | 2010-06-09 | 2010-06-10 | #VALUE! | 0 | #VALUE! | 2010-06-10 | 2010-07-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-30 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Brewster | 1635 | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-16 | 2010-08-13 | #VALUE! | 42 | #VALUE! | 2010-08-19 | 2011-01-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-17 |  | 2011-02-17 | Online |  | Private | N
NSTAR | Framingham | 1636 | 1701 | 2000 | Diesel | Sta 175 | 2010-06-16 | 2010-06-18 | #VALUE! | 2 | #VALUE! | 2010-06-18 | 2010-07-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-08 |  | 2010-11-10 | Online |  | Private | Y
NSTAR | Framingham | 1637 | 2030 | 110 | PV | 2410 | 2010-06-17 | 2010-06-25 | #VALUE! | 6 | #VALUE! | 2010-07-01 | 2010-08-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-13 |  | 2010-10-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-10-14 |  | 2011-10-14 | Online |  | Private | Y
NSTAR | Charlestown | 1638 | 2129 | 1500 | Wind | 387-148H1 | 2010-06-28 | 2010-07-02 | #VALUE! | 4 | #VALUE! | 2010-07-07 | 2010-08-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-10-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-11-01 | Online |  | Gov't | Y
NSTAR | Wellfleet | 1639 | 2667 | 52 | PV | 4-94B-653 | 2010-06-22 | 2010-07-16 | #VALUE! | 19 | #VALUE! | 2010-07-16 | 2010-08-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Brewster | 1640 | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-29 | 2010-07-06 | #VALUE! | 5 | #VALUE! | 2010-07-06 | 2010-08-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-10-14 | Online |  | Gov't | N
NSTAR | Dorchester | 1641 | 2125 | 197 | PV | 483-01 | 2010-06-29 | 2010-07-02 | #VALUE! | 3 | #VALUE! | 2010-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Plymouth | 1642 | 2532 | 10000 | Wind | 221 | 2010-06-29 | 2010-07-02 | #VALUE! | 3 | #VALUE! | 2010-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Bourne | 1643 | 2532 | 15000 | Wind | 4-81A-81A | 2010-07-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Boston | 1644 | 2116 | 195 | Natural Gas | 71-1N35 | 2010-07-09 | 2010-07-13 | #VALUE! | 2 | #VALUE! | 2010-07-13 | 2010-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
NSTAR | Mattapan | 1645 | 2126 | 38 | PV | 311-05 | 2010-07-09 | 2010-07-14 | #VALUE! | 3 | #VALUE! | 2010-07-14 | 2010-08-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-06 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
NSTAR | Mattapan | 1646 | 2126 | 14 | PV | 311-05 | 2010-07-09 | 2010-07-14 | #VALUE! | 3 | #VALUE! | 2010-07-14 | 2010-08-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
NSTAR | Mattapan | 1647 | 2126 | 15 | PV | 311-05 | 2010-07-13 | 2010-07-22 | #VALUE! | 7 | #VALUE! | 2010-07-22 | 2010-09-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-31 |  | 2012-01-31 | Online |  | Gov't | N
NSTAR | Hyannis | 1648 | 2601 | 766 | PV | 4-80B-523 | 2010-07-14 | 2010-07-28 | #VALUE! | 10 | #VALUE! | 2010-08-02 | 2010-09-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2012-01-31 | Online |  | Gov't | Y
NSTAR | Dennis | 1649 | 2660 | 30 | PV | 4-92B-92B | 2010-07-14 | 2010-07-29 | #VALUE! | 11 | #VALUE! | 2010-07-30 | 2010-10-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2011-01-21 | Online |  | Private | Y
NSTAR | Dennis | 1650 | 2660 | 82 | PV | 4-92B-92B | 2010-07-15 | 2010-08-05 | #VALUE! | 14 | #VALUE! | 2010-08-05 | 2010-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-12-06 | Online |  | Private | Y
NSTAR | Chelsea | 1652 | 2150 | 175 | PV | 488-H2 | 2010-07-19 | 2010-08-30 | #VALUE! | 30 | #VALUE! | 2010-08-31 | 2010-12-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2011-02-08 | Online |  | Gov't | Y
NSTAR | Norfolk | 1653 | 2056 | 82 | PV | 146-H9 | 2010-07-19 | 2010-08-06 | #VALUE! | 14 | #VALUE! | 2010-08-09 | 2010-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-03 |  | 2010-07-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-06-12 |  | 2011-07-14 | Online |  | Gov't | N
NSTAR | Walpole | 1654 | 2081 | 95 | PV | 146-H4 | 2010-07-19 | 2010-08-06 | #VALUE! | 14 | #VALUE! | 2010-08-09 | 2010-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-16 |  | 2011-03-21 | Online |  | Gov't | Y
NSTAR | Norfolk | 1655 | 2056 | 142 | PV | 146-H2 | 2010-07-23 | 2010-08-13 | #VALUE! | 15 | #VALUE! | 2010-08-18 | 2010-09-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-02-08 |  | 2012-02-08 | Online |  | Gov't | Y
NSTAR | Kingston | 1656 | 2364 | 6000 | Wind | 3-17-913 | 2010-07-27 | 2010-08-17 | #VALUE! | 14 | #VALUE! | 2010-08-17 | 2010-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-28 | Online |  | Gov't | Y
NSTAR | Wellfleet | 1657 | 2667 | 28 | PV | 4-96-677 | 2010-07-29 | 2010-08-17 | #VALUE! | 13 | #VALUE! | 2010-08-17 | 2010-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-18 |  | 2011-02-18 | Online |  | Private | Y
NSTAR | Walpole | 1658 | 2081 | 28 | PV | 2-105-105 | 2010-07-30 | 2010-08-17 | #VALUE! | 12 | #VALUE! | 2010-08-17 | 2010-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-29 | Online |  | Private | Y
NSTAR | New Bedford | 1659 | 2745 | 16 | PV | 2-105-105 | 2010-08-02 | 2010-08-16 | #VALUE! | 10 | #VALUE! | 2010-08-16 | 2010-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | Online |  | Private | Y
NSTAR | Westport | 1660 | 2791 | 7 | PV | 2-523-523 | 2010-08-01 | 2010-08-13 | #VALUE! | 7 | #VALUE! | 2010-08-16 | 2010-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-16 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-16 | Online |  | Private | Y
NSTAR | Edgartown | 1661 | 2539 | 42 | PV | 4-99-223 | 2010-08-03 | 2010-08-12 | #VALUE! | 5 | #VALUE! | 2010-08-18 | 2010-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-13 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Online |  | Gov't | Y
NSTAR | South Dennis | 1662 | 2660 | 100 | Wind | 4-92B-92B | 2010-08-06 | 2010-08-19 | #VALUE! | 5 | #VALUE! | 2010-08-19 | 2010-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-01 | Online |  | Gov't | N
NSTAR | Fairhaven | 1663 | 2719 | 1500 | Wind | 2-220-220 | 2010-08-06 | 2010-08-13 | #VALUE! | 1 | #VALUE! | 2010-08-18 | 2010-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-05-01 | Online |  | Gov't | N
NSTAR | Fairhaven | 1664 | 2719 | 1500 | Wind | 2-220-220 | 2010-08-17 | 2010-08-25 | #VALUE! | 5 | #VALUE! | 2010-08-26 | 2010-10-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2012-05-03 | Online |  | Gov't | Y
NSTAR | Hopkinton | 1665 | 1748 | 36 | PV | 65-H7 | 2010-08-18 | 2010-08-27 | #VALUE! | 6 | #VALUE! | 2010-08-27 | 2010-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2011-01-19 | Online |  | Private | Y
NSTAR | Woburn | 1666 | 1801 | 60 | PV | 375-H11 | 2010-08-20 | 2010-09-01 | #VALUE! | 8 | #VALUE! | 2010-09-01 | 2010-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-13 |  | 2010-10-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-04-27 | Online |  | Private | Y
NSTAR | Jamaica Plain | 1667 | 2130 | 75 | PV | 350-H2 | 2010-08-23 | 2011-08-01 | #VALUE! | 245 | #VALUE! | 2011-08-01 | 2011-09-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-02-24 | Online |  | Gov't | Y
NSTAR | Cambridge | 1668 | 2139 | 30 | PV | 819-1NB2 | 2010-08-20 | 2010-09-15 | #VALUE! | 17 | #VALUE! | 2010-09-15 | 2010-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2012-12-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Bourne | 1669 | 2532 | 2000 | Wind | 4-81A-81A | 2010-08-24 | 2010-08-30 | #VALUE! | 4 | #VALUE! | 2010-09-01 | 2010-10-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-24 |  | 2011-03-25 | Online |  | Private | Y
NSTAR | Mattapoisett | 1670 | 2739 | 164 | PV | 2-304-304 | 2010-08-24 | 2010-08-26 | #VALUE! | 2 | #VALUE! | 2010-08-26 | 2010-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-21 | Online |  | Private | Y
NSTAR | Fairhaven | 1671 | 2719 | 100 | PV | 2-220-201 | 2010-08-24 | 2010-08-26 | #VALUE! | 2 | #VALUE! | 2010-08-26 | 2010-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-02 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-05-29 | Online |  | Private | N
NSTAR | Dartmouth | 1672 | 2747 | 1000 | PV | 2-532-532 | 2010-08-26 | 2010-09-02 | #VALUE! | 4 | #VALUE! | 2010-09-02 | 2010-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-29 |  | 2012-05-25 | Online |  | Private | Y
NSTAR | Cambridge | 1673 | 2138 | 75 | PV | 828-1104H1 | 2010-09-09 | 2010-09-17 | #VALUE! | 5 | #VALUE! | 2010-09-17 | 2010-10-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-10 | Online |  | Gov't | Y
NSTAR | Edgartown | 1674 | 2539 | 15 | PV | 4-99-99 | 2010-09-13 | 2010-09-22 | #VALUE! | 7 | #VALUE! | 2011-01-24 | 2011-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-25 |  | 2010-03-28 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-05-19 | Online |  | Private | Y
NSTAR | Vineyard Haven | 1675 | 2568 | 72 | PV | 4-91-222 | 2010-09-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wareham | 1676 | 2571 | 11500 | Wind | 3-83-966 | 2010-09-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wareham | 1677 | 2571 | 4600 | Wind | 3-85-928 | 2010-09-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wareham | 1678 | 2571 | 2300 | Wind | 3-83-966 | 2010-09-15 | 2010-09-20 | #VALUE! | 2 | #VALUE! | 2010-09-20 | 2010-10-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-11-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-12-23 | Online |  | Private | Y
NSTAR | Hopkinton | 1679 | 1748 | 20 | PV | 126-H1 | 2010-09-15 | 2010-09-22 | #VALUE! | 4 | #VALUE! | 2010-09-22 | 2010-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-12-15 | Online |  | Gov't | Y
NSTAR | Watertown | 1680 | 2742 | 50 | PV | 467-H4 | 2010-09-21 | 2010-09-28 | #VALUE! | 4 | #VALUE! | 2010-10-04 | 2010-11-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-19 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-11-30 | Online |  | Private | Y
NSTAR | Falmouth | 1681 | 2540 | 75 | PV | 4-72-72 | 2010-09-21 | 2010-09-28 | #VALUE! | 4 | #VALUE! | 2010-10-04 | 2010-11-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-02 |  | 2010-12-02 | Online |  | Gov't | Y
NSTAR | Acusnet | 1682 | 2743 | 20 | PV | 2-241-237 | 2010-09-21 | 2010-09-28 | #VALUE! | 3 | #VALUE! | 2010-10-04 | 2010-11-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-08 | Online |  | Private | Y
NSTAR | North Falmouth | 1683 | 2556 | 43 | PV | 4-78-420 | 2010-09-20 | 2010-09-30 | #VALUE! | 2 | #VALUE! | 2010-10-01 | 2010-11-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-10-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-25 |  | 2011-02-02 | Online |  | Private | Y
NSTAR | Dartmouth | 1684 | 2748 | 95 | PV | 2-524-524 | 2010-09-27 | 2010-10-14 | #VALUE! | 9 | #VALUE! | 2010-10-14 | 2010-12-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-03-10 | Online |  | Private | Y
NSTAR | Dartmouth | 1685 | 2790 | 70 | PV | 2-523-523 | 2010-09-22 | 2010-10-01 | #VALUE! | 2 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
NSTAR | South Dartmouth | 1686 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | #VALUE! | 2 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
NSTAR | South Dartmouth | 1687 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | #VALUE! | 2 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
NSTAR | South Dartmouth | 1689 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | #VALUE! | 2 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
NSTAR | South Dartmouth | 1690 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | #VALUE! | 2 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
NSTAR | South Dartmouth | 1691 | 2748 | 14 | PV | 2-53-65 | 2010-09-24 | 2010-11-02 | #VALUE! | 23 | #VALUE! | 2010-11-02 | 2010-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-29 |  | 2011-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-11-08 |  | 2011-11-08 | Online |  | Gov't | N
NSTAR | Bourne | 1692 | 2542 | 3000 | Wind | 3-88-923 | 2010-09-28 | 2010-10-01 | #VALUE! | 0 | #VALUE! | 2010-10-25 | 2010-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Gov't | Y
NSTAR | South Dartmouth | 1693 | 2748 | 17 | PV | 2-53-65 | 2010-09-27 | 2010-10-14 | #VALUE! | 9 | #VALUE! | 2010-10-15 | 2010-11-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-08 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-04 | Online |  | Private | Y
NSTAR | Needham | 1694 | 2492 | 15 | PV | 148-H1 | 2010-10-01 | 2010-10-19 | #VALUE! | 11 | #VALUE! | 2010-10-20 | 2010-12-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-30 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-08-22 |  | 2011-09-08 | Online |  | Private | Y
NSTAR | Canton | 1695 | 2021 | 261.45 | PV | 470-H4 | 2010-10-01 | 2010-10-18 | #VALUE! | 10 | #VALUE! | 2010-10-20 | 2011-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-09-01 | Online |  | Private | Y
NSTAR | Plymouth | 1696 | 2360 | 95 | PV | 3-14-911 | 2010-10-07 | 2010-10-20 | #VALUE! | 4 | #VALUE! | 2010-10-20 | 2010-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-10-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-04-08 | Online |  | Private | Y
NSTAR | Falmouth | 1697 | 2536 | 95 | PV | 4-98A-98A | 2010-10-01 | 2010-10-22 | #VALUE! | 13 | #VALUE! | 2010-10-22 | 2011-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hopkinton | 1698 | 1748 | 2250 | Natural Gas | 455-H3 | 2010-09-01 | 2010-11-12 | #VALUE! | 26 | #VALUE! | 2010-11-18 | 2010-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dorchester | 1700 | 2122 | 65 | Natural Gas | 466-1482H1 | 2009-10-01 | 2010-11-09 | #VALUE! | 19 | #VALUE! | 2010-11-09 | 2010-12-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-13 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-03-04 |  | 2011-03-07 | Online |  | Gov't | N
NSTAR | Boston | 1701 | 2222 | 28 | PV | 2-1N43 | 2010-10-18 | 2010-10-19 | #VALUE! | 1 | #VALUE! | 2010-10-19 | 2010-10-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-21 |  | 2010-10-25 | Online |  | Private | Y
NSTAR | Fairhaven | 1702 | 2719 | 30 | PV | 2-220-201 | 2010-10-15 | 2010-10-25 | #VALUE! | 4 | #VALUE! | 2010-10-26 | 2010-12-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Milton | 1703 | 2186 | 2000 | Wind | 362-02 | 2010-10-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Cambridge | 1705 | 2139 | 1500 | Natural Gas | 813-36 | 2010-10-18 | 2011-04-04 | #VALUE! | 118 | #VALUE! | 2011-04-04 | 2011-05-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | Y
NSTAR | East Boston | 1706 | 2128 | 82 | PV | 592-72XY | 2010-10-20 | 2010-11-04 | #VALUE! | 9 | #VALUE! | 2010-11-08 | 2010-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-20 |  | 2010-11-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-02-14 | Online |  | Private | Y
NSTAR | Dartmouth | 1707 | 2747 | 33 | PV | 2-543-543 | 2010-10-24 | 2010-11-16 | #VALUE! | 16 | #VALUE! | 2010-11-16 | 2010-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-22 |  | 2010-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-28 | Online |  | Private | Y
NSTAR | Framingham | 1708 | 1701 | 500 | PV | 433-H4 | 2010-10-26 | 2010-10-28 | #VALUE! | 0 | #VALUE! | 2010-11-08 | 2010-11-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-29 |  | 2010-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Charlestown | 1709 | 2129 | 30 | Wind | 287-148H1 | 2010-10-27 | 2010-11-23 | #VALUE! | 17 | #VALUE! | 2010-11-23 | 2011-01-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2010-11-25 | No | STD |  |  |  | 0 | 0 | 0 | 2011-09-22 |  | 2011-09-30 | Online |  | Gov't | N
NSTAR | Boston | 1710 | 2108 | 16 | PV | 2-1N45 | 2010-10-27 | 2010-11-09 | #VALUE! | 5 | #VALUE! | 2010-11-09 | 2010-12-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-15 | Online |  | Private | Y
NSTAR | Cambridge | 1711 | 2138 | 250 | PV | 828-1104H1 | 2010-11-02 | 2010-11-10 | #VALUE! | 5 | #VALUE! | 2010-11-18 | 2010-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2011-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2011-06-16 | Online |  | Gov't | N
NSTAR | Dennis | 1712 | 2660 | 1250 | PV | 4-92B-92B | 2010-11-08 | 2010-11-19 | #VALUE! | 8 | #VALUE! | 2010-11-23 | 2011-01-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-20 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-25 |  | 2011-05-25 | Online |  | Gov't | Y
NSTAR | Chilmark | 1713 | 2535 | 88 | PV | 4-97-226 | 2010-11-10 | 2010-11-16 | #VALUE! | 1 | #VALUE! | 2010-11-19 | 2010-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-11-26 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-03-21 |  | 2013-03-21 | Online |  | Gov't | N
NSTAR | Fairhaven | 1714 | 2719 | 577.28 | PV | 2-222-222 | 2010-11-12 | 2010-12-02 | #VALUE! | 13 | #VALUE! | 2010-12-03 | 2011-02-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-21 | Online |  | Private | N
NSTAR | Boston | 1715 | 2134 | 75 | Natural Gas | 329-H1 | 2010-11-10 | 2010-11-19 | #VALUE! | 4 | #VALUE! | 2010-11-23 | 2010-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-19 | 2011-04-19 | 2011-04-21 | Online |  | Private | Y
NSTAR | Framingham | 1716 | 1701 | 50 | PV | 342-H4 | 2010-11-15 | 2010-11-22 | #VALUE! | 2 | #VALUE! | 2010-11-24 | 2010-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2010-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Weston | 1717 | 2493 | 300 | PV | 282-H3 | 2010-11-16 | 2010-11-24 | #VALUE! | 3 | #VALUE! | 2010-11-30 | 2011-01-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  |  | Withdrawn |  | Private | Y
NSTAR | Boston | 1718 | 2210 | 125 | PV | 385-H10 | 2010-11-16 | 2010-11-24 | #VALUE! | 3 | #VALUE! | 2010-11-30 | 2010-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Decommissioned | 2021-12-29 | Private | Y
NSTAR | Boston | 1719 | 2210 | 200 | PV | 385-H5 | 2010-11-16 | 2010-11-24 | #VALUE! | 2 | #VALUE! | 2010-11-30 | 2011-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Decommissioned | 2021-12-29 | Private | Y
NSTAR | Boston | 1720 | 2210 | 200 | PV | 385-H15 | 2010-11-18 | 2010-12-06 | #VALUE! | 10 | #VALUE! | 2010-12-07 | 2010-12-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-26 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-08 | Decommissioned | 2021-12-29 | Private | Y
NSTAR | Brewster | 1721 | 2170 | 10 | Wind | 4-89B-576 | 2010-11-19 | 2010-12-03 | #VALUE! | 9 | #VALUE! | 2010-12-03 | 2011-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-21 | Online |  | Private | Y
NSTAR | Hyannis | 1722 | 2601 | 43 | PV | 4-80B-80B | 2010-12-01 | 2010-12-13 | #VALUE! | 7 | #VALUE! | 2010-12-13 | 2011-01-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-14 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-27 |  | 2011-05-27 | Online |  | Private | Y
NSTAR | Cambridge | 1723 | 2141 | 28 | PV | 820-15 | 2010-12-07 | 2010-12-15 | #VALUE! | 3 | #VALUE! | 2010-12-16 | 2011-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-16 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-20 |  | 2011-05-04 | Online |  | Private | Y
NSTAR | Dorchester | 1724 | 2122 | 100 | PV | 466-1482H1 | 2010-12-03 | 2010-12-15 | #VALUE! | 3 | #VALUE! | 2010-12-16 | 2011-02-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Milton | 1725 | 2186 | 26 | PV | 496-H7 | 2010-12-13 | 2010-12-21 | #VALUE! | 5 | #VALUE! | 2010-12-22 | 2011-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Canton | 1726 | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | #VALUE! | 5 | #VALUE! | 2010-12-22 | 2011-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Canton | 1727 | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | #VALUE! | 5 | #VALUE! | 2010-12-22 | 2011-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Canton | 1728 | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | #VALUE! | 5 | #VALUE! | 2010-12-22 | 2011-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Canton | 1729 | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | #VALUE! | 5 | #VALUE! | 2010-12-22 | 2011-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Canton | 1730 | 2021 | 950 | PV | 470-H4 | 2010-12-15 | 2011-01-06 | #VALUE! | 16 | #VALUE! | 2011-01-07 | 2011-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2012-08-03 | Online |  | Gov't | N
NSTAR | Dartmouth | 1731 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | #VALUE! | 16 | #VALUE! | 2011-01-07 | 2011-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
NSTAR | Dartmouth | 1732 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | #VALUE! | 16 | #VALUE! | 2011-01-07 | 2011-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
NSTAR | Dartmouth | 1733 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | #VALUE! | 16 | #VALUE! | 2011-01-07 | 2011-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
NSTAR | Dartmouth | 1734 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | #VALUE! | 16 | #VALUE! | 2011-01-07 | 2011-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
NSTAR | Dartmouth | 1735 | 2747 | 82 | PV | 2-525-525 | 2010-12-15 | 2010-12-21 | #VALUE! | 1 | #VALUE! | 2010-12-21 | 2011-01-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-03-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-18 | Online |  | Private | N
NSTAR | Ashland | 1736 | 1721 | 500 | PV | 274-H1 | 2010-12-20 | 2011-01-05 | #VALUE! | 11 | #VALUE! | 2011-01-05 | 2011-02-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online |  | Gov't | Y
NSTAR | Framingham | 1737 | 1701 | 82 | PV | 455-H5 | 2010-12-20 | 2011-01-05 | #VALUE! | 11 | #VALUE! | 2011-01-05 | 2011-02-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online |  | Gov't | Y
NSTAR | Framingham | 1738 | 1701 | 26 | PV | 455-H5 | 2010-12-20 | 2011-01-26 | #VALUE! | 25 | #VALUE! | 2011-01-26 | 2011-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-03 |  | 2011-04-21 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  | 2011-12-29 | Online |  | Private | Y
NSTAR | Chilmark | 1739 | 2535 | 68 | Wind | 4-97-226 | 2010-12-21 | 2011-01-04 | #VALUE! | 6 | #VALUE! | 2011-01-04 | 2011-02-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-06-09 | Online |  | Gov't | Y
NSTAR | Yarmouth | 1740 | 2664 | 266 | PV | 4-92B-563 | 2010-12-29 | 2011-01-13 | #VALUE! | 9 | #VALUE! | 2011-01-13 | 2011-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-07-18 |  |  |  |  | Private | Y
NSTAR | East Falmouth | 1741 | 2536 | 97 | PV | 4-98A-98A | 2011-01-03 | 2011-01-04 | #VALUE! | 1 | #VALUE! | 2011-01-04 | 2011-01-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-10 |  | 2013-01-03 | Online |  | Gov't | Y
NSTAR | Orleans | 1742 | 2653 | 16 | PV | 4-94A-633 | 2011-01-05 | 2011-01-13 | #VALUE! | 4 | #VALUE! | 2011-01-13 | 2011-02-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-02-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-11 |  | 2011-05-11 | Online |  | Private | Y
NSTAR | Mattapoisett | 1743 | 2739 | 60 | PV | 2-301-301 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1744 | 2740 | 88 | PV | 2-38-38 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1745 | 2740 | 14 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1746 | 2740 | 42 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1747 | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1748 | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | #VALUE! | 42 | #VALUE! | 2011-03-09 | 2011-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | New Bedford | 1749 | 2740 | 56 | PV | 2-6-10 | 2011-01-07 | 2011-03-01 | #VALUE! | 36 | #VALUE! | 2011-03-01 | 2011-03-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-12 |  | 2011-05-12 | Online |  | Private | Y
NSTAR | Roxbury | 1750 | 2119 | 75 | PV | 483-H3 | 2011-01-07 | 2011-03-22 | #VALUE! | 51 | #VALUE! | 2011-03-22 | 2011-04-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-05-24 | Online |  | Private | Y
NSTAR | Plymouth | 1751 | 2360 | 49 | PV | 3-13-936 | 2011-01-17 | 2011-01-28 | #VALUE! | 8 | #VALUE! | 2011-01-28 | 2011-03-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online |  | Private | Y
NSTAR | Brighton | 1752 | 2135 | 14 | PV | 315-H5 | 2011-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 1753 | 2747 | 600 | Wind | 2-525-525 | 2011-01-20 | 2011-02-01 | #VALUE! | 7 | #VALUE! | 2011-02-01 | 2011-03-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online |  | Gov't | Y
NSTAR | Dedham | 1754 | 2026 | 26 | PV | 20-H1 | 2011-01-21 | 2011-01-25 | #VALUE! | 1 | #VALUE! | 2011-01-25 | 2011-04-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online |  | Gov't | N
NSTAR | Dedham | 1755 | 2026 | 120 | PV | 20-H5 | 2011-01-21 | 2011-02-08 | #VALUE! | 8 | #VALUE! | 2011-02-08 | 2011-03-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-30 |  | 2012-05-30 | Online |  | Private | N
NSTAR | Cambridge | 1756 | 2139 | 150 | Natural Gas | 831-1324 | 2011-01-24 | 2011-02-01 | #VALUE! | 3 | #VALUE! | 2011-02-01 | 2011-04-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-15 |  | 2011-02-20 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-05-31 | Online |  | Private | Y
NSTAR | Hyannis | 1757 | 2601 | 82 | PV | 4-63-521 | 2011-01-31 | 2011-08-16 | #VALUE! | 140 | #VALUE! | 2011-08-16 | 2011-11-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2012-06-27 | Online |  | Private | Y
NSTAR | Roslindale | 1759 | 2131 | 26 | PV | 13-H1 | 2011-02-01 | 2011-02-11 | #VALUE! | 6 | #VALUE! | 2011-02-11 | 2011-04-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-06 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-03 |  | 2011-08-04 | Online |  | Private | Y
NSTAR | Assonett | 1760 | 2702 | 11 | PV | 2-605-605 | 2011-02-03 | 2011-03-16 | #VALUE! | 29 | #VALUE! | 2011-03-16 | 2011-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-30 |  | 2011-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-16 | Online |  | Private | N
NSTAR | Edgartown | 1761 | 2539 | 55 | Wind | 4-97-97 | 2011-02-03 | 2011-02-07 | #VALUE! | 1 | #VALUE! | 2011-02-07 | 2011-03-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-01 |  | 2011-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-28 |  | 2011-05-04 | Online |  | Private | Y
NSTAR | Chelsea | 1762 | 2150 | 39 | PV | 488-H2 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online |  | Gov't | N
NSTAR | Dartmouth | 1763 | 2747 | 4560 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1764 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1765 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1766 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1767 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | #VALUE! | 0 | #VALUE! | 2011-02-14 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1768 | 2747 | 1000 | PV | 2-525-525 | 2011-02-11 | 2011-02-28 | #VALUE! | 10 | #VALUE! | 2011-02-28 | 2011-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  |  | Withdrawn |  | Gov't | Y
NSTAR | Cambridge | 1769 | 2139 | 82 | PV | 831-1324 | 2011-02-14 | 2011-03-07 | #VALUE! | 14 | #VALUE! | 2011-03-07 | 2011-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-05-21 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2013-01-24 | Online |  | Private | Y
NSTAR | Milton | 1770 | 2186 | 200 | PV | 4306 | 2011-02-11 | 2011-02-28 | #VALUE! | 9 | #VALUE! | 2011-02-28 | 2011-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-06-07 | Online |  | Private | Y
NSTAR | Jamaica Plain | 1771 | 2130 | 30 | PV | 396-01 | 2011-02-17 | 2011-04-22 | #VALUE! | 45 | #VALUE! | 2011-04-22 | 2011-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-31 |  | 2012-07-31 | Online |  | Private | Y
NSTAR | Wareham | 1772 | 2571 | 875 | PV | 3-86-966 | 2011-02-24 | 2011-03-16 | #VALUE! | 13 | #VALUE! | 2011-03-16 | 2011-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2012-07-31 | Online |  | Private | Y
NSTAR | Brewster | 1773 | 2631 | 15 | PV | 4-89B-577 | 2011-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Brewster | 1774 | 2631 | 2 | PV | 4-89B-577 | 2011-02-24 | 2011-03-16 | #VALUE! | 13 | #VALUE! | 2011-03-16 | 2011-03-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-31 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2011-05-20 | Online |  | Private | Y
NSTAR | Brewster | 1775 | 2631 | 21 | PV | 4-89B-577 | 2011-03-03 | 2011-03-07 | #VALUE! | 1 | #VALUE! | 2011-03-07 | 2011-05-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Kingston | 1776 | 2364 | 1000 | PV | 3-17-913 | 2011-03-07 | 2011-03-07 | 0 | 0 | 0 | 2011-03-07 | 2011-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  |  | Withdrawn |  | Gov't | N
NSTAR | Dartmouth | 1777 | 2748 | 1000 | PV | 2-528-528 | 2011-03-08 | 2011-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Chatham | 1778 | 2633 | 31 | PV | 4-95A-608 | 2011-03-10 | 2011-04-15 | #VALUE! | 25 | #VALUE! | 2011-04-15 | 2011-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-06-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-06 | Online |  | Private | Y
NSTAR | Stoneham | 1779 | 2180 | 72 | PV | 375-H7 | 2011-03-10 | 2011-05-12 | #VALUE! | 44 | #VALUE! | 2011-05-13 | 2011-07-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2013-01-28 | Online |  | Private | Y
NSTAR | Somerville | 1780 | 2143 | 120 | PV | 250-1N39H1 | 2011-03-10 | 2011-04-28 | #VALUE! | 34 | #VALUE! | 2011-04-28 | 2011-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-19 |  | 2012-06-19 | Online |  | Private | Y
NSTAR | Ashland | 1781 | 1721 | 30 | PV | 519-175H1 | 2011-03-15 | 2011-09-26 | #VALUE! | 139 | #VALUE! | 2011-09-26 | 2011-10-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bedford | 1782 | 1730 | 51 | PV | 592-70H | 2011-03-15 | 2011-03-18 | #VALUE! | 2 | #VALUE! | 2011-03-18 | 2011-04-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 |  | 2011-12-08 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-08-02 | Online |  | Gov't | N
NSTAR | Dartmouth | 1783 | 2747 | 600 | Wind | 2-525-525 | 2011-03-21 | 2011-03-21 | 0 | 0 | 0 | 2011-03-21 | 2011-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-01 | Online |  | Private | Y
NSTAR | West Dennis | 1784 | 2670 | 30 | PV | 4-92B-571 | 2011-03-28 | 2011-04-06 | #VALUE! | 5 | #VALUE! | 2011-04-06 | 2011-06-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-10 |  | 2011-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-16 | Online |  | Private | N
NSTAR | Medway | 1785 | 2053 | 350 | PV | 65-H3 | 2011-03-30 | 2011-04-29 | #VALUE! | 20 | #VALUE! | 2011-04-29 | 2011-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-29 |  | 2011-09-13 | Online |  | Gov't | Y
NSTAR | Acton | 1787 | 1720 | 24 | PV | 416-H2 | 2011-04-01 | 2011-04-12 | #VALUE! | 5 | #VALUE! | 2011-04-12 | 2011-05-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online |  | Private | Y
NSTAR | Acton | 1788 | 1720 | 142 | PV | 416-H5 | 2011-04-01 | 2011-04-08 | #VALUE! | 3 | #VALUE! | 2011-04-08 | 2011-05-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-04-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-18 |  | 2011-09-07 | Online |  | Gov't | Y
NSTAR | Milton | 1789 | 2186 | 60 | PV | 362-05 | 2011-04-05 | 2011-05-06 | #VALUE! | 23 | #VALUE! | 2011-05-09 | 2011-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-06 |  | 2011-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online |  | Private | Y
NSTAR | Canton | 1790 | 2021 | 100 | PV | 470-H7 | 2011-04-08 | 2011-04-12 | #VALUE! | 1 | #VALUE! | 2011-04-12 | 2011-05-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | Y
NSTAR | East Boston | 1791 | 2128 | 345 | PV | 592-72XY | 2011-04-08 | 2011-10-27 | #VALUE! | 142 | #VALUE! | 2011-10-28 | 2011-12-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-07 |  | 2011-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-12 |  |  |  |  | Private | Y
NSTAR | Jamaica Plain | 1792 | 2130 | 30 | PV | 284-1360H2 | 2011-04-12 | 2011-04-15 | #VALUE! | 2 | #VALUE! | 2011-04-15 | 2011-05-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-23 |  | 2011-06-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-08-25 | Online |  | Private | Y
NSTAR | Sherborn | 1793 | 1770 | 16 | PV | 240-H1 | 2011-04-20 | 2011-08-24 | #VALUE! | 89 | #VALUE! | 2011-08-24 | 2012-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-03 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2011-10-03 | Private | N
NSTAR | Charlestown | 1794 | 2129 | 250 | Natural Gas | 250-H3 | 2011-04-25 | 2011-04-27 | #VALUE! | 1 | #VALUE! | 2011-05-02 | 2011-06-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-17 | Online |  | Private | Y
NSTAR | Brookline | 1796 | 2446 | 75 | Natural Gas | 350-H12 | 2011-04-27 | 2011-05-19 | #VALUE! | 15 | #VALUE! | 2011-05-19 | 2011-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-08 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-08 | Online |  | Gov't | N
NSTAR | Fairhaven | 1797 | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-04-25 | 2011-05-31 | #VALUE! | 23 | #VALUE! | 2011-05-31 | 2011-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-12 |  | 2011-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
NSTAR | Mashpee | 1798 | 2649 | 270 | PV | 4-77A-454 | 2011-04-27 | 2011-05-13 | #VALUE! | 10 | #VALUE! | 2011-05-13 | 2011-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-05-23 | Online |  | Private | Y
NSTAR | Dedham | 1799 | 2026 | 100 | PV | 344-07 | 2011-04-27 | 2011-05-12 | #VALUE! | 9 | #VALUE! | 2011-05-13 | 2011-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-29 | Online |  | Private | Y
NSTAR | Jamaica Plain | 1800 | 2130 | 100 | PV | 496-H4 | 2011-04-29 | 2011-05-12 | #VALUE! | 8 | #VALUE! | 2011-05-13 | 2011-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-18 |  | 2013-01-18 | Online |  | Private | Y
NSTAR | Dedham | 1802 | 2026 | 250 | PV | 20-H8 | 2011-04-29 | 2011-05-12 | #VALUE! | 7 | #VALUE! | 2011-05-13 | 2011-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Marshfield | 1803 | 2050 | 100 | PV | 3-24-915 | 2011-05-03 | 2011-05-10 | #VALUE! | 2 | #VALUE! | 2011-05-10 | 2011-06-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-13 |  | 2011-06-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-29 | Online |  | Private | Y
NSTAR | Dorchester | 1804 | 2125 | 250 | PV | 106-H2 | 2011-05-03 | 2011-05-09 | #VALUE! | 1 | #VALUE! | 2011-05-09 | 2011-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-27 | Online |  | Gov't | Y
NSTAR | Waltham | 1805 | 2452 | 182 | PV | 3316 | 2011-05-05 | 2011-10-20 | #VALUE! | 118 | #VALUE! | 2011-10-21 | 2011-12-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  | 2012-04-06 | Online |  | Gov't | Y
NSTAR | Canton | 1806 | 2021 | 50 | PV | 470-H8 | 2011-05-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Fairhaven | 1807 | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-05-09 | 2011-05-11 | #VALUE! | 1 | #VALUE! | 2011-05-11 | 2011-06-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-28 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-10-12 |  | 2011-10-12 | Online |  | Private | Y
NSTAR | Harwich | 1808 | 2645 | 32 | PV | 4-95A-599 | 2011-05-13 | 2011-06-03 | #VALUE! | 13 | #VALUE! | 2011-06-03 | 2011-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2012-07-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-12-19 |  |  | TBD | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2013-02-06 | Online |  | Private | N
NSTAR | Acusnet | 1809 | 2743 | 1142.68 | PV | 2-241-238 | 2011-05-16 | 2011-06-01 | #VALUE! | 11 | #VALUE! | 2011-06-01 | 2011-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2013-02-06 | Online |  | Gov't | Y
NSTAR | Milton | 1810 | 2186 | 75 | PV | 311-04 | 2011-05-16 | 2011-06-01 | #VALUE! | 11 | #VALUE! | 2011-06-01 | 2011-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | Online |  | Gov't | N
NSTAR | Milton | 1811 | 2186 | 100 | PV | 496-H7 | 2011-05-16 | 2011-06-01 | #VALUE! | 11 | #VALUE! | 2011-06-01 | 2011-09-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-27 | Online |  | Gov't | N
NSTAR | Milton | 1812 | 2186 | 400 | PV | 496-H7 | 2011-05-16 | 2011-05-31 | #VALUE! | 9 | #VALUE! | 2011-06-01 | 2011-07-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-21 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-24 | Online |  | Gov't | N
NSTAR | Milton | 1813 | 2186 | 200 | PV | 4303 | 2011-05-17 | 2011-06-06 | #VALUE! | 13 | #VALUE! | 2011-06-06 | 2011-07-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-15 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-25 | Online |  | Private | Y
NSTAR | Boston | 1814 | 2127 | 50 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | #VALUE! | 12 | #VALUE! | 2011-06-06 | 2011-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2011-12-22 | Online |  | Private | Y
NSTAR | Boston | 1815 | 2127 | 28 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | #VALUE! | 10 | #VALUE! | 2011-06-06 | 2011-07-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-08 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2012-01-09 | Online |  | Private | Y
NSTAR | Boston | 1816 | 2127 | 28 | PV | 385-H1 | 2011-05-26 | 2011-05-26 | 0 | 0 | 0 | 2011-05-26 | 2011-07-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-30 |  | 2011-10-04 | Online |  | Private | Y
NSTAR | Chatham | 1817 | 2633 | 21 | PV | 4-95B-941 | 2011-05-25 | 2011-06-06 | #VALUE! | 7 | #VALUE! | 2011-06-06 | 2011-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-06-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-28 | Online |  | Gov't | Y
NSTAR | Natick | 1818 | 1760 | 175 | PV | 433-H12 | 2011-05-23 | 2011-05-31 | #VALUE! | 3 | #VALUE! | 2011-05-31 | 2011-07-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-25 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-24 | Online |  | Private | Y
NSTAR | Carver | 1819 | 2330 | 833 | PV | 3-10-930 | 2011-05-25 | 2011-08-22 | #VALUE! | 58 | #VALUE! | 2011-08-22 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2012-01-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | East Falmouth | 1820 | 2536 | 225 | Wind | 4-98A-98A | 2011-05-26 | 2011-06-02 | #VALUE! | 0 | #VALUE! | 2011-06-02 | 2011-07-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  |  | Withdrawn |  | Private | N
NSTAR | Wareham | 1821 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | #VALUE! | 0 | #VALUE! | 2011-06-02 | 2011-07-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
NSTAR | Wareham | 1822 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | #VALUE! | 0 | #VALUE! | 2011-06-02 | 2011-07-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
NSTAR | Wareham | 1823 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | #VALUE! | 0 | #VALUE! | 2011-06-02 | 2011-07-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
NSTAR | Wareham | 1824 | 2576 | 500 | PV | 3-86-86 | 2011-06-01 | 2011-06-08 | #VALUE! | 3 | #VALUE! | 2011-06-08 | 2011-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-17 | Online |  | Private | Y
NSTAR | Hopkinton | 1825 | 1748 | 69 | PV | 65-1325H3 | 2011-05-31 | 2011-06-14 | #VALUE! | 6 | #VALUE! | 2011-06-14 | 2011-09-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2011-12-06 | Online |  | Private | Y
NSTAR | Dedham | 1826 | 2026 | 150 | PV | 344-07 | 2011-06-01 | 2011-07-06 | #VALUE! | 21 | #VALUE! | 2011-07-06 | 2011-08-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-21 |  | 2011-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-22 |  | 2013-01-22 | Online |  | Private | Y
NSTAR | Freetown | 1827 | 2717 | 1304.16 | PV | 2-102-604 | 2011-06-07 | 2011-06-15 | #VALUE! | 6 | #VALUE! | 2011-06-15 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-11-29 |  | 2013-01-22 | Online |  | Private | N
NSTAR | Westwood | 1828 | 2090 | 150 | Natural Gas | 148-H3 | 2011-06-13 | 2011-06-27 | #VALUE! | 10 | #VALUE! | 2011-06-27 | 2011-08-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-15 |  | 2011-07-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-07 | Online |  | Private | Y
NSTAR | New Bedford | 1829 | 2745 | 26 | PV | 2-106-160 | 2011-05-31 | 2011-06-14 | #VALUE! | 1 | #VALUE! | 2011-06-14 | 2011-08-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2012-01-11 | Online |  | Private | Y
NSTAR | Roxbury | 1830 | 2119 | 150 | PV | 52-1487H1 | 2011-06-13 | 2011-06-24 | #VALUE! | 9 | #VALUE! | 2011-06-24 | 2011-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-07-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | New Bedford | 1831 | 2740 | 200 | PV | 2-220-9 | 2011-06-13 | 2011-07-29 | #VALUE! | 30 | #VALUE! | 2011-07-29 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-16 | Online |  | Private | Y
NSTAR | Mattapoisett | 1832 | 2739 | 82 | PV | 2-304-304 | 2011-06-20 | 2011-06-30 | #VALUE! | 7 | #VALUE! | 2011-06-30 | 2011-08-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2011-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online |  | Gov't | N
NSTAR | Kingston | 1833 | 2364 | 2100 | Wind | 3-17-913 | 2011-06-21 | 2011-06-24 | #VALUE! | 3 | #VALUE! | 2011-06-24 | 2011-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-21 | Online |  | Gov't | Y
NSTAR | Waltham | 1834 | 2452 | 395 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | #VALUE! | 3 | #VALUE! | 2011-06-24 | 2011-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | Y
NSTAR | Waltham | 1835 | 2451 | 130 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | #VALUE! | 3 | #VALUE! | 2011-06-24 | 2011-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | Y
NSTAR | Waltham | 1836 | 2452 | 75 | PV | 282-H2 | 2011-06-21 | 2011-06-24 | #VALUE! | 3 | #VALUE! | 2011-06-24 | 2011-07-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-29 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-09 | Online |  | Gov't | Y
NSTAR | Waltham | 1837 | 2453 | 75 | PV | 467-H5 | 2011-06-23 | 2011-08-05 | #VALUE! | 31 | #VALUE! | 2011-08-05 | 2011-08-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-06 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-09 | Online |  | Private | Y
NSTAR | Natick | 1838 | 1760 | 332 | Natural Gas | 433-H7 | 2011-06-24 | 2011-06-28 | #VALUE! | 2 | #VALUE! | 2011-06-28 | 2011-08-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Holliston | 1839 | 1746 | 1750 | PV | 274-H2 | 2011-06-24 | 2011-07-29 | #VALUE! | 23 | #VALUE! | 2011-07-29 | 2011-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 1842 | 2748 | 50 | PV | 2-524-524 | 2011-07-01 | 2011-07-18 | #VALUE! | 11 | #VALUE! | 2011-07-18 | 2011-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Gov't | Y
NSTAR | East Freetown | 1843 | 2717 | 1723 | PV | 2-102-102 | 2011-07-01 | 2011-07-18 | #VALUE! | 11 | #VALUE! | 2011-07-18 | 2011-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Gov't | Y
NSTAR | East Freetown | 1844 | 2717 | 2000 | PV | 2-102-102 | 2011-07-01 | 2011-07-08 | #VALUE! | 3 | #VALUE! | 2011-07-08 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-15 | Online |  | Gov't | Y
NSTAR | New Bedford | 1845 | 2746 | 177 | PV | 2-84-15 | 2011-07-04 | 2011-07-05 | #VALUE! | 0 | #VALUE! | 2011-07-05 | 2011-08-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2011-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Private | Y
NSTAR | Norfolk | 1846 | 2056 | 1375 | PV | 65-H1 | 2011-07-06 | 2011-07-07 | #VALUE! | 0 | #VALUE! | 2011-07-07 | 2011-08-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Gov't | N
NSTAR | Boston | 1847 | 2125 | 82 | PV | 511-1497H | 2011-07-11 | 2011-07-20 | #VALUE! | 7 | #VALUE! | 2011-07-20 | 2011-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | Online |  | Gov't | Y
NSTAR | Sharon | 1848 | 2067 | 30 | PV | 470-H12 | 2011-07-13 | 2011-08-02 | #VALUE! | 14 | #VALUE! | 2011-08-02 | 2011-09-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2013-09-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-03-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online |  | Gov't | N
NSTAR | Freetown | 1849 | 2717 | 4200 | PV | 2-102-102 | 2011-07-13 | 2011-08-02 | #VALUE! | 14 | #VALUE! | 2011-08-02 | 2011-09-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Freetown | 1850 | 2717 | 2000 | PV | 2-102-102 | 2011-07-07 | 2011-09-09 | #VALUE! | 42 | #VALUE! | 2011-09-09 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 1851 | 2116 | 1000 | PV | 2-241-241 | 2011-07-07 | 2011-09-09 | #VALUE! | 42 | #VALUE! | 2011-09-09 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 1852 | 2116 | 1000 | PV | 2-241-241 | 2011-07-14 | 2011-07-20 | #VALUE! | 4 | #VALUE! | 2011-07-20 | 2011-08-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acton | 1853 | 1720 | 128 | PV | 416-H9 | 2011-07-20 | 2011-07-27 | #VALUE! | 5 | #VALUE! | 2011-07-27 | 2011-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-15 | Online |  | Private | Y
NSTAR | New Bedford | 1854 | 2745 | 250 | PV | 2-82-82 | 2011-07-20 | 2011-08-02 | #VALUE! | 8 | #VALUE! | 2011-08-02 | 2011-09-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Freetown | 1855 | 2717 | 2000 | PV | 2-102-102 | 2011-07-21 | 2011-09-20 | #VALUE! | 43 | #VALUE! | 2011-09-20 | 2011-10-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-31 |  | 2011-08-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-13 | Online |  | Private | Y
NSTAR | Plymouth | 1856 | 2360 | 190 | PV | 3-12-12 | 2011-07-22 | 2011-07-28 | #VALUE! | 4 | #VALUE! | 2011-07-28 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
NSTAR | New Bedford | 1857 | 2745 | 110 | PV | 2-105-105 | 2011-07-22 | 2011-07-28 | #VALUE! | 3 | #VALUE! | 2011-07-28 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
NSTAR | New Bedford | 1858 | 2740 | 50 | PV | 2-73-16 | 2011-07-22 | 2011-07-28 | #VALUE! | 3 | #VALUE! | 2011-07-28 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
NSTAR | New Bedford | 1859 | 2745 | 50 | PV | 2-79-79 | 2011-07-22 | 2011-07-28 | #VALUE! | 3 | #VALUE! | 2011-07-28 | 2011-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2011-09-19 | Gov't | Y
NSTAR | New Bedford | 1860 | 2744 | 110 | PV | 2-7-34 | 2011-07-22 | 2011-07-28 | #VALUE! | 3 | #VALUE! | 2011-07-28 | 2011-08-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-31 |  | 2011-10-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | Y
NSTAR | New Bedford | 1861 | 2746 | 50 | PV | 2-83-403 | 2011-07-25 | 2011-07-28 | #VALUE! | 2 | #VALUE! | 2011-07-29 | 2011-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-26 |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online |  | Private | Y
NSTAR | Dartmouth | 1862 | 2747 | 2000 | PV | 2-541-541 | 2011-07-26 | 2011-07-28 | #VALUE! | 2 | #VALUE! | 2011-07-29 | 2011-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2012-07-05 | Online |  | Gov't | N
NSTAR | New Bedford | 1863 | 2740 | 108 | PV | 2-71-71 | 2011-07-26 | 2011-07-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | 2011-08-31 | Private | Y
NSTAR | New Bedford | 1864 | 2745 | 625 | PV | 2-59-59 | 2011-07-27 | 2011-08-02 | #VALUE! | 4 | #VALUE! | 2011-08-04 | 2011-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
NSTAR | Marshfield | 1865 | 1845 | 3000 | PV | 3-21-34J1 | 2011-07-27 | 2011-08-02 | #VALUE! | 4 | #VALUE! | 2011-08-04 | 2011-09-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Marshfield | 1866 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | #VALUE! | 4 | #VALUE! | 2011-08-04 | 2011-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Marshfield | 1867 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | #VALUE! | 4 | #VALUE! | 2011-08-04 | 2011-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Marshfield | 1868 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-07-28 | #VALUE! | 0 | #VALUE! | 2011-07-28 | 2011-09-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  |  | Withdrawn |  | Private | Y
NSTAR | Wareham | 1869 | 2671 | 30 | PV | 3-86-966 | 2011-07-28 | 2011-07-28 | 0 | 0 | 0 | 2011-07-28 | 2011-09-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online |  | Private | Y
NSTAR | Sherborn | 1870 | 1770 | 60 | PV | 240-H6 | 2011-07-28 | 2011-08-01 | #VALUE! | 1 | #VALUE! | 2011-08-01 | 2011-09-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-29 |  | 2011-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-02-03 | Online |  | Private | Y
NSTAR | Brewster | 1871 | 2631 | 310 | PV | 4-95B-600 | 2011-08-02 | 2011-08-04 | #VALUE! | 2 | #VALUE! | 2011-08-04 | 2011-09-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  |  |  |  | Gov't | N
NSTAR | Waltham | 1872 | 2452 | 310 | PV | 450-H6 | 2011-08-02 | 2011-08-09 | #VALUE! | 4 | #VALUE! | 2011-08-09 | 2011-09-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-29 | Online |  | Private | Y
NSTAR | Framingham | 1873 | 1701 | 225 | PV | 433-H8 | 2011-08-03 | 2012-09-10 | #VALUE! | 287 | #VALUE! | 2012-09-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | New Bedford | 1874 | 2744 | 310 | PV | 12457 | 2011-08-04 | 2011-09-28 | #VALUE! | 39 | #VALUE! | 2011-09-28 | 2011-11-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 | 2012-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-12-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-09-27 | 2012-10-02 |  |  |  | Private | Y
NSTAR | Hyannis | 1875 | 2601 | 1238 | PV | 4-80B-80-B | 2011-08-04 | 2011-08-09 | #VALUE! | 2 | #VALUE! | 2011-08-09 | 2011-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-08-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-27 | Online |  | Private | Y
NSTAR | Waltham | 1876 | 2453 | 30 | PV | 467-H5 | 2011-08-08 | 2011-08-09 | #VALUE! | 0 | #VALUE! | 2011-08-10 | 2011-09-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-09 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-07 | 2012-08-07 | 2012-08-07 | Online |  | Private | N
NSTAR | Hopkinton | 1877 | 1748 | 1000 | Natural Gas | 455-H3 | 2011-08-09 | 2011-08-10 | #VALUE! | 1 | #VALUE! | 2011-08-10 | 2011-09-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-15 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-04 |  | 2012-04-11 | Online |  | Private | Y
NSTAR | West Tisbury | 1879 | 2575 | 5 | Wind | 4-97-97 | 2011-08-09 | 2011-08-11 | #VALUE! | 1 | #VALUE! | 2011-08-12 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bourne | 1880 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | #VALUE! | 1 | #VALUE! | 2011-08-12 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bourne | 1881 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | #VALUE! | 1 | #VALUE! | 2011-08-12 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bourne | 1882 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-16 | 2011-08-30 | #VALUE! | 10 | #VALUE! | 2011-08-30 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | East Freetown | 1883 | 2717 | 1000 | PV | 604 | 2011-08-18 | 2011-08-25 | #VALUE! | 5 | #VALUE! | 2011-08-26 | 2011-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2012-03-08 | Online |  | Private | Y
NSTAR | Boston | 1884 | 2119 | 75 | PV | 323-05 | 2011-08-18 | 2011-08-25 | #VALUE! | 5 | #VALUE! | 2011-08-26 | 2011-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-04 |  | 2011-10-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-27 |  | 2012-07-06 | Online |  | Private | Y
NSTAR | Boston | 1885 | 2128 | 75 | PV | 108-196H1 | 2011-08-17 | 2011-08-22 | #VALUE! | 1 | #VALUE! | 2011-08-22 | 2011-09-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-05-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2014-06-09 | 2014-06-09 | 2014-06-16 | Online |  | Gov't | Y
NSTAR | Edgartown | 1886 | 2539 | 1083 | PV | 4-97-227 | 2011-08-22 | 2011-08-22 | 0 | 0 | 0 | 2011-08-23 | 2011-09-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-06-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online |  | Gov't | Y
NSTAR | Edgartown | 1887 | 2539 | 1083 | PV | 4-97-97 | 2011-08-22 | 2011-08-25 | #VALUE! | 2 | #VALUE! | 2011-08-25 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Gov't | Y
NSTAR | Dartmouth | 1888 | 2747 | 1146 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | #VALUE! | 2 | #VALUE! | 2011-08-25 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Private | Y
NSTAR | Dartmouth | 1889 | 2747 | 1000 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | #VALUE! | 2 | #VALUE! | 2011-08-25 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Private | Y
NSTAR | Dartmouth | 1890 | 2747 | 1146 | PV | 2-107-107 | 2011-08-23 | 2011-08-29 | #VALUE! | 4 | #VALUE! | 2011-08-29 | 2011-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2013-03-27 | Online |  | Private | Y
NSTAR | Harwich | 1891 | 2645 | 36 | PV | 4-89A-556 | 2011-08-26 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-10-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-05 | Online |  | Gov't | Y
NSTAR | Natick | 1892 | 1760 | 100 | PV | 240-H5 | 2011-08-26 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-10-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | N
NSTAR | Natick | 1893 | 1760 | 90 | PV | 433-H5 | 2011-08-26 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | East Freetown | 1894 | 2717 | 1000 | PV | 604 | 2011-08-26 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online |  | Private | Y
NSTAR | East Freetown | 1895 | 2717 | 2984 | PV | 2-108-108 | 2011-08-26 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-20 | Online |  | Gov't | Y
NSTAR | East Freetown | 1896 | 2717 | 1000 | PV | 2-102-604 | 2011-08-25 | 2011-08-29 | #VALUE! | 0 | #VALUE! | 2011-08-29 | 2011-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2015-03-20 | Online |  | Private | Y
NSTAR | Harwich | 1897 | 2645 | 36 | PV | 4-89A-556 | 2011-08-29 | 2011-08-30 | #VALUE! | 1 | #VALUE! | 2011-08-30 | 2011-11-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-14 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | N
NSTAR | Natick | 1898 | 1760 | 260 | PV | 433-H5 | 2011-08-30 | 2011-10-05 | #VALUE! | 25 | #VALUE! | 2011-10-05 | 2011-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online |  | Private | Y
NSTAR | Canton | 1899 | 2021 | 46 | PV | 269-1321H2 | 2011-08-31 | 2011-09-02 | #VALUE! | 2 | #VALUE! | 2011-09-02 | 2011-10-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-03 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-05 | Online |  | Private | Y
NSTAR | North Dartmouth | 1900 | 2747 | 17 | PV | 2-72-501 | 2011-09-01 | 2011-09-08 | #VALUE! | 5 | #VALUE! | 2011-09-08 | 2011-11-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1901 | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | #VALUE! | 5 | #VALUE! | 2011-09-08 | 2011-11-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1902 | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-08 | #VALUE! | 5 | #VALUE! | 2011-09-08 | 2011-11-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1903 | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | #VALUE! | 5 | #VALUE! | 2011-09-08 | 2011-11-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1904 | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-06 | #VALUE! | 3 | #VALUE! | 2011-09-06 | 2011-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-03 |  | 2012-04-03 | Online |  | Private | Y
NSTAR | Wayland | 1906 | 1778 | 12 | PV | 342-H1 | 2011-09-01 | 2011-09-08 | #VALUE! | 4 | #VALUE! | 2011-09-08 | 2011-11-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Roslindale | 1907 | 2131 | 35 | PV | 1310 | 2011-09-02 | 2011-10-25 | #VALUE! | 35 | #VALUE! | 2011-10-25 | 2012-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-14 | Online |  | Gov't | Y
NSTAR | Chatham | 1908 | 2633 | 50 | PV | 4-95A-606 | 2011-09-09 | 2011-09-15 | #VALUE! | 3 | #VALUE! | 2011-09-15 | 2011-10-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1909 | 2019 | 600 | PV | 65-H4 | 2011-09-09 | 2011-09-15 | #VALUE! | 3 | #VALUE! | 2011-09-15 | 2011-10-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Medway | 1910 | 2053 | 600 | PV | 65-H2 | 2011-09-12 | 2011-09-20 | #VALUE! | 6 | #VALUE! | 2011-09-20 | 2011-10-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 | 2012-06-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Chatham | 1911 | 2633 | 1500 | PV | 4-95B-606 | 2011-09-12 | 2011-10-21 | #VALUE! | 29 | #VALUE! | 2011-10-24 | 2012-01-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-09 | 2012-06-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-29 | Online |  | Gov't | Y
NSTAR | Brewster | 1912 | 2631 | 1083 | PV | 4-89A-553 | 2011-09-09 | 2011-09-20 | #VALUE! | 6 | #VALUE! | 2011-09-20 | 2011-10-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online |  | Gov't | Y
NSTAR | Harwich | 1913 | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2011-09-20 | #VALUE! | 6 | #VALUE! | 2011-09-20 | 2011-10-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Harwich | 1914 | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2012-02-21 | #VALUE! | 116 | #VALUE! | 2012-02-21 | 2012-04-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Eastham | 1915 | 2642 | 500 | PV | 4-94B-646 | 2011-09-15 | 2011-09-21 | #VALUE! | 4 | #VALUE! | 2011-09-21 | 2011-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-17 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-02-16 | Online |  | Private | Y
NSTAR | Wayland | 1916 | 1778 | 60 | PV | 342-H3 | 2011-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Edgartown | 1917 | 2539 | 1500 | PV | 4-97-97 | 2011-09-15 | 2011-09-20 | #VALUE! | 1 | #VALUE! | 2011-09-21 | 2011-11-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-08 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Cambridge | 1918 | 2141 | 38 | Natural Gas | 812-16 | 2011-09-20 | 2011-09-21 | #VALUE! | 0 | #VALUE! | 2011-09-21 | 2012-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-04 | Online |  | Private | Y
NSTAR | Hyde Park | 1919 | 2136 | 177 | PV | 496-H2 | 2011-09-21 | 2011-09-26 | #VALUE! | 3 | #VALUE! | 2011-09-26 | 2011-11-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-27 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-23 | Online |  | Private | Y
NSTAR | Sudbury | 1920 | 1776 | 95 | PV | 342-H5 | 2011-05-23 | 2011-05-31 | #VALUE! | 3 | #VALUE! | 2011-05-31 | 2011-07-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-06 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Carver | 1921 | 2346 | 1000 | PV | 930 | 2011-09-22 | 2011-09-28 | #VALUE! | 1 | #VALUE! | 2011-09-28 | 2011-10-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Carlisle | 1922 | 1741 | 11 | PV | 512-1399H1 | 2011-09-29 | 2011-10-21 | #VALUE! | 15 | #VALUE! | 2011-10-24 | 2012-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-05-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online |  | Gov't | Y
NSTAR | Tisbury | 1923 | 2568 | 1083 | PV | 4-91-91 | 2011-09-30 | 2011-10-04 | #VALUE! | 2 | #VALUE! | 2011-10-04 | 2011-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 | 2012-05-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-11-19 |  | 2012-08-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-25 | Online |  | Gov't | Y
NSTAR | Dartmouth | 1924 | 2747 | 2750 | PV | 2-541-541 | 2011-09-30 | 2011-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2014-03-24 | Online |  | Gov't | Y
NSTAR | Dartmouth | 1925 | 2747 | 4000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | #VALUE! | 2 | #VALUE! | 2011-10-04 | 2011-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dartmouth | 1926 | 2747 | 2000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | #VALUE! | 2 | #VALUE! | 2011-10-04 | 2011-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dartmouth | 1927 | 2747 | 2000 | PV | 2-532-532 | 2011-10-03 | 2011-10-04 | #VALUE! | 1 | #VALUE! | 2011-10-04 | 2011-11-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Winchester | 1928 | 1890 | 17 | PV | 211-H4 | 2011-09-30 | 2012-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-05-29 | Private | N
NSTAR | Cambridge | 1929 | 2142 | 5750 | Natural Gas | 831-1301 | 2011-10-03 | 2011-10-04 | #VALUE! | 1 | #VALUE! | 2011-10-04 | 2011-11-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-06-27 | Online |  | Gov't | N
NSTAR | Waltham | 1930 | 2452 | 666 | PV | 450-H1 | 2011-10-03 | 2011-10-05 | #VALUE! | 2 | #VALUE! | 2011-10-05 | 2011-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-06-06 | Online |  | Private | Y
NSTAR | Acton | 1931 | 1720 | 42 | PV | 416-H9 | 2011-10-04 | 2011-10-04 | 0 | 0 | 0 | 2011-10-05 | 2012-01-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-06 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-15 | Online |  | Private | Y
NSTAR | Hopkinton | 1932 | 1748 | 200 | PV | 519-175H1 | 2011-10-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1933 | 2019 | 5800 | PV | 65-H4 | 2011-10-06 | 2011-10-12 | #VALUE! | 3 | #VALUE! | 2011-10-12 | 2011-11-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-14 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2012-02-28 | Withdrawn |  | Private | Y
NSTAR | Chilmark | 1934 | 2535 | 62 | PV | 4-97-220 | 2011-10-10 | 2011-10-12 | #VALUE! | 1 | #VALUE! | 2011-10-20 | 2012-01-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
NSTAR | Hyannis | 1935 | 2601 | 35 | PV | 4-84B-524 | 2011-10-10 | 2011-10-12 | #VALUE! | 1 | #VALUE! | 2011-10-20 | 2012-01-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
NSTAR | Hyannis | 1936 | 2601 | 50 | PV | 4-84B-524 | 2011-10-07 | 2011-10-12 | #VALUE! | 1 | #VALUE! | 2011-10-13 | 2011-11-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-04-17 |  | 2012-04-19 | Online |  | Private | Y
NSTAR | Mattapoisett | 1937 | 2739 | 82 | PV | 2-304-304 | 2011-10-12 | 2011-10-12 | 0 | 0 | 0 | 2011-10-12 | 2011-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-15 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-15 | Online |  | Private | Y
NSTAR | Hopkinton | 1938 | 1748 | 30 | PV | 65-H6 | 2011-10-13 | 2011-10-19 | #VALUE! | 3 | #VALUE! | 2011-10-20 | 2012-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 | 2012-07-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-08-12 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-29 | Online |  | Private | Y
NSTAR | New Bedford | 1939 | 2740 | 1500 | PV | 2-70-502 | 2011-10-12 | 2011-10-21 | #VALUE! | 4 | #VALUE! | 2011-10-24 | 2012-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 1940 | 2743 | 2000 | PV | 2-241-241 | 2011-10-12 | 2011-10-21 | #VALUE! | 4 | #VALUE! | 2011-10-24 | 2012-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 1941 | 2743 | 2000 | PV | 2-240-240 | 2011-10-12 | 2011-10-21 | #VALUE! | 4 | #VALUE! | 2011-10-24 | 2012-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 1942 | 2743 | 2000 | PV | 2-242-242 | 2011-10-17 | 2011-10-24 | #VALUE! | 5 | #VALUE! | 2011-10-24 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 1943 | 1702 | 750 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | #VALUE! | 5 | #VALUE! | 2011-10-24 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 1944 | 1702 | 875 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | #VALUE! | 5 | #VALUE! | 2011-10-24 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 1945 | 1702 | 875 | PV | 274-H1 | 2011-10-20 | 2011-10-21 | #VALUE! | 1 | #VALUE! | 2011-10-21 | 2012-01-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  |  | Withdrawn |  | Private | Y
NSTAR | Hyannis | 1946 | 2601 | 475.2 | PV | 4-80B-80B | 2011-10-20 | 2011-10-20 | 0 | 0 | 0 | 2011-10-21 | 2011-12-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-18 |  | 2012-07-13 | Online |  | Private | Y
NSTAR | Marion | 1947 | 2378 | 39 | PV | 3-85-957 | 2011-10-20 | 2011-10-28 | #VALUE! | 6 | #VALUE! | 2011-10-31 | 2012-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Freetown | 1948 | 2717 | 1785 | PV | 2-102-604 | 2011-10-07 | 2011-11-21 | #VALUE! | 21 | #VALUE! | 2011-11-21 | 2012-02-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2011-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2012-05-07 | Private | Y
NSTAR | Boston | 1949 | 2215 | 225 | PV | 329-H4 | 2011-10-27 | 2011-10-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2014-07-10 | Online |  | Private | Y
NSTAR | Brewster | 1950 | 2631 | 1785 | PV | 4-95B-600 | 2011-10-24 | 2011-10-25 | #VALUE! | 0 | #VALUE! | 2011-10-25 | 2011-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-03-15 | Online |  | Private | Y
NSTAR | Carver | 1951 | 2330 | 150 | PV | 3-10-917 | 2011-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1952 | 2019 | 5800 | PV | 65-H4 | 2011-10-27 | 2011-11-01 | #VALUE! | 1 | #VALUE! | 2011-11-02 | 2011-12-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-20 |  | 2011-11-04 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-10 | Withdrawn |  | Private | Y
NSTAR | Edgartown | 1953 | 2539 | 12 | PV | 4-75-227 | 2011-10-28 | 2011-11-01 | #VALUE! | 1 | #VALUE! | 2011-11-01 | 2011-11-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | New Bedford | 1954 | 2740 | 50 | PV | 2-5-5 | 2011-10-31 | 2011-11-01 | #VALUE! | 1 | #VALUE! | 2011-11-01 | 2012-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-08-24 |  | 2012-08-24 | Online |  | Private | Y
NSTAR | Carver | 1955 | 2330 | 225 | PV | 3-10-917 | 2011-10-31 | 2011-11-01 | #VALUE! | 1 | #VALUE! | 2011-11-01 | 2011-12-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
NSTAR | Cambridge | 1956 | 2142 | 75 | Natural Gas | 875-1N25A | 2011-10-31 | 2011-11-01 | #VALUE! | 1 | #VALUE! | 2011-11-01 | 2011-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
NSTAR | Roxbury | 1957 | 2119 | 75 | Natural Gas | 106-1N18H1 | 2011-11-01 | 2011-11-28 | #VALUE! | 18 | #VALUE! | 2011-11-28 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-25 |  | 2011-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-21 | Online |  | Private | Y
NSTAR | North Dartmouth | 1958 | 2747 | 125 | PV | 2-541-541 | 2011-11-04 | 2011-11-04 | 0 | 0 | 0 | 2011-11-04 | 2011-12-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online |  | Private | Y
NSTAR | Carver | 1959 | 2330 | 21 | PV | 3-11-11 | 2011-11-04 | 2011-11-14 | #VALUE! | 5 | #VALUE! | 2011-11-14 | 2012-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Fairhaven | 1960 | 2719 | 1000 | PV | 2-220-220 | 2011-11-04 | 2011-11-08 | #VALUE! | 1 | #VALUE! | 2011-11-08 | 2012-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Maynard | 1961 | 1754 | 1000 | PV | 416-H6 | 2011-11-09 | 2011-11-15 | #VALUE! | 3 | #VALUE! | 2011-11-21 | 2012-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-30 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Yarmouth | 1962 | 2675 | 75 | PV | 4-92A-92A | 2011-11-09 | 2011-11-15 | #VALUE! | 3 | #VALUE! | 2011-11-15 | 2012-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-27 |  | 2012-03-27 | Online |  | Private | Y
NSTAR | Barnstable | 1963 | 2630 | 14 | PV | 4-82-518 | 2011-11-10 | 2011-11-18 | #VALUE! | 4 | #VALUE! | 2011-11-22 | 2012-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
NSTAR | Barnstable | 1964 | 2655 | 2000 | PV | 4-80A-80A | 2011-11-10 | 2011-11-18 | #VALUE! | 4 | #VALUE! | 2011-11-22 | 2012-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
NSTAR | Barnstable | 1965 | 2648 | 1681 | PV | 4-88-88 | 2011-11-14 | 2011-11-21 | #VALUE! | 4 | #VALUE! | 2011-11-23 | 2012-02-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-11-21 |  | 2014-09-02 | Online |  | Gov't | N
NSTAR | Framingham | 1966 | 1702 | 725 | PV | 2408 | 2011-11-17 | 2011-12-01 | #VALUE! | 9 | #VALUE! | 2011-12-01 | 2012-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Gov't | Y
NSTAR | Edgartown | 1967 | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | #VALUE! | 9 | #VALUE! | 2011-12-01 | 2012-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Private | Y
NSTAR | Edgartown | 1968 | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | #VALUE! | 9 | #VALUE! | 2011-12-01 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Private | Y
NSTAR | West Tisbury | 1969 | 2575 | 250 | PV | 4-91-91 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1970 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1971 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1972 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1973 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1974 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 5 | #VALUE! | 2011-11-28 | 2012-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Ashland | 1975 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | #VALUE! | 4 | #VALUE! | 2011-11-28 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 1976 | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-28 | #VALUE! | 4 | #VALUE! | 2011-11-28 | 2012-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 1977 | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-22 | #VALUE! | 0 | #VALUE! | 2011-11-23 | 2012-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  |  | Withdrawn |  | Private | Y
NSTAR | Dover | 1978 | 2030 | 16 | PV | 456-H5 | 2011-11-23 | 2011-12-01 | #VALUE! | 4 | #VALUE! | 2011-12-01 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-12 |  | 2012-02-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-06-29 | Online |  | Private | Y
NSTAR | Bedford | 1979 | 1730 | 500 | PV | 533-H8 | 2011-11-23 | 2011-12-06 | #VALUE! | 7 | #VALUE! | 2011-12-08 | 2012-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-06-29 | Online |  | Private | Y
NSTAR | New Bedford | 1980 | 2745 | 30 | PV | 2-79-79 | 2011-11-30 | 2011-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private | Y
NSTAR | Dartmouth | 1981 | 2747 | 4400 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | #VALUE! | 1 | #VALUE! | 2011-12-01 | 2012-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 1982 | 2747 | 2000 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | #VALUE! | 1 | #VALUE! | 2011-12-01 | 2012-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 1983 | 2747 | 1000 | PV | 2-533-533 | 2011-11-30 | 2011-12-15 | #VALUE! | 9 | #VALUE! | 2011-12-15 | 2012-03-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-07 |  | 2011-12-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-15 |  |  | Withdrawn |  | Private | Y
NSTAR | Hyannis | 1984 | 2601 | 46 | PV | 4-84B-524 | 2011-11-30 | 2012-02-22 | #VALUE! | 58 | #VALUE! | 2012-02-29 | 2012-05-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1985 | 2019 | 2000 | PV | 65-H4 | 2011-11-30 | 2012-02-22 | #VALUE! | 58 | #VALUE! | 2012-02-29 | 2012-05-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1986 | 2019 | 2000 | PV | 65-H4 | 2011-11-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 1987 | 2019 | 2000 | PV | 65-H4 | 2011-12-01 | 2011-12-07 | #VALUE! | 3 | #VALUE! | 2011-12-07 | 2012-02-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-16 |  |  | Withdrawn |  | Private | Y
NSTAR | Norfolk | 1988 | 2056 | 270 | PV | 146-H3 | 2011-12-01 | 2011-12-09 | #VALUE! | 4 | #VALUE! | 2011-12-15 | 2012-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Medway | 1989 | 2053 | 2000 | Other | 65-H2 | 2011-12-06 | 2011-12-12 | #VALUE! | 2 | #VALUE! | 2011-12-13 | 2012-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-04-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Watertown | 1990 | 2472 | 120 | PV | 467-H6 | 2011-12-08 | 2011-12-13 | #VALUE! | 3 | #VALUE! | 2011-12-15 | 2012-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online |  | Private | Y
NSTAR | Fairhaven | 1991 | 2719 | 82 | PV | 2-220-201 | 2011-12-05 | 2011-12-09 | #VALUE! | 0 | #VALUE! | 2012-11-13 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage |  | Private | N
NSTAR | Plymouth | 1992 | 2360 | 2000 | Wind | 3-89-925 | 2011-12-08 | 2011-12-13 | #VALUE! | 0 | #VALUE! | 2011-12-15 | 2012-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  | 2011-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2016-08-10 | Online |  | Gov't | Y
NSTAR | Fairhaven | 1993 | 2719 | 120 | PV | 2-220-201 | 2011-12-08 | 2011-12-13 | #VALUE! | 0 | #VALUE! | 2011-12-15 | 2012-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online |  | Private | Y
NSTAR | Fairhaven | 1994 | 2719 | 60 | PV | 2-220-201 | 2011-12-13 | 2011-12-14 | #VALUE! | 0 | #VALUE! | 2011-12-15 | 2012-01-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
NSTAR | Brighton | 1995 | 2135 | 75 | Natural Gas | 329-H3 | 2011-12-13 | 2011-12-16 | #VALUE! | 2 | #VALUE! | 2011-12-20 | 2012-02-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-03-16 | Online |  | Private | Y
NSTAR | New Bedford | 1996 | 2745 | 135 | PV | 2-104-104 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
NSTAR | Carver | 1997 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
NSTAR | Carver | 1998 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
NSTAR | Carver | 1999 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
NSTAR | Carver | 2000 | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
NSTAR | Carver | 2001 | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | #VALUE! | 5 | #VALUE! | 2011-12-27 | 2012-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Carver | 2002 | 2355 | 200 | PV | 3-10-10 | 2011-12-16 | 2011-12-20 | #VALUE! | 0 | #VALUE! | 2011-12-27 | 2012-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Cambridge | 2003 | 2140 | 85 | Natural Gas | 825-20 | 2011-12-16 | 2011-12-20 | #VALUE! | 0 | #VALUE! | 2011-12-27 | 2012-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-23 | Online |  | Private | N
NSTAR | Cambridge | 2004 | 2140 | 85 | Natural Gas | 825-20 | 2011-12-20 | 2011-12-23 | #VALUE! | 1 | #VALUE! | 2011-12-27 | 2012-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-10-10 |  | 2012-10-10 | Online |  | Private | Y
NSTAR | New Bedford | 2005 | 2746 | 287.35 | PV | 2-24-182 | 2011-12-20 | 2011-12-22 | #VALUE! | 0 | #VALUE! | 2011-12-22 | 2012-01-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2015-02-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-10-10 | Online |  | Private | Y
NSTAR | North Truro | 2006 | 2652 | 39 | PV | 4-96-674 | 2011-12-21 | 2011-12-22 | #VALUE! | 0 | #VALUE! | 2012-04-09 | 2012-05-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-20 | Online |  | Private | Y
NSTAR | Norfolk | 2007 | 2056 | 45 | PV | 146-H3 | 2011-12-28 | 2012-01-03 | #VALUE! | 0 | #VALUE! | 2012-01-03 | 2012-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online |  | Private | Y
NSTAR | Bourne | 2008 | 2532 | 14 | PV | 3-84-961 | 2011-12-28 | 2012-01-12 | #VALUE! | 7 | #VALUE! | 2012-01-16 | 2012-05-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online |  | Gov't | Y
NSTAR | Canton | 2009 | 2021 | 360 | PV | 470-H6 | 2012-01-03 | 2012-01-11 | #VALUE! | 5 | #VALUE! | 2012-01-12 | 2012-02-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-05 |  | 2013-08-13 | Online |  | Gov't | Y
NSTAR | Woburn | 2010 | 1801 | 50 | PV | 211-H8 | 2011-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Edgartown | 2011 | 2539 | 1250 | PV | 4-97-97 | 2011-12-15 | 2012-01-09 | #VALUE! | 0 | #VALUE! | 2012-01-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Canton | 2012 | 2021 | 14 | PV | 269-1320H1 | 2012-01-05 | 2012-01-17 | #VALUE! | 5 | #VALUE! | 2012-01-24 | 2012-04-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-30 |  | 2012-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online |  | Gov't | Y
NSTAR | Canton | 2013 | 2021 | 225 | PV | 269-1321H2 | 2012-01-05 | 2012-01-17 | #VALUE! | 5 | #VALUE! | 2012-01-27 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Canton | 2014 | 2021 | 120 | PV | 470-H10 | 2012-01-05 | 2012-02-02 | #VALUE! | 17 | #VALUE! | 2012-02-02 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-22 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-04-20 |  | 2012-05-04 | Online |  | Private | Y
NSTAR | Kingston | 2015 | 2364 | 60 | PV | 3-17-913 | 2012-01-02 | 2012-02-01 | #VALUE! | 16 | #VALUE! | 2012-02-01 | 2012-03-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-05 |  | 2012-02-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-03 | Online |  | Private | Y
NSTAR | Brewster | 2016 | 2631 | 11 | PV | 4-89B-576 | 2012-01-06 | 2012-01-11 | #VALUE! | 0 | #VALUE! | 2012-01-11 | 2012-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-27 |  | 2012-03-10 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Private | Y
NSTAR | Bourne | 2017 | 2532 | 250 | PV | 4-86-86 | 2011-11-08 | 2012-02-08 | #VALUE! | 20 | #VALUE! | 2012-02-08 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Gov't | Y
NSTAR | Waltham | 2018 | 2453 | 30 | PV | 3311 | 2012-01-10 | 2012-01-18 | #VALUE! | 4 | #VALUE! | 2012-01-18 | 2012-02-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2011-12-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-23 | Online |  | Private | Y
NSTAR | Orleans | 2019 | 2653 | 11 | PV | 4-95B-600 | 2012-01-13 | 2012-01-18 | #VALUE! | 2 | #VALUE! | 2012-01-24 | 2012-03-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  | 2012-07-13 | Online |  | Private | Y
NSTAR | Falmouth | 2020 | 2536 | 750 | PV | 4-98A-98A | 2012-01-16 | 2012-02-27 | #VALUE! | 30 | #VALUE! | 2012-02-27 | 2012-04-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-11 |  | 2012-07-13 | Online |  | Private | Y
NSTAR | Hyde Park | 2021 | 2136 | 975 | PV | 344-07 | 2012-01-16 | 2012-01-24 | #VALUE! | 5 | #VALUE! | 2012-01-27 | 2012-04-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Sharon | 2022 | 2067 | 999 | PV | 146-H1 | 2012-01-17 | 2012-03-20 | #VALUE! | 44 | #VALUE! | 2012-03-20 | 2012-04-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-11 |  | 2012-07-03 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-09 | Withdrawn |  | Gov't | Y
NSTAR | Woburn | 2023 | 1801 | 90 | PV | 375-H4 | 2012-01-18 | 2012-01-24 | #VALUE! | 3 | #VALUE! | 2012-01-24 | 2012-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-05 |  | 2012-04-11 | Online |  | Private | Y
NSTAR | South Wellfleet | 2024 | 2663 | 60 | PV | 4-94B-653 | 2012-01-19 | 2012-02-06 | #VALUE! | 12 | #VALUE! | 2012-02-06 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-05-25 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online |  | Private | Y
NSTAR | Provincetown | 2025 | 2657 | 34 | PV | 4-96-675 | 2012-01-18 | 2012-01-23 | #VALUE! | 0 | #VALUE! | 2012-01-30 | 2012-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-09-06 | Online |  | Private | Y
NSTAR | Fairhaven | 2026 | 2719 | 66 | PV | 2-240-240 | 2012-01-18 | 2012-02-21 | #VALUE! | 21 | #VALUE! | 2012-02-21 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2027 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | #VALUE! | 21 | #VALUE! | 2012-02-21 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2028 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | #VALUE! | 21 | #VALUE! | 2012-02-21 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2029 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | #VALUE! | 21 | #VALUE! | 2012-02-21 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2030 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | #VALUE! | 21 | #VALUE! | 2012-02-21 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2031 | 2714 | 1000 | PV | 2-541-541 | 2012-01-19 | 2012-02-02 | #VALUE! | 8 | #VALUE! | 2012-02-02 | 2012-03-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online |  | Private | Y
NSTAR | Eastham | 2032 | 2642 | 210 | PV | 4-94B-94B | 2012-01-19 | 2012-02-02 | #VALUE! | 8 | #VALUE! | 2012-02-02 | 2012-03-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
NSTAR | Eastham | 2033 | 2642 | 220 | PV | 4-94B-94B | 2012-01-23 | 2012-01-26 | #VALUE! | 2 | #VALUE! | 2012-01-26 | 2012-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  | 2011-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-20 | Online |  | Private | Y
NSTAR | Bedford | 2034 | 1703 | 13 | PV | 533-H8 | 2012-01-16 | 2012-02-02 | #VALUE! | 5 | #VALUE! | 2012-02-02 | 2012-03-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-07-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | 2013-05-28 | Gov't | N
NSTAR | Plymouth | 2035 | 2360 | 2000 | PV | 3-89-89 | 2012-01-16 | 2012-02-02 | #VALUE! | 5 | #VALUE! | 2012-02-02 | 2012-03-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-04-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | 2013-05-28 | Gov't | Y
NSTAR | Plymouth | 2036 | 2360 | 500 | PV | 3-89-89 | 2012-01-27 | 2012-02-07 | #VALUE! | 7 | #VALUE! | 2012-02-07 | 2012-04-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-23 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-17 | Online |  | Private | Y
NSTAR | Cotuit | 2037 | 2635 | 12 | PV | 4-88-485 | 2012-01-23 | 2012-01-30 | #VALUE! | 1 | #VALUE! | 2012-01-30 | 2012-02-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online |  | Private | Y
NSTAR | South Yarmouth | 2038 | 2664 | 100 | PV | 4-90-90 | 2012-01-31 | 2012-02-03 | #VALUE! | 3 | #VALUE! | 2012-02-03 | 2012-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Private | N
NSTAR | Ashland | 2039 | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | #VALUE! | 3 | #VALUE! | 2012-02-03 | 2012-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online |  | Private | N
NSTAR | Ashland | 2040 | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | #VALUE! | 3 | #VALUE! | 2012-02-03 | 2012-04-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Ashland | 2041 | 1721 | 500 | PV | 274-H1 | 2012-01-31 | 2012-02-17 | #VALUE! | 12 | #VALUE! | 2012-02-17 | 2012-03-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-21 |  | 2012-12-21 | Online |  | Private | Y
NSTAR | Jamaica Plain | 2042 | 2130 | 100 | PV | 284-1300H1 | 2012-02-01 | 2012-02-13 | #VALUE! | 7 | #VALUE! | 2012-02-13 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-23 | Online |  | Gov't | N
NSTAR | Sandwich | 2043 | 2563 | 3500 | PV | 4-81B-443 | 2012-02-01 | 2012-02-13 | #VALUE! | 7 | #VALUE! | 2012-02-13 | 2012-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Sandwich | 2044 | 2563 | 1500 | PV | 4-81B-443 | 2012-02-03 | 2012-02-21 | #VALUE! | 11 | #VALUE! | 2012-02-21 | 2012-03-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-13 | 2012-06-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-06-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2045 | 2330 | 2000 | PV | 3-10-10 | 2012-01-25 | 2012-03-01 | #VALUE! | 16 | #VALUE! | 2012-03-01 | 2012-04-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-25 |  | 2012-01-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  |  | Withdrawn |  | Private | Y
NSTAR | Sudbury | 2046 | 1776 | 18 | PV | 342-H2 | 2012-01-24 | 2012-02-22 | #VALUE! | 9 | #VALUE! | 2012-02-22 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-28 | Online |  | Private | Y
NSTAR | Roxbury Crossing | 2047 | 2021 | 96 | PV | 483-H6 | 2011-11-15 | 2012-03-08 | #VALUE! | 20 | #VALUE! | 2012-03-08 | 2012-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-06-12 | Online |  | Private | Y
NSTAR | Plymouth | 2048 | 2360 | 11 | PV | 3-89-925 | 2012-01-02 | 2012-03-26 | #VALUE! | 31 | #VALUE! | 2012-03-26 | 2012-04-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 | 2013-01-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
NSTAR | Mashpee | 2049 | 2649 | 1500 | PV | 4-88-455 | 2012-02-06 | 2012-02-15 | #VALUE! | 3 | #VALUE! | 2012-02-16 | 2012-03-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-06-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
NSTAR | Vineyard Haven | 2050 | 2568 | 135 | PV | 4-75-75 | 2012-02-10 | 2012-02-22 | #VALUE! | 7 | #VALUE! | 2012-02-22 | 2012-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-10 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
NSTAR | Medfield | 2051 | 2052 | 20 | PV | 456-H3 | 2012-02-09 | 2012-03-27 | #VALUE! | 31 | #VALUE! | 2012-03-28 | 2012-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-25 |  | 2012-06-26 | Online |  | Private | Y
NSTAR | Boston | 2052 | 2119 | 18 | PV | 106-1N18H1 | 2012-02-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dennis | 2053 | 2638 | 1250 | PV | 4-92B-92B | 2012-02-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dennis | 2054 | 2638 | 1250 | PV | 4-92B-92B | 2012-02-13 | 2012-02-24 | #VALUE! | 5 | #VALUE! | 2012-08-23 | 2012-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-01 |  | 2012-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Withdrawn |  | Private | Y
NSTAR | West Barnstable | 2055 | 2668 | 581 | PV | 4-82-516 | 2012-02-17 | 2012-02-23 | #VALUE! | 4 | #VALUE! | 2012-02-23 | 2012-05-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-11 | 2012-09-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2012-10-04 |  | 2012-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-23 | 2013-12-23 | 2012-10-11 | Online |  | Gov't | Y
NSTAR | Acton | 2056 | 1720 | 1500 | PV | 416-H4 | 2012-02-21 | 2012-03-05 | #VALUE! | 7 | #VALUE! | 2012-03-05 | 2012-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-03-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online |  | Gov't | Y
NSTAR | Westport | 2057 | 2790 | 20 | PV | 2-524-524 | 2012-02-21 | 2012-03-01 | #VALUE! | 5 | #VALUE! | 2012-03-01 | 2012-05-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
NSTAR | Hyannis | 2058 | 2601 | 26 | PV | 4-84A-520 | 2012-02-23 | 2012-02-27 | #VALUE! | 1 | #VALUE! | 2012-02-28 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online |  | Private | Y
NSTAR | Marion | 2059 | 2738 | 18 | PV | 3-85-969 | 2012-02-24 | 2012-03-13 | #VALUE! | 12 | #VALUE! | 2012-03-13 | 2012-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-31 |  | 2012-06-26 | Online |  | Private | Y
NSTAR | Chelsea | 2060 | 2150 | 30 | PV | 488-H2 | 2012-02-24 | 2012-06-26 | #VALUE! | 86 | #VALUE! | 2012-06-26 | 2012-07-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-01 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online |  | Private | Y
NSTAR | Acton | 2061 | 1720 | 12 | PV | 416-H8 | 2012-02-27 | 2012-02-29 | #VALUE! | 2 | #VALUE! | 2012-02-29 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-08 | 2013-08-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-04-08 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-10-02 | 2013-10-02 | 2013-10-04 | Online |  | Gov't | Y
NSTAR | Plympton | 2062 | 2367 | 4000 | PV | 3-51-901 | 2012-02-27 | 2012-02-29 | #VALUE! | 2 | #VALUE! | 2012-02-29 | 2012-03-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2063 | 2367 | 2000 | PV | 3-51-901 | 2012-02-29 | 2012-03-05 | #VALUE! | 3 | #VALUE! | 2012-03-05 | 2012-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-08 |  |  | Withdrawn |  | Private | Y
NSTAR | West Wareham | 2064 | 2756 | 30 | PV | 3-86-966 | 2012-03-01 | 2012-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-03-28 | Private | Y
NSTAR | New Bedford | 2065 | 2740 | 60 | PV | 2-5-5 | 2010-11-02 | 2010-11-10 | #VALUE! | 5 | #VALUE! | 2010-11-18 | 2010-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dennis | 2066 | 2660 | 1250 | PV | 4-92B-92B | 2012-03-02 | 2012-03-23 | #VALUE! | 14 | #VALUE! | 2012-03-23 | 2012-05-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-25 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-22 | Online |  | Private | Y
NSTAR | Falmouth | 2067 | 2540 | 70 | PV | 4-98A-461 | 2012-03-06 | 2012-03-08 | #VALUE! | 2 | #VALUE! | 2012-03-08 | 2012-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-10 | Online |  | Private | Y
NSTAR | Oak Bluffs | 2068 | 2575 | 13 | PV | 4-99-99 | 2012-03-01 | 2012-03-06 | #VALUE! | 0 | #VALUE! | 2012-03-07 | 2012-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | West Tisbury | 2069 | 2568 | 31 | PV | 4-97-97 | 2012-03-05 | 2012-04-03 | #VALUE! | 19 | #VALUE! | 2012-04-03 | 2012-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Norfolk | 2070 | 2056 | 5000 | PV | 65-H1 | 2012-03-09 | 2012-03-15 | #VALUE! | 3 | #VALUE! | 2012-03-15 | 2012-04-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 | 2013-03-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-11-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bourne | 2071 | 2532 | 1785 | PV | 4-86-402 | 2012-03-12 | 2012-03-23 | #VALUE! | 9 | #VALUE! | 2012-03-23 | 2012-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-18 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Milton | 2072 | 2186 | 190 | PV | 362-05 | 2012-03-13 | 2012-03-20 | #VALUE! | 5 | #VALUE! | 2012-03-20 | 2012-04-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-27 |  | 2012-04-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2012-04-27 | Private | Y
NSTAR | Dartmouth | 2073 | 2747 | 16 | PV | 2-543-543 | 2012-03-14 | 2012-04-09 | #VALUE! | 16 | #VALUE! | 2012-04-09 | 2012-06-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wareham | 2074 | 2576 | 1000 | PV | 3-83-83 | 2012-03-19 | 2012-04-19 | #VALUE! | 21 | #VALUE! | 2012-04-19 | 2012-05-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Norfolk | 2075 | 2056 | 82 | PV | 146-H9 | 2012-03-22 | 2012-04-26 | #VALUE! | 22 | #VALUE! | 2012-04-26 | 2012-06-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Sandwich | 2076 | 2537 | 6000 | PV | 4-81B-443 | 2012-03-26 | 2012-04-25 | #VALUE! | 21 | #VALUE! | 2012-04-25 | 2012-06-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-07 |  | 2012-05-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-09-12 | Online |  | Gov't | Y
NSTAR | West Roxbury | 2077 | 2132 | 100 | PV | 468-01 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2012-09-13 | Online |  | Private | Y
NSTAR | Plymouth | 2078 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2079 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2080 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2081 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2082 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2083 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2084 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2085 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2086 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | #VALUE! | 3 | #VALUE! | 2012-04-03 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2087 | 2360 | 1000 | PV | 3-89-925 | 2012-03-30 | 2012-04-05 | #VALUE! | 4 | #VALUE! | 2012-07-03 | 2012-08-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-03-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Hyannis | 2088 | 2601 | 110 | PV | 4-80B-514 | 2012-03-29 | 2012-05-02 | #VALUE! | 23 | #VALUE! | 2012-05-02 | 2012-06-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-14 |  | 2012-03-30 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online |  | Private | Y
NSTAR | Canton | 2089 | 2021 | 14 | PV | 269-1320H1 | 2012-03-29 | 2012-04-03 | #VALUE! | 1 | #VALUE! | 2012-04-05 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-15 |  | 2012-06-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-07 | Online |  | Gov't | Y
NSTAR | Falmouth | 2090 | 2540 | 26 | PV | 4-107-830 | 2012-03-30 | 2012-04-05 | #VALUE! | 2 | #VALUE! | 2012-04-05 | 2012-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Natick | 2091 | 1760 | 14 | PV | 240-H1 | 2012-03-30 | 2012-04-03 | #VALUE! | 0 | #VALUE! | 2012-04-13 | 2012-05-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Assonett | 2092 | 2702 | 12 | PV | 2-605-605 | 2012-04-04 | 2012-04-05 | #VALUE! | 0 | #VALUE! | 2012-04-09 | 2012-05-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Medfield | 2093 | 2081 | 41 | PV | 146-H6 | 2012-04-03 | 2012-04-10 | #VALUE! | 3 | #VALUE! | 2012-04-10 | 2012-05-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-21 | Online |  | Private | Y
NSTAR | Marshfield | 2094 | 2050 | 334 | PV | 3-25-908 | 2012-04-04 | 2012-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-05-04 | Private | Y
NSTAR | Brookline | 2095 | 2467 | 51 | PV | 369-07 | 2012-04-04 | 2012-04-06 | #VALUE! | 0 | #VALUE! | 2012-04-06 | 2012-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-08-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2012-06-29 | Private | Y
NSTAR | Brookline | 2096 | 2467 | 111 | PV | 369-07 | 2012-04-10 | 2012-05-24 | #VALUE! | 31 | #VALUE! | 2012-05-24 | 2012-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-07-24 | Online |  | Private | Y
NSTAR | Kingston | 2097 | 2364 | 11 | PV | 3-909-909 | 2012-04-11 | 2012-04-12 | #VALUE! | 1 | #VALUE! | 2012-04-12 | 2012-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-04 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-05 | Online |  | Private | Y
NSTAR | West Tisbury | 2098 | 2575 | 13 | PV | 4-97-226 | 2012-04-12 | 2012-06-27 | #VALUE! | 54 | #VALUE! | 2012-06-27 | 2012-08-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online |  | Private | Y
NSTAR | West Roxbury | 2099 | 1746 | 60 | PV | 468-01 | 2012-04-13 | 2012-08-29 | #VALUE! | 96 | #VALUE! | 2012-08-29 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-03 | Online |  | Private | Y
NSTAR | Dorchester | 2100 | 2124 | 60 | Natural Gas | 511-1495H | 2012-04-13 | 2012-08-29 | #VALUE! | 96 | #VALUE! | 2012-08-29 | 2012-10-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Private | Y
NSTAR | East Boston | 2101 | 2128 | 60 | Natural Gas | MC-8 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage |  | Private | Y
NSTAR | Plymouth | 2102 | 2360 | 2000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online |  | Private | Y
NSTAR | Plymouth | 2103 | 2360 | 4000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online |  | Private | Y
NSTAR | Plymouth | 2104 | 2360 | 1500 | Wind | 3-89-925 | 2012-04-18 | 2012-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-08-10 | Online | 2013-07-24 | Private | Y
NSTAR | Carver | 2105 | 2330 | 833 | PV | 3-10-929 | 2012-04-17 | 2012-04-19 | #VALUE! | 1 | #VALUE! | 2012-04-19 | 2012-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 | 2013-04-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-11-15 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-07-01 | Online |  | Private | Y
NSTAR | Plymouth | 2106 | 2360 | 500 | PV | 3-11-11 | 2012-04-18 | 2012-04-25 | #VALUE! | 4 | #VALUE! | 2012-04-25 | 2012-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-10 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-12 | Online |  | Private | Y
NSTAR | Assonett | 2107 | 2702 | 13 | PV | 2-605-605 | 2012-04-19 | 2012-04-20 | #VALUE! | 0 | #VALUE! | 2012-04-24 | 2012-06-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-01 |  | 2012-09-21 | Online |  | Private | Y
NSTAR | South Boston | 2108 | 2127 | 75 | Natural Gas | 106-H3 | 2012-04-19 | 2012-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2013-01-22 |  | 2013-01-22 | Online |  | Private | Y
NSTAR | Freetown | 2109 | 2717 | 648.98 | PV | 2-102-604 | 2012-04-21 | 2012-05-01 | #VALUE! | 5 | #VALUE! | 2012-05-01 | 2012-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-22 | Online |  | Gov't | Y
NSTAR | Natick | 2110 | 1760 | 260 | PV | 240-H1 | 2012-04-23 | 2012-04-27 | #VALUE! | 2 | #VALUE! | 2012-04-27 | 2012-06-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-06 | Online |  | Gov't | Y
NSTAR | Natick | 2111 | 1760 | 50 | PV | 240-H2 | 2012-04-23 | 2012-06-11 | #VALUE! | 33 | #VALUE! | 2012-06-11 | 2012-07-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-19 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-10 | Online |  | Private | Y
NSTAR | Holliston | 2112 | 1746 | 18 | PV | 65-H5 | 2012-04-23 | 2012-05-24 | #VALUE! | 21 | #VALUE! | 2012-05-24 | 2012-06-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
NSTAR | Vineyard Haven | 2113 | 2568 | 19 | PV | 4-75-75 | 2012-04-23 | 2012-05-01 | #VALUE! | 4 | #VALUE! | 2012-05-01 | 2012-06-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-28 | Online |  | Gov't | Y
NSTAR | Aquinnah | 2114 | 2575 | 54 | PV | 4-97-126 | 2012-04-21 | 2012-04-30 | #VALUE! | 3 | #VALUE! | 2012-04-30 | 2012-06-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-09-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-12 | Online |  | Gov't | Y
NSTAR | Dennis | 2115 | 2660 | 2500 | PV | 4-92B-92B | 2012-04-21 | 2012-04-30 | #VALUE! | 3 | #VALUE! | 2012-04-30 | 2012-06-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dennis | 2116 | 2660 | 1250 | PV | 4-92B-92B | 2012-04-25 | 2012-05-01 | #VALUE! | 3 | #VALUE! | 2012-05-01 | 2012-06-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  | 2012-07-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | 2013-01-07 | Private | Y
NSTAR | Marion | 2117 | 2740 | 1000 | PV | 3-85-85 | 2012-04-27 | 2012-05-01 | #VALUE! | 2 | #VALUE! | 2012-05-03 | 2012-06-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Plymouth | 2118 | 2360 | 1000 | PV | 3311 | 2012-04-27 | 2012-05-01 | #VALUE! | 2 | #VALUE! | 2012-05-03 | 2012-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Plymouth | 2119 | 2360 | 2000 | PV | 3-89-926 | 2012-05-01 | 2012-05-07 | #VALUE! | 3 | #VALUE! | 2012-05-08 | 2012-07-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Walpole | 2120 | 2071 | 1000 | PV | 146-H9 | 2012-05-01 | 2012-05-07 | #VALUE! | 3 | #VALUE! | 2012-05-08 | 2012-07-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online |  | Private | Y
NSTAR | Walpole | 2121 | 2071 | 1398.22 | PV | 146-H9 | 2012-05-02 | 2012-05-04 | #VALUE! | 2 | #VALUE! | 2012-05-04 | 2012-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-08-10 |  | 2015-02-03 | Online |  | Gov't | Y
NSTAR | Carver | 2122 | 2330 | 95 | PV | 3-10-930 | 2012-05-04 | 2012-05-16 | #VALUE! | 8 | #VALUE! | 2012-05-22 | 2012-08-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-22 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2012-08-22 | Private | Y
NSTAR | Woburn | 2123 | 1801 | 288 | PV | 375-H1 | 2012-05-04 | 2012-05-07 | #VALUE! | 1 | #VALUE! | 2012-05-08 | 2012-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2124 | 2367 | 1500 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | #VALUE! | 1 | #VALUE! | 2012-05-08 | 2012-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2125 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | #VALUE! | 1 | #VALUE! | 2012-05-08 | 2012-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2126 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | #VALUE! | 1 | #VALUE! | 2012-05-08 | 2012-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2127 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-08 | 2012-05-15 | #VALUE! | 5 | #VALUE! | 2012-05-15 | 2012-07-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-02-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-05-10 |  | 2012-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Wareham | 2128 | 2571 | 583 | PV | 4-83-83 | 2012-05-10 | 2012-06-11 | #VALUE! | 22 | #VALUE! | 2012-06-11 | 2012-07-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-27 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-27 | Online |  | Private | Y
NSTAR | Wayland | 2129 | 1778 | 150 | PV | 342-H1 | 2012-05-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2012-11-16 | Online |  | Gov't | Y
NSTAR | Wareham | 2130 | 2571 | 583 | PV | 3-83-83 | 2012-05-11 | 2012-05-14 | #VALUE! | 0 | #VALUE! | 2012-05-14 | 2012-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-07-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Newton | 2131 | 2465 | 11 | PV | 1707 | 2012-05-15 | 2012-05-25 | #VALUE! | 8 | #VALUE! | 2012-05-29 | 2012-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-14 | Online |  | Private | Y
NSTAR | Norfolk | 2132 | 2056 | 14 | PV | 146-H3 | 2012-05-16 | 2012-06-27 | #VALUE! | 30 | #VALUE! | 2012-06-27 | 2012-07-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-06-18 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-07 |  | 2012-12-07 | Online |  | Gov't | Y
NSTAR | Boston | 2133 | 2218 | 102 | PV | 574-70H | 2012-05-14 | 2012-06-01 | #VALUE! | 12 | #VALUE! | 2012-06-01 | 2012-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-19 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-24 | Online |  | Private | Y
NSTAR | Dover | 2134 | 2030 | 13 | PV | 456-H3 | 2012-05-16 | 2012-06-01 | #VALUE! | 12 | #VALUE! | 2012-06-01 | 2012-07-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2012-07-18 | Private | Y
NSTAR | Lincoln | 2135 | 1733 | 11 | PV | 282-H1 | 2012-05-17 | 2012-05-17 | 0 | 0 | 0 | 2012-05-22 | 2012-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-20 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online |  | Private | Y
NSTAR | Dartmouth | 2136 | 2747 | 276 | PV | 2-543-543 | 2012-05-21 | 2012-05-21 | 0 | 0 | 0 | 2012-05-22 | 2012-08-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | East Walpole | 2137 | 2032 | 360 | PV | 135-1319H1 | 2012-05-21 | 2012-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Design Stage |  | Private | Y
NSTAR | Boston | 2138 | 2114 | 555 | Natural Gas | 2-1N11 | 2012-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Boston | 2140 | 2118 | 60 | Natural Gas | 528-129H | 2012-05-23 | 2012-09-19 | #VALUE! | 84 | #VALUE! | 2012-09-19 | 2013-01-07 | #VALUE! | 25 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-11 | Online |  | Gov't | Y
NSTAR | Buzzards Bay | 2141 | 2532 | 96 | PV | 3-84-965 | 2012-05-22 | 2012-06-29 | #VALUE! | 26 | #VALUE! | 2012-06-29 | 2012-08-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-12-10 | Online |  | Private | Y
NSTAR | Wayland | 2142 | 1778 | 19 | PV | 278-H2 | 2012-05-30 | 2012-06-20 | #VALUE! | 13 | #VALUE! | 2012-06-20 | 2012-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-23 | Online |  | Gov't | Y
NSTAR | Duxbury | 2143 | 2331 | 500 | PV | 3-26-903 | 2012-06-04 | 2012-06-19 | #VALUE! | 10 | #VALUE! | 2012-06-19 | 2012-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-10-02 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-26 |  | 2014-06-23 | Online |  | Gov't | Y
NSTAR | Framingham | 2144 | 1702 | 500 | PV | 455-H6 | 2012-06-01 | 2012-06-14 | #VALUE! | 7 | #VALUE! | 2012-06-14 | 2012-07-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-26 | Online |  | Private | Y
NSTAR | West Tisbury | 2145 | 2568 | 13 | PV | 4-97-220 | 2012-05-23 | 2012-09-27 | #VALUE! | 82 | #VALUE! | 2012-09-27 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 | 2013-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | New Bedford | 2146 | 2745 | 1750 | PV | 2-102-102 | 2012-06-01 | 2012-08-07 | #VALUE! | 45 | #VALUE! | 2013-03-12 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-04-13 | Private | Y
NSTAR | Canton | 2147 | 2021 | 260 | PV | 470-H11 | 2012-06-01 | 2012-08-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2013-08-06 | Eng Stage: Awaiting Customer's Response/Docs | 2012-09-24 | Private | Y
NSTAR | Canton | 2148 | 2021 | 200 | PV | 470-H11 | 2012-06-05 | 2012-06-08 | #VALUE! | 0 | #VALUE! | 2012-06-08 | 2012-08-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online |  | Private | Y
NSTAR | New Bedford | 2149 | 2745 | 100 | PV | 2-103-103 | 2012-06-06 | 2012-06-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Design Stage |  | Private | N
NSTAR | Cambridge | 2150 | 2142 | 1966 | Natural Gas | 814-17 | 2012-06-11 | 2012-07-26 | #VALUE! | 30 | #VALUE! | 2012-07-27 | 2012-08-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-04 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-29 | Online |  | Gov't | Y
NSTAR | Millis | 2151 | 2054 | 135 | PV | 146-H10 | 2012-06-07 | 2012-09-27 | #VALUE! | 75 | #VALUE! | 2012-09-27 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | New Bedford | 2152 | 2745 | 1750 | PV | 2-102-102 | 2012-06-18 | 2012-10-23 | #VALUE! | 89 | #VALUE! | 2012-10-23 | 2012-11-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online |  | Private | Y
NSTAR | Weston | 2153 | 2493 | 60 | PV | 450-H7 | 2012-06-18 | 2012-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-08-29 | Private | Y
NSTAR | Marshfield | 2154 | 2500 | 14 | PV | 3-25-25 | 2012-06-20 | 2012-08-16 | #VALUE! | 33 | #VALUE! | 2012-08-16 | 2012-12-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-15 | 2012-12-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-06-05 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-06 | Online |  | Gov't | Y
NSTAR | West Wareham | 2156 | 2576 | 60 | PV | 3-86-966 | 2012-06-20 | 2012-08-16 | #VALUE! | 33 | #VALUE! | 2012-08-16 | 2012-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Plymouth | 2157 | 2360 | 2000 | PV | 3-89-89 | 2012-06-20 | 2012-08-16 | #VALUE! | 33 | #VALUE! | 2012-08-16 | 2012-09-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Plymouth | 2158 | 2360 | 2000 | PV | 3-89-89 | 2012-06-27 | 2012-08-16 | #VALUE! | 29 | #VALUE! | 2012-08-16 | 2012-09-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-18 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
NSTAR | Hyannis | 2159 | 2601 | 60 | PV | 4-63-905 | 2012-06-28 | 2012-07-24 | #VALUE! | 12 | #VALUE! | 2012-07-24 | 2012-08-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-31 |  | 2012-08-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-08 | Online |  | Private | Y
NSTAR | Newton Center | 2160 | 2459 | 11 | PV | 467-H12 | 2012-07-02 | 2012-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2013-04-29 | Gov't | Y
NSTAR | Burlington | 2161 | 1805 | 3000 | Natural Gas | 541-1377H | 2012-07-13 | 2012-07-25 | #VALUE! | 7 | #VALUE! | 2012-07-25 | 2012-11-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-23 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2162 | 2360 | 142 | PV | 3-13-936 | 2012-07-10 | 2012-07-18 | #VALUE! | 1 | #VALUE! | 2012-07-18 | 2012-08-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-08-28 | Private | Y
NSTAR | Boston | 2163 | 2210 | 250 | Natural Gas | 385-H5 | 2012-07-10 | 2012-08-10 | #VALUE! | 17 | #VALUE! | 2012-08-10 | 2012-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-11 | 2013-12-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 2164 | 2743 | 2000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | #VALUE! | 17 | #VALUE! | 2012-08-10 | 2012-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 2165 | 2743 | 1000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | #VALUE! | 17 | #VALUE! | 2012-08-10 | 2012-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Acusnet | 2166 | 2743 | 2000 | PV | 2-241-327 | 2012-07-18 | 2012-07-25 | #VALUE! | 3 | #VALUE! | 2012-07-27 | 2012-11-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | South Dennis | 2167 | 2660 | 500 | PV | 4-89A-553 | 2012-07-18 | 2012-07-27 | #VALUE! | 5 | #VALUE! | 2012-07-27 | 2012-12-18 | #VALUE! | 8 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 | 2013-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-11-19 | Online |  | Gov't | Y
NSTAR | West Yarmouth | 2168 | 2673 | 750 | PV | 4-92A-92A | 2012-07-18 | 2012-07-27 | #VALUE! | 5 | #VALUE! | 2012-07-27 | 2013-01-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-27 | Online |  | Gov't | Y
NSTAR | West Yarmouth | 2169 | 2673 | 200 | PV | 4-92A-92A | 2012-07-20 | 2012-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-09-14 | Private | Y
NSTAR | Woburn | 2170 | 1801 | 485 | PV | 375-H4 | 2012-07-20 | 2012-07-31 | #VALUE! | 5 | #VALUE! | 2012-08-01 | 2012-09-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  | 2012-08-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-11-15 |  |  | Withdrawn |  | Private | Y
NSTAR | Marshfield | 2171 | 2050 | 82 | PV | 3-24A-24A | 2012-07-24 | 2012-10-22 | #VALUE! | 64 | #VALUE! | 2012-10-22 | 2013-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | West Yarmouth | 2172 | 2673 | 750 | PV | 4-92A-92A | 2012-07-25 | 2012-11-30 | #VALUE! | 92 | #VALUE! | 2012-11-30 | 2013-02-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-06-19 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | South Yarmouth | 2173 | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-10-31 | #VALUE! | 70 | #VALUE! | 2012-10-31 | 2013-03-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-14 | Online |  | Gov't | Y
NSTAR | West Dennis | 2174 | 2122 | 75 | PV | 4-92B-92B | 2012-07-25 | 2012-11-30 | #VALUE! | 92 | #VALUE! | 2012-11-30 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-05-05 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-05 | Online |  | Gov't | Y
NSTAR | South Yarmouth | 2175 | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-08-06 | #VALUE! | 8 | #VALUE! | 2012-08-06 | 2012-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-08-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-10-24 | 2013-10-24 | 2015-03-05 | Online |  | Gov't | Y
NSTAR | Sudbury | 2176 | 1776 | 1333 | PV | 342-H3 | 2012-07-26 | 2012-08-15 | #VALUE! | 14 | #VALUE! | 2012-08-16 | 2012-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-14 |  | 2012-08-06 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online |  | Gov't | Y
NSTAR | Wayland | 2177 | 1778 | 12 | PV | 278-H2 | 2012-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Buzzards Bay | 2178 | 2532 | 50 | PV | 3-88-88 | 2012-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Buzzards Bay | 2179 | 2532 | 21 | PV | 3-89-925 | 2012-07-30 | 2012-10-22 | #VALUE! | 59 | #VALUE! | 2012-12-18 | 2013-01-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-01-31 | Gov't | Y
NSTAR | Bourne | 2180 | 2532 | 425 | PV | 4-86-402 | 2013-05-01 | 2013-05-03 | #VALUE! | 0 | #VALUE! | 2013-05-03 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 | 2013-09-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-15 | Online |  | Gov't | Y
NSTAR | Hyannis | 2181 | 2601 | 4500 | PV | 4-84B-524 | 2012-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Forestdale | 2182 | 2644 | 100 | PV | 4-81B-443 | 2012-07-30 | 2012-11-06 | #VALUE! | 70 | #VALUE! | 2012-11-06 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-15 | Online |  | Gov't | Y
NSTAR | Provincetown | 2183 | 2657 | 135 | PV | 4-96-675 | 2012-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | East Sandwich | 2184 | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-08-22 | #VALUE! | 16 | #VALUE! | 2012-08-22 | 2012-09-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-29 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Hyannis | 2185 | 2601 | 500 | PV | 4-80B-514 | 2012-07-30 | 2012-08-22 | #VALUE! | 16 | #VALUE! | 2012-08-22 | 2012-11-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-20 | Online |  | Gov't | Y
NSTAR | Marston Mills | 2186 | 2648 | 61 | PV | 4-88-88 | 2012-07-30 | 2012-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | 2013-01-15 | Gov't | Y
NSTAR | Chatham | 2188 | 2633 | 868 | PV | 4-95B-95B | 2012-07-30 | 2012-10-23 | #VALUE! | 59 | #VALUE! | 2012-10-23 | 2012-12-20 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-07-30 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-12-31 | Online |  | Gov't | Y
NSTAR | West Tisbury | 2189 | 2568 | 850 | PV | 4-91-220 | 2012-07-30 | 2012-10-23 | #VALUE! | 59 | #VALUE! | 2013-04-08 | 2013-05-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Vineyard Haven | 2190 | 2568 | 50 | PV | 4-97-228 | 2012-07-30 | 2012-08-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-17 | Online |  | Gov't | N
NSTAR | Assonett | 2191 | 2702 | 1500 | PV | 2-606-605 | 2012-07-30 | 2012-12-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Gov't | Y
NSTAR | Barnstable | 2192 | 2601 | 1250 | PV | 4-80B-80B | 2012-07-30 | 2012-12-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Barnstable | 2193 | 2601 | 1750 | PV | 4-80B-80B | 2012-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | East Sandwich | 2194 | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-10-23 | #VALUE! | 59 | #VALUE! | 2012-10-23 | 2013-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Buzzards Bay | 2195 | 2532 | 35 | PV | 3-88-88 | 2012-08-02 | 2012-08-06 | #VALUE! | 2 | #VALUE! | 2012-08-08 | 2012-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-08-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-25 | Online |  | Private | Y
NSTAR | Needham | 2196 | 2492 | 14 | PV | 148-01 | 2012-08-02 | 2012-08-13 | #VALUE! | 7 | #VALUE! | 2012-08-14 | 2012-10-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-25 |  | 2012-09-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-10 | Online |  | Private | Y
NSTAR | Natick | 2197 | 1760 | 14 | PV | 433-H5 | 2012-08-01 | 2012-08-23 | #VALUE! | 14 | #VALUE! | 2012-08-23 | 2012-11-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-29 | Online |  | Gov't | Y
NSTAR | West Tisbury | 2198 | 2575 | 34 | PV | 4-97-97 | 2012-08-03 | 2012-09-13 | #VALUE! | 29 | #VALUE! | 2012-09-13 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-01-08 | Gov't | Y
NSTAR | Eastham | 2199 | 2642 | 500 | PV | 4-94B-646 | 2012-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Oak Bluffs | 2200 | 2557 | 100 | PV | 4-75-75 | 2012-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Provincetown | 2201 | 2657 | 50 | PV | 4-96-675 | 2012-08-06 | 2012-08-23 | #VALUE! | 13 | #VALUE! | 2012-08-23 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hyannis | 2202 | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | #VALUE! | 13 | #VALUE! | 2012-08-23 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hyannis | 2203 | 2601 | 1000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | #VALUE! | 13 | #VALUE! | 2012-08-23 | 2012-10-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hyannis | 2204 | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-12-27 | #VALUE! | 103 | #VALUE! | 2012-12-27 | 2013-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Brewster | 2205 | 2631 | 750 | PV | 4-89B-576 | 2012-08-06 | 2012-12-14 | #VALUE! | 94 | #VALUE! | 2012-12-21 | 2013-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Brewster | 2206 | 2631 | 3000 | PV | 4-95B-600 | 2012-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Brewster | 2207 | 2631 | 1000 | PV | 4-95B-600 | 2012-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2208 | 2747 | 500 | PV | 2-543-543 | 2012-08-06 | 2012-11-07 | #VALUE! | 66 | #VALUE! | 2012-11-07 | 2013-01-22 | #VALUE! | 13 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-04 | 2013-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-08-05 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dartmouth | 2209 | 2747 | 3500 | PV | 2-532-532 | 2012-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2210 | 2747 | 1000 | PV | 2-543-543 | 2012-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dartmouth | 2211 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dartmouth | 2212 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | #VALUE! | 9 | #VALUE! | 2012-08-23 | 2012-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dartmouth | 2213 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-10-12 | #VALUE! | 47 | #VALUE! | 2012-10-12 | 2012-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-04 | 2013-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Westport | 2214 | 2790 | 500 | PV | 2-523-523 | 2012-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Freetown | 2215 | 2717 | 1500 | PV | 2-102-102 | 2012-08-13 | 2012-08-13 | 0 | 0 | 0 | 2012-08-13 | 2012-09-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | North Dartmouth | 2216 | 2747 | 100 | PV | 2-543-543 | 2012-08-10 | 2012-08-15 | #VALUE! | 2 | #VALUE! | 2012-08-15 | 2012-09-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-06 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online |  | Gov't | Y
NSTAR | Orleans | 2217 | 2653 | 500 | PV | 4-95B-95B | 2012-08-10 | 2012-09-25 | #VALUE! | 30 | #VALUE! | 2012-09-25 | 2012-10-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Boston | 2218 | 2210 | 500 | PV | 385-H12 | 2012-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Freetown | 2219 | 2717 | 1500 | PV | 2-102-102 | 2012-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Freetown | 2220 | 2717 | 1500 | PV | 2-102-102 | 2012-08-16 | 2012-08-21 | #VALUE! | 3 | #VALUE! | 2012-08-22 | 2012-10-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-06-12 | 2013-06-12 |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2221 | 2360 | 649.74 | PV | 3-13-13 | 2012-08-15 | 2012-08-17 | #VALUE! | 1 | #VALUE! | 2012-08-17 | 2012-09-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online |  | Private | Y
NSTAR | Vineyard Haven | 2222 | 2568 | 12 | PV | 4-91-122 | 2012-08-07 | 2012-08-27 | #VALUE! | 7 | #VALUE! | 2012-08-27 | 2012-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-09 | Online |  | Private | Y
NSTAR | Sagamore Beach | 2223 | 2562 | 250 | PV | 3-89-925 | 2012-07-17 | 2012-08-21 | #VALUE! | 3 | #VALUE! | 2012-08-21 | 2012-09-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  | 2012-10-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-04 |  | 2014-09-09 | Online |  | Private | Y
NSTAR | Rochester | 2224 | 2770 | 17 | PV | 3-702-702 | 2012-08-16 | 2012-08-17 | #VALUE! | 1 | #VALUE! | 2012-10-12 | 2013-01-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Allston | 2225 | 2134 | 354 | PV | 467-H11 | 2012-08-16 | 2012-08-17 | #VALUE! | 0 | #VALUE! | 2012-08-17 | 2012-11-19 | #VALUE! | 21 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-14 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs and NSTARwork completion |  | Gov't | Y
NSTAR | Wareham | 2226 | 2538 | 4000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | #VALUE! | 0 | #VALUE! | 2012-08-17 | 2012-10-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Wareham | 2227 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | #VALUE! | 0 | #VALUE! | 2012-08-17 | 2012-10-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Wareham | 2228 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | #VALUE! | 0 | #VALUE! | 2012-08-17 | 2012-10-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Wareham | 2229 | 2538 | 1000 | PV | 3-83-83 | 2012-08-20 | 2012-08-27 | #VALUE! | 5 | #VALUE! | 2012-08-27 | 2012-10-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-25 | No | EXP |  |  |  | 0 | 0 | 0 |  | 2013-03-11 |  |  |  | Private | Y
NSTAR | Dover | 2230 | 2030 | 23 | PV | 456-H5 | 2012-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Westport | 2231 | 2790 | 500 | PV | 2-523-523 | 2012-08-24 | 2012-09-06 | #VALUE! | 8 | #VALUE! | 2012-09-06 | 2012-11-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-09-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Lincoln | 2232 | 1733 | 13 | PV | 320-H6 | 2012-08-24 | 2012-08-30 | #VALUE! | 3 | #VALUE! | 2012-08-30 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2014-06-24 |  |  | Awaiting Witness test |  | Gov't | Y
NSTAR | Newton | 2233 | 2460 | 260 | PV | 17-H1 | 2012-08-24 | 2012-08-30 | #VALUE! | 3 | #VALUE! | 2012-08-30 | 2012-11-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-24 | Online |  | Gov't | Y
NSTAR | Newton | 2234 | 2461 | 100 | PV | 433-02 | 2012-08-24 | 2012-08-30 | #VALUE! | 3 | #VALUE! | 2012-08-30 | 2012-09-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-05 | 2012-09-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online |  | Gov't | Y
NSTAR | Newton | 2235 | 2459 | 200 | PV | 292-H8 | 2012-08-27 | 2012-08-30 | #VALUE! | 3 | #VALUE! | 2013-09-06 | 2013-10-10 | #VALUE! | 228 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online |  | Gov't | Y
NSTAR | Lexington | 2236 | 2421 | 260 | PV | 533-H2 | 2012-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Barnstable | 2237 | 2360 | 11 | PV | 4-82-518 | 2012-08-29 | 2012-10-16 | #VALUE! | 34 | #VALUE! | 2012-10-16 | 2013-01-30 | #VALUE! | 65 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2238 | 2360 | 95 | PV | 3-12-12 | 2012-08-29 | 2012-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2012-09-21 | Private | Y
NSTAR | West Yarmouth | 2239 | 2673 | 150 | PV | 4-92A-536 | 2012-08-30 | 2012-10-03 | #VALUE! | 24 | #VALUE! | 2012-10-03 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dorchester | 2240 | 2122 | 95 | PV | 511-1498H1 | 2012-08-28 | 2012-09-12 | #VALUE! | 3 | #VALUE! | 2012-09-12 | 2013-04-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-01-06 | Online |  | Private | Y
NSTAR | New Bedford | 2241 | 2740 | 190 | PV | 2-81-94 | 2012-08-21 | 2012-09-07 | #VALUE! | 6 | #VALUE! | 2012-09-07 | 2012-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-31 |  | 2012-10-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-09-11 | 2013-10-11 | Online |  | Private | Y
NSTAR | New Bedford | 2242 | 2740 | 225 | PV | 2-84-84 | 2012-08-22 | 2012-09-07 | #VALUE! | 5 | #VALUE! | 2012-09-07 | 2012-11-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-11 | Online |  | Private | Y
NSTAR | East Falmouth | 2243 | 2536 | 11 | PV | 4-98B-449 | 2012-08-31 | 2012-09-06 | #VALUE! | 4 | #VALUE! | 2012-09-06 | 2012-10-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-13 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-30 | 2013-01-30 | 2013-01-30 | Online |  | Gov't | Y
NSTAR | Lexington | 2244 | 2421 | 56 | PV | 320-H5XY | 2012-08-30 | 2012-09-11 | #VALUE! | 5 | #VALUE! | 2012-09-11 | 2013-01-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-23 | 2013-04-23 | 2013-04-23 | Online |  | Gov't | Y
NSTAR | Harwich | 2245 | 2661 | 20 | PV | 320-H5XY | 2012-09-05 | 2012-12-05 | #VALUE! | 65 | #VALUE! | 2012-12-05 | 2013-02-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-05 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-02-21 | 2013-02-21 | 2013-02-21 | Online |  | Private | Y
NSTAR | Walpole | 2246 | 2081 | 300 | PV | 4-85-592 | 2012-09-05 | 2012-09-26 | #VALUE! | 15 | #VALUE! | 2012-09-26 | 2012-12-18 | #VALUE! | 46 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online |  | Private | Y
NSTAR | Canton | 2247 | 2021 | 237 | PV | 135-1319H1 | 2012-09-05 | 2012-09-10 | #VALUE! | 3 | #VALUE! | 2012-09-10 | 2012-11-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-04 | Online |  | Private | Y
NSTAR | Woburn | 2248 | 1801 | 12 | PV | 211-H5 | 2012-09-04 | 2012-09-11 | #VALUE! | 3 | #VALUE! | 2012-09-11 | 2012-11-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Newton | 2250 | 2461 | 50 | PV | 292-H11 | 2012-09-06 | 2013-05-10 | #VALUE! | 175 | #VALUE! | 2013-05-10 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
NSTAR | Assonett | 2251 | 2702 | 500 | PV | 2-605-605 | 2012-09-14 | 2012-09-24 | #VALUE! | 6 | #VALUE! | 2012-09-24 | 2012-12-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Newton | 2252 | 2460 | 20 | PV | 282-H9 | 2012-09-17 | 2012-09-18 | #VALUE! | 1 | #VALUE! | 2012-09-18 | 2012-10-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-26 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online |  | Private | Y
NSTAR | Lexington | 2253 | 2420 | 18 | PV | 391-H3 | 2012-09-17 | 2012-09-19 | #VALUE! | 1 | #VALUE! | 2012-10-04 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-13 | 2013-12-13 | 2013-12-20 | Online |  | Private | Y
NSTAR | Plymouth | 2254 | 2360 | 361 | PV | 3-14-911 | 2012-09-17 | 2012-09-20 | #VALUE! | 2 | #VALUE! | 2012-09-20 | 2012-10-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-10 | 2013-09-19 | #VALUE! | 0 | #VALUE! | 2013-09-26 |  | #VALUE! | 0 | #VALUE! | 2013-12-09 |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online |  | Private | N
NSTAR | Acusnet | 2255 | 2745 | 750 | PV | 221 | 2012-09-18 | 2012-12-27 | #VALUE! | 70 | #VALUE! | 2013-11-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-29 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-10-17 |  | 2013-07-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage |  | Gov't | Y
NSTAR | New Bedford | 2256 | 2745 | 5000 | PV | 2-102-604 | 2012-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Harwich | 2257 | 2645 | 4000 | PV | 4-89A-89A | 2012-09-21 | 2012-09-26 | #VALUE! | 3 | #VALUE! | 2012-09-26 | 2013-01-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | West Harwich | 2258 | 2671 | 11 | PV | 4-85-925 | 2012-09-21 | 2012-09-26 | #VALUE! | 3 | #VALUE! | 2012-09-26 | 2013-01-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | West Harwich | 2259 | 2671 | 11 | PV | 4-85-925 | 2012-09-26 | 2012-10-12 | #VALUE! | 12 | #VALUE! | 2012-10-16 | 2013-01-30 | #VALUE! | 36 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | #VALUE! | 0 | #VALUE! | 2013-09-26 |  | #VALUE! | 0 | #VALUE! | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-19 | Online |  | Gov't | Y
NSTAR | Mattapoisett | 2260 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-10-12 | #VALUE! | 12 | #VALUE! | 2012-10-16 | 2013-01-30 | #VALUE! | 36 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | #VALUE! | 0 | #VALUE! | 2013-09-26 |  | #VALUE! | 0 | #VALUE! | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage |  | Gov't | N
NSTAR | Mattapoisett | 2261 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-11-27 | #VALUE! | 44 | #VALUE! | 2012-11-27 | 2013-02-06 | #VALUE! | 11 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-02-25 |  | 2013-10-15 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-18 | Online |  | Private | Y
NSTAR | Holliston | 2262 | 1746 | 3000 | PV | 3-88-2J2 | 2012-09-28 | 2012-09-28 | 0 | 0 | 0 | 2012-10-17 | 2012-12-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-11 | Online |  | Gov't | Y
NSTAR | Wayland | 2263 | 1778 | 13 | PV | 342-H1 | 2012-09-29 | 2012-10-17 | #VALUE! | 12 | #VALUE! | 2012-10-17 | 2012-12-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
NSTAR | Sudbury | 2264 | 1776 | 12 | PV | 342-H8 | 2012-09-29 | 2012-11-07 | #VALUE! | 27 | #VALUE! | 2012-11-07 | 2012-12-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-11 |  | 2012-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online |  | Private | Y
NSTAR | Sudbury | 2265 | 1776 | 12 | PV | 342-H2 | 2012-09-29 | 2012-10-17 | #VALUE! | 12 | #VALUE! | 2012-10-17 | 2012-12-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wayland | 2266 | 1778 | 12 | PV | 342-H9 | 2012-10-01 | 2012-11-28 | #VALUE! | 41 | #VALUE! | 2012-11-28 | 2013-01-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-09 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online |  | Private | Y
NSTAR | Plymouth | 2267 | 2360 | 12 | PV | 3-11-11 | 2012-10-01 | 2012-11-28 | #VALUE! | 41 | #VALUE! | 2012-11-28 | 2013-01-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online |  | Private | Y
NSTAR | Wayland | 2268 | 1778 | 10 | PV | 342-H1 | 2012-10-01 | 2012-10-24 | #VALUE! | 16 | #VALUE! | 2012-10-24 | 2013-01-15 | #VALUE! | 26 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 |  | 2012-10-22 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online |  | Private | Y
NSTAR | Brewster | 2269 | 2631 | 16 | PV | 4-89B-89B | 2012-10-02 | 2012-10-24 | #VALUE! | 16 | #VALUE! | 2012-10-24 | 2012-12-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-13 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-05 | Online |  | Private | Y
NSTAR | Wayland | 2270 | 1778 | 17 | PV | 342-H1 | 2012-10-02 | 2012-11-07 | #VALUE! | 26 | #VALUE! | 2012-11-14 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-31 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-14 | Online |  | Private | Y
NSTAR | Lincoln | 2271 | 1773 | 14 | PV | 282-H1 | 2012-10-02 | 2012-10-24 | #VALUE! | 16 | #VALUE! | 2012-10-24 | 2012-12-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-28 | Online |  | Private | Y
NSTAR | Lincoln | 2272 | 1773 | 12 | PV | 320-H6 | 2012-10-02 | 2012-11-13 | #VALUE! | 30 | #VALUE! | 2012-11-13 | 2012-12-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  | 2012-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-09 | Online |  | Private | Y
NSTAR | Wayland | 2273 | 1778 | 14 | PV | 278-H2 | 2012-10-02 | 2012-11-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2013-03-19 | Private | Y
NSTAR | Bellingham | 2274 | 2019 | 1000 | PV | 65-H4 | 2012-10-02 | 2012-11-06 | #VALUE! | 23 | #VALUE! | 2012-11-06 | 2013-01-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-11-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-01 | 2013-04-01 |  |  |  | Private | Y
NSTAR | Brewster | 2275 | 2631 | 25 | PV | 4-89B-945 | 2012-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Bellingham | 2276 | 2019 | 1000 | PV | 65-H4 | 2012-10-03 | 2012-10-12 | #VALUE! | 6 | #VALUE! | 2012-10-12 | 2012-12-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-31 |  |  |  |  | Private | Y
NSTAR | Waltham | 2277 | 2452 | 12 | PV | 33-H2 | 2012-10-03 | 2012-10-12 | #VALUE! | 6 | #VALUE! | 2012-10-12 | 2013-01-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-01 | Online |  | Private | Y
NSTAR | Harwich | 2278 | 2645 | 13 | PV | 4-95A-597 | 2012-10-04 | 2012-10-31 | #VALUE! | 18 | #VALUE! | 2012-10-31 | 2012-12-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
NSTAR | Holliston | 2279 | 1746 | 15 | PV | 65-H5 | 2012-10-15 | 2012-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-12-23 | Online |  | Private | Y
NSTAR | Cambridge | 2280 | 2139 | 7500 | Natural Gas | 817-48 | 2012-10-17 | 2012-10-25 | #VALUE! | 5 | #VALUE! | 2012-10-26 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online |  | Private | Y
NSTAR | Sudbury | 2281 | 1776 | 12 | PV | 342-H8 | 2012-10-18 | 2012-11-29 | #VALUE! | 30 | #VALUE! | 2012-11-29 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-07 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wayland | 2282 | 1778 | 11 | PV | 342-H1 | 2012-10-22 | 2012-11-07 | #VALUE! | 12 | #VALUE! | 2012-11-07 | 2012-12-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-08-14 |  | 2012-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online |  | Gov't | Y
NSTAR | Plymouth | 2283 | 2360 | 4260 | PV | 3-71-71 | 2012-10-23 | 2012-10-25 | #VALUE! | 2 | #VALUE! | 2012-10-26 | 2012-12-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online |  | Gov't | Y
NSTAR | Plymouth | 2284 | 2360 | 75 | PV | 3-14-911 | 2012-10-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2285 | 2360 | 75 | PV | 3-14-911 | 2012-10-25 | 2012-11-06 | #VALUE! | 8 | #VALUE! | 2012-11-06 | 2013-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online |  | Private | Y
NSTAR | Carlisle | 2286 | 1741 | 14 | PV | 512-1399H1 | 2012-10-25 | 2012-11-01 | #VALUE! | 4 | #VALUE! | 2012-11-01 | 2012-12-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-14 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-25 | Online |  | Private | Y
NSTAR | West Tisbury | 2287 | 2575 | 26 | PV | 4-97-220 | 2012-10-25 | 2012-10-31 | #VALUE! | 3 | #VALUE! | 2012-10-31 | 2013-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2012-12-12 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online |  | Private | Y
NSTAR | Framingham | 2288 | 1701 | 25 | PV | 433-H4 | 2012-10-25 | 2012-10-31 | #VALUE! | 3 | #VALUE! | 2012-10-31 | 2013-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-11-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-24 | Online |  | Private | Y
NSTAR | Framingham | 2289 | 1702 | 20 | PV | 278-H1 | 2012-10-26 | 2012-11-29 | #VALUE! | 24 | #VALUE! | 2012-11-29 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-29 | Online |  | Private | Y
NSTAR | Cambridge | 2290 | 2139 | 14 | PV | 817-03 | 2012-10-26 | 2013-01-07 | #VALUE! | 51 | #VALUE! | 2013-01-11 | 2013-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Framingham | 2291 | 1702 | 20 | PV | 455-H5 | 2012-10-31 | 2012-11-27 | #VALUE! | 19 | #VALUE! | 2012-11-27 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-13 | Online |  | Private | Y
NSTAR | Lincoln | 2292 | 1773 | 12 | PV | 320-H8 | 2012-10-31 | 2012-11-30 | #VALUE! | 22 | #VALUE! | 2012-11-30 | 2013-01-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Lincoln | 2293 | 1773 | 11 | PV | 320-H1 | 2012-10-31 | 2012-11-27 | #VALUE! | 19 | #VALUE! | 2012-11-27 | 2013-01-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online |  | Private | Y
NSTAR | Lincoln | 2294 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | #VALUE! | 1 | #VALUE! | 2013-04-22 | 2013-04-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-05 | Online |  | Private | Y
NSTAR | Lincoln | 2295 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | #VALUE! | 1 | #VALUE! | 2012-11-01 | 2012-12-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
NSTAR | Wayland | 2296 | 1778 | 12 | PV | 342-H1 | 2012-10-31 | 2012-11-01 | #VALUE! | 1 | #VALUE! | 2012-11-01 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-23 | Online |  | Private | Y
NSTAR | Wayland | 2297 | 1778 | 11 | PV | 342-H1 | 2012-11-02 | 2012-11-07 | #VALUE! | 3 | #VALUE! | 2012-11-27 | 2013-01-22 | #VALUE! | 17 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-11-14 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online |  | Private | Y
NSTAR | Acusnet | 2298 | 2745 | 425 | PV | 2-86-86 | 2012-11-06 | 2012-11-08 | #VALUE! | 2 | #VALUE! | 2012-11-08 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-13 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online |  | Private | Y
NSTAR | Plymouth | 2299 | 2360 | 132 | PV | 3-89-925 | 2012-11-06 | 2012-11-27 | #VALUE! | 15 | #VALUE! | 2012-11-27 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-12-27 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-24 | Online |  | Private | Y
NSTAR | North Dartmouth | 2300 | 2747 | 20 | PV | 2-528-528 | 2012-10-31 | 2012-11-14 | #VALUE! | 0 | #VALUE! | 2012-11-14 | 2013-01-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online |  | Gov't | Y
NSTAR | West Roxbury | 2301 | 2132 | 60 | PV | 468-01 | 2012-11-09 | 2012-11-16 | #VALUE! | 2 | #VALUE! | 2012-11-16 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Framingham | 2302 | 1702 | 4400 | PV | 274-H4 | 2012-11-13 | 2012-11-19 | #VALUE! | 3 | #VALUE! | 2012-11-19 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Withdrawn |  | Private | Y
NSTAR | Lexington | 2303 | 2421 | 11 | PV | 3409 | 2012-11-04 | 2012-11-20 | #VALUE! | 4 | #VALUE! | 2012-11-20 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2012-04-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Gov't | Y
NSTAR | Somerville | 2304 | 2145 | 42 | PV | 250-1N90H2 | 2012-11-19 | 2012-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Lexington | 2305 | 2421 | 10 | PV | 320-H5XY | 2012-11-21 | 2012-11-28 | #VALUE! | 5 | #VALUE! | 2012-11-28 | 2012-12-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online |  | Private | Y
NSTAR | Dover | 2306 | 2030 | 12 | PV | 456-H5 | 2012-11-26 | 2012-12-05 | #VALUE! | 3 | #VALUE! | 2012-12-05 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2013-01-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online |  | Private | Y
NSTAR | Lincoln | 2307 | 1773 | 12 | PV | 320-H8 | 2012-11-27 | 2012-12-04 | #VALUE! | 5 | #VALUE! | 2012-12-04 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-02 | Online |  | Private | Y
NSTAR | West Barnstable | 2308 | 2668 | 40 | PV | 4-87B-473 | 2012-11-28 | 2012-12-11 | #VALUE! | 9 | #VALUE! | 2012-12-11 | 2013-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online |  | Private | Y
NSTAR | Woburn | 2309 | 1801 | 60 | PV | 375-H6 | 2012-11-28 | 2012-12-27 | #VALUE! | 19 | #VALUE! | 2012-12-27 | 2013-02-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-06 |  | 2013-01-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online |  | Private | Y
NSTAR | North Dartmouth | 2310 | 2747 | 13 | PV | 2-524-524 | 2012-12-03 | 2012-12-27 | #VALUE! | 16 | #VALUE! | 2012-12-27 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-07 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-20 | Online |  | Private | Y
NSTAR | Lincoln | 2311 | 1773 | 10 | PV | 320-H6 | 2012-12-03 | 2012-12-13 | #VALUE! | 6 | #VALUE! | 2012-12-27 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Online |  | Private | Y
NSTAR | Wayland | 2312 | 1778 | 18 | PV | 342-H3 | 2012-12-04 | 2012-12-11 | #VALUE! | 1 | #VALUE! | 2012-12-11 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-24 | Online |  | Gov't | Y
NSTAR | Plymouth | 2313 | 2360 | 333 | PV | 3-13-943 | 2012-12-05 | 2012-12-13 | #VALUE! | 1 | #VALUE! | 2012-12-13 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-26 |  | 2013-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-14 | Online |  | Gov't | Y
NSTAR | Sandwich | 2314 | 2537 | 28 | PV | 4-87B-473 | 2012-12-12 | 2012-12-17 | #VALUE! | 2 | #VALUE! | 2012-12-17 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-11 |  | 2013-01-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online |  | Private | Y
NSTAR | Plympton | 2315 | 2367 | 12 | PV | 3-51-901 | 2012-12-12 | 2012-12-20 | #VALUE! | 4 | #VALUE! | 2012-12-20 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2013-03-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-01 | Online |  | Private | Y
NSTAR | New Bedford | 2316 | 2745 | 100 | PV | 2-103-103 | 2012-12-13 | 2012-12-21 | #VALUE! | 5 | #VALUE! | 2012-12-21 | 2013-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online |  | Private | Y
NSTAR | Needham | 2317 | 2492 | 12 | PV | 148-03 | 2012-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Plymouth | 2318 | 2360 | 333 | PV | 3-13-943 | 2012-12-14 | 2012-12-27 | #VALUE! | 9 | #VALUE! | 2012-12-27 | 2013-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2013-01-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wayland | 2319 | 1778 | 11 | PV | 342-H1 | 2012-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | New Bedford | 2320 | 2745 | 100 | PV | 2-103-103 | 2012-12-17 | 2013-01-24 | #VALUE! | 26 | #VALUE! | 2013-01-24 | 2013-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-22 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-03-25 | Private | Y
NSTAR | Bedford | 2321 | 1730 | 24 | PV | 533-H8 | 2012-12-18 | 2012-12-20 | #VALUE! | 1 | #VALUE! | 2013-03-26 | 2013-04-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-06 | Online |  | Private | Y
NSTAR | Hopkinton | 2322 | 1748 | 190 | PV | 126-H1 | 2012-12-19 | 2012-12-21 | #VALUE! | 1 | #VALUE! | 2013-04-08 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-24 | Online |  | Private | Y
NSTAR | Brewster | 2323 | 2631 | 16 | PV | 4-89B-946 | 2012-12-26 | 2012-12-27 | #VALUE! | 1 | #VALUE! | 2012-12-27 | 2013-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-02-21 | Private | Y
NSTAR | Newton | 2324 | 2458 | 13 | PV | 277-05 | 2012-12-28 | 2013-01-24 | #VALUE! | 19 | #VALUE! | 2013-01-24 | 2013-04-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-05-02 | 2013-05-02 | 2013-05-02 | Online |  | Private | Y
NSTAR | Mashpee | 2325 | 2649 | 18 | PV | 4-71-455 | 2013-01-02 | 2013-01-09 | #VALUE! | 3 | #VALUE! | 2013-01-10 | 2013-04-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-02 |  | 2013-05-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online |  | Private | Y
NSTAR | North Dartmouth | 2326 | 2747 | 134 | PV | 2-533-503 | 2013-01-04 | 2013-01-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage |  | Gov't | Y
NSTAR | Carver | 2327 | 2330 | 2000 | PV | 433-H8 | 2013-01-08 | 2013-01-11 | #VALUE! | 3 | #VALUE! | 2013-01-16 | 2013-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-01-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-06-13 | 2013-06-13 | 2016-10-04 | Online |  | Private | Y
NSTAR | New Bedford | 2328 | 2745 | 345 | PV | 240-H3 | 2013-01-15 | 2013-01-22 | #VALUE! | 1 | #VALUE! | 2013-01-28 | 2013-03-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2013-03-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-13 | Online |  | Private | Y
NSTAR | Lincoln | 2329 | 1773 | 11 | PV | 320-H6 | 2013-01-21 | 2013-01-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2013-05-07 | Gov't | Y
NSTAR | West Yarmouth | 2330 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | West Yarmouth | 2331 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-23 | 2013-01-28 | #VALUE! | 0 | #VALUE! | 2013-04-22 | 2013-05-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | South Sandwich | 2332 | 2653 | 2250 | PV | 2-87A-475 | 2013-01-21 | 2013-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for the Study of a Nearby System | 2013-05-09 | Gov't | Y
NSTAR | West Yarmouth | 2333 | 2673 | 500 | PV | 2-92A-92A | 2013-01-21 | 2013-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | 2013-06-03 | Gov't | Y
NSTAR | Tisbury | 2334 | 2568 | 500 | PV | 4-91-91 | 2013-01-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | East Falmouth | 2335 | 2536 | 54 | PV | 4-98A-98A | 2013-01-25 | 2013-02-01 | #VALUE! | 4 | #VALUE! | 2013-02-27 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Gov't | Y
NSTAR | Bourne | 2336 | 2532 | 1680 | Wind | 4-81A-81A | 2013-01-25 | 2013-02-06 | #VALUE! | 7 | #VALUE! | 2013-03-01 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Gov't | N
NSTAR | Framingham | 2337 | 1702 | 150 | PV | 433-H8 | 2013-01-25 | 2013-02-06 | #VALUE! | 7 | #VALUE! | 2013-02-27 | 2013-04-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-05 | Online |  | Private | Y
NSTAR | Framingham | 2338 | 1702 | 190 | PV | 240-H3 | 2013-01-28 | 2013-01-29 | #VALUE! | 0 | #VALUE! | 2013-01-29 | 2013-02-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-11 |  | 2013-02-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online |  | Private | Y
NSTAR | Lincoln | 2339 | 1773 | 9 | PV | 320-H8 | 2013-01-28 | 2013-03-12 | #VALUE! | 30 | #VALUE! | 2013-03-13 | 2013-04-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-17 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-12 | 2013-08-12 | 2013-08-16 | Online |  | Private | N
NSTAR | Woburn | 2340 | 1801 | 336 | Natural Gas | 301-1386H | 2013-01-29 | 2013-02-06 | #VALUE! | 4 | #VALUE! | 2013-02-13 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2013-02-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online |  | Private | Y
NSTAR | Sudbury | 2341 | 1776 | 12 | PV | 342-H8 | 2013-01-31 | 2013-02-06 | #VALUE! | 3 | #VALUE! | 2013-02-27 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2342 | 2367 | 1000 | PV | 3-10-930 | 2013-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Chilmark | 2343 | 2535 | 12 | PV | 4-97-226 | 2013-02-01 | 2013-02-07 | #VALUE! | 1 | #VALUE! | 2013-03-06 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Millis | 2344 | 2052 | 1000 | PV | 65-H1 | 2013-02-05 | 2013-03-06 | #VALUE! | 19 | #VALUE! | 2013-03-21 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2013-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Boston | 2345 | 2118 | 60 | PV | 323-02 | 2013-02-04 | 2013-04-01 | #VALUE! | 36 | #VALUE! | 2013-04-02 | 2013-05-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-27 |  | 2013-03-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online |  | Private | Y
NSTAR | Sudbury | 2346 | 1776 | 41 | PV | 342-H7 | 2013-03-26 | 2013-04-01 | #VALUE! | 0 | #VALUE! | 2013-04-01 | 2013-05-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
NSTAR | Burlington | 2347 | 1803 | 351 | PV | 391-H12 | 2013-02-08 | 2013-05-14 | #VALUE! | 50 | #VALUE! | 2013-06-24 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-11 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
NSTAR | Kingston | 2348 | 2364 | 33 | PV | 3-26-902 | 2013-02-08 | 2013-03-06 | #VALUE! | 18 | #VALUE! | 2013-03-11 | 2013-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2013-11-08 | Online |  | Private | Y
NSTAR | Waltham | 2349 | 2451 | 120 | PV | 282-H5 | 2013-02-11 | 2013-02-14 | #VALUE! | 0 | #VALUE! | 2013-02-27 | 2013-04-09 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-16 | Online |  | Private | Y
NSTAR | Wareham | 2350 | 2571 | 1000 | PV | 3-83-83 | 2013-02-22 | 2013-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for Customer's Response / Revised Docs | 2013-06-17 | Private | Y
NSTAR | Boston | 2351 | 2115 | 5750 | Natural Gas | 335-1141 | 2013-02-21 | 2013-02-27 | #VALUE! | 3 | #VALUE! | 2013-02-28 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Norfolk | 2352 | 2056 | 82 | PV | 65-H1 | 2013-02-22 | 2013-03-06 | #VALUE! | 5 | #VALUE! | 2013-03-07 | 2013-04-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-05-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-08 | Online |  | Private | Y
NSTAR | Assonett | 2353 | 2702 | 142 | PV | 2-605-605 | 2013-02-26 | 2013-03-28 | #VALUE! | 20 | #VALUE! | 2013-04-01 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-31 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online |  | Private | Y
NSTAR | Plymouth | 2354 | 2360 | 85 | PV | 3-73-927 | 2013-03-04 | 2013-05-30 | #VALUE! | 62 | #VALUE! | 2013-05-30 | 2013-07-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-26 |  | 2013-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-08-11 | Online |  | Gov't | Y
NSTAR | Carver | 2355 | 2330 | 250 | PV | 3-51-901 | 2013-03-06 | 2013-03-06 | 0 | 0 | 0 | 2013-03-08 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-05-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Wayland | 2356 | 1778 | 10 | PV | 278-H2 | 2013-03-06 | 2013-03-13 | #VALUE! | 2 | #VALUE! | 2013-03-15 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-18 | Online |  | Private | Y
NSTAR | New Bedford | 2357 | 2746 | 50 | PV | 2-82-82 | 2013-03-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Winchester | 2358 | 1890 | 11 | PV | 211-H7XY | 2013-03-15 | 2013-10-09 | #VALUE! | 146 | #VALUE! | 2013-10-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-04-11 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
NSTAR | Oak Bluffs | 2359 | 2557 | 260 | PV | 4-75-75 | 2013-03-18 | 2013-03-25 | #VALUE! | 0 | #VALUE! | 2013-03-25 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
NSTAR | South Boston | 2360 | 2127 | 142 | PV | 106-H1 | 2013-03-21 | 2013-04-12 | #VALUE! | 14 | #VALUE! | 2013-04-17 | 2013-05-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-11-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | New Bedford | 2361 | 2745 | 2000 | PV | 4-??-103 | 2013-01-29 | 2013-03-25 | #VALUE! | 0 | #VALUE! | 2013-03-25 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Westwood | 2362 | 2090 | 17 | PV | 148-H3 | 2013-03-25 | 2013-03-29 | #VALUE! | 2 | #VALUE! | 2013-04-02 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-26 | Online |  | Private | Y
NSTAR | Weston | 2363 | 2493 | 20 | PV | 342-H1 | 2013-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2013-03-27 | Private | Y
NSTAR | Dartmouth | 2364 | 2747 | 17 | PV | 2-543-543 | 2013-03-27 | 2013-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Detailed Study Stage | 2013-08-16 | Private | Y
NSTAR | Edgartown | 2365 | 2539 | 266 | PV | 4-97-97 | 2013-03-26 | 2013-10-03 | #VALUE! | 133 | #VALUE! | 2013-10-04 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online |  | Private | Y
NSTAR | Edgartown | 2366 | 2539 | 18 | PV | 4-75-123 | 2013-03-28 | 2013-04-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | 2013-07-22 | Private | Y
NSTAR | Millis | 2367 | 2054 | 500 | PV | 146-H10 | 2013-03-21 | 2013-04-10 | #VALUE! | 5 | #VALUE! | 2013-04-10 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-18 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 |  | Withdrawn |  | Private | Y
NSTAR | North Dartmouth | 2368 | 2747 | 225 | PV | 2-543-543 | 2013-04-03 | 2013-04-26 | #VALUE! | 14 | #VALUE! | 2013-05-01 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Private | Y
NSTAR | New Bedford | 2369 | 2740 | 500 | PV | 2-59-59 | 2013-03-26 | 2013-04-08 | #VALUE! | 0 | #VALUE! | 2013-04-12 | 2013-04-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-02 | Online |  | Private | Y
NSTAR | Westport | 2370 | 2767 | 82 | PV | 2-522-522 | 2013-04-12 | 2013-04-17 | #VALUE! | 1 | #VALUE! | 2013-04-25 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-24 |  | 2013-06-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-13 | Online |  | Private | Y
NSTAR | Dartmouth | 2371 | 2747 | 19 | PV | 2-533-533 | 2013-04-10 | 2013-04-30 | #VALUE! | 10 | #VALUE! | 2013-04-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Freetown | 2372 | 2702 | 4999 | PV | 2-102-102 | 2013-04-12 | 2013-06-14 | #VALUE! | 43 | #VALUE! | 2013-06-17 | 2013-07-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-11-27 | #VALUE! | 11 | #VALUE! |  |  | 0 | 0 | 0 | 2014-03-13 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Dedham | 2373 | 2136 | 2000 | PV | 344-1413H1 | 2013-04-19 | 2013-04-29 | #VALUE! | 3 | #VALUE! | 2013-04-30 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Private | Y
NSTAR | West Tisbury | 2374 | 2575 | 15 | PV | 4-97-97 | 2013-04-24 | 2013-05-01 | #VALUE! | 3 | #VALUE! | 2013-05-01 | 2013-06-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Hopkinton | 2375 | 1748 | 4000 | PV | 126-H1 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Cambridge | 2376 | 2140 | 28 | PV | 825-26 | 2013-04-30 | 2013-06-19 | #VALUE! | 36 | #VALUE! | 2013-06-20 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-08 | Online |  | Private | Y
NSTAR | Arlington | 2377 | 2476 | 34 | PV | 5905 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-23 | Online |  | Private | Y
NSTAR | Cambridge | 2378 | 2140 | 35 | PV | 825-26 | 2013-04-30 | 2013-05-06 | #VALUE! | 4 | #VALUE! | 2013-05-20 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-24 | Online |  | Private | Y
NSTAR | Jamaica Plain | 2379 | 2130 | 60 | PV | 396 | 2013-05-01 | 2013-05-14 | #VALUE! | 9 | #VALUE! | 2013-05-16 | 2013-06-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Gov't | N
NSTAR | Boston | 2380 | 2129 | 75 | Natural Gas | 530-178 | 2013-05-01 | 2013-05-06 | #VALUE! | 3 | #VALUE! | 2013-05-06 | 2013-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-27 | Online |  | Private | Y
NSTAR | Chilmark | 2381 | 2535 | 27 | PV | 4-97-126 | 2013-04-17 | 2013-05-08 | #VALUE! | 5 | #VALUE! | 2013-05-17 | 2013-06-26 | #VALUE! | 6 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Mashpee | 2382 | 2649 | 5000 | PV | 4-88-453 | 2013-05-02 | 2013-05-31 | #VALUE! | 19 | #VALUE! | 2013-06-01 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | North Dartmouth | 2383 | 2747 | 75 | PV | 2-532-532 | 2013-05-07 | 2013-05-16 | #VALUE! | 6 | #VALUE! | 2013-05-17 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-25 | Online |  | Private | Y
NSTAR | Chelsea | 2384 | 2150 | 50 | PV | 488-H7 | 2013-05-08 | 2013-05-16 | #VALUE! | 5 | #VALUE! | 2013-05-21 | 2013-09-05 | #VALUE! | 0 | #VALUE! | 2013-09-13 | 2013-09-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-17 |  | 2013-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Boston | 2385 | 2109 | 35 | PV | 3009 | 2013-05-10 | 2013-05-21 | #VALUE! | 3 | #VALUE! | 2013-05-23 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | N
NSTAR | Boston | 2386 | 2210 | 75 | Natural Gas | 385-H4 | 2013-05-17 | 2013-06-10 | #VALUE! | 15 | #VALUE! | 2013-06-10 | 2013-07-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-21 |  | 2013-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-30 | Online |  | Private | Y
NSTAR | Roxbury | 2387 | 2492 | 32 | PV | 483-H6 | 2013-05-20 | 2013-05-31 | #VALUE! | 9 | #VALUE! | 2013-05-31 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | West Tisbury | 2388 | 2575 | 15 | PV | 4-97-97 | 2013-05-17 | 2013-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-09 | Online |  | Private | Y
NSTAR | Holliston | 2389 | 1746 | 1000 | PV | 65-1325H | 2013-05-20 | 2013-07-02 | #VALUE! | 30 | #VALUE! | 2013-07-02 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-06-07 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-07-09 | Online |  | Private | Y
NSTAR | Edgartown | 2390 | 2539 | 26 | PV | 4-75-75 | 2013-05-21 | 2013-05-28 | #VALUE! | 5 | #VALUE! | 2013-05-28 | 2013-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-08 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
NSTAR | Falmouth | 2391 | 2540 | 60 | PV | 4-76-437 | 2013-04-16 | 2013-05-22 | #VALUE! | 23 | #VALUE! | 2013-05-22 | 2013-06-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-13 | Online |  | Private | Y
NSTAR | Chilmark | 2392 | 2535 | 23 | PV | 4-97-226 | 2013-05-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | New Bedford | 2393 | 2746 | 1000 | PV | 2-7-34 | 2013-05-28 | 2013-06-18 | #VALUE! | 13 | #VALUE! | 2013-06-19 | 2013-10-29 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-30 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Falmouth | 2394 | 2540 | 25 | PV | 4-107-830 | 2013-05-31 | 2013-06-26 | #VALUE! | 18 | #VALUE! | 2013-07-01 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-26 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online |  | Private | Y
NSTAR | Bedford | 2395 | 1730 | 500 | PV | 391-H10 | 2013-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Norfolk | 2396 | 2056 | 1000 | PV | 146-H3 | 2013-06-05 | 2013-06-10 | #VALUE! | 3 | #VALUE! | 2013-10-01 | 2013-10-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Medway | 2397 | 2053 | 103 | PV | 65-H3 | 2013-06-05 | 2013-06-07 | #VALUE! | 2 | #VALUE! | 2013-10-10 | 2013-10-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-06 | Online |  | Private | Y
NSTAR | Medway | 2398 | 2053 | 50 | PV | 65-H2 | 2013-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2013-06-10 | Private | Y
NSTAR | Acusnet | 2399 | 2743 | 750 | PV | 2-231-231 | 2013-06-10 | 2013-06-20 | #VALUE! | 7 | #VALUE! | 2013-06-26 | 2013-07-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-25 |  | 2013-07-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Walpole | 2400 | 2081 | 49 | PV | 146-H3 | 2013-06-12 | 2013-07-30 | #VALUE! | 33 | #VALUE! | 2013-07-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-05-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plympton | 2401 | 2364 | 4000 | PV | 3-15-901 | 2013-06-12 | 2013-08-20 | #VALUE! | 48 | #VALUE! | 2013-08-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-11 | 2013-11-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-05-09 |  | 2013-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Norfolk | 2402 | 2056 | 1000 | PV | 146-H3 | 2013-06-07 | 2013-07-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Response and/or Cost Estimates from Eng | 2013-08-26 | Gov't | Y
NSTAR | Acusnet | 2403 | 2743 | 500 | PV | 2-240-240 | 2013-06-17 | 2013-06-20 | #VALUE! | 2 | #VALUE! | 2013-06-24 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2017-01-06 | Online |  | Private | Y
NSTAR | Framingham | 2404 | 1702 | 18 | PV | 433-H12 | 2013-06-17 | 2013-06-19 | #VALUE! | 1 | #VALUE! | 2013-06-19 | 2013-08-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-17 | Online |  | Private | Y
NSTAR | New Bedford | 2405 | 2740 | 100 | PV | 2-38-38 | 2013-06-18 | 2013-06-24 | #VALUE! | 3 | #VALUE! | 2013-06-26 | 2013-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-15 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-04 | Online |  | Private | Y
NSTAR | Cambridge | 2406 | 2140 | 40 | PV | 824-25 | 2013-06-18 | 2013-06-24 | #VALUE! | 2 | #VALUE! | 2013-06-24 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-10-09 |  | 2013-12-15 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage C&P |  | Gov't | Y
NSTAR | Mattapoisett | 2407 | 2739 | 4500 | PV | 2-302-302 | 2013-06-19 | 2013-07-01 | #VALUE! | 7 | #VALUE! | 2013-07-03 | 2013-08-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-24 |  | 2013-08-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
NSTAR | Framingham | 2408 | 1701 | 46 | PV | 455-H5 | 2013-06-20 | 2013-08-20 | #VALUE! | 41 | #VALUE! | 2013-08-20 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-03 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online |  | Private | Y
NSTAR | Boston | 2409 | 2121 | 60 | PV | 323-02 | 2013-06-25 | 2013-06-27 | #VALUE! | 2 | #VALUE! | 2013-06-27 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-05 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | Online |  | Private | Y
NSTAR | Waltham | 2410 | 2451 | 750 | PV | 320-H3 | 2013-06-24 | 2013-07-01 | #VALUE! | 2 | #VALUE! | 2013-07-01 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online |  | Private | Y
NSTAR | Dorchester | 2411 | 2122 | 85 | PV | 511-1498H1 | 2013-06-26 | 2013-06-28 | #VALUE! | 1 | #VALUE! | 2013-07-02 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Holliston | 2412 | 1746 | 2000 | PV | 130-H1 | 2013-01-25 | 2013-02-01 | #VALUE! | 4 | #VALUE! | 2013-02-27 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Bourne | 2413 | 2532 | 1680 | Wind | 4-81A-81A | 2013-07-08 | 2013-10-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2013-11-18 | Private | Y
NSTAR | Newton | 2414 | 2458 | 57 | PV | 467-H5 | 2013-07-08 | 2013-10-29 | #VALUE! | 80 | #VALUE! | 2013-11-05 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Newton | 2415 | 2458 | 62 | PV | 467-H3 | 2013-07-08 | 2013-07-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | 2013-09-16 | Private | Y
NSTAR | Framingham | 2416 | 1702 | 1000 | PV | 455-H6 | 2013-07-09 | 2013-07-22 | #VALUE! | 7 | #VALUE! | 2013-07-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-05-21 |  | 2013-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Sudbury | 2417 | 1776 | 980 | PV | 416-H4 | 2013-07-03 | 2013-08-20 | #VALUE! | 28 | #VALUE! | 2013-08-20 |  | #VALUE! | 0 | #VALUE! | 2013-09-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-05-19 | Online |  | Private | Y
NSTAR | Boston | 2418 | 2119 | 36 | PV | 385-H1 | 2013-07-03 | 2013-08-20 | #VALUE! | 28 | #VALUE! | 2013-08-20 |  | #VALUE! | 0 | #VALUE! | 2013-09-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-24 | Online |  | Private | Y
NSTAR | Boston | 2419 | 2119 | 50 | PV | 385-H19 | 2013-07-09 | 2013-07-12 | #VALUE! | 1 | #VALUE! | 2013-07-12 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-15 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-09 | Online |  | Private | Y
NSTAR | Falmouth | 2420 | 2540 | 40 | PV | 4-76-76 | 2013-07-09 | 2013-10-02 | #VALUE! | 58 | #VALUE! | 2013-10-08 | 2013-12-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-10 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-03 | Online |  | Private | Y
NSTAR | New Bedford | 2421 | 2740 | 75 | Natural Gas | 2-67-14 | 2013-07-11 | 2013-07-23 | #VALUE! | 6 | #VALUE! | 2013-07-24 | 2013-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-11-18 | Online |  | Private | Y
NSTAR | Chilmark | 2422 | 2535 | 17 | PV | 4-97-126 | 2013-07-15 | 2013-08-12 | #VALUE! | 18 | #VALUE! | 2013-08-12 | 2013-09-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online |  | Gov't | Y
NSTAR | Hyannis | 2423 | 2601 | 750 | PV | 4-84B-510 | 2013-07-22 | 2013-07-25 | #VALUE! | 2 | #VALUE! | 2013-07-26 |  | #VALUE! | 0 | #VALUE! | 2013-09-11 | 2013-10-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-10 |  | 2013-10-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online |  | Gov't | Y
NSTAR | Needham | 2424 | 2494 | 30 | PV | 148-H7 | 2013-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Norfolk | 2425 | 2056 | 266 | PV | 146-H3 | 2013-07-29 | 2013-08-02 | #VALUE! | 3 | #VALUE! | 2013-08-05 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-13 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Chilmark | 2426 | 2535 | 17 | PV | 4-97-226 | 2013-08-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage |  | Gov't | Y
NSTAR | Carver | 2427 | 2330 | 5000 | PV | 3-10-930 | 2013-08-13 | 2013-08-22 | #VALUE! | 6 | #VALUE! | 2013-08-22 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-03 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-09-03 | Private | Y
NSTAR | Somerville | 2428 | 2143 | 85 | PV | 250-1N35H2 | 2013-08-13 | 2013-08-26 | #VALUE! | 7 | #VALUE! | 2013-08-26 |  | #VALUE! | 0 | #VALUE! | 2013-09-24 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Wayland | 2429 | 1778 | 325 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | #VALUE! | 7 | #VALUE! | 2013-08-26 |  | #VALUE! | 0 | #VALUE! | 2013-09-24 | 2013-10-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-12-02 | Gov't | Y
NSTAR | Natick | 2430 | 1778 | 225 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Construction Stage |  | Gov't | Y
NSTAR | Framingham | 2431 | 1701 | 250 | PV | 433-H4 | 2013-08-13 | 2013-08-30 | #VALUE! | 11 | #VALUE! | 2013-08-30 |  | #VALUE! | 0 | #VALUE! | 2013-11-07 | 2013-11-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
NSTAR | Framingham | 2432 | 1702 | 1364 | PV | 278-H2 | 2013-08-21 | 2013-08-30 | #VALUE! | 6 | #VALUE! | 2013-08-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-15 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Plymouth | 2433 | 2360 | 75 | PV | 3-13-943 | 2013-08-22 | 2013-08-27 | #VALUE! | 0 | #VALUE! | 2013-08-27 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-23 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online |  | Private | Y
NSTAR | Walpole | 2434 | 2081 | 24 | PV | 456-H1 | 2013-09-03 | 2013-09-11 | #VALUE! | 5 | #VALUE! | 2013-09-11 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-28 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online |  | Private | Y
NSTAR | Burlington | 2435 | 1803 | 232 | PV | 391-H5 | 2013-09-03 | 2013-11-22 | #VALUE! | 57 | #VALUE! | 2013-11-22 |  | #VALUE! | 60 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-12 | 2014-12-04 | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-04 | Online |  | Private | Y
NSTAR | Natick | 2436 | 1760 | 550 | PV | 433-H10 | 2013-09-10 | 2013-09-13 | #VALUE! | 3 | #VALUE! | 2013-09-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-06 | Online |  | Private | Y
NSTAR | Lexington | 2437 | 2420 | 32 | PV | 391-H11 | 2013-09-10 | 2013-09-11 | #VALUE! | 0 | #VALUE! | 2013-09-11 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-16 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-18 | Online |  | Private | Y
NSTAR | Sharon | 2438 | 2067 | 185 | PV | 146-H1 | 2013-09-12 | 2013-10-30 | #VALUE! | 33 | #VALUE! | 2013-10-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-02 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online |  | Private | Y
NSTAR | Framingham | 2439 | 1702 | 40 | PV | 433-H8 | 2013-09-16 | 2013-10-02 | #VALUE! | 12 | #VALUE! | 2013-10-02 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-10-21 | Awaiting Completion Docs | 2013-12-09 | Private | Y
NSTAR | Cotuit | 2440 | 2635 | 30 | PV | 4-71-455 | 2013-09-18 | 2013-09-20 | #VALUE! | 2 | #VALUE! | 2013-09-20 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-13 | Online |  | Private | Y
NSTAR | Waltham | 2441 | 2451 | 60 | PV | 282-H1 | 2013-09-16 | 2013-09-20 | #VALUE! | 1 | #VALUE! | 2013-09-20 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Private | Y
NSTAR | Lexington | 2442 | 2421 | 46 | PV | 3402 | 2013-09-19 | 2013-10-24 | #VALUE! | 24 | #VALUE! | 2013-10-24 |  | #VALUE! | 31 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-07 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2014-04-08 | 2014-04-08 | 2014-04-08 | Online |  | Private | Y
NSTAR | Framingham | 2443 | 1701 | 75 | Natural Gas | 342-H4 | 2013-09-20 | 2013-09-30 | #VALUE! | 4 | #VALUE! | 2013-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-29 | Online |  | Private | Y
NSTAR | Brookline | 2444 | 2446 | 46 | PV | 329-H7 | 2013-09-23 | 2013-10-01 | #VALUE! | 5 | #VALUE! | 2013-10-04 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online |  | Private | Y
NSTAR | Sherborn | 2445 | 1770 | 19 | PV | 130-H2 | 2013-09-23 | 2013-09-30 | #VALUE! | 2 | #VALUE! | 2013-10-04 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online |  | Private | Y
NSTAR | North Dartmouth | 2446 | 2747 | 383 | PV | 2-531-530 | 2013-09-23 | 2013-09-27 | #VALUE! | 1 | #VALUE! | 2013-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-10-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online |  | Private | Y
NSTAR | Assonett | 2447 | 2702 | 10 | PV | 2-605-605 | 2013-10-02 | 2013-10-07 | #VALUE! | 0 | #VALUE! | 2013-10-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-19 | Online |  | Private | Y
NSTAR | Plympton | 2448 | 2367 | 24 | PV | 3-51-901 | 2013-10-04 | 2013-10-10 | #VALUE! | 2 | #VALUE! | 2013-10-11 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-01 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Westwood | 2449 | 2090 | 20 | PV | 456-H1 | 2013-10-09 | 2013-10-15 | #VALUE! | 2 | #VALUE! | 2013-10-17 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online |  | Private | Y
NSTAR | Woburn | 2450 | 1801 | 50 | PV | 211-H2 | 2013-10-09 | 2013-10-16 | #VALUE! | 3 | #VALUE! | 2013-10-18 |  | #VALUE! | 0 | #VALUE! | 2013-12-02 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-13 |  | 2013-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-04 | Online |  | Private | Y
NSTAR | Cambridge | 2451 | 2138 | 70 | PV | 827-31 | 2013-10-15 | 2013-10-23 | #VALUE! | 5 | #VALUE! | 2013-10-23 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  | 2013-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-11 | Online |  | Private | Y
NSTAR | Dover | 2452 | 2030 | 20 | PV | 456-H3 | 2013-10-15 | 2013-10-21 | #VALUE! | 3 | #VALUE! | 2013-10-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
NSTAR | Westport | 2453 | 2790 | 100 | PV | 2-532-532 | 2013-10-16 | 2013-10-18 | #VALUE! | 0 | #VALUE! | 2013-10-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-14 | Online |  | Private | Y
NSTAR | North Dartmouth | 2454 | 2747 | 25 | PV | 2-531-531 | 2013-10-18 | 2013-11-01 | #VALUE! | 10 | #VALUE! | 2013-11-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-31 | Online |  | Private | Y
NSTAR | East Falmouth | 2455 | 2536 | 85 | PV | 4-77A-450 | 2013-10-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2013-10-18 | Private | Y
NSTAR | East Falmouth | 2456 | 2536 | 90 | PV | 4-98A-98A | 2013-10-18 | 2013-10-24 | #VALUE! | 3 | #VALUE! | 2013-12-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
NSTAR | Kingston | 2457 | 2364 | 19 | PV | 3-17-910 | 2013-10-18 | 2013-10-28 | #VALUE! | 5 | #VALUE! | 2013-10-28 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
NSTAR | Hopkinton | 2458 | 1748 | 85 | PV | 126-H1 | 2013-10-18 | 2013-10-28 | #VALUE! | 5 | #VALUE! | 2013-10-28 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online |  | Private | Y
NSTAR | Hopkinton | 2459 | 1748 | 18 | PV | 126-H1 | 2013-10-21 | 2013-11-01 | #VALUE! | 9 | #VALUE! | 2013-11-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | 2013-12-04 | Private | Y
NSTAR | Canton | 2460 | 2021 | 60 | PV | 269-1320H1 | 2013-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2013-10-24 | Private | Y
NSTAR | Sudbury | 2461 | 1778 | 225 | PV | 342-H3 | 2013-10-28 | 2013-11-13 | #VALUE! | 12 | #VALUE! | 2013-11-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-05-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2014-06-09 |  | 2014-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dedham | 2462 | 2026 | 1750 | PV | 20-H2, 20-H3 | 2013-10-25 | 2014-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Mattapoisett | 2463 | 2739 | 4000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage |  | Private | Y
NSTAR | Mattapoisett | 2464 | 2739 | 1000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage |  | Private | Y
NSTAR | Mattapoisett | 2465 | 2739 | 1000 | PV | 2-302-302 | 2013-10-30 | 2013-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private | Y
NSTAR | Dorchester | 2466 | 2121 | 27 | PV | 483-H3 | 2013-10-29 | 2013-11-18 | #VALUE! | 12 | #VALUE! | 2013-11-19 |  | #VALUE! | 0 | #VALUE! | 2013-12-05 | 2014-01-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-28 |  | 2013-12-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-25 | Online |  | Private | Y
NSTAR | Charlestown | 2467 | 2129 | 11 | PV | 10-H2 | 2013-11-08 | 2013-11-14 | #VALUE! | 1 | #VALUE! | 2013-11-15 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-19 |  | 2013-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-14 | Online |  | Private | Y
NSTAR | Chilmark | 2468 | 2535 | 42 | PV | 4-91-220 | 2014-11-18 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2016-03-11 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 1972361 | 2571 | 5000 | PV | 3-83-83 | 2013-11-25 | 2013-12-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2015-12-29 | 2016-04-19 | Online |  | Gov't
NSTAR | Carver | 1972386 | 2330 | 5000 | PV | 3-83-83 | 2013-12-02 | 2013-12-03 | #VALUE! | 0 | #VALUE! | 2013-12-05 | 2013-12-27 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2014-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wayland | 1973375 | 1778 | 200 | PV | 342-H3 | 2013-12-10 | 2013-12-10 | 0 | 0 | 0 | 2013-12-11 | 2013-12-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-27 | 2013-12-31 | 2014-07-18 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2013-12-27 |  | Withdrawn |  | Private
NSTAR | East Boston | 1976430 | 2128 | 100 | PV | 488-H4 | 2013-12-11 | 2013-12-12 | #VALUE! | 0 | #VALUE! | 2013-12-17 | 2015-03-10 | #VALUE! | 3 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-21 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Woburn | 1976701 | 1801 | 1000 | PV | 375-H14 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-10-15 | #VALUE! | 297 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-03 | 2015-05-20 | 2015-09-27 | No | EXP | 30 | 2014-10-14 | 2014-10-14 | 0 |  | 0 |  | 2015-10-20 |  | Withdrawn |  | Gov't
NSTAR | Plymouth | 1977739 | 2360 | 600 | PV | 3-13-943 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-01-15 | #VALUE! | 7 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | 2014-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-01-02 | 2015-10-21 | Online |  | GOV'T
NSTAR | Burlington | 1977755 | 1803 | 500 | PV | 391-H12 | 2013-12-19 | 2013-12-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Provincetown | 1978458 | 2657 | 20 | PV | 4-96-676 | 2013-12-23 | 2013-12-24 | #VALUE! | 0 | #VALUE! | 2013-12-31 | 2016-06-08 | #VALUE! | 604 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-31 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Mattapoisett | 1978822 | 2739 | 750 | PV | 2-301-301 | 2014-01-02 | 2014-01-02 | 0 | 106 | 0 | 2014-01-03 | 2015-01-07 | #VALUE! | 139 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Waltham | 1980806 | 2451 | 1000 | PV | 526-1361H | 2014-01-03 | 2014-01-03 | 0 | 0 | 0 | 2014-02-04 | 2014-02-04 | 0 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-31 | 2014-06-05 | 2014-09-30 | No | EXP | 30 | 2014-09-04 | 2014-09-04 | 0 |  | 0 |  | 2014-09-25 |  | Withdrawn |  | Gov't
NSTAR | Chilmark | 1981127 | 2535 | 95 | PV | 4-97-126 | 2014-01-08 | 2014-01-08 | 0 | 0 | 0 | 2014-01-14 | 2014-02-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-10 |  | 2014-08-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online |  | Private
NSTAR | Hatchville | 1982667 | 2536 | 48 | PV | 4-98B-448 | 2014-01-09 | 2014-01-09 | 0 | 0 | 0 | 2014-01-15 | 2014-02-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-16 |  | 2014-09-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-05-16 | 2014-05-16 | Online |  | Private
NSTAR | Brighton | 1982906 | 2135 | 75 | Natural Gas | 467-H13 | 2014-01-16 | 2014-01-16 | 0 | 0 | 0 | 2014-01-24 | 2014-02-07 | #VALUE! | 0 | #VALUE! | 2014-02-20 | 2014-03-24 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-27 | 2014-04-17 | 2014-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Marshfield | 1984064 | 2050 | 18.5 | PV | 3-25-976 | 2014-01-20 | 2014-01-21 | #VALUE! | 0 | #VALUE! | 2014-01-20 | 2014-01-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wayland | 1984570 | 1778 | 225 | PV | 342-H3 | 2014-01-21 | 2014-04-30 | #VALUE! | 0 | #VALUE! | 2014-01-24 | 2014-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 | 2014-05-13 | 2014-08-26 | TBD | EXP | 30 | 2014-05-16 | 2014-05-16 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acusnet | 1984711 | 2743 | 40 | PV | 2-241-241 | 2014-01-27 | 2014-05-06 | #VALUE! | 0 | #VALUE! | 2014-06-25 | 2014-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2014-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-26 | Online |  | Private
NSTAR | Falmouth | 1985442 | 2536 | 90 | PV | 4-98A-98A | 2014-01-28 | 2014-01-30 | #VALUE! | 0 | #VALUE! | 2014-01-30 | 2014-02-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-09-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Framingham | 1985681 | 1702 | 27.6 | PV | 240-H4 | 2014-01-30 | 2014-01-30 | 0 | 0 | 0 | 2014-02-05 | 2014-02-26 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-20 | 2014-08-25 | 2014-09-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-08-22 | 2014-08-22 | Online |  | Private
NSTAR | Dartmouth | 1986041 | 2748 | 21 | PV | 2-524-524 | 2014-02-10 | 2014-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-08-19 | Online |  | Private
NSTAR | Harwich | 1987679 | 2671 | 23 | PV | 4-92B-572 | 2014-02-10 | 2014-02-11 | #VALUE! | 0 | #VALUE! | 2014-02-11 | 2014-02-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-13 | 2014-04-15 | 2014-09-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-29 | Online |  | Private | Y
NSTAR | Bellingham | 1987709 | 2019 | 52.5 | PV | 65-H4 | 2014-02-12 | 2014-02-14 | #VALUE! | 0 | #VALUE! | 2014-02-14 | 2014-03-06 | #VALUE! | 28 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-29 |  | 2014-09-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-07-18 | Online |  | Private
NSTAR | Plymouth | 1988060 | 2360 | 38 | PV | 3-12-41J1 | 2014-02-18 | 2014-07-10 | #VALUE! | 0 | #VALUE! | 2014-02-19 | 2014-04-07 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-04 | 2016-01-05 | 2016-10-07 | Yes | EXP | 30 | 2016-07-22 |  | #VALUE! |  | #VALUE! |  |  |  | Awaiting Completion Docs |  | Private | N
NSTAR | Plympton | 1988677 | 2367 | 840 | PV | 3-15-906 | 2014-01-30 | 2014-02-20 | #VALUE! | 0 | #VALUE! | 2014-03-07 | 2014-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-09-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-12-19 | Online |  | Private
NSTAR | Ashland | 1988954 | 1721 | 80 | PV | 274-1429H1 | 2014-02-05 | 2014-02-24 | #VALUE! | 0 | #VALUE! | 2014-02-28 | 2014-02-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-11 |  | 2014-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-09-11 | Online |  | Private | N
NSTAR | Lexington | 1989453 | 2421 | 25.9 | PV | 533-H1 | 2014-02-11 | 2014-02-26 | #VALUE! | 0 | #VALUE! | 2014-03-14 | 2014-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-04-11 | 2014-08-07 | #VALUE! | 7 | #VALUE! | 2015-05-04 | 2015-05-07 | #VALUE! | 0 | #VALUE! | 2014-08-04 | 2015-05-11 | 2015-11-30 | No | STD | 60 | 2015-09-30 | 2015-09-30 | 0 |  | 0 |  | 2016-03-01 | 2016-03-01 | Online |  | Private | N
NSTAR | Needham | 1989732 | 2492 | 3120 | PV | 148-H1 | 2014-02-14 | 2014-02-28 | #VALUE! | 0 | #VALUE! | 2014-03-04 | 2014-03-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-10-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-23 | Online |  | Gov't | Y
NSTAR | Wayland | 1989963 | 1778 | 20 | PV | 342-H1 | 2014-02-28 | 2014-09-20 | #VALUE! | 0 | #VALUE! | 2014-03-05 | 2014-04-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-11-03 | 2015-06-05 | #VALUE! | 9 | #VALUE! | 2015-11-16 | 2015-11-25 | #VALUE! | 0 | #VALUE! | 2015-03-04 | 2016-04-20 | 2016-11-01 | No | STD | 60 | 2016-05-27 |  | #VALUE! |  | #VALUE! |  |  |  | Online |  | PRIVATE | N
NSTAR | Hyde Park | 1990011 | 2136 | 3190 | PV | 496-H2 | 2014-02-28 | 2014-03-06 | #VALUE! | 0 | #VALUE! | 2014-03-10 | 2014-04-29 | #VALUE! | 22 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 |  | 2014-10-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-28 | Online |  | Gov't | Y
NSTAR | Wareham | 1991204 | 2538 | 100 | PV | 3-84-961 | 2014-03-14 | 2014-03-14 | 0 | 0 | 0 | 2014-03-20 | 2014-03-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-28 | 2014-05-05 | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-01 | 2015-05-01 | Online |  | Private
NSTAR | Roxbury | 1992441 | 2120 | 75 | Natural Gas | 5201 | 2014-03-18 | 2014-10-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-05-20 | Private
NSTAR | Mattapoisett | 1992844 | 2739 | 2000 | PV | 2-301-301 | 2014-03-18 | 2014-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-27 | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-03-12 | Private
NSTAR | Mattapoisett | 1992854 | 2739 | 2000 | PV | 2-306-306 | 2014-03-18 | 2014-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-05-20 | Private
NSTAR | Mattapoisett | 1992858 | 2739 | 1000 | PV | 2-306-306 | 2014-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Jamaica Plain | 1994005 | 2130 | 34.2 | PV | 284-1300H1 | 2014-03-26 | 2014-04-01 | #VALUE! | 0 | #VALUE! | 2014-04-01 | 2014-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-15 | 2014-11-03 | 2014-10-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online |  | Private | N
NSTAR | Cambridge | 1994170 | 2142 | 75 | Natural Gas | 875-1328 | 2014-01-22 | 2014-03-27 | #VALUE! | 0 | #VALUE! | 2014-03-31 | 2014-04-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-15 | 2014-09-03 | 2014-10-31 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online |  | Private
NSTAR | Waltham | 1994357 | 2453 | 75 | Natural Gas | 33-H1 | 2014-04-20 | 2014-04-22 | #VALUE! | 0 | #VALUE! | 2014-05-12 | 2014-05-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-29 |  | 2014-11-28 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-18 |  | Withdrawn |  | Gov't
NSTAR | Natick | 1998808 | 1760 | 150 | Natural Gas | 23-1339H1 | 2014-04-29 | 2014-04-30 | #VALUE! | 0 | #VALUE! | 2014-05-13 | 2014-08-20 | #VALUE! | 64 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-19 | 2016-03-11 | 2014-12-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2000080 | 2458 | 100 | PV | 467-H3 | 2014-03-20 | 2014-03-27 | #VALUE! | 0 | #VALUE! | 2014-05-06 | 2014-05-08 | #VALUE! | 0 | #VALUE! | 2014-05-13 | 2014-05-28 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2017-10-31 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Walpole | 2000815 | 2071 | 3450 | PV | 146-H3 | 2014-03-13 | 2014-03-13 | 0 |  | 0 | 2014-03-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-01 | 2015-09-01 | [6 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online
NSTAR | Natick | 2001305 | 1760 | 580 | PV | 433-H10 | 2014-05-05 | 2014-05-06 | #VALUE! | 0 | #VALUE! | 2014-05-07 | 2014-09-23 | #VALUE! | 131 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-29 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-03 | Online |  | Private
NSTAR | Natick | 2001314 | 1760 | 620 | PV | 433-H9 | 2014-03-24 | 2014-05-05 | #VALUE! | 0 | #VALUE! | 2014-05-07 | 2014-11-26 | #VALUE! | 132 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-30 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-28 | 2016-06-03 | Online |  | Private
NSTAR | Natick | 2001342 | 1760 | 520 | PV | 433-H10 | 2014-01-30 | 2014-03-27 | #VALUE! | 0 | #VALUE! | 2014-05-14 | 2014-06-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 |  | 2014-12-17 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-24 | 2015-12-28 | Online |  | Private | Y
NSTAR | Pocasset | 2002111 | 2559 | 248.4 | PV | 4-86-86 | 2014-02-05 | 2014-04-22 | #VALUE! | 0 | #VALUE! | 2014-05-16 | 2014-05-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-20 | 2014-08-14 | 2014-12-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-10-23 | Online |  | Private
NSTAR | Marshfield | 2002502 | 2050 | 9 | PV | 3-24B-915 | 2014-02-14 | 2014-05-02 | #VALUE! | 0 | #VALUE! | 2014-05-19 | 2014-05-28 | #VALUE! | 7 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-30 |  | 2014-12-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | West Tisbury | 2002682 | 2575 | 204 | PV | 4-97-220 | 2014-05-14 | 2014-05-15 | #VALUE! | 0 | #VALUE! | 2014-06-18 | 2015-06-15 | #VALUE! | 243 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Cambridge | 2002879 | 2139 | 802 | PV | 817-05 | 2014-05-15 | 2014-05-16 | #VALUE! | 0 | #VALUE! | 2014-05-19 | 2014-06-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-07-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2003173 | 2745 | 810 | Natural Gas | 2-107-107 | 2014-03-10 | 2014-05-12 | #VALUE! | 0 | #VALUE! | 2014-06-06 | 2014-06-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-19 | 2014-08-11 | 2015-01-05 | TBD | EXP | 30 | 2014-10-01 | 2014-10-01 | 0 |  | 0 |  |  | 2014-10-10 | Online |  | Private
NSTAR | Chatham | 2004834 | 2659 | 44 | PV | 4-95A-95A | 2014-03-20 | 2014-05-13 | #VALUE! | 0 | #VALUE! | 2014-06-03 | 2014-06-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-10 | 2014-11-19 | 2015-06-30 | TBD | EXP | 30 | 2015-07-17 | 2015-07-17 | 0 |  | 0 |  |  | 2015-07-28 | Online |  | Private
NSTAR | Edgartown | 2005414 | 2539 | 80 | PV | 4-75-123 | 2014-05-30 | 2015-05-07 | #VALUE! | 0 | #VALUE! | 2014-06-05 | 2014-12-29 | #VALUE! | 148 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2015-01-08 | No | STD | 60 |  |  | 0 |  | 0 |  | 2016-06-23 | 2016-06-30 | Online |  | Private | N
NSTAR | Jamaica Plain | 2005440 | 2130 | 1640 | Natural Gas | 496-H4 | 2014-05-30 | 2015-05-16 | #VALUE! | 0 | #VALUE! | 2014-06-05 | 2015-01-19 | #VALUE! | 148 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-01-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-30 | Online
NSTAR | New Bedford | 2005461 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-05-14 | 2014-06-03 | #VALUE! | 0 | #VALUE! | 2014-06-06 | 2014-06-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 | 2014-09-12 | 2015-01-12 | TBD | EXP | 30 | 2014-10-09 | 2014-10-09 | 0 |  | 0 |  | 2014-11-05 | 2014-11-18 | Withdrawn |  | Private
NSTAR | Framingham | 2006363 | 1702 | 120 | PV | 274-H4 | 2014-05-16 | 2014-06-03 | #VALUE! | 0 | #VALUE! | 2014-06-06 | 2014-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 |  | 2015-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-11-21 | Online |  | Private
NSTAR | Boston | 2006387 | 2109 | 45 | PV | 3009 | 2014-05-19 | 2014-06-05 | #VALUE! | 0 | #VALUE! | 2014-06-12 | 2014-10-23 | #VALUE! | 45 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-01-14 | No | EXP | 30 | 2015-01-12 | 2015-01-12 | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | East Boston | 2006940 | 2128 | 750 | PV | 108-196H1 | 2014-06-06 | 2014-06-09 | #VALUE! | 0 | #VALUE! | 2014-06-11 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 |  | 2015-01-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Dover | 2007317 | 2030 | 20.2 | PV | 456-H5 | 2014-06-03 | 2014-06-09 | #VALUE! | 0 | #VALUE! | 2014-06-11 | 2014-06-23 | #VALUE! | 4 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-25 | 2014-10-01 | 2015-01-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online |  | Private
NSTAR | Chatham | 2007346 | 2659 | 50 | PV | 4-95A-95A | 2014-06-06 | 2014-06-11 | #VALUE! | 0 | #VALUE! | 2014-06-13 | 2014-06-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-18 | 2014-10-01 | 2015-01-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online |  | Private
NSTAR | Edgartown | 2007907 | 2539 | 18.7 | PV | 4-75-123 | 2014-06-06 | 2014-06-11 | #VALUE! | 0 | #VALUE! | 2014-06-13 | 2014-10-07 | #VALUE! | 46 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | #VALUE! | 0 | #VALUE! | 2015-08-31 | 2015-10-13 | #VALUE! | 0 | #VALUE! | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online |  | Private | N
NSTAR | Canton | 2007950 | 2021 | 980 | PV | 470-H7 | 2014-06-11 | 2014-06-11 | 0 | 0 | 0 | 2014-06-13 | 2014-10-07 | #VALUE! | 46 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | #VALUE! | 0 | #VALUE! | 2015-08-31 | 2015-10-13 | #VALUE! | 0 | #VALUE! | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online |  | Private | N
NSTAR | Holliston | 2008170 | 1746 | 17 | PV | 274-H5 | 2014-06-11 | 2014-06-12 | #VALUE! | 0 | #VALUE! | 2014-06-16 | 2014-07-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 | 2014-09-22 | 2014-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Stoneham | 2008179 | 2180 | 15.9 | PV | 375-H8 | 2014-06-11 | 2014-06-17 | #VALUE! | 0 | #VALUE! | 2014-06-20 | 2014-09-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-11 | 2014-09-11 | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-11 | Online |  | Private | N
NSTAR | Plymouth | 2009028 | 2360 | 20 | PV | 3-89-926 | 2014-06-13 | 2014-06-17 | #VALUE! | 0 | #VALUE! | 2014-06-20 | 2014-08-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-09 | 2014-11-17 | Online |  | Private
NSTAR | Wareham | 2009038 | 2576 | 18 | PV | 3-85-85 | 2014-06-13 | 2014-06-18 | #VALUE! | 0 | #VALUE! | 2014-06-27 | 2014-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 | 2014-09-03 | 2015-01-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-02-04 | 2016-02-04 | Online |  | Private
NSTAR | Boston | 2009215 | 2118 | 75 | Natural Gas | 385-H17 | 2014-06-16 | 2014-06-20 | #VALUE! | 0 | #VALUE! | 2014-06-26 | 2014-07-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online |  | Gov't
NSTAR | Lexington | 2009595 | 2421 | 388 | PV | 320-H5XY | 2014-06-16 | 2014-06-20 | #VALUE! | 0 | #VALUE! | 2014-06-26 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online |  | Gov't | N
NSTAR | Lexington | 2009605 | 2420 | 135 | PV | 391-H11 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-26 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online |  | Gov't
NSTAR | Lexington | 2009611 | 2420 | 135 | PV | 533-H3 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-27 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-02 | 2014-12-10 | Online |  | Private
NSTAR | Lexington | 2009615 | 2421 | 79 | PV | 320-H5XY | 2014-06-20 | 2014-06-27 | #VALUE! | 0 | #VALUE! | 2014-06-26 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-16 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online |  | Private
NSTAR | Lexington | 2009625 | 2421 | 171 | PV | 320-H5XY | 2014-06-20 | 2014-06-26 | #VALUE! | 0 | #VALUE! | 2014-06-26 | 2014-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-23 | Online |  | Private
NSTAR | Lexington | 2009631 | 2420 | 40 | PV | 3403 | 2014-06-23 | 2014-06-26 | #VALUE! | 0 | #VALUE! | 2014-06-27 | 2014-07-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-03 | 2014-10-01 | 2015-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-19 | Online |  | Private
NSTAR | Chatham | 2009828 | 2659 | 60 | PV | 4-95A-95A | 2014-06-23 | 2014-06-26 | #VALUE! | 0 | #VALUE! | 2014-06-27 | 2014-07-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-24 |  | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-31 | 2015-04-08 | Online |  | Private
NSTAR | Waltham | 2009878 | 2451 | 675 | PV | 531-1359H | 2014-06-24 | 2014-06-24 | 0 | 0 | 0 | 2014-07-01 | 2014-07-29 | #VALUE! | 308 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | East Boston | 2010040 | 2128 | 552 | PV | 108-196H1 | 2014-06-26 | 2014-07-01 | #VALUE! | 0 | #VALUE! | 2014-07-03 | 2014-07-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-08 | 2014-10-06 | 2015-02-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2011256 | 2576 | 42 | PV | 3-86-966 | 2014-06-26 | 2014-07-03 | #VALUE! | 0 | #VALUE! | 2014-08-04 | 2014-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 | 2015-02-05 | 2015-10-01 | TBD | EXP | 30 | 2015-01-30 |  | #VALUE! |  | #VALUE! |  | 2015-09-23 |  | Withdrawn |  | Gov't
NSTAR | Framingham | 2012062 | 1701 | 500 | PV | 278-H2 | 2014-07-09 | 2014-07-10 | #VALUE! | 0 | #VALUE! | 2014-07-11 | 2014-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-06 | 2015-03-02 | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-02 | 2015-09-21 | Online |  | Gov't
NSTAR | Falmouth | 2012720 | 2540 | 47.8 | PV | 4-107-830 | 2014-07-09 | 2014-07-10 | #VALUE! | 0 | #VALUE! | 2014-07-11 | 2014-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-16 |  | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hyannis | 2012789 | 2601 | 252 | PV | 4-84B-524 | 2014-07-03 | 2014-07-10 | #VALUE! | 0 | #VALUE! | 2014-07-16 | 2014-08-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 | 2014-09-03 | 2015-02-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 |  | Withdrawn |  | Private
NSTAR | Allston | 2012919 | 2134 | 90 | PV | 548-92H3 | 2014-07-15 | 2014-07-22 | #VALUE! | 0 | #VALUE! | 2014-08-04 | 2014-07-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 | 2014-10-27 | 2015-02-23 | No | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2014-12-19 | 2015-01-02 | Online |  | Private | N
NSTAR | Acton | 2013623 | 1720 | 126 | PV | 416-H9 | 2014-07-18 | 2014-07-22 | #VALUE! | 0 | #VALUE! | 2014-07-28 | 2014-07-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-10 | Online |  | Private
NSTAR | Acton | 2014462 | 1720 | 81 | PV | 416-H1 | 2014-07-23 | 2014-07-28 | #VALUE! | 0 | #VALUE! | 2014-08-19 | 2014-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 |  | 2015-10-01 | TBD | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2015-09-17 | 2015-09-17 | Online |  | Gov't
NSTAR | Framingham | 2015313 | 1701 | 500 | PV | 433-H11 | 2014-07-22 | 2014-07-23 | #VALUE! | 0 | #VALUE! | 2014-07-25 | 2014-08-05 | #VALUE! | 73 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2015-01-27 | 2015-06-19 | No | EXP | 30 | 2015-05-27 | 2015-05-27 | 0 |  | 0 |  | 2015-06-16 | 2015-07-08 | Online |  | Private
NSTAR | Holliston | 2015374 | 1746 | 300 | PV | 65-H7 | 2014-07-24 | 2014-08-19 | #VALUE! | 0 | #VALUE! | 2014-08-04 | 2014-08-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-17 | 2014-11-03 | 2015-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-08 | Online |  | Private
NSTAR | Dorchester | 2015660 | 2122 | 89 | PV | 6702 | 2014-07-30 | 2014-08-01 | #VALUE! | 0 | #VALUE! | 2014-08-05 | 2014-08-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-09-29 | 2015-04-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 2015-03-10 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2016902 | 2770 | 2000 | PV | 3-703-703 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | 2014-08-11 | 2014-12-02 | #VALUE! | 60 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-17 | 2015-09-08 | 2016-03-15 | No | EXP | 30 | 2016-01-28 | 2016-01-28 | 0 |  | 0 |  | 2016-04-14 |  | Withdrawn |  | Private | N
NSTAR | Charlestown | 2017443 | 2129 | 391 | PV | 10-H1 | 2014-08-05 | 2014-08-11 | #VALUE! | 0 | #VALUE! | 2014-08-15 | 2014-11-21 | #VALUE! | 34 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-04-11 | 2016-04-14 | #VALUE! | 0 | #VALUE! | 2015-03-26 | 2016-07-28 | 2016-12-15 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Field Com |  | Private | N
NSTAR | Hopkinton | 2017615 | 1748 | 342 | PV | 126-H4 | 2014-08-06 | 2014-08-15 | #VALUE! | 0 | #VALUE! | 2014-09-24 |  | #VALUE! |  | #VALUE! |  |  | 0 | 0 | 0 | 2014-08-15 | 2014-10-04 | #VALUE! | 11 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-23 |  | 2015-03-17 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2017870 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-08-07 | 2014-08-15 | #VALUE! | 0 | #VALUE! | 2014-09-24 | 2014-09-24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-30 | 2014-10-06 | 2015-03-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online |  | Private | N
NSTAR | Kingston | 2018246 | 2364 | 142.5 | PV | 3-15-15 | 2014-08-11 | 2014-08-15 | #VALUE! | 0 | #VALUE! | 2014-09-24 | 2014-10-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-10 |  | 2015-03-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-08-17 | 2015-08-18 | Online |  | PRIVATE
NSTAR | East Walpole | 2018681 | 2032 | 325.6 | PV | 135-1301 | 2014-08-12 | 2014-08-15 | #VALUE! | 0 | #VALUE! | 2014-08-15 | 2014-08-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 |  | 2015-03-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-13 | Online |  | Private | N
NSTAR | South Walpole | 2018960 | 2071 | 85 | PV | 146-H3 | 2014-08-12 | 2014-08-15 | #VALUE! | 0 | #VALUE! | 2014-08-19 | 2014-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-03 |  | 2015-03-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-20 | Online |  | Private
NSTAR | Plymouth | 2018969 | 2360 | 50 | PV | 4-81A-406 | 2014-08-19 | 2014-08-19 | 0 | 0 | 0 | 2014-08-21 | 2014-09-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-16 | 2015-03-02 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2015-03-30 | Online |  | Private
NSTAR | Dover | 2019996 | 2030 | 21.2 | PV | 456-H5 | 2014-08-19 | 2014-08-20 | #VALUE! | 0 | #VALUE! | 2014-08-20 | 2014-09-26 | #VALUE! | 9 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2016-08-18 | 2015-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee |  | Gov't
NSTAR | Truro | 2020127 | 2666 | 1000 | PV | 4-96-96 | 2014-08-20 | 2014-08-25 | #VALUE! | 0 | #VALUE! | 2014-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 | 0 | 0 | 2014-10-21 | 2015-01-09 | #VALUE! | 120 | #VALUE! | 2015-07-02 | 2015-07-10 | #VALUE! | 3 | #VALUE! | 2016-03-10 | 2016-03-31 | #VALUE! | 0 | #VALUE! | 2015-07-08 | 2016-04-25 | 2016-12-02 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Kingston | 2020238 | 2364 | 668 | PV | 3-909-909 | 2014-08-21 | 2014-08-25 | #VALUE! | 0 | #VALUE! | 2014-08-25 | 2014-09-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 | 2015-07-15 | 2015-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-08 | Online |  | Private
NSTAR | Plymouth | 2020496 | 2360 | 92.8 | PV | 3-14-911 | 2014-08-25 | 2014-08-28 | #VALUE! | 0 | #VALUE! | 2014-08-28 | 2014-11-10 | #VALUE! | 16 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-17 |  | 2015-04-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2015-01-02 | Online |  | Private
NSTAR | Dartmouth | 2020964 | 2747 | 232 | PV | 2-532-532 | 2014-08-26 | 2014-08-28 | #VALUE! | 0 | #VALUE! | 2014-08-28 | 2014-09-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-25 | 2014-10-31 | 2014-12-15 | TBD | EXP | 30 | 2014-12-12 | 2014-12-12 | 0 |  | 0 |  |  | 2014-12-17 | Online |  | Private
NSTAR | Holliston | 2021069 | 1746 | 185 | PV | 65-H2 | 2014-08-26 | 2014-08-28 | #VALUE! | 0 | #VALUE! | 2014-08-28 | 2014-10-15 | #VALUE! | 22 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 | 2014-12-05 | 2014-12-31 | No | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  | 2015-02-18 | 2015-02-27 | Online |  | Private
NSTAR | Holliston | 2021094 | 1746 | 500 | PV | 65-H2 | 2014-08-27 | 2014-08-28 | #VALUE! | 0 | #VALUE! | 2014-09-04 | 2014-10-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 |  | 2017-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online |  | Private
NSTAR | Plymouth | 2021322 | 2360 | 500 | PV | 3-12-12 | 2014-09-02 | 2014-09-03 | #VALUE! | 0 | #VALUE! | 2014-09-04 | 2015-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-05 |  | 2015-04-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wianno | 2022522 | 2655 | 32.8 | PV | 4-80A-892 | 2014-09-04 | 2014-09-04 | 0 | 0 | 0 | 2015-02-13 | 2015-04-01 | #VALUE! | 107 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-04-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-06 |  | Withdrawn |  | Private
NSTAR | Canton | 2022843 | 2021 | 300 | PV | 470-H7 | 2014-09-03 | 2014-09-04 | #VALUE! | 0 | #VALUE! | 2014-09-09 | 2014-09-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 | 2014-10-02 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-06 | Online |  | Private
NSTAR | Canton | 2022875 | 2021 | 170 | PV | 470-H8 | 2014-09-02 | 2014-09-03 | #VALUE! | 0 | #VALUE! | 2014-09-09 | 2014-09-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-26 | 2014-09-29 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-19 | Online |  | Private
NSTAR | Dennis | 2022973 | 2660 | 75 | PV | 4-92B-92B | 2014-09-03 | 2014-09-04 | #VALUE! | 0 | #VALUE! | 2014-09-09 | 2014-09-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-29 | 2014-10-06 | 2015-04-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online |  | Private
NSTAR | Kingston | 2023232 | 2364 | 21.5 | PV | 3-15-15 | 2014-09-18 |  | #VALUE! | 0 | #VALUE! | 2014-09-10 | 2014-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 |  | 2015-04-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-23 | 2014-12-31 | Online |  | Private
NSTAR | Wareham | 2023726 | 2571 | 324.8 | PV | 3-86-966 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | 2014-09-18 | 2014-10-10 | #VALUE! | 8 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-08 |  | 2015-04-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2014-12-23 | Online |  | Private
NSTAR | Dartmouth | 2024047 | 2747 | 301.6 | PV | 2-531-531 | 2014-09-11 | 2014-09-12 | #VALUE! | 0 | #VALUE! | 2014-09-19 | 2015-01-16 | #VALUE! | 53 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-04-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2024196 | 2571 | 2000 | PV | 3-84-84 | 2014-08-13 | 2014-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hatchville | 2024739 | 2536 | 3000 | PV | 4-98A-98A | 2014-09-16 |  | #VALUE! | 0 | #VALUE! | 2014-09-18 | 2014-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2015-04-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-21 | 2017-04-06 | Online |  | Gov't
NSTAR | Natick | 2024912 | 1760 | 264 | PV | 433-H9 | 2014-08-27 | 2014-09-15 | #VALUE! | 0 | #VALUE! | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-02 | 2015-04-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-21 | Online |  | Private
NSTAR | Dorchester | 2025617 | 2122 | 56 | PV | 466-1482H1 | 2014-09-18 | 2014-09-18 | 0 | 0 | 0 | 2014-09-22 | 2014-10-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-16 | 2014-10-17 | 2015-04-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online |  | Private
NSTAR | Canton | 2025700 | 2021 | 85 | PV | 470-H11 | 2014-09-19 | 2014-09-20 | #VALUE! | 0 | #VALUE! | 2014-09-22 | 2014-10-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-20 |  | 2015-04-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Bourne | 2025848 | 2532 | 499 | PV | 3-89-925 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | 2014-09-30 | 2014-11-10 | #VALUE! | 9 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-30 |  | Withdrawn |  | Private
NSTAR | Burlington | 2026226 | 1803 | 500 | PV | 391-H9 | 2014-09-25 | 2014-09-25 | 0 | 0 | 0 | 2014-09-29 | 2015-07-21 | #VALUE! | 195 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2015-11-18 | 2016-06-16 | No | EXP | 30 | 2016-05-16 | 2016-05-16 | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Norfolk | 2026963 | 2056 | 499 | PV | 146-H3 | 2014-09-25 | 2014-09-26 | #VALUE! | 0 | #VALUE! | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-05-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-28 | Online |  | Private
NSTAR | Lexington | 2027027 | 2420 | 15 | PV | 391-H3 | 2014-09-26 | 2014-09-27 | #VALUE! | 0 | #VALUE! | 2014-09-30 | 2014-10-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Somerville | 2027112 | 2145 | 50 | PV | 14N26 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | 2014-10-01 | 2014-11-21 | #VALUE! | 19 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-08 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-21 | 2014-12-24 | Online |  | Private
NSTAR | Woburn | 2027532 | 1801 | 278.4 | PV | 375-H9 | 2014-09-30 | 2014-10-02 | #VALUE! | 0 | #VALUE! | 2014-10-03 | 2014-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-14 |  | 2015-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-22 | Online |  | Private
NSTAR | Holliston | 2027916 | 1746 | 42 | PV | 274-H3 | 2014-10-01 | 2014-12-09 | #VALUE! | 0 | #VALUE! | 2014-12-09 | 2014-12-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 |  | 2015-03-01 | TBD | EXP | 30 | 2015-03-02 | 2015-03-02 | 0 |  | 0 |  |  | 2015-07-28 | Online |  | Private
NSTAR | Norfolk | 2028128 | 2056 | 22 | PV | 146-H3 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-14 | 2014-11-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online |  | Private
NSTAR | Pocasset | 2029122 | 2559 | 55.2 | PV | 4-81A-406 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-08 | 2014-11-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-09 | 2015-01-15 | 2015-04-30 | No | EXP | 30 | 2015-03-09 | 2015-03-09 | 0 |  | 0 |  | 2015-04-27 | 2015-04-27 | Online |  | Private | N
NSTAR | Marion | 2029145 | 2738 | 783 | PV | 3-85-85 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-27 | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-27 | Online |  | Private
NSTAR | Framingham | 2029290 | 1702 | 42.5 | PV | 240-H4 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-31 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-27 | Online |  | Private
NSTAR | Plymouth | 2029298 | 2360 | 30.9 | PV | 3-89-926 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online |  | Private
NSTAR | Pocasset | 2029376 | 2559 | 34.2 | PV | 4-81A-406 | 2014-10-09 | 2014-10-09 | 0 | 0 | 0 | 2014-10-17 | 2015-05-20 | #VALUE! | 115 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-03 |  | 2015-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-02 | 2016-03-02 | Online |  | Gov't | N
NSTAR | Plymouth | 2029874 | 2360 | 225 | Natural Gas | 3-13-943 | 2014-10-09 | 2014-10-10 | #VALUE! | 0 | #VALUE! | 2014-10-27 | 2014-11-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-10 |  | 2015-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2029884 | 2571 | 60 | PV | 3-86-966 | 2014-10-21 | 2014-10-21 | 0 | 0 | 0 | 2014-10-23 | 2014-12-22 | #VALUE! | 39 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-23 | 2015-06-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-12 | 2015-04-22 | Online |  | Private
NSTAR | Dennis | 2031577 | 2641 | 16.1 | PV | 4-89A-552 | 2014-10-22 | 2014-10-23 | #VALUE! | 0 | #VALUE! | 2014-10-27 | 2014-10-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Dennisport | 2031909 | 2639 | 72 | PV | 4-92B-583 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-10-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Yarmouth | 2032033 | 2664 | 42 | PV | 4-92A-562 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-11-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 | 2015-02-18 | 2015-06-15 | TBD | EXP | 30 | 2015-05-21 | 2015-05-21 | 0 |  | 0 |  | 2015-07-08 | 2015-07-13 | Online |  | Private
NSTAR | Marion | 2032055 | 2738 | 250 | PV | 3-304-304 | 2014-10-27 | 2014-11-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Bellingham | 2032500 | 2019 | 480 | PV | 65-H4 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-05 | 2014-11-21 | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online |  | Private
NSTAR | Hopkinton | 2033025 | 1748 | 15.2 | PV | 65-H6 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-01-12 | Online |  | Private
NSTAR | Westport | 2033167 | 2790 | 30 | PV | 2-532-532 | 2014-10-30 | 2014-12-18 | #VALUE! | 0 | #VALUE! | 2014-12-29 | 2015-01-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights |  | Private
NSTAR | Chilmark | 2033372 | 2535 | 195.2 | PV | 4-97-126 | 2014-11-03 | 2014-11-03 | 0 | 0 | 0 | 2014-11-06 | 2014-11-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-06-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Buzzards Bay | 2034325 | 2532 | 104 | PV | 3-88-2J4 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | 2014-11-07 | 2014-11-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2034511 | 2459 | 36 | PV | 292-H3 | 2014-11-05 | 2015-01-20 | #VALUE! | 0 | #VALUE! | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-21 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-28 | Online |  | Private
NSTAR | New Bedford | 2034765 | 2740 | 30.9 | PV | 2-89-14 | 2014-11-05 | 2014-11-06 | #VALUE! | 0 | #VALUE! | 2014-11-10 | 2014-12-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-12 | 2015-05-12 | Online |  | Private
NSTAR | New Bedford | 2034871 | 2746 | 600 | PV | 2-83-403 | 2014-11-06 | 2014-11-07 | #VALUE! | 0 | #VALUE! | 2014-12-12 | 2015-03-30 | #VALUE! | 65 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-12 | Online |  | Private
NSTAR | Dedham | 2034950 | 2026 | 794 | PV | 20-H5 | 2014-11-10 | 2014-11-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Ashland | 2035449 | 1721 | 3756 | PV | 274-1429H1 | 2014-11-10 | 2014-11-18 | #VALUE! | 61 | #VALUE! | 2014-11-14 | 2015-01-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-12-01 | 2015-12-14 | #VALUE! | 0 | #VALUE! | 2015-05-13 | 2016-02-29 | 2016-08-12 | No | STD | 60 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Wareham | 2035472 | 2571 | 999 | PV | 3-85-955 | 2014-11-12 | 2014-11-13 | #VALUE! | 0 | #VALUE! | 2014-11-14 | 2015-01-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-12-29 | 2015-06-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  | 2016-08-29 | Online |  | Private
NSTAR | Plymouth | 2035699 | 2360 | 993.6 | PV | 3-89-926 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | 2014-11-18 | 2014-11-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-05 |  | 2015-06-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acusnet | 2035823 | 2743 | 43.6 | PV | 2-106-160 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | 2014-12-24 | 2015-02-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-04-21 | 2015-04-24 | Online |  | Private
NSTAR | Dedham | 2035957 | 2026 | 150 | Natural Gas | 13-H1 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | 2015-02-10 | 2015-09-01 | #VALUE! | 112 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-06-24 | No | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Screening |  | Private
NSTAR | Plymouth | 2036219 | 2360 | 4000 | PV | 3-14-934 | 2014-11-18 | 2014-12-16 | #VALUE! | 0 | #VALUE! | 2014-12-16 | 2015-02-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 | 2015-08-25 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Lexington | 2036677 | 2421 | 15.75 | PV | TBD | 2014-11-17 |  | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-14 |  | 2015-06-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Walpole | 2036754 | 2081 | 138 | PV | 146-H3 | 2015-08-04 | 2015-08-07 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-11 |  | #VALUE! | 172 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 |  | 2016-03-14 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Plymouth | 2036912 | 2360 | 960 | PV | 3-12-12 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2014-12-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-06-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-01 |  | Withdrawn |  | Private
NSTAR | Yarmouth | 2036990 | 2664 | - | PV | TBD | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-12-12 | 2014-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-27 | 2015-06-29 | No | EXP | 30 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  | 2015-03-06 | 2015-03-06 | Online |  | Gov't
NSTAR | New Bedford | 2037115 | 2745 | 300 | PV | 2-104-104 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2015-02-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-23 | 2015-06-02 | 2015-06-29 | No | EXP | 30 | 2015-07-06 | 2015-07-06 | 0 |  | 0 |  | 2015-07-14 | 2015-07-17 | Online |  | Private
NSTAR | New Bedford | 2037121 | 2745 | 266 | PV | 2-104-104 | 2014-11-20 | 2014-11-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hopkinton | 2037342 | 1748 | 3000 | PV | 65-H6 | 2014-11-21 | 2015-02-10 | #VALUE! | 0 | #VALUE! | 2014-11-24 | 2015-04-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
NSTAR | Bellingham | 2037441 | 2019 | 480 | PV | 65-H4 | 2014-11-21 | 2015-02-10 | #VALUE! | 0 | #VALUE! | 2014-11-24 | 2015-03-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Bellingham | 2037449 | 2019 | 480 | PV | 65-H4 | 2014-11-25 | 2014-12-08 | #VALUE! | 0 | #VALUE! | 2014-12-02 | 2015-02-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-21 |  | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 | 2015-07-31 |  | 2015-07-03 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2037775 | 2770 | 1500 | PV | 3-702-702 | 2014-11-28 | 2014-12-23 | #VALUE! | 0 | #VALUE! | 2014-12-23 | 2014-12-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Yarmouth | 2038201 | 2664 | 40 | PV | 4-92A-562 | 2014-12-02 | 2014-12-23 | #VALUE! | 0 | #VALUE! | 2014-12-23 | 2015-02-26 | #VALUE! | 35 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-07-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-19 | Online |  | Private
NSTAR | Wayland | 2038683 | 1778 | 131 | PV | 342-H1 | 2014-12-02 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-12-02 | #VALUE! | 215 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 | 2016-03-11 | 2016-08-15 | No | EXP | 30 | 2016-03-24 |  | #VALUE! |  | #VALUE! |  |  | 2016-04-14 | Online |  | Private
NSTAR | Ashland | 2038832 | 1721 | 200 | PV | 274-1429H1 | 2014-12-03 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-12-02 | #VALUE! | 215 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 |  | 2015-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online |  | Private
NSTAR | Ashland | 2039760 | 1721 | 200 | PV | 274-1429H1 | 2014-12-04 | 2015-01-23 | #VALUE! | 0 | #VALUE! | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 |  | 2015-07-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online |  | Private
NSTAR | New Bedford | 2041158 | 2746 | 18 | PV | 2-84-133 | 2014-12-04 | 2015-01-13 | #VALUE! | 0 | #VALUE! | 2015-01-13 | 2015-02-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-02-23 | 2015-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2015-04-29 |  | 2015-07-13 | TBD | STD | 60 |  |  | 0 |  | 0 |  | 2015-12-17 | 2015-12-17 | Online |  | PRIVATE
NSTAR | East Freetown | 2041172 | 2717 | 1137 | Natural Gas | 2-606-606 | 2014-12-08 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-26 |  | 2015-07-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2041620 | 2139 | 22.8 | PV | 815-10 | 2014-12-08 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-02-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-03 |  | 2015-07-15 | TBD | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  |  | 2015-06-12 | Online |  | Private
NSTAR | Cambridge | 2041623 | 2139 | 22.8 | PV | 814-12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 |  | 2015-07-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-05 | Online |  | Private | N
NSTAR | Dartmouth | 2042098 | 2747 | 17.5 | PV | 2-533-533 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-04 | Online |  | Private
NSTAR | Sherborn | 2042113 | 1770 | 29 | PV | 240-H1 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-15 | 2015-01-14 | 2015-05-22 | No | EXP | 30 | 2015-05-08 | 2015-05-08 | 0 |  | 0 |  |  | 2015-05-29 | Online |  | Private
NSTAR | Newton | 2042189 | 2466 | 16.4 | PV | 292-H12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-02-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-04 | Online |  | Private
NSTAR | Mashpee | 2042191 | 2649 | 11.4 | PV | 4-77A-454 | 2014-12-16 | 2014-12-17 | #VALUE! | 0 | #VALUE! | 2014-12-19 | 2015-03-30 | #VALUE! | 36 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-16 | 2015-05-27 | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2043228 | 1760 | 211 | PV | 23-H1 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-22 | 2015-03-18 | #VALUE! | 27 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-18 |  | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-15 | 2016-01-15 | Online |  | Private
NSTAR | Framingham | 2043236 | 1701 | 524 | PV | 433-H3 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-19 | 2015-03-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 | 2015-09-14 | 2016-01-15 | No | EXP | 30 | 2015-10-30 | 2015-10-30 | 0 |  | 0 |  | 2016-02-03 | 2016-01-15 | Online |  | Private
NSTAR | Bourne | 2043278 | 2532 | 650 | PV | 4-86-402 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 | 2015-02-02 | 2015-03-01 | No | EXP | 30 | 2015-03-26 | 2015-03-26 | 0 |  | 0 |  |  | 2015-12-31 | Online |  | Private
NSTAR | Somerville | 2043499 | 2145 | 50 | PV | 585-114H4 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-22 | 2014-12-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-23 | Online |  | Private
NSTAR | Brewster | 2043623 | 2631 | 132 | PV | 4-89A-553 | 2014-12-22 | 2014-12-24 | #VALUE! | 0 | #VALUE! | 2014-12-29 | 2015-01-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2015-02-05 | 2015-04-01 | TBD | EXP | 30 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 2015-04-07 | Online |  | Private
NSTAR | Yarmouthport | 2044156 | 2675 | 57 | PV | 4-92A-92A | 2014-12-23 | 2014-12-24 | #VALUE! | 0 | #VALUE! | 2014-12-29 | 2015-01-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-30 | 2015-01-29 | 2015-06-19 | No | EXP | 30 | 2015-05-20 | 2015-05-20 | 0 |  | 0 |  |  | 2015-06-17 | Online |  | Private
NSTAR | Canton | 2044274 | 2021 | 18.9 | PV | 269-1320H1 | 2014-12-26 | 2014-12-26 | 0 | 0 | 0 | 2015-01-01 | 2015-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 |  | 2015-08-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-03-26 | Online |  | Private
NSTAR | Holliston | 2044550 | 1746 | 15.2 | PV | 65-H2 | 2014-12-26 | 2014-12-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Gov't
NSTAR | Boston | 2044564 | 2118 | 2000 | Natural Gas | 4910 | 2014-12-31 | 2014-12-31 | 0 | 0 | 0 | 2015-01-06 | 2015-01-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-08 | 2015-01-08 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-09 | Online |  | Private | N
NSTAR | Truro | 2045149 | 2652 | 16 | PV | 4-96-674 | 2014-12-31 | 2015-01-02 | #VALUE! | 0 | #VALUE! | 2015-01-02 | 2015-01-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-12 | 2015-01-12 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-11 | Online |  | Private
NSTAR | Dennisport | 2045155 | 2639 | 72 | PV | 4-92B-583 | 2015-01-06 | 2015-01-08 | #VALUE! | 0 | #VALUE! | 2015-01-12 | 2015-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-25 | Online |  | Private
NSTAR | Millis | 2048757 | 2054 | 131 | PV | 146-H10 | 2015-01-07 | 2015-01-08 | #VALUE! | 0 | #VALUE! | 2015-01-12 | 2015-03-31 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-14 | 2015-04-14 | 2015-08-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-18 | 2015-12-18 | Online |  | Private
NSTAR | Boston | 2048937 | 2118 | 85 | Natural Gas | 318-10 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 2015-01-13 | 2015-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-29 | Online |  | Private
NSTAR | Millis | 2049131 | 2054 | 42 | PV | 146-H10 | 2015-01-09 | 2015-01-12 | #VALUE! | 0 | #VALUE! | 2015-01-15 | 2015-03-26 | #VALUE! | 15 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 | 2015-03-31 | 2015-07-23 | No | EXP | 30 | 2015-06-15 |  | #VALUE! |  | #VALUE! |  | 2015-09-11 | 2015-09-11 | Online |  | Private
NSTAR | Millis | 2049284 | 2054 | 300 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | #VALUE! | 0 | #VALUE! | 2015-01-15 | 2015-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-11 | Online |  | Private
NSTAR | Millis | 2049734 | 2054 | 75 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | #VALUE! | 0 | #VALUE! | 2015-01-15 | 2015-03-31 | #VALUE! | 40 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 | 2015-06-02 | 2015-09-30 | TBD | EXP | 30 | 2015-07-15 | 2015-07-15 | 0 |  | 0 |  | 2015-09-28 | 2015-09-28 | Online |  | Private
NSTAR | New Bedford | 2049774 | 2745 | 200 | PV | 2-104-104 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-01 | Online |  | Private
NSTAR | Dartmouth | 2049963 | 2748 | 17.8 | PV | 2-2-505 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Sharon | 2049971 | 2067 | 15.8 | PV | 470-H3 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-22 | Withdrawn |  | Private
NSTAR | Wayland | 2050518 | 1778 | 113 | PV | 433-H6 | 2015-01-16 | 2015-01-19 | #VALUE! | 0 | #VALUE! | 2015-01-21 | 2015-02-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-03 | Online |  | Private
NSTAR | Canton | 2050531 | 2021 | 95 | PV | 470-H4 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-07-07 | 2015-07-31 | TBD | EXP | 30 | 2015-07-28 | 2015-07-28 | 0 |  | 0 |  |  | 2015-08-18 | Online |  | Private
NSTAR | Wareham | 2050542 | 2576 | 23.6 | PV | 3-85-928 | 2015-01-20 | 2015-01-20 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study |  | Private | N
NSTAR | Acusnet | 2051046 | 2743 | 1904 | PV | 2-241-238 | 2015-01-20 | 2015-01-21 | #VALUE! | 0 | #VALUE! | 2015-01-27 | 2015-09-03 | #VALUE! | 152 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-04-29 | Online |  | Private
NSTAR | Holliston | 2051070 | 1746 | 2000 | PV | 130-H1 | 2015-01-21 | 2015-01-21 | 0 | 64 | 0 | 2015-01-23 | 2016-01-19 | #VALUE! | 66 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2016-12-31 | No | COMP | 160 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2051273 | 2330 | 1500 | PV | 3-10-930 | 2015-01-21 | 2015-01-23 | #VALUE! | 0 | #VALUE! | 2015-01-23 |  | #VALUE! | 395 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2017-01-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2015-10-02 | 2015-05-14 | 2015-08-26 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online | 2015-01-27 | Private
NSTAR | Acusnet | 2051285 | 2743 | 4000 | PV | 2-241-238 | 2015-01-21 | 2015-01-23 | #VALUE! | 0 | #VALUE! | 2015-01-27 | 2015-02-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-05-19 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 | 2015-10-02 |  |  |  | STD |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hopkinton | 2051301 | 1748 | 31 | PV | 65-H2 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 | 2015-04-20 | 2015-08-26 | TBD | EXP | 30 | 2015-05-18 | 2015-05-18 | 0 |  | 0 |  |  | 2015-09-04 | Online |  | Private
NSTAR | Falmouth | 2051319 | 2536 | 56 | PV | 4-76-436 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
NSTAR | Maynard | 2051324 | 1754 | 15.2 | PV | 355-05 | 2015-01-21 | 2015-01-22 | #VALUE! | 0 | #VALUE! | 2015-01-23 | 2015-02-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-09-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2051325 | 2747 | 360 | PV | 2-532-532 | 2015-01-21 | 2015-01-21 | 0 |  | 0 | 2015-01-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-03 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2051336 | 2571 | 150 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 | 2015-02-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Witness Test Awaiting Cust Response/Doc |  | Gov't
NSTAR | Cambridge | 2051340 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-07 | Online |  | Private
NSTAR | Wareham | 2051382 | 2571 | 56 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-02-18 | 2015-08-26 | TBD | EXP | 30 | 2015-03-19 | 2015-03-19 | 0 |  | 0 |  |  | 2015-03-27 | Online |  | Private
NSTAR | Framingham | 2051390 | 1701 | 17.6 | PV | 433-H4 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Cambridge | 2051393 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-24 | Online |  | Private
NSTAR | Westport | 2051411 | 2790 | 16.3 | PV | 2-523-523 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 |  | 2015-08-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private | N
NSTAR | Roxbury | 2051417 | 2119 | 42 | PV | 323-05 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | 2015-01-29 | 2015-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-25 | 2015-09-09 | #VALUE! | 0 | #VALUE! | 2015-03-25 | 2015-09-24 | 2016-04-01 | No | COMP | 160 | 2015-11-19 | 2015-11-19 | 0 |  | 0 |  | 2016-05-23 | 2016-09-28 | Online |  | Private
NSTAR | Wareham | 2051455 | 2538 | 2000 | PV | 3-84-961 | 2015-01-22 | 2015-01-22 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online |  | Private
NSTAR | Mattapoisett | 2051477 | 2739 | 2250 | PV | 2-304-304 | 2015-01-22 | 2015-01-23 | #VALUE! | 0 | #VALUE! | 2015-02-19 | 2015-03-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-27 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Mattapoisett | 2051498 | 2739 | 2500 | PV | 2-304-304 | 2015-01-26 | 2015-01-29 | #VALUE! | 0 | #VALUE! | 2015-02-02 | 2015-02-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-06 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Assonett | 2051972 | 2702 | 24.1 | PV | 2-605-605 | 2015-01-26 | 2015-01-29 | #VALUE! | 0 | #VALUE! | 2015-02-02 | 2015-02-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-24 | Online |  | Private
NSTAR | Wayland | 2052009 | 1778 | 42 | PV | 433-H6 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | 2015-02-02 | 2015-02-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-06 | Online |  | Private
NSTAR | Framingham | 2052167 | 1702 | 15.2 | PV | 455-H3 | 2015-01-29 | 2015-01-29 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Ashland | 2052252 | 1721 | 2413 | PV | 274-H1 | 2015-01-30 | 2015-01-30 | 0 | 0 | 0 | 2015-02-04 | 2015-02-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-09 |  | 2015-09-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
NSTAR | East Freetown | 2052538 | 2717 | 17.4 | PV | 2-102-102 | 2014-11-05 | 2014-11-12 | #VALUE! |  | #VALUE! | 2015-02-03 |  | #VALUE! |  | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-02-09 | 2015-02-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2016-02-12 | Online |  | Private | N
NSTAR | Lexington | 2052550 | 2421 | 2964 | PV | 533-H2 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2016-12-04 | 2015-09-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-15 | Online |  | Gov't
NSTAR | Arlington | 2053824 | 2476 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-18 | Online |  | Gov't
NSTAR | Arlington | 2053835 | 2476 | 176 | PV | 211-H3 | 2015-02-03 | 2015-02-04 | #VALUE! | 0 | #VALUE! | 2015-02-13 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Arlington | 2053837 | 2474 | 74 | PV | 59-1383H1 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 |  | 2015-09-09 | TBD | EXP | 30 | 2015-03-05 | 2015-03-05 | 0 |  | 0 |  |  | 2015-11-18 | Online |  | Gov't
NSTAR | Arlington | 2053847 | 2476 | 74 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-19 | Online |  | Gov't
NSTAR | Arlington | 2053868 | 2474 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee/ Agreement |  | Private
NSTAR | Acusnet | 2053880 | 2743 | 1995 | PV | 2-241-238 | 2015-02-04 | 2017-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | impact study |  | Private
NSTAR | Plymouth | 2053997 | 2360 | 112 | PV | 3-13-936 | 2015-02-05 | 2015-02-05 | 0 | 0 | 0 | 2015-02-10 | 2015-03-26 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-09-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-09 | 2016-03-29 | Online |  | Private
NSTAR | Framingham | 2054091 | 1701 | 322 | PV | 433-H3 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | 2015-02-11 |  | #VALUE! | 145 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-14 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-07-23 | Online |  | Private
NSTAR | Plymouth | 2054256 | 2360 | 1000 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 |  | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-10-03 | Online |  | Private
NSTAR | Lexington | 2054352 | 2421 | 15.9 | PV | 320-H2 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-11 |  | #VALUE! | 115 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-15 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Plymouth | 2054376 | 2360 | 500 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 | 2015-02-19 | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | hold - cluster |  | Private
NSTAR | Harwichport | 2054472 | 2646 | 15.2 | PV | 4-95A-95A | 2015-02-10 | 2015-02-11 | #VALUE! | 0 | #VALUE! | 2015-02-13 | 2015-02-19 | #VALUE! | 47 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Ashland | 2054585 | 1721 | 21.2 | PV | 519-175H1 | 2015-02-12 | 2015-02-13 | #VALUE! | 0 | #VALUE! | 2015-02-17 | 2015-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-31 |  | 2016-04-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2054857 | 2747 | 800 | PV | 2-533-530 | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dennis | 2055020 | 2660 | 56 | PV | 4-92B-92B | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online |  | Private
NSTAR | Dennis | 2055023 | 2660 | 70 | PV | 4-92B-92B | 2015-02-18 | 2015-02-19 | #VALUE! | 0 | #VALUE! | 2015-02-23 | 2015-02-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-09-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online |  | Gov't
NSTAR | Arlington | 2055516 | 2476 | 56 | PV | 320-H7 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | 2015-02-27 | 2015-03-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-03-05 | 2015-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
NSTAR | Dennis | 2055761 | 2660 | 15.2 | PV | 4-92B-572 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-15 |  | Construction |  | Private | N
NSTAR | Weston | 2055868 | 2493 | 1795 | PV | 450-H7 | 2015-02-24 | 2015-03-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-15 | Online |  | Private | Y
NSTAR | Oak Bluffs | 2055949 | 2557 | 2000 | PV | 4-75-75 | 2015-02-24 | 2015-02-25 | #VALUE! | 0 | #VALUE! | 2015-02-27 | 2015-04-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Forestdale | 2055988 | 2644 | 15.8 | PV | 4-81B-443 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | 2015-03-02 | 2015-03-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-29 | Online |  | Private
NSTAR | Plymouth | 2056169 | 2360 | 100 | PV | 3-14-911 | 2015-02-26 | 2015-02-26 | 0 | 0 | 0 | 2015-03-04 | 2015-03-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-27 |  | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | East Freetown | 2056337 | 2717 | 52 | PV | 2-102-602 | 2015-02-27 | 2015-02-27 | 0 | 0 | 0 | 2015-03-04 | 2015-03-30 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-13 |  | 2015-10-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online |  | Private
NSTAR | Chelsea | 2056434 | 2150 | 394.4 | PV | 488-H2 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-28 |  | 2016-09-30 | TBD | EXP | 30 | 2016-03-02 |  | #VALUE! |  | #VALUE! |  |  |  | Withdrawn |  | Private
NSTAR | Chelsea | 2056439 | 2150 | 185.6 | PV | 488-H2 | 2015-02-03 | 2015-02-03 | 0 |  | 0 | 2015-03-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-15 | 2015-04-27 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2056449 | 2770 | 840 | PV | 3-702-702 | 2015-03-03 | 2015-03-03 | 0 | 0 | 0 | 2015-03-06 | 2015-03-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online |  | Private
NSTAR | Rochester | 2056499 | 2770 | 2500 | PV | 3-703-703 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-07-28 | 2016-09-12 | 2016-12-16 | TBD | EXP | 30 | 2016-03-02 | 2016-03-02 | 0 |  | 0 |  | 2017-01-13 | 2017-01-13 | Online |  | Private
NSTAR | Acusnet | 2057145 | 2743 | 18 | PV | 2-241-237 | 2015-03-04 | 2015-03-09 | #VALUE! | 49 | #VALUE! | 2015-06-03 | 2015-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 |  | 2015-10-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Hopkinton | 2057252 | 1748 | 308 | PV | 126-H2 | 2015-03-21 | 2015-05-06 | #VALUE! | 5 | #VALUE! | 2015-05-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 | [7 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online |  | Private
NSTAR | Millis | 2057504 | 2054 | 296 | PV | 65-H3 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-03-13 | Private
NSTAR | Marion | 2057875 | 2738 | 482 | PV | 2-304-304 | 2015-03-12 | 2015-03-12 | 0 | 0 | 0 | 2015-03-17 | 2015-04-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 |  | 2015-10-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2058198 | 2747 | 17 | PV | 2-532-532 | 2015-03-16 | 2015-03-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-03-24 | Private
NSTAR | Acusnet | 2058670 | 2743 | 1000 | PV | 2-241-241 | 2015-03-17 | 2015-03-17 | 0 | 0 | 0 | 2015-03-24 | 2015-04-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-17 | 2019-08-21 | 2015-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | Westwood | 2059020 | 2090 | 40 | PV | 456-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-04-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-01 | 2016-06-06 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Wayland | 2059369 | 1778 | 176 | PV | 342-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-05-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online |  | Private
NSTAR | Wayland | 2059403 | 1778 | 207 | PV | 342-H3 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-06-22 | #VALUE! | 25 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-18 | 2016-01-11 | 2016-07-29 | TBD | EXP | 30 | 2016-04-29 |  | #VALUE! |  | #VALUE! |  |  | 2016-12-30 | Online |  | Gov't
NSTAR | Wayland | 2059432 | 1778 | 500 | PV | 278-H2 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-23 | 2015-05-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Wayland | 2059441 | 1778 | 217 | PV | 433-H6 | 2015-03-19 | 2015-03-20 | #VALUE! | 0 | #VALUE! | 2015-07-23 | 2015-07-30 | #VALUE! | 85 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-22 | 2016-06-30 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-29 | Online |  | Private
NSTAR | Natick | 2059455 | 1760 | 240 | PV | 433-H7 | 2015-03-23 | 2015-03-23 | 0 | 0 | 0 | 2015-03-31 | 2015-04-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-15 |  | 2015-10-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Woburn | 2059849 | 1801 | 65 | PV | 211-H2 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-06-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-14 | 2016-02-05 | 2015-10-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Plymouth | 2059927 | 2360 | 500 | PV | 3-12-12 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-04-21 | #VALUE! | 7 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 |  | 2015-10-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2059968 | 2790 | 21 | PV | 2-523-523 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | 2015-04-09 | 2015-05-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-08 | 2015-05-08 | 2015-10-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private
NSTAR | Medfield | 2060105 | 2052 | 196 | PV | 456-H2 | 2015-03-31 | 2015-04-01 | #VALUE! | 0 | #VALUE! | 2015-04-03 | 2015-09-21 | #VALUE! | 117 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2060976 | 1760 | 500 | PV | 408-1433 | 2015-03-31 | 2015-03-31 | 0 | 0 | 0 | 2015-04-03 | 2015-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-30 |  | 2015-11-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Holliston | 2061089 | 1746 | 28 | PV | 65-H5 | 2015-03-31 | 2015-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Westport | 2061122 | 2790 | 2000 | PV | 2-532-532 | 2015-04-01 | 2015-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-09-27 | Online |  | Private
NSTAR | Walpole | 2061451 | 2081 | 2280 | PV | 146-H6 | 2015-04-02 | 2015-04-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 76 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2015-11-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-06-26 | Online |  | Private | N
NSTAR | Bellingham | 2061830 | 2019 | 1976 | PV | 65-H4 | 2015-04-03 | 2015-04-17 | #VALUE! | 0 | #VALUE! | 2015-04-20 | 2015-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-11 | 2015-09-07 | 2015-11-09 | TBD | EXP | 30 | 2015-10-16 | 2015-10-16 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Falmouth | 2062098 | 2540 | 56 | PV | 4-76-436 | 2015-04-03 | 2015-04-17 | #VALUE! | 0 | #VALUE! | 2015-04-22 | 2015-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 | 2015-04-23 | 2015-11-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-04 | Online |  | Private
NSTAR | Provincetown | 2062144 | 2657 | 27 | PV | 4-96-675 | 2015-04-06 | 2015-04-13 | #VALUE! | 0 | #VALUE! | 2015-04-16 | 2015-04-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 |  | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-08 | Online |  | Private
NSTAR | Wareham | 2062402 | 2571 | 17 | PV | 3-84-84 | 2015-04-06 | 2015-04-16 | #VALUE! | 0 | #VALUE! | 2015-04-20 | 2015-04-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-22 | 2015-04-22 | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Meter |  | Private
NSTAR | Edgartown | 2062416 | 2539 | 56 | PV | 4-97-97 | 2015-04-07 | 2015-04-07 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-07-21 | 2016-08-29 | Online |  | Private | N
NSTAR | Marion | 2062768 | 2738 | 882 | PV | 3-85-85 | 2015-04-08 | 2015-04-22 | #VALUE! | 3 | #VALUE! | 2015-04-24 | 2015-05-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-20 | Online |  | Private
NSTAR | Boston | 2062878 | 2118 | 100 | PV | 2-543-543 | 2015-04-08 | 2015-04-21 | #VALUE! | 0 | #VALUE! | 2015-04-23 | 2015-07-17 | #VALUE! | 59 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-22 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-25 | Online |  | Private
NSTAR | New Bedford | 2062901 | 2745 | 40 | PV | 2-88-18 | 2015-04-09 | 2015-04-15 | #VALUE! | 0 | #VALUE! | 2015-04-16 | 2015-07-07 | #VALUE! | 23 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-08 |  | 2015-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Dedham | 2063144 | 2026 | 210 | PV | 469-H4 | 2015-04-09 | 2015-04-16 | #VALUE! | 0 | #VALUE! | 2015-04-20 | 2015-04-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Orleans | 2063168 | 2653 | 100 | PV | 4-89B-618 | 2015-04-13 | 2015-04-14 | #VALUE! | 0 | #VALUE! | 2015-04-16 | 2015-04-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
NSTAR | Harwichport | 2063694 | 2646 | 40 | PV | 4-85-592 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-05-16 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2016-06-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | East Boston | 2063933 | 2128 | 499 | PV | 108-196H1 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-07-07 | #VALUE! | 28 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-07 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | East Boston | 2063964 | 2128 | 499 | PV | 108-196H1 | 2015-04-16 | 2015-04-16 | 0 | 0 | 0 | 2015-05-01 | 2015-05-28 | #VALUE! | 7 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2015-11-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-29 | 2017-04-06 | Online |  | Private | N
NSTAR | Waltham | 2064568 | 2451 | 500 | PV | 363-1369 | 2015-04-17 | 2015-04-17 | 0 | 37 | 0 | 2015-04-24 | 2015-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-02 |  | 2015-11-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Dartmouth | 2064782 | 2748 | 20 | PV | 2-528-528 | 2015-04-17 | 2015-04-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-28 | Online |  | Private
NSTAR | Woburn | 2064809 | 1801 | 2640 | PV | 375-H6 | 2015-04-21 | 2015-04-28 | #VALUE! | 49 | #VALUE! | 2015-05-05 | 2015-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-12 | 2015-09-15 | 2015-11-25 | No | EXP | 30 | 2015-12-11 | 2015-12-11 | 0 |  | 0 |  | 2015-12-22 | 2017-06-15 | Online |  | Private
NSTAR | Dartmouth | 2065135 | 2747 | 239.4 | PV | 2-532-532 | 2015-04-21 | 2015-04-22 | #VALUE! | 0 | #VALUE! | 2015-04-24 | 2015-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2015-08-26 | 2015-11-25 | No | EXP | 30 | 2015-09-16 | 2015-09-16 | 0 |  | 0 |  | 2015-12-22 | 2016-02-28 | Online |  | Private
NSTAR | Dartmouth | 2065189 | 2747 | 360 | PV | 2-532-532 | 2015-04-22 | 2015-07-28 | #VALUE! | 60 | #VALUE! | 2015-08-03 | 2016-08-01 | #VALUE! | 63 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-07 |  | 2015-11-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee |  | Private | N
NSTAR | Plympton | 2065453 | 2367 | 5000 | PV | 3-51-DSS | 2015-04-23 | 2015-04-24 | #VALUE! | 0 | #VALUE! | 2015-05-04 | 2016-05-24 | #VALUE! | 256 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Millis | 2065662 | 2054 | 2000 | PV | 65-H1 | 2015-04-24 | 2015-04-29 | #VALUE! | 0 | #VALUE! | 2015-04-30 | 2015-05-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-04 |  | 2015-12-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2065777 | 2140 | 36 | PV | 826-20 | 2015-04-24 | 2015-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Centerville | 2065805 | 2632 | 17.4 | PV | 4-82-508 | 2015-04-27 | 2015-05-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2015-07-27 | Private
NSTAR | Boston | 2066237 | 2118 | 96 | PV | 528-129H | 2015-04-28 | 2015-04-29 | #VALUE! | 0 | #VALUE! | 2015-04-29 | 2015-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-21 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 |  | Withdrawn |  | Gov't
NSTAR | Cambridge | 2066481 | 2139 | 568 | PV | 817-05 | 2015-04-28 | 2015-05-05 | #VALUE! | 0 | #VALUE! | 2015-05-07 | 2015-05-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-27 |  | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-24 | Withdrawn |  | Private
NSTAR | Boston | 2066533 | 2118 | 48 | PV | 385-H15 | 2015-04-28 | 2015-05-19 | #VALUE! | 11 | #VALUE! | 2015-05-20 | 2015-06-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-24 | 2015-06-24 | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-07-12 | 2016-07-22 | Online |  | Private
NSTAR | Provincetown | 2066548 | 2657 | 30 | PV | 4-96-676 | 2015-05-05 | 2015-05-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Bellingham | 2068158 | 2019 | 497 | PV | 65-H4 | 2015-05-06 | 2015-05-07 | #VALUE! | 0 | #VALUE! | 2015-07-01 | 2015-07-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-09 | 2016-09-12 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | ISA Received/Signed |  | Private
NSTAR | Waltham | 2068489 | 2451 | 96 | PV | 450-H8 | 2015-05-07 | 2015-05-11 | #VALUE! | 0 | #VALUE! | 2015-05-14 | 2015-06-22 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-01 |  | 2015-12-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-22 | 2016-01-25 | Online |  | Private
NSTAR | Woburn | 2068626 | 1801 | 300 | PV | 375-H11 | 2015-05-07 | 2015-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private | N
NSTAR | Westport | 2068650 | 2790 | 2550 | PV | 2-522-522 | 2015-05-08 | 2015-05-12 | #VALUE! | 0 | #VALUE! | 2015-05-15 | 2015-05-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-05 |  | 2015-12-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-01 | Online |  | Private | Y
NSTAR | Lexington | 2068862 | 2420 | 19 | PV | 391-H11 | 2015-05-08 | 2015-05-12 | #VALUE! | 0 | #VALUE! | 2015-05-15 | 2015-05-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-29 | 2015-05-29 | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-05 | Online |  | Private
NSTAR | Natick | 2068895 | 1760 | 19 | PV | 240-H5 | 2015-05-11 | 2015-05-13 | #VALUE! | 0 | #VALUE! | 2015-05-15 | 2015-05-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-01 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online |  | Private
NSTAR | Duxbury | 2069125 | 2332 | 16 | PV | 3-23-981 | 2015-05-11 | 2015-05-13 | #VALUE! | 0 | #VALUE! | 2015-05-15 | 2015-07-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-06 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-20 | 2016-01-25 | Online |  | Private
NSTAR | Lexington | 2069155 | 2421 | 319 | PV | 320-H5XY | 2015-05-15 | 2015-05-16 | #VALUE! | 47 | #VALUE! | 2015-05-18 | 2015-08-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-19 | Online |  | Private
NSTAR | Norfolk | 2070139 | 2056 | 475 | PV | 146-H3 | 2015-05-19 | 2015-05-21 | #VALUE! | 0 | #VALUE! | 2015-05-25 | 2015-08-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2015-12-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Woburn | 2070813 | 1801 | 662 | PV | 211-H5 | 2015-05-19 | 2015-05-27 | #VALUE! | 0 | #VALUE! | 2015-05-28 | 2015-06-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2015-06-25 | 2015-12-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Watertown | 2070884 | 2472 | 156 | PV | 467-H9 | 2015-05-20 | 2015-05-26 | #VALUE! | 45 | #VALUE! | 2015-05-28 | 2015-07-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2015-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Ashland | 2071026 | 1721 | 498 | PV | 519-175H1 | 2015-05-20 | 2015-05-22 | #VALUE! | 0 | #VALUE! | 2015-05-27 | 2015-06-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-07-09 | 2015-12-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online |  | Private
NSTAR | Ashland | 2071030 | 1721 | 186 | PV | 274-1429H1 | 2015-05-20 | 2015-05-26 | #VALUE! | 0 | #VALUE! | 2015-05-28 | 2015-07-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2016-02-29 | 2016-12-27 | No | EXP | 30 | 2016-02-23 |  | #VALUE! | 0 | #VALUE! |  |  | 2017-02-23 | Online |  | Private
NSTAR | Ashland | 2071039 | 1721 | 728 | PV | 455-H3 | 2015-05-21 | 2015-06-10 | #VALUE! | 0 | #VALUE! | 2015-06-11 | 2015-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Hyannis | 2071355 | 2601 | 144 | PV | 4-80B-523 | 2015-05-21 | 2015-06-25 | #VALUE! | 0 | #VALUE! | 2015-07-01 | 2015-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online |  | Private
NSTAR | Hyannis | 2071356 | 2601 | 120 | PV | 4-84B-524 | 2015-05-26 | 2015-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | 2015-06-23 | Private | N
NSTAR | Wareham | 2071689 | 2576 | 1800 | PV | 3-85-85 | 2015-05-27 | 2015-05-28 | #VALUE! | 0 | #VALUE! | 2015-05-28 | 2015-06-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-10 |  | 2016-01-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-17 | Online |  | Private
NSTAR | Natick | 2071934 | 1760 | 148 | PV | 240-H5 | 2015-05-28 | 2015-06-01 | #VALUE! | 0 | #VALUE! | 2015-06-03 | 2015-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2016-01-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online |  | Private
NSTAR | Plymouth | 2072210 | 2360 | 112 | PV | 3-12-12 | 2015-05-28 | 2015-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Framingham | 2072250 | 1702 | 4279 | PV | 274-H4 | 2015-05-29 | 2015-05-30 | #VALUE! | 0 | #VALUE! | 2015-06-05 | 2016-01-27 | #VALUE! | 158 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-23 | 2016-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-18 | Online |  | Private
NSTAR | Woburn | 2072460 | 1801 | 225 | PV | 375-H6 | 2015-06-01 | 2015-06-04 | #VALUE! | 0 | #VALUE! | 2015-06-08 | 2015-07-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-29 | 2015-10-23 | 2016-03-17 | TBD | EXP | 30 | 2016-01-15 | 2016-01-15 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2072760 | 2748 | 100 | PV | 2-528-528 | 2015-06-01 | 2015-06-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Impct Stdy:Awaiting Customers Response/Doc | 2016-06-14 | Private
NSTAR | Millis | 2072811 | 2054 | 1002 | PV | 65-H3 | 2015-06-02 | 2015-06-03 | #VALUE! | 0 | #VALUE! | 2015-06-05 | 2015-07-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-24 | 2015-12-10 | 2016-01-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-11-01 | Online |  | Private
NSTAR | Woburn | 2073317 | 1801 | 100 | PV | 211-H8 | 2015-06-03 | 2016-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-03-02 | Online |  | Private
NSTAR | Arlington | 2073733 | 2474 | 92 | PV | 59-1383H1 | 2015-06-03 | 2015-10-28 | #VALUE! | 87 | #VALUE! | 2015-10-28 | 2015-10-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-11-02 | 2016-01-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-28 | 2015-12-08 | Online |  | Private | N
NSTAR | Arlington | 2073753 | 2476 | 69 | PV | 351-1385H1 | 2015-06-04 | 2015-06-08 | #VALUE! | 0 | #VALUE! | 2015-06-09 | 2015-07-30 | #VALUE! | 34 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private | N
NSTAR | Lincoln | 2073947 | 1773 | 84 | PV | 320-H8 | 2015-06-04 | 2015-06-08 | #VALUE! | 0 | #VALUE! | 2015-06-10 | 2015-07-17 | #VALUE! | 26 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-30 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-18 | Online |  | Private | N
NSTAR | Lincoln | 2073959 | 1773 | 112 | PV | 320-H8 | 2015-06-09 | 2015-06-11 | #VALUE! | 0 | #VALUE! | 2015-06-15 | 2015-06-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-12-18 | 2016-01-20 | TBD | EXP | 30 | 2015-12-28 | 2015-12-28 | 0 |  | 0 |  |  | 2016-01-29 | Online |  | Private
NSTAR | Holliston | 2074665 | 1746 | 20 | PV | 274-H5 | 2015-06-10 | 2015-06-12 | #VALUE! | 0 | #VALUE! | 2015-06-17 | 2015-08-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 |  | 2016-01-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-19 | Online |  | Private | N
NSTAR | Wianno | 2074867 | 2655 | 44 | PV | 4-80A-892 | 2015-06-19 | 2015-06-25 | #VALUE! | 0 | #VALUE! | 2015-06-24 |  | #VALUE! | 290 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-01-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-06-26 | Private
NSTAR | Dartmouth | 2076812 | 2747 | 4500 | PV | 2-532-532 | 2015-06-23 | 2015-06-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-07-03 | Private
NSTAR | Acusnet | 2077489 | 2743 | 1080 | PV | 2-241-241 | 2015-06-25 | 2015-06-30 | #VALUE! | 0 | #VALUE! | 2015-07-02 | 2015-07-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-02-02 | No | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | Wareham | 2077939 | 2571 | 200 | PV | 3-84-961 | 2015-06-30 | 2015-07-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Ashland | 2078781 | 1721 | 183.287 | PV | 274-1429H1 | 2015-07-02 | 2015-07-06 | #VALUE! | 0 | #VALUE! | 2015-07-08 | 2015-07-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-17 | 2015-09-30 | 2015-11-06 | No | EXP | 30 | 2015-10-20 | 2015-10-20 | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private | N
NSTAR | Walpole | 2079372 | 2081 | 153 | PV | 146-H3 | 2015-07-02 | 2015-07-09 | #VALUE! | 0 | #VALUE! | 2015-07-10 | 2015-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-16 |  | 2016-02-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-13 | Online |  | Private
NSTAR | Assonett | 2079393 | 2702 | 20 | PV | 2-605-605 | 2015-07-09 | 2015-07-16 | #VALUE! | 0 | #VALUE! | 2015-07-20 | 2015-08-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2016-02-12 | 2016-06-30 | No | EXP | 30 | 2016-08-10 |  | #VALUE! |  | #VALUE! |  |  |  | Construction |  | Private
NSTAR | Woburn | 2080949 | 1801 | 696 | PV | 375-H4 | 2015-07-16 | 2015-07-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private | N
NSTAR | Bellingham | 2082060 | 2019 | 990 | PV | 65-H4 | 2015-07-17 | 2015-07-20 | #VALUE! | 0 | #VALUE! | 2015-07-23 | 2015-08-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2016-02-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2082435 | 2360 | 79 | PV | 3-12-12 | 2015-07-17 | 2015-07-21 | #VALUE! | 0 | #VALUE! | 2015-07-23 | 2016-02-10 | #VALUE! | 50 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-01 | 2016-05-25 | 2016-10-14 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online |  | Private
NSTAR | Plympton | 2082491 | 2367 | 990 | PV | 3-51-901 | 2015-07-17 | 2015-07-21 | #VALUE! | 0 | #VALUE! | 2015-07-23 | 2015-08-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 | 2016-02-10 | 2016-02-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-09 | Online |  | Private
NSTAR | Woburn | 2082549 | 1801 | 495 | PV | 375-H3 | 2015-07-21 | 2015-07-22 | #VALUE! | 0 | #VALUE! | 2015-07-24 | 2015-09-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-29 | 2016-05-30 | 2016-02-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-03-29 | Online |  | Private
NSTAR | Woburn | 2083212 | 1801 | 263 | PV | 325-03 | 2015-07-21 | 2015-07-22 | #VALUE! | 3 | #VALUE! | 2015-07-24 | 2015-09-02 | #VALUE! | 194 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-16 | 2016-01-06 | 2016-02-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online |  | Gov't | Y
NSTAR | Woburn | 2083239 | 1801 | 454 | PV | 211-H5 | 2015-07-22 | 2015-07-23 | #VALUE! | 0 | #VALUE! | 2015-07-27 | 2015-09-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-25 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Woburn | 2083306 | 1801 | 265 | PV | 211-H10 | 2015-07-22 | 2015-07-23 | #VALUE! | 0 | #VALUE! | 2015-07-27 | 2015-08-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Jamaica Plain | 2083371 | 2130 | 28 | PV | 496-H4 | 2015-07-23 | 2015-07-24 | #VALUE! | 0 | #VALUE! | 2015-07-28 | 2015-08-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2016-03-15 | 2016-08-25 | TBD | EXP | 30 | 2016-08-04 | 2016-08-04 | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Mattapoisett | 2083555 | 2739 | 60 | PV | 2-304-304 | 2015-07-27 | 2015-07-29 | #VALUE! | 0 | #VALUE! | 2015-07-30 | 2015-07-30 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-05 | Online |  | Private
NSTAR | Somerville | 2084293 | 2145 | 54 | PV | 250-1N81H1 | 2015-07-27 | 2015-07-28 | #VALUE! | 0 | #VALUE! | 2015-07-31 | 2015-08-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-10 | Online |  | Private
NSTAR | Roxbury | 2084347 | 2119 | 27 | PV | 323-05 | 2015-07-27 | 2015-07-31 | #VALUE! | 0 | #VALUE! | 2015-08-04 | 2015-08-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-20 | 2015-08-19 | 2016-03-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online |  | Private
NSTAR | Needham | 2084378 | 2494 | 40 | PV | 148-H7 | 2015-07-28 | 2015-08-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-08-13 | Private
NSTAR | Acton | 2084724 | 1720 | 2000 | PV | 416-H2 | 2015-07-29 | 2015-08-03 | #VALUE! | 0 | #VALUE! | 2015-08-05 | 2016-01-20 | #VALUE! | 108 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-22 | No | EXP | 30 | 2016-05-11 |  | #VALUE! |  | #VALUE! |  | 2016-06-08 |  | Withdrawn |  | Private | N
NSTAR | Natick | 2085006 | 1760 | 492 | PV | 433-H9 | 2015-07-30 | 2015-08-01 | #VALUE! | 0 | #VALUE! | 2015-08-04 | 2015-09-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-19 | Online |  | Private
NSTAR | Woburn | 2085086 | 1801 | 336 | PV | 258-1394H2 | 2015-07-30 | 2015-08-01 | #VALUE! | 0 | #VALUE! | 2015-08-04 | 2015-09-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Woburn | 2085091 | 1801 | 377 | PV | 258-1394H2 | 2015-07-30 | 2015-08-04 | #VALUE! | 0 | #VALUE! | 2015-08-06 | 2016-01-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-26 |  | 2017-02-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Woburn | 2085252 | 1801 | 624 | PV | 375-H12 | 2015-07-31 | 2015-08-01 | #VALUE! | 0 | #VALUE! | 2015-08-07 | 2016-03-23 | #VALUE! | 142 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2085492 | 2790 | 2000 | PV | 2-524-524 | 2015-07-31 | 2015-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-08-17 | Gov't
NSTAR | Dorchester | 2085514 | 2125 | 4600 | Natural Gas | 511-1497H | 2015-08-04 | 2015-08-07 | #VALUE! | 0 | #VALUE! | 2015-08-11 | 2015-09-15 | #VALUE! | 13 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | East Freetown | 2086294 | 2717 | 1440 | PV | 2-102-604 | 2015-08-06 | 2015-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-09-28 | Private
NSTAR | Wareham | 2086312 | 2576 | 1440 | PV | 3-85-928 | 2015-08-05 | 2015-08-07 | #VALUE! | 0 | #VALUE! | 2015-08-11 | 2015-09-15 | #VALUE! | 23 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Assonett | 2086459 | 2702 | 1440 | PV | 2-605-605 | 2013-11-25 | 2013-12-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-20 |  | Withdrawn
NSTAR | Acusnet | 2086742 | 2743 | 1990 | PV | 2-241-241 | 2015-08-07 | 2015-08-17 | #VALUE! | 0 | #VALUE! | 2015-09-28 |  | #VALUE! | 81 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-03-17 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2016-04-27 | Private
NSTAR | Acusnet | 2086776 | 2743 | 1000 | PV | 2-241-241 | 2015-08-11 | 2015-08-18 | #VALUE! | 0 | #VALUE! | 2015-08-20 | 2016-01-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2019-08-21 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval |  | Private | N
NSTAR | Woburn | 2087191 | 1801 | 29 | PV | 211-H2 | 2015-08-11 | 2015-08-18 | #VALUE! | 0 | #VALUE! | 2015-08-18 | 2015-10-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2017-01-05 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online |  | PRIVATE | N
NSTAR | Cambridge | 2087199 | 2138 | 171.1 | PV | 828-1105 | 2015-08-11 | 2015-08-18 | #VALUE! | 0 | #VALUE! | 2015-08-20 | 2015-08-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-27 | 2015-08-26 | 2016-03-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-26 | Online |  | Private
NSTAR | Brewster | 2087387 | 2631 | 111 | PV | 4-95A-597 | 2015-08-14 | 2015-08-15 | #VALUE! | 0 | #VALUE! | 2015-08-21 | 2015-12-15 | #VALUE! | 53 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acusnet | 2088074 | 2743 | 4000 | PV | 2-241-238 | 2015-08-19 | 2015-08-20 | #VALUE! | 0 | #VALUE! | 2015-08-25 | 2015-09-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Roxbury | 2088902 | 2120 | 75 | Natural Gas | 106-H8 | 2015-08-19 | 2015-08-20 | #VALUE! | 0 | #VALUE! | 2015-08-25 | 2015-09-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online |  | Private
NSTAR | Boston | 2088913 | 2118 | 75 | Natural Gas | 106-H4 | 2015-08-19 | 2015-08-21 | #VALUE! | 0 | #VALUE! | 2015-08-25 | 2015-12-15 | #VALUE! | 72 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-21 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online |  | Private
NSTAR | Waltham | 2088991 | 2451 | 175 | PV | 282-H6 | 2015-08-20 | 2015-08-21 | #VALUE! | 98 | #VALUE! | 2015-08-25 | 2016-04-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-17 | Online |  | Private
NSTAR | Boston | 2089121 | 2115 | 128 | PV | 492-1N14S | 2015-08-20 | 2015-08-20 | 0 | 0 | 0 | 2015-08-20 | 2015-08-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-10 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online |  | Private
NSTAR | Waltham | 2089144 | 2451 | 96 | PV | 450-H8 | 2015-08-21 | 2015-08-24 | #VALUE! | 0 | #VALUE! | 2015-08-26 | 2015-09-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-23 |  | 2016-03-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-05 | Online |  | Private
NSTAR | Mashpee | 2089388 | 2649 | 90 | PV | 4-88-455 | 2015-08-24 | 2015-08-26 | #VALUE! | 0 | #VALUE! | 2015-08-28 | 2015-10-26 | #VALUE! | 11 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Dover | 2089416 | 2030 | 27.75 | PV | 456-H3 | 2015-07-31 | 2015-08-11 | #VALUE! |  | #VALUE! | 2015-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-06-15 | [6 empty] | 0 |  | 0 |  |  | 2016-09-15 | Online
NSTAR | Carlisle | 2089685 | 1741 | 216 | PV | 512-1399H1 | 2015-08-24 | 2015-08-27 | #VALUE! | 0 | #VALUE! | 2015-08-31 | 2015-09-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-24 |  | 2016-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Roxbury | 2089776 | 2119 | 33 | PV | 106-H5 | 2015-08-26 | 2015-08-27 | #VALUE! | 44 | #VALUE! | 2015-08-31 | 2015-12-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Arlington | 2090065 | 2476 | 118 | PV | 320-H7 | 2015-08-26 | 2015-08-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2090094 | 2360 | 4999 | PV | 3-012-012 | 2015-08-26 | 2015-08-28 | #VALUE! | 0 | #VALUE! | 2015-08-31 | 2015-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-03 |  | 2016-11-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2090242 | 2744 | 843 | PV | 2-7-95 | 2015-08-26 | 2015-08-28 | #VALUE! | 0 | #VALUE! | 2015-09-02 | 2015-10-27 | #VALUE! | 20 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-04-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-04 | Online |  | Private
NSTAR | Rochester | 2090360 | 2770 | 1000 | PV | 3-702-702 | 2015-08-27 | 2015-08-28 | #VALUE! | 0 | #VALUE! | 2015-08-31 | 2015-11-23 | #VALUE! | 53 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-22 |  | 2016-04-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-14 | Customer Cost |  | Private
NSTAR | Chatham | 2090556 | 2650 | 296 | PV | 4-95A-608 | 2015-08-28 | 2015-09-01 | #VALUE! | 0 | #VALUE! | 2015-09-02 |  | #VALUE! | 241 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-07 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-09-03 | Gov't
NSTAR | Acton | 2090728 | 1720 | 420 | PV | 416-H4 | 2015-08-14 | 2015-09-01 | #VALUE! | 0 | #VALUE! | 2015-09-01 | 2015-09-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent |  | Private
NSTAR | Dartmouth | 2090751 | 2748 | 18 | PV | 2-524-524 | 2015-09-01 | 2015-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Sandwich | 2091380 | 2563 | 1476 | PV | 4-81A-439 | 2015-09-02 | 2015-09-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-08 | Online | 2015-09-28 | Private
NSTAR | Acusnet | 2092115 | 2743 | 2000 | PV | 2-241-238 | 2015-09-02 | 2015-09-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-09-28 | Private
NSTAR | Acusnet | 2092123 | 2743 | 2000 | PV | 2-241-238 | 2015-09-03 | 2015-09-04 | #VALUE! | 0 | #VALUE! | 2015-09-11 | 2015-11-09 | #VALUE! | 29 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-09-29 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2092354 | 2770 | 2000 | PV | 3-702-702 | 2015-09-03 | 2015-09-04 | #VALUE! | 0 | #VALUE! | 2015-09-11 | 2016-04-06 | #VALUE! | 130 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2092534 | 2770 | 1000 | PV | 3-702-702 | 2015-09-08 | 2015-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-17 | Private
NSTAR | Wareham | 2092960 | 2571 | 5500 | PV | 3-82-82 | 2015-09-08 | 2015-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online | 2016-04-25 | Private
NSTAR | Wareham | 2093002 | 2571 | 4000 | PV | 3-83-83 | 2015-09-08 | 2015-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Canton | 2093030 | 2021 | 990 | PV | 470-H7 | 2015-09-09 | 2015-09-10 | #VALUE! | 0 | #VALUE! | 2015-09-14 | 2015-10-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-17 | 2016-03-09 | 2016-05-27 | No | EXP | 30 | 2016-02-24 |  | #VALUE! |  | #VALUE! |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Holliston | 2093131 | 1746 | 990 | PV | 65-H2 | 2015-09-09 | 2015-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online |  | Private
NSTAR | Fairhaven | 2093189 | 2719 | 2000 | PV | 2-221-221 | 2015-09-09 | 2015-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-05 | Online |  | Private
NSTAR | Carver | 2093250 | 2330 | 990 | PV | 3-10-929 | 2015-09-09 | 2015-09-10 | #VALUE! | 0 | #VALUE! | 2015-09-14 | 2016-03-19 | #VALUE! | 37 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 |  | 2016-04-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-01-23 | Online |  | Private
NSTAR | Somerville | 2093280 | 2145 | 999 | PV | 250-H3 | 2015-09-10 | 2015-09-11 | #VALUE! | 0 | #VALUE! | 2015-09-10 |  | #VALUE! |  | #VALUE! |  |  | 0 | 0 | 0 | 2015-09-15 | 2015-10-16 | #VALUE! | 2 | #VALUE! | 2016-02-19 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2016-02-04 | 2016-02-04 | [6 empty] | 0 |  | 0 |  |  | 2017-05-02 | Online |  | Private | N
NSTAR | Acton | 2093456 | 1720 | 750 | PV | 416-H1 | 2015-09-10 | 2015-09-14 | #VALUE! | 0 | #VALUE! | 2015-09-15 | 2016-01-26 | #VALUE! | 54 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-07-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2093470 | 2746 | 990 | PV | 2-38-38 | 2015-09-10 | 2015-09-11 | #VALUE! | 0 | #VALUE! | 2015-09-15 | 2015-10-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-28 | 2017-05-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Milton | 2093526 | 2186 | 512 | PV | 496-H1XY | 2015-09-11 | 2015-09-15 | #VALUE! | 0 | #VALUE! | 2015-09-18 | 2015-10-26 | #VALUE! | 205 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-10-27 | Private
NSTAR | Waltham | 2093779 | 2451 | 1000 | PV | 450-H3 | 2015-09-14 | 2015-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Acton | 2093910 | 1720 | 1940 | PV | 416-H1 | 2015-09-14 | 2015-09-15 | #VALUE! | 0 | #VALUE! | 2015-09-18 | 2015-10-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Falmouth | 2093955 | 2540 | 19 | PV | 4-76-436 | 2015-09-14 | 2015-09-15 | #VALUE! | 0 | #VALUE! | 2015-09-16 | 2015-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 | 2015-10-30 | 2016-01-20 | TBD | EXP | 30 | 2016-01-04 | 2016-01-04 | 0 |  | 0 |  | 2016-01-26 |  | Withdrawn |  | Private
NSTAR | Dennis | 2094068 | 2660 | 300 | PV | 4-92B-92B | 2015-09-14 | 2015-09-15 | #VALUE! | 0 | #VALUE! | 2015-09-18 | 2015-10-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 | 2016-06-06 | 2016-11-18 | No | EXP | 30 | 2016-06-06 |  | #VALUE! |  | #VALUE! |  | 2016-06-06 | 2016-01-26 | Online |  | Private
NSTAR | Lexington | 2094085 | 2421 | 815 | PV | 320-H2 | 2015-08-20 | 2015-08-26 | #VALUE! |  | #VALUE! | 2015-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-17 | 2015-11-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-08 | Online
NSTAR | Waltham | 2094179 | 2451 | 1200 | Natural Gas | 373-1358 | 2015-09-16 | 2015-09-22 | #VALUE! | 0 | #VALUE! | 2015-09-24 | 2015-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2016-02-25 | 2016-03-30 | TBD | EXP | 30 | 2016-02-25 | 2016-02-25 | 0 |  | 0 |  |  | 2016-04-14 | Online |  | Private
NSTAR | Harwich | 2094563 | 2671 | 72 | PV | 4-85-592 | 2015-09-16 | 2015-09-17 | #VALUE! | 0 | #VALUE! | 2015-09-22 | 2015-10-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-15 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Somerville | 2094631 | 2145 | 24 | PV | 250-H4XY | 2015-09-16 | 2015-09-22 | #VALUE! | 0 | #VALUE! | 2015-09-24 | 2015-10-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-14 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-30 | Online |  | Private
NSTAR | Natick | 2094705 | 1760 | 75 | PV | 433-H11 | 2015-09-16 | 2015-09-21 | #VALUE! | 0 | #VALUE! | 2015-09-23 | 2015-10-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-06 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online |  | Private
NSTAR | Burlington | 2094742 | 1803 | 100 | PV | 211-H13 | 2015-09-17 | 2015-09-21 | #VALUE! | 0 | #VALUE! | 2015-09-23 | 2016-01-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-04-07 | 2016-06-24 | No | EXP | 30 | 2016-05-18 |  | #VALUE! |  | #VALUE! |  | 2015-10-14 |  | Awaiting Completion Docs |  | Private | N
NSTAR | Monument Beach | 2094911 | 2553 | 496 | PV | 4-86-408 | 2015-09-22 | 2015-09-23 | #VALUE! | 0 | #VALUE! | 2015-09-23 | 2016-04-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-09 | 2016-02-09 | 2016-05-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-30 | Online |  | Private
NSTAR | Mashpee | 2095832 | 2649 | 264 | PV | 4-88-455 | 2015-09-22 | 2015-09-23 | #VALUE! | 0 | #VALUE! | 2015-09-28 | 2015-10-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2015-12-02 | 2016-01-29 | TBD | EXP | 30 | 2015-12-30 | 2015-12-30 | 0 |  | 0 | [5 empty] | Private
NSTAR | Brookline | 2095914 | 2467 | 32 | PV | 496-H4 | 2015-09-24 | 2015-09-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage |  | Private
NSTAR | Woburn | 2096036 | 1801 | 499.8 | PV | 375-H12 | 2015-09-04 | 2015-09-09 | #VALUE! |  | #VALUE! | 2015-09-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-25 | 2015-11-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-10 | Online |  | PRIVATE
NSTAR | Plymouth | 2096227 | 2360 | 4000 | PV | 3-88-924 | 2015-09-25 | 2015-09-26 | #VALUE! | 0 | #VALUE! | 2015-09-30 | 2016-04-28 | #VALUE! | 130 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Holliston | 2096409 | 1746 | 476 | PV | 274-H1 | 2015-09-25 | 2015-09-28 | #VALUE! | 0 | #VALUE! | 2015-09-30 | 2015-11-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-01-21 | 2016-06-30 | No | EXP | 30 | 2016-04-07 | 2016-04-07 | 0 |  | 0 |  | 2016-06-24 |  | Withdrawn |  | Private
NSTAR | Mashpee | 2096431 | 2649 | 371 | PV | 4-77A-454 | 2015-09-25 | 2015-09-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Bellingham | 2096445 | 2019 | 984 | PV | 65-H4 | 2015-09-28 | 2015-09-30 | #VALUE! | 2 | #VALUE! | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-12 | 2016-10-11 | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hopkinton | 2096675 | 1748 | 170 | PV | 126-H1 | 2015-09-28 | 2015-09-30 | #VALUE! | 0 | #VALUE! | 2015-10-05 | 2015-10-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-05 |  | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online |  | Private
NSTAR | New Bedford | 2096734 | 2746 | 157 | PV | 2-87-135 | 2015-10-01 | 2015-10-02 | #VALUE! | 8 | #VALUE! | 2015-10-16 | 2015-11-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-05 | 2016-10-09 |  | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 | 2016-04-29 | Online |  | Private | Y
NSTAR | Natick | 2097431 | 1760 | 207 | PV | 433-H7 | 2015-10-01 | 2015-10-02 | #VALUE! | 0 | #VALUE! | 2015-10-05 | 2015-10-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Westport | 2097455 | 2790 | 32.85 | PV | 2-523-523 | 2015-09-22 | 2015-09-24 | #VALUE! |  | #VALUE! | 2015-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-10-29 | 2015-11-30 | [6 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online |  | Private | Y
NSTAR | New Bedford | 2097474 | 2746 | 360 | PV | 2-134-134 | 2015-10-02 | 2015-10-05 | #VALUE! | 0 | #VALUE! | 2015-10-07 | 2015-10-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-10-30 | 2016-05-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-03 | Online |  | Private
NSTAR | Somerville | 2097809 | 2144 | 20 | PV | 227-51H2 | 2015-10-05 | 2015-10-06 | #VALUE! | 0 | #VALUE! | 2015-10-12 | 2016-03-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Bourne | 2098326 | 2532 | 4800 | Natural Gas | 4-81A-81A | 2015-10-05 | 2015-10-09 | #VALUE! | 0 | #VALUE! | 2015-10-14 | 2015-10-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2015-11-11 | 2016-06-15 | TBD | EXP | 30 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Mattapoisett | 2098384 | 2739 | 25 | WIND | 2-301-301 | 2015-10-05 | 2015-10-09 | #VALUE! | 73 | #VALUE! | 2015-10-14 | 2016-06-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Woburn | 2098750 | 1801 | 252 | PV | 211-H5 | 2015-10-06 | 2015-10-08 | #VALUE! | 0 | #VALUE! | 2015-10-12 | 2016-02-18 | #VALUE! | 18 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-06 | 2016-05-13 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-12 | Online |  | Private
NSTAR | Dedham | 2099070 | 2026 | 765 | PV | 20-H2 | 2015-10-07 | 2015-10-08 | #VALUE! | 0 | #VALUE! | 2015-10-14 | 2016-05-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-04 | Online |  | Private
NSTAR | Plymouth | 2099348 | 2360 | 420 | PV | 3-12-12 | 2015-10-08 | 2015-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plympton | 2099482 | 2367 | 880 | PV | 3-51-901 | 2015-10-08 | 2015-10-21 | #VALUE! | 0 | #VALUE! | 2015-10-27 | 2015-11-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-01 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sudbury | 2099532 | 1776 | 42 | PV | 342-H2 | 2015-10-08 | 2015-10-13 | #VALUE! | 0 | #VALUE! | 2015-10-14 | 2015-11-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Woburn | 2099592 | 1801 | 84 | PV | 211-01 | 2015-10-08 | 2015-10-13 | #VALUE! | 0 | #VALUE! | 2015-10-14 | 2016-01-25 | #VALUE! | 57 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-14 |  | 2016-05-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Burlington | 2099699 | 1803 | 360 | PV | 391-H15 | 2015-10-08 | 2015-10-14 | #VALUE! | 1 | #VALUE! | 2015-10-16 | 2016-08-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2099704 | 2360 | 996 | PV | 31313 | 2015-10-13 | 2015-10-14 | #VALUE! | 14 | #VALUE! | 2015-10-16 | 2016-02-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
NSTAR | Woburn | 2100110 | 1801 | 360 | PV | 258-1394H2 | 2015-10-13 | 2015-10-14 | #VALUE! | 14 | #VALUE! | 2015-10-16 | 2016-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Woburn | 2100120 | 1801 | 480 | PV | 258-1394H2 | 2015-10-14 | 2015-10-15 | #VALUE! | 0 | #VALUE! | 2015-10-19 | 2016-01-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-13 |  | 2016-05-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Woburn | 2100528 | 1801 | 40 | PV | 258-1394H4 | 2015-10-16 | 2015-10-19 | #VALUE! | 0 | #VALUE! | 2015-10-21 | 2016-01-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Bourne | 2101008 | 2532 | 468 | PV | 4-86-402 | 2015-10-16 | 2015-10-19 | #VALUE! | 0 | #VALUE! | 2015-10-20 | 2015-10-20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2017-04-03 |  | 2017-04-11 | Online |  | Private
NSTAR | Westport | 2101010 | 2790 | 19 | PV | 2-523-523 | 2015-10-16 | 2015-10-19 | #VALUE! | 0 | #VALUE! | 2015-10-21 | 2015-11-23 | #VALUE! | 9 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-11 | 2016-01-11 | 2016-04-15 | No | EXP | 30 | 2016-03-11 |  | #VALUE! |  | #VALUE! |  |  | 2016-12-07 | Online |  | Private | N
NSTAR | Waltham | 2101013 | 2453 | 126 | PV | 467-H8 | 2015-10-20 | 2015-10-21 | #VALUE! | 0 | #VALUE! | 2015-10-27 | 2016-03-31 | #VALUE! | 102 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-16 | Online |  | PRIVATE
NSTAR | Lincoln | 2102041 | 1773 | 20 | PV | 320-H1 | 2015-10-21 | 2015-10-22 | #VALUE! | 0 | #VALUE! | 2015-10-23 | 2015-10-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Dartmouth | 2102045 | 2747 | 98 | PV | 2-543-543 | 2015-10-23 | 2015-10-24 | #VALUE! | 0 | #VALUE! | 2015-11-03 | 2016-06-27 | #VALUE! | 157 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acton | 2102432 | 1720 | 830 | PV | 416-H1 | 2015-10-23 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-10-27 | 2016-08-01 | #VALUE! | 26 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 |  | 2016-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  | Private
NSTAR | Wareham | 2102456 | 2576 | 600 | PV | 3-85-85 | 2015-10-23 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-10-28 | 2016-01-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 | 2016-03-08 | 2017-01-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | New Bedford | 2102526 | 2745 | 928 | PV | 2-88-88 | 2015-10-23 | 2015-10-26 | #VALUE! | 0 | #VALUE! | 2015-10-28 | 2016-02-10 | #VALUE! | 57 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Chatham | 2102528 | 2650 | 88 | PV | 4-95A-608 | 2015-10-23 | 2015-10-24 | #VALUE! | 0 | #VALUE! | 2015-10-27 | 2016-04-19 | #VALUE! | 112 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Assonett | 2102530 | 2702 | 1992 | PV | 2-605-605 | 2015-10-23 | 2015-10-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Falmouth | 2102531 | 2536 | 48 | PV | 4-98A-98A | 2015-10-26 | 2015-10-29 | #VALUE! | 0 | #VALUE! | 2015-10-29 | 2016-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-14 | Online |  | Private
NSTAR | Pocasset | 2102746 | 2559 | 27 | PV | 4-81A-81A | 2015-10-27 | 2015-10-29 | #VALUE! | 0 | #VALUE! | 2015-11-02 | 2015-12-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-15 | 2016-02-10 | 2016-07-15 | TBD | EXP | 30 | 2016-06-09 | 2016-06-09 | 0 |  | 0 |  |  | 2016-07-22 | Online |  | Private
NSTAR | Canton | 2102821 | 2021 | 324.6 | PV | 470-H8 | 2015-10-09 | 2016-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-25 | 2016-05-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online |  | PRIVATE
NSTAR | Jamaica Plain | 2103067 | 2130 | 17 | PV | 554-79H1 | 2015-10-28 | 2015-10-29 | #VALUE! | 0 | #VALUE! | 2015-11-04 | 2016-04-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Plymouth | 2103303 | 2360 | 5976 | PV | 3-73-73 | 2015-10-28 | 2015-10-29 | #VALUE! | 0 | #VALUE! | 2015-11-04 | 2016-04-05 | #VALUE! | 15 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Assonett | 2103346 | 2702 | 984 | PV | 2-605-605 | 2015-10-29 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-11-03 |  | #VALUE! | 199 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-04 | Private
NSTAR | West Tisbury | 2103349 | 2575 | 233.1 | PV | 4-97-220 | 2015-10-15 | 2015-10-23 | #VALUE! |  | #VALUE! | 2015-10-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-12-07 | [7 empty] | 0 |  | 0 | 2017-03-23 | 2017-03-23 | 2017-04-10 | Online |  | PRIVATE
NSTAR | Rochester | 2103573 | 2770 | 2000 | PV | 3-703-703 | 2015-10-29 | 2015-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-04 | Private
NSTAR | Rochester | 2103577 | 2770 | 3000 | PV | 3-702-702 | 2015-11-03 | 2015-11-03 | 0 | 0 | 0 | 2015-11-09 | 2015-11-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-31 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2104785 | 1760 | 36 | PV | 433-H11 | 2015-11-03 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-11-09 | 2015-11-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-25 | Online |  | Private
NSTAR | Provincetown | 2104938 | 2657 | 168 | PV | 4-96-674 | 2015-11-03 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-11-09 | 2016-04-18 | #VALUE! | 46 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage |  | Private
NSTAR | Somerville | 2104944 | 2143 | 996 | PV | 387-148H2 | 2015-11-03 | 2015-11-04 | #VALUE! | 0 | #VALUE! | 2015-11-09 | 2015-11-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | Provincetown | 2104946 | 2657 | 124 | PV | 4-96-674 | 2015-11-05 | 2015-11-06 | #VALUE! | 0 | #VALUE! | 2015-11-11 | 2015-12-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 | 2015-12-07 | 2016-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-21 | Online |  | Private
NSTAR | Hyannis | 2105424 | 2601 | 96 | PV | 4-84A-520 | 2015-11-05 | 2015-11-06 | #VALUE! | 0 | #VALUE! | 2015-11-11 | 2015-11-27 | #VALUE! | 5 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-04 | 2016-02-12 | 2016-03-31 | TBD | EXP | 30 | 2016-03-31 | 2016-03-31 | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private
NSTAR | Provincetown | 2105431 | 2657 | 100 | PV | 4-96-676 | 2015-11-05 | 2015-11-06 | #VALUE! | 0 | #VALUE! | 2015-11-11 | 2016-02-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-14 |  | 2016-06-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Canton | 2105434 | 2021 | 630 | PV | 269-1320H1 | 2015-11-05 | 2015-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | South Boston | 2105436 | 2210 | 2280 | PV | 106-H1 | 2015-11-10 | 2015-11-11 | #VALUE! | 0 | #VALUE! | 2015-11-18 | 2016-04-19 | #VALUE! | 24 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online |  | Private
NSTAR | Assonett | 2106271 | 2702 | 1992 | PV | 2-605-605 | 2015-11-12 | 2015-11-17 | #VALUE! | 0 | #VALUE! | 2015-11-18 | 2015-12-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 4 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2106576 | 2360 | 21.07 | PV | 3-14-931 | 2015-10-27 | 2015-10-28 | #VALUE! |  | #VALUE! | 2015-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-01-29 | [6 empty] | 0 |  | 0 |  |  | 2016-03-10 | Online
NSTAR | Carver | 2106584 | 2330 | 28 | PV | 3-10-929 | 2015-11-12 | 2015-11-17 | #VALUE! | 0 | #VALUE! | 2015-11-18 | 2015-12-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-09 |  | 2016-06-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online |  | Private | N
NSTAR | Woburn | 2106588 | 1801 | 85 | PV | 375-H3 | 2015-11-13 | 2015-11-17 | #VALUE! | 0 | #VALUE! | 2015-11-18 | 2016-03-25 | #VALUE! | 34 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-27 |  | 2016-06-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Norfolk | 2106809 | 2056 | 186.5 | PV | 146-H3 | 2015-11-17 | 2015-11-19 | #VALUE! | 0 | #VALUE! | 2015-11-23 | 2015-12-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-24 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-14 | Online |  | Private
NSTAR | Westport | 2107466 | 2790 | 36 | PV | 2-523-523 | 2015-11-17 | 2015-11-19 | #VALUE! | 0 | #VALUE! | 2015-11-23 | 2015-11-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online |  | Private
NSTAR | Dartmouth | 2107468 | 2747 | 72 | PV | 2-543-543 | 2015-11-17 | 2015-11-19 | #VALUE! | 0 | #VALUE! | 2015-11-23 | 2015-12-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online |  | Gov't
NSTAR | Hopkinton | 2107469 | 1748 | 87 | PV | 65-H7 | 2015-11-18 | 2015-11-19 | #VALUE! | 0 | #VALUE! | 2015-11-20 |  | #VALUE! | 187 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-23 | Private
NSTAR | Carver | 2107748 | 2330 | 5966 | PV & Battery | 3-83-83 | 2015-11-19 | 2015-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online | 2015-11-25 | Private
NSTAR | East Freetown | 2108032 | 2717 | 4000 | PV | 2-102-102 | 2015-11-23 | 2015-11-25 | #VALUE! | 0 | #VALUE! | 2015-11-26 | 2015-12-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-23 | 2016-06-24 | No | EXP | 30 | 2016-04-08 | 2016-04-08 | 0 |  | 0 |  |  |  | Meter |  | Private | N
NSTAR | Wellfleet | 2108544 | 2663 | 50 | PV | 4-94B-653 | 2015-11-23 | 2015-11-25 | #VALUE! | 0 | #VALUE! | 2015-11-26 | 2015-11-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-03 | 2016-06-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online |  | Gov't
NSTAR | Truro | 2108546 | 2652 | 30 | PV | 4-96-674 | 2015-11-25 | 2015-11-26 | #VALUE! | 0 | #VALUE! | 2015-12-03 | 2015-12-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 | 2017-11-28 | 2016-07-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-10 | Online |  | Private
NSTAR | Hyannis | 2108876 | 2601 | 120 | PV | 4-84B-524 | 2015-12-03 | 2015-12-04 | #VALUE! | 18 | #VALUE! | 2015-12-08 | 2016-01-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Plymouth | 2108966 | 2360 | 23.75 | PV | 3-89-926 | 2015-11-24 | 2015-11-24 | 0 |  | 0 | 2015-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-07-26 | Online
NSTAR | West Tisbury | 2109230 | 2575 | 213.2 | PV | 4-97-220 | 2015-11-17 | 2015-11-30 | #VALUE! |  | #VALUE! | 2015-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-11-30 | Online
NSTAR | Cambridge | 2109233 | 2138 | 26.6 | PV | 821-05 | 2015-11-10 | 2015-11-10 | 0 |  | 0 | 2015-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-11 | 2016-01-19 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Milton | 2109234 | 2186 | 32.4 | PV | 496-H7 | 2015-11-06 | 2015-11-30 | #VALUE! |  | #VALUE! | 2015-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-06-10 | Online
NSTAR | Plymouth | 2110218 | 2360 | 394.8 | PV | 3-14-931 | 2015-11-17 | 2015-11-17 | 0 |  | 0 | 2016-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-10 | [6 empty] | 0 |  | 0 |  |  | 2016-11-08 | Online |  | PRIVATE
NSTAR | Hyde Park | 2110822 | 2136 | 1200 | PV | 344-07 | 2015-12-03 | 2015-12-04 | #VALUE! | 0 | #VALUE! | 2015-12-08 | 2016-07-18 | #VALUE! | 86 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2110823 | 2790 | 1000 | PV | 2-523-523 | 2015-12-07 | 2015-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2015-12-16 | Private
NSTAR | East Freetown | 2113074 | 2717 | 2000 | PV | 2-102-604 | 2015-12-09 | 2015-12-11 | #VALUE! |  | #VALUE! | 2015-12-14 | 2016-01-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2018-12-12 | 2018-12-13 | 2018-12-13 | Online |  | Private
NSTAR | Sudbury | 2114162 | 1776 | 15.5 | PV | 342-H7 | 2015-10-19 | 2015-10-20 | #VALUE! |  | #VALUE! | 2015-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-15 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Acton | 2114164 | 1720 | 17 | PV | 416-H8 | 2015-12-09 | 2015-12-11 | #VALUE! | 0 | #VALUE! | 2015-12-14 | 2016-01-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Ashland | 2114171 | 1721 | 17 | PV | 519-175H1 | 2015-12-14 | 2015-12-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2114406 | 2330 | 17.5 | PV | 3-83-950 | 2015-11-19 | 2016-01-05 | #VALUE! |  | #VALUE! | 2016-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online |  | PRIVATE
NSTAR | Carver | 2114902 | 2330 | 499 | PV | 3-10-929 | 2015-12-14 | 2015-12-22 | #VALUE! | 0 | #VALUE! | 2015-12-23 | 2015-12-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-10 | 2016-07-04 | 2016-07-21 | TBD | EXP | 30 | 2016-07-06 | 2016-07-06 | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Plymouth | 2114928 | 2360 | 57 | PV | 3-89-922 | 2015-12-14 | 2015-12-15 | #VALUE! | 0 | #VALUE! | 2015-12-16 | 2016-04-26 | #VALUE! | 74 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-07-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Rochester | 2114929 | 2770 | 392 | PV | 3-702-702 | 2015-12-15 | 2015-12-15 | 0 | 1 | 0 | 2015-12-18 | 2016-01-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 | 2016-05-25 | 2016-07-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
NSTAR | Holliston | 2115036 | 1746 | 21 | PV | 274-H1 | 2015-12-16 | 2015-12-18 | #VALUE! | 0 | #VALUE! | 2015-12-22 | 2016-01-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-20 |  | 2016-07-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online |  | Private
NSTAR | Dover | 2115395 | 2030 | 20 | PV | 456-H5 | 2015-12-16 | 2015-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study |  | Private | N
NSTAR | Canton | 2115399 | 2021 | 432 | PV | 470-H11 | 2015-12-17 | 2015-12-18 | #VALUE! | 21 | #VALUE! | 2015-12-22 | 2016-02-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-05-04 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-19 | Online |  | Private
NSTAR | Boston | 2115948 | 2110 | 75 | Natural Gas | 12-1N82N | 2015-12-17 | 2015-12-17 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2016-02-01 | Private
NSTAR | Cambridge | 2115956 | 2139 | 1000 | Natural Gas | 875-1N35B | 2015-12-18 | 2015-12-19 | #VALUE! | 0 | #VALUE! | 2015-12-24 | 2016-01-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Canton | 2116306 | 2021 | 396 | PV | 470-H4 | 2015-12-18 | 2015-12-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study |  | Private
NSTAR | Carver | 2116312 | 2330 | 2000 | PV | 3-10-929 | 2015-12-18 | 2015-12-22 | #VALUE! | 0 | #VALUE! | 2015-12-30 |  | #VALUE! | 155 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2019-02-28 | Online | 2016-01-11 | Private
NSTAR | Wareham | 2116332 | 2538 | 7450 | PV | 3-84-961 | 2015-12-22 | 2016-01-15 | #VALUE! | 0 | #VALUE! | 2016-01-15 | 2016-04-16 | #VALUE! | 54 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Brewster | 2116973 | 2631 | 82 | PV | 4-89A-553 | 2015-12-22 | 2015-12-23 | #VALUE! | 0 | #VALUE! | 2015-12-29 | 2015-12-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 |  | 2016-07-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-21 | Online |  | Private
NSTAR | Lexington | 2116975 | 2421 | 20.35 | PV | 320-H5XY | 2015-12-11 | 2015-12-15 | #VALUE! |  | #VALUE! | 2015-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-27 | 2016-04-19 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online |  | PRIVATE
NSTAR | Acusnet | 2116976 | 2743 | 16 | PV | 2-241-237 | 2015-12-23 | 2015-12-24 | #VALUE! | 0 | #VALUE! | 2016-01-05 | 2016-02-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | North Dartmouth | 2117201 | 2747 | 19.3 | PV | 2-107-107 | 2015-12-11 | 2015-12-15 | #VALUE! |  | #VALUE! | 2015-12-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2016-01-03 | Online |  | PRIVATE
NSTAR | Duxbury | 2117204 | 2332 | 360 | PV | 3-27-970 | 2015-12-23 | 2015-12-24 | #VALUE! | 0 | #VALUE! | 2016-01-05 | 2016-02-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-08-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Duxbury | 2117207 | 2332 | 480 | PV | 3-26-903 | 2015-12-24 | 2015-12-29 | #VALUE! | 13 | #VALUE! | 2016-01-05 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-08-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Kingston | 2117310 | 2364 | 600 | PV | 3-26-902 | 2015-12-29 | 2015-12-30 | #VALUE! | 2 | #VALUE! | 2016-01-05 | 2016-07-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-12-31 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-19 | Online |  | Private
NSTAR | Plymouth | 2117742 | 2360 | 21.4 | PV | 3-73-27J2 | 2015-12-09 | 2016-12-10 | #VALUE! |  | #VALUE! | 2016-01-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-12 | [6 empty] | 0 |  | 0 |  |  | 2016-03-17 | Online
NSTAR | Woburn | 2117752 | 1810 | 42.3 | PV | 211-H2 | 2015-12-01 | 2015-12-28 | #VALUE! |  | #VALUE! | 2016-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2117764 | 2030 | 1000 | PV | 456-H4 | 2015-12-30 | 2016-01-01 | #VALUE! | 0 | #VALUE! | 2016-01-06 | 2016-05-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-08-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Stoneham | 2119971 | 2180 | 16.95 | PV | 375H8 | 2016-12-17 | 2016-12-22 | #VALUE! |  | #VALUE! | 2016-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-06-27 | Online
NSTAR | New Bedford | 2119974 | 2746 | 280 | PV | 2-80-80 | 2016-01-05 | 2016-01-08 | #VALUE! | 5 | #VALUE! | 2016-01-11 | 2016-02-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-23 | 2016-03-28 | 2016-08-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online |  | Private
NSTAR | Natick | 2120155 | 1760 | 457 | PV | 240-H1 | 2016-01-05 | 2016-01-08 | #VALUE! | 0 | #VALUE! | 2016-01-11 | 2016-01-11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-21 |  | 2016-08-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-06 | Online |  | Gov't
NSTAR | Natick | 2120191 | 1760 | 24.8 | PV | 2302 | 2016-12-22 | 2016-12-26 | #VALUE! |  | #VALUE! | 2016-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-28 | 2016-01-28 | [6 empty] | 0 |  | 0
NSTAR | Natick | 2120194 | 1760 | 120 | PV | 23-H1 | 2016-01-06 | 2016-01-08 | #VALUE! | 0 | #VALUE! | 2016-01-11 | 2016-02-10 | #VALUE! | 19 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-11 | 2016-02-11 | 2016-08-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
NSTAR | Edgartown | 2120504 | 2539 | 36 | PV | 4-97-97 | 2016-01-11 | 2016-01-26 | #VALUE! | 0 | #VALUE! | 2016-01-26 | 2016-01-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2016-06-25 | TBD | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  | 2016-06-08 | Online |  | Private
NSTAR | Woburn | 2120505 | 1801 | 16.7 | PV | 375-H11 | 2015-11-05 | 2015-11-08 | #VALUE! |  | #VALUE! | 2016-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-23 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
NSTAR | Wareham | 2122405 | 2576 | 16.5 | PV | 3-86-966 | 2015-12-04 | 2016-01-07 | #VALUE! |  | #VALUE! | 2016-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-03-11 | Online
NSTAR | Sharon | 2122406 | 2067 | 17.5 | PV | 470-h12 | 2015-12-02 | 2016-01-07 | #VALUE! |  | #VALUE! | 2016-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-12 | 2016-03-23 | [6 empty] | 0 |  | 0 |  |  | 2016-04-29 | Online
NSTAR | Maynard | 2122407 | 1754 | 32.85 | PV | 416-H6 | 2016-12-21 | 2017-01-05 | #VALUE! |  | #VALUE! | 2017-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-10-21 | Online
NSTAR | Framingham | 2122694 | 1701 | 328.75 | CHP | 433-H1 | 2016-01-04 | 2016-03-16 | #VALUE! |  | #VALUE! | 2016-01-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-10-19 | [6 empty] | 0 |  | 0 |  |  | 2017-04-04 | Online |  | NO EXPORT
NSTAR | Plympton | 2122696 | 2367 | 24 | PV | 3-51-901 | 2016-01-13 | 2016-01-15 | #VALUE! | 0 | #VALUE! | 2016-01-18 | 2016-02-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-23 |  | 2016-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval |  | Private
NSTAR | Brewster | 2122697 | 2631 | 73.2 | PV | 4-89B-89B | 2016-01-05 | 2016-01-08 | #VALUE! |  | #VALUE! | 2016-01-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-17 | 2016-02-25 | [6 empty] | 0 |  | 0 |  |  | 2016-07-11 | Online
NSTAR | Acton | 2123114 | 2747 | 17.6 | PV | 416-H4 | 2016-01-04 | 2016-01-05 | #VALUE! |  | #VALUE! | 2016-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-03-03 | [6 empty] | 0 |  | 0 |  |  | 2016-03-24 | Online
NSTAR | Marshfield | 2123118 | 2050 | 19.35 | PV | 3-25-42J2 | 2016-12-23 | 2017-01-11 | #VALUE! |  | #VALUE! | 2017-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-10 | 2016-02-11 | [6 empty] | 0 |  | 0
NSTAR | Charlestown | 2123364 | 2129 | 30 | PV | 250-H5 | 2016-01-14 | 2016-01-19 | #VALUE! | 0 | #VALUE! | 2016-01-21 | 2016-01-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-01 | 2016-08-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Edgartown | 2123548 | 2539 | 36 | PV | 4-97-97 | 2016-01-14 | 2016-01-19 | #VALUE! | 0 | #VALUE! | 2016-01-21 | 2016-03-14 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-12 | 2016-08-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
NSTAR | Lexington | 2123559 | 2421 | 720 | PV | 2-1N11 | 2016-01-15 | 2016-01-19 | #VALUE! | 7 | #VALUE! | 2016-01-21 | 2016-03-21 | #VALUE! | 9 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-06 |  | 2016-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private | N
NSTAR | Marston Mills | 2123807 | 2648 | 19.3 | PV | 4-88-478 | 2012-01-11 | 2016-01-15 | #VALUE! |  | #VALUE! | 2016-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-10 | 2016-03-15 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2123809 | 1803 | 672 | PV | 391-H16 | 2016-01-20 | 2016-01-22 | #VALUE! | 0 | #VALUE! | 2016-01-27 |  | #VALUE! | 41 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-08-25 | No | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review
NSTAR | West Tisbury | 2124323 | 2575 | 33.9 | PV | 4-97-97 | 2016-01-13 | 2016-01-15 | #VALUE! |  | #VALUE! | 2016-01-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-03 | 2016-02-17 | [6 empty] | 0 |  | 0 |  |  | 2016-08-05 | Online
NSTAR | Cambridge | 2124635 | 2139 | 4400 | Natural Gas | 831-1110 | 2016-01-06 | 2016-01-07 | #VALUE! | 0 | #VALUE! | 2016-01-27 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-06-07 | 2017-08-11 |  | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2020-12-14 | Online |  | Private
NSTAR | Hatchville | 2124636 | 2536 | 1500 | PV | 4-98A-98A | 2016-01-21 | 2016-01-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-02-16 | Private
NSTAR | Dedham | 2124992 | 2026 | 1740 | PV | 344-1413H1 | 2016-01-21 | 2016-01-25 | #VALUE! | 0 | #VALUE! | 2016-01-27 | 2016-01-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-11-16 | Online |  | Private
NSTAR | Sagamore Beach | 2124995 | 2562 | 150 | PV | 3-89-925 | 2016-01-22 | 2016-01-26 | #VALUE! | 0 | #VALUE! | 2016-01-28 | 2016-03-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-02-17 | 2016-08-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online |  | Private | N
NSTAR | Chelsea | 2125197 | 2150 | 491 | PV | 488-H2 | 2016-01-22 | 2016-01-26 | #VALUE! | 0 | #VALUE! | 2016-01-28 | 2016-02-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-28 | Online |  | Private
NSTAR | Ashland | 2125198 | 1721 | 90 | PV | 519-175H1 | 2016-01-25 | 2016-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-10 | Online |  | Private
NSTAR | Holliston | 2125460 | 1746 | 432 | PV | 274-H1 | 2016-01-25 | 2016-01-26 | #VALUE! | 0 | #VALUE! | 2016-01-28 | 2016-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-30 |  | 2016-08-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Dorchester | 2125462 | 2124 | 300 | PV | 311-07 | 2016-01-27 | 2016-01-28 | #VALUE! | 0 | #VALUE! | 2016-02-01 | 2016-02-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 |  | 2016-09-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-19 | Online |  | Private
NSTAR | Bedford | 2125698 | 1730 | 16.7 | PV | 533-H8 | 2016-12-31 | 2017-01-06 | #VALUE! |  | #VALUE! | 2017-01-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-11 | 2016-03-14 | [6 empty] | 0 |  | 0 |  |  | 2016-09-06 | Online |  | PRIVATE
NSTAR | Falmouth | 2125878 | 2540 | 250 | PV | 10494/020 | 2016-01-28 | 2016-01-29 | #VALUE! | 0 | #VALUE! | 2016-02-01 | 2016-06-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-20 |  | 2016-09-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Needham | 2126109 | 2494 | 828 | PV | 148-H6 | 2016-01-29 | 2016-02-01 | #VALUE! | 0 | #VALUE! | 2016-02-04 | 2016-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 |  | 2016-09-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 |  |  | Private
NSTAR | Hopkinton | 2126313 | 1748 | 6 | PV | 65-H6 | 2016-02-01 | 2016-02-02 | #VALUE! | 0 | #VALUE! | 2016-02-05 | 2016-03-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 |  | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Woburn | 2126828 | 1801 | 168 | PV | 375-H3 | 2016-02-01 | 2016-02-02 | #VALUE! | 0 | #VALUE! | 2016-02-05 | 2016-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-16 | Online |  | Private
NSTAR | Hyde Park | 2126908 | 2136 | 168 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | #VALUE! | 0 | #VALUE! | 2016-02-09 | 2016-03-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2016-03-18 | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-02 | Online |  | Private
NSTAR | Hyde Park | 2126921 | 2136 | 192 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | #VALUE! | 0 | #VALUE! | 2016-02-09 | 2016-03-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online |  | Private
NSTAR | Hyde Park | 2126922 | 2136 | 288 | PV | 344-1411H2 | 2016-02-01 | 2016-02-02 | #VALUE! | 0 | #VALUE! | 2016-02-05 | 2016-05-19 | #VALUE! | 31 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-12 | 2017-04-18 |  | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online |  | Private
NSTAR | Woburn | 2126923 | 1801 | 726 | PV | 375-H14 | 2016-02-02 | 2016-02-02 | 0 | 0 | 0 | 2016-02-08 | 2016-05-06 | #VALUE! | 35 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Bedford | 2127134 | 1730 | 370 | PV | 322-1397H1 | 2016-02-02 | 2016-02-03 | #VALUE! | 0 | #VALUE! | 2016-02-09 | 2016-07-20 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Bourne | 2127227 | 2532 | 1000 | PV | 4-98A-98A | 2016-02-02 | 2016-02-03 | #VALUE! | 0 | #VALUE! | 2016-02-09 | 2016-04-04 | #VALUE! | 21 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 |  | 2016-09-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Burlington | 2127236 | 1803 | 170 | PV | 211-H13 | 2016-02-04 | 2016-02-05 | #VALUE! | 0 | #VALUE! | 2016-02-15 | 2016-07-11 | #VALUE! | 91 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Millis | 2127532 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127571 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127590 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127594 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127596 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127597 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Oak Bluffs | 2127808 | 2568 | 566.1 | PV | 4-75-75 | 2016-01-14 | 2016-01-20 | #VALUE! |  | #VALUE! | 2016-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-07 | [6 empty] | 0 |  | 0
NSTAR | Maynard | 2127819 | 1754 | 750 | PV | STA207 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | 2016-03-17 | 2016-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | West Roxbury | 2127824 | 2132 | 40 | PV | 468-01 | 2016-02-05 | 2016-02-08 | #VALUE! | 0 | #VALUE! | 2016-02-10 | 2016-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Falmouth | 2128032 | 2536 | 16.7 | PV | 4-98B-845 | 2016-02-09 | 2016-02-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-03-09 | Private
NSTAR | New Bedford | 2128034 | 2740 | 17.45 | PV | 2.3.96 | 2016-01-27 | 2016-02-01 | #VALUE! |  | #VALUE! | 2016-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-26 | 2016-03-07 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2128036 | 2332 | 20.25 | PV | 3-27-970 | 2016-01-27 | 2016-02-01 | #VALUE! |  | #VALUE! | 2016-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-11 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-13 | Online
NSTAR | Hyde Park | 2128422 | 2136 | 540 | PV | 344-1413H1 | 2016-02-09 | 2016-02-10 | #VALUE! | 0 | #VALUE! | 2016-02-12 | 2016-02-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 | 2016-06-06 | 2016-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dennisport | 2128423 | 2639 | 72 | PV | 4-92B-572 | 2016-02-10 | 2016-02-11 | #VALUE! | 0 | #VALUE! | 2016-02-15 | 2016-02-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-23 | Online |  | Private
NSTAR | Edgartown | 2128645 | 2539 | 72 | PV | 4-97-97 | 2016-02-11 | 2016-02-12 | #VALUE! | 0 | #VALUE! | 2016-02-18 | 2016-03-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 |  | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-22 | Online |  | Private
NSTAR | Canton | 2128797 | 2021 | 19 | PV | 470-H9 | 2016-02-11 | 2016-02-12 | #VALUE! | 0 | #VALUE! | 2016-02-18 | 2016-03-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-07-12 | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
NSTAR | Brighton | 2128801 | 2135 | 111 | PV | 329-H9 | 2016-02-11 | 2016-02-12 | #VALUE! | 0 | #VALUE! | 2016-02-18 |  | #VALUE! | 129 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-19 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online | 2016-02-18 | Private
NSTAR | Wareham | 2128802 | 2571 | 1992 | PV | 3-83-966 | 2016-02-12 | 2016-02-16 | #VALUE! | 0 | #VALUE! | 2016-02-23 | 2016-03-08 | #VALUE! | 6 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 |  | 2016-09-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2129051 | 2790 | 25 | PV | 2-532-532 | 2016-02-12 | 2016-02-17 | #VALUE! | 0 | #VALUE! | 2016-02-23 | 2016-05-26 | #VALUE! | 63 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-27 |  | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Gov't
NSTAR | Newton | 2129052 | 2459 | 104 | PV | 292-H8 | 2016-02-12 | 2016-02-13 | #VALUE! | 0 | #VALUE! | 2016-02-23 | 2016-05-27 | #VALUE! | 63 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2016-05-31 | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-09 | Online |  | Private
NSTAR | Acusnet | 2129053 | 2743 | 168 | PV | 2-231-231 | 2016-02-16 | 2016-02-17 | #VALUE! | 0 | #VALUE! | 2016-02-18 |  | #VALUE! | 74 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-09-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Plymouth | 2129459 | 2360 | 840 | PV | 3-12-12 | 2016-02-16 | 2016-02-17 | #VALUE! | 0 | #VALUE! | 2016-02-18 | 2016-05-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-08-02 | 2016-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2129461 | 2360 | 308 | PV | 3-71-71 | 2016-02-17 | 2016-02-18 | #VALUE! | 0 | #VALUE! | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-25 |  | 2016-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Arlington | 2129730 | 2476 | 115 | PV | 320-H7 | 2016-02-17 | 2016-02-19 | #VALUE! | 0 | #VALUE! | 2016-02-25 | 2016-04-26 | #VALUE! | 27 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-02 |  | 2016-09-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | New Bedford | 2129733 | 2745 | 496 | PV | 2-103-103 | 2016-02-18 | 2016-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-03-17 | Private
NSTAR | Marston Mills | 2129905 | 2648 | 4400 | PV | 4-88-478 | 2016-02-18 | 2016-02-19 | #VALUE! | 73 | #VALUE! | 2016-02-22 | 2016-03-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-15 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-10-03 | 2016-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-05-09 | Private
NSTAR | Framingham | 2129908 | 1701 | 1250 | PV | 203-1348H3 | 2016-02-01 | 2016-02-04 | #VALUE! |  | #VALUE! | 2016-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  | 2017-12-18 | Online
NSTAR | Watertown | 2130080 | 2472 | 216 | PV | 467-H6 | 2016-02-19 | 2016-02-22 | #VALUE! | 0 | #VALUE! | 2016-02-25 | 2016-03-01 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 | 2016-03-02 | 2016-09-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online |  | Private
NSTAR | Edgartown | 2130081 | 2539 | 170 | PV | 4-97-97 | 2016-02-22 | 2016-02-23 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-03-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-25 |  | 2016-09-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-26 | Online |  | Private
NSTAR | Canton | 2130083 | 2021 | 495.72 | PV | 470-H11 | 2016-01-12 | 2016-01-24 | #VALUE! |  | #VALUE! | 2016-02-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2016-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-07-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2130412 | 2719 | 16.4 | PV | 2-221-221 | 2016-02-02 | 2016-02-02 | 0 |  | 0 | 2016-02-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-07 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-07-01 | Online
NSTAR | Cambridge | 2130419 | 2140 | 36 | PV | 824-26 | 2016-02-23 | 2016-02-26 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-03-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-23 | Online |  | Private
NSTAR | Cambridge | 2130635 | 2139 | 27 | PV | 815-10 | 2016-02-23 | 2016-03-09 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-06-23 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-15 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost |  | Private
NSTAR | Woburn | 2130638 | 1801 | 50 | PV | 375-H4 | 2016-02-24 | 2016-04-08 | #VALUE! | 0 | #VALUE! | 2016-04-25 | 2016-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-07-25 | 2016-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-18 | Online |  | Private
NSTAR | Stoneham | 2130639 | 2180 | 30.3 | PV | 301-03 | 2016-02-05 | 2016-02-10 | #VALUE! |  | #VALUE! | 2016-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-06-01 | [6 empty] | 0 |  | 0 |  |  | 2016-12-14 | Online |  | PRIVATE
NSTAR | New Bedford | 2130836 | 2744 | 144 | PV | 2-69-69 | 2016-02-24 | 2016-02-29 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-03-23 | #VALUE! | 3 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hyannis | 2130872 | 2601 | 21.045 | PV | 4-63-521 | 2016-02-09 | 2016-02-12 | #VALUE! |  | #VALUE! | 2016-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-06 | 2016-04-27 | [6 empty] | 0 |  | 0 |  |  | 2016-07-28 | Online
NSTAR | Newton | 2130935 | 2468 | 36 | PV | 292-H12 | 2016-02-25 | 2016-02-26 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-06-06 | #VALUE! | 58 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-19 | Online |  | Private
NSTAR | Newton | 2130936 | 2461 | 57.5 | PV | 369-01 | 2016-02-08 | 2016-02-10 | #VALUE! |  | #VALUE! | 2016-02-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-14 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online
NSTAR | Plymouth | 2131133 | 2360 | 22.575 | PV | 3-71-71 | 2016-02-01 | 2016-02-01 | 0 |  | 0 | 2016-02-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-29 | 2016-03-30 | [6 empty] | 0 |  | 0 |  |  | 2016-10-26 | Online
NSTAR | Canton | 2131137 | 2021 | 496 | PV | 470-H8 | 2016-02-25 | 2016-02-29 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-03-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-18 |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Framingham | 2131138 | 1702 | 60 | WIND | 240-H4 | 2016-02-26 | 2016-02-29 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-10-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Rochester | 2131315 | 2770 | 15.2 | PV | 3-702-702 | 2016-02-04 | 2016-02-12 | #VALUE! |  | #VALUE! | 2016-02-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-20 | 2016-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2131316 | 2537 | 15.2 | PV | 4-81B-443 | 2016-02-08 | 2016-02-12 | #VALUE! |  | #VALUE! | 2016-02-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-28 | 2016-04-25 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online |  | PRIVATE
NSTAR | Somerville | 2131317 | 2145 | 56 | PV | 227-51H2 | 2016-02-29 |  | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-05-27 | #VALUE! | 48 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Watertown | 2131752 | 2472 | 125 | PV | 467-H2 | 2016-02-29 | 2016-03-02 | #VALUE! | 0 | #VALUE! | 2016-03-03 | 2016-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Newton | 2131753 | 2461 | 492 | PV | 292-H2 | 2016-03-01 | 2016-03-29 | #VALUE! | 0 | #VALUE! | 2016-03-29 | 2016-05-12 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 | 2016-05-12 | 2016-10-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
NSTAR | Plymouth | 2132061 | 2360 | 2000 | PV | 3-89-925 | 2016-03-02 | 2016-03-03 | #VALUE! | 0 | #VALUE! | 2016-03-09 | 2016-06-02 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 |  | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
NSTAR | Somerville | 2132326 | 2145 | 84 | PV | 227-52H3 | 2016-03-02 | 2016-03-03 | #VALUE! | 0 | #VALUE! | 2016-03-09 | 2016-05-14 | #VALUE! | 32 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-31 | 2016-06-03 | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-14 | Online |  | Private
NSTAR | Dennisport | 2132327 | 2639 | 65.7 | PV | 4-92B-583 | 2016-02-16 | 2016-02-18 | #VALUE! |  | #VALUE! | 2016-03-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-10-24 | [6 empty] | 0 |  | 0 |  |  | 2017-03-23 | Online |  | PRIVATE
NSTAR | Dennisport | 2132335 | 2639 | 40 | PV | 4-92B-583 | 2016-03-02 | 2016-03-03 | #VALUE! | 22 | #VALUE! | 2016-04-25 | 2016-05-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Falmouth | 2132336 | 2536 | 185 | PV | 4-92B-583 | 2016-03-03 | 2016-07-14 | #VALUE! | 0 | #VALUE! | 2016-07-14 | 2016-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-20 | 2016-10-24 | 2016-10-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2132937 | 2571 | 150 | PV | 3-84-84 | 2016-03-04 | 2016-03-08 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-03-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 | 2016-09-01 | 2016-10-11 | No | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  |  | ISA Received/Signed |  | Private
NSTAR | Carlisle | 2133263 | 1741 | 22 | PV | 533-H8 | 2016-03-04 | 2016-03-07 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-05-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-10-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Plymouth | 2133265 | 2360 | 66 | PV | 3-12-12 | 2016-03-07 | 2016-03-10 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-04-25 | #VALUE! | 24 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 | 2016-07-25 | 2016-10-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-03 | Online |  | Private
NSTAR | Bedford | 2133471 | 1730 | 312 | PV | 487-1376H1 | 2016-03-07 | 2016-03-09 | #VALUE! | 0 | #VALUE! | 2016-03-15 |  | #VALUE! | 18 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-12 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private
NSTAR | Buzzards Bay | 2133572 | 2532 | 66 | PV | 3-90-10J2 | 2016-03-07 | 2016-03-09 | #VALUE! | 0 | #VALUE! | 2016-03-15 | 2016-06-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-12 | 2016-12-19 | 2016-10-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
NSTAR | Arlington | 2133574 | 2476 | 40.32 | PV | 211-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-15 | 2016-07-12 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online |  | PRIVATE
NSTAR | Ashland | 2133577 | 1721 | 756.4 | PV | 274-H5 | 2016-02-07 | 2016-02-22 | #VALUE! |  | #VALUE! | 2016-03-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-16 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Brighton | 2133578 | 2135 | 48 | PV | 329-H7 | 2016-03-09 | 2016-03-11 | #VALUE! | 0 | #VALUE! | 2016-03-21 | 2016-04-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-13 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2133801 | 2461 | 47.52 | PV | 1701 | 2016-02-19 | 2016-04-07 | #VALUE! |  | #VALUE! | 2016-03-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | 2016-04-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2133803 | 2461 | 41.76 | PV | 467-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-23 | 2016-05-23 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2134025 | 2601 | 72 | PV | 4-84B-524 | 2016-03-09 | 2016-03-11 | #VALUE! | 0 | #VALUE! | 2016-03-21 | 2016-04-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | West Tisbury | 2134027 | 2575 | 95.4 | PV | 4-97-97 | 2016-02-17 | 2016-02-23 | #VALUE! |  | #VALUE! | 2016-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-05-10 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | PRIVATE | Y
NSTAR | Sudbury | 2134028 | 1776 | 112 | PV | 342-H2 | 2016-03-09 | 2016-03-10 | #VALUE! | 0 | #VALUE! | 2016-03-21 | 2016-04-06 | #VALUE! | 4 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2134029 | 2462 | 15.2 | PV | 292-H7 | 2016-02-24 | 2016-02-24 | 0 |  | 0 | 2016-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-04 | 2016-05-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online |  | PRIVATE
NSTAR | Newton | 2134030 | 2459 | 159 | PV | 292-H2 | 2016-03-10 | 2016-03-14 | #VALUE! | 0 | #VALUE! | 2016-03-17 | 2016-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-10-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | South Walpole | 2134146 | 2071 | - |  | TBD | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-17 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Sudbury | 2134239 | 1776 | 600 | PV | 342-H2 | 2016-03-10 | 2016-03-11 | #VALUE! | 0 | #VALUE! | 2016-03-21 | 2016-04-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Carlisle | 2134241 | 1741 | 39 | PV | 512-1399H1 | 2016-03-11 | 2016-03-12 | #VALUE! | 0 | #VALUE! | 2016-03-22 | 2016-06-16 | #VALUE! | 40 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-16 | Online |  | Private | Y
NSTAR | Woburn | 2134403 | 1801 | 200 | PV | 375-H6 | 2016-03-11 | 2016-03-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2016-03-21 | Private
NSTAR | Waltham | 2134404 | 2453 | 16.15 | PV | 3311 | 2016-03-10 | 2016-03-11 | #VALUE! |  | #VALUE! | 2016-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-08 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-08-02 | Online
NSTAR | Acton | 2134405 | 1720 | 990 | PV | 416-H4 | 2016-03-15 | 2016-04-20 | #VALUE! | 39 | #VALUE! | 2016-03-22 | 2016-05-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sandwich | 2135023 | 2537 | 984 | PV | 4-87A-471 | 2016-03-15 | 2016-03-16 | #VALUE! | 0 | #VALUE! | 2016-03-23 | 2016-05-16 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-06-17 | 2016-10-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights |  | Private
NSTAR | Woburn | 2135024 | 1801 | 378 | PV | 375-H4 | 2016-03-15 | 2016-03-18 | #VALUE! | 0 | #VALUE! | 2016-03-28 | 2016-05-16 | #VALUE! | 28 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 | 2016-06-08 | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-09 | Online |  | Private
NSTAR | Needham | 2135025 | 2494 | 150 | PV | 148-H1 | 2016-03-16 | 2016-03-17 | #VALUE! | 11 | #VALUE! | 2016-04-04 | 2016-06-14 | #VALUE! | 5 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2135260 | 2138 | 405 | PV | 819-1NB3 | 2016-03-16 | 2016-03-17 | #VALUE! | 0 | #VALUE! | 2016-03-22 | 2016-04-20 | #VALUE! | 16 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2135261 | 2360 | 2000 | PV | 3-89-922 | 2016-03-16 | 2016-03-31 | #VALUE! | 0 | #VALUE! | 2016-04-07 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2135262 | 2770 | 260 | PV | 3-702-702 | 2016-03-16 | 2016-03-22 | #VALUE! | 0 | #VALUE! | 2016-03-22 |  | #VALUE! | 97 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2017-01-24 | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-03-08 | Online |  | Private | N
NSTAR | Carver | 2135263 | 2330 | 490 | PV | 3-81-950 | 2016-03-17 | 2016-03-18 | #VALUE! | 0 | #VALUE! | 2016-03-28 | 2016-04-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-06 |  | 2016-10-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent |  | Private
NSTAR | Dedham | 2135559 | 2026 | 112 | PV | 20-H5 | 2016-03-18 | 2016-03-21 | #VALUE! | 0 | #VALUE! | 2016-03-28 | 2016-05-24 | #VALUE! | 28 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-10-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Waltham | 2135867 | 2451 | 270 | PV | 450-H8 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | 2016-05-24 | 2016-08-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-10-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dedham | 2135868 | 2026 | 84 | PV | 20-H1 | 2016-03-18 | 2016-03-30 | #VALUE! | 0 | #VALUE! | 2016-03-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-25 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review |  | Private | N
NSTAR | Cambridge | 2135869 | 2140 | 270 | PV | 828-1NA9 | 2016-03-21 | 2016-03-29 | #VALUE! | 0 | #VALUE! | 2016-04-04 | 2016-04-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-05-22 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Carver | 2135870 | 2330 | 34.2 | PV | 3-10-930 | 2016-02-24 | 2016-02-29 | #VALUE! |  | #VALUE! | 2016-03-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-09 | 2016-05-12 | [6 empty] | 0 |  | 0 |  |  | 2017-01-20 | Online
NSTAR | Carlisle | 2136139 | 1741 | 17 | PV | 512-1399H1 | 2016-03-21 | 2016-03-25 | #VALUE! | 0 | #VALUE! | 2016-03-31 | 2016-06-14 | #VALUE! | 22 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-21 | 2016-09-08 | 2016-10-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-18 | Online |  | Private
NSTAR | Somerville | 2136141 | 2145 | 499.5 | PV | 250-H4XY | 2016-03-21 | 2016-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2016-03-31 | Private
NSTAR | Hopkinton | 2136142 | 1748 | 2000 | PV | 126-H1 | 2016-03-23 | 2016-05-12 | #VALUE! | 0 | #VALUE! | 2016-03-31 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Chestnut Hill | 2136357 | 2467 | 324.8 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | #VALUE! |  | #VALUE! | 2016-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-03 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online |  | Private | Y
NSTAR | Chestnut Hill | 2136359 | 2467 | 196.24 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | #VALUE! |  | #VALUE! | 2016-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online |  | Private | Y
NSTAR | Hyannis | 2136574 | 2601 | 465 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | #VALUE! |  | #VALUE! | 2016-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Hyannis | 2136578 | 2601 | 364 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | #VALUE! |  | #VALUE! | 2016-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Newton | 2136579 | 2459 | 240 | PV | 292-H8 | 2016-03-24 | 2016-04-04 | #VALUE! | 0 | #VALUE! | 2016-04-04 | 2016-04-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 | 2016-04-05 | 2016-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
NSTAR | Hatchville | 2136806 | 2536 | 15.4 | PV | 4-98A-98A | 2016-03-25 | 2016-03-28 | #VALUE! | 0 | #VALUE! | 2016-03-29 | 2016-04-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-05 | 2016-06-16 | 2016-11-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online |  | Private
NSTAR | Dennis | 2136807 | 2660 | 21.75 | PV | 4-92B-92B | 2016-03-01 | 2016-03-02 | #VALUE! |  | #VALUE! | 2016-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-19 | 2016-06-22 | [6 empty] | 0 |  | 0
NSTAR | Newton | 2136808 | 2468 | 109.25 | PV | 292-H12 | 2016-02-25 | 2016-03-02 | #VALUE! |  | #VALUE! | 2016-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-06 | 2016-07-25 | 2016-07-25 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2136975 | 2740 | 468 | PV | 2-110-110 | 2016-03-25 | 2016-03-28 | #VALUE! | 0 | #VALUE! | 2016-03-31 |  | #VALUE! | 86 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-01 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online | 2016-04-20 | Private
NSTAR | Acton | 2136976 | 1720 | 990 | PV | 416-H4 | 2016-03-28 | 2016-03-29 | #VALUE! | 0 | #VALUE! | 2016-03-29 |  | #VALUE! | 81 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-04-27 | Private
NSTAR | Dartmouth | 2137247 | 2747 | 1000 | PV | 2-532-532 | 2016-03-28 | 2016-03-28 | 0 | 0 | 0 | 2016-03-29 | 2016-04-28 | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plympton | 2137254 | 2367 | 972 | PV | 3-51-901 | 2016-03-29 | 2016-03-30 | #VALUE! | 0 | #VALUE! | 2016-04-07 | 2016-05-18 | #VALUE! | 17 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2016-11-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Design Approval |  | Private
NSTAR | Jamaica Plain | 2137255 | 2130 | 21.9 | PV | 496-H4 | 2016-02-24 | 2016-02-29 | #VALUE! |  | #VALUE! | 2016-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-30 | 2016-04-08 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
NSTAR | Carver | 2137495 | 2330 | 1860 | PV | 3-51-980 | 2016-03-08 | 2016-03-08 | 0 |  | 0 | 2016-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-15 | 2016-08-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online
NSTAR | Dorchester | 2137497 | 2121 | 57.6 | PV | 106-H2 | 2016-02-15 | 2016-02-26 | #VALUE! |  | #VALUE! | 2016-04-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2137498 | 2451 | 290 | PV | 450-H3 | 2016-03-30 | 2016-03-31 | #VALUE! | 0 | #VALUE! | 2016-04-07 |  | #VALUE! | 86 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-11-04 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-06 | Private
NSTAR | Lexington | 2137830 | 2421 | 360 | PV | 320-H4 | 2016-03-30 | 2016-04-01 | #VALUE! | 0 | #VALUE! | 2016-04-07 | 2016-05-31 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-30 |  | 2016-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Framingham | 2137840 | 1702 | 219 | PV | 455-H5 | 2016-03-31 | 2016-04-01 | #VALUE! | 0 | #VALUE! | 2016-04-07 | 2016-04-11 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-12 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2138143 | 2747 | 18 | PV | 2-532-532 | 2016-04-01 | 2016-04-05 | #VALUE! | 0 | #VALUE! | 2016-04-11 | 2016-06-22 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-29 |  | 2016-11-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private | N
NSTAR | Mashpee | 2138475 | 2649 | 53.8 | PV | 4-88-455 | 2016-03-28 | 2016-03-30 | #VALUE! |  | #VALUE! | 2016-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2019-01-10 | Online
NSTAR | Dover | 2138477 | 2030 | 282 | PV | 456-H5 | 2016-04-06 | 2016-04-07 | #VALUE! | 0 | #VALUE! | 2016-04-25 | 2016-06-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | East Freetown | 2139202 | 2717 | 24.32 | PV | 2-102-602 | 2016-03-23 | 2016-04-06 | #VALUE! |  | #VALUE! | 2016-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-09 | 2016-06-10 | [6 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
NSTAR | Natick | 2139413 | 1760 | 16.2 | PV | 240-H1 | 2016-03-20 | 2016-03-28 | #VALUE! |  | #VALUE! | 2016-04-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-22 | 2016-07-11 | [6 empty] | 0 |  | 0
NSTAR | Weston | 2139664 | 2493 | 20.16 | PV | 282-H2 | 2016-03-28 | 2016-03-28 | 0 |  | 0 | 2016-04-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-28 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online |  | PRIVATE
NSTAR | Canton | 2139666 | 2021 | 192 | PV | 470-H7 | 2016-04-07 | 2016-04-11 | #VALUE! | 0 | #VALUE! | 2016-04-20 | 2016-06-20 | #VALUE! | 6 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-28 | 2016-08-24 | 2016-11-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost |  | Private
NSTAR | Newton | 2139847 | 2468 | 982 | PV | 292-H2 | 2016-04-08 | 2016-04-09 | #VALUE! | 0 | #VALUE! | 2016-04-19 | 2016-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-25 |  | 2016-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent |  | Private
NSTAR | Duxbury | 2139848 | 2332 | 24.32 | PV | 3-26-903 | 2016-03-17 | 2016-03-28 | #VALUE! |  | #VALUE! | 2016-05-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-09 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | private
NSTAR | Charlestown | 2140031 | 2129 | 288 | PV | 10-H1 | 2016-04-11 | 2016-04-12 | #VALUE! | 0 | #VALUE! | 2016-04-25 | 2016-05-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-11-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Kingston | 2140338 | 2364 | 50 | PV | 3-17-17 | 2016-04-11 | 2016-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-28 | Online |  | Private
NSTAR | Woburn | 2140339 | 1801 | 480 | PV | 375-H6 | 2016-04-11 | 2016-04-25 | #VALUE! | 0 | #VALUE! | 2016-04-28 | 2016-07-13 | #VALUE! | 49 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2016-11-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval |  | Private
NSTAR | Plymouth | 2140340 | 2360 | 364.3 | PV | 3-89-922 | 2016-04-12 | 2016-04-13 | #VALUE! | 0 | #VALUE! | 2016-04-18 | 2016-05-02 | #VALUE! | 3 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-13 | 2016-12-22 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-24 | Online |  | Private
NSTAR | Weston | 2140569 | 2493 | 246 | PV | 433-H6 | 2016-04-14 | 2016-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | 2016-04-27 | Private
NSTAR | Burlington | 2140576 | 1803 | 16.72 | PV | 391-H6 | 2016-03-29 | 2016-04-05 | #VALUE! |  | #VALUE! | 2016-04-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-12 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140849 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140850 | 2121 | 43.2 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2140851 | 2121 | 43.2 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2141085 | 2021 | 252 | PV | 470-H11 | 2016-04-14 | 2016-04-20 | #VALUE! | 0 | #VALUE! | 2016-04-27 | 2016-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-11-02 | 2016-11-17 | 2016-11-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-16 | Online |  | Private
NSTAR | Dorchester | 2141087 | 2121 | 57 | PV | 106-H2 | 2016-04-15 | 2016-04-27 | #VALUE! | 0 | #VALUE! | 2016-04-27 | 2016-05-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-16 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Somerville | 2141311 | 2145 | 18 | PV | 250-H4XY | 2016-04-18 | 2016-04-20 | #VALUE! | 0 | #VALUE! | 2016-04-27 | 2016-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-15 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval |  | Private
NSTAR | Dorchester | 2141870 | 2121 | 48 | PV | 106-H2 | 2016-04-21 | 2016-04-22 | #VALUE! | 0 | #VALUE! | 2016-05-12 | 2016-06-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dorchester | 2141880 | 2121 | 30.4 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2141881 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142397 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142398 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142654 | 2121 | 26.6 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142655 | 2121 | 28.8 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Sudbury | 2142844 | 1776 | 21.6 | PV | 342-h8 | 2016-04-11 | 2016-04-19 | #VALUE! |  | #VALUE! | 2016-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-10 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142845 | 2121 | 45.6 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142846 | 2124 | 57 | PV | 106-H2 | 2016-03-31 | 2016-04-05 | #VALUE! |  | #VALUE! | 2016-04-28 | 2016-05-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dorchester | 2143232 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2143233 | 2121 | 26.6 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Harwich | 2143454 | 2645 | 16.77 | PV | 4-95A-599 | 2016-03-31 | 2016-04-05 | #VALUE! |  | #VALUE! | 2016-04-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-24 | [6 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online |  | PRIVATE
NSTAR | Kingston | 2143458 | 2364 | 48 | PV | 3-17-910 | 2016-04-26 | 2016-04-28 | #VALUE! | 0 | #VALUE! | 2016-05-02 | 2016-05-06 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-16 | 2016-09-08 | 2016-12-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online |  | Private
NSTAR | Woburn | 2143665 | 1801 | 140 | PV | 211-H5 | 2016-04-27 | 2016-04-29 | #VALUE! | 0 | #VALUE! | 2016-04-29 | 2016-06-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-09 | Online |  | Private
NSTAR | Woburn | 2143667 | 1801 | 112 | PV | 211-H5 | 2016-04-27 | 2016-05-20 | #VALUE! | 0 | #VALUE! | 2016-05-26 | 2016-08-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-23 | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-05 | Online |  | Private | Y
NSTAR | Natick | 2143668 | 1760 | 16.25 | PV | 433-H5 | 2016-04-05 | 2016-04-11 | #VALUE! |  | #VALUE! | 2016-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-16 | 2010-06-03 | [6 empty] | 0 |  | 0 |  |  | 2016-09-19 | Online |  | PRIVATE
NSTAR | Carlisle | 2143902 | 1741 | 17.4 | PV | 512-1399h1 | 2016-04-10 | 2016-04-11 | #VALUE! |  | #VALUE! | 2016-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-27 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online
NSTAR | Jamaica Plain | 2143903 | 2130 | 30 | PV | 284-07 | 2016-04-28 | 2016-05-03 | #VALUE! | 0 | #VALUE! | 2016-05-13 | 2016-05-16 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-26 | 2016-06-02 | 2016-12-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-02 | Online |  | Private
NSTAR | Milton | 2144091 | 2186 | 25.05 | PV | 496-H7 | 2016-03-11 | 2016-04-01 | #VALUE! |  | #VALUE! | 2016-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2144430 | 1720 | 18 | PV | 416-H4 | 2016-05-02 | 2016-05-03 | #VALUE! | 0 | #VALUE! | 2016-05-13 | 2016-05-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-01 |  | 2016-12-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-31 | Online |  | Private
NSTAR | Weston | 2145203 | 2493 | 20 | PV | 282-H10 | 2016-05-04 | 2016-05-05 | #VALUE! | 0 | #VALUE! | 2016-05-11 | 2016-05-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 |  | 2016-12-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-13 | Online |  | Private
NSTAR | Canton | 2145484 | 2021 | 780 | PV | 269-1320H1 | 2016-05-05 | 2016-05-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study |  | Private
NSTAR | West Roxbury | 2145690 | 2132 | 684 | PV | 374-04 | 2016-05-06 | 2016-05-11 | #VALUE! | 0 | #VALUE! | 2016-05-16 |  | #VALUE! | 1 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 2016-12-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Mashpee | 2145692 | 2649 | 58.9 | PV | 4-88-453 | 2016-02-10 | 2016-04-27 | #VALUE! |  | #VALUE! | 2016-05-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2016-12-05 | Online |  | PRIVATE
NSTAR | Woburn | 2145950 | 1801 | 43.009 | PV | 211-H5 | 2016-04-20 | 2016-05-02 | #VALUE! |  | #VALUE! | 2016-05-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-31 | 2016-09-06 | 2016-09-06 | [5 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online |  | PRIVATE
NSTAR | West Newton | 2145951 | 2465 | 21.681 | PV | 282-H9 | 2016-04-26 | 2016-04-29 | #VALUE! |  | #VALUE! | 2016-05-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-11 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online |  | PRIVATE | Y
NSTAR | Plymouth | 2146368 | 2360 | 99.9 | PV | 3-88-924 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2146377 | 2332 | 28.8 | PV | 3-26-903 | 2016-03-24 | 2016-05-02 | #VALUE! |  | #VALUE! | 2016-05-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | PRIVATE
NSTAR | Dennisport | 2146378 | 2639 | 34.77 | PV | 4-85-592 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-01 | 2016-06-24 | [6 empty] | 0 |  | 0 |  |  | 2016-08-11 | Online
NSTAR | Sherborn | 2146567 | 1770 | 19 | PV | 274-H2 | 2016-05-12 | 2016-05-18 | #VALUE! | 0 | #VALUE! | 2016-05-26 | 2016-06-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-08 | Online |  | Private
NSTAR | New Bedford | 2146760 | 2744 | 499.5 | PV | 2-69-52 | 2016-05-08 | 2016-05-09 | #VALUE! |  | #VALUE! | 2016-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online
NSTAR | Waltham | 2147316 | 2452 | 16.15 | PV | 33-H2 | 2016-05-13 | 2016-05-16 | #VALUE! |  | #VALUE! | 2016-05-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online |  | PRIVATE
NSTAR | Ashland | 2147605 | 1721 | 728 | PV | 3-10-929 | 2016-05-18 | 2016-05-19 | #VALUE! | 0 | #VALUE! | 2016-07-14 | 2016-07-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2015-08-18 | 2016-12-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Field Com |  | Private
NSTAR | Carver | 2147609 | 2330 | 20 | PV | 3-10-929 | 2016-05-18 | 2016-05-23 | #VALUE! | 0 | #VALUE! | 2016-05-26 | 2016-08-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-22 | 2017-01-19 | 2016-12-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online |  | Private | N
NSTAR | Boston | 2147800 | 2118 | 336 | PV | 106-H4 | 2016-05-19 | 2016-05-20 | #VALUE! | 0 | #VALUE! | 2016-05-23 | 2016-08-10 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-15 | 2016-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed |  | Private
NSTAR | Assonett | 2148246 | 2702 | 432 | PV | 2-605-605 | 2016-05-23 | 2016-05-24 | #VALUE! | 0 | #VALUE! | 2016-05-24 |  | #VALUE! | 58 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-14 |  | 2016-12-30 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-10-23 | Online | 2016-05-30 | Private
NSTAR | Natick | 2148247 | 1760 | 280 | PV | 433-H7 | 2016-05-23 | 2016-05-24 | #VALUE! | 0 | #VALUE! | 2016-05-30 | 2016-07-25 | #VALUE! | 18 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-08-24 | 2016-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online |  | Private
NSTAR | Newton | 2148462 | 2466 | 1800 | PV | 33-H3 | 2016-05-24 | 2016-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online | 2016-06-06 | Private
NSTAR | Roxbury | 2148650 | 2120 | 936 | PV | 483-H6 | 2016-05-25 | 2016-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Gov't
NSTAR | Sherborn | 2148838 | 1770 | 23.1 | PV | 274-H3 | 2016-05-03 | 2016-05-18 | #VALUE! |  | #VALUE! | 2016-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-07 | [7 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online |  | PRIVATE
NSTAR | Lexington | 2149011 | 2421 | 15.4 | PV | 3408 | 2016-05-16 | 2016-05-18 | #VALUE! |  | #VALUE! | 2016-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online |  | PRIVATE
NSTAR | Stoneham | 2150045 | 2180 | 15.98 | PV | 375-H8 | 2016-05-13 | 2016-05-18 | #VALUE! |  | #VALUE! | 2016-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-08-10 | [6 empty] | 0 |  | 0 | [5 empty] | PRIVATE
NSTAR | Hyannis | 2151036 | 2601 | 38 | PV | 4-63-63 | 2016-06-02 | 2016-06-08 | #VALUE! | 0 | #VALUE! | 2016-06-14 | 2016-06-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2017-01-11 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | Bedford | 2151037 | 1730 | 288 | PV | 391-H8 | 2016-05-23 | 2016-05-31 | #VALUE! |  | #VALUE! | 2016-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-12 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online |  | Private
NSTAR | Hyannis | 2151406 | 2601 | 136.5 | PV | 4-63-521 | 2016-05-12 | 2016-05-31 | #VALUE! |  | #VALUE! | 2016-06-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-15 | 2016-08-08 | [6 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | Boston | 2151408 | 2215 | 367 | PV | 350-H5 | 2016-06-03 | 2016-06-04 | #VALUE! | 0 | #VALUE! | 2016-06-09 | 2016-06-21 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2151948 | 1760 | 75 | Natural Gas | 433-H7 | 2016-06-07 | 2016-06-09 | #VALUE! | 38 | #VALUE! | 2016-06-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-29 | 2016-01-03 | 2017-01-17 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | 2016-06-28 | Private
NSTAR | Cotuit | 2152205 | 2635 | 1992 | PV | 4-88-880 | 2016-06-08 | 2016-06-13 | #VALUE! | 0 | #VALUE! | 2016-06-14 |  | #VALUE! | 45 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2016-09-28 |  | 2017-01-18 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-17 | Private
NSTAR | Bourne | 2152371 | 2532 | 566.1 | PV | 3-89-925 | 2016-03-04 | 2016-05-18 | #VALUE! |  | #VALUE! | 2016-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | 2016-09-01 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2152922 | 1801 | 49.14 | PV | 533-H7 | 2016-05-10 | 2016-06-02 | #VALUE! |  | #VALUE! | 2016-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online |  | PRIVATE
NSTAR | Orleans | 2152923 | 2653 | 300 | PV | 4-83-952 | 2016-06-13 | 2016-06-15 | #VALUE! | 0 | #VALUE! | 2016-06-20 | 2016-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-27 |  | 2017-01-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-18 | Online |  | Private
NSTAR | Cotuit | 2153294 | 2635 | 1992 | PV | 4-88-880 | 2016-06-15 | 2016-06-16 | #VALUE! | 0 | #VALUE! | 2016-06-27 |  | #VALUE! | 37 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2016-09-26 | 2016-09-28 | 2017-01-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-29 | Private
NSTAR | Newton | 2154090 | 2460 | 75 | PV | 467-H5 | 2016-06-20 | 2016-06-21 | #VALUE! | 0 | #VALUE! | 2016-06-27 | 2016-06-29 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-27 |  | 2017-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online |  | Private
NSTAR | Watertown | 2154091 | 2472 | 432 | PV | 467-H6 | 2016-06-20 | 2016-06-21 | #VALUE! | 0 | #VALUE! | 2016-06-28 | 2016-08-03 | #VALUE! | 22 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-08-24 | 2017-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-23 | Online |  | Private
NSTAR | Framingham | 2154503 | 1701 | 105 | PV | 433-H3 | 2016-06-22 | 2016-06-23 | #VALUE! | 2 | #VALUE! | 2016-06-28 | 2016-07-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Framingham | 2154699 | 1701 | 105 | PV | 433-H3 | 2016-06-23 | 2016-06-24 | #VALUE! | 2 | #VALUE! | 2016-07-05 | 2016-07-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Dedham | 2154886 | 2026 | 189.2 | PV | 20-H5 | 2016-06-24 | 2016-06-27 | #VALUE! | 0 | #VALUE! | 2016-07-04 | 2016-07-26 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-03 | 2016-08-03 | 2017-02-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-30 | Online |  | Private
NSTAR | Sandwich | 2155321 | 2537 | 468 | PV | 4-81B-81B | 2016-06-28 | 2016-06-29 | #VALUE! | 0 | #VALUE! | 2016-07-04 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 2016-09-08 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 | 2016-12-19 |  | 2017-02-07 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Sent ISA |  | Private
NSTAR | Brighton | 2155327 | 2135 | 75 | PV | 315-H11 | 2016-06-28 | 2016-06-29 | #VALUE! | 0 | #VALUE! | 2016-07-04 | 2016-07-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 |  | 2017-02-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-07 | Online |  | Private
NSTAR | Dennis | 2155620 | 2638 | 89.9 | PV | 4-92B-92B | 2016-05-13 | 2016-06-08 | #VALUE! |  | #VALUE! | 2016-06-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-28 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  |  | isa received/signed
NSTAR | Sandwich | 2155836 | 2563 | 109.2 | PV | 4-81B-443 | 2016-06-09 | 2016-06-22 | #VALUE! |  | #VALUE! | 2016-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2156003 | 2122 | 170 | PV | 496-H1XY | 2016-07-01 | 2016-07-05 | #VALUE! | 0 | #VALUE! | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-07-26 | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-01 | Online |  | Private
NSTAR | Chatham | 2156004 | 2650 | 21.44 | PV | 4-95B-612 | 2016-06-10 | 2016-06-13 | #VALUE! |  | #VALUE! | 2016-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-13 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online |  | PRIVATE
NSTAR | Needham | 2156671 | 2494 | 90 | PV | 148-H7 | 2016-07-05 | 2016-07-06 | #VALUE! | 0 | #VALUE! | 2016-07-14 | 2016-08-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-23 | 2016-08-25 | 2017-02-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-07 | Online |  | Private
NSTAR | North Dartmouth | 2157001 | 2747 | 16.25 | PV | 2-541-541 | 2016-06-01 | 2016-06-20 | #VALUE! |  | #VALUE! | 2016-07-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-09-12 | [6 empty] | 0 |  | 0 |  |  | 2016-09-26 | Online |  | PRIVATE
NSTAR | Waltham | 2157007 | 2453 | 180 | PV | 33-H3 | 2016-07-06 | 2016-07-07 | #VALUE! | 0 | #VALUE! | 2016-07-14 |  | #VALUE! | 12 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Online | 2016-08-04 | Private
NSTAR | Dartmouth | 2157191 | 2747 | 150 | Natural Gas | 2-541-542 | 2016-07-07 | 2016-07-11 | #VALUE! | 0 | #VALUE! | 2016-07-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-22 | 2017-02-15 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-31 | Online |  | Gov't
NSTAR | Dover | 2157192 | 2030 | 21 | PV | 456-H5 | 2016-07-07 | 2016-07-11 | #VALUE! | 0 | #VALUE! | 2016-07-15 | 2016-08-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2017-02-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-02 | Online |  | Private
NSTAR | Woburn | 2157251 | 1801 | 499 | PV | 375-H3 | 2016-07-08 | 2016-07-11 | #VALUE! | 0 | #VALUE! | 2016-07-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-16 | TBD | TBD | 30 |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | South Boston | 2157900 | 2210 | 456 | PV | 385-H18 | 2016-06-09 | 2016-06-22 | #VALUE! | 0 | #VALUE! | 2016-07-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-23 | 2017-02-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-07-20 | Online |  | Private
NSTAR | Acusnet | 2157905 | 2743 | 144.4 | PV | 2-231-231 | 2016-05-27 | 2016-06-27 | #VALUE! |  | #VALUE! | 2016-07-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2158112 | 2648 | 50.4 | PV | 4-88-478 | 2016-05-24 | 2016-06-28 | #VALUE! |  | #VALUE! | 2016-07-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent |  | PRIVATE
NSTAR | South Boston | 2158329 | 2127 | 486.2 | PV | 385-H17 | 2016-05-11 | 2016-05-16 | #VALUE! |  | #VALUE! | 2016-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Boston | 2158505 | 2127 | 500 | PV | 106-H1 | 2016-07-15 | 2016-07-25 | #VALUE! | 0 | #VALUE! | 2016-07-25 |  | #VALUE! | 16 | #VALUE! | 2016-08-31 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-24 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acton | 2158995 | 1720 | 294 | PV | 416-H4 | 2016-07-18 | 2016-07-25 | #VALUE! | 0 | #VALUE! | 2016-07-28 |  | #VALUE! | 14 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-02 | Private
NSTAR | Milton | 2158997 | 2186 | 30 | PV | 362-1209H1 | 2016-07-18 | 2016-07-20 | #VALUE! | 0 | #VALUE! | 2016-07-28 | 2016-08-09 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-15 |  | 2017-02-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  | Private
NSTAR | Weston | 2159240 | 2493 | 20 | PV | 282-H1 | 2016-07-19 | 2016-07-20 | #VALUE! | 0 | #VALUE! | 2016-07-28 |  | #VALUE! | 8 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-01-30 |  | 2017-02-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-10 | Private
NSTAR | Framingham | 2159493 | 2472 | 166.5 | PV | 467-H2 | 2016-06-29 | 2016-07-12 | #VALUE! |  | #VALUE! | 2016-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 2159738 | 2367 | 1000 | PV | TBD | 2016-07-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | West Roxbury | 2160263 | 2132 | 250 | Natural Gas | 374-2215 | 2016-07-25 | 2016-07-27 | #VALUE! | 0 | #VALUE! | 2016-08-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-18 | 2016-09-09 | 2017-03-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed |  | Gov't
NSTAR | Westwood | 2160448 | 2090 | 126.5 | PV | 456-h1 | 2016-07-14 | 2016-07-18 | #VALUE! |  | #VALUE! | 2016-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-02 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2017-04-27 | Online
NSTAR | Hatchville | 2160717 | 2536 | 98 | PV | 4-98A-98A | 2016-07-27 | 2016-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Maynard | 2160866 | 1754 | 576 | PV | 416-H3 | 2016-07-28 | 2016-08-01 | #VALUE! | 0 | #VALUE! | 2016-08-05 |  | #VALUE! | 7 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-09 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-11 | Private
NSTAR | Westwood | 2161143 | 2090 | 161 | PV | 469-H2 | 2016-07-29 | 2016-08-01 | #VALUE! | 0 | #VALUE! | 2016-08-05 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-16 | 2016-09-23 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-27 | Online |  | Private
NSTAR | Hopkinton | 2161144 | 1748 | 252 | PV | 126-H1 | 2016-07-29 | 2016-08-02 | #VALUE! | 0 | #VALUE! | 2016-08-05 | 2016-08-19 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-12 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online | 2016-08-22 | Private
NSTAR | Westwood | 2161690 | 2090 | 164 | PV | 456-H4 | 2016-07-16 | 2016-08-09 | #VALUE! | 0 | #VALUE! | 2016-08-03 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-09-14 | 2017-03-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online |  | Private
NSTAR | Waltham | 2162221 | 2452 | 380 | PV | 277-1367 | 2016-08-03 | 2016-08-09 | #VALUE! | 0 | #VALUE! | 2016-08-11 |  | #VALUE! | 6 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-19 | 2016-09-29 | 2017-03-15 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-12 | Private
NSTAR | East Boston | 2162392 | 2128 | 72 | PV | 488-H8 | 2016-08-04 | 2016-08-09 | #VALUE! | 0 | #VALUE! | 2016-08-11 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-16 |  | 2017-03-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Ashland | 2162591 | 1721 | 148.9 | PV | 274-H1 | 2016-07-18 | 2016-07-25 | #VALUE! |  | #VALUE! | 2016-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 2164625 | 2019 | 497.5 | PV | 65-H4 | 2016-06-10 | 2016-07-25 | #VALUE! |  | #VALUE! | 2016-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-12 | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-07-28 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Mattapoisett | 2164627 | 2739 | 16.92 | PV | 2-301-301 | 2016-07-05 | 2016-07-27 | #VALUE! |  | #VALUE! | 2016-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | New Bedford | 2164917 | 2745 | 272 | PV | 2-103-103 | 2016-07-22 | 2016-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | Private
NSTAR | Westwood | 2165129 | 2090 | 138 | PV | 456-H4 | 2016-07-14 | 2016-07-28 | #VALUE! | 0 | #VALUE! | 2016-08-22 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-29 | 2017-03-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-25 | Online |  | Gov't
NSTAR | Roxbury | 2165132 | 2119 | 57.6 | PV | 106-H5 | 2016-07-11 | 2016-07-28 | #VALUE! |  | #VALUE! | 2016-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Roxbury | 2165395 | 2119 | 115.2 | PV | 106-H4 | 2016-07-13 | 2016-08-01 | #VALUE! |  | #VALUE! | 2016-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2165396 | 2648 | 19.6 | PV | 4-88-485 | 2016-07-26 | 2016-08-01 | #VALUE! |  | #VALUE! | 2016-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-17 | Online |  | PRIVATE
NSTAR | Falmouth | 2165668 | 2536 | 90 | PV | 4-98A-98A | 2016-07-29 | 2016-08-09 | #VALUE! |  | #VALUE! | 2016-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online |  | PRIVATE | Y
NSTAR | Framingham | 2165880 | 1701 | 30 | PV | 4-98A-98A | 2016-07-22 | 2016-08-09 | #VALUE! |  | #VALUE! | 2016-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | [7 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online |  | PRIVATE
NSTAR | Westwood | 2165893 | 2090 | 266.4 | PV | 456-H1 | 2016-08-05 | 2016-08-12 | #VALUE! |  | #VALUE! | 2016-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2017-10-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-21 | Online |  | PRIVATE | Y
NSTAR | Hyannis | 2166109 | 2601 | 20 | PV | 4-63-63 | 2016-07-13 | 2016-08-15 | #VALUE! |  | #VALUE! | 2016-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent |  | PRIVATE
NSTAR | Falmouth | 2166111 | 2536 | 100.8 | PV | 4-98A-98A | 2016-07-26 | 2016-08-29 | #VALUE! |  | #VALUE! | 2016-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2017-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-04-28 | Online
NSTAR | Waltham | 2166275 | 2453 | 60 | PV | 282-H4 | 2016-08-09 | 2016-08-15 | #VALUE! |  | #VALUE! | 2016-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online |  | PRIVATE
NSTAR | Waltham | 2166276 | 2453 | 50 | PV | 282-H9 | 2016-08-09 | 2016-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-16 | Online |  | PRIVATE
NSTAR | Dedham | 2166557 | 2026 | 525 | PV | 344-1413H1 | 2016-07-20 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2016-12-29 | [7 empty] | 0 |  | 0 |  |  |  | isa sent
NSTAR | Dorchester | 2166559 | 2124 | 20 | PV | 511-1497H3 | 2016-08-11 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-22 | 2016-09-23 | [6 empty] | 0 |  | 0 |  |  | 2017-06-02 | Online |  | PRIVATE
NSTAR | Cambridge | 2166793 | 2140 | 22.8 | PV | 825-27 | 2016-08-03 | 2016-08-04 | #VALUE! |  | #VALUE! | 2016-09-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-21 | [6 empty] | 0 |  | 0 |  |  | 2017-01-03 | Online |  | PRIVATE
NSTAR | Newton | 2166797 | 2458 | 150 | PV | 467-H14 | 2016-08-12 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-09-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-03-29 | Online |  | PRIVATE
NSTAR | Newton | 2166988 | 2466 | 57.5 | PV | 292-H7 | 2016-08-18 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-09-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-03-01 | Online |  | PRIVATE
NSTAR | Cambridge | 2166994 | 2140 | 115.2 | PV | 825-26 | 2016-08-16 | 2016-08-24 | #VALUE! |  | #VALUE! | 2016-09-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2167216 | 2453 | 73.3 | PV | 33-H1 | 2016-08-09 | 2016-08-16 | #VALUE! |  | #VALUE! | 2016-09-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online
NSTAR | Allston | 2168053 | 2134 | 60 | PV | 329-H7 | 2016-08-17 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-09-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-02 | Online |  | PRIVATE
NSTAR | Boston | 2168059 | 2118 | 75 | PV | 323-06 | 2016-08-12 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-09-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Bedford | 2168512 | 1731 | 2805 | PV | 320-H6 | 2016-09-01 | 2016-09-07 | #VALUE! |  | #VALUE! | 2016-09-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2168736 | 1760 | 21.9 | PV | 240-H2 | 2016-08-11 | 2016-08-22 | #VALUE! |  | #VALUE! | 2016-09-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2016-11-29 | Online |  | PRIVATE | Y
NSTAR | Sudbury | 2168989 | 1776 | 20 | PV | 342-H7 | 2016-08-16 | 2016-08-24 | #VALUE! |  | #VALUE! | 2016-09-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online |  | PRIVATE
NSTAR | North Dartmouth | 2168995 | 2747 | 40 | PV | 2-541-542 | 2016-07-28 | 2016-08-29 | #VALUE! |  | #VALUE! | 2016-09-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-30 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | PRIVATE | Y
NSTAR | Brewster | 2169301 | 2631 | 19.25 | PV | 4-89B-576 | 2016-08-18 | 2016-08-24 | #VALUE! |  | #VALUE! | 2016-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Somerville | 2169544 | 2143 | 45 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | #VALUE! |  | #VALUE! | 2016-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  | 2019-02-05 | isa sent |  | PRIVATE
NSTAR | Somerville | 2169546 | 2143 | 105 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | #VALUE! |  | #VALUE! | 2016-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-09 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-18 | Online
NSTAR | Cambridge | 2169551 | 2139 | 57.6 | PV | 814-13 | 2016-09-02 | 2016-09-07 | #VALUE! |  | #VALUE! | 2016-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-06 | Online |  | PRIVATE
NSTAR | Boston | 2169723 | 2188 | 72 | PV | 106-H4 | 2016-08-17 | 2016-08-26 | #VALUE! |  | #VALUE! | 2016-09-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2017-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-11-09 | Online
NSTAR | Brighton | 2169751 | 2135 | 64 | PV | 467-H12 | 2016-08-17 | 2016-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2169753 | 2128 | 167 | PV | 108-196H1 | 2016-08-17 | 2016-08-26 | #VALUE! |  | #VALUE! | 2016-09-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Stoneham | 2170420 | 2180 | 84 | PV | 375-H7 | 2016-08-17 | 2016-08-26 | #VALUE! |  | #VALUE! | 2016-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-14 | Online
NSTAR | Hopkinton | 2170421 | 1748 | 22.7 | PV | 126-H1 | 2016-08-29 | 2016-08-31 | #VALUE! |  | #VALUE! | 2016-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-01-05 | Online |  | PRIVATE
NSTAR | Rochester | 2170422 | 2770 | 21.9 | PV | 5-702-702 | 2016-08-25 | 2016-08-29 | #VALUE! |  | #VALUE! | 2016-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Plymouth | 2170423 | 2360 | 188.42 | PV | 3-14-911 | 2016-08-19 | 2016-08-30 | #VALUE! |  | #VALUE! | 2016-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Hyannis | 2170678 | 2601 | 306.07 | PV | 4-84B-524 | 2016-08-19 | 2016-08-30 | #VALUE! |  | #VALUE! | 2016-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-03-28 | Online |  | PRIVATE
NSTAR | Kingston | 2170680 | 2364 | 80 | PV | 3-26-902 | 2016-08-23 | 2016-09-01 | #VALUE! |  | #VALUE! | 2016-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-28 | Online |  | PRIVATE
NSTAR | Acton | 2170908 | 1720 | 21.9 | PV | 416-H4 | 2016-08-25 | 2016-09-01 | #VALUE! |  | #VALUE! | 2016-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
NSTAR | Arlington | 2170910 | 2475 | 396 | PV | 211-H11 | 2016-08-22 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2016-12-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 |  |  | 2017-08-04 | Online |  | PRIVATE
NSTAR | West Wareham | 2170912 | 2576 | 24.5 | PV | 3-85-85 | 2016-08-30 | 2016-09-06 | #VALUE! |  | #VALUE! | 2016-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Framingham | 2171111 | 1701 | 1760 | PV | 455-H7 | 2016-07-29 | 2016-09-07 | #VALUE! |  | #VALUE! | 2016-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-22 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2018-04-30 | Online
NSTAR | Acton | 2171112 | 1720 | 39.1 | PV | 416-H5 | 2016-08-22 | 2016-09-06 | #VALUE! |  | #VALUE! | 2016-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Marion | 2171654 | 2738 | 15.2 | PV | 3-85-85 | 2016-09-01 | 2016-09-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online |  | PRIVATE
NSTAR | Woburn | 2171655 | 1888 | 466.2 | PV | 375-H3 | 2016-06-01 | 2016-09-07 | #VALUE! |  | #VALUE! | 2016-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-08-18 | 2017-08-23 | [6 empty] | 0 |  | 0 |  |  | 2018-02-26 | Online
NSTAR | Hopkinton | 2171656 | 1748 | 433 | PV | 126-H1 | 2016-09-01 | 2016-09-06 | #VALUE! |  | #VALUE! | 2016-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | 2016-11-17 | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  |  | WO Request
NSTAR | Acton | 2171989 | 1720 | 40 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Acton | 2171992 | 1720 | 52.9 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Truro | 2172198 | 2666 | 18.9 | PV | 4-96-674 | 2016-09-07 | 2016-09-09 | #VALUE! |  | #VALUE! | 2016-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online |  | PRIVATE
NSTAR | East Falmouth | 2172199 | 2536 | 48 | PV | 4-98A-98A | 2016-07-15 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Acton | 2172398 | 1720 | 101 | PV | 416-H9 | 2016-08-18 | 2016-09-07 | #VALUE! |  | #VALUE! | 2016-10-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2172403 | 2140 | 66.6 | PV | 824-28 | 2016-09-09 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-02 | 2016-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-06-26 | Online
NSTAR | Orleans | 2172699 | 2653 | 33.5 | PV | 4-83-952 | 2016-09-06 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | [7 empty] | 0 |  | 0 |  |  | 2017-05-18 | Online |  | PRIVATE
NSTAR | East Boston | 2173575 | 2128 | 75 | CHP | 488-H8 | 2016-09-12 | 2016-10-04 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2016-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-02-10 | Online |  | NO EXPORT
NSTAR | Buzzards Bay | 2173585 | 2532 | 100 | PV | 3-88-2J4 | 2016-09-08 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2173782 | 2630 | 50 | PV | 4-84B-524 | 2016-08-29 | 2016-09-09 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-03-10 | Online |  | PRIVATE
NSTAR | Arlington | 2173991 | 2476 | 34.5 | PV | 211-H3 | 2016-08-25 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Natick | 2173993 | 1760 | 126 | PV | 240-H2 | 2016-09-09 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | ISA SENT
NSTAR | West Tisbury | 2173995 | 2575 | 22.8 | PV | 4-97-97 | 2016-09-12 | 2016-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-16 | Online |  | PRIVATE
NSTAR | West Tisbury | 2173999 | 2575 | 22.8 | PV | 4-97-226 | 2016-09-12 | 2016-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online |  | PRIVATE
NSTAR | Framingham | 2174568 | 1701 | 165 | PV | 433-H3 | 2016-09-09 | 2016-09-15 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Walpole | 2174571 | 2081 | 135 | PV | 2611 | 2016-09-08 | 2016-09-14 | #VALUE! |  | #VALUE! | 2016-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marion | 2174858 | 2738 | 27.72 | PV | 2-304-304 | 2016-09-08 | 2016-09-15 | #VALUE! |  | #VALUE! | 2016-10-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online |  | PRIVATE
NSTAR | Framingham | 2175097 | 1702 | 180 | PV | 240-H4 | 2016-09-28 | 2016-10-03 | #VALUE! |  | #VALUE! | 2016-10-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2175313 | 2452 | 18.4 | PV | 282-H7 | 2016-09-15 | 2016-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Assonett | 2175318 | 2702 | 16.7 | PV | 2-605-605 | 2016-09-13 | 2016-09-17 | #VALUE! |  | #VALUE! | 2016-10-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | New Bedford | 2175669 | 2746 | 180 | PV | 2-24-11 | 2016-09-16 | 2016-09-19 | #VALUE! |  | #VALUE! | 2016-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-25 | 2017-03-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online
NSTAR | Acusnet | 2176279 | 2743 | 15.36 | PV | 2-241-241 | 2016-09-20 | 2016-09-20 | 0 |  | 0 | 2016-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-08 | 2016-12-09 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online |  | PRIVATE
NSTAR | Holliston | 2176549 | 1746 | 36 | PV | 274-H3 | 2016-09-09 | 2016-09-23 | #VALUE! |  | #VALUE! | 2016-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online |  | PRIVATE
NSTAR | Harwich | 2176727 | 2645 | 30 | PV | 4-89A-556 | 2016-09-19 | 2016-09-21 | #VALUE! |  | #VALUE! | 2016-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-01 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
NSTAR | Needham | 2176734 | 2494 | 866 | PV | 148-H6 | 2016-07-13 | 2016-09-23 | #VALUE! |  | #VALUE! | 2016-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2177085 | 2145 | 210 | PV | 210-1N81H1 | 2016-08-19 | 2016-09-23 | #VALUE! |  | #VALUE! | 2016-10-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2177087 | 2360 | 32.35 | PV | 3-13-936 | 2016-09-20 | 2016-09-26 | #VALUE! |  | #VALUE! | 2016-10-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-04-05 | Online |  | Private | Y
NSTAR | Brookline | 2177319 | 2446 | 16.5 | PV | 350-H12 | 2016-09-15 | 2016-09-26 | #VALUE! |  | #VALUE! | 2016-10-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-04-19 | Online |  | PRIVATE
NSTAR | Lexington | 2177534 | 2420 | 79.2 | PV | 391-H11 | 2016-09-21 | 2016-09-28 | #VALUE! |  | #VALUE! | 2016-10-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2177535 | 2557 | 21.15 | PV | 4-99-224 | 2016-08-25 | 2016-10-19 | #VALUE! |  | #VALUE! | 2016-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-03 | Online |  | PRIVATE
NSTAR | Medway | 2177856 | 2053 | 180 | PV | 65-H3 | 2016-09-30 | 2016-10-26 | #VALUE! |  | #VALUE! | 2016-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2178416 | 2539 | 21.38 | PV | 4-75-75 | 2016-06-15 | 2016-10-19 | #VALUE! |  | #VALUE! | 2016-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online |  | PRIVATE
NSTAR | North Dartmouth | 2178419 | 2747 | 499.5 | PV | 2-533-530 | 2016-09-30 | 2016-10-04 | #VALUE! |  | #VALUE! | 2016-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-02 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online
NSTAR | Natick | 2178429 | 1760 | 458 | PV | TBD | 2016-10-31 |  | #VALUE! | 0 | #VALUE! | 2016-11-04 | 2017-08-17 | #VALUE! | 188 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Somerville | 2178439 | 2143 | 30.24 | PV | 250-1N90H2 | 2016-09-20 | 2016-09-29 | #VALUE! |  | #VALUE! | 2016-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online |  | PRIVATE | Y
NSTAR | Yarmouth | 2178449 | 2664 | 127.8 | PV | 4-92a-562 | 2016-09-26 | 2016-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Teaticket | 2178798 | 2536 | 228 | PV | 4-76-437 | 2016-09-26 | 2016-10-03 | #VALUE! |  | #VALUE! | 2016-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | [7 empty] | 0 |  | 0 |  |  | 2017-12-01 | Online
NSTAR | New Bedford | 2179799 | 2745 | 208 | PV | 2-82-82 | 2016-10-09 | 2016-10-12 | #VALUE! |  | #VALUE! | 2016-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | 2016-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | Private
NSTAR | Falmouth | 2179819 | 2540 | 32.4 | PV | 4-72-433 | 2016-09-26 | 2016-10-03 | #VALUE! |  | #VALUE! | 2016-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Falmouth | 2180040 | 2540 | 16 | PV | 4-72-433 | 2016-09-27 | 2016-10-03 | #VALUE! |  | #VALUE! | 2016-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
NSTAR | Waltham | 2180042 | 2453 | 30 | PV | 467-H5 | 2016-09-30 | 2016-10-04 | #VALUE! |  | #VALUE! | 2016-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-28 | 2016-12-13 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
NSTAR | Bourne | 2180239 | 2542 | 7950 | PV | 4-98A-98A | 2016-10-04 | 2016-10-12 | #VALUE! |  | #VALUE! | 2016-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-05-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2180242 | 1760 | 252 | PV | 240-H1 | 2016-09-29 | 2016-10-04 | #VALUE! |  | #VALUE! | 2016-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-03 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2180244 | 1730 | 5198 | CHP | 319-1377 | 2016-09-29 | 2016-10-04 | #VALUE! |  | #VALUE! | 2016-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | 2180484 | 2052 | 70 | PV | 146-H2 | 2016-11-07 | 2016-11-07 | 0 |  | 0 | 2016-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online |  | GOV'T
NSTAR | North Dartmouth | 2180485 | 2748 | 39.6 | PV | 2-524-524 | 2016-09-22 | 2016-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-08 | Waiting for ISA |  | PRIVATE
NSTAR | Framingham | 2180488 | 1702 | 50 | PV | 2408 | 2016-09-19 | 2016-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-17 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online |  | PRIVATE
NSTAR | Brookline | 2180952 | 2455 | 60 | PV | 506-07 | 2016-09-30 | 2016-10-12 | #VALUE! |  | #VALUE! | 2016-11-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-16 | 2016-01-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Walpole | 2180956 | 2081 | 28.8 | PV | 146-H3 | 2016-10-05 | 2016-10-17 | #VALUE! |  | #VALUE! | 2016-11-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online |  | PRIVATE
NSTAR | Framingham | 2181138 | 1702 | 51 | PV | 278-H1 | 2016-09-19 | 2016-10-12 | #VALUE! |  | #VALUE! | 2016-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-04-10 | [6 empty] | 0 |  | 0 |  |  | 2017-09-20 | Online |  | PRIVATE
NSTAR | Holliston | 2181140 | 1746 | 42 | PV | 274-H3 | 2016-10-13 | 2016-10-21 | #VALUE! | 7 | #VALUE! | 2016-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | [7 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online |  | PRIVATE
NSTAR | Bedford | 2181646 | 1731 | 430 | PV | 319-1378 | 2016-10-11 | 2016-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-22 | Online
NSTAR | Holliston | 2181649 | 1746 | 32.5 | PV | 130-H1 | 2016-10-06 | 2016-10-19 | #VALUE! |  | #VALUE! | 2016-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-03-13 | Online |  | PRIVATE
NSTAR | Dedham | 2181650 | 2026 | 150 | CHP | 20-H5 | 2016-10-14 | 2016-10-19 | #VALUE! |  | #VALUE! | 2016-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online
NSTAR | South Dartmouth | 2181937 | 2748 | 57.6 | PV | 2-2-505 | 2016-10-04 | 2016-10-20 | #VALUE! |  | #VALUE! | 2016-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-21 | Online |  | PRIVATE
NSTAR | Needham | 2181939 | 2494 | 64.8 | PV | 148-H1 | 2016-10-17 | 2016-10-21 | #VALUE! |  | #VALUE! | 2016-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-07 | 2016-12-15 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2181940 | 2445 | 89 | PV | 369-07 | 2016-10-20 | 2016-10-25 | #VALUE! |  | #VALUE! | 2016-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sherborn | 2181941 | 1770 | 35.6 | PV | 274-H2 | 2016-10-11 | 2016-10-17 | #VALUE! |  | #VALUE! | 2016-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Weston | 2182191 | 2493 | 18 | PV | 433-H6 | 2016-10-12 | 2016-10-18 | #VALUE! |  | #VALUE! | 2016-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online |  | PRIVATE
NSTAR | Hyannis | 2182194 | 2601 | 19 | PV | 4-63-905 | 2016-10-12 | 2016-10-18 | #VALUE! |  | #VALUE! | 2016-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Westwood | 2182386 | 2090 | 480 | PV | 469-H3 | 2016-09-15 | 2016-10-18 | #VALUE! |  | #VALUE! | 2016-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Lexington | 2182387 | 2420 | 20 | PV | 391-H11 | 2016-05-23 | 2016-10-18 | #VALUE! |  | #VALUE! | 2016-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-15 | [6 empty] | 0 |  | 0 |  |  |  | isa sent |  | PRIVATE
NSTAR | Canton | 2182736 | 2021 | 980 | PV | 470-H7 | 2014-06-17 | 2014-06-17 | 0 |  | 0 | 2017-06-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-20 | 2014-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2016-09-09 | 2016-09-09 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2182805 | 2445 | 28 | PV | 350-H8 | 2016-10-21 | 2016-10-24 | #VALUE! |  | #VALUE! | 2016-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-22 | Online |  | PRIVATE | Y
NSTAR | Framingham | 2182806 | 1702 | 648 | PV | 240-H6 | 2016-10-03 | 2016-11-18 | #VALUE! |  | #VALUE! | 2016-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 2182807 | 2474 | 18 | PV | 5905 | 2016-10-18 | 2016-10-24 | #VALUE! |  | #VALUE! | 2016-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
NSTAR | Acton | 2182998 | 1720 | 288 | PV | 416-H4 | 2016-10-21 | 2016-10-24 | #VALUE! |  | #VALUE! | 2016-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2183002 | 2539 | 21.75 | PV | 4-97-97 | 2016-10-21 | 2016-10-27 | #VALUE! |  | #VALUE! | 2016-11-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2016-12-16 | [6 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online |  | PRIVATE
NSTAR | Natick | 2183182 | 1760 | 94.52 | PV | 240-H5 | 2016-10-18 | 2016-10-27 | #VALUE! |  | #VALUE! | 2016-11-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | Framingham | 2183183 | 1702 | 220 | Battery | 455-H5 | 2016-10-28 | 2016-11-14 | #VALUE! |  | #VALUE! | 2016-11-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2184042 | 2747 | 22 | PV | 2-523-523 | 2016-07-21 | 2016-10-28 | #VALUE! |  | #VALUE! | 2016-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-13 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | PRIVATE
NSTAR | Westwood | 2184045 | 2090 | 2310 | PV | 344-1412H1 | 2016-10-21 | 2016-10-31 | #VALUE! |  | #VALUE! | 2016-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-20 | 2017-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 2184047 | 1776 | 17.4 | PV | 342-H7 | 2016-10-25 | 2016-10-31 | #VALUE! |  | #VALUE! | 2016-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | isa sent |  | PRIVATE
NSTAR | Westwood | 2184048 | 2090 | 30.14 | PV | 148-H3 | 2016-10-24 | 2016-11-15 | #VALUE! |  | #VALUE! | 2016-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Canton | 2184049 | 2021 | 660 | PV | TBD | 2016-11-30 |  | #VALUE! | 0 | #VALUE! | 2016-12-08 | 2016-12-23 | #VALUE! | 8 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2184402 | 1760 | 720 | PV | 433-H12 | 2016-10-17 | 2016-10-31 | #VALUE! |  | #VALUE! | 2016-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Cambridge | 2184403 | 2140 | 2442 | PV | 828-1375 | 2016-10-24 | 2017-10-31 | #VALUE! |  | #VALUE! | 2016-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-08-16 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyde Park | 2184405 | 2136 | 510 | PV | TBD | 2016-12-01 |  | #VALUE! | 0 | #VALUE! | 2016-12-06 | 2016-12-23 | #VALUE! | 2 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2184406 | 2468 | 480 | PV | 292-H12 | 2016-10-24 | 2016-10-31 | #VALUE! |  | #VALUE! | 2016-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-19 | 2017-06-19 |  |  |  | 87 |  |  | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Dedham | 2184658 | 2026 | 66.6 | PV | 374-04 | 2016-10-31 | 2016-11-01 | #VALUE! |  | #VALUE! | 2016-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | East Falmouth | 2187033 | 2536 | 16.7 | PV | 4-98A-98A | 2016-10-27 | 2016-11-02 | #VALUE! |  | #VALUE! | 2016-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2016-12-15 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online |  | PRIVATE
NSTAR | Woburn | 2187229 | 1801 | 180 | PV | TBD | 2016-12-06 |  | #VALUE! | 0 | #VALUE! | 2016-12-09 | 2017-03-03 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-06 |  | 2017-07-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Hopkinton | 2187300 | 1748 | 2820 | PV | 455=H3 | 2016-11-18 | 2016-11-18 | 0 |  | 0 | 2016-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2187307 | 2138 | 23.4 | PV | 821-05 | 2016-11-21 | 2016-11-28 | #VALUE! |  | #VALUE! | 2016-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | 2017-02-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online |  | PRIVATE
NSTAR | Eastham | 2187463 | 2642 | 23.04 | PV | 4-94B-956 | 2016-11-15 | 2016-11-17 | #VALUE! |  | #VALUE! | 2016-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-18 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online |  | PRIVATE
NSTAR | Cambridge | 2187497 | 2139 | 60 | CHP | 831-1NC7 | 2016-10-31 | 2016-11-05 | #VALUE! |  | #VALUE! | 2016-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-26 | ISA Received |  | PRIVATE
NSTAR | Winchester | 2187499 | 1890 | 60 | PV | 211-H4 | 2016-11-07 | 2016-11-09 | #VALUE! |  | #VALUE! | 2016-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Weston | 2187501 | 2493 | 16.7 | PV | 450-H7 | 2016-11-10 | 2016-11-15 | #VALUE! |  | #VALUE! | 2016-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Woburn | 2187695 | 1801 | 15.875 | PV | 211-H8 | 2016-11-10 | 2016-11-15 | #VALUE! |  | #VALUE! | 2016-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online |  | PRIVATE
NSTAR | Mashpee | 2187699 | 2649 | 496 | PV | 4-88-455 | 2016-11-14 | 2016-11-16 | #VALUE! |  | #VALUE! | 2016-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Edgartown | 2187701 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | #VALUE! |  | #VALUE! | 2016-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-08-03 | Online |  | PRIVATE
NSTAR | Sandwich | 2187704 | 2542 | 4700 | Micro Grid | 4-98A-98A | 2016-12-07 | 2016-12-21 | #VALUE! |  | #VALUE! | 2016-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-20 | [7 empty] | 0 |  | 0 |  |  | 2019-10-17 | Online
NSTAR | Wareham | 2188254 | 2571 | 77.6 | PV | 3-84-968 | 2016-09-28 | 2016-12-09 | #VALUE! |  | #VALUE! | 2016-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | 2017-01-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online |  | PRIVATE
NSTAR | Edgartown | 2188255 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | #VALUE! |  | #VALUE! | 2016-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-08-23 | Online |  | PRIVATE
NSTAR | Assonett | 2188539 | 2702 | 16.7 | PV | 2-605-605 | 2016-11-17 | 2016-11-21 | #VALUE! |  | #VALUE! | 2016-12-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Wareham | 2188540 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11
NSTAR | Wareham | 2188541 | 2571 | 2000 | PV | 3-83-83 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2188542 | 2571 | 1500 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20 | Online
NSTAR | Wareham | 2188543 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20
NSTAR | Wareham | 2188544 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online
NSTAR | Hopkinton | 2188716 | 1748 | 990 | PV | 126-H1 | 2016-11-15 | 2016-11-21 | #VALUE! |  | #VALUE! | 2016-12-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-04 | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2188717 | 2717 | 4950 | PV | 2-102-102 | 2016-11-15 | 2016-11-21 | #VALUE! |  | #VALUE! | 2016-12-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2188718 | 2740 | 27 | PV | 2-73-47 | 2016-08-29 | 2016-10-28 | #VALUE! |  | #VALUE! | 2016-12-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-23 | Online |  | NO EXPORT | N
NSTAR | Wayland | 2189506 | 1778 | 93.275 | PV | 342-H3 | 2016-11-09 | 2016-11-22 | #VALUE! |  | #VALUE! | 2016-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-26 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online
NSTAR | Rochester | 2189508 | 2770 | 3300 | PV | 3-702-702 | 2016-11-15 | 2016-11-21 | #VALUE! |  | #VALUE! | 2016-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-04 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2189509 | 1748 | 2120 | PV | 126-H2 | 2016-11-17 | 2016-11-23 | #VALUE! |  | #VALUE! | 2016-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-04-18 | Online
NSTAR | Weston | 2190095 | 2493 | 115 | PV | 282-H1 | 2016-11-17 | 2016-11-23 | #VALUE! |  | #VALUE! | 2016-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-27 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-07-06 | Online
NSTAR | Bellingham | 2190097 | 2019 | 16.09 | PV | 65-H4 | 2016-11-22 | 2016-11-30 | #VALUE! |  | #VALUE! | 2016-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-28 | [7 empty] | 0 |  | 0 |  |  | 2017-09-18 | Online |  | PRIVATE
NSTAR | Westport | 2190239 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | #VALUE! |  | #VALUE! | 2016-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online |  | PRIVATE
NSTAR | Westport | 2190240 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | #VALUE! |  | #VALUE! | 2016-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Chilmark | 2191358 | 2535 | 65.2 | PV | 4-91-226 | 2016-11-22 | 2016-11-30 | #VALUE! |  | #VALUE! | 2016-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2191380 | 1801 | 86.4 | PV | 325-01 | 2016-11-29 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-30 | 2017-04-06 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
NSTAR | Hopkinton | 2191381 | 1748 | 28.8 | PV | 65-H6 | 2016-11-28 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-06-21 | Online |  | PRIVATE
NSTAR | Natick | 2191567 | 1760 | 20 | PV | 240-H5 | 2016-11-28 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-12-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-06-27 | Online |  | PRIVATE
NSTAR | Holliston | 2191568 | 1746 | 47.7 | PV | 65-H2 | 2016-12-02 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-12-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | 2017-02-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online |  | PRIVATE
NSTAR | North Dartmouth | 2193439 | 2747 | 15.34 | PV | 2-541-541 | 2016-11-30 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-01-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | North Dartmouth | 2193440 | 2747 | 15.2 | PV | 2-107-107 | 2016-11-29 | 2016-12-05 | #VALUE! |  | #VALUE! | 2016-01-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Burlington | 2193629 | 1803 | 19.75 | PV | 391-H6 | 2016-12-06 | 2016-12-08 | #VALUE! |  | #VALUE! | 2016-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-03-29 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online |  | PRIVATE
NSTAR | West Roxbury | 2193924 | 2132 | 300 | CHP | 496-H6 | 2016-12-06 | 2016-12-08 | #VALUE! |  | #VALUE! | 2017-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-27 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-01-24 | Online
NSTAR | Canton | 2195719 | 2021 | 128 | PV | 470-H4 | 2016-12-09 | 2016-12-13 | #VALUE! |  | #VALUE! | 2017-01-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20
NSTAR | Milton | 2195721 | 2186 | 17.4 | PV | 60-1409H1 | 2016-11-28 | 2016-12-13 | #VALUE! |  | #VALUE! | 2017-01-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-17 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online |  | PRIVATE
NSTAR | Cambridge | 2195978 | 2138 | 42 | PV | 828-1NC8 | 2016-12-08 | 2016-12-15 | #VALUE! |  | #VALUE! | 2017-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online |  | PRIVATE
NSTAR | Cambridge | 2195981 | 2138 | 214.2 | PV | 821-05 | 2016-12-08 | 2016-12-15 | #VALUE! |  | #VALUE! | 2017-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online
NSTAR | Boston | 2196194 | 2163 | 32 | PV | 817-03 | 2016-12-22 | 2016-12-29 | #VALUE! |  | #VALUE! | 2017-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-02-28 | [6 empty] | 0 |  | 0 | [5 empty] | PRIVATE
NSTAR | Woburn | 2196195 | 1801 | 119.9 | PV | 375-H3 | 2016-12-16 | 2016-12-27 | #VALUE! |  | #VALUE! | 2017-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-05-16 |  |  | EXP |  |  |  | 0 |  | 0 | [5 empty] | PRIVATE | Y
NSTAR | Rochester | 2196392 | 2770 | 3180 | PV | 3-702-702 | 2016-12-12 | 2016-12-15 | #VALUE! |  | #VALUE! | 2017-01-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-26 | 2017-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-05-01 | [7 empty] | 0 |  | 0 | [6 empty] | Y
NSTAR | Sherborn | 2196661 | 1770 | 75 | PV | 240-H1 | 2016-12-16 | 2016-12-28 | #VALUE! |  | #VALUE! | 2017-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-01-19 | [6 empty] | 0 |  | 0 |  |  | 2017-05-24 | Online
NSTAR | New Bedford | 2196803 | 2745 | 296 | PV | 2-101-101 | 2016-12-28 | 2016-12-30 | #VALUE! |  | #VALUE! | 2016-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-17 | [6 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | New Bedford | 2197507 | 2745 | 496 | PV | 2-152-152 | 2016-12-21 | 2016-12-30 | #VALUE! |  | #VALUE! | 2017-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-09 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online
NSTAR | Ashland | 2197716 | 1721 | 728 | PV |  | 2017-01-19 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2017-09-29 | 2018-05-30 | TBD |  | 30 | 2018-04-05 | 2018-04-05 | 0 |  | 0 |  | 2018-06-14 | 2018-06-15 | Online |  | Private
NSTAR | Natick | 2197718 | 1760 | 737 | PV | 339-1345H | 2016-12-21 | 2017-01-05 | #VALUE! |  | #VALUE! | 2017-01-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2197892 | 2360 | 21.6 | PV | 3-89-926 | 2016-11-16 | 2017-01-05 | #VALUE! |  | #VALUE! | 2017-01-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-08 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Hyannis | 2198079 | 2601 | 38 | PV | 4-63-63 | 2017-01-09 | 2017-01-11 | #VALUE! |  | #VALUE! | 2017-01-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-02-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-01 | Online |  | PRIVATE
NSTAR | Holliston | 2198478 | 1746 | 110 | Battery | 274-H3 | 2016-12-01 | 2017-01-12 | #VALUE! |  | #VALUE! | 2017-01-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | N/A | N
NSTAR | Natick | 2199089 | 1760 | 16.78 | PV | 433-H5 | 2017-01-11 | 2017-01-18 | #VALUE! |  | #VALUE! | 2017-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | PRIVATE
NSTAR | Woburn | 2199093 | 1801 | 8.35 | PV | 211-H2 | 2017-01-17 | 2017-01-20 | #VALUE! |  | #VALUE! | 2017-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Canton | 2199637 | 2021 | 16.7 | PV | 470-H11 | 2017-01-11 | 2017-01-20 | #VALUE! |  | #VALUE! | 2017-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 | [5 empty] | PRIVATE
NSTAR | Burlington | 2199843 | 1803 | 182.65 | PV | 391-H15 | 2017-01-11 | 2017-01-18 | #VALUE! |  | #VALUE! | 2017-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-21 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-24 | Online
NSTAR | Walpole | 2200165 | 2081 | 16.7 | PV | 146-H9 | 2017-01-11 | 2017-01-20 | #VALUE! |  | #VALUE! | 2017-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-04-24 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online |  | PRIVATE
NSTAR | Westport | 2200167 | 2790 | 15.2 | PV | 2-523-523 | 2017-01-11 | 2017-01-20 | #VALUE! |  | #VALUE! | 2017-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Sudbury | 2200633 | 1776 | 96 | PV | 342-H2 | 2017-02-09 | 2017-02-09 | 0 |  | 0 | 2017-02-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-31 | 2017-04-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-25 | Online |  | P2 | N
NSTAR | Dedham | 2200785 | 2026 | 153.2 | PV | 20-H1 | 2017-01-24 | 2017-01-25 | #VALUE! |  | #VALUE! | 2017-02-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2200960 | 1776 | 16.2 | PV | 375-H2 | 2017-01-24 | 2017-01-27 | #VALUE! |  | #VALUE! | 2017-02-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | East Freetown | 2200961 | 2717 | - |  | TBD | 2017-02-09 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-09-15 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Fairhaven | 2201063 | 2719 | 2000 | PV | 2-221-221 | 2017-01-31 | 2017-01-31 | 0 |  | 0 | 2017-02-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Sudbury | 2201274 | 1776 | 21.4 | PV | 342-H5 | 2017-02-03 | 2017-02-08 | #VALUE! |  | #VALUE! | 2017-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-06-06 | Online |  | PRIVATE
NSTAR | Vineyard Haven | 2201898 | 2568 | 166.5 | PV | 4-75-75 | 2017-01-30 | 2017-02-13 | #VALUE! |  | #VALUE! | 2017-02-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-18 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Plymouth | 2202211 | 2367 | 18.6 | PV | 3-51-43J1 | 2017-02-09 | 2017-02-13 | #VALUE! |  | #VALUE! | 2017-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-10 | [6 empty] | 0 |  | 0 |  |  | 2017-08-09 | Online |  | PRIVATE
NSTAR | Needham | 2202454 | 2492 | 69 | PV | 342-H5 | 2017-02-13 | 2017-02-13 | 0 |  | 0 | 2017-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-04-28 |  | YES | EXP |  |  |  | 0 |  | 0 |  |  | 2017-10-10 | Online |  | PRIVATE | Y
NSTAR | East Falmouth | 2202817 | 2536 | 109.25 | PV | 4-98A-98A | 2017-01-27 | 2017-02-13 | #VALUE! |  | #VALUE! | 2017-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | 2017-05-03 | [6 empty] | 0 |  | 0 |  |  | 2017-08-17 | Online |  | Private
NSTAR | Fairhaven | 2202964 | 2719 | 184 | PV | 2-240-209 | 2017-02-15 | 2017-02-15 | 0 |  | 0 | 2017-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Plymouth | 2203287 | 2360 | 208 | PV | 3-14-911 | 2017-01-31 | 2017-02-03 | #VALUE! |  | #VALUE! | 2017-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-04-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online |  | PRIVATE | Y
NSTAR | New Bedford | 2203288 | 2740 | 496 | PV | TBD | 2017-02-27 |  | #VALUE! | 0 | #VALUE! | 2017-03-01 | 2017-04-07 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-29 |  | 2017-10-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hopkinton | 2203698 | 1748 | 1980 | PV | 126-H4 | 2015-08-14 | 2015-08-14 | 0 |  | 0 | 2015-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-03-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Woburn | 2204382 | 1801 | 17.4 | PV | 211-H10 | 2017-02-17 | 2017-02-23 | #VALUE! |  | #VALUE! | 2017-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Kingston | 2204685 | 2364 | 366.4 | PV | 3-26-902 | 2017-02-03 | 2017-02-09 | #VALUE! |  | #VALUE! | 2017-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2205487 | 1801 | 17.4 | PV | 211-H5 | 2017-02-17 | 2017-02-23 | #VALUE! |  | #VALUE! | 2017-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-27 | 2017-03-28 | [6 empty] | 0 |  | 0 |  |  | 2017-11-15 | Online |  | PRIVATE
NSTAR | West Roxbury | 2205777 | 2132 | 300 | Fuel Cell & Battery | 496-H3 | 2017-02-09 | 2017-02-27 | #VALUE! |  | #VALUE! | 2017-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-27 | 2017-11-03 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Arlington | 2206239 | 2474 | 16.45 | PV | 211-H11 | 2017-03-01 | 2017-03-03 | #VALUE! |  | #VALUE! | 2017-03-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Westwood | 2206500 | 2090 | 20 | PV | 148-H3 | 2017-02-28 | 2017-03-06 | #VALUE! |  | #VALUE! | 2017-03-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-25 | 2017-04-26 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online |  | PRIVATE
NSTAR | Boston | 2206844 | 2130 | 75 | CHP | 536-76H2 | 2016-12-08 | 2017-03-08 | #VALUE! |  | #VALUE! | 2017-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-24 | Online
NSTAR | Woburn | 2207029 | 1801 | 576 | PV | 258-1394H2 | 2017-03-09 | 2017-03-10 | #VALUE! |  | #VALUE! | 2017-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-17 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Cambridge | 2207242 | 2139 | 75 | CHP | 817-03 | 2017-03-08 | 2017-03-20 | #VALUE! |  | #VALUE! | 2017-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-06-21 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2207411 | 2142 | 35 | CHP | 875-1328 | 2017-03-10 | 2017-03-20 | #VALUE! |  | #VALUE! | 2017-03-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-09-07 | Online |  | PRIVATE | Y
NSTAR | Cambridge | 2207804 | 2142 | 35 | CHP | 875-1343 | 2017-03-10 | 2017-03-20 | #VALUE! |  | #VALUE! | 2017-03-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  | NO | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26 |  |  | PRIVATE
NSTAR | Canton | 2207988 | 2021 | 19.8 | PV | 269-1320H1 | 2017-03-06 | 2017-03-20 | #VALUE! |  | #VALUE! | 2017-03-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | New Bedford | 2208391 | 2740 | 36 | PV | 2-59-96 | 2017-02-20 | 2017-03-20 | #VALUE! |  | #VALUE! | 2017-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-02 | 2017-05-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online |  | PRIVATE
NSTAR | Natick | 2208547 | 1760 | 449.5 | PV | 433-H5 | 2017-02-10 | 2017-03-23 | #VALUE! |  | #VALUE! | 2017-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE | N
NSTAR | Natick | 2209451 | 1760 | 466.2 | PV | 433-H12 | 2017-02-10 | 2017-03-23 | #VALUE! |  | #VALUE! | 2017-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE | N
NSTAR | Wareham | 2209835 | 2571 | - |  | TBD | 2017-04-06 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2018-05-01 | 2018-03-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2210401 | 2747 | 20.35 | PV | 274-H3 | 2017-03-22 | 2017-03-28 | #VALUE! |  | #VALUE! | 2017-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-30 | 2017-06-30 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Onset | 2210632 | 2558 | 19.5 | PV | 3-84-17J1 | 2017-03-22 | 2017-03-28 | #VALUE! |  | #VALUE! | 2017-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-19 | [7 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online |  | PRIVATE
NSTAR | Plympton | 2211077 | 2367 | 4950 | PV & Battery | 3-15-901 | 2017-03-30 | 2017-04-05 | #VALUE! |  | #VALUE! | 2017-04-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-11 | 2017-05-11 | #VALUE! |  | #VALUE! | 2017-09-01 | 2017-08-10 | #VALUE! |  | #VALUE! | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2211409 | 2129 | 403.2 | PV & Battery | 5-208H/22-208 | 2017-03-16 | 2017-04-01 | #VALUE! |  | #VALUE! | 2017-04-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-06 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2018-02-13 | Online
NSTAR | Woburn | 2211603 | 1801 | 20.35 | PV | 211-H8 | 2017-03-30 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
NSTAR | Millis | 2211983 | 2054 | 350.4 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2211985 | 2054 | 175.2 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2212591 | 2090 | 858 | PV | 469-H6 | 2017-03-30 | 2017-04-05 | #VALUE! |  | #VALUE! | 2017-04-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2212756 | 2021 | 330 | PV | 470-H1 | 2017-03-30 | 2017-04-05 | #VALUE! |  | #VALUE! | 2017-04-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-26 | Online
NSTAR | Wayland | 2212763 | 1778 | 15.2 | PV | 342-H1 | 2017-03-31 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Woburn | 2212768 | 1801 | 16.7 | PV | 211-H13 | 2017-03-31 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-01 | 2017-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20 | Online
NSTAR | Burlington | 2212942 | 1803 | 16.95 | PV | 391-H7 | 2017-03-31 | 2017-04-10 | #VALUE! |  | #VALUE! | 2017-04-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-27 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2213109 | 1803 | 176.4 | PV | 211-H13 | 2017-03-10 | 2017-04-11 | #VALUE! |  | #VALUE! | 2017-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2213428 | 2360 | 210 | PV & Battery | 3-13-943 | 2017-04-07 | 2017-04-11 | #VALUE! |  | #VALUE! | 2017-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-20 | 2017-07-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Cambridge | 2214153 | 2412 | 47.5 | PV | 875-1N38A | 2017-03-01 | 2017-04-13 | #VALUE! |  | #VALUE! | 2017-05-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-02 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2214303 | 2630 | 373 | PV | 4-84B-524 | 2017-04-12 | 2017-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-25 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-04-09 | Online
NSTAR | Lincoln | 2214304 | 1773 | 24 | PV | 320-H8 | 2017-04-12 | 2017-04-18 | #VALUE! |  | #VALUE! | 2017-05-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-07 | 2017-06-20 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Canton | 2214562 | 2021 | 462 | PV | 470-H11 | 2017-04-13 | 2017-04-14 | #VALUE! |  | #VALUE! | 2017-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2018-12-27 |  | 2018-12-28 | Online
NSTAR | Cambridge | 2214784 | 2139 | 14.4 | PV | 831-1NC7 | 2017-03-31 | 2017-04-11 | #VALUE! |  | #VALUE! | 2017-05-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-25 | 2018-03-01 | [6 empty] | 0 |  | 0 |  |  | 2018-09-07 | Online
NSTAR | Chatham | 2214785 | 2659 | 47 | PV | 4-95A-95A | 2017-04-11 | 2017-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | Carver | 2214971 | 2330 | 30 | PV | 3-81-950 | 2017-04-13 | 2017-04-21 | #VALUE! |  | #VALUE! | 2017-05-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-05 | 2017-07-14 | [6 empty] | 0 |  | 0
NSTAR | Walpole | 2215756 | 2081 | 19.15 | PV | 146-H3 | 2017-04-14 | 2017-04-24 | #VALUE! |  | #VALUE! | 2017-05-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2215757 | 2180 | 16.7 | PV | 375-H8 | 2017-04-14 | 2017-04-24 | #VALUE! |  | #VALUE! | 2017-05-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-25 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2216193 | 2571 | 17.575 | PV | 3-84-963 | 2017-04-14 | 2017-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-10-27 | Online
NSTAR | Osterville | 2216608 | 2655 | 18.91 | PV | 4-80A-490 | 2017-04-19 | 2017-04-26 | #VALUE! |  | #VALUE! | 2017-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2017-09-12 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03
NSTAR | Chelsea | 2217046 | 2150 | 996 | PV | 14-113H1 | 2017-04-20 | 2017-04-27 | #VALUE! |  | #VALUE! | 2017-05-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-11 | 2017-07-12 | [6 empty] | 0 |  | 0 | 2018-12-28
NSTAR | Burlington | 2217047 | 1803 | 180 | PV | 346-1395H1 | 2017-04-21 | 2017-05-01 | #VALUE! |  | #VALUE! | 2017-05-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2217262 | 2747 | 210 | Fuel Cell | 2-531-531 | 2017-05-02 | 2017-05-02 | 0 |  | 0 | 2017-05-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Woburn | 2217434 | 1801 | 224.25 | PV | 375-H4 | 2017-05-01 | 2017-05-02 | #VALUE! |  | #VALUE! | 2017-05-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-22 | Online
NSTAR | Cambridge | 2217599 | 2141 | 153.2 | PV | 875-1N36B | 2017-04-25 | 2017-05-03 | #VALUE! |  | #VALUE! | 2017-05-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-25 | 2017-08-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Yarmouth | 2217600 | 2673 | 1560 | PV | 4-92A-92A | 2017-05-08 | 2017-06-13 | #VALUE! |  | #VALUE! | 2017-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2217818 | 2740 | 1070 | PV | 2-151-151 | 2017-05-08 | 2017-06-13 | #VALUE! |  | #VALUE! | 2017-06-16 | 2017-06-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-01-22 | [7 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Westwood | 2218004 | 2090 | 302 | PV | 469-H6 | 2017-05-09 | 2017-05-16 | #VALUE! |  | #VALUE! | 2017-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-02 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-10-29 | Online |  | Private
NSTAR | Plymouth | 2218005 | 2360 | 1176 | PV | 3-12-12 | 2017-05-08 | 2017-06-13 | #VALUE! |  | #VALUE! | 2017-06-16 | 2017-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-10 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-22 | Online
NSTAR | Sandwich | 2218204 | 2563 | 70 | PV | 4-81B-443 | 2017-05-11 | 2017-05-17 | #VALUE! |  | #VALUE! | 2017-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-06 | [6 empty] | 0 |  | 0 |  |  | 2018-04-19 | Online
NSTAR | Wareham | 2218205 | 2571 | 210 | Fuel Cell | 3-84-961 | 2017-05-11 | 2017-05-17 | #VALUE! |  | #VALUE! | 2017-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 1900-04-05 | 2017-06-20 | [5 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Norfolk | 2218206 | 2056 | 72 | PV | 146-H3 | 2017-05-01 | 2017-05-19 | #VALUE! |  | #VALUE! | 2017-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-10-06 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2218766 | 1748 | 16.7 | PV | 65-H6 | 2017-05-15 | 2017-05-22 | #VALUE! |  | #VALUE! | 2017-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2219177 | 2747 | 2300 | PV | 2-543-543 | 2017-05-01 | 2017-05-19 | #VALUE! |  | #VALUE! | 2017-06-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-29 | Online
NSTAR | Roxbury | 2219411 | 2119 | 24 | PV | 483-H6 | 2017-05-13 | 2017-05-22 | #VALUE! |  | #VALUE! | 2017-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-17 | 2017-09-20 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | New Bedford | 2219644 | 2745 | 336 | PV | 2-88-18 | 2017-05-19 | 2017-05-22 | #VALUE! |  | #VALUE! | 2017-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-06-26 | [6 empty] | 0 |  | 0 |  |  | 2017-12-29 | Online
NSTAR | Falmouth | 2219873 | 2540 | 54.88 | PV | 4-72-433 | 2017-05-23 | 2017-05-25 | #VALUE! |  | #VALUE! | 2017-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2220027 | 2453 | 72 | PV | 282-H8 | 2017-05-01 | 2017-05-23 | #VALUE! |  | #VALUE! | 2017-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-09-18 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2220029 | 2576 | 18 | PV | 3-85-85 | 2017-05-24 | 2017-05-30 | #VALUE! |  | #VALUE! | 2017-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online
NSTAR | Dorchester | 2220311 | 2124 | 45.15 | PV | 483-H7 | 2017-03-22 | 2017-03-28 | #VALUE! |  | #VALUE! | 2017-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-07-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-23 | Online |  | PRIVATE
NSTAR | Ashland | 2220527 | 1721 | 4450 | PV | 274-1429H1 | 2017-05-16 | 2017-05-22 | #VALUE! |  | #VALUE! | 2017-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-29 | 2017-09-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2221535 | 2330 | 2000 | PV | 3-10-10 | 2017-05-19 | 2017-05-30 | #VALUE! |  | #VALUE! | 2017-06-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-11-20 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2019-05-17 | Online
NSTAR | North Dartmouth | 2223159 | 2747 | 100.8 | PV | 2-532-532 | 2017-05-22 | 2017-05-31 | #VALUE! |  | #VALUE! | 2017-06-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Newton | 2223207 | 2465 | 17.75 | PV | 292-H12 | 2017-05-22 | 2017-06-02 | #VALUE! |  | #VALUE! | 2017-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-24 | 2017-09-13 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online
NSTAR | Dedham | 2223211 | 2026 | 135 | CHP | 20-H6 | 2017-05-26 | 2017-06-05 | #VALUE! |  | #VALUE! | 2017-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2223213 | 2053 | 20 | PV | 65-H5 | 2017-05-16 | 2017-06-05 | #VALUE! |  | #VALUE! | 2017-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-04 | 2017-08-09 | [6 empty] | 0 |  | 0 |  |  | 2017-10-02 | Online
NSTAR | Woburn | 2223988 | 2116 | 602 | PV | 375-H9 | 2017-06-05 | 2017-06-07 | #VALUE! |  | #VALUE! | 2017-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2223989 | 2739 | 43.17 | PV | 2-301-301 | 2017-06-02 | 2017-06-08 | #VALUE! |  | #VALUE! | 2017-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-26 | 2017-08-17 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2223990 | 1720 | 167 | PV | 416-H4 | 2017-06-07 | 2017-06-15 | #VALUE! |  | #VALUE! | 2017-07-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2224177 | 2054 | 17.1 | PV | 65-H1 | 2017-06-01 | 2017-06-19 | #VALUE! |  | #VALUE! | 2017-07-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-08 | 2017-10-04 | [6 empty] | 0 |  | 0 |  |  | 2018-01-03 | Online
NSTAR | West Roxbury | 2224405 | 2132 | 498 | PV | 496-H3 | 2017-06-09 | 2017-06-19 | #VALUE! |  | #VALUE! | 2017-07-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2224625 | 2452 | 499.5 | PV | 277-1367XYH | 2017-06-28 | 2017-07-03 | #VALUE! |  | #VALUE! | 2017-07-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-21 | Online
NSTAR | Fairhaven | 2224661 | 2702 | 4900 | PV | 2-605-605 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2224664 | 2571 | 3300 | PV | 3-85-928 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-12-06 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-12-12 | Online
NSTAR | Freetown | 2224890 | 2702 | 4900 | PV | 2-102-102 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2225509 | 2125 | 210 | Fuel Cell | 106-H4 | 2017-06-15 | 2017-06-19 | #VALUE! |  | #VALUE! | 2017-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2019-04-04 | Online
NSTAR | Kingston | 2225512 | 2364 | 20.4 | PV | 3-18-36J1 | 2017-06-08 | 2017-06-20 | #VALUE! |  | #VALUE! | 2017-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-20 | 2017-07-21 | [6 empty] | 0 |  | 0 |  |  | 2017-09-05 | Online
NSTAR | Waltham | 2226333 | 2453 | 180 | PV | 282-H8 | 2017-06-01 | 2017-06-20 | #VALUE! |  | #VALUE! | 2017-07-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Dorchester | 2226367 | 2021 | 56.35 | PV | 143-109H4 | 2017-06-12 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | West Newton | 2226368 | 2465 | 15.95 | PV | 282-H9 | 2017-06-15 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-29 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Brewster | 2226549 | 2631 | 19.2 | PV | 4-89B-576 | 2017-06-23 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-01 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online
NSTAR | Framingham | 2226553 | 1702 | 120 | PV | 240-H4 | 2017-06-26 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Natick | 2226744 | 1760 | 497 | PV | 240-H1 | 2017-06-26 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-05-01 | [6 empty] | 0 |  | 0
NSTAR | Lexington | 2226745 | 2421 | 860.6 | PV | 450-H5 | 2017-06-27 | 2017-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | New Bedford | 2227188 | 2745 | 499.05 | PV | 2-107-107 | 2017-06-16 | 2017-07-10 | #VALUE! |  | #VALUE! | 2017-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2017-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | New Bedford | 2227197 | 2740 | 700 | PV | 2-152-152 | 2017-06-15 | 2017-06-29 | #VALUE! |  | #VALUE! | 2017-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | [7 empty] | 0 |  | 0 | 2018-12-21 |  | 2018-12-21
NSTAR | Maynard | 2227357 | 1754 | 3516 | PV | 416-H6 | 2017-06-22 | 2017-07-06 | #VALUE! |  | #VALUE! | 2017-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-19 | 2018-02-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-11-20 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Orleans | 2227358 | 2653 | 58.6 | PV | 4-83-952 | 2017-06-05 | 2017-06-15 | #VALUE! |  | #VALUE! | 2017-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Plymouth | 2227360 | 2360 | 18 | PV | 3-89-926 | 2017-06-27 | 2017-07-06 | #VALUE! |  | #VALUE! | 2017-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-02 | [6 empty] | 0 |  | 0 |  |  | 2017-12-11 | Online
NSTAR | Westport | 2227530 | 2790 | 480 | PV | 2-523-523 | 2017-05-09 | 2017-06-28 | #VALUE! |  | #VALUE! | 2017-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | New Bedford | 2227939 | 2745 | 632.7 | PV | 2-83-83 | 2017-06-30 | 2017-07-07 | #VALUE! |  | #VALUE! | 2017-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-11-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2227941 | 1702 | 1095.78 | PV | 240-H6 | 2017-06-26 | 2017-07-06 | #VALUE! |  | #VALUE! | 2017-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Weston | 2228145 | 2493 | 24.82 | PV | 282-H1 | 2017-06-27 | 2017-07-11 | #VALUE! |  | #VALUE! | 2017-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-21 | 2017-08-25 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Westport | 2228336 | 2790 | 2000 | PV | 2-524-524 | 2017-07-03 | 2017-07-11 | #VALUE! |  | #VALUE! | 2017-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-12-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2228337 | 2601 | 997.965 | PV | 4-80B-80B | 2017-06-13 | 2017-07-12 | #VALUE! |  | #VALUE! | 2017-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | West Yarmouth | 2228338 | 2673 | 39 | PV | 4-64-536 | 2017-06-26 | 2017-07-12 | #VALUE! |  | #VALUE! | 2017-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-26 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Falmouth | 2228808 | 2536 | 7190 | PV | 4-98A-429 | 2017-06-30 | 2017-07-12 | #VALUE! |  | #VALUE! | 2017-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-23 | 2018-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
NSTAR | Mattapoisett | 2229139 | 2739 | - |  | TBD | 2017-08-07 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-03-16 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
NSTAR | Dorchester | 2229211 | 2121 | 40.7 | PV | 483-H2 | 2017-07-10 | 2017-07-17 | #VALUE! |  | #VALUE! | 2017-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dover | 2229213 | 2030 | 28 | PV | 456-H3 | 2017-07-07 | 2017-07-19 | #VALUE! |  | #VALUE! | 2017-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2229434 | 1746 | 44 | PV | 130-H1 | 2017-07-18 | 2017-07-21 | #VALUE! |  | #VALUE! | 2017-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-23 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Norfolk | 2229611 | 2056 | 34.5 | PV | 146-H3 | 2017-07-11 | 2017-07-19 | #VALUE! |  | #VALUE! | 2017-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Holliston | 2229612 | 1746 | 15.2 | PV | 130-H1 | 2017-06-16 | 2017-07-19 | #VALUE! |  | #VALUE! | 2017-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-01 | Online
NSTAR | Acton | 2229787 | 1720 | 22.8 | PV | 416-H4 | 2017-07-10 | 2017-07-24 | #VALUE! |  | #VALUE! | 2017-08-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2229788 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-08-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Natick | 2229922 | 1760 | 466.2 | PV | 433-H10 | 2017-07-18 | 2017-07-20 | #VALUE! |  | #VALUE! | 2017-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-04 | 2018-01-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online |  | Private
NSTAR | Natick | 2229933 | 1760 | 466.2 | PV | 433-H14 | 2017-07-18 | 2017-07-20 | #VALUE! |  | #VALUE! | 2017-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-02 | 2017-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-05-04 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2019-11-20 | Online
NSTAR | Dorchester | 2229935 | 2124 | 24 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-30 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Wareham | 2230372 | 2576 | 24.5 | PV | 3-85-85 | 2017-07-14 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-08 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2230376 | 1748 | 3960 | PV | 126-H2 | 2017-07-21 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2230557 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2230560 | 2081 | 590 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-08-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dorchester | 2230829 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231017 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231474 | 2121 | 32.85 | PV | 143-109H4 | 2017-07-17 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231481 | 2124 | 30 | PV | 143-109H4 | 2017-07-18 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231678 | 2121 | 36 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2017-12-04 | Online
NSTAR | Dorchester | 2231683 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | #VALUE! |  | #VALUE! | 2017-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Walpole | 2231849 | 2081 | 402 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | #VALUE! |  | #VALUE! | 2017-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2231851 | 2081 | 362 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | #VALUE! |  | #VALUE! | 2017-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Lexington | 2231852 | 2420 | 25 | PV | 533-H3 | 2017-07-07 | 2017-07-27 | #VALUE! |  | #VALUE! | 2017-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Sandwich | 2232261 | 2563 | 66.6 | PV | 4-81B-81B | 2017-07-23 | 2017-07-31 | #VALUE! |  | #VALUE! | 2017-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2018-01-02 | [6 empty] | 0 |  | 0 |  |  | 2018-04-16 | Online
NSTAR | Dorchester | 2232263 | 2124 | 48 | PV | 483-H7 | 2017-07-27 | 2017-07-31 | #VALUE! |  | #VALUE! | 2017-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Bourne | 2232421 | 2532 | 36 | PV | 3-89-925 | 2017-07-25 | 2017-07-31 | #VALUE! |  | #VALUE! | 2017-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-13 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Dorchester | 2232422 | 2124 | 43.2 | PV | 483-H5 | 2017-07-27 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online
NSTAR | Dorchester | 2232784 | 2124 | 72 | PV | 483-H4 | 2017-07-27 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-22 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03 | Online
NSTAR | Walpole | 2233507 | 2081 | 336 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2233722 | 2081 | 368 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2019-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-07-03 | Online
NSTAR | Walpole | 2233726 | 2081 | 662 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Wareham | 2233733 | 2576 | 2000 | PV | 3-85-85 | 2017-07-31 | 2017-08-01 | #VALUE! |  | #VALUE! | 2017-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-26 | 2018-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Woods Hole | 2233739 | 2540 | 86.4 | PV | 4-72-433 | 2017-08-03 | 2017-08-03 | 0 |  | 0 | 2017-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-06-08 | Online
NSTAR | Falmouth | 2233941 | 2540 | 33.3 | PV | 4-72-433 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | West Tisbury | 2233942 | 2575 | 48 | PV | 4-97-220 | 2017-08-02 | 2017-08-08 | #VALUE! |  | #VALUE! | 2017-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2234087 | 2081 | 24 | PV | 456-H1 | 2017-08-01 | 2017-08-15 | #VALUE! |  | #VALUE! | 2017-09-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-17 | 2017-10-17 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2234091 | 2081 | 782 | PV | 146-H1 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2234593 | 2081 | 132 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | #VALUE! |  | #VALUE! | 2017-09-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dartmouth | 2234626 | 2747 | 594 | PV | 2-532-532 | 2017-08-08 | 2017-08-11 | #VALUE! |  | #VALUE! | 2017-09-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2234823 | 1721 | 1080 | PV | 274-1429H1 | 2017-08-02 | 2017-08-15 | #VALUE! |  | #VALUE! | 2017-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2234830 | 2330 | 21.9 | PV | 3-10-929 | 2017-08-10 | 2017-08-15 | #VALUE! | 0 | #VALUE! | 2017-09-13 |  | #VALUE! | 6 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-24 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Woburn | 2234836 | 1801 | 16.7 | PV | 375-H12 | 2017-08-09 | 2017-08-15 | #VALUE! |  | #VALUE! | 2017-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-12-05 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2234838 | 1801 | 16.7 | PV | 375-H14 | 2017-08-09 | 2017-08-15 | #VALUE! |  | #VALUE! | 2017-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2235080 | 2131 | 180 | PV | 385-H15 | 2017-07-06 | 2017-08-15 | #VALUE! |  | #VALUE! | 2017-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2235082 | 1748 | 59 | PV | 126-H2 | 2017-08-01 | 2017-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-23 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-04-11 | Online
NSTAR | Barnstable | 2235087 | 2090 | 3720 | PV | 4-88-453 | 2017-08-17 | 2017-08-18 | #VALUE! |  | #VALUE! | 2017-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-26 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2235287 | 1802 | 42 | PV | 240-H3 | 2017-08-16 | 2017-08-22 | #VALUE! |  | #VALUE! | 2017-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2018-05-29 | Online
NSTAR | Barnstable | 2235688 | 2571 | 472 | PV | 4-80B-80B | 2017-07-24 | 2017-10-17 | #VALUE! |  | #VALUE! | 2017-11-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2235692 | 2134 | 133.2 | PV | 250-1N39H1 | 2017-08-22 | 2017-08-28 | #VALUE! |  | #VALUE! | 2017-10-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-16 | 2017-10-19 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Hyannis | 2235860 | 2601 | 28.8 | PV | 4-84B-524 | 2017-08-25 | 2017-08-29 | #VALUE! |  | #VALUE! | 2017-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-05 | 2018-01-12 | [6 empty] | 0 |  | 0 |  |  | 2018-02-08 | Online
NSTAR | Wareham | 2236093 | 2571 | 46.8 | PV | 3-85-964 | 2017-08-07 | 2017-08-29 | #VALUE! |  | #VALUE! | 2017-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-27 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Natick | 2236094 | 1760 | 51.75 | PV | 433-H9 | 2017-08-29 | 2017-08-30 | #VALUE! |  | #VALUE! | 2017-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-10-25 | [6 empty] | 0 |  | 0 |  |  | 2018-03-23 | Online
NSTAR | Canton | 2236306 | 2021 | 208 | PV | 470-H11 | 2017-08-24 | 2017-08-30 | #VALUE! |  | #VALUE! | 2017-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2236312 | 2126 | 30.5 | PV | 311-12 | 2017-08-31 | 2017-08-31 | 0 |  | 0 | 2017-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Ashland | 2236318 | 1721 | 92 | PV | 274-1429H1 | 2017-08-31 | 2017-09-01 | #VALUE! |  | #VALUE! | 2017-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2236710 | 2026 | 170 | PV | 20-H6 | 2017-08-31 | 2017-09-05 | #VALUE! |  | #VALUE! | 2017-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-07 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2019-06-25 | Online
NSTAR | Boston | 2236712 | 2115 | 15.2 | PV | 2-1N45 | 2017-08-31 | 2017-09-05 | #VALUE! |  | #VALUE! | 2017-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-18 | 2017-12-19 | [6 empty] | 0 |  | 0 |  |  | 2018-04-24 | Online
NSTAR | Boston | 2236713 | 2215 | 21.9 | PV | 350-H10 | 2017-08-31 | 2017-09-05 | #VALUE! |  | #VALUE! | 2017-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-08 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Yarmouth | 2236910 | 2675 | 23.2 | PV | 4-90-541 | 2017-09-01 | 2017-09-06 | #VALUE! |  | #VALUE! | 2017-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-26 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2236911 | 1803 | 27.9 | PV | 346-1395H1 | 2017-09-01 | 2017-09-06 | #VALUE! |  | #VALUE! | 2017-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2237110 | 2536 | 159.9 | PV | 4-98B-449 | 2017-09-06 | 2017-09-08 | #VALUE! |  | #VALUE! | 2017-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-21 | [6 empty] | 0 |  | 0 |  |  | 2018-06-28 | Online
NSTAR | Wellfleet | 2237326 | 2667 | 17.92 | PV | 4-96-960 | 2017-09-07 | 2017-09-14 | #VALUE! |  | #VALUE! | 2017-09-29 | 2017-10-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-10-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Westport | 2237335 | 2790 | 268 | PV | 2-532-532 | 2017-09-06 | 2017-09-14 | #VALUE! |  | #VALUE! | 2017-09-29 | 2017-10-16 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-12-27 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2237797 | 2571 | 294 | PV | 3-86-966 | 2017-09-06 | 2017-09-11 | #VALUE! |  | #VALUE! | 2017-10-03 | 2017-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marshfield | 2237799 | 2050 | 27.5 | PV | 3-25-42J2 | 2017-08-22 | 2017-09-13 | #VALUE! |  | #VALUE! | 2017-10-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-11 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Plymouth | 2238366 | 2360 | 499.5 | PV | 3-14-911 | 2017-05-15 | 2017-09-13 | #VALUE! |  | #VALUE! | 2017-10-04 | 2017-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2019-02-11
NSTAR | Hopkinton | 2238660 | 1748 | 7520 | PV | 126-H2 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2238661 | 2717 | 1156 | PV & Battery |  | 2017-10-04 | 2017-10-06 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2019-05-16 | #VALUE! | 333 | #VALUE! |  |  | 0 |  | 0 | 2019-06-25 | 2019-07-10 | #VALUE! | 0 | #VALUE! | 2019-02-25 | 2019-08-01 | 2020-03-01 | No |  | 60 | 2020-01-30 |  | #VALUE! |  | #VALUE! |  |  |  | In Queue |  | Private | N
NSTAR | Cambridge | 2238845 | 2139 | 1330 | PV | 875-1312 | 2017-06-02 | 2017-10-05 | #VALUE! |  | #VALUE! | 2017-10-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-09 | 2018-01-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online |  | Public
NSTAR | Buzzards Bay | 2239274 | 2532 | 119.9 | PV | 3-88-2J4 | 2017-09-12 | 2017-09-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Plympton | 2239531 | 2367 | 4695 | PV & Battery | TBD | 2017-09-17 | 2017-09-17 | 0 |  | 0 | 2017-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-21 | Online
NSTAR | Brighton | 2239744 | 2134 | 7500 | CHP |  | 2017-10-04 | 2017-10-04 | 0 |  | 0 | 2017-10-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-26 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Dartmouth | 2239746 | 2747 | 997.7 | PV | 2-543-543 | 2017-09-11 | 2017-09-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2239974 | 1801 | 57.5 | PV | 4W5-H1 | 2017-09-07 | 2017-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-07-20 | Online
NSTAR | Roslindale | 2240297 | 2131 | 338 | PV | 496-H4 | 2017-09-12 | 2017-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Waltham | 2240718 | 2452 | 266.4 | PV | 450-H4 | 2017-09-21 | 2017-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2018-07-06 | Online
NSTAR | Plymouth | 2240998 | 2360 | - |  | TBD | 2017-10-18 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sharon | 2241001 | 2067 | 272 | PV | 146-H1 | 2017-10-04 | 2017-10-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-28 | 2018-08-30 | [6 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online |  | Private
NSTAR | Acton | 2241211 | 1720 | 22.8 | PV | 416-H8 | 2017-09-22 | 2017-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-28 | 2017-12-05 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2241214 | 2364 | 33.3 | PV | 3-17-17 | 2017-09-27 | 2017-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Milton | 2241676 | 2186 | 21.9 | PV | 362-02 | 2017-10-03 | 2017-10-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-10 | 2017-11-13 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online
NSTAR | South Yarmouth | 2241680 | 2664 | 124.47 | PV | 4-92A-562 | 2017-09-27 | 2017-10-03 | #VALUE! |  | #VALUE! | 2017-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Dartmouth | 2241682 | 2748 | 22.8 | PV | 2-528-528 | 2017-10-02 | 2017-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-09 | Online
NSTAR | Framingham | 2242066 | 1702 | 20 | PV | 455-H5 | 2017-08-30 | 2017-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2242067 | 1748 | 299.7 | PV | 126-H1 | 2017-09-29 | 2017-10-10 | #VALUE! |  | #VALUE! | 2017-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
NSTAR | Waltham | 2242293 | 2451 | 210 | PV | 450-H1 | 2017-10-10 | 2017-10-31 | #VALUE! |  | #VALUE! | 2017-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-19 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Roxbury | 2242468 | 2119 | 15.5 | PV | 52-148H1 | 2017-09-13 | 2017-10-17 | #VALUE! |  | #VALUE! | 2017-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-29 | 2017-12-07 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Framingham | 2243010 | 1702 | 256 | PV | 455-H4 | 2017-10-04 | 2017-10-18 | #VALUE! |  | #VALUE! | 2017-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-08-06 | Online
NSTAR | Barnstable | 2243747 | 2668 | 33.6 | PV | 4-82-516 | 2017-10-10 | 2017-10-18 | #VALUE! |  | #VALUE! | 2017-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-09-17 | Online
NSTAR | Vineyard Haven | 2243750 | 2658 | 22 | PV | 4-91-228 | 2017-10-16 | 2017-10-18 | #VALUE! |  | #VALUE! | 2017-11-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | 2018-08-09 | [6 empty] | 0 |  | 0 |  |  |  | Revised ISA/WO (2287709)
NSTAR | Westport | 2243995 | 2790 | 2400 | PV | 2-532-532 | 2017-10-04 | 2017-10-13 | #VALUE! |  | #VALUE! | 2017-11-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-14 | Online
NSTAR | Oak Bluffs | 2244459 | 2557 | 20.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2244463 | 2557 | 27.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2244680 | 2139 | 33.3 | PV | 814-13 | 2017-10-17 | 2017-10-19 | #VALUE! |  | #VALUE! | 2017-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2244684 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | #VALUE! |  | #VALUE! | 2017-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | West Roxbury | 2244833 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | #VALUE! |  | #VALUE! | 2017-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Waltham | 2245190 | 2451 | 599 | PV | TBD | 2017-11-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Waltham | 2245192 | 2451 | 599 | PV | 450-H2 | 2017-10-10 | 2017-10-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2245194 | 2451 | 632.7 | PV | 282-H5 | 2017-08-15 | 2017-10-27 | #VALUE! |  | #VALUE! | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2245195 | 2539 | 74.4 | PV | 4-97-97 | 2017-10-18 | 2017-10-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-04 | Online
NSTAR | South Carver | 2245475 | 2366 | 88 | PV | 3-81-81 | 2017-10-23 | 2017-10-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Ashland | 2245647 | 1721 | 773.6 | PV | 274-H1 | 2017-11-02 | 2017-11-02 | 0 |  | 0 | 2017-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2245650 | 1773 | 199.8 | PV | 320-H6 | 2017-09-26 | 2017-11-02 | #VALUE! |  | #VALUE! | 2018-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-03 | 2018-02-15 | [6 empty] | 0 |  | 0 |  |  | 2018-10-04 | Online
NSTAR | Plymouth | 2245961 | 2360 | 48 | PV | 3-13-936 | 2017-10-19 | 2017-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-30 | Online
NSTAR | Allston | 2246186 | 2134 | 66.6 | PV | 3614 | 2017-10-19 | 2017-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-27 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-27 | Online
NSTAR | Canton | 2246191 | 2021 | 24 | PV | 470-H9 | 2017-10-10 | 2017-10-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2246192 | 2790 | 21.95 | PV | 2-532-532 | 2017-10-11 | 2017-10-23 | #VALUE! |  | #VALUE! | 2017-11-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Boston | 2246431 | 2128 | 978 | PV | 108-195H1 | 2017-10-31 | 2017-11-03 | #VALUE! |  | #VALUE! | 2017-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | 2018-03-02 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2246432 | 1748 | 15.2 | PV | 65-H6 | 2017-10-16 | 2017-10-26 | #VALUE! |  | #VALUE! | 2017-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-02 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2246565 | 2451 | 366.3 | PV | 282-H5 | 2017-08-11 | 2017-10-27 | #VALUE! |  | #VALUE! | 2017-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2246979 | 2536 | 1500 | PV | 4-98A-98A | 2017-10-12 | 2017-11-07 | #VALUE! |  | #VALUE! | 2017-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-22 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2246980 | 2770 | 1000 | PV | 3-85-85 | 2017-10-27 | 2017-11-07 | #VALUE! |  | #VALUE! | 2017-11-29 | 2018-11-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | STD |  |  |  | 0 |  | 0 | [5 empty] | Private
NSTAR | Wareham | 2247147 | 2571 | 26.35 | PV | 3-85-85 | 2017-10-20 | 2017-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2247148 | 2121 | 57.6 | PV | 483-H3 | 2017-10-20 | 2017-10-27 | #VALUE! |  | #VALUE! | 2017-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2247317 | 2421 | 840 | PV | TBD | 2017-11-29 | 2017-11-30 | #VALUE! | 0 | #VALUE! | 2017-12-05 | 2018-02-09 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-12-28 |  | 2018-07-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-12-29 | Withdrawn
NSTAR | Fairhaven | 2247327 | 2719 | 53.3 | PV | 2-240-240 | 2017-10-24 | 2017-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2247506 | 2364 | 23 | PV | 3-18-36J1 | 2017-10-10 | 2017-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Edgartown | 2247507 | 2539 | 133.2 | PV | 4-97-97 | 2017-10-23 | 2017-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Carver | 2247816 | 2330 | 1500 | PV | 3-10-10 | 2017-10-27 | 2017-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2247819 | 2571 | 8300 | PV & Battery | 3-83-83 | 2017-11-09 | 2017-11-23 | #VALUE! |  | #VALUE! | 2017-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-12-16 | Online
NSTAR | Hopkinton | 2249982 | 1748 | 84 | PV | 126-H4 | 2017-10-19 | 2017-10-19 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-08 | Online
NSTAR | Canton | 2250080 | 2021 | 964 | PV | 470-H10 | 2017-10-18 | 2017-11-15 | #VALUE! |  | #VALUE! | 2017-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-07-23 | Online
NSTAR | Burlington | 2250081 | 1803 | 34.8 | PV | 391-H2 | 2017-11-09 | 2017-11-14 | #VALUE! |  | #VALUE! | 2017-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-03-22 | [6 empty] | 0 |  | 0 |  |  | 2018-06-07 | Online
NSTAR | Carver | 2250250 | 2330 | 8300 | PV & Battery | 3-81-81 | 2017-11-14 | 2017-11-14 | 0 |  | 0 | 2017-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Somerville | 2250465 | 2144 | 100.8 | PV | 1604 | 2017-11-14 | 2017-11-29 | #VALUE! |  | #VALUE! | 2017-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Assonett | 2250466 | 2702 | 15.2 | PV | 2-605-605 | 2017-11-14 | 2017-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Somerville | 2250669 | 2143 | 150 | PV | 387-148H2 | 2017-11-10 | 2017-11-14 | #VALUE! |  | #VALUE! | 2017-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-26 | 2018-03-12 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2250671 | 1720 | 66 | PV | 416-H4 | 2017-11-08 | 2017-11-17 | #VALUE! |  | #VALUE! | 2017-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-30 | Online
NSTAR | Duxbury | 2251155 | 2332 | 300 | PV | 3-26-903 | 2017-11-17 | 2017-11-17 | 0 |  | 0 | 2017-12-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2251157 | 2421 | 21.11 | PV | 320-H5XY | 2017-11-13 | 2017-11-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-25 | Online
NSTAR | Kingston | 2251317 | 2364 | 232 | PV | 3-17-17 | 2017-10-15 | 2017-11-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-16 | Online
NSTAR | Hyannis | 2251318 | 2601 | 250 | PV | 4-63-63 | 2017-11-10 | 2017-11-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-08 | Online
NSTAR | Plymouth | 2251494 | 2360 | 20 | PV | 40613 | 2017-11-15 | 2017-11-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Orleans | 2251495 | 2653 | 64 | PV | 4-94A-633 | 2017-10-15 | 2017-11-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Natick | 2252677 | 1760 | 1700 | CHP | 23-1339H2 | 2017-12-01 | 2017-12-19 | #VALUE! |  | #VALUE! | 2017-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2252869 | 2536 | 19.3 | PV | 4-98B-449 | 2017-11-10 | 2017-11-30 | #VALUE! |  | #VALUE! | 2017-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-01 | [6 empty] | 0 |  | 0 |  |  | 2018-10-05 | Online
NSTAR | Millis | 2253053 | 2054 | 46 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | #VALUE! |  | #VALUE! | 2017-12-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-21 | 2018-03-27 | [6 empty] | 0 |  | 0
NSTAR | Millis | 2253054 | 2054 | 40.25 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2253056 | 2021 | 432.9 | PV | 470-H4 | 2017-11-24 | 2017-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Newton | 2253263 | 2465 | 24.95 | PV | 282-H9 | 2017-10-30 | 2017-12-05 | #VALUE! |  | #VALUE! | 2018-12-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Somerville | 2253264 | 2144 | 52.2 | PV | 1604 | 2017-11-10 | 2017-12-12 | #VALUE! |  | #VALUE! | 2017-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Wareham | 2253372 | 2576 | 4320 | PV & Battery | 3-83-83 | 2017-11-10 | 2017-12-07 | #VALUE! |  | #VALUE! | 2017-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2253373 | 2144 | 72 | PV | 1604 | 2017-11-10 | 2017-12-07 | #VALUE! |  | #VALUE! | 2017-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Somerville | 2253374 | 2144 | 50.4 | PV | 1604 | 2017-11-10 | 2017-12-12 | #VALUE! |  | #VALUE! | 2017-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Hopkinton | 2255236 | 1748 | 18 | PV | 126-H1 | 2017-11-30 | 2017-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-03 | Online
NSTAR | Norfolk | 2255237 | 2056 | 152 | PV | 146-H3 | 2017-12-08 | 2017-12-18 | #VALUE! |  | #VALUE! | 2018-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-08-15 | Online
NSTAR | Bedford | 2255723 | 1730 | 138 | PV | 533-H7 | 2017-12-01 | 2017-12-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2255727 | 2330 | 5980 | PV & Battery | 3-83-83 | 2017-11-20 | 2017-12-11 | #VALUE! |  | #VALUE! | 2018-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Fairhaven | 2255728 | 2719 | 3750 | PV | 2-221-221 | 2017-12-04 | 2017-12-11 | #VALUE! |  | #VALUE! | 2018-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-24 | 2018-04-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-09-26 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Plymouth | 2257795 | 2360 | 480 | PV | 3-13-943 | 2017-12-12 | 2017-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Stoneham | 2257799 | 2180 | 15.95 | PV | 375-H8 | 2017-12-05 | 2017-12-11 | #VALUE! |  | #VALUE! | 2018-01-09 | 2018-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-01 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2258018 | 2571 | 15.2 | PV | 3-84-968 | 2017-12-12 | 2017-12-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2258119 | 2136 | 19.6 | PV | 60-1409H1 | 2017-12-13 | 2017-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2258239 | 2081 | 218.5 | PV | 146-H1 | 2017-10-31 | 2017-12-18 | #VALUE! |  | #VALUE! | 2018-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2258388 | 2180 | 17.575 | PV | 375-H8 | 2017-12-18 | 2017-12-21 | #VALUE! |  | #VALUE! | 2018-01-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2258392 | 2458 | 199.8 | PV | 467-H3 | 2017-12-15 | 2017-12-22 | #VALUE! |  | #VALUE! | 2018-01-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-14 | 2018-03-16 | [6 empty] | 0 |  | 0 |  |  | 2019-01-28 | Online
NSTAR | Boston | 2258582 | 2136 | 992 | PV | 344-1413H1 | 2017-12-22 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Rochester | 2258583 | 2770 | 7415 | PV |  | 2018-01-12 | 2018-01-17 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-17 | 2020-01-07 | #VALUE! | 234 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-17 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  | 2023-01-19 | Online |  | Private | N
NSTAR | Assonett | 2258821 | 2702 | 16.7 | PV | 2-605-605 | 2017-12-18 | 2017-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2258823 | 2130 | 23 | PV | 284-02 | 2017-12-21 | 2017-12-28 | #VALUE! |  | #VALUE! | 2018-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2259134 | 2660 | 149.5 | PV | 4-92B-92B | 2017-10-23 | 2017-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-03-12
NSTAR | Allston | 2259136 | 2134 | 99.9 | PV | 456-H3 | 2017-12-02 | 2017-12-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Rochester | 2259340 | 2770 | 3320 | PV | TBD | 2018-01-18 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-01-23 | 2019-09-30 | #VALUE! | 160 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-05-07 |  | 2019-06-30 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2259341 | 2138 | 13.6 | PV & Battery | 821-22 | 2017-12-14 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-22 |  | -30768 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0
NSTAR | Vineyard Haven | 2259526 | 2658 | 20 | PV | 4-91-228 | 2017-10-16 | 2018-01-04 | #VALUE! |  | #VALUE! | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2259745 | 2139 | 76.6 | PV | 814-13 | 2017-12-14 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-03-05 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2259746 | 2122 | 51.75 | PV | 466-1481H1 | 2017-12-12 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-14 | 2018-03-28 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | Cambridge | 2259916 | 2138 | 53.3 | PV | 830-11 | 2017-12-14 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-04-19 | [6 empty] | 0 |  | 0
NSTAR | Lincoln | 2260143 | 1773 | 43.8 | PV | 320-H1 | 2017-10-16 | 2018-01-03 | #VALUE! |  | #VALUE! | 2018-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-27 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Wareham | 2260144 | 2571 | 7310 | PV & Battery | 3-83-83 | 2017-11-16 | 2018-01-11 | #VALUE! |  | #VALUE! | 2018-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2260285 | 1760 | 40.25 | PV | 433-H5 | 2017-12-28 | 2017-12-28 | 0 |  | 0 | 2018-01-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-04-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Woburn | 2260286 | 1801 | 23.4 | PV | 325-03 | 2017-12-26 | 2018-01-05 | #VALUE! |  | #VALUE! | 2018-01-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bourne | 2260502 | 2559 | 32 | PV | 4-86-86 | 2017-12-28 | 2018-01-08 | #VALUE! |  | #VALUE! | 2018-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Hopkinton | 2260503 | 1748 | 4000 | PV | 126-H4 | 2017-12-19 | 2018-01-09 | #VALUE! |  | #VALUE! | 2018-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2260699 | 2571 | 8300 | PV & Battery | 3-83-83 | 2018-01-09 | 2018-01-09 | 0 |  | 0 | 2018-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2260702 | 2770 | 540 | PV | TBD | 2018-01-29 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-09-04 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2260703 | 2770 | 2540 | PV |  | 2018-01-29 | 2018-01-31 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 |  | #VALUE! | 394 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-20 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Carver | 2260848 | 2330 | 6415 | PV | 3-10-917 | 2017-12-11 | 2018-01-02 | #VALUE! |  | #VALUE! | 2018-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2261351 | 1801 | 15.2 | PV | 375-H12 | 2018-01-03 | 2018-01-29 | #VALUE! |  | #VALUE! | 2018-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | [7 empty] | 0 |  | 0 |  |  | 2019-09-27 | Online
NSTAR | Canton | 2261355 | 2021 | 288 | PV | 269-1321H2 | 2018-01-09 | 2018-01-17 | #VALUE! |  | #VALUE! | 2018-02-01 | 2018-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 | [6 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online |  | Private
NSTAR | Acton | 2261525 | 1720 | 143.2 | PV | 416-H4 | 2017-06-07 | 2018-01-11 | #VALUE! |  | #VALUE! | 2018-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Sudbury | 2261526 | 1776 | 29.58 | PV | 342-H7 | 2017-12-04 | 2018-01-19 | #VALUE! |  | #VALUE! | 2018-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-23 | [6 empty] | 0 |  | 0 |  |  | 2018-07-24 | Online
NSTAR | Wayland | 2261527 | 1778 | 15.2 | PV | 433-H6 | 2017-12-12 | 2018-01-19 | #VALUE! |  | #VALUE! | 2018-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Medway | 2261707 | 2053 | 22.95 | PV | 65-H5 | 2017-12-14 | 2018-01-19 | #VALUE! |  | #VALUE! | 2018-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Osterville | 2262127 | 2665 | 36 | PV | 4-80A-892 | 2018-01-09 | 2018-01-17 | #VALUE! |  | #VALUE! | 2018-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-08-08 | Online
NSTAR | Millis | 2262130 | 2054 | 97.75 | PV | 146-H10 | 2017-12-01 | 2018-01-23 | #VALUE! |  | #VALUE! | 2018-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-09 | [6 empty] | 0 |  | 0 |  |  | 2018-09-12 | Online
NSTAR | East Freetown | 2262266 | 2717 | 15.95 | PV | 2-107-107 | 2018-01-16 | 2018-01-23 | #VALUE! |  | #VALUE! | 2018-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-28 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2262268 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | #VALUE! |  | #VALUE! | 2018-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-14 | Online
NSTAR | Maynard | 2262282 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | #VALUE! |  | #VALUE! | 2018-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2262431 | 2492 | 18.56 | PV | 148-01 | 2017-12-22 | 2018-01-25 | #VALUE! |  | #VALUE! | 2018-02-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-07 | Online
NSTAR | Waltham | 2262433 | 2465 | 80.5 | PV | 282-H9 | 2018-01-02 | 2018-01-26 | #VALUE! |  | #VALUE! | 2018-02-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Brookline | 2262436 | 2445 | 21.9 | PV | 496-H4 | 2017-10-09 | 2018-01-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2019-01-03 | Online
NSTAR | Natick | 2262597 | 1760 | 37.5 | PV | 433-H12 | 2018-01-16 | 2018-01-29 | #VALUE! |  | #VALUE! | 2018-02-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Oak Bluffs | 2262599 | 2557 | 90 | PV | 4-99-99 | 2018-01-24 | 2018-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Provincetown | 2262605 | 2657 | 276.6 | PV | 4-96-675 | 2018-01-24 | 2018-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Truro | 2262805 | 2666 | 80 | PV | 4-96-674 | 2018-01-24 | 2018-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Eastham | 2262807 | 2642 | 109.8 | PV | 4-94A-648 | 2018-01-24 | 2018-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | Chatham | 2262808 | 2633 | 86.4 | PV | 4-95B-940 | 2018-01-24 | 2018-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-31
NSTAR | Sherborn | 2262993 | 1770 | 110 | PV | 274-H4 | 2017-11-17 | 2018-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-25 | 2018-06-29 | [6 empty] | 0 |  | 0 |  |  | 2018-04-25
NSTAR | Eastham | 2262994 | 2642 | 83 | PV | 4-94b-646 | 2018-01-13 | 2018-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Plympton | 2262995 | 2367 | 2310 | PV & Battery |  | 2018-02-13 | 2018-02-27 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 | 2018-08-24 | #VALUE! | 96 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-08-28 |  | 2020-03-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Wareham | 2263854 | 2532 | 4875 | PV | 3-85-928 | 2018-01-26 | 2018-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2263856 | 2675 | 104.4 | PV | 4-92A-536 | 2018-01-24 | 2018-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-06-27 | [6 empty] | 0 |  | 0 |  |  | 2019-11-08 | Online
NSTAR | West Roxbury | 2263857 | 2132 | 588 | PV | 496-H3 | 2018-02-01 | 2018-02-05 | #VALUE! |  | #VALUE! | 2018-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Framingham | 2264047 | 1702 | 125 | PV | 2410 | 2018-01-16 | 2018-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | [7 empty] | 0 |  | 0 |  |  | 2019-04-22 | Online
NSTAR | Boston | 2264049 | 2118 | 109.25 | PV | 318-10 | 2018-02-02 | 2018-02-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-18 | [6 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2264227 | 2664 | 33.6 | PV | 4-92A-562 | 2018-02-07 | 2018-02-12 | #VALUE! |  | #VALUE! | 2018-02-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-21 | [6 empty] | 0 |  | 0
NSTAR | Dartmouth | 2264231 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | #VALUE! |  | #VALUE! | 2018-02-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Dartmouth | 2264232 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-04
NSTAR | Cambridge | 2264395 | 2140 | 466.2 | PV | 828-1382 | 2018-02-02 | 2018-02-15 | #VALUE! |  | #VALUE! | 2018-02-26 | 2018-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-23 | 2018-06-14 |  |  | EXP |  |  |  | 0 |  | 0 | 2018-11-19 | 2018-11-19 | 2018-11-20 | Online
NSTAR | Canton | 2264634 | 2021 | 700 | PV | 470-H7 | 2014-06-12 | 2014-06-12 | 0 | 0 | 0 | 2014-06-16 | 2014-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-12-23 | Online |  | Private
NSTAR | Dartmouth | 2264640 | 2747 | 1500 | PV | 2-107-107 | 2018-02-26 | 2018-02-27 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | 2020-05-04 | #VALUE! | 122 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-12 |  | 2019-06-14 | TBD |  | 60 |  |  | 0 |  | 0 |  | 2019-06-11 | 2019-06-11 | Online |  | Private
NSTAR | Woburn | 2264643 | 1801 | 50 | PV | 211-H6 | 2018-01-26 | 2018-02-15 | #VALUE! |  | #VALUE! | 2018-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | 2018-05-18 | [6 empty] | 0 |  | 0 |  |  | 2018-10-19
NSTAR | Yarmouth | 2264855 | 2664 | 52.2 | PV | 4-92a-562 | 2018-01-24 | 2018-02-15 | #VALUE! |  | #VALUE! | 2018-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Rochester | 2264857 | 2770 | 4650 | PV |  | 2018-02-27 | 2018-03-01 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 |  | #VALUE! | 660 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | 2018-05-11 | Private
NSTAR | Walpole | 2265026 | 2032 | 2370 | PV | 146-H6 | 2018-02-16 | 2018-04-03 | #VALUE! |  | #VALUE! | 2018-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-03-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2265032 | 2118 | 30 | PV | 323-175H | 2018-02-02 | 2018-08-23 | #VALUE! |  | #VALUE! | 2018-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 2265246 | 2186 | 15.2 | PV | 362-02 | 2018-02-09 | 2018-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2265247 | 2576 | 201.6 | PV | 3-83-83 | 2018-02-05 | 2018-02-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-09 | [6 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Cambridge | 2267013 | 2138 | 100.8 | PV | 829-19 | 2018-01-09 | 2018-02-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-05 | Online
NSTAR | Cambridge | 2267217 | 2138 | 66.6 | PV | 814-13 | 2018-02-08 | 2018-02-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Plymouth | 2267338 | 2360 | 272 | PV | 3-71-937 | 2017-11-30 | 2018-02-07 | #VALUE! |  | #VALUE! | 2018-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-04-30 | [6 empty] | 0 |  | 0 |  |  | 2018-08-17 | Online
NSTAR | Boston | 2267381 | 2135 | 75 | Gas Turbine | 548-193 | 2017-12-21 | 2018-02-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-08-27 | Online
NSTAR | Somerville | 2267712 | 2143 | 42 | PV | 250-1N81H1 | 2018-02-14 | 2018-02-28 | #VALUE! |  | #VALUE! | 2018-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-07-17 | Online
NSTAR | Dorchester | 2267902 | 2121 | 43.2 | PV | 483-H5 | 2018-02-28 | 2018-02-28 | 0 |  | 0 | 2018-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | Westport | 2268194 | 2748 | 5000 | PV & Battery | 2-523-523 | 2018-02-15 | 2018-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2268196 | 2056 | 66.6 | PV | 146-H3 | 2018-02-21 | 2018-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0 |  |  | 2018-12-04 | Online
NSTAR | New Bedford | 2268420 | 2745 | 120 | PV | 2-104-104 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! | 2018-03-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online |  | Private
NSTAR | New Bedford | 2268649 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268650 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268651 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268866 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268869 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2269021 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Rochester | 2269022 | 2770 | 1250 | PV | TBD | 2018-03-30 |  | #VALUE! | 0 | #VALUE! | 2018-04-02 | 2020-07-20 | #VALUE! | 572 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sudbury | 2269609 | 1776 | 240 | PV | 342-H5 | 2018-02-21 | 2018-03-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-10 | [6 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Dartmouth | 2269612 | 2747 | 1000 | PV | 2-532-532 | 2018-02-02 | 2018-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-31 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2269886 | 2030 | 25 | PV | 456-H5 | 2018-02-23 | 2018-03-06 | #VALUE! |  | #VALUE! | 2018-04-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2018-07-19 | Online
NSTAR | Dartmouth | 2269896 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | #VALUE! |  | #VALUE! | 2018-04-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2270084 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | #VALUE! |  | #VALUE! | 2018-04-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2270087 | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-31 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2270295 | 2364 | 150 | PV | 3-26-902 | 2018-02-22 | 2018-03-07 | #VALUE! |  | #VALUE! | 2018-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0
NSTAR | Marion | 2270301 | 2738 | 17.6 | PV | 2-304-304 | 2018-03-08 | 2018-03-09 | #VALUE! |  | #VALUE! | 2018-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | New Bedford | 2270504 | 2744 | 599.4 | PV | 2-54-54 | 2018-01-22 | 2018-03-14 | #VALUE! |  | #VALUE! | 2018-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-15 | 2018-06-22 | [6 empty] | 0 |  | 0 |  |  | 2019-07-19 | Online
NSTAR | Fairhaven | 2270747 | 2719 | 8300 | PV & Battery | 2-241-241 | 2018-03-01 | 2018-03-14 | #VALUE! |  | #VALUE! | 2018-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2270749 | 2743 | 5000 | PV |  | 2018-04-09 | 2018-04-11 | #VALUE! | 0 | #VALUE! | 2018-04-11 |  | #VALUE! | 681 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2018-04-12 | Private
NSTAR | Millis | 2270750 | 2054 | 199.8 | PV | 65-H1 | 2018-02-23 | 2018-03-16 | #VALUE! |  | #VALUE! | 2018-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Framingham | 2270751 | 1702 | 528 | PV | 519-175H1 | 2018-01-31 | 2018-03-21 | #VALUE! |  | #VALUE! | 2018-04-11 | 2018-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2021-06-28 | Online |  | Private
NSTAR | Acton | 2271183 | 1720 | 5040 | PV & Battery | 416-H9 | 2018-03-01 | 2018-03-21 | #VALUE! |  | #VALUE! | 2018-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Chilmark | 2271199 | 2535 | 40.35 | PV | 4-97-226 | 2018-02-06 | 2018-03-21 | #VALUE! |  | #VALUE! | 2018-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-24 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271201 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-22 | #VALUE! |  | #VALUE! | 2018-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Wellfleet | 2271202 | 2663 | 48.56 | PV | 4-96-960 | 2018-02-26 | 2018-03-23 | #VALUE! |  | #VALUE! | 2018-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271377 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-26 | #VALUE! |  | #VALUE! | 2018-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | [6 empty] | 2018-07-16 | #VALUE! |  | #VALUE! |  |  | 2019-05-16 | Online
NSTAR | Walpole | 2271379 | 2081 | 480 | PV | 146-H6 | 2018-03-16 | 2018-03-26 | #VALUE! |  | #VALUE! | 2018-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2271383 | 2360 | 4986 | PV | 3-89-922 | 2018-03-12 | 2018-03-27 | #VALUE! |  | #VALUE! | 2018-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2271557 | 2743 | 9878 | PV & Battery | 2-106-160 | 2018-03-19 | 2018-03-28 | #VALUE! |  | #VALUE! | 2018-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2271561 | 2163 | 56 | PV | 821-05 | 2018-03-21 | 2018-03-29 | #VALUE! |  | #VALUE! | 2018-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2272015 | 2138 | 16 | PV | 821-05 | 2018-03-21 | 2018-03-29 | #VALUE! |  | #VALUE! | 2018-04-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2272017 | 2138 | 32 | PV | 821-05 | 2018-03-21 | 2018-03-29 | #VALUE! |  | #VALUE! | 2018-04-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-27
NSTAR | Orleans | 2272019 | 2653 | 23.1 | PV | 4-83-952 | 2018-03-26 | 2018-03-29 | #VALUE! |  | #VALUE! | 2018-04-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-06-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-20 | Online
NSTAR | Watertown | 2272442 | 2472 | 166.5 | PV | 467-H6 | 2018-03-16 | 2018-03-29 | #VALUE! |  | #VALUE! | 2018-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Acton | 2272445 | 1720 | 2100 | PV & Battery | 416-H2 | 2018-03-23 | 2018-04-04 | #VALUE! |  | #VALUE! | 2018-04-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Hopkinton | 2272446 | 1748 | 19 | PV | 130-H1 | 2018-03-01 | 2018-04-03 | #VALUE! |  | #VALUE! | 2018-04-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-05 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Carver | 2272654 | 2330 | 104.4 | PV | 3-81-81 | 2018-03-16 | 2018-04-03 | #VALUE! |  | #VALUE! | 2018-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-18 | [6 empty] | 0 |  | 0 |  |  | 2021-06-18 | Online
NSTAR | Holliston | 2272656 | 1746 | 7.6 | PV | 274-H3 | 2018-04-04 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Carver | 2272658 | 2330 | 2980 | PV & Battery | 3-10-10 | 2018-03-27 | 2018-04-05 | #VALUE! |  | #VALUE! | 2018-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2272821 | 1748 | 86.25 | PV | 4-92A-558 | 2018-03-29 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Hopkinton | 2272822 | 1748 | 86.25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273069 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2273079 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273089 | 1748 | 25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | #VALUE! |  | #VALUE! | 2018-04-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | New Bedford | 2273298 | 2745 | 1384 | PV |  | 2018-04-24 | 2018-04-25 | #VALUE! | 0 | #VALUE! | 2018-05-04 | 2018-10-03 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-07-10 | 2019-04-30 | 2020-02-28 | TBD | EXP | 30 | 2020-02-27 |  | #VALUE! |  | #VALUE! |  |  |  | In Queue |  | Private
NSTAR | Dartmouth | 2273508 | 2747 | 4999 | PV | 2-107-107 | 2018-04-04 | 2018-04-11 | #VALUE! |  | #VALUE! | 2018-04-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-22 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273509 | 2021 | 240 | PV | 269-1321H2 | 2018-02-20 | 2018-04-12 | #VALUE! |  | #VALUE! | 2018-04-26 | 2018-04-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-12-13 | [6 empty] | 0 |  | 0
NSTAR | Chelsea | 2273722 | 2150 | 153.2 | PV | 488-H6 | 2018-03-22 | 2018-04-12 | #VALUE! |  | #VALUE! | 2018-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | 2273723 | 2150 | 196.6 | PV | 488-H7 | 2018-03-22 | 2018-04-12 | #VALUE! |  | #VALUE! | 2018-04-27 | 2018-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | Hopkinton | 2273879 | 1748 | 74 | PV | 65-H6 | 2018-03-30 | 2018-04-11 | #VALUE! |  | #VALUE! | 2018-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273880 | 2021 | 610 | PV | 470-H1 | 2018-04-05 | 2018-04-12 | #VALUE! |  | #VALUE! | 2018-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-03-12 | Online
NSTAR | Woburn | 2274149 | 1801 | 180 | PV | 375-H10 | 2016-10-26 | 2016-11-02 | #VALUE! |  | #VALUE! | 2016-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2018-08-23 | Online
NSTAR | Framingham | 2274154 | 1702 | 198 | PV | 2411 | 2018-04-13 | 2018-04-17 | #VALUE! |  | #VALUE! | 2018-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | [7 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Westport | 2274155 | 2790 | 4500 | PV | 2-532-532 | 2018-03-02 | 2018-04-15 | #VALUE! |  | #VALUE! | 2018-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2274401 | 2743 | 4990 | PV & Battery | 2-241-241 | 2018-04-04 | 2018-04-16 | #VALUE! |  | #VALUE! | 2018-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2274408 | 2770 | 1000 | PV | 3-703-703 | 2018-04-11 | 2018-04-17 | #VALUE! |  | #VALUE! | 2018-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | 2274649 | 2790 | 8300 | PV & Battery | 2-523-523 | 2018-04-11 | 2018-04-17 | #VALUE! |  | #VALUE! | 2018-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Freetown | 2274652 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-11 | 2018-04-17 | #VALUE! |  | #VALUE! | 2018-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2274654 | 2360 | 3750 | PV & Battery | 3-89-89 | 2018-04-11 | 2018-04-17 | #VALUE! |  | #VALUE! | 2018-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Vineyard Haven | 2275151 | 2568 | 5666.1 | PV & Battery | 4-75-75 | 2016-01-19 | 2016-02-08 | #VALUE! |  | #VALUE! | 2016-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-05-31 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Wayland | 2275155 | 1778 | 16.32 | PV | 342-H1 | 2018-04-17 | 2018-04-24 | #VALUE! |  | #VALUE! | 2018-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-06 | 2018-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Dorchester | 2275333 | 2122 | 64 | PV | 466-1481H1 | 2018-04-12 | 2018-04-27 | #VALUE! |  | #VALUE! | 2018-05-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Norfolk | 2275667 | 2056 | 15.2 | PV | 146-H3 | 2018-04-09 | 2018-04-24 | #VALUE! |  | #VALUE! | 2018-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Somerville | 2276155 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | #VALUE! |  | #VALUE! | 2018-05-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2276157 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | #VALUE! |  | #VALUE! | 2018-05-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2276786 | 1701 | 15.8 | PV | 433-H8 | 2018-03-01 | 2018-04-27 | #VALUE! |  | #VALUE! | 2018-05-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2276951 | 1773 | 250 | PV | 320-H1 | 2018-04-26 | 2018-05-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-31 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2277112 | 2790 | 8300 | PV & Battery | 2-522-522 | 2018-04-27 | 2018-05-04 | #VALUE! |  | #VALUE! | 2018-05-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2277113 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-27 | 2018-05-04 | #VALUE! |  | #VALUE! | 2018-05-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2277114 | 2702 | 5000 | PV & Battery | 532 | 2018-04-27 | 2018-05-04 | #VALUE! |  | #VALUE! | 2018-05-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2277378 | 2790 | 4875 | PV & Battery |  | 2018-05-17 | 2018-05-22 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-12-26 | #VALUE! | 148 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-22 |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Acusnet | 2277380 | 2743 | 8980 | PV & Battery | 2-241-241 | 2018-04-11 | 2018-05-04 | #VALUE! |  | #VALUE! | 2018-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2277381 | 2330 | 8980 | PV & Battery | 3-81-81 | 2018-04-06 | 2018-05-04 | #VALUE! |  | #VALUE! | 2018-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2277865 | 2576 | 3300 | PV & Battery | 3-86-966 | 2018-04-25 | 2018-05-08 | #VALUE! |  | #VALUE! | 2018-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-31 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Woburn | 2277867 | 1801 | 130 | PV | 258-1394-H1 | 2018-03-07 | 2018-05-10 | #VALUE! |  | #VALUE! | 2018-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-09 | 2018-08-22 | [6 empty] | 0 |  | 0 |  |  | 2018-09-24 | Online
NSTAR | Wareham | 2278333 | 2576 | 201.6 | PV | 3-86-966 | 2018-05-01 | 2018-05-11 | #VALUE! |  | #VALUE! | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-17 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2278335 | 2451 | 210 | Fuel Cell | 450-H2 | 2018-04-05 | 2018-05-15 | #VALUE! |  | #VALUE! | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-14 | 2018-07-06 | [6 empty] | 0 |  | 0
NSTAR | Rochester | 2278508 | 2770 | 3345 | PV & Battery | 3-702-702 | 2018-05-14 | 2018-05-15 | #VALUE! |  | #VALUE! | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2279017 | 2575 | 22.8 | PV | 4-97-222 | 2018-05-03 | 2018-05-16 | #VALUE! |  | #VALUE! | 2018-05-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Medway | 2279222 | 2053 | 27.72 | PV | 65-H5 | 2018-04-26 | 2018-05-16 | #VALUE! |  | #VALUE! | 2018-05-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2279224 | 1776 | 249.8 | PV | 342-H2 | 2018-05-11 | 2018-05-16 | #VALUE! |  | #VALUE! | 2018-05-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0
NSTAR | Medfield | 2279225 | 2052 | 264 | PV | 456-H2 | 2018-05-07 | 2018-05-11 | #VALUE! |  | #VALUE! | 2018-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-06-05 | Online
NSTAR | Wayland | 2279425 | 1778 | 21.9 | PV | 342-H1 | 2018-05-04 | 2018-05-16 | #VALUE! |  | #VALUE! | 2018-06-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-07 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-03-11
NSTAR | Plympton | 2279426 | 2367 | 2500 | PV & Battery | 3-15-906 | 2018-04-25 | 2018-05-11 | #VALUE! |  | #VALUE! | 2018-06-01 | 2018-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2023-02-06 | Online |  | Private
NSTAR | Plympton | 2279636 | 2367 | 4998 | PV & Battery | 3-51-43J1 | 2018-05-04 | 2018-05-17 | #VALUE! |  | #VALUE! | 2018-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online
NSTAR | Barnstable | 2279638 | 2648 | 4998 | PV & Battery | 4-88-478 | 2018-05-16 | 2018-05-22 | #VALUE! |  | #VALUE! | 2018-06-04 | 2018-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 | [6 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online |  | Private
NSTAR | Cambridge | 2280401 | 2142 | 35 | CHP | 875-1399 | 2018-05-15 | 2018-05-22 | #VALUE! |  | #VALUE! | 2018-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-18 | [6 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Waltham | 2280855 | 2453 | 780 | PV & Battery | 386-1356 | 2018-05-03 | 2018-05-22 | #VALUE! |  | #VALUE! | 2018-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-10-01 | Online |  | Private
NSTAR | Acton | 2280862 | 1720 | 1496 | PV & Battery | 416-H1 | 2018-03-01 | 2018-05-23 | #VALUE! |  | #VALUE! | 2018-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 2281067 | 2667 | 700 | PV | 4-96-677 | 2018-05-18 | 2018-05-23 | #VALUE! |  | #VALUE! | 2018-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online
NSTAR | Westport | 2281069 | 2790 | 995 | Gas Turbine | 2-523-523 | 2018-05-16 | 2018-05-30 | #VALUE! |  | #VALUE! | 2018-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2281481 | 2330 | 2000 | PV & Battery |  | 2018-06-11 | 2018-06-12 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 |  | #VALUE! | 135 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-20 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Carver | 2281482 | 2330 | 1000 | PV & Battery | 3-81-950 | 2018-05-18 | 2018-05-30 | #VALUE! |  | #VALUE! | 2018-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2282055 | 2539 | 466.6 | PV & Battery | 4-97-97 | 2018-05-29 | 2018-05-31 | #VALUE! |  | #VALUE! | 2018-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Framingham | 2282056 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | #VALUE! |  | #VALUE! | 2018-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2282057 | 2138 | 28.8 | PV | 825-18 | 2018-05-29 | 2018-06-01 | #VALUE! |  | #VALUE! | 2018-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | [7 empty] | 0 |  | 0 |  |  | 2019-02-04 |  |  | Private
NSTAR | Barnstable | 2282058 | 2668 | 44.5 | PV | 4-87B-473 | 2018-05-15 | 2018-06-01 | #VALUE! |  | #VALUE! | 2018-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-03 | 2018-08-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2282066 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256 | 2576 | 1497 | PV | TBD | 2018-06-15 |  | #VALUE! | 0 | #VALUE! | 2018-09-22 | 2018-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-01-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Medfield | 2282637 | 2052 | 240 | PV | 456-H2 | 2018-05-30 | 2018-06-04 | #VALUE! |  | #VALUE! | 2018-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | 2018-08-23 | [6 empty] | 0 |  | 0 |  |  | 2019-06-10 | Online
NSTAR | Ashland | 2282638 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | #VALUE! |  | #VALUE! | 2018-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282639 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2282640 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | #VALUE! |  | #VALUE! | 2018-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282847 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | #VALUE! |  | #VALUE! | 2018-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2283031 | 2130 | 38 | PV | 350-H11 | 2018-06-04 | 2018-06-06 | #VALUE! |  | #VALUE! | 2018-06-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 |  |  | 2019-01-22 | Online
NSTAR | Westport | 2283036 | 2790 | 2000 | PV | 2-523-523 | 2018-05-23 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2283230 | 2081 | 486.6 | PV | 146-H1 | 2018-06-05 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Walpole | 2283639 | 2081 | 7499 | PV & Battery | 456-H1 | 2018-06-01 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2283640 | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Wareham | 2284066 | 2571 | 15.13 | PV | 3-84-963 | 2018-04-23 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-08-01 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Ashland | 2284070 | 1721 | 100 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2284071 | 2563 | 133.2 | PV | 4-81B-443 | 2018-06-04 | 2018-06-14 | #VALUE! |  | #VALUE! | 2018-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online |  | Private
NSTAR | Acton | 2284261 | 1720 | - |  | TBD | 2018-06-28 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-11-23 | TBD | TBD |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2284288 | 2740 | 250 | PV | 110-110 | 2018-05-29 | 2018-06-14 | #VALUE! |  | #VALUE! | 2018-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2284555 | 1776 | 25 | PV | 342-H7 | 2018-05-31 | 2018-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Plymouth | 2284556 | 2360 | 250 | PV | 3-13-943 | 2018-06-11 | 2018-06-18 | #VALUE! |  | #VALUE! | 2018-07-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2285552 | 2743 | 2000 | PV |  | 2018-07-05 | 2018-07-06 | #VALUE! | 0 | #VALUE! | 2018-07-06 |  | #VALUE! | 619 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2018-07-11 | Private
NSTAR | Mattapoisett | 2285553 | 2739 | 3560 | PV | 2-302-302 | 2018-06-08 | 2018-06-20 | #VALUE! |  | #VALUE! | 2018-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2285554 | 2739 | 4980 | PV & Battery | 2-301-301 | 2018-06-08 | 2018-06-20 | #VALUE! |  | #VALUE! | 2018-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Vineyard Haven | 2285555 | 2568 | 29.75 | PV | 4-97-222 | 2018-06-12 | 2018-06-19 | #VALUE! |  | #VALUE! | 2018-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-07 | [7 empty] | 0 |  | 0 |  |  | 2018-11-08 | Online
NSTAR | Westport | 2285715 | 2790 | 2200 | PV & Battery | 33-H3 | 2018-06-08 | 2018-06-20 | #VALUE! |  | #VALUE! | 2018-07-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2285721 | 2446 | 86 | PV | 33-H3 | 2018-06-12 | 2018-06-20 | #VALUE! |  | #VALUE! | 2018-07-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2285991 | 2458 | 50 | PV | 292-H1 | 2018-05-31 | 2018-06-26 | #VALUE! |  | #VALUE! | 2018-07-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-05 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2286172 | 1748 | 100 | PV | TBD | 2018-07-10 | 2018-07-11 | #VALUE! | 0 | #VALUE! | 2018-07-13 | 2018-07-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Medway | 2286612 | 2053 | 180 | PV | 65-H3 | 2018-07-12 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2019-07-30 | Online |  | Private
NSTAR | Bedford | 2286613 | 1730 | 52.2 | PV | 533-H7 | 2018-06-21 | 2018-06-27 | #VALUE! |  | #VALUE! | 2018-07-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-10 | [7 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Hopkinton | 2286965 | 1748 | 100 | PV | 3-86-966 | 2018-05-23 | 2018-06-27 | #VALUE! |  | #VALUE! | 2018-07-11 | 2018-12-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-10-16 | Online |  | Private
NSTAR | New Bedford | 2286967 | 2740 | 28 | PV | TBD | 2018-07-16 | 2018-07-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2286968 | 2576 | 2660 | PV & Battery | 3-81-81 | 2018-06-13 | 2018-06-29 | #VALUE! |  | #VALUE! | 2018-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2286970 | 1701 | 21.68 | PV | 342-H4 | 2018-05-15 | 2018-06-29 | #VALUE! |  | #VALUE! | 2018-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Wayland | 2286971 | 1778 | 208 | PV | 433-H6 | 2018-06-29 | 2018-06-29 | 0 |  | 0 | 2018-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2287284 | 1701 | 249.8 | PV | 278-H1 | 2018-06-06 | 2018-06-29 | #VALUE! |  | #VALUE! | 2018-07-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-09-21 | [6 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Boston | 2287285 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | #VALUE! |  | #VALUE! | 2018-07-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-02 | Online
NSTAR | Woburn | 2287543 | 1801 | 1310 | PV | 375-H1 | 2018-07-02 | 2018-07-03 | #VALUE! |  | #VALUE! | 2018-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Boston | 2287544 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | #VALUE! |  | #VALUE! | 2018-07-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Vineyard Haven | 2287709 | 2658 | 19.78 | PV | 4-91-228 | 2017-11-03 | 2017-11-03 | 0 |  | 0 | 2017-11-03 | 2018-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | [7 empty] | 0 |  | 0 |  |  | 2018-10-10 | Online |  | Private
NSTAR | Plymouth | 2287723 | 2360 | 780 | PV | TBD | 2018-07-19 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2287856 | 2576 | 3992 | PV | TBD | 2018-07-20 |  | #VALUE! | 0 | #VALUE! | 2018-09-22 | 2018-09-28 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2287931 | 2790 | 4950 | PV | 2-522-522 | 2018-06-29 | 2018-07-03 | #VALUE! |  | #VALUE! | 2018-07-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2288242 | 1801 | 942 | PV | 146-H1 | 2018-07-10 | 2018-07-10 | 0 |  | 0 | 2018-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0
NSTAR | Tisbury | 2288244 | 2575 | 18 | PV | 4-97-222 | 2018-05-25 | 2018-07-10 | #VALUE! |  | #VALUE! | 2018-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2018-11-16 | Online
NSTAR | Stoneham | 2288415 | 2180 | 17.17 | PV | 375-H8 | 2018-07-10 | 2018-07-24 | #VALUE! |  | #VALUE! | 2018-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-28 | [7 empty] | 0 |  | 0 |  |  | 2020-01-24 | Online
NSTAR | Hyannis | 2288599 | 2601 | 1500 | PV | 4-84B-524 | 2018-05-31 | 2018-07-11 | #VALUE! |  | #VALUE! | 2018-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2288600 | 2360 | 780 | PV | 3-73-73 | 2018-07-03 | 2018-07-11 | #VALUE! |  | #VALUE! | 2018-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2288772 | 1803 | 17.49 | PV | 391-H6 | 2018-07-03 | 2018-07-11 | #VALUE! |  | #VALUE! | 2018-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2288774 | 1720 | 999 | PV | 416-H4 | 2018-06-20 | 2018-07-12 | #VALUE! |  | #VALUE! | 2018-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2020-09-30
NSTAR | Carver | 2288775 | 2330 | 5000 | PV & Battery | 3-83-83 | 2018-07-06 | 2018-07-12 | #VALUE! |  | #VALUE! | 2018-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Norfolk | 2288776 | 2056 | 250 | PV | 146-H3 | 2018-06-07 | 2018-07-12 | #VALUE! |  | #VALUE! | 2018-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-09-07 | Online
NSTAR | Holliston | 2288918 | 1746 | 66.6 | PV | 65-H9 | 2018-07-13 | 2018-07-16 | #VALUE! |  | #VALUE! | 2018-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-06 | [6 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online
NSTAR | Holliston | 2289154 | 1746 | 17.28 | PV | 274-H3 | 2018-04-10 | 2018-07-17 | #VALUE! |  | #VALUE! | 2018-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-05-11 | Online
NSTAR | Woburn | 2289155 | 1801 | 15.34 | PV | 211-H10 | 2018-07-03 | 2018-07-17 | #VALUE! |  | #VALUE! | 2018-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Burlington | 2289156 | 1803 | 15.2 | PV | 391-H7 | 2018-07-03 | 2018-07-17 | #VALUE! |  | #VALUE! | 2018-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-11-25 | Online
NSTAR | Wareham | 2289380 | 2571 | 996 | PV & Battery | 3-84-961 | 2018-06-27 | 2018-07-18 | #VALUE! |  | #VALUE! | 2018-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2289611 | 2532 | 115.2 | PV | 4-86-402 | 2018-07-10 | 2018-07-18 | #VALUE! |  | #VALUE! | 2018-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Brookline | 2289821 | 2445 | 17.28 | PV | 350-H3 | 2018-07-18 | 2018-07-19 | #VALUE! |  | #VALUE! | 2018-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-21 | [7 empty] | 0 |  | 0 |  |  | 2019-03-19 | Online
NSTAR | Cambridge | 2289823 | 2138 | 510 | Fuel Cell | 819-1NC3 | 2018-06-12 | 2018-07-20 | #VALUE! |  | #VALUE! | 2018-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 | 2018-12-20 |  | 2018-12-21
NSTAR | Westport | 2289828 | 2770 | 4498 | PV & Battery | 2-532-532 | 2018-04-30 | 2018-07-20 | #VALUE! |  | #VALUE! | 2018-08-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290339 | 1720 | 300 | PV | 416-H4 | 2018-07-10 | 2018-07-20 | #VALUE! |  | #VALUE! | 2018-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290347 | 1720 | 360 | PV | 416-H9 | 2018-07-10 | 2018-07-20 | #VALUE! |  | #VALUE! | 2018-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2290688 | 1801 | 16.42 | PV | 211-H8 | 2018-07-03 | 2018-07-17 | #VALUE! |  | #VALUE! | 2018-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2290690 | 2770 | 4000 | PV | 3-702-702 | 2018-07-18 | 2018-07-23 | #VALUE! |  | #VALUE! | 2018-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2290691 | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | #VALUE! |  | #VALUE! | 2018-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-06 | 2018-09-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online |  | Private
NSTAR | Bedford | 2290881 | 1731 | 1645 | PV & Battery | 320-H6 | 2018-07-19 | 2018-07-24 | #VALUE! |  | #VALUE! | 2018-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2290885 | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | #VALUE! |  | #VALUE! | 2018-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Edgartown | 2291054 | 2539 | 19.6 | PV | 4-99-99 | 2018-05-31 | 2018-07-25 | #VALUE! |  | #VALUE! | 2018-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0
NSTAR | Chelsea | 2291056 | 2150 | 33.3 | PV | 488-H7 | 2018-07-20 | 2018-07-25 | #VALUE! |  | #VALUE! | 2018-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | 2018-10-03 | [6 empty] | 0 |  | 0 |  |  | 2019-11-07 | Online
NSTAR | Woburn | 2291058 | 1801 | 15.2 | PV | 391-H11 | 2018-07-18 | 2018-07-26 | #VALUE! |  | #VALUE! | 2018-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Norfolk | 2291293 | 2056 | 996 | PV | 146-H3 | 2018-07-24 | 2018-07-26 | #VALUE! |  | #VALUE! | 2018-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2291296 | 1801 | 16.56 | PV | 375-H14 | 2018-05-22 | 2018-07-26 | #VALUE! |  | #VALUE! | 2018-08-10 | 2018-12-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2291297 | 2644 | 15.2 | PV | 4-81B-443 | 2018-07-18 | 2018-07-26 | #VALUE! |  | #VALUE! | 2018-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Westport | 2291742 | 2790 | 500 | PV | 2-522-522 | 2018-07-23 | 2018-07-27 | #VALUE! |  | #VALUE! | 2018-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2291743 | 2124 | 86 | PV | 311-12 | 2018-07-27 | 2018-08-02 | #VALUE! |  | #VALUE! | 2018-08-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-06-19 | Online |  | Private
NSTAR | New Bedford | 2291744 | 2740 | 36 | PV | 2-69-69 | 2018-06-25 | 2018-08-03 | #VALUE! |  | #VALUE! | 2018-08-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online |  | Private
NSTAR | Harwich | 2291972 | 2645 | 30 | PV | 4-92B-92B | 2018-08-02 | 2018-08-07 | #VALUE! |  | #VALUE! | 2018-08-15 | 2018-11-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Bellingham | 2292179 | 2019 | 6310 | PV & Battery | 65-H4 | 2018-08-03 | 2018-08-07 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2021-11-30 | Online
NSTAR | Carver | 2292181 | 2330 | 2468 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2292182 | 2655 | 23.04 | PV | 4-80A-892 | 2018-07-20 | 2018-08-08 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Rochester | 2292307 | 2770 | 16.7 | PV | 3-702-702 | 2018-08-08 | 2018-08-15 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-21 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online |  | Private
NSTAR | Newton | 2292310 | 2460 | 90 | PV | 467-H3 | 2018-07-20 | 2018-08-08 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2293955 | 1720 | 17.56 | PV | 416-H4 | 2018-07-20 | 2018-08-10 | #VALUE! |  | #VALUE! | 2018-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-23 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  | 2019-04-05 | Online |  | Private
NSTAR | Allston | 2294148 | 2134 | 70 | PV | 548-92H3 | 2018-08-09 | 2018-08-10 | #VALUE! |  | #VALUE! | 2018-08-30 | 2018-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-31 | 2018-11-16 | [6 empty] | 0 |  | 0
NSTAR | Plymouth | 2294151 | 2362 | 133.2 | PV | 3-14-911 | 2018-08-09 | 2018-08-10 | #VALUE! |  | #VALUE! | 2018-08-30 | 2018-11-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-08-18 | Online |  | Private
NSTAR | Barnstable | 2294153 | 1801 | 22.8 | PV | 4-81B-443 | 2018-07-24 | 2018-08-15 | #VALUE! |  | #VALUE! | 2018-08-30 | 2018-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-12-17 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-06-04 | Online |  | Private
NSTAR | Brewster | 2294155 | 2631 | 15.2 | PV | 4-89A-553 | 2018-08-02 | 2018-08-15 | #VALUE! |  | #VALUE! | 2018-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-04 | Online
NSTAR | Waltham | 2294156 | 2451 | 496 | PV | 320-H3 | 2018-06-05 | 2018-08-15 | #VALUE! |  | #VALUE! | 2018-08-30 | 2018-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-05-21 |  |  | Private
NSTAR | Mattapoisett | 2295025 | 2739 | 960 | PV | 2-302-302 | 2018-08-14 | 2018-08-17 | #VALUE! |  | #VALUE! | 2018-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online
NSTAR | Natick | 2295244 | 1760 | 180 | PV | 433-H12 | 2018-08-09 | 2018-08-17 | #VALUE! |  | #VALUE! | 2018-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2295246 | 2740 | 86.4 | PV | 2-49-49 | 2018-08-14 | 2018-08-20 | #VALUE! |  | #VALUE! | 2018-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Boston | 2295249 | 2163 | 46 | PV | STATION890 | 2018-07-26 | 2018-08-20 | #VALUE! |  | #VALUE! | 2018-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online |  | Private
NSTAR | Cambridge | 2295384 | 2138 | 80.5 | PV | 821-05 | 2018-07-31 | 2018-08-20 | #VALUE! |  | #VALUE! | 2018-09-07 | 2018-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26
NSTAR | New Bedford | 2295385 | 2744 | 233.1 | PV | 2-41-41 | 2018-08-06 | 2018-09-04 | #VALUE! |  | #VALUE! | 2018-09-07 | 2018-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-11-27
NSTAR | Wareham | 2295386 | 2738 | 2925 | PV | 3-85-85 | 2018-08-07 | 2018-08-22 | #VALUE! |  | #VALUE! | 2018-09-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2295579 | 2740 | 150 | PV | 2-70-70 | 2018-08-07 | 2018-08-22 | #VALUE! |  | #VALUE! | 2018-09-11 | 2018-10-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | 2018-10-30 | [6 empty] | 0 |  | 0 |  |  | 2019-12-19 | Online |  | Private
NSTAR | Oak Bluffs | 2295584 | 2557 | 280 | PV & Battery | 4-75-75 | 2018-08-20 | 2018-08-22 | #VALUE! |  | #VALUE! | 2018-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Rochester | 2295586 | 2738 | 996 | PV | 3-85-85 | 2018-08-20 | 2018-08-23 | #VALUE! |  | #VALUE! | 2018-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2295850 | 1721 | 22.95 | PV | 455-H3 | 2018-08-23 | 2018-08-23 | 0 |  | 0 | 2018-09-12 | 2018-11-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2295852 | 2576 | 3000 | PV & Battery | 3-81-81 | 2018-08-16 | 2018-08-23 | #VALUE! |  | #VALUE! | 2018-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2295857 | 2453 | 73.3 | PV | 33-H2 | 2018-08-08 | 2018-08-23 | #VALUE! |  | #VALUE! | 2018-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-29 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2296072 | 2364 | 3510 | PV | 3/14-14 | 2018-08-22 | 2018-08-24 | #VALUE! |  | #VALUE! | 2018-09-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-24 | Online
NSTAR | Carver | 2296366 | 2330 | 4650 | PV |  | 2018-09-12 | 2018-09-18 | #VALUE! | 0 | #VALUE! | 2018-09-18 |  | #VALUE! | 569 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2018-09-20 | Private
NSTAR | Westport | 2296371 | 2790 | 2000 | PV | 2-532-532 | 2018-08-22 | 2018-08-24 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2296372 | 2770 | 4998 | PV & Battery | 3-703-703 | 2018-08-14 | 2018-08-24 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2296373 | 2571 | 4890 | PV | 3-82-82 | 2018-08-09 | 2018-08-28 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Dartmouth | 2296559 | 2747 | 4990 | PV | 2-103-103 | 2018-08-09 | 2018-08-28 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-03 | Online
NSTAR | Framingham | 2296563 | 1702 | 15.2 | PV | 274-H1 | 2018-08-02 | 2018-08-29 | #VALUE! |  | #VALUE! | 2018-09-18 | 2018-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-11-16 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sandwich | 2296564 | 2563 | 4890 | PV & Battery | 4-81B-443 | 2018-07-24 | 2018-08-29 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2296607 | 1721 | 4450 | PV |  | 2018-09-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-31 | TBD |  | 30 | 2019-10-30 | 2019-10-30 | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Wareham | 2296718 | 2538 | 199.8 | PV | 3-81-81 | 2018-08-23 | 2018-08-29 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2296720 | 2330 | 3500 | PV | 3-10-10 | 2018-08-27 | 2018-08-29 | #VALUE! |  | #VALUE! | 2018-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2296721 | 2120 | 27 | PV | 5203 | 2018-06-25 | 2018-08-30 | #VALUE! |  | #VALUE! | 2018-09-18 | 2018-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-09 | Online |  | Private
NSTAR | Rochester | 2296978 | 2770 | - |  | TBD | 2018-09-17 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-04-26 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Needham | 2297073 | 2494 | 99.9 | PV | 148-H4 | 2018-08-30 | 2018-08-31 | #VALUE! |  | #VALUE! | 2018-09-19 | 2018-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-31 | Online |  | Private
NSTAR | Westport | 2297080 | 2790 | 1000 | PV | 2-532-532 | 2018-08-20 | 2018-08-31 | #VALUE! |  | #VALUE! | 2018-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297083 | 2576 | 4075 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | #VALUE! |  | #VALUE! | 2018-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2297267 | 2576 | 500 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | #VALUE! |  | #VALUE! | 2018-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297500 | 2571 | 4890 | PV | 8-83-83 | 2018-08-09 | 2018-09-19 | #VALUE! |  | #VALUE! | 2018-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2297501 | 2639 | 40 | PV | 4-92B-583 | 2018-08-03 | 2018-08-18 | #VALUE! |  | #VALUE! | 2018-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-05
NSTAR | Wareham | 2297503 | 2576 | 250 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | #VALUE! |  | #VALUE! | 2018-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2297504 | 2210 | 75 | PV | 323-06 | 2018-08-09 | 2018-09-05 | #VALUE! |  | #VALUE! | 2018-09-20 | 2018-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-11-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-27 |  |  | Private
NSTAR | Freetown | 2297681 | 2717 | 4500 | PV & Battery | 2-108-108 | 2018-08-28 | 2018-09-06 | #VALUE! |  | #VALUE! | 2018-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2297682 | 2738 | 3500 | PV & Battery | 3-85-85 | 2018-08-14 | 2018-09-06 | #VALUE! |  | #VALUE! | 2018-09-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298087 | 1754 | 462 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298090 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 2298091 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298092 | 1754 | 1254 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2298285 | 1720 | 490 | PV | 416-H4 | 2018-07-10 | 2018-09-06 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2298289 | 1730 | 72 | PV | 533-H5 | 2018-08-28 | 2018-09-06 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2298290 | 1801 | 924 | PV | 258-1394-H1 | 2018-08-24 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Woburn | 2298553 | 1801 | 490 | PV | 258-1394H8 | 2018-08-24 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online
NSTAR | Burlington | 2298565 | 1803 | 990 | PV | 391-H16 | 2018-08-24 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-27 | 2018-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0
NSTAR | Burlington | 2298567 | 1803 | 990 | PV | 391-H9 | 2018-08-24 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-27 | 2018-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Barnstable | 2298568 | 2648 | 4990 | PV | 4-88-453 | 2018-09-04 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2298768 | 2770 | 1782 | PV | 3-702-702 | 2018-08-28 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2298783 | 1746 | 31 | PV | 130-H1 | 2018-08-30 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-28 | 2018-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-03-06
NSTAR | New Bedford | 2298790 | 2745 | 1220 | PV | 2-107-107 | 2018-09-04 | 2018-09-07 | #VALUE! |  | #VALUE! | 2018-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2298981 | 2747 | 185 | PV & Battery | 2-525-525 | 2018-08-31 | 2018-09-10 | #VALUE! |  | #VALUE! | 2018-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2299343 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-06 | 2018-09-11 | #VALUE! |  | #VALUE! | 2018-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2299346 | 2330 | 8300 | PV & Battery | 3-51-901 | 2018-09-07 | 2018-09-11 | #VALUE! |  | #VALUE! | 2018-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2299348 | 2360 | 924 | PV | 3-12-41J1 | 2018-08-17 | 2018-09-12 | #VALUE! |  | #VALUE! | 2018-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-12-21 | Online
NSTAR | Rochester | 2299350 | 2770 | 1250 | PV & Battery | 5-702-702 | 2018-09-06 | 2018-09-12 | #VALUE! |  | #VALUE! | 2018-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2299602 | 2659 | 78.2 | PV | 4-95A-95A | 2018-09-12 | 2018-09-19 | #VALUE! |  | #VALUE! | 2018-10-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Acusnet | 2299606 | 2743 | 4950 | PV & Battery | 2-241-241 | 2018-09-07 | 2018-09-20 | #VALUE! |  | #VALUE! | 2018-10-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300058 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | #VALUE! |  | #VALUE! | 2018-10-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2300060 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | #VALUE! |  | #VALUE! | 2018-10-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300709 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | #VALUE! |  | #VALUE! | 2018-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2300908 | 2576 | 4180 | PV & Battery | 3-81-81 | 2018-09-04 | 2018-09-21 | #VALUE! |  | #VALUE! | 2018-10-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Woburn | 2300919 | 1801 | 15.2 | PV | 211-H13 | 2018-09-07 | 2018-09-25 | #VALUE! |  | #VALUE! | 2018-10-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  | 2020-03-24 | Online |  | Private
NSTAR | Watertown | 2300922 | 2472 | 475.2 | PV | 467-H4 | 2018-09-18 | 2018-09-25 | #VALUE! |  | #VALUE! | 2018-10-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | [7 empty] | 0 |  | 0 |  |  | 2019-11-15 | Online |  | Private
NSTAR | Sandwich | 2301106 | 2563 | 133.2 | PV | 4-81B-443 | 2018-09-19 | 2018-09-26 | #VALUE! |  | #VALUE! | 2018-10-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cambridge | 2301108 | 2142 | 63.3 | PV | 831-1336XY | 2018-09-24 | 2018-09-27 | #VALUE! |  | #VALUE! | 2018-10-12 | 2018-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-28 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-22 | Online |  | Private
NSTAR | East Freetown | 2301315 | 2717 | 220 | PV | 604 | 2018-09-24 | 2018-09-27 | #VALUE! |  | #VALUE! | 2018-10-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online |  | Private
NSTAR | Acusnet | 2301808 | 2743 | 5000 | PV |  | 2018-10-16 | 2018-10-17 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2019-12-18 | #VALUE! | 41 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-06-13 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2021-09-23 | Online |  | Private
NSTAR | Acusnet | 2301817 | 2743 | 5000 | PV | 2-241-241 | 2018-09-26 | 2018-09-28 | #VALUE! |  | #VALUE! | 2018-10-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Chelsea | 2302133 | 2150 | 66.6 | PV | 488-H2 | 2018-09-26 | 2018-10-01 | #VALUE! |  | #VALUE! | 2018-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2302146 | 2770 | 1000 | PV & Battery | 3-702-702 | 2018-09-20 | 2018-09-21 | #VALUE! |  | #VALUE! | 2018-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Plymouth | 2302150 | 2360 | 133.2 | PV | 3-13-943 | 2018-09-25 | 2018-10-02 | #VALUE! |  | #VALUE! | 2018-10-18 | 2018-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2302380 | 2571 | 100 | PV | 8-83-83 | 2018-09-25 | 2018-10-02 | #VALUE! |  | #VALUE! | 2018-10-19 | 2018-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-20 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Milton | 2302387 | 2186 | 38 | PV | 362-03 | 2018-09-26 | 2018-10-02 | #VALUE! |  | #VALUE! | 2018-10-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-04 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Canton | 2302390 | 2021 | 3992 | PV | 269-1321H | 2018-09-28 | 2018-10-03 | #VALUE! |  | #VALUE! | 2018-10-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online |  | Private
NSTAR | Barnstable | 2302867 | 2632 | 66.6 | PV | 4-88-88 | 2018-10-05 | 2018-10-05 | 0 |  | 0 | 2018-10-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Plymouth | 2303219 | 2360 | 199.8 | PV | 3-10-10 | 2018-10-01 | 2018-10-05 | #VALUE! |  | #VALUE! | 2018-10-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2303220 | 2746 | 86.4 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | #VALUE! |  | #VALUE! | 2018-10-25 | 2018-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-05-10 | Online |  | Private
NSTAR | New Bedford | 2303221 | 2746 | 57.6 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | #VALUE! |  | #VALUE! | 2018-10-25 | 2018-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-30 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-08-23 | Online |  | Public
NSTAR | Natick | 2303427 | 1760 | 100 | PV & Battery | 240-H3 | 2018-10-11 | 2018-10-18 | #VALUE! |  | #VALUE! |  | 2018-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-22 | Online |  | Private
NSTAR | Plymouth | 2303429 | 2360 | 144 | PV | 3-13-943 | 2018-10-11 | 2018-10-18 | #VALUE! |  | #VALUE! | 2018-10-31 | 2018-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-21 | Online |  | Private
NSTAR | Vineyard Haven | 2303430 | 2568 | 23.36 | PV | 3-24B-95 | 2018-10-05 | 2018-10-11 | #VALUE! |  | #VALUE! | 2018-10-31 | 2018-12-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hyannis | 2303431 | 2601 | 40 | PV | 4-80B-514 | 2018-10-15 | 2018-10-19 | #VALUE! |  | #VALUE! | 2018-10-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0 |  |  | 2019-09-06 | Online |  | Private
NSTAR | Natick | 2303432 | 1760 | 366.6 | PV | 433-H9 | 2018-10-05 | 2018-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Falmouth | 2303631 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2018-10-08 | 2018-10-12 | #VALUE! |  | #VALUE! | 2018-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-04 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Woburn | 2304049 | 1801 | 15.2 | PV | 375-H14 | 2018-10-09 | 2018-10-12 | #VALUE! |  | #VALUE! | 2018-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Canton | 2304052 | 2021 | 496.2 | PV | 269-1321H | 2018-10-12 | 2018-10-12 | 0 |  | 0 | 2018-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2020-12-08 | Online |  | Private
NSTAR | Plymouth | 2304254 | 2360 | 366.6 | PV | 3-13-943 | 2019-04-04 | 2019-04-12 | #VALUE! |  | #VALUE! | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Canton | 2304257 | 2021 | 350 | PV | 470-h7 | 2018-10-10 | 2018-10-18 | #VALUE! |  | #VALUE! | 2018-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2304259 | 2790 | 5000 | PV & Battery | 2-523-523 | 2018-10-02 | 2018-10-18 | #VALUE! |  | #VALUE! | 2018-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acusnet | 2304486 | 2743 | 3060 | PV & Battery | 2-241-238 | 2018-10-15 | 2018-10-18 | #VALUE! |  | #VALUE! | 2018-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Newton | 2304489 | 2468 | 75.6 | PV | 292-H12 | 2018-10-18 | 2018-11-02 | #VALUE! |  | #VALUE! | 2018-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-19 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05 | Online |  | Private
NSTAR | Framingham | 2304490 | 1701 | 43.2 | PV | 433-H2 | 2018-10-15 | 2018-10-19 | #VALUE! |  | #VALUE! | 2018-11-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online |  | Private
NSTAR | New Bedford | 2305081 | 2740 | 199.4 | PV | 2-38-38 | 2018-10-18 | 2018-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online |  | Public
NSTAR | Marion | 2305082 | 2738 | 20.88 | PV | 3-85-969 | 2018-10-19 | 2018-10-19 | 0 |  | 0 | 2018-11-05 | 2018-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-29 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-01-09 | Online |  | Private
NSTAR | New Bedford | 2305084 | 2746 | 428 | PV | 2-80-401 | 2018-10-18 | 2018-10-19 | #VALUE! |  | #VALUE! | 2018-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online |  | Public
NSTAR | Winchester | 2305372 | 2890 | 50 | PV | 211-H10 | 2018-10-19 | 2018-10-23 | #VALUE! |  | #VALUE! | 2018-11-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online |  | Private
NSTAR | Winchester | 2305374 | 1890 | 60 | PV | 211-H1 | 2018-10-19 | 2018-10-23 | #VALUE! |  | #VALUE! | 2018-11-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online |  | Private
NSTAR | Roslindale | 2305544 | 2131 | 336 | PV & Battery | 496-H4 | 2018-10-24 | 2018-11-07 | #VALUE! |  | #VALUE! | 2018-11-07 | 2018-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-04 | Online |  | Private
NSTAR | Jamaica Plain | 2305731 | 2130 | 60 | PV | 284-02 | 2018-10-19 | 2018-11-08 | #VALUE! |  | #VALUE! | 2018-11-08 | 2018-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-12-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-02-26 | Online |  | Private
NSTAR | Burlington | 2305732 | 1803 | 400 | PV | 391-H5 | 2018-11-06 | 2018-11-08 | #VALUE! |  | #VALUE! | 2018-11-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Burlington | 2305734 | 1803 | 800 | PV | 391-H5 | 2018-10-25 | 2018-11-08 | #VALUE! |  | #VALUE! | 2018-11-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Dartmouth | 2305846 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | #VALUE! |  | #VALUE! | 2018-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Dartmouth | 2305925 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | #VALUE! |  | #VALUE! | 2018-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online |  | Private
NSTAR | Holliston | 2306412 | 1746 | 490 | PV | 274-H3 | 2018-10-29 | 2018-11-14 | #VALUE! |  | #VALUE! | 2018-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2306416 | 2330 | 1625 | PV | 3-10-929 | 2018-10-29 | 2018-11-14 | #VALUE! |  | #VALUE! | 2018-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Rochester | 2306598 | 2770 | 1750 | PV | 3-703-703 | 2018-10-31 | 2018-11-15 | #VALUE! |  | #VALUE! | 2018-11-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Wareham | 2306600 | 2571 | 4999 | PV & Battery | 3-82-82 | 2018-11-01 | 2018-11-15 | #VALUE! |  | #VALUE! | 2018-11-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Norfolk | 2306602 | 2056 | 15.2 | PV | 146-H9 | 2018-11-01 | 2018-11-15 | #VALUE! |  | #VALUE! | 2018-11-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Lincoln | 2306816 | 1773 | 86.4 | PV | 320-H1 | 2018-11-01 | 2018-11-16 | #VALUE! |  | #VALUE! | 2018-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-23 | Online |  | Private
NSTAR | Edgartown | 2306817 | 2539 | 22.4 | PV | 4-99-99 | 2018-11-01 | 2018-11-16 | #VALUE! |  | #VALUE! | 2018-11-16 | 2018-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2306818 | 2571 | 240 | PV | 3-85-955 | 2018-11-01 | 2018-11-16 | #VALUE! |  | #VALUE! | 2018-11-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 | [5 empty] | Public
NSTAR | Framingham | 2307344 | 1702 | 57.6 | PV | 24-H1 | 2018-11-05 | 2018-11-20 | #VALUE! |  | #VALUE! | 2018-11-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-27 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-13 | Online |  | Private
NSTAR | Framingham | 2307346 | 1701 | 81 | PV | 278-H1 | 2018-11-05 | 2018-11-20 | #VALUE! |  | #VALUE! | 2018-11-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Chestnut Hill | 2307511 | 2467 | 496.2 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | #VALUE! |  | #VALUE! | 2018-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Chestnut Hill | 2307513 | 2467 | 499.8 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | #VALUE! |  | #VALUE! | 2018-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Rochester | 2307638 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-11-06 | 2018-11-23 | #VALUE! |  | #VALUE! | 2018-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Westport | 2307639 | 2790 | 1500 | PV | 2-532-532 | 2018-11-06 | 2018-11-23 | #VALUE! |  | #VALUE! | 2018-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Somerville | 2307640 | 2145 | 250 | PV & Battery | 250-H4XY | 2018-11-08 | 2018-11-23 | #VALUE! |  | #VALUE! | 2018-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Westport | 2307641 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-06 | 2018-11-23 | #VALUE! |  | #VALUE! | 2018-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Woburn | 2307642 | 1801 | 208.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | #VALUE! |  | #VALUE! | 2018-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online |  | Private
NSTAR | Woburn | 2308000 | 1801 | 333.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | #VALUE! |  | #VALUE! | 2018-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Westport | 2308001 | 2790 | 37.8 | PV | 2-532-532 | 2018-11-07 | 2018-11-27 | #VALUE! |  | #VALUE! | 2018-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | New Bedford | 2308002 | 2740 | 43.2 | PV | 2-24-182 | 2018-11-07 | 2018-11-27 | #VALUE! |  | #VALUE! | 2018-11-27 | 2018-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-04 | 2018-12-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-20 | Online |  | Private
NSTAR | West Tisbury | 2308167 | 2575 | 22.33 | PV & Battery | 3-24B-95 | 2018-11-07 | 2018-11-28 | #VALUE! |  | #VALUE! | 2018-11-28 | 2018-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-07 | 2018-12-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-09-06 | Online |  | Private
NSTAR | Boston | 2308171 | 2114 | 50 | CHP | 274-H3 | 2018-11-07 | 2018-11-28 | #VALUE! |  | #VALUE! | 2018-11-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online |  | Private
NSTAR | Dennis | 2308172 | 2638 | 17.4 | PV | 4-92B-92B | 2018-11-07 | 2018-11-28 | #VALUE! |  | #VALUE! | 2018-11-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2019-04-30 | Online |  | Private
NSTAR | Boston | 2308328 | 2115 | 1600 | PV & Battery | 528-169H | 2018-11-27 |  | #VALUE! |  | #VALUE! | 2018-12-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Plymouth | 2308333 | 2360 | 500 | PV | 3-13-943 | 2018-11-13 | 2018-11-29 | #VALUE! |  | #VALUE! | 2018-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Hopkinton | 2308334 | 1748 | 2000 | PV & Battery | 126-H4 | 2018-11-14 | 2018-11-29 | #VALUE! |  | #VALUE! | 2018-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dartmouth | 2308512 | 2748 | 17.4 | PV | 2-528-528 | 2018-11-14 | 2018-11-30 | #VALUE! |  | #VALUE! | 2018-11-30 | 2018-12-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 | 2018-12-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-30 | Online |  | Private
NSTAR | Carver | 2308513 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-11-15 | 2018-11-30 | #VALUE! |  | #VALUE! | 2018-11-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Somerville | 2308642 | 2145 | 600 | Fuel Cell | 250-H4XY | 2018-11-15 | 2018-12-03 | #VALUE! |  | #VALUE! | 2018-12-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online |  | Private
NSTAR | North Dartmouth | 2308643 | 2747 | 18.15 | PV | 2-532-532 | 2018-11-16 | 2018-12-03 | #VALUE! |  | #VALUE! | 2018-12-03 | 2018-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-24 | Online |  | Private
NSTAR | Kingston | 2311123 | 2364 | 1531.8 | PV | 3/14-14 | 2018-11-16 | 2018-12-05 | #VALUE! |  | #VALUE! | 2018-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Marshfield | 2311127 | 2050 | 2112 | PV | 3-24A-24A | 2018-11-16 | 2018-12-05 | #VALUE! |  | #VALUE! | 2018-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online |  | Private
NSTAR | Framingham | 2311128 | 1702 | 492 | PV | 455-H2 | 2018-12-05 | 2018-12-05 | 0 |  | 0 | 2018-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Canton | 2311297 | 2021 | 225 | PV | 470-H7 | 2018-11-14 | 2018-11-21 | #VALUE! |  | #VALUE! | 2018-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Plymouth | 2311298 | 2360 | 233.1 | PV | 3-13-13 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2311303 | 2535 | 83.52 | PV | 4-91-126 | 2018-11-21 | 2018-12-06 | #VALUE! |  | #VALUE! | 2018-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | 2018-12-27 | [6 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Woburn | 2311476 | 1801 | 249.8 | PV | 211-H2 | 2018-11-21 | 2018-12-07 | #VALUE! |  | #VALUE! | 2018-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-08 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online |  | Private
NSTAR | Plympton | 2311480 | 2367 | 2000 | PV & Battery | 3-51-901 | 2018-11-21 | 2018-12-07 | #VALUE! |  | #VALUE! | 2018-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Natick | 2311483 | 1760 | 180 | PV | 433-H10 | 2018-11-21 | 2018-12-07 | #VALUE! |  | #VALUE! | 2018-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online |  | Private
NSTAR | Rochester | 2311484 | 2770 | 19 | PV | 3-703-703 | 2018-11-21 | 2018-12-07 | #VALUE! |  | #VALUE! | 2018-12-07 | 2018-12-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Cotuit | 2311617 | 2635 | 17.93 | PV & Battery | 4-88-880 | 2018-11-26 | 2018-12-10 | #VALUE! |  | #VALUE! | 2018-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-15 | [7 empty] | 0 |  | 0 |  |  | 2019-10-21 | Online |  | Private
NSTAR | Lexington | 2311846 | 2421 | 1149 | PV & Battery | 533-H1 | 2018-11-27 | 2018-12-11 | #VALUE! |  | #VALUE! | 2018-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2311847 | 2050 | 115.44 | PV | 3-24A-24A | 2018-11-28 | 2018-12-11 | #VALUE! |  | #VALUE! | 2018-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Oak Bluffs | 2311848 | 2557 | 249.8 | PV | 4-75-75 | 2018-11-29 | 2018-12-11 | #VALUE! |  | #VALUE! | 2018-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2312220 | 2459 | 200 | PV | 292-H3 | 2018-11-28 | 2018-11-29 | #VALUE! |  | #VALUE! | 2018-12-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 |  |  |  | EXP |  |  |  | 0 |  | 0
NSTAR | Stoneham | 2312221 | 2180 | 15.98 | PV | 375-H8 | 2018-11-07 | 2018-11-29 | #VALUE! |  | #VALUE! | 2018-12-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-01 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2312223 | 2067 | 660 | PV & Battery | 146-H7 | 2018-10-25 | 2018-12-03 | #VALUE! |  | #VALUE! | 2018-12-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2020-09-30
NSTAR | Roxbury | 2312379 | 2119 | 199.8 | PV | 106-H4 | 2018-12-03 | 2018-12-03 | 0 |  | 0 | 2018-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Bourne | 2312381 | 2532 | 999 | PV | 3-88-88 | 2018-11-21 | 2018-12-03 | #VALUE! |  | #VALUE! | 2018-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Falmouth | 2313194 | 2540 | 24.84 | PV | 4-98A-98A | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0 |  |  | 2019-05-02 | Online
NSTAR | Roxbury | 2313198 | 2119 | 36 | PV | 106-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Westport | 2313433 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-29 | 2018-12-04 | #VALUE! |  | #VALUE! | 2018-12-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2313435 | 2655 | 4998 | PV & Battery | 4-96-674 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2313788 | 2770 | 496.6 | PV | 3-85-85 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Boston | 2313793 | 2128 | 250 | PV | 488-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Canton | 2313802 | 2021 | 100 | PV | 269-1320H1 | 2018-12-04 | 2018-12-06 | #VALUE! |  | #VALUE! | 2018-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Hyde Park | 2313809 | 2136 | 15.2 | PV | 441-06 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2313811 | 1749 | 31.7 | PV | 386-1356 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2313933 | 2575 | 92.4 | PV | 4-97-97 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0
NSTAR | Cotuit | 2314367 | 2635 | 15.2 | PV | 4-88-880 | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2314368 | 2645 | 20 | PV | 4-92B-92B | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-05-21 | Online
NSTAR | Carver | 2314369 | 2330 | 3500 | PV | 3-81-950 | 2018-11-27 | 2018-12-10 | #VALUE! |  | #VALUE! | 2018-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2314370 | 2451 | 40 | PV | 282-H8 | 2018-12-11 |  | #VALUE! |  | #VALUE! | 2018-12-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2314371 | 2745 | 100 | PV | 2-137-139 | 2018-12-12 | 2018-12-12 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-08
NSTAR | East Freetown | 2314499 | 2717 | 3300 | PV & Battery | 2-102-604 | 2018-10-19 | 2018-12-14 | #VALUE! |  | #VALUE! | 2018-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Stoneham | 2314500 | 2180 | 72 | PV | 375-H7 | 2018-12-13 | 2018-12-17 | #VALUE! |  | #VALUE! | 2018-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2019-08-07 | Online
NSTAR | Stoneham | 2314501 | 2180 | 150 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | #VALUE! |  | #VALUE! | 2018-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2316352 | 2180 | 50 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | #VALUE! |  | #VALUE! | 2019-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-03 | [7 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Plympton | 2316354 | 2364 | 4999 | PV & Battery | 3-15-15 | 2018-12-12 | 2018-12-18 | #VALUE! |  | #VALUE! | 2019-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2316355 | 1748 | 6310 | PV & Battery | 533-H7 | 2018-12-20 | 2018-12-20 | 0 |  | 0 | 2019-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2316959 | 2601 | 500 | PV | 4-63-63 | 2018-11-21 | 2018-12-12 | #VALUE! |  | #VALUE! | 2019-01-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2316966 | 2536 | 4500 | PV | 4-98A-98A | 2018-12-11 | 2018-12-17 | #VALUE! |  | #VALUE! | 2019-01-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online
NSTAR | East Falmouth | 2317177 | 2536 | 4000 | PV | 4-98A-98A | 2018-12-12 | 2018-12-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-14 | Online
NSTAR | Sudbury | 2317182 | 1766 | 499.99 | PV | 342-H2 | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2317183 | 2540 | 1000 | PV | 4-98A-98A | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2319218 | 2717 | 8360 | PV & Battery | 2-605-605 | 2018-12-07 | 2018-12-18 | #VALUE! |  | #VALUE! | 2019-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319219 | 2460 | 206 | PV | 17-H2 | 2018-12-17 | 2018-12-20 | #VALUE! |  | #VALUE! | 2019-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319220 | 2460 | 66.66 | PV | 467-H3 | 2018-12-17 | 2018-12-19 | #VALUE! |  | #VALUE! | 2019-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2319393 | 2360 | 999 | PV & Battery | 3-73-73 | 2018-12-18 | 2018-12-18 | 0 |  | 0 | 2018-01-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2319563 | 2460 | 233 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | #VALUE! |  | #VALUE! | 2019-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2319566 | 2460 | 66.66 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | #VALUE! |  | #VALUE! | 2019-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Holliston | 2319567 | 1746 | 1640 | PV | 274-H3 | 2018-12-17 | 2018-12-19 | #VALUE! |  | #VALUE! | 2019-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Vineyard Haven | 2319568 | 2568 | 43.2 | PV | 4-75-75 | 2018-12-13 | 2018-12-20 | #VALUE! |  | #VALUE! | 2019-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-04 | [7 empty] | 0 |  | 0 |  |  | 2019-10-29
NSTAR | Marshfield | 2319796 | 2050 | 15.2 | PV | 3-25-42J2 | 2018-12-11 | 2018-12-21 | #VALUE! |  | #VALUE! | 2019-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online
NSTAR | Waltham | 2319797 | 2451 | 106.6 | PV | 3-25-42J2 | 2018-12-19 | 2018-12-21 | #VALUE! |  | #VALUE! | 2019-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Westport | 2319812 | 2790 | 22.1 | PV | 2-532-532 | 2018-12-19 | 2018-12-21 | #VALUE! |  | #VALUE! | 2019-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Kingston | 2319914 | 2364 | 406.5 | PV | 3-26-902 | 2018-12-19 | 2019-01-02 | #VALUE! |  | #VALUE! | 2019-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-09 | Online
NSTAR | Newton | 2320273 | 2468 | 133.3 | PV | 17-H2 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-05-04 | Online
NSTAR | Dover | 2320293 | 2030 | 19.8 | PV | 456-H1 | 2018-12-26 | 2019-01-07 | #VALUE! |  | #VALUE! | 2019-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-05 | [7 empty] | 0 |  | 0 |  |  | 2019-07-22 | Online
NSTAR | Wareham | 2320442 | 2571 | 5000 | PV | 8-83-83 | 2018-12-12 | 2018-12-21 | #VALUE! |  | #VALUE! | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2320444 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-12-16 | 2018-12-19 | #VALUE! |  | #VALUE! | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2320445 | 2021 | 3240 | PV | 269-1320H1 | 2018-12-19 | 2018-12-26 | #VALUE! |  | #VALUE! | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2320446 | 2770 | 2900 | PV | 3-703-703 | 2018-12-21 | 2018-12-26 | #VALUE! |  | #VALUE! | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2320561 | 2563 | 500 | PV | 4-87A-471 | 2019-01-02 | 2019-01-02 | 0 |  | 0 | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2320621 | 2702 | 4875 | PV | 2-605-605 | 2018-12-26 | 2018-12-27 | #VALUE! |  | #VALUE! | 2019-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2320623 | 2770 | 4890 | PV & Battery | 3-703-703 | 2018-12-26 | 2018-12-27 | #VALUE! |  | #VALUE! | 2019-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2320809 | 2360 | 4999 | PV & Battery | 3-73-73 | 2019-01-08 | 2019-01-08 | 0 |  | 0 | 2019-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2320829 | 2026 | 399.6 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | #VALUE! |  | #VALUE! | 2019-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online
NSTAR | Acusnet | 2320833 | 2743 | 21.34 | PV & Battery | 2-241-241 | 2018-04-06 | 2018-12-26 | #VALUE! |  | #VALUE! | 2019-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-01 | Online
NSTAR | West Yarmouth | 2320835 | 2673 | 498 | PV | 4-92A-534 | 2018-12-20 | 2018-12-26 | #VALUE! |  | #VALUE! | 2019-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 2321103 | 1773 | 20 | PV & Battery | 320-H6 | 2018-12-20 | 2019-01-08 | #VALUE! |  | #VALUE! | 2019-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 | [7 empty] | 0 |  | 0 |  |  | 2019-09-03 | Online
NSTAR | Watertown | 2321147 | 2472 | 100 | PV | 467-H4 | 2018-12-26 | 2018-12-27 | #VALUE! |  | #VALUE! | 2019-01-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Dedham | 2321149 | 2026 | 199.8 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | #VALUE! |  | #VALUE! | 2019-01-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-11-07 | Online
NSTAR | Dedham | 2321151 | 2026 | 119 | PV | 20-H6 | 2018-12-19 | 2018-12-28 | #VALUE! |  | #VALUE! | 2019-01-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2321334 | 1760 | 32.4 | PV | TBD | 2019-01-18 |  | #VALUE! | 0 | #VALUE! | 2019-01-22 | 2019-03-05 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2321677 | 2330 | 6500 | PV | 3-10-930 | 2019-01-07 | 2019-01-08 | #VALUE! |  | #VALUE! | 2019-01-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2321814 | 2021 | 132 | PV | 269-1320H1 | 2018-12-18 | 2019-01-09 | #VALUE! |  | #VALUE! | 2019-01-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-29 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2321912 | 1760 | 72 | PV | 433-H10 | 2019-01-15 | 2019-01-15 | 0 |  | 0 | 2019-01-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Wareham | 2322036 | 2571 | 2250 | PV | 8-83-83 | 2019-01-04 | 2019-01-07 | #VALUE! |  | #VALUE! | 2019-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2322113 | 2532 | 1390 | PV | 4-86-402 | 2019-01-07 | 2019-01-16 | #VALUE! |  | #VALUE! | 2019-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2322158 | 1721 | 346.2 | PV | 455-H3 | 2018-12-19 | 2019-01-16 | #VALUE! |  | #VALUE! | 2019-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Woburn | 2322181 | 1801 | 15.2 | PV | 375-H12 | 2018-12-28 | 2019-01-16 | #VALUE! |  | #VALUE! | 2019-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | Watertown | 2322219 | 2472 | 249.9 | PV | 467-H4 | 2019-01-15 | 2019-01-17 | #VALUE! |  | #VALUE! | 2019-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2322394 | 2026 | 499.5 | PV | 20-H5 | 2018-12-19 | 2019-01-17 | #VALUE! |  | #VALUE! | 2019-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online
NSTAR | Mattapoisett | 2322525 | 2739 | 115.2 | PV | 2-302-302 | 2019-01-15 | 2019-01-17 | #VALUE! |  | #VALUE! | 2019-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2020-01-10 | Online
NSTAR | North Dartmouth | 2322528 | 2747 | 720 | PV | 2-541-541 | 2018-12-19 | 2019-01-17 | #VALUE! |  | #VALUE! | 2019-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2322577 | 2136 | 60 | PV | 344-08 | 2019-01-18 | 2019-01-18 | 0 |  | 0 | 2019-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Falmouth | 2322598 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2019-01-17 |  | #VALUE! |  | #VALUE! | 2019-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2322632 | 1720 | 242 | PV | 416-H4 | 2019-01-18 |  | #VALUE! |  | #VALUE! | 2019-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2322689 | 2134 | 57.6 | PV | 456-H3 | 2019-01-04 | 2019-01-09 | #VALUE! |  | #VALUE! | 2019-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Needham | 2322796 | 2492 | 28.8 | PV | 148-H1 | 2019-01-18 | 2019-01-25 | #VALUE! |  | #VALUE! | 2019-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Barnstable | 2322818 | 2668 | 17.92 | PV | 4-87B-473 | 2019-01-30 | 2019-01-30 | 0 | 0 | 0 | 2019-02-01 | 2019-02-26 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-02-26 | 2019-03-01 | 2019-09-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-07-16 | Online |  | Private
NSTAR | Dorchester | 2322890 | 2122 | 260 | PV & Battery | 483-H7 | 2019-01-02 |  | #VALUE! |  | #VALUE! | 2019-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | South Dennis | 2323237 | 2660 | 4951 | PV | tbd | 2019-01-24 | 2019-01-28 | #VALUE! |  | #VALUE! | 2019-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323317 | 2360 | 26.55 | PV | 3-13-943 | 2019-01-23 |  | #VALUE! |  | #VALUE! | 2019-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2323381 | 2459 | 1000 | PV | 282-H8 | 2019-01-24 |  | #VALUE! |  | #VALUE! | 2019-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2323400 | 2451 | 480 | PV | 450-H7 | 2019-01-25 |  | #VALUE! |  | #VALUE! | 2019-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online
NSTAR | Dorchester | 2323443 | 2124 | 15.2 | PV | 483-H2 | 2019-01-07 | 2019-01-14 | #VALUE! |  | #VALUE! | 2019-02-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-24 | Online
NSTAR | Sandwich | 2323654 | 2563 | 2660 | PV | 4-81B-443 | 2019-01-23 | 2019-01-29 | #VALUE! |  | #VALUE! | 2019-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2323699 | 2790 | 72 | PV | 2-532-532 | 2019-01-22 | 2019-01-31 | #VALUE! |  | #VALUE! | 2019-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323714 | 2360 | 700 | PV | 3-71-937 | 2019-01-25 | 2019-01-29 | #VALUE! |  | #VALUE! | 2019-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-05-21 | Online
NSTAR | Ashland | 2323862 | 1721 | 500 | PV | 455-H3 | 2019-01-07 | 2019-01-11 | #VALUE! |  | #VALUE! | 2019-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2323875 | 2747 | 699.3 | PV | 2-528-528 | 2019-01-17 | 2019-01-22 | #VALUE! |  | #VALUE! | 2019-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2323953 | 2571 | 2000 | PV | 3-82-82 | 2019-02-06 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-24 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Carver | 2324188 | 2330 | 2350 | PV | 3-10-930 | 2019-01-18 | 2019-01-23 | #VALUE! |  | #VALUE! | 2019-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Boston | 2324396 | 2128 | 115.2 | PV | 488-H5 | 2019-01-18 | 2019-01-23 | #VALUE! |  | #VALUE! | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Canton | 2324409 | 2021 | 299.7 | PV | 269-1320H1 | 2019-01-17 |  | #VALUE! |  | #VALUE! | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2324659 | 1701 | 4980 | PV & Battery | 2-605-605 | 2018-12-27 | 2019-02-01 | #VALUE! |  | #VALUE! | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2324673 | 2631 | 25 | PV | 4-95A-597 | 2019-01-28 | 2019-02-01 | #VALUE! |  | #VALUE! | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0 |  |  | 2019-07-01 | Online
NSTAR | South Dennis | 2324745 | 2660 | 133.3 | PV | 4-92B-92B | 2019-02-01 | 2019-02-01 | 0 |  | 0 | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Cambridge | 2324814 | 2139 | 44000 | CHP | 831-1314 | 2019-02-12 | 2019-02-19 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | 2019-03-04 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Woburn | 2325016 | 1801 | 243.1 | PV | 375-H3 | 2018-12-26 | 2019-02-07 | #VALUE! |  | #VALUE! | 2019-02-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-16 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | Acton | 2325167 | 1720 | 43.2 | PV | 416-H2 | 2019-02-07 | 2019-02-07 | 0 |  | 0 | 2019-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Framingham | 2325422 | 1702 | 240 | PV | 433-H8 | 2019-01-14 | 2019-01-14 | 0 |  | 0 | 2019-02-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Weston | 2325546 | 2493 | 200 | PV | 342-H1 | 2019-02-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Brewster | 2325660 | 2631 | 24.99 | PV | 4-95B-600 | 2019-02-05 | 2019-02-08 | #VALUE! |  | #VALUE! | 2019-02-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2019-07-15 | Online
NSTAR | Framingham | 2325768 | 1702 | 996 | PV | 240-H6 | 2019-02-06 | 2019-02-08 | #VALUE! |  | #VALUE! | 2019-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2325785 | 1801 | 216 | PV | 375-H14 | 2019-02-05 | 2019-02-08 | #VALUE! |  | #VALUE! | 2019-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Woburn | 2325824 | 1801 | 250 | PV | 211-H6 | 2019-02-06 | 2019-02-08 | #VALUE! |  | #VALUE! | 2019-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Rochester | 2325833 | 2770 | 20 | PV | 3-703-703 | 2019-02-06 | 2019-02-11 | #VALUE! |  | #VALUE! | 2019-02-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online
NSTAR | East Walpole | 2326033 | 2032 | 2370 | PV | 2-102-604 | 2019-01-29 | 2019-02-11 | #VALUE! |  | #VALUE! | 2019-02-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-07-20 | Online
NSTAR | Boston | 2326176 | 2130 | 37.8 | PV | 528-169H | 2019-01-23 | 2019-02-04 | #VALUE! |  | #VALUE! | 2019-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Dorchester | 2326311 | 2125 | 1516 | PV | 466-1481H1 | 2019-01-28 |  | #VALUE! |  | #VALUE! | 2019-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2326325 | 2494 | 194 | PV | 148-H4 | 2019-02-04 |  | #VALUE! |  | #VALUE! | 2019-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2019-09-10 | Online
NSTAR | Dorchester | 2326537 | 2122 | 52.2 | PV | 466-1482H1 | 2019-02-07 |  | #VALUE! |  | #VALUE! | 2019-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-08 | Online
NSTAR | Carver | 2326793 | 2330 | 2000 | PV | 3-10-917 | 2019-02-11 | 2019-02-12 | #VALUE! |  | #VALUE! | 2019-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2326814 | 1801 | 233.1 | PV | 211-H6 | 2019-02-12 | 2019-02-12 | 0 |  | 0 | 2019-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Hopkinton | 2326836 | 1748 | 206 | PV | 126-H2 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Stoneham | 2326872 | 2180 | 200 | PV | 375-H7 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Chatham | 2326896 | 2633 | 117.12 | PV & Battery | 4-95A-95A | 2019-01-23 | 2019-02-04 | #VALUE! |  | #VALUE! | 2019-02-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0 |  |  | 2020-07-01 | Online
NSTAR | Burlington | 2327102 | 1805 | 5274.6 | PV & Battery | 541-1377H | 2019-01-22 | 2019-02-15 | #VALUE! |  | #VALUE! | 2019-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2327130 | 2540 | 4980 | PV & Battery | 4-98B-448 | 2019-02-01 | 2019-02-15 | #VALUE! |  | #VALUE! | 2019-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2327251 | 2138 | 86.4 | PV | 831-1336XY | 2019-02-14 | 2019-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Chilmark | 2327284 | 2535 | 25 | PV | 4-91-126 | 2019-02-20 | 2019-02-22 | #VALUE! |  | #VALUE! | 2019-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0 |  |  | 2019-10-02 | Online
NSTAR | Plympton | 2327303 | 2367 | 2000 | PV | 3-10-930 | 2019-02-11 | 2019-02-12 | #VALUE! |  | #VALUE! | 2019-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2327320 | 2739 | 2000 | PV | 2-302-302 | 2019-02-12 | 2019-02-14 | #VALUE! |  | #VALUE! | 2019-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2327357 | 2114 | 50 | PV | 528-169H | 2019-02-14 | 2019-02-14 | 0 |  | 0 | 2019-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Chilmark | 2327379 | 2535 | 16.24 | PV | 4-97-220 | 2019-02-20 | 2019-02-20 | 0 |  | 0 | 2019-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-08 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2327596 | 2090 | - |  | TBD | 2019-03-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-10-04 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Rochester | 2328012 | 2770 | 15000 | PV | 3-85-85 | 2018-12-12 | 2018-12-18 | #VALUE! |  | #VALUE! | 2019-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2328021 | 2330 | 499 | PV |  | 2019-03-04 | 2019-03-07 | #VALUE! | 0 | #VALUE! | 2019-03-07 | 2019-03-20 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2019-04-17 | 2020-10-16 | No | EXP | 30 | 2020-10-14 |  | #VALUE! |  | #VALUE! |  |  |  | In Queue |  | Private
NSTAR | Plymouth | 2328025 | 2360 | 630 | PV & Battery | 3-71-937 | 2019-02-19 | 2019-02-19 | 0 |  | 0 | 2019-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2328085 | 2717 | 27.42 | PV | 2-102-102 | 2019-02-20 | 2019-02-21 | #VALUE! |  | #VALUE! | 2019-03-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Plymouth | 2328095 | 2360 | 500 | PV & Battery | 3-89-89 | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-03-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2328177 | 1760 | 32.4 | PV | 433-H10 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Framingham | 2328190 | 1701 | 57 | PV |  | 2019-03-05 | 2019-11-25 | #VALUE! | 182 | #VALUE! | 2019-11-25 | 2019-12-10 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-12-20 |  | 2019-10-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2022-11-21 | Online |  | Private | N
NSTAR | Boston | 2328228 | 2134 | 180 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | #VALUE! |  | #VALUE! | 2019-03-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-08 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online
NSTAR | Roxbury Crossing | 2328268 | 2120 | 72 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | #VALUE! |  | #VALUE! | 2019-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2328535 | 2460 | 220 | PV | 17-H1 | 2019-01-17 | 2019-02-26 | #VALUE! |  | #VALUE! | 2019-03-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Norfolk | 2328724 | 2056 | 195 | PV | 146-H9 | 2019-02-14 | 2019-02-19 | #VALUE! |  | #VALUE! | 2019-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2328863 | 2601 | 100 | PV | 4-63-63 | 2019-02-21 | 2019-02-25 | #VALUE! |  | #VALUE! | 2019-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-18 | Online
NSTAR | Waltham | 2329018 | 2451 | 924 | PV | 450-H7 | 2019-02-21 | 2019-03-04 | #VALUE! |  | #VALUE! | 2019-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2329096 | 2021 | 1100 | PV | 269-1320H1 | 2019-02-06 | 2019-02-28 | #VALUE! |  | #VALUE! | 2019-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2329126 | 2131 | 20.7 | PV | 468-02 | 2019-01-04 | 2019-02-27 | #VALUE! |  | #VALUE! | 2019-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2019-08-05 | Online
NSTAR | Hyannis | 2329185 | 2601 | 43.6 | PV | 4-63-63 | 2019-02-25 | 2019-02-28 | #VALUE! |  | #VALUE! | 2019-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-09-23 | Online
NSTAR | Sherborn | 2329192 | 1770 | 34.78 | PV | 240-H1 | 2019-02-15 | 2019-02-26 | #VALUE! |  | #VALUE! | 2019-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Brewster | 2329348 | 2631 | 20 | PV | 4-89B-576 | 2019-02-28 | 2019-03-05 | #VALUE! |  | #VALUE! | 2019-03-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329391 | 2739 | 4600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | #VALUE! |  | #VALUE! | 2019-03-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329466 | 2743 | 4980 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | #VALUE! |  | #VALUE! | 2019-03-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330206 | 2739 | 2600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-03-06 | #VALUE! |  | #VALUE! | 2019-03-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2330259 | 1801 | 233.2 | PV | 375-H3 | 2019-03-05 | 2019-03-08 | #VALUE! |  | #VALUE! | 2019-03-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-12 | Online
NSTAR | Sandwich | 2330325 | 2644 | 5000 | PV & Battery | 4-81B-443 | 2019-02-22 | 2019-02-27 | #VALUE! |  | #VALUE! | 2019-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2330355 | 2459 | 266 | PV | 17-H2 | 2019-03-11 | 2019-03-11 | 0 |  | 0 | 2019-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sandwich | 2330360 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330392 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2330416 | 2492 | 23.3 | PV | 148-H4 | 2019-02-12 | 2019-03-07 | #VALUE! |  | #VALUE! | 2019-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-21
NSTAR | South Yarmouth | 2330447 | 2664 | 233.64 | PV | 4-90-90 | 2019-02-28 | 2019-03-06 | #VALUE! |  | #VALUE! | 2019-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2330458 | 2601 | 699.9 | PV | 4-63-63 | 2019-03-04 | 2019-03-12 | #VALUE! |  | #VALUE! | 2019-03-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2022-12-31 | Online
NSTAR | Assonett | 2330491 | 2702 | 4890 | PV & Battery |  | 2019-03-19 | 2019-03-20 | #VALUE! | 0 | #VALUE! | 2019-03-26 |  | #VALUE! | 439 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-04-02 | Private
NSTAR | Winchester | 2330512 | 1890 | 37.8 | PV | 211-H1 | 2019-03-01 | 2019-03-11 | #VALUE! |  | #VALUE! | 2019-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09 | Online
NSTAR | Sandwich | 2330718 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330720 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330775 | 2739 | 4980 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-06 | #VALUE! |  | #VALUE! | 2019-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | Roslindale | 2330819 | 2131 | 42.8 | PV | 1312 | 2019-02-21 | 2019-03-04 | #VALUE! |  | #VALUE! | 2019-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05
NSTAR | Sandwich | 2330875 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330882 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330923 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330926 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-07 | 2019-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2330941 | 2081 | 250 | PV | 146-H1 | 2019-03-08 | 2019-03-13 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2331027 | 2653 | 133.3 | PV | TBD | 2019-03-22 |  | #VALUE! | 0 | #VALUE! | 2019-04-17 | 2019-05-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-04-15 | 2019-11-21 | 2019-10-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Sandwich | 2331148 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331153 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331280 | 2744 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | #VALUE! |  | #VALUE! | 2019-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331299 | 2743 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | #VALUE! |  | #VALUE! | 2019-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331348 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331371 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2331457 | 2118 | 1000 | PV & Battery | 4912 | 2019-02-11 | 2019-03-14 | #VALUE! |  | #VALUE! | 2019-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2331587 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331592 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-01-02 | 2019-02-26 | #VALUE! |  | #VALUE! | 2019-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2331739 | 2142 | 75 | PV | 875-1N35B | 2019-02-14 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Walpole | 2331931 | 2081 | 407 | PV | 146-H1 | 2019-01-11 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2332061 | 2649 | 254.29 | PV | 4-88-483 | 2019-03-13 | 2019-03-15 | #VALUE! |  | #VALUE! | 2019-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-03 | Online
NSTAR | Ashland | 2333111 | 1721 | 250 | PV & Battery | 455-H3 | 2019-03-05 | 2019-03-18 | #VALUE! |  | #VALUE! | 2019-04-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2333220 | 1721 | 250 | PV | 455-H3 | 2019-01-11 | 2019-03-18 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2333229 | 1760 | 407 | PV & Battery | 433-H10 | 2019-01-17 | 2019-03-18 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2333242 | 2601 | 254.29 | PV | 4-63-63 | 2019-03-14 | 2019-03-19 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0 |  |  | 2020-01-09 | Online
NSTAR | Dorchester | 2333256 | 2124 | 240 | PV | 466-1481H1 | 2019-03-08 | 2019-03-19 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2333267 | 2421 | - |  | TBD | 2019-04-04 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Duxbury | 2333489 | 2332 | 20 | PV | 3-26-903 | 2019-03-07 | 2019-03-22 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333508 | 2740 | 346.5 | PV | 2-137-139 | 2019-03-18 | 2019-03-22 | #VALUE! |  | #VALUE! | 2019-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333666 | 2745 | 22.8 | PV | 2-87-135 | 2019-03-13 | 2019-03-25 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Newton | 2333672 | 2460 | 360 | PV | 282-H8 | 2019-03-22 | 2019-03-25 | #VALUE! |  | #VALUE! | 2019-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-11 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Wareham | 2333726 | 2571 | 4500 | PV | 8-83-83 | 2019-03-22 | 2019-03-25 | #VALUE! |  | #VALUE! | 2019-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2333746 | 2571 | 4500 | PV |  | 2019-04-08 | 2019-04-09 | #VALUE! | 0 | #VALUE! | 2019-04-10 |  | #VALUE! | 427 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-04-18 | Private
NSTAR | South Boston | 2333766 | 2127 | 172.8 | PV | 106-H3 | 2019-03-05 | 2019-03-25 | #VALUE! |  | #VALUE! | 2019-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Walpole | 2333782 | 2081 | 34.2 | PV | 146-H4 | 2019-04-08 | 2019-04-12 | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | South Dennis | 2333807 | 2660 | 699.7 | PV | 4-92B-92B | 2019-03-04 | 2019-03-25 | #VALUE! |  | #VALUE! | 2019-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Edgartown | 2333814 | 2539 | 24 | PV | TBD | 2019-02-26 | 2019-03-20 | #VALUE! |  | #VALUE! | 2019-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Walpole | 2334013 | 2081 | 400 | PV |  | 2019-04-10 | 2019-04-12 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-19 | 2020-06-03 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 | 2020-11-17 | 2020-11-20 | #VALUE! | 0 | #VALUE! | 2020-02-21 | 2020-12-29 | 2021-01-15 | No |  | 60 | 2020-02-10 |  | #VALUE! |  | #VALUE! |  |  | 2021-05-24 | Online |  | Private | N
NSTAR | Walpole | 2334039 | 2081 | 131.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-06-15 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | 2020-06-09 | 2020-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Forestdale | 2334165 | 2644 | 4990 | PV | 4-81B-443 | 2019-03-14 | 2019-03-26 | #VALUE! |  | #VALUE! | 2019-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2334186 | 2360 | 144 | PV | 3-89-89 | 2019-03-20 | 2019-03-26 | #VALUE! |  | #VALUE! | 2019-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-11-18 | Online
NSTAR | Walpole | 2334212 | 2081 | 37.8 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-18 | 2019-05-31 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-04 | 2019-06-18 | 2020-06-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
NSTAR | Walpole | 2334218 | 2081 | 32.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online |  | Private
NSTAR | Walpole | 2334252 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online |  | Gov't
NSTAR | Walpole | 2334255 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online |  | Gov't
NSTAR | Mattapoisett | 2334358 | 2739 | 3300 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-27 | #VALUE! |  | #VALUE! | 2019-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | New Bedford | 2334371 | 2744 | 180 | PV | 2-137-139 | 2019-01-31 | 2019-03-27 | #VALUE! |  | #VALUE! | 2019-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-07-29 | Online
NSTAR | Sandwich | 2334390 | 2563 | 250 | PV & Battery | 4-81B-443 | 2019-03-27 | 2019-03-27 | 0 |  | 0 | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2334399 | 1730 | 200 | PV | 322-05 | 2019-03-25 | 2019-03-28 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2334411 | 2081 | 142 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-18 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-09 | Online |  | Gov't
NSTAR | Walpole | 2334415 | 2081 | 129.6 | PV | TBD | 2019-04-11 |  | #VALUE! | 0 | #VALUE! | 2019-04-19 | 2019-05-30 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-06-04 | 2020-01-08 | 2019-11-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Sandwich | 2334444 | 2563 | 77.5 | PV | 4-81B-443 | 2019-02-19 | 2019-03-28 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | East Dennis | 2334447 | 2641 | 36 | PV | 4-89A-552 | 2019-03-25 | 2019-03-28 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | Sudbury | 2334450 | 1776 | 15.2 | PV & Battery | 342-H5 | 2019-03-29 | 2019-04-12 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Walpole | 2334456 | 2081 | 1000 | PV & Battery | 146-H1 | 2019-03-15 | 2019-03-28 | #VALUE! |  | #VALUE! | 2019-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 | 2745 | 496 | PV |  | 2019-04-12 | 2019-04-16 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-18 | 2020-09-08 | #VALUE! | 319 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-09-20 | Private
NSTAR | Lexington | 2334511 | 2421 | 1500 | PV & Battery | 533-H1 | 2019-03-15 | 2019-03-20 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2334531 | 2747 | 1000 | PV | 2-528-528 | 2019-03-08 | 2019-03-19 | #VALUE! |  | #VALUE! | 2019-04-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334854 | 2745 | 199.8 | PV | 2-137-139 | 2019-04-15 | 2019-04-16 | #VALUE! | 0 | #VALUE! | 2019-04-18 |  | #VALUE! | 379 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-06-26 | Private
NSTAR | Milton | 2335039 | 2186 | 61.2 | PV | 496-H2 | 2019-03-28 | 2019-04-01 | #VALUE! |  | #VALUE! | 2019-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Plymouth | 2335156 | 2360 | - |  | TBD | 2019-04-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Norfolk | 2335261 | 2056 | 50 | PV | 146-H9 | 2019-04-01 | 2019-04-01 | 0 |  | 0 | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-05 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Jamaica Plain | 2335383 | 2130 | 432.9 | PV | 496-H4 | 2019-04-02 | 2019-04-02 | 0 |  | 0 | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-01 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2335440 | 1760 | 150 | CHP | 433-H7 | 2019-03-26 | 2019-04-02 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-02-18 | Online
NSTAR | South Dennis | 2335447 | 2660 | 133.2 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | South Dennis | 2335454 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2335459 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2335506 | 2770 | 25 | PV | 3-702-702 | 2019-03-20 | 2019-04-02 | #VALUE! |  | #VALUE! | 2019-05-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2335814 | 2360 | 1800 | PV | 3-89-89 | 2019-03-20 | 2019-04-04 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2335827 | 2330 | 2000 | PV & Battery | 3-81-950 | 2019-03-28 | 2019-04-04 | #VALUE! |  | #VALUE! | 2019-04-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2336013 | 2021 | 200.4 | PV | 269-1320H1 | 2019-04-05 | 2019-04-08 | #VALUE! |  | #VALUE! | 2019-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | Plymouth | 2336042 | 2360 | 366 | PV |  | 2019-04-23 | 2019-04-23 | 0 | 0 | 0 | 2019-04-23 | 2019-05-22 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | 2020-09-02 | 2019-11-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2023-03-28 | Online |  | Private
NSTAR | Cambridge | 2336049 | 2142 | 35 | CHP | 875-1N25A | 2019-03-12 | 2019-04-08 | #VALUE! |  | #VALUE! | 2019-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2336071 | 2056 | 4990 | PV & Battery | 146-H9 | 2019-04-05 | 2019-04-08 | #VALUE! |  | #VALUE! | 2019-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 2336099 | 2719 | 5000 | PV |  | 2019-04-23 | 2019-04-25 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-25 |  | #VALUE! | 256 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-04-18 | Private
NSTAR | West Wareham | 2336183 | 2576 | 57.6 | PV | 3-86-86 | 2019-04-10 | 2019-04-10 | 0 |  | 0 | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-16 | Online
NSTAR | Rochester | 2336283 | 2770 | 17.52 | PV | 3-85-85 | 2019-04-09 | 2019-04-11 | #VALUE! |  | #VALUE! | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-11 | Online
NSTAR | Falmouth | 2336292 | 2556 | 26 | PV | 4-98B-448 | 2019-04-04 | 2019-04-11 | #VALUE! |  | #VALUE! | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Natick | 2336317 | 1760 | 366.6 | PV | 433-H5 | 2019-04-04 | 2019-04-12 | #VALUE! |  | #VALUE! | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2336372 | 2451 | 166.6 | PV | 450-H7 | 2019-04-04 | 2019-04-12 | #VALUE! |  | #VALUE! | 2019-04-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2336465 | 1741 | 496 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | #VALUE! |  | #VALUE! | 2019-04-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2337102 | 1741 | 484 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | #VALUE! |  | #VALUE! | 2019-04-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-26 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Freetown | 2337126 | 2702 | 4890 | PV & Battery | 2-605-605 | 2019-04-12 | 2019-04-15 | #VALUE! |  | #VALUE! | 2019-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2337174 | 2717 | 4890 | PV & Battery | 2-605-605 | 2019-04-16 | 2019-04-17 | #VALUE! |  | #VALUE! | 2019-05-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2337311 | 2360 | 195 | PV | 3-89-89 | 2019-03-26 | 2019-04-01 | #VALUE! |  | #VALUE! | 2019-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 2337320 | 2135 | 250 | PV | 467-H12 | 2019-03-29 | 2019-04-03 | #VALUE! |  | #VALUE! | 2019-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2337333 | 2021 | 133.6 | PV | 269-1320H1 | 2019-02-11 | 2019-04-08 | #VALUE! |  | #VALUE! | 2019-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | Hatchville | 2337408 | 2536 | 28.5 | PV | 4-98A-98A | 2019-02-26 | 2019-04-12 | #VALUE! |  | #VALUE! | 2019-05-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2337464 | 1730 | 35 | CHP | 322-05 | 2019-04-01 | 2019-04-22 | #VALUE! |  | #VALUE! | 2019-05-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Brighton | 2337496 | 2135 | 86.6 | PV | 329-H2 | 2019-04-18 | 2019-04-22 | #VALUE! |  | #VALUE! | 2019-05-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Somerville | 2338222 | 2145 | 99.9 | PV | 250-H4XY | 2019-04-18 | 2019-04-22 | #VALUE! |  | #VALUE! | 2019-05-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Ashland | 2338277 | 1721 | 19 | PV | 519-175H1 | 2019-04-17 | 2019-04-18 | #VALUE! |  | #VALUE! | 2019-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Carver | 2338333 | 2330 | - |  | TBD | 2019-05-06 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-12 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2338339 | 2330 | 9500 | PV & Battery | 3-81-950 | 2019-04-08 | 2019-04-30 | #VALUE! |  | #VALUE! | 2019-05-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2338418 | 2738 | 99.9 | PV | 3-304-304 | 2019-04-18 | 2019-04-18 | 0 |  | 0 | 2019-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | East Boston | 2338574 | 2128 | 43.2 | PV | 488-H5 | 2019-04-22 | 2019-04-23 | #VALUE! |  | #VALUE! | 2019-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | East Boston | 2338586 | 2128 | 28.8 | PV | 592-72XY | 2019-04-22 | 2019-04-23 | #VALUE! |  | #VALUE! | 2019-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1900-01-03 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Waltham | 2338649 | 2453 | 99.9 | PV | 33-H3 | 2019-04-17 | 2019-04-23 | #VALUE! |  | #VALUE! | 2019-05-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Framingham | 2338764 | 1702 | 15.2 | PV | 455-H5 | 2019-01-04 | 2019-04-19 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Plymouth | 2338789 | 2360 | 756 | PV | 3-89-89 | 2019-04-09 | 2019-04-25 | #VALUE! |  | #VALUE! | 2019-05-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Assonett | 2339086 | 2702 | 4498 | PV |  | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 |  | #VALUE! | 409 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2019-12-18 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-05-14 | Private
NSTAR | New Bedford | 2339142 | 2746 | 355 | PV |  | 2019-05-10 | 2019-05-17 | #VALUE! | 0 | #VALUE! | 2019-05-27 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 |  | 2020-03-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
NSTAR | New Bedford | 2339509 | 2744 | 113 | PV |  | 2019-05-13 | 2019-05-17 | #VALUE! | 0 | #VALUE! | 2019-05-27 | 2020-06-16 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Sharon | 2339541 | 2067 | 57.6 | PV | 146-H7 | 2019-04-23 | 2019-04-25 | #VALUE! |  | #VALUE! | 2019-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-29 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | New Bedford | 2339571 | 2745 | 129.6 | PV |  | 2019-05-13 | 2019-05-22 | #VALUE! | 0 | #VALUE! | 2019-05-27 | 2020-09-17 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
NSTAR | New Bedford | 2339580 | 2745 | - |  | TBD | 2019-05-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-19 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | New Bedford | 2339584 | 2746 | 369.6 | PV | 2-89-181 | 2019-05-13 | 2019-05-21 | #VALUE! | 0 | #VALUE! | 2019-05-27 | 2019-11-13 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-03-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
NSTAR | Woburn | 2339665 | 1801 | 66.6 | PV | 375-H1 | 2019-04-18 | 2019-04-29 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Hyde Park | 2339703 | 2136 | 40 | PV | 311-13 | 2019-04-19 | 2019-04-29 | #VALUE! |  | #VALUE! | 2019-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Westwood | 2339939 | 2090 | 60 | PV | 20-H3 | 2019-04-18 | 2019-04-29 | #VALUE! |  | #VALUE! | 2019-05-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Newton | 2340114 | 2459 | 57.6 | PV | 1708 | 2019-05-01 | 2019-05-02 | #VALUE! |  | #VALUE! | 2019-05-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | North Dartmouth | 2340119 | 2747 | 999 | PV & Battery | 2-541-541 | 2019-03-21 | 2019-05-07 | #VALUE! |  | #VALUE! | 2019-05-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2340125 | 2745 | 200 | PV | 2-137-139 | 2019-04-18 | 2019-05-08 | #VALUE! |  | #VALUE! | 2019-05-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-19 | Online
NSTAR | Boston | 2340373 | 2118 | 60 | PV | 323-78H1 | 2019-04-19 | 2019-04-30 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Waltham | 2340378 | 2136 | - |  | TBD | 2019-05-17 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-26 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Acusnet | 2340380 | 2743 | 2999 | PV & Battery | 2-241-241 | 2019-04-12 | 2019-04-30 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2340383 | 2453 | 40 | PV | 311-13 | 2019-04-17 | 2019-04-29 | #VALUE! |  | #VALUE! | 2019-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Newton | 2340567 | 2460 | 72 | PV | 282-H8 | 2019-04-26 | 2019-05-01 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Lincoln | 2340569 | 1773 | 38 | PV | 320-H8 | 2019-04-22 | 2019-05-01 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Kingston | 2340663 | 2364 | 1800 | PV | 3-17-17 | 2019-04-25 | 2019-05-02 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-03-30 | Online
NSTAR | Walpole | 2340703 | 2071 | 99.9 | PV | 146-H1 | 2019-05-01 | 2019-05-03 | #VALUE! |  | #VALUE! | 2019-05-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2340718 | 2637 | 250 | PV | 4-92B-583 | 2019-04-25 | 2019-04-30 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Dover | 2340724 | 2030 | 20.2 | PV | 456-H5 | 2019-04-11 | 2019-05-06 | #VALUE! |  | #VALUE! | 2019-05-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Dedham | 2340807 | 2026 | 20 | PV | 148-H3 | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-03-27 | Online
NSTAR | Brewster | 2340839 | 2631 | 20.01 | PV | 4-89B-618 | 2019-04-12 | 2019-05-14 | #VALUE! |  | #VALUE! | 2019-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2340888 | 2138 | 66.6 | PV | 819-1NE4 | 2019-05-21 | 2019-05-22 | #VALUE! | 0 | #VALUE! | 2019-05-23 | 2019-06-18 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 |  | 2019-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-12-16 | Online |  | Private
NSTAR | Woburn | 2340946 | 1801 | 480 | PV | TBD | 2019-05-08 | 2019-05-14 | #VALUE! |  | #VALUE! | 2019-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-18 | Online
NSTAR | Cambridge | 2341088 | 2138 | 20.4 | PV | 831-1336XY | 2019-04-17 | 2019-05-15 | #VALUE! |  | #VALUE! | 2019-05-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Woburn | 2341172 | 1801 | 166.5 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | #VALUE! |  | #VALUE! | 2019-05-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-08 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2341237 | 1801 | 249.8 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | #VALUE! |  | #VALUE! | 2019-05-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2341375 | 2748 | 200 | PV | 2-528-528 | 2019-05-09 | 2019-05-16 | #VALUE! |  | #VALUE! | 2019-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2341496 | 2747 | 1000 | PV & Battery | 2-528-528 | 2019-02-25 | 2019-05-16 | #VALUE! |  | #VALUE! | 2019-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sagamore Beach | 2341513 | 2562 | 20 | PV | 3-89-925 | 2019-05-16 | 2019-05-17 | #VALUE! |  | #VALUE! | 2019-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | East Freetown | 2341535 | 2717 | 25 | PV | 2-102-102 | 2019-05-16 | 2019-05-17 | #VALUE! |  | #VALUE! | 2019-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-01 | [7 empty] | 0 |  | 0 |  |  | 2020-10-22 | Online
NSTAR | Sharon | 2341555 | 2067 | 20.35 | PV | 470-H12 | 2019-04-22 | 2019-05-17 | #VALUE! |  | #VALUE! | 2019-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Norfolk | 2341849 | 2056 | 1000 | PV | 146-H9 | 2019-05-16 | 2019-05-20 | #VALUE! |  | #VALUE! | 2019-05-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2341861 | 2360 | 114 | PV | 3-89-89 | 2019-05-20 | 2019-05-21 | #VALUE! |  | #VALUE! | 2019-05-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2341981 | 2050 | 31.5 | PV & Battery | 3-25-42J2 | 2019-04-18 | 2019-05-21 | #VALUE! |  | #VALUE! | 2019-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2342846 | 2743 | 2640 | PV & Battery | 2-241-241 | 2019-04-10 | 2019-05-31 | #VALUE! |  | #VALUE! | 2019-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2342972 | 1741 | 18.7 | PV | 512-1399h1 | 2019-05-16 | 2019-05-24 | #VALUE! |  | #VALUE! | 2019-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-12 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Dartmouth | 2342977 | 2747 | - | PV | TBD | 2019-06-03 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Needham | 2342982 | 2494 | 43.2 | PV | 148-H1 | 2019-05-16 | 2019-05-22 | #VALUE! |  | #VALUE! | 2019-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Plymouth | 2343065 | 2360 | 250 | PV & Battery | 3-71-937 | 2019-05-21 | 2019-05-24 | #VALUE! |  | #VALUE! | 2019-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2343104 | 1748 | 8485 | PV & Battery | 533-H7 | 2019-05-16 | 2019-05-24 | #VALUE! |  | #VALUE! | 2019-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343408 | 2536 | 36 | PV | 4-98A-98A | 2019-05-29 | 2019-05-29 | 0 |  | 0 | 2019-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-03-05 | Online
NSTAR | Wareham | 2343539 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-21 | 2019-05-29 | #VALUE! |  | #VALUE! | 2019-06-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2343563 | 2747 | 6000 | PV | 2-528-528 | 2019-05-06 | 2019-05-29 | #VALUE! |  | #VALUE! | 2019-06-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2343564 | 1801 | 50 | PV | 211-H2 | 2019-05-14 | 2019-05-22 | #VALUE! |  | #VALUE! | 2019-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-16 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21
NSTAR | Cambridge | 2343568 | 2140 | 32.4 | PV | 824-26 | 2019-05-13 | 2019-05-22 | #VALUE! |  | #VALUE! | 2019-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2343632 | 1801 | 66.6 | PV | 211-H6 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-01-20 | Online
NSTAR | Cambridge | 2343786 | 2138 | 924 | PV | 831-1336XY | 2019-05-21 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343832 | 2536 | 72 | PV | 4-98B-449 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online
NSTAR | West Yarmouth | 2343868 | 2673 | 174 | PV & Battery | 4-92A-536 | 2019-05-21 | 2019-05-28 | #VALUE! |  | #VALUE! | 2019-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-26 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Wareham | 2344136 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-24 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2344165 | 2460 | 216 | PV | 282-H8 | 2019-05-20 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344421 | 2468 | 86 | PV | 292-H12 | 2019-04-25 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344584 | 2460 | 109 | PV | TBD | 2019-05-08 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344713 | 2460 | 133 | PV | TBD | 2019-05-08 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 | 2019-05-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344729 | 2460 | 60 | PV | TBD | 2019-05-08 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344792 | 2459 | 136 | PV | 292-H8 | 2019-04-25 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344807 | 2460 | 109 | PV | 467-H14 | 2019-05-20 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344839 | 2459 | 146 | PV | TBD | 2019-05-20 | 2019-05-30 | #VALUE! |  | #VALUE! | 2019-06-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2344916 | 2119 | 52.2 | PV | TBD | 2019-05-16 | 2019-05-31 | #VALUE! |  | #VALUE! | 2019-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | New Bedford | 2345033 | 2746 | 496 | PV | 2-83-403 | 2017-02-01 | 2017-02-17 | #VALUE! |  | #VALUE! | 2017-02-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31
NSTAR | Cambridge | 2345372 | 2138 | 330 | PV | TBD | 2019-05-21 | 2019-06-03 | #VALUE! |  | #VALUE! | 2019-06-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2345373 | 2421 | 22.95 | PV & Battery | 320-H2 | 2019-05-28 | 2019-06-04 | #VALUE! |  | #VALUE! | 2019-06-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2345601 | 2459 | 100 | PV | TBD | 2019-04-25 | 2020-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2345649 | 2664 | 249.9 | PV | TBD | 2019-05-29 | 2019-06-05 | #VALUE! |  | #VALUE! | 2019-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-19 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Canton | 2345712 | 2021 | 688 | PV & Battery | 269-1320H1 | 2019-04-26 | 2019-06-06 | #VALUE! |  | #VALUE! | 2019-06-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2345953 | 2021 | 250 | PV | TBD | 2019-05-30 | 2019-06-07 | #VALUE! |  | #VALUE! | 2019-06-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-02 | Online
NSTAR | Newton | 2346031 | 2461 | 145.1 | PV | 292-H1 | 2019-05-29 | 2019-06-07 | #VALUE! |  | #VALUE! | 2019-06-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Chelsea | 2346218 | 2150 | 1736 | CHP | TBD | 2019-03-20 | 2019-06-03 | #VALUE! |  | #VALUE! | 2019-06-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Canton | 2346246 | 2021 | 100 | PV | TBD | 2019-06-06 | 2019-06-10 | #VALUE! |  | #VALUE! | 2019-06-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2346323 | 2119 | 37.8 | PV | TBD | 2019-06-06 | 2019-06-10 | #VALUE! |  | #VALUE! | 2019-06-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Watertown | 2346407 | 2472 | 133.2 | PV | TBD | 2019-06-06 | 2019-06-10 | #VALUE! |  | #VALUE! | 2019-06-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Westport | 2346438 | 2790 | 20 | PV | TBD | 2019-05-29 | 2019-06-10 | #VALUE! |  | #VALUE! | 2019-06-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Boston | 2346459 | 2125 | 133.2 | PV | 321-02 | 2019-06-07 | 2019-06-11 | #VALUE! |  | #VALUE! | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Wareham | 2346531 | 2576 | 4980 | PV | TBD | 2019-06-24 | 2019-06-26 | #VALUE! | 0 | #VALUE! | 2019-06-27 |  | #VALUE! | 371 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-02-03 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-07-09 | Private
NSTAR | Boston | 2346677 | 2163 | 43.2 | PV | TBD | 2019-05-31 | 2019-06-12 | #VALUE! |  | #VALUE! | 2019-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Hopkinton | 2346774 | 1748 | 480 | PV | TBD | 2019-05-23 | 2019-06-13 | #VALUE! |  | #VALUE! | 2019-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2346835 | 2120 | 57.6 | PV | TBD | 2019-06-10 | 2019-06-13 | #VALUE! |  | #VALUE! | 2019-06-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Sharon | 2346951 | 2067 | 50 | PV | 470-H3 | 2019-05-07 | 2019-06-14 | #VALUE! |  | #VALUE! | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online
NSTAR | Duxbury | 2346979 | 2332 | 200 | PV | 3-27-970 | 2019-06-19 | 2019-06-19 | 0 |  | 0 | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-23 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Needham | 2347063 | 2492 | 57.6 | PV | 148-H4 | 2019-06-13 | 2019-06-17 | #VALUE! |  | #VALUE! | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Boston | 2347214 | 2115 | 57.6 | PV | TBD | 2019-06-12 | 2019-06-14 | #VALUE! |  | #VALUE! | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2347229 | 1773 | 17.4 | PV | 320-H6 | 2019-05-31 | 2019-06-14 | #VALUE! |  | #VALUE! | 2019-06-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Acton | 2347245 | 1720 | 60 | PV | 416-H8 | 2019-06-06 | 2019-06-17 | #VALUE! |  | #VALUE! | 2019-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Assonett | 2347725 | 2702 | 3000 | PV & Battery | TBD | 2019-06-17 | 2019-06-20 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2347755 | 2631 | 1490 | PV & Battery | TBD | 2019-05-31 | 2019-06-21 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22
NSTAR | Walpole | 2348516 | 2081 | 17.5 | PV | TBD | 2019-06-17 | 2019-06-21 | #VALUE! |  | #VALUE! | 2019-07-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Brewster | 2348521 | 2631 | 480 | PV | TBD | 2019-05-30 | 2019-06-21 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-08-12 | Online
NSTAR | South Yarmouth | 2348526 | 2664 | 1560 | PV & Battery | 4-92A-563 | 2019-05-30 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2348529 | 2645 | 166.5 | PV | 4-95A-95A | 2019-05-31 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Newton | 2348530 | 2465 | 20 | PV & Battery | 282-H9 | 2019-05-31 | 2019-06-20 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-01-22 | Online
NSTAR | Ashland | 2348725 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | #VALUE! |  | #VALUE! | 2019-07-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-12 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Ashland | 2348729 | 1721 | 144 | PV | TBD | 2019-06-17 | 2019-06-24 | #VALUE! |  | #VALUE! | 2019-07-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-05-04 | Online
NSTAR | Woburn | 2349171 | 1801 | 333 | PV | TBD | 2019-06-21 | 2019-06-24 | #VALUE! |  | #VALUE! | 2019-07-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2349180 | 2461 | 133.2 | PV | TBD | 2019-06-17 | 2019-06-25 | #VALUE! |  | #VALUE! | 2019-07-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Ashland | 2349389 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | #VALUE! |  | #VALUE! | 2019-07-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | East Freetown | 2349398 | 2717 | 1750 | PV | TBD | 2019-05-09 | 2019-06-24 | #VALUE! |  | #VALUE! | 2019-07-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2349404 | 1890 | 108 | PV | 211-H4 | 2019-06-21 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Fairhaven | 2349408 | 2719 | 2000 | PV & Battery | TBD | 2019-05-28 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2349571 | 2717 | 1000 | PV | TBD | 2019-06-21 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Sandwich | 2349576 | 2537 | 849.5 | PV & Battery | 4-87A-471 | 2019-05-31 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2349579 | 2537 | 3510 | PV & Battery | 4-87A-471 | 2019-05-30 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2349583 | 2644 | 849.5 | PV & Battery | 4-81B-443 | 2019-05-30 | 2019-06-26 | #VALUE! |  | #VALUE! | 2019-07-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2349777 | 1701 | 57.6 | PV | TBD | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Roxbury | 2349780 | 2119 | 37.8 | PV | tbd | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Wareham | 2349786 | 2571 | 5500 | PV & Battery | TBD | 2019-06-21 | 2019-06-28 | #VALUE! |  | #VALUE! | 2019-07-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Tisbury | 2349997 | 2573 | 19.17 | PV | TBD | 2019-06-26 | 2019-06-28 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Framingham | 2350003 | 1701 | 72 | PV | 433-H8 | 2019-06-24 | 2019-07-08 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-13 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350004 | 1773 | 107.84 | PV & Battery | 320-H8 | 2019-02-11 | 2019-07-10 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350022 | 1773 | 17.6 | PV | 320-H6 | 2019-05-31 | 2019-07-03 | #VALUE! |  | #VALUE! | 2019-07-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2350124 | 1720 | 999 | PV | TBD | 2019-07-02 | 2019-07-09 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2350166 | 2770 | 1000 | PV & Battery | 3-702-702 | 2019-07-03 | 2019-07-10 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2350185 | 2119 | 25 | PV | 106-1N31H4 | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Natick | 2350187 | 1760 | 466.6 | PV | TBD | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | West Tisbury | 2350188 | 2568 | 20 | PV | TBD | 2019-05-23 | 2019-07-02 | #VALUE! |  | #VALUE! | 2019-07-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0 |  |  | 2020-03-11 | Online
NSTAR | Hyannis | 2350400 | 2601 | 112.5 | PV | TBD | 2019-06-25 | 2019-07-11 | #VALUE! |  | #VALUE! | 2019-07-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Plymouth | 2350447 | 2360 | 250 | CHP | 3-73-927 | 2019-06-27 | 2019-07-02 | #VALUE! |  | #VALUE! | 2019-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2350448 | 2452 | 133.2 | PV | TBD | 2019-07-09 | 2019-07-12 | #VALUE! |  | #VALUE! | 2019-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2020-08-24 | Online
NSTAR | Bass River | 2350641 | 2664 | 180 | PV | TBD | 2019-07-18 |  | #VALUE! | 0 | #VALUE! | 2019-07-23 | 2019-08-17 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-09-05 |  | 2020-02-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Yarmouth | 2350705 | 2664 | 187.5 | PV |  | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 2019-07-23 | 2019-09-06 | #VALUE! | 22 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | 2019-10-10 | 2020-02-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Provincetown | 2350711 | 2657 | 53.76 | PV | TBD | 2019-06-26 | 2019-07-12 | #VALUE! |  | #VALUE! | 2019-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2350752 | 2368 | 333 | PV | TBD | 2019-06-24 | 2019-07-01 | #VALUE! |  | #VALUE! | 2019-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | West Newton | 2350781 | 2465 | 100 | PV | 467-H5 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23
NSTAR | Plymouth | 2350809 | 2360 | 49.59 | PV | 3-10-10 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2351221 | 1803 | 999 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | New Bedford | 2351223 | 2745 | 499.5 | PV | TBD | 2019-07-01 | 2019-07-08 | #VALUE! |  | #VALUE! | 2019-07-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Lexington | 2351263 | 2421 | 110 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2351363 | 2420 | 491 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2351364 | 1746 | 4999 | PV & Battery | TBD | 2019-07-05 | 2019-07-10 | #VALUE! |  | #VALUE! | 2019-07-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2351423 | 2026 | 22.8 | PV | 20-H7 | 2019-07-08 | 2019-07-10 | #VALUE! |  | #VALUE! | 2019-07-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | New Bedford | 2351619 | 2740 | 236 | PV | TBD | 2019-07-10 | 2019-07-11 | #VALUE! |  | #VALUE! | 2019-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Boston | 2351637 | 2115 | 43.2 | PV | TBD | 2019-06-27 | 2019-07-11 | #VALUE! |  | #VALUE! | 2019-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2351638 | 2745 | 466.6 | PV | TBD | 2019-07-08 | 2019-07-11 | #VALUE! |  | #VALUE! | 2019-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2351639 | 2747 | 150 | PV | TBD | 2019-07-12 | 2019-07-12 | 0 |  | 0 | 2019-07-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Medfield | 2351919 | 2052 | 1280 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | #VALUE! |  | #VALUE! | 2019-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2351939 | 2664 | 92.16 | PV | TBD | 2019-07-12 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Sandwich | 2351960 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2351984 | 2330 | 4999 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352055 | 2420 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Lexington | 2352056 | 2421 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Provincetown | 2352065 | 2657 | 325 | PV | TBD | 2019-07-12 |  | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Lexington | 2352139 | 2421 | 180 | PV | TBD | 2019-07-10 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2352175 | 2743 | 84 | PV | TBD | 2019-07-18 | 2019-07-18 | 0 |  | 0 | 2019-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2352275 | 2139 | 694 | PV & Battery | 831-1118 | 2019-06-19 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352285 | 2421 | 905 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Medfield | 2352302 | 2052 | 766.6 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2352308 | 2053 | 250 | PV | TBD | 2019-06-26 | 2019-07-16 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Cambridge | 2352522 | 2139 | 460 | PV & Battery | 831-1304 | 2019-06-19 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2352540 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352572 | 2421 | 247 | PV & Battery | TBD | 2019-07-11 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Dorchester | 2352639 | 2124 | 199.8 | PV | TBD | 2019-07-01 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2352680 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2352731 | 2747 | 516 | PV | TBD | 2019-06-24 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2352774 | 1801 | 100 | PV | 211-H6 | 2019-07-18 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Stoneham | 2352776 | 2180 | 166.6 | PV | TBD | 2019-06-21 | 2019-07-17 | #VALUE! |  | #VALUE! | 2019-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-08 | Online
NSTAR | Lexington | 2352782 | 2421 | 330 | PV | TBD | 2019-08-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-12 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Lexington | 2352860 | 2421 | 297 | PV | TBD | 2019-07-10 | 2019-07-15 | #VALUE! |  | #VALUE! | 2019-08-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Medfield | 2352954 | 2052 | 150 | PV | TBD | 2019-07-18 | 2019-07-22 | #VALUE! |  | #VALUE! | 2019-08-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-09-13 | Online
NSTAR | Carver | 2352975 | 2330 | 1250 | PV & Battery | TBD | 2019-07-12 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2353430 | 2571 | 5000 | PV & Battery | tbd | 2019-06-04 | 2019-07-23 | #VALUE! |  | #VALUE! | 2019-08-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2353437 | 1760 | 496 | PV | 240-H1 | 2017-06-28 | 2017-06-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Roxbury | 2353454 | 2120 | 66.6 | PV | TBD | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Milton | 2353541 | 2186 | 25.2 | PV | 496-H7 | 2019-06-05 | 2019-07-26 | #VALUE! |  | #VALUE! | 2019-08-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online
NSTAR | Mattapoisett | 2353656 | 2739 | 4999 | PV & Battery | TBD | 2019-07-16 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2353669 | 2139 | 133.2 | PV | TBD | 2019-06-19 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2353792 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2353830 | 1803 | 43.2 | PV | TBD | 2019-07-16 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | South Yarmouth | 2353833 | 2664 | 756 | PV | TBD | 2019-06-24 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2353838 | 2717 | 500 | PV & Battery | TBD | 2019-05-29 | 2019-07-22 | #VALUE! |  | #VALUE! | 2019-08-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2354057 | 2120 | 43.2 | PV | TBD | 2019-07-09 | 2019-07-24 | #VALUE! |  | #VALUE! | 2019-08-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-03-30
NSTAR | Sandwich | 2354118 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354162 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354172 | 2563 | 3250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Roxbury | 2354364 | 2120 | 22.8 | PV | 52-1499H2 | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | East Wareham | 2354403 | 2538 | 15.2 | PV | 3-84-960 | 2019-04-19 | 2019-07-25 | #VALUE! |  | #VALUE! | 2019-08-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Freetown | 2354457 | 2717 | 5000 | PV & Battery | TBD | 2019-06-03 | 2019-07-30 | #VALUE! |  | #VALUE! | 2019-08-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2354467 | 2645 | 3750 | PV | TBD | 2019-07-24 | 2019-08-01 | #VALUE! |  | #VALUE! | 2019-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2354511 | 2537 | 900 | PV | TBD | 2019-06-24 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2354558 | 2659 | 1560 | PV | TBD | 2019-06-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2354628 | 2139 | 594.6 | PV & Battery | 831-1301 | 2019-06-18 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2354633 | 1801 | 100 | PV | 375-H14 | 2019-07-18 | 2019-07-19 | #VALUE! |  | #VALUE! | 2019-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Chatham | 2354636 | 2650 | 24.64 | PV | TBD | 2019-07-16 | 2019-07-22 | #VALUE! |  | #VALUE! | 2019-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Boston | 2354844 | 2120 | 43.2 | PV | TBD | 2019-07-10 | 2019-07-24 | #VALUE! |  | #VALUE! | 2019-08-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2354849 | 2747 | 5000 | PV & Battery | TBD | 2019-05-09 | 2019-07-26 | #VALUE! |  | #VALUE! | 2019-08-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2355009 | 2571 | 500 | PV & Battery | 3-84-968 | 2019-07-18 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 2355012 | 2659 | 2500 | PV & Battery | TBD | 2019-07-25 | 2019-07-25 | 0 |  | 0 | 2019-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2355014 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355015 | 2563 | 250 | PV & Battery | TBD | 2019-07-29 | 2019-07-29 | 0 |  | 0 | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355016 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355017 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2355098 | 2163 | 166.6 | PV | TBD | 2019-07-19 | 2019-08-05 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-24 | Online
NSTAR | Sandwich | 2355143 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2355146 | 2743 | 4995 | PV & Battery | TBD | 2019-07-24 | 2019-08-01 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2355147 | 2664 | 264 | PV | TBD | 2019-07-22 | 2019-08-02 | #VALUE! |  | #VALUE! | 2019-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Boston | 2355397 | 2127 | 275 | PV & Battery | 293-09 | 2019-07-12 | 2019-08-05 | #VALUE! |  | #VALUE! | 2019-08-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-14 | Online
NSTAR | Dorchester | 2355449 | 2125 | 366.3 | PV | TBD | 2019-08-19 |  | #VALUE! | 0 | #VALUE! | 2019-08-22 | 2019-11-01 | #VALUE! | 40 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Boston | 2355531 | 2163 | 66.6 | PV | TBD | 2019-07-29 | 2019-08-05 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-03-23 | Online
NSTAR | Bourne | 2355532 | 2532 | 499 | PV | TBD | 2019-07-29 | 2019-08-06 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2355569 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Falmouth | 2355581 | 2540 | 46.08 | PV | TBD | 2019-08-01 | 2019-08-07 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-24 | Online
NSTAR | Boston | 2355610 | 2115 | 100 | PV | 493-1411H | 2019-08-07 | 2019-08-08 | #VALUE! |  | #VALUE! | 2019-08-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | Bellingham | 2355844 | 2019 | 250 | PV | TBD | 2019-07-15 | 2019-08-06 | #VALUE! |  | #VALUE! | 2019-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-19 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2355854 | 1720 | 750 | PV | tbd | 2019-07-30 | 2019-08-05 | #VALUE! |  | #VALUE! | 2019-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-12 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Fairhaven | 2355860 | 2719 | 100 | PV | TBD | 2019-08-05 | 2019-08-05 | 0 |  | 0 | 2019-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Burlington | 2355861 | 1821 | 1000 | PV & Battery | TBD | 2019-07-30 | 2019-08-01 | #VALUE! |  | #VALUE! | 2019-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2355862 | 2420 | 22.8 | PV | TBD | 2019-07-25 | 2019-08-06 | #VALUE! |  | #VALUE! | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Sudbury | 2355864 | 1776 | 15.2 | PV | TBD | 2019-07-31 | 2019-08-06 | #VALUE! |  | #VALUE! | 2019-08-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-13 | Online
NSTAR | Boston | 2355992 | 2119 | 43.2 | PV | TBD | 2019-07-10 | 2019-08-09 | #VALUE! |  | #VALUE! | 2019-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-05-13 | Online
NSTAR | South Yarmouth | 2356024 | 2664 | 100 | PV | TBD | 2019-08-07 | 2019-08-07 | 0 |  | 0 | 2019-08-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Buzzards Bay | 2356276 | 2532 | 4975 | PV & Battery | TBD | 2019-08-05 | 2019-08-09 | #VALUE! |  | #VALUE! | 2019-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2356386 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | #VALUE! |  | #VALUE! | 2019-08-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Medway | 2356387 | 2053 | 500 | PV | TBD | 2019-08-08 | 2019-08-15 | #VALUE! |  | #VALUE! | 2019-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Burlington | 2356435 | 1803 | 130 | PV | 391-H2 | 2019-08-01 | 2019-08-07 | #VALUE! |  | #VALUE! | 2019-08-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Stoneham | 2356835 | 1757 | 86.4 | PV | TBD | 2019-08-14 | 2019-08-19 | #VALUE! |  | #VALUE! | 2019-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Stoneham | 2357040 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-16 | #VALUE! |  | #VALUE! | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Hopkinton | 2357587 | 1748 | 2770 | PV & Battery | 126-H2 | 2019-08-15 | 2020-08-16 | #VALUE! |  | #VALUE! | 2020-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2357591 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-19 | #VALUE! |  | #VALUE! | 2019-09-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-16 | Online
NSTAR | Norfolk | 2357740 | 2056 | 100.8 | PV | TBD | 2019-08-20 | 2019-08-20 | 0 |  | 0 | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2357988 | 2360 | 150 | PV | 3-12-12 | 2019-08-13 | 2019-08-13 | 0 |  | 0 | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Provincetown | 2357992 | 2657 | 30.39 | PV | 4-96-974 | 2019-08-06 | 2019-08-08 | #VALUE! |  | #VALUE! | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 2357995 | 2638 | 100 | PV | TBD | 2019-08-01 | 2019-08-09 | #VALUE! |  | #VALUE! | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | Wareham | 2358028 | 2571 | 300 | PV | 3-86-966 | 2019-08-20 | 2019-08-22 | #VALUE! |  | #VALUE! | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0 |  |  | 2020-11-18 | Online
NSTAR | Sherborn | 2358191 | 1770 | 17.6 | PV & Battery | TBD | 2019-08-07 | 2019-08-13 | #VALUE! |  | #VALUE! | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-02-25 | Online
NSTAR | Boston | 2358194 | 2121 | 20 | PV | TBD | 2019-07-10 | 2019-08-09 | #VALUE! |  | #VALUE! | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Acusnet | 2358231 | 2743 | 22 | PV | 2-231-231 | 2019-08-22 | 2019-08-26 | #VALUE! |  | #VALUE! | 2019-09-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Hopkinton | 2358327 | 1748 | 2770 | PV | TBD | 2019-09-06 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Framingham | 2358332 | 1749 | 216 | PV | TBD | 2019-08-19 | 2019-08-21 | #VALUE! |  | #VALUE! | 2019-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Dorchester | 2358592 | 2124 | 45.4 | PV | 511-1498H1 | 2019-08-26 | 2019-08-26 | 0 |  | 0 | 2019-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Osterville | 2358595 | 2655 | 240 | PV | 4-88-491 | 2019-08-14 | 2019-08-27 | #VALUE! |  | #VALUE! | 2019-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Provincetown | 2358697 | 2657 | - |  | TBD | 2019-09-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-20 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wareham | 2358992 | 2571 | 16.59 | PV | 3-83-83 | 2018-04-25 | 2018-06-13 | #VALUE! |  | #VALUE! | 2018-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-24 | 2018-08-14 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Orleans | 2358998 | 2653 | 86 | PV | 4-83-951 | 2019-08-20 | 2019-08-27 | #VALUE! |  | #VALUE! | 2019-09-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2359000 | 2143 | 2400 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2020-09-30 | Online
NSTAR | Somerville | 2359001 | 2143 | 600 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2359588 | 2571 | 5000 | PV |  | 2019-09-16 | 2019-09-18 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-04-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Harwich | 2359695 | 2645 | 5000 | PV & Battery | TBD | 2019-08-26 | 2019-08-29 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2359696 | 2364 | 250 | PV | TBD | 2019-08-23 | 2019-09-03 | #VALUE! |  | #VALUE! | 2019-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Framingham | 2359697 | 1701 | 43.2 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2359768 | 2601 | 17.6 | PV | 4-80B-514 | 2019-05-06 | 2019-09-03 | #VALUE! |  | #VALUE! | 2019-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2359934 | 1720 | 100 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2359951 | 2702 | 250 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0
NSTAR | East Sandwich | 2360131 | 2537 | 4600 | PV | TBD | 2019-08-28 | 2019-09-04 | #VALUE! |  | #VALUE! | 2019-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2360135 | 2143 | 1200 | CHP | TBD | 2019-08-06 | 2019-08-29 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | North Dartmouth | 2360141 | 2747 | 200 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Woburn | 2360146 | 1801 | 240 | PV | TBD | 2019-08-29 | 2019-09-04 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-10-29 | Online
NSTAR | Cambridge | 2360150 | 2141 | 125 | CHP | TBD | 2019-08-05 | 2019-09-05 | #VALUE! |  | #VALUE! | 2019-09-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2360179 | 2381 | 19 | PV | TBD | 2019-07-25 | 2019-09-05 | #VALUE! |  | #VALUE! | 2019-09-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2360354 | 2539 | 286 | PV & Battery | TBD | 2019-08-16 | 2019-09-05 | #VALUE! |  | #VALUE! | 2019-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Falmouth | 2360385 | 2536 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Marston Mills | 2360391 | 2635 | 210 | Fuel Cell | 4-88-485 | 2019-09-05 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | East Wareham | 2360402 | 2538 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Hyannis | 2360467 | 2601 | 262.5 | Fuel Cell | 4-84A-520 | 2019-09-04 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Sandwich | 2360491 | 2563 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Mashpee | 2360533 | 2649 | 210 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Harwich | 2360563 | 2645 | 262.5 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Freetown | 2360807 | 2717 | 1125 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 2360809 | 2053 | 500 | PV | 65-H2 | 2019-08-22 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2361120 | 2571 | - |  | TBD | 2019-09-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-05 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2361242 | 2330 | 4999 | PV & Battery | TBD | 2019-09-04 | 2019-09-11 | #VALUE! |  | #VALUE! | 2019-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2361243 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-13 | #VALUE! |  | #VALUE! | 2019-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2361417 | 2601 | 24.78 | PV | 4-63-63 | 2019-09-05 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-18 | [7 empty] | 0 |  | 0 |  |  | 2020-05-19 | Online
NSTAR | Carver | 2361424 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-09-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2361428 | 2330 | 2000 | PV & Battery | TBD | 2019-09-06 | 2019-09-13 | #VALUE! |  | #VALUE! | 2019-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2361432 | 2717 | 4000 | PV |  | 2019-09-26 | 2019-10-02 | #VALUE! | 0 | #VALUE! | 2019-10-07 |  | #VALUE! | 298 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-05-06 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-10-22 | Private
NSTAR | Hopkinton | 2361481 | 1748 | 333.3 | PV | TBD | 2019-09-03 | 2019-09-12 | #VALUE! |  | #VALUE! | 2019-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2361879 | 1890 | 25.2 | PV & Battery | 211-H3 | 2019-09-03 | 2019-09-17 | #VALUE! |  | #VALUE! | 2019-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Carver | 2361931 | 2330 | - |  | TBD | 2019-10-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Carver | 2361932 | 2330 | 2000 | PV & Battery | TBD | 2019-10-01 |  | #VALUE! | 0 | #VALUE! | 2019-10-10 | 2019-10-24 | #VALUE! | 8 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Lexington | 2361940 | 2421 | 250 | PV | TBD | 2019-09-03 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-10-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-18 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Foxboro | 2362818 | 2035 | 3900 | PV | TBD | 2019-09-18 | 2019-09-23 | #VALUE! |  | #VALUE! | 2019-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2363245 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | #VALUE! |  | #VALUE! | 2019-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2363249 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | #VALUE! |  | #VALUE! | 2019-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2363427 | 2770 | 3500 | PV & Battery | TBD | 2019-09-19 | 2019-09-24 | #VALUE! |  | #VALUE! | 2019-10-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2363669 | 2645 | 210 | PV | 4-95A-597 | 2019-09-13 | 2019-09-19 | #VALUE! |  | #VALUE! | 2019-10-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | New Bedford | 2363671 | 2746 | 200 | PV | TBD | 2019-09-23 | 2019-09-25 | #VALUE! |  | #VALUE! | 2019-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2363676 | 2030 | 17.6 | PV & Battery | TBD | 2019-09-20 | 2019-09-26 | #VALUE! |  | #VALUE! | 2019-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2019-01-08 | Online
NSTAR | Brewster | 2363697 | 2631 | 2500 | PV | TBD | 2019-09-06 | 2019-09-25 | #VALUE! |  | #VALUE! | 2019-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2363855 | 2601 | 112.1 | PV | TBD | 2019-09-05 | 2019-09-09 | #VALUE! |  | #VALUE! | 2019-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-19 | Online
NSTAR | Natick | 2363856 | 1760 | 66 | PV & Battery | 433-H9 | 2019-08-22 | 2019-09-30 | #VALUE! |  | #VALUE! | 2019-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Holliston | 2364171 | 1746 | - |  | TBD | 2019-10-15 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-22 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Holliston | 2364172 | 1746 | 240 | PV | TBD | 2019-09-09 | 2019-09-26 | #VALUE! |  | #VALUE! | 2019-10-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Newton | 2364472 | 2459 | 15.2 | PV | TBD | 2019-09-27 | 2019-10-03 | #VALUE! |  | #VALUE! | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Dedham | 2364473 | 2026 | 125 | PV & Battery | 20-H8 | 2019-07-30 | 2019-10-03 | #VALUE! |  | #VALUE! | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Acusnet | 2364982 | 2743 | 500 | PV & Battery |  | 2019-10-21 | 2019-10-22 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 |  | #VALUE! | 86 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2022-02-09 | Online |  | Private
NSTAR | Weston | 2365270 | 2493 | 57.6 | PV | 282-H1 | 2019-10-01 | 2019-10-03 | #VALUE! |  | #VALUE! | 2019-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2019-12-11 | [6 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Framingham | 2365418 | 1701 | 199.8 | PV | TBD | 2019-09-27 | 2019-10-09 | #VALUE! |  | #VALUE! | 2019-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2365634 | 2360 | 17.6 | PV | TBD | 2019-04-18 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Lincoln | 2365635 | 1773 | 1831.4 | PV & Battery | 320-H8 | 2019-09-13 | 2019-10-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0
NSTAR | North Harwich | 2365636 | 2645 | 23.2 | PV | 4-92B-92B | 2019-10-07 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Wareham | 2366043 | 2571 | 499 | Fuel Cell | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2366044 | 1760 | 43.2 | PV | TBD | 2019-10-11 | 2019-10-15 | #VALUE! |  | #VALUE! | 2019-10-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2366164 | 2114 | 66 | PV | TBD | 2019-08-23 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2366298 | 2745 | 200 | PV | 2-79-404 | 2019-09-25 | 2019-10-09 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | East Falmouth | 2366343 | 2536 | 39.83 | PV | TBD | 2019-09-27 | 2019-10-09 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-13
NSTAR | Watertown | 2366357 | 2472 | 480 | PV | TBD | 2019-09-30 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Watertown | 2366405 | 2472 | 99.9 | PV | TBD | 2019-09-30 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 2366415 | 2472 | 353 | PV | TBD | 2019-09-30 | 2019-10-10 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Orleans | 2366434 | 2653 | 20 | PV | 4-89B-89B | 2019-09-20 | 2019-10-09 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0 |  |  | 2020-04-08 | Online
NSTAR | Natick | 2366438 | 1760 | 100 | PV | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2366447 | 2740 | 1400 | Fuel Cell | TBD | 2019-10-11 | 2019-10-15 | #VALUE! |  | #VALUE! | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Falmouth | 2366459 | 2556 | 15.2 | PV | TBD | 2019-08-01 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Marshfield | 2366460 | 2050 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2366461 | 2717 | 2000 | PV | TBD | 2019-08-14 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2366478 | 1760 | 250 | PV | TBD | 2019-10-31 |  | #VALUE! | 0 | #VALUE! | 2019-11-05 | 2020-07-01 | #VALUE! | 13 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Milton | 2366661 | 2186 | 18.2 | PV | TBD | 2019-09-23 | 2019-10-21 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Kingston | 2366662 | 2364 | 15.3 | PV | 3-15-15 | 2019-09-19 | 2019-10-22 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2366684 | 2186 | 15.2 | PV | 311-11 | 2019-08-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Woburn | 2366729 | 1801 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Newton | 2366803 | 2465 | 21.4 | PV | 1713 | 2019-09-25 | 2019-10-22 | #VALUE! |  | #VALUE! | 2019-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Waltham | 2367388 | 2453 | 480 | PV | TBD | 2019-09-25 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2367405 | 1890 | 15.2 | PV | 211-H10 | 2019-08-28 | 2019-10-16 | #VALUE! |  | #VALUE! | 2019-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Boston | 2367475 | 2116 | 1150 | CHP | TBD | 2019-09-25 | 2019-10-18 | #VALUE! |  | #VALUE! | 2019-11-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brighton | 2367836 | 2135 | 456 | PV | TBD | 2019-10-07 | 2019-10-22 | #VALUE! |  | #VALUE! | 2019-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Sherborn | 2367897 | 1770 | 22.8 | PV | 240-H1 | 2019-10-18 | 2019-10-24 | #VALUE! |  | #VALUE! | 2019-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | East Falmouth | 2367955 | 2536 | 134 | PV | TBD | 2019-10-18 | 2019-10-23 | #VALUE! |  | #VALUE! | 2019-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Newton | 2367956 | 2459 | 436 | PV | TBD | 2019-07-16 | 2019-10-25 | #VALUE! |  | #VALUE! | 2019-11-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-26 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2368084 | 1773 | 129.6 | PV | TBD | 2019-10-28 | 2019-10-28 | 0 |  | 0 | 2019-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brewster | 2368090 | 2631 | 199.8 | PV | 4-95A-597 | 2018-09-12 | 2018-09-20 | #VALUE! |  | #VALUE! | 2018-10-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-14 | [7 empty] | 0 |  | 0 |  |  | 2020-11-10 | Online
NSTAR | Lincoln | 2368534 | 1773 | 23.7 | PV | 282-H1 | 2019-08-05 | 2019-10-28 | #VALUE! |  | #VALUE! | 2019-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Hatchville | 2368537 | 2536 | 20 | PV | TBD | 2019-10-18 | 2019-10-28 | #VALUE! |  | #VALUE! | 2019-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2368538 | 2739 | 15.2 | PV | 2-301-301 | 2019-09-10 | 2019-10-28 | #VALUE! |  | #VALUE! | 2019-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368571 | 2067 | 499 | PV & Battery | TBD | 2019-10-24 | 2019-10-29 | #VALUE! |  | #VALUE! | 2019-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368605 | 2067 | 999 | PV | TBD | 2019-09-05 | 2019-10-29 | #VALUE! |  | #VALUE! | 2019-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 2368750 | 1890 | 35.2 | PV | TBD | 2019-10-18 | 2019-10-29 | #VALUE! |  | #VALUE! | 2019-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-02 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Hyannis | 2368753 | 2601 | 200 | PV | TBD | 2019-10-29 | 2019-10-31 | #VALUE! |  | #VALUE! | 2019-11-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Charlestown | 2368889 | 2129 | 250 | PV | TBD | 2019-10-22 | 2019-10-25 | #VALUE! |  | #VALUE! | 2019-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2368913 | 2459 | 220 | PV | TBD | 2019-09-20 | 2019-11-01 | #VALUE! |  | #VALUE! | 2019-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2368944 | 2702 | 15.2 | PV | 2-605-605 | 2019-09-13 | 2019-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Watertown | 2369438 | 2472 | 700 | PV & Battery | TBD | 2019-10-10 | 2019-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2369465 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | #VALUE! |  | #VALUE! | 2019-11-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Yarmouth | 2369488 | 2661 | 17.23 | PV | 4-92A-562 | 2019-10-16 | 2019-11-04 | #VALUE! |  | #VALUE! | 2019-11-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-03 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Rochester | 2369675 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2369838 | 2601 | 975 | PV |  | 2019-11-20 | 2019-11-27 | #VALUE! | 0 | #VALUE! | 2019-11-28 |  | #VALUE! | 264 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-06-29 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2019-12-10 | Private
NSTAR | Dorchester | 2369846 | 2122 | 66.6 | PV | TBD | 2019-11-05 | 2019-11-07 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2369848 | 1770 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Orleans | 2369981 | 2653 | 133.7 | PV | 4-83-952 | 2019-03-04 | 2019-03-12 | #VALUE! |  | #VALUE! | 2019-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-04 | Online
NSTAR | Canton | 2370020 | 2021 | 133.2 | PV | TBD | 2019-11-07 | 2019-11-08 | #VALUE! |  | #VALUE! | 2019-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370022 | 2458 | 200 | PV | TBD | 2019-08-29 | 2020-09-16 | #VALUE! |  | #VALUE! | 2020-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Wayland | 2370024 | 1778 | 80 | PV | TBD | 2019-10-28 | 2019-11-08 | #VALUE! |  | #VALUE! | 2019-11-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | New Bedford | 2370116 | 2745 | 100 | PV | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2019-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2370417 | 1746 | 437.5 | PV | TBD | 2019-11-08 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370419 | 2458 | 100 | PV | TBD | 2019-11-05 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2370420 | 2129 | 100 | PV | TBD | 2019-11-04 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2370421 | 2458 | 62.5 | PV | TBD | 2019-11-04 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chatham | 2370503 | 2633 | 133.3 | PV | TBD | 2019-11-08 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Marshfield | 2370516 | 2050 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2370546 | 2021 | 495.8 | PV | TBD | 2019-11-04 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2370560 | 1746 | 499 | PV | TBD | 2019-11-04 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2370575 | 2081 | 312.5 | PV | TBD | 2019-11-04 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370582 | 2607 | 370 | PV | TBD | 2019-10-07 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2370583 | 1721 | 125 | PV | TBD | 2019-10-31 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2370630 | 2607 | 660 | PV | TBD | 2019-10-07 | 2019-11-12 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370666 | 2607 | 5000 | PV & Battery | TBD | 2019-10-07 | 2019-11-13 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2370690 | 2721 | 3375 | PV | TBD | 2019-10-29 | 2019-11-14 | #VALUE! |  | #VALUE! | 2019-11-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 2370768 | 2474 | 19.86 | PV & Battery | 59-1383H1 | 2019-10-31 | 2019-11-19 | #VALUE! |  | #VALUE! | 2019-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2370777 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2370785 | 2744 | 150 | PV | TBD | 2019-11-07 | 2019-11-19 | #VALUE! |  | #VALUE! | 2019-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2021-05-18 | Online
NSTAR | Plympton | 2370996 | 2367 | 1560 | PV | 3-51-980 | 2019-10-24 | 2019-11-07 | #VALUE! |  | #VALUE! | 2019-12-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2371039 | 2576 | 100 | PV | TBD | 2019-11-08 | 2019-11-15 | #VALUE! |  | #VALUE! | 2019-12-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2371521 | 2601 | 250 | PV | TBD | 2019-09-30 | 2019-10-28 | #VALUE! |  | #VALUE! | 2019-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Canton | 2371598 | 2021 | 325 | Natural Gas | 269-1321H2 | 2019-11-14 | 2019-11-14 | 0 |  | 0 | 2019-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2371602 | 2571 | 166.6 | PV | TBD | 2019-11-08 | 2019-11-15 | #VALUE! |  | #VALUE! | 2019-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2372155 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2372185 | 2642 | 37.7 | PV | TBD | 2019-11-13 | 2019-11-20 | #VALUE! |  | #VALUE! | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Framingham | 2372222 | 1702 | 250 | PV | TBD | 2019-10-11 | 2019-10-15 | #VALUE! |  | #VALUE! | 2019-11-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2372246 | 2421 | 3000 | CHP | 2-1N11 | 2019-11-18 | 2019-11-19 | #VALUE! |  | #VALUE! | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2372255 | 2535 | - |  | TBD | 2019-12-04 |  | #VALUE! | 0 | #VALUE! | 2019-12-19 | 2020-01-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-02-20 | 2020-10-01 | 2020-07-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Dedham | 2372263 | 2026 | 15.2 | PV | TBD | 2019-11-06 | 2019-11-18 | #VALUE! |  | #VALUE! | 2019-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | South Yarmouth | 2372266 | 2664 | 160 | PV & Battery | TBD | 2019-06-14 | 2019-07-02 | #VALUE! |  | #VALUE! | 2019-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2372267 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2373333 | 2451 | 144 | PV | 450-H7 | 2019-11-14 | 2019-11-08 | #VALUE! |  | #VALUE! | 2019-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-27 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 2373342 | 2717 | 17.6 | PV & Battery | 2-102-602 | 2019-11-07 | 2019-11-22 | #VALUE! |  | #VALUE! | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2373431 | 2563 | 112.5 | PV | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Sandwich | 2373432 | 2644 | 2500 | PV & Battery | TBD | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2373744 | 1748 | 15.2 | PV | 126-H1 | 2019-11-18 | 2019-11-21 | #VALUE! |  | #VALUE! | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2373797 | 2362 | 60 | PV | 3-13-13 | 2019-11-11 | 2019-11-25 | #VALUE! |  | #VALUE! | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2373810 | 2653 | 89.39 | PV | TBD | 2019-05-28 | 2019-06-20 | #VALUE! |  | #VALUE! | 2019-07-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Centerville | 2373813 | 2632 | 747 | PV & Battery | tbd | 2019-11-15 | 2019-11-20 | #VALUE! |  | #VALUE! | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2373814 | 2144 | 133.2 | PV | TBD | 2019-11-18 | 2019-11-27 | #VALUE! |  | #VALUE! | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Chelsea | 2373967 | 2150 | 275 | PV & Battery | 488-H2 | 2019-11-08 | 2019-11-26 | #VALUE! |  | #VALUE! | 2019-12-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Sandwich | 2374039 | 2563 | 249 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | #VALUE! |  | #VALUE! | 2019-12-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2374058 | 2067 | 200 | PV | 146-H1 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Waltham | 2374169 | 2451 | 250 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | #VALUE! |  | #VALUE! | 2019-12-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2374177 | 2719 | 200 | PV | 2-220-206 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Medfield | 2374353 | 2052 | 17.6 | PV & Battery | TBD | 2019-11-21 | 2019-12-02 | #VALUE! |  | #VALUE! | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | West Harwich | 2374665 | 2671 | 25.6 | PV & Battery | 4-85-592 | 2019-11-22 | 2019-12-02 | #VALUE! |  | #VALUE! | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2374769 | 2120 | 55.8 | PV | TBD | 2019-12-02 | 2019-12-02 | 0 |  | 0 | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Chatham | 2374770 | 2659 | 25 | PV & Battery | 4-95A-606 | 2019-11-15 | 2019-12-02 | #VALUE! |  | #VALUE! | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-07 | Online
NSTAR | Mattapoisett | 2374771 | 2739 | - | PV & Battery | TBD | 2019-11-27 | 2019-12-03 | #VALUE! |  | #VALUE! | 2019-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2375330 | 2739 | 28.7 | PV & Battery | 2-301-301 | 2019-11-27 | 2019-12-03 | #VALUE! |  | #VALUE! | 2019-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Arlington | 2375571 | 2476 | 275 | PV & Battery | TBD | 2019-11-27 | 2019-12-05 | #VALUE! |  | #VALUE! | 2019-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Lexington | 2375572 | 2420 | 15.2 | PV | TBD | 2019-11-27 | 2019-12-03 | #VALUE! |  | #VALUE! | 2019-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Woburn | 2375623 | 1801 | 150 | PV | TBD | 2019-12-02 | 2019-12-05 | #VALUE! |  | #VALUE! | 2019-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2375708 | 2476 | 15.2 | PV | TBD | 2019-12-03 | 2019-12-10 | #VALUE! |  | #VALUE! | 2019-12-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Plymouth | 2375823 | 2360 | 173.46 | PV | TBD | 2019-12-11 | 2019-12-11 | 0 |  | 0 | 2019-12-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Falmouth | 2376010 | 2540 | 133.2 | PV | TBD | 2019-12-09 | 2019-12-12 | #VALUE! |  | #VALUE! | 2019-12-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Carlisle | 2376068 | 1741 | 17.6 | PV | 512-1399H1 | 2019-10-22 | 2019-12-11 | #VALUE! |  | #VALUE! | 2019-12-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0
NSTAR | Cotuit | 2376383 | 2635 | 200 | PV | TBD | 2019-12-12 | 2019-12-16 | #VALUE! |  | #VALUE! | 2019-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Bedford | 2376385 | 1730 | 25 | PV & Battery | 533-H8 | 2019-12-11 | 2019-12-19 | #VALUE! |  | #VALUE! | 2019-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Burlington | 2377387 | 1803 | 19.57 | PV & Battery | TBD | 2019-11-22 | 2019-11-26 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2377419 | 2136 | - |  | TBD | 2020-01-02 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-06 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Wayland | 2377433 | 1778 | 20 | PV & Battery | 342-H1 | 2019-11-07 | 2019-11-22 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2377476 | 2125 | 72 | PV | TBD | 2019-10-18 | 2019-11-22 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2377493 | 2453 | 80 | PV | TBD | 2019-12-13 | 2019-12-20 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Centerville | 2377494 | 2632 | 15.2 | PV | TBD | 2019-11-25 | 2019-12-20 | #VALUE! |  | #VALUE! | 2020-01-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Harwich | 2378433 | 2645 | 3150 | PV & Battery | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2378459 | 2364 | 320 | PV | 3-17-916 | 2019-11-13 | 2019-11-25 | #VALUE! |  | #VALUE! | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2378471 | 1702 | 15.2 | PV | 274-H1 | 2019-12-02 | 2019-12-12 | #VALUE! |  | #VALUE! | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Medway | 2378489 | 2053 | 230 | PV | TBD | 2019-11-20 | 2019-12-13 | #VALUE! |  | #VALUE! | 2020-01-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | South Dennis | 2378744 | 2660 | 30.72 | PV | TBD | 2019-11-20 | 2019-11-26 | #VALUE! |  | #VALUE! | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2378798 | 2563 | 490 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | #VALUE! |  | #VALUE! | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Roxbury | 2378813 | 2132 | 43.2 | PV | TBD | 2019-12-11 | 2019-12-19 | #VALUE! |  | #VALUE! | 2020-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Carver | 2378857 | 2330 | 2500 | PV & Battery | TBD | 2019-11-19 | 2019-12-23 | #VALUE! |  | #VALUE! | 2020-01-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2378858 | 2532 | 5000 | PV & Battery | TBD | 2019-11-21 | 2019-12-23 | #VALUE! |  | #VALUE! | 2020-01-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2380743 | 2719 | 200 | PV | 2-221-221 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2020-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Waltham | 2380747 | 2451 | 16 | Battery | 450-H3 | 2019-11-27 | 2019-12-02 | #VALUE! |  | #VALUE! | 2020-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2380929 | 2421 | 133.3 | PV | 533-H1 | 2019-12-02 | 2019-12-05 | #VALUE! |  | #VALUE! | 2020-01-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2380935 | 1748 | 250 | PV |  | 2020-01-08 | 2020-01-09 | #VALUE! | 0 | #VALUE! | 2020-01-10 | 2020-05-08 | #VALUE! | 4 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 |  | 2020-08-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Marshfield | 2381120 | 2048 | 4600 | PV & Battery | TBD | 2019-12-18 | 2019-12-26 | #VALUE! |  | #VALUE! | 2020-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2381326 | 2180 | 20 | PV & Battery | 375-H8 | 2019-11-18 | 2019-12-26 | #VALUE! |  | #VALUE! | 2020-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Westport | 2381437 | 2790 | 4000 | PV & Battery | TBD | 2019-11-19 | 2019-12-30 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | 2381519 | 2472 | 100 | PV | 467-H5 | 2019-12-20 | 2019-12-20 | 0 |  | 0 | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Lexington | 2381543 | 2421 | 130 | PV | 533-H1 | 2019-12-10 | 2019-12-13 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2381555 | 2453 | 748 | PV | TBD | 2019-12-09 | 2019-12-12 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2381556 | 2136 | 19 | PV | 60-1409H1 | 2019-10-31 | 2019-12-02 | #VALUE! |  | #VALUE! | 2020-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Walpole | 2381558 | 2032 | 23.8 | PV | TBD | 2019-12-11 | 2019-12-16 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2381571 | 1801 | 3623 | PV | TBD | 2019-12-05 | 2019-12-09 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-24 | [7 empty] | 0 |  | 0
NSTAR | Bourne | 2381610 | 2532 | 5000 | PV & Battery | TBD | 2019-12-13 | 2019-12-23 | #VALUE! |  | #VALUE! | 2020-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2381700 | 2770 | 21.4 | PV | TBD | 2019-11-06 | 2019-12-30 | #VALUE! |  | #VALUE! | 2020-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2381703 | 2360 | 249.9 | PV & Battery | TBD | 2019-12-30 | 2019-12-30 | 0 |  | 0 | 2020-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2381861 | 2648 | 40 | PV | TBD | 2019-12-19 | 2020-01-02 | #VALUE! |  | #VALUE! | 2020-01-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Carver | 2382007 | 2330 | 50 | PV | TBD | 2019-12-26 | 2020-01-06 | #VALUE! |  | #VALUE! | 2020-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Needham | 2382008 | 2494 | 17 | PV & Battery | 148-08 | 2019-12-05 | 2020-01-06 | #VALUE! |  | #VALUE! | 2020-01-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Lexington | 2382228 | 2421 | 22.72 | PV | 320-H2 | 2019-12-20 | 2020-01-02 | #VALUE! |  | #VALUE! | 2020-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Needham | 2382255 | 2494 | 17.25 | PV | 148-H4 | 2019-12-09 | 2020-01-02 | #VALUE! |  | #VALUE! | 2020-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | East Freetown | 2382455 | 2717 | 25 | PV & Battery | TBD | 2020-01-06 | 2020-01-06 | 0 |  | 0 | 2020-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2382474 | 2571 | 66.6 | PV | 3-84-960 | 2019-12-19 | 2020-01-06 | #VALUE! |  | #VALUE! | 2020-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2383462 | 2053 | 15.2 | PV | 130-H2 | 2019-12-18 | 2019-12-20 | #VALUE! |  | #VALUE! | 2020-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 2383471 | 1741 | 17.6 | PV & Battery | 512-1399H1 | 2019-12-13 | 2020-01-13 | #VALUE! |  | #VALUE! | 2020-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hyde Park | 2383520 | 2136 | 333.2 | PV | TBD | 2020-01-02 | 2020-01-13 | #VALUE! |  | #VALUE! | 2020-01-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Dennis | 2383632 | 2670 | 20 | PV & Battery | 4-92B-571 | 2020-01-04 | 2020-01-13 | #VALUE! |  | #VALUE! | 2020-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-05-21
NSTAR | South Dennis | 2383634 | 2660 | 37.6 | PV | TBD | 2020-01-06 | 2020-01-13 | #VALUE! |  | #VALUE! | 2020-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | North Falmouth | 2383638 | 2556 | 15.2 | PV | 4-78-78 | 2020-01-08 | 2020-01-15 | #VALUE! |  | #VALUE! | 2020-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Watertown | 2383645 | 2472 | 52.2 | PV | TBD | 2020-01-06 | 2020-01-07 | #VALUE! |  | #VALUE! | 2020-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Westport | 2383646 | 2790 | 4000 | PV & Battery | TBD | 2019-12-20 | 2020-01-08 | #VALUE! |  | #VALUE! | 2020-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2384268 | 2642 | 10 | PV & Battery | 4-94A-633 | 2019-11-22 | 2020-01-16 | #VALUE! |  | #VALUE! | 2020-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2384357 | 2453 | 40 | PV | TBD | 2019-06-14 | 2020-01-21 | #VALUE! |  | #VALUE! | 2020-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marshfield | 2384377 | 2050 | 16.2 | PV | 3-24A-971 | 2019-09-18 | 2019-12-11 | #VALUE! |  | #VALUE! | 2020-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Brookline | 2384381 | 2446 | 38.5 | PV | TBD | 2020-01-16 | 2020-01-17 | #VALUE! |  | #VALUE! | 2020-02-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2384383 | 2420 | 17 | PV & Battery | 320-H5XY | 2020-01-15 | 2020-01-22 | #VALUE! |  | #VALUE! | 2020-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | New Bedford | 2384474 | 2746 | 133 | PV |  | 2020-02-04 | 2020-02-07 | #VALUE! | 0 | #VALUE! | 2020-02-13 | 2020-02-28 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 |  | 2020-09-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Provincetown | 2384542 | 2657 | 70 | PV | 4-96-675 | 2020-01-15 | 2020-01-22 | #VALUE! |  | #VALUE! | 2020-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hopkinton | 2384545 | 1748 | 111.5 | PV & Battery | 126-H2 | 2019-12-10 | 2020-01-02 | #VALUE! |  | #VALUE! | 2020-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-31
NSTAR | Wareham | 2384553 | 2538 | 4995 | PV & Battery | TBD | 2019-12-30 | 2020-01-06 | #VALUE! |  | #VALUE! | 2020-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2384624 | 1702 | 440 | PV | TBD | 2020-01-21 | 2020-01-23 | #VALUE! |  | #VALUE! | 2020-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-12 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Freetown | 2384761 | 2717 | 2000 | PV & Battery | TBD | 2020-01-07 | 2020-01-08 | #VALUE! |  | #VALUE! | 2020-02-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2384826 | 2451 | 166.6 | PV | TBD | 2019-12-30 | 2020-01-08 | #VALUE! |  | #VALUE! | 2020-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2384945 | 2653 | 60 | PV |  | 2020-02-06 | 2020-02-11 | #VALUE! | 0 | #VALUE! | 2020-02-11 | 2020-02-12 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | 2020-03-02 | 2020-09-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-10-06 | Online |  | Private
NSTAR | South Yarmouth | 2384954 | 2664 | 437.5 | PV | TBD | 2019-12-19 | 2020-01-06 | #VALUE! |  | #VALUE! | 2020-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online
NSTAR | Walpole | 2384980 | 2081 | 30.2 | PV & Battery | 146-H4 | 2020-01-10 | 2020-01-26 | #VALUE! |  | #VALUE! | 2020-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Dorchester | 2384991 | 2122 | 100 | PV & Battery | 6702 | 2020-01-22 | 2020-01-28 | #VALUE! |  | #VALUE! | 2020-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Burlington | 2385267 | 1803 | 19.76 | PV | 346-1395H1 | 2020-01-17 | 2020-01-27 | #VALUE! |  | #VALUE! | 2020-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | West Tisbury | 2385299 | 2575 | 25 | PV | TBD | 2020-01-22 | 2020-01-28 | #VALUE! |  | #VALUE! | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-18 | Online
NSTAR | Watertown | 2385313 | 2472 | 43.2 | PV | 282-H8 | 2020-01-22 | 2020-01-28 | #VALUE! |  | #VALUE! | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Westwood | 2385414 | 2090 | 25 | PV & Battery | 469-H2 | 2020-01-21 | 2020-01-28 | #VALUE! |  | #VALUE! | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Acton | 2385734 | 1720 | 200 | PV | TBD | 2019-12-12 | 2020-01-31 | #VALUE! |  | #VALUE! | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2385800 | 1702 | 187.5 | PV | TBD | 2020-01-30 | 2020-01-30 | 0 |  | 0 | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-12 | Online
NSTAR | Needham | 2385802 | 2494 | 460 | PV | TBD | 2019-12-09 | 2020-01-30 | #VALUE! |  | #VALUE! | 2020-02-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online
NSTAR | Falmouth | 2386189 | 2540 | 34.6 | PV & Battery | 4-78-420 | 2020-01-22 | 2020-02-03 | #VALUE! |  | #VALUE! | 2020-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2386275 | 2657 | 28.8 | PV | TBD | 2020-01-30 | 2020-02-03 | #VALUE! |  | #VALUE! | 2020-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 2386320 | 2332 | 66.6 | PV | TBD | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Barnstable | 2386368 | 2630 | 240 | PV | 4-84B-510 | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2386391 | 2745 | 30 | PV | 2-137-137 | 2019-12-03 | 2020-02-04 | #VALUE! |  | #VALUE! | 2020-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Ashland | 2386559 | 1721 | 10 | PV & Battery | 274-H1 | 2020-01-23 | 2020-02-04 | #VALUE! |  | #VALUE! | 2020-02-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Wareham | 2386584 | 2538 | 30 | PV | 3-84-960 | 2019-12-03 | 2020-02-04 | #VALUE! |  | #VALUE! | 2020-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Dedham | 2386594 | 2026 | 10 | PV & Battery | 20-H7 | 2020-01-29 | 2020-02-04 | #VALUE! |  | #VALUE! | 2020-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2387342 | 1746 | 4999 | PV & Battery | TBD | 2019-12-26 | 2020-02-06 | #VALUE! |  | #VALUE! | 2020-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-12-05 | Online
NSTAR | Marshfield | 2387378 | 2050 | 15.1 | PV | 3-24B-24B | 2019-12-23 | 2020-02-06 | #VALUE! |  | #VALUE! | 2020-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Bourne | 2387476 | 2532 | 43.2 | PV | 4-86-402 | 2020-02-10 | 2020-02-13 | #VALUE! |  | #VALUE! | 2020-02-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Winchester | 2387543 | 1890 | 20 | PV | 211-H10 | 2020-04-14 | 2020-02-21 | #VALUE! |  | #VALUE! | 2020-03-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Needham | 2387570 | 2494 | 7 | PV & Battery | 148-H4 | 2020-01-06 | 2020-01-16 | #VALUE! |  | #VALUE! | 2020-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Boston | 2387593 | 2210 | 233.3 | PV | TBD | 2019-12-19 | 2020-02-14 | #VALUE! |  | #VALUE! | 2020-02-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2387744 | 2601 | 115.05 | PV | TBD | 2020-02-10 | 2020-02-13 | #VALUE! |  | #VALUE! | 2020-03-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | Brookline | 2387929 | 2467 | 20 | PV & Battery | 496-H5 | 2020-01-16 | 2020-02-14 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | East Freetown | 2387969 | 2717 | 15.2 | PV | 2-107-107 | 2020-01-22 | 2020-02-18 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2387970 | 2649 | 499.73 | PV | TBD | 2020-02-10 | 2020-02-13 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-17 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2387981 | 2420 | 20 | PV & Battery | 533-H3 | 2019-12-02 | 2020-02-14 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | Walpole | 2388024 | 2021 | 20 | PV | TBD | 2020-02-06 | 2020-02-14 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Mattapoisett | 2388535 | 2739 | 800 | PV | TBD | 2020-01-30 | 2020-02-18 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388537 | 2364 | 2760 | PV | TBD | 2020-01-22 | 2020-02-18 | #VALUE! |  | #VALUE! | 2020-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2388583 | 2125 | 366.3 | PV | TBD | 2020-02-18 | 2020-02-18 | 0 |  | 0 | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388590 | 2364 | 66.6 | PV | TBD | 2020-02-14 | 2020-02-18 | #VALUE! |  | #VALUE! | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Winchester | 2388617 | 1890 | 17.6 | PV & Battery | TBD | 2020-01-16 | 2020-02-19 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-12 | Online
NSTAR | Needham | 2388633 | 2492 | 18.8 | PV | 148-06 | 2019-12-02 | 2020-02-19 | #VALUE! |  | #VALUE! | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2388772 | 2125 | 121.22 | PV | TBD | 2020-02-10 | 2020-02-19 | #VALUE! |  | #VALUE! | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Plympton | 2388822 | 2367 | 15.2 | PV | TBD | 2020-02-10 | 2020-02-21 | #VALUE! |  | #VALUE! | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Framingham | 2388879 | 1702 | 400 | PV | TBD | 2020-01-21 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Newton | 2388945 | 2378 | 2400 | CHP | TBD | 2019-12-20 | 2020-02-20 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2389165 | 2655 | 23.3 | PV & Battery | 4-80A-490 | 2019-11-04 | 2020-02-21 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2389174 | 2332 | 16.7 | PV | TBD | 2020-02-18 | 2020-02-21 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Falmouth | 2389176 | 2540 | 21.58 | PV & Battery | 4-72-433 | 2019-12-18 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2389199 | 2540 | 958 | PV & Battery | TBD | 2020-02-18 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2389233 | 1776 | 20 | PV & Battery | TBD | 2020-02-07 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-10-08 | Online
NSTAR | Ashland | 2389241 | 1721 | 20 | Battery | 519-175H1 | 2020-01-15 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2389247 | 2420 | 10 | PV & Battery | TBD | 2020-01-15 | 2020-02-24 | #VALUE! |  | #VALUE! | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Wayland | 2389401 | 1778 | 20 | PV | TBD | 2020-02-20 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Boston | 2389473 | 2135 | 1150 | PV & Battery | TBD | 2020-01-29 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | Natick | 2389477 | 1760 | 133.2 | PV | TBD | 2020-03-03 | 2020-03-04 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online
NSTAR | Barnstable | 2389479 | 2630 | 66.6 | PV | TBD | 2020-02-24 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2389481 | 1890 | 17.6 | PV & Battery | 211-H1 | 2020-02-20 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Edgartown | 2389485 | 2539 | 22.8 | PV | TBD | 2019-12-26 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Acton | 2389509 | 1720 | 27 | Battery | 416-H4 | 2020-02-21 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2389511 | 2067 | 480 | PV | TBD | 2020-02-24 | 2020-02-25 | #VALUE! |  | #VALUE! | 2020-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online
NSTAR | Lexington | 2389932 | 2420 | 25 | PV & Battery | TBD | 2020-02-20 | 2020-02-27 | #VALUE! |  | #VALUE! | 2020-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-10-20 | Online
NSTAR | Chatham | 2390124 | 2633 | 18.7 | PV & Battery | TBD | 2020-02-28 | 2020-03-03 | #VALUE! |  | #VALUE! | 2020-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-07-16 | Online
NSTAR | Boston | 2390327 | 2118 | 557.5 | PV & Battery | 4912 | 2020-02-10 | 2020-03-06 | #VALUE! |  | #VALUE! | 2020-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Bellingham | 2390335 | 2019 | 15.2 | PV | 65-H4 | 2020-03-05 | 2020-03-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2390546 | 1702 | 100 | PV | TBD | 2020-03-02 | 2020-03-04 | #VALUE! |  | #VALUE! | 2020-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 2390669 | 1778 | 17.6 | PV & Battery | 342-H1 | 2020-02-25 | 2020-03-05 | #VALUE! |  | #VALUE! | 2020-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 2390776 | 2670 | 233.3 | PV | TBD | 2020-03-06 | 2020-03-06 | 0 |  | 0 | 2020-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2390944 | 2090 | 10 | PV & Battery | 148-H3 | 2020-02-18 | 2020-03-10 | #VALUE! |  | #VALUE! | 2020-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | North Dartmouth | 2390961 | 2747 | 150 | PV | TBD | 2020-03-09 | 2020-03-09 | 0 |  | 0 | 2020-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Weston | 2391087 | 2493 | 25 | PV & Battery | TBD | 2020-02-25 | 2020-03-09 | #VALUE! |  | #VALUE! | 2020-03-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Falmouth | 2391172 | 2536 | 4990 | PV & Battery | TBD | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2391210 | 2645 | 23 | PV |  | 2020-03-24 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-10-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Harwich | 2391216 | 2645 | 23 | PV | TBD | 2020-03-06 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | East Falmouth | 2391234 | 2536 | 3000 | PV & Battery | TBD | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2391270 | 2601 | 133.2 | PV | TBD | 2019-07-26 | 2019-07-29 | #VALUE! |  | #VALUE! | 2019-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Cataumet | 2391363 | 2534 | 29.23 | PV & Battery | 4-78-410 | 2020-02-21 | 2020-03-11 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Newton | 2391435 | 2459 | - | Battery | 292-H8 | 2020-01-15 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2391457 | 2540 | 15.2 | PV | 4-72-72 | 2020-03-10 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2391467 | 1746 | 20 | PV & Battery | TBD | 2020-03-09 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chelsea | 2391483 | 2150 | 199.8 | PV | TBD | 2020-03-10 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2391527 | 1776 | 17.6 | PV & Battery | 342-H7 | 2020-03-09 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Falmouth | 2391570 | 2540 | 24.6 | PV & Battery | 4-107-832 | 2020-03-05 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-03-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Holliston | 2391752 | 1746 | 200 | PV | TBD | 2020-02-27 | 2020-03-16 | #VALUE! |  | #VALUE! | 2020-03-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2391763 | 1730 | 15.2 | PV | TBD | 2020-01-15 | 2020-03-16 | #VALUE! |  | #VALUE! | 2020-03-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2391862 | 1803 | 19.12 | PV & Battery | TBD | 2020-03-09 | 2020-03-16 | #VALUE! |  | #VALUE! | 2020-04-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-28 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | East Freetown | 2391908 | 2717 | 25 | PV | TBD | 2020-03-16 | 2020-03-16 | 0 |  | 0 | 2020-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2391934 | 2571 | 28.8 | PV | TBD | 2020-03-16 | 2020-03-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | South Chatham | 2392011 | 2659 | 24.92 | PV & Battery | 4-95A-606 | 2020-03-09 | 2020-03-12 | #VALUE! |  | #VALUE! | 2020-04-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2392014 | 2557 | 1500 | PV |  | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 2020-04-08 |  | #VALUE! | 179 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-03 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-04-17 | Private
NSTAR | Sandwich | 2392033 | 2563 | 250 | PV | TBD | 2020-02-27 | 2020-03-16 | #VALUE! |  | #VALUE! | 2020-04-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2392113 | 2743 | 4000 | PV & Battery | TBD | 2020-03-12 | 2020-03-18 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2392127 | 2054 | 250 | PV | TBD | 2020-03-18 | 2020-03-18 | 0 |  | 0 | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2392184 | 1730 | 20 | PV | 533-H8 | 2020-03-17 | 2020-03-18 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2392188 | 2132 | 344.8 | PV & Battery | TBD | 2020-03-05 | 2020-03-18 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | Walpole | 2392586 | 2081 | 2000 | PV & Battery | TBD | 2020-03-06 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2392595 | 1760 | 456 | PV & Battery | TBD | 2020-03-05 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Marshfield | 2392617 | 2050 | 500 | PV | TBD | 2020-03-18 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2392719 | 2050 | 250 | PV | TBD | 2020-03-18 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Online
NSTAR | Natick | 2392730 | 1760 | 180 | PV | TBD | 2020-03-02 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Arlington | 2392742 | 2474 | 17.6 | PV & Battery | TBD | 2020-02-20 | 2020-03-18 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Harwich | 2392746 | 2645 | 4990 | PV & Battery | TBD | 2020-03-16 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2392870 | 2576 | 133.2 | PV | TBD | 2020-03-18 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2392879 | 2134 | 36 | CHP | TBD | 2020-03-18 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Duxbury | 2392885 | 2332 | 4000 | PV & Battery | TBD | 2020-03-20 | 2020-03-23 | #VALUE! |  | #VALUE! | 2020-04-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2392889 | 2601 | 72 | PV | TBD | 2020-03-17 | 2020-03-20 | #VALUE! |  | #VALUE! | 2020-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2392993 | 2360 | 144 | PV | TBD | 2020-03-20 | 2020-03-23 | #VALUE! |  | #VALUE! | 2020-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Mashpee | 2393455 | 2649 | 5000 | PV & Battery | TBD | 2020-02-20 | 2020-03-27 | #VALUE! |  | #VALUE! | 2020-04-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2393736 | 2571 | 8500 | PV |  | 2020-04-13 | 2020-12-21 | #VALUE! | 0 | #VALUE! | 2020-12-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-05-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Wareham | 2393742 | 2571 | 8500 | PV |  | 2020-04-13 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-03-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Stoneham | 2393943 | 2180 | 486 | PV | TBD | 2020-03-25 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2393958 | 2719 | 245 | PV | TBD | 2020-03-18 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2394000 | 1741 | 19.5 | PV | TBD | 2020-01-17 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Charlestown | 2394014 | 2129 | 4990 | PV | TBD | 2020-03-27 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2394160 | 2081 | 1000 | PV | TBD | 2020-03-27 | 2020-04-01 | #VALUE! |  | #VALUE! | 2020-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394184 | 2740 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394211 | 2740 | 250 | PV | TBD | 2020-03-20 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2394461 | 2743 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-17 | Online
NSTAR | New Bedford | 2394463 | 2745 | 133.3 | PV | TBD | 2020-03-18 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Boston | 2394534 | 2109 | 750 | CHP | TBD | 2020-04-06 | 2020-04-06 | 0 |  | 0 | 2020-04-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2394648 | 2458 | 25 | PV & Battery | TBD | 2020-03-20 | 2020-03-31 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Plympton | 2394682 | 2367 | 4975 | PV |  | 2020-04-20 |  | #VALUE! | 0 | #VALUE! | 2020-04-25 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | New Bedford | 2394787 | 2745 | 100 | PV | TBD | 2020-04-06 | 2020-04-08 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Falmouth | 2394862 | 2536 | 3500 | PV & Battery | TBD | 2020-03-27 | 2020-04-08 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2394867 | 2536 | 3500 | PV |  | 2020-04-21 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | South Dennis | 2395010 | 2368 | 112.5 | PV | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-04-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | East Freetown | 2395036 | 2717 | 149.3 | PV | TBD | 2020-03-26 | 2020-04-06 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Wareham | 2395041 | 2571 | 216 | PV | TBD | 2020-03-27 | 2020-04-13 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-28 | Online
NSTAR | Provincetown | 2395067 | 2657 | 495.8 | PV | TBD | 2020-04-08 | 2020-04-08 | 0 |  | 0 | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2395093 | 2462 | 17.6 | PV & Battery | TBD | 2020-04-06 | 2020-04-09 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Boston | 2395099 | 2134 | 40 | PV | TBD | 2020-04-06 | 2020-04-09 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Canton | 2395122 | 2021 | 15.2 | PV | TBD | 2020-03-18 | 2020-04-09 | #VALUE! |  | #VALUE! | 2020-04-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Rochester | 2395209 | 2770 | 999 | PV |  | 2020-04-23 | 2020-04-27 | #VALUE! | 0 | #VALUE! | 2020-04-28 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Dennis | 2395295 | 2638 | 16.6 | PV & Battery | 4-90-90 | 2020-03-27 | 2020-04-15 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Acton | 2395297 | 1720 | 240 | PV | TBD | 2020-04-08 | 2020-04-15 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Wareham | 2395408 | 2576 | 470 | PV | TBD | 2020-04-06 | 2020-04-09 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2395414 | 2648 | 16.38 | PV | TBD | 2020-04-01 | 2020-04-09 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Boston | 2395480 | 2136 | 99.9 | PV | TBD | 2020-04-06 | 2020-04-13 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2395483 | 2717 | 149.3 | PV | TBD | 2020-03-09 | 2020-04-10 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Hyannis | 2395561 | 2601 | 50 | PV | 4-80B-80B | 2020-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2395617 | 2118 | 484 | PV | TBD | 2020-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2395659 | 1701 | 57.6 | PV | TBD | 2020-04-20 | 2020-04-20 | 0 |  | 0 | 2020-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Milton | 2395800 | 2186 | 57.6 | PV | TBD | 2020-02-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Brewster | 2395844 | 2631 | 16.28 | PV & Battery | 4-89A-553 | 2020-03-27 | 2020-04-15 | #VALUE! |  | #VALUE! | 2020-04-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Falmouth | 2395855 | 2536 | 4990 | PV |  | 2020-04-29 | 2020-04-30 | #VALUE! | 0 | #VALUE! | 2020-04-30 |  | #VALUE! | 169 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-04 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-05-01 | Private
NSTAR | Plymouth | 2395947 | 2360 | 5466 | PV & Battery | TBD | 2020-03-27 | 2020-04-15 | #VALUE! |  | #VALUE! | 2020-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hatchville | 2395965 | 2536 | 3300 | PV |  | 2020-04-30 | 2020-04-30 | 0 | 0 | 0 | 2020-04-30 |  | #VALUE! | 169 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-05-01 | Private
NSTAR | Falmouth | 2395998 | 2536 | 3000 | PV |  | 2020-04-30 | 2020-05-01 | #VALUE! | 0 | #VALUE! |  |  | 0 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-05-01 | Private
NSTAR | Falmouth | 2396002 | 2540 | 958 | PV |  | 2020-04-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | East Boston | 2396083 | 2128 | 1700 | Steam Turbine |  | 2020-05-01 |  | #VALUE! | 0 | #VALUE! | 2020-05-01 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
NSTAR | Framingham | 2396140 | 1702 | 400 | PV | TBD | 2020-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 2396188 | 2535 | 20.95 | PV | TBD | 2020-04-06 | 2020-04-27 | #VALUE! |  | #VALUE! | 2020-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Plymouth | 2396211 | 2360 | 1000 | PV & Battery | TBD | 2020-04-15 | 2020-04-16 | #VALUE! |  | #VALUE! | 2020-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2396597 | 2631 | 86.4 | PV | TBD | 2020-05-04 |  | #VALUE! | 0 | #VALUE! | 2020-05-06 | 2020-05-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-05-13 | 2020-05-12 | 2020-12-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
NSTAR | Brewster | 2396639 | 2631 | 66.6 | PV | TBD | 2020-03-13 | 2020-04-20 | #VALUE! |  | #VALUE! | 2020-05-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2396686 | 1746 | 14 | Battery | 274-H5 | 2020-02-18 | 2020-04-20 | #VALUE! |  | #VALUE! | 2020-05-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2396845 | 2563 | 133.3 | PV | TBD | 2020-03-17 | 2020-04-20 | #VALUE! |  | #VALUE! | 2020-05-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2397127 | 2536 | 18.85 | PV | TBD | 2020-04-23 | 2020-04-27 | #VALUE! |  | #VALUE! | 2020-05-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-26 | Online
NSTAR | Oak Bluffs | 2397130 | 2557 | 300 | PV | 4-99-224 | 2020-03-18 | 2020-04-22 | #VALUE! |  | #VALUE! | 2020-05-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online
NSTAR | Hopkinton | 2397168 | 1748 | 3900 | PV & Battery | TBD | 2020-02-10 | 2020-04-23 | #VALUE! |  | #VALUE! | 2020-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2397176 | 2652 | 35 | PV | TBD | 2020-05-07 |  | #VALUE! | 0 | #VALUE! | 2020-06-25 | 2020-06-26 | #VALUE! | 15 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-07-15 |  | 2020-12-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Natick | 2397214 | 1760 | 13.92 | PV | 240-H1 | 2020-03-09 | 2020-04-22 | #VALUE! |  | #VALUE! | 2020-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Waltham | 2397225 | 2453 | 80 | PV | TBD | 2020-03-20 | 2020-04-23 | #VALUE! |  | #VALUE! | 2020-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Online
NSTAR | Stoneham | 2397255 | 2180 | 15.2 | PV | TBD | 2020-03-17 | 2020-03-27 | #VALUE! |  | #VALUE! | 2020-05-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2397442 | 2030 | 17.7 | PV | 456-H3 | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Waltham | 2397603 | 2453 | 46 | PV | TBD | 2020-04-16 | 2020-04-27 | #VALUE! |  | #VALUE! | 2020-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2397610 | 2657 | 54 | PV | TBD | 2020-04-06 | 2020-04-23 | #VALUE! |  | #VALUE! | 2020-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Framingham | 2397729 | 1702 | 240 | PV | TBD | 2020-04-23 | 2020-04-27 | #VALUE! |  | #VALUE! | 2020-05-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2397818 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397824 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397836 | 1760 | 330 | PV |  | 2020-05-12 |  | #VALUE! | 0 | #VALUE! | 2020-05-18 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-17 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-04-25 | Online |  | Private
NSTAR | Holliston | 2397865 | 1746 | 200 | PV |  | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-13 |  | 2020-12-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-03-19 | Online |  | Private
NSTAR | Canton | 2397898 | 2021 | 499 | PV & Battery | TBD | 2020-04-29 | 2020-04-30 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2398079 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2398156 | 2645 | 22.2 | PV | 4-95A-95A | 2020-04-27 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2398168 | 2747 | 15.2 | PV | 2-532-532 | 2020-03-16 | 2020-04-30 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Natick | 2398175 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2398227 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | East Falmouth | 2398257 | 2536 | 500 | PV | TBD | 2020-04-27 | 2020-04-30 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2398274 | 1748 | 24.28 | PV | TBD | 2020-04-09 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Cambridge | 2398561 | 2138 | 200 | PV | TBD | 2020-03-27 | 2020-04-30 | #VALUE! |  | #VALUE! | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brewster | 2398609 | 2631 | 4999 | PV & Battery | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2398639 | 1773 | 43.2 | PV | 240-H1 | 2020-04-15 | 2020-05-04 | #VALUE! |  | #VALUE! | 2020-05-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | Somerville | 2398711 | 2143 | 211 | PV | TBD | 2020-05-05 | 2020-05-08 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Lincoln | 2398773 | 1773 | 86.4 | PV | TBD | 2020-04-15 | 2020-05-04 | #VALUE! |  | #VALUE! | 2020-05-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | South Dartmouth | 2398833 | 2748 | 20.8 | PV & Battery | 2-53-65 | 2020-04-30 | 2020-05-05 | #VALUE! |  | #VALUE! | 2020-05-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2398880 | 2360 | 7.6 | PV & Battery | TBD | 2020-04-29 | 2020-04-29 | 0 |  | 0 | 2020-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Framingham | 2398893 | 1701 | - |  | TBD | 2020-05-20 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Holliston | 2399007 | 1746 | 300 | PV | TBD | 2020-04-20 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2399041 | 2717 | 25 | PV | TBD | 2020-05-07 | 2020-05-07 | 0 |  | 0 | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2399048 | 2744 | 15.2 | PV | TBD | 2020-05-05 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Framingham | 2399085 | 1702 | 22 | PV | TBD | 2020-05-21 |  | #VALUE! | 0 | #VALUE! | 2020-05-26 | 2020-06-24 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Duxbury | 2399108 | 2332 | 25 | PV & Battery | TBD | 2020-04-29 | 2020-05-08 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2399178 | 2601 | 460 | PV | 4-80B-80B | 2020-04-16 | 2020-04-20 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2399192 | 2631 | 4999 | PV & Battery | TBD | 2020-05-05 | 2020-05-08 | #VALUE! |  | #VALUE! | 2020-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2399437 | 2660 | 15.2 | PV | TBD | 2020-04-01 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Natick | 2399566 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2399596 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2399599 | 2645 | 240 | PV | TBD | 2020-04-29 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2399607 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Hyannis | 2399725 | 2601 | 73.3 | PV | TBD | 2020-04-06 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Hyannis | 2399742 | 2601 | 60 | PV | TBD | 2020-04-08 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Plymouth | 2399743 | 2360 | 17.6 | PV | 3-72-940 | 2020-05-08 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Cambridge | 2399827 | 2141 | 60 | CHP | TBD | 2020-02-04 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online
NSTAR | Acusnet | 2399839 | 2743 | 5000 | PV | TBD | 2019-09-13 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 2399904 | 2030 | 35.2 | PV | TBD | 2020-05-05 | 2020-05-13 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Sandwich | 2400107 | 2653 | 150 | PV | TBD | 2020-05-08 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Freetown | 2400205 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | 2400260 | 2649 | 1490 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plympton | 2400919 | 2367 | 149.3 | PV | TBD | 2020-05-20 | 2020-05-20 | 0 |  | 0 | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2400943 | 2653 | 499 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Natick | 2400946 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | #VALUE! |  | #VALUE! | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Mashpee | 2400979 | 2649 | 2075 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2401009 | 2653 | 200 | PV | TBD | 2020-04-30 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2401149 | 2132 | 149.8 | PV | TBD | 2020-04-27 | 2020-05-26 | #VALUE! |  | #VALUE! | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2401235 | 2649 | 730 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2401247 | 2738 | 700 | PV & Battery | TBD | 2020-04-30 | 2020-05-18 | #VALUE! |  | #VALUE! | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2401361 | 2537 | 499 | PV | TBD | 2020-05-04 | 2020-05-20 | #VALUE! |  | #VALUE! | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2401405 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | #VALUE! |  | #VALUE! | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2401687 | 2746 | 499 | PV | TBD | 2020-05-18 | 2020-05-20 | #VALUE! |  | #VALUE! | 2020-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-05 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2401948 | 1746 | 216 | PV | TBD | 2020-05-15 | 2020-05-26 | #VALUE! |  | #VALUE! | 2020-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Lincoln | 2401979 | 1773 | 22.6 | PV & Battery | TBD | 2020-05-18 | 2020-05-28 | #VALUE! |  | #VALUE! | 2020-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Chatham | 2402094 | 2633 | 22.32 | PV | TBD | 2020-05-26 | 2020-05-28 | #VALUE! |  | #VALUE! | 2020-06-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-10 | Online
NSTAR | Falmouth | 2402100 | 2540 | 133 | PV |  | 2020-06-11 | 2020-06-15 | #VALUE! | 0 | #VALUE! | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | 2020-07-06 | 2020-12-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-08-19 | Online |  | Private
NSTAR | Waltham | 2402126 | 2451 | 375 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-29 | [7 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2402135 | 2747 | 149.3 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2402181 | 2132 | 226.9 | PV | TBD | 2020-04-27 | 2020-05-26 | #VALUE! |  | #VALUE! | 2020-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2402255 | 1721 | 10 | PV & Battery | TBD | 2020-05-26 | 2020-06-01 | #VALUE! |  | #VALUE! | 2020-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Kingston | 2402374 | 2364 | 499 | PV |  | 2020-06-15 | 2020-06-16 | #VALUE! | 0 | #VALUE! | 2020-06-30 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Centerville | 2402410 | 2632 | 7.6 | PV | 4-82-508 | 2020-05-18 | 2020-06-03 | #VALUE! |  | #VALUE! | 2020-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-04-21
NSTAR | Carver | 2402730 | 2330 | 200 | PV | TBD | 2020-05-15 | 2020-06-03 | #VALUE! |  | #VALUE! | 2020-06-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2402767 | 2649 | 10 | PV & Battery | 4-452-452 | 2020-05-15 | 2020-06-03 | #VALUE! |  | #VALUE! | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | New Bedford | 2402897 | 2746 | 499 | PV | TBD | 2020-05-28 | 2020-06-01 | #VALUE! |  | #VALUE! | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2402933 | 2130 | 1489 | PV |  | 2020-06-17 | 2020-06-19 | #VALUE! | 0 | #VALUE! | 2020-06-29 |  | #VALUE! | 128 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-06-30 | Private
NSTAR | West Wareham | 2402967 | 2576 | 10 | PV & Battery | 3-85-85 | 2020-05-28 | 2020-06-03 | #VALUE! |  | #VALUE! | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Sandwich | 2403120 | 2563 | 90 | PV & Battery | TBD | 2020-05-28 | 2020-06-03 | #VALUE! |  | #VALUE! | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2403255 | 1801 | 63.3 | PV | TBD | 2020-06-01 | 2020-06-04 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2403259 | 2421 | 25.5 | PV & Battery | TBD | 2020-06-03 | 2020-06-05 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-01-08 | Online
NSTAR | Fairhaven | 2403269 | 2719 | 469.8 | PV | TBD | 2020-03-16 | 2020-06-05 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Newton | 2403398 | 2459 | 19.84 | PV & Battery | 443-02 | 2020-06-05 | 2020-06-05 | 0 |  | 0 | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 2403403 | 2130 | 10 | PV & Battery | 284-1300H1 | 2020-05-20 | 2020-06-08 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 2403438 | 2673 | 232 | PV | TBD | 2020-05-18 | 2020-06-08 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2403475 | 1730 | 31 | PV & Battery | TBD | 2020-06-01 | 2020-06-08 | #VALUE! |  | #VALUE! | 2020-06-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Wareham | 2403535 | 2571 | 149.3 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Centerville | 2403564 | 2632 | 15.2 | PV | TBD | 2020-04-20 | 2020-06-18 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | West Wareham | 2403572 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2403584 | 2714 | 2958 | PV & Battery | 2-543-543 | 2020-02-20 | 2020-06-08 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2403624 | 2451 | 144 | PV | TBD | 2020-04-15 | 2020-05-26 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-21 | Online
NSTAR | Provincetown | 2403670 | 2567 | 22.89 | PV & Battery | 4-96-675 | 2020-06-03 | 2020-06-10 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Forestdale | 2403701 | 2644 | - |  | TBD | 2020-06-24 |  | #VALUE! | 0 | #VALUE! | 2020-06-30 | 2020-07-13 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-08-12 | 2020-09-14 | 2020-12-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Medway | 2403742 | 2053 | 25.75 | PV | TBD | 2019-10-09 | 2020-06-10 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2403835 | 1776 | 200 | PV | TBD | 2020-04-16 | 2020-06-10 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Plymouth | 2403991 | 2360 | 180 | PV | TBD | 2020-05-18 | 2020-06-11 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Dennis | 2404237 | 2660 | 3176 | PV | TBD | 2020-04-01 | 2020-06-11 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Barnstable | 2404275 | 2630 | 3146 | PV & Battery | TBD | 2019-05-26 | 2020-06-15 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Orleans | 2404297 | 2643 | 10 | PV & Battery | 4-95B-628 | 2020-05-28 | 2020-06-15 | #VALUE! |  | #VALUE! | 2020-06-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Boston | 2404393 | 2126 | 129.6 | PV | TBD | 2020-06-08 | 2020-06-15 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0
NSTAR | Millis | 2404399 | 2054 | 2500 | PV & Battery | TBD | 2020-06-03 | 2020-06-15 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2404421 | 2631 | 10 | PV & Battery | 4-95A-597 | 2020-06-15 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Wayland | 2404425 | 1778 | 10 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2404430 | 1748 | 15.2 | PV | 126-H1 | 2020-06-02 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Framingham | 2404459 | 1702 | 61.2 | PV | TBD | 2020-04-30 | 2020-06-10 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Needham | 2404602 | 2492 | 19.84 | PV | 148-H2 | 2020-06-22 | 2020-06-22 | 0 |  | 0 | 2020-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2404607 | 1746 | 21 | PV & Battery | 274-H5 | 2020-06-10 | 2020-06-23 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Hyannis | 2404659 | 2601 | 999 | PV & Battery | TBD | 2020-02-07 | 2020-06-11 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2404678 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-11 | #VALUE! |  | #VALUE! | 2020-07-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2404735 | 2476 | 17.6 | PV & Battery | TBD | 2020-06-10 | 2020-06-15 | #VALUE! |  | #VALUE! | 2020-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Jamaica Plain | 2404933 | 2130 | 1360 | PV | TBD | 2020-04-16 | 2020-06-02 | #VALUE! |  | #VALUE! | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2404942 | 2143 | 22.8 | PV | TBD | 2020-06-15 | 2020-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Cambridge | 2405400 | 2139 | 16 | PV & Battery | 817-03 | 2020-06-15 | 2020-06-22 | #VALUE! |  | #VALUE! | 2020-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2405461 | 1701 | 365 | PV | TBD | 2020-06-01 | 2020-07-06 | #VALUE! |  | #VALUE! | 2020-07-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0
NSTAR | Truro | 2405858 | 2652 | 4107 | PV & Battery | TBD | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2406412 | 1748 | 250 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2406453 | 2492 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Waban | 2406455 | 2468 | 19.84 | PV & Battery | 292-H12 | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2406457 | 2186 | 21.67 | PV & Battery | 4303 | 2020-06-10 | 2020-06-23 | #VALUE! |  | #VALUE! | 2020-07-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 2406653 | 1776 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2406660 | 1701 | 17.6 | PV & Battery | TBD | 2020-06-15 | 2020-06-15 | 0 |  | 0 | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-07-01 | Online
NSTAR | Bedford | 2406661 | 1730 | 21 | PV & Battery | 322-1397H1 | 2020-06-23 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Westport | 2406662 | 2790 | 19 | PV | 2-523-523 | 2020-06-09 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Waltham | 2406861 | 2452 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-06-29 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Somerville | 2406866 | 2145 | 23 | PV |  | 2020-07-15 | 2020-07-20 | #VALUE! | 0 | #VALUE! | 2020-08-04 | 2020-08-21 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-09-10 | 2020-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Buzzards Bay | 2407059 | 2532 | 133.2 | PV | TBD | 2020-04-20 | 2020-06-30 | #VALUE! |  | #VALUE! | 2020-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2407070 | 2563 | 499 | PV |  | 2020-07-16 | 2020-07-20 | #VALUE! | 0 | #VALUE! | 2020-08-04 |  | #VALUE! | 100 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-08-10 | Private
NSTAR | Hopkinton | 2407210 | 1748 | 480 | PV |  | 2020-07-17 | 2020-07-20 | #VALUE! | 0 | #VALUE! | 2020-07-22 |  | #VALUE! | 104 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-08-04 | Private
NSTAR | Lexington | 2407464 | 2421 | 19.86 | PV & Battery | 320-H2 | 2020-07-03 | 2020-07-03 | 0 |  | 0 | 2020-07-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wellfleet | 2407474 | 2667 | 2000 | PV & Battery | TBD | 2020-07-01 | 2020-07-02 | #VALUE! |  | #VALUE! | 2020-07-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2407481 | 2557 | 22 | PV & Battery | TBD | 2020-06-29 | 2020-07-01 | #VALUE! |  | #VALUE! | 2020-07-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2407609 | 2053 | 1476 | PV & Battery | TBD | 2020-07-06 | 2020-07-09 | #VALUE! |  | #VALUE! | 2020-07-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2407667 | 1770 | 17.4 | PV | TBD | 2020-07-10 | 2020-07-10 | 0 |  | 0 | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Acton | 2407706 | 1720 | 15 | PV & Battery | 416-H4 | 2020-07-21 |  | #VALUE! | 0 | #VALUE! | 2020-08-06 | 2020-11-12 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-21 |  | 2020-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | New Bedford | 2407717 | 2745 | 500 | PV & Battery | TBD | 2020-06-01 | 2020-07-13 | #VALUE! |  | #VALUE! | 2020-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-11 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2407737 | 2460 | 115.2 | PV | TBD | 2020-07-06 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online
NSTAR | Newton | 2407743 | 2459 | 20 | PV & Battery | TBD | 2020-06-23 | 2020-07-01 | #VALUE! |  | #VALUE! | 2020-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | Mattapoisett | 2407746 | 2739 | 15.2 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Hyannis | 2407747 | 2601 | 24.07 | PV | TBD | 2020-07-06 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2407835 | 2143 | 22.8 | PV | TBD | 2020-06-02 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Holliston | 2407949 | 2532 | 15.2 | PV | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chestnut Hill | 2407979 | 2467 | 36 | PV & Battery | 467-H12 | 2020-07-01 | 2020-07-02 | #VALUE! |  | #VALUE! | 2020-07-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2408018 | 1701 | 22 | PV & Battery | TBD | 2020-07-01 | 2020-07-03 | #VALUE! |  | #VALUE! | 2020-07-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Fairhaven | 2408049 | 2719 | 99 | PV |  | 2020-07-23 | 2020-07-27 | #VALUE! | 0 | #VALUE! | 2020-08-04 | 2020-08-19 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 |  | 2020-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Wayland | 2408090 | 1778 | 17.6 | PV & Battery | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2408258 | 1701 | 245 | PV & Battery | TBD | 2020-07-15 | 2020-07-17 | #VALUE! |  | #VALUE! | 2020-07-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2408289 | 2719 | 99.09 | PV | TBD | 2020-07-10 | 2020-07-14 | #VALUE! |  | #VALUE! | 2020-07-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2408400 | 1746 | 499 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2408483 | 2360 | 1000 | PV & Battery | TBD | 2020-06-30 | 2020-07-02 | #VALUE! |  | #VALUE! | 2020-07-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2408542 | 1730 | 25 | PV & Battery | 533-H5 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Needham | 2408568 | 2492 | 17 | PV & Battery | TBD | 2020-07-06 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Ashland | 2408580 | 1721 | 7 | PV & Battery | 519-175H1 | 2020-06-05 | 2020-07-13 | #VALUE! |  | #VALUE! | 2020-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 2408582 | 1760 | 43.2 | PV | TBD | 2020-05-28 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Rochester | 2408783 | 2770 | 4999 | PV & Battery | TBD | 2020-07-07 | 2020-07-13 | #VALUE! |  | #VALUE! | 2020-07-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2408881 | 2459 | 10 | PV | 1709 | 2020-07-30 | 2020-09-10 | #VALUE! | 0 | #VALUE! | 2020-09-10 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-02-15 | Online |  | Private
NSTAR | Marshfield | 2409029 | 2050 | 7.6 | PV | 3-24B-915 | 2020-05-26 | 2020-07-07 | #VALUE! |  | #VALUE! | 2020-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-12 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Acton | 2409041 | 1702 | 15.6 | PV & Battery | 416-H5 | 2020-07-11 | 2020-07-15 | #VALUE! |  | #VALUE! | 2020-08-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Cambridge | 2409461 | 2140 | 14 | PV & Battery | 825-27 | 2020-06-11 | 2020-07-16 | #VALUE! |  | #VALUE! | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | West Wareham | 2409477 | 2576 | 7.6 | PV | TBD | 2020-07-01 | 2020-07-16 | #VALUE! |  | #VALUE! | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Orleans | 2409513 | 2145 | 245 | PV | TBD | 2020-07-15 | 2020-07-16 | #VALUE! |  | #VALUE! | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2409582 | 1746 | 250 | PV | TBD | 2020-07-08 | 2020-07-14 | #VALUE! |  | #VALUE! | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2409588 | 2115 | 180 | PV |  | 2020-08-03 | 2020-08-04 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Canton | 2409650 | 2021 | 21.4 | PV & Battery | TBD | 2020-07-20 | 2020-07-20 | 0 |  | 0 | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Plymouth | 2409661 | 2360 | 10 | PV & Battery | 3-14-934 | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | Hopkinton | 2409830 | 1748 | 5000 | PV & Battery | TBD | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2409880 | 1803 | 95.5 | PV | TBD | 2020-07-22 | 2020-07-23 | #VALUE! |  | #VALUE! | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2409915 | 2649 | 245 | PV & Battery | TBD | 2020-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-05 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2409919 | 2128 | 57.6 | PV | TBD | 2020-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-03-22 | Online
NSTAR | Burlington | 2409940 | 1803 | 20.4 | PV & Battery | 346-1395H1 | 2020-06-29 | 2020-07-28 | #VALUE! |  | #VALUE! | 2020-08-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Winchester | 2409982 | 1890 | 18 | PV & Battery |  | 2020-08-07 | 2020-08-10 | #VALUE! | 0 | #VALUE! | 2020-08-13 | 2020-08-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-08-31 | 2020-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2022-02-03 | Online |  | Private
NSTAR | Lexington | 2409998 | 2420 | 20 | PV & Battery | TBD | 2020-07-15 | 2020-07-20 | #VALUE! |  | #VALUE! | 2020-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Fairhaven | 2410005 | 2719 | 750 | PV | TBD | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2410106 | 2563 | 7.6 | PV | 4-81B-443 | 2020-06-23 | 2020-07-28 | #VALUE! |  | #VALUE! | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2410160 | 2115 | 180 | PV | TBD | 2020-07-28 | 2020-07-29 | #VALUE! |  | #VALUE! | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2410254 | 2649 | 499 | PV & Battery | TBD | 2020-07-27 | 2020-08-03 | #VALUE! |  | #VALUE! | 2020-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2410310 | 2364 | 133.2 | PV | TBD | 2020-07-29 | 2020-08-03 | #VALUE! |  | #VALUE! | 2020-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online
NSTAR | Mattapoisett | 2410489 | 2739 | 5000 | PV & Battery | TBD | 2020-07-29 | 2020-08-04 | #VALUE! |  | #VALUE! | 2020-08-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2410632 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-13 | #VALUE! |  | #VALUE! | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2410727 | 2021 | 249.8 | PV | 470-H7 | 2020-07-29 | 2020-07-29 | 0 |  | 0 | 2020-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Natick | 2410746 | 1760 | 10 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2410747 | 2494 | 19.57 | PV & Battery | 292-H4 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2410763 | 2452 | 7.6 | PV | 450-H6 | 2020-08-04 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Wareham | 2410816 | 2576 | - |  | TBD | 2020-08-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2030-12-20 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
NSTAR | Brookline | 2410954 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2410982 | 1760 | 497 | PV | 240-H1 | 2020-08-17 | 2020-09-29 | #VALUE! | 0 | #VALUE! | 2020-09-29 | 2020-10-07 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Woburn | 2411000 | 1801 | 15.2 | PV | TBD | 2020-06-08 | 2020-07-28 | #VALUE! |  | #VALUE! | 2020-08-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-20 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2411056 | 1803 | 500 | PV |  | 2020-08-17 | 2020-08-17 | 0 | 0 | 0 | 2020-08-25 |  | #VALUE! | 65 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-09-30 | Private
NSTAR | Falmouth | 2411073 | 2540 | 15.2 | PV | 4-76-436 | 2020-06-15 | 2020-07-28 | #VALUE! |  | #VALUE! | 2020-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2411107 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-30 | #VALUE! |  | #VALUE! | 2020-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2411131 | 1730 | 25 | PV & Battery | TBD | 2020-07-22 | 2020-08-03 | #VALUE! |  | #VALUE! | 2020-08-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Brookline | 2411200 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Stoneham | 2411309 | 2180 | 10 | PV & Battery | 375-H8 | 2020-07-22 | 2020-08-03 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Framingham | 2411344 | 1702 | 573 | PV |  | 2020-08-18 | 2020-09-09 | #VALUE! | 0 | #VALUE! | 2020-09-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
NSTAR | Hyannis | 2411466 | 2601 | 186 | PV | TBD | 2020-08-06 | 2020-08-06 | 0 |  | 0 | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2411491 | 2536 | - | PV & Battery | TBD | 2020-07-06 | 2020-07-03 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2411492 | 2421 | 361.5 | PV | TBD | 2020-07-29 | 2020-08-04 | #VALUE! |  | #VALUE! | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Falmouth | 2411634 | 2540 | 66.6 | PV | TBD | 2020-08-03 | 2020-08-07 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Falmouth | 2411656 | 2540 | 18.7 | PV & Battery | TBD | 2020-07-15 | 2020-08-03 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Wayland | 2411668 | 1778 | 23.01 | PV | TBD | 2020-07-22 | 2020-08-07 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | North Falmouth | 2411670 | 2556 | 18 | PV & Battery | TBD | 2020-08-04 | 2020-08-10 | #VALUE! |  | #VALUE! | 2020-08-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2411939 | 2631 | 57.6 | PV | TBD | 2020-07-22 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2411957 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Mashpee | 2411961 | 2649 | 750 | PV & Battery | TBD | 2020-07-27 | 2020-08-06 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2412130 | 2747 | 15.2 | PV | TBD | 2020-07-27 | 2020-08-07 | #VALUE! |  | #VALUE! | 2020-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2412133 | 2050 | 15.2 | PV | TBD | 2020-08-06 | 2020-08-07 | #VALUE! |  | #VALUE! | 2020-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2412211 | 2090 | 3104.5 | PV & Battery | TBD | 2020-08-07 | 2020-08-11 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2412218 | 2125 | 19 | PV & Battery | 483-01 | 2020-07-29 | 2020-08-11 | #VALUE! |  | #VALUE! | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Onset | 2412247 | 2558 | 17.6 | PV | TBD | 2020-06-23 | 2020-08-13 | #VALUE! |  | #VALUE! | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Fairhaven | 2412322 | 2719 | 66.6 | PV | TBD | 2020-08-10 | 2020-08-10 | 0 |  | 0 | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Holliston | 2412335 | 1746 | 20 | PV | TBD | 2020-08-26 | 2020-08-31 | #VALUE! | 0 | #VALUE! | 2020-09-14 |  | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-01 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Falmouth | 2412337 | 2540 | 122 | PV | TBD | 2020-08-06 | 2020-08-11 | #VALUE! |  | #VALUE! | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Online
NSTAR | Pocasset | 2412341 | 2559 | 999 | PV & Battery | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2412477 | 2601 | 250 | PV | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2412478 | 2421 | 133.3 | PV | TBD | 2020-05-05 | 2020-08-13 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2412543 | 2180 | 15.2 | PV | TBD | 2020-07-22 | 2020-08-14 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Lexington | 2412545 | 2421 | 15.2 | PV | TBD | 2020-08-12 | 2020-08-14 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2412573 | 2021 | 2660 | PV & Battery | TBD | 2020-07-29 | 2020-08-17 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2412636 | 2140 | 19.12 | PV | TBD | 2020-08-12 | 2020-08-17 | #VALUE! |  | #VALUE! | 2020-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | New Bedford | 2412695 | 2746 | 250 | PV | TBD | 2019-12-30 | 2020-01-21 | #VALUE! |  | #VALUE! | 2020-09-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2412699 | 2026 | 4990 | PV |  | 2020-08-31 | 2020-09-09 | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 |  | #VALUE! | 62 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | 2020-10-05 | Private
NSTAR | Plymouth | 2412755 | 2360 | 17.6 | PV & Battery | TBD | 2020-07-28 | 2020-08-14 | #VALUE! |  | #VALUE! | 2020-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2412838 | 2364 | 15.2 | PV | 3-51-980 | 2020-07-22 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Medfield | 2412922 | 2052 | 250 | PV | TBD | 2020-09-01 | 2020-09-03 | #VALUE! | 0 | #VALUE! | 2020-09-14 | 2020-11-25 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-12-14 |  | 2020-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Norfolk | 2412929 | 2056 | 5000 | PV & Battery | TBD | 2020-08-06 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2413383 | 1746 | 5000 | PV & Battery | TBD | 2020-08-06 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2413389 | 1720 | 5000 | PV & Battery | TBD | 2020-08-06 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2413390 | 2360 | 21.4 | PV & Battery | TBD | 2020-08-11 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Carlisle | 2413532 | 1741 | 17.6 | PV & Battery | TBD | 2020-08-12 | 2020-08-18 | #VALUE! |  | #VALUE! | 2020-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | Waltham | 2413861 | 2451 | 487.5 | PV | TBD | 2020-06-22 | 2020-08-25 | #VALUE! |  | #VALUE! | 2020-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2413980 | 2445 | 133.2 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Hyde Park | 2414035 | 2136 | 15.2 | PV | TBD | 2020-08-04 | 2020-08-18 | #VALUE! |  | #VALUE! | 2020-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Brookline | 2414048 | 2446 | 200 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acusnet | 2414312 | 2743 | 1220 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2414387 | 2743 | 610 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | #VALUE! |  | #VALUE! | 2020-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4253275 | 2130 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | #VALUE! |  | #VALUE! | 2020-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 4257166 | 2633 | 86.6 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | #VALUE! |  | #VALUE! | 2020-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 4258230 | 2136 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | #VALUE! |  | #VALUE! | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Yarmouth | 4263458 | 2673 | 158.4 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | #VALUE! |  | #VALUE! | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4280601 | 2652 | 35 | PV | TBD | 2020-09-03 | 2020-09-03 | 0 |  | 0 | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-01-28 | Online
NSTAR | Burlington | 4280698 | 1803 | 30.2 | PV & Battery | TBD | 2020-07-22 | 2020-08-18 | #VALUE! |  | #VALUE! | 2020-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Aquinnah | 4281091 | 2635 | 54.2 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | #VALUE! |  | #VALUE! | 2020-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 4284906 | 2653 | 51.62 | PV | TBD | 2020-08-27 | 2020-09-01 | #VALUE! |  | #VALUE! | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Acusnet | 4287867 | 2743 | 610 | PV & Battery | TBD | 2020-09-01 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-09-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 4288338 | 2536 | 33.3 | PV | TBD | 2020-09-01 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Lexington | 4289037 | 2421 | 21.4 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | East Falmouth | 4290987 | 2536 | 17.04 | PV | 4-77A-77A | 2020-08-27 | 2020-09-02 | #VALUE! |  | #VALUE! | 2020-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Dover | 4296074 | 2030 | 200 | PV | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4304369 | 2667 | 28.7 | PV & Battery | TBD | 2020-08-04 | 2020-09-08 | #VALUE! |  | #VALUE! | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | East Falmouth | 4304824 | 2536 | 20 | PV & Battery | TBD | 2020-09-03 | 2020-09-09 | #VALUE! |  | #VALUE! | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Hyannis | 4305225 | 2601 | 86.4 | PV | TBD | 2020-08-27 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Woburn | 4305278 | 1801 | 111.5 | PV & Battery | TBD | 2020-09-08 | 2020-09-11 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | West Tisbury | 4307156 | 2658 | 48 | PV | TBD | 2020-09-04 | 2020-09-14 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Sudbury | 4307664 | 1776 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-09-15 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 4307751 | 2445 | 100 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online
NSTAR | East Dennis | 4308158 | 2641 | 10 | PV & Battery | 4-89A-552 | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 4310270 | 2535 | 166.9 | PV | 4-97-226 | 2020-09-16 | 2020-09-16 | 0 |  | 0 | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | West Yarmouth | 4311398 | 2673 | 370 | PV | TBD | 2020-08-18 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 4311559 | 2666 | 15.2 | PV | TBD | 2020-08-07 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Acton | 4312709 | 1720 | 15.2 | PV | TBD | 2020-08-27 | 2020-09-03 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 4314087 | 1721 | 27.6 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 4318460 | 1741 | 30.2 | PV & Battery | TBD | 2020-09-01 | 2020-09-10 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Needham | 4318615 | 2494 | 1300 | PV & Battery | TBD | 2020-08-27 | 2020-09-10 | #VALUE! |  | #VALUE! | 2020-10-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 4323415 | 2571 | 200 | PV | TBD | 2020-08-06 | 2020-09-10 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 4324124 | 2492 | 144 | PV | TBD | 2020-09-03 | 2020-09-11 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4325211 | 2030 | 20 | PV | 456-H5 | 2020-09-11 | 2020-09-18 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4325236 | 2179 | 300 | PV | TBD | 2020-09-08 | 2020-09-14 | #VALUE! |  | #VALUE! | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | 4336889 | 1778 | 20 | PV & Battery | TBD | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 4340257 | 2557 | 233.1 | PV | TBD | 2020-05-26 | 2020-09-15 | #VALUE! |  | #VALUE! | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4340848 | 2472 | 430.3 | PV | TBD | 2020-09-08 | 2020-09-16 | #VALUE! |  | #VALUE! | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Millis | 4345313 | 2054 | 19 | PV | TBD | 2020-09-14 | 2020-09-18 | #VALUE! |  | #VALUE! | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Wareham | 4350518 | 2576 | 266.3 | PV | TBD | 2020-09-18 | 2020-09-22 | #VALUE! |  | #VALUE! | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Online
NSTAR | Canton | 4350632 | 2021 | 35.2 | PV & Battery | TBD | 2020-09-08 | 2020-09-22 | #VALUE! |  | #VALUE! | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4351141 | 2030 | 20.22 | PV & Battery | 456-H5 | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Bedford | 4352135 | 1730 | 100.8 | PV | TBD | 2020-09-10 | 2020-09-24 | #VALUE! |  | #VALUE! | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-12 | Online
NSTAR | Sudbury | 4352193 | 2453 | 17.86 | PV & Battery | TBD | 2020-09-18 | 2020-09-24 | #VALUE! |  | #VALUE! | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Boston | 4352975 | 2215 | 75 | CHP | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | East Freetown | 4355122 | 2717 | 61.6 | PV | TBD | 2020-09-25 | 2020-09-25 | 0 |  | 0 | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Online
NSTAR | Allston | 4367936 | 2134 | 125 | PV & Battery | TBD | 2020-09-18 | 2020-09-25 | #VALUE! |  | #VALUE! | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4371445 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372220 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372438 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Carver | 4377469 | 2330 | 200 | PV | TBD | 2020-09-18 | 2020-09-30 | #VALUE! |  | #VALUE! | 2020-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4380220 | 2186 | 17.6 | PV & Battery | TBD | 2020-09-22 | 2020-10-05 | #VALUE! |  | #VALUE! | 2020-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 4389990 | 2332 | 16.24 | PV & Battery | 3-26-903 | 2020-09-30 | 2020-10-05 | #VALUE! |  | #VALUE! | 2020-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Natick | 4397054 | 1760 | 100 | PV | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-15 | Withdrawn
NSTAR | Waltham | 4399358 | 2453 | 75 | chp | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Forestdale | 4399952 | 2644 | 15.2 | PV | 4-81B-443 | 2020-09-18 | 2020-09-18 | 0 |  | 0 | 2020-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 4403448 | 2472 | 583.3 | PV & Battery | TBD | 2020-09-22 | 2020-09-30 | #VALUE! |  | #VALUE! | 2020-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4404039 | 2472 | 320.8 | PV | TBD | 2020-09-22 | 2020-09-30 | #VALUE! |  | #VALUE! | 2020-10-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4404592 | 2719 | 2000 | PV & Battery | TBD | 2020-09-24 | 2020-09-25 | #VALUE! |  | #VALUE! | 2020-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4406125 | 2139 | 77.8 | PV | TBD | 2020-09-30 | 2020-09-30 | 0 |  | 0 | 2020-10-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Sherborn | 4425381 | 1770 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 4425492 | 2132 | 15.2 | PV | TBD | 2020-09-24 | 2020-10-07 | #VALUE! |  | #VALUE! | 2020-10-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 4427690 | 1760 | 25 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-11-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Vineyard Haven | 4429285 | 2568 | 19.68 | PV | TBD | 2020-08-27 | 2020-10-07 | #VALUE! |  | #VALUE! | 2020-11-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | East Falmouth | 4430372 | 2536 | 198 | PV | TBD | 2020-09-30 | 2020-10-08 | #VALUE! |  | #VALUE! | 2020-11-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4433447 | 2360 | 66.6 | PV | TBD | 2020-10-06 | 2020-10-07 | #VALUE! |  | #VALUE! | 2020-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Somerville | 4467249 | 2143 | 250 | PV | TBD | 2020-10-19 | 2020-10-19 | 0 |  | 0 | 2020-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 4468058 | 2067 | 19 | PV | TBD | 2020-10-07 | 2020-10-15 | #VALUE! |  | #VALUE! | 2020-11-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4469232 | 2667 | 23.2 | PV | 4-96-677 | 2020-09-18 | 2020-10-08 | #VALUE! |  | #VALUE! | 2020-11-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-04
NSTAR | Newton | 4469731 | 2458 | 19.75 | PV & Battery | 277-05 | 2020-09-18 | 2020-10-05 | #VALUE! |  | #VALUE! | 2020-11-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Medway | 4470535 | 2053 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-19 | #VALUE! |  | #VALUE! | 2020-11-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-08 | Online
NSTAR | Canton | 4470982 | 2021 | 245 | PV | TBD | 2020-10-08 | 2020-10-19 | #VALUE! |  | #VALUE! | 2020-11-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0
NSTAR | North Falmouth | 4479289 | 2649 | 25.81 | PV & Battery | TBD | 2020-10-15 | 2020-10-19 | #VALUE! |  | #VALUE! | 2020-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Somerville | 4487617 | 2145 | 250 | PV | TBD | 2020-10-15 | 2020-10-15 | 0 |  | 0 | 2020-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Sharon | 4488554 | 2067 | 18.75 | PV | TBD | 2020-10-16 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  | 2021-06-03 | Online
NSTAR | Rochester | 4489081 | 2770 | 22 | PV | TBD | 2020-10-15 | 2020-10-19 | #VALUE! |  | #VALUE! | 2020-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-25 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Jamaica Plain | 4489427 | 2130 | 400 | PV | TBD | 2020-10-16 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Lexington | 4490263 | 2421 | 24 | PV & Battery | 3401 | 2020-10-15 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Wareham | 4490547 | 2576 | 233.2 | PV | TBD | 2020-10-16 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4490762 | 2739 | 5000 | PV & Battery | TBD | 2020-10-16 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4492827 | 2030 | 36 | PV & Battery | TBD | 2020-10-15 | 2020-10-21 | #VALUE! |  | #VALUE! | 2020-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 4493355 | 2050 | 19.6 | PV & Battery | 3-25-25 | 2020-10-21 | 2020-10-22 | #VALUE! |  | #VALUE! | 2020-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 4494158 | 2702 | 18.85 | PV | TBD | 2020-10-22 | 2020-10-22 | 0 |  | 0 | 2020-12-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Newton | 4495812 | 2459 | 18 | PV & Battery | TBD | 2020-10-16 | 2020-10-22 | #VALUE! |  | #VALUE! | 2020-11-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 4500410 | 2121 | 16.8 | PV | TBD | 2020-10-07 | 2020-10-27 | #VALUE! |  | #VALUE! | 2020-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Canton | 4503033 | 2021 | 200 | PV | TBD | 2020-10-21 | 2020-10-22 | #VALUE! |  | #VALUE! | 2020-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4506135 | 2360 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | #VALUE! |  | #VALUE! | 2020-11-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 4506942 | 2143 | 53.6 | PV & Battery | TBD | 2020-10-19 | 2020-10-27 | #VALUE! |  | #VALUE! | 2020-11-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | Carver | 4507889 | 2330 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4518746 | 2330 | 5000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | #VALUE! |  | #VALUE! | 2020-11-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 4519305 | 2476 | 17.6 | PV & Battery | TBD | 2020-10-05 | 2020-10-15 | #VALUE! |  | #VALUE! | 2020-11-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Walpole | 4519566 | 2081 | 15.2 | PV | TBD | 2020-09-14 | 2020-10-15 | #VALUE! |  | #VALUE! | 2020-11-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Plympton | 4519678 | 2367 | 15.2 | PV | TBD | 2020-10-08 | 2020-10-16 | #VALUE! |  | #VALUE! | 2020-11-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 4529021 | 2021 | 166.5 | PV | 269-1321H2 | 2020-09-28 | 2020-09-28 | 0 |  | 0 | 2020-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-11-15 | Online |  | Private
NSTAR | Framingham | 4532766 | 1701 | 16.4 | PV | TBD | 2020-09-30 | 2020-11-02 | #VALUE! |  | #VALUE! | 2020-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Westwood | 4533474 | 2090 | 20 | PV & Battery | TBD | 2020-11-16 | 2020-11-18 | #VALUE! |  | #VALUE! | 2020-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-12 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 4534965 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | #VALUE! |  | #VALUE! | 2020-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | 4535505 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | #VALUE! |  | #VALUE! | 2020-12-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 4550665 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0
NSTAR | Boston | 4550829 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4551603 | 2120 | 43.2 | PV | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Assonett | 4556815 | 2702 | 15.2 | PV | TBD | 2020-10-15 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 4556854 | 1773 | 20 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Acusnet | 4556908 | 2743 | 500 | PV & Battery | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4556981 | 2740 | 999 | PV & Battery | TBD | 2020-10-27 | 2020-11-02 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-17
NSTAR | Woburn | 4557000 | 1801 | 57.6 | PV | TBD | 2020-10-27 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Sherborn | 4557126 | 1770 | 18.6 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4562972 | 2130 | 75 | CHP | TBD | 2020-11-02 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Dedham | 4575161 | 2026 | 4990 | PV & Battery | TBD | 2020-05-07 |  | #VALUE! |  | #VALUE! | 2020-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Norfolk | 4578744 | 2056 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | #VALUE! |  | #VALUE! | 2020-12-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | New Bedford | 4579621 | 2746 | 93.45 | PV | TBD | 2020-10-29 | 2020-11-10 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-13 | Online
NSTAR | Medfield | 4581063 | 2052 | 17.6 | PV | 456-H5 | 2020-09-18 | 2020-11-04 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-09-14 | Online
NSTAR | Bellingham | 4581275 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4581293 | 2067 | 15.2 | PV | TBD | 2020-11-06 | 2020-11-09 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Dartmouth | 4581517 | 2747 | 200 | PV | TBD | 2020-11-04 | 2020-11-06 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Newton | 4581647 | 2464 | 25 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Walpole | 4581720 | 2071 | 20 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0 |  |  | 2021-06-25 | Online
NSTAR | Westwood | 4581827 | 2090 | 20 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4582227 | 2451 | 7.6 | PV | TBD | 2020-10-29 | 2020-11-06 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | New Bedford | 4582294 | 2745 | 17.6 | PV & Battery | 2-104-104 | 2020-10-21 | 2020-11-09 | #VALUE! |  | #VALUE! | 2020-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-04-06 | Online
NSTAR | Medfield | 4589421 | 2052 | 200 | PV | TBD | 2020-10-27 | 2020-11-09 | #VALUE! |  | #VALUE! | 2020-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4590471 | 2740 | 20 | PV | TBD | 2020-11-09 | 2020-11-16 | #VALUE! |  | #VALUE! | 2020-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Walpole | 4590656 | 2081 | 10 | PV & Battery | 146-H3 | 2020-11-06 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4590784 | 2770 | 20 | PV | TBD | 2020-11-06 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Needham | 4590881 | 2494 | 17.36 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-07 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4590902 | 2743 | 61.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Newton | 4590939 | 2461 | 10 | PV & Battery | 292-01 | 2020-11-13 | 2020-11-16 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 4606031 | 1730 | 20 | PV & Battery | TBD | 2020-11-18 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 4606031 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | New Bedford | 4607301 | 2745 | 2125 | PV | TBD | 2020-11-18 | 2020-12-01 | #VALUE! |  | #VALUE! | 2020-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 4607939 | 1748 | 19.72 | PV | TBD | 2020-11-24 | 2020-12-01 | #VALUE! |  | #VALUE! | 2020-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-19 | Online
NSTAR | West Newton | 4610357 | 2465 | 17.6 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Maynard | 4614920 | 1754 | 86.4 | PV | TBD | 2020-11-13 | 2020-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29
NSTAR | Burlington | 4615024 | 1803 | 58.2 | PV | TBD | 2020-11-02 | 2020-11-18 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Holliston | 4615055 | 1746 | 19.8 | PV & Battery | TBD | 2020-11-18 | 2020-11-19 | #VALUE! |  | #VALUE! | 2020-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Dorchester | 4615111 | 2124 | 15.2 | PV | TBD | 2020-12-01 | 2020-12-07 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 4615145 | 2476 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | #VALUE! |  | #VALUE! | 2020-12-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online
NSTAR | North Dartmouth | 4615175 | 2747 | 35.2 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online
NSTAR | Sudbury | 4619003 | 1776 | 5 | Battery | 342-H4 | 2020-11-06 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4619474 | 1701 | 17.6 | PV & Battery | 278-H1 | 2020-11-09 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Framingham | 4619506 | 1702 | 205 | PV | TBD | 2020-11-18 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 4619563 | 1890 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Mattapoisett | 4619595 | 2739 | 2250 | PV & Battery | TBD | 2020-11-06 | 2020-11-25 | #VALUE! |  | #VALUE! | 2020-12-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4619617 | 2067 | 20 | PV & Battery | TBD | 2020-10-29 | 2020-11-25 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Sudbury | 4619695 | 1776 | 23.8 | PV & Battery | TBD | 2020-11-06 | 2020-11-24 | #VALUE! |  | #VALUE! | 2020-12-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4619716 | 2360 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4621310 | 2666 | 62.93 | PV | TBD | 2020-12-01 | 2020-12-07 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Online
NSTAR | Lexington | 4621352 | 2420 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-16 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Mashpee | 4632820 | 2649 | 13.8 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | South Dartmouth | 4632856 | 2748 | 43.92 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-15 | Online
NSTAR | Medfield | 4635189 | 2052 | 25 | PV & Battery | TBD | 2020-11-25 | 2020-12-14 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Stoneham | 4635296 | 2180 | 180 | PV | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 4635371 | 2090 | 20 | PV & Battery | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Westwood | 4636581 | 2090 | 25.2 | PV & Battery | TBD | 2020-11-25 | 2020-12-07 | #VALUE! |  | #VALUE! | 2020-12-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Needham | 4637344 | 2494 | 22.6 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Sharon | 4637394 | 2067 | 18.5 | PV | TBD | 2020-11-13 | 2020-11-18 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Manomet | 4637511 | 2345 | 17.4 | PV | TBD | 2020-11-13 | 2020-11-18 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Marshfield | 4637609 | 2050 | 13.8 | PV & Battery | 3-22-973 | 2020-10-29 |  | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Cambridge | 4637828 | 2140 | 75 | CHP | TBD | 2020-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15
NSTAR | Boston | 4637851 | 2135 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4637906 | 1701 | 250 | PV | TBD | 2020-11-25 | 2020-11-25 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4642133 | 2421 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-12-01 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | North Cambridge | 4642185 | 2140 | 19.57 | PV & Battery | TBD | 2020-11-06 | 2020-12-01 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | West Roxbury | 4642220 | 2132 | 15.2 | PV | TBD | 2020-11-25 | 2020-12-01 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 4642283 | 2459 | 28.8 | PV & Battery | 292-H6 | 2020-11-18 | 2020-12-07 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Somerville | 4642301 | 2145 | 201.6 | PV | TBD | 2020-12-01 | 2020-12-07 | #VALUE! |  | #VALUE! | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Millis | 4642384 | 2054 | 15.2 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Newton | 4658683 | 2459 | 15 | PV & Battery | 292-H11 | 2020-11-13 | 2020-11-24 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online
NSTAR | Truro | 4658780 | 2666 | 249.8 | PV | TBD | 2020-11-24 | 2020-11-24 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 4659394 | 2090 | 95.8 | PV | TBD | 2020-11-06 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Wareham | 4659423 | 2571 | 4980 | PV & Battery | TBD | 2020-12-07 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 4659441 | 1803 | 23.49 | PV | TBD | 2020-12-07 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Watertown | 4659469 | 2122 | 57.6 | PV | TBD | 2020-12-07 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Acton | 4659513 | 1720 | 4980 | PV & Battery | TBD | 2020-11-25 | 2020-12-15 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4661337 | 2030 | 20 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Weston | 4663199 | 2493 | 35.2 | PV & Battery | TBD | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Holliston | 4664449 | 1746 | 10 | Battery | TBD | 2020-11-16 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4664554 | 2030 | 19.84 | PV & Battery | 456-H5 | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4665887 | 1720 | 17.6 | PV & Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acton | 4668063 | 1720 | 25.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Winchester | 4668160 | 1890 | 25 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marion | 4668251 | 2738 | 22.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Marshfield | 4668327 | 2050 | 18 | PV | TBD | 2020-12-17 | 2020-12-17 | 0 |  | 0 | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4669412 | 2770 | 149.3 | PV | TBD | 2020-12-01 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 4675384 | 2364 | 499 | PV & Battery | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4676006 | 2180 | 150 | PV | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Wayland | 4676256 | 1778 | 20 | PV | TBD | 2020-11-25 | 2020-12-14 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Roslindale | 4677350 | 2131 | 18 | PV & Battery | 496-H8 | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 4680348 | 2124 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Online
NSTAR | Stoneham | 4680468 | 2180 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 4680531 | 1748 | 35.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 4680587 | 2186 | 16 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4680617 | 1770 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Hopkinton | 4683322 | 1748 | 20 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Waltham | 4683376 | 2451 | 166 | PV | TBD | 2020-12-14 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Mattapan | 4683605 | 2126 | 7.6 | PV | TBD | 2020-12-14 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-22 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4685975 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 4686146 | 2717 | 149.3 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4686399 | 2451 | 233 | PV | TBD | 2020-12-14 | 2020-12-22 | #VALUE! |  | #VALUE! | 2021-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 4696273 | 2793 | 2500 | PV & Battery | TBD | 2020-11-04 | 2020-11-25 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 4698222 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | South Dartmouth | 4698354 | 2748 | 15.2 | PV | TBD | 2020-12-14 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 4698431 | 1760 | 7.6 | PV | 240-H3 | 2020-12-14 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 4698540 | 2081 | 495 | PV | TBD | 2020-11-13 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4701003 | 2030 | 20.92 | PV | 456-H5 | 2020-12-14 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 4702589 | 2743 | 4990 | PV & Battery | TBD | 2020-12-17 | 2020-12-29 | #VALUE! |  | #VALUE! | 2021-01-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4706363 | 2330 | 248 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 4707682 | 2026 | 66.6 | PV | 20-H1 | 2020-12-01 | 2020-12-30 | #VALUE! |  | #VALUE! | 2021-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-20 | Online
NSTAR | Newton | 4708433 | 2459 | 66.6 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 4708506 | 2367 | 19 | PV | TBD | 2020-12-29 | 2020-12-30 | #VALUE! |  | #VALUE! | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4708532 | 2421 | 17.44 | PV & Battery | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4708871 | 1720 | 2495 | Battery | TBD | 2020-12-29 | 2020-12-29 | 0 |  | 0 | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4713423 | 2139 | 75 | CHP | 831-1394 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Holliston | 4713490 | 1746 | 20 | PV & Battery | TBD | 2020-07-29 | 2020-08-10 | #VALUE! |  | #VALUE! | 2020-08-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Lincoln | 4713513 | 1773 | 14 | Battery | 320-H8 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Medfield | 4714661 | 2052 | 250 | PV | TBD | 2020-08-14 |  | #VALUE! |  | #VALUE! | 2020-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4717011 | 2420 | 40 | PV & Battery | TBD | 2020-12-30 | 2020-12-31 | #VALUE! |  | #VALUE! | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4717656 | 2739 | 2496 | Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4832256 | 2492 | 16 | PV | TBD | 2020-12-22 | 2020-12-23 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Walpole | 4833200 | 2081 | 15.2 | PV | TBD | 2020-12-23 | 2020-12-23 | 0 |  | 0 | 2021-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4841015 | 2180 | 15.2 | PV | 375-H8 | 2020-12-29 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Stoneham | 4841178 | 2180 | 19 | PV | TBD | 2020-12-29 | 2021-01-06 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | Canton | 4849001 | 2021 | 53.2 | PV | TBD | 2021-01-04 | 2021-01-07 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Carver | 4849634 | 2330 | 72 | PV | TBD | 2020-12-30 | 2021-01-06 | #VALUE! |  | #VALUE! | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Milton | 4850213 | 2186 | 23.78 | PV | TBD | 2021-01-07 | 2021-01-07 | 0 |  | 0 | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 4850477 | 1776 | 35.2 | PV & Battery | TBD | 2020-12-24 | 2020-12-24 | 0 |  | 0 | 2021-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 4869494 | 2747 | 18.6 | PV | TBD | 2021-01-07 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Freetown | 4869709 | 2702 | 4999 | PV & Battery | TBD | 2020-12-30 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4869810 | 2492 | 17.04 | PV | TBD | 2020-12-31 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Rochester | 4869940 | 2770 | 250 | PV | TBD | 2020-12-31 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4869990 | 2360 | 110 | PV | TBD | 2020-12-31 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | South Dartmouth | 4870032 | 2748 | 18 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4874091 | 2420 | 25.2 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Carver | 4876930 | 2330 | 15.2 | PV | TBD | 2020-12-16 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | East Wareham | 4877705 | 2538 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Acton | 4878009 | 1720 | 20 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-23 | Online
NSTAR | West Somerville | 4878069 | 2144 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878172 | 2493 | 18 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878244 | 2393 | 21.4 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Newton | 4878336 | 2468 | 35.2 | PV & Battery | TBD | 2020-12-01 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-23 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Sudbury | 4878402 | 1776 | 20 | PV & Battery | TBD | 2021-01-11 | 2021-01-11 | 0 |  | 0 | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 4878461 | 1803 | 20 | PV & Battery | 391-H7 | 2020-12-14 | 2021-01-11 | #VALUE! |  | #VALUE! | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | North Acton | 4886788 | 1720 | 57.6 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Hyannis | 4886864 | 2601 | 7.6 | PV | 4-84A-520 | 2020-12-14 | 2021-01-12 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | East Walpole | 4886981 | 2032 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-12 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Westwood | 4887029 | 2090 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Westport | 4887097 | 2790 | 23.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 4887205 | 2649 | 52.78 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-10 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Plymouth | 4887324 | 2360 | 17.6 | PV & Battery | TBD | 2020-11-25 | 2021-01-12 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Waltham | 4887381 | 2451 | 466 | PV | TBD | 2020-12-31 | 2021-01-25 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-30 | Online
NSTAR | Wayland | 4894418 | 1778 | 16.78 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2022-05-16 | Online
NSTAR | Bedford | 4896010 | 1730 | 15.2 | PV | TBD | 2021-01-12 | 2021-01-14 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | East Freetown | 4896804 | 2717 | 25 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907766 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907809 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 4907860 | 2673 | 21.75 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Medway | 4920759 | 2053 | 29.5 | PV | TBD | 2020-12-30 | 2021-01-19 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Medway | 4920922 | 2053 | 19.75 | PV | TBD | 2020-12-30 | 2021-01-19 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4921183 | 2186 | 15.2 | PV | 311-04 | 2021-01-12 | 2021-01-19 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4921323 | 2770 | 25.2 | PV & Battery | TBD | 2020-12-14 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 4921387 | 2476 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-19 | #VALUE! |  | #VALUE! | 2021-02-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Sharon | 4921508 | 2067 | 13.8 | PV & Battery | TBD | 2020-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online
NSTAR | Hyannis | 4936393 | 2601 | 69.25 | PV | TBD | 2021-01-21 |  | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 4936614 | 2134 | 43.2 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4937121 | 1703 | 21.83 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Hyannis | 4945477 | 2601 | 86.6 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Online
NSTAR | Hyannis | 4945583 | 2601 | 120 | PV | TBD | 2021-01-12 | 2021-01-21 | #VALUE! |  | #VALUE! | 2021-02-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Mashpee | 4962795 | 2649 | 495 | PV | TBD | 2021-01-21 | 2021-01-26 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4963253 | 2666 | 17.68 | battery | TBD | 2021-01-21 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Duxbury | 4963456 | 2332 | 25.2 | PV | TBD | 2021-01-21 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4963535 | 1770 | 15.2 | PV & Battery | TBD | 2020-11-24 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 4963768 | 2360 | 20 | PV & Battery | TBD | 2020-12-01 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Walpole | 4963817 | 2081 | 10 | PV & Battery | TBD | 2020-12-14 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-18 | Online
NSTAR | Marston Mills | 4971708 | 2648 | 11.6 | Battery | TBD | 2021-01-21 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 4972029 | 1778 | 10 | Battery | TBD | 2021-01-27 | 2021-01-28 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Acton | 4972089 | 1720 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-01-27 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 4972223 | 2747 | 200 | PV | TBD | 2021-03-02 | 2021-03-02 | 0 |  | 0 | 2021-03-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 4983194 | 2601 | 51.9 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4983372 | 2186 | 15.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Hyannis | 4983604 | 2601 | 90 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Sudbury | 4983699 | 1776 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4983727 | 2067 | 16.48 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Bourne | 4991635 | 2532 | 19.9 | PV | TBD | 2021-01-21 | 2021-01-26 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | New Bedford | 4991678 | 2740 | 15.2 | PV | TBD | 2021-01-06 | 2021-01-26 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 4999717 | 2645 | 213.2 | PV | TBD | 2021-01-12 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Kingston | 5000850 | 2364 | 250 | PV | TBD | 2021-01-14 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-02-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Carver | 5001002 | 2330 | 1992 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Carver | 5016871 | 2366 | 23.8 | PV & Battery | TBD | 2021-01-25 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5017076 | 2474 | 19 | Battery | TBD | 2021-01-21 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | Carlisle | 5017153 | 1741 | 35.2 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 5018578 | 2601 | 120 | PV | TBD | 2021-01-21 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Holliston | 5025553 | 1746 | 120 | PV | TBD | 2020-12-31 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | Canton | 5057342 | 2021 | 7.6 | PV | TBD | 2021-01-27 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Yarmouth | 5057452 | 2673 | 188 | PV | TBD | 2021-01-27 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5057606 | 2420 | 20 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Lexington | 5058397 | 2421 | 20 | PV & Battery | TBD | 2020-11-06 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online
NSTAR | West Barnstable | 5058535 | 2668 | 20.88 | PV | TBD | 2021-02-05 | 2021-02-05 | 0 |  | 0 | 2021-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Kingston | 5077570 | 2364 | 22.8 | PV & Battery | TBD | 2021-01-21 | 2021-02-08 | #VALUE! |  | #VALUE! | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5077813 | 2492 | 10 | Battery | TBD | 2021-02-05 | 2021-02-08 | #VALUE! |  | #VALUE! | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5077946 | 1722 | 466.6 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5077981 | 1722 | 233.2 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078034 | 1722 | 200 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078087 | 1722 | 100 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087787 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087888 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087946 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088024 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088121 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088220 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088274 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088314 | 1720 | 500 | PV | TBD | 2020-12-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097801 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097909 | 1720 | 1000 | PV & Battery | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 5099394 | 1801 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Hopkinton | 5099581 | 1848 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Westwood | 5099732 | 2090 | 15.2 | PV | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0
NSTAR | Pocasset | 5099887 | 2559 | 20 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acton | 5103412 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5112763 | 1748 | 166.6 | PV | TBD | 2021-02-10 | 2021-02-10 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marston Mills | 5113061 | 2648 | 433 | PV | TBD | 2021-01-06 | 2021-02-10 | #VALUE! |  | #VALUE! | 2021-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marston Mills | 5113167 | 2648 | 500 | PV | TBD | 2021-01-06 | 2021-02-10 | #VALUE! |  | #VALUE! | 2021-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 5113369 | 2743 | 17.6 | PV & Battery | TBD | 2020-12-17 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Winchester | 5113444 | 1890 | 18 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Weston | 5113544 | 2493 | 33.8 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 5113610 | 1701 | 35.2 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5113674 | 1721 | 22.6 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Wayland | 5113728 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 5113853 | 2021 | 18 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2021-04-20 | [6 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Carver | 5114629 | 2330 | 5000 | PV & Battery | TBD | 2020-11-25 | 2021-01-25 | #VALUE! |  | #VALUE! | 2021-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5122500 | 2420 | 30.2 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Ashland | 5122724 | 1721 | 250 | PV | TBD | 2021-02-08 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5122828 | 1746 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 5123008 | 2330 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 5123184 | 2050 | 2000 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 5123430 | 2054 | 5000 | PV & Battery | TBD | 2020-12-31 | 2021-01-25 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5123449 | 1748 | 100 | PV | TBD | 2021-01-19 | 2021-01-20 | #VALUE! |  | #VALUE! | 2021-03-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Holliston | 5131879 | 1746 | 150 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5131937 | 1721 | 200 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5132026 | 1746 | 466.6 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 5132026 | [7 empty] | 0 |  | 0 |  |  | 2022-08-03 | Online
NSTAR | East Wareham | 5132131 | 2538 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 5132174 | 2719 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 5132265 | 2452 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 5132388 | 2645 | 20 | Battery | TBD | 2021-02-08 | 2021-02-17 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Carver | 5132501 | 2330 | 3000 | PV & Battery | 3-81-81 | 2018-10-04 | 2018-10-11 | #VALUE! |  | #VALUE! | 2018-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Sharon | 5132549 | 2067 | 30 | PV & Battery | TBD | 2020-10-15 | 2021-02-17 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 5140433 | 1746 | 100 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140517 | 1746 | 133.2 | PV | TBD | 2021-02-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140889 | 1746 | 150 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5141509 | 1720 | 1125 | PV & Battery | TBD | 2020-12-31 | 2021-02-05 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5141690 | 2717 | 25 | PV | TBD | 2020-12-30 | 2021-02-10 | #VALUE! |  | #VALUE! | 2021-03-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-27 | Online
NSTAR | Brewster | 5149756 | 2601 | 13.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-08 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-20 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5149891 | 1720 | 84 | PV | TBD | 2021-02-10 | 2021-02-19 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-05 | Online
NSTAR | Lexington | 5149929 | 2421 | 19.86 | battery | TBD | 2021-02-19 | 2021-02-19 | 0 |  | 0 | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online
NSTAR | Natick | 5158094 | 1760 | 26.4 | PV & Battery | TBD | 2021-02-19 | 2021-03-01 | #VALUE! |  | #VALUE! | 2021-03-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Watertown | 5164450 | 2472 | 66.6 | PV | TBD | 2021-02-17 | 2021-02-22 | #VALUE! |  | #VALUE! | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-01 | Online
NSTAR | Wayland | 5164657 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Sudbury | 5164789 | 1776 | 36 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 5164886 | 2492 | 19.84 | battery | TBD | 2021-02-18 | 2021-02-23 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-26 | Online
NSTAR | Ashland | 5174138 | 1721 | 199.8 | PV | TBD | 2021-02-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-06 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marshfield | 5174339 | 2050 | 172 | PV | TBD | 2021-02-17 | 2021-02-23 | #VALUE! |  | #VALUE! | 2021-03-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01
NSTAR | Orleans | 5174743 | 2653 | 18.32 | PV & Battery | TBD | 2021-02-18 | 2021-02-23 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | North Chatham | 5174898 | 2650 | 17.6 | battery | TBD | 2021-02-23 | 2021-02-25 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | East Falmouth | 5184793 | 2536 | 22.32 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5184938 | 2367 | 233.2 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-22 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 5193836 | 2332 | 19.5 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | #VALUE! |  | #VALUE! | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Mattapoisett | 5193909 | 2739 | 148.92 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 5202637 | 2653 | 262.5 | Fuel Cell | TBD | 2021-02-26 | 2021-02-26 | 0 |  | 0 | 2021-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Sharon | 5215247 | 2067 | 30.2 | PV & Battery | TBD | 2020-12-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Harwich | 5233905 | 2645 | 72 | Wind | TBD | 2020-01-22 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-03-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5233972 | 2673 | 187.5 | PV & Battery | TBD | 2021-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5243395 | 2664 | 5325 | PV & Battery | TBD | 2021-02-17 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5243558 | 2360 | 1519.1 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5243871 | 2021 | 499 | PV & Battery | TBD | 2020-12-30 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5244434 | 1754 | 495.3 | PV | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 5247195 | 2670 | 5 | battery | TBD | 2021-02-17 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5247213 | 1760 | 17.6 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Weston | 5247231 | 2493 | 35.2 | PV | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5247359 | 2673 | 17.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Online
NSTAR | New Bedford | 5256352 | 2745 | 445 | PV | TBD | 2021-02-18 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0
NSTAR | Harwich | 5256465 | 2645 | 255 | PV | TBD | 2021-02-18 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5256556 | 1754 | 774.3 | PV | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 5256604 | 1754 | 1400.5 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Walpole | 5256722 | 2032 | 15.2 | PV | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Marion | 5256768 | 2738 | 25.2 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 5256844 | 2135 | 43.2 | PV | TBD | 2021-02-03 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Natick | 5273003 | 1760 | 19.86 | Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Orleans | 5273198 | 2643 | 17.4 | PV | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5273453 | 1720 | 30.2 | PV & Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5273636 | 2021 | 20 | PV & Battery | TBD | 2021-03-02 | 2021-03-08 | #VALUE! |  | #VALUE! | 2021-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Online
NSTAR | Lincoln | 5273781 | 2748 | 15.2 | PV | TBD | 2021-03-09 | 2021-03-09 | 0 |  | 0 | 2021-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Dartmouth | 5273833 | 2748 | 15 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | #VALUE! |  | #VALUE! | 2021-03-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sharon | 5286859 | 2067 | 15.2 | PV | TBD | 2020-10-15 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 5287061 | 2130 | 18 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 5287511 | 2366 | 19.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 5287647 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 5298461 | 2474 | 17.68 | Battery | TBD | 2021-03-02 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Online
NSTAR | Wellfleet | 5298773 | 2663 | 18.16 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5299014 | 2538 | 19 | PV | TBD | 2021-02-19 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-11-12 | Online
NSTAR | West Tisbury | 5299167 | 2575 | 16.225 | PV | TBD | 2021-03-02 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | New Bedford | 5299345 | 2740 | 120 | PV | TBD | 2021-02-25 | 2021-03-10 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Onset | 5308165 | 2053 | 33.3 | PV | TBD | 2021-02-12 | 2021-02-24 | #VALUE! |  | #VALUE! | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Online
NSTAR | Arlington | 5308545 | 2474 | 4.93 | PV | TBD | 2021-02-23 | 2021-02-23 | 0 |  | 0 | 2021-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5317803 | 1803 | 35.2 | PV & Battery | TBD | 2020-12-14 | 2021-03-12 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0
NSTAR | Chestnut Hill | 5333163 | 2467 | 100.8 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-20 | Online
NSTAR | West Barnstable | 5333489 | 2668 | 450 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5333657 | 2494 | 86.4 | PV | TBD | 2021-01-27 | 2021-03-15 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-31 | Online
NSTAR | Chestnut Hill | 5333799 | 2467 | 86.4 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5333868 | 2673 | 999 | PV & Battery | TBD | 2021-03-02 | 2021-03-15 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 5343412 | 1776 | 400 | PV | TBD | 2021-03-16 | 2021-03-15 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0
NSTAR | Milton | 5343599 | 2364 | 125 | PV | TBD | 2021-02-25 | 2021-03-16 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Natick | 5343911 | 1760 | 10 | Battery | TBD | 2021-03-12 | 2021-03-16 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online
NSTAR | Hatchville | 5344212 | 2536 | 44.98 | PV | TBD | 2021-03-15 | 2021-03-17 | #VALUE! |  | #VALUE! | 2021-03-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Needham | 5354359 | 2492 | 20 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-01 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5354616 | 1860 | 17.6 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Hopkinton | 5354874 | 1748 | 240 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 5354925 | 1748 | 233.2 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online
NSTAR | Marston Mills | 5355181 | 2648 | 19.84 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online
NSTAR | Needham | 5355247 | 2492 | 24.86 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 5355312 | 2744 | 480 | PV | 2-7-7 | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | 2018-10-10 | [6 empty] | 0 |  | 0 | [5 empty] | Private
NSTAR | Acton | 5367340 | 1720 | 199.8 | PV | TBD | 2021-03-02 | 2021-03-19 | #VALUE! |  | #VALUE! | 2021-04-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377708 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | #VALUE! |  | #VALUE! | 2021-04-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377796 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | #VALUE! |  | #VALUE! | 2021-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dartmouth | 5392200 | 2748 | 21.4 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 5392364 | 2649 | 17.6 | PV & Battery | TBD | 2021-03-12 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 5392588 | 2136 | 16 | PV | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 5392648 | 2125 | 15.2 | PV | TBD | 2021-02-12 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-10 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 5392760 | 2067 | 250 | PV | TBD | 2021-03-16 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 5392843 | 2026 | 250 | PV | TBD | 2021-03-17 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0
NSTAR | Newton | 5392881 | 2459 | 19.84 | PV & Battery | TBD | 2021-03-17 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Vineyard Haven | 5392988 | 2568 | 16.26 | PV & Battery | TBD | 2021-03-15 | 2021-03-22 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | Framingham | 5393050 | 1701 | 10 | Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5393125 | 2360 | 499 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393165 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393188 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5402282 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403022 | 2420 | 250 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403190 | 2420 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403580 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403662 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403782 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | #VALUE! |  | #VALUE! | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 5403892 | 1803 | 52.2 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 5404047 | 2461 | 158.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online
NSTAR | Newton | 5404188 | 2461 | 86.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 5414087 | 2360 | 1366.4 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | #VALUE! |  | #VALUE! | 2021-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5415234 | 2717 | 1000 | PV & Battery | 2-102-608 | 2016-12-14 | 2016-12-27 | #VALUE! |  | #VALUE! | 2017-01-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-05-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-28 | Online
NSTAR | Marston Mills | 5447070 | 2648 | 15.2 | PV | TBD | 2021-03-17 | 2021-03-29 | #VALUE! |  | #VALUE! | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5447224 | 1760 | 16.24 | PV | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5447287 | 1803 | 17.6 | Battery | TBD | 2021-03-17 | 2021-03-29 | #VALUE! |  | #VALUE! | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 5447348 | 2748 | 27.28 | PV & Battery | TBD | 2021-03-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Plymouth | 5447376 | 2360 | 747 | PV & Battery | TBD | 2021-03-05 | 2021-03-29 | #VALUE! |  | #VALUE! | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-10 | [7 empty] | 0 |  | 0
NSTAR | Centerville | 5447504 | 2632 | 15.68 | Battery | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brookline | 5447826 | 2445 | 25 | PV & Battery | TBD | 2020-12-16 | 2021-03-29 | #VALUE! |  | #VALUE! | 2021-04-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0
NSTAR | East Walpole | 5483759 | 2032 | 26.4 | PV & Battery | TBD | 2021-03-29 | 2021-04-01 | #VALUE! |  | #VALUE! | 2021-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5483849 | 2538 | 21.4 | PV | TBD | 2021-03-29 | 2021-04-01 | #VALUE! |  | #VALUE! | 2021-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-21 | Online
NSTAR | Hyannis | 5483911 | 2601 | 400 | PV | TBD | 2021-03-16 | 2021-04-01 | #VALUE! |  | #VALUE! | 2021-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5483954 | 2673 | 160 | PV | TBD | 2021-03-16 | 2021-04-01 | #VALUE! |  | #VALUE! | 2021-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Hyannisport | 5518451 | 2678 | 28 | Battery | TBD | 2021-04-09 | 2021-04-09 | 0 |  | 0 | 2021-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Plymouth | 5518643 | 2360 | 25 | PV & Battery | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Falmouth | 5518931 | 2540 | 27.6 | PV & Battery | TBD | 2021-01-26 | 2021-03-19 | #VALUE! |  | #VALUE! | 2021-04-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 5530688 | 2130 | 199.8 | PV | TBD | 2020-07-01 | 2021-04-06 | #VALUE! |  | #VALUE! | 2021-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | Somerville | 5540752 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-15 | #VALUE! |  | #VALUE! | 2021-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 5566155 | 1748 | 1000 | PV | TBD | 2021-03-17 | 2021-04-13 | #VALUE! |  | #VALUE! | 2021-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 5577223 | 2026 | 86.4 | PV | TBD | 2021-02-25 | 2021-04-12 | #VALUE! |  | #VALUE! | 2021-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Framingham | 5587228 | 1702 | 167.32 | PV | TBD | 2021-04-13 | 2021-04-14 | #VALUE! |  | #VALUE! | 2021-04-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1932-09-13 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 5608635 | 2081 | 15.2 | PV | TBD | 2020-09-08 | 2021-04-16 | #VALUE! |  | #VALUE! | 2021-05-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 5758561 | 2660 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-05-04 | #VALUE! |  | #VALUE! | 2021-05-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5758591 | 2367 | 742 | PV & Battery | TBD | 2021-02-25 | 2021-05-04 | #VALUE! |  | #VALUE! | 2021-05-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 5813985 | 2633 | 100.8 | PV & Battery | TBD | 2020-08-19 | 2021-05-14 | #VALUE! |  | #VALUE! | 2021-05-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5913979 | 2476 | 16 | Battery | TBD | 2020-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Hatchville | 9568068 | 2536 | 4000 | PV & Battery |  | 2020-08-19 | 2020-08-24 | #VALUE! | 0 | #VALUE! | 2020-09-16 |  | #VALUE! | 0 | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
NSTAR | Kingston | 23815557 | 2364 | 19.27 | PV | 3-17-910 | 2019-12-05 | 2019-12-10 | #VALUE! |  | #VALUE! | 2020-01-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 2065453a | 2367 | 1000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | #VALUE! |  | #VALUE! | 2015-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
NSTAR | Plympton | 2065453b | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | #VALUE! |  | #VALUE! | 2015-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
NSTAR | Plympton | 2065453c | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | #VALUE! |  | #VALUE! | 2015-07-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
NSTAR | Canton | 2093030b | 2021 | 990 | PV | 470-H7 | 2015-08-31 | 2015-09-04 | #VALUE! |  | #VALUE! | 2015-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  |  | Cust Docs
NSTAR | Plymouth | 2155/2249 | 2360 | 4750 | PV | 3-89-89 | 2012-06-20 | 2012-07-09 | #VALUE! | 4 | #VALUE! | 2012-07-18 | 2012-08-27 | #VALUE! | 0 | #VALUE! |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-28 |  | 2012-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-02 | Online |  | Gov't | Y
NSTAR | Freetown | 2238661 - A | 2717 | 4090 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2238661 - B | 2717 | 4990 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Rochester | 2260703 - A | 2770 | 2000 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | #VALUE! |  | #VALUE! | 2018-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-30
NSTAR | Rochester | 2260703 - B | 2770 | 540 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | #VALUE! |  | #VALUE! | 2018-01-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! | 2018-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! | 2018-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! | 2018-07-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2287285-B | 2125 | 500 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | #VALUE! |  | #VALUE! | 2018-07-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2287856-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-D | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-E | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-F | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-G | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-H | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2292181 - A | 2330 | 2000 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2292181 - B | 2330 | 466 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | #VALUE! |  | #VALUE! | 2018-08-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 & 2334854 | 2745 | 695.6 | PV | TBD | 2019-03-25 | 2020-03-29 | #VALUE! |  | #VALUE! | 2020-04-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 24-9982 | 1701 | 22 | PV & Battery | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | ISO NE | 2770 | 15000 | PV & Battery | 3-703-703 | 2018-12-18 | 2018-12-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | MULTIPLE WOS | 2081 | 2167.6 | PV | 146-H4 | 2019-01-14 | 2019-03-28 | #VALUE! |  | #VALUE! | 2019-04-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | pp02295853 | 2770 | 2000 | PV & Battery | 3-85-85 | 2021-01-17 | 2021-01-17 | 0 |  | 0 | 2021-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | PP02407747 | 2601 | 19.92 | PV | TBD | 2020-10-15 | 2020-11-12 | #VALUE! |  | #VALUE! | 2021-01-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Provincetown | TBD | 2657 | 28.13 | PV | TBD | 2019-08-06 | 2019-08-08 | #VALUE! |  | #VALUE! | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2019-01-06 | Online
NSTAR | Ashland | TBD | 1721 | 4450 | PV | TBD | 2017-05-08 | 2017-05-25 | #VALUE! |  | #VALUE! | 2017-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Dedham | TBD | 2026 | 20 | PV | TBD | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Lincoln | TBD | 1773 | 109.6 | PV & Battery | 416-H1 | 2018-01-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-16 | 2018-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-23 | 2018-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 27.48 | PV & Battery | 416-H1 | 2018-02-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 15 | PV & Battery | 416-H1 | 2018-02-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Weston | TBD | 2493 | 21.6 | PV & Battery | 416-H1 | 2018-02-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Provincetown | TBD | 2657 | 10 | PV & Battery | 4-96-675 | 2018-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rcohester | TBD | 2770 | 22.6 | PV & Battery | 3-702-702 | 2018-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 18.35 | PV & Battery | 416-H1 | 2018-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Darmouth | TBD | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 8300 | PV & Battery | 416-H1 | 2018-03-01 | 2018-03-14 | #VALUE! |  | #VALUE! | 2018-04-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | TBD | 1773 | 17.6 | PV & Battery | 416-H1 | 2018-03-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 153.2 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 196.6 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | TBD | 2472 | 166.5 | PV | 467-H6 | 2018-03-29 | 2018-03-29 | 0 |  | 0 | 2018-04-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 10 | PV & Battery | 2-241-241 | 2018-04-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 9878 | PV & Battery | 416-H1 | 2018-04-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | TBD | 2122 | 64 | PV | 416-H1 | 2018-04-12 | 2018-04-27 | #VALUE! |  | #VALUE! | 2018-05-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2538 | 7.6 | PV | 416-H1 | 2018-04-19 |  | #VALUE! |  | #VALUE! | 2018-04-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 5 | PV | 342-H4 | 2018-04-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | TBD | 2770 | 4200 | PV & Battery | 4-80B-514 | 2018-04-30 | 2018-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Yarmouth | TBD | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV | 416-H1 | 2018-05-18 | 2018-05-30 | #VALUE! |  | #VALUE! | 2018-06-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 995 | PV & Battery | 416-H1 | 2018-05-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 300 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 660 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 360 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 4000 | PV | 4-80B-514 | 2018-07-18 | 2018-07-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 685 | PV | 2-41-41 | 2018-08-06 | 2018-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2142 | 63.3 | PV | 416-H1 | 2018-09-24 | 2018-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 143.2 | PV | TBD | 2019-01-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennis | TBD | 2660 | 4951 | PV | TBD | 2019-01-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 43.2 | PV | TBD | 2019-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4980 | PV & Battery | TBD | 2019-02-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2492 | 23.5 | PV | TBD | 2019-02-12 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 81 | PV | TBD | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-02-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 699.9 | PV | TBD | 2019-03-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.485 | PV | TBD | 2019-03-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | TBD | 2739 | 5000 | PV | TBD | 2019-03-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2702 | 4500 | PV & Battery | tbd | 2019-04-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2745 | 5000 | PV | TBD | 2019-04-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2138 | 66.6 | PV | TBD | 2019-05-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Newton | TBD | 2465 | 20 | PV & Battery | TBD | 2019-05-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 25.2 | PV & Battery | TBD | 2019-06-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | TBD | 1803 | 15.2 | PV | TBD | 2019-08-01 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | TBD | 2710 | 100 | PV | TBD | 2019-08-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 25.2 | PV | TBD | 2019-08-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | TBD | 2666 | 16.4 | PV | TBD | 2019-08-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4000 | PV & Battery | TBD | 2019-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 998 | PV | TBD | 2019-10-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 15.2 | PV | TBD | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | 15.2 | PV | TBD | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 15.2 | PV | TBD | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | TBD | 2067 | 15.2 | PV | TBD | 2019-10-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 15.2 | PV | TBD | 2019-10-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.2 | PV | TBD | 2019-10-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 19 | PV | TBD | 2019-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 180.96 | PV | TBD | 2019-11-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Onset | TBD | 2558 | 25 | PV & Battery | TBD | 2019-11-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 2000 | PV & Battery | TBD | 2019-12-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 19.27 | PV | TBD | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 330 | PV | TBD | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2494 | 3623 | PV | TBD | 2019-12-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | TBD | 2453 | 748 | PV | TBD | 2019-12-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 15.2 | PV | TBD | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | TBD | 2421 | 130 | PV | TBD | 2019-12-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Walpole | TBD | 2032 | 23.8 | PV | TBD | 2019-12-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 | 2019-12-23 | #VALUE! |  | #VALUE! | 2020-01-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2130 | 37.8 | PV | TBD | 2020-01-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2120 | 200 | PV | TBD | 2020-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Falmouth | TBD | 2556 | 15.2 | PV | TBD | 2020-01-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 1500 | PV & Battery | TBD | 2020-01-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 6 | PV | TBD | 2020-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 20 | Battery | TBD | 2020-01-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 14 | Battery | TBD | 2020-01-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | TBD | 2081 | 16 | PV | TBD | 2020-02-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2714 | 2958 | Battery | TBD | 2020-02-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | TBD | 1778 | 29 | Battery | TBD | 2020-02-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 15.2 | PV | TBD | 2020-02-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | TBD | 2649 | 153.85 | PV | TBD | 2020-03-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | TBD | 2026 | 108.375 | PV | TBD | 2020-03-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sagamore Beach | TBD | 2561 | 150.45 | PV | TBD | 2020-03-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | - | PV | TBD | 2020-03-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 8.5 | PV | TBD | 2020-03-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | TBD | 2645 | 175.9 | PV | TBD | 2020-03-25 | 2020-05-15 | #VALUE! |  | #VALUE! | 2020-06-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 9999 | PV & Battery | TBD | 2020-04-09 | 2020-04-15 | #VALUE! |  | #VALUE! | 2020-04-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 400 | PV | TBD | 2020-04-09 | 2020-04-17 | #VALUE! |  | #VALUE! | 2020-05-04 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 999 | PV & Battery | TBD | 2020-04-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 15.2 | PV | TBD | 2020-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 90 | Battery | TBD | 2020-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 15.2 | PV | TBD | 2020-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 5000 | PV & Battery | TBD | 2020-05-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | TBD | 2019 | 4990 | PV & Battery | TBD | 2020-06-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 499 | PV & Battery | TBD | 2020-06-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | TBD | 2030 | 15.2 | PV | TBD | 2020-07-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 573 | PV & Battery | TBD | 2020-07-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 610 | Battery | TBD | 2020-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Aquinnah | TBD | 2635 | 144.8 | PV & Battery | TBD | 2020-08-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | TBD | 1770 | 39 | PV & Battery | TBD | 2020-08-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 4000 | PV & Battery | TBD | 2020-09-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 2875 | PV | TBD | 2020-09-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2740 | 250 | PV | TBD | 2020-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 200 | PV | TBD | 2020-10-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 5 | battery | TBD | 2020-11-06 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 20.5 | Battery | TBD | 2020-11-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 16.19 | PV | TBD | 2020-11-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 149.3 | PV | TBD | 2020-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 17.6 | PV & Battery | TBD | 2020-12-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 15.2 | PV | TBD | 2020-12-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | TBD | 1757 | 180 | PV | TBD | 2021-01-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 18.5 | PV | TBD | 2021-01-21 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 3000 | PV & Battery | TBD | 2021-01-27 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 15 | PV | TBD | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | TBD | 2021 | 16 | PV | TBD | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 2000 | PV | TBD | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 4990 | PV & Battery | TBD | 2021-02-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2144 | 170.4 | PV | TBD | 2021-02-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Centerville | TBD | 2632 | 15.2 | PV | TBD | 2021-02-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 15 | PV | TBD | 2021-03-02 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Auburndale | TBD | 2466 | 10 | Battery | TBD | 2021-03-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 500 | PV | TBD | 2021-03-19 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 1500 | PV | TBD | 2021-03-29 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | ESMAEX-00027 | 02719 | 300 | Battery | 2-221-221 | 2021-04-02 | 2021-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-11 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-00028 | 02719 | 223 | Battery | 2-220-206 | 2021-04-02 | 2021-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Newton Highlands | ESMAEX-00002 | 02461 | 7.68 | Battery | 292-H14 | 2021-03-29 | 2021-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-11 | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-00097 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00034 | 02021 | 250 | Solar | 470-H11 | 2021-04-07 | 2021-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-26 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00010 | 02421 | 420 | Solar | 320-H5XY | 2021-03-30 | 2021-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00009 | 02745 | 73.3 | Solar | 2-104-104 | 2021-03-30 | 2021-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-00063 | 02738 | 21.21 | Solar & Battery | 3-85-85 | 2021-04-21 | 2021-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00166 | 02360 | 8.7 | Solar | 3-90-90 | 2021-06-04 | 2021-07-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Application Completed/Closed | Online
NSTAR | South Sandwich | ESMAEX-00143 | 02563 | 10 | Battery | 4-455-455 | 2021-05-20 | 2021-06-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Application Completed/Closed | Online
NSTAR | Newton Highlands | ESMAEX-00023 | 02461 | 18.88 | Solar & Battery | 292-H5 | 2021-04-02 | 2021-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0 |  |  | 2022-01-04 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00020 | 02081 | 20 | Solar & Battery | 146-H4 | 2021-04-01 | 2021-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-09 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-00425 | 02739 | 79.75 | Solar | 2-304-304 | 2021-09-20 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-14 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-00030 | 02135 | 150 | Internal Combustion Engine | 467-H12 | 2021-04-06 | 2021-05-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00049 | 02745 | 166.6 | Solar | 2-82-82 | 2021-04-14 | 2021-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-19 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00032 | 01720 | 3800 | Solar & Battery | 416-H8 | 2021-04-07 | 2021-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Upload Technical Documents Customer Action Required | Technical Review
NSTAR | Needham | ESMAEX-00041 | 02494 | 250 | Solar | 148-H7 | 2021-04-13 | 2021-05-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Application Completed/Closed | Online
NSTAR | South Yarmouth | ESMAEX-00060 | 02664 | 250 | Battery |  | 2021-04-19 | 2021-05-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-00065 | 02130 | 30 | Solar |  | 2021-04-21 | 2021-05-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-00058 | 01746 | 133.2 | Solar | 65-H2 | 2021-04-16 | 2021-05-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-12-07 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00053 | 02740 | 100 | Solar | 2-42-42 | 2021-04-14 | 2021-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Application Completed/Closed | Online
NSTAR | Bourne | ESMAEX-00059 | 02532 | 499 | Solar & Battery | 4-86-86 | 2021-04-16 | 2021-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Waquoit | ESMAEX-00367 | 02536 | 20 | Solar & Battery | 4-77B-456 | 2021-08-27 | 2021-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Application Completed/Closed | Online
NSTAR | South Sandwich | ESMAEX-00055 | 02563 | 250 | Solar | 4-87A-87A | 2021-04-14 | 2021-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-00096 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-00073 | 02642 | 18.41 | Solar & Battery | 4-94A-648 | 2021-04-23 | 2021-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00062 | 02740 | 16.57 | Solar & Battery | 2-531-531 | 2021-04-20 | 2021-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2021-11-10 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00071 | 01720 | 16.23 | Solar | 416-H9 | 2021-04-23 | 2021-05-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-00070 | 02633 | 22 | Solar & Battery | 4-95B-941 | 2021-04-22 | 2021-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-00081 | 02367 | 999 | Solar & Battery | 3-15-15 | 2021-04-28 | 2021-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | East Freetown | ESMAEX-00079 | 02717 | 69.2 | Solar | 2-102-102 | 2021-04-28 | 2021-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-00080 | 02717 | 69.2 | Solar | 2-102-604 | 2021-04-28 | 2021-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-00082 | 01801 | 17.4 | Solar | 533-H9 | 2021-04-28 | 2021-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-00101 | 01746 | 140 | Solar | 65-H2 | 2021-05-05 | 2021-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-18 | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-00276 | 02642 | 20 | Solar & Battery | 4-94A-648 | 2021-07-30 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00132 | 02540 | 5 | Solar | 4-76-436 | 2021-05-18 | 2021-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Application Completed/Closed | Online
NSTAR | West Falmouth | ESMAEX-00109 | 02574 | 17.772 | Solar & Battery | 4-98A-98A | 2021-05-07 | 2021-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2021-11-15 | Application Completed/Closed | Online
NSTAR | Harwich | ESMAEX-00094 | 02645 | 499 | Solar & Battery | 4-95A-599 | 2021-05-03 | 2021-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Waltham | ESMAEX-00098 | 02451 | 1994 | Internal Combustion Engine | 526-1361H | 2021-05-03 | 2021-05-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Application Completed/Closed | Online
NSTAR | East Harwich | ESMAEX-00111 | 02645 | 20 | Battery | 4-95A-95A | 2021-05-10 | 2021-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Application Completed/Closed | Online
NSTAR | North Cambridge | ESMAEX-00182 | 02140 | 22.8 | Solar | 824-25 | 2021-06-13 | 2021-06-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-00102 | 02747 | 86.4 | Solar | 2-533-503 | 2021-05-05 | 2021-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-00104 | 02790 | 20 | Solar | 2-532-532 | 2021-05-05 | 2021-06-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00121 | 02492 | 18.56 | Solar | 148-H7 | 2021-05-13 | 2021-05-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-02 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00105 | 01701 | 16 | Solar | 342-H4 | 2021-05-05 | 2021-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00122 | 01760 | 251.3 | Solar | 433-H12 | 2021-05-13 | 2021-05-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-00108 | 02124 | 15.2 | Solar | 496-H8 | 2021-05-06 | 2021-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00113 | 02451 | 3012 | Internal Combustion Engine | 531-1359H | 2021-05-10 | 2021-06-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brighton | ESMAEX-00117 | 02135 | 100 | Solar | 329-H6 | 2021-05-11 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Application Completed/Closed | Online
NSTAR | South Boston | ESMAEX-00116 | 02127 | 100 | Solar | 385-H1 | 2021-05-11 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00119 | 02468 | 10 | Battery | 292-H2 | 2021-05-13 | 2021-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-01 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00129 | 02050 | 499 | Solar & Battery | 3-24B-915 | 2021-05-17 | 2021-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Arlington | ESMAEX-00151 | 02476 | 20 | Solar | 320-H7 | 2021-05-27 | 2021-06-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-00138 | 02633 | 10.15 | Solar | 4-95B-941 | 2021-05-19 | 2021-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-27 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00124 | 02540 | 36.54 | Solar | 4-72-72 | 2021-05-15 | 2021-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-00142 | 02493 | 20 | Solar & Battery | 282-H1 | 2021-05-20 | 2021-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-00148 | 01721 | 75 | Solar | 274-H1 | 2021-05-24 | 2021-06-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00139 | 02468 | 15 | Solar & Battery | 292-H7 | 2021-05-19 | 2021-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-00141 | 01801 | 20 | Solar & Battery | 391-H11 | 2021-05-20 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Application Completed/Closed | Online
NSTAR | Forestdale | ESMAEX-00149 | 02644 | 20 | Solar & Battery | 4-81B-443 | 2021-05-25 | 2021-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00145 | 01748 | 250 | Solar | 126-H1 | 2021-05-21 | 2021-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-03 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-00380 | 01801 | 216 | Solar | 375-H6 | 2021-09-02 | 2021-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00175 | 01803 | 499.5 | Solar | 391-H12 | 2021-06-08 | 2021-06-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Application Completed/Closed | Online
NSTAR | North Harwich | ESMAEX-00217 | 02645 | 10 | Battery | 4-89A-89A | 2021-06-28 | 2021-07-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-09 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-00169 | 01890 | 2.03 | Solar | 211-H7XY | 2021-06-07 | 2021-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Application Completed/Closed | Online
NSTAR | Mattapan | ESMAEX-00192 | 02126 | 78.8 | Solar | 496-H8 | 2021-06-18 | 2021-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00174 | 01803 | 233.1 | Solar | 391-H12 | 2021-06-08 | 2021-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-06-03 | Application Completed/Closed | Online
NSTAR | Marstons Mills | ESMAEX-00172 | 02648 | 20.67 | Battery | 4-88-88 | 2021-06-08 | 2021-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-29 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00171 | 01776 | 34.2 | Solar | 342-H8 | 2021-06-08 | 2021-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01605 | 01803 | 43.2 | Solar | 346-1395H1 | 2022-09-19 | 2022-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00234 | 01741 | 15 | Battery | 533-H8 | 2021-07-12 | 2021-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-10-06 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00822 | 02360 | 40.4 | Solar & Battery | 3-90-90 | 2022-02-08 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-00176 | 02467 | 16.57 | Solar & Battery | 467-H12 | 2021-06-09 | 2021-06-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-18 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-00197 | 02367 | 499 | Solar | 3-15-15 | 2021-06-21 | 2021-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Pocasset | ESMAEX-00188 | 02559 | 36.83 | Solar |  | 2021-06-15 | 2021-07-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00184 | 02053 | 22 | Solar & Battery | 65-H3 | 2021-06-14 | 2021-06-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-00189 | 02739 | 9 | Solar | 2-301-301 | 2021-06-16 | 2021-07-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Application Completed/Closed | Online
NSTAR | Truro | ESMAEX-00190 | 02666 | 50 | Solar & Battery | 4-96-96 | 2021-06-16 | 2021-07-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Application Completed/Closed | Online
NSTAR | Oak Bluffs | ESMAEX-00193 | 02557 | 19.92 | Solar | 4-99-224 | 2021-06-19 | 2021-07-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-00196 | 02364 | 7.6 | Solar & Battery | 3-18-18 | 2021-06-21 | 2021-07-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00191 | 02081 | 15.2 | Solar | 456-H1 | 2021-06-17 | 2021-07-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Application Completed/Closed | Online
NSTAR | Assonett | ESMAEX-00195 | 02702 | 15.2 | Solar | 2-606-606 | 2021-06-21 | 2021-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-01-20 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-00211 | 01730 | 17.6 | Solar | 322-1397H1 | 2021-06-24 | 2021-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-05 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-00200 | 02739 | 18.28 | Solar | 2-301-301 | 2021-06-22 | 2021-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2021-12-22 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00251 | 02139 | 129.6 | Solar | 875-1328 | 2021-07-20 | 2021-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00228 | 01748 | 20 | Solar | 65-H7 | 2021-07-06 | 2021-07-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00206 | 01773 | 17.6 | Solar | 320-H8 | 2021-06-23 | 2021-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-29 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00235 | 02421 | 33.3 | Solar | 34-1352H1 | 2021-07-13 | 2021-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00210 | 02421 | 15.2 | Solar | 320-H5XY | 2021-06-24 | 2021-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00213 | 01760 | 12.6 | Solar & Battery | 240-H6 | 2021-06-25 | 2021-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-00215 | 02536 | 15.2 | Solar | 4-98B-449 | 2021-06-25 | 2021-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00218 | 02468 | 25 | Solar & Battery | 1701 | 2021-06-28 | 2021-07-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00293 | 02030 | 3.8 | Solar | 456-H5 | 2021-08-09 | 2021-08-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-15 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00259 | 01776 | 20 | Solar | 342-H6 | 2021-07-22 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Application Completed/Closed | Online
NSTAR | West Wareham | ESMAEX-00219 | 02576 | 15.2 | Solar | 3-85-85 | 2021-06-29 | 2021-07-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-10-22 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00222 | 01701 | 9.8 | Solar & Battery | 342-H4 | 2021-07-01 | 2021-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00226 | 01773 | 12.6 | Solar & Battery | 320-H6 | 2021-07-02 | 2021-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Application Completed/Closed | Online
NSTAR | Dartmouth | ESMAEX-00238 | 02747 | 148.92 | Solar | 2-532-532 | 2021-07-13 | 2021-07-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00265 | 02090 | 76 | Solar | 148-H3 | 2021-07-26 | 2021-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-00304 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2021-08-12 | 2021-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-00232 | 01754 | 17.8 | Solar & Battery | 355-04 | 2021-07-12 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-00231 | 02445 | 200 | Solar | 350-H8 | 2021-07-09 | 2021-07-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Application Completed/Closed | Online
NSTAR | Sandwich | ESMAEX-00305 | 02644 | 60.5 | Solar |  | 2021-08-12 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00264 | 02492 | 23.4 | Solar | 148-04 | 2021-07-26 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-11-29 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00570 | 02360 | 10 | Battery | 3-71-71 | 2021-11-05 | 2021-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-06 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00236 | 01701 | 4999 | Battery | 433-H2 | 2021-08-31 | 2021-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wayland | ESMAEX-00252 | 01778 | 80 | Solar | 342-H3 | 2021-07-20 | 2021-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00240 | 02451 | 233.1 | Solar |  | 2021-07-14 | 2021-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-24 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00302 | 01803 | 19.825 | Solar | 375-H14 | 2021-08-11 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00267 | 01741 | 18.18 | Solar | 512-1399H1 | 2021-07-27 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Application Completed/Closed | Online
NSTAR | Dennis | ESMAEX-00336 | 02638 | 262.5 | Fuel Cell | 4-92B-92B | 2021-08-20 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-00263 | 02134 | 133.2 | Solar | 329-H5 | 2021-07-23 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00285 | 01770 | 19.7 | Solar | 130-H2 | 2021-08-04 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-07 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00248 | 01770 | 5.7 | Battery | 240-H1 | 2021-07-19 | 2021-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-02-18 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-00247 | 01754 | 16.4 | Solar | 416-H1 | 2021-07-19 | 2021-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-02-02 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00250 | 02745 | 15.2 | Solar | 2-106-160 | 2021-07-20 | 2021-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00337 | 01803 | 138.4 | Solar | 391-H9 | 2021-08-23 | 2021-09-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | Roslindale | ESMAEX-00257 | 02131 | 10 | Battery | 516-06 | 2021-07-21 | 2021-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Application Completed/Closed | Online
NSTAR | West Yarmouth | ESMAEX-00278 | 02673 | 170 | Internal Combustion Engine |  | 2021-08-02 | 2021-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-04 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00282 | 02420 | 11.52 | Battery | 533-H9 | 2021-08-03 | 2021-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-00273 | 02649 | 80 | Solar | 4-452-452 | 2021-07-28 | 2021-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00274 | 02090 | 24 | Solar & Battery | 148-H3 | 2021-07-29 | 2021-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-00313 | 02445 | 7.68 | Solar & Battery | 23N30 | 2021-08-13 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-00299 | 02445 | 19.764 | Solar | 350-H8 | 2021-08-10 | 2021-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-00270 | 02738 | 22.8 | Solar | 3-85-85 | 2021-07-28 | 2021-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-00298 | 02019 | 4947 | Battery | 65-H4 | 2021-08-10 | 2021-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-00271 | 02360 | 15 | Solar & Battery | 3-71-71 | 2021-07-28 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-01-07 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-00272 | 02467 | 5.16 | Battery | 496-H5 | 2021-07-28 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-00303 | 02653 | 15.2 | Solar & Battery | 4-94A-94A | 2021-08-12 | 2021-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00320 | 01720 | 66.6 | Solar | 416-H9 | 2021-08-17 | 2021-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Cummaquid | ESMAEX-00283 | 02637 | 18 | Solar | 4-92A-912 | 2021-08-03 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-00280 | 02026 | 86.4 | Solar | 148-H3 | 2021-08-02 | 2021-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-05 | Application Completed/Closed | Online
NSTAR | Marstons Mills | ESMAEX-00284 | 02648 | 6 | Solar | 4-87A-87A | 2021-08-03 | 2021-08-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00322 | 02745 | 249.9 | Solar | 2-79-404 | 2021-08-17 | 2021-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-00287 | 02332 | 15.2 | Solar | 3-26-26 | 2021-08-04 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-06 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00288 | 02030 | 10 | Battery | 456-H5 | 2021-08-05 | 2021-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-21 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-00297 | 02364 | 10 | Battery | 3-51-980 | 2021-08-10 | 2021-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-15 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00393 | 02492 | 20 | Battery | 148-H4 | 2021-09-08 | 2021-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-00292 | 02056 | 15.29 | Solar & Battery | 65-H1 | 2021-08-09 | 2021-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00317 | 01748 | 15.2 | Solar | 126-H2 | 2021-08-17 | 2021-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00301 | 02468 | 7.67 | Solar & Battery | 292-H2 | 2021-08-11 | 2021-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-00318 | 01890 | 17.58 | Solar & Battery | 211-07 | 2021-08-17 | 2021-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-14 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00315 | 02067 | 250 | Solar | 146-H1 | 2021-08-16 | 2021-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00340 | 02745 | 50 | Solar | 2-103-103 | 2021-08-23 | 2021-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-01118 | 02139 | 21.4 | Solar | 820-45 | 2022-04-26 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00365 | 01720 | 110.8 | Solar | 416-H8 | 2021-08-27 | 2021-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-15 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00473 | 01760 | 9.516 | Solar & Battery | 433-H12 | 2021-10-05 | 2021-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00316 | 02030 | 12.685 | Solar & Battery | 456-H5 | 2021-08-16 | 2021-09-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00312 | 02360 | 7.6 | Solar & Battery | 3-14-934 | 2021-08-13 | 2021-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-17 | [7 empty] | 0 |  | 0 |  |  | 2022-01-27 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00495 | 02050 | 5.51 | Solar & Battery | 3-22-33J2 | 2021-10-13 | 2021-11-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-19 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00310 | 01741 | 15.2 | Solar & Battery | 512-1399H1 | 2021-08-13 | 2021-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2022-11-29 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-00607 | 02186 | 19.8 | Battery | 496-H2 | 2021-11-18 | 2022-01-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00308 | 02138 | 17.6 | Solar & Battery | 825-18 | 2021-08-13 | 2021-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-00424 | 01778 | 7.68 | Battery | 278-H2 | 2021-09-20 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-05-26 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00331 | 02451 | 100 | Solar | 450-H2 | 2021-08-19 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-00319 | 02536 | 310 | Solar |  | 2021-11-10 | 2021-12-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00321 | 01748 | 17.6 | Solar & Battery | 126-H2 | 2021-08-17 | 2022-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00323 | 01770 | 20 | Solar & Battery | 240-H1 | 2021-08-17 | 2021-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-00326 | 02332 | 46.2 | Solar | 3-23-23 | 2021-08-18 | 2021-09-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00328 | 01720 | 20 | Solar | 416-H8 | 2021-08-18 | 2021-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-00379 | 02054 | 27.13 | Battery | 146-H10 | 2021-09-02 | 2021-09-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00335 | 01770 | 24.19 | Solar | 274-H2 | 2021-08-20 | 2021-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-00334 | 02631 | 10 | Solar & Battery | 4-628-628 | 2021-08-20 | 2021-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-00346 | 02332 | 21.44 | Solar | 3-24B-24B | 2021-08-25 | 2021-09-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-00339 | 02052 | 17.68 | Solar & Battery | 146-H2 | 2021-08-23 | 2021-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00406 | 01773 | 21.65 | Solar & Battery | 320-H8 | 2021-09-13 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00422 | 02021 | 16 | Solar | 470-H11 | 2021-09-17 | 2022-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00344 | 01803 | 17.6 | Solar & Battery | 346-1395H1 | 2021-08-24 | 2021-09-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00350 | 02138 | 17.6 | Solar & Battery | 830-11 | 2021-08-26 | 2021-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-00345 | 02056 | 17.68 | Solar & Battery | 146-H3 | 2021-08-24 | 2021-09-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-14 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00352 | 02067 | 20.2 | Solar & Battery | 146-H7 | 2021-08-26 | 2021-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00416 | 01720 | 19.79 | Battery | 416-H4 | 2021-09-16 | 2021-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-00349 | 02474 | 12.6 | Solar & Battery | 211-H14 | 2021-08-25 | 2021-09-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-00359 | 02446 | 15 | Battery | 4911 | 2021-08-26 | 2021-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Charlestown | ESMAEX-00488 | 02129 | 86.5 | Solar |  | 2021-10-12 | 2021-11-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2023-12-05 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00360 | 01720 | 17.6 | Solar & Battery | 416-H4 | 2021-08-26 | 2021-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00357 | 02067 | 498 | Solar | 146-H1 | 2021-10-02 | 2021-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medway | ESMAEX-00399 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00398 | 02053 | 43.2 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-10 | Application Completed/Closed | Online
NSTAR | Bourne | ESMAEX-00461 | 02532 | 39.98 | Solar | 4-86-408 | 2021-09-30 | 2021-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00373 | 01720 | 21.4 | Solar & Battery | 416-H9 | 2021-08-31 | 2021-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00420 | 02472 | 325 | Solar & Battery | 240-H5 | 2021-09-17 | 2022-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00400 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-00378 | 01746 | 19 | Solar | 130-H1 | 2021-09-01 | 2021-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Application Completed/Closed | Online
NSTAR | East Sandwich | ESMAEX-00397 | 02537 | 10 | Solar & Battery | 4-87A-87A | 2021-09-09 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-04-11 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-00386 | 02465 | 17.6 | Solar & Battery | 282-H9 | 2021-09-06 | 2021-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00376 | 01773 | 52.8 | Solar & Battery | 320-H8 | 2021-09-01 | 2021-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00389 | 02452 | 150 | Solar | 33-H2 | 2021-09-07 | 2021-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00392 | 02468 | 25.2 | Solar & Battery | 292-H12 | 2021-09-08 | 2021-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00388 | 01720 | 9.6 | Solar & Battery | 416-H2 | 2021-09-07 | 2021-09-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-10 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00440 | 02090 | 25.37 | Solar & Battery | 456-H1 | 2021-09-22 | 2021-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-00411 | 02128 | 75 | Internal Combustion Engine | 488-H5 | 2021-09-14 | 2021-09-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Application Completed/Closed | Online
NSTAR | Assonett | ESMAEX-00396 | 02702 | 149.76 | Solar | 2-102-604 | 2021-09-09 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-00391 | 02056 | 13.15 | Battery | 146-H3 | 2021-09-08 | 2021-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00438 | 01702 | 21.28 | Solar & Battery | 455-H5 | 2021-09-21 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | North Falmouth | ESMAEX-00404 | 02556 | 25.075 | Solar | 4-78-861 | 2021-09-10 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-30 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-00405 | 02135 | 100 | Solar | 329-H2 | 2021-09-10 | 2021-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-17 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00408 | 02118 | 100 | Solar | 106-H4 | 2021-09-13 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00403 | 02421 | 21.43 | Solar & Battery | 3409 | 2021-09-10 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00414 | 02090 | 20 | Solar & Battery | 469-H2 | 2021-09-16 | 2021-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-08 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00412 | 01748 | 27.6 | Solar & Battery | 126-H4 | 2021-09-14 | 2021-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-00410 | 02747 | 15.2 | Solar | 2-531-531 | 2021-09-14 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-00415 | 02659 | 180 | Solar | 4-95A-95A | 2021-09-16 | 2022-01-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-00445 | 02364 | 100 | Solar | 3-14-14 | 2021-09-23 | 2021-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-24 | [7 empty] | 0 |  | 0 |  |  | 2023-11-17 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00418 | 02740 | 50 | Solar | 2-73-16 | 2021-09-17 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00426 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-09-20 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00460 | 02215 | 120.8 | Solar | 350-H12 | 2021-09-30 | 2021-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00419 | 01701 | 17.6 | Solar & Battery | 433-H8 | 2021-09-17 | 2021-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Application Completed/Closed | Online
NSTAR | North Falmouth | ESMAEX-00539 | 02556 | 12 | Battery | 4-78-420 | 2021-10-25 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-00421 | 02770 | 20 | Solar | 3-702-702 | 2021-09-17 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00428 | 02030 | 30 | Solar & Battery | 456-H5 | 2021-09-20 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-14 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00429 | 02472 | 492 | Solar |  | 2021-10-26 | 2021-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-00446 | 02575 | 12.98 | Solar | 4-97-97 | 2021-09-24 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00435 | 02540 | 16.82 | Solar | 4-76-76 | 2021-09-21 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-00454 | 02458 | 200 | Solar | 467-H14 | 2021-09-28 | 2021-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00436 | 02740 | 75 | Internal Combustion Engine | 2-67-28 | 2021-09-21 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00437 | 02740 | 75 | Internal Combustion Engine | 2-4-51 | 2021-09-21 | 2021-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00464 | 01803 | 15.2 | Solar & Battery | 391-H6 | 2021-10-01 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-00480 | 02747 | 86.4 | Solar | 2-532-532 | 2021-10-07 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Dartmouth | ESMAEX-00455 | 02747 | 100 | Solar |  | 2021-09-28 | 2022-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-00450 | 02739 | 17.6 | Solar | 2-302-302 | 2021-09-27 | 2021-10-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-00513 | 02119 | 52.2 | Solar | 52-1499H4 | 2021-10-19 | 2021-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00457 | 02067 | 420 | Solar | 470-H12 | 2021-09-29 | 2021-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-00644 | 02575 | 25.568 | Solar & Battery |  | 2021-12-07 | 2021-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-00465 | 01730 | 12.6 | Solar & Battery | 533-H8 | 2021-10-03 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00506 | 01702 | 316.6 | Solar | 24-H1 | 2021-10-15 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-00658 | 02738 | 22.8 | Solar | 3-304-304 | 2021-12-14 | 2022-01-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-00467 | 02026 | 17.6 | Solar & Battery | 20-H3 | 2021-10-04 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Application Completed/Closed | Online
NSTAR | Harwich | ESMAEX-00466 | 02645 | 12.68 | Solar & Battery | 4-89B-576 | 2021-10-04 | 2021-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00472 | 01760 | 10.248 | Solar & Battery | 240-H1 | 2021-10-05 | 2021-10-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-00682 | 02539 | 11.21 | Solar & Battery |  | 2021-12-21 | 2022-02-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Application Completed/Closed | Online
NSTAR | Osterville | ESMAEX-00494 | 02655 | 28 | Solar & Battery | 4-80A-488 | 2021-10-13 | 2021-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00478 | 01748 | 19.77 | Solar | 126-H1 | 2021-10-06 | 2021-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-00505 | 02667 | 7.14 | Solar | 4-94B-656 | 2021-10-15 | 2021-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-00486 | 01801 | 109.8 | Solar | 211-H2 | 2021-10-10 | 2021-11-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-00548 | 02467 | 199.8 | Solar | 443-08 | 2021-10-27 | 2021-11-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00498 | 02081 | 15.8 | Solar | 456-H1 | 2021-10-13 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-00485 | 02739 | 16.24 | Solar | 2-302-302 | 2021-10-09 | 2021-11-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00500 | 02030 | 26 | Solar | 456-H5 | 2021-10-14 | 2021-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-00508 | 02717 | 149.76 | Solar | 2-108-108 | 2021-10-18 | 2021-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-00507 | 02652 | 8 | Solar | 4-96-96 | 2021-10-18 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Application Completed/Closed | Online
NSTAR | Hyde Park | ESMAEX-00537 | 02136 | 30.45 | Solar | 60-1409H1 | 2021-10-21 | 2021-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00547 | 02030 | 7.678 | Solar & Battery | 456-H5 | 2021-10-27 | 2021-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00514 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-10-19 | 2022-01-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-00561 | 02125 | 43.2 | Solar | 106-1N31H1 | 2021-11-02 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00516 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-10-20 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | East Sandwich | ESMAEX-00517 | 02537 | 9.12 | Solar & Battery | 4-87B-87B | 2021-10-20 | 2021-11-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Application Completed/Closed | Online
NSTAR | South Chatham | ESMAEX-00522 | 02659 | 10 | Battery | 4-95A-606 | 2021-10-21 | 2021-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-04 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-00664 | 02667 | 8 | Battery | 4-94B-94B | 2021-12-15 | 2022-01-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-00546 | 02601 | 150 | Solar | 4-63-531 | 2021-10-26 | 2021-12-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyannis Port | ESMAEX-00558 | 02672 | 10 | Battery | 4-80B-80B | 2021-11-01 | 2021-11-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00563 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-11-03 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-00600 | 02748 | 48.03 | Solar & Battery | 2-524-524 | 2021-11-17 | 2022-01-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-00540 | 02532 | 196 | Solar | 3-83-83 | 2021-10-25 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-00557 | 01721 | 250 | Solar | 274-H5 | 2021-11-01 | 2021-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Chatham | ESMAEX-00542 | 02633 | 15.39 | Solar | 4-95B-95B | 2021-10-26 | 2021-11-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-00544 | 02747 | 57.6 | Solar | 2-532-532 | 2021-10-26 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-08-16 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-00545 | 02467 | 17.6 | Solar & Battery | 329-H6 | 2021-10-26 | 2021-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-03-21 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00551 | 02459 | 1.5 | Solar & Battery | 292-H8 | 2021-10-28 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-25 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00830 | 02492 | 480 | Solar & Battery | 148-H1 | 2022-02-11 | 2022-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Submit Compliances Documents | Compliances Documents
NSTAR | Needham | ESMAEX-00552 | 02494 | 750 | Solar & Battery | 148-H6 | 2021-12-23 | 2022-01-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-00554 | 01803 | 20 | Solar & Battery | 391-H7 | 2021-10-28 | 2021-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-21 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00560 | 02494 | 11.4 | Battery | 292-H4 | 2021-11-02 | 2021-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-02 | [7 empty] | 0 |  | 0 |  |  | 2022-03-23 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00572 | 02081 | 400 | Solar | 146-H8 | 2021-11-08 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-00565 | 02649 | 85.76 | Solar | 4-455-455 | 2021-11-04 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00562 | 02021 | 8.56 | Solar & Battery | 470-H8 | 2021-11-02 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-14 | Application Completed/Closed | Online
NSTAR | Newton Lower Falls | ESMAEX-00571 | 02462 | 9.75 | Solar & Battery | 292-H2 | 2021-11-08 | 2021-12-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00566 | 02030 | 10 | Battery | 148-H2 | 2021-11-05 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-00589 | 02747 | 20 | Solar | 2-532-532 | 2021-11-15 | 2021-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00596 | 01741 | 14 | Battery | 512-1399H1 | 2021-11-17 | 2021-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-00573 | 02743 | 15.2 | Solar | 2-241-241 | 2021-11-09 | 2021-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-08-23 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-00574 | 02770 | 10.03 | Solar | 3-703-703 | 2021-11-09 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-00576 | 02030 | 16.225 | Solar | 456-H5 | 2021-11-10 | 2021-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00582 | 02492 | 11.4 | Battery | 148-H4 | 2021-11-11 | 2021-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-00580 | 02150 | 43.2 | Solar | 488-H3 | 2021-11-10 | 2021-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-00581 | 02150 | 43.2 | Solar | 488-H7 | 2021-11-10 | 2021-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-00586 | 02633 | 12 | Battery | 4-95B-95B | 2021-11-15 | 2021-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-24 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00584 | 02050 | 9 | Battery | 3-27-970 | 2021-11-15 | 2021-12-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-02467 | 02330 | 4990 | Solar | 3-10-10 | 2023-06-26 | 2023-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | North Truro | ESMAEX-00585 | 02652 | 15.2 | Solar & Battery | 4-96-96 | 2021-11-15 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-00590 | 02738 | 17.6 | Solar & Battery | 3-85-85 | 2021-11-16 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00601 | 02459 | 15.2 | Solar | 443-02 | 2021-11-17 | 2022-01-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-00605 | 01746 | 80 | Solar | 274-H3 | 2021-11-18 | 2021-12-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00604 | 02540 | 19 | Solar | 4-78-78 | 2021-11-18 | 2022-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Application Completed/Closed | Online
NSTAR | Assonett | ESMAEX-00610 | 02702 | 17.25 | Solar | 2-605-605 | 2021-11-22 | 2021-12-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00597 | 02138 | 34.2 | Solar | 821-05 | 2021-11-17 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2023-09-01 | Application Completed/Closed | Online
NSTAR | South Chatham | ESMAEX-00602 | 02659 | 16 | Solar |  | 2021-11-17 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00603 | 02360 | 17.6 | Solar | 3-90-90 | 2021-11-17 | 2022-01-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00606 | 02021 | 140 | Solar | 470-H4 | 2021-11-18 | 2022-01-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-00630 | 02790 | 10 | Battery | 2-523-523 | 2021-11-30 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-00890 | 02748 | 220 | Solar | 2-53-65 | 2022-03-08 | 2022-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-01-04 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00638 | 02139 | 14.79 | Solar | 817-46 | 2021-12-03 | 2022-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00637 | 02420 | 10.03 | Solar & Battery | 391-H11 | 2021-12-02 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Application Completed/Closed | Online
NSTAR | Silver Beach | ESMAEX-00636 | 02565 | 6.1 | Battery | 4-78-861 | 2021-12-02 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00635 | 02360 | 72 | Solar | 3-12-28J3 | 2021-12-01 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00621 | 01748 | 20 | Solar & Battery | 126-H4 | 2021-11-24 | 2021-12-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-00622 | 01730 | 17.4 | Solar | 533-H8 | 2021-11-24 | 2021-12-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-00624 | 02667 | 23.78 | Solar | 4-94B-653 | 2021-11-27 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-25 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00626 | 02067 | 7.6 | Solar & Battery | 470-H12 | 2021-11-28 | 2021-12-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2023-04-14 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00667 | 02090 | 18 | Solar & Battery | 456-H4 | 2021-12-16 | 2022-01-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-00672 | 02150 | 86.4 | Solar | 488-H7 | 2021-12-20 | 2022-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Application Completed/Closed | Online
NSTAR | East Brewster | ESMAEX-00650 | 02631 | 100 | Solar |  | 2021-12-09 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00733 | 02163 | 43.2 | Solar | 831-1107 | 2022-01-18 | 2022-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-00648 | 02601 | 220 | Solar | 4-63-521 | 2021-12-08 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-00641 | 02067 | 9.15 | Solar & Battery | 470-H12 | 2021-12-03 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Application Completed/Closed | Online
NSTAR | West Barnstable | ESMAEX-00730 | 02668 | 15.36 | Solar | 4-87B-87B | 2022-01-16 | 2022-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00647 | 02421 | 8.85 | Solar | 320-H2 | 2021-12-08 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-00678 | 02445 | 14 | Battery | 350-H3 | 2021-12-20 | 2022-02-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-00740 | 02652 | 16.56 | Solar |  | 2022-01-19 | 2022-02-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-00646 | 02332 | 10 | Solar | 3-26-26 | 2021-12-07 | 2021-12-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Application Completed/Closed | Online
NSTAR | Hatchville | ESMAEX-00685 | 02536 | 10 | Solar | 4-98A-429 | 2021-12-21 | 2022-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00703 | 02090 | 16.054 | Solar | 148-H3 | 2022-01-03 | 2022-01-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00656 | 02492 | 15.707 | Solar & Battery | 148-08 | 2021-12-13 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00651 | 01776 | 199.9 | Solar | 342-H2 | 2021-12-09 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-28 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00654 | 02125 | 98 | Solar | 483-H3 | 2021-12-10 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Eversource Review Schedule Z | Technical Review
NSTAR | Hyde Park | ESMAEX-00655 | 02136 | 3.8 | Solar | 441-02 | 2021-12-10 | 2021-12-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-29 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00676 | 01748 | 7.6 | Solar & Battery | 126-H3 | 2021-12-20 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-04-21 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00662 | 02472 | 10 | Battery | 467-H8 | 2021-12-15 | 2022-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00666 | 02215 | 116 | Solar |  | 2021-12-15 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00683 | 02050 | 17.7 | Solar | 3-24A-34J1 | 2021-12-21 | 2022-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-08-29 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00665 | 02021 | 15.2 | Solar | 470-H10 | 2021-12-15 | 2022-01-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00669 | 02124 | 130 | Solar | 496-H8 | 2021-12-17 | 2022-01-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Permission To Operate | Permission to Operate
NSTAR | Dover | ESMAEX-00704 | 02030 | 16.403 | Solar | 456-H5 | 2022-01-03 | 2022-01-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00693 | 02494 | 140 | Solar |  | 2021-12-23 | 2022-01-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-00673 | 02575 | 20 | Solar |  | 2021-12-20 | 2022-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-22 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00721 | 02540 | 10 | Battery | 4-76-436 | 2022-01-11 | 2022-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-21 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00681 | 02021 | 4999.2 | Battery | 470-H4 | 2022-11-29 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-00687 | 02539 | 8.12 | Solar & Battery |  | 2021-12-22 | 2022-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00688 | 02459 | 25.2 | Solar & Battery | 292-H6 | 2021-12-22 | 2022-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-00686 | 02054 | 498 | Solar & Battery | 456-H2 | 2023-01-26 | 2023-02-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-00692 | 02420 | 22.8 | Solar & Battery | 533-H9 | 2021-12-23 | 2022-01-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-09-30 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00696 | 02472 | 400 | Solar | 315-H4 | 2022-01-20 | 2022-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00697 | 01702 | 11.5 | Solar & Battery | 519-175H1 | 2021-12-28 | 2022-01-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01930 | 02030 | 15.37 | Solar | 456-H3 | 2022-12-16 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-00702 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2022-01-03 | 2022-01-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00722 | 02118 | 43.2 | Solar |  | 2022-01-11 | 2022-03-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00709 | 02090 | 480 | Solar | 469-H6 | 2022-05-11 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | South Boston | ESMAEX-00753 | 02127 | 28.8 | Solar | 385-H19 | 2022-01-24 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | West Yarmouth | ESMAEX-00719 | 02673 | 20.2 | Solar & Battery | 4-64-64 | 2022-01-11 | 2022-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-05 | Application Completed/Closed | Online
NSTAR | Centerville | ESMAEX-00711 | 02632 | 18.25 | Solar & Battery | 4-82-82 | 2022-01-05 | 2022-01-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-00716 | 02458 | 13.05 | Solar & Battery | 467-H12 | 2022-01-06 | 2022-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00809 | 01748 | 24.78 | Solar | 126-H4 | 2022-02-04 | 2022-03-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-00727 | 02465 | 15.51 | Solar & Battery | 316-03 | 2022-01-13 | 2022-02-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-00725 | 02738 | 10 | Solar & Battery | 3-304-304 | 2022-01-12 | 2022-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00724 | 02360 | 43.2 | Solar | 3-89-922 | 2022-01-11 | 2022-02-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00720 | 02492 | 10 | Battery | 148-07 | 2022-01-11 | 2022-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00723 | 01776 | 21.4 | Solar & Battery | 342-H8 | 2022-01-11 | 2022-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-03-14 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00726 | 02472 | 636 | Solar | 370-1323 | 2022-03-15 | 2022-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00757 | 02090 | 15.2 | Solar & Battery | 456-H4 | 2022-01-25 | 2022-02-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-00743 | 02493 | 18.148 | Solar | 282-H1 | 2022-01-20 | 2022-02-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-01133 | 02539 | 44.37 | Solar |  | 2022-05-02 | 2022-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Application Completed/Closed | Online
NSTAR | North Cambridge | ESMAEX-00732 | 02140 | 6.38 | Solar & Battery | 824-28 | 2022-01-18 | 2022-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-00729 | 02134 | 40 | Solar | 315-H8 | 2022-01-14 | 2022-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Application Completed/Closed | Online
NSTAR | East Harwich | ESMAEX-00737 | 02645 | 19.14 | Solar | 4-95A-95A | 2022-01-19 | 2022-02-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-10-26 | Eversource Review Schedule Z | Technical Review
NSTAR | Needham | ESMAEX-00736 | 02494 | 3.8 | Solar & Battery | 148-H4 | 2022-01-18 | 2022-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00811 | 01773 | 7.68 | Battery | 320-H6 | 2022-02-04 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-11-16 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-00744 | 02150 | 250 | Battery | 488-H1 | 2022-03-08 | 2022-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-00891 | 02539 | 29 | Solar | 4-75-227 | 2022-03-09 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-00745 | 02150 | 250 | Solar |  | 2022-03-08 | 2022-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chelsea | ESMAEX-00747 | 02150 | 375 | Solar |  | 2022-03-08 | 2022-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-00913 | 02139 | 9.15 | Solar & Battery | 816-02 | 2022-03-14 | 2022-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-25 | Application Completed/Closed | Online
NSTAR | Waquoit | ESMAEX-00748 | 02536 | 11.52 | Solar & Battery |  | 2022-01-20 | 2022-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Application Completed/Closed | Online
NSTAR | East Harwich | ESMAEX-00874 | 02645 | 11 | Solar & Battery | 4-95A-95A | 2022-03-03 | 2022-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Application Completed/Closed | Online
NSTAR | Roxbury Crossing | ESMAEX-00802 | 02120 | 43.2 | Solar | 52-1499H4 | 2022-02-03 | 2022-03-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-00820 | 02633 | 19.14 | Solar | 4-95A-606 | 2022-02-07 | 2022-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-05 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00922 | 01770 | 15.705 | Solar | 274-H2 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00767 | 01741 | 15.95 | Solar | 512-1399H1 | 2022-01-31 | 2022-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00764 | 02540 | 9.6 | Solar & Battery | 4-72-72 | 2022-01-28 | 2022-02-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-00907 | 02467 | 8 | Battery | 443-07 | 2022-03-11 | 2022-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00758 | 02142 | 133.2 | Solar | 875-1392 | 2022-01-26 | 2022-04-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-27 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-00761 | 02451 | 250 | Solar & Battery | 450-H8 | 2022-01-27 | 2022-02-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chelsea | ESMAEX-00888 | 02150 | 495.8 | Solar | 488-H6 | 2022-03-29 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00762 | 02472 | 99.9 | Solar | 315-H4 | 2022-01-28 | 2022-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-00785 | 02748 | 22.8 | Solar | 2-524-524 | 2022-02-01 | 2022-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Application Completed/Closed | Online
NSTAR | Roxbury Crossing | ESMAEX-00768 | 02120 | 250 | Solar | 510-77H | 2022-03-04 | 2022-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Boston | ESMAEX-00770 | 02131 | 250 | Solar | 496-H8 | 2022-03-04 | 2022-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00772 | 02124 | 480 | Solar | 483-H1 | 2022-03-14 | 2022-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-24 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00776 | 02540 | 4999.2 | Battery | 4-76-76 | 2022-09-20 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Duxbury | ESMAEX-00807 | 02332 | 11.4 | Battery | 3-23-23 | 2022-02-04 | 2022-03-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Application Completed/Closed | Online
NSTAR | Woods Hole | ESMAEX-00827 | 02543 | 18.99 | Solar & Battery | 4-91-91 | 2022-02-10 | 2022-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Application Completed/Closed | Online
NSTAR | Mattapan | ESMAEX-00796 | 02126 | 250 | Solar | 311-09 | 2022-08-04 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00801 | 01701 | 20 | Solar | 455-H1 | 2022-02-03 | 2022-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Application Completed/Closed | Online
NSTAR | Harwichport | ESMAEX-00821 | 02646 | 15.2 | Solar | 4-95A-95A | 2022-02-08 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-11-03 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-00842 | 02476 | 166.5 | Solar | 211-H13 | 2022-02-18 | 2022-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00804 | 02081 | 133.3 | Solar | 146-H4 | 2022-02-03 | 2022-03-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-00805 | 02032 | 100 | Solar | 146-H8 | 2022-02-03 | 2022-03-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00841 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-17 | 2022-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-00808 | 02090 | 11 | Solar & Battery | 456-H4 | 2022-02-04 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-00864 | 02536 | 15.93 | Solar | 4-76-437 | 2022-02-28 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-00832 | 02539 | 2490 | Solar & Battery | 4-75-223 | 2022-02-14 | 2022-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Completed | Impact Study
NSTAR | Ashland | ESMAEX-01234 | 01721 | 120 | Solar | 274-1429H | 2022-05-27 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-00825 | 01890 | 19 | Solar | 211-H4 | 2022-02-09 | 2022-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-00824 | 01770 | 13.275 | Solar | 274-H2 | 2022-02-09 | 2022-03-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-00886 | 02790 | 5.12 | Battery | 2-523-523 | 2022-03-07 | 2022-07-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-00834 | 02601 | 75 | Solar | 4-63-521 | 2022-02-15 | 2022-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-00831 | 02568 | 70 | Solar | 4-75-75 | 2022-02-12 | 2022-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-17 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00838 | 02050 | 4999.2 | Battery | 3-22-973 | 2022-03-16 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-00860 | 02421 | 240 | Solar | 3402 | 2022-02-25 | 2022-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00861 | 02421 | 133.3 | Solar | 3402 | 2022-02-25 | 2022-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-00866 | 02472 | 160 | Solar |  | 2022-03-01 | 2022-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Application Completed/Closed | Online
NSTAR | Dennis | ESMAEX-00946 | 02638 | 17.6 | Solar & Battery | 4-89A-89A | 2022-03-18 | 2022-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-00843 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-21 | 2022-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00844 | 02360 | 10.03 | Solar & Battery | 3-11-11 | 2022-02-21 | 2022-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-06-21 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-00851 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-02-22 | 2022-03-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-00918 | 02139 | 84.6 | Solar | 820-15 | 2022-03-15 | 2022-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Application Completed/Closed | Online
NSTAR | Mattapan | ESMAEX-00867 | 02126 | 60 | Solar | 311-1403H1 | 2022-03-01 | 2022-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00859 | 02053 | 10.25 | Solar & Battery | 65-H3 | 2022-02-25 | 2022-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-25 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-00863 | 02748 | 4.64 | Solar | 2-528-528 | 2022-02-28 | 2022-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-12 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00889 | 02459 | 480 | Solar | 292-H3 | 2022-04-07 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2025-09-29 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00984 | 02459 | 60 | Solar |  | 2022-03-29 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-22 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00872 | 01776 | 15.2 | Solar & Battery | 342-H2 | 2022-03-02 | 2022-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00885 | 02128 | 249.9 | Solar | 152-87H | 2022-03-07 | 2022-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Application Completed/Closed | Online
NSTAR | Aquinnah | ESMAEX-00875 | 02535 | 8.7 | Solar & Battery | 4-97-97 | 2022-03-03 | 2022-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00985 | 02459 | 240 | Solar | 292-H3 | 2022-03-29 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-00877 | 01730 | 16.104 | Solar | 533-H5 | 2022-03-04 | 2022-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-00880 | 01801 | 15.2 | Solar | 325-03 | 2022-03-04 | 2022-03-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00912 | 01773 | 9.216 | Solar | 320-H6 | 2022-03-14 | 2022-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00887 | 02053 | 6 | Solar | 65-H3 | 2022-03-07 | 2022-03-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Application Completed/Closed | Online
NSTAR | Chilmark | ESMAEX-01041 | 02535 | 15.2 | Solar & Battery | 4-97-97 | 2022-04-08 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00951 | 01702 | 240 | Solar |  | 2022-03-21 | 2022-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-00923 | 02186 | 15.2 | Solar & Battery | 362-1209H2 | 2022-03-15 | 2022-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-01252 | 02142 | 100 | Solar | 875-1N39A | 2022-06-02 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-27 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-00917 | 01773 | 15.36 | Solar | 320-H6 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00899 | 01760 | 86.5 | Solar | 433-H11 | 2022-03-11 | 2022-03-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00895 | 02053 | 14.46 | Solar | 65-H5 | 2022-03-10 | 2022-03-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-00901 | 02019 | 15.2 | Solar & Battery | 65-H4 | 2022-03-11 | 2022-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-22 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-00902 | 02053 | 25.2 | Solar | 65-H3 | 2022-03-11 | 2022-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00900 | 02745 | 999 | Solar & Battery | 2-79-404 | 2022-04-06 | 2022-05-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wayland | ESMAEX-00903 | 01778 | 12.6 | Solar | 433-H2 | 2022-03-11 | 2022-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01033 | 02492 | 15.2 | Solar & Battery | 148-06 | 2022-04-07 | 2022-04-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-00908 | 02652 | 24.94 | Solar |  | 2022-03-11 | 2022-04-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | Cotuit | ESMAEX-00929 | 02635 | 15.2 | Solar & Battery | 4-88-88 | 2022-03-16 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-00949 | 02493 | 5 | Battery | 282-H1 | 2022-03-20 | 2022-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-00919 | 02652 | 28.71 | Solar | 4-96-96 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00916 | 01702 | 3.8 | Solar | 455-H5 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-00940 | 01702 | 10 | Solar & Battery | 455-H5 | 2022-03-17 | 2022-04-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Application Completed/Closed | Online
NSTAR | Buzzards Bay | ESMAEX-00920 | 02532 | 11.4 | Solar | 3-88-88 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00921 | 02459 | 3.5 | Solar | 1709 | 2022-03-15 | 2022-04-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-00945 | 01776 | 43.2 | Solar | 342-H2 | 2022-03-18 | 2022-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00927 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2022-03-16 | 2022-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-00931 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2022-03-16 | 2022-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-00936 | 01746 | 4.93 | Solar | 274-H3 | 2022-03-17 | 2022-04-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01801 | 02451 | 33.3 | Solar | 450-H7 | 2022-11-11 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-00935 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-03-17 | 2022-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-00938 | 02719 | 200 | Solar | 2-230-230 | 2022-06-22 | 2022-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-00953 | 02118 | 51.9 | Solar | 218-80H1 | 2022-03-21 | 2022-04-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00947 | 02021 | 7.6 | Solar & Battery | 470-H10 | 2022-03-19 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-00956 | 02459 | 15.2 | Solar & Battery | 292-H6 | 2022-03-22 | 2022-04-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-01083 | 02476 | 13 | Solar & Battery | 320-H7 | 2022-04-15 | 2022-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-13 | Application Completed/Closed | Online
NSTAR | Bourne | ESMAEX-00959 | 02532 | 18 | Solar | 4-86-408 | 2022-03-23 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Application Completed/Closed | Online
NSTAR | West Dennis | ESMAEX-00986 | 02670 | 3.8 | Solar & Battery | 4-92B-92B | 2022-03-29 | 2022-04-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-00962 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2022-03-24 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-00960 | 02468 | 23.424 | Solar | 292-H2 | 2022-03-23 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00967 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-03-25 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-00963 | 02536 | 15.2 | Solar & Battery | 4-98B-449 | 2022-03-24 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-00964 | 02360 | 15.2 | Solar & Battery | 3-89-925 | 2022-03-24 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-00961 | 02021 | 250 | Solar | 269-1320H1 | 2022-06-06 | 2022-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-00972 | 02134 | 34.6 | Solar | 315-H3 | 2022-03-28 | 2022-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-00987 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2022-03-29 | 2022-05-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-00968 | 02540 | 15.2 | Solar & Battery | 4-72-72 | 2022-03-25 | 2022-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-00974 | 02050 | 7.6 | Solar & Battery | 3-24A-974 | 2022-03-28 | 2022-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-00965 | 02717 | 15.2 | Solar | 2-108-108 | 2022-03-24 | 2022-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-00970 | 02420 | 7.6 | Solar & Battery | 3406 | 2022-03-26 | 2022-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | West Dennis | ESMAEX-00971 | 02670 | 15.2 | Solar & Battery |  | 2022-03-27 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-01255 | 02738 | 17.568 | Solar |  | 2022-06-03 | 2022-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00976 | 02746 | 480 | Solar | 2-81-81 | 2022-06-08 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-01006 | 02539 | 132.48 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-30 | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-01005 | 02568 | 156.16 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Application Completed/Closed | Online
NSTAR | Oak Bluffs | ESMAEX-00991 | 02557 | 20 | Solar | 4-99-225 | 2022-03-30 | 2022-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-00996 | 02740 | 120 | Solar | 2-83-403 | 2022-03-31 | 2022-04-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-00995 | 02118 | 250 | Solar |  | 2022-06-15 | 2022-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-00997 | 02081 | 10 | Solar | 146-H4 | 2022-03-31 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-01398 | 02459 | 22.5 | Solar & Battery | 292-H6 | 2022-07-21 | 2022-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-01000 | 02467 | 15.2 | Solar | 443-07 | 2022-04-01 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-01003 | 02032 | 17.6 | Solar & Battery | 146-H4 | 2022-04-04 | 2022-04-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-01017 | 01890 | 15.2 | Solar & Battery | 211-H10 | 2022-04-06 | 2022-04-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01082 | 02090 | 20.2 | Solar & Battery | 148-H3 | 2022-04-15 | 2022-05-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-01004 | 02459 | 492 | Solar | 292-H11 | 2022-04-27 | 2022-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-01094 | 02459 | 240 | Solar | 292-H3 | 2022-04-20 | 2022-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Stoneham | ESMAEX-01007 | 02180 | 15.2 | Solar | 375-H8 | 2022-04-04 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01055 | 01720 | 12.6 | Solar & Battery | 416-H9 | 2022-04-08 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Application Completed/Closed | Online
NSTAR | South Yarmouth | ESMAEX-01089 | 02664 | 18.56 | Solar | 4-92A-92A | 2022-04-18 | 2022-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01016 | 02090 | 15.2 | Solar | 148-H3 | 2022-04-06 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01043 | 02420 | 9.3 | Solar | 533-H9 | 2022-04-08 | 2022-04-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-01030 | 02467 | 25.2 | Solar & Battery | 443-08 | 2022-04-07 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01022 | 01746 | 15.2 | Solar & Battery | 65-H5 | 2022-04-06 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Application Completed/Closed | Online
NSTAR | East Sandwich | ESMAEX-01023 | 02537 | 26.4 | Solar & Battery | 4-87A-87A | 2022-04-06 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-01027 | 02032 | 15.2 | Solar & Battery | 146-H4 | 2022-04-06 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-01031 | 02536 | 15.2 | Solar & Battery | 4-77A-77A | 2022-04-07 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-01034 | 02745 | 15.2 | Solar & Battery | 2-106-161 | 2022-04-07 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-05-11 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01026 | 02210 | 300 | Solar | 385-H12 | 2022-06-17 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-01028 | 01770 | 30 | Solar | 240-H1 | 2022-04-07 | 2022-04-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-18 | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-01058 | 02631 | 25.2 | Solar & Battery | 4-89A-89A | 2022-04-08 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01105 | 02215 | 170 | Solar | 508-91 | 2022-04-24 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01104 | 02215 | 70 | Solar | 329-H9 | 2022-04-24 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-01299 | 02536 | 20 | Solar & Battery | 4-98B-449 | 2022-06-16 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01038 | 01760 | 15.2 | Solar & Battery | 240-H5 | 2022-04-07 | 2022-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-01039 | 02056 | 21 | Solar & Battery | 146-H10 | 2022-04-07 | 2022-04-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-01296 | 02021 | 20.2 | Solar & Battery | 470-H9 | 2022-06-15 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01052 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2022-04-08 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-01137 | 02125 | 43.5 | Solar | 483-H3 | 2022-05-03 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-01138 | 02125 | 31.7 | Solar | 6703 | 2022-05-03 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01049 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-04-08 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01086 | 01741 | 17.9 | Solar | 512-1399H1 | 2022-04-16 | 2022-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-01062 | 02119 | 50 | Solar | 510-77H3 | 2022-04-11 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-01100 | 02667 | 21.83 | Solar | 4-96-96 | 2022-04-22 | 2022-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-01066 | 02134 | 480 | Solar | 508-91 | 2022-05-20 | 2022-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01067 | 01748 | 250 | Solar | 65-H7 | 2022-05-11 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Application Completed/Closed | Online
NSTAR | Chilmark | ESMAEX-01069 | 02535 | 24.3 | Solar | 4-97-97 | 2022-04-11 | 2022-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-18 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01068 | 01748 | 120 | Solar | 126-H2 | 2022-05-11 | 2022-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01113 | 02067 | 8.85 | Solar & Battery | 146-H7 | 2022-04-26 | 2022-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01155 | 02119 | 30.16 | Solar | 396-1050H | 2022-05-06 | 2022-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-01147 | 02653 | 10 | Battery | 4-89B-89B | 2022-05-05 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-05 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01079 | 02493 | 7.6 | Solar & Battery | 282-H8 | 2022-04-13 | 2022-05-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Application Completed/Closed | Online
NSTAR | South Sandwich | ESMAEX-01088 | 02563 | 15.2 | Solar & Battery | 4-81B-81B | 2022-04-16 | 2022-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-11-21 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01080 | 01746 | 15.18 | Solar | 65-H5 | 2022-04-14 | 2022-05-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01084 | 02451 | 17.6 | Solar & Battery | 282-H7 | 2022-04-15 | 2022-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01095 | 02364 | 15.2 | Solar & Battery | 3-18-18 | 2022-04-20 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Application Completed/Closed | Online
NSTAR | Bourne | ESMAEX-01091 | 02532 | 6 | Solar & Battery | 4-86-86 | 2022-04-19 | 2022-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01125 | 02360 | 10 | Solar | 3-90-90 | 2022-04-29 | 2022-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-20 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01098 | 02360 | 7 | Battery | 3-73-938 | 2022-04-21 | 2022-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-02-24 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01786 | 02090 | 10 | Solar & Battery | 148-H3 | 2022-11-08 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01115 | 01803 | 6.4 | Battery | 391-H7 | 2022-04-26 | 2022-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01111 | 02360 | 10 | Battery | 3-89-922 | 2022-04-25 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01103 | 01760 | 18.29 | Solar | 433-H7 | 2022-04-22 | 2022-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-15 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-01099 | 02138 | 10 | Solar & Battery | 827-21 | 2022-04-21 | 2022-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01112 | 01720 | 17 | Solar & Battery | 416-H8 | 2022-04-25 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01108 | 01702 | 480 | Solar | 455-H5 | 2022-05-20 | 2022-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Vineyard Haven | ESMAEX-01162 | 02568 | 25 | Solar |  | 2022-05-10 | 2022-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-09-02 | Application Completed/Closed | Online
NSTAR | South Yarmouth | ESMAEX-01232 | 02664 | 20.2 | Solar & Battery | 4-92A-560 | 2022-05-27 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-01896 | 02738 | 20.65 | Solar | 3-304-304 | 2022-12-06 | 2023-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Application Completed/Closed | Online
NSTAR | Mattapan | ESMAEX-01121 | 02126 | 24.78 | Solar | 441-02 | 2022-04-27 | 2022-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-01119 | 02601 | 7.6 | Solar & Battery |  | 2022-04-27 | 2022-05-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Application Completed/Closed | Online
NSTAR | North Falmouth | ESMAEX-01123 | 02556 | 15.29 | Battery | 4-78-420 | 2022-04-28 | 2022-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01143 | 01778 | 10.248 | Solar & Battery | 342-H1 | 2022-05-04 | 2022-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01124 | 01746 | 19.99 | Solar & Battery | 65-H2 | 2022-04-28 | 2022-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-01150 | 02130 | 50 | Solar | 284-1430H | 2022-05-05 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2025-06-02 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01130 | 01702 | 67.3 | Solar | 455-H5 | 2022-04-29 | 2022-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-01197 | 02740 | 100 | Solar | 2-55-47 | 2022-05-19 | 2022-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-01131 | 02332 | 4990 | Battery | 3-25-25 | 2022-10-04 | 2022-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lincoln | ESMAEX-01144 | 01773 | 25.828 | Solar | 320-H6 | 2022-05-04 | 2022-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-01145 | 02459 | 19.398 | Solar | 292-H12 | 2022-05-04 | 2022-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-01136 | 02539 | 34.2 | Solar | 4-75-75 | 2022-05-03 | 2022-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01142 | 02420 | 8.4 | Solar | 533-H4 | 2022-05-04 | 2022-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | East Brewster | ESMAEX-01151 | 02631 | 10 | Battery | 4-89B-577 | 2022-05-05 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01154 | 01748 | 140 | Solar | 65-H7 | 2022-05-06 | 2022-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-20 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01156 | 02081 | 250 | Solar | 146-H6 | 2022-05-06 | 2022-06-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-01213 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-05-24 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-07 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-01170 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-01149 | 02032 | 9.74 | Solar & Battery | 146-H4 | 2022-05-05 | 2022-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Application Completed/Closed | Online
NSTAR | South Yarmouth | ESMAEX-01173 | 02664 | 79.8 | Solar | 4-92A-563 | 2022-05-11 | 2022-06-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01172 | 01741 | 16.24 | Solar | 533-H8 | 2022-05-11 | 2022-06-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01152 | 01776 | 15.2 | Solar | 342-H2 | 2022-05-05 | 2022-06-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01177 | 02090 | 15.045 | Solar | 456-H1 | 2022-05-12 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Application Completed/Closed | Online
NSTAR | Woods Hole | ESMAEX-01153 | 02543 | 7.8 | Solar & Battery | 4-91-91 | 2022-05-06 | 2022-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-24 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01157 | 01778 | 24.192 | Solar | 342-H1 | 2022-05-09 | 2022-06-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-01169 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01178 | 01760 | 160 | Solar | 23-H1 | 2022-05-13 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-01215 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-05-24 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-01160 | 02186 | 11.52 | Solar & Battery | 362-02 | 2022-05-09 | 2022-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01174 | 02180 | 1500 | Solar & Battery | 375-H8 | 2022-06-03 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Wareham | ESMAEX-01200 | 02576 | 15.045 | Solar | MID-702 | 2022-05-20 | 2022-06-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-01167 | 01721 | 29.5 | Solar & Battery | 274-H5 | 2022-05-11 | 2022-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-01310 | 02743 | 11.52 | Battery | 2-241-241 | 2022-06-20 | 2022-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-19 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01196 | 02420 | 34.6 | Solar | 533-H4 | 2022-05-19 | 2022-06-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-01179 | 02747 | 10 | Solar & Battery | 2-541-541 | 2022-05-13 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01202 | 02128 | 100 | Solar | 108-195H4 | 2022-05-20 | 2022-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-15 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-01201 | 02128 | 100 | Solar | 108-195H1 | 2022-05-20 | 2022-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-01176 | 02021 | 15.2 | Solar & Battery | 470-H8 | 2022-05-12 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-01233 | 01773 | 24.78 | Solar | 320-H6 | 2022-05-27 | 2022-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01181 | 01701 | 16.512 | Solar | 278-H2 | 2022-05-15 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Application Completed/Closed | Online
NSTAR | West Harwich | ESMAEX-01185 | 02671 | 17.2 | Solar & Battery | 4-85-925 | 2022-05-16 | 2022-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-01228 | 02748 | 15.2 | Solar | 2-528-528 | 2022-05-26 | 2022-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01184 | 01748 | 16.4 | Solar & Battery | 130-H1 | 2022-05-16 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01186 | 02421 | 15.3 | Solar | 320-H5XY | 2022-05-17 | 2022-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01238 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2022-06-01 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01194 | 02090 | 25 | Solar | 148-H3 | 2022-05-18 | 2022-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01193 | 01776 | 15.2 | Solar & Battery | 342-H4 | 2022-05-18 | 2022-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-01195 | 02130 | 3.8 | Solar | 496-H4 | 2022-05-18 | 2022-06-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01198 | 01741 | 15.2 | Solar | 533-H8 | 2022-05-19 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01212 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-05-23 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-03 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-01203 | 01890 | 9.984 | Solar & Battery | 211-H6 | 2022-05-20 | 2022-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-01253 | 02019 | 20 | Solar | 65-H4 | 2022-06-02 | 2022-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01256 | 02421 | 19.175 | Solar | 320-H5XY | 2022-06-06 | 2022-06-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-28 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01204 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-05-20 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01211 | 01803 | 10.03 | Solar & Battery | 346-1395H1 | 2022-05-23 | 2022-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-07 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-01216 | 02719 | 15.2 | Solar | 2-220-201 | 2022-05-24 | 2022-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-01217 | 01773 | 14.455 | Solar & Battery | 320-H8 | 2022-05-25 | 2022-06-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01235 | 02420 | 22.85 | Solar & Battery | 391-H11 | 2022-05-30 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01225 | 01778 | 16 | Solar | 342-H1 | 2022-05-26 | 2022-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-01226 | 02026 | 999 | Solar | 20-H1 | 2022-07-19 | 2022-08-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Needham | ESMAEX-01227 | 02494 | 10 | Solar & Battery | 292-H4 | 2022-05-26 | 2022-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01236 | 01760 | 6.6 | Solar & Battery | 433-H12 | 2022-05-31 | 2022-06-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01242 | 02090 | 486 | Solar | 456-H4 | 2022-12-05 | 2023-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-01231 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-05-27 | 2022-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01237 | 01741 | 7.2 | Battery | 533-H8 | 2022-06-01 | 2022-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01239 | 01754 | 430 | Solar | 416-H6 | 2023-01-04 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-01243 | 02575 | 17.6 | Solar & Battery | 4-97-97 | 2022-06-02 | 2022-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-12-01 | Application Completed/Closed | Online
NSTAR | Dartmouth | ESMAEX-01244 | 02748 | 500 | Solar | 2-53-65 | 2022-10-04 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Osterville | ESMAEX-01248 | 02655 | 18.59 | Solar | 4-88-88 | 2022-06-02 | 2022-07-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-01278 | 01730 | 7.08 | Solar & Battery |  | 2022-06-10 | 2022-07-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Application Completed/Closed | Online
NSTAR | Buzzards Bay | ESMAEX-01254 | 02532 | 6 | Battery | 3-88-2J3 | 2022-06-03 | 2022-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Application Completed/Closed | Online
NSTAR | West Somerville | ESMAEX-01294 | 02144 | 8.418 | Solar & Battery | 250-H6 | 2022-06-14 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01262 | 01754 | 62.5 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-01338 | 02459 | 67.3 | Solar | 443-02 | 2022-06-30 | 2022-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01259 | 02452 | 15.2 | Solar & Battery | 450-H4 | 2022-06-07 | 2022-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01497 | 02421 | 15.2 | Solar & Battery | 3401 | 2022-08-23 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01260 | 01720 | 17.6 | Solar & Battery | 416-H4 | 2022-06-07 | 2022-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-01387 | 02330 | 38 | Solar |  | 2022-07-19 | 2022-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01263 | 01754 | 125 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01264 | 01754 | 33.3 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01266 | 01754 | 125 | Solar | 416-H6 | 2022-06-07 | 2022-06-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01267 | 01754 | 487.5 | Solar | 342-H8 | 2022-08-15 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01315 | 02134 | 200 | Solar | 329-H2 | 2022-06-21 | 2022-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-27 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-01305 | 02125 | 499 | Solar | 106-H2 | 2022-06-17 | 2022-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-02 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01275 | 01741 | 21.4 | Solar | 512-1399H1 | 2022-06-09 | 2022-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01283 | 02090 | 16.5 | Solar | 456-H1 | 2022-06-10 | 2022-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-28 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01312 | 02420 | 11.4 | Solar & Battery |  | 2022-06-20 | 2022-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01683 | 02067 | 230 | Other | 146-H1 | 2022-10-14 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01285 | 02492 | 20 | Solar | 148-01 | 2022-06-13 | 2022-07-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-01290 | 02642 | 3.8 | Solar | 4-94A-94A | 2022-06-14 | 2022-08-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01331 | 01760 | 15.2 | Solar | 433-H12 | 2022-06-28 | 2022-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Application Completed/Closed | Online
NSTAR | Chilmark | ESMAEX-01416 | 02535 | 8.26 | Solar & Battery | 4-97-97 | 2022-07-28 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01320 | 01803 | 15.3 | Solar | 391-H7 | 2022-06-24 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01309 | 02360 | 10 | Solar & Battery | 3-90-90 | 2022-06-18 | 2022-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01313 | 02030 | 38.904 | Solar & Battery | 456-H5 | 2022-06-21 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01526 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-08-30 | 2022-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Application Completed/Closed | Online
NSTAR | Green Harbor | ESMAEX-01300 | 02041 | 103.68 | Solar | 3-27-970 | 2024-01-09 | 2024-01-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-08 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-01362 | 01721 | 15.2 | Solar & Battery | 274-H6 | 2022-07-11 | 2022-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-01394 | 01773 | 22.6 | Solar & Battery | 320-H8 | 2022-07-20 | 2022-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-23 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01355 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-07-08 | 2022-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02499 | 02476 | 133.3 | Solar | 211-H3 | 2023-05-21 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Sharon | ESMAEX-01322 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2022-06-24 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-01321 | 02053 | 19.032 | Solar | 65-H2 | 2022-06-24 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-01433 | 02135 | 100 | Solar | 315-H1 | 2022-08-04 | 2022-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-01415 | 02539 | 16.1 | Solar |  | 2022-07-28 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-01347 | 02458 | 50 | Solar | 467-H14 | 2022-07-06 | 2022-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-01327 | 02330 | 100 | Solar | 3-81-81 | 2022-06-27 | 2022-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-01340 | 02575 | 23.6 | Solar & Battery | 4-97-97 | 2022-07-01 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-01348 | 02539 | 466.66 | Solar & Battery |  | 2022-07-06 | 2022-07-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01339 | 02493 | 17.6 | Solar | 282-H10 | 2022-06-30 | 2022-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-01336 | 02743 | 9.3 | Solar & Battery | 2-241-241 | 2022-06-30 | 2022-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-01359 | 01721 | 240 | Solar | 274-1429H1 | 2022-07-11 | 2022-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01373 | 02030 | 150 | Solar | 456-H5 | 2022-07-13 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-07-02 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01365 | 02421 | 7 | Solar & Battery | 320-H5XY | 2022-07-12 | 2022-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01342 | 01701 | 6 | Solar | 278-H1 | 2022-07-01 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Application Completed/Closed | Online
NSTAR | Charlestown | ESMAEX-01343 | 02129 | 4999 | Battery | 250-H3 | 2022-09-23 | 2022-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-01364 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-07-12 | 2022-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-27 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01344 | 01801 | 7.38 | Solar & Battery | 211-H8 | 2022-07-05 | 2022-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-01374 | 02745 | 17.57 | Solar | 2-102-608 | 2022-07-13 | 2022-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Application Completed/Closed | Online
NSTAR | Oak Bluffs | ESMAEX-01389 | 02557 | 26.385 | Solar |  | 2022-07-20 | 2022-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01354 | 01760 | 17.6 | Solar | 433-H7 | 2022-07-08 | 2022-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-01363 | 02649 | 6 | Solar | 4-77A-77A | 2022-07-11 | 2022-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-01378 | 02652 | 10 | Battery | 4-96-96 | 2022-07-15 | 2022-08-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-01368 | 02186 | 17.6 | Solar | 4309 | 2022-07-12 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01437 | 01741 | 20.2 | Solar & Battery | 512-1399H1 | 2022-08-04 | 2022-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-10 | Application Completed/Closed | Online
NSTAR | Harwichport | ESMAEX-01388 | 02646 | 10 | Battery | 4-85-592 | 2022-07-19 | 2022-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01503 | 02090 | 15.2 | Solar & Battery | 456-H1 | 2022-08-23 | 2022-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-01508 | 02186 | 19 | Solar & Battery | 362-1209H2 | 2022-08-24 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-03 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01377 | 01702 | 200 | Solar |  | 2022-08-04 | 2022-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01603 | 02130 | 100 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Norfolk | ESMAEX-01417 | 02056 | 20.2 | Solar & Battery | 146-H10 | 2022-07-29 | 2022-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01900 | 02125 | 34.6 | Solar | 106-1N31H1 | 2022-12-07 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01407 | 02119 | 120 | Solar | 106-1N31H6 | 2022-07-22 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01386 | 01702 | 200 | Solar | 455-H4 | 2022-08-08 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01390 | 02493 | 10 | Solar & Battery | 282-H1 | 2022-07-20 | 2022-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-01393 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-07-20 | 2022-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-06-27 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01659 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2022-10-05 | 2022-11-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-01395 | 02747 | 19 | Solar | 2-528-528 | 2022-07-21 | 2022-08-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01399 | 02360 | 48 | Solar | 3-89-922 | 2022-07-21 | 2022-08-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01409 | 01702 | 200 | Solar | 455-H4 | 2022-08-15 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01411 | 02360 | 67.3 | Solar | 3-12-932 | 2022-07-25 | 2022-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-01414 | 02657 | 12.005 | Solar & Battery | 4-675-675 | 2022-07-27 | 2022-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Application Completed/Closed | Online
NSTAR | Hatchville | ESMAEX-01412 | 02536 | 17.6 | Solar | 4-78-78 | 2022-07-27 | 2022-08-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-01442 | 02052 | 19.8 | Solar | 456-H3 | 2022-08-08 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-01443 | 02472 | 16.83 | Solar & Battery | 467-H4 | 2022-08-08 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-21 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-01505 | 02125 | 72 | Solar | 483-H1 | 2022-08-24 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-01418 | 02540 | 178.2 | Solar | 4-72-72 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-09 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01424 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2022-08-02 | 2022-08-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01419 | 01702 | 200 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-30 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01420 | 02030 | 17.6 | Solar | 456-H5 | 2022-08-01 | 2022-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Application Completed/Closed | Online
NSTAR | Chilmark | ESMAEX-01423 | 02535 | 17.6 | Solar & Battery | 4-97-97 | 2022-08-02 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-01422 | 02540 | 17.4 | Solar | 4-72-72 | 2022-08-02 | 2022-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01425 | 02180 | 18.6 | Solar | 375-H8 | 2022-08-03 | 2022-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01432 | 01701 | 15.2 | Solar | 455-H1 | 2022-08-03 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01431 | 02364 | 240 | Solar | 3-26-26 | 2022-08-03 | 2022-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-01429 | 02026 | 270 | Solar | 13-H1 | 2022-08-03 | 2022-08-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-27 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01541 | 02090 | 15.2 | Solar & Battery | 469-H2 | 2022-09-02 | 2022-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-01446 | 02468 | 12.078 | Solar & Battery | 277-04 | 2022-08-08 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01458 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-08-10 | 2022-09-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01436 | 02360 | 15.2 | Solar | 3-90-10J2 | 2022-08-04 | 2022-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01496 | 01778 | 22.8 | Solar & Battery | 342-H3 | 2022-08-22 | 2022-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01440 | 02452 | 15.2 | Solar | 282-H7 | 2022-08-05 | 2022-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01441 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01453 | 02420 | 6 | Solar | 391-H11 | 2022-08-09 | 2022-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01463 | 02492 | 20 | Solar | 148-H7 | 2022-08-11 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-06 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-01610 | 02128 | 69.2 | Solar | 488-H8 | 2022-09-20 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-01452 | 02052 | 8.7 | Solar & Battery | 456-H2 | 2022-08-09 | 2022-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01459 | 01801 | 6 | Solar | 375-H6 | 2022-08-10 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01464 | 01748 | 250 | Solar | 126-H1 | 2022-09-09 | 2022-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01467 | 01720 | 250 | Solar | 416-H9 | 2022-09-09 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01470 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01471 | 01778 | 16 | Solar | 278-H2 | 2022-08-15 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01472 | 02067 | 19 | Solar | 470-H3 | 2022-08-15 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01487 | 01748 | 220 | Solar | 126-H1 | 2022-08-19 | 2022-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01490 | 02493 | 15.3 | Solar & Battery | 282-H1 | 2022-08-19 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-01657 | 02653 | 29.76 | Solar & Battery | 4-628-628 | 2022-10-03 | 2022-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-06 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01491 | 01801 | 217.3 | Solar | 375-H3 | 2022-08-19 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-01481 | 02642 | 7.68 | Battery | 4-94A-648 | 2022-08-18 | 2022-08-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-01485 | 02652 | 21.6 | Solar | 4-96-96 | 2022-08-18 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-01-10 | Missing Schedule Z Details - Customer Action Required | Compliances Documents
NSTAR | Woburn | ESMAEX-01493 | 01801 | 237.5 | Solar | 375-H3 | 2022-08-19 | 2022-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01531 | 01778 | 19.398 | Solar | 342-H1 | 2022-09-01 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-01498 | 02472 | 492 | Solar | 370-1327 | 2022-09-29 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01660 | 02453 | 90 | Solar | 33-H1 | 2022-10-05 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Watertown | ESMAEX-01499 | 02472 | 492 | Solar | 305-1422H2 | 2022-09-29 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-21 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-01542 | 02367 | 15.2 | Solar & Battery | 3-50-50 | 2022-09-06 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-01516 | 02453 | 73.3 | Solar | 33-H2 | 2022-08-26 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Ready for PTO | Permission to Operate
NSTAR | Newton Upper Falls | ESMAEX-01543 | 02464 | 15.2 | Solar & Battery | 292-H7 | 2022-09-06 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01509 | 01701 | 17.1 | Solar | 455-H1 | 2022-08-25 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Application Completed/Closed | Online
NSTAR | Green Harbor | ESMAEX-01684 | 02041 | 20.2 | Solar & Battery | 3-27-970 | 2022-10-17 | 2022-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01513 | 01776 | 17.6 | Solar | 342-H6 | 2022-08-25 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-05-09 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01537 | 01748 | 250 | Solar | 65-H7 | 2022-09-02 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01521 | 01778 | 20.2 | Solar & Battery | 342-H3 | 2022-08-29 | 2022-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01525 | 02492 | 15.2 | Solar | 148-H4 | 2022-08-30 | 2022-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01528 | 01803 | 32.85 | Solar | 391-H2 | 2022-08-30 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-01540 | 02050 | 3.8 | Solar | 3-25-42J2 | 2022-09-02 | 2022-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-30 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01619 | 01748 | 16.2 | Solar | 126-H1 | 2022-09-22 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01538 | 01748 | 250 | Solar | 126-H2 | 2022-09-02 | 2022-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01534 | 01720 | 100 | Solar | 416-H4 | 2022-11-21 | 2023-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-01585 | 02468 | 15.2 | Solar & Battery | 292-H7 | 2022-09-14 | 2022-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-01545 | 02186 | 13.44 | Solar | 362-1209H2 | 2022-09-06 | 2022-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01553 | 01760 | 19.8 | Solar | 240-H5 | 2022-09-08 | 2022-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Application Completed/Closed | Online
NSTAR | Newton Highlands | ESMAEX-01549 | 02461 | 6.3 | Solar & Battery | 292-H12 | 2022-09-07 | 2022-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01562 | 01801 | 210 | Solar | 375-H9 | 2022-09-09 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-01673 | 01890 | 17.6 | Solar & Battery | 211-H1 | 2022-10-11 | 2022-11-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-01548 | 01730 | 15.744 | Solar & Battery | 533-H7 | 2022-09-07 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01560 | 02090 | 15.2 | Solar | 456-H4 | 2022-09-09 | 2022-09-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-01633 | 02332 | 15.738 | Solar | 3-26-26 | 2022-09-27 | 2022-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01601 | 02360 | 22.8 | Solar & Battery | 3-71-38J1 | 2022-09-19 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-03 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01636 | 02493 | 20.352 | Solar | 282-H10 | 2022-09-27 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01804 | 02421 | 10 | Battery | 320-H2 | 2022-11-14 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01692 | 01748 | 15.2 | Solar & Battery | 455-H8 | 2022-10-18 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-01589 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-09-14 | 2022-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-01911 | 02138 | 30 | Solar | 831-1111 | 2022-12-09 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | Truro | ESMAEX-01579 | 02666 | 17.6 | Solar & Battery | 4-96-96 | 2022-09-13 | 2022-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-01703 | 02138 | 30 | Solar | 819-1NB2 | 2022-10-21 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01604 | 02130 | 86.4 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-01599 | 02493 | 25 | Solar & Battery | 282-H8 | 2022-09-16 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-01591 | 02667 | 18.816 | Solar | 4-94B-94B | 2022-09-15 | 2022-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-01596 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-09-16 | 2022-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Application Completed/Closed | Online
NSTAR | West Wareham | ESMAEX-01592 | 02576 | 19 | Solar | 3-85-85 | 2022-09-15 | 2022-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01627 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-26 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  | 2023-02-15 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-01664 | 01773 | 19.845 | Solar | 320-H8 | 2022-10-06 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Application Completed/Closed | Online
NSTAR | Newton Lower Falls | ESMAEX-01607 | 02462 | 34 | Solar & Battery | 292-H2 | 2022-09-20 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01623 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-09-23 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01611 | 01720 | 15.3 | Solar | 416-H5 | 2022-09-21 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Application Completed/Closed | Online
NSTAR | Cummaquid | ESMAEX-01616 | 02637 | 9 | Solar | 4-92A-912 | 2022-09-21 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01617 | 01760 | 250 | Solar | 433-H5 | 2022-10-14 | 2022-11-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01624 | 01803 | 18.9 | Solar | 391-H6 | 2022-09-23 | 2022-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01634 | 01701 | 17.92 | Solar | 433-H3 | 2022-09-27 | 2022-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01628 | 02081 | 10 | Solar | 2607 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01629 | 02494 | 17.6 | Solar | 292-H4 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01825 | 01778 | 19.5 | Solar | 342-H1 | 2022-11-17 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01630 | 02030 | 9 | Solar | 456-H5 | 2022-09-26 | 2022-10-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-21 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01644 | 02360 | 25 | Solar | 3-10-10 | 2022-09-29 | 2022-10-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01653 | 01803 | 15.2 | Solar & Battery | 346-1395H1 | 2022-10-03 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-01663 | 01770 | 15.2 | Solar & Battery | 274-H2 | 2022-10-06 | 2022-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01646 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-29 | 2022-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01648 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-09-30 | 2022-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Application Completed/Closed | Online
NSTAR | Onset | ESMAEX-01649 | 02558 | 10 | Battery | 3-88-17J1 | 2022-10-03 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01796 | 01760 | 16.2 | Solar | 2304 | 2022-11-10 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01655 | 01702 | 15.2 | Solar | 24-H1 | 2022-10-03 | 2022-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01714 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01661 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2022-10-05 | 2022-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-01787 | 02719 | 100 | Solar | 2-221-221 | 2022-11-09 | 2022-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01665 | 02360 | 16 | Solar | 3-12-12 | 2022-10-06 | 2022-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-01779 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2022-11-08 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-01669 | 02539 | 37.6 | Solar | 4-75-75 | 2022-10-07 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Westwood | ESMAEX-01668 | 02090 | 15.2 | Solar | 456-H1 | 2022-10-07 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-01670 | 02367 | 17.6 | Solar | 3-50-50 | 2022-10-10 | 2022-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-01675 | 02067 | 250 | Solar | 416-H6 | 2022-10-11 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  |  | Post ISA Technical Review | Technical Review
NSTAR | Natick | ESMAEX-01854 | 01760 | 19.8 | Solar | 240-H1 | 2022-11-28 | 2022-12-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01680 | 02360 | 25 | Solar | 3-10-10 | 2022-10-12 | 2022-10-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01681 | 02492 | 15.2 | Solar & Battery | 391-H11 | 2022-10-13 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-12-20 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01725 | 02364 | 7.6 | Solar & Battery | 3-50-914 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01892 | 01778 | 17.6 | Solar | 342-H1 | 2022-12-06 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-01685 | 01721 | 19.92 | Solar & Battery | 455-H3 | 2022-10-17 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-05 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01690 | 02067 | 16.47 | Solar | 470-H12 | 2022-10-17 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01720 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-01691 | 02717 | 2000 | Solar & Battery | 2-108-108 | 2022-11-17 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Lexington | ESMAEX-01807 | 02420 | 20.2 | Solar & Battery | 391-H11 | 2022-11-14 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01716 | 01720 | 15.2 | Solar & Battery | 512-1399H1 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Application Completed/Closed | Online
NSTAR | North Eastham | ESMAEX-01694 | 02651 | 16 | Solar | 4-94B-646 | 2022-10-19 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-01699 | 02132 | 483 | Solar |  | 2022-10-19 | 2022-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01697 | 02421 | 22.8 | Solar & Battery | 320-H2 | 2022-10-19 | 2022-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01711 | 01776 | 17.6 | Solar & Battery | 342-H7 | 2022-10-24 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01706 | 01741 | 10 | Battery | 512-1399H1 | 2022-10-21 | 2022-11-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-15 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-01740 | 02367 | 15.2 | Solar & Battery | 3-50-43J1 | 2022-10-31 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-01966 | 02717 | 10 | Battery | 2-108-108 | 2023-01-05 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01717 | 02420 | 57 | Solar | 3406 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01718 | 01748 | 15.2 | Solar | 126-H4 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01929 | 01760 | 10 | Battery | 433-H10 | 2022-12-16 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-18 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-01723 | 02601 | 166.6 | Solar | 4-64-64 | 2022-10-25 | 2022-12-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01722 | 02081 | 22.2 | Solar | 2606 | 2022-10-25 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-01726 | 02332 | 9.9 | Solar & Battery | 3-26-26 | 2022-10-26 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Application Completed/Closed | Online
NSTAR | Centerville | ESMAEX-01727 | 02632 | 20 | Solar | 4-82-82 | 2022-10-26 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-01729 | 02667 | 18.9 | Solar |  | 2022-10-26 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-08 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01734 | 02030 | 20 | Solar | 456-H5 | 2022-10-27 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-18 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01739 | 02180 | 7.6 | Solar & Battery | 211-H12 | 2022-10-31 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-01768 | 02026 | 15.2 | Solar & Battery | 456-H4 | 2022-11-04 | 2022-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01757 | 01748 | 12.9 | Solar | 126-H2 | 2022-11-03 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-19 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01736 | 01803 | 21.12 | Solar | 391-H6 | 2022-10-28 | 2023-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-01737 | 02745 | 10 | Solar | 2-105-105 | 2022-10-28 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01738 | 02494 | 20 | Solar & Battery | 148-H1 | 2022-10-28 | 2022-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Application Completed/Closed | Online
NSTAR | Dartmouth | ESMAEX-01745 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dartmouth | ESMAEX-01746 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dartmouth | ESMAEX-01747 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-01775 | 01770 | 9.7 | Solar | 130-H2 | 2022-11-08 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-01771 | 02747 | 15.2 | Solar & Battery | 2-541-541 | 2022-11-04 | 2022-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01784 | 02081 | 15.2 | Solar | 146-H4 | 2022-11-08 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-25 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-01753 | 02330 | 17.7 | Solar | 3-10-10 | 2022-11-02 | 2022-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01974 | 02090 | 120 | Solar | 469-H4 | 2023-01-05 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01756 | 01776 | 16 | Solar | 342-H8 | 2022-11-02 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-01822 | 02493 | 15.2 | Solar & Battery | 342-H1 | 2022-11-16 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-01765 | 02649 | 15.2 | Solar & Battery | 4-77B-454 | 2022-11-03 | 2022-11-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Application Completed/Closed | Online
NSTAR | West Somerville | ESMAEX-01788 | 02144 | 27.57 | Solar & Battery | 1603 | 2022-11-09 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-01970 | 02601 | 100 | Solar | 4-84B-524 | 2023-01-05 | 2023-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01843 | 01748 | 18 | Solar | 126-H3 | 2022-11-23 | 2023-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Application Completed/Closed | Online
NSTAR | Orleans | ESMAEX-01973 | 02653 | 80 | Solar | 4-89B-89B | 2023-01-05 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-01770 | 02021 | 35.2 | Solar & Battery | 470-H7 | 2022-11-04 | 2022-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01773 | 01741 | 15.2 | Solar | 533-H8 | 2022-11-07 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-05-25 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-01774 | 02571 | 66.6 | Solar | 3-86-966 | 2022-11-07 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01798 | 02364 | 180 | Solar | 3-17-17 | 2022-11-10 | 2022-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-16 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-01780 | 02748 | 17.6 | Solar | 2-53-65 | 2022-11-08 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-13 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-01782 | 02056 | 12.6 | Solar & Battery | 65-H1 | 2022-11-08 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-01781 | 02186 | 15.2 | Solar | 362-1209H2 | 2022-11-08 | 2022-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-01778 | 02770 | 15.2 | Solar | 3-702-702 | 2022-11-08 | 2022-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01884 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-12-02 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01785 | 01760 | 13.8 | Solar | 240-H1 | 2022-11-08 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01910 | 01748 | 20 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01795 | 02421 | 15.2 | Solar & Battery | 533-H4 | 2022-11-10 | 2022-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Application Completed/Closed | Online
NSTAR | Freetown | ESMAEX-01812 | 02717 | 249 | Solar | 2-108-108 | 2022-11-15 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-01944 | 01770 | 18.66 | Solar | 274-H2 | 2022-12-23 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01805 | 01803 | 15.2 | Solar & Battery | 391-H7 | 2022-11-14 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01885 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2022-12-02 | 2023-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01811 | 02180 | 10 | Solar & Battery | 375-H2 | 2022-11-15 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-01827 | 02030 | 19.58 | Solar | 456-H3 | 2022-11-17 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | Roslindale | ESMAEX-01858 | 02131 | 6 | Solar & Battery | 496-H5 | 2022-11-29 | 2022-12-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-01831 | 02465 | 31.49 | Solar | 1713 | 2022-11-18 | 2022-12-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01829 | 02081 | 20.06 | Solar | 146-H4 | 2022-11-17 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-01842 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2022-11-22 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01863 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2022-11-29 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01856 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-11-29 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-01835 | 02649 | 17.58 | Solar | 4-452-452 | 2022-11-21 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01837 | 01701 | 20.2 | Solar & Battery | 455-H1 | 2022-11-21 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-01836 | 02571 | 12.9 | Solar | 3-83-83 | 2022-11-21 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-01932 | 01776 | 17.568 | Solar | 342-H7 | 2022-12-16 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01838 | 02492 | 15.2 | Solar & Battery | 148-H4 | 2022-11-21 | 2022-12-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01864 | 02364 | 15.2 | Solar & Battery | 3-15-15 | 2022-11-29 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01871 | 02492 | 4.35 | Solar | 148-H6 | 2022-11-30 | 2022-12-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01851 | 01778 | 187.3 | Solar | 342-H3 | 2022-11-28 | 2022-12-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-01845 | 02332 | 11.4 | Solar & Battery | 3-23-23 | 2022-11-23 | 2022-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-01848 | 02056 | 19.2 | Solar | 65-H1 | 2022-11-26 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-01850 | 02050 | 10 | Solar & Battery | 3-25-42J2 | 2022-11-28 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02179 | 02021 | 240 | Solar | 470-H10 | 2023-02-21 | 2023-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01853 | 02090 | 15.2 | Solar | 456-H4 | 2022-11-28 | 2022-12-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-02077 | 02575 | 30.975 | Solar |  | 2023-01-27 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-05-05 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-01859 | 02330 | 15.2 | Solar | 3-10-10 | 2022-11-29 | 2023-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01868 | 01746 | 15.2 | Solar | 130-H1 | 2022-11-29 | 2022-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01908 | 01748 | 16 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-30 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-01870 | 01803 | 22.272 | Solar | 391-H6 | 2022-11-30 | 2023-02-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01939 | 01701 | 16.104 | Solar | 455-H1 | 2022-12-21 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-01876 | 01701 | 20 | Solar | 455-H4 | 2022-12-01 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01922 | 02067 | 15.2 | Solar | 146-H7 | 2022-12-14 | 2023-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-01947 | 02081 | 15.2 | Solar & Battery | 456-H1 | 2022-12-27 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-01889 | 02021 | 17.28 | Solar | 470-H8 | 2022-12-04 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-01898 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-12-07 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-02046 | 02748 | 10 | Battery | 2-528-528 | 2023-01-20 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-22 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01948 | 01720 | 10 | Battery | 416-H5 | 2022-12-27 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-01891 | 02052 | 17.6 | Solar | 146-H6 | 2022-12-06 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-01903 | 02332 | 10.5 | Solar & Battery | 3-26-26 | 2022-12-08 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01895 | 02090 | 15.2 | Solar | 148-H3 | 2022-12-06 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01902 | 01720 | 16.5 | Solar | 416-H1 | 2022-12-07 | 2022-12-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Application Completed/Closed | Online
NSTAR | East Wareham | ESMAEX-02002 | 02538 | 7.6 | Solar | 3-82-82 | 2023-01-11 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02352 | 01778 | 15 | Battery | 342-H1 | 2023-04-06 | 2023-05-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-05-17 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-01983 | 02739 | 19.5 | Solar | 2-301-305 | 2023-01-09 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-01906 | 01741 | 17.6 | Solar & Battery | 533-H8 | 2022-12-08 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02025 | 02421 | 15.2 | Solar & Battery | 320-H5XY | 2023-01-14 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-01912 | 02601 | 100 | Solar | 4-80B-514 | 2022-12-09 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-01916 | 02421 | 15.372 | Solar | 320-H5XY | 2022-12-12 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-01914 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-12-09 | 2023-01-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-01957 | 02364 | 10 | Battery | 3-50-914 | 2023-01-03 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-01993 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2023-01-10 | 2023-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-01927 | 02719 | 10 | Solar & Battery | 2-222-222 | 2022-12-14 | 2023-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-01921 | 01778 | 15 | Battery | 278-H2 | 2022-12-13 | 2023-01-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-01935 | 02332 | 15 | Solar & Battery | 3-23-23 | 2022-12-20 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Application Completed/Closed | Online
NSTAR | Newton Upper Falls | ESMAEX-01928 | 02464 | 19 | Solar | 292-H2 | 2022-12-14 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01972 | 02090 | 200 | Solar | 456-H5 | 2023-01-05 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-01971 | 02090 | 240 | Solar | 469-H4 | 2023-01-05 | 2023-02-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01931 | 02360 | 3.8 | Solar | 3-12-12 | 2022-12-16 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Application Completed/Closed | Online
NSTAR | Harwichport | ESMAEX-01990 | 02646 | 39.6 | Solar |  | 2023-01-10 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-27 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-02182 | 02050 | 15.2 | Solar | 3-25-25 | 2023-02-21 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01936 | 02360 | 7.6 | Solar | 3-14-934 | 2022-12-20 | 2023-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-24 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-01956 | 01720 | 16.104 | Solar | 416-H8 | 2023-01-03 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-01942 | 02465 | 25.62 | Solar | 1713 | 2022-12-22 | 2023-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-01962 | 02571 | 7.6 | Solar & Battery | 3-84-84 | 2023-01-05 | 2023-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-30 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-01940 | 02026 | 15.2 | Solar | 344-1412H1 | 2022-12-21 | 2023-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-01943 | 02459 | 15.9 | Solar | 292-H11 | 2022-12-22 | 2023-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-18 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-02060 | 02081 | 15.2 | Solar & Battery | 146-H6 | 2023-01-23 | 2023-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-02044 | 02748 | 6.59 | Solar & Battery | 2-2-505 | 2023-01-20 | 2023-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-25 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01961 | 02492 | 39.75 | Solar & Battery | 148-H6 | 2023-01-04 | 2023-01-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02005 | 02052 | 17.934 | Solar | 146-H2 | 2023-01-11 | 2023-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-11 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-01953 | 02790 | 7.6 | Solar & Battery | 2-523-523 | 2023-01-03 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-01965 | 02067 | 19.845 | Solar | LINE48C | 2023-01-05 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02092 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-31 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-01977 | 02492 | 16.836 | Solar | 148-H4 | 2023-01-06 | 2023-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-01978 | 02747 | 250 | Solar | 2-70-502 | 2023-01-06 | 2023-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02001 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-11 | 2023-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-02019 | 02081 | 15.3 | Solar | 146-H8 | 2023-01-13 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-02061 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2023-01-23 | 2023-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-01963 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-05 | 2023-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-01967 | 01746 | 15.2 | Solar | 274-H1 | 2023-01-05 | 2023-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-02890 | 02186 | 19.8 | Solar | 470-H9 | 2023-09-21 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03217 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 | [7 empty] | 0 |  | 0 |  |  |  | Post ISA Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-03216 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Roslindale | ESMAEX-01975 | 02131 | 7.6 | Solar & Battery | 496-H6 | 2023-01-06 | 2023-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-01992 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2023-01-10 | 2023-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02023 | 01778 | 15.2 | Solar | 342-H1 | 2023-01-13 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-18 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-01998 | 02360 | 11.4 | Solar & Battery | 3-89-922 | 2023-01-11 | 2023-02-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-02081 | 01721 | 87 | Solar | 455-H3 | 2023-01-27 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-26 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02004 | 02420 | 15.2 | Solar & Battery | 391-H11 | 2023-01-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Application Completed/Closed | Online
NSTAR | Hatchville | ESMAEX-02000 | 02536 | 17.6 | Solar | 4-78-78 | 2023-01-11 | 2023-02-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-09-06 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02007 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2023-01-12 | 2023-02-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-02047 | 02459 | 15.2 | Solar & Battery | 1708 | 2023-01-20 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-02021 | 02652 | 15 | Battery | 4-96-96 | 2023-01-13 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02110 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-02-03 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Application Completed/Closed | Online
NSTAR | East Brewster | ESMAEX-02011 | 02631 | 18 | Solar | 4-89B-577 | 2023-01-12 | 2023-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Application Completed/Closed | Online
NSTAR | East Wareham | ESMAEX-02014 | 02538 | 360 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-02029 | 02021 | 18.585 | Solar | 269-1320H1 | 2023-01-16 | 2023-02-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02035 | 02052 | 15.2 | Solar & Battery | 146-H2 | 2023-01-17 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02026 | 02056 | 17.6 | Solar | 146-H3 | 2023-01-14 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-09-26 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02027 | 01760 | 16.4 | Solar | 240-H5 | 2023-01-14 | 2023-02-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-02031 | 02743 | 4999 | Solar & Battery | 2-241-241 | 2023-01-17 | 2023-02-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medway | ESMAEX-02114 | 02053 | 10 | Battery | 65-H3 | 2023-02-04 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02057 | 02067 | 20.2 | Solar & Battery | 470-H3 | 2023-01-23 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-17 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02068 | 02492 | 8.027 | Solar | 148-H1 | 2023-01-25 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-30 | Application Completed/Closed | Online
NSTAR | West Roxbury | ESMAEX-02076 | 02132 | 100 | Solar | 496-H3 | 2023-01-27 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02049 | 02474 | 16.5 | Solar | 211-H11 | 2023-01-22 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Freetown | ESMAEX-02038 | 02717 | 4980 | Solar & Battery | 2-102-608 | 2023-05-16 | 2023-06-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Walpole | ESMAEX-02041 | 02081 | 15.2 | Solar & Battery | 2601 | 2023-01-19 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02100 | 01801 | 35.1 | Solar | 211-H5 | 2023-02-01 | 2023-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-02048 | 02465 | 15.36 | Solar | 1703 | 2023-01-20 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02053 | 01760 | 19.84 | Solar | 433-H7 | 2023-01-23 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02054 | 01778 | 15.2 | Solar | 278-H2 | 2023-01-23 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-02105 | 02134 | 66.6 | Solar | 315-H3 | 2023-02-02 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-13 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-02064 | 02747 | 10 | Battery | 2-541-541 | 2023-01-24 | 2023-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-02066 | 02744 | 200 | Solar | 2-24-24 | 2023-03-15 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Acton | ESMAEX-02070 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-25 | 2023-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-02075 | 02717 | 17.6 | Solar | 2-108-108 | 2023-01-26 | 2023-02-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-02083 | 02747 | 312.5 | Solar | 2-543-543 | 2023-07-28 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-02135 | 02130 | 10 | Battery | 284-1300H1 | 2023-02-07 | 2023-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03358 | 02021 | 100 | Solar | 470-H7 | 2024-01-12 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Milton | ESMAEX-02091 | 02186 | 16 | Solar | 470-H9 | 2023-01-30 | 2023-02-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02117 | 02067 | 100 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-02098 | 02115 | 15.2 | Solar & Battery | 5202 | 2023-02-01 | 2023-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02245 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2023-03-08 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-02097 | 01730 | 19.96 | Solar | 533-H7 | 2023-02-01 | 2023-02-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02126 | 02067 | 60 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02108 | 02052 | 15.2 | Solar & Battery | 456-H2 | 2023-02-02 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-02331 | 02744 | 10 | Solar & Battery | 2-25-25 | 2023-03-31 | 2023-04-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02373 | 02139 | 20.06 | Solar | 814-12 | 2023-04-13 | 2023-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02188 | 02138 | 9.6 | Battery | 823-21 | 2023-02-22 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Application Completed/Closed | Online
NSTAR | East Wareham | ESMAEX-02199 | 02538 | 120 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Walpole | ESMAEX-02431 | 02081 | 100 | Solar | 146-H8 | 2023-04-28 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02432 | 01801 | 75 | Solar | 375-H6 | 2023-04-29 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-31 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-02129 | 02081 | 19.52 | Solar | 146-H4 | 2023-02-07 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02157 | 02420 | 19 | Solar | 320-H7 | 2023-02-14 | 2023-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02177 | 02492 | 15.2 | Solar | 148-01 | 2023-02-17 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-05 | Application Completed/Closed | Online
NSTAR | Onset | ESMAEX-02152 | 02558 | 1.28 | Battery | 3-88-17J1 | 2023-02-13 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02136 | 01778 | 16.2 | Solar | 278-H2 | 2023-02-07 | 2023-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Application Completed/Closed | Online
NSTAR | Sagamore Beach | ESMAEX-02140 | 02562 | 15.2 | Solar & Battery | 3-89-925 | 2023-02-08 | 2023-02-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-02150 | 02472 | 120 | Solar | 470-H10 | 2023-02-13 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-02166 | 01890 | 220 | Solar | 211-H13 | 2023-02-15 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-22 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02353 | 02139 | 19.18 | Solar | 817-03 | 2023-04-06 | 2023-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02167 | 02067 | 15.2 | Solar | 146-H1 | 2023-02-16 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-15 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02153 | 02494 | 7.6 | Solar | 148-H1 | 2023-02-13 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-02209 | 02030 | 25.2 | Solar | 456-H5 | 2023-02-27 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-02154 | 02465 | 15.2 | Solar & Battery | 282-H9 | 2023-02-13 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02183 | 01748 | 15.2 | Solar | 455-H8 | 2023-02-21 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02186 | 01801 | 150 | Solar | 211-H2 | 2023-02-22 | 2023-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-06 | Application Completed/Closed | Online
NSTAR | North Truro | ESMAEX-02223 | 02652 | 10.25 | Solar & Battery | 4-96-96 | 2023-03-02 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-29 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-02358 | 02790 | 1350 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-02169 | 01742 | 499 | Battery | 146-H10 | 2023-02-16 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Norfolk | ESMAEX-02208 | 02056 | 200 | Solar | 65-H1 | 2023-02-27 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-02172 | 01702 | 15.2 | Solar & Battery | 240-H4 | 2023-02-17 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02180 | 01720 | 199.9 | Solar | 416-H8 | 2023-02-21 | 2023-03-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-02173 | 01720 | 960 | Solar | 416-H9 | 2023-03-31 | 2023-04-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Needham | ESMAEX-02181 | 02494 | 17.5698 | Solar | 148-H7 | 2023-02-21 | 2023-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02213 | 02090 | 18.3 | Solar | 456-H1 | 2023-02-28 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02187 | 01720 | 160 | Solar & Battery | 416-H5 | 2023-02-22 | 2023-03-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-01-19 | Amended ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Lexington | ESMAEX-02229 | 02421 | 10 | Battery | 320-H5XY | 2023-03-03 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-09 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02195 | 01801 | 166.6 | Solar & Battery | 211-H2 | 2023-02-23 | 2023-03-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02203 | 01746 | 120 | Solar | 65-H2 | 2023-02-24 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2024-07-23 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-02191 | 02019 | 6 | Solar | 65-H4 | 2023-02-22 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-02197 | 02631 | 16 | Solar & Battery | 4-89B-89B | 2023-02-23 | 2023-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-03 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02207 | 02067 | 19 | Solar | 470-H3 | 2023-02-27 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Application Completed/Closed | Online
NSTAR | Brewster | ESMAEX-02212 | 02631 | 15.2 | Solar | 4-89B-576 | 2023-02-28 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02248 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2023-03-08 | 2023-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02218 | 02052 | 100 | Solar | 456-H2 | 2023-03-23 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02219 | 02052 | 480 | Solar | 456-H2 | 2023-03-24 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medfield | ESMAEX-02220 | 02052 | 250 | Solar | 146-H2 | 2023-03-24 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Woburn | ESMAEX-02255 | 01801 | 117.3 | Solar | 375-H14 | 2023-03-09 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-02224 | 02746 | 999 | Solar & Battery | 2-83-403 | 2023-08-08 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Additional Details Required for CR - Customer Action Required | Technical Review
NSTAR | North Dartmouth | ESMAEX-02225 | 02747 | 999 | Solar & Battery | 2-543-543 | 2023-08-08 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Rochester | ESMAEX-03301 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Plymouth | ESMAEX-02240 | 02360 | 16.9 | Solar | 3-71-38J1 | 2023-03-08 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02234 | 02053 | 16.4 | Solar & Battery | 65-H2 | 2023-03-05 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02242 | 01760 | 16.47 | Solar | 240-H1 | 2023-03-08 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-02237 | 02770 | 4980 | Solar & Battery | 3-702-702 | 2023-06-02 | 2023-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Post ISA Technical Review | Technical Review
NSTAR | South Orleans | ESMAEX-02239 | 02662 | 17.4 | Solar | 4-628-628 | 2023-03-07 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-02243 | 02539 | 15 | Solar | 4-75-75 | 2023-03-08 | 2024-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02247 | 01701 | 15.3 | Solar | 342-H4 | 2023-03-08 | 2023-03-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-02249 | 01890 | 8.4 | Solar | 211-H3 | 2023-03-08 | 2023-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-03 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02271 | 02139 | 7.6 | Solar | 817-01 | 2023-03-15 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-12 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-02257 | 02180 | 9.6 | Battery | 375-H2 | 2023-03-10 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Application Completed/Closed | Online
NSTAR | Marstons Mills | ESMAEX-02419 | 02648 | 19.8 | Solar | 4-87A-87A | 2023-04-26 | 2023-05-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-02305 | 02360 | 16.5 | Solar | 3-14-931 | 2023-03-24 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-02263 | 02127 | 34.6 | Solar | 385-H1 | 2023-03-14 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02268 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-03-14 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-07 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02270 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-03-15 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Application Completed/Closed | Online
NSTAR | Barnstable | ESMAEX-02273 | 02630 | 8 | Battery | 4-84B-510 | 2023-03-15 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-02 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-02277 | 02367 | 5559.66 | Solar & Battery | 3-51-51 | 2023-03-17 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Framingham | ESMAEX-02275 | 01701 | 15.2 | Solar | 455-H1 | 2023-03-16 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02286 | 02474 | 100 | Solar | 59-1393H1 | 2023-03-20 | 2023-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02297 | 02090 | 16.47 | Solar | 469-H2 | 2023-03-22 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-02338 | 02130 | 19.47 | Solar | 350-H2 | 2023-04-03 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02281 | 02021 | 19 | Solar | 470-H9 | 2023-03-17 | 2023-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02282 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2023-03-17 | 2023-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-30 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02291 | 01748 | 15.2 | Solar | 455-H8 | 2023-03-21 | 2023-04-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-02292 | 02445 | 20 | Solar | 20N28 | 2023-03-21 | 2023-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02293 | 02021 | 19 | Solar | 470-H6 | 2023-03-21 | 2023-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Application Completed/Closed | Online
NSTAR | South Dartmouth | ESMAEX-02398 | 02748 | 34.6 | Solar | 2-60-63 | 2023-04-20 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Eversource Review Schedule Z | Technical Review
NSTAR | Canton | ESMAEX-02308 | 02021 | 100 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02310 | 02021 | 70 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-02299 | 02717 | 20 | Solar & Battery | 2-108-108 | 2023-03-22 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02319 | 01773 | 10 | Battery | 320-H6 | 2023-03-29 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02332 | 01778 | 18.3 | Solar | 342-H3 | 2023-04-01 | 2023-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-02371 | 02119 | 67.3 | Solar | 52-1487H1 | 2023-04-12 | 2023-05-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-02359 | 02790 | 1200 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-02313 | 02364 | 180 | Solar | 3-14-14 | 2023-04-11 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Holliston | ESMAEX-02318 | 01746 | 7.4 | Battery | 65-H5 | 2023-03-28 | 2023-04-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-02420 | 02125 | 480 | Solar | 511-1495H1 | 2023-04-26 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-02328 | 02493 | 100 | Solar | 450-H7 | 2023-03-31 | 2023-04-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Application Completed/Closed | Online
NSTAR | Truro | ESMAEX-02713 | 02652 | 50 | Solar | 4-96-96 | 2023-07-26 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Application Completed/Closed | Online
NSTAR | Woods Hole | ESMAEX-02335 | 02543 | 40 | Solar | 4-91-91 | 2023-04-03 | 2023-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02333 | 01746 | 20 | Solar & Battery | 130-H1 | 2023-04-03 | 2023-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02337 | 02090 | 360 | Solar | 148-H3 | 2023-06-27 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02346 | 01773 | 20 | Solar | 320-H8 | 2023-04-05 | 2023-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Application Completed/Closed | Online
NSTAR | Marion | ESMAEX-02355 | 02738 | 15.2 | Solar & Battery | 3-702-702 | 2023-04-06 | 2023-04-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-01 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02341 | 01773 | 11.52 | Solar | 342-H1 | 2023-04-04 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-02342 | 02770 | 14.5 | Solar | 3-702-702 | 2023-04-04 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02345 | 02067 | 18.5 | Solar | LINE48C | 2023-04-05 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02349 | 02021 | 15.3 | Solar | 269-1320H1 | 2023-04-05 | 2023-04-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-02347 | 01754 | 7.6 | Solar | 416-H6 | 2023-04-05 | 2023-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-02538 | 01721 | 22.8 | Solar & Battery | 274-H5 | 2023-05-30 | 2023-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02356 | 01748 | 19.9 | Solar & Battery | 126-H4 | 2023-04-06 | 2023-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02366 | 02492 | 15.2 | Solar & Battery | 148-07 | 2023-04-10 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02363 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-04-10 | 2023-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02364 | 01720 | 16.8 | Solar | 416-H5 | 2023-04-10 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-02368 | 02770 | 4999 | Solar & Battery | 3-703-703 | 2023-04-11 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Auburndale | ESMAEX-02380 | 02466 | 67.3 | Solar | 292-H7 | 2023-04-14 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Application Completed/Closed | Online
NSTAR | West Roxbury | ESMAEX-02372 | 02132 | 15.3 | Solar | 468-06 | 2023-04-13 | 2023-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-02376 | 02465 | 15.2 | Solar & Battery | 33-H3 | 2023-04-13 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-02379 | 02030 | 17.6 | Solar | 148-H3 | 2023-04-14 | 2023-05-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-20 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02476 | 01773 | 15.2 | Solar & Battery | 320-H6 | 2023-05-15 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-02401 | 02332 | 13.2 | Solar & Battery | 3-26-26 | 2023-04-21 | 2023-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-22 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-02387 | 02360 | 16 | Solar | 3-10-10 | 2023-04-18 | 2023-05-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-02427 | 02119 | 50 | Solar | 52-1487H1 | 2023-04-28 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-07 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-02389 | 02667 | 6.4 | Battery | 4-94B-94B | 2023-04-19 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-18 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02392 | 01778 | 100 | Solar | 433-H2 | 2023-05-26 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02574 | 02139 | 28.8 | Solar | 819-1NE4 | 2023-06-12 | 2023-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02403 | 01760 | 15 | Battery | 433-H5 | 2023-04-21 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2023-09-22 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-02400 | 02452 | 16 | Solar | 450-H4 | 2023-04-21 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-02402 | 02451 | 15.2 | Solar | 450-H1 | 2023-04-21 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-02406 | 02364 | 15.2 | Solar | 3-909-909 | 2023-04-21 | 2023-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02429 | 02056 | 15 | Battery | 65-H1 | 2023-04-28 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Application Completed/Closed | Online
NSTAR | Somerville | ESMAEX-02814 | 02143 | 25.37 | Solar | 13N14 | 2023-08-15 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-05 | [7 empty] | 0 |  | 0 |  |  |  | Wiring Issue - Customer Action Required | Meter
NSTAR | Sharon | ESMAEX-02413 | 02067 | 250 | Solar | 470-H12 | 2023-05-17 | 2023-06-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Waban | ESMAEX-02444 | 02468 | 25.2 | Solar & Battery | 292-H2 | 2023-05-04 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02416 | 02053 | 15.2 | Solar | 65-H3 | 2023-04-26 | 2023-05-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02417 | 01701 | 17.4 | Solar | 342-H2 | 2023-04-26 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-02424 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2023-04-27 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02426 | 02476 | 67.3 | Solar | 211-H3 | 2023-04-28 | 2023-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-02460 | 02445 | 12.54 | Solar & Battery | 350-H8 | 2023-05-08 | 2023-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02433 | 02067 | 480 | Solar | 146-H1 | 2023-08-04 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-02439 | 02421 | 15.2 | Solar | 320-H2 | 2023-05-02 | 2023-05-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-07-31 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02478 | 01760 | 4.4 | Solar & Battery | 23-H1 | 2023-05-15 | 2023-06-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02449 | 01746 | 19.98 | Solar | 65-H5 | 2023-05-05 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-02441 | 02738 | 2000 | Solar & Battery | 3-85-85 | 2023-08-08 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Ashland | ESMAEX-02440 | 01721 | 15.2 | Solar & Battery | 455-H3 | 2023-05-03 | 2023-05-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Application Completed/Closed | Online
NSTAR | Newton Highlands | ESMAEX-02447 | 02461 | 17.9 | Solar | 292-H16 | 2023-05-05 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-29 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02445 | 02056 | 15.2 | Solar | 65-H1 | 2023-05-04 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-02446 | 02790 | 199 | Solar & Battery | 2-523-523 | 2023-05-04 | 2023-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-02454 | 02421 | 15.2 | Solar | 533-H1 | 2023-05-05 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02455 | 01748 | 15.2 | Solar | 455-H8 | 2023-05-06 | 2023-05-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02453 | 02052 | 19.584 | Solar | 456-H3 | 2023-05-05 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02461 | 02056 | 15.2 | Solar & Battery | 146-H9 | 2023-05-08 | 2023-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02481 | 01701 | 6.39 | Battery | 433-H4 | 2023-05-16 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-02464 | 01770 | 210 | Solar | 240-H1 | 2023-05-09 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-02465 | 01770 | 15.2 | Solar | 274-H2 | 2023-05-09 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-02468 | 01770 | 10 | Solar | 274-H2 | 2023-05-09 | 2023-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02469 | 01748 | 15.2 | Solar | 126-H1 | 2023-05-10 | 2023-05-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02474 | 01701 | 14.1 | Solar | 342-H4 | 2023-05-11 | 2023-05-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Application Completed/Closed | Online
NSTAR | South Truro | ESMAEX-02472 | 02666 | 17.82 | Solar | 4-96-669 | 2023-05-11 | 2023-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-02518 | 02050 | 20 | Solar & Battery | 3-25-42J2 | 2023-05-25 | 2023-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-02477 | 02330 | 14.976 | Solar | 3-51-980 | 2023-05-15 | 2023-06-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-08 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-02654 | 02186 | 48 | Solar | 362-1209H2 | 2023-07-10 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-02487 | 02332 | 15.2 | Solar | 3-26-26 | 2023-05-17 | 2023-05-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02491 | 01701 | 17.1 | Solar | 342-H4 | 2023-05-18 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Application Completed/Closed | Online
NSTAR | North Eastham | ESMAEX-02498 | 02651 | 82.01 | Solar | 4-94A-94A | 2023-05-19 | 2023-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-22 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-02567 | 02770 | 15.3 | Solar | 3-703-703 | 2023-06-07 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-12 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02505 | 02053 | 17.6 | Solar | 65-H1 | 2023-05-22 | 2023-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-02555 | 01730 | 15.2 | Solar | 533-H8 | 2023-06-05 | 2023-06-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02510 | 01720 | 17.1 | Solar | 416-H8 | 2023-05-23 | 2023-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-24 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02509 | 01746 | 15.36 | Solar | 274-H3 | 2023-05-23 | 2023-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02533 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2023-05-26 | 2023-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2025-02-14 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-02592 | 02330 | 50 | Solar | 3-10-10 | 2023-06-16 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-02602 | 02134 | 100 | Solar | 329-H5 | 2023-06-22 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02513 | 02053 | 18 | Solar | 65-H1 | 2023-05-24 | 2023-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-21 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02516 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2023-05-24 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02587 | 02021 | 25.5 | Solar | 470-H9 | 2023-06-15 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-02558 | 02186 | 22.4 | Solar | 496-H7 | 2023-06-06 | 2023-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-02519 | 02747 | 200 | Solar | 2-543-543 | 2023-05-25 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Canton | ESMAEX-02521 | 02021 | 15.2 | Solar | 470-H1 | 2023-05-25 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-02526 | 02026 | 250 | Solar |  | 2023-07-06 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Orleans | ESMAEX-02525 | 02643 | 6 | Solar | 4-628-628 | 2023-05-26 | 2023-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-02527 | 02026 | 120 | Solar | 456-H4 | 2023-07-10 | 2023-07-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-02612 | 02360 | 50 | Solar | 3-12-932 | 2023-06-23 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-09 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02530 | 01748 | 22.8 | Solar & Battery | 126-H4 | 2023-05-26 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-06-19 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02562 | 01801 | 200 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Woburn | ESMAEX-02565 | 01801 | 150 | Solar | 211-H2 | 2023-06-07 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Woburn | ESMAEX-02537 | 01801 | 10 | Battery | 211-H6 | 2023-05-30 | 2023-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Application Completed/Closed | Online
NSTAR | Truro | ESMAEX-02539 | 02666 | 17.16 | Solar & Battery | 4-96-96 | 2023-05-30 | 2023-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-02563 | 01801 | 240 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Woburn | ESMAEX-02564 | 01801 | 200 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Medway | ESMAEX-02561 | 02053 | 200 | Solar | 65-H2 | 2023-06-06 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-15 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02545 | 02021 | 16 | Solar | 470-H9 | 2023-06-01 | 2023-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02544 | 02421 | 100 | Solar | 320-H5XY | 2023-07-07 | 2023-07-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-30 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-02550 | 02026 | 200 | Solar | 20-H5 | 2023-06-02 | 2023-06-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | South Dartmouth | ESMAEX-02553 | 02748 | 20.1 | Solar | 2-528-528 | 2023-06-02 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-19 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-02569 | 01741 | 15.36 | Solar | 533-H8 | 2023-06-08 | 2023-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Application Completed/Closed | Online
NSTAR | Dennisport | ESMAEX-02976 | 02639 | 18 | Solar | 4-92B-583 | 2023-09-28 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-02674 | 02138 | 200 | Solar | 831-1332 | 2023-07-13 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Stoneham | ESMAEX-02566 | 02180 | 20 | Solar | 375-H8 | 2023-06-07 | 2023-06-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-02717 | 02135 | 200 | Solar | 467-H9 | 2023-07-26 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02581 | 01760 | 7.6 | Solar & Battery | 240-H3 | 2023-06-14 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-02577 | 02030 | 7.6 | Solar & Battery | 456-H5 | 2023-06-12 | 2023-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-02572 | 01803 | 25.728 | Solar | 375-H6 | 2023-06-09 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-02576 | 02770 | 20 | Solar | 3-703-703 | 2023-06-12 | 2023-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-02600 | 02458 | 16 | Solar | 277-05 | 2023-06-21 | 2023-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-06 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02579 | 01760 | 14 | Battery | 433-H5 | 2023-06-13 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-02608 | 02050 | 10 | Battery | 3-25-25 | 2023-06-23 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-02642 | 02467 | 100 | Solar | 292-H5 | 2023-07-06 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chestnut Hill | ESMAEX-02646 | 02467 | 62.5 | Solar | 292-H5 | 2023-07-07 | 2023-07-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chestnut Hill | ESMAEX-02586 | 02467 | 19 | Solar | 350-H7 | 2023-06-14 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02589 | 02494 | 15.2 | Solar | 148-H1 | 2023-06-16 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02676 | 02090 | 15.36 | Solar | 148-H3 | 2023-07-15 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02590 | 01748 | 19.968 | Solar | 126-H4 | 2023-06-16 | 2023-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-02673 | 02186 | 15.2 | Solar & Battery | 496-H7 | 2023-07-13 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-07 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-02595 | 02332 | 16.64 | Solar | 3-27-970 | 2023-06-20 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Marshfield | ESMAEX-02616 | 02050 | 19 | Solar | 3-24B-915 | 2023-06-26 | 2023-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02596 | 02420 | 25 | Solar | 533-H9 | 2023-06-20 | 2023-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-01 | [7 empty] | 0 |  | 0 |  |  | 2024-05-13 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02718 | 02138 | 60 | Solar |  | 2023-07-26 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-02755 | 02115 | 120 | Solar | 452-1401 | 2023-08-04 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02601 | 01778 | 20 | Solar | 342-H1 | 2023-06-22 | 2023-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Application Completed/Closed | Online
NSTAR | East Wareham | ESMAEX-02609 | 02538 | 10 | Battery | 3-82-82 | 2023-06-23 | 2023-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-02607 | 02052 | 30 | Solar | 456-H3 | 2023-06-23 | 2023-07-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02615 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-06-26 | 2023-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-18 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02618 | 02067 | 3.9 | Solar | 470-H12 | 2023-06-27 | 2023-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Application Completed/Closed | Online
NSTAR | West Wareham | ESMAEX-02629 | 02576 | 10 | Solar | 3-86-966 | 2023-06-29 | 2023-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-02620 | 02139 | 7.6 | Solar | 817-01 | 2023-06-27 | 2023-06-27 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02636 | 01746 | 11.712 | Solar & Battery | 274-H3 | 2023-07-05 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Application Completed/Closed | Online
NSTAR | South Chatham | ESMAEX-02644 | 02659 | 10 | Battery | 4-95A-95A | 2023-07-07 | 2023-07-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-02628 | 02493 | 19.72 | Solar | 282-H10 | 2023-06-29 | 2023-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02627 | 02021 | 18.1 | Solar & Battery | 269-1320H1 | 2023-06-28 | 2023-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-02635 | 01730 | 196.99 | Solar | 533-H3 | 2023-06-30 | 2023-07-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-23 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02633 | 02090 | 13.056 | Solar | 456-H4 | 2023-06-30 | 2023-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-21 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-02657 | 02032 | 15.2 | Solar | 146-H4 | 2023-07-10 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-02745 | 01741 | 16 | Solar | 512-1399H1 | 2023-08-02 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-03936 | 02770 | 20 | Solar | 3-703-703 | 2024-07-30 | 2024-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02875 | 02421 | 19.8 | Solar | 320-H2 | 2023-08-29 | 2023-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-02645 | 02747 | 200 | Solar | 2-541-541 | 2023-10-06 | 2023-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-02648 | 01702 | 15.2 | Solar | 455-H3 | 2023-07-07 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-02660 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-11 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Arlington | ESMAEX-02707 | 02476 | 150 | Solar |  | 2023-07-24 | 2023-08-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Norfolk | ESMAEX-02658 | 02056 | 140 | Solar | 146-H3 | 2023-07-28 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02659 | 02056 | 100 | Solar | 146-H3 | 2023-07-28 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mashpee | ESMAEX-02671 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-13 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02664 | 02476 | 4.39 | Solar | 211-H11 | 2023-07-12 | 2023-07-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-07 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-02667 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-13 | 2023-07-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-02678 | 02445 | 200 | Solar | 350-H7 | 2023-07-17 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02686 | 02474 | 20 | Solar | 59-1383H1 | 2023-07-18 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-07-26 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-02677 | 02180 | 180 | Solar | 375-H2 | 2023-07-17 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-02876 | 02745 | 199 | Solar | 2-102-102 | 2023-08-29 | 2023-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Winchester | ESMAEX-02690 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-19 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Application Completed/Closed | Online
NSTAR | Sandwich | ESMAEX-02681 | 02563 | 200 | Solar | 4-81A-81A | 2023-07-17 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-02680 | 02090 | 17.28 | Solar | 456-H4 | 2023-07-17 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-02751 | 02122 | 10 | Battery | 511-1498H1 | 2023-08-04 | 2023-08-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-02803 | 02667 | 17.4 | Battery | 4-94B-94B | 2023-10-27 | 2023-09-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-09 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02827 | 01773 | 25.8 | Solar & Battery | 320-H6 | 2023-08-17 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02783 | 02492 | 15.2 | Solar | 148-H4 | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-08-23 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-02687 | 01803 | 17.4 | Solar | 391-H6 | 2023-07-19 | 2023-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-02688 | 02465 | 16 | Solar | 316-05 | 2023-07-19 | 2023-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-02693 | 02332 | 19 | Solar | 3-24B-24B | 2023-07-20 | 2023-08-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-21 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02703 | 02420 | 15.2 | Solar | 533-H9 | 2023-07-21 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03180 | 01803 | 240 | Solar | 391-H16 | 2023-11-20 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02705 | 02090 | 15.2 | Solar | 148-H3 | 2023-07-24 | 2023-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02825 | 02341 | 27.3 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-03169 | 02119 | 67.3 | Solar | 396-1050H4 | 2023-11-17 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-02781 | 01803 | 15.68 | Solar | 346-1395H1 | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-02824 | 02053 | 50 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-02813 | 01741 | 7.8 | Solar & Battery | 512-1399H1 | 2023-08-15 | 2023-09-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-06 | [7 empty] | 0 |  | 0 |  |  | 2024-06-24 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-02711 | 02364 | 18.3 | Solar | 3-18-18 | 2023-07-26 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Ashland | ESMAEX-02740 | 01721 | 200 | Solar | 274-H1 | 2023-08-01 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-02 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-02734 | 02633 | 19.14 | Solar | 4-95B-95B | 2023-08-01 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02722 | 02492 | 20.2 | Solar & Battery | 148-02 | 2023-07-28 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-02730 | 01890 | 200 | Fuel Cell | 211-H1 | 2023-07-31 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-02733 | 01803 | 1500 | Fuel Cell | 391-H13 | 2023-07-31 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Hyannis | ESMAEX-02732 | 02601 | 200 | Fuel Cell | 4-63-521 | 2023-07-31 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-02731 | 02138 | 550 | Fuel Cell | 819-1NB5 | 2023-07-31 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Arlington | ESMAEX-02744 | 02474 | 13 | Solar & Battery | 211-H11 | 2023-08-01 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02724 | 02067 | 15.2 | Solar | 146-H8 | 2023-07-28 | 2023-08-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-02726 | 02130 | 10 | Battery | 284-07 | 2023-07-30 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-02728 | 02030 | 10 | Battery | 456-H3 | 2023-07-31 | 2023-08-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02729 | 01773 | 699.3 | Solar | 320-H6 | 2023-11-01 | 2024-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-04016 | 02210 | 80 | Solar | 99-H2 | 2024-08-29 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-02772 | 02054 | 17.28 | Battery | 65-H1 | 2023-08-08 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03392 | 02139 | 30 | Solar | 816-04 | 2024-01-29 | 2024-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  | 2025-04-03 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02739 | 01746 | 480 | Solar | 274-H1 | 2023-09-01 | 2023-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02747 | 01773 | 15.2 | Solar & Battery | 320-H8 | 2023-08-02 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03046 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2023-10-12 | 2023-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02919 | 01701 | 60 | Solar | 433-H4 | 2023-09-14 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02779 | 02492 | 200 | Fuel Cell | 148-03 | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-02746 | 02030 | 15.2 | Solar | 456-H5 | 2023-08-02 | 2023-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-02760 | 02459 | 8.7 | Solar & Battery | 369-06 | 2023-08-07 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02748 | 02420 | 19 | Solar | 351-01 | 2023-08-03 | 2023-08-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | East Freetown | ESMAEX-02750 | 02717 | 15.744 | Solar | 2-108-108 | 2023-08-03 | 2023-08-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Application Completed/Closed | Online
NSTAR | East Cambridge | ESMAEX-02775 | 02141 | 1550 | Fuel Cell | 875-1N23B | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Burlington | ESMAEX-02777 | 01803 | 200 | Fuel Cell | 391-H6 | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newtonville | ESMAEX-02776 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-09 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Walpole | ESMAEX-02761 | 02081 | 15.2 | Solar & Battery | 146-H4 | 2023-08-07 | 2023-09-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02857 | 01748 | 15.2 | Solar | 455-H8 | 2023-08-23 | 2023-09-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-02796 | 01720 | 19.39 | Solar | 416-H5 | 2023-08-11 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-11-13 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-02762 | 01741 | 17.1 | Solar | 512-1399H1 | 2023-08-07 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-02771 | 02446 | 15.36 | Solar | 315-H8 | 2023-08-08 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Newtonville | ESMAEX-02784 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-10 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Needham | ESMAEX-02807 | 02494 | 9.6 | Solar & Battery | 148-H4 | 2023-08-14 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-02805 | 01770 | 20 | Solar | 456-H5 | 2023-08-14 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Eversource Review Schedule Z | Technical Review
NSTAR | Holliston | ESMAEX-02786 | 01746 | 10 | Solar & Battery | 130-H1 | 2023-08-10 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-02793 | 02493 | 15.2 | Solar | 282-H10 | 2023-08-10 | 2023-08-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02800 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-08-11 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-02879 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-08-31 | 2023-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02801 | 01701 | 10 | Battery | 342-H9 | 2023-08-11 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-02802 | 02451 | 5 | Battery | 450-H1 | 2023-08-11 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02810 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2023-08-14 | 2023-09-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-05 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02831 | 02056 | 15.2 | Solar | 146-H10 | 2023-08-17 | 2023-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-29 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02816 | 01773 | 15 | Solar & Battery | 282-H1 | 2023-08-15 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Application Completed/Closed | Online
NSTAR | West Roxbury | ESMAEX-02817 | 02132 | 18.88 | Solar | 496-H6 | 2023-08-15 | 2023-08-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-18 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02820 | 02021 | 10.368 | Solar | 269-1321H2 | 2023-08-16 | 2023-10-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02832 | 01748 | 120 | Solar | 126-H2 | 2023-08-18 | 2023-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-02840 | 02739 | 4980 | Solar & Battery | 2-301-301 | 2023-09-27 | 2023-10-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-02842 | 02493 | 19 | Solar | 342-H1 | 2023-08-18 | 2023-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-02844 | 02056 | 15.2 | Solar & Battery | 65-H1 | 2023-08-18 | 2023-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03544 | 02459 | 20 | Solar | 1701 | 2024-03-18 | 2024-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Lexington | ESMAEX-02850 | 02420 | 15.2 | Solar | 533-H9 | 2023-08-21 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02848 | 01701 | 7.6 | Solar | 433-H3 | 2023-08-21 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-17 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-02851 | 01803 | 17.6 | Solar | 391-H7 | 2023-08-22 | 2023-09-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-21 | Application Completed/Closed | Online
NSTAR | Auburndale | ESMAEX-02860 | 02466 | 5 | Battery | 292-H7 | 2023-08-23 | 2023-09-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-02865 | 02026 | 60 | Solar |  | 2023-08-25 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-08 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02868 | 01778 | 17.1 | Solar | 342-H1 | 2023-08-25 | 2023-09-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-02931 | 01741 | 19.8 | Solar | 512-1399H1 | 2023-09-18 | 2023-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-03210 | 02128 | 60 | Solar | 488-H8 | 2023-12-01 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02873 | 01760 | 13.05 | Solar | 240-H1 | 2023-08-28 | 2023-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-02884 | 01803 | 16.8 | Solar | 346-1395H1 | 2023-09-01 | 2023-10-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02980 | 02492 | 19.8 | Solar & Battery | 148-H1 | 2023-09-28 | 2023-10-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-14 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-02877 | 01702 | 20 | Solar | 240-H6 | 2023-08-29 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-16 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-02886 | 02474 | 50 | Solar | 59-1393H1 | 2023-09-01 | 2023-09-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-28 | [7 empty] | 0 |  | 0 |  |  |  | Amended ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Framingham | ESMAEX-02932 | 01701 | 15.2 | Solar | 433-H8 | 2023-09-19 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-02896 | 01778 | 15.2 | Solar | 342-H1 | 2023-09-07 | 2023-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-02917 | 02445 | 16.2 | Solar | 350-H3 | 2023-09-13 | 2023-09-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Boston | ESMAEX-03020 | 02210 | 300 | Solar | 99-H2 | 2023-10-04 | 2023-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Ready for PTO | Permission to Operate
NSTAR | East Walpole | ESMAEX-03053 | 02032 | 15.2 | Solar | 146-H4 | 2023-10-16 | 2023-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-02898 | 02743 | 1.5 | Solar & Battery | 2-230-230 | 2023-09-08 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02905 | 01748 | 199 | Solar | 126-H2 | 2023-09-11 | 2023-09-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03061 | 02090 | 10 | Battery | 148-H3 | 2023-10-17 | 2023-11-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-02929 | 02747 | 15.2 | Solar | 2-70-502 | 2023-09-18 | 2023-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-02911 | 01746 | 20 | Solar & Battery | 130-H2 | 2023-09-12 | 2023-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-02934 | 02032 | 15.2 | Solar | 146-H4 | 2023-09-19 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-02909 | 02186 | 16.53 | Solar & Battery | 496-H7 | 2023-09-12 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-02936 | 02452 | 15.2 | Solar | 450-H4 | 2023-09-19 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Application Completed/Closed | Online
NSTAR | Falmouth | ESMAEX-02922 | 02540 | 15 | Battery | 4-72-72 | 2023-09-15 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-06-20 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03028 | 01701 | 10 | Battery | 278-H2 | 2023-10-06 | 2023-10-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-01-26 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02926 | 02090 | 10 | Battery | 469-H2 | 2023-09-15 | 2023-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-02920 | 02067 | 15.04 | Solar | 146-H7 | 2023-09-14 | 2023-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-02930 | 02030 | 5 | Battery | 456-H5 | 2023-09-18 | 2023-10-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-03167 | 02332 | 30 | Solar | 3-23-23 | 2023-11-17 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-02955 | 02081 | 15.2 | Solar | 146-H6 | 2023-09-26 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03044 | 02140 | 300 | Solar | 828-1NC8 | 2023-11-08 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Duxbury | ESMAEX-02921 | 02332 | 14 | Battery | 3-24B-24B | 2023-09-15 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-06 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Application Completed/Closed | Online
NSTAR | Fairhaven | ESMAEX-02923 | 02719 | 15 | Battery | 2-230-230 | 2023-09-15 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-05-19 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-02925 | 01748 | 11.4 | Solar | 274-H5 | 2023-09-15 | 2023-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-02959 | 02021 | 15.2 | Solar & Battery | 269-1321H2 | 2023-09-26 | 2023-10-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-30 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-03017 | 02119 | 20 | Solar | 143-151H1 | 2023-10-04 | 2023-11-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-02933 | 02090 | 19.968 | Solar | 148-H3 | 2023-09-19 | 2023-10-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-02947 | 02360 | 77.3 | Solar | 3-13-943 | 2023-09-22 | 2024-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-03003 | 02030 | 16.2 | Solar | 456-H3 | 2023-10-03 | 2023-10-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Application Completed/Closed | Online
NSTAR | Charlestown | ESMAEX-02954 | 02129 | 80 | Solar | 218-80H | 2023-09-25 | 2023-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-02998 | 01760 | 15.2 | Solar | 433-H7 | 2023-10-02 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-02951 | 01803 | 66.6 | Solar | 375-H6 | 2023-09-22 | 2023-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-13 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-02995 | 01773 | 3.8 | Solar & Battery | 320-H6 | 2023-10-02 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-02997 | 02081 | 7.6 | Solar | 146-H4 | 2023-10-02 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-02991 | 02492 | 20.1 | Solar | 148-01 | 2023-09-29 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-02956 | 02453 | 10 | Solar | 467-H5 | 2023-09-26 | 2023-10-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-03023 | 02539 | 400 | Battery |  | 2023-10-25 | 2024-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Winchester | ESMAEX-03063 | 01890 | 72.2 | Solar | 211-H11 | 2023-10-18 | 2023-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-02986 | 02472 | 16.47 | Solar | 467-H8 | 2023-09-29 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-02960 | 01721 | 10 | Solar | 519-175H1 | 2023-09-26 | 2023-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-26 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Brookline | ESMAEX-02973 | 02467 | 35 | Internal Combustion Engine |  | 2023-09-27 | 2023-10-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-02985 | 01702 | 250 | Solar | 240-H3 | 2023-10-27 | 2023-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-03070 | 02138 | 12.3 | Solar & Battery | 817-09 | 2023-10-19 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-03001 | 02150 | 30.4 | Solar | 488-H6 | 2023-10-02 | 2023-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-02989 | 02717 | 10 | Solar | 2-108-108 | 2023-09-29 | 2023-10-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-02994 | 02745 | 999 | Solar & Battery | 2-151-151 | 2023-09-29 | 2023-10-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Burlington | ESMAEX-02999 | 01803 | 15.8 | Solar | 391-H7 | 2023-10-02 | 2023-10-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03007 | 01760 | 17.28 | Solar | 240-H1 | 2023-10-03 | 2023-10-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-03016 | 02210 | 999 | Solar & Battery | 151-140H | 2023-12-22 | 2024-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Newtonville | ESMAEX-03021 | 02460 | 20 | Solar & Battery | 277-04 | 2023-10-04 | 2023-10-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Jamaica Plain | ESMAEX-03407 | 02130 | 15 | Battery | 496-H4 | 2024-02-01 | 2024-02-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03027 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2023-10-05 | 2023-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03030 | 02139 | 487.5 | Solar | 828-1369 | 2023-10-06 | 2023-10-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Cambridge | ESMAEX-03029 | 02139 | 375 | Solar | 828-1370 | 2023-10-06 | 2023-10-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Arlington | ESMAEX-03265 | 02474 | 21.66 | Solar & Battery | 211-H11 | 2023-12-12 | 2024-01-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-03032 | 01754 | 19.5 | Solar | 416-H6 | 2023-10-09 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03037 | 01760 | 20 | Solar | 240-H5 | 2023-10-11 | 2023-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03038 | 02067 | 23.36 | Solar | 470-H12 | 2023-10-11 | 2023-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-05 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Hopkinton | ESMAEX-03043 | 01748 | 18.816 | Solar | 126-H1 | 2023-10-12 | 2023-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-03161 | 01801 | 20 | Battery | 211-H13 | 2023-11-15 | 2023-12-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03049 | 01803 | 20.8 | Solar | 391-H7 | 2023-10-13 | 2023-11-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03055 | 01748 | 15.2 | Solar | 126-H2 | 2023-10-16 | 2023-11-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-03054 | 01741 | 17.6 | Battery | 533-H8 | 2023-10-16 | 2023-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03079 | 01701 | 18.9 | Solar | 342-H5 | 2023-10-23 | 2023-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-03058 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Framingham | ESMAEX-03059 | 01701 | 20 | Solar | 342-H4 | 2023-10-17 | 2023-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03069 | 02021 | 5 | Solar & Battery | 269-1321H2 | 2023-10-19 | 2023-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03071 | 01701 | 498 | Solar | 455-H1 | 2023-10-19 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-03073 | 01741 | 15.7 | Solar | 533-H8 | 2023-10-19 | 2023-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03077 | 02493 | 16.25 | Solar | 282-H10 | 2023-10-22 | 2023-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-03076 | 01778 | 1 | Battery | 342-H1 | 2023-10-20 | 2023-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-03273 | 02130 | 16.8 | Solar | 496-H4 | 2023-12-13 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03177 | 01748 | 15.2 | Solar | 126-H4 | 2023-11-20 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03078 | 01720 | 250 | Solar | 416-H8 | 2024-02-26 | 2024-03-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-03178 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-11-20 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03084 | 02090 | 19 | Solar | 456-H1 | 2023-11-07 | 2023-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03155 | 01803 | 15.2 | Solar | 391-H7 | 2023-11-15 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-03091 | 01770 | 5 | Battery | 130-H2 | 2023-10-26 | 2023-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-03130 | 02119 | 100 | Solar | 396-05 | 2023-11-08 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-31 | Application Completed/Closed | Online
NSTAR | Truro | ESMAEX-03089 | 02666 | 9.9 | Solar | 4-96-96 | 2023-10-25 | 2023-11-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03133 | 02186 | 15.2 | Solar | 4303 | 2023-11-08 | 2023-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03110 | 02067 | 15 | Battery | 470-H12 | 2023-11-02 | 2023-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-03100 | 01778 | 50 | Solar | 342-H3 | 2023-10-31 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-03098 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2023-10-30 | 2023-11-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-27 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03149 | 01760 | 240 | Solar | 433-H11 | 2023-11-14 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Rochester | ESMAEX-03258 | 02770 | 56.14 | Solar | 3-702-702 | 2023-12-07 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03154 | 01720 | 23 | Solar & Battery | 416-H5 | 2023-11-15 | 2023-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03102 | 01701 | 19.2 | Solar | 278-H2 | 2023-10-31 | 2023-11-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03122 | 01720 | 14 | Battery | 416-H2 | 2023-11-07 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-09 | [7 empty] | 0 |  | 0 |  |  | 2024-04-02 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-03116 | 02465 | 20.125 | Battery | 282-H9 | 2023-11-03 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-16 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03134 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2023-11-08 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-20 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-03114 | 02601 | 499.5 | Solar | 4-84B-524 | 2023-12-06 | 2024-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyannis | ESMAEX-03148 | 02601 | 150 | Solar | 4-84B-524 | 2023-11-14 | 2023-12-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Arlington | ESMAEX-03117 | 02474 | 67.3 | Solar | 211-H3 | 2023-11-03 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-03135 | 02111 | 24.4 | Solar | 514-1N25S | 2024-08-14 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03146 | 02139 | 30 | Solar | 831-1394 | 2023-11-14 | 2023-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03147 | 02139 | 40 | Solar | 831-1303 | 2023-11-14 | 2023-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03166 | 02458 | 2.24 | Solar | 277-05 | 2023-11-16 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-03131 | 02030 | 5 | Battery | 456-H5 | 2023-11-08 | 2023-11-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-04 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03140 | 02090 | 8.64 | Solar | 148-H3 | 2023-11-10 | 2023-11-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03393 | 02139 | 60 | Solar |  | 2024-01-29 | 2024-02-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03165 | 02458 | 15.3 | Solar | 277-05 | 2023-11-16 | 2023-12-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-03138 | 02657 | 19.9 | Solar & Battery | 4-675-675 | 2023-11-10 | 2023-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03151 | 01702 | 20 | Solar | 240-H6 | 2023-11-14 | 2023-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-08 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03182 | 01748 | 10 | Battery | 126-H2 | 2023-11-21 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03143 | 01720 | 15.2 | Solar | 416-H5 | 2023-11-13 | 2023-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-03183 | 02494 | 15.2 | Solar | 148-H4 | 2023-11-21 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-16 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-03144 | 02135 | 15.3 | Solar | 315-H10 | 2023-11-13 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-03159 | 02053 | 80 | Solar | 65-H3 | 2023-12-15 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-13 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-03158 | 02633 | 15.2 | Solar | 4-95B-95B | 2023-11-15 | 2023-12-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-15 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03162 | 02451 | 100 | Solar | 282-H1 | 2023-11-15 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-03163 | 01746 | 20 | Battery | 65-H5 | 2023-11-16 | 2023-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Application Completed/Closed | Online
NSTAR | Newton Highlands | ESMAEX-03164 | 02461 | 15.2 | Solar | 292-H3 | 2023-11-16 | 2023-11-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03175 | 02493 | 22.2 | Solar | 282-H8 | 2023-11-20 | 2024-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03320 | 02493 | 15.6 | Solar | 282-H1 | 2023-12-29 | 2024-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-08 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-03181 | 01721 | 10 | Battery | 455-H8 | 2023-11-21 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-03187 | 01890 | 490 | Solar | 211-07 | 2023-12-11 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-03189 | 01748 | 15.744 | Solar | 126-H2 | 2023-11-22 | 2023-12-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-03195 | 02360 | 6 | Solar | 3-14-934 | 2023-11-27 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03202 | 02452 | 15.2 | Solar | 450-H6 | 2023-11-29 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-08-12 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-03339 | 02740 | 250 | Solar | 2-89-94 | 2024-01-08 | 2024-01-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Milton | ESMAEX-03206 | 02186 | 20 | Solar | 311-04 | 2023-11-29 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Application Completed/Closed | Online
NSTAR | Billerica | ESMAEX-03207 | 01821 | 10 | Solar & Battery | 533-H7 | 2023-11-30 | 2023-12-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-03281 | 01778 | 12.21 | Solar | 342-H1 | 2023-12-14 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-03255 | 01770 | 18.56 | Solar | 240-H1 | 2023-12-06 | 2024-01-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-01 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03212 | 02420 | 23 | Solar & Battery | 3406 | 2023-12-01 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03261 | 01803 | 34.5 | Solar & Battery | 346-1395H1 | 2023-12-08 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-03209 | 02476 | 490 | Solar | 211-H3 | 2023-12-28 | 2024-01-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-03307 | 02090 | 15.2 | Solar & Battery | 148-H3 | 2023-12-21 | 2024-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Application Completed/Closed | Online
NSTAR | Chilmark | ESMAEX-03230 | 02535 | 11.4 | Solar | 4-97-97 | 2023-12-05 | 2024-02-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Application Completed/Closed | Online
NSTAR | West Brewster | ESMAEX-03274 | 02631 | 20.44 | Solar | 4-89A-89A | 2023-12-13 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03260 | 02420 | 16.64 | Solar | 533-H9 | 2023-12-08 | 2023-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-10 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03335 | 02186 | 15.2 | Solar | 362-1209H2 | 2024-01-04 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-03302 | 02459 | 20.2 | Solar & Battery | 292-H6 | 2023-12-20 | 2024-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-08 | [7 empty] | 0 |  | 0 |  |  | 2025-08-07 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03395 | 02142 | 120 | Solar |  | 2024-01-29 | 2024-02-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Millis | ESMAEX-03263 | 02054 | 19 | Solar & Battery | 130-H2 | 2023-12-11 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-03264 | 02717 | 15.36 | Solar | 2-108-108 | 2023-12-12 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03269 | 02090 | 23 | Solar & Battery | 456-H1 | 2023-12-12 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03272 | 01748 | 15.2 | Solar | 126-H4 | 2023-12-13 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-03277 | 02657 | 19.8 | Solar | 4-675-675 | 2023-12-14 | 2024-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-05-02 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03278 | 02420 | 15.2 | Solar | 351-02 | 2023-12-14 | 2024-01-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-03 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03348 | 01720 | 50 | Solar | 416-H5 | 2024-01-09 | 2024-01-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-08-21 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03398 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-01-30 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03289 | 02421 | 17.6 | Solar & Battery | 450-H5 | 2023-12-19 | 2024-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-03291 | 02050 | 999 | Other | 3-24B-915 | 2024-06-12 | 2024-07-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Lexington | ESMAEX-03387 | 02421 | 1836 | Solar & Battery | 319-1377 | 2024-06-06 | 2024-07-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Upload Technical Documents Customer Action Required | Technical Review
NSTAR | Natick | ESMAEX-03384 | 01760 | 16.8 | Solar | 240-H5 | 2024-01-25 | 2024-02-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03313 | 02420 | 15.2 | Solar | 391-H11 | 2023-12-27 | 2024-01-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03532 | 02421 | 17.6 | Solar & Battery | 3402 | 2024-03-12 | 2024-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-03362 | 01776 | 43.01 | Solar & Battery | 416-H6 | 2024-01-16 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03351 | 02067 | 12.6 | Solar & Battery | 470-H3 | 2024-01-10 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-20 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-03324 | 02052 | 23 | Solar & Battery | 456-H2 | 2024-01-03 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-03333 | 02130 | 50 | Solar | 496-H4 | 2024-01-04 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03376 | 01748 | 4.8 | Solar & Battery | 126-H2 | 2024-01-22 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03366 | 02458 | 22.8 | Solar & Battery | 467-H3 | 2024-01-17 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-03369 | 02180 | 10 | Battery | 375-H7 | 2024-01-18 | 2024-02-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-13 | Application Completed/Closed | Online
NSTAR | East Walpole | ESMAEX-03354 | 02032 | 7.6 | Solar | 146-H4 | 2024-01-10 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03391 | 02139 | 160 | Solar |  | 2024-01-29 | 2024-02-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-03341 | 01746 | 7.6 | Solar | 65-H2 | 2024-01-09 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-03353 | 01778 | 16 | Solar | 342-H1 | 2024-01-10 | 2024-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03357 | 01701 | 30.66 | Solar & Battery | 455-H1 | 2024-01-12 | 2024-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-03423 | 02139 | 20 | Solar | 814-12 | 2024-02-07 | 2024-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03422 | 02139 | 20 | Solar | 815-10 | 2024-02-07 | 2024-02-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Somerville | ESMAEX-03421 | 02145 | 25 | Solar | 387-148H2 | 2024-02-07 | 2024-02-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-03546 | 02030 | 23.03 | Solar | 456-H3 | 2024-03-18 | 2024-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | East Freetown | ESMAEX-03512 | 02717 | 200 | Solar | 2-108-108 | 2024-03-06 | 2024-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Application Completed/Closed | Online
NSTAR | Ashland | ESMAEX-03400 | 01721 | 15.29 | Solar | 274-H6 | 2024-01-30 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-03386 | 01746 | 480 | Solar | 65-H5 | 2024-03-04 | 2024-03-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Holliston | ESMAEX-03401 | 01746 | 50 | Solar | 65-H2 | 2024-01-30 | 2024-02-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Application Completed/Closed | Online
NSTAR | Waban | ESMAEX-03429 | 02468 | 17.6 | Solar & Battery | 1701 | 2024-02-08 | 2024-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03414 | 01720 | 40 | Solar | 416-H1 | 2024-02-05 | 2024-02-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Application Completed/Closed | Online
NSTAR | South Wellfleet | ESMAEX-03501 | 02663 | 12.6 | Solar & Battery | 4-94B-653 | 2024-03-01 | 2024-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-03405 | 02459 | 10 | Battery | 292-H11 | 2024-02-01 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03430 | 01748 | 23 | Battery | 126-H4 | 2024-02-09 | 2024-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-03553 | 02119 | 34.6 | Solar | 396-1050H4 | 2024-03-19 | 2024-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brighton | ESMAEX-03476 | 02135 | 34.6 | Solar | 329-1N51H2 | 2024-02-23 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-16 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03457 | 02138 | 225 | Solar | 827-31 | 2024-02-16 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-15 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-03506 | 01741 | 10 | Battery | 533-H8 | 2024-03-05 | 2024-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03436 | 02420 | 5 | Battery | 533-H9 | 2024-02-14 | 2024-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03424 | 02186 | 10 | Battery | 362-1209H2 | 2024-02-07 | 2024-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Weston | ESMAEX-03452 | 02493 | 34.2 | Solar | 282-H10 | 2024-02-15 | 2024-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03425 | 01720 | 10 | Battery | 512-1399H1 | 2024-02-07 | 2024-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03426 | 01760 | 15.2 | Solar | 433-H10 | 2024-02-08 | 2024-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03427 | 02421 | 16 | Solar | 3409 | 2024-02-08 | 2024-02-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-06-12 | Application Completed/Closed | Online
NSTAR | North Cambridge | ESMAEX-03439 | 02140 | 16.8 | Solar | 823-23 | 2024-02-14 | 2024-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03472 | 01760 | 200 | Fuel Cell | 2302 | 2024-02-22 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03433 | 02420 | 300 | Solar + Battery | 34-1378 | 2024-06-07 | 2024-08-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-31 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-03461 | 02332 | 15.36 | Solar & Battery | 3-26-26 | 2024-02-19 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03450 | 02090 | 10 | Solar & Battery | 148-H3 | 2024-02-14 | 2024-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03454 | 02493 | 20 | Solar & Battery | 433-H5 | 2024-02-15 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03460 | 02421 | 11.4 | Solar & Battery | 3409 | 2024-02-19 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03618 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Cataumet | ESMAEX-03462 | 02534 | 34.2 | Solar | 4-81A-81A | 2024-02-20 | 2024-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-03557 | 02119 | 20 | Solar | 483-H3 | 2024-03-20 | 2024-05-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-03475 | 02360 | 23.8 | Battery | 3-73-927 | 2024-02-23 | 2024-03-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-03469 | 02492 | 22.8 | Solar | 148-02 | 2024-02-22 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-26 | Application Completed/Closed | Online
NSTAR | Winchester | ESMAEX-03466 | 01890 | 17.6 | Solar & Battery | 211-H6 | 2024-02-20 | 2024-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Application Completed/Closed | Online
NSTAR | Mattapan | ESMAEX-03465 | 02126 | 7.6 | Solar | 311-02 | 2024-02-20 | 2024-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-03497 | 02081 | 3.8 | Solar | 2601 | 2024-02-29 | 2024-03-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-03477 | 02090 | 9.9 | Solar & Battery | 456-H1 | 2024-02-26 | 2024-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-03470 | 01773 | 23.7 | Solar | 320-H6 | 2024-02-22 | 2024-03-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-03509 | 02445 | 24.9 | Solar & Battery | 350-H8 | 2024-03-05 | 2024-03-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-03508 | 02474 | 10 | Battery | 211-H11 | 2024-03-05 | 2024-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Application Completed/Closed | Online
NSTAR | Dartmouth | ESMAEX-03486 | 02748 | 150 | Solar | 2-53-65 | 2024-02-28 | 2024-04-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-03496 | 01778 | 10 | Solar & Battery | 278-H2 | 2024-02-29 | 2024-04-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-08 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-03484 | 02492 | 15.2 | Solar | 148-H7 | 2024-02-28 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03478 | 01701 | 21.6 | Solar | 455-H1 | 2024-02-26 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-25 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Waltham | ESMAEX-03522 | 02451 | 250 | Fuel Cell | 282-H2 | 2024-03-08 | 2024-03-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-03480 | 01741 | 3 | Solar | 533-H8 | 2024-02-27 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Application Completed/Closed | Online
NSTAR | Acusnet | ESMAEX-03479 | 02743 | 15.2 | Solar | 2-241-241 | 2024-02-27 | 2024-03-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03494 | 01701 | 16 | Solar | 455-H1 | 2024-02-29 | 2024-03-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-03491 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2024-02-29 | 2024-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-03487 | 02053 | 109 | Solar | 65-H3 | 2024-02-28 | 2024-04-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-03535 | 02122 | 250 | Solar | 43-1490H3 | 2024-03-13 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-03500 | 01776 | 800 | Solar | 342-H2 | 2024-03-01 | 2024-03-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Arlington | ESMAEX-03505 | 02476 | 360 | Solar | 320-H7 | 2024-04-19 | 2024-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dorchester | ESMAEX-03518 | 02121 | 22.8 | Solar | 483-H5 | 2024-03-08 | 2024-03-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-03515 | 02459 | 10 | Solar & Battery | 292-H11 | 2024-03-07 | 2024-03-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Application Completed/Closed | Online
NSTAR | Duxbury | ESMAEX-03525 | 02332 | 166 | Solar | 3-24B-24B | 2024-06-04 | 2024-07-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sharon | ESMAEX-03527 | 02067 | 487.5 | Solar | 470-H3 | 2024-03-11 | 2024-03-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-03529 | 02459 | 10 | Solar | 292-H5 | 2024-03-11 | 2024-03-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-10-11 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-03534 | 02019 | 15.2 | Solar | 65-H4 | 2024-03-13 | 2024-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Application Completed/Closed | Online
NSTAR | North Cambridge | ESMAEX-03668 | 02140 | 108 | Solar | 828-1378 | 2024-04-15 | 2024-06-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dorchester | ESMAEX-03542 | 02124 | 60 | Solar | 496-H8 | 2024-03-15 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-03616 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Burlington | ESMAEX-03615 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Burlington | ESMAEX-03614 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Roslindale | ESMAEX-03543 | 02131 | 60 | Solar | 1312 | 2024-03-15 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brighton | ESMAEX-03559 | 02135 | 133.2 | Solar | 329-H6 | 2024-03-21 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-03685 | 02657 | 50 | Battery | 4-675-675 | 2024-04-18 | 2024-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-05 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03680 | 02021 | 15.2 | Solar & Battery | 269-1320H1 | 2024-04-17 | 2024-05-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03613 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Bourne | ESMAEX-03619 | 02562 | 27.3 | Solar | 3-89-925 | 2024-04-02 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-06 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Burlington | ESMAEX-03610 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Burlington | ESMAEX-03609 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Westwood | ESMAEX-03549 | 02090 | 3.9 | Solar | 456-H4 | 2024-03-19 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-03552 | 01801 | 48.38 | Solar | 375-H9 | 2024-03-19 | 2024-05-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-03564 | 02446 | 29.58 | Solar | 329-H8 | 2024-03-21 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Application Completed/Closed | Online
NSTAR | Hatchville | ESMAEX-03554 | 02536 | 7.6 | Solar & Battery | 4-98A-98A | 2024-03-20 | 2024-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-26 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03606 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Burlington | ESMAEX-03605 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Orleans | ESMAEX-03556 | 02653 | 204.96 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Orleans | ESMAEX-03558 | 02653 | 249.9 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wareham | ESMAEX-03560 | 02571 | 3 | Solar & Battery | 3-84-12J1 | 2024-03-21 | 2024-04-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-06 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-03621 | 02054 | 20.2 | Solar | 65-H1 | 2024-04-03 | 2024-05-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Application Completed/Closed | Online
NSTAR | West Roxbury | ESMAEX-04120 | 02132 | 240 | Solar | 468-06 | 2024-09-27 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Needham | ESMAEX-03575 | 02492 | 18.048 | Solar | 148-06 | 2024-03-26 | 2024-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-13 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-04119 | 02130 | 120 | Solar | 350-H2 | 2024-09-27 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | South Wellfleet | ESMAEX-03774 | 02663 | 22.11 | Solar | 4-94B-656 | 2024-05-16 | 2024-06-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-13 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Newton Lower Falls | ESMAEX-03674 | 02462 | 20 | Solar | 292-H2 | 2024-04-16 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-18 | [7 empty] | 0 |  | 0 |  |  | 2025-01-03 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Chatham | ESMAEX-03577 | 02633 | 15.36 | Battery | 4-95B-95B | 2024-03-26 | 2024-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-22 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-03683 | 02150 | 67.3 | Solar | 14-113H2 | 2024-04-18 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Framingham | ESMAEX-03580 | 01701 | 7.6 | Solar | 455-H1 | 2024-03-26 | 2024-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-03649 | 02465 | 60 | Solar | 292-H7 | 2024-04-09 | 2024-04-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Medway | ESMAEX-03582 | 02053 | 15.2 | Solar | 65-H3 | 2024-03-27 | 2024-04-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-03642 | 02633 | 150 | Solar | 4-95B-95B | 2024-04-09 | 2024-04-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Barnstable | ESMAEX-03860 | 02630 | 23.52 | Solar | 4-84A-84A | 2024-06-25 | 2024-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03594 | 02453 | 2000 | Battery | 386-1366 | 2024-05-22 | 2024-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-03593 | 02453 | 1500 | Battery | 386-1356 | 2024-05-22 | 2024-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Eastham | ESMAEX-03679 | 02642 | 15.2 | Solar & Battery | 4-94A-648 | 2024-04-17 | 2024-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-28 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03592 | 02493 | 15.2 | Solar | 282-H1 | 2024-03-29 | 2024-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Application Completed/Closed | Online
NSTAR | Plympton | ESMAEX-03629 | 02367 | 4999 | Solar & Battery | 3-51-51 | 2024-04-04 | 2024-04-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Kingston | ESMAEX-03636 | 02364 | 4999 | Solar & Battery | 3-50-50 | 2024-04-05 | 2024-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Winchester | ESMAEX-03628 | 01890 | 23 | Solar & Battery | 211-H6 | 2024-04-04 | 2024-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03622 | 01760 | 3.8 | Solar | 433-H5 | 2024-04-03 | 2024-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Application Completed/Closed | Online
NSTAR | East Harwich | ESMAEX-03623 | 02645 | 17.6 | Solar & Battery | 4-89B-576 | 2024-04-03 | 2024-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03627 | 01701 | 9.735 | Solar & Battery | 455-H1 | 2024-04-03 | 2024-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-03639 | 02494 | 24.96 | Solar | 292-H4 | 2024-04-08 | 2024-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-03633 | 02056 | 19 | Solar | 146-H9 | 2024-04-05 | 2024-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03645 | 01720 | 17.28 | Solar | 416-H8 | 2024-04-09 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03673 | 02420 | 20 | Solar & Battery | 211-H10 | 2024-04-16 | 2024-06-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Framingham | ESMAEX-03641 | 01701 | 15.2 | Solar | 342-H9 | 2024-04-08 | 2024-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Application Completed/Closed | Online
NSTAR | Roslindale | ESMAEX-03646 | 02131 | 6.9 | Solar | 496-H5 | 2024-04-09 | 2024-04-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-20 | Eversource Review Schedule Z | Technical Review
NSTAR | Marshfield | ESMAEX-03643 | 02050 | 3.8 | Solar | 3-27-970 | 2024-04-09 | 2024-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-03651 | 02446 | 34.6 | Solar | 329-H10 | 2024-04-10 | 2024-04-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03687 | 02453 | 110 | Solar | 33-H2 | 2024-04-18 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-03656 | 01730 | 15.2 | Solar & Battery | 533-H3 | 2024-04-11 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-03660 | 01741 | 10 | Battery | 533-H8 | 2024-07-25 | 2024-07-25 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-03658 | 02467 | 19.86 | Solar & Battery | 1706 | 2024-04-11 | 2024-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-22 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-03661 | 02746 | 3.8 | Solar | 2-85-130 | 2024-04-12 | 2024-05-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03666 | 02067 | 17.58 | Solar & Battery | 146-H1 | 2024-04-15 | 2024-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03885 | 02139 | 40 | Solar & Battery | 817-01 | 2024-07-08 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-03692 | 02030 | 67.3 | Solar | 456-H2 | 2024-04-22 | 2024-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-25 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-03677 | 02119 | 27.3 | Solar | 510-77H3 | 2024-04-17 | 2024-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03734 | 02451 | 180 | Solar | 450-H2 | 2024-05-03 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-28 | Application Completed/Closed | Online
NSTAR | Somerville | ESMAEX-03749 | 02144 | 120 | Solar | 59-1471 | 2024-05-10 | 2024-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bellingham | ESMAEX-03684 | 02019 | 17.6 | Solar | 65-H4 | 2024-04-18 | 2024-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03688 | 02067 | 15.2 | Solar | 146-H7 | 2024-04-19 | 2024-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Application Completed/Closed | Online
NSTAR | Bellingham | ESMAEX-03689 | 02019 | 20 | Solar | 65-H4 | 2024-04-19 | 2024-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Lincoln | ESMAEX-03690 | 01773 | 20 | Battery | 320-H6 | 2024-04-19 | 2024-05-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-03714 | 02472 | 120 | Solar | 370-1327 | 2024-07-10 | 2024-08-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-03717 | 01720 | 0 | Battery | 416-H1 | 2024-04-29 | 2024-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-03703 | 02476 | 8.68 | Battery | 211-H14 | 2024-04-23 | 2024-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-03702 | 02138 | 23 | Solar & Battery | 823-30 | 2024-04-23 | 2024-05-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03705 | 02421 | 7.68 | Battery | 3409 | 2024-04-23 | 2024-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03791 | 02021 | 11.5 | Solar & Battery | 269-1320H1 | 2024-05-28 | 2024-07-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-03719 | 02446 | 300 | Fuel Cell | 329-H8 | 2024-04-30 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-03706 | 01701 | 7.6 | Solar | 433-H8 | 2024-04-23 | 2024-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Bedford | ESMAEX-03852 | 01730 | 20 | Solar & Battery | 533-H7 | 2024-06-24 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Chatham | ESMAEX-03710 | 02633 | 36.9 | Solar & Battery | 4-95A-608 | 2024-04-24 | 2024-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-13 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03724 | 02186 | 240 | Solar | 496-H2 | 2024-05-01 | 2024-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Milton | ESMAEX-03736 | 02186 | 240 | Solar | 60-1409H1 | 2024-05-06 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-03716 | 01803 | 6.4 | Solar & Battery | 375-H6 | 2024-04-29 | 2024-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03735 | 02186 | 150 | Solar |  | 2024-05-06 | 2024-06-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-03776 | 01720 | 19 | Solar | 416-H5 | 2024-05-16 | 2024-06-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-03 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03721 | 01720 | 7.6 | Solar | 416-H4 | 2024-05-01 | 2024-05-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Application Completed/Closed | Online
NSTAR | Charlestown | ESMAEX-03722 | 02129 | 280 | Internal Combustion Engine | 225-184 | 2024-10-16 | 2024-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-04059 | 01702 | 100 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-04058 | 01702 | 150 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-04057 | 01702 | 150 | Solar | 455-H4 | 2024-09-13 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chestnut Hill | ESMAEX-03777 | 02467 | 18.12 | Solar & Battery | 350-H7 | 2024-05-17 | 2024-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-03758 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-13 | 2024-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-03767 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-15 | 2024-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Acton | ESMAEX-03785 | 01720 | 7.6 | Solar | 416-H8 | 2024-10-17 | 2024-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-03765 | 01805 | 4998 | Battery | 541-1377H | 2024-07-16 | 2024-08-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Cambridge | ESMAEX-03813 | 02138 | 24.96 | Solar | 824-27 | 2024-06-05 | 2024-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-03741 | 02493 | 17.99 | Solar | 282-H8 | 2024-05-08 | 2024-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Eversource Review Schedule Z | Technical Review
NSTAR | Falmouth | ESMAEX-03752 | 02540 | 120 | Solar | 4-98A-98A | 2024-05-13 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-03781 | 01720 | 22.34 | Solar & Battery | 416-H5 | 2024-05-21 | 2024-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-03845 | 02747 | 17.6 | Solar & Battery | 2-531-531 | 2024-06-17 | 2024-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-03759 | 02180 | 8.77 | Battery | 211-H12 | 2024-05-14 | 2024-06-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-03816 | 02657 | 11.6 | Battery | 4-675-675 | 2024-06-05 | 2024-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2024-11-19 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03773 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-05-16 | 2024-06-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-03762 | 02150 | 490 | Solar | 488-H7 | 2024-07-23 | 2024-08-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Jamaica Plain | ESMAEX-03783 | 02130 | 20 | Solar | 284-01 | 2024-05-21 | 2024-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-03847 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-03792 | 02180 | 13.92 | Solar | 375-H2 | 2024-05-28 | 2024-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-03789 | 01776 | 20 | Solar | 342-H2 | 2024-05-23 | 2024-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03796 | 02186 | 23 | Solar & Battery | 362-1207H1 | 2024-05-28 | 2024-06-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-03788 | 02568 | 16.8 | Solar | 4-75-75 | 2024-05-23 | 2024-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-28 | [7 empty] | 0 |  | 0 |  |  | 2025-04-04 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-03794 | 02452 | 16.72 | Battery | 450-H6 | 2024-05-28 | 2024-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-03790 | 02054 | 20 | Solar | 130-H2 | 2024-05-24 | 2024-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Wiring Issue - Customer Action Required | Meter
NSTAR | Framingham | ESMAEX-03799 | 01701 | 46.08 | Solar | 455-H1 | 2024-05-29 | 2024-06-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-03795 | 02744 | 480 | Solar | 2-69-69 | 2024-06-19 | 2024-07-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Walpole | ESMAEX-03797 | 02081 | 20 | Solar | 146-H2 | 2024-05-29 | 2024-06-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-03801 | 02492 | 36.52 | Solar & Battery | 148-H2 | 2024-05-29 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-12 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-03803 | 01801 | 10 | Solar | 375-H14 | 2024-05-29 | 2024-06-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-29 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-03807 | 02642 | 249.6 | Solar | 4-94B-647 | 2024-05-31 | 2024-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-03848 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-03810 | 01741 | 11.515 | Solar & Battery | 533-H8 | 2024-06-04 | 2024-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-03-14 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-03814 | 02128 | 100 | Solar | 108-195H1 | 2024-06-05 | 2024-07-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03826 | 01760 | 120 | Solar | 339-1345H | 2024-12-03 | 2025-01-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-03863 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-03864 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Amended ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Natick | ESMAEX-03865 | 01760 | 150 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-03818 | 01770 | 18.88 | Solar | 274-H2 | 2024-06-06 | 2024-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-03815 | 01776 | 486.6 | Solar | 146-H1 | 2024-08-22 | 2024-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyannis | ESMAEX-03844 | 02601 | 100 | Solar | 4-84A-84A | 2024-06-14 | 2024-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-03823 | 02476 | 15.2 | Solar | 211-H14 | 2024-06-11 | 2024-06-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Application Completed/Closed | Online
NSTAR | Medway | ESMAEX-03873 | 02053 | 5 | Solar & Battery | 65-H5 | 2024-07-01 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-03825 | 02150 | 34.6 | Solar | 488-H2 | 2024-06-11 | 2024-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Winchester | ESMAEX-03840 | 01890 | 20 | Battery | 211-H7XY | 2024-06-14 | 2024-07-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-15 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03856 | 01702 | 100 | Solar | 2410 | 2024-06-24 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-26 | [7 empty] | 0 |  | 0 |  |  | 2025-07-16 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03850 | 02021 | 15.2 | Solar | 470-H4 | 2024-06-19 | 2024-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-03851 | 02050 | 150 | Solar | 3-24A-24A | 2024-06-21 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | Customer ISA eSignature Completed | ISA Agreement
NSTAR | Ashland | ESMAEX-03859 | 01721 | 15.2 | Solar | 455-H3 | 2024-06-25 | 2024-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03900 | 02421 | 9624.5 | Solar & Battery | 244-1362 | 2024-07-16 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Medfield | ESMAEX-03858 | 02052 | 22.8 | Solar | 456-H3 | 2024-06-24 | 2024-07-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-21 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-03868 | 02180 | 15.59 | Battery | 375-H2 | 2024-06-27 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-03874 | 01776 | 20.46 | Solar | 342-H4 | 2024-07-01 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-04153 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Boston | ESMAEX-04152 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Boston | ESMAEX-04151 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-03889 | 01776 | 50 | Solar | 342-H5 | 2024-07-10 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Application Completed/Closed | Online
NSTAR | Stoneham | ESMAEX-03882 | 02180 | 5.7 | Solar | 375-H8 | 2024-07-02 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-03887 | 02021 | 120 | Solar | 470-H7 | 2024-07-09 | 2024-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-28 | Application Completed/Closed | Online
NSTAR | Maynard | ESMAEX-03886 | 01754 | 7.68 | Solar & Battery | 416-H6 | 2024-07-08 | 2024-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Application Completed/Closed | Online
NSTAR | Sherborn | ESMAEX-03940 | 01770 | 15 | Solar | 240-H1 | 2024-07-31 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-10 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03986 | 02421 | 100 | Solar | 320-H5XY | 2024-08-22 | 2024-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Harwichport | ESMAEX-03912 | 02646 | 0 | Battery | 4-95A-95A | 2024-07-18 | 2024-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Westwood | ESMAEX-04028 | 02090 | 20 | Battery | 148-H3 | 2024-09-04 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-03911 | 01720 | 17.28 | Solar | 416-H5 | 2024-07-18 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-03903 | 02081 | 300 | Solar | 146-H4 | 2024-11-22 | 2025-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brookline | ESMAEX-03908 | 02446 | 20 | Battery | 506-07 | 2024-07-17 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Stoneham | ESMAEX-03909 | 02180 | 10.62 | Solar & Battery | 375-H12 | 2024-07-17 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03926 | 01748 | 16.8 | Solar | 126-H4 | 2024-07-26 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-08 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03910 | 01748 | 7.6 | Solar | 126-H2 | 2024-07-18 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-04 | Application Completed/Closed | Online
NSTAR | Assonett | ESMAEX-03917 | 02702 | 15.2 | Solar | 2-605-605 | 2024-07-22 | 2024-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-03927 | 01741 | 19.99 | Solar | 512-1399H1 | 2024-07-26 | 2024-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Application Completed/Closed | Online
NSTAR | Hyannis | ESMAEX-04053 | 02601 | 150 | Solar | 4-63-63 | 2024-09-12 | 2024-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Woburn | ESMAEX-03923 | 01801 | 9.98 | Solar & Battery | 211-H5 | 2024-07-24 | 2024-08-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-03958 | 01748 | 11.5 | Solar & Battery | 455-H8 | 2024-08-09 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Natick | ESMAEX-03959 | 01760 | 8.95 | Solar | 240-H5 | 2024-08-09 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Application Completed/Closed | Online
NSTAR | Hyde Park | ESMAEX-03944 | 02136 | 15.2 | Solar | 496-H7 | 2024-08-02 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-03935 | 01760 | 20 | Solar & Battery | 433-H12 | 2024-07-30 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-03988 | 02459 | 50 | Solar | 292-H11 | 2024-08-22 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newtonville | ESMAEX-03934 | 02460 | 31.2 | Solar & Battery | 1705 | 2024-07-30 | 2024-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-03946 | 01730 | 19.9 | Battery | 533-H3 | 2024-08-02 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-03943 | 01701 | 20 | Solar | 455-H1 | 2024-08-02 | 2024-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-03969 | 02186 | 51.456 | Solar | 362-1209H2 | 2024-08-14 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Somerville | ESMAEX-03945 | 02145 | 27.3 | Solar | 250-1N81H1 | 2024-08-02 | 2024-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Application Completed/Closed | Online
NSTAR | Newtonville | ESMAEX-03948 | 02460 | 20 | Solar & Battery | 467-H5 | 2024-08-07 | 2024-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-03947 | 01760 | 17.202 | Solar | 23-H1 | 2024-08-06 | 2024-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03974 | 02458 | 10 | Battery | 277-05 | 2024-08-15 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-03955 | 02067 | 12.4 | Battery | 146-H1 | 2024-08-08 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-03979 | 02421 | 250 | Fuel Cell | 34-1385 | 2024-08-19 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-03965 | 01760 | 10.1 | Battery | 240-H1 | 2024-08-14 | 2024-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-03991 | 01720 | 5 | Battery | 416-H8 | 2024-08-23 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-03976 | 02476 | 15.2 | Solar | 320-H7 | 2024-08-16 | 2024-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04000 | 02360 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Natick | ESMAEX-03996 | 01760 | 20 | Battery | 240-H1 | 2024-08-23 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-03995 | 01801 | 20 | Solar & Battery |  | 2024-08-23 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-03980 | 02135 | 130 | Solar | 467-H3 | 2024-08-20 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Oak Bluffs | ESMAEX-04133 | 02557 | 15.2 | Solar | 4-99-99 | 2024-10-01 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-28 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Eversource Initiated Construction | Construction Stage
NSTAR | Carver | ESMAEX-03999 | 02330 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Roxbury | ESMAEX-03992 | 02119 | 120 | Solar | 465-129H1 | 2024-08-23 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-03993 | 01720 | 10 | Battery | 416-H1 | 2024-08-23 | 2024-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-03997 | 02122 | 300 | Solar | 466-1481H1 | 2024-09-30 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-03998 | 02130 | 280 | Solar | 396-01 | 2024-09-27 | 2024-10-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-04022 | 01741 | 18.88 | Solar | 512-1399H1 | 2024-08-30 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-08 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-04003 | 02451 | 14.2 | Battery | 450-H4 | 2024-08-27 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-18 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-04004 | 02067 | 10 | Battery | 146-H1 | 2024-08-27 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-04036 | 02127 | 240 | Solar | 385-H18 | 2024-09-05 | 2024-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Roxbury | ESMAEX-04037 | 02120 | 130 | Solar | 5210 | 2024-09-05 | 2024-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04007 | 02021 | 990 | Solar | 269-1321H2 | 2024-09-24 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-04091 | 01741 | 21.888 | Solar | 512-1399H1 | 2024-09-24 | 2024-10-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04009 | 02021 | 320 | Solar | 470-H10 | 2024-09-23 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Roxbury | ESMAEX-04011 | 02132 | 17.6 | Solar & Battery | 496-H6 | 2024-08-27 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-04010 | 02150 | 150 | Solar | 488-H2 | 2024-09-24 | 2024-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cotuit | ESMAEX-04012 | 02635 | 15.2 | Solar & Battery | 4-88-880 | 2024-08-27 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-04017 | 02139 | 50 | Solar | 814-12 | 2024-08-29 | 2025-01-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brewster | ESMAEX-04019 | 02631 | 17.4 | Solar | 4-89B-573 | 2024-08-30 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Eastham | ESMAEX-04020 | 02642 | 11.5 | Battery | 4-94A-648 | 2024-08-30 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-04040 | 02124 | 220 | Solar | 466-1481H | 2024-09-06 | 2024-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-04027 | 02421 | 27.3 | Solar | 533-H2 | 2024-09-04 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Sherborn | ESMAEX-04034 | 01770 | 16.104 | Solar | 240-H1 | 2024-09-05 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Application Completed/Closed | Online
NSTAR | Norfolk | ESMAEX-04031 | 02056 | 37 | Solar & Battery | 146-H10 | 2024-09-05 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westport | ESMAEX-04049 | 02790 | 25.242 | Solar & Battery | 2-523-523 | 2024-09-11 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-27 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-04038 | 01801 | 250 | Solar | 375-H4 | 2024-09-24 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Waltham | ESMAEX-04050 | 02451 | 140 | Solar | 282-H2 | 2024-09-11 | 2024-10-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-25 | Application Completed/Closed | Online
NSTAR | West Barnstable | ESMAEX-04110 | 02668 | 22.09 | Solar | 4-84A-84A | 2024-09-26 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-04045 | 02460 | 27.3 | Solar | 467-H3 | 2024-09-09 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Harwich | ESMAEX-04046 | 02645 | 420 | Solar | 4-89B-89B | 2024-11-14 | 2024-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carver | ESMAEX-04072 | 02330 | 4980 | Solar & Battery | 3-10-929 | 2024-09-19 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04073 | 02330 | 4980 | Solar & Battery | 3-11-11 | 2024-09-19 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Framingham | ESMAEX-04048 | 01701 | 17.3 | Solar | 278-H1 | 2024-09-11 | 2024-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-16 | Application Completed/Closed | Online
NSTAR | Brookline | ESMAEX-04052 | 02445 | 7.67 | Solar & Battery | 315-H2 | 2024-09-11 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-04055 | 01776 | 15.2 | Solar & Battery | 342-H7 | 2024-09-13 | 2024-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-22 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-04051 | 02090 | 7.5 | Solar | 148-H3 | 2024-09-11 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-04116 | 02472 | 372 | Solar | 370-1327 | 2024-09-27 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-04070 | 01760 | 20 | Battery | 240-H6 | 2024-09-18 | 2024-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-04080 | 01778 | 20 | Battery | 278-H2 | 2024-09-20 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-03-13 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-04060 | 02030 | 16.2 | Solar | 456-H5 | 2024-09-13 | 2024-10-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-04062 | 02364 | 498 | Solar | 3-15-15 | 2024-09-13 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Falmouth | ESMAEX-04064 | 02540 | 17.644 | Solar & Battery | 4-72-72 | 2024-09-17 | 2024-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-04066 | 01778 | 11.5 | Battery | 433-H2 | 2024-09-17 | 2024-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-04074 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2024-09-19 | 2024-10-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Rochester | ESMAEX-04075 | 02770 | 4980 | Solar & Battery | 3-703-703 | 2024-09-19 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Carver | ESMAEX-04076 | 02330 | 4980 | Solar & Battery | 3-81-81 | 2024-09-19 | 2024-10-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Carver | ESMAEX-04077 | 02330 | 996 | Solar & Battery | 3-81-81 | 2024-09-19 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Woburn | ESMAEX-04071 | 01801 | 15.744 | Solar | 325-03 | 2024-09-19 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-04078 | 02421 | 11.5 | Solar & Battery | 320-H2 | 2024-09-19 | 2024-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-04124 | 02125 | 80 | Solar |  | 2024-09-30 | 2024-10-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04111 | 02021 | 13.8 | Battery | 470-H10 | 2024-09-26 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-03-12 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-04079 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2024-09-19 | 2024-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-04118 | 02124 | 150 | Solar | 4302 | 2024-09-27 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Holliston | ESMAEX-04083 | 01746 | 23 | Solar & Battery | 65-H5 | 2024-09-20 | 2024-12-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-04137 | 02030 | 23 | Solar & Battery | 456-H3 | 2024-10-03 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Eversource QF - Schedule Z Review | Technical Review
NSTAR | Burlington | ESMAEX-04102 | 01803 | 20 | Battery | 346-1395H1 | 2024-09-25 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-04089 | 02030 | 20.1 | Solar | 148-H3 | 2024-09-23 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-04135 | 02568 | 50 | Solar |  | 2024-10-03 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-04101 | 02747 | 11.88 | Solar | 2-541-541 | 2024-09-24 | 2024-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-16 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Westwood | ESMAEX-04092 | 02090 | 20 | Solar | 456-H1 | 2024-09-24 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-12 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Needham | ESMAEX-04117 | 02492 | 5 | Battery | 148-02 | 2024-09-27 | 2024-11-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-15 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-04125 | 02472 | 920 | Solar & Battery | 467-H4 | 2024-12-19 | 2025-07-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Bass River | ESMAEX-04123 | 02664 | 7.6 | Solar & Battery | 4-92A-92A | 2024-09-27 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-04140 | 02364 | 200 | Solar | 3-17-17 | 2024-10-04 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-04131 | 01748 | 7.65 | Battery | 126-H2 | 2024-10-01 | 2024-10-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-11 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-04149 | 02451 | 13.3 | Solar | 282-H2 | 2024-10-07 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Application Completed/Closed | Online
NSTAR | Auburndale | ESMAEX-04178 | 02466 | 24.06 | Solar & Battery | 292-H7 | 2024-10-17 | 2024-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-04134 | 02421 | 23.908 | Solar & Battery | 320-H2 | 2024-10-03 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-04159 | 02128 | 30 | Solar | 488-H5 | 2024-10-09 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | Eastham | ESMAEX-04142 | 02642 | 11.5 | Battery | 4-94A-648 | 2024-10-04 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-04186 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2024-10-17 | 2024-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Sudbury | ESMAEX-04146 | 01776 | 25.73 | Solar & Battery | 342-H7 | 2024-10-07 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dorchester | ESMAEX-04355 | 02122 | 180 | Solar |  | 2024-12-10 | 2025-01-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Application Completed/Closed | Online
NSTAR | Marstons Mills | ESMAEX-04284 | 02648 | 100 | Solar | 4-88-88 | 2024-11-18 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Holliston | ESMAEX-04150 | 01746 | 14.98 | Solar | 65-H5 | 2024-10-08 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-04154 | 02539 | 17.6 | Solar |  | 2024-10-08 | 2024-10-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | Chestnut Hill | ESMAEX-04158 | 02467 | 17.6 | Solar & Battery | 292-H6 | 2024-10-09 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-04308 | 02134 | 80 | Solar | 144-138 | 2024-11-26 | 2024-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-04204 | 02493 | 19.99 | Solar | 282-H1 | 2024-10-25 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Carver | ESMAEX-04185 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-17 | 2024-11-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Bedford | ESMAEX-04160 | 01730 | 49.7 | Solar | 533-H8 | 2024-10-10 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-08-13 | Application Completed/Closed | Online
NSTAR | Roslindale | ESMAEX-04167 | 02131 | 11.5 | Battery | 496-H5 | 2024-10-11 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-04161 | 01730 | 82.9 | Solar |  | 2024-10-10 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-29 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-04195 | 02139 | 19.72 | Solar | 814-12 | 2024-10-18 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Acton | ESMAEX-04207 | 01720 | 15.2 | Solar | 416-H4 | 2024-10-25 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-02 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-04175 | 02186 | 498 | Solar | 362-1209H2 | 2024-12-20 | 2025-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sharon | ESMAEX-04170 | 02067 | 10 | Battery | 146-H7 | 2024-10-14 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Application Completed/Closed | Online
NSTAR | Milton | ESMAEX-04171 | 02186 | 10 | Solar & Battery | 362-1209H1 | 2024-10-14 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Application Completed/Closed | Online
NSTAR | Centerville | ESMAEX-04173 | 02632 | 17.26 | Solar | 4-82-82 | 2024-10-15 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Application Completed/Closed | Online
NSTAR | Westport | ESMAEX-04293 | 02790 | 10 | Battery | 2-523-523 | 2025-02-06 | 2024-12-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-05 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-04183 | 02330 | 996 | Solar & Battery | 3-81-950 | 2024-10-17 | 2024-11-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04181 | 02330 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04182 | 01851 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Waltham | ESMAEX-04179 | 02451 | 17.86 | Solar | 282-H2 | 2024-10-17 | 2024-11-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Post ISA Technical Review | Technical Review
NSTAR | Norfolk | ESMAEX-04595 | 02056 | 66.6 | Solar | 146-H9 | 2025-03-05 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Acton | ESMAEX-04198 | 01720 | 34.5 | Solar & Battery | 416-H8 | 2024-10-21 | 2024-11-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-04199 | 02493 | 17.6 | Solar | 282-H8 | 2024-10-21 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-04-14 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-04213 | 02571 | 999.45 | Solar & Battery | 3-84-84 | 2024-10-28 | 2024-12-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04214 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04215 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04219 | 02330 | 4980 | Solar & Battery | 3-14-934 | 2024-10-28 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Carver | ESMAEX-04218 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-28 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04220 | 02330 | 4980 | Solar & Battery | 3-10-917 | 2024-10-28 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Plympton | ESMAEX-04221 | 02367 | 4980 | Solar & Battery | 3-10-917 | 2024-10-29 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Wayland | ESMAEX-04281 | 01778 | 20 | Battery | 433-H2 | 2024-11-17 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-20 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | West Newton | ESMAEX-04223 | 02465 | 110 | Solar | 292-H12 | 2024-10-29 | 2024-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acusnet | ESMAEX-04226 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acusnet | ESMAEX-04227 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medfield | ESMAEX-04225 | 02052 | 16.13 | Solar | 456-H5 | 2024-10-30 | 2024-11-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Application Completed/Closed | Online
NSTAR | Sudbury | ESMAEX-04234 | 01776 | 240 | Solar | 342-H8 | 2024-11-01 | 2024-11-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-04232 | 01776 | 23 | Solar & Battery | 416-H7 | 2024-11-01 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-04229 | 01748 | 34.6 | Solar | 342-H1 | 2024-11-01 | 2024-11-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wayland | ESMAEX-04364 | 01778 | 11.74 | Solar | 342-H1 | 2024-12-11 | 2025-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Oak Bluffs | ESMAEX-04236 | 02557 | 15.36 | Solar | 4-99-225 | 2024-11-01 | 2025-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carver | ESMAEX-04272 | 02330 | 4750 | Solar & Battery | 3-83-83 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Carver | ESMAEX-04268 | 02330 | 990 | Solar | 3-10-10 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Plymouth | ESMAEX-04270 | 02360 | 500 | Solar | 3-90-90 | 2024-11-12 | 2024-11-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Plymouth | ESMAEX-04269 | 02360 | 990 | Solar | 3-11-11 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04271 | 02330 | 4999 | Solar & Battery | 3-81-81 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Carver | ESMAEX-04267 | 02330 | 990 | Solar | 3-10-929 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04241 | 02330 | 4999 | Solar & Battery | 3-11-11 | 2024-11-06 | 2024-11-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Tisbury | ESMAEX-04245 | 02575 | 97 | Solar |  | 2024-11-07 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Yarmouth | ESMAEX-04247 | 02673 | 10 | Battery | 4-63-532 | 2024-11-07 | 2024-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-04244 | 01748 | 20.06 | Solar | 126-H2 | 2024-11-07 | 2025-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Application Completed/Closed | Online
NSTAR | Newton Lower Falls | ESMAEX-04246 | 02462 | 1500 | Fuel Cell | 292-H2 | 2025-04-23 | 2025-05-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Plymouth | ESMAEX-04253 | 02360 | 999 | Solar & Battery | 3-12-12 | 2024-11-11 | 2024-12-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Plymouth | ESMAEX-04256 | 02360 | 3500 | Solar & Battery | 3-90-90 | 2024-11-11 | 2024-11-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Waltham | ESMAEX-04262 | 02451 | 13.65 | Solar | 282-H2 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  | 2025-08-26 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-04250 | 02067 | 4950 | Other | 146-H1 | 2025-05-09 | 2025-07-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Oak Bluffs | ESMAEX-04259 | 02557 | 17.6 | Solar | 4-99-224 | 2024-11-12 | 2024-11-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Freetown | ESMAEX-04294 | 02717 | 19 | Solar | 2-102-608 | 2024-11-22 | 2024-12-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-04254 | 02472 | 16.2 | Solar | 467-H10 | 2024-11-11 | 2025-01-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Application Completed/Closed | Online
NSTAR | Carver | ESMAEX-04255 | 02330 | 4999 | Solar & Battery | 3-81-950 | 2024-11-11 | 2024-11-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Carver | ESMAEX-04257 | 02330 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-11-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04258 | 02360 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-12-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Waltham | ESMAEX-04438 | 02453 | 33.1 | Solar | 282-H4 | 2025-01-16 | 2025-02-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Plymouth | ESMAEX-04273 | 02360 | 15.2 | Solar | 3-14-30J2 | 2024-11-12 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-01 | Application Completed/Closed | Online
NSTAR | Medfield | ESMAEX-04277 | 02052 | 18.705 | Solar | 146-H6 | 2024-11-14 | 2025-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-04282 | 02421 | 20 | Solar & Battery | 320-H5XY | 2024-11-18 | 2024-12-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-04486 | 02465 | 17.3 | Solar | 33-H3 | 2025-02-05 | 2025-02-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Application Completed/Closed | Online
NSTAR | Jamaica Plain | ESMAEX-04567 | 02130 | 17.3 | Solar | 350-H2 | 2025-02-25 | 2025-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-04433 | 01720 | 300 | Solar | 416-H5 | 2025-03-20 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Needham | ESMAEX-04301 | 02492 | 21.5 | Solar & Battery | 148-06 | 2024-11-26 | 2025-01-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-05 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-04387 | 02090 | 150 | Solar | 469-H4 | 2024-12-17 | 2025-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-04315 | 02459 | 30 | Solar | 292-H3 | 2024-11-27 | 2025-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Application Completed/Closed | Online
NSTAR | Mashpee | ESMAEX-04319 | 02649 | 50 | Solar |  | 2024-12-03 | 2024-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Medfield | ESMAEX-04317 | 02052 | 19.1 | Solar & Battery | 456-H2 | 2024-12-02 | 2025-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Application Completed/Closed | Online
NSTAR | Marshfield | ESMAEX-04585 | 02051 | 4980 | Other | 3-25-25 | 2025-02-28 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Westwood | ESMAEX-04345 | 02090 | 20 | Solar & Battery | 469-H2 | 2024-12-06 | 2024-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Application Completed/Closed | Online
NSTAR | Arlington | ESMAEX-04400 | 02476 | 7.59 | Solar | 211-H14 | 2024-12-20 | 2025-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-04326 | 02150 | 67.3 | Solar | 488-H5 | 2025-05-01 | 2025-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-04327 | 02740 | 77.3 | Solar |  | 2025-08-13 | 2025-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Freetown | ESMAEX-04331 | 02717 | 4980 | Solar & Battery | 2-102-102 | 2025-01-15 | 2025-01-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Westwood | ESMAEX-04344 | 02090 | 20 | Battery | 148-H3 | 2024-12-06 | 2025-01-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Application Completed/Closed | Online
NSTAR | Yarmouthport | ESMAEX-04346 | 02675 | 7.6 | Solar | 4-90-90 | 2024-12-06 | 2025-01-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-04347 | 02026 | 15.2 | Solar | 344-1412H1 | 2024-12-06 | 2025-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-04518 | 02568 | 260 | Solar | 4-75-75 | 2025-05-06 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04383 | 02021 | 720 | Solar & Battery | 470-H7 | 2025-06-30 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Canton | ESMAEX-04350 | 02021 | 33 | Solar | 269-1320H1 | 2024-12-09 | 2025-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Application Completed/Closed | Online
NSTAR | Hyde Park | ESMAEX-04353 | 02136 | 200 | Solar | 344-07 | 2025-01-13 | 2025-01-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dennis | ESMAEX-04354 | 02638 | 44.88 | Solar | 4-89A-552 | 2024-12-10 | 2025-01-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Application Completed/Closed | Online
NSTAR | Weston | ESMAEX-04371 | 02493 | 80 | Solar | 282-H8 | 2024-12-23 | 2025-01-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-08 | [7 empty] | 0 |  | 0 |  |  | 2025-09-05 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-04363 | 02026 | 17.26 | Solar | 344-1412H1 | 2024-12-11 | 2024-12-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-04369 | 01778 | 22.8 | Solar | 2409 | 2024-12-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Burlington | ESMAEX-04441 | 01803 | 15.28 | Solar | 391-H7 | 2025-01-17 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-18 | [7 empty] | 0 |  | 0 |  |  | 2025-07-07 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-04386 | 01701 | 480 | Other | 433-H10 | 2025-04-07 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bourne | ESMAEX-04382 | 02532 | 450 | Solar | 4-71-455 | 2025-02-14 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 | [7 empty] | 0 |  | 0 |  |  |  | Amended ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Falmouth | ESMAEX-04421 | 02540 | 40 | Solar | 4-76-437 | 2025-01-08 | 2025-01-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Application Completed/Closed | Online
NSTAR | Teaticket | ESMAEX-04396 | 02536 | 550 | Solar | 4-76-437 | 2025-06-03 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | West Roxbury | ESMAEX-04411 | 02132 | 11.5 | Solar & Battery | 496-H6 | 2024-12-31 | 2025-01-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Application Completed/Closed | Online
NSTAR | 0 | ESMAEX-04409 | 02739 | 4990 | Battery | 2-301-301 | 2024-12-30 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | 0 | ESMAEX-04410 | 02739 | 4990 | Battery | 2-301-301 | 2024-12-30 | 2025-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Stoneham | ESMAEX-04401 | 02180 | 15.36 | Solar & Battery | 211-H12 | 2024-12-21 | 2025-01-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Roxbury | ESMAEX-04402 | 02119 | 20 | Solar | 510-77H5 | 2024-12-23 | 2025-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Fairhaven | ESMAEX-04405 | 02719 | 240 | Solar | 2-230-230 | 2024-12-27 | 2025-04-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-04420 | 02746 | 15.2 | Solar | 2-87-135 | 2025-01-07 | 2025-02-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Application Completed/Closed | Online
NSTAR | Dennis | ESMAEX-04408 | 02638 | 23 | Solar & Battery | 4-89A-89A | 2024-12-31 | 2025-01-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Falmouth | ESMAEX-04407 | 02540 | 0 | Battery | 4-72-72 | 2024-12-30 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-14 | [7 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | West Tisbury | ESMAEX-04471 | 02575 | 90 | Solar & Battery | 4-97-97 | 2025-01-28 | 2025-02-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-04432 | 02493 | 20.352 | Solar | 282-H10 | 2025-01-14 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Canton | ESMAEX-04417 | 02021 | 100 | Solar | 470-H4 | 2025-01-03 | 2025-01-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-04434 | 01773 | 15.5 | Other | 320-H6 | 2025-01-15 | 2025-01-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-04430 | 01730 | 999 | Solar | 391-H8 | 2025-03-28 | 2025-04-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Hopkinton | ESMAEX-04426 | 01748 | 10 | Other | 126-H4 | 2025-01-10 | 2025-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Application Completed/Closed | Online
NSTAR | West Newton | ESMAEX-04422 | 02465 | 15.2 | Solar & Battery | 316-01 | 2025-01-10 | 2025-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-04427 | 01720 | 19.58 | Solar & Battery | 416-H4 | 2025-01-10 | 2025-01-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-04534 | 01760 | 23 | Other | 23-H1 | 2025-02-18 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Application Completed/Closed | Online
NSTAR | Westwood | ESMAEX-04689 | 02090 | 17.48 | Solar | 148-H3 | 2025-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-04477 | 01803 | 15.18 | Solar | 346-1395H1 | 2025-01-30 | 2025-02-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sharon | ESMAEX-04435 | 02067 | 240 | Solar | 146-H7 | 2025-05-19 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Milton | ESMAEX-04437 | 02186 | 17.6 | Solar & Battery | 496-H7 | 2025-01-15 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-04481 | 01760 | 20 | Other | 240-H5 | 2025-02-03 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Lexington | ESMAEX-04440 | 02421 | 490 | Solar | 320-H2 | 2025-01-17 | 2025-02-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-04455 | 02539 | 60 | Solar | 4-97-97 | 2025-01-21 | 2025-02-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-29 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Walpole | ESMAEX-04454 | 02081 | 15.3 | Solar & Battery | 146-H4 | 2025-01-21 | 2025-02-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-04695 | 01741 | 60 | Solar & Battery | 512-1399H1 | 2025-03-26 | 2025-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-31 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04457 | 02360 | 15.36 | Solar | 3-72-940 | 2025-01-22 | 2025-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-04462 | 01702 | 23 | Solar & Battery | 455-H5 | 2025-01-23 | 2025-02-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Marion | ESMAEX-04464 | 02738 | 480 | Solar | 3-304-304 | 2025-02-10 | 2025-02-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Waltham | ESMAEX-04466 | 02451 | 4999 | Other | 450-H7 | 2025-04-09 | 2025-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Acton | ESMAEX-04469 | 01720 | 23 | Other | 416-H8 | 2025-01-28 | 2025-03-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Roxbury Crossing | ESMAEX-04674 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-20 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-04555 | 01730 | 22.8 | Solar | 322-1397H1 | 2025-02-21 | 2025-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Roxbury Crossing | ESMAEX-04684 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-25 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Truro | ESMAEX-04490 | 02652 | 11.5 | Solar & Battery | 4-96-96 | 2025-02-06 | 2025-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-04537 | 02539 | 4.72 | Solar | 4-75-123 | 2025-02-19 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Application Completed/Closed | Online
NSTAR | Millis | ESMAEX-04479 | 02054 | 25 | Solar | 130-H2 | 2025-02-03 | 2025-02-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-04-29 | Application Completed/Closed | Online
NSTAR | North Eastham | ESMAEX-04488 | 02651 | 15.2 | Solar & Battery | 4-94B-956 | 2025-02-05 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-04482 | 02360 | 500 | Solar | 3-13-943 | 2025-08-15 | 2025-09-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Marion | ESMAEX-04485 | 02738 | 15.2 | Solar | 3-85-85 | 2025-02-13 | 2025-03-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Application Completed/Closed | Online
NSTAR | Newton | ESMAEX-04493 | 02458 | 23 | Solar & Battery | 467-H12 | 2025-02-06 | 2025-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-04499 | 02747 | 15.2 | Solar | 2-533-503 | 2025-02-07 | 2025-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-09 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-04502 | 01720 | 23 | Solar & Battery | 416-H2 | 2025-02-07 | 2025-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Norfolk | ESMAEX-04491 | 02056 | 20 | Solar & Battery | 146-H3 | 2025-02-07 | 2025-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04741 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2025-04-05 | 2025-09-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Woburn | ESMAEX-04492 | 01801 | 20.1 | Solar | 375-H6 | 2025-02-06 | 2025-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-07-28 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-04512 | 01801 | 22.66 | Solar & Battery | 211-H8 | 2025-02-27 | 2025-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Sharon | ESMAEX-04496 | 02067 | 15.2 | Solar | 470-H12 | 2025-02-06 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-14 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Application Completed/Closed | Online
NSTAR | South Walpole | ESMAEX-04522 | 02071 | 100 | Solar | 146-H3 | 2025-02-14 | 2025-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-04501 | 01770 | 23 | Solar & Battery | 274-H2 | 2025-02-07 | 2025-03-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-04-26 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-04500 | 02130 | 84.6 | Solar |  | 2025-02-07 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Walpole | ESMAEX-04525 | 02081 | 18.78 | Solar & Battery | 146-H4 | 2025-02-15 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-08-11 | Application Completed/Closed | Online
NSTAR | Rochester | ESMAEX-04503 | 02770 | 4980 | Solar & Battery | 3-702-702 | 2025-03-17 | 2025-04-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Upload Technical Documents Customer Action Required | Technical Review
NSTAR | Newton | ESMAEX-04830 | 02456 | 15.58 | Solar | 316-01 | 2025-04-23 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-04506 | 01741 | 15.2 | Solar | 533-H8 | 2025-02-10 | 2025-02-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Application Completed/Closed | Online
NSTAR | Burlington | ESMAEX-04579 | 01803 | 4.5 | Solar | 346-1395H1 | 2025-02-27 | 2025-04-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-04563 | 02494 | 50 | Solar | 292-H9 | 2025-02-25 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lincoln | ESMAEX-04519 | 01773 | 17.16 | Solar | 320-H8 | 2025-02-14 | 2025-03-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-16 | Application Completed/Closed | Online
NSTAR | Chelsea | ESMAEX-04664 | 02150 | 302 | Solar | 488-H7 | 2025-03-19 | 2025-03-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Wayland | ESMAEX-04560 | 01778 | 18.4 | Solar & Battery | 278-H2 | 2025-02-24 | 2025-04-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Application Completed/Closed | Online
NSTAR | Vineyard Haven | ESMAEX-04529 | 02568 | 15.2 | Solar | 4-91-228 | 2025-02-17 | 2025-02-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Cambridge | ESMAEX-04531 | 02138 | 29.31 | Solar & Battery | 821-22 | 2025-02-18 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-19 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-04669 | 01730 | 32.256 | Solar & Battery | 533-H7 | 2025-03-19 | 2025-03-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-04538 | 02021 | 250 | Solar | 470-H7 | 2025-03-31 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-04539 | 01720 | 7.6 | Solar | 512-1399H1 | 2025-02-19 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Application Completed/Closed | Online
NSTAR | Wayland | ESMAEX-04541 | 01778 | 15.2 | Solar |  | 2025-02-19 | 2025-03-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-08-18 | Application Completed/Closed | Online
NSTAR | Needham | ESMAEX-04571 | 02492 | 16.89 | Solar | 148-07 | 2025-02-26 | 2025-03-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Application Completed/Closed | Online
NSTAR | East Freetown | ESMAEX-04551 | 02717 | 20 | Solar & Battery | 2-108-108 | 2025-02-20 | 2025-03-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Application Completed/Closed | Online
NSTAR | Dover | ESMAEX-04544 | 02030 | 19.58 | Solar & Battery | 456-H5 | 2025-02-20 | 2025-03-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-04546 | 01773 | 18.43 | Solar | 320-H8 | 2025-02-20 | 2025-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-04547 | 01701 | 7.6 | Solar | 342-H4 | 2025-02-20 | 2025-03-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | New Bedford | ESMAEX-04597 | 02740 | 80 | Solar | 2-53-65 | 2025-03-05 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westport | ESMAEX-04580 | 02790 | 13.8 | Solar & Battery | 2-522-522 | 2025-02-27 | 2025-06-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Newtonville | ESMAEX-04552 | 02460 | 15.2 | Solar | 467-H5 | 2025-02-24 | 2025-03-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Chatham | ESMAEX-04615 | 02633 | 23 | Other | 4-95B-95B | 2025-03-11 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Roslindale | ESMAEX-04613 | 02131 | 110 | Solar | 1306 | 2025-03-11 | 2025-03-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Oak Bluffs | ESMAEX-04561 | 02557 | 15.36 | Solar | 4-75-75 | 2025-02-24 | 2025-03-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Centerville | ESMAEX-04574 | 02632 | 11.5 | Other | 4-82-82 | 2025-02-26 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-29 | Application Completed/Closed | Online
NSTAR | Sharon | ESMAEX-04575 | 02067 | 10 | Solar | 146-H1 | 2025-02-26 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Hyannis | ESMAEX-04569 | 02601 | 36.16 | Solar | 4-63-532 | 2025-03-05 | 2025-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Lexington | ESMAEX-04572 | 02421 | 9 | Solar | 320-H2 | 2025-02-26 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-06-27 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-04581 | 02472 | 8.25 | Solar | 467-H9 | 2025-02-28 | 2025-03-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-06-09 | Application Completed/Closed | Online
NSTAR | Kingston | ESMAEX-04582 | 02364 | 1800 | Solar & Battery | 3-17-17 | 2025-05-01 | 2025-05-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Centerville | ESMAEX-04587 | 02632 | 19.1 | Solar & Battery | 4-82-82 | 2025-02-28 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Falmouth | ESMAEX-04621 | 02540 | 0 | Other | 4-76-436 | 2025-03-12 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Ashland | ESMAEX-04591 | 01721 | 7.6 | Solar | 455-H8 | 2025-03-05 | 2025-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Osterville | ESMAEX-04658 | 02655 | 57.5 | Solar & Battery | 4-88-88 | 2025-03-18 | 2025-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-05-29 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-04666 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyde Park | ESMAEX-04903 | 02136 | 250 | Solar | 344-1411H | 2025-05-12 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | New Bedford | ESMAEX-04596 | 02745 | 15.2 | Solar | 2-105-105 | 2025-03-05 | 2025-05-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Norfolk | ESMAEX-04601 | 02056 | 18.81 | Solar | 65-H1 | 2025-03-05 | 2025-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Provincetown | ESMAEX-04763 | 02657 | 17.3 | Solar |  | 2025-04-08 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | On Hold | On Hold
NSTAR | Provincetown | ESMAEX-04762 | 02657 | 27.3 | Solar |  | 2025-04-08 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | On Hold | On Hold
NSTAR | Rochester | ESMAEX-04606 | 02770 | 4999 | Solar | 3-703-703 | 2025-03-07 | 2025-04-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Started | Impact Study
NSTAR | Provincetown | ESMAEX-04761 | 02657 | 27.3 | Solar |  | 2025-04-08 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | On Hold | On Hold
NSTAR | Provincetown | ESMAEX-04759 | 02110 | 17.3 | Solar |  | 2025-04-08 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | On Hold | On Hold
NSTAR | Canton | ESMAEX-04610 | 02021 | 5.76 | Solar | 470-H1 | 2025-03-10 | 2025-03-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | Carlisle | ESMAEX-04619 | 01741 | 9.9 | Solar | 512-1399H1 | 2025-03-12 | 2025-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Application Completed/Closed | Online
NSTAR | Waltham | ESMAEX-04625 | 02452 | 15.2 | Solar | 282-H7 | 2025-03-13 | 2025-03-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | West Falmouth | ESMAEX-04618 | 02574 | 30.72 | Other | 4-98A-98A | 2025-03-11 | 2025-03-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Newton Center | ESMAEX-04690 | 02459 | 16.8 | Solar | 443-02 | 2025-03-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Application Completed/Closed | Online
NSTAR | Cambridge | ESMAEX-04705 | 02139 | 90 | Solar | 814-12 | 2025-03-28 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sharon | ESMAEX-04679 | 02067 | 8.784 | Solar | 146-H7 | 2025-03-24 | 2025-04-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-07-18 | Application Completed/Closed | Online
NSTAR | Watertown | ESMAEX-04636 | 02472 | 11.5 | Other | 124-04 | 2025-03-14 | 2025-04-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-04728 | 02119 | 50 | Solar | 52-1487H | 2025-04-02 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Brookline | ESMAEX-04714 | 02446 | 105 | Solar |  | 2025-03-31 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-04631 | 02360 | 425 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Plymouth | ESMAEX-04634 | 02360 | 185 | Solar | 3-13-943 | 2025-04-11 | 2025-04-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04635 | 02360 | 195 | Solar | 3-13-943 | 2025-04-11 | 2025-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Plymouth | ESMAEX-04643 | 02360 | 499.9 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Chilmark | ESMAEX-04641 | 02535 | 16.24 | Solar | 4-97-97 | 2025-03-14 | 2025-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-04660 | 02420 | 9.57 | Solar | 391-H11 | 2025-03-18 | 2025-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-04646 | 01720 | 23.81 | Solar & Battery | 416-H5 | 2025-03-17 | 2025-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Application Completed/Closed | Online
NSTAR | East Boston | ESMAEX-04647 | 02128 | 15.2 | Solar | 108-196H1 | 2025-03-17 | 2025-04-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-07-09 | Application Completed/Closed | Online
NSTAR | Bedford | ESMAEX-04652 | 01730 | 22.6 | Solar & Battery | 533-H7 | 2025-03-18 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-03 | [7 empty] | 0 |  | 0 |  |  | 2025-08-19 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-04649 | 02135 | 23.76 | Solar & Battery | 315-H7 | 2025-03-18 | 2025-03-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-15 | [7 empty] | 0 |  | 0 |  |  | 2025-07-30 | Application Completed/Closed | Online
NSTAR | Wareham | ESMAEX-04650 | 02571 | 990 | Solar | 3-85-928 | 2025-04-11 | 2025-04-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Woburn | ESMAEX-04653 | 01801 | 770 | Solar | 375-H6 | 2025-05-13 | 2025-06-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Kingston | ESMAEX-04654 | 02364 | 990 | Solar | 3-17-17 | 2025-04-11 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | North Dartmouth | ESMAEX-04655 | 02747 | 990 | Solar | 2-533-533 | 2025-04-11 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dedham | ESMAEX-04656 | 02026 | 990 | Solar | 20-H1 | 2025-04-11 | 2025-04-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Winchester | ESMAEX-04720 | 01890 | 35.2 | Solar | 211-H11 | 2025-03-31 | 2025-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 | [7 empty] | 0 |  | 0 |  |  | 2025-06-25 | Application Completed/Closed | Online
NSTAR | Brighton | ESMAEX-04665 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Somerville | ESMAEX-04662 | 02143 | 499 | Solar | 387-148H2 | 2025-04-11 | 2025-05-23 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Fairhaven | ESMAEX-04668 | 02719 | 7.6 | Solar | 2-240-209 | 2025-03-19 | 2025-05-12 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Somerville | ESMAEX-04671 | 02145 | 15.2 | Solar | 250-H4XY | 2025-03-20 | 2025-03-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Arlington | ESMAEX-04715 | 02474 | 16.512 | Solar | 59-1393H1 | 2025-03-31 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-04711 | 01748 | 4980 | Other | 126-H4 | 2025-03-28 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Boston | ESMAEX-04756 | 02128 | 40 | Solar |  | 2025-04-08 | 2025-04-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04692 | 02360 | 23 | Solar & Battery |  | 2025-03-26 | 2025-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Brewster | ESMAEX-04724 | 02631 | 14.73 | Solar | 4-89A-89A | 2025-04-01 | 2025-04-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dorchester | ESMAEX-04718 | 02122 | 40 | Solar | 466-1481H1 | 2025-03-31 | 2025-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-04694 | 01803 | 23 | Solar & Battery | 391-H6 | 2025-03-26 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Application Completed/Closed | Online
NSTAR | West Tisbury | ESMAEX-04700 | 02575 | 22.8 | Solar | 4-97-97 | 2025-03-27 | 2025-08-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Lincoln | ESMAEX-04722 | 01773 | 9.6 | Solar | 282-H1 | 2025-04-01 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Plymouth | ESMAEX-04702 | 02360 | 7.6 | Solar | 3-90-90 | 2025-03-27 | 2025-04-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-24 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-04709 | 01746 | 5.76 | Solar | 65-H5 | 2025-03-28 | 2025-04-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wayland | ESMAEX-04717 | 01778 | 16.1 | Solar | 342-H1 | 2025-03-31 | 2025-04-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 | [7 empty] | 0 |  | 0 |  |  | 2025-07-25 | Application Completed/Closed | Online
NSTAR | South Dennis | ESMAEX-04729 | 02660 | 30.4 | Solar | 4-92B-92B | 2025-04-02 | 2025-04-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wareham | ESMAEX-04732 | 02571 | 10 | Other | 3-84-84 | 2025-04-03 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Roxbury Crossing | ESMAEX-04723 | 02120 | 100 | Solar | 299-1180H | 2025-04-01 | 2025-05-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-04721 | 02030 | 20.2 | Solar | 456-H5 | 2025-04-04 | 2025-04-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-26 | [7 empty] | 0 |  | 0 |  |  | 2025-08-13 | Application Completed/Closed | Online
NSTAR | Boston | ESMAEX-04730 | 02115 | 225 | Internal Combustion Engine | MC-9 | 2025-04-02 | 2025-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sagamore Beach | ESMAEX-04727 | 02562 | 17.6 | Solar | 3-89-925 | 2025-04-02 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04731 | 02360 | 6 | Solar | 3-90-90 | 2025-04-03 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 | [7 empty] | 0 |  | 0 |  |  | 2025-08-11 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-04735 | 02124 | 15.2 | Solar | 483-H5 | 2025-04-03 | 2025-04-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Stoneham | ESMAEX-04737 | 02180 | 7.6 | Solar | 375-H8 | 2025-04-03 | 2025-05-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Application Completed/Closed | Online
NSTAR | Holliston | ESMAEX-04739 | 01746 | 5.76 | Solar | 130-H1 | 2025-04-03 | 2025-05-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-04754 | 02459 | 19.968 | Solar | 292-H11 | 2025-04-29 | 2025-05-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Dartmouth | ESMAEX-04740 | 02747 | 23 | Solar & Battery | 2-522-522 | 2025-04-04 | 2025-05-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 | [7 empty] | 0 |  | 0 |  |  | 2025-08-11 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-04805 | 02539 | 25.74 | Solar | 4-75-75 | 2025-04-17 | 2025-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-08 | Application Completed/Closed | Online
NSTAR | Lexington | ESMAEX-04777 | 02420 | 20.736 | Solar | 533-H3 | 2025-04-09 | 2025-04-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 | [7 empty] | 0 |  | 0 |  |  | 2025-06-05 | Application Completed/Closed | Online
NSTAR | Acton | ESMAEX-04820 | 01720 | 20 | Solar | 416-H8 | 2025-04-21 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Plymouth | ESMAEX-04758 | 02360 | 7.6 | Solar | 3-14-934 | 2025-04-08 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-13 | Application Completed/Closed | Online
NSTAR | Allston | ESMAEX-04752 | 02134 | 50 | Solar | 315-H3 | 2025-04-08 | 2025-04-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-04821 | 02740 | 156 | Solar |  | 2025-04-21 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cataumet | ESMAEX-04846 | 02534 | 10.6 | Solar | 4-78-410 | 2025-04-27 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Ready for PTO | Permission to Operate
NSTAR | Hyannis | ESMAEX-04772 | 02601 | 15.2 | Solar | 4-80B-80B | 2025-04-09 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Framingham | ESMAEX-04778 | 01702 | 4999 | Other | 274-H4 | 2025-05-22 | 2025-06-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Kingston | ESMAEX-04780 | 02364 | 7.6 | Solar | 3-14-14 | 2025-04-09 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Application Completed/Closed | Online
NSTAR | Natick | ESMAEX-04812 | 01760 | 17.66 | Solar | 240-H1 | 2025-04-18 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Application Completed/Closed | Online
NSTAR | Roxbury | ESMAEX-04783 | 02119 | 330 | Solar | 106-H4 | 2025-06-05 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | East Orleans | ESMAEX-04822 | 02643 | 22.8 | Solar & Battery |  | 2025-04-22 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medway | ESMAEX-04788 | 02053 | 15.2 | Solar | 130-H2 | 2025-04-11 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-04789 | 02740 | 30 | Solar | 2-59-38 | 2025-04-14 | 2025-04-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | Wayland | ESMAEX-04790 | 01778 | 5.76 | Solar | 342-H1 | 2025-04-14 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-26 | Application Completed/Closed | Online
NSTAR | Dedham | ESMAEX-04795 | 02026 | 20.76 | Solar & Battery | 2002 | 2025-04-15 | 2025-04-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Yarmouth | ESMAEX-04804 | 02673 | 7.6 | Solar | 4-64-557 | 2025-04-17 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mashpee | ESMAEX-04811 | 02649 | 11.5 | Other | 4-455-455 | 2025-04-17 | 2025-04-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | North Dartmouth | ESMAEX-04807 | 02747 | 10.2 | Solar | 2-107-107 | 2025-04-17 | 2025-04-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Application Completed/Closed | Online
NSTAR | Lincoln | ESMAEX-04808 | 01773 | 6.14 | Solar | 320-H6 | 2025-04-17 | 2025-05-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-04825 | 02536 | 11.5 | Solar & Battery | 4-77A-77A | 2025-04-22 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-04817 | 02332 | 498 | Solar | 3-26-26 | 2025-05-14 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request ISA - Customer Action Required | ISA Agreement
NSTAR | Winchester | ESMAEX-04818 | 01890 | 990 | Solar | 211-H2 | 2025-05-29 | 2025-06-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Hyannis | ESMAEX-04819 | 02601 | 10 | Solar | 4-63-521 | 2025-04-18 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-15 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Chestnut Hill | ESMAEX-04854 | 02467 | 43.056 | Solar & Battery | 496-H5 | 2025-04-30 | 2025-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Newton | ESMAEX-04838 | 02458 | 11.5 | Other | 467-H12 | 2025-04-23 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-04824 | 01730 | 23 | Solar & Battery | 533-H8 | 2025-04-22 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Application Completed/Closed | Online
NSTAR | Walpole | ESMAEX-04840 | 02081 | 16.128 | Solar | 2601 | 2025-04-24 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Application Completed/Closed | Online
NSTAR | Harwich | ESMAEX-04826 | 02645 | 499 | Solar & Battery | 4-95A-95A | 2025-04-23 | 2025-05-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Plymouth | ESMAEX-04832 | 02360 | 11.5 | Other | 3-90-90 | 2025-04-23 | 2025-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lincoln | ESMAEX-04827 | 01773 | 17.1 | Solar | 320-H6 | 2025-04-22 | 2025-04-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  | 2025-09-03 | Application Completed/Closed | Online
NSTAR | Dorchester | ESMAEX-05151 | 02125 | 49.7 | Solar |  | 2025-07-02 | 2025-08-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-04836 | 02421 | 23 | Other | 533-H1 | 2025-04-23 | 2025-05-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 | [7 empty] | 0 |  | 0 |  |  | 2025-08-22 | Application Completed/Closed | Online
NSTAR | West Dennis | ESMAEX-04841 | 02670 | 5 | Other |  | 2025-04-24 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 | [7 empty] | 0 |  | 0 |  |  | 2025-08-18 | Application Completed/Closed | Online
NSTAR | Plymouth | ESMAEX-04837 | 02360 | 15.2 | Solar | 3-88-923 | 2025-04-23 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Application Completed/Closed | Online
NSTAR | Edgartown | ESMAEX-04954 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-04896 | 02138 | 50 | Solar | 828-1369 | 2025-05-07 | 2025-05-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-04955 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Winchester | ESMAEX-04920 | 01890 | 5.84 | Solar | 211-H1 | 2025-05-14 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 | [7 empty] | 0 |  | 0 |  |  | 2025-08-14 | Application Completed/Closed | Online
NSTAR | Pocasset | ESMAEX-04845 | 02559 | 23 | Solar & Battery | 4-86-408 | 2025-04-25 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | North Dartmouth | ESMAEX-04849 | 02747 | 20 | Solar & Battery | 2-533-503 | 2025-04-28 | 2025-05-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-07-29 | Application Completed/Closed | Online
NSTAR | Hopkinton | ESMAEX-04847 | 01748 | 22.288 | Solar & Battery | 274-H5 | 2025-04-28 | 2025-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Chestnut Hill | ESMAEX-04848 | 02467 | 19.2 | Solar | 292-H5 | 2025-04-28 | 2025-05-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-04933 | 01720 | 10 | Other | 416-H1 | 2025-05-15 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-08 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Newton Center | ESMAEX-04853 | 02459 | 11.5 | Other | 292-H11 | 2025-04-29 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mattapan | ESMAEX-04859 | 02126 | 24.58 | Solar | 496-H8 | 2025-04-30 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-04939 | 02493 | 9.24 | Solar | 282-H10 | 2025-05-15 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Sandwich | ESMAEX-04862 | 02537 | 21.88 | Solar | 4-87A-87A | 2025-05-01 | 2025-05-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carver | ESMAEX-04864 | 02330 | 7.6 | Solar | 3-10-10 | 2025-05-01 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-04872 | 02021 | 225 | Solar | 470-H7 | 2025-05-05 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | South Boston | ESMAEX-04869 | 02127 | 15.36 | Solar | 139-160H1 | 2025-05-02 | 2025-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-01 | Application Completed/Closed | Online
NSTAR | Mattapoisett | ESMAEX-04871 | 02739 | 10 | Solar | 2-302-302 | 2025-05-05 | 2025-05-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Boston | ESMAEX-04914 | 02118 | 27.3 | Solar | 318-14 | 2025-05-14 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-04981 | 02459 | 160 | Solar | 17-H2 | 2025-05-27 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-04874 | 02360 | 910 | Solar |  | 2025-06-11 | 2025-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Hyannis | ESMAEX-05058 | 02601 | 84.6 | Solar | 4-84A-84A | 2025-06-13 | 2025-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Missing Agreement Sign - Customer Action Required | Compliances Documents
NSTAR | Boston | ESMAEX-04915 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lincoln | ESMAEX-05031 | 01773 | 13.71 | Solar | 320-H6 | 2025-06-09 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-04916 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-04918 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Watertown | ESMAEX-04885 | 02472 | 66.5 | Solar | 124-02 | 2025-05-06 | 2025-05-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Fairhaven | ESMAEX-04890 | 02719 | 15.76 | Solar | 2-222-222 | 2025-05-06 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Sharon | ESMAEX-04952 | 02067 | 18.85 | Solar |  | 2025-05-19 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sharon | ESMAEX-04899 | 02067 | 2.065 | Solar | 470-H12 | 2025-05-07 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-04894 | 02421 | 11.904 | Solar & Battery | 320-H2 | 2025-05-07 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Chelsea | ESMAEX-04897 | 02150 | 500 | Other | 488-H6 | 2025-07-11 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Hopkinton | ESMAEX-04944 | 01748 | 11.5 | Solar & Battery | 126-H2 | 2025-05-16 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Ready for PTO | Permission to Operate
NSTAR | Acton | ESMAEX-04924 | 01720 | 51.9 | Solar | 416-H2 | 2025-05-15 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-04926 | 02139 | 20 | Solar | 820-45 | 2025-05-15 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-04927 | 02138 | 20 | Solar | 821-24 | 2025-05-15 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Cambridge | ESMAEX-04931 | 02141 | 17.6 | Solar | 812-16 | 2025-05-15 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-04907 | 01720 | 20 | Other | 416-H2 | 2025-05-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Mattapoisett | ESMAEX-04940 | 02739 | 19.1 | Solar & Battery | 2-302-302 | 2025-05-16 | 2025-05-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-16 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Wayland | ESMAEX-05117 | 01778 | 35.75 | Solar | 342-H3 | 2025-06-24 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-04911 | 01776 | 15.2 | Solar | 342-H8 | 2025-05-13 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carlisle | ESMAEX-05321 | 01741 | 38.4 | Solar | 512-1399H1 | 2025-08-14 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-04912 | 02740 | 15.2 | Solar | 2-89-14 | 2025-05-13 | 2025-05-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Arlington | ESMAEX-04919 | 02476 | 29.592 | Solar & Battery | 320-H7 | 2025-05-14 | 2025-07-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Burlington | ESMAEX-04948 | 01803 | 23 | Other | 346-1395H1 | 2025-05-19 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-18 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-04942 | 02746 | 10 | Other | 2-24-182 | 2025-05-16 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-04921 | 02459 | 15.2 | Solar | 443-02 | 2025-05-14 | 2025-05-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dorchester | ESMAEX-05011 | 02124 | 15.7 | Solar | 483-H1 | 2025-06-03 | 2025-06-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request ISA - Customer Action Required | ISA Agreement
NSTAR | Canton | ESMAEX-04922 | 02021 | 17.48 | Solar | 269-1320H1 | 2025-05-14 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-04971 | 02030 | 24.576 | Solar | 456-H3 | 2025-05-22 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Truro | ESMAEX-04945 | 02652 | 11.5 | Other | 4-96-96 | 2025-05-17 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-04956 | 02539 | 31.5 | Solar | 4-75-227 | 2025-05-19 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-04949 | 02127 | 960 | Solar | 99-H7 | 2025-06-03 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Framingham | ESMAEX-04951 | 01701 | 4999 | Other | 455-H2 | 2025-07-31 | 2025-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Duxbury | ESMAEX-04970 | 02332 | 46 | Solar & Battery | 3-26-26 | 2025-05-22 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Application Completed/Closed | Online
NSTAR | North Dartmouth | ESMAEX-04961 | 02747 | 16.5 | Solar | 2-70-506 | 2025-05-19 | 2025-06-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Falmouth | ESMAEX-05104 | 02540 | 200 | Solar | 4-76-436 | 2025-06-23 | 2025-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Natick | ESMAEX-05186 | 01760 | 15.2 | Solar | 23-H1 | 2025-07-09 | 2025-07-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chelsea | ESMAEX-04979 | 02150 | 250 | Solar | 488-H7 | 2025-05-23 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | East Boston | ESMAEX-04978 | 02128 | 50 | Solar | 488-H8 | 2025-05-23 | 2025-06-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-05022 | 02124 | 100 | Solar | 511-1495H | 2025-06-06 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Norfolk | ESMAEX-04967 | 02056 | 240 | Solar | 146-H9 | 2025-07-24 | 2025-08-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Waltham | ESMAEX-04968 | 02451 | 750 | Other | 450-H2 | 2025-08-12 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Natick | ESMAEX-04973 | 01760 | 750 | Other | 433-H9 | 2025-08-01 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dorchester | ESMAEX-05039 | 02125 | 150 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Kingston | ESMAEX-04975 | 02364 | 9.9 | Solar & Battery | 3-18-18 | 2025-05-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Dorchester | ESMAEX-05038 | 02125 | 200 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Kingston | ESMAEX-04976 | 02364 | 28 | Solar & Battery | 3-17-17 | 2025-05-23 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-04992 | 01702 | 100 | Solar | 455-H4 | 2025-05-29 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Roxbury | ESMAEX-05035 | 02119 | 110 | Solar | 143-151H1 | 2025-06-10 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mattapoisett | ESMAEX-04982 | 02739 | 250 | Solar | 2-304-304 | 2025-06-16 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Carlisle | ESMAEX-04996 | 01741 | 18.048 | Solar | 533-H8 | 2025-05-30 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Provincetown | ESMAEX-04986 | 02657 | 14400 | Battery | BESS_POWER_PLANT_928 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-04987 | 02657 | 14400 | Battery | BESS_POWER_PLANT_928 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-04988 | 02657 | 14400 | Battery | BESS_POWER_PLANT_928 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Provincetown | ESMAEX-04989 | 02657 | 14400 | Battery | BESS_POWER_PLANT_928 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Completed/Closed | Online
NSTAR | Canton | ESMAEX-04990 | 02021 | 15.2 | Solar | 470-H6 | 2025-05-29 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Sudbury | ESMAEX-04991 | 01776 | 15.2 | Solar | 342-H8 | 2025-05-29 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-05053 | 01701 | 11.5 | Other | 342-H4 | 2025-06-12 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Edgartown | ESMAEX-05002 | 02539 | 34.6 | Solar | 4-75-75 | 2025-06-02 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Falmouth | ESMAEX-05017 | 02556 | 5 | Solar |  | 2025-06-05 | 2025-06-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westport | ESMAEX-05055 | 02790 | 10 | Solar | 2-532-532 | 2025-06-13 | 2025-07-28 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Marshfield | ESMAEX-04999 | 02050 | 22.8 | Solar | 3-25-42J2 | 2025-05-30 | 2025-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Framingham | ESMAEX-05062 | 01701 | 10 | Solar | 278-H1 | 2025-06-13 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | East Orleans | ESMAEX-05046 | 02643 | 23 | Other | 4-89B-89B | 2025-06-10 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Millis | ESMAEX-05142 | 02054 | 30 | Solar & Battery | 65-H1 | 2025-06-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | Kingston | ESMAEX-05006 | 02364 | 17.6 | Solar | 3-15-15 | 2025-06-03 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Teaticket | ESMAEX-05008 | 02536 | 400 | Solar | 4-76-437 | 2025-06-03 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dedham | ESMAEX-05009 | 02026 | 17.6 | Solar | 2007 | 2025-06-03 | 2025-06-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-11 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Acton | ESMAEX-05020 | 01720 | 160 | Solar & Battery | 416-H5 | 2025-06-05 | 2025-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Walpole | ESMAEX-05014 | 02081 | 15.2 | Solar | 2606 | 2025-06-04 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Application Completed/Closed | Online
NSTAR | East Falmouth | ESMAEX-05061 | 02536 | 11.5 | Other | 4-98B-449 | 2025-06-13 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | West Wareham | ESMAEX-05019 | 02576 | 15.2 | Solar | 3-85-928 | 2025-06-05 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton | ESMAEX-05101 | 02459 | 130 | Solar | 292-H3 | 2025-06-23 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Harwich | ESMAEX-05025 | 02645 | 22.272 | Solar | 4-95A-95A | 2025-06-09 | 2025-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Lincoln | ESMAEX-05027 | 01773 | 24.75 | Solar |  | 2025-06-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Boston | ESMAEX-05089 | 02119 | 40 | Solar | 510-77H | 2025-06-18 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-05040 | 02332 | 20 | Solar | 3-23-23 | 2025-06-10 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Duxbury | ESMAEX-05028 | 02332 | 23.8 | Solar | 3-17-17 | 2025-06-09 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Walpole | ESMAEX-05029 | 02032 | 5.7 | Solar | 146-H4 | 2025-06-09 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Ashland | ESMAEX-05032 | 01721 | 5.76 | Solar | 274-H6 | 2025-06-09 | 2025-06-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-05033 | 02021 | 720 | Solar | 470-H8 | 2025-08-14 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Duxbury | ESMAEX-05041 | 02332 | 20 | Solar |  | 2025-06-10 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-05070 | 02459 | 40 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-05044 | 01770 | 15.2 | Solar | 274-H2 | 2025-06-10 | 2025-06-27 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  | 2025-07-18 | Application Completed/Closed | Online
NSTAR | Newton Center | ESMAEX-05071 | 02459 | 69 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyde Park | ESMAEX-05047 | 02136 | 19.968 | Solar | 441-01 | 2025-06-11 | 2025-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Duxbury | ESMAEX-05049 | 02332 | 20 | Solar | 3-23-23 | 2025-06-11 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-05073 | 02459 | 50 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Falmouth | ESMAEX-05271 | 02540 | 184.3 | Solar | 4-76-436 | 2025-08-01 | 2025-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Needham | ESMAEX-05065 | 02492 | 16.4 | Solar | 148-01 | 2025-06-16 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Carver | ESMAEX-05064 | 02330 | 1999 | Solar & Battery | 3-10-917 | 2025-06-16 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study Hold | Impact Study
NSTAR | Sherborn | ESMAEX-05077 | 01770 | 16.128 | Solar | 274-H2 | 2025-06-17 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-01 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Application Completed/Closed | Online
NSTAR | Wellfleet | ESMAEX-05068 | 02667 | 34.8 | Solar & Battery | 4-94B-656 | 2025-06-16 | 2025-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Marshfield | ESMAEX-05092 | 02050 | 21.88 | Solar & Battery | 3-24A-974 | 2025-06-19 | 2025-06-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Construction | Construction Stage
NSTAR | Walpole | ESMAEX-05078 | 02081 | 15.2 | Solar | 146-H4 | 2025-06-17 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Medfield | ESMAEX-05091 | 02052 | 0 | Battery | 456-H3 | 2025-06-18 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-05079 | 02090 | 19 | Solar | 148-H3 | 2025-06-17 | 2025-07-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Centerville | ESMAEX-05103 | 02632 | 67.3 | Solar | 4-82-82 | 2025-06-23 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-05086 | 02090 | 15.2 | Solar | 456-H1 | 2025-06-18 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lexington | ESMAEX-05087 | 02420 | 15.2 | Solar | 533-H9 | 2025-06-18 | 2025-07-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-05130 | 01748 | 29.952 | Solar & Battery | 126-H4 | 2025-06-26 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Post ISA Technical Review | Technical Review
NSTAR | Holliston | ESMAEX-05088 | 01746 | 15.2 | Solar | 130-H1 | 2025-06-18 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Maynard | ESMAEX-05090 | 01754 | 27.28 | Solar & Battery | 416-H6 | 2025-06-18 | 2025-08-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Yarmouth | ESMAEX-05097 | 02673 | 11.5 | Solar & Battery | 4-92A-561 | 2025-06-20 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Walpole | ESMAEX-05113 | 02081 | 240 | Solar | 146-H8 | 2025-06-25 | 2025-07-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mattapoisett | ESMAEX-05098 | 02739 | 3.8 | Solar | 2-301-305 | 2025-06-20 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-05108 | 01730 | 19 | Solar | 533-H3 | 2025-06-23 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Ashland | ESMAEX-05115 | 01721 | 15.2 | Solar & Battery | 274-H1 | 2025-06-24 | 2025-07-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Cataumet | ESMAEX-05135 | 02534 | 19.18 | Solar & Battery | 4-78-410 | 2025-06-26 | 2025-07-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-05112 | 01701 | 15.376 | Solar & Battery | 278-H1 | 2025-06-24 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-05129 | 01770 | 4.392 | Solar & Battery | 130-H2 | 2025-06-26 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Wayland | ESMAEX-05137 | 01778 | 15.738 | Solar | 278-H2 | 2025-06-27 | 2025-07-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Application Completed/Closed | Online
NSTAR | Framingham | ESMAEX-05121 | 01701 | 7.6 | Solar | 433-H4 | 2025-06-25 | 2025-07-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Canton | ESMAEX-05138 | 02021 | 35.672 | Solar & Battery | 269-1320H1 | 2025-06-27 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Maynard | ESMAEX-05122 | 01754 | 199.8 | Solar | 342-H8 | 2025-06-25 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Maynard | ESMAEX-05123 | 01754 | 199.8 | Solar |  | 2025-06-25 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sharon | ESMAEX-05124 | 02067 | 240 | Solar | 146-H1 | 2025-06-25 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-05163 | 02360 | 990 | Solar |  | 2025-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Assonett | ESMAEX-05134 | 02702 | 23 | Solar & Battery | 2-606-606 | 2025-06-26 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 | [7 empty] | 0 |  | 0 |  |  | 2025-08-29 | Application Completed/Closed | Online
NSTAR | New Bedford | ESMAEX-05255 | 02740 | 27.3 | Solar | 2-55-55 | 2025-07-30 | 2025-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Dartmouth | ESMAEX-05143 | 02747 | 11.9 | Solar | 2-532-532 | 2025-06-29 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Waltham | ESMAEX-05144 | 02451 | 7.296 | Solar & Battery | 450-H6 | 2025-06-30 | 2025-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Winchester | ESMAEX-05147 | 01890 | 31.95 | Solar & Battery | 211-H7XY | 2025-06-30 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Millis | ESMAEX-05149 | 02054 | 15.744 | Solar & Battery | 130-H2 | 2025-07-01 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hyannis | ESMAEX-05157 | 02601 | 20.86 | Solar | 4-63-531 | 2025-07-07 | 2025-08-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-05152 | 01702 | 7.8 | Battery | 455-H5 | 2025-07-02 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Fairhaven | ESMAEX-05159 | 02719 | 150 | Solar | 2-220-220 | 2025-07-07 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Fairhaven | ESMAEX-05158 | 02719 | 150 | Solar | 2-240-209 | 2025-07-07 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wayland | ESMAEX-05156 | 01778 | 34.5 | Other | 342-H1 | 2025-07-04 | 2025-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-05164 | 02021 | 21.88 | Solar | 470-H6 | 2025-07-08 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bedford | ESMAEX-05165 | 01730 | 9.6 | Solar & Battery | 322-1397H1 | 2025-07-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | Harwich | ESMAEX-05188 | 02645 | 90 | Solar | 4-89A-556 | 2025-07-09 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Woburn | ESMAEX-05167 | 01801 | 15.2 | Solar | 211-H6 | 2025-07-08 | 2025-07-21 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dedham | ESMAEX-05175 | 02026 | 7.6 | Solar | 344-1412H1 | 2025-07-08 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-08-06 | Application Completed/Closed | Online
NSTAR | Woburn | ESMAEX-05177 | 01801 | 15.2 | Solar | 375-H6 | 2025-07-08 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Acton | ESMAEX-05180 | 01720 | 17.66 | Solar | 126-H2 | 2025-07-08 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-05181 | 02090 | 15.2 | Solar | 148-H3 | 2025-07-08 | 2025-07-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | New Bedford | ESMAEX-05200 | 02745 | 38.95 | Solar | 2-104-104 | 2025-07-16 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Framingham | ESMAEX-05187 | 01701 | 300 | Solar | 455-H6 | 2025-08-01 | 2025-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sherborn | ESMAEX-05218 | 01770 | 21.12 | Solar | 274-H2 | 2025-07-23 | 2025-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Initiate Meter Installation | Meter
NSTAR | New Bedford | ESMAEX-05207 | 02744 | 180 | Solar | 2-62-62 | 2025-08-20 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Medfield | ESMAEX-05224 | 02052 | 16.512 | Solar | 146-H6 | 2025-07-24 | 2025-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Jamaica Plain | ESMAEX-05191 | 02130 | 10 | Solar | 350-H2 | 2025-07-11 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-05520 | 01803 | 100 | Solar | 391-H8 | 2025-09-26 | 2025-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Bellingham | ESMAEX-05196 | 02019 | 150 | Solar | 65-H4 | 2025-07-14 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-05220 | 02127 | 67.3 | Solar | 465-129H | 2025-07-22 | 2025-07-31 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sagamore | ESMAEX-05406 | 02561 | 10.045 | Solar & Battery | 4-81A-81A | 2025-08-31 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Somerville | ESMAEX-05211 | 02143 | 17.28 | Solar | 13N29 | 2025-07-16 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Boston | ESMAEX-05199 | 80302 | 249.99 | Solar | 323-78H1 | 2025-07-31 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | South Dartmouth | ESMAEX-05203 | 02748 | 10 | Solar | 2-524-524 | 2025-07-15 | 2025-07-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Plymouth | ESMAEX-05204 | 02360 | 250 | Solar | 3-73-927 | 2025-08-15 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Boston | ESMAEX-05240 | 02115 | 34.6 | Solar |  | 2025-07-28 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Missing Agreement Sign - Customer Action Required | Compliances Documents
NSTAR | New Bedford | ESMAEX-05210 | 02744 | 480 | Solar | 2-7-7 | 2025-08-20 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Boston | ESMAEX-05239 | 02136 | 70 | Solar | 60-1409H1 | 2025-07-28 | 2025-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Edgartown | ESMAEX-05229 | 02539 | 106.92 | Solar | 4-75-223 | 2025-07-25 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | New Bedford | ESMAEX-05253 | 02745 | 200 | Solar | 2-103-103 | 2025-07-30 | 2025-09-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | CIP On Hold | On Hold
NSTAR | Waltham | ESMAEX-05217 | 02453 | 45.87 | Solar | 467-H5 | 2025-07-18 | 2025-08-19 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Barnstable | ESMAEX-05237 | 02648 | 11.5 | Other |  | 2025-07-31 | 2025-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Customer ISA eSignature Completed | ISA Agreement
NSTAR | Acton | ESMAEX-05219 | 01720 | 14.19 | Solar & Battery | 416-H1 | 2025-07-21 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Fairhaven | ESMAEX-05230 | 02719 | 200 | Solar | 2-220-201 | 2025-07-25 | 2025-08-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Dorchester | ESMAEX-05382 | 02125 | 200 | Solar | 511-1498H | 2025-08-27 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Mattapoisett | ESMAEX-05238 | 02739 | 16 | Battery | 2-301-301 | 2025-07-28 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dedham | ESMAEX-05225 | 02026 | 15.36 | Solar | 344-1413H1 | 2025-07-24 | 2025-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plympton | ESMAEX-05352 | 02367 | 15 | Other | 3-50-50 | 2025-08-21 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request Customer Care For Additional Details | Compliances Documents
NSTAR | Watertown | ESMAEX-05264 | 02472 | 240 | Solar | 467-H4 | 2025-07-31 | 2025-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Lexington | ESMAEX-05231 | 02421 | 23 | Solar & Battery | 533-H4 | 2025-07-25 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Bellingham | ESMAEX-05263 | 02019 | 200 | Solar | 65-H4 | 2025-07-31 | 2025-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sudbury | ESMAEX-05232 | 01776 | 23.33 | Solar | 342-H8 | 2025-07-25 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Marshfield | ESMAEX-05234 | 02050 | 30.29 | Solar & Battery | 3-27-970 | 2025-07-27 | 2025-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request ISA - Customer Action Required | ISA Agreement
NSTAR | Edgartown | ESMAEX-05236 | 02539 | 15 | Solar | 4-75-123 | 2025-07-28 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Bourne | ESMAEX-05246 | 02559 | 160 | Solar |  | 2025-08-05 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request Customer Care For Additional Details | Compliances Documents
NSTAR | Sharon | ESMAEX-05241 | 02067 | 15.2 | Solar | 470-H12 | 2025-07-28 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Falmouth | ESMAEX-05298 | 02540 | 200 | Solar | 4-98A-98A | 2025-08-08 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Sudbury | ESMAEX-05342 | 01776 | 11.5 | Other | 342-H2 | 2025-08-20 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-05254 | 02360 | 17.28 | Solar | 3-88-923 | 2025-07-30 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Falmouth | ESMAEX-05329 | 02556 | 150 | Solar | 4-78-420 | 2025-08-15 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Wayland | ESMAEX-05257 | 01778 | 15.76 | Solar | 278-H2 | 2025-07-30 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Dartmouth | ESMAEX-05258 | 02747 | 7.6 | Solar | 2-541-541 | 2025-07-30 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Mashpee | ESMAEX-05267 | 02649 | 90 | Other |  | 2025-07-31 | 2025-08-07 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-05323 | 02360 | 100 | Solar | 3-13-943 | 2025-08-14 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | West Yarmouth | ESMAEX-05266 | 02673 | 25 | Other | 4-64-557 | 2025-07-31 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | North Eastham | ESMAEX-05269 | 02651 | 7.6 | Solar & Battery | 4-94A-648 | 2025-08-01 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sudbury | ESMAEX-05279 | 01776 | 20 | Other | 342-H7 | 2025-08-05 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Needham | ESMAEX-05284 | 02494 | 15.2 | Solar | 148-H1 | 2025-08-05 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | West Yarmouth | ESMAEX-05491 | 02673 | 210 | Solar | 4-64-64 | 2025-09-19 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Hyannis | ESMAEX-05490 | 02601 | 210 | Solar | 4-63-521 | 2025-09-19 | 2025-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Orleans | ESMAEX-05273 | 02653 | 102.72 | Solar | 4-89B-89B | 2025-08-05 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request ISA - Customer Action Required | ISA Agreement
NSTAR | Lexington | ESMAEX-05275 | 02421 | 11.5 | Other | 320-H5XY | 2025-08-04 | 2025-08-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Wellfleet | ESMAEX-05274 | 02667 | 15.2 | Solar | 4-94B-656 | 2025-08-04 | 2025-08-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | South Yarmouth | ESMAEX-05489 | 02664 | 180 | Solar | 4-92A-92A | 2025-09-19 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | West Roxbury | ESMAEX-05278 | 02132 | 5.376 | Solar & Battery | 496-H6 | 2025-08-05 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Weston | ESMAEX-05281 | 02493 | 20.73 | Solar | 342-H1 | 2025-08-05 | 2025-08-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-05293 | 01760 | 17.3 | Solar | 23-H1 | 2025-08-07 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Burlington | ESMAEX-05288 | 01803 | 6 | Solar | 391-H7 | 2025-08-06 | 2025-08-13 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-29 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Acton | ESMAEX-05295 | 01720 | 9.1 | Solar & Battery | 416-H5 | 2025-08-08 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Missing Documents - Customer Action Required | Compliances Documents
NSTAR | Newton Center | ESMAEX-05348 | 02459 | 19.2 | Solar | 292-H8 | 2025-08-22 | 2025-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lexington | ESMAEX-05294 | 02421 | 19.968 | Solar | 320-H2 | 2025-08-07 | 2025-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Centerville | ESMAEX-05301 | 02632 | 11.5 | Other | 4-82-82 | 2025-08-11 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Holliston | ESMAEX-05330 | 01746 | 4.392 | Solar & Battery | 274-H3 | 2025-08-18 | 2025-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Plymouth | ESMAEX-05296 | 02360 | 13.36 | Solar | 3-90-90 | 2025-08-22 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Chestnut Hill | ESMAEX-05299 | 02467 | 19.5 | Solar & Battery | 443-07 | 2025-08-09 | 2025-08-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-05380 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-05378 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Rochester | ESMAEX-05300 | 02770 | 7.6 | Solar & Battery | 3-703-703 | 2025-08-11 | 2025-08-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-05307 | 02021 | 250 | Solar |  | 2025-08-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Lincoln | ESMAEX-05308 | 01773 | 9.15 | Solar | 320-H6 | 2025-08-12 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Westwood | ESMAEX-05305 | 02090 | 16.5 | Solar | 456-H1 | 2025-08-11 | 2025-08-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | East Boston | ESMAEX-05304 | 02128 | 121.1 | Solar | 488-H5 | 2025-08-11 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Cambridge | ESMAEX-05417 | 02138 | 7.6 | Solar |  | 2025-09-03 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Details Required for CR - Customer Action Required | Technical Review
NSTAR | Canton | ESMAEX-05303 | 02021 | 5.76 | Solar | 269-1320H1 | 2025-08-11 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-05379 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-05366 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waltham | ESMAEX-05365 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Maximo WO | Impact Study
NSTAR | East Orleans | ESMAEX-05309 | 02643 | 20 | Solar | 4-628-628 | 2025-08-12 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Waltham | ESMAEX-05353 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Allston | ESMAEX-05312 | 02134 | 40 | Solar | 3604 | 2025-08-12 | 2025-08-20 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Fairhaven | ESMAEX-05311 | 02719 | 15.2 | Solar | 2-222-222 | 2025-08-12 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Boston | ESMAEX-05371 | 02122 | 250 | Solar | 483-H4 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Holliston | ESMAEX-05313 | 01746 | 17.28 | Solar | 274-H5 | 2025-08-13 | 2025-08-25 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Cambridge | ESMAEX-05317 | 02138 | 240 | Solar | 828-1104H | 2025-08-14 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Norfolk | ESMAEX-05314 | 02056 | 7.6 | Solar | 146-H3 | 2025-08-13 | 2025-08-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Osterville | ESMAEX-05324 | 02655 | 5 | Other | 4-80A-80A | 2025-08-14 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Natick | ESMAEX-05328 | 01760 | 220 | Solar | 433-H11 | 2025-08-15 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Yarmouth | ESMAEX-05320 | 02664 | 240 | Solar | 4-64-64 | 2025-08-27 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Pocasset | ESMAEX-05344 | 02559 | 9.91 | Battery | 4-81A-81A | 2025-08-20 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | East Walpole | ESMAEX-05319 | 02032 | 3.8 | Solar | 135-1319H1 | 2025-08-14 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lexington | ESMAEX-05346 | 02421 | 19.2 | Solar & Battery | 3402 | 2025-08-20 | 2025-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Chatham | ESMAEX-05325 | 02659 | 42.9 | Solar | 4-95A-95A | 2025-08-15 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Holliston | ESMAEX-05374 | 01746 | 11.712 | Solar & Battery | 274-H3 | 2025-08-26 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Sudbury | ESMAEX-05333 | 01776 | 12.81 | Solar & Battery | 416-H6 | 2025-08-18 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Lower Falls | ESMAEX-05334 | 02462 | 3.3 | Solar & Battery | 292-H2 | 2025-08-18 | 2025-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Waban | ESMAEX-05335 | 02468 | 15.744 | Solar | 292-H12 | 2025-08-18 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Assonett | ESMAEX-05396 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Dedham | ESMAEX-05327 | 02026 | 11.5 | Solar & Battery | 2007 | 2025-08-15 | 2025-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lexington | ESMAEX-05360 | 02421 | 19.14 | Solar | 3401 | 2025-08-25 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Rochester | ESMAEX-05331 | 02770 | 7.6 | Solar | 3-702-702 | 2025-08-15 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Lincoln | ESMAEX-05337 | 01773 | 23.81 | Solar | 320-H8 | 2025-08-18 | 2025-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | North Dartmouth | ESMAEX-05336 | 02747 | 15.2 | Solar | 2-522-522 | 2025-08-18 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Lexington | ESMAEX-05351 | 02420 | 16.83 | Solar | 533-H9 | 2025-08-21 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Weston | ESMAEX-05338 | 02493 | 20 | Solar | 282-H8 | 2025-08-18 | 2025-08-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Acton | ESMAEX-05400 | 01720 | 15.36 | Solar | 416-H8 | 2025-08-29 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Orleans | ESMAEX-05370 | 02653 | 150 | Solar | 4-83-83 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | East Harwich | ESMAEX-05458 | 02645 | 66.24 | Solar | 4-95A-95A | 2025-09-15 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Natick | ESMAEX-05341 | 01760 | 10 | Solar & Battery | 240-H1 | 2025-08-19 | 2025-08-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 | [7 empty] | 0 |  | 0 |  |  |  | Initiated Eversource Document Verification | Compliances Documents
NSTAR | Burlington | ESMAEX-05343 | 01803 | 11.5 | Other | 346-1395H1 | 2025-08-20 | 2025-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-05392 | 01748 | 11.5 | Other | 126-H4 | 2025-08-28 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Chelsea | ESMAEX-05345 | 02150 | 200 | Solar | 488-H2 | 2025-08-20 | 2025-09-01 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Holliston | ESMAEX-05347 | 01746 | 23 | Solar & Battery | 65-H5 | 2025-08-21 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Kingston | ESMAEX-05349 | 02364 | 11.5 | Other | 3-18-18 | 2025-08-21 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dennisport | ESMAEX-05350 | 02639 | 6.144 | Solar & Battery | 4-92B-583 | 2025-08-21 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lincoln | ESMAEX-05381 | 01773 | 7.6 | Solar | 342-H1 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Sudbury | ESMAEX-05359 | 01776 | 17.28 | Solar & Battery | 342-H6 | 2025-08-22 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Dover | ESMAEX-05373 | 02030 | 9.882 | Solar | 456-H5 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Mashpee | ESMAEX-05355 | 02649 | 11.5 | Other | 4-71-71 | 2025-08-22 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | Lexington | ESMAEX-05354 | 02420 | 7.6 | Solar | 391-H11 | 2025-08-22 | 2025-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Newton Center | ESMAEX-05358 | 02459 | 11.5 | Other | 292-H11 | 2025-08-22 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lexington | ESMAEX-05363 | 02420 | 23 | Solar & Battery | 351-02 | 2025-08-25 | 2025-09-04 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Watertown | ESMAEX-05372 | 02472 | 10 | Other | 467-H4 | 2025-08-26 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Maynard | ESMAEX-05369 | 01754 | 3.8 | Solar & Battery | 342-H8 | 2025-08-25 | 2025-09-05 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | New Bedford | ESMAEX-05395 | 02746 | 15.2 | Solar | 2-110-110 | 2025-08-29 | 2025-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Medfield | ESMAEX-05383 | 02052 | 18.048 | Solar | 456-H2 | 2025-08-27 | 2025-09-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Wellfleet | ESMAEX-05403 | 02667 | 67.3 | Solar |  | 2025-08-29 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Wayland | ESMAEX-05397 | 01778 | 15.84 | Solar | 342-H1 | 2025-08-29 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 | [7 empty] | 0 |  | 0 |  |  |  | Customer Accepted ISA Agreement | ISA Agreement
NSTAR | Carlisle | ESMAEX-05390 | 01741 | 18.3 | Solar | UNLINKED | 2025-08-28 | 2025-09-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Canton | ESMAEX-05384 | 02021 | 7.686 | Solar | 470-H10 | 2025-08-28 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Assonett | ESMAEX-05394 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Natick | ESMAEX-05385 | 01760 | 6 | Solar | 240-H3 | 2025-08-27 | 2025-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-05387 | 02360 | 17.6 | Solar | 3-73-73 | 2025-08-28 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Winchester | ESMAEX-05389 | 01890 | 8.064 | Solar & Battery | 211-H7XY | 2025-08-28 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lincoln | ESMAEX-05467 | 01773 | 30 | Other | 320-H6 | 2025-09-17 | 2025-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | West Falmouth | ESMAEX-05412 | 02574 | 19.5 | Solar & Battery | 4-78-420 | 2025-09-03 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Bedford | ESMAEX-05393 | 01730 | 11.5 | Other | 533-H2 | 2025-08-28 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | West Somerville | ESMAEX-05488 | 02144 | 50 | Solar | 250-H6 | 2025-09-19 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Rochester | ESMAEX-05399 | 02770 | 15.76 | Solar | 3-703-703 | 2025-08-29 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | North Chatham | ESMAEX-05404 | 02650 | 8.58 | Solar | 4-95B-95B | 2025-08-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | Brookline | ESMAEX-05438 | 02446 | 140 | Solar | 350-H8 | 2025-09-09 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 | [7 empty] | 0 |  | 0 |  |  |  | Meter Review | Meter
NSTAR | Winchester | ESMAEX-05421 | 01890 | 33.176 | Solar & Battery | 211-H7XY | 2025-09-04 | 2025-09-15 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Hopkinton | ESMAEX-05408 | 01748 | 7.6 | Solar | 126-H2 | 2025-09-02 | 2025-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Lexington | ESMAEX-05410 | 02420 | 11.5 | Other | 351-02 | 2025-09-02 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Chestnut Hill | ESMAEX-05413 | 02467 | 7.4 | Solar | 329-H6 | 2025-09-03 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Wareham | ESMAEX-05414 | 02538 | 3.8 | Solar | 3-82-82 | 2025-09-03 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Kingston | ESMAEX-05416 | 02364 | 200 | Solar | 3-14-14 | 2025-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Newton Center | ESMAEX-05418 | 02459 | 21.4 | Solar & Battery | 467-H14 | 2025-09-03 | 2025-09-11 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Medway | ESMAEX-05419 | 02053 | 200 | Solar | 65-H1 | 2025-09-03 | 2025-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Orleans | ESMAEX-05433 | 02653 | 7.26 | Solar | 4-94A-94A | 2025-09-09 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Maximo WO | Impact Study
NSTAR | Medfield | ESMAEX-05424 | 02052 | 20.13 | Solar | 146-H2 | 2025-09-05 | 2025-09-18 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Woburn | ESMAEX-05425 | 01801 | 11.5 | Solar & Battery | 533-H9 | 2025-09-05 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Natick | ESMAEX-05428 | 01760 | 20.35 | Solar | 240-H5 | 2025-09-16 | 2025-09-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Mashpee | ESMAEX-05426 | 02649 | 7.6 | Solar & Battery | 4-452-452 | 2025-09-08 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Mashpee | ESMAEX-05429 | 02649 | 15.2 | Solar | 4-81B-81B | 2025-09-08 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Framingham | ESMAEX-05431 | 01701 | 19.584 | Solar | 455-H1 | 2025-09-08 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Westwood | ESMAEX-05430 | 02090 | 20 | Solar | 469-H2 | 2025-09-08 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Arlington | ESMAEX-05530 | 02474 | 4.95 | Solar & Battery | 211-H11 | 2025-09-30 | 2025-10-14 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Canton | ESMAEX-05499 | 02021 | 10 | Solar | 470-H11 | 2025-09-23 | 2025-10-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Dover | ESMAEX-05432 | 02030 | 17.56 | Solar | 456-H5 | 2025-09-09 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Lincoln | ESMAEX-05434 | 01773 | 15.2 | Solar | 320-H8 | 2025-09-09 | 2025-09-17 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Eversource Sent ISA Agreement - Customer Action Required | ISA Agreement
NSTAR | West Wareham | ESMAEX-05435 | 02576 | 15.744 | Solar | 3-86-966 | 2025-09-09 | 2025-09-16 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dartmouth | ESMAEX-05436 | 02747 | 367.22 | Solar | 2-541-541 | 2025-09-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Maximo WO | Impact Study
NSTAR | Hopkinton | ESMAEX-05452 | 01748 | 9.15 | Solar | 126-H4 | 2025-09-23 | 2025-09-30 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Request Customer Care For Additional Details | Compliances Documents
NSTAR | Walpole | ESMAEX-05439 | 02081 | 20 | Solar | 456-H1 | 2025-09-09 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Arlington | ESMAEX-05442 | 02474 | 17.92 | Solar | 211-H3 | 2025-09-10 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Hopkinton | ESMAEX-05444 | 01748 | 11.5 | Other | 126-H1 | 2025-09-10 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | East Boston | ESMAEX-05446 | 02128 | 103.8 | Solar | 488-H5 | 2025-09-11 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Marshfield | ESMAEX-05445 | 02050 | 30 | Solar | 3-25-25 | 2025-09-10 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Hopkinton | ESMAEX-05512 | 01748 | 18.048 | Solar | 274-H5 | 2025-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | Milton | ESMAEX-05466 | 02186 | 3.294 | Solar | 496-H7 | 2025-09-16 | 2025-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Dennis | ESMAEX-05448 | 02638 | 15.2 | Solar | 4-89A-89A | 2025-09-12 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Customer Accepted ISA Agreement | ISA Agreement
NSTAR | Lexington | ESMAEX-05453 | 02420 | 19.968 | Solar | 533-H4 | 2025-09-15 | 2025-09-22 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | West Newton | ESMAEX-05451 | 02465 | 11.5 | Other | 1713 | 2025-09-14 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | Provincetown | ESMAEX-05456 | 02657 | 25 | Solar | 4-675-974 | 2025-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Sharon | ESMAEX-05460 | 02067 | 100 | Solar | 146-H1 | 2025-09-15 | 2025-10-03 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Burlington | ESMAEX-05459 | 01803 | 15.2 | Solar & Battery | 391-H7 | 2025-09-15 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sudbury | ESMAEX-05461 | 01776 | 12.87 | Solar | 342-H7 | 2025-09-15 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Dover | ESMAEX-05462 | 02030 | 45.6 | Solar | 456-H5 | 2025-09-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Dover | ESMAEX-05465 | 02030 | 23 | Solar & Battery | 456-H5 | 2025-09-16 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | North Dartmouth | ESMAEX-05472 | 02747 | 15.2 | Solar | 2-523-523 | 2025-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Wayland | ESMAEX-05478 | 01778 | 18.48 | Solar | 278-H2 | 2025-09-17 | 2025-10-08 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Milton | ESMAEX-05475 | 02186 | 23 | Solar & Battery | 362-02 | 2025-09-17 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | Mattapoisett | ESMAEX-05497 | 02739 | 11.5 | Solar & Battery | 3-702-702 | 2025-09-23 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Perform Initial Review | Application Review
NSTAR | New Bedford | ESMAEX-05476 | 02740 | 17.3 | Solar | 2-89-14 | 2025-09-17 | 2025-09-29 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Plymouth | ESMAEX-05479 | 02360 | 17.16 | Solar | 3-89-922 | 2025-09-17 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Technical Review Completed | Technical Review
NSTAR | Sudbury | ESMAEX-05481 | 01776 | 15.2 | Solar | 416-H6 | 2025-09-17 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | North Dartmouth | ESMAEX-05482 | 02747 | 15.2 | Solar | 2-522-522 | 2025-09-17 | 2025-09-24 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Additional Technical Details Required - Customer Action Required | Technical Review
NSTAR | Carlisle | ESMAEX-05483 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2025-09-18 | 2025-09-26 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Submit Compliances Documents | Compliances Documents
NSTAR | South Yarmouth | ESMAEX-05484 | 02664 | 7.6 | Solar | 4-92A-560 | 2025-09-18 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Holliston | ESMAEX-05486 | 01746 | 21.504 | Solar | 274-H3 | 2025-09-19 | 2025-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | West Tisbury | ESMAEX-05505 | 02568 | 45.6 | Solar & Battery |  | 2025-09-24 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Medfield | ESMAEX-05492 | 02052 | 19.2 | Solar | 146-H2 | 2025-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Oak Bluffs | ESMAEX-05514 | 02557 | 33.6 | Solar |  | 2025-09-25 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Maximo WO | Impact Study
NSTAR | Arlington | ESMAEX-05494 | 02474 | 18.048 | Solar | 211-H3 | 2025-09-22 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Maximo WO | Impact Study
NSTAR | Bourne | ESMAEX-05495 | 02532 | 23 | Solar & Battery | 4-86-408 | 2025-09-22 | 2025-10-10 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Sharon | ESMAEX-05496 | 02067 | 50 | Solar |  | 2025-09-23 | 2025-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Weston | ESMAEX-05509 | 02493 | 21.12 | Solar | 282-H1 | 2025-09-25 | 2025-10-06 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Medfield | ESMAEX-05518 | 02052 | 15.2 | Solar | 146-H10 | 2025-09-26 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Acton | ESMAEX-05515 | 01720 | 13.82 | Solar | 416-H5 | 2025-09-25 | 2025-10-09 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Canton | ESMAEX-05517 | 02021 | 24.57 | Solar | 470-H11 | 2025-09-25 | 2025-10-02 | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Initiated Technical Review | Technical Review
NSTAR | Harwich | ESMAEX-05521 | 02645 | 11.5 | Solar & Battery | 4-95A-598 | 2025-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Lexington | ESMAEX-05522 | 02421 | 11.5 | Solar & Battery | 320-H5XY | 2025-09-28 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Incomplete Application - Customer Action Required | Compliances Documents
NSTAR | Plymouth | ESMAEX-05528 | 02360 | 8.064 | Solar & Battery |  | 2025-09-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
NSTAR | Acton | ESMAEX-05529 | 01720 | 11.4 | Solar | 416-H5 | 2025-09-30 |  | #VALUE! |  | #VALUE! |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eversource Waiting For Payment | Application Review
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
[9 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
Formulas:
Total Time Lapsed in Appl Stage = IF([Date Appl Received]=[Date Appl Deemed],0,NETWORKDAYS(WORKDAY([Date Appl Received],1,MALegalHolidays),[Date Appl Deemed],MALegalHolidays))
Total Time Lapsed in Scrn Review Stage = IF([Date Review of Screens Begun]=[Date Review of Screens Completed],0,NETWORKDAYS(WORKDAY([Date Review of Screens Begun],1,MALegalHolidays),[Date Review of Screens Completed],MALegalHolidays))
Tot Time lapsed for SR = IF([Date Suppl Review Began]=[Date Suppl Review Complete],0,NETWORKDAYS(WORKDAY([Date Suppl Review Began],1,MALegalHolidays),[Date Suppl Review Complete],MALegalHolidays))
Tot Time lapsed for Standard Rev = IF([Date Standard Process Rev Began]=[Date Standard Process Rev complete],0,NETWORKDAYS(WORKDAY([Date Standard Process Rev Began],1,MALegalHolidays),[Date Standard Process Rev complete],MALegalHolidays))
Total Time Lapsed for the IS = IF([Date Impact Study Begun]=[Date Impact Study Sent],0,NETWORKDAYS(WORKDAY([Date Impact Study Begun],1,MALegalHolidays),[Date Impact Study Sent],MALegalHolidays))
Total Time Lapsed for DS = IF([Date Detail Study Began]=[Date Detail Study Completed],0,NETWORKDAYS(WORKDAY([Date Detail Study Began],1,MALegalHolidays),[Date Detail Study Completed],MALegalHolidays))
Total Const Time Lapsed = IF([Date Const Began]=[Date Const Completed],0,NETWORKDAYS(WORKDAY([Date Const Began],1,MALegalHolidays),[Date Const Completed],MALegalHolidays))

## Sheet1
DOER Status | Raw Data Enterprise Report Status
Online | Application Completed/Closed
Application Review | Awaiting Work Order Number
Application Review | Eversource Waiting For Payment
Application Review | Incomplete Application Customer Action Required
Application Review | Awaiting App Fee and/or Further Info
Application Review | Awaiting Fee
Technical Review | Eversource Initiated Technical Review
Technical Review | Eversource Technical Review Completed
Technical Review | Initiate Additional Technical Review
Technical Review | Additional Technical Details Required - Customer Action Required
Technical Review | Additional Details Required for CR - Customer Action Required
Technical Review | Eversource Review Schedule Z
Technical Review | Eversource QF - Schedule Z Review
Technical Review | Eversource Initiate Detailed Study
Technical Review | Additional Technical Review Completed
Technical Review | Initiate Application Additional Review
Engineering Review | Awaiting Response and/or Cost Estimates from Eng
Engineering Review | Eng Stage: Awaiting Customer's Response/Docs
Engineering Review | Engineering Review Stage
Engineering Review | Engineering Screen Review
Engineering Review | Engineering Screen Review Desn1 Stage
Engineering Review | Eng Screen Review: Awaiting Customer's Response/Docs
Impact Study | Eng. Impact Study
Impact Study | Eng Impct Stdy:Awaiting Customers Response/Doc
Impact Study | Awaiting Impact Study WO
Impact Study | Awaiting Impact Study Fee & Agreement
Impact Study | Impact Study Stage
Impact Study | Impact Study Started
Impact Study | Awaiting Maximo WO
Impact Study | Impact Study Hold
ISA Agreement | ISA Received/Signed
ISA Agreement | ISA sent
ISA Agreement | Awaiting ISA Receipt/Approval
ISA Agreement | Amended ISA Agreement - Customer Action Required
ISA Agreement | Customer ISA eSignature Completed
ISA Agreement | Amended ISA Agreement Customer Action Required
ISA Agreement | Missing Agreement Sign Customer Action Required
ISA Agreement | Eversource Sent ISA Agreement - Customer Action Required
ISA Agreement | Customer Accepted ISA Agreement
Withdrawn | Application Withdrawn
Design Stage | Design Approval
Construction Stage | Eversource Initiated Construction
Meter | Eversource Initiate Meter Installation
Meter | Meter Review
Meter | Wiring Issues
Permission to Operate | Ready for PTO
Permission to Operate | Permission to Operate
Permission to Operate | Final Close Out Documents - Customer Action Required
Compliances Documents | Submit Compliances Documents
Compliances Documents | Missing Documents - Customer Action Required
Compliances Documents | Awaiting Completion Docs
Compliances Documents | Awaiting Completion Docs and NSTARwork completion
Compliances Documents | Missing Documents - Customer Action Required
Compliances Documents | Missing Agreement Sign - Customer Action Required
Compliances Documents | Incomplete Application - Customer Action Required
Compliances Documents | Initiated Eversource Document Verification
Compliances Documents | Waiting for Customer's Response / Revised Docs
Witness Test | Witness Test Awaiting Cust Response/Doc
Customer Cost | Customer Cost
Cust Docs | Cust Docs
Decommissioned | Decommissioned
Detailed Study Stage | Detailed Study Stage
Exhibit E Agreement | Exhibit E Agreement - Customer Action Required
Field Com | Field Com
Cluster Study | hold cluster
In Queue | In Queue
Rights & Rights/Customer Cost | Same as the status
Study | Waiting for the Study of a Nearby System
In Queue
Compliances Documents | Missing Schedule Z Details - Customer Action Required
On Hold | On Hold
Compliances Documents | Request Customer Care For Additional Details
ISA Agreement | Request ISA - Customer Action Required
Compliances Documents | Supplemental Review Completed
Meter | Wiring Issue - Customer Action Required
Compliance Documents | Request Project Changes - Customer Action Required
Application Review | Eversource Perform Initial Review
Technical Review | Post ISA Technical Review
Technical Review | Upload Technical Documents Customer Action Required
Compliance Documents | Upload Technical Documents (Impact Study)– Customer Action Required
Impact Study | Impact Study Review
ISA Agreement | Permission To Install/ISA Approval
Impact Study | Impact Study Completed
Cancelled | Cancelled
On Hold | CIP On Hold

## Sheet5
WO "withdrawn" in Maximo | Size (AC)
1980806 | 1
2057704 ID2401 | 4
2036912 | 960
2051070 | 2
2086459 | 1440
2086294 | 1440
ID2462
2092354 | 1
2092354 | 1
2088074 | 2
2088074 | 2
TBD-XX | 504
2110822 | 1200
2059927 | 500
2093526 | 512
2098326 | 4.8
2085492 | 2
2101737 | 504
2103346 | 984
2092534 | 1
2103303 | 1992
2103303 | 1992
2103303 | 1992
2102530 | 1992
2106271 | 1992
2135261 | 2
2137254 | 972
2099348 | 420
2090094 | 4.999
2065662 | 2
2117954 | 587
2117955 | 471
1978822 | 2000
1978822 | 2000
2051498 | 500
2051498 | 2000
2054857 | 800
2102432 | 830
2099482 | 880
2127819 | 750
2093910 | 1940
2110823 | 1000
2127227 | 10000
2037775 | 1500
2076812 | 4500
2035449 | 3756
2085514 | 4600
2070813 | 662
2137247 | 1000
2134405 | 990
2136976 | 990
2168512 | 2805
2085252 | 600
2100120 | 480
2099699 | 360
2100110 | 360
2128422 | 540
2020127 | 1000
2136142 | 2000
2184049 | 660
2184405 | 510
2055949 | 2000
2103573 | 2000
2129459 | 840
2126923 | 726
2103577 | 2000
2103577 | 1000
2124636 | 1500
2082060 | 990
2036219 | 4800
2152371 | 566.1
2096445 | 984
2176734 | 770
2200167 | 15.2
2187300 | 2820
2200960 | 16.2
2188716 | 990
2145690 | 648
2135869 | 270
2223988 | 602
2215756 | 19.15
2152205 | 1992
2153294 | 1992
2084724 | 1000
2093470 | 990
2092960 2188541 2209835 | 2000
2158505 | 496
2093456 | 750
2212942 | 16.95
2224405 | 498
2090728 | 420
1992854
1992858
2234626 | 594
2128802 | 1992
2224890 | 4900
2160866 | 576
2245647 | 773
2132335 | 40
2243750 | 22
2217600 | 916
2224661 | 4900
2251155 | 300
2182806 | 648
2116332 | 2000
2116332 | 1800
2116332 | 2000
2116332 | 1650
2217047 | 180
2228336 | 2000
2228336 | 2000
2136808 | 109
2204685 | 366.4
2271383 | 4986
2265026 | 2370
2053880 | 1995
2129905 | 3720
2235087 | 0
2227939 | 632.7
2246192 | 21.95
2269896 | 8300
2270084 | 8300
2051285 | 4000
2212591 | 858
2211077 | 4950
2289828 | 4998
2260848 | 4000
2282256 | 1497
2287856 | 3992
2260503 | 4000
2279222 | 27.72
2263857 | 1580
2291297 | 15
2235688 | 496
2291972
2284556 | 250
2285554 | 4980
2285553 | 3560
2273879 | 72
2273069 | 51.75
2272822 | 86.25
2317182 | 499.9
2284069 | 17
2236306 | 208
2207988 | 27
2313435 | 4998
2336465 | 496
2298565 | 990
2184403 | 2442
2331457 | 1000
2297682 | 3500
2340119 | 1000
2343786 | 924
2270747 | 8300
2327320 | 2000
2345372 | 330
2328095 | 500
2259340 | 3320
2278508 | 1000
2235080 | 180
2361424 | 2000
2361932 | 2000
2361243 | 2000
2361428 | 2000
2277114 | 3000 or 8300
2323381 | 1000
2298092 2298090 | 396
2334415 | 129.6
2180242 | 246
2298567 | 990
2227357 | 2868
2308334 | 2000
2366447 | 1400
2345712 | 1068
2354511 | 1400
2352731 | 516
2290690 | 4000
2297267 | 500
2297503 | 500
2320442 | 7250
2329096 | 1100
2349398 | 1750
2304259 | 5000
2373432 | 2500
2299606 | 4950
2354467 | 3750
2298768 | 999
2354628 | 594.6
2352275 | 694.5
2322219 | 249.9
2252677 | 2695
2317183 | 1000
2369438 | 700
2367475 | 1150
2319563 | 233
2330775 | 4980
2334358 | 3300
2342846 | 2400
2307639 | 1500
2308333 | 500
2281069 | 996
2355861 | 1000
2334531 | 1000
2326311 | 1516
2392617 | 500
2374771 | 3 Options
2299350 | 1250
2304486 | 3060
2300060 | 3060
2285715 | 2200
2327303 | 2000
2269022 | 1250
2349571 | 1000
2394014 | 4990
2323862 | 500
2388535 | 800
2388945 | 2400
2297080 | 1000
2341496 | 1500
2354849 | 5000
2298092 2298087 | 462
2298092 2298091 | 396
2296372 | 4998
2360807 | 1125
2299346 | 8300
2320623 | 999
2392113 | 4000
2288774 | 999
2312223 | 660 / 499
2392885 | 4000
2408783 | 4999
2307641 | 4998
2313433 | 4998
2350166 | 1000
2391483 | 199.8
2412573 | 2260
2130083 | 495.72
2307640 | 250
2404275 | 3146
2295853 | 2000
2303423 | 3000
2306600 | 4999
2412211 | 3104.5
2320445 | 3240
2395067 | 496
2234823 | 480
2326793 | 2000
2277378 | 2500
2407609 | 1420
PP02408258 | 245
5367340 | 199.8
2412699 4575161 | 4990
2301817 | 1000
2388537 | 2760
5403022 | 250
5403782 | 125
2368605 | 999
2238660 6019486 | 7520
2180239 | 4800
5256604 | 1400.5
5244434 | 495.3
5077946 | 466.6
5077981 | 233.2
5078034 | 200
5078087 | 200
5122724 | 250
5131937 | 166
5131879 | 150
5140889 | 150
5140517 | 133.2
5140433 | 100
2319393 | 999
2372246 | 3000
5087787 | 500
5087888 | 250
5087946 | 500
5088024 | 250
5088121 | 500
5088220 | 250
5103412 | 250
4708871 | 2495
5123430 | 4500
2351919 | 1280
5825325 | 499.5
2184045 5541137 | 1200
5243558 | 1519.1
5414087 | 1366.4
PP02333782 | 34.2
PP02334212 | 37.8
2351263 | 110
2334039 | 131.4
PP02271379 | 400
2334854 | 199.8
2334473 | 496
5747397 | 499.5
4470982 | 245
5825273 | 499.5
6620234 | 483.3
PP02329018 | 492
PP02322528 | 499.5
PP02401405 | 2 Options
PP02311123 | 1531.8
2414387 | 610
4258166 | 610
4287867 | 610
2414312 | 1220
5403662 | 125
5747447
PP02330941 | 250
PP02325768 | 463.3
5132265 | 240
PP02392746 | 500
5113061 | 433
7169274 | 806.6
PP02314369 | 3500
PP02340380 | 999
5814399 | 250
PP02331280 | 250
PP02331299 | 250
7920908 | 999
7907672 | 11000
PP02361432 | 4000
PP02285552 | 2000
PP02408400 | 680
2239746 5414930 | 997.7
PP02306598 | 1000
PP02341375 | 200
7332788 | 483.3
PP02273508 | 2000
8638009 | 4999.2
PP02381559 | 865.8
5473617 | 486
5473473 | 500
PP02328012 | 15000
5088274 | 500
5088314 | 500
5097801 | 250
PP02316355 | 999
2126109 | 828
4972223 | 1122
PP02274408 | 500
8638134 | 4999
PP02363427 | 2000
4619595 | 2500
4696273 | 2500
5354874 | 240
PP02296371 | 1000
PP02356276 | 4975
PP02370996 | 1560
PP02289380 | 1000
PP02291742 | 500
5113167 | 500
PP02336099 | 1500
4607301 | 2125
PP02409830 | 5000
5509173 | 500
PP02283036 | 2000
PP02343563 | 5000
PP02399839 | 4999
5256556 | 774.3
PP02329391 | 1500
PP02329466 | 4000
PP02330206 | 500
2412929 9567890 | 4500
4490762 | 5000
4717656 | 2495
PP02403584 | 2958
PP02323237 | 2925
4404592 | 2000
PP02407070 | 499
PP02327130 | 4980
8976639 | 2000
5132501 | 3000
11390811 | 510.3
8637148 | 4999.2
6932569 | 2500
5566155 | 1000

## Sheet3
Facility ID (if any) | City/Town | ZIP Code | Design Capacity (kW) | Fuel Type (PV, Wind, etc) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Begun | Date Review of Screens Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/Standard / Complex Project** | Construction Timeline Commitment (Workdays) | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | NOTES | Date of Info Request | Private/Gov't | Net Metered? (Y/N)
1721 | Brewster | 2170 | 10 | Wind | 4-89B-576 | 2010-11-19 | 2010-12-03 | 10 | 9 | 1 | 2010-12-03 | 2011-02-04 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-21 | Online |  | Private | Y
5202637 | Orleans |  | 262.5 | Fuel Cell | TBD | 2021-02-26 | 2021-02-26 |  |  |  | 2021-03-16 | [37 empty] | 2021-07-21 | Online
5333489 | West Barnstable | 450 | 450 | PV | TBD | 2021-03-15 | 2021-03-15 |  |  |  | 2021-03-31 | [24 empty] | 2021-05-19
2282638 | Ashland | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
5377796 | Acton | 1270 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 |  |  |  | 2021-04-06
5377708 | Acton | 1270 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 |  |  |  | 2021-04-07
5367340 | Acton | 1270 | 199.8 | PV | TBD | 2021-03-02 | 2021-03-19 |  |  |  | 2021-04-02
2392184 | Bedford | 1370 | 20 | PV | 533-H8 | 2020-03-17 | 2020-03-18 |  |  |  | 2020-04-03 | [24 empty] | 2020-04-22 | [13 empty] | Withdrawn
2370583 | Ashland | 1421 | 125 | PV | TBD | 2019-10-31 | 2019-11-12 |  |  |  | 2019-11-27 | [24 empty] | 2020-05-21
2296564 | Sandwich | 1543 | 4890 | PV & Battery | 4-81B-443 | 2018-07-24 | 2018-08-29 | 26 |  | 26 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0
2165880 | Framingham | 1701 | 30 | PV | 4-98A-98A | 2016-07-22 | 2016-08-09 | 12 |  | 12 | 2016-08-29 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | [7 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online |  | PRIVATE
2122694 | Framingham | 1701 | 328.75 | CHP | 433-H1 | 2016-01-04 | 2016-03-16 | 52 |  | 52 | 2016-01-12 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-10-19 | [6 empty] | 0 |  | 0 |  |  | 2017-04-04 | Online |  | NO EXPORT | N
2174568 | Framingham | 1701 | 165 | PV | 433-H3 | 2016-09-09 | 2016-09-15 | 4 |  | 4 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
2129908 | Framingham | 1701 | 1250 | PV | 203-1348H3 | 2016-02-01 | 2016-02-04 | 3 |  | 3 | 2016-02-19 |  | -30301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  | 2017-12-18 | Online
2171111 | Framingham | 1701 | 1760 | PV | 455-H7 | 2016-07-29 | 2016-09-07 | 28 |  | 28 | 2016-09-23 |  | -30456 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-22 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2018-04-30 | Online
2287284 | Framingham | 1701 | 249.8 | PV | 278-H1 | 2018-06-06 | 2018-06-29 | 17 |  | 17 | 2018-07-18 |  | -30919 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-09-21 | [6 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
2349777 | Framingham | 1701 | 57.6 | PV | TBD | 2019-06-27 | 2019-06-27 |  |  |  | 2019-07-15 | [24 empty] | 2019-07-17 | [12 empty] | 2019-12-31 | Online
2304490 | Framingham | 1701 | 43.2 | PV | 433-H2 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-11-02 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online |  | Private
4619474 | Framingham | 1701 | 17.6 | PV & Battery | 278-H1 | 2020-11-09 | 2020-11-24 |  |  |  | 2020-12-21 | [24 empty] | 2021-01-20 | [12 empty] | 2021-03-18 | Online
2276786 | Framingham | 1701 | 15.8 | PV | 433-H8 | 2018-03-01 | 2018-04-27 | 41 |  | 41 | 2018-05-15 |  | -30873 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2286970 | Framingham | 1701 | 21.68 | PV | 342-H4 | 2018-05-15 | 2018-06-29 | 33 |  | 33 | 2018-07-17 |  | -30918 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | [7 empty] | 0 |  | 0 |  |  |  | In Queue
2307346 | Framingham | 1701 | 81 | PV | 278-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -31008 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2282639 | Ashland | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2350003 | Framingham | 1701 | 72 | PV | 433-H8 | 2019-06-24 | 2019-07-08 |  |  |  | 2019-07-17 | [24 empty] | 2019-08-13
2359697 | Framingham | 1701 | 43.2 | PV | TBD | 2019-09-03 | 2019-09-03 |  |  |  | 2019-09-17 | [24 empty] | 2019-10-10 | [13 empty] | Withdrawn
2365418 | Framingham | 1701 | 199.8 | PV | TBD | 2019-09-27 | 2019-10-09 |  |  |  | 2019-10-24
2395659 | Framingham | 1701 | 57.6 | PV | TBD | 2020-04-20 | 2020-04-20 |  |  |  | 2020-05-04 | [24 empty] | 2020-07-07 | [12 empty] | 2022-03-08 | Online
2405461 | Framingham | 1701 | 365 | PV | TBD | 2020-06-01 | 2020-07-06 |  |  |  | 2020-07-06 | [24 empty] | 2020-09-09
2406660 | Framingham | 1701 | 17.6 | PV & Battery | TBD | 2020-06-15 | 2020-06-15 |  |  |  | 2020-07-20 | [24 empty] | 2020-10-15 | [12 empty] | 2021-07-01 | Online
2408018 | Framingham | 1701 | 22 | PV & Battery | TBD | 2020-07-01 | 2020-07-03 |  |  |  | 2020-07-27 | [24 empty] | 2020-12-24 | [12 empty] | 2022-01-06 | Online
2408258 | Framingham | 1701 | 245 | PV & Battery | TBD | 2020-07-15 | 2020-07-17 |  |  |  | 2020-07-28 | [24 empty] | 2021-02-10
4532766 | Framingham | 1701 | 16.4 | PV | TBD | 2020-09-30 | 2020-11-02 |  |  |  | 2020-11-25 | [24 empty] | 2020-12-15 | [12 empty] | 2021-10-20 | Online
4637906 | Framingham | 1701 | 250 | PV | TBD | 2020-11-25 | 2020-11-25 |  |  |  | 2021-01-05 | [24 empty] | 2021-02-24
5113610 | Framingham | 1701 | 35.2 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | [28 empty] | 2021-08-23 | [13 empty] | Withdrawn
5393050 | Framingham | 1701 | 10 | Battery | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08
ESMAEX-00105 | Framingham | 1701 | 16 | PV | 342-H4 | 2021-05-05 | 2021-05-20 | [28 empty] | 2021-06-03 | [12 empty] | 2021-08-04 | Online |  |  | Y
ESMAEX-00222 | Framingham | 1701 | 9.8 | PV & Battery | 342-H4 | 2021-07-01 | 2021-07-21 | [28 empty] | 2021-09-28 | [12 empty] | 2022-05-20 | Online |  |  | Y
ESMAEX-00236 | Framingham | 1701 | 4999 | Battery | TBD | 2021-08-31 | 2021-09-16 | [42 empty] | In Queue |  |  | Y
ESMAEX-00419 | Framingham | 1701 | 17.6 | PV & Battery | 433-H8 | 2021-09-17 | 2021-10-12 | [28 empty] | 2022-10-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-00801 | Framingham | 1701 | 20 | PV | 455-H1 | 2022-02-03 | 2022-02-24 | [28 empty] | 2022-02-25 | [12 empty] | 2022-06-22 | Online |  |  | Y
ESMAEX-01117 | Framingham | 1701 | 16 | PV | 433-H4 | 2022-04-26 | 2022-05-18 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01181 | Framingham | 1701 | 16.512 | PV & Battery | 278-H2 | 2022-05-15 | 2022-06-06 | [28 empty] | 2022-06-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01342 | Framingham | 1701 | 6 | PV & Battery | 278-H1 | 2022-07-01 | 2022-07-21 | [28 empty] | 2022-09-06 | [12 empty] | 2022-11-02 | Online |  |  | Y
ESMAEX-01432 | Framingham | 1701 | 15.2 | PV & Battery | 455-H1 | 2022-08-03 | 2022-09-27 | [28 empty] | 2022-10-24 | [12 empty] | 2023-03-10 | Online |  |  | Y
ESMAEX-01509 | Framingham | 1701 | 17.1 | PV | 455-H1 | 2022-08-25 | 2022-09-22 | [28 empty] | 2022-10-14 | [12 empty] | 2023-03-13 | Online |  |  | Y
ESMAEX-01634 | Framingham | 1701 | 17.92 | PV & Battery | 433-H3 | 2022-09-27 | 2022-10-14 | [28 empty] | 2022-10-21 | [12 empty] | 2023-03-23 | Online |  |  | Y
ESMAEX-01640 | Framingham | 1701 | 19.9 | PV & Battery | 455-H1 | 2022-09-28 | 2022-10-18 | [28 empty] | 2023-01-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01837 | Framingham | 1701 | 20.2 | PV & Battery | 455-H1 | 2022-11-21 | 2022-12-13 | [28 empty] | 2023-01-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01876 | Framingham | 1701 | 20 | PV | 455-H4 | 2022-12-01 | 2022-12-29 | [28 empty] | 2023-01-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01939 | Framingham | 1701 | 16.104 | PV | 455-H1 | 2022-12-21 | 2023-01-10 | [28 empty] | 2023-01-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02247 | Framingham | 1701 | 15.3 | PV | 342-H4 | 2023-03-08 | 2023-03-23 | [28 empty] | 2023-03-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02275 | Framingham | 1701 | 15.2 | PV | 455-H1 | 2023-03-16 | 2023-04-03 | [28 empty] | 2023-04-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-02417 | Framingham | 1701 | 17.4 | PV | 342-H2 | 2023-04-26 | [43 empty] | In Queue |  |  | Y
2324659 | Freetown | 1701 | 4980 | PV & Battery | 2-605-605 | 2018-12-27 | 2019-02-01 | 26 |  | 26 | 2019-02-11 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
24-9982 | Winchester | 1701 | 22 | PV & Battery | TBD | 2020-07-21 | 2020-07-21 |  |  |  | 2020-08-10
2409041 | Acton | 1702 | 15.6 | PV & Battery | 416-H5 | 2020-07-11 | 2020-07-15 |  |  |  | 2020-08-03 | [38 empty] | Withdrawn
2385800 | Arlington | 1702 | 187.5 | PV | TBD | 2020-01-30 | 2020-01-30 |  |  |  | 2020-02-14 | [37 empty] | 2021-10-12 | Online
2180488 | Framingham | 1702 | 50 | PV | 2408 | 2016-09-19 | 2016-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-17 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online |  | PRIVATE
2181138 | Framingham | 1702 | 51 | PV | 278-H1 | 2016-09-19 | 2016-10-12 | 17 |  | 17 | 2016-11-14 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-04-10 | [6 empty] | 0 |  | 0 |  |  | 2017-09-20 | Online |  | PRIVATE
2226553 | Framingham | 1702 | 120 | PV | 240-H4 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30666 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
2243010 | Framingham | 1702 | 256 | PV | 455-H4 | 2017-10-04 | 2017-10-18 | 9 |  | 9 | 2017-11-03 |  | -30738 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-08-06 | Online
2227941 | Framingham | 1702 | 1095.78 | PV | 240-H6 | 2017-06-26 | 2017-07-06 | 7 |  | 7 | 2017-08-01 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
2274154 | Framingham | 1702 | 198 | PV | 2411 | 2018-04-13 | 2018-04-17 | 2 |  | 2 | 2018-05-01 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | [7 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
2264047 | Framingham | 1702 | 125 | PV | 2410 | 2018-01-16 | 2018-02-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | [7 empty] | 0 |  | 0 |  |  | 2019-04-22 | Online
2307344 | Framingham | 1702 | 57.6 | PV | 24-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -31008 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-27 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-13 | Online |  | Private
2338764 | Framingham | 1702 | 15.2 | PV | 455-H5 | 2019-01-04 | 2019-04-19 |  |  |  | 2019-05-21 | [24 empty] | 2019-06-21 | [12 empty] | 2019-12-30 | Online
2325422 | Framingham | 1702 | 240 | PV | 433-H8 | 2019-01-14 | 2019-01-14 | 0 |  | 0 | 2019-02-15 |  | -31071 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
2296563 | Framingham | 1702 | 15.2 | PV | 274-H1 | 2018-08-02 | 2018-08-29 | 19 |  | 19 | 2018-09-18 | 2018-11-15 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-11-16 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2270751 | Framingham | 1702 | 528 | PV | 519-175H1 | 2018-01-31 | 2018-03-21 | 35 |  | 35 | 2018-04-11 | 2018-11-29 | 166 |  | 166 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2021-06-28 | Online |  | Private
2175097 | Framingham | 1702 | 180 | PV | 240-H4 | 2016-09-28 | 2016-10-03 | 3 |  | 3 | 2016-10-14 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2182806 | Framingham | 1702 | 648 | PV | 240-H6 | 2016-10-03 | 2016-11-18 | 34 |  | 34 | 2016-11-22 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2183183 | Framingham | 1702 | 220 | Battery | 455-H5 | 2016-10-28 | 2016-11-14 | 11 |  | 11 | 2016-11-28 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2242066 | Framingham | 1702 | 20 | PV | 455-H5 | 2017-08-30 | 2017-10-11 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2311128 | Framingham | 1702 | 492 | PV | 455-H2 | 2018-12-05 | 2018-12-05 | 0 |  | 0 | 2018-12-05 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2325768 | Framingham | 1702 | 996 | PV | 240-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
2372222 | Framingham | 1702 | 250 | PV | TBD | 2019-10-11 | 2019-10-15 |  |  |  | 2019-11-01 | [38 empty] | Withdrawn
2378471 | Framingham | 1702 | 15.2 | PV | 274-H1 | 2019-12-02 | 2019-12-12 |  |  |  | 2020-01-06 | [24 empty] | 2020-04-02 | [13 empty] | Withdrawn
2384624 | Framingham | 1702 | 440 | PV | TBD | 2020-01-21 | 2020-01-23 |  |  |  | 2020-02-06 | [24 empty] | 2020-06-12 | [12 empty] | 2021-08-03 | Online
2388879 | Framingham | 1702 | 400 | PV | TBD | 2020-01-21 | 2020-02-24 |  |  |  | 2020-03-06 | [24 empty] | 2020-10-30 | [12 empty] | 2021-12-31 | Online
2390546 | Framingham | 1702 | 100 | PV | TBD | 2020-03-02 | 2020-03-04 |  |  |  | 2020-03-19 | [24 empty] | 2020-05-21 | [13 empty] | Withdrawn
2396140 | Framingham | 1702 | 400 | PV | TBD | 2020-04-09 | [43 empty] | Withdrawn
2284070 | Ashland | 1721 | 100 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 |  |  |  | 2018-06-28 | [24 empty] | 2019-07-17
2397729 | Framingham | 1702 | 240 | PV | TBD | 2020-04-23 | 2020-04-27 |  |  |  | 2020-05-14 | [24 empty] | 2020-12-18 | [13 empty] | Withdrawn
2404459 | Framingham | 1702 | 61.2 | PV | TBD | 2020-04-30 | 2020-06-10 |  |  |  | 2020-07-01 | [24 empty] | 2020-09-09 | [12 empty] | 2021-09-27 | Online
2311297 | Canton | 2021 | 225 | PV | 470-H7 | 2018-11-14 | 2018-11-21 |  |  |  | 2018-12-06 | [24 empty] | 2020-01-15 | [12 empty] | 2021-02-04 | Online
4619506 | Framingham | 1702 | 205 | PV | TBD | 2020-11-18 | 2020-11-24 |  |  |  | 2020-12-23 | [24 empty] | 2021-03-03
5587228 | Framingham | 1702 | 167.32 | PV | TBD | 2021-04-13 | 2021-04-14 |  |  |  | 2021-04-29 | [24 empty] | 1932-09-13
ESMAEX-00438 | Framingham | 1702 | 21.28 | PV & Battery | 455-H5 | 2021-09-21 | 2021-10-07 | [28 empty] | 2021-12-06 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00697 | Framingham | 1702 | 11.5 | PV & Battery | 519-175H1 | 2021-12-28 | 2022-01-14 | [28 empty] | 2022-05-18 | [12 empty] | 2023-03-01 | Online |  |  | Y
ESMAEX-00787 | Framingham | 1702 | 4999.2 | Battery | 433-H11 | 2022-03-09 | 2022-08-01 | [42 empty] | In Queue |  |  | Y
ESMAEX-00916 | Framingham | 1702 | 3.8 | PV | 455-H5 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-05-02 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-00940 | Framingham | 1702 | 10 | PV & Battery | 455-H5 | 2022-03-17 | 2022-04-08 | [28 empty] | 2022-05-11 | [12 empty] | 2022-06-29 | Online |  |  | Y
ESMAEX-00951 | Framingham | 1702 | 240 | PV & Battery | 455-H5 | 2022-03-21 | 2022-05-24 | [28 empty] | 2022-11-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01108 | Framingham | 1702 | 480 | PV | 455-H5 | 2022-05-20 | 2022-06-09 | [28 empty] | 2022-11-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01126 | Framingham | 1702 | 67.3 | PV & Battery | TBD | 2022-04-29 | 2022-05-18 | [28 empty] | 2022-06-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-01127 | Framingham | 1702 | 50 | PV | TBD | 2022-04-29 | 2022-05-24 | [28 empty] | 2022-06-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-01130 | Framingham | 1702 | 67.3 | PV & Battery | TBD | 2022-04-29 | 2022-05-24 | [28 empty] | 2022-06-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01377 | Framingham | 1702 | 200 | PV | TBD | 2022-08-04 | 2022-08-25 | [28 empty] | 2022-10-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01386 | Framingham | 1702 | 200 | PV | 455-H4 | 2022-08-08 | 2022-09-01 | [28 empty] | 2022-10-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01409 | Framingham | 1702 | 200 | PV | 455-H4 | 2022-08-15 | 2022-09-09 | [28 empty] | 2022-10-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-01419 | Framingham | 1702 | 200 | PV & Battery | 455-H4 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-10-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01441 | Framingham | 1702 | 250 | PV | 455-H4 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-10-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-01470 | Framingham | 1702 | 250 | PV & Battery | 455-H4 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-10-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-01655 | Framingham | 1702 | 15.2 | PV & Battery | 24-H1 | 2022-10-03 | 2022-10-14 | [28 empty] | 2022-10-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-02172 | Framingham | 1702 | 15.2 | PV & Battery | 240-H4 | 2023-02-17 | 2023-03-08 | [28 empty] | 2023-03-23 | [13 empty] | In Queue |  |  | Y
4937121 | Framingham | 1703 | 21.83 | PV | TBD | 2021-01-21 | 2021-01-21 |  |  |  | 2021-02-17 | [24 empty] | 2021-08-18 | [12 empty] | 2022-07-08 | Online
2282056 | Framingham | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 | 2018-06-15 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2282066 | Framingham | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
1466 | Acton | 1720 | 190 | PV | 416-H2 | 2009-10-09 | 2009-10-15 | 4 | 2 | 2 | 2009-10-15 | 2009-11-19 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-10 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-14 |  | 2010-01-14 | Online |  | Private | Y
1464 | Acton | 1720 | 95 | PV | 416-H2 | 2009-10-06 | 2009-10-09 | 3 | 0 | 3 | 2009-10-09 | 2009-12-10 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2009-06-22 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-25 |  | 2010-02-25 | Online |  | Private | Y
2170908 | Acton | 1720 | 21.9 | PV | 416-H4 | 2016-08-25 | 2016-09-01 | 5 |  | 5 | 2016-07-22 |  | -30411 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
2229787 | Acton | 1720 | 22.8 | PV | 416-H4 | 2017-07-10 | 2017-07-24 | 10 |  | 10 | 2017-08-11 |  | -30680 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2241211 | Acton | 1720 | 22.8 | PV | 416-H8 | 2017-09-22 | 2017-09-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-28 | 2017-12-05 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
2293955 | Acton | 1720 | 17.56 | PV | 416-H4 | 2018-07-20 | 2018-08-10 | 15 |  | 15 | 2018-08-29 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-23 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  | 2019-04-05 | Online |  | Private
2347245 | Acton | 1720 | 60 | PV | 416-H8 | 2019-06-06 | 2019-06-17 |  |  |  | 2019-06-28 | [24 empty] | 2019-07-10 | [12 empty] | 2019-12-31 | Online
2290885 | Acton | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | 44 |  | 44 | 2018-08-08 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
2325167 | Acton | 1720 | 43.2 | PV | 416-H2 | 2019-02-07 | 2019-02-07 |  |  |  | 2019-02-14 | [24 empty] | 2019-05-13 | [12 empty] | 2020-09-25 | Online
2355854 | Acton | 1720 | 750 | PV | tbd | 2019-07-30 | 2019-08-05 |  |  |  | 2019-08-23 | [24 empty] | 2019-11-12 | [12 empty] | 2020-11-04 | Online
2272445 | Acton | 1720 | 2100 | PV & Battery | 416-H2 | 2018-03-23 | 2018-04-04 | 8 |  | 8 | 2018-04-19 |  | -30855 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
2172398 | Acton | 1720 | 101 | PV | 416-H9 | 2016-08-18 | 2016-09-07 | 14 |  | 14 | 2016-10-03 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2171112 | Acton | 1720 | 39.1 | PV | 416-H5 | 2016-08-22 | 2016-09-06 | 11 |  | 11 | 2016-09-23 |  | -30456 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2171989 | Acton | 1720 | 40 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2171992 | Acton | 1720 | 52.9 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2182998 | Acton | 1720 | 288 | PV | 416-H4 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-23 |  | -30499 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 | [7 empty] | 0 |  | 0
2223990 | Acton | 1720 | 167 | PV | 416-H4 | 2017-06-07 | 2017-06-15 | 6 |  | 6 | 2017-07-07 |  | -30655 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2261525 | Acton | 1720 | 143.2 | PV | 416-H4 | 2017-06-07 | 2018-01-11 | 151 |  | 151 | 2018-01-11 |  | -30785 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | [7 empty] | 0 |  | 0 |  |  |  | In Queue
2271183 | Acton | 1720 | 5040 | PV & Battery | 416-H9 | 2018-03-01 | 2018-03-21 | 14 |  | 14 | 2018-04-12 |  | -30850 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
2280862 | Acton | 1720 | 1496 | PV & Battery | 416-H1 | 2018-03-01 | 2018-05-23 | 59 |  | 59 | 2018-06-07 |  | -30890 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
2288774 | Acton | 1720 | 999 | PV | 416-H4 | 2018-06-20 | 2018-07-12 | 16 |  | 16 | 2018-07-27 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2020-09-30
2290339 | Acton | 1720 | 300 | PV | 416-H4 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30933 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2290347 | Acton | 1720 | 360 | PV | 416-H9 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30933 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2298285 | Acton | 1720 | 490 | PV | 416-H4 | 2018-07-10 | 2018-09-06 | 42 |  | 42 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2320442 | Wareham | 2571 | 5000 | PV | 8-83-83 | 2018-12-12 | 2018-12-21 | 7 |  | 7 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2322632 | Acton | 1720 | 242 | PV | 416-H4 | 2019-01-18 |  | -31051 |  | 0 | 2019-01-30 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0
2322525 | Mattapoisett | 2739 | 115.2 | PV | 2-302-302 | 2019-01-15 | 2019-01-17 |  |  |  | 2019-01-29 | [24 empty] | 2019-05-14 | [12 empty] | 2020-01-10 | Online
2350124 | Acton | 1720 | 999 | PV | TBD | 2019-07-02 | 2019-07-09 |  |  |  | 2019-07-17
2359934 | Acton | 1720 | 100 | PV | TBD | 2019-09-03 | 2019-09-03 |  |  |  | 2019-09-19 | [24 empty] | 2019-09-27
2385734 | Acton | 1720 | 200 | PV | TBD | 2019-12-12 | 2020-01-31 |  |  |  | 2020-02-14 | [24 empty] | 2020-03-25
2389509 | Acton | 1720 | 27 | Battery | 416-H4 | 2020-02-21 | 2020-02-25 |  |  |  | 2020-03-11
2395297 | Acton | 1720 | 240 | PV | TBD | 2020-04-08 | 2020-04-15 |  |  |  | 2020-04-27 | [24 empty] | 2020-07-07 | [12 empty] | 2022-08-22 | Online
2413389 | Acton | 1720 | 5000 | PV & Battery | TBD | 2020-08-06 |  |  |  |  | 2020-09-03 | [24 empty] | 2022-06-09
4312709 | Acton | 1720 | 15.2 | PV | TBD | 2020-08-27 | 2020-09-03 |  |  |  | 2020-10-01 | [24 empty] | 2020-10-15 | [13 empty] | Withdrawn
4659513 | Acton | 1720 | 4980 | PV & Battery | TBD | 2020-11-25 | 2020-12-15 |  |  |  | 2021-01-05
4685975 | Acton | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-22 |  |  |  | 2021-01-25 | [24 empty] | 2022-06-01
4698222 | Acton | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-29 |  |  |  | 2021-01-13 | [24 empty] | 2022-06-01
4668063 | Acton | 1720 | 25.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-05 | [37 empty] | 2021-03-16 | Online
4972089 | Acton | 1720 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-01-27 |  |  |  | 2021-02-17 | [24 empty] | 2021-03-09
4878009 | Acton | 1720 | 20 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-19 | [12 empty] | 2021-08-23 | Online
5087787 | Acton | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5087888 | Acton | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5087946 | Acton | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5088024 | Acton | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5088121 | Acton | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5088220 | Acton | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5088314 | Acton | 1720 | 500 | PV | TBD | 2020-12-17
5088274 | Acton | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5097801 | Acton | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5097909 | Acton | 1720 | 1000 | PV & Battery | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
5103412 | Acton | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 |  |  |  | 2021-03-08
4665887 | Acton | 1720 | 17.6 | PV & Battery | TBD | 2020-12-22 | 2020-12-22 |  |  |  | 2021-01-05 | [24 empty] | 2021-02-09 | [12 empty] | 2022-03-28 | Online
4708871 | Acton | 1720 | 2495 | Battery | TBD | 2020-12-29 | 2020-12-29 |  |  |  | 2021-01-19
5141509 | Acton | 1720 | 1125 | PV & Battery | TBD | 2020-12-31 | 2021-02-05 |  |  |  | 2021-03-08
5149891 | Acton | 1720 | 84 | PV | TBD | 2021-02-10 | 2021-02-19 |  |  |  | 2021-03-08 | [24 empty] | 2021-03-25 | [12 empty] | 2021-08-05 | Online
5273453 | Acton | 1720 | 30.2 | PV & Battery | TBD | 2021-03-08 | 2021-03-08 |  |  |  | 2021-03-23
ESMAEX-00032 | Acton | 1720 | 4999 | PV & Battery | 416-H8 | 2021-04-07 | 2021-04-20 | [42 empty] | In Queue |  |  | Y
ESMAEX-00038 | Acton | 1720 | 687.5 | PV | TBD | 2021-06-22 | 2021-07-13 | [28 empty] | 2022-07-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00071 | Acton | 1720 | 16.23 | PV | 416-H9 | 2021-04-23 | 2021-05-11 | [28 empty] | 2021-06-16 | [12 empty] | 2021-12-17 | Online |  |  | Y
ESMAEX-00320 | Acton | 1720 | 66.6 | PV | 416-H9 | 2021-08-17 | 2021-09-02 | [28 empty] | 2021-11-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-00328 | Acton | 1720 | 20 | PV | 416-H8 | 2021-08-18 | 2021-09-22 | [28 empty] | 2021-12-01 | [12 empty] | 2022-06-17 | Online |  |  | Y
ESMAEX-00360 | Acton | 1720 | 17.6 | PV & Battery | 416-H4 | 2021-08-26 | 2021-09-14 | [28 empty] | 2021-12-21 | [12 empty] | 2022-03-16 | Online |  |  | Y
ESMAEX-00365 | Acton | 1720 | 110.8 | PV | 416-H8 | 2021-08-27 | 2021-09-15 | [28 empty] | 2021-12-09 | [12 empty] | 2022-06-15 | Online |  |  | Y
ESMAEX-00373 | Acton | 1720 | 21.4 | PV & Battery | 416-H9 | 2021-08-31 | 2021-09-16 | [28 empty] | 2022-03-16 | [12 empty] | 2022-06-08 | Online |  |  | Y
ESMAEX-00388 | Acton | 1720 | 9.6 | PV & Battery | 416-H2 | 2021-09-07 | 2021-09-21 | [28 empty] | 2022-03-16 | [12 empty] | 2022-08-10 | Online |  |  | Y
ESMAEX-00416 | Acton | 1720 | 19.79 | Battery | 416-H4 | 2021-09-16 | 2021-10-04 | [28 empty] | 2022-06-02 | [12 empty] | 2022-08-08 | Online |  |  | Y
ESMAEX-00962 | Acton | 1720 | 15.2 | PV & Battery | 416-H1 | 2022-03-24 | 2022-04-14 | [28 empty] | 2022-05-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-01055 | Acton | 1720 | 12.6 | PV & Battery | 416-H9 | 2022-04-08 | 2022-04-28 | [28 empty] | 2022-06-08 | [12 empty] | 2023-02-28 | Online |  |  | Y
ESMAEX-01112 | Acton | 1720 | 17 | PV & Battery | 416-H8 | 2022-04-25 | 2022-05-26 | [28 empty] | 2022-06-18 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01260 | Acton | 1720 | 17.6 | PV & Battery | 416-H4 | 2022-06-07 | 2022-06-24 | [28 empty] | 2022-09-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01467 | Acton | 1720 | 250 | PV | 416-H9 | 2022-09-09 | 2022-09-27 | [28 empty] | 2022-11-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01534 | Acton | 1720 | 90 | PV | 416-H4 | 2022-11-21 | 2023-01-30 | [42 empty] | In Queue |  |  | Y
ESMAEX-01611 | Acton | 1720 | 15.3 | PV | 416-H5 | 2022-09-21 | 2022-12-29 | [28 empty] | 2023-03-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-01648 | Acton | 1720 | 15.2 | PV & Battery | 416-H5 | 2022-09-30 | 2022-10-19 | [28 empty] | 2022-10-21 | [12 empty] | 2023-04-03 | Online |  |  | Y
ESMAEX-01714 | Acton | 1720 | 15.2 | PV & Battery | 416-H5 | 2022-10-25 | 2022-11-16 | [28 empty] | 2023-01-12 | [12 empty] | 2023-04-26 | Online |  |  | Y
ESMAEX-01716 | Acton | 1720 | 15.2 | PV & Battery | 512-1399H1 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-11-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01902 | Acton | 1720 | 16.5 | PV | 416-H1 | 2022-12-07 | 2022-12-29 | [28 empty] | 2023-02-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01946 | Acton | 1720 | 200 | PV | 416-H2 | 2022-12-23 | 2023-02-14 | [28 empty] | 2023-03-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-01948 | Acton | 1720 | 10 | Battery | 416-H5 | 2022-12-27 | 2023-01-23 | [28 empty] | 2023-02-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01956 | Acton | 1720 | 16.104 | PV | 416-H8 | 2023-01-03 | 2023-01-23 | [28 empty] | 2023-02-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-02070 | Acton | 1720 | 15.2 | PV & Battery | 416-H8 | 2023-01-25 | 2023-02-14 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02092 | Acton | 1720 | 15.2 | PV & Battery | 416-H8 | 2023-01-31 | 2023-02-10 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02173 | Acton | 1720 | 960 | PV | 416-H9 | 2023-03-31 | 2023-04-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-02180 | Acton | 1720 | 199.9 | Battery | 416-H8 | 2023-02-21 | 2023-03-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-02187 | Acton | 1720 | 160 | PV & Battery | TBD | 2023-02-22 | 2023-03-30 | [42 empty] | In Queue |  |  | Y
ESMAEX-02216 | Acton | 1720 | 18.6 | Battery | 416-H8 | 2023-03-01 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02268 | Acton | 1720 | 15.2 | PV | 416-H8 | 2023-03-14 | 2023-04-03 | [28 empty] | 2023-04-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-02364 | Acton | 1720 | 16.8 | PV | 416-H5 | 2023-04-10 | [43 empty] | In Queue |  |  | Y
4886788 | North Acton | 1720 | 57.6 | PV | TBD | 2021-01-12 | 2021-01-12 |  |  |  | 2021-01-28 | [24 empty] | 2021-03-25 | [12 empty] | 2022-02-28 | Online
2133577 | Ashland | 1721 | 756.4 | PV | 274-H5 | 2016-02-07 | 2016-02-22 | 11 |  | 11 | 2016-03-10 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-16 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
2338277 | Ashland | 1721 | 19 | PV | 519-175H1 | 2019-04-17 | 2019-04-18 | 1 |  | 1 | 2019-05-08 |  | -31129 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
2402255 | Ashland | 1721 | 10 | PV & Battery | TBD | 2020-05-26 | 2020-06-01 |  |  |  | 2020-06-16 | [24 empty] | 2020-07-15 | [12 empty] | 2020-10-15 | Online
2348725 | Ashland | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 |  |  |  | 2019-07-10 | [24 empty] | 2019-07-12 | [12 empty] | 2021-04-16 | Online
2349389 | Ashland | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 |  |  |  | 2019-07-11 | [24 empty] | 2019-07-17 | [12 empty] | 2021-04-16 | Online
2348729 | Ashland | 1721 | 144 | PV | TBD | 2019-06-17 | 2019-06-24 |  |  |  | 2019-07-10 | [24 empty] | 2019-07-17 | [12 empty] | 2021-05-04 | Online
2295850 | Ashland | 1721 | 22.95 | PV | 455-H3 | 2018-08-23 | 2018-08-23 | 0 |  | 0 | 2018-09-12 | 2018-11-05 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2162591 | Ashland | 1721 | 148.9 | PV | 274-H1 | 2016-07-18 | 2016-07-25 | 5 |  | 5 | 2016-08-09 |  | -30423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0
2220527 | Ashland | 1721 | 4450 | PV | 274-1429H1 | 2017-05-16 | 2017-05-22 | 4 |  | 4 | 2017-06-15 |  | -30640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-29 | 2017-09-21 | -8 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2234823 | Ashland | 1721 | 1080 | PV | 274-1429H1 | 2017-08-02 | 2017-08-15 | 9 |  | 9 | 2017-09-14 |  | -30703 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2236318 | Ashland | 1721 | 92 | PV | 274-1429H1 | 2017-08-31 | 2017-09-01 | 1 |  | 1 | 2017-09-22 |  | -30709 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2372263 | Dedham | 2026 | 15.2 | PV | TBD | 2019-11-06 | 2019-11-18 |  |  |  | 2019-12-06 | [24 empty] | 2020-01-15 | [12 empty] | 2022-05-03 | Online
2397818 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2397824 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2399566 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2282640 | Ashland | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2282847 | Ashland | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2411491 | Hatchville | 02536 | 4000 | PV & Battery | TBD | 2020-08-19 | 2020-08-24 | 3 | 0 | 3 | 2020-09-16 |  | 75 | 0 | 75 | [22 empty] | 2020-12-01 | TBD |  | 30 | [8 empty] | In Queue |  | Private
5174138 | Ashland | 1721 | 199.8 | PV | TBD | 2021-02-23 | [29 empty] | 2021-10-06 | [12 empty] | 2022-06-27 | Online
2322158 | Ashland | 1721 | 346.2 | PV | 455-H3 | 2018-12-19 | 2019-01-16 | 20 |  | 20 | 2019-01-25 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
2323862 | Ashland | 1721 | 500 | PV | 455-H3 | 2019-01-07 | 2019-01-11 | 4 |  | 4 | 2019-02-05 |  | -31063 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2333220 | Ashland | 1721 | 250 | PV | 455-H3 | 2019-01-11 | 2019-03-18 | 46 |  | 46 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2333111 | Ashland | 1721 | 250 | PV & Battery | 455-H3 | 2019-03-05 | 2019-03-18 | 9 |  | 9 | 2019-04-04 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2389241 | Ashland | 1721 | 20 | Battery | 519-175H1 | 2020-01-15 | 2020-02-24 |  |  |  | 2020-03-09 | [38 empty] | Withdrawn
2408580 | Ashland | 1721 | 7 | PV & Battery | 519-175H1 | 2020-06-05 | 2020-07-13 |  |  |  | 2020-07-30 | [24 empty] | 2021-03-25 | [12 empty] | 2021-12-07 | Online
4314087 | Ashland | 1721 | 27.6 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 |  |  |  | 2020-10-01 | [24 empty] | 2021-02-04
5113674 | Ashland | 1721 | 22.6 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08 | [24 empty] | 2021-11-08 | [12 empty] | 2022-03-03 | Online
5122724 | Ashland | 1721 | 250 | PV | TBD | 2021-02-08 | 2021-02-16 |  |  |  | 2021-03-08
5131937 | Ashland | 1721 | 200 | PV | TBD | 2021-02-17 | 2021-02-17 |  |  |  | 2021-03-08
ESMAEX-00148 | Ashland | 1721 | 75 | PV | 274-H1 | 2021-05-24 | 2021-06-16 | [28 empty] | 2021-08-02 | [12 empty] | 2022-05-31 | Online |  |  | Y
ESMAEX-00155 | Ashland | 1721 | 1000 | PV | 274-H5 | 2021-08-03 | 2021-12-09 | [42 empty] | In Queue |  |  | Y
ESMAEX-00557 | Ashland | 1721 | 250 | PV | 274-H5 | 2021-11-01 | 2021-11-18 | [28 empty] | 2022-09-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-00896 | Ashland | 1721 | 162.5 | PV & Battery | 519-175H1 | 2022-03-10 | 2022-03-30 | [28 empty] | 2022-06-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01167 | Ashland | 1721 | 29.5 | PV & Battery | 274-H5 | 2022-05-11 | 2022-06-02 | [28 empty] | 2022-06-15 | [12 empty] | 2022-11-09 | Online |  |  | Y
ESMAEX-01234 | Ashland | 1721 | 120 | PV & Battery | 274-1429H | 2022-05-27 | 2022-07-21 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01286 | Ashland | 1721 | 15.2 | PV & Battery | 274-H1 | 2022-06-13 | 2022-07-13 | [28 empty] | 2022-08-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01359 | Ashland | 1721 | 240 | PV | 274-1429H1 | 2022-07-11 | 2022-07-26 | [28 empty] | 2022-12-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01362 | Ashland | 1721 | 15.2 | PV & Battery | 274-H6 | 2022-07-11 | 2022-08-01 | [28 empty] | 2022-09-13 | [12 empty] | 2023-02-01 | Online |  |  | Y
ESMAEX-01510 | Ashland | 1721 | 15.6 | PV | 274-H6 | 2022-08-25 | 2022-09-22 | [28 empty] | 2022-10-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-01685 | Ashland | 1721 | 19.92 | PV & Battery | 455-H3 | 2022-10-17 | 2022-11-04 | [28 empty] | 2022-11-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01883 | Ashland | 1721 | 15.2 | PV & Battery | 274-H5 | 2022-12-02 | 2023-01-23 | [28 empty] | 2023-02-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-02081 | Ashland | 1721 | 87 | PV | 455-H3 | 2023-01-27 | 2023-02-10 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
2386559 | Ashland | 1721 | 10 | PV & Battery | 274-H1 | 2020-01-23 | 2020-02-04 |  |  |  | 2020-02-20 | [24 empty] | 2020-06-30 | [13 empty] | Withdrawn
2245647 | Ashland | 1721 | 773.6 | PV | 274-H1 | 2017-11-02 | 2017-11-02 | 0 |  | 0 | 2017-11-16 |  | -30747 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5077946 | Ashland | 1722 | 466.6 | PV | TBD | 2021-02-08 | 2021-02-08 |  |  |  | 2021-03-01
5077981 | Ashland | 1722 | 233.2 | PV | TBD | 2021-02-08 | 2021-02-08 |  |  |  | 2021-03-01
5078034 | Ashland | 1722 | 200 | PV | TBD | 2021-02-08 | 2021-02-08 |  |  |  | 2021-03-01
5078087 | Ashland | 1722 | 100 | PV | TBD | 2021-02-08 | 2021-02-08 |  |  |  | 2021-03-01
2125698 | Bedford | 1730 | 16.7 | PV | 533-H8 | 2016-12-31 | 2017-01-06 | 4 |  | 4 | 2017-01-27 |  | -30544 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-11 | 2016-03-14 | [6 empty] | 0 |  | 0 |  |  | 2016-09-06 | Online |  | PRIVATE
2151037 | Bedford | 1730 | 288 | PV | 391-H8 | 2016-05-23 | 2016-05-31 | 6 |  | 6 | 2016-06-07 |  | -30378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-12 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online |  | Private
2286613 | Bedford | 1730 | 52.2 | PV | 533-H7 | 2018-06-21 | 2018-06-27 | 4 |  | 4 | 2018-07-13 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-10 | [7 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
2376385 | Bedford | 1730 | 25 | PV & Battery | 533-H8 | 2019-12-11 | 2019-12-19 |  |  |  | 2019-12-31 | [24 empty] | 2020-01-30 | [12 empty] | 2020-06-19 | Online
2411131 | Bedford | 1730 | 25 | PV & Battery | TBD | 2020-07-22 | 2020-08-03 |  |  |  | 2020-08-18 | [24 empty] | 2020-10-01 | [12 empty] | 2020-12-24 | Online
2406661 | Bedford | 1730 | 21 | PV & Battery | 322-1397H1 | 2020-06-23 | 2020-06-29 |  |  |  | 2020-07-20 | [24 empty] | 2020-10-01 | [12 empty] | 2020-12-30 | Online
2408542 | Bedford | 1730 | 25 | PV & Battery | 533-H5 | 2020-07-22 | 2020-07-22 |  |  |  | 2020-08-07 | [24 empty] | 2020-10-01 | [12 empty] | 2020-12-30 | Online
4606031 | Bedford | 1730 | 20 | PV & Battery | TBD | 2020-11-18 | 2020-11-24 |  |  |  | 2020-12-15 | [37 empty] | 2021-02-10 | Online
2180244 | Bedford | 1730 | 5198 | CHP | 319-1377 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2255723 | Bedford | 1730 | 138 | PV | 533-H7 | 2017-12-01 | 2017-12-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2298289 | Bedford | 1730 | 72 | PV | 533-H5 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0
2334399 | Bedford | 1730 | 200 | PV | 322-05 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2391763 | Bedford | 1730 | 15.2 | PV | TBD | 2020-01-15 | 2020-03-16 |  |  |  | 2020-03-30 | [24 empty] | 2020-11-17 | [13 empty] | Withdrawn
2403475 | Bedford | 1730 | 31 | PV & Battery | TBD | 2020-06-01 | 2020-06-08 |  |  |  | 2020-06-23 | [24 empty] | 2020-08-05 | [12 empty] | 2021-09-20 | Online
4352135 | Bedford | 1730 | 100.8 | PV | TBD | 2020-09-10 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2020-11-17 | [12 empty] | 2022-04-12 | Online
4896010 | Bedford | 1730 | 15.2 | PV | TBD | 2021-01-12 | 2021-01-14 |  |  |  | 2021-02-05 | [24 empty] | 2021-02-19 | [12 empty] | 2021-11-19 | Online
2139203 | Bedford | 1730 | 21.9 | PV | 322-05 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00211 | Bedford | 1730 | 17.6 | PV | 322-1397H1 | 2021-06-24 | 2021-07-13 | [28 empty] | 2021-07-22 | [12 empty] | 2021-10-05 | Online |  |  | Y
ESMAEX-00465 | Bedford | 1730 | 12.6 | PV & Battery | 533-H8 | 2021-10-03 | 2021-11-16 | [28 empty] | 2022-02-07 | [12 empty] | 2022-04-13 | Online |  |  | Y
ESMAEX-00622 | Bedford | 1730 | 17.4 | PV | 533-H8 | 2021-11-24 | 2021-12-15 | [28 empty] | 2022-01-18 | [12 empty] | 2022-04-05 | Online |  |  | Y
ESMAEX-00877 | Bedford | 1730 | 16.104 | PV | 533-H5 | 2022-03-04 | 2022-03-22 | [28 empty] | 2022-04-20 | [12 empty] | 2022-06-30 | Online |  |  | Y
ESMAEX-01215 | Bedford | 1730 | 15.2 | PV & Battery | 533-H8 | 2022-05-24 | 2022-06-17 | [28 empty] | 2022-06-30 | [12 empty] | 2023-01-17 | Online |  |  | Y
ESMAEX-01278 | Bedford | 1730 | 7.08 | PV & Battery | TBD | 2022-06-10 | 2022-07-01 | [28 empty] | 2022-09-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01393 | Bedford | 1730 | 15.2 | PV & Battery | 533-H8 | 2022-07-20 | 2022-09-29 | [28 empty] | 2022-11-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01548 | Bedford | 1730 | 15.744 | PV & Battery | 533-H7 | 2022-09-07 | 2022-10-27 | [28 empty] | 2023-01-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01779 | Bedford | 1730 | 15.2 | PV & Battery | 533-H7 | 2022-11-08 | 2022-12-05 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02061 | Bedford | 1730 | 15.2 | PV & Battery | 533-H8 | 2023-01-23 | 2023-02-14 | [28 empty] | 2023-03-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-02097 | Bedford | 1730 | 24.96 | Battery | 533-H7 | 2023-02-01 | 2023-02-14 | [42 empty] | In Queue |  |  | Y
ESMAEX-02307 | Bedford | 1730 | 240 | PV | 320-H2 | 2023-03-24 | 2023-04-06 | [42 empty] | In Queue |  |  | Y
2181646 | Bedford | 1731 | 430 | PV | 319-1378 | 2016-10-11 | 2016-10-18 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-22 | Online
2168512 | Bedford | 1731 | 2805 | PV | 320-H6 | 2016-09-01 | 2016-09-07 | 4 |  | 4 | 2016-09-12 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2290881 | Bedford | 1731 | 1645 | PV & Battery | 320-H6 | 2018-07-19 | 2018-07-24 | 3 |  | 3 | 2018-08-08 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0
2143902 | Carlisle | 1741 | 17.4 | PV | 512-1399h1 | 2016-04-10 | 2016-04-11 | 1 |  | 1 | 2016-05-02 |  | -30352 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-27 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online
2342972 | Carlisle | 1741 | 18.7 | PV | 512-1399h1 | 2019-05-16 | 2019-05-24 |  |  |  | 2019-06-04 | [24 empty] | 2019-08-12 | [12 empty] | 2020-03-03 | Online
2394000 | Carlisle | 1741 | 19.5 | PV | TBD | 2020-01-17 | 2020-03-31 |  |  |  | 2020-04-16 | [24 empty] | 2020-04-21 | [12 empty] | 2020-08-31 | Online
2383471 | Carlisle | 1741 | 17.6 | PV & Battery | 512-1399H1 | 2019-12-13 | 2020-01-13 |  |  |  | 2020-01-31 | [24 empty] | 2020-05-28 | [12 empty] | 2021-03-09 | Online
2336465 | Carlisle | 1741 | 496 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-26 |  | -31121 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2337102 | Carlisle | 1741 | 484 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-30 |  | -31123 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-26 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
2376068 | Carlisle | 1741 | 17.6 | PV | 512-1399H1 | 2019-10-22 | 2019-12-11 |  |  |  | 2019-12-26 | [24 empty] | 2020-01-21
2413532 | Carlisle | 1741 | 17.6 | PV & Battery | TBD | 2020-08-12 | 2020-08-18 |  |  |  | 2020-09-09 | [24 empty] | 2021-01-29 | [12 empty] | 2021-06-01 | Online
4318460 | Carlisle | 1741 | 30.2 | PV & Battery | TBD | 2020-09-01 | 2020-09-10 |  |  |  | 2020-10-01 | [24 empty] | 2020-12-24 | [12 empty] | 2021-06-15 | Online
5017153 | Carlisle | 1741 | 35.2 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 |  |  |  | 2021-03-01 | [24 empty] | 2021-04-19
ESMAEX-00234 | Carlisle | 1741 | 15 | Battery | 512-1399H1 | 2021-07-12 | 2021-07-27 | [28 empty] | 2021-08-24 | [12 empty] | 2021-10-06 | Online |  |  | Y
ESMAEX-00267 | Carlisle | 1741 | 18.18 | PV | 512-1399H1 | 2021-07-27 | 2021-08-12 | [28 empty] | 2021-08-19 | [12 empty] | 2022-03-08 | Online |  |  | Y
ESMAEX-00310 | Carlisle | 1741 | 15.2 | PV & Battery | 512-1399H1 | 2021-08-13 | 2021-08-31 | [28 empty] | 2021-10-19 | [12 empty] | 2022-11-29 | Online |  |  | Y
ESMAEX-00596 | Carlisle | 1741 | 14 | Battery | 512-1399H1 | 2021-11-17 | 2021-12-07 | [28 empty] | 2022-02-14 | [12 empty] | 2022-06-02 | Online |  |  | Y
ESMAEX-00767 | Carlisle | 1741 | 15.95 | PV | 512-1399H1 | 2022-01-31 | 2022-02-22 | [28 empty] | 2022-03-16 | [12 empty] | 2022-07-18 | Online |  |  | Y
ESMAEX-00987 | Carlisle | 1741 | 15.2 | PV & Battery | 533-H8 | 2022-03-29 | 2022-05-02 | [28 empty] | 2022-06-01 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01086 | Carlisle | 1741 | 17.9 | PV | 512-1399H1 | 2022-04-16 | 2022-05-03 | [28 empty] | 2022-06-01 | [12 empty] | 2022-07-20 | Online |  |  | Y
ESMAEX-01172 | Carlisle | 1741 | 16.24 | PV & Battery | 533-H8 | 2022-05-11 | 2022-06-03 | [28 empty] | 2022-07-07 | [12 empty] | 2022-11-18 | Online |  |  | Y
ESMAEX-01198 | Carlisle | 1741 | 15.2 | PV | 533-H8 | 2022-05-19 | 2022-06-17 | [28 empty] | 2022-07-18 | [12 empty] | 2023-01-30 | Online |  |  | Y
ESMAEX-01237 | Carlisle | 1741 | 7.2 | Battery | 533-H8 | 2022-06-01 | 2022-06-21 | [28 empty] | 2022-07-08 | [12 empty] | 2022-11-15 | Online |  |  | Y
ESMAEX-01275 | Carlisle | 1741 | 21.4 | PV | 512-1399H1 | 2022-06-09 | 2022-06-24 | [28 empty] | 2022-07-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01437 | Carlisle | 1741 | 20.2 | PV & Battery | 512-1399H1 | 2022-08-04 | 2022-08-25 | [28 empty] | 2022-10-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01706 | Carlisle | 1741 | 10 | Battery | 512-1399H1 | 2022-10-21 | 2022-11-10 | [28 empty] | 2022-12-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01773 | Carlisle | 1741 | 15.2 | PV & Battery | 533-H8 | 2022-11-07 | 2022-12-05 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01906 | Carlisle | 1741 | 17.6 | PV & Battery | 533-H8 | 2022-12-08 | 2023-01-04 | [28 empty] | 2023-01-17 | [12 empty] | 2023-04-07 | Online |  |  | Y
ESMAEX-02226 | Carlisle | 1741 | 15.2 | PV & Battery | 533-H8 | 2023-03-02 | 2023-03-23 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-02340 | Carlisle | 1741 | 20 | PV | 512-1399H1 | 2023-04-04 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
ESMAEX-02397 | Carlisle | 1741 | 17.4 | PV | 512-1399H1 | 2023-04-20 | [43 empty] | In Queue |  |  | Y
ESMAEX-02169 | Millis | 1742 | 650 | Battery | 146-H10 | 2023-02-16 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
2181649 | Holliston | 1746 | 32.5 | PV | 130-H1 | 2016-10-06 | 2016-10-19 | 9 |  | 9 | 2016-11-16 |  | -30494 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-03-13 | Online |  | PRIVATE
2198478 | Holliston | 1746 | 110 | Battery | 274-H3 | 2016-12-01 | 2017-01-12 | 29 |  | 29 | 2017-01-27 |  | -30544 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | N/A | N
2176549 | Holliston | 1746 | 36 | PV | 274-H3 | 2016-09-09 | 2016-09-23 | 10 |  | 10 | 2016-10-21 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online |  | PRIVATE
2191568 | Holliston | 1746 | 47.7 | PV | 65-H2 | 2016-12-02 | 2016-12-05 | 1 |  | 1 | 2016-12-30 |  | -30526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | 2017-02-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online |  | PRIVATE
2181140 | Holliston | 1746 | 42 | PV | 274-H3 | 2016-10-13 | 2016-10-21 | 6 | 7 | -1 | 2016-11-14 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | [7 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online |  | PRIVATE
2229434 | Holliston | 1746 | 44 | PV | 130-H1 | 2017-07-18 | 2017-07-21 | 3 |  | 3 | 2017-08-09 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-23 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
2229612 | Holliston | 1746 | 15.2 | PV | 130-H1 | 2017-06-16 | 2017-07-19 | 22 |  | 22 | 2017-08-10 |  | -30679 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-01 | Online
2298783 | Holliston | 1746 | 31 | PV | 130-H1 | 2018-08-30 | 2018-09-07 | 6 |  | 6 | 2018-09-28 | 2018-12-06 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-03-06 | Online
2288918 | Holliston | 1746 | 66.6 | PV | 65-H9 | 2018-07-13 | 2018-07-16 | 1 |  | 1 | 2018-07-30 |  | -30927 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-06 | [6 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online
2272656 | Holliston | 1746 | 7.6 | PV | 274-H3 | 2018-04-04 | 2018-04-09 | 3 |  | 3 | 2018-04-20 |  | -30856 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
2289154 | Holliston | 1746 | 17.28 | PV | 274-H3 | 2018-04-10 | 2018-07-17 | 70 |  | 70 | 2018-08-02 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-05-11 | Online
2319567 | Holliston | 1746 | 1640 | PV | 274-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
2364172 | Holliston | 1746 | 240 | PV | TBD | 2019-09-09 | 2019-09-26 |  |  |  | 2019-10-16 | [24 empty] | 2019-11-14 | [12 empty] | 2020-12-31 | Online
2401948 | Holliston | 1746 | 216 | PV | TBD | 2020-05-15 | 2020-05-26 |  |  |  | 2020-06-10 | [24 empty] | 2021-04-01 | [12 empty] | 2021-04-01 | Online
2404607 | Holliston | 1746 | 21 | PV & Battery | 274-H5 | 2020-06-10 | 2020-06-23 |  |  |  | 2020-07-20 | [24 empty] | 2020-10-08 | [12 empty] | 2021-05-07 | Online
2306412 | Holliston | 1746 | 490 | PV | 274-H3 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2351364 | Holliston | 1746 | 4999 | PV & Battery | TBD | 2019-07-05 | 2019-07-10 |  |  |  | 2019-07-23 | [24 empty] | 2020-08-14
2370560 | Holliston | 1746 | 499 | PV | TBD | 2019-11-04 | 2019-11-12 |  |  |  | 2019-11-27 | [24 empty] | 2020-05-27
2370417 | Holliston | 1746 | 437.5 | PV | TBD | 2019-11-08 | 2019-11-12 |  |  |  | 2019-11-26 | [24 empty] | 2021-01-28
2387342 | Holliston | 1746 | 4999 | PV & Battery | TBD | 2019-12-26 | 2020-02-06 |  |  |  | 2020-02-25 | [37 empty] | 2022-12-05 | Online
2396686 | Holliston | 1746 | 14 | Battery | 274-H5 | 2020-02-18 | 2020-04-20 |  |  |  | 2020-05-06 | [38 empty] | Withdrawn
2391752 | Holliston | 1746 | 200 | PV | TBD | 2020-02-27 | 2020-03-16 |  |  |  | 2020-03-30
2399007 | Holliston | 1746 | 300 | PV | TBD | 2020-04-20 | 2020-05-13 |  |  |  | 2020-05-27 | [24 empty] | 2020-06-09 | [13 empty] | Withdrawn
2409582 | Holliston | 1746 | 250 | PV | TBD | 2020-07-08 | 2020-07-14 |  |  |  | 2020-08-04 | [38 empty] | Withdrawn
4713490 | Holliston | 1746 | 20 | PV & Battery | TBD | 2020-07-29 | 2020-08-10 |  |  |  | 2020-08-31 | [37 empty] | 2022-01-05 | Online
4664449 | Holliston | 1746 | 10 | Battery | TBD | 2020-11-16 | 2020-12-14 |  |  |  | 2021-01-25 | [24 empty] | 2021-03-23
5025553 | Holliston | 1746 | 120 | PV | TBD | 2020-12-31 | 2021-02-05 |  |  |  | 2021-03-01 | [24 empty] | 2021-06-04 | [12 empty] | 2022-08-04 | Online
5122828 | Holliston | 1746 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08
5132026 | Holliston | 1746 | 466.6 | PV | TBD | 2021-02-17 | 2021-02-17 |  |  |  | 2021-03-08 | [37 empty] | 2022-08-03 | Online
5131879 | Holliston | 1746 | 150 | PV | TBD | 2021-02-17 | 2021-02-17 |  |  |  | 2021-03-08
5140889 | Holliston | 1746 | 150 | PV | TBD | 2021-02-18 | 2021-02-18 |  |  |  | 2021-03-08
5140517 | Holliston | 1746 | 133.2 | PV | TBD | 2021-02-18
5140433 | Holliston | 1746 | 100 | PV | TBD | 2021-02-18 | 2021-02-18
ESMAEX-00058 | Holliston | 1746 | 133.2 | PV | 65-H2 | 2021-04-16 | 2021-05-04 | [28 empty] | 2021-08-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-00101 | Holliston | 1746 | 140 | PV | 65-H2 | 2021-05-05 | 2021-05-20 | [28 empty] | 2021-10-18 | [12 empty] | 2022-04-18 | Online |  |  | Y
ESMAEX-00378 | Holliston | 1746 | 19 | PV | 130-H1 | 2021-09-01 | 2021-09-16 | [28 empty] | 2021-11-30 | [12 empty] | 2022-02-01 | Online |  |  | Y
ESMAEX-00605 | Holliston | 1746 | 80 | PV | 274-H3 | 2021-11-18 | 2021-12-09 | [28 empty] | 2022-02-10 | [12 empty] | 2022-11-09 | Online |  |  | Y
ESMAEX-00936 | Holliston | 1746 | 4.93 | PV | 274-H3 | 2022-03-17 | 2022-04-07 | [28 empty] | 2022-06-07 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01022 | Holliston | 1746 | 15.2 | PV & Battery | 65-H5 | 2022-04-06 | 2022-04-28 | [28 empty] | 2022-05-23 | [12 empty] | 2023-02-22 | Online |  |  | Y
ESMAEX-01080 | Holliston | 1746 | 15.18 | PV & Battery | 65-H5 | 2022-04-14 | 2022-05-02 | [28 empty] | 2022-06-07 | [12 empty] | 2023-02-10 | Online |  |  | Y
ESMAEX-01124 | Holliston | 1746 | 19.99 | PV & Battery | 65-H2 | 2022-04-28 | 2022-05-18 | [28 empty] | 2022-07-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01204 | Holliston | 1746 | 15.2 | PV & Battery | 274-H3 | 2022-05-20 | 2022-06-17 | [28 empty] | 2022-07-13 | [12 empty] | 2023-03-20 | Online |  |  | Y
ESMAEX-01856 | Holliston | 1746 | 15.2 | PV & Battery | 274-H3 | 2022-11-29 | 2022-12-19 | [28 empty] | 2022-12-21 | [12 empty] | 2023-03-20 | Online |  |  | Y
ESMAEX-01868 | Holliston | 1746 | 15.2 | PV | 130-H1 | 2022-11-29 | 2022-12-19 | [28 empty] | 2023-02-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01967 | Holliston | 1746 | 15.2 | PV | 274-H1 | 2023-01-05 | 2023-01-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-02203 | Holliston | 1746 | 120 | Battery | 65-H2 | 2023-02-24 | 2023-03-21 | [28 empty] | 2023-03-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-02253 | Holliston | 1746 | 8.26 | Battery | 65-H5 | 2023-03-09 | 2023-04-03 | [28 empty] | 2023-04-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-02318 | Holliston | 1746 | 7.4 | Battery | 65-H5 | 2023-03-28 | 2023-04-13 | [28 empty] | 2023-05-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02333 | Holliston | 1746 | 20 | PV | 130-H1 | 2023-04-03 | 2023-04-17 | [42 empty] | In Queue |  |  | Y
4615055 | Holliston | 1746 | 19.8 | PV & Battery | TBD | 2020-11-18 | 2020-11-19 |  |  |  | 2020-12-21 | [24 empty] | 2021-01-26 | [12 empty] | 2021-04-01 | Online
2391467 | Holliston | 1746 | 20 | PV & Battery | TBD | 2020-03-09 | 2020-03-12 |  |  |  | 2020-03-27 | [24 empty] | 2020-06-04 | [13 empty] | Withdrawn
2408400 | Holliston | 1746 | 499 | PV | TBD | 2020-07-21 | 2020-07-21 |  |  |  | 2020-08-04
2413383 | Holliston | 1746 | 5000 | PV & Battery | TBD | 2020-08-06 |  |  |  |  | 2020-09-03
2170421 | Hopkinton | 1748 | 22.7 | PV | 126-H1 | 2016-08-29 | 2016-08-31 | 2 |  | 2 | 2016-09-20 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-01-05 | Online |  | PRIVATE
2191381 | Hopkinton | 1748 | 28.8 | PV | 65-H6 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-29 |  | -30525 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-06-21 | Online |  | PRIVATE
2255236 | Hopkinton | 1748 | 18 | PV | 126-H1 | 2017-11-30 | 2017-12-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-03 | Online
2235082 | Hopkinton | 1748 | 59 | PV | 126-H2 | 2017-08-01 | 2017-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-23 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-04-11 | Online
2249982 | Hopkinton | 1748 | 84 | PV | 126-H4 | 2017-10-19 | 2017-10-19 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-08 | Online
2189509 | Hopkinton | 1748 | 2120 | PV | 126-H2 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-04-18 | Online
2326836 | Hopkinton | 1748 | 206 | PV | 126-H2 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-25 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
2272446 | Hopkinton | 1748 | 19 | PV | 130-H1 | 2018-03-01 | 2018-04-03 | 23 |  | 23 | 2018-04-19 |  | -30855 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-05 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
2286965 | Hopkinton | 1748 | 100 | PV | 3-86-966 | 2018-05-23 | 2018-06-27 | 25 |  | 25 | 2018-07-11 | 2018-12-10 | 108 |  | 108 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-10-16 | Online |  | Private
2398274 | Hopkinton | 1748 | 24.28 | PV | TBD | 2020-04-09 | 2020-04-29 |  |  |  | 2020-05-18 | [24 empty] | 2020-11-05 | [12 empty] | 2021-02-12 | Online
2384545 | Hopkinton | 1748 | 111.5 | PV & Battery | 126-H2 | 2019-12-10 | 2020-01-02 |  |  |  | 2020-02-07 | [24 empty] | 2020-02-12 | [12 empty] | 2021-03-31 | Online
4607939 | Hopkinton | 1748 | 19.72 | PV | TBD | 2020-11-24 | 2020-12-01 |  |  |  | 2020-12-17 | [24 empty] | 2021-02-09 | [12 empty] | 2021-05-19 | Online
2203698 | Hopkinton | 1748 | 1980 | PV | 126-H4 | 2015-08-14 | 2015-08-14 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-03-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2188716 | Hopkinton | 1748 | 990 | PV | 126-H1 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-04 | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2187300 | Hopkinton | 1748 | 2820 | PV | 455=H3 | 2016-11-18 | 2016-11-18 | 0 |  | 0 | 2016-12-07 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2218766 | Hopkinton | 1748 | 16.7 | PV | 65-H6 | 2017-05-15 | 2017-05-22 | 5 |  | 5 | 2017-06-05 |  | -30632 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2230376 | Hopkinton | 1748 | 3960 | PV | 126-H2 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-16 |  | -30683 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2238660 | Hopkinton | 1748 | 7520 | PV | 126-H2 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-05 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2242067 | Hopkinton | 1748 | 299.7 | PV | 126-H1 | 2017-09-29 | 2017-10-10 | 6 |  | 6 | 2017-11-02 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2260503 | Hopkinton | 1748 | 4000 | PV | 126-H4 | 2017-12-19 | 2018-01-09 | 14 |  | 14 | 2018-01-29 |  | -30797 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-03 |  | -30931 |  | 0 |  |  | 0 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2272822 | Hopkinton | 1748 | 86.25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-23 |  | -30857 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
2273069 | Hopkinton | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30858 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2273079 | Hopkinton | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30858 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
2273089 | Hopkinton | 1748 | 25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30858 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
2273879 | Hopkinton | 1748 | 74 | PV | 65-H6 | 2018-03-30 | 2018-04-11 | 8 |  | 8 | 2018-05-01 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
2308334 | Hopkinton | 1748 | 2000 | PV & Battery | 126-H4 | 2018-11-14 | 2018-11-29 | 11 |  | 11 | 2018-11-29 |  | -31015 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2316355 | Hopkinton | 1748 | 6310 | PV & Battery | 533-H7 | 2018-12-20 | 2018-12-20 | 0 |  | 0 | 2019-01-03 |  | -31040 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0
2343104 | Hopkinton | 1748 | 8485 | PV & Battery | 533-H7 | 2019-05-16 | 2019-05-24 |  |  |  | 2019-06-05 | [24 empty] | 2020-10-16
2346774 | Hopkinton | 1748 | 480 | PV | TBD | 2019-05-23 | 2019-06-13 |  |  |  | 2019-06-26 | [24 empty] | 2019-10-10
2357587 | Hopkinton | 1748 | 2770 | PV & Battery | 126-H2 | 2019-08-15 | 2020-08-16 |  |  |  | 2020-09-06 | [24 empty] | 2020-03-24
2361481 | Hopkinton | 1748 | 333.3 | PV | TBD | 2019-09-03 | 2019-09-12 |  |  |  | 2019-10-01 | [24 empty] | 2019-12-02 | [13 empty] | Withdrawn
2373744 | Hopkinton | 1748 | 15.2 | PV | 126-H1 | 2019-11-18 | 2019-11-21 |  |  |  | 2019-12-10 | [24 empty] | 2020-03-02 | [13 empty] | Withdrawn
2397168 | Hopkinton | 1748 | 3900 | PV & Battery | TBD | 2020-02-10 | 2020-04-23 |  |  |  | 2020-05-08
2404430 | Hopkinton | 1748 | 15.2 | PV | 126-H1 | 2020-06-02 | 2020-06-29 |  |  |  | 2020-07-01 | [24 empty] | 2020-07-21 | [12 empty] | 2021-05-27 | Online
2406412 | Hopkinton | 1748 | 250 | PV | TBD | 2020-07-01 | 2020-07-01 |  |  |  | 2020-07-15 | [24 empty] | 2020-08-28 | [13 empty] | Withdrawn
2409830 | Hopkinton | 1748 | 5000 | PV & Battery | TBD | 2020-07-15 | 2020-07-15 |  |  |  | 2020-08-07
4680531 | Hopkinton | 1748 | 35.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-11 | [38 empty] | Withdrawn
4683322 | Hopkinton | 1748 | 20 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-11 | [37 empty] | 2021-06-24 | Online
5123449 | Hopkinton | 1748 | 100 | PV | TBD | 2021-01-19 | 2021-01-20 |  |  |  | 2021-03-12 | [24 empty] | 2021-03-25 | [12 empty] | 2021-11-19 | Online
5112763 | Hopkinton | 1748 | 166.6 | PV | TBD | 2021-02-10 | 2021-02-10 |  |  |  | 2021-03-08 | [24 empty] | 2021-03-17 | [12 empty] | 2022-06-27 | Online
5354874 | Hopkinton | 1748 | 240 | PV | TBD | 2021-03-17 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-09-14
5354925 | Hopkinton | 1748 | 233.2 | PV | TBD | 2021-03-17 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-09-14 | [12 empty] | 2022-05-20 | Online
5566155 | Hopkinton | 1748 | 1000 | PV | TBD | 2021-03-17 | 2021-04-13 |  |  |  | 2021-04-29
ESMAEX-00145 | Hopkinton | 1748 | 250 | PV | 126-H1 | 2021-05-21 | 2021-05-26 | [28 empty] | 2021-06-17 | [12 empty] | 2022-06-03 | Online |  |  | Y
ESMAEX-00228 | Hopkinton | 1748 | 20 | PV | 65-H7 | 2021-07-06 | 2021-07-22 | [28 empty] | 2021-08-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00317 | Hopkinton | 1748 | 15.2 | PV | 126-H2 | 2021-08-17 | 2021-09-02 | [28 empty] | 2021-09-28 | [12 empty] | 2022-05-23 | Online |  |  | Y
ESMAEX-00321 | Hopkinton | 1748 | 17.6 | PV & Battery | 126-H2 | 2021-08-17 | 2022-06-01 | [28 empty] | 2022-06-27 | [12 empty] | 2022-09-26 | Online |  |  | Y
ESMAEX-00412 | Hopkinton | 1748 | 27.6 | PV & Battery | 126-H4 | 2021-09-14 | 2021-10-26 | [28 empty] | 2022-03-28 | [12 empty] | 2022-10-07 | Online |  |  | Y
ESMAEX-00478 | Hopkinton | 1748 | 19.77 | PV | 126-H1 | 2021-10-06 | 2021-11-18 | [28 empty] | 2022-01-12 | [12 empty] | 2022-03-10 | Online |  |  | Y
ESMAEX-00621 | Hopkinton | 1748 | 20 | PV & Battery | 126-H4 | 2021-11-24 | 2021-12-14 | [28 empty] | 2022-04-14 | [12 empty] | 2022-10-07 | Online |  |  | Y
ESMAEX-00676 | Hopkinton | 1748 | 7.6 | PV & Battery | 126-H3 | 2021-12-20 | 2022-01-20 | [28 empty] | 2022-02-14 | [12 empty] | 2022-04-21 | Online |  |  | Y
ESMAEX-00809 | Hopkinton | 1748 | 24.78 | PV | 126-H4 | 2022-02-04 | 2022-03-18 | [28 empty] | 2022-03-30 | [12 empty] | 2022-08-26 | Online |  |  | Y
ESMAEX-00841 | Hopkinton | 1748 | 15.2 | PV | 126-H4 | 2022-02-17 | 2022-03-10 | [28 empty] | 2022-03-10 | [12 empty] | 2022-06-07 | Online |  |  | Y
ESMAEX-00843 | Hopkinton | 1748 | 15.2 | PV | 126-H4 | 2022-02-21 | 2022-03-08 | [28 empty] | 2022-03-30 | [12 empty] | 2022-08-01 | Online |  |  | Y
ESMAEX-01067 | Hopkinton | 1748 | 250 | PV | 65-H7 | 2022-05-11 | 2022-06-22 | [28 empty] | 2022-08-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01068 | Hopkinton | 1748 | 120 | PV | 126-H2 | 2022-05-11 | 2022-06-01 | [28 empty] | 2022-07-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01154 | Hopkinton | 1748 | 140 | PV | 65-H7 | 2022-05-06 | 2022-06-14 | [28 empty] | 2022-07-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01184 | Hopkinton | 1748 | 16.4 | PV & Battery | 130-H1 | 2022-05-16 | 2022-06-06 | [28 empty] | 2022-06-09 | [12 empty] | 2023-02-01 | Online |  |  | Y
ESMAEX-01231 | Hopkinton | 1748 | 15.2 | PV | 126-H4 | 2022-05-27 | 2022-06-15 | [28 empty] | 2022-06-18 | [12 empty] | 2023-03-01 | Online |  |  | Y
ESMAEX-01345 | Hopkinton | 1748 | 15.975 | Battery | 126-H4 | 2022-07-06 | 2022-07-26 | [28 empty] | 2022-09-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01424 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H1 | 2022-08-02 | 2022-08-23 | [28 empty] | 2022-09-13 | [12 empty] | 2023-04-07 | Online |  |  | Y
ESMAEX-01458 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2022-08-10 | 2022-09-07 | [28 empty] | 2022-09-20 | [12 empty] | 2023-03-23 | Online |  |  | Y
ESMAEX-01464 | Hopkinton | 1748 | 250 | PV | 265-1386 | 2022-09-09 | 2022-09-29 | [28 empty] | 2022-10-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01487 | Hopkinton | 1748 | 220 | PV | 126-H1 | 2022-08-19 | 2022-09-01 | [28 empty] | 2022-10-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01537 | Hopkinton | 1748 | 250 | PV | 65-H7 | 2022-09-02 | 2022-09-22 | [42 empty] | In Queue |  |  | Y
ESMAEX-01538 | Hopkinton | 1748 | 250 | PV | 65-H7 | 2022-09-02 | 2022-09-22 | [28 empty] | 2022-10-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01619 | Hopkinton | 1748 | 16.2 | PV | 126-H1 | 2022-09-22 | 2022-10-13 | [28 empty] | 2022-10-19 | [12 empty] | 2023-02-01 | Online |  |  | Y
ESMAEX-01627 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2022-09-26 | 2022-10-27 | [28 empty] | 2022-11-01 | [12 empty] | 2023-02-15 | Online |  |  | Y
ESMAEX-01646 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2022-09-29 | 2022-10-19 | [28 empty] | 2022-11-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01692 | Hopkinton | 1748 | 15.2 | PV & Battery | 455-H8 | 2022-10-18 | 2022-11-04 | [28 empty] | 2022-11-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01718 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-11-21 | [12 empty] | 2023-02-28 | Online |  |  | Y
ESMAEX-01757 | Hopkinton | 1748 | 12.9 | PV & Battery | 126-H2 | 2022-11-03 | 2022-12-05 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01840 | Hopkinton | 1748 | 19 | PV & Battery | 126-H4 | 2022-11-22 | 2022-12-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-01843 | Hopkinton | 1748 | 18 | PV | 126-H3 | 2022-11-23 | 2023-02-03 | [28 empty] | 2023-03-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01884 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2022-12-02 | 2022-12-19 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01885 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H2 | 2022-12-02 | 2023-01-12 | [28 empty] | 2023-03-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01908 | Hopkinton | 1748 | 16 | PV | 126-H2 | 2022-12-09 | 2023-01-04 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01910 | Hopkinton | 1748 | 20 | PV & Battery | 126-H2 | 2022-12-09 | 2023-01-04 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01963 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H2 | 2023-01-05 | 2023-02-07 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01980 | Hopkinton | 1748 | 20 | PV | 126-H2 | 2023-01-09 | 2023-02-01 | [42 empty] | In Queue |  |  | Y
ESMAEX-02001 | Hopkinton | 1748 | 15.2 | PV | 126-H2 | 2023-01-11 | 2023-02-02 | [28 empty] | 2023-02-09 | [12 empty] | 2023-04-07 | Online |  |  | Y
ESMAEX-02110 | Hopkinton | 1748 | 15.2 | PV & Battery | 126-H4 | 2023-02-03 | 2023-02-23 | [28 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02160 | Hopkinton | 1748 | 15.2 | Battery | 126-H1 | 2023-02-14 | 2023-03-02 | [28 empty] | 2023-03-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-02164 | Hopkinton | 1748 | 199 | Battery | 126-H2 | 2023-02-15 | 2023-03-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-02183 | Hopkinton | 1748 | 15.2 | Battery | 455-H8 | 2023-02-21 | 2023-03-08 | [28 empty] | 2023-03-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02284 | Hopkinton | 1748 | 22.8 | PV | 126-H1 | 2023-03-20 | 2023-04-06 | [42 empty] | In Queue |  |  | Y
ESMAEX-02291 | Hopkinton | 1748 | 15.2 | PV | 455-H8 | 2023-03-21 | 2023-04-06 | [28 empty] | 2023-04-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-02298 | Hopkinton | 1748 | 120 | PV | TBD | 2023-03-22 | 2023-04-06 | [42 empty] | In Queue |  |  | Y
ESMAEX-02309 | Hopkinton | 1748 | 10.23 | PV | 126-H2 | 2023-03-24 | 2023-04-11 | [28 empty] | 2023-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02356 | Hopkinton | 1748 | 19.9 | PV | 126-H4 | 2023-04-06 | 2023-04-25 | [28 empty] | 2023-04-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-02363 | Hopkinton | 1748 | 15.2 | PV | 126-H4 | 2023-04-10 | 2023-04-25 | [28 empty] | 2023-04-25 | [13 empty] | In Queue |  |  | Y
2272821 | Yarmouth | 1748 | 86.25 | PV | 4-92A-558 | 2018-03-29 | 2018-04-09 | 7 |  | 7 | 2018-04-23 |  | -30857 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-14 | Online
2358332 | Framingham | 1749 | 216 | PV | TBD | 2019-08-19 | 2019-08-21 |  |  |  | 2019-09-09 | [24 empty] | 2020-02-14 | [12 empty] | 2020-12-16 | Online
2313811 | Waltham | 1749 | 31.7 | PV | 386-1356 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2122407 | Maynard | 1754 | 32.85 | PV | 416-H6 | 2016-12-21 | 2017-01-05 | 10 |  | 10 | 2017-01-11 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-10-21 | Online
2262268 | Maynard | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30805 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-14 | Online
2227357 | Maynard | 1754 | 3516 | PV | 416-H6 | 2017-06-22 | 2017-07-06 | 9 |  | 9 | 2017-07-27 |  | -30669 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-19 | 2018-02-20 | -21 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-12-18 | [6 empty] | 0 |  | 0
2262282 | Maynard | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30805 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
4614920 | Maynard | 1754 | 86.4 | PV | TBD | 2020-11-13 | 2020-11-16 | 2020-12-23 | [27 empty] | 2021-03-01 | [12 empty] | 2022-06-29 | Online
5256604 | Maynard | 1754 | 1400.5 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-24 | [38 empty] | Withdrawn
5244434 | Maynard | 1754 | 495.3 | PV | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-22 | [38 empty] | Withdrawn
5256556 | Maynard | 1754 | 774.3 | PV | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-24
ESMAEX-00224 | Maynard | 1754 | 1750 | PV & Battery | 416-H6 | 2021-07-02 | 2021-07-20 | [42 empty] | In Queue |  |  | Y
ESMAEX-00232 | Maynard | 1754 | 17.8 | PV & Battery | 355-04 | 2021-07-12 | 2021-08-16 | [28 empty] | 2021-09-20 | [12 empty] | 2021-12-28 | Online |  |  | Y
ESMAEX-00247 | Maynard | 1754 | 16.4 | PV | 416-H1 | 2021-07-19 | 2021-08-09 | [28 empty] | 2021-09-20 | [12 empty] | 2022-02-02 | Online |  |  | Y
ESMAEX-01239 | Maynard | 1754 | 430 | PV & Battery | 416-H6 | 2023-01-04 | 2023-02-01 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01262 | Maynard | 1754 | 83.3 | PV | 342-H8 | 2022-06-07 | 2022-06-22 | [28 empty] | 2022-07-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01263 | Maynard | 1754 | 133.3 | PV & Battery | 342-H8 | 2022-06-07 | 2022-06-22 | [28 empty] | 2022-07-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01264 | Maynard | 1754 | 50 | PV | 342-H8 | 2022-06-07 | 2022-06-22 | [28 empty] | 2022-08-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01265 | Maynard | 1754 | 24 | PV | 342-H8 | 2022-06-07 | 2022-06-22 | [28 empty] | 2022-08-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01266 | Maynard | 1754 | 125 | PV | 416-H6 | 2022-06-07 | 2022-06-22 | [28 empty] | 2022-08-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01267 | Maynard | 1754 | 487.5 | PV & Battery | 342-H8 | 2022-08-15 | 2022-09-09 | [28 empty] | 2022-10-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-01324 | Maynard | 1754 | 199.9 | PV & Battery | 342-H8 | 2022-06-25 | 2022-08-15 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01325 | Maynard | 1754 | 199.8 | PV & Battery | 342-H8 | 2022-06-25 | 2022-08-15 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01588 | Maynard | 1754 | 4990 | Battery | 416-H6 | 2022-09-14 | 2022-11-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-02347 | Maynard | 1754 | 7.6 | PV | 416-H6 | 2023-04-05 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
2356835 | Stoneham | 1757 | 86.4 | PV | TBD | 2019-08-14 | 2019-08-19 |  |  |  | 2019-08-29 | [24 empty] | 2019-10-04 | [12 empty] | 2020-04-21 | Online
2143668 | Natick | 1760 | 16.25 | PV | 433-H5 | 2016-04-05 | 2016-04-11 | 4 |  | 4 | 2016-04-29 |  | -30351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-16 | 2010-06-03 | [6 empty] | 0 |  | 0 |  |  | 2016-09-19 | Online |  | PRIVATE
2168736 | Natick | 1760 | 21.9 | PV | 240-H2 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-09-12 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2016-11-29 | Online |  | PRIVATE | Y
2183182 | Natick | 1760 | 94.52 | PV | 240-H5 | 2016-10-18 | 2016-10-27 | 7 |  | 7 | 2016-11-28 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online
2191567 | Natick | 1760 | 20 | PV | 240-H5 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-30 |  | -30526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-06-27 | Online |  | PRIVATE
2199089 | Natick | 1760 | 16.78 | PV | 433-H5 | 2017-01-11 | 2017-01-18 | 4 |  | 4 | 2017-01-31 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | PRIVATE
2236094 | Natick | 1760 | 51.75 | PV | 433-H9 | 2017-08-29 | 2017-08-30 | 1 |  | 1 | 2017-09-21 |  | -30708 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-10-25 | [6 empty] | 0 |  | 0 |  |  | 2018-03-23 | Online
2260285 | Natick | 1760 | 40.25 | PV | 433-H5 | 2017-12-28 | 2017-12-28 | 0 |  | 0 | 2018-01-26 |  | -30796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-04-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
2262597 | Natick | 1760 | 37.5 | PV | 433-H12 | 2018-01-16 | 2018-01-29 | 9 |  | 9 | 2018-02-12 |  | -30807 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
2229922 | Natick | 1760 | 466.2 | PV | 433-H10 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-04 | 2018-01-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online |  | Private
2229933 | Natick | 1760 | 466.2 | PV | 433-H14 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-02 | 2017-01-08 | -272 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2019-11-20 | Online
2328177 | Natick | 1760 | 32.4 | PV | 433-H10 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-03-04 |  | -31082 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
2311483 | Natick | 1760 | 180 | PV | 433-H10 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online |  | Private
2335440 | Natick | 1760 | 150 | CHP | 433-H7 | 2019-03-26 | 2019-04-02 | 5 |  | 5 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-02-18 | Online
2321912 | Natick | 1760 | 72 | PV | 433-H10 | 2019-01-15 | 2019-01-15 | 0 |  | 0 | 2019-01-23 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
2303427 | Natick | 1760 | 100 | PV & Battery | 240-H3 | 2018-10-11 | 2018-10-18 | 5 |  | 5 |  | 2018-11-26 | 31011 |  | 31011 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-22 | Online |  | Private
2363856 | Natick | 1760 | 66 | PV & Battery | 433-H9 | 2019-08-22 | 2019-09-30 |  |  |  | 2019-10-15 | [24 empty] | 2019-11-27 | [12 empty] | 2020-09-21 | Online
2397214 | Natick | 1760 | 13.92 | PV | 240-H1 | 2020-03-09 | 2020-04-22 |  |  |  | 2020-05-08 | [24 empty] | 2020-08-27 | [12 empty] | 2020-12-11 | Online
4397054 | Natick | 1760 | 100 | PV | TBD | 2020-10-05 | 2020-10-05 |  |  |  | 2020-10-22 | [37 empty] | 2020-12-15 | Online
2139413 | Natick | 1760 | 16.2 | PV | 240-H1 | 2016-03-20 | 2016-03-28 | 6 |  | 6 | 2016-04-07 |  | -30335 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-22 | 2016-07-11 | [6 empty] | 0 |  | 0
2173993 | Natick | 1760 | 126 | PV | 240-H2 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | In Queue
2180242 | Natick | 1760 | 252 | PV | 240-H1 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-03 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2184402 | Natick | 1760 | 720 | PV | 433-H12 | 2016-10-17 | 2016-10-31 | 10 |  | 10 | 2016-12-02 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
2197718 | Natick | 1760 | 737 | PV | 339-1345H | 2016-12-21 | 2017-01-05 | 10 |  | 10 | 2017-01-20 |  | -30539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-16 | [7 empty] | 0 |  | 0
2120191 | Natick | 1760 | 24.8 | PV | 2302 | 2016-12-22 | 2016-12-26 | 2 |  | 2 | 2016-01-08 |  | -30271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-28 | 2016-01-28 | [6 empty] | 0 |  | 0
2208547 | Natick | 1760 | 449.5 | PV | 433-H5 | 2017-02-10 | 2017-03-23 | 28 |  | 28 | 2017-04-06 |  | -30592 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE | N
2209451 | Natick | 1760 | 466.2 | PV | 433-H12 | 2017-02-10 | 2017-03-23 | 28 |  | 28 | 2017-04-06 |  | -30592 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE | N
2226744 | Natick | 1760 | 497 | PV | 240-H1 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30666 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-05-01 | [6 empty] | 0 |  | 0
2252677 | Natick | 1760 | 1700 | CHP | 23-1339H2 | 2017-12-01 | 2017-12-19 | 12 |  | 12 | 2017-12-20 |  | -30770 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2295244 | Natick | 1760 | 180 | PV | 433-H12 | 2018-08-09 | 2018-08-17 | 6 |  | 6 | 2018-09-06 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2303432 | Natick | 1760 | 366.6 | PV | 433-H9 | 2018-10-05 | 2018-10-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2333229 | Natick | 1760 | 407 | PV & Battery | 433-H10 | 2019-01-17 | 2019-03-18 | 42 |  | 42 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2336317 | Natick | 1760 | 366.6 | PV | 433-H5 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2350187 | Natick | 1760 | 466.6 | PV | TBD | 2019-07-01 | 2019-07-01 |  |  |  | 2019-07-22 | [24 empty] | 2019-09-05
2366044 | Natick | 1760 | 43.2 | PV | TBD | 2019-10-11 | 2019-10-15 |  |  |  | 2019-10-29 | [24 empty] | 2019-11-29 | [13 empty] | Withdrawn
2366438 | Natick | 1760 | 100 | PV | TBD | 2019-10-15 | 2019-10-15 |  |  |  | 2019-10-31 | [24 empty] | 2019-11-20
2392730 | Natick | 1760 | 180 | PV | TBD | 2020-03-02 | 2020-03-20 |  |  |  | 2020-04-03 | [24 empty] | 2020-05-29 | [12 empty] | 2023-01-13 | Online
2389477 | Natick | 1760 | 133.2 | PV | TBD | 2020-03-03 | 2020-03-04 |  |  |  | 2020-03-11 | [24 empty] | 2020-03-31 | [12 empty] | 2022-02-08 | Online
2392595 | Natick | 1760 | 456 | PV & Battery | TBD | 2020-03-05 | 2020-03-20 |  |  |  | 2020-04-03 | [24 empty] | 2020-05-29 | [12 empty] | 2023-01-13 | Online
2398079 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-27 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2398175 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-27 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2398227 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-04-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2399596 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2399607 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-05-29 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2400946 | Natick | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 |  |  |  | 2020-06-04 | [24 empty] | 2020-12-01 | [12 empty] | 2022-02-15 | Online
2408582 | Natick | 1760 | 43.2 | PV | TBD | 2020-05-28 | 2020-07-07 |  |  |  | 2020-07-30 | [24 empty] | 2020-10-08 | [12 empty] | 2022-02-01 | Online
2410746 | Natick | 1760 | 10 | PV | TBD | 2020-07-21 | 2020-07-21 |  |  |  | 2020-08-14 | [38 empty] | Withdrawn
4427690 | Natick | 1760 | 25 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 |  |  |  | 2020-11-04 | [24 empty] | 2021-04-06 | [12 empty] | 2021-09-30 | Online
4698431 | Natick | 1760 | 7.6 | PV | 240-H3 | 2020-12-14 | 2020-12-29 |  |  |  | 2021-01-19 | [24 empty] | 2021-07-26
5247213 | Natick | 1760 | 17.6 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 |  |  |  | 2021-03-24 | [24 empty] | 2021-04-01 | [12 empty] | 2022-02-01 | Online
5158094 | Natick | 1760 | 26.4 | PV & Battery | TBD | 2021-02-19 | 2021-03-01 |  |  |  | 2021-03-08 | [24 empty] | 2021-07-12 | [12 empty] | 2022-07-14 | Online
5343911 | Natick | 1760 | 10 | Battery | TBD | 2021-03-12 | 2021-03-16 |  |  |  | 2021-03-31 | [24 empty] | 2021-04-19 | [12 empty] | 2023-03-09 | Online
5273003 | Natick | 1760 | 19.86 | Battery | TBD | 2021-03-08 | 2021-03-08 |  |  |  | 2021-03-23 | [24 empty] | 2021-05-05 | [12 empty] | 2022-01-19 | Online
5447224 | Natick | 1760 | 16.24 | PV | TBD | 2021-03-29 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2021-04-19
ESMAEX-00122 | Natick | 1760 | 251.3 | PV | 433-H12 | 2021-05-13 | 2021-05-27 | [28 empty] | 2022-02-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-00213 | Natick | 1760 | 12.6 | PV & Battery | 240-H6 | 2021-06-25 | 2021-07-13 | [28 empty] | 2022-01-14 | [12 empty] | 2022-06-22 | Online |  |  | Y
ESMAEX-00472 | Natick | 1760 | 10.248 | PV & Battery | 240-H1 | 2021-10-05 | 2021-10-26 | [28 empty] | 2022-02-03 | [12 empty] | 2022-11-08 | Online |  |  | Y
ESMAEX-00473 | Natick | 1760 | 9.516 | PV & Battery | 433-H12 | 2021-10-05 | 2021-10-26 | [28 empty] | 2021-12-13 | [12 empty] | 2022-02-08 | Online |  |  | Y
ESMAEX-00514 | Natick | 1760 | 10.248 | PV & Battery | 240-H3 | 2021-10-19 | 2022-01-25 | [28 empty] | 2022-02-14 | [12 empty] | 2022-05-20 | Online |  |  | Y
ESMAEX-00563 | Natick | 1760 | 10.248 | PV & Battery | 240-H3 | 2021-11-03 | 2021-11-23 | [28 empty] | 2022-03-03 | [12 empty] | 2022-06-02 | Online |  |  | Y
ESMAEX-00738 | Natick | 1760 | 199.9 | PV | 240-H6 | 2022-01-19 | 2022-02-11 | [28 empty] | 2022-02-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-00899 | Natick | 1760 | 86.5 | PV & Battery | 433-H11 | 2022-03-11 | 2022-03-30 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-00915 | Natick | 1760 | 126.9 | PV & Battery | 23-H1 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-05-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00935 | Natick | 1760 | 15.2 | PV & Battery | 240-H1 | 2022-03-17 | 2022-04-06 | [28 empty] | 2022-04-28 | [12 empty] | 2022-06-02 | Online |  |  | Y
ESMAEX-01038 | Natick | 1760 | 15.2 | PV & Battery | 240-H5 | 2022-04-07 | 2022-04-11 | [28 empty] | 2022-05-02 | [12 empty] | 2023-03-10 | Online |  |  | Y
ESMAEX-01103 | Natick | 1760 | 18.29 | PV | 433-H7 | 2022-04-22 | 2022-05-12 | [28 empty] | 2022-07-15 | [12 empty] | 2022-10-17 | Online |  |  | Y
ESMAEX-01178 | Natick | 1760 | 160 | PV | TBD | 2022-05-13 | 2022-06-06 | [28 empty] | 2022-06-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01236 | Natick | 1760 | 6.6 | PV & Battery | 433-H12 | 2022-05-31 | 2022-06-23 | [28 empty] | 2022-09-09 | [12 empty] | 2022-10-19 | Online |  |  | Y
ESMAEX-01331 | Natick | 1760 | 15.2 | PV | 433-H12 | 2022-06-28 | 2022-09-29 | [28 empty] | 2022-10-11 | [12 empty] | 2023-04-07 | Online |  |  | Y
ESMAEX-01354 | Natick | 1760 | 17.6 | PV & Battery | 433-H7 | 2022-07-08 | 2022-07-26 | [28 empty] | 2022-09-06 | [12 empty] | 2022-11-18 | Online |  |  | Y
ESMAEX-01553 | Natick | 1760 | 19.8 | PV | 240-H5 | 2022-09-08 | 2022-09-26 | [28 empty] | 2022-10-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01617 | Natick | 1760 | 250 | PV | 433-H5 | 2022-10-14 | 2022-11-23 | [28 empty] | 2022-12-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01632 | Natick | 1760 | 15.2 | PV | 240-H1 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-10-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01785 | Natick | 1760 | 13.8 | PV & Battery | 240-H1 | 2022-11-08 | 2022-12-08 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01796 | Natick | 1760 | 16.2 | PV | 2304 | 2022-11-10 | 2022-12-08 | [28 empty] | 2022-12-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01854 | Natick | 1760 | 19.8 | PV & Battery | 240-H1 | 2022-11-28 | 2022-12-09 | [28 empty] | 2023-03-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01914 | Natick | 1760 | 15.2 | PV & Battery | 240-H1 | 2022-12-09 | 2023-01-04 | [28 empty] | 2023-01-09 | [12 empty] | 2023-04-18 | Online |  |  | Y
ESMAEX-01929 | Natick | 1760 | 10 | Battery | 433-H10 | 2022-12-16 | 2023-01-10 | [28 empty] | 2023-01-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-02027 | Natick | 1760 | 16.4 | PV | 240-H5 | 2023-01-14 | 2023-02-01 | [28 empty] | 2023-03-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-02053 | Natick | 1760 | 19.84 | PV | 433-H7 | 2023-01-23 | 2023-02-10 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02221 | Natick | 1760 | 10 | PV & Battery | 433-H12 | 2023-03-01 | 2023-03-29 | [42 empty] | In Queue |  |  | Y
ESMAEX-02242 | Natick | 1760 | 16.47 | PV | 240-H1 | 2023-03-08 | 2023-03-23 | [28 empty] | 2023-04-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-02403 | Natick | 1760 | 15 | PV | 433-H5 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
ESMAEX-02428 | Natick | 1760 | 25 | PV | 240-H1 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
2317182 | Sudbury | 1766 | 499.99 | PV | 342-H2 | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2148838 | Sherborn | 1770 | 23.1 | PV | 274-H3 | 2016-05-03 | 2016-05-18 | 11 |  | 11 | 2016-06-02 |  | -30375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-07 | [7 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online |  | PRIVATE
2196661 | Sherborn | 1770 | 75 | PV | 240-H1 | 2016-12-16 | 2016-12-28 | 8 |  | 8 | 2017-01-13 |  | -30535 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-01-19 | [6 empty] | 0 |  | 0 |  |  | 2017-05-24 | Online
2262993 | Sherborn | 1770 | 110 | PV | 274-H4 | 2017-11-17 | 2018-02-01 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-25 | 2018-06-29 | [6 empty] | 0 |  | 0 |  |  | 2018-04-25 | Online
2329192 | Sherborn | 1770 | 34.78 | PV | 240-H1 | 2019-02-15 | 2019-02-26 | 7 |  | 7 | 2019-03-12 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
2358191 | Sherborn | 1770 | 17.6 | PV & Battery | TBD | 2019-08-07 | 2019-08-13 |  |  |  | 2019-09-06 | [24 empty] | 2019-09-24 | [12 empty] | 2020-02-25 | Online
2407667 | Sherborn | 1770 | 17.4 | PV | TBD | 2020-07-10 | 2020-07-10 |  |  |  | 2020-07-27 | [24 empty] | 2020-09-09 | [12 empty] | 2020-11-12 | Online
2181941 | Sherborn | 1770 | 35.6 | PV | 274-H2 | 2016-10-11 | 2016-10-17 | 4 |  | 4 | 2016-11-17 |  | -30495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2367897 | Sherborn | 1770 | 22.8 | PV | 240-H1 | 2019-10-18 | 2019-10-24 |  |  |  | 2019-11-07 | [24 empty] | 2019-11-29 | [12 empty] | 2021-06-01 | Online
2369848 | Sherborn | 1770 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 |  |  |  | 2019-11-22 | [24 empty] | 2020-06-04 | [13 empty] | Withdrawn
4425381 | Sherborn | 1770 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 |  |  |  | 2020-10-28 | [24 empty] | 2021-01-29
4557126 | Sherborn | 1770 | 18.6 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 |  |  |  | 2020-12-04 | [24 empty] | 2021-02-09
4963535 | Sherborn | 1770 | 15.2 | PV & Battery | TBD | 2020-11-24 | 2021-01-27 |  |  |  | 2021-02-11 | [24 empty] | 2021-09-14 | [13 empty] | Withdrawn
4680617 | Sherborn | 1770 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-02-02 | [12 empty] | 2022-05-18 | Online
ESMAEX-00248 | Sherborn | 1770 | 5.7 | Battery | 240-H1 | 2021-07-19 | 2021-08-03 | [28 empty] | 2021-10-04 | [12 empty] | 2022-02-18 | Online |  |  | Y
ESMAEX-00285 | Sherborn | 1770 | 19.7 | PV | 130-H2 | 2021-08-04 | 2021-08-16 | [28 empty] | 2021-09-20 | [12 empty] | 2022-07-07 | Online |  |  | Y
ESMAEX-00323 | Sherborn | 1770 | 20 | PV & Battery | 240-H1 | 2021-08-17 | 2021-10-21 | [28 empty] | 2022-01-14 | [12 empty] | 2022-05-23 | Online |  |  | Y
ESMAEX-00335 | Sherborn | 1770 | 24.19 | PV | 274-H2 | 2021-08-20 | 2021-09-08 | [28 empty] | 2021-09-20 | [12 empty] | 2022-08-17 | Online |  |  | Y
ESMAEX-00824 | Sherborn | 1770 | 13.275 | PV & Battery | 274-H2 | 2022-02-09 | 2022-03-01 | [28 empty] | 2022-03-16 | [12 empty] | 2022-07-21 | Online |  |  | Y
ESMAEX-00922 | Sherborn | 1770 | 15.705 | PV | 274-H2 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-04-05 | [12 empty] | 2022-06-30 | Online |  |  | Y
ESMAEX-01028 | Sherborn | 1770 | 30 | PV | 240-H1 | 2022-04-07 | 2022-04-27 | [28 empty] | 2022-06-14 | [12 empty] | 2023-01-18 | Online |  |  | Y
ESMAEX-01323 | Sherborn | 1770 | 16.8 | PV | 240-H1 | 2022-06-25 | 2022-08-15 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01663 | Sherborn | 1770 | 15.2 | PV & Battery | 274-H2 | 2022-10-06 | 2022-10-25 | [28 empty] | 2022-10-28 | [12 empty] | 2023-04-10 | Online |  |  | Y
ESMAEX-01775 | Sherborn | 1770 | 20 | PV | 130-H2 | 2022-11-08 | 2022-11-16 | [28 empty] | 2022-11-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-01944 | Sherborn | 1770 | 18.66 | PV & Battery | 274-H2 | 2022-12-23 | 2023-01-10 | [28 empty] | 2023-01-18 | [13 empty] | In Queue |  |  | Y
2214304 | Lincoln | 1773 | 24 | PV | 320-H8 | 2017-04-12 | 2017-04-18 | 3 |  | 3 | 2017-05-05 |  | -30612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-07 | 2017-06-20 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
2260143 | Lincoln | 1773 | 43.8 | PV | 320-H1 | 2017-10-16 | 2018-01-03 | 55 |  | 55 | 2018-01-25 |  | -30795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-27 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
2321103 | Lincoln | 1773 | 20 | PV & Battery | 320-H6 | 2018-12-20 | 2019-01-08 | 13 |  | 13 | 2019-01-29 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 | [7 empty] | 0 |  | 0 |  |  | 2019-09-03 | Online
2340569 | Lincoln | 1773 | 38 | PV | 320-H8 | 2019-04-22 | 2019-05-01 | 7 |  | 7 | 2019-05-21 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
2347229 | Lincoln | 1773 | 17.4 | PV | 320-H6 | 2019-05-31 | 2019-06-14 |  |  |  | 2019-06-27 | [24 empty] | 2019-08-02 | [12 empty] | 2020-03-31 | Online
2368534 | Lincoln | 1773 | 23.7 | PV | 282-H1 | 2019-08-05 | 2019-10-28 |  |  |  | 2019-11-13 | [24 empty] | 2019-12-30 | [12 empty] | 2020-09-11 | Online
2306816 | Lincoln | 1773 | 86.4 | PV | 320-H1 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -31006 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-23 | Online |  | Private
2401979 | Lincoln | 1773 | 22.6 | PV & Battery | TBD | 2020-05-18 | 2020-05-28 |  |  |  | 2020-06-12 | [24 empty] | 2020-10-01 | [12 empty] | 2020-12-30 | Online
4713513 | Lincoln | 1773 | 14 | Battery | 320-H8 | 2020-12-31 | 2020-12-31 |  |  |  | 2021-01-19 | [24 empty] | 2021-03-09 | [12 empty] | 2021-04-30 | Online
4556854 | Lincoln | 1773 | 20 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 |  |  |  | 2020-12-04 | [24 empty] | 2021-03-09 | [12 empty] | 2021-05-05 | Online
2276951 | Lincoln | 1773 | 250 | PV | 320-H1 | 2018-04-26 | 2018-05-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-31 | [7 empty] | 0 |  | 0
2350004 | Lincoln | 1773 | 107.84 | PV & Battery | 320-H8 | 2019-02-11 | 2019-07-10 | 107 |  | 107 | 2019-07-17 |  | -31179 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0
2350022 | Lincoln | 1773 | 17.6 | PV | 320-H6 | 2019-05-31 | 2019-07-03 |  |  |  | 2019-07-16
2365635 | Lincoln | 1773 | 1831.4 | PV & Battery | 320-H8 | 2019-09-13 | 2019-10-28 | [28 empty] | 2021-11-16
2368084 | Lincoln | 1773 | 129.6 | PV | TBD | 2019-10-28 | 2019-10-28 |  |  |  | 2019-12-04 | [38 empty] | Withdrawn
2398639 | Lincoln | 1773 | 43.2 | PV | 240-H1 | 2020-04-15 | 2020-05-04 |  |  |  | 2020-05-20 | [24 empty] | 2020-06-30 | [12 empty] | 2022-09-27 | Online
2398773 | Lincoln | 1773 | 86.4 | PV | TBD | 2020-04-15 | 2020-05-04 |  |  |  | 2020-05-20 | [24 empty] | 2020-06-30 | [12 empty] | 2022-09-27 | Online
ESMAEX-00206 | Lincoln | 1773 | 17.6 | PV | 320-H8 | 2021-06-23 | 2021-07-13 | [28 empty] | 2021-07-22 | [12 empty] | 2022-03-29 | Online |  |  | Y
ESMAEX-00226 | Lincoln | 1773 | 12.6 | PV & Battery | 320-H2 | 2021-07-02 | 2021-07-21 | [28 empty] | 2021-08-03 | [12 empty] | 2022-03-15 | Online |  |  | Y
ESMAEX-00376 | Lincoln | 1773 | 52.8 | PV & Battery | 320-H8 | 2021-09-01 | 2021-09-16 | [28 empty] | 2021-10-20 | [12 empty] | 2022-07-19 | Online |  |  | Y
ESMAEX-00406 | Lincoln | 1773 | 21.65 | PV & Battery | 320-H8 | 2021-09-13 | 2021-09-29 | [28 empty] | 2021-11-29 | [12 empty] | 2022-02-03 | Online |  |  | Y
ESMAEX-00763 | Lincoln | 1773 | 10 | Battery | 342-H1 | 2022-01-28 | 2022-02-24 | [28 empty] | 2022-03-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00811 | Lincoln | 1773 | 7.68 | Battery | 320-H8 | 2022-02-04 | 2022-02-28 | [28 empty] | 2022-04-26 | [12 empty] | 2022-11-16 | Online |  |  | Y
ESMAEX-00912 | Lincoln | 1773 | 9.216 | PV | 320-H2 | 2022-03-14 | 2022-03-31 | [28 empty] | 2022-05-04 | [12 empty] | 2022-09-26 | Online |  |  | Y
ESMAEX-00917 | Lincoln | 1773 | 15.36 | PV & Battery | 320-H2 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-05-04 | [12 empty] | 2022-10-14 | Online |  |  | Y
ESMAEX-01144 | Lincoln | 1773 | 25.828 | PV & Battery | 320-H8 | 2022-05-04 | 2022-05-25 | [28 empty] | 2022-07-18 | [12 empty] | 2022-10-21 | Online |  |  | Y
ESMAEX-01217 | Lincoln | 1773 | 14.455 | PV & Battery | 320-H8 | 2022-05-25 | 2022-06-23 | [28 empty] | 2022-08-04 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-01233 | Lincoln | 1773 | 24.78 | PV | 320-H2 | 2022-05-27 | 2022-06-15 | [28 empty] | 2022-06-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-01394 | Lincoln | 1773 | 22.6 | PV & Battery | 320-H8 | 2022-07-20 | 2022-08-10 | [28 empty] | 2022-10-12 | [12 empty] | 2023-02-23 | Online |  |  | Y
ESMAEX-01664 | Lincoln | 1773 | 19.845 | PV | 320-H8 | 2022-10-06 | 2022-10-25 | [28 empty] | 2022-11-23 | [12 empty] | 2023-03-10 | Online |  |  | Y
ESMAEX-01981 | Lincoln | 1773 | 14 | Battery | 320-H8 | 2023-01-09 | 2023-02-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02130 | Lincoln | 1773 | 10 | Battery | 320-H8 | 2023-02-07 | 2023-03-22 | [42 empty] | In Queue |  |  | Y
ESMAEX-02319 | Lincoln | 1773 | 10 | Battery | 320-H2 | 2023-03-29 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-02341 | Lincoln | 1773 | 15.36 | PV | 342-H1 | 2023-04-04 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
ESMAEX-02346 | Lincoln | 1773 | 20 | PV | 320-H8 | 2023-04-05 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
2200960 | Stoneham | 1776 | 16.2 | PV | 375-H2 | 2017-01-24 | 2017-01-27 | 3 |  | 3 | 2017-02-10 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2114162 | Sudbury | 1776 | 15.5 | PV | 342-H7 | 2015-10-19 | 2015-10-20 | 1 |  | 1 | 2015-12-11 |  | -30251 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-15 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
2168989 | Sudbury | 1776 | 20 | PV | 342-H7 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-13 |  | -30448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online |  | PRIVATE
2200633 | Sudbury | 1776 | 96 | PV | 342-H2 | 2017-02-09 | 2017-02-09 | 0 |  | 0 | 2017-02-10 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-31 | 2017-04-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-25 | Online |  | P2 | N
2201274 | Sudbury | 1776 | 21.4 | PV | 342-H5 | 2017-02-03 | 2017-02-08 | 3 |  | 3 | 2017-02-14 |  | -30556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-06-06 | Online |  | PRIVATE
2261526 | Sudbury | 1776 | 29.58 | PV | 342-H7 | 2017-12-04 | 2018-01-19 | 33 |  | 33 | 2018-02-02 |  | -30801 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-23 | [6 empty] | 0 |  | 0 |  |  | 2018-07-24 | Online
2284555 | Sudbury | 1776 | 25 | PV | 342-H7 | 2018-05-31 | 2018-06-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
2269609 | Sudbury | 1776 | 240 | PV | 342-H5 | 2018-02-21 | 2018-03-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-10 | [6 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
2355864 | Sudbury | 1776 | 15.2 | PV | TBD | 2019-07-31 | 2019-08-06 |  |  |  | 2019-08-22 | [24 empty] | 2019-09-12 | [12 empty] | 2019-12-13 | Online
2389233 | Sudbury | 1776 | 20 | PV & Battery | TBD | 2020-02-07 | 2020-02-24 |  |  |  | 2020-03-09 | [24 empty] | 2020-05-21 | [12 empty] | 2020-10-08 | Online
2391527 | Sudbury | 1776 | 17.6 | PV & Battery | 342-H7 | 2020-03-09 | 2020-03-12 |  |  |  | 2020-03-27 | [24 empty] | 2020-05-06 | [12 empty] | 2020-10-23 | Online
2334450 | Sudbury | 1776 | 15.2 | PV & Battery | 342-H5 | 2019-03-29 | 2019-04-12 | 10 |  | 10 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
2142844 | Sudbury | 1776 | 21.6 | PV | 342-h8 | 2016-04-11 | 2016-04-19 | 6 |  | 6 | 2016-04-25 |  | -30347 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-10 | [6 empty] | 0 |  | 0
2184047 | Sudbury | 1776 | 17.4 | PV | 342-H7 | 2016-10-25 | 2016-10-31 | 4 |  | 4 | 2016-12-01 |  | -30505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | In Queue |  | PRIVATE
2279224 | Sudbury | 1776 | 249.8 | PV | 342-H2 | 2018-05-11 | 2018-05-16 | 3 |  | 3 | 2018-05-31 |  | -30885 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0
2403835 | Sudbury | 1776 | 200 | PV | TBD | 2020-04-16 | 2020-06-10 |  |  |  | 2020-06-29 | [24 empty] | 2020-11-05 | [12 empty] | 2022-05-13 | Online
4307664 | Sudbury | 1776 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-09-15 |  |  |  | 2020-10-05 | [24 empty] | 2021-01-26
2406653 | Sudbury | 1776 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 |  |  |  | 2020-07-20 | [24 empty] | 2020-12-24 | [13 empty] | Withdrawn
4619003 | Sudbury | 1776 | 5 | Battery | 342-H4 | 2020-11-06 | 2020-11-24 |  |  |  | 2020-12-21 | [24 empty] | 2021-02-09
4619695 | Sudbury | 1776 | 23.8 | PV & Battery | TBD | 2020-11-06 | 2020-11-24 |  |  |  | 2020-12-22 | [24 empty] | 2022-04-06
4983699 | Sudbury | 1776 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-20 |  |  |  | 2021-02-11
4850477 | Sudbury | 1776 | 35.2 | PV & Battery | TBD | 2020-12-24 | 2020-12-24 |  |  |  | 2021-01-25
4878402 | Sudbury | 1776 | 20 | PV & Battery | TBD | 2021-01-11 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-19 | [13 empty] | Withdrawn
5164789 | Sudbury | 1776 | 36 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 |  |  |  | 2021-03-16
2140033 | Sudbury | 1776 | 15.75 | PV | 342-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5343412 | Sudbury | 1776 | 400 | PV | TBD | 2021-03-16 | 2021-03-15 |  |  |  | 2021-03-31 | [24 empty] | 2022-04-08
ESMAEX-00171 | Sudbury | 1776 | 34.2 | PV | 342-H8 | 2021-06-08 | 2021-06-24 | [28 empty] | 2021-08-02 | [12 empty] | 2022-01-13 | Online |  |  | Y
ESMAEX-00259 | Sudbury | 1776 | 20 | PV | 342-H6 | 2021-07-22 | 2021-08-12 | [28 empty] | 2021-10-20 | [12 empty] | 2022-03-16 | Online |  |  | Y
ESMAEX-00625 | Sudbury | 1776 | 26.4 | PV & Battery | 342-H8 | 2021-11-28 | 2022-01-18 | [28 empty] | 2022-04-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-00651 | Sudbury | 1776 | 199.9 | PV | 342-H2 | 2021-12-09 | 2021-12-30 | [28 empty] | 2022-03-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-00723 | Sudbury | 1776 | 21.4 | PV & Battery | 342-H8 | 2022-01-11 | 2022-02-03 | [28 empty] | 2022-02-17 | [12 empty] | 2022-03-14 | Online |  |  | Y
ESMAEX-00872 | Sudbury | 1776 | 15.2 | PV & Battery | 342-H2 | 2022-03-02 | 2022-04-18 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-00945 | Sudbury | 1776 | 43.2 | PV | 342-H2 | 2022-03-18 | 2022-04-07 | [28 empty] | 2022-05-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01152 | Sudbury | 1776 | 15.2 | PV | 342-H2 | 2022-05-05 | 2022-06-29 | [28 empty] | 2022-12-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01163 | Sudbury | 1776 | 25.2 | PV & Battery | 342-H6 | 2022-05-10 | [43 empty] | In Queue |  |  | Y
ESMAEX-01193 | Sudbury | 1776 | 15.2 | PV & Battery | 342-H4 | 2022-05-18 | 2022-06-07 | [28 empty] | 2022-06-09 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01357 | Sudbury | 1776 | 7.6 | PV & Battery | 342-H7 | 2022-07-08 | 2022-07-26 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01513 | Sudbury | 1776 | 17.6 | PV | 342-H6 | 2022-08-25 | 2022-09-22 | [28 empty] | 2022-10-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-01709 | Sudbury | 1776 | 50 | PV & Battery | 342-H5 | 2022-10-24 | 2022-11-18 | [28 empty] | 2022-11-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01710 | Sudbury | 1776 | 50 | PV | 342-H4 | 2022-10-24 | 2022-11-22 | [28 empty] | 2022-11-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01711 | Sudbury | 1776 | 17.6 | PV & Battery | 342-H7 | 2022-10-24 | 2022-11-16 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01756 | Sudbury | 1776 | 16 | PV | 342-H8 | 2022-11-02 | 2022-11-16 | [28 empty] | 2022-11-21 | [12 empty] | 2023-02-17 | Online |  |  | Y
ESMAEX-01932 | Sudbury | 1776 | 17.568 | PV | 342-H7 | 2022-12-16 | 2023-01-10 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-02015 | Sudbury | 1776 | 15.6 | PV | 342-H2 | 2023-01-13 | 2023-01-26 | [28 empty] | 2023-02-03 | [13 empty] | Withdrawn |  |  | Y
ESMAEX-02256 | Sudbury | 1776 | 14 | Battery | 342-H2 | 2023-03-09 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
2189506 | Wayland | 1778 | 93.275 | PV | 342-H3 | 2016-11-09 | 2016-11-22 | 9 |  | 9 | 2016-12-28 |  | -30524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-26 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online
2261527 | Wayland | 1778 | 15.2 | PV | 433-H6 | 2017-12-12 | 2018-01-19 | 27 |  | 27 | 2018-02-02 |  | -30801 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
2275155 | Wayland | 1778 | 16.32 | PV | 342-H1 | 2018-04-17 | 2018-04-24 | 5 |  | 5 | 2018-05-04 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-06 | 2018-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
2279425 | Wayland | 1778 | 21.9 | PV | 342-H1 | 2018-05-04 | 2018-05-16 | 8 |  | 8 | 2018-06-01 |  | -30886 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-07 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-03-11 | Online
2286971 | Wayland | 1778 | 208 | PV | 433-H6 | 2018-06-29 | 2018-06-29 | 0 |  | 0 | 2018-07-17 |  | -30918 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
2370024 | Wayland | 1778 | 80 | PV | TBD | 2019-10-28 | 2019-11-08 |  |  |  | 2019-11-22 | [24 empty] | 2020-04-03 | [12 empty] | 2022-05-03 | Online
2377433 | Wayland | 1778 | 20 | PV & Battery | 342-H1 | 2019-11-07 | 2019-11-22 |  |  |  | 2020-01-03 | [24 empty] | 2020-03-24 | [13 empty] | Withdrawn
2389401 | Wayland | 1778 | 20 | PV | TBD | 2020-02-20 | 2020-02-25 |  |  |  | 2020-03-11 | [24 empty] | 2020-08-05 | [12 empty] | 2021-09-27 | Online
2390669 | Wayland | 1778 | 17.6 | PV & Battery | 342-H1 | 2020-02-25 | 2020-03-05 |  |  |  | 2020-03-23 | [24 empty] | 2020-05-14 | [13 empty] | Withdrawn
2404425 | Wayland | 1778 | 10 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 |  |  |  | 2020-07-01
2408090 | Wayland | 1778 | 17.6 | PV & Battery | TBD | 2020-07-14 | 2020-07-14 | [28 empty] | 2020-08-28 | [13 empty] | Withdrawn
2411668 | Wayland | 1778 | 23.01 | PV | TBD | 2020-07-22 | 2020-08-07 |  |  |  | 2020-10-05 | [24 empty] | 2021-01-26 | [12 empty] | 2021-08-06 | Online
4336889 | Wayland | 1778 | 20 | PV & Battery | TBD | 2020-09-15 | 2020-09-15 |  |  |  | 2020-10-05 | [24 empty] | 2020-12-18 | [13 empty] | Withdrawn
4371445 | Wayland | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2020-10-19
4372220 | Wayland | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2020-10-19
4372438 | Wayland | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2020-10-19
4676256 | Wayland | 1778 | 20 | PV | TBD | 2020-11-25 | 2020-12-14 |  |  |  | 2021-01-11 | [24 empty] | 2021-02-04
4894418 | Wayland | 1778 | 16.78 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | [28 empty] | 2021-04-30 | [12 empty] | 2022-05-16 | Online
4972029 | Wayland | 1778 | 10 | Battery | TBD | 2021-01-27 | 2021-01-28 |  |  |  | 2021-02-11 | [24 empty] | 2021-02-19 | [12 empty] | 2022-06-16 | Online
5113728 | Wayland | 1778 | 17.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-30 | [13 empty] | Withdrawn
5164657 | Wayland | 1778 | 17.6 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 |  |  |  | 2021-03-16 | [24 empty] | 2021-04-01 | [12 empty] | 2022-03-17 | Online
ESMAEX-00252 | Wayland | 1778 | 80 | PV | 342-H3 | 2021-07-20 | 2021-08-03 | [28 empty] | 2021-11-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-00424 | Wayland | 1778 | 7.68 | Battery | 278-H2 | 2021-09-20 | 2021-11-09 | [28 empty] | 2022-03-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-00903 | Wayland | 1778 | 12.6 | PV | 433-H2 | 2022-03-11 | 2022-03-31 | [28 empty] | 2022-05-11 | [12 empty] | 2023-03-06 | Online |  |  | Y
ESMAEX-01143 | Wayland | 1778 | 10.248 | PV & Battery | 342-H1 | 2022-05-04 | 2022-05-25 | [28 empty] | 2022-06-02 | [12 empty] | 2023-02-07 | Online |  |  | Y
ESMAEX-01157 | Wayland | 1778 | 24.192 | PV & Battery | 342-H1 | 2022-05-09 | 2022-06-03 | [28 empty] | 2022-06-15 | [12 empty] | 2022-12-16 | Online |  |  | Y
ESMAEX-01225 | Wayland | 1778 | 16 | PV | 342-H1 | 2022-05-26 | 2022-06-15 | [28 empty] | 2022-06-18 | [12 empty] | 2022-12-13 | Online |  |  | Y
ESMAEX-01457 | Wayland | 1778 | 20 | PV & Battery | 278-H2 | 2022-08-10 | 2022-08-29 | [28 empty] | 2022-09-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01471 | Wayland | 1778 | 16 | PV | 278-H2 | 2022-08-15 | 2022-09-01 | [28 empty] | 2022-09-13 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-01496 | Wayland | 1778 | 22.8 | PV & Battery | 342-H3 | 2022-08-22 | 2022-09-14 | [28 empty] | 2022-10-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01521 | Wayland | 1778 | 20.2 | PV & Battery | 342-H3 | 2022-08-29 | 2022-09-14 | [28 empty] | 2022-11-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01531 | Wayland | 1778 | 19.398 | PV | 342-H1 | 2022-09-01 | 2022-10-25 | [28 empty] | 2022-10-31 | [12 empty] | 2023-03-23 | Online |  |  | Y
ESMAEX-01659 | Wayland | 1778 | 7.6 | PV & Battery | 342-H1 | 2022-10-05 | 2022-11-10 | [28 empty] | 2022-11-17 | [12 empty] | 2023-03-23 | Online |  |  | Y
ESMAEX-01732 | Wayland | 1778 | 15.2 | PV & Battery | 342-H3 | 2022-10-27 | 2022-11-16 | [28 empty] | 2023-01-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01825 | Wayland | 1778 | 19.5 | PV & Battery | 342-H1 | 2022-11-17 | 2023-01-04 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01851 | Wayland | 1778 | 187.3 | PV & Battery | 342-H3 | 2022-11-28 | 2022-12-09 | [28 empty] | 2023-01-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01892 | Wayland | 1778 | 17.6 | PV | 342-H1 | 2022-12-06 | 2022-12-29 | [28 empty] | 2023-01-06 | [13 empty] | Withdrawn |  |  | Y
ESMAEX-01921 | Wayland | 1778 | 15 | Battery | 278-H2 | 2022-12-13 | 2023-01-11 | [28 empty] | 2023-03-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01982 | Wayland | 1778 | 22.8 | PV | 342-H1 | 2023-01-09 | 2023-03-29 | [28 empty] | 2023-04-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-02023 | Wayland | 1778 | 15.2 | PV | 342-H1 | 2023-01-13 | 2023-02-01 | [28 empty] | 2023-02-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-02054 | Wayland | 1778 | 15.2 | PV | 278-H2 | 2023-01-23 | 2023-02-10 | [28 empty] | 2023-02-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-02136 | Wayland | 1778 | 16.2 | Battery | 278-H2 | 2023-02-07 | 2023-02-16 | [28 empty] | 2023-02-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-02211 | Wayland | 1778 | 10 | Battery | 342-H1 | 2023-02-28 | 2023-03-21 | [28 empty] | 2023-03-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02245 | Wayland | 1778 | 7.6 | PV | 342-H1 | 2023-03-08 | 2023-03-23 | [28 empty] | 2023-03-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-02332 | Wayland | 1778 | 18.3 | PV | 342-H3 | 2023-04-01 | 2023-04-17 | [42 empty] | In Queue |  |  | Y
ESMAEX-02352 | Wayland | 1778 | 15 | Battery | 342-H1 | 2023-04-06 | [43 empty] | In Queue |  |  | Y
ESMAEX-02369 | Wayland | 1778 | 5 | Battery | 342-H1 | 2023-04-11 | [43 empty] | In Queue |  |  | Y
2294153 | Barnstable | 1801 | 22.8 | PV | 4-81B-443 | 2018-07-24 | 2018-08-15 | 16 |  | 16 | 2018-08-30 | 2018-11-02 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-12-17 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-06-04 | Online |  | Private
2152922 | Bedford | 1801 | 49.14 | PV | 533-H7 | 2016-05-10 | 2016-06-02 | 17 |  | 17 | 2016-06-15 |  | -30384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online |  | PRIVATE
2288242 | Sharon | 1801 | 942 | PV | 146-H1 | 2018-07-10 | 2018-07-10 | 0 |  | 0 | 2018-07-24 |  | -30923 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0
2096036 | Woburn | 1801 | 499.8 | PV | 375-H12 | 2015-09-04 | 2015-09-09 | 3 |  | 3 | 2015-09-24 |  | -30195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-25 | 2015-11-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-10 | Online |  | PRIVATE
2145950 | Woburn | 1801 | 43.009 | PV | 211-H5 | 2016-04-20 | 2016-05-02 | 8 |  | 8 | 2016-05-12 |  | -30360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-31 | 2016-09-06 | 2016-09-06 | [5 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online |  | PRIVATE
2120505 | Woburn | 1801 | 16.7 | PV | 375-H11 | 2015-11-05 | 2015-11-08 | 1 |  | 1 | 2016-01-08 |  | -30271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-23 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
2191380 | Woburn | 1801 | 86.4 | PV | 325-01 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-12-29 |  | -30525 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-30 | 2017-04-06 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
2205487 | Woburn | 1801 | 17.4 | PV | 211-H5 | 2017-02-17 | 2017-02-23 | 3 |  | 3 | 2017-03-16 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-27 | 2017-03-28 | [6 empty] | 0 |  | 0 |  |  | 2017-11-15 | Online |  | PRIVATE
2187695 | Woburn | 1801 | 15.875 | PV | 211-H8 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-09 |  | -30511 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online |  | PRIVATE
2212768 | Woburn | 1801 | 16.7 | PV | 211-H13 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-01 | 2017-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20 | Online
2217434 | Woburn | 1801 | 224.25 | PV | 375-H4 | 2017-05-01 | 2017-05-02 | 1 |  | 1 | 2017-05-26 |  | -30627 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-22 | Online
2207029 | Woburn | 1801 | 576 | PV | 258-1394H2 | 2017-03-09 | 2017-03-10 | 1 |  | 1 | 2017-03-23 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-17 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
2274149 | Woburn | 1801 | 180 | PV | 375-H10 | 2016-10-26 | 2016-11-02 | 5 |  | 5 | 2016-12-06 |  | -30508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2018-08-23 | Online
2277867 | Woburn | 1801 | 130 | PV | 258-1394-H1 | 2018-03-07 | 2018-05-10 | 46 |  | 46 | 2018-05-22 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-09 | 2018-08-22 | [6 empty] | 0 |  | 0 |  |  | 2018-09-24 | Online
2264643 | Woburn | 1801 | 50 | PV | 211-H6 | 2018-01-26 | 2018-02-15 | 14 |  | 14 | 2018-02-27 |  | -30818 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | 2018-05-18 | [6 empty] | 0 |  | 0 |  |  | 2018-10-19 | Online
2261351 | Woburn | 1801 | 15.2 | PV | 375-H12 | 2018-01-03 | 2018-01-29 | 18 |  | 18 | 2018-02-01 |  | -30800 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | [7 empty] | 0 |  | 0 |  |  | 2019-09-27 | Online
2330259 | Woburn | 1801 | 233.2 | PV | 375-H3 | 2019-03-05 | 2019-03-08 | 3 |  | 3 | 2019-03-18 |  | -31092 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-12 | Online
2289155 | Woburn | 1801 | 15.34 | PV | 211-H10 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2322181 | Woburn | 1801 | 15.2 | PV | 375-H12 | 2018-12-28 | 2019-01-16 | 13 |  | 13 | 2019-01-25 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
2300919 | Woburn | 1801 | 15.2 | PV | 211-H13 | 2018-09-07 | 2018-09-25 | 12 |  | 12 | 2018-10-11 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  | 2020-03-24 | Online |  | Private
2325824 | Woburn | 1801 | 250 | PV | 211-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
2343564 | Woburn | 1801 | 50 | PV | 211-H2 | 2019-05-14 | 2019-05-22 |  |  |  | 2019-06-13 | [24 empty] | 2019-07-16 | [12 empty] | 2020-07-21 | Online
2325785 | Woburn | 1801 | 216 | PV | 375-H14 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-19 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
2352774 | Woburn | 1801 | 100 | PV | 211-H6 | 2019-07-18 | 2019-07-19 |  |  |  | 2019-08-02 | [24 empty] | 2019-09-20 | [12 empty] | 2020-10-06 | Online
2354633 | Woburn | 1801 | 100 | PV | 375-H14 | 2019-07-18 | 2019-07-19 |  |  |  | 2019-08-14 | [24 empty] | 2019-10-04 | [12 empty] | 2020-10-06 | Online
2360146 | Woburn | 1801 | 240 | PV | TBD | 2019-08-29 | 2019-09-04 |  |  |  | 2019-09-19 | [24 empty] | 2020-01-30 | [12 empty] | 2020-10-29 | Online
2339665 | Woburn | 1801 | 66.6 | PV | 375-H1 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-21 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
2326814 | Woburn | 1801 | 233.1 | PV | 211-H6 | 2019-02-12 | 2019-02-12 | 0 |  | 0 | 2019-02-25 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
2307642 | Woburn | 1801 | 208.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online |  | Private
2287543 | Woburn | 1801 | 1310 | PV | 375-H1 | 2018-07-02 | 2018-07-03 | 1 |  | 1 | 2018-07-19 |  | -30920 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
2343632 | Woburn | 1801 | 66.6 | PV | 211-H6 | 2019-05-28 | 2019-05-28 |  |  |  | 2019-06-06 | [24 empty] | 2019-06-18 | [12 empty] | 2021-01-20 | Online
2340946 | Woburn | 1801 | 480 | PV | TBD | 2019-05-08 | 2019-05-14 | 4 |  | 4 | 2019-05-22 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-18 | Online
2311476 | Woburn | 1801 | 249.8 | PV | 211-H2 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-08 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online |  | Private
2291296 | Woburn | 1801 | 16.56 | PV | 375-H14 | 2018-05-22 | 2018-07-26 | 47 |  | 47 | 2018-08-10 | 2018-12-10 | 86 |  | 86 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
2196195 | Woburn | 1801 | 119.9 | PV | 375-H3 | 2016-12-16 | 2016-12-27 | 7 |  | 7 | 2017-01-11 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-05-16 |  |  | EXP |  |  |  | 0 |  | 0 | [5 empty] | PRIVATE | Y
2199093 | Woburn | 1801 | 8.35 | PV | 211-H2 | 2017-01-17 | 2017-01-20 | 3 |  | 3 | 2017-01-31 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2204382 | Woburn | 1801 | 17.4 | PV | 211-H10 | 2017-02-17 | 2017-02-23 | 3 |  | 3 | 2017-03-06 |  | -30569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2211603 | Woburn | 1801 | 20.35 | PV | 211-H8 | 2017-03-30 | 2017-04-10 | 7 |  | 7 | 2017-04-24 |  | -30603 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2234836 | Woburn | 1801 | 16.7 | PV | 375-H12 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30703 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-12-05 | [6 empty] | 0 |  | 0
2234838 | Woburn | 1801 | 16.7 | PV | 375-H14 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30703 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2260286 | Woburn | 1801 | 23.4 | PV | 325-03 | 2017-12-26 | 2018-01-05 | 8 |  | 8 | 2018-01-26 |  | -30796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2290688 | Woburn | 1801 | 16.42 | PV | 211-H8 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-07 |  | -30933 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
2291058 | Woburn | 1801 | 15.2 | PV | 391-H11 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-09 |  | -30935 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
2298290 | Woburn | 1801 | 924 | PV | 258-1394-H1 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
2298553 | Woburn | 1801 | 490 | PV | 258-1394H8 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online
2304049 | Woburn | 1801 | 15.2 | PV | 375-H14 | 2018-10-09 | 2018-10-12 | 3 |  | 3 | 2018-10-31 |  | -30994 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2308000 | Woburn | 1801 | 333.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2325016 | Woburn | 1801 | 243.1 | PV | 375-H3 | 2018-12-26 | 2019-02-07 | 31 |  | 31 | 2019-02-13 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-16 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
2341172 | Woburn | 1801 | 166.5 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-08 | [7 empty] | 0 |  | 0
2341237 | Woburn | 1801 | 249.8 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2349171 | Woburn | 1801 | 333 | PV | TBD | 2019-06-21 | 2019-06-24 |  |  |  | 2019-07-15 | [24 empty] | 2019-09-05
2366729 | Woburn | 1801 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 |  |  |  | 2019-11-05 | [24 empty] | 2020-01-17 | [12 empty] | 2022-04-13 | Online
2375623 | Woburn | 1801 | 150 | PV | TBD | 2019-12-02 | 2019-12-05 |  |  |  | 2019-12-20 | [24 empty] | 2020-01-28
2381571 | Woburn | 1801 | 3623 | PV | TBD | 2019-12-05 | 2019-12-09 |  |  |  | 2020-01-14 | [24 empty] | 2021-05-24
2403255 | Woburn | 1801 | 63.3 | PV | TBD | 2020-06-01 | 2020-06-04 |  |  |  | 2020-06-23 | [24 empty] | 2020-07-07
2411000 | Woburn | 1801 | 15.2 | PV | TBD | 2020-06-08 | 2020-07-28 |  |  |  | 2020-08-17 | [24 empty] | 2020-08-20
4305278 | Woburn | 1801 | 111.5 | PV & Battery | TBD | 2020-09-08 | 2020-09-11 |  |  |  | 2020-10-01 | [24 empty] | 2020-11-23 | [12 empty] | 2023-04-03 | Online
4557000 | Woburn | 1801 | 57.6 | PV | TBD | 2020-10-27 | 2020-11-04 |  |  |  | 2020-12-04 | [24 empty] | 2020-12-15 | [12 empty] | 2022-02-16 | Online
2128688 | Woburn | 1801 | 53 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2146188 | Woburn | 1801 | 15.2 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5099394 | Woburn | 1801 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-12 | [12 empty] | 2022-07-27 | Online
ESMAEX-00082 | Woburn | 1801 | 17.4 | PV | 533-H9 | 2021-04-28 | 2021-05-14 | [28 empty] | 2021-06-21 | [12 empty] | 2022-02-04 | Online |  |  | Y
ESMAEX-00141 | Woburn | 1801 | 20 | PV & Battery | 391-H11 | 2021-05-20 | 2021-06-11 | [28 empty] | 2021-08-27 | [12 empty] | 2021-12-07 | Online |  |  | Y
ESMAEX-00380 | Woburn | 1801 | 216 | PV | TBD | 2021-09-02 | 2021-09-22 | [28 empty] | 2021-12-29 | [12 empty] | 2022-05-19 | Online |  |  | Y
ESMAEX-00486 | Woburn | 1801 | 109.8 | PV | 211-H2 | 2021-10-10 | 2021-11-03 | [28 empty] | 2021-12-09 | [12 empty] | 2022-06-09 | Online |  |  | Y
ESMAEX-00880 | Woburn | 1801 | 15.2 | PV | 325-03 | 2022-03-04 | 2022-03-29 | [28 empty] | 2022-04-20 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01164 | Woburn | 1801 | 250 | PV & Battery | 375-H6 | 2022-05-10 | 2022-06-02 | [28 empty] | 2022-08-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-01344 | Woburn | 1801 | 7.38 | PV & Battery | 211-H8 | 2022-07-05 | 2022-07-21 | [28 empty] | 2022-09-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01459 | Woburn | 1801 | 6 | PV | 375-H6 | 2022-08-10 | 2022-09-01 | [28 empty] | 2022-09-14 | [12 empty] | 2023-02-07 | Online |  |  | Y
ESMAEX-01491 | Woburn | 1801 | 217.3 | PV & Battery | 375-H3 | 2022-08-19 | 2022-09-27 | [28 empty] | 2023-03-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-01493 | Woburn | 1801 | 237.5 | PV & Battery | 375-H3 | 2022-08-19 | 2022-09-09 | [28 empty] | 2023-03-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-01562 | Woburn | 1801 | 210 | PV & Battery | 375-H9 | 2022-09-09 | 2022-09-27 | [28 empty] | 2023-02-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01720 | Woburn | 1801 | 15.2 | PV & Battery | 375-H14 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01993 | Woburn | 1801 | 15.2 | PV & Battery | 375-H14 | 2023-01-10 | 2023-01-31 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02100 | Woburn | 1801 | 35.1 | Battery | 211-H5 | 2023-02-01 | 2023-02-16 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02186 | Woburn | 1801 | 150 | Battery | 211-H2 | 2023-02-22 | 2023-04-04 | [42 empty] | In Queue |  |  | Y
ESMAEX-02195 | Woburn | 1801 | 66.66 | PV & Battery | 211-H2 | 2023-02-23 | 2023-03-02 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02255 | Woburn | 1801 | 117.3 | PV | TBD | 2023-03-09 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02432 | Woburn | 1801 | 100 | PV | 375-H6 | 2023-04-29 | [43 empty] | In Queue |  |  | Y
2235287 | Framingham | 1802 | 42 | PV | 240-H3 | 2017-08-16 | 2017-08-22 | 4 |  | 4 | 2017-09-18 |  | -30705 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2018-05-29 | Online
2199843 | Burlington | 1803 | 182.65 | PV | 391-H15 | 2017-01-11 | 2017-01-18 | 4 |  | 4 | 2017-02-02 |  | -30548 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-21 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-24 | Online
2193629 | Burlington | 1803 | 19.75 | PV | 391-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2016-01-05 |  | -30268 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-03-29 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online |  | PRIVATE
2250081 | Burlington | 1803 | 34.8 | PV | 391-H2 | 2017-11-09 | 2017-11-14 | 3 |  | 3 | 2017-12-06 |  | -30760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-03-22 | [6 empty] | 0 |  | 0 |  |  | 2018-06-07 | Online
2289156 | Burlington | 1803 | 15.2 | PV | 391-H7 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-11-25 | Online
2356435 | Burlington | 1803 | 130 | PV | 391-H2 | 2019-08-01 | 2019-08-07 |  |  |  | 2019-08-27 | [24 empty] | 2019-10-10 | [12 empty] | 2020-04-02 | Online
2385267 | Burlington | 1803 | 19.76 | PV | 346-1395H1 | 2020-01-17 | 2020-01-27 |  |  |  | 2020-02-11 | [37 empty] | 2020-09-09 | Online
2391862 | Burlington | 1803 | 19.12 | PV & Battery | TBD | 2020-03-09 | 2020-03-16 |  |  |  | 2020-04-01 | [24 empty] | 2020-07-28 | [12 empty] | 2020-11-06 | Online
4659441 | Burlington | 1803 | 23.49 | PV | TBD | 2020-12-07 | 2020-12-14 |  |  |  | 2021-01-05 | [24 empty] | 2021-03-09 | [12 empty] | 2021-05-07 | Online
2298565 | Burlington | 1803 | 990 | PV | 391-H16 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0
2298567 | Burlington | 1803 | 990 | PV | 391-H9 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2140576 | Burlington | 1803 | 16.72 | PV | 391-H6 | 2016-03-29 | 2016-04-05 | 5 |  | 5 | 2016-04-14 |  | -30340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-12 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2213109 | Burlington | 1803 | 176.4 | PV | 211-H13 | 2017-03-10 | 2017-04-11 | 22 |  | 22 | 2017-05-01 |  | -30608 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2212942 | Burlington | 1803 | 16.95 | PV | 391-H7 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-28 |  | -30607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-27 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2217047 | Burlington | 1803 | 180 | PV | 346-1395H1 | 2017-04-21 | 2017-05-01 | 6 |  | 6 | 2017-05-24 |  | -30625 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2236911 | Burlington | 1803 | 27.9 | PV | 346-1395H1 | 2017-09-01 | 2017-09-06 | 2 |  | 2 | 2017-09-27 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | [7 empty] | 0 |  | 0
2288772 | Burlington | 1803 | 17.49 | PV | 391-H6 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-27 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2305734 | Burlington | 1803 | 800 | PV | 391-H5 | 2018-10-25 | 2018-11-08 | 10 |  | 10 | 2018-11-08 |  | -31000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2305732 | Burlington | 1803 | 400 | PV | 391-H5 | 2018-11-06 | 2018-11-08 | 2 |  | 2 | 2018-11-08 |  | -31000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2351221 | Burlington | 1803 | 999 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-07-25 | [24 empty] | 2019-10-23 | [12 empty] | 2021-08-25 | Online
2409940 | Burlington | 1803 | 20.4 | PV & Battery | 346-1395H1 | 2020-06-29 | 2020-07-28 |  |  |  | 2020-08-11 | [24 empty] | 2020-10-01 | [12 empty] | 2021-06-15 | Online
2409880 | Burlington | 1803 | 95.5 | PV | TBD | 2020-07-22 | 2020-07-23 |  |  |  | 2020-08-14 | [24 empty] | 2020-11-05
4280698 | Burlington | 1803 | 30.2 | PV & Battery | TBD | 2020-07-22 | 2020-08-18 |  |  |  | 2020-09-25 | [24 empty] | 2020-11-05 | [12 empty] | 2021-06-11 | Online
4615024 | Burlington | 1803 | 58.2 | PV | TBD | 2020-11-02 | 2020-11-18 |  |  |  | 2020-12-23 | [24 empty] | 2021-02-09 | [12 empty] | 2021-07-26 | Online
4878461 | Burlington | 1803 | 20 | PV & Battery | 391-H7 | 2020-12-14 | 2021-01-11 |  |  |  | 2021-01-28 | [24 empty] | 2021-01-29 | [12 empty] | 2021-12-01 | Online
5317803 | Burlington | 1803 | 35.2 | PV & Battery | TBD | 2020-12-14 | 2021-03-12 |  |  |  | 2021-03-31 | [24 empty] | 2021-05-12
5447287 | Burlington | 1803 | 17.6 | Battery | TBD | 2021-03-17 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2021-06-17
5403892 | Burlington | 1803 | 52.2 | PV | TBD | 2021-03-23 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-05-26 | [13 empty] | Withdrawn
ESMAEX-00159 | Burlington | 1803 | 125 | PV | 391-H10 | 2021-06-01 | 2021-06-18 | [28 empty] | 2021-08-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-00174 | Burlington | 1803 | 233.1 | PV | 391-H12 | 2021-06-08 | 2021-06-24 | [28 empty] | 2021-09-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-00175 | Burlington | 1803 | 499.5 | PV | 391-H12 | 2021-06-08 | 2021-06-25 | [28 empty] | 2022-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-00302 | Burlington | 1803 | 19.825 | PV | 375-H14 | 2021-08-11 | 2021-09-08 | [28 empty] | 2021-10-12 | [12 empty] | 2022-03-07 | Online |  |  | Y
ESMAEX-00337 | Burlington | 1803 | 138.4 | PV | TBD | 2021-08-23 | 2021-09-21 | [28 empty] | 2021-12-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-00344 | Burlington | 1803 | 17.6 | PV & Battery | 346-1395H1 | 2021-08-24 | 2021-09-13 | [28 empty] | 2021-09-22 | [12 empty] | 2022-04-27 | Online |  |  | Y
ESMAEX-00464 | Burlington | 1803 | 15.2 | PV & Battery | 391-H6 | 2021-10-01 | 2021-12-28 | [28 empty] | 2022-01-18 | [12 empty] | 2022-03-17 | Online |  |  | Y
ESMAEX-00554 | Burlington | 1803 | 20 | PV & Battery | 391-H7 | 2021-10-28 | 2021-11-18 | [28 empty] | 2021-12-10 | [12 empty] | 2022-01-21 | Online |  |  | Y
ESMAEX-00978 | Burlington | 1803 | 1000 | PV & Battery | 487-1378H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-00979 | Burlington | 1803 | 1000 | PV & Battery | 487-1376H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-00980 | Burlington | 1803 | 1000 | PV & Battery | 487-1376H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-00981 | Burlington | 1803 | 1000 | PV & Battery | 487-1376H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-00982 | Burlington | 1803 | 1000 | PV & Battery | 487-1376H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-00983 | Burlington | 1803 | 1000 | PV & Battery | 487-1376H | 2022-04-19 | [43 empty] | In Queue |  |  | Y
ESMAEX-01115 | Burlington | 1803 | 6.4 | Battery | 391-H7 | 2022-04-26 | 2022-05-18 | [28 empty] | 2022-06-20 | [12 empty] | 2022-09-09 | Online |  |  | Y
ESMAEX-01211 | Burlington | 1803 | 10.03 | PV & Battery | 346-1395H1 | 2022-05-23 | 2022-06-14 | [28 empty] | 2022-07-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01213 | Burlington | 1803 | 15.2 | PV & Battery | 391-H16 | 2022-05-24 | 2022-06-17 | [28 empty] | 2022-08-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01320 | Burlington | 1803 | 15.3 | PV | 391-H7 | 2022-06-24 | 2022-07-13 | [28 empty] | 2022-08-15 | [12 empty] | 2023-01-05 | Online |  |  | Y
ESMAEX-01364 | Burlington | 1803 | 15.2 | PV & Battery | 391-H16 | 2022-07-12 | 2022-08-01 | [28 empty] | 2022-09-13 | [12 empty] | 2023-02-27 | Online |  |  | Y
ESMAEX-01366 | Burlington | 1803 | 11.4 | PV | 346-1395H1 | 2022-07-12 | 2022-08-10 | [28 empty] | 2022-09-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01528 | Burlington | 1803 | 32.85 | PV & Battery | 391-H2 | 2022-08-30 | 2022-09-22 | [28 empty] | 2022-09-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01605 | Burlington | 1803 | 43.2 | PV & Battery | 346-1395H1 | 2022-09-19 | 2022-10-07 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01653 | Burlington | 1803 | 15.2 | PV & Battery | 346-1395H1 | 2022-10-03 | 2022-10-25 | [28 empty] | 2022-11-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01701 | Burlington | 1803 | 15.2 | PV | 391-H7 | 2022-10-20 | 2022-11-10 | [28 empty] | 2022-12-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01736 | Burlington | 1803 | 21.12 | PV | 391-H6 | 2022-10-28 | 2023-03-22 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01776 | Burlington | 1803 | 10.2 | PV & Battery | TBD | 2022-11-08 | 2022-12-05 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01805 | Burlington | 1803 | 15.2 | PV & Battery | 391-H7 | 2022-11-14 | 2022-12-08 | [28 empty] | 2023-01-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01870 | Burlington | 1803 | 22.272 | PV | 391-H6 | 2022-11-30 | 2023-02-06 | [28 empty] | 2023-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-02202 | Burlington | 1803 | 15.2 | PV & Battery | 391-H6 | 2023-02-24 | 2023-03-21 | [28 empty] | 2023-04-21 | [13 empty] | In Queue |  |  | Y
2353830 | Burlington | 1803 | 43.2 | PV | TBD | 2019-07-16 | 2019-07-19 |  |  |  | 2019-08-08 | [24 empty] | 2019-10-10 | [12 empty] | 2020-04-21 | Online
2377387 | Burlington | 1803 | 19.57 | PV & Battery | TBD | 2019-11-22 | 2019-11-26 |  |  |  | 2020-01-03
2117752 | Woburn | 1810 | 42.3 | PV | 211-H2 | 2015-12-01 | 2015-12-28 | 19 |  | 19 | 2016-01-05 |  | -30268 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2355861 | Burlington | 1821 | 1000 | PV & Battery | TBD | 2019-07-30 | 2019-08-01 |  |  |  | 2019-08-22 | [24 empty] | 2019-11-27 | [13 empty] | Withdrawn
5099581 | Hopkinton | 1848 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 |  |  |  | 2021-03-11 | [24 empty] | 2021-04-01 | [12 empty] | 2022-08-22 | Online
5354616 | Natick | 1860 | 17.6 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-04-19 | [12 empty] | 2021-12-17 | Online
2171655 | Woburn | 1888 | 466.2 | PV | 375-H3 | 2016-06-01 | 2016-09-07 | 70 |  | 70 | 2016-09-28 |  | -30459 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 |  | -30576 |  | 0 |  |  | 0 |  | 0 | 2017-08-18 | 2017-08-23 | [6 empty] | 0 |  | 0 |  |  | 2018-02-26 | Online
2305374 | Winchester | 1890 | 60 | PV | 211-H1 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30998 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online |  | Private
2361879 | Winchester | 1890 | 25.2 | PV & Battery | 211-H3 | 2019-09-03 | 2019-09-17 |  |  |  | 2019-10-02 | [24 empty] | 2019-11-14 | [12 empty] | 2020-04-29 | Online
2368750 | Winchester | 1890 | 35.2 | PV | TBD | 2019-10-18 | 2019-10-29 |  |  |  | 2019-11-14 | [24 empty] | 2020-01-02 | [12 empty] | 2020-05-29 | Online
2388617 | Winchester | 1890 | 17.6 | PV & Battery | TBD | 2020-01-16 | 2020-02-19 |  |  |  | 2020-03-27 | [24 empty] | 2020-04-20 | [12 empty] | 2020-06-12 | Online
2367405 | Winchester | 1890 | 15.2 | PV | 211-H10 | 2019-08-28 | 2019-10-16 |  |  |  | 2019-11-05 | [24 empty] | 2019-11-29 | [12 empty] | 2020-07-27 | Online
2389481 | Winchester | 1890 | 17.6 | PV & Battery | 211-H1 | 2020-02-20 | 2020-02-25 |  |  |  | 2020-03-11 | [37 empty] | 2020-07-27 | Online
2330512 | Winchester | 1890 | 37.8 | PV | 211-H1 | 2019-03-01 | 2019-03-11 | 6 |  | 6 | 2019-03-22 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09 | Online
2349404 | Winchester | 1890 | 108 | PV | 211-H4 | 2019-06-21 | 2019-06-26 |  |  |  | 2019-07-12 | [24 empty] | 2019-07-17 | [12 empty] | 2020-10-06 | Online
2387543 | Winchester | 1890 | 20 | PV | 211-H10 | 2020-04-14 | 2020-02-21 |  |  |  | 2020-03-02 | [24 empty] | 2020-09-14 | [12 empty] | 2020-12-17 | Online
2187499 | Winchester | 1890 | 60 | PV | 211-H4 | 2016-11-07 | 2016-11-09 | 2 |  | 2 | 2016-12-08 |  | -30510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
4619563 | Winchester | 1890 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-24 |  |  |  | 2020-12-23 | [24 empty] | 2021-01-06 | [12 empty] | 2021-06-07 | Online
4668160 | Winchester | 1890 | 25 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-02-09 | [12 empty] | 2021-06-07 | Online
5113444 | Winchester | 1890 | 18 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-28
ESMAEX-00169 | Winchester | 1890 | 2.03 | PV | 211-H7XY | 2021-06-07 | 2021-06-22 | [28 empty] | 2021-08-10 | [12 empty] | 2021-12-17 | Online |  |  | Y
ESMAEX-00318 | Winchester | 1890 | 17.58 | PV & Battery | 211-07 | 2021-08-17 | 2021-10-15 | [28 empty] | 2021-11-23 | [12 empty] | 2022-01-14 | Online |  |  | Y
ESMAEX-00825 | Winchester | 1890 | 19 | PV & Battery | 211-H4 | 2022-02-09 | 2022-02-28 | [28 empty] | 2022-03-31 | [12 empty] | 2023-04-20 | Online |  |  | Y
ESMAEX-00948 | Winchester | 1890 | 15.2 | PV & Battery | 211-H11 | 2022-03-19 | 2022-05-13 | [28 empty] | 2022-05-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01017 | Winchester | 1890 | 15.2 | PV & Battery | 211-H10 | 2022-04-06 | 2022-04-21 | [28 empty] | 2022-05-05 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01203 | Winchester | 1890 | 9.984 | PV & Battery | 211-H6 | 2022-05-20 | 2022-06-09 | [28 empty] | 2022-08-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01673 | Winchester | 1890 | 17.6 | PV & Battery | 211-H1 | 2022-10-11 | 2022-11-10 | [28 empty] | 2022-12-27 | [12 empty] | 2023-03-10 | Online |  |  | Y
ESMAEX-02166 | Winchester | 1890 | 220 | Battery | 211-H13 | 2023-02-15 | 2023-03-02 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02249 | Winchester | 1890 | 8.4 | PV | 211-H3 | 2023-03-08 | 2023-03-28 | [42 empty] | In Queue |  |  | Y
2164625 | Bellingham | 2019 | 497.5 | PV | 65-H4 | 2016-06-10 | 2016-07-25 | 31 |  | 31 | 2016-08-22 |  | -30432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-12 | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-07-28 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18 | Online
2292179 | Bellingham | 2019 | 6310 | PV & Battery | 65-H4 | 2018-08-03 | 2018-08-07 | 2 |  | 2 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2021-11-30 | Online
2355844 | Bellingham | 2019 | 250 | PV | TBD | 2019-07-15 | 2019-08-06 |  |  |  | 2019-08-22 | [24 empty] | 2019-09-19
2390335 | Bellingham | 2019 | 15.2 | PV | 65-H4 | 2020-03-05 | 2020-03-09 | [42 empty] | Withdrawn
4534965 | Bellingham | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 |  |  |  | 2020-12-01
4535505 | Bellingham | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 |  |  |  | 2020-12-01
4581275 | Bellingham | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 |  |  |  | 2020-12-09
ESMAEX-00298 | Bellingham | 2019 | 9992 | Battery | 65-H4 | 2021-08-10 | 2021-10-18 | [42 empty] | In Queue |  |  | Y
ESMAEX-00901 | Bellingham | 2019 | 15.2 | PV & Battery | 65-H4 | 2022-03-11 | 2022-03-31 | [28 empty] | 2022-04-21 | [12 empty] | 2022-10-22 | Online |  |  | Y
ESMAEX-01253 | Bellingham | 2019 | 20 | PV & Battery | 65-H4 | 2022-06-02 | 2022-06-20 | [28 empty] | 2022-07-27 | [12 empty] | 2022-11-01 | Online |  |  | Y
ESMAEX-02191 | Bellingham | 2019 | 6 | Battery | 65-H4 | 2023-02-22 | 2023-03-21 | [28 empty] | 2023-04-06 | [13 empty] | In Queue |  |  | Y
2102821 | Canton | 2021 | 324.6 | PV | 470-H8 | 2015-10-09 | 2016-10-16 | 265 |  | 265 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-25 | 2016-05-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online |  | PRIVATE
2195719 | Canton | 2021 | 128 | PV | 470-H4 | 2016-12-09 | 2016-12-13 | 2 |  | 2 | 2017-01-09 |  | -30531 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20 | Online
2253056 | Canton | 2021 | 432.9 | PV | 470-H4 | 2017-11-24 | 2017-12-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
2214562 | Canton | 2021 | 462 | PV | 470-H11 | 2017-04-13 | 2017-04-14 | 1 |  | 1 | 2017-05-08 |  | -30613 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -44 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2018-12-27 |  | 2018-12-28 | Online
2212756 | Canton | 2021 | 330 | PV | 470-H1 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-28 |  | -30607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -44 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-26 | Online
2261355 | Canton | 2021 | 288 | PV | 269-1321H2 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-01 | 2018-11-20 | 208 |  | 208 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 | [6 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online |  | Private
2313802 | Canton | 2021 | 100 | PV | 269-1320H1 | 2018-12-04 | 2018-12-06 | 2 |  | 2 | 2018-12-21 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
2336013 | Canton | 2021 | 200.4 | PV | 269-1320H1 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31118 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
2273880 | Canton | 2021 | 610 | PV | 470-H1 | 2018-04-05 | 2018-04-12 | 5 |  | 5 | 2018-05-01 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-03-12 | Online
2250080 | Canton | 2021 | 964 | PV | 470-H10 | 2017-10-18 | 2017-11-15 |  |  |  | 2017-12-06 | [24 empty] | 2019-01-18 | [12 empty] | 2020-07-23 | Online
2337333 | Canton | 2021 | 133.6 | PV | 269-1320H1 | 2019-02-11 | 2019-04-08 | 40 |  | 40 | 2019-05-02 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
2304052 | Canton | 2021 | 496.2 | PV | 269-1321H | 2018-10-12 | 2018-10-12 | 0 |  | 0 | 2018-10-31 |  | -30994 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2020-12-08 | Online |  | Private
2395122 | Canton | 2021 | 15.2 | PV | TBD | 2020-03-18 | 2020-04-09 |  |  |  | 2020-04-23 | [24 empty] | 2020-05-28 | [12 empty] | 2021-02-04 | Online
2345953 | Canton | 2021 | 250 | PV | TBD | 2019-05-30 | 2019-06-07 |  |  |  | 2019-06-20 | [24 empty] | 2020-06-23 | [12 empty] | 2021-03-02 | Online
2273509 | Canton | 2021 | 240 | PV | 269-1321H2 | 2018-02-20 | 2018-04-12 | 37 |  | 37 | 2018-04-26 | 2018-04-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-12-13 | [6 empty] | 0 |  | 0
4529021 | Canton | 2021 | 166.5 | PV | 269-1321H2 | 2020-09-28 | 2020-09-28 | 0 |  | 0 | 2020-09-28 |  | -31492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-11-15 | Online |  | Private
2182736 | Canton | 2021 | 980 | PV | 470-H7 | 2014-06-17 | 2014-06-17 | 0 |  | 0 | 2017-06-30 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-20 | 2014-10-14 | -6 |  | 0 |  |  | 0 |  | 0 | 2016-09-09 | 2016-09-09 | [6 empty] | 0 |  | 0
2093030b | Canton | 2021 | 990 | PV | 470-H7 | 2015-08-31 | 2015-09-04 | 4 |  | 4 | 2015-09-09 |  | -30184 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  |  | In Queue
2130083 | Canton | 2021 | 495.72 | PV | 470-H11 | 2016-01-12 | 2016-01-24 | 8 |  | 8 | 2016-02-23 |  | -30303 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2016-06-10 | 30380 |  | 30380 |  |  | 0 |  | 0 | 2017-07-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2199637 | Canton | 2021 | 16.7 | PV | 470-H11 | 2017-01-11 | 2017-01-20 | 6 |  | 6 | 2017-02-01 |  | -30547 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 | [5 empty] | PRIVATE
2207988 | Canton | 2021 | 19.8 | PV | 269-1320H1 | 2017-03-06 | 2017-03-20 | 10 |  | 10 | 2017-03-30 |  | -30587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2236306 | Canton | 2021 | 208 | PV | 470-H11 | 2017-08-24 | 2017-08-30 | 4 |  | 4 | 2017-09-22 |  | -30709 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2302390 | Canton | 2021 | 3992 | PV | 269-1321H | 2018-09-28 | 2018-10-03 | 3 |  | 3 | 2018-10-19 |  | -30986 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online |  | Private
2304257 | Canton | 2021 | 350 | PV | 470-h7 | 2018-10-10 | 2018-10-18 | 6 |  | 6 | 2018-11-01 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2321814 | Canton | 2021 | 132 | PV | 269-1320H1 | 2018-12-18 | 2019-01-09 | 16 |  | 16 | 2019-01-23 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-29 | [7 empty] | 0 |  | 0
2320445 | Canton | 2021 | 3240 | PV | 269-1320H1 | 2018-12-19 | 2018-12-26 | 5 |  | 5 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2329096 | Canton | 2021 | 1100 | PV | 269-1320H1 | 2019-02-06 | 2019-02-28 | 16 |  | 16 | 2019-03-12 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2345712 | Canton | 2021 | 688 | PV & Battery | 269-1320H1 | 2019-04-26 | 2019-06-06 | 29 |  | 29 | 2019-06-20 |  | -31160 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2346246 | Canton | 2021 | 100 | PV | TBD | 2019-06-06 | 2019-06-10 |  |  |  | 2019-06-24 | [24 empty] | 2019-08-19 | [13 empty] | Withdrawn
2370546 | Canton | 2021 | 495.8 | PV | TBD | 2019-11-04 | 2019-11-12 |  |  |  | 2019-11-27 | [24 empty] | 2020-07-13
2370020 | Canton | 2021 | 133.2 | PV | TBD | 2019-11-07 | 2019-11-08 |  |  |  | 2019-11-25 | [24 empty] | 2020-02-28
2397898 | Canton | 2021 | 499 | PV & Battery | TBD | 2020-04-29 | 2020-04-30 |  |  |  | 2020-05-18 | [24 empty] | 2020-07-27
2409650 | Canton | 2021 | 21.4 | PV & Battery | TBD | 2020-07-20 | 2020-07-20 |  |  |  | 2020-08-04 | [24 empty] | 2020-09-03 | [12 empty] | 2021-07-26 | Online
2410727 | Canton | 2021 | 249.8 | PV | 470-H7 | 2020-07-29 | 2020-07-29 | 0 |  | 0 | 2020-07-29 |  | -31449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
2412573 | Canton | 2021 | 2660 | PV & Battery | TBD | 2020-07-29 | 2020-08-17 |  |  |  | 2020-08-31 | [38 empty] | Withdrawn
4350632 | Canton | 2021 | 35.2 | PV & Battery | TBD | 2020-09-08 | 2020-09-22 |  |  |  | 2020-10-08 | [24 empty] | 2020-12-24
4470982 | Canton | 2021 | 245 | PV | TBD | 2020-10-08 | 2020-10-19 |  |  |  | 2020-11-12 | [24 empty] | 2021-06-07
4503033 | Canton | 2021 | 200 | PV | TBD | 2020-10-21 | 2020-10-22 |  |  |  | 2020-11-23 | [24 empty] | 2021-03-12
5243871 | Canton | 2021 | 499 | PV & Battery | TBD | 2020-12-30 | 2021-03-02 |  |  |  | 2021-03-22 | [24 empty] | 2022-06-22
4849001 | Canton | 2021 | 53.2 | PV | TBD | 2021-01-04 | 2021-01-07 |  |  |  | 2021-01-25 | [24 empty] | 2021-04-06 | [12 empty] | 2021-09-01 | Online
5057342 | Canton | 2021 | 7.6 | PV | TBD | 2021-01-27 | 2021-02-05 |  |  |  | 2021-02-24 | [24 empty] | 2021-03-15 | [13 empty] | Withdrawn
5113853 | Canton | 2021 | 18 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 |  |  |  | 2021-03-08 | [25 empty] | 2021-04-20 | [11 empty] | 2022-02-01 | Online
5273636 | Canton | 2021 | 20 | PV & Battery | TBD | 2021-03-02 | 2021-03-08 |  |  |  | 2021-03-23 | [24 empty] | 2021-05-27 | [12 empty] | 2021-09-17 | Online
ESMAEX-00034 | Canton | 2021 | 250 | PV | 470-H11 | 2021-04-07 | 2021-05-03 | [28 empty] | 2021-12-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-00266 | Canton | 2021 | 4999 | Battery | 470-H1 | 2021-08-31 | 2021-09-16 | [42 empty] | In Queue |  |  | Y
ESMAEX-00361 | Canton | 2021 | 100 | PV | 470-H11 | 2021-08-27 | 2021-09-15 | [28 empty] | 2021-12-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00422 | Canton | 2021 | 16 | PV | 470-H11 | 2021-09-17 | 2022-02-01 | [28 empty] | 2022-02-28 | [12 empty] | 2022-06-16 | Online |  |  | Y
ESMAEX-00562 | Canton | 2021 | 8.56 | PV & Battery | 470-H8 | 2021-11-02 | 2021-11-23 | [28 empty] | 2021-12-22 | [12 empty] | 2022-04-14 | Online |  |  | Y
ESMAEX-00606 | Canton | 2021 | 140 | PV | 470-H4 | 2021-11-18 | 2022-01-13 | [28 empty] | 2022-02-24 | [12 empty] | 2023-01-06 | Online |  |  | Y
ESMAEX-00661 | Canton | 2021 | 4999.2 | Battery | 269-1320H1 | 2022-03-09 | 2022-04-05 | [42 empty] | In Queue |  |  | Y
ESMAEX-00665 | Canton | 2021 | 15.2 | PV | 470-H10 | 2021-12-15 | 2022-01-07 | [28 empty] | 2022-02-17 | [12 empty] | 2022-05-12 | Online |  |  | Y
ESMAEX-00681 | Canton | 2021 | 4999.2 | Battery | 470-H4 | 2022-11-29 | 2022-12-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-00947 | Canton | 2021 | 7.6 | PV & Battery | 470-H10 | 2022-03-19 | 2022-04-14 | [28 empty] | 2022-05-12 | [12 empty] | 2023-03-22 | Online |  |  | Y
ESMAEX-00961 | Canton | 2021 | 250 | PV | 269-1320H1 | 2022-06-06 | 2022-06-21 | [28 empty] | 2022-10-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-01176 | Canton | 2021 | 15.2 | PV & Battery | 470-H8 | 2022-05-12 | 2022-07-21 | [28 empty] | 2022-09-13 | [12 empty] | 2022-12-12 | Online |  |  | Y
ESMAEX-01296 | Canton | 2021 | 20.2 | PV & Battery | 470-H9 | 2022-06-15 | 2022-07-13 | [28 empty] | 2022-08-24 | [12 empty] | 2023-02-22 | Online |  |  | Y
ESMAEX-01307 | Canton | 2021 | 15.2 | PV | 269-1320H1 | 2022-06-17 | 2022-07-07 | [28 empty] | 2022-08-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-01770 | Canton | 2021 | 35.2 | PV & Battery | 470-H7 | 2022-11-04 | 2022-11-18 | [28 empty] | 2023-01-06 | [12 empty] | 2023-04-06 | Online |  |  | Y
ESMAEX-01889 | Canton | 2021 | 17.28 | PV | 470-H8 | 2022-12-04 | 2022-12-29 | [28 empty] | 2023-01-05 | [12 empty] | 2023-03-22 | Online |  |  | Y
ESMAEX-02022 | Canton | 2021 | 20.2 | PV & Battery | 470-H9 | 2023-01-13 | 2023-02-01 | [28 empty] | 2023-04-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02029 | Canton | 2021 | 18.585 | PV & Battery | 269-1320H1 | 2023-01-16 | 2023-02-09 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-02175 | Canton | 2021 | 4999 | Other | 269-1320H1 | 2023-03-31 | 2023-04-19 | [42 empty] | In Queue |  |  | N
ESMAEX-02179 | Canton | 2021 | 240 | Battery | 470-H10 | 2023-02-21 | 2023-03-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-02244 | Canton | 2021 | 18.88 | PV | 470-H4 | 2023-03-08 | 2023-03-23 | [28 empty] | 2023-03-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-02281 | Canton | 2021 | 19 | PV | 470-H9 | 2023-03-17 | 2023-04-25 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-02293 | Canton | 2021 | 19 | PV | 470-H6 | 2023-03-21 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02308 | Canton | 2021 | 100 | PV | 470-H4 | 2023-03-24 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02310 | Canton | 2021 | 70 | PV | 470-H4 | 2023-03-24 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02349 | Canton | 2021 | 15.3 | PV | 269-1320H1 | 2023-04-05 | 2023-04-20 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
2324409 | Canton | 2021 | 299.7 | PV | 269-1320H1 | 2019-01-17 |  | -31050 |  | 0 | 2019-02-11 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
2371598 | Canton | 2021 | 325 | Natural Gas | 269-1321H2 | 2019-11-14 | 2019-11-14 |  |  |  | 2019-12-04 | [24 empty] | 2020-10-22
2226367 | Dorchester | 2021 | 56.35 | PV | 143-109H4 | 2017-06-12 | 2017-06-28 | 12 |  | 12 | 2017-07-20 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2388024 | Walpole | 2021 | 20 | PV | TBD | 2020-02-06 | 2020-02-14 |  |  |  | 2020-03-04 | [24 empty] | 2020-04-17 | [12 empty] | 2020-10-28 | Online
2184658 | Dedham | 2026 | 66.6 | PV | 374-04 | 2016-10-31 | 2016-11-01 | 1 |  | 1 | 2016-12-05 |  | -30507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
2181650 | Dedham | 2026 | 150 | CHP | 20-H5 | 2016-10-14 | 2016-10-19 | 3 |  | 3 | 2016-11-16 |  | -30494 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online
2340807 | Dedham | 2026 | 20 | PV | 148-H3 | 2019-05-13 | 2019-05-13 |  |  |  | 2019-05-22 | [24 empty] | 2019-06-12 | [12 empty] | 2019-03-27 | Online
2236710 | Dedham | 2026 | 170 | PV | 20-H6 | 2017-08-31 | 2017-09-05 | 2 |  | 2 | 2017-09-26 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-07 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2019-06-25 | Online
2351423 | Dedham | 2026 | 22.8 | PV | 20-H7 | 2019-07-08 | 2019-07-10 |  |  |  | 2019-07-24 | [24 empty] | 2019-10-09 | [12 empty] | 2020-02-27 | Online
2364473 | Dedham | 2026 | 125 | PV & Battery | 20-H8 | 2019-07-30 | 2019-10-03 |  |  |  | 2019-10-18 | [24 empty] | 2019-11-29 | [12 empty] | 2021-02-12 | Online
2166557 | Dedham | 2026 | 525 | PV | 344-1413H1 | 2016-07-20 | 2016-08-22 | 23 |  | 23 | 2016-08-30 |  | -30438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-20 |  | -30475 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | [7 empty] | 0 |  | 0 |  |  |  | In Queue
2200785 | Dedham | 2026 | 153.2 | PV | 20-H1 | 2017-01-24 | 2017-01-25 | 1 |  | 1 | 2017-02-09 |  | -30553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2223211 | Dedham | 2026 | 135 | CHP | 20-H6 | 2017-05-26 | 2017-06-05 | 5 |  | 5 | 2017-07-06 |  | -30654 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | [7 empty] | 0 |  | 0
2320829 | Dedham | 2026 | 399.6 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-17 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online
2321149 | Dedham | 2026 | 199.8 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-18 |  | -31051 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-11-07 | Online
2321151 | Dedham | 2026 | 119 | PV | 20-H6 | 2018-12-19 | 2018-12-28 | 7 |  | 7 | 2019-01-18 |  | -31051 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
2322394 | Dedham | 2026 | 499.5 | PV | 20-H5 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-28 |  | -31057 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online
2386594 | Dedham | 2026 | 10 | PV & Battery | 20-H7 | 2020-01-29 | 2020-02-04 |  |  |  | 2020-02-24 | [24 empty] | 2020-03-31
5577223 | Dedham | 2026 | 86.4 | PV | TBD | 2021-02-25 | 2021-04-12 |  |  |  | 2021-04-29 | [24 empty] | 2021-05-26 | [12 empty] | 2022-07-08 | Online
5392843 | Dedham | 2026 | 250 | PV | TBD | 2021-03-17 | 2021-03-22 |  |  |  | 2021-05-04 | [24 empty] | 2021-06-04
ESMAEX-00280 | Dedham | 2026 | 86.4 | PV | 148-H3 | 2021-08-02 | 2021-08-13 | [28 empty] | 2022-02-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-00467 | Dedham | 2026 | 17.6 | PV & Battery | 20-H3 | 2021-10-04 | 2021-11-09 | [28 empty] | 2021-12-13 | [12 empty] | 2022-12-13 | Online |  |  | Y
ESMAEX-01429 | Dedham | 2026 | 270 | PV | 13-H1 | 2022-08-03 | 2022-08-19 | [28 empty] | 2022-10-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01430 | Dedham | 2026 | 150 | PV | 20-H1 | 2022-08-03 | 2022-08-19 | [28 empty] | 2022-09-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01768 | Dedham | 2026 | 15.2 | PV & Battery | 456-H4 | 2022-11-04 | 2022-11-22 | [28 empty] | 2022-12-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-01940 | Dedham | 2026 | 15.2 | PV & Battery | 344-1412H1 | 2022-12-21 | 2023-01-17 | [28 empty] | 2023-03-20 | [13 empty] | In Queue |  |  | Y
4575161 | Dedham | 2026 | 4990 | PV & Battery | TBD | 2020-05-07 |  |  |  |  | 2020-09-11
4707682 | Dedham | 2026 | 66.6 | PV | 20-H1 | 2020-12-01 | 2020-12-30 |  |  |  | 2021-01-21 | [24 empty] | 2021-03-24 | [12 empty] | 2022-10-20 | Online
2089416 | Dover | 2030 | 27.75 | PV | 456-H3 | 2015-07-31 | 2015-08-11 | 7 |  | 7 | 2015-08-24 |  | -30172 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-06-15 | [6 empty] | 0 |  | 0 |  |  | 2016-09-15 | Online
2269886 | Dover | 2030 | 25 | PV | 456-H5 | 2018-02-23 | 2018-03-06 | 7 |  | 7 | 2018-04-04 |  | -30844 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2018-07-19 | Online
2363676 | Dover | 2030 | 17.6 | PV & Battery | TBD | 2019-09-20 | 2019-09-26 |  |  |  | 2019-10-10 | [24 empty] | 2019-10-28 | [12 empty] | 2019-01-08 | Online
2320293 | Dover | 2030 | 19.8 | PV | 456-H1 | 2018-12-26 | 2019-01-07 | 8 |  | 8 | 2019-01-14 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-05 | [7 empty] | 0 |  | 0 |  |  | 2019-07-22 | Online
2340724 | Dover | 2030 | 20.2 | PV | 456-H5 | 2019-04-11 | 2019-05-06 | 17 |  | 17 | 2019-05-21 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
2397442 | Dover | 2030 | 17.7 | PV | 456-H3 | 2020-04-30 | 2020-04-30 |  |  |  | 2020-05-11 | [37 empty] | 2020-09-14 | Online
2399904 | Dover | 2030 | 35.2 | PV | TBD | 2020-05-05 | 2020-05-13 |  |  |  | 2020-06-02 | [24 empty] | 2020-06-19 | [12 empty] | 2021-03-09 | Online
4351141 | Dover | 2030 | 20.22 | PV & Battery | 456-H5 | 2020-09-24 | 2020-09-24 |  |  |  | 2020-10-08 | [24 empty] | 2020-12-18 | [12 empty] | 2021-05-14 | Online
2229213 | Dover | 2030 | 28 | PV | 456-H3 | 2017-07-07 | 2017-07-19 | 8 |  | 8 | 2017-08-08 |  | -30677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-13 | [7 empty] | 0 |  | 0
4296074 | Dover | 2030 | 200 | PV | TBD | 2020-09-04 | 2020-09-04 |  |  |  | 2020-09-29 | [24 empty] | 2021-04-22
4325211 | Dover | 2030 | 20 | PV | 456-H5 | 2020-09-11 | 2020-09-18 |  |  |  | 2020-10-05 | [24 empty] | 2021-01-26
4492827 | Dover | 2030 | 36 | PV & Battery | TBD | 2020-10-15 | 2020-10-21 |  |  |  | 2020-11-18 | [24 empty] | 2021-02-02
4664554 | Dover | 2030 | 19.84 | PV & Battery | 456-H5 | 2020-12-14 | 2020-12-14 |  |  |  | 2021-01-05 | [24 empty] | 2021-02-02
4701003 | Dover | 2030 | 20.92 | PV | 456-H5 | 2020-12-14 | 2020-12-29 |  |  |  | 2021-01-13 | [38 empty] | Withdrawn
4661337 | Dover | 2030 | 20 | PV | TBD | 2020-12-22 | 2020-12-22 |  |  |  | 2021-01-05 | [24 empty] | 2021-03-09 | [12 empty] | 2021-06-21 | Online
2130937 | Dover | 2030 | 16.7 | PV | 456-H5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00288 | Dover | 2030 | 10 | Battery | 456-H5 | 2021-08-05 | 2021-08-16 | [28 empty] | 2021-09-21 | [12 empty] | 2022-04-13 | Online |  |  | Y
ESMAEX-00293 | Dover | 2030 | 3.8 | PV | 456-H5 | 2021-08-09 | 2021-08-19 | [28 empty] | 2022-02-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-00316 | Dover | 2030 | 12.685 | PV & Battery | 456-H5 | 2021-08-16 | 2021-09-02 | [28 empty] | 2021-10-27 | [12 empty] | 2022-02-17 | Online |  |  | Y
ESMAEX-00428 | Dover | 2030 | 30 | PV & Battery | 456-H5 | 2021-09-20 | 2021-10-07 | [28 empty] | 2022-02-07 | [12 empty] | 2022-06-14 | Online |  |  | Y
ESMAEX-00500 | Dover | 2030 | 26 | PV | 456-H5 | 2021-10-14 | 2021-11-04 | [28 empty] | 2022-01-19 | [12 empty] | 2022-06-07 | Online |  |  | Y
ESMAEX-00547 | Dover | 2030 | 7.678 | PV & Battery | 456-H5 | 2021-10-27 | 2021-11-18 | [28 empty] | 2022-01-10 | [12 empty] | 2022-07-06 | Online |  |  | Y
ESMAEX-00566 | Dover | 2030 | 10 | Battery | 148-H2 | 2021-11-05 | 2021-11-23 | [28 empty] | 2021-12-13 | [12 empty] | 2023-01-03 | Online |  |  | Y
ESMAEX-00576 | Dover | 2030 | 16.225 | PV | 456-H5 | 2021-11-10 | 2021-11-23 | [28 empty] | 2022-02-07 | [12 empty] | 2022-05-24 | Online |  |  | Y
ESMAEX-00704 | Dover | 2030 | 16.403 | PV | 456-H5 | 2022-01-03 | 2022-01-25 | [28 empty] | 2022-02-28 | [12 empty] | 2022-05-24 | Online |  |  | Y
ESMAEX-01238 | Dover | 2030 | 19.8 | PV & Battery | 456-H5 | 2022-06-01 | 2022-07-13 | [28 empty] | 2022-12-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01288 | Dover | 2030 | 28.8 | PV & Battery | 456-H5 | 2022-06-13 | 2022-07-18 | [28 empty] | 2022-11-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-01313 | Dover | 2030 | 38.904 | PV & Battery | 456-H5 | 2022-06-21 | 2022-10-25 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01373 | Dover | 2030 | 150 | PV | 456-H5 | 2022-07-13 | 2022-08-15 | [28 empty] | 2022-09-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01397 | Dover | 2030 | 15.2 | PV & Battery | 456-H5 | 2022-07-21 | 2022-08-23 | [28 empty] | 2022-10-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01420 | Dover | 2030 | 17.6 | PV | 456-H5 | 2022-08-01 | 2022-08-17 | [28 empty] | 2022-09-23 | [12 empty] | 2022-12-08 | Online |  |  | Y
ESMAEX-01630 | Dover | 2030 | 9 | PV & Battery | 456-H5 | 2022-09-26 | 2022-10-13 | [28 empty] | 2023-01-18 | [12 empty] | 2023-04-21 | Online |  |  | Y
ESMAEX-01734 | Dover | 2030 | 20 | PV & Battery | 456-H5 | 2022-10-27 | 2022-11-16 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01827 | Dover | 2030 | 19.58 | PV | 456-H3 | 2022-11-17 | 2022-12-19 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01930 | Dover | 2030 | 15.37 | PV & Battery | 456-H3 | 2022-12-16 | 2023-01-10 | [28 empty] | 2023-01-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02209 | Dover | 2030 | 25.2 | Battery | 456-H5 | 2023-02-27 | 2023-03-21 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02321 | Dover | 2030 | 15 | Battery | 456-H5 | 2023-03-29 | 2023-04-27 | [42 empty] | In Queue |  |  | Y
ESMAEX-02379 | Dover | 2030 | 17.6 | PV | 148-H3 | 2023-04-14 | [43 empty] | In Queue |  |  | Y
ESMAEX-02425 | Dover | 2030 | 16.2 | PV | 456-H3 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
ESMAEX-02430 | Dover | 2030 | 17.6 | PV | 456-H5 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
4886981 | East Walpole | 2032 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-01 | [12 empty] | 2022-07-27 | Online
ESMAEX-00805 | East Walpole | 2032 | 100 | PV | 146-H8 | 2022-02-03 | 2022-03-16 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-01003 | East Walpole | 2032 | 17.6 | PV & Battery | 146-H4 | 2022-04-04 | 2022-04-21 | [28 empty] | 2022-06-02 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01027 | East Walpole | 2032 | 15.2 | PV & Battery | 146-H4 | 2022-04-06 | 2022-04-28 | [28 empty] | 2022-05-31 | [12 empty] | 2023-03-07 | Online |  |  | Y
ESMAEX-01128 | East Walpole | 2032 | 17.6 | PV & Battery | 135-1319H1 | 2022-04-29 | 2022-05-31 | [28 empty] | 2022-06-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-01149 | East Walpole | 2032 | 9.74 | PV & Battery | 146-H4 | 2022-05-05 | 2022-05-25 | [28 empty] | 2022-06-30 | [12 empty] | 2023-04-18 | Online |  |  | Y
ESMAEX-01964 | East Walpole | 2032 | 15.2 | PV | 146-H4 | 2023-01-05 | 2023-01-23 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
5256722 | East Walpole | 2032 | 15.2 | PV | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-09 | [12 empty] | 2021-08-04 | Online
5483759 | East Walpole | 2032 | 26.4 | PV & Battery | TBD | 2021-03-29 | 2021-04-01 |  |  |  | 2021-04-16 | [24 empty] | 2021-05-13 | [12 empty] | 2021-12-01 | Online
2326033 | East Walpole | 2032 | 2370 | PV | 2-102-604 | 2019-01-29 | 2019-02-11 | 9 |  | 9 | 2019-02-20 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-07-20 | Online
2265026 | Walpole | 2032 | 2370 | PV | 146-H6 | 2018-02-16 | 2018-04-03 | 32 |  | 32 | 2018-03-01 |  | -30820 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-03-01 | 30819 |  | 30819 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2381558 | Walpole | 2032 | 23.8 | PV | TBD | 2019-12-11 | 2019-12-16 |  |  |  | 2020-01-14 | [38 empty] | Withdrawn
2362818 | Foxboro | 2035 | 3900 | PV | TBD | 2019-09-18 | 2019-09-23 |  |  |  | 2019-10-08
ESMAEX-01684 | Green Harbor | 2041 | 20.2 | PV & Battery | 3-27-970 | 2022-10-17 | 2022-11-23 | [28 empty] | 2022-12-15 | [13 empty] | In Queue |  |  | Y
2381120 | Marshfield | 2048 | 4600 | PV & Battery | TBD | 2019-12-18 | 2019-12-26 |  |  |  | 2020-01-10
2237799 | Marshfield | 2050 | 27.5 | PV | 3-25-42J2 | 2017-08-22 | 2017-09-13 | 15 |  | 15 | 2017-10-03 |  | -30716 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-11 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
2311847 | Marshfield | 2050 | 115.44 | PV | 3-24A-24A | 2018-11-28 | 2018-12-11 | 9 |  | 9 | 2018-12-11 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
2387378 | Marshfield | 2050 | 15.1 | PV | 3-24B-24B | 2019-12-23 | 2020-02-06 |  |  |  | 2020-02-25 | [24 empty] | 2020-03-06 | [12 empty] | 2021-03-09 | Online
2123118 | Marshfield | 2050 | 19.35 | PV | 3-25-42J2 | 2016-12-23 | 2017-01-11 | 12 |  | 12 | 2017-01-15 |  | -30535 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-10 | 2016-02-11 | [6 empty] | 0 |  | 0
2311127 | Marshfield | 2050 | 2112 | PV | 3-24A-24A | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online |  | Private
2319796 | Marshfield | 2050 | 15.2 | PV | 3-25-42J2 | 2018-12-11 | 2018-12-21 | 8 |  | 8 | 2019-01-11 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online
2341981 | Marshfield | 2050 | 31.5 | PV & Battery | 3-25-42J2 | 2019-04-18 | 2019-05-21 | 23 |  | 23 | 2019-06-04 |  | -31148 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2366460 | Marshfield | 2050 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 |  |  |  | 2019-11-01 | [38 empty] | Withdrawn
2409029 | Marshfield | 2050 | 7.6 | PV | 3-24B-915 | 2020-05-26 | 2020-07-07 |  |  |  | 2020-08-03 | [24 empty] | 2020-08-12 | [12 empty] | 2021-10-25 | Online
2412133 | Marshfield | 2050 | 15.2 | PV | TBD | 2020-08-06 | 2020-08-07 |  |  |  | 2020-08-26 | [24 empty] | 2020-09-11
4493355 | Marshfield | 2050 | 19.6 | PV & Battery | 3-25-25 | 2020-10-21 | 2020-10-22 |  |  |  | 2020-11-18 | [24 empty] | 2020-11-25
4637609 | Marshfield | 2050 | 13.8 | PV & Battery | 3-22-973 | 2020-10-29 |  |  |  |  | 2020-12-29 | [24 empty] | 2021-01-11 | [12 empty] | 2021-05-21 | Online
4668327 | Marshfield | 2050 | 18 | PV | TBD | 2020-12-17 | 2020-12-17 |  |  |  | 2021-01-05 | [24 empty] | 2021-01-14
5123184 | Marshfield | 2050 | 2000 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08
5174339 | Marshfield | 2050 | 172 | PV | TBD | 2021-02-17 | 2021-02-23 |  |  |  | 2021-03-11 | [24 empty] | 2021-05-13 | [12 empty] | 2023-02-01 | Online
5393165 | Marshfield | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2022-08-02
5393188 | Marshfield | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08
ESMAEX-00127 | Marshfield | 2050 | 195 | PV | TBD | 2021-05-17 | 2021-06-15 | [28 empty] | 2022-05-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-00128 | Marshfield | 2050 | 249 | PV & Battery | 3-24B-915 | 2021-05-17 | 2021-06-07 | [28 empty] | 2022-06-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-00129 | Marshfield | 2050 | 499 | PV & Battery | TBD | 2021-05-17 | 2021-06-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-00381 | Marshfield | 2050 | 150 | PV | TBD | 2021-09-02 | 2022-01-19 | [28 empty] | 2022-06-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-00495 | Marshfield | 2050 | 5.51 | PV & Battery | 3-22-33J2 | 2021-10-13 | 2021-11-24 | [28 empty] | 2021-12-30 | [12 empty] | 2022-09-19 | Online |  |  | Y
ESMAEX-00584 | Marshfield | 2050 | 9 | Battery | 3-27-970 | 2021-11-15 | 2021-12-17 | [28 empty] | 2021-12-23 | [12 empty] | 2022-10-17 | Online |  |  | Y
ESMAEX-00683 | Marshfield | 2050 | 17.7 | PV | 3-24A-34J1 | 2021-12-21 | 2022-01-11 | [28 empty] | 2022-02-17 | [12 empty] | 2022-08-29 | Online |  |  | Y
ESMAEX-00684 | Marshfield | 2050 | 499 | PV & Battery | 3-27-970 | 2021-12-21 | 2022-02-24 | [28 empty] | 2022-07-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00706 | Marshfield | 2050 | 249 | PV & Battery | 3-22-973 | 2022-01-04 | 2022-01-25 | [28 empty] | 2022-06-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-00707 | Marshfield | 2050 | 249 | PV & Battery | 3-27-970 | 2022-01-04 | 2022-01-25 | [28 empty] | 2022-07-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00708 | Marshfield | 2050 | 240 | PV | TBD | 2022-01-04 | 2022-01-25 | [28 empty] | 2022-09-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-00779 | Marshfield | 2050 | 4999.2 | Battery | 3-24B-915 | 2022-03-09 | 2022-06-09 | [42 empty] | In Queue |  |  | Y
ESMAEX-00838 | Marshfield | 2050 | 4999.2 | Battery | 3-22-973 | 2022-03-16 | 2022-05-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-00974 | Marshfield | 2050 | 7.6 | PV & Battery | 3-24A-974 | 2022-03-28 | 2022-04-13 | [28 empty] | 2022-05-16 | [12 empty] | 2023-03-09 | Online |  |  | Y
ESMAEX-01540 | Marshfield | 2050 | 3.8 | PV | 3-25-42J2 | 2022-09-02 | 2022-09-29 | [28 empty] | 2022-10-05 | [12 empty] | 2023-03-30 | Online |  |  | Y
ESMAEX-01850 | Marshfield | 2050 | 10 | PV & Battery | 3-25-42J2 | 2022-11-28 | 2022-12-29 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01941 | Marshfield | 2050 | 249 | PV & Battery | 3-24B-915 | 2023-03-14 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-02182 | Marshfield | 2050 | 15.2 | Battery | 45741 | 2023-02-21 | 2023-03-08 | [28 empty] | 2023-04-03 | [13 empty] | In Queue |  |  | Y
2384377 | Marshfield | 2050 | 16.2 | PV | 3-24A-971 | 2019-09-18 | 2019-12-11 |  |  |  | 2020-02-04 | [24 empty] | 2020-02-21 | [12 empty] | 2020-12-30 | Online
2370516 | Marshfield | 2050 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 |  |  |  | 2019-11-27 | [24 empty] | 2020-06-15
2392617 | Marshfield | 2050 | 500 | PV | TBD | 2020-03-18 | 2020-03-20 |  |  |  | 2020-04-03
2392719 | Marshfield | 2050 | 250 | PV | TBD | 2020-03-18 | 2020-03-20 |  |  |  | 2020-04-03 | [24 empty] | 2020-08-03 | [12 empty] | 2022-06-08 | Online
2180484 | Medfield | 2052 | 70 | PV | 146-H2 | 2016-11-07 | 2016-11-07 | 0 |  | 0 | 2016-11-09 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online |  | GOV'T
2279225 | Medfield | 2052 | 264 | PV | 456-H2 | 2018-05-07 | 2018-05-11 | 4 |  | 4 | 2018-06-05 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-06-05 | Online
2282637 | Medfield | 2052 | 240 | PV | 456-H2 | 2018-05-30 | 2018-06-04 | 3 |  | 3 | 2018-06-19 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | 2018-08-23 | [6 empty] | 0 |  | 0 |  |  | 2019-06-10 | Online
2374353 | Medfield | 2052 | 17.6 | PV & Battery | TBD | 2019-11-21 | 2019-12-02 |  |  |  | 2019-12-17 | [24 empty] | 2020-01-13 | [12 empty] | 2020-12-30 | Online
2351919 | Medfield | 2052 | 1280 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 |  |  |  | 2019-07-29 | [24 empty] | 2021-02-10
2352302 | Medfield | 2052 | 766.6 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 |  |  |  | 2019-07-31 | [24 empty] | 2021-02-10
2352954 | Medfield | 2052 | 150 | PV | TBD | 2019-07-18 | 2019-07-22 |  |  |  | 2019-08-05 | [24 empty] | 2019-10-08 | [12 empty] | 2022-09-13 | Online
4714661 | Medfield | 2052 | 250 | PV | TBD | 2020-08-14 |  |  |  |  | 2020-09-03 | [24 empty] | 2020-12-14
4581063 | Medfield | 2052 | 17.6 | PV | 456-H5 | 2020-09-18 | 2020-11-04 |  |  |  | 2020-12-09 | [24 empty] | 2020-12-18 | [12 empty] | 2021-09-14 | Online
4589421 | Medfield | 2052 | 200 | PV | TBD | 2020-10-27 | 2020-11-09 |  |  |  | 2020-12-11 | [24 empty] | 2021-02-24
4635189 | Medfield | 2052 | 25 | PV & Battery | TBD | 2020-11-25 | 2020-12-14 |  |  |  | 2020-12-23 | [24 empty] | 2021-03-05 | [12 empty] | 2022-05-13 | Online
ESMAEX-00339 | Medfield | 2052 | 17.68 | PV & Battery | 146-H2 | 2021-08-23 | 2021-09-09 | [28 empty] | 2021-11-08 | [12 empty] | 2023-02-16 | Online |  |  | Y
ESMAEX-00999 | Medfield | 2052 | 16 | PV & Battery | 146-H2 | 2022-03-31 | 2022-06-09 | [28 empty] | 2022-06-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01442 | Medfield | 2052 | 19.8 | PV | 456-H3 | 2022-08-08 | 2022-09-01 | [28 empty] | 2022-10-14 | [12 empty] | 2023-01-09 | Online |  |  | Y
ESMAEX-01452 | Medfield | 2052 | 8.7 | PV & Battery | 456-H2 | 2022-08-09 | 2022-08-29 | [28 empty] | 2022-10-25 | [12 empty] | 2023-03-08 | Online |  |  | Y
ESMAEX-01891 | Medfield | 2052 | 17.6 | PV | 146-H6 | 2022-12-06 | 2022-12-29 | [28 empty] | 2023-01-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-02005 | Medfield | 2052 | 17.934 | PV & Battery | 146-H2 | 2023-01-11 | 2023-02-02 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02035 | Medfield | 2052 | 15.2 | PV & Battery | 146-H2 | 2023-01-17 | 2023-02-10 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02108 | Medfield | 2052 | 15.2 | PV & Battery | 456-H2 | 2023-02-02 | 2023-02-23 | [28 empty] | 2023-03-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02218 | Medfield | 2052 | 300 | PV | 456-H2 | 2023-03-23 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02219 | Medfield | 2052 | 480 | PV | 456-H2 | 2023-03-24 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-02220 | Medfield | 2052 | 250 | PV | 146-H2 | 2023-03-24 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
2223213 | Medway | 2053 | 20 | PV | 65-H5 | 2017-05-16 | 2017-06-05 | 13 |  | 13 | 2017-07-06 |  | -30654 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-04 | 2017-08-09 | [6 empty] | 0 |  | 0 |  |  | 2017-10-02 | Online
2378489 | Medway | 2053 | 230 | PV | TBD | 2019-11-20 | 2019-12-13 |  |  |  | 2020-01-23 | [24 empty] | 2020-02-11 | [12 empty] | 2020-09-21 | Online
2352308 | Medway | 2053 | 250 | PV | TBD | 2019-06-26 | 2019-07-16 |  |  |  | 2019-07-31 | [24 empty] | 2019-08-05 | [12 empty] | 2020-11-13 | Online
2356387 | Medway | 2053 | 500 | PV | TBD | 2019-08-08 | 2019-08-15 |  |  |  | 2019-08-28 | [24 empty] | 2019-12-24 | [12 empty] | 2020-12-31 | Online
2177856 | Medway | 2053 | 180 | PV | 65-H3 | 2016-09-30 | 2016-10-26 | 18 |  | 18 | 2016-10-28 |  | -30481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2261707 | Medway | 2053 | 22.95 | PV | 65-H5 | 2017-12-14 | 2018-01-19 | 25 |  | 25 | 2018-02-06 |  | -30803 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2279222 | Medway | 2053 | 27.72 | PV | 65-H5 | 2018-04-26 | 2018-05-16 | 14 |  | 14 | 2018-05-31 |  | -30885 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2360809 | Medway | 2053 | 500 | PV | 65-H2 | 2019-08-22 | 2019-09-09 |  |  |  | 2019-09-25 | [24 empty] | 2019-10-31
2403742 | Medway | 2053 | 25.75 | PV | TBD | 2019-10-09 | 2020-06-10 |  |  |  | 2020-06-29 | [38 empty] | Withdrawn
2383462 | Medway | 2053 | 15.2 | PV | 130-H2 | 2019-12-18 | 2019-12-20 |  |  |  | 2020-01-30 | [24 empty] | 2020-02-13
2407609 | Medway | 2053 | 1476 | PV & Battery | TBD | 2020-07-06 | 2020-07-09 |  |  |  | 2020-07-21
4470535 | Medway | 2053 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-19 |  |  |  | 2020-11-12 | [24 empty] | 2021-01-06 | [12 empty] | 2021-06-08 | Online
4920759 | Medway | 2053 | 29.5 | PV | TBD | 2020-12-30 | 2021-01-19 |  |  |  | 2021-02-02 | [24 empty] | 2021-05-20 | [12 empty] | 2021-12-15 | Online
4920922 | Medway | 2053 | 19.75 | PV | TBD | 2020-12-30 | 2021-01-19 |  |  |  | 2021-02-02 | [24 empty] | 2021-03-09
2101737 | Medway | 2053 | 504 | PV | 65-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00184 | Medway | 2053 | 22 | PV & Battery | 65-H3 | 2021-06-14 | 2021-06-30 | [28 empty] | 2021-07-13 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00398 | Medway | 2053 | 43.2 | PV | TBD | 2021-09-09 | 2021-09-29 | [28 empty] | 2021-12-23 | [12 empty] | 2022-11-10 | Online |  |  | Y
ESMAEX-00399 | Medway | 2053 | 28.8 | PV | TBD | 2021-09-09 | 2021-09-29 | [28 empty] | 2021-12-23 | [12 empty] | 2022-11-08 | Online |  |  | Y
ESMAEX-00400 | Medway | 2053 | 28.8 | PV | TBD | 2021-09-09 | 2021-09-29 | [28 empty] | 2021-12-23 | [12 empty] | 2022-12-13 | Online |  |  | Y
ESMAEX-00859 | Medway | 2053 | 10.25 | PV & Battery | 65-H3 | 2022-02-25 | 2022-03-11 | [28 empty] | 2022-03-28 | [12 empty] | 2022-10-25 | Online |  |  | Y
ESMAEX-00887 | Medway | 2053 | 6 | PV | 65-H3 | 2022-03-07 | 2022-03-24 | [28 empty] | 2022-03-28 | [12 empty] | 2022-10-27 | Online |  |  | Y
ESMAEX-00895 | Medway | 2053 | 14.46 | PV | 65-H5 | 2022-03-10 | 2022-03-30 | [28 empty] | 2022-05-02 | [12 empty] | 2022-08-22 | Online |  |  | Y
ESMAEX-00902 | Medway | 2053 | 25.2 | PV & Battery | 65-H3 | 2022-03-11 | 2022-03-31 | [28 empty] | 2022-05-12 | [12 empty] | 2023-03-21 | Online |  |  | Y
ESMAEX-01878 | Medway | 2053 | 15.2 | PV & Battery | 65-H5 | 2022-12-01 | 2022-12-29 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-02114 | Medway | 2053 | 10 | Battery | 65-H3 | 2023-02-04 | 2023-02-23 | [28 empty] | 2023-03-01 | [12 empty] | 2023-04-18 | Online |  |  | Y
ESMAEX-02234 | Medway | 2053 | 16.4 | PV | 65-H2 | 2023-03-05 | 2023-03-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-02416 | Medway | 2053 | 15.2 | PV | 65-H3 | 2023-04-26 | [43 empty] | In Queue |  |  | Y
5308165 | Onset | 2053 | 33.3 | PV | TBD | 2021-02-12 | 2021-02-24 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-13 | [12 empty] | 2021-12-13 | Online
5123430 | Medway | 2054 | 5000 | PV & Battery | TBD | 2020-12-31 | 2021-01-25 |  |  |  | 2021-03-08
2127532 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2127571 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2127590 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2127594 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2127596 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2127597 | Millis | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
2224177 | Millis | 2054 | 17.1 | PV | 65-H1 | 2017-06-01 | 2017-06-19 | 12 |  | 12 | 2017-07-10 |  | -30656 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-08 | 2017-10-04 | [6 empty] | 0 |  | 0 |  |  | 2018-01-03 | Online
2211983 | Millis | 2054 | 350.4 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2211985 | Millis | 2054 | 175.2 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2270750 | Millis | 2054 | 199.8 | PV | 65-H1 | 2018-02-23 | 2018-03-16 | 15 |  | 15 | 2018-04-11 |  | -30849 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
2392127 | Millis | 2054 | 250 | PV | TBD | 2020-03-18 | 2020-03-18 |  |  |  | 2020-04-03 | [24 empty] | 2020-05-28
2404399 | Millis | 2054 | 2500 | PV & Battery | TBD | 2020-06-03 | 2020-06-15 |  |  |  | 2020-07-01 | [24 empty] | 2022-06-15
4345313 | Millis | 2054 | 19 | PV | TBD | 2020-09-14 | 2020-09-18 |  |  |  | 2020-10-08 | [24 empty] | 2021-01-26 | [13 empty] | Withdrawn
4642384 | Millis | 2054 | 15.2 | PV | TBD | 2020-12-07 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-13 | [12 empty] | 2021-08-06 | Online
ESMAEX-00379 | Millis | 2054 | 27.13 | Battery | 146-H10 | 2021-09-02 | 2021-09-21 | [28 empty] | 2021-11-29 | [12 empty] | 2022-05-03 | Online |  |  | Y
ESMAEX-00686 | Millis | 2054 | 498 | PV & Battery | 456-H2 | 2023-01-26 | 2023-02-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-01866 | Millis | 2054 | 4999 | PV & Battery | 146-H10 | 2022-11-29 | 2022-12-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-02296 | Millis | 2054 | 25 | PV | 130-H2 | 2023-03-22 | 2023-04-19 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
2262130 | Millis | 2054 | 97.75 | PV | 146-H10 | 2017-12-01 | 2018-01-23 | 36 |  | 36 | 2018-02-07 |  | -30804 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-09 | [6 empty] | 0 |  | 0 |  |  | 2018-09-12 | Online
2253053 | Millis | 2054 | 46 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 3 |  | 3 | 2017-12-22 |  | -30772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-21 | 2018-03-27 | [6 empty] | 0 |  | 0
2253054 | Millis | 2054 | 40.25 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2229611 | Norfolk | 2056 | 34.5 | PV | 146-H3 | 2017-07-11 | 2017-07-19 | 6 |  | 6 | 2017-08-10 |  | -30679 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
2255237 | Norfolk | 2056 | 152 | PV | 146-H3 | 2017-12-08 | 2017-12-18 | 6 |  | 6 | 2018-01-03 |  | -30779 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-08-15 | Online
2268196 | Norfolk | 2056 | 66.6 | PV | 146-H3 | 2018-02-21 | 2018-02-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0 |  |  | 2018-12-04 | Online
2275667 | Norfolk | 2056 | 15.2 | PV | 146-H3 | 2018-04-09 | 2018-04-24 | 11 |  | 11 | 2018-05-08 |  | -30868 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2335261 | Norfolk | 2056 | 50 | PV | 146-H9 | 2019-04-01 | 2019-04-01 | 0 |  | 0 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-05 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
2218206 | Norfolk | 2056 | 72 | PV | 146-H3 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-02 |  | -30631 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-10-06 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2288776 | Norfolk | 2056 | 250 | PV | 146-H3 | 2018-06-07 | 2018-07-12 | 25 |  | 25 | 2018-07-27 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-09-07 | Online
2291293 | Norfolk | 2056 | 996 | PV | 146-H3 | 2018-07-24 | 2018-07-26 | 2 |  | 2 | 2018-08-10 |  | -30936 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
2306602 | Norfolk | 2056 | 15.2 | PV | 146-H9 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2328724 | Norfolk | 2056 | 195 | PV | 146-H9 | 2019-02-14 | 2019-02-19 | 3 |  | 3 | 2019-03-08 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0
2336071 | Norfolk | 2056 | 4990 | PV & Battery | 146-H9 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31118 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2341849 | Norfolk | 2056 | 1000 | PV | 146-H9 | 2019-05-16 | 2019-05-20 |  |  |  | 2019-05-30 | [24 empty] | 2019-10-11
2357740 | Norfolk | 2056 | 100.8 | PV | TBD | 2019-08-20 | 2019-08-20 |  |  |  | 2019-09-06 | [24 empty] | 2019-09-16
2412929 | Norfolk | 2056 | 5000 | PV & Battery | TBD | 2020-08-06 |  |  |  |  | 2020-09-03
4578744 | Norfolk | 2056 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 |  |  |  | 2020-12-08 | [24 empty] | 2021-01-26 | [12 empty] | 2021-08-03 | Online
ESMAEX-00292 | Norfolk | 2056 | 15.29 | PV & Battery | 65-H1 | 2021-08-09 | 2021-09-24 | [28 empty] | 2021-10-26 | [12 empty] | 2022-04-06 | Online |  |  | Y
ESMAEX-00345 | Norfolk | 2056 | 17.68 | PV & Battery | 146-H3 | 2021-08-24 | 2021-09-13 | [28 empty] | 2021-12-14 | [12 empty] | 2022-09-22 | Online |  |  | Y
ESMAEX-00391 | Norfolk | 2056 | 13.15 | Battery | 146-H3 | 2021-09-08 | 2021-09-23 | [28 empty] | 2021-11-29 | [12 empty] | 2022-11-15 | Online |  |  | Y
ESMAEX-01039 | Norfolk | 2056 | 21 | PV & Battery | 146-H10 | 2022-04-07 | 2022-04-26 | [28 empty] | 2022-06-01 | [12 empty] | 2022-10-19 | Online |  |  | Y
ESMAEX-01417 | Norfolk | 2056 | 20.2 | PV & Battery | 146-H10 | 2022-07-29 | 2022-08-17 | [28 empty] | 2022-09-23 | [12 empty] | 2023-04-06 | Online |  |  | Y
ESMAEX-01589 | Norfolk | 2056 | 15.2 | PV & Battery | 146-H3 | 2022-09-14 | 2022-09-29 | [28 empty] | 2022-11-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01782 | Norfolk | 2056 | 12.6 | PV & Battery | 65-H1 | 2022-11-08 | 2022-12-05 | [28 empty] | 2023-01-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01848 | Norfolk | 2056 | 19.2 | PV & Battery | 65-H1 | 2022-11-26 | 2022-12-19 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01898 | Norfolk | 2056 | 15.2 | PV & Battery | 146-H3 | 2022-12-07 | 2022-12-29 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-02026 | Norfolk | 2056 | 17.6 | PV | 146-H3 | 2023-01-14 | 2023-02-01 | [28 empty] | 2023-04-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-02208 | Norfolk | 2056 | 200 | Battery | 65-H1 | 2023-02-27 | 2023-03-21 | [42 empty] | In Queue |  |  | Y
ESMAEX-02429 | Norfolk | 2056 | 15 | Battery | 65-H1 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
ESMAEX-01675 | Maynard | 2067 | 250 | PV & Battery | 416-H6 | 2022-10-11 | 2022-11-04 | [28 empty] | 2022-12-09 | [13 empty] | In Queue |  |  | Y
2122406 | Sharon | 2067 | 17.5 | PV | 470-h12 | 2015-12-02 | 2016-01-07 | 26 |  | 26 | 2016-01-11 |  | -30272 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-12 | 2016-03-23 | [6 empty] | 0 |  | 0 |  |  | 2016-04-29 | Online
2339541 | Sharon | 2067 | 57.6 | PV | 146-H7 | 2019-04-23 | 2019-04-25 | 2 |  | 2 | 2019-05-14 |  | -31133 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-29 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2341555 | Sharon | 2067 | 20.35 | PV | 470-H12 | 2019-04-22 | 2019-05-17 | 19 |  | 19 | 2019-05-29 |  | -31144 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
2241001 | Sharon | 2067 | 272 | PV | 146-H1 | 2017-10-04 | 2017-10-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-28 | 2018-08-30 | [6 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online |  | Private
4581293 | Sharon | 2067 | 15.2 | PV | TBD | 2020-11-06 | 2020-11-09 |  |  |  | 2020-12-09 | [24 empty] | 2021-01-20 | [12 empty] | 2021-03-29 | Online
2374058 | Sharon | 2067 | 200 | PV | 146-H1 | 2019-11-27 | 2019-11-27 |  |  |  | 2019-12-17 | [24 empty] | 2020-02-06 | [12 empty] | 2021-04-20 | Online
2312223 | Sharon | 2067 | 660 | PV & Battery | 146-H7 | 2018-10-25 | 2018-12-03 | 27 |  | 27 | 2018-12-13 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2020-09-30
2346951 | Sharon | 2067 | 50 | PV | 470-H3 | 2019-05-07 | 2019-06-14 | 28 |  | 28 | 2019-06-27 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online
2368605 | Sharon | 2067 | 999 | PV | TBD | 2019-09-05 | 2019-10-29 |  |  |  | 2019-11-14 | [24 empty] | 2020-07-27
2368571 | Sharon | 2067 | 499 | PV & Battery | TBD | 2019-10-24 | 2019-10-29 |  |  |  | 2019-11-14 | [24 empty] | 2020-04-03
2389511 | Sharon | 2067 | 480 | PV | TBD | 2020-02-24 | 2020-02-25 |  |  |  | 2020-03-11 | [37 empty] | 2022-07-20 | Online
4468058 | Sharon | 2067 | 19 | PV | TBD | 2020-10-07 | 2020-10-15 |  |  |  | 2020-11-09 | [24 empty] | 2021-01-20
5132549 | Sharon | 2067 | 30 | PV & Battery | TBD | 2020-10-15 | 2021-02-17 |  |  |  | 2021-03-08 | [24 empty] | 2021-06-18
5286859 | Sharon | 2067 | 15.2 | PV | TBD | 2020-10-15 | 2021-03-02 |  |  |  | 2021-03-26 | [24 empty] | 2021-05-05 | [13 empty] | Withdrawn
4488554 | Sharon | 2067 | 18.75 | PV | TBD | 2020-10-16 | 2020-10-21 |  |  |  | 2020-11-17 | [24 empty] | 2020-12-17 | [12 empty] | 2021-06-03 | Online
4619617 | Sharon | 2067 | 20 | PV & Battery | TBD | 2020-10-29 | 2020-11-25 |  |  |  | 2020-12-23 | [24 empty] | 2021-02-24 | [12 empty] | 2021-11-19 | Online
4637394 | Sharon | 2067 | 18.5 | PV | TBD | 2020-11-13 | 2020-11-18 |  |  |  | 2020-12-29 | [24 empty] | 2021-03-17 | [13 empty] | Withdrawn
5215247 | Sharon | 2067 | 30.2 | PV & Battery | TBD | 2020-12-14 | [29 empty] | 2021-04-09 | [12 empty] | 2022-03-17 | Online
4921508 | Sharon | 2067 | 13.8 | PV & Battery | TBD | 2020-12-14 | [29 empty] | 2021-04-01 | [12 empty] | 2021-11-04 | Online
4983727 | Sharon | 2067 | 16.48 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 |  |  |  | 2021-02-11 | [24 empty] | 2021-04-12 | [12 empty] | 2022-02-07 | Online
5392760 | Sharon | 2067 | 250 | PV | TBD | 2021-03-16 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-10-26
ESMAEX-00315 | Sharon | 2067 | 250 | PV | 146-H1 | 2021-08-16 | 2021-09-02 | [28 empty] | 2022-05-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-00352 | Sharon | 2067 | 20.2 | PV & Battery | 146-H7 | 2021-08-26 | 2021-09-14 | [28 empty] | 2021-12-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-00357 | Sharon | 2067 | 900 | PV & Battery | 146-H1 | 2021-10-02 | 2021-11-15 | [42 empty] | In Queue |  |  | Y
ESMAEX-00457 | Sharon | 2067 | 988 | PV & Battery | 470-H12 | 2021-09-29 | 2021-10-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-00479 | Sharon | 2067 | 933.2 | PV | 146-H1 | 2021-10-07 | 2022-01-06 | [42 empty] | In Queue |  |  | Y
ESMAEX-00626 | Sharon | 2067 | 7.6 | PV & Battery | 470-H12 | 2021-11-28 | 2021-12-14 | [28 empty] | 2022-02-08 | [12 empty] | 2023-04-14 | Online |  |  | Y
ESMAEX-00641 | Sharon | 2067 | 9.15 | PV & Battery | 470-H12 | 2021-12-03 | 2021-12-28 | [28 empty] | 2022-02-14 | [12 empty] | 2022-12-29 | Online |  |  | Y
ESMAEX-01049 | Sharon | 2067 | 15.2 | PV & Battery | 470-H12 | 2022-04-08 | 2022-04-28 | [28 empty] | 2022-05-26 | [12 empty] | 2023-04-10 | Online |  |  | Y
ESMAEX-01113 | Sharon | 2067 | 8.85 | PV & Battery | 146-H7 | 2022-04-26 | 2022-05-24 | [28 empty] | 2022-06-29 | [12 empty] | 2023-02-01 | Online |  |  | Y
ESMAEX-01212 | Sharon | 2067 | 15.2 | PV | 470-H12 | 2022-05-23 | 2022-06-17 | [28 empty] | 2022-07-27 | [12 empty] | 2023-03-03 | Online |  |  | Y
ESMAEX-01322 | Sharon | 2067 | 15.2 | PV & Battery | 470-H3 | 2022-06-24 | 2022-07-21 | [28 empty] | 2022-09-06 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01472 | Sharon | 2067 | 19 | PV & Battery | 470-H3 | 2022-08-15 | 2022-09-09 | [28 empty] | 2022-10-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01661 | Sharon | 2067 | 15.2 | PV & Battery | 146-H1 | 2022-10-05 | 2022-11-29 | [28 empty] | 2022-12-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01683 | Sharon | 2067 | 230 | Other | 146-H1 | 2022-10-14 | 2022-11-04 | [42 empty] | In Queue |  |  | N
ESMAEX-01690 | Sharon | 2067 | 16.47 | PV & Battery | 470-H12 | 2022-10-17 | 2022-11-04 | [28 empty] | 2023-01-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01832 | Sharon | 2067 | 10 | Battery | 470-H3 | 2022-11-18 | 2022-12-29 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01863 | Sharon | 2067 | 15.2 | PV & Battery | 146-H7 | 2022-11-29 | 2022-12-19 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01922 | Sharon | 2067 | 15.2 | PV | 146-H7 | 2022-12-14 | 2023-01-12 | [28 empty] | 2023-03-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-01965 | Sharon | 2067 | 19.845 | PV & Battery | LINE48C | 2023-01-05 | 2023-01-23 | [28 empty] | 2023-03-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02037 | Sharon | 2067 | 19.89 | PV | 470-H3 | 2023-01-18 | [43 empty] | In Queue |  |  | Y
ESMAEX-02057 | Sharon | 2067 | 20.2 | PV & Battery | 470-H3 | 2023-01-23 | 2023-02-10 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02107 | Sharon | 2067 | 15.2 | Battery | 470-H3 | 2023-02-02 | 2023-03-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-02117 | Sharon | 2067 | 100 | Battery | 470-H12 | 2023-02-06 | 2023-02-23 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02126 | Sharon | 2067 | 60 | Battery | 470-H12 | 2023-02-06 | 2023-02-23 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02167 | Sharon | 2067 | 15.2 | Battery | 146-H1 | 2023-02-16 | 2023-03-08 | [28 empty] | 2023-03-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02207 | Sharon | 2067 | 21.4 | Battery | 470-H3 | 2023-02-27 | 2023-03-23 | [42 empty] | In Queue |  |  | Y
ESMAEX-02282 | Sharon | 2067 | 15.2 | PV | 470-H3 | 2023-03-17 | 2023-04-06 | [28 empty] | 2023-04-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-02345 | Sharon | 2067 | 18.5 | PV | LINE48C | 2023-04-05 | 2023-04-20 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
4581720 | South Walpole | 2071 | 20 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 |  |  |  | 2020-12-04 | [24 empty] | 2021-01-28 | [12 empty] | 2021-06-25 | Online
2000815 | Walpole | 2071 | 3450 | PV | 146-H3 | 2014-03-13 | 2014-03-13 | 0 |  | 0 | 2014-03-13 |  | -29795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-01 | 2015-09-01 | [6 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online
2340703 | Walpole | 2071 | 99.9 | PV | 146-H1 | 2019-05-01 | 2019-05-03 | 2 |  | 2 | 2019-05-23 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2180956 | Walpole | 2081 | 28.8 | PV | 146-H3 | 2016-10-05 | 2016-10-17 | 8 |  | 8 | 2016-11-10 |  | -30490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online |  | PRIVATE
2200165 | Walpole | 2081 | 16.7 | PV | 146-H9 | 2017-01-11 | 2017-01-20 | 6 |  | 6 | 2017-02-08 |  | -30552 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-04-24 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online |  | PRIVATE
2234087 | Walpole | 2081 | 24 | PV | 456-H1 | 2017-08-01 | 2017-08-15 | 10 |  | 10 | 2017-09-12 |  | -30701 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-17 | 2017-10-17 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2230560 | Walpole | 2081 | 590 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-17 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2231849 | Walpole | 2081 | 402 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2231851 | Walpole | 2081 | 362 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2234593 | Walpole | 2081 | 132 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-09-13 |  | -30702 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2233507 | Walpole | 2081 | 336 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-06 |  | -30697 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2233726 | Walpole | 2081 | 662 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2234091 | Walpole | 2081 | 782 | PV | 146-H1 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-12 |  | -30701 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
2233722 | Walpole | 2081 | 368 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2019-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-07-03 | Online
2348516 | Walpole | 2081 | 17.5 | PV | TBD | 2019-06-17 | 2019-06-21 |  |  |  | 2019-07-08 | [24 empty] | 2019-08-07 | [12 empty] | 2019-12-27 | Online
2384980 | Walpole | 2081 | 30.2 | PV & Battery | 146-H4 | 2020-01-10 | 2020-01-26 |  |  |  | 2020-02-07 | [24 empty] | 2020-03-04 | [12 empty] | 2020-07-21 | Online
2174571 | Walpole | 2081 | 135 | PV | 2611 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2215756 | Walpole | 2081 | 19.15 | PV | 146-H3 | 2017-04-14 | 2017-04-24 | 5 |  | 5 | 2017-05-16 |  | -30619 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2258239 | Walpole | 2081 | 218.5 | PV | 146-H1 | 2017-10-31 | 2017-12-18 | 33 |  | 33 | 2018-01-11 |  | -30785 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 |  | -30785 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2271379 | Walpole | 2081 | 480 | PV | 146-H6 | 2018-03-16 | 2018-03-26 | 6 |  | 6 | 2018-04-13 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0
2283639 | Walpole | 2081 | 7499 | PV & Battery | 456-H1 | 2018-06-01 | 2018-06-13 | 8 |  | 8 | 2018-06-26 |  | -30903 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0
2283230 | Walpole | 2081 | 486.6 | PV | 146-H1 | 2018-06-05 | 2018-06-13 | 6 |  | 6 | 2018-06-26 |  | -30903 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
2331931 | Walpole | 2081 | 407 | PV | 146-H1 | 2019-01-11 | 2019-03-15 | 45 |  | 45 | 2019-03-29 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
MULTIPLE WOS | Walpole | 2081 | 2167.6 | PV | 146-H4 | 2019-01-14 | 2019-03-28 | 53 |  | 53 | 2019-04-15 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
2330941 | Walpole | 2081 | 250 | PV | 146-H1 | 2019-03-08 | 2019-03-13 | 3 |  | 3 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
2334456 | Walpole | 2081 | 1000 | PV & Battery | 146-H1 | 2019-03-15 | 2019-03-28 | 9 |  | 9 | 2019-04-15 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
2370575 | Walpole | 2081 | 312.5 | PV | TBD | 2019-11-04 | 2019-11-12 |  |  |  | 2019-11-29
2392586 | Walpole | 2081 | 2000 | PV & Battery | TBD | 2020-03-06 | 2020-03-20 |  |  |  | 2020-04-03
2394160 | Walpole | 2081 | 1000 | PV | TBD | 2020-03-27 | 2020-04-01 |  |  |  | 2020-04-20 | [24 empty] | 2020-09-29
5608635 | Walpole | 2081 | 15.2 | PV | TBD | 2020-09-08 | 2021-04-16 |  |  |  | 2021-05-05 | [24 empty] | 2021-05-26
4519566 | Walpole | 2081 | 15.2 | PV | TBD | 2020-09-14 | 2020-10-15 |  |  |  | 2020-11-24 | [24 empty] | 2021-01-06 | [12 empty] | 2021-11-09 | Online
4590656 | Walpole | 2081 | 10 | PV & Battery | 146-H3 | 2020-11-06 | 2020-11-13 |  |  |  | 2020-12-11 | [24 empty] | 2021-01-28
4698540 | Walpole | 2081 | 495 | PV | TBD | 2020-11-13 | 2020-12-29 |  |  |  | 2021-01-13 | [24 empty] | 2021-07-26
4963817 | Walpole | 2081 | 10 | PV & Battery | TBD | 2020-12-14 | 2021-01-27 |  |  |  | 2021-02-11 | [24 empty] | 2021-04-19 | [12 empty] | 2021-08-18 | Online
4833200 | Walpole | 2081 | 15.2 | PV | TBD | 2020-12-23 | 2020-12-23 |  |  |  | 2021-01-21 | [24 empty] | 2021-03-25
ESMAEX-00020 | Walpole | 2081 | 20 | PV & Battery | 146-H4 | 2021-04-01 | 2021-04-20 | [28 empty] | 2021-07-09 | [12 empty] | 2022-11-22 | Online |  |  | Y
ESMAEX-00191 | Walpole | 2081 | 15.2 | PV | 456-H1 | 2021-06-17 | 2021-07-06 | [28 empty] | 2021-08-09 | [12 empty] | 2021-12-13 | Online |  |  | Y
ESMAEX-00498 | Walpole | 2081 | 15.8 | PV | 456-H1 | 2021-10-13 | 2021-11-16 | [28 empty] | 2021-12-07 | [12 empty] | 2022-08-12 | Online |  |  | Y
ESMAEX-00572 | Walpole | 2081 | 400 | PV | 146-H8 | 2021-11-08 | 2021-11-23 | [28 empty] | 2022-05-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-00791 | Walpole | 2081 | 4999.2 | Battery | 146-H6 | 2022-11-29 | [43 empty] | In Queue |  |  | Y
ESMAEX-00804 | Walpole | 2081 | 133.3 | PV | 146-H4 | 2022-02-03 | 2022-03-16 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-00997 | Walpole | 2081 | 10 | PV & Battery | 146-H4 | 2022-03-31 | 2022-05-26 | [28 empty] | 2022-06-28 | [12 empty] | 2022-10-24 | Online |  |  | Y
ESMAEX-01040 | Walpole | 2081 | 20.2 | PV & Battery | 146-H4 | 2022-04-07 | 2022-04-28 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01156 | Walpole | 2081 | 250 | PV | 146-H6 | 2022-05-06 | 2022-06-01 | [28 empty] | 2022-08-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01628 | Walpole | 2081 | 10 | PV | 2607 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-11-04 | [12 empty] | 2023-03-13 | Online |  |  | Y
ESMAEX-01722 | Walpole | 2081 | 22.2 | PV & Battery | 2606 | 2022-10-25 | 2022-11-16 | [28 empty] | 2023-01-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01784 | Walpole | 2081 | 15.2 | PV | 146-H4 | 2022-11-08 | 2022-12-05 | [28 empty] | 2022-12-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-01829 | Walpole | 2081 | 20.06 | PV | 146-H4 | 2022-11-17 | 2022-12-19 | [28 empty] | 2023-01-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01947 | Walpole | 2081 | 15.2 | PV & Battery | 456-H1 | 2022-12-27 | 2023-01-23 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01958 | Walpole | 2081 | 4999 | Other | 146-H8 | 2023-01-04 | 2023-01-26 | [42 empty] | In Queue |  |  | N
ESMAEX-02003 | Walpole | 2081 | 15.2 | PV | 456-H1 | 2023-01-11 | 2023-03-08 | [28 empty] | 2023-03-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02019 | Walpole | 2081 | 15.3 | PV | 146-H8 | 2023-01-13 | 2023-01-23 | [28 empty] | 2023-03-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-02041 | Walpole | 2081 | 15.2 | PV & Battery | 2601 | 2023-01-19 | 2023-02-10 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02060 | Walpole | 2081 | 15.2 | PV & Battery | 146-H6 | 2023-01-23 | 2023-02-14 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02129 | Walpole | 2081 | 19.52 | Battery | 146-H4 | 2023-02-07 | 2023-03-21 | [28 empty] | 2023-04-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-02254 | Walpole | 2081 | 19.8 | PV | 2611 | 2023-03-09 | 2023-04-03 | [28 empty] | 2023-04-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-02431 | Walpole | 2081 | 100 | PV | 146-H8 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
2235087 | Barnstable | 2090 | 3720 | PV | 4-88-453 | 2017-08-17 | 2017-08-18 | 1 |  | 1 | 2017-09-18 |  | -30705 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-26 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
4533474 | Westwood | 2090 | 20 | PV & Battery | TBD | 2020-11-16 | 2020-11-18 |  |  |  | 2020-11-25 | [24 empty] | 2021-01-12
2165893 | Westwood | 2090 | 266.4 | PV | 456-H1 | 2016-08-05 | 2016-08-12 | 5 |  | 5 | 2016-08-26 |  | -30436 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2017-10-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-21 | Online |  | PRIVATE | Y
2160448 | Westwood | 2090 | 126.5 | PV | 456-h1 | 2016-07-14 | 2016-07-18 | 2 |  | 2 | 2016-07-27 |  | -30414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-02 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2017-04-27 | Online
2206500 | Westwood | 2090 | 20 | PV | 148-H3 | 2017-02-28 | 2017-03-06 | 4 |  | 4 | 2017-03-20 |  | -30579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-25 | 2017-04-26 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online |  | PRIVATE
2182386 | Westwood | 2090 | 480 | PV | 469-H3 | 2016-09-15 | 2016-10-18 | 23 |  | 23 | 2016-11-21 |  | -30497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
2218004 | Westwood | 2090 | 302 | PV | 469-H6 | 2017-05-09 | 2017-05-16 | 5 |  | 5 | 2017-06-16 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-04 | 30674 |  | 30674 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-02 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-10-29 | Online |  | Private
2385414 | Westwood | 2090 | 25 | PV & Battery | 469-H2 | 2020-01-21 | 2020-01-28 |  |  |  | 2020-02-14 | [24 empty] | 2020-04-03 | [12 empty] | 2020-07-08 | Online
2339939 | Westwood | 2090 | 60 | PV | 20-H3 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-16 |  | -31135 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
2390944 | Westwood | 2090 | 10 | PV & Battery | 148-H3 | 2020-02-18 | 2020-03-10 |  |  |  | 2020-03-23 | [37 empty] | 2020-12-22 | Online
2184045 | Westwood | 2090 | 2310 | PV | 344-1412H1 | 2016-10-21 | 2016-10-31 | 6 |  | 6 | 2016-12-01 |  | -30505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-20 | 2017-05-18 | 20 |  | 20 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2184048 | Westwood | 2090 | 30.14 | PV | 148-H3 | 2016-10-24 | 2016-11-15 | 16 |  | 16 | 2016-12-01 |  | -30505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2212591 | Westwood | 2090 | 858 | PV | 469-H6 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-26 |  | -30605 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2412211 | Westwood | 2090 | 3104.5 | PV & Battery | TBD | 2020-08-07 | 2020-08-11 |  |  |  | 2020-08-31 | [38 empty] | Withdrawn
4659394 | Westwood | 2090 | 95.8 | PV | TBD | 2020-11-06 | 2020-12-14 |  |  |  | 2021-01-05 | [24 empty] | 2021-03-25 | [12 empty] | 2022-03-17 | Online
4581827 | Westwood | 2090 | 20 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 |  |  |  | 2020-12-09 | [24 empty] | 2021-02-24
4636581 | Westwood | 2090 | 25.2 | PV & Battery | TBD | 2020-11-25 | 2020-12-07 |  |  |  | 2020-12-23 | [24 empty] | 2021-04-05 | [12 empty] | 2022-03-08 | Online
4635371 | Westwood | 2090 | 20 | PV & Battery | TBD | 2020-12-01 | 2020-12-01 |  |  |  | 2020-12-29 | [24 empty] | 2021-02-24 | [12 empty] | 2021-06-24 | Online
4887029 | Westwood | 2090 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-05
5099732 | Westwood | 2090 | 15.2 | PV | TBD | 2021-02-12 | 2021-02-12 |  |  |  | 2021-03-11 | [24 empty] | 2021-04-06
ESMAEX-00265 | Westwood | 2090 | 76 | PV | 148-H3 | 2021-07-26 | 2021-08-24 | [28 empty] | 2022-03-07 | [12 empty] | 2022-11-08 | Online |  |  | Y
ESMAEX-00274 | Westwood | 2090 | 24 | PV & Battery | 148-H3 | 2021-07-29 | 2021-09-17 | [28 empty] | 2021-11-22 | [12 empty] | 2022-09-15 | Online |  |  | Y
ESMAEX-00289 | Westwood | 2090 | 276 | PV | 456-H4 | 2021-08-05 | 2021-09-07 | [28 empty] | 2022-06-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-00414 | Westwood | 2090 | 20 | PV & Battery | 469-H2 | 2021-09-16 | 2021-10-04 | [28 empty] | 2021-12-08 | [12 empty] | 2022-10-27 | Online |  |  | Y
ESMAEX-00440 | Westwood | 2090 | 25.37 | PV & Battery | 456-H1 | 2021-09-22 | 2021-12-07 | [28 empty] | 2022-01-19 | [12 empty] | 2022-08-19 | Online |  |  | Y
ESMAEX-00667 | Westwood | 2090 | 18 | PV & Battery | 456-H4 | 2021-12-16 | 2022-01-07 | [28 empty] | 2022-02-17 | [12 empty] | 2023-02-01 | Online |  |  | Y
ESMAEX-00703 | Westwood | 2090 | 16.054 | PV | 148-H3 | 2022-01-03 | 2022-01-25 | [28 empty] | 2022-02-28 | [12 empty] | 2022-05-19 | Online |  |  | Y
ESMAEX-00709 | Westwood | 2090 | 480 | PV | 469-H6 | 2022-05-11 | 2022-07-21 | [28 empty] | 2023-04-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00757 | Westwood | 2090 | 15.2 | PV & Battery | 456-H4 | 2022-01-25 | 2022-02-17 | [28 empty] | 2022-03-09 | [12 empty] | 2023-01-31 | Online |  |  | Y
ESMAEX-00808 | Westwood | 2090 | 11 | PV & Battery | 456-H4 | 2022-02-04 | 2022-02-28 | [28 empty] | 2022-03-24 | [12 empty] | 2022-08-19 | Online |  |  | Y
ESMAEX-01016 | Westwood | 2090 | 15.2 | PV & Battery | 148-H3 | 2022-04-06 | 2022-05-23 | [28 empty] | 2022-06-28 | [12 empty] | 2022-12-16 | Online |  |  | Y
ESMAEX-01082 | Westwood | 2090 | 20.2 | PV & Battery | 148-H3 | 2022-04-15 | 2022-05-02 | [28 empty] | 2022-06-29 | [12 empty] | 2023-04-12 | Online |  |  | Y
ESMAEX-01177 | Westwood | 2090 | 15.045 | PV | 456-H1 | 2022-05-12 | 2022-06-06 | [28 empty] | 2022-07-07 | [12 empty] | 2022-11-17 | Online |  |  | Y
ESMAEX-01194 | Westwood | 2090 | 25 | PV | TBD | 2022-05-18 | 2022-06-13 | [28 empty] | 2022-07-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01242 | Westwood | 2090 | 486 | PV & Battery | 456-H4 | 2022-12-05 | 2023-01-26 | [28 empty] | 2023-04-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01283 | Westwood | 2090 | 16.5 | PV & Battery | 456-H1 | 2022-06-10 | 2022-07-18 | [28 empty] | 2022-09-06 | [12 empty] | 2022-11-28 | Online |  |  | Y
ESMAEX-01503 | Westwood | 2090 | 15.2 | PV & Battery | 456-H1 | 2022-08-23 | 2022-09-14 | [28 empty] | 2022-10-24 | [12 empty] | 2023-04-12 | Online |  |  | Y
ESMAEX-01541 | Westwood | 2090 | 15.2 | PV & Battery | 469-H2 | 2022-09-02 | 2022-10-11 | [28 empty] | 2022-11-03 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01560 | Westwood | 2090 | 15.2 | PV & Battery | 456-H4 | 2022-09-09 | 2022-09-27 | [28 empty] | 2022-10-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01668 | Westwood | 2090 | 15.2 | PV | 456-H1 | 2022-10-07 | 2022-10-27 | [28 empty] | 2022-10-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01786 | Westwood | 2090 | 10 | PV & Battery | 148-H3 | 2022-11-08 | 2022-12-05 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01853 | Westwood | 2090 | 15.2 | PV & Battery | 456-H4 | 2022-11-28 | 2022-12-09 | [28 empty] | 2023-02-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01895 | Westwood | 2090 | 15.2 | PV | 148-H3 | 2022-12-06 | 2023-01-23 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01971 | Westwood | 2090 | 240 | PV | 469-H4 | 2023-01-05 | 2023-02-09 | [42 empty] | In Queue |  |  | Y
ESMAEX-01972 | Westwood | 2090 | 200 | PV | 469-H4 | 2023-01-05 | 2023-03-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-01974 | Westwood | 2090 | 120 | PV & Battery | 469-H4 | 2023-01-05 | 2023-02-23 | [28 empty] | 2023-04-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-02080 | Westwood | 2090 | 15.24 | Battery | 148-H3 | 2023-01-27 | 2023-02-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-02213 | Westwood | 2090 | 18.3 | Battery | 456-H1 | 2023-02-28 | 2023-03-21 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02297 | Westwood | 2090 | 16.47 | PV | 469-H2 | 2023-03-22 | 2023-04-03 | [28 empty] | 2023-04-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-02304 | Westwood | 2090 | 15.2 | PV | 469-H2 | 2023-03-23 | 2023-04-06 | [28 empty] | 2023-04-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-02374 | Westwood | 2090 | 15.2 | PV | 456-H4 | 2023-04-13 | 2023-04-25 | [28 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
2394534 | Boston | 2109 | 750 | CHP | TBD | 2020-04-06 | 2020-04-06 |  |  |  | 2020-04-20
2308171 | Boston | 2114 | 50 | CHP | 274-H3 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -31014 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online |  | Private
2327357 | Boston | 2114 | 50 | PV | 528-169H | 2019-02-14 | 2019-02-14 | 0 |  | 0 | 2019-02-28 |  | -31080 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
2366164 | Boston | 2114 | 66 | PV | TBD | 2019-08-23 | 2019-10-10 |  |  |  | 2019-10-29
2236712 | Boston | 2115 | 15.2 | PV | 2-1N45 | 2017-08-31 | 2017-09-05 | 2 |  | 2 | 2017-09-26 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-18 | 2017-12-19 | [6 empty] | 0 |  | 0 |  |  | 2018-04-24 | Online
2308328 | Boston | 2115 | 1600 | PV & Battery | 528-169H | 2018-11-27 |  | -31013 |  | 0 | 2018-12-26 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
2355610 | Boston | 2115 | 100 | PV | 493-1411H | 2019-08-07 | 2019-08-08 |  |  |  | 2019-08-21 | [24 empty] | 2019-10-28 | [12 empty] | 2020-12-29 | Online
2347214 | Boston | 2115 | 57.6 | PV | TBD | 2019-06-12 | 2019-06-14 |  |  |  | 2019-06-27
2351637 | Boston | 2115 | 43.2 | PV | TBD | 2019-06-27 | 2019-07-11 |  |  |  | 2019-07-26 | [38 empty] | Withdrawn
2410160 | Boston | 2115 | 180 | PV | TBD | 2020-07-28 | 2020-07-29 |  |  |  | 2020-08-14 | [24 empty] | 2020-10-08 | [13 empty] | Withdrawn
ESMAEX-02098 | Boston | 2115 | 15.2 | PV & Battery | 25N30 | 2023-02-01 | 2023-02-16 | [28 empty] | 2023-03-07 | [13 empty] | In Queue |  |  | Y
2367475 | Boston | 2116 | 1150 | CHP | TBD | 2019-09-25 | 2019-10-18 |  |  |  | 2019-11-05 | [38 empty] | Withdrawn
2223988 | Woburn | 2116 | 602 | PV | 375-H9 | 2017-06-05 | 2017-06-07 | 2 |  | 2 | 2017-07-06 |  | -30654 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30682 |  | 30682 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2168059 | Boston | 2118 | 75 | PV | 323-06 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-07 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
2340373 | Boston | 2118 | 60 | PV | 323-78H1 | 2019-04-19 | 2019-04-30 | 7 |  | 7 | 2019-05-21 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
2264049 | Boston | 2118 | 109.25 | PV | 318-10 | 2018-02-02 | 2018-02-08 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-18 | [6 empty] | 0 |  | 0
2265032 | Boston | 2118 | 30 | PV | 323-175H | 2018-02-02 | 2018-08-23 | 144 |  | 144 | 2018-08-23 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-25 | [7 empty] | 0 |  | 0
2331457 | Boston | 2118 | 1000 | PV & Battery | 4912 | 2019-02-11 | 2019-03-14 | 23 |  | 23 | 2019-03-26 |  | -31098 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2390327 | Boston | 2118 | 557.5 | PV & Battery | 4912 | 2020-02-10 | 2020-03-06 |  |  |  | 2020-03-19 | [24 empty] | 2020-11-12 | [12 empty] | 2023-02-02 | Online
2117954 | Boston | 2118 | 587 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2117955 | Boston | 2118 | 471 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00408 | Boston | 2118 | 100 | PV | 106-H4 | 2021-09-13 | 2021-11-16 | [28 empty] | 2021-11-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00722 | Boston | 2118 | 43.2 | PV | TBD | 2022-01-11 | 2022-03-01 | [28 empty] | 2022-03-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-00953 | Boston | 2118 | 51.9 | PV & Battery | 318-10 | 2022-03-21 | 2022-04-08 | [28 empty] | 2022-04-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-00995 | Boston | 2118 | 250 | PV & Battery | TBD | 2022-06-15 | 2022-08-01 | [28 empty] | 2022-08-18 | [13 empty] | In Queue |  |  | Y
2395617 | Dorchester | 2118 | 484 | PV | TBD | 2020-04-09 | [29 empty] | 2020-05-14 | [13 empty] | Withdrawn
2355992 | Boston | 2119 | 43.2 | PV | TBD | 2019-07-10 | 2019-08-09 |  |  |  | 2019-08-26 | [24 empty] | 2019-09-25 | [12 empty] | 2020-05-13 | Online
ESMAEX-01155 | Boston | 2119 | 30.16 | PV | 396-1050H | 2022-05-06 | 2022-06-02 | [28 empty] | 2022-06-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01407 | Boston | 2119 | 120 | PV | 465-129H | 2022-07-22 | 2022-08-15 | [28 empty] | 2022-08-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-02427 | Boston | 2119 | 50 | PV | TBD | 2023-04-28 | [43 empty] | In Queue |  |  | Y
2219411 | Roxbury | 2119 | 24 | PV | 483-H6 | 2017-05-13 | 2017-05-22 | 6 |  | 6 | 2017-06-07 |  | -30634 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-17 | 2017-09-20 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
2242468 | Roxbury | 2119 | 15.5 | PV | 52-148H1 | 2017-09-13 | 2017-10-17 | 23 |  | 23 | 2017-11-03 |  | -30738 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-29 | 2017-12-07 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
2313198 | Roxbury | 2119 | 36 | PV | 106-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31028 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
2312379 | Roxbury | 2119 | 199.8 | PV | 106-H4 | 2018-12-03 | 2018-12-03 | 0 |  | 0 | 2018-12-14 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
2349780 | Roxbury | 2119 | 37.8 | PV | tbd | 2019-06-27 | 2019-06-27 |  |  |  | 2019-07-15 | [24 empty] | 2019-08-06 | [12 empty] | 2020-12-17 | Online
2350185 | Roxbury | 2119 | 25 | PV | 106-1N31H4 | 2019-06-27 | 2019-06-27 |  |  |  | 2019-07-17 | [24 empty] | 2019-08-05 | [12 empty] | 2020-12-22 | Online
2344916 | Roxbury | 2119 | 52.2 | PV | TBD | 2019-05-16 | 2019-05-31 |  |  |  | 2019-06-19 | [24 empty] | 2019-08-06 | [12 empty] | 2020-12-29 | Online
2346323 | Roxbury | 2119 | 37.8 | PV | TBD | 2019-06-06 | 2019-06-10 |  |  |  | 2019-06-24 | [24 empty] | 2019-08-06 | [12 empty] | 2021-01-26 | Online
2165132 | Roxbury | 2119 | 57.6 | PV | 106-H5 | 2016-07-11 | 2016-07-28 | 13 |  | 13 | 2016-08-22 |  | -30432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2165395 | Roxbury | 2119 | 115.2 | PV | 106-H4 | 2016-07-13 | 2016-08-01 | 13 |  | 13 | 2016-08-24 |  | -30434 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00513 | Roxbury | 2119 | 52.2 | PV | 52-1499H4 | 2021-10-19 | 2021-11-15 | [28 empty] | 2021-11-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01062 | Roxbury | 2119 | 50 | PV | 510-77H3 | 2022-04-11 | 2022-04-28 | [28 empty] | 2022-05-02 | [12 empty] | 2023-03-08 | Online |  |  | Y
ESMAEX-02371 | Roxbury | 2119 | 67.3 | PV | TBD | 2023-04-12 | [43 empty] | In Queue |  |  | Y
2296721 | Boston | 2120 | 27 | PV | 5203 | 2018-06-25 | 2018-08-30 | 48 |  | 48 | 2018-09-18 | 2018-11-02 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-09 | Online |  | Private
2354057 | Boston | 2120 | 43.2 | PV | TBD | 2019-07-09 | 2019-07-24 |  |  |  | 2019-08-09 | [24 empty] | 2019-08-26 | [12 empty] | 2020-03-30 | Online
2354844 | Boston | 2120 | 43.2 | PV | TBD | 2019-07-10 | 2019-07-24 |  |  |  | 2019-08-15 | [24 empty] | 2019-08-29
4550665 | Boston | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 |  |  |  | 2020-12-04 | [24 empty] | 2020-12-15
4550829 | Boston | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 |  |  |  | 2020-12-04 | [24 empty] | 2020-12-18
ESMAEX-00858 | Boston | 2120 | 133.2 | PV | 5210 | 2022-02-25 | 2022-03-10 | [28 empty] | 2022-04-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-00152 | Roxbury | 2120 | 66.6 | PV | 350-H6 | 2021-05-27 | 2021-06-11 | [28 empty] | 2021-08-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-00768 | Roxbury | 2120 | 250 | PV | TBD | 2022-03-04 | 2022-03-21 | [28 empty] | 2022-04-04 | [13 empty] | In Queue |  |  | Y
2346835 | Roxbury | 2120 | 57.6 | PV | TBD | 2019-06-10 | 2019-06-13 |  |  |  | 2019-06-26 | [24 empty] | 2019-08-06 | [12 empty] | 2020-12-16 | Online
2374769 | Roxbury | 2120 | 55.8 | PV | TBD | 2019-12-02 | 2019-12-02 |  |  |  | 2019-12-17 | [24 empty] | 2020-01-03 | [12 empty] | 2020-12-16 | Online
2353454 | Roxbury | 2120 | 66.6 | PV | TBD | 2019-07-24 | 2019-07-24 |  |  |  | 2019-08-06 | [24 empty] | 2019-08-16 | [12 empty] | 2020-12-30 | Online
2354364 | Roxbury | 2120 | 22.8 | PV | 52-1499H2 | 2019-07-24 | 2019-07-24 |  |  |  | 2019-08-12 | [24 empty] | 2019-08-16 | [12 empty] | 2020-12-30 | Online
2328268 | Roxbury Crossing | 2120 | 72 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-06 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
4551603 | Stoneham | 2120 | 43.2 | PV | TBD | 2020-11-02 | 2020-11-02 |  |  |  | 2020-12-04 | [24 empty] | 2020-12-15 | [12 empty] | 2021-06-11 | Online
2358194 | Boston | 2121 | 20 | PV | TBD | 2019-07-10 | 2019-08-09 |  |  |  | 2019-09-06 | [24 empty] | 2019-11-05 | [12 empty] | 2020-05-29 | Online
2229788 | Dorchester | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-11 |  | -30680 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
2231017 | Dorchester | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-21 |  | -30686 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
2231683 | Dorchester | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
2231678 | Dorchester | 2121 | 36 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2017-12-04 | Online
2229211 | Dorchester | 2121 | 40.7 | PV | 483-H2 | 2017-07-10 | 2017-07-17 | 5 |  | 5 | 2017-08-08 |  | -30677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2230557 | Dorchester | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2230829 | Dorchester | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-18 |  | -30685 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2231474 | Dorchester | 2121 | 32.85 | PV | 143-109H4 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-23 |  | -30688 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
2267902 | Dorchester | 2121 | 43.2 | PV | 483-H5 | 2018-02-28 | 2018-02-28 | 0 |  | 0 | 2018-03-26 |  | -30837 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19 | Online
2137497 | Dorchester | 2121 | 57.6 | PV | 106-H2 | 2016-02-15 | 2016-02-26 | 9 |  | 9 | 2016-04-01 |  | -30331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2140849 | Dorchester | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2140850 | Dorchester | 2121 | 43.2 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
2140851 | Dorchester | 2121 | 43.2 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2141880 | Dorchester | 2121 | 30.4 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
2141881 | Dorchester | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2142397 | Dorchester | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2142398 | Dorchester | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2142654 | Dorchester | 2121 | 26.6 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2142655 | Dorchester | 2121 | 28.8 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
2142845 | Dorchester | 2121 | 45.6 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
2143232 | Dorchester | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2143233 | Dorchester | 2121 | 26.6 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
4500410 | Dorchester | 2121 | 16.8 | PV | TBD | 2020-10-07 | 2020-10-27 |  |  |  | 2020-11-23 | [24 empty] | 2020-11-25
2322890 | Dorchester | 2122 | 260 | PV & Battery | 483-H7 | 2019-01-02 |  | -31039 |  | 0 | 2019-01-31 |  | -31060 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
2259746 | Dorchester | 2122 | 51.75 | PV | 466-1481H1 | 2017-12-12 | 2018-01-03 | 15 |  | 15 | 2018-01-23 |  | -30793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-14 | 2018-03-28 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
2275333 | Dorchester | 2122 | 64 | PV | 466-1481H1 | 2018-04-12 | 2018-04-27 | 11 |  | 11 | 2018-05-07 |  | -30867 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
2384991 | Dorchester | 2122 | 100 | PV & Battery | 6702 | 2020-01-22 | 2020-01-28 |  |  |  | 2020-02-11 | [24 empty] | 2020-04-02 | [12 empty] | 2020-11-06 | Online
2369846 | Dorchester | 2122 | 66.6 | PV | TBD | 2019-11-05 | 2019-11-07 |  |  |  | 2020-01-03
ESMAEX-00799 | Dorchester | 2122 | 250 | PV & Battery | 43-1490H | 2022-08-04 | 2022-08-25 | [28 empty] | 2022-09-13 | [13 empty] | In Queue |  |  | Y
4659469 | Watertown | 2122 | 57.6 | PV | TBD | 2020-12-07 | 2020-12-14 |  |  |  | 2021-01-05 | [24 empty] | 2020-10-28 | [12 empty] | 2021-08-30 | Online
ESMAEX-00669 | Boston | 2124 | 130 | PV | 496-H8 | 2021-12-17 | 2022-01-20 | [28 empty] | 2022-02-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-00772 | Boston | 2124 | 480 | PV | 483-H1 | 2022-03-14 | 2022-03-31 | [28 empty] | 2022-04-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00797 | Boston | 2124 | 250 | PV | 511-1495H | 2022-03-14 | 2022-03-31 | [28 empty] | 2022-06-21 | [13 empty] | In Queue |  |  | Y
2166559 | Dorchester | 2124 | 20 | PV | 511-1497H3 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-08-22 |  | -30432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-22 | 2016-09-23 | [6 empty] | 0 |  | 0 |  |  | 2017-06-02 | Online |  | PRIVATE
2229935 | Dorchester | 2124 | 24 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-14 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-30 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
2231481 | Dorchester | 2124 | 30 | PV | 143-109H4 | 2017-07-18 | 2017-07-26 | 6 |  | 6 | 2017-08-23 |  | -30688 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
2232784 | Dorchester | 2124 | 72 | PV | 483-H4 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-09-05 |  | -30696 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-22 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03 | Online
2232422 | Dorchester | 2124 | 43.2 | PV | 483-H5 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-08-30 |  | -30693 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online
2232263 | Dorchester | 2124 | 48 | PV | 483-H7 | 2017-07-27 | 2017-07-31 | 2 |  | 2 | 2017-08-29 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
2220311 | Dorchester | 2124 | 45.15 | PV | 483-H7 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-06-13 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-07-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-23 | Online |  | PRIVATE
2352639 | Dorchester | 2124 | 199.8 | PV | TBD | 2019-07-01 | 2019-07-17 |  |  |  | 2019-08-01 | [24 empty] | 2019-10-10 | [12 empty] | 2020-06-19 | Online
2323443 | Dorchester | 2124 | 15.2 | PV | 483-H2 | 2019-01-07 | 2019-01-14 | 5 |  | 5 | 2019-02-01 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-24 | Online
4680348 | Dorchester | 2124 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-01-29 | [12 empty] | 2021-09-24 | Online
4615111 | Dorchester | 2124 | 15.2 | PV | TBD | 2020-12-01 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-11 | [13 empty] | Withdrawn
ESMAEX-00108 | Dorchester | 2124 | 15.2 | PV | 496-H8 | 2021-05-06 | 2021-05-25 | [28 empty] | 2021-07-07 | [12 empty] | 2022-04-15 | Online |  |  | Y
ESMAEX-02423 | Dorchester | 2124 | 15.2 | PV | 483-H2 | 2023-04-26 | [43 empty] | In Queue |  |  | Y
2358592 | Dorchester | 2124 | 45.4 | PV | 511-1498H1 | 2019-08-26 | 2019-08-26 |  |  |  | 2019-09-11 | [37 empty] | 2020-10-28 | Online
2333256 | Dorchester | 2124 | 240 | PV | 466-1481H1 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2291743 | Mattapan | 2124 | 86 | PV | 311-12 | 2018-07-27 | 2018-08-02 | 4 |  | 4 | 2018-08-15 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-06-19 | Online |  | Private
2346459 | Boston | 2125 | 133.2 | PV | 321-02 | 2019-06-07 | 2019-06-11 |  |  |  | 2019-06-27 | [24 empty] | 2019-08-05 | [12 empty] | 2019-12-31 | Online
2287285 | Boston | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30919 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-02 | Online
2287544 | Boston | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30919 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
2287285-B | Boston | 2125 | 500 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-19 |  | -30920 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2377476 | Boston | 2125 | 72 | PV | TBD | 2019-10-18 | 2019-11-22 |  |  |  | 2020-01-03 | [24 empty] | 2020-01-29
ESMAEX-00654 | Boston | 2125 | 90 | PV | 483-H3 | 2021-12-10 | 2021-12-30 | [28 empty] | 2022-01-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01900 | Boston | 2125 | 34.6 | PV & Battery | 106-1N31H1 | 2022-12-07 | 2023-01-04 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-02095 | Boston | 2125 | 67.3 | PV & Battery | 566-1475H | 2023-01-31 | 2023-03-08 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02096 | Boston | 2125 | 40 | PV & Battery | 566-1475H | 2023-01-31 | 2023-03-08 | [28 empty] | 2023-03-17 | [13 empty] | In Queue |  |  | Y
2225509 | Dorchester | 2125 | 210 | Fuel Cell | 106-H4 | 2017-06-15 | 2017-06-19 | 2 |  | 2 | 2017-07-17 |  | -30661 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2019-04-04 | Online
2412218 | Dorchester | 2125 | 19 | PV & Battery | 483-01 | 2020-07-29 | 2020-08-11 |  |  |  | 2020-08-28 | [24 empty] | 2020-09-14 | [12 empty] | 2020-12-31 | Online
2388772 | Dorchester | 2125 | 121.22 | PV | TBD | 2020-02-10 | 2020-02-19 |  |  |  | 2020-03-06 | [24 empty] | 2020-07-27 | [12 empty] | 2021-02-02 | Online
2326311 | Dorchester | 2125 | 1516 | PV | 466-1481H1 | 2019-01-28 |  | -31057 |  | 0 | 2019-02-22 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2388583 | Dorchester | 2125 | 366.3 | PV | TBD | 2020-02-18 | 2020-02-18 |  |  |  | 2020-03-06 | [24 empty] | 2020-09-02 | [13 empty] | Withdrawn
5392648 | Dorchester | 2125 | 15.2 | PV | TBD | 2021-02-12 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-05-10
ESMAEX-00561 | Dorchester | 2125 | 43.2 | PV | 106-1N31H1 | 2021-11-02 | 2021-11-23 | [28 empty] | 2021-12-09 | [12 empty] | 2022-08-12 | Online |  |  | Y
ESMAEX-01137 | Dorchester | 2125 | 43.5 | PV | 483-H3 | 2022-05-03 | 2022-05-26 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01138 | Dorchester | 2125 | 31.7 | PV | 6703 | 2022-05-03 | 2022-05-26 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01305 | Dorchester | 2125 | 499 | PV & Battery | 106-H2 | 2022-06-17 | 2022-07-07 | [28 empty] | 2022-08-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01505 | Dorchester | 2125 | 72 | PV & Battery | 483-H1 | 2022-08-24 | 2022-09-09 | [28 empty] | 2022-09-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-02420 | Dorchester | 2125 | 480 | PV | 511-1495H1 | 2023-04-26 | [43 empty] | In Queue |  |  | Y
2404393 | Boston | 2126 | 129.6 | PV | TBD | 2020-06-08 | 2020-06-15 |  |  |  | 2020-07-01 | [24 empty] | 2020-07-08
ESMAEX-00857 | Boston | 2126 | 240 | PV | 311-01 | 2022-02-25 | 2022-03-10 | [28 empty] | 2022-03-25 | [13 empty] | In Queue |  |  | Y
2236312 | Mattapan | 2126 | 30.5 | PV | 311-12 | 2017-08-31 | 2017-08-31 | 0 |  | 0 | 2017-09-22 |  | -30709 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
4683605 | Mattapan | 2126 | 7.6 | PV | TBD | 2020-12-14 | 2020-12-22 |  |  |  | 2021-01-25 | [24 empty] | 2021-02-22
ESMAEX-00192 | Mattapan | 2126 | 78.8 | PV | 496-H8 | 2021-06-18 | 2021-07-27 | [28 empty] | 2021-08-23 | [12 empty] | 2022-07-12 | Online |  |  | Y
ESMAEX-00796 | Mattapan | 2126 | 250 | PV & Battery | 311-09 | 2022-08-04 | 2022-09-09 | [28 empty] | 2022-09-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01121 | Mattapan | 2126 | 24.78 | PV & Battery | 441-02 | 2022-04-27 | 2022-05-18 | [28 empty] | 2022-05-23 | [12 empty] | 2022-11-18 | Online |  |  | Y
2355397 | Boston | 2127 | 275 | PV & Battery | 293-09 | 2019-07-12 | 2019-08-05 |  |  |  | 2019-08-20 | [24 empty] | 2019-10-24 | [12 empty] | 2020-12-14 | Online
ESMAEX-00862 | Boston | 2127 | 240 | PV | 385-H18 | 2022-02-28 | 2022-03-11 | [28 empty] | 2022-04-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-02263 | Boston | 2127 | 34.6 | PV | 385-H1 | 2023-03-14 | 2023-04-20 | [28 empty] | 2023-04-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-02339 | Boston | 2127 | 20 | PV | 385-H19 | 2023-04-04 | 2023-04-20 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
2333766 | South Boston | 2127 | 172.8 | PV | 106-H3 | 2019-03-05 | 2019-03-25 | 14 |  | 14 | 2019-04-09 |  | -31108 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
ESMAEX-00116 | South Boston | 2127 | 100 | PV | 385-H1 | 2021-05-11 | 2021-06-11 | [28 empty] | 2021-08-02 | [12 empty] | 2023-04-20 | Online |  |  | Y
ESMAEX-00753 | South Boston | 2127 | 28.8 | PV | 385-H19 | 2022-01-24 | 2022-02-28 | [28 empty] | 2022-03-07 | [12 empty] | 2023-02-01 | Online |  |  | Y
2158329 | South Boston | 2127 | 486.2 | PV | 385-H17 | 2016-05-11 | 2016-05-16 | 3 |  | 3 | 2016-06-08 |  | -30379 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2169753 | Boston | 2128 | 167 | PV | 108-196H1 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
2313793 | Boston | 2128 | 250 | PV | 488-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
2409919 | Boston | 2128 | 57.6 | PV | TBD | 2020-08-07 | [29 empty] | 2020-10-15 | [12 empty] | 2021-03-22 | Online
ESMAEX-00769 | Boston | 2128 | 250 | PV | 488-H4 | 2022-03-14 | 2022-03-31 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
ESMAEX-00885 | Boston | 2128 | 249.9 | PV & Battery | 152-87H | 2022-03-07 | 2022-03-28 | [28 empty] | 2022-05-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-01202 | Boston | 2128 | 126.3 | PV & Battery | TBD | 2022-05-20 | 2022-06-09 | [28 empty] | 2022-06-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01396 | Boston | 2128 | 100 | PV | 108-195H1 | 2022-07-21 | 2022-08-15 | [28 empty] | 2022-10-21 | [13 empty] | In Queue |  |  | Y
2173575 | East Boston | 2128 | 75 | CHP | 488-H8 | 2016-09-12 | 2016-10-04 | 16 |  | 16 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2016-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-02-10 | Online |  | NO EXPORT | N
ESMAEX-00411 | East Boston | 2128 | 75 | Internal Combustion Engine | 488-H5 | 2021-09-14 | 2021-09-30 | [28 empty] | 2021-11-04 | [12 empty] | 2022-08-22 | Online |  |  | N
ESMAEX-01169 | East Boston | 2128 | 43.5 | PV & Battery | 108-196H1 | 2022-05-11 | 2022-06-03 | [28 empty] | 2022-07-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01170 | East Boston | 2128 | 43.5 | PV | 108-196H1 | 2022-05-11 | 2022-06-03 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01201 | East Boston | 2128 | 126.3 | PV & Battery | 108-195H1 | 2022-05-20 | 2022-06-09 | [28 empty] | 2022-07-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01610 | East Boston | 2128 | 69.2 | PV | 488-H8 | 2022-09-20 | 2022-10-13 | [28 empty] | 2022-12-19 | [13 empty] | In Queue |  |  | Y
2324396 | East Boston | 2128 | 115.2 | PV | 488-H5 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-11 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2338574 | East Boston | 2128 | 43.2 | PV | 488-H5 | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31129 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2338586 | East Boston | 2128 | 28.8 | PV | 592-72XY | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31129 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2246431 | East Boston | 2128 | 978 | PV | 108-195H1 | 2017-10-31 | 2017-11-03 | 3 |  | 3 | 2017-11-21 |  | -30750 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | 2018-03-02 | [6 empty] | 0 |  | 0
2314366 | East Boston | 2128 | 79.2 | PV | 592-72XY |  | 2018-12-07 | 31020 |  | 31020 | 2018-12-28 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-02018 | Boston | 2129 | 4999 | PV | 5-208H | 2023-04-04 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02198 | Boston | 2129 | 240 | Battery | 218-80H1 | 2023-02-24 | 2023-03-08 | [42 empty] | In Queue |  |  | Y
2211409 | Charlestown | 2129 | 403.2 | PV & Battery | 5-208H/22-208 | 2017-03-16 | 2017-04-01 | 11 |  | 11 | 2017-04-18 |  | -30599 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-06 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2018-02-13 | Online
2368889 | Charlestown | 2129 | 250 | PV | TBD | 2019-10-22 | 2019-10-25 |  |  |  | 2019-11-18 | [24 empty] | 2020-02-06 | [13 empty] | Withdrawn
2370420 | Charlestown | 2129 | 100 | PV | TBD | 2019-11-04 | 2019-11-12 |  |  |  | 2019-11-26 | [24 empty] | 2019-12-02 | [13 empty] | Withdrawn
2394014 | Charlestown | 2129 | 4990 | PV | TBD | 2020-03-27 | 2020-03-31 |  |  |  | 2020-04-15 | [38 empty] | Withdrawn
ESMAEX-00488 | Charlestown | 2129 | 86.5 | PV | TBD | 2021-10-12 | 2021-11-03 | [28 empty] | 2022-01-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-00926 | Charlestown | 2129 | 3300 | PV & Battery | TBD | 2022-04-14 | 2022-05-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-01343 | Charlestown | 2129 | 4999 | Battery | 529-202 | 2022-09-23 | 2022-10-14 | [42 empty] | In Queue |  |  | Y
2283031 | Boston | 2130 | 38 | PV | 350-H11 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-21 |  | -30900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 |  |  | 2019-01-22 | Online
2206844 | Boston | 2130 | 75 | CHP | 536-76H2 | 2016-12-08 | 2017-03-08 | 61 |  | 61 | 2017-04-11 |  | -30595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-24 | Online
2326176 | Boston | 2130 | 37.8 | PV | 528-169H | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-22 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
ESMAEX-00771 | Boston | 2130 | 460 | PV & Battery | 350-H2 | 2022-03-04 | 2022-03-21 | [28 empty] | 2022-05-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01603 | Boston | 2130 | 100 | PV | 483-H6 | 2022-09-19 | 2022-10-07 | [28 empty] | 2022-10-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01604 | Boston | 2130 | 86.4 | PV & Battery | 483-H6 | 2022-09-19 | 2022-10-07 | [28 empty] | 2022-10-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01195 | Jamaica Plain | 2130 | 3.8 | PV | 496-H4 | 2022-05-18 | 2022-06-07 | [28 empty] | 2022-06-13 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-02135 | Jamaica Plain | 2130 | 10 | Battery | 284-1300H1 | 2023-02-07 | 2023-03-07 | [28 empty] | 2023-03-22 | [12 empty] | 2023-04-18 | Online |  |  | Y
ESMAEX-02176 | Jamaica Plain | 2130 | 15.2 | PV & Battery | 496-H4 | 2023-02-17 | 2023-03-08 | [28 empty] | 2023-03-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02338 | Jamaica Plain | 2130 | 25.37 | PV | 350-H2 | 2023-04-03 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
2305731 | Jamaica Plain | 2130 | 60 | PV | 284-02 | 2018-10-19 | 2018-11-08 | 14 |  | 14 | 2018-11-08 | 2018-11-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-12-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-02-26 | Online |  | Private
2258823 | Jamaica Plain | 2130 | 23 | PV | 284-02 | 2017-12-21 | 2017-12-28 | 4 |  | 4 | 2018-01-17 |  | -30789 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2335383 | Jamaica Plain | 2130 | 432.9 | PV | 496-H4 | 2019-04-02 | 2019-04-02 | 0 |  | 0 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-01 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
5287061 | Jamaica Plain | 2130 | 18 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 |  |  |  | 2021-03-26 | [24 empty] | 2021-05-12 | [13 empty] | Withdrawn
5530688 | Jamaica Plain | 2130 | 199.8 | PV | TBD | 2020-07-01 | 2021-04-06 |  |  |  | 2021-04-29 | [24 empty] | 2021-06-24 | [12 empty] | 2022-08-24 | Online
ESMAEX-00065 | Jamaica Plain | 2130 | 30 | PV | 396-1050H | 2021-04-21 | 2021-05-11 | [28 empty] | 2021-05-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01150 | Jamaica Plain | 2130 | 50 | PV | 284-1430H | 2022-05-05 | 2022-05-26 | [28 empty] | 2022-06-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01192 | Jamaica Plain | 2130 | 250 | PV | 396-01 | 2022-05-18 | 2022-06-07 | [28 empty] | 2022-06-22 | [13 empty] | In Queue |  |  | Y
2137255 | Jamaica Plain | 2130 | 21.9 | PV | 496-H4 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-29 |  | -30328 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-30 | 2016-04-08 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
4489427 | Jamaica Plain | 2130 | 400 | PV | TBD | 2020-10-16 | 2020-10-21 |  |  |  | 2020-11-17 | [37 empty] | 2022-03-28 | Online
2404933 | Jamaica Plain | 2130 | 1360 | PV | TBD | 2020-04-16 | 2020-06-02 |  |  |  | 2020-06-19
2403403 | Jamaica Plain | 2130 | 10 | PV & Battery | 284-1300H1 | 2020-05-20 | 2020-06-08 |  |  |  | 2020-06-23 | [24 empty] | 2020-08-05
4253275 | Jamaica Plain | 2130 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 |  |  |  | 2020-09-17 | [24 empty] | 2020-11-30 | [13 empty] | Withdrawn
4562972 | Jamaica Plain | 2130 | 75 | CHP | TBD | 2020-11-02 | 2020-11-04 |  |  |  | 2020-12-09 | [24 empty] | 2021-09-29 | [12 empty] | 2021-12-17 | Online
2329126 | Boston | 2131 | 20.7 | PV | 468-02 | 2019-01-04 | 2019-02-27 | 38 |  | 38 | 2019-03-12 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2019-08-05 | Online
2235080 | Boston | 2131 | 180 | PV | 385-H15 | 2017-07-06 | 2017-08-15 | 28 |  | 28 | 2017-09-18 |  | -30705 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | [7 empty] | 0 |  | 0
ESMAEX-00770 | Boston | 2131 | 250 | PV | 496-H8 | 2022-03-04 | 2022-03-21 | [28 empty] | 2022-06-21 | [13 empty] | In Queue |  |  | Y
2330819 | Roslindale | 2131 | 42.8 | PV | 1312 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-22 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05 | Online
2305544 | Roslindale | 2131 | 336 | PV & Battery | 496-H4 | 2018-10-24 | 2018-11-07 | 10 |  | 10 | 2018-11-07 | 2018-11-14 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-04 | Online |  | Private
2240297 | Roslindale | 2131 | 338 | PV | 496-H4 | 2017-09-12 | 2017-09-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
ESMAEX-00257 | Roslindale | 2131 | 10 | Battery | 516-06 | 2021-07-21 | 2021-08-04 | [28 empty] | 2021-10-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01698 | Roslindale | 2131 | 15.2 | PV & Battery | 1304 | 2022-10-19 | 2022-11-04 | [28 empty] | 2022-11-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01858 | Roslindale | 2131 | 6 | PV | 496-H5 | 2022-11-29 | 2022-12-09 | [28 empty] | 2023-04-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01975 | Roslindale | 2131 | 7.6 | PV & Battery | 496-H6 | 2023-01-06 | 2023-02-03 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
4677350 | Roslindale | 2131 | 18 | PV & Battery | 496-H8 | 2020-12-16 | 2020-12-16 |  |  |  | 2021-01-25 | [24 empty] | 2021-02-09 | [13 empty] | Withdrawn
ESMAEX-01699 | Boston | 2132 | 483 | PV | 496-H3 | 2022-10-19 | 2022-11-07 | [28 empty] | 2022-11-28 | [13 empty] | In Queue |  |  | Y
4425492 | West Roxbury | 2132 | 15.2 | PV | TBD | 2020-09-24 | 2020-10-07 |  |  |  | 2020-10-28 | [24 empty] | 2020-11-09 | [13 empty] | Withdrawn
ESMAEX-02372 | West Roxbury | 2132 | 15.3 | PV | 468-06 | 2023-04-13 | 2023-05-03 | [42 empty] | In Queue |  |  | Y
4642220 | West Roxbury | 2132 | 15.2 | PV | TBD | 2020-11-25 | 2020-12-01 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-06 | [13 empty] | Withdrawn
2378813 | West Roxbury | 2132 | 43.2 | PV | TBD | 2019-12-11 | 2019-12-19 |  |  |  | 2020-01-08 | [24 empty] | 2020-01-31 | [12 empty] | 2021-02-08 | Online
2193924 | West Roxbury | 2132 | 300 | CHP | 496-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2017-01-06 |  | -30530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-27 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-01-24 | Online
2205777 | West Roxbury | 2132 | 300 | Fuel Cell & Battery | 496-H3 | 2017-02-09 | 2017-02-27 | 11 |  | 11 | 2017-03-16 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-27 | 2017-11-03 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
2244684 | West Roxbury | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30744 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
2244833 | West Roxbury | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30744 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
2224405 | West Roxbury | 2132 | 498 | PV | 496-H3 | 2017-06-09 | 2017-06-19 | 6 |  | 6 | 2017-07-10 |  | -30656 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2263857 | West Roxbury | 2132 | 588 | PV | 496-H3 | 2018-02-01 | 2018-02-05 | 2 |  | 2 | 2018-02-05 |  | -30802 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2392188 | West Roxbury | 2132 | 344.8 | PV & Battery | TBD | 2020-03-05 | 2020-03-18 |  |  |  | 2020-04-03 | [24 empty] | 2020-07-07 | [12 empty] | 2021-10-15 | Online
2401149 | West Roxbury | 2132 | 149.8 | PV | TBD | 2020-04-27 | 2020-05-26 |  |  |  | 2020-06-08 | [24 empty] | 2020-08-14
2402181 | West Roxbury | 2132 | 226.9 | PV | TBD | 2020-04-27 | 2020-05-26 |  |  |  | 2020-06-16 | [24 empty] | 2020-07-15 | [13 empty] | Withdrawn
ESMAEX-00553 | West Roxbury | 2132 | 4999.2 | Battery | 496-H3 | 2022-03-09 | 2022-06-09 | [42 empty] | In Queue |  |  | Y
ESMAEX-02076 | West Roxbury | 2132 | 100 | PV | 496-H3 | 2023-01-27 | 2023-02-10 | [28 empty] | 2023-03-30 | [13 empty] | In Queue |  |  | Y
2168053 | Allston | 2134 | 60 | PV | 329-H7 | 2016-08-17 | 2016-08-22 | 3 |  | 3 | 2016-09-07 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-02 | Online |  | PRIVATE
2259136 | Allston | 2134 | 99.9 | PV | 456-H3 | 2017-12-02 | 2017-12-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
2322689 | Allston | 2134 | 57.6 | PV | 456-H3 | 2019-01-04 | 2019-01-09 | 3 |  | 3 | 2019-01-30 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
2392879 | Allston | 2134 | 36 | CHP | TBD | 2020-03-18 | 2020-03-20 |  |  |  | 2020-04-07 | [24 empty] | 2020-04-17 | [12 empty] | 2020-09-25 | Online
2294148 | Allston | 2134 | 70 | PV | 548-92H3 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-31 | 2018-11-16 | [6 empty] | 0 |  | 0
4367936 | Allston | 2134 | 125 | PV & Battery | TBD | 2020-09-18 | 2020-09-25 |  |  |  | 2020-10-15 | [24 empty] | 2020-11-05
ESMAEX-00263 | Allston | 2134 | 133.2 | PV | TBD | 2021-07-23 | 2021-08-12 | [28 empty] | 2021-09-01 | [12 empty] | 2022-09-27 | Online |  |  | Y
ESMAEX-00729 | Allston | 2134 | 40 | PV | 315-H8 | 2022-01-14 | 2022-02-10 | [28 empty] | 2022-03-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00972 | Allston | 2134 | 34.6 | PV | 315-H3 | 2022-03-28 | 2022-04-13 | [28 empty] | 2022-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01066 | Allston | 2134 | 480 | PV | TBD | 2022-05-20 | 2022-06-09 | [28 empty] | 2022-06-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-02105 | Allston | 2134 | 66.6 | Battery | 315-H3 | 2023-02-02 | 2023-03-21 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
2328228 | Boston | 2134 | 180 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-05 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-08 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online
2395099 | Boston | 2134 | 40 | PV | TBD | 2020-04-06 | 2020-04-09 |  |  |  | 2020-04-27 | [24 empty] | 2020-07-07 | [12 empty] | 2022-07-14 | Online
ESMAEX-01315 | Boston | 2134 | 200 | PV | 329-H2 | 2022-06-21 | 2022-07-07 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
2239744 | Brighton | 2134 | 7500 | CHP | TBD | 2017-10-04 | 2017-10-04 |  |  |  | 2017-10-13 | [24 empty] | 2018-10-26 | [12 empty] | 2019-12-11 | Online
4936614 | Brighton | 2134 | 43.2 | PV | TBD | 2021-01-21 | 2021-01-21 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-09
2235692 | Somerville | 2134 | 133.2 | PV | 250-1N39H1 | 2017-08-22 | 2017-08-28 | 4 |  | 4 | 2017-10-19 |  | -30727 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-16 | 2017-10-19 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
2267381 | Boston | 2135 | 75 | Gas Turbine | 548-193 | 2017-12-21 | 2018-02-21 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-08-27 | Online
ESMAEX-00519 | Boston | 2135 | 133.2 | PV | 329-H6 | 2021-10-20 | 2022-06-20 | [28 empty] | 2022-06-22 | [13 empty] | In Queue |  |  | Y
2389473 | Boston | 2135 | 1150 | PV & Battery | TBD | 2020-01-29 | 2020-02-25 |  |  |  | 2020-03-11 | [37 empty] | 2023-01-20 | Online
4637851 | Boston | 2135 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 |  |  |  | 2021-01-05 | [24 empty] | 2021-01-06
2337496 | Brighton | 2135 | 86.6 | PV | 329-H2 | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-03 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
2367836 | Brighton | 2135 | 456 | PV | TBD | 2019-10-07 | 2019-10-22 |  |  |  | 2019-11-07 | [24 empty] | 2020-03-09 | [12 empty] | 2021-04-30 | Online
2169751 | Brighton | 2135 | 64 | PV | 467-H12 | 2016-08-17 | 2016-08-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2337320 | Brighton | 2135 | 250 | PV | 467-H12 | 2019-03-29 | 2019-04-03 | 3 |  | 3 | 2019-05-02 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
5256844 | Brighton | 2135 | 43.2 | PV | TBD | 2021-02-03 | 2021-03-05 |  |  |  | 2021-03-22 | [24 empty] | 2021-04-06 | [12 empty] | 2022-02-07 | Online
ESMAEX-00030 | Brighton | 2135 | 150 | Internal Combustion Engine | TBD | 2021-04-06 | 2021-05-04 | [28 empty] | 2021-11-15 | [12 empty] | 2021-12-28 | Online |  |  | N
ESMAEX-00117 | Brighton | 2135 | 100 | PV | 329-H6 | 2021-05-11 | 2021-06-11 | [28 empty] | 2021-07-20 | [12 empty] | 2023-04-20 | Online |  |  | Y
ESMAEX-00405 | Brighton | 2135 | 100 | PV | 329-H2 | 2021-09-10 | 2021-09-29 | [28 empty] | 2021-10-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-01433 | Brighton | 2135 | 100000 | PV | 315-H1 | 2022-08-04 | 2022-08-25 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
2395480 | Boston | 2136 | 99.9 | PV | TBD | 2020-04-06 | 2020-04-13 |  |  |  | 2020-04-27
2322577 | Hyde Park | 2136 | 60 | PV | 344-08 | 2019-01-18 | 2019-01-18 | 0 |  | 0 | 2019-01-29 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
2381556 | Hyde Park | 2136 | 19 | PV | 60-1409H1 | 2019-10-31 | 2019-12-02 |  |  |  | 2020-01-15 | [24 empty] | 2020-01-30 | [12 empty] | 2020-08-31 | Online
2339703 | Hyde Park | 2136 | 40 | PV | 311-13 | 2019-04-19 | 2019-04-29 | 6 |  | 6 | 2019-05-14 |  | -31133 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
2383520 | Hyde Park | 2136 | 333.2 | PV | TBD | 2020-01-02 | 2020-01-13 |  |  |  | 2020-01-30 | [24 empty] | 2020-04-20 | [12 empty] | 2020-12-15 | Online
2258119 | Hyde Park | 2136 | 19.6 | PV | 60-1409H1 | 2017-12-13 | 2017-12-18 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2313809 | Hyde Park | 2136 | 15.2 | PV | 441-06 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2414035 | Hyde Park | 2136 | 15.2 | PV | TBD | 2020-08-04 | 2020-08-18 |  |  |  | 2020-09-09 | [24 empty] | 2020-09-16 | [12 empty] | 2021-07-08 | Online
4258230 | Hyde Park | 2136 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 |  |  |  | 2020-09-29 | [37 empty] | 2021-09-27 | Online
2126261 | Hyde Park | 2136 | 5 | PV | 6006 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5392588 | Hyde Park | 2136 | 16 | PV | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-04-30
ESMAEX-00537 | Hyde Park | 2136 | 30.45 | PV | 60-1409H1 | 2021-10-21 | 2021-11-15 | [28 empty] | 2021-11-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00655 | Hyde Park | 2136 | 3.8 | PV | 441-02 | 2021-12-10 | 2021-12-30 | [28 empty] | 2022-01-04 | [12 empty] | 2023-03-29 | Online |  |  | Y
ESMAEX-01841 | Hyde Park | 2136 | 8 | PV & Battery | 344-03 | 2022-11-22 | 2022-12-29 | [28 empty] | 2023-02-08 | [13 empty] | In Queue |  |  | Y
2109233 | Cambridge | 2138 | 26.6 | PV | 821-05 | 2015-11-10 | 2015-11-10 | 0 |  | 0 | 2015-12-01 |  | -30243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-11 | 2016-01-19 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
2195978 | Cambridge | 2138 | 42 | PV | 828-1NC8 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online |  | PRIVATE
2195981 | Cambridge | 2138 | 214.2 | PV | 821-05 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online
2187307 | Cambridge | 2138 | 23.4 | PV | 821-05 | 2016-11-21 | 2016-11-28 | 5 |  | 5 | 2016-12-07 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | 2017-02-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online |  | PRIVATE
2267013 | Cambridge | 2138 | 100.8 | PV | 829-19 | 2018-01-09 | 2018-02-20 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-05 | Online
2267217 | Cambridge | 2138 | 66.6 | PV | 814-13 | 2018-02-08 | 2018-02-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
2289823 | Cambridge | 2138 | 510 | Fuel Cell | 819-1NC3 | 2018-06-12 | 2018-07-20 | 28 |  | 28 | 2018-08-03 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 | 2018-12-20 |  | 2018-12-21 | Online
2295384 | Cambridge | 2138 | 80.5 | PV | 821-05 | 2018-07-31 | 2018-08-20 | 14 |  | 14 | 2018-09-07 | 2018-11-09 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26 | Online
2272015 | Cambridge | 2138 | 16 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30853 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26 | Online
2272017 | Cambridge | 2138 | 32 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30853 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-27 | Online
2282057 | Cambridge | 2138 | 28.8 | PV | 825-18 | 2018-05-29 | 2018-06-01 | 3 |  | 3 | 2018-06-15 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | [7 empty] | 0 |  | 0 |  |  | 2019-02-04 | Online |  | Private
2341088 | Cambridge | 2138 | 20.4 | PV | 831-1336XY | 2019-04-17 | 2019-05-15 | 20 |  | 20 | 2019-05-23 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2327251 | Cambridge | 2138 | 86.4 | PV | 831-1336XY | 2019-02-14 | 2019-02-22 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
2259341 | Cambridge | 2138 | 13.6 | PV & Battery | 821-22 | 2017-12-14 | 2018-01-03 | 13 |  | 13 | 2018-01-22 |  | -30792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0
2259916 | Cambridge | 2138 | 53.3 | PV | 830-11 | 2017-12-14 | 2018-01-03 | 13 |  | 13 | 2018-01-24 |  | -30794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-04-19 | [6 empty] | 0 |  | 0
2343786 | Cambridge | 2138 | 924 | PV | 831-1336XY | 2019-05-21 | 2019-05-30 |  |  |  | 2019-06-07
2345372 | Cambridge | 2138 | 330 | PV | TBD | 2019-05-21 | 2019-06-03 |  |  |  | 2019-06-18 | [38 empty] | Withdrawn
2398561 | Cambridge | 2138 | 200 | PV | TBD | 2020-03-27 | 2020-04-30 |  |  |  | 2020-05-18 | [24 empty] | 2020-08-05 | [12 empty] | 2022-03-17 | Online
ESMAEX-00308 | Cambridge | 2138 | 17.6 | PV & Battery | 825-18 | 2021-08-13 | 2021-10-21 | [28 empty] | 2021-11-10 | [12 empty] | 2022-05-03 | Online |  |  | Y
ESMAEX-00350 | Cambridge | 2138 | 17.6 | PV & Battery | 830-11 | 2021-08-26 | 2021-09-14 | [28 empty] | 2021-09-20 | [12 empty] | 2022-05-02 | Online |  |  | Y
ESMAEX-00597 | Cambridge | 2138 | 34.2 | PV | 821-05 | 2021-11-17 | 2021-12-30 | [28 empty] | 2022-01-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-01099 | Cambridge | 2138 | 10 | PV & Battery | 827-21 | 2022-04-21 | 2022-06-02 | [28 empty] | 2022-06-13 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01109 | Cambridge | 2138 | 56.3 | PV | 827-18 | 2022-04-25 | 2022-05-23 | [28 empty] | 2022-06-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01703 | Cambridge | 2138 | 30 | PV & Battery | 819-1306 | 2022-10-21 | 2022-11-04 | [28 empty] | 2022-12-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01911 | Cambridge | 2138 | 40 | PV | 831-1111 | 2022-12-09 | 2023-01-04 | [28 empty] | 2023-01-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-02115 | Cambridge | 2138 | 25.2 | PV & Battery | 830-11 | 2023-02-04 | 2023-03-02 | [28 empty] | 2023-03-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02188 | Cambridge | 2138 | 9.6 | Battery | 823-21 | 2023-02-22 | 2023-03-21 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
2169551 | Cambridge | 2139 | 57.6 | PV | 814-13 | 2016-09-02 | 2016-09-07 | 3 |  | 3 | 2016-09-15 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-06 | Online |  | PRIVATE
2187497 | Cambridge | 2139 | 60 | CHP | 831-1NC7 | 2016-10-31 | 2016-11-05 | 4 |  | 4 | 2016-12-08 |  | -30510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-26 | Online |  | PRIVATE
2214784 | Cambridge | 2139 | 14.4 | PV | 831-1NC7 | 2017-03-31 | 2017-04-11 | 7 |  | 7 | 2017-05-09 |  | -30614 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-25 | 2018-03-01 | [6 empty] | 0 |  | 0 |  |  | 2018-09-07 | Online
2207242 | Cambridge | 2139 | 75 | CHP | 817-03 | 2017-03-08 | 2017-03-20 | 8 |  | 8 | 2017-03-23 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-06-21 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26 | Online
2238845 | Cambridge | 2139 | 1330 | PV | 875-1312 | 2017-06-02 | 2017-10-05 | 87 |  | 87 | 2017-10-06 |  | -30719 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-09 | 2018-01-05 | -4 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online |  | Public
2244680 | Cambridge | 2139 | 33.3 | PV | 814-13 | 2017-10-17 | 2017-10-19 | 2 |  | 2 | 2017-11-13 |  | -30744 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2259745 | Cambridge | 2139 | 76.6 | PV | 814-13 | 2017-12-14 | 2018-01-03 | 13 |  | 13 | 2018-01-23 |  | -30793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-03-05 | [6 empty] | 0 |  | 0
2354628 | Cambridge | 2139 | 594.6 | PV & Battery | 831-1301 | 2019-06-18 | 2019-07-19 |  |  |  | 2019-08-14
2352275 | Cambridge | 2139 | 694 | PV & Battery | 831-1118 | 2019-06-19 | 2019-07-19 |  |  |  | 2019-07-31
2352522 | Cambridge | 2139 | 460 | PV & Battery | 831-1304 | 2019-06-19 | 2019-07-19 |  |  |  | 2019-07-31 | [24 empty] | 2020-02-06
2353669 | Cambridge | 2139 | 133.2 | PV | TBD | 2019-06-19 | 2019-07-19 |  |  |  | 2019-08-06 | [24 empty] | 2019-11-25
2405400 | Cambridge | 2139 | 16 | PV & Battery | 817-03 | 2020-06-15 | 2020-06-22 |  |  |  | 2020-07-06 | [24 empty] | 2020-09-11
4406125 | Cambridge | 2139 | 77.8 | PV | TBD | 2020-09-30 | 2020-09-30 |  |  |  | 2020-10-23 | [24 empty] | 2020-11-09 | [12 empty] | 2021-06-21 | Online
4713423 | Cambridge | 2139 | 75 | CHP | 831-1394 | 2020-12-31 | 2020-12-31 |  |  |  | 2021-01-25 | [24 empty] | 2021-10-04 | [12 empty] | 2022-03-17 | Online
ESMAEX-00251 | Cambridge | 2139 | 129.6 | PV | 875-1328 | 2021-07-20 | 2021-09-24 | [28 empty] | 2021-10-19 | [12 empty] | 2023-04-26 | Online |  |  | Y
ESMAEX-00638 | Cambridge | 2139 | 14.79 | PV | 817-46 | 2021-12-03 | 2022-01-03 | [28 empty] | 2022-01-27 | [12 empty] | 2022-11-02 | Online |  |  | Y
ESMAEX-00913 | Cambridge | 2139 | 9.15 | PV & Battery | 816-02 | 2022-03-14 | 2022-04-01 | [28 empty] | 2022-05-16 | [12 empty] | 2022-11-25 | Online |  |  | Y
ESMAEX-00918 | Cambridge | 2139 | 84.6 | PV & Battery | 820-15 | 2022-03-15 | 2022-05-31 | [28 empty] | 2022-06-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01118 | Cambridge | 2139 | 21.4 | PV | 820-45 | 2022-04-26 | 2022-05-23 | [28 empty] | 2022-06-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-02271 | Cambridge | 2139 | 7.6 | PV | 831-1NA6 | 2023-03-15 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02302 | Cambridge | 2139 | 22.125 | PV | 814-12 | 2023-03-23 | 2023-04-03 | [28 empty] | 2023-04-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-02353 | Cambridge | 2139 | 19.18 | PV | 817-03 | 2023-04-06 | 2023-04-24 | [28 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02373 | Cambridge | 2139 | 25.08 | PV | 814-12 | 2023-04-13 | 2023-04-24 | [42 empty] | In Queue |  |  | Y
2166793 | Cambridge | 2140 | 22.8 | PV | 825-27 | 2016-08-03 | 2016-08-04 | 1 |  | 1 | 2016-09-01 |  | -30440 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-21 | [6 empty] | 0 |  | 0 |  |  | 2017-01-03 | Online |  | PRIVATE
2172403 | Cambridge | 2140 | 66.6 | PV | 824-28 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-03 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-02 | 2016-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-06-26 | Online
2264395 | Cambridge | 2140 | 466.2 | PV | 828-1382 | 2018-02-02 | 2018-02-15 | 9 |  | 9 | 2018-02-26 | 2018-03-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-23 | 2018-06-14 |  |  | EXP |  |  |  | 0 |  | 0 | 2018-11-19 | 2018-11-19 | 2018-11-20 | Online
2166994 | Cambridge | 2140 | 115.2 | PV | 825-26 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-02 |  | -30441 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2184403 | Cambridge | 2140 | 2442 | PV | 828-1375 | 2016-10-24 | 2017-10-31 | 258 |  | 258 | 2016-12-02 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 |  | -30590 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2343568 | Cambridge | 2140 | 32.4 | PV | 824-26 | 2019-05-13 | 2019-05-22 |  |  |  | 2019-06-13 | [24 empty] | 2019-07-17
2412636 | Cambridge | 2140 | 19.12 | PV | TBD | 2020-08-12 | 2020-08-17 |  |  |  | 2020-09-09 | [24 empty] | 2020-09-11 | [12 empty] | 2021-09-08 | Online
4637828 | Cambridge | 2140 | 75 | CHP | TBD | 2020-11-18 | [29 empty] | 2021-11-08 | [12 empty] | 2022-11-15 | Online
ESMAEX-00182 | North Cambridge | 2140 | 22.8 | PV | 824-25 | 2021-06-13 | 2021-06-30 | [28 empty] | 2021-07-14 | [12 empty] | 2022-03-22 | Online |  |  | Y
ESMAEX-00732 | North Cambridge | 2140 | 6.38 | PV & Battery | 824-28 | 2022-01-18 | 2022-02-22 | [28 empty] | 2022-03-09 | [12 empty] | 2022-03-30 | Online |  |  | Y
2409461 | North Cambridge | 2140 | 14 | PV & Battery | 825-27 | 2020-06-11 | 2020-07-16 |  |  |  | 2020-08-04 | [37 empty] | 2020-11-17 | Online
4642185 | North Cambridge | 2140 | 19.57 | PV & Battery | TBD | 2020-11-06 | 2020-12-01 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-06 | [12 empty] | 2021-05-21 | Online
2217599 | Cambridge | 2141 | 153.2 | PV | 875-1N36B | 2017-04-25 | 2017-05-03 | 6 |  | 6 | 2017-05-30 |  | -30628 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-25 | 2017-08-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
2360150 | Cambridge | 2141 | 125 | CHP | TBD | 2019-08-05 | 2019-09-05 |  |  |  | 2019-09-19 | [24 empty] | 2020-09-18
2399827 | Cambridge | 2141 | 60 | CHP | TBD | 2020-02-04 | 2020-05-13 |  |  |  | 2020-05-29 | [24 empty] | 2020-07-08 | [12 empty] | 2022-06-22 | Online
2207411 | Cambridge | 2142 | 35 | CHP | 875-1328 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30585 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-09-07 | Online |  | PRIVATE | Y
2207804 | Cambridge | 2142 | 35 | CHP | 875-1343 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30585 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  | NO | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26 | Online |  | PRIVATE
2331739 | Cambridge | 2142 | 75 | PV | 875-1N35B | 2019-02-14 | 2019-03-15 | 21 |  | 21 | 2019-03-28 |  | -31100 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
2280401 | Cambridge | 2142 | 35 | CHP | 875-1399 | 2018-05-15 | 2018-05-22 | 5 |  | 5 | 2018-06-05 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-18 | [6 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
2301108 | Cambridge | 2142 | 63.3 | PV | 831-1336XY | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-12 | 2018-11-14 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-28 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-22 | Online |  | Private
2336049 | Cambridge | 2142 | 35 | CHP | 875-1N25A | 2019-03-12 | 2019-04-08 | 19 |  | 19 | 2019-04-23 |  | -31118 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0
ESMAEX-00758 | Cambridge | 2142 | 133.2 | PV | 850-1310 | 2022-01-26 | 2022-04-19 | [28 empty] | 2022-05-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01252 | Cambridge | 2142 | 100 | PV | TBD | 2022-06-02 | 2022-06-17 | [28 empty] | 2022-06-22 | [13 empty] | In Queue |  |  | Y
2178439 | Somerville | 2143 | 30.24 | PV | 250-1N90H2 | 2016-09-20 | 2016-09-29 | 7 |  | 7 | 2016-11-01 |  | -30483 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online |  | PRIVATE | Y
2169546 | Somerville | 2143 | 105 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-09 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-18 | Online
2169544 | Somerville | 2143 | 45 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  | 2019-02-05 | Online |  | PRIVATE
2267712 | Somerville | 2143 | 42 | PV | 250-1N81H1 | 2018-02-14 | 2018-02-28 | 10 |  | 10 | 2018-03-23 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-07-17 | Online
2359000 | Somerville | 2143 | 2400 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 |  |  |  | 2019-09-19 | [24 empty] | 2020-02-19 | [12 empty] | 2020-09-30 | Online
2276155 | Somerville | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30870 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30979 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0
2276157 | Somerville | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30870 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30979 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2359001 | Somerville | 2143 | 600 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 |  |  |  | 2019-09-19 | [24 empty] | 2020-02-19 | [12 empty] | 2021-07-08 | Online
2360135 | Somerville | 2143 | 1200 | CHP | TBD | 2019-08-06 | 2019-08-29 |  |  |  | 2019-09-19 | [24 empty] | 2020-02-19 | [12 empty] | 2021-07-08 | Online
2398711 | Somerville | 2143 | 211 | PV | TBD | 2020-05-05 | 2020-05-08 |  |  |  | 2020-05-27 | [24 empty] | 2020-07-07 | [12 empty] | 2022-03-11 | Online
2407835 | Somerville | 2143 | 22.8 | PV | TBD | 2020-06-02 | 2020-07-07 |  |  |  | 2020-07-27 | [24 empty] | 2020-07-29 | [12 empty] | 2021-08-04 | Online
2404942 | Somerville | 2143 | 22.8 | PV | TBD | 2020-06-15 | 2020-06-22 | [28 empty] | 2020-07-15 | [12 empty] | 2021-06-16 | Online
4467249 | Somerville | 2143 | 250 | PV | TBD | 2020-10-19 | 2020-10-19 |  |  |  | 2020-11-09 | [24 empty] | 2021-01-13
4506942 | Somerville | 2143 | 53.6 | PV & Battery | TBD | 2020-10-19 | 2020-10-27 |  |  |  | 2020-11-23 | [24 empty] | 2020-11-25 | [12 empty] | 2023-04-03 | Online
2133805 | Somerville | 2143 | 23.04 | PV | 250-1N90H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00742 | Somerville | 2143 | 14.8 | PV & Battery | 14N29 | 2022-01-20 | 2022-02-17 | [28 empty] | 2022-04-26 | [13 empty] | In Queue |  |  | Y
2253374 | Somerville | 2144 | 50.4 | PV | 1604 | 2017-11-10 | 2017-12-12 | 21 |  | 21 | 2017-12-28 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Online
2253264 | Somerville | 2144 | 52.2 | PV | 1604 | 2017-11-10 | 2017-12-12 | 21 |  | 21 | 2017-12-28 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
2253373 | Somerville | 2144 | 72 | PV | 1604 | 2017-11-10 | 2017-12-07 | 18 |  | 18 | 2017-12-28 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
2250465 | Somerville | 2144 | 100.8 | PV | 1604 | 2017-11-14 | 2017-11-29 | 10 |  | 10 | 2017-12-07 |  | -30761 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
2373814 | Somerville | 2144 | 133.2 | PV | TBD | 2019-11-18 | 2019-11-27 |  |  |  | 2019-12-10 | [24 empty] | 2020-02-18 | [12 empty] | 2022-02-09 | Online
5287647 | Somerville | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-10 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-21 | [13 empty] | Withdrawn
5540752 | Somerville | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-15 |  |  |  | 2021-04-29 | [24 empty] | 2021-05-12 | [13 empty] | Withdrawn
ESMAEX-01294 | West Somerville | 2144 | 8.418 | PV & Battery | 250-H6 | 2022-06-14 | 2022-07-13 | [28 empty] | 2022-09-19 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01788 | West Somerville | 2144 | 27.57 | PV & Battery | 1603 | 2022-11-09 | 2022-12-05 | [28 empty] | 2023-03-31 | [13 empty] | In Queue |  |  | Y
4878069 | West Somerville | 2144 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-09
2409513 | Orleans | 2145 | 245 | PV | TBD | 2020-07-15 | 2020-07-16 |  |  |  | 2020-08-04 | [24 empty] | 2021-06-21 | [13 empty] | Withdrawn
2308642 | Somerville | 2145 | 600 | Fuel Cell | 250-H4XY | 2018-11-15 | 2018-12-03 | 12 |  | 12 | 2018-12-03 |  | -31017 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online |  | Private
2338222 | Somerville | 2145 | 99.9 | PV | 250-H4XY | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-06 |  | -31127 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
2177085 | Somerville | 2145 | 210 | PV | 210-1N81H1 | 2016-08-19 | 2016-09-23 | 25 |  | 25 | 2016-10-25 |  | -30478 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2307640 | Somerville | 2145 | 250 | PV & Battery | 250-H4XY | 2018-11-08 | 2018-11-23 | 11 |  | 11 | 2018-11-23 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 | [5 empty] | Private
4487617 | Somerville | 2145 | 250 | PV | TBD | 2020-10-15 | 2020-10-15 |  |  |  | 2020-11-17 | [24 empty] | 2020-12-18 | [12 empty] | 2022-02-09 | Online
4642301 | Somerville | 2145 | 201.6 | PV | TBD | 2020-12-01 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-02-19
ESMAEX-00258 | Somerville | 2145 | 875 | PV | 286-1322H | 2021-09-01 | 2021-09-16 | [28 empty] | 2023-03-08 | [13 empty] | In Queue |  |  | Y
2291056 | Chelsea | 2150 | 33.3 | PV | 488-H7 | 2018-07-20 | 2018-07-25 | 3 |  | 3 | 2018-08-09 |  | -30935 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | 2018-10-03 | [6 empty] | 0 |  | 0 |  |  | 2019-11-07 | Online
2273723 | Chelsea | 2150 | 196.6 | PV | 488-H7 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 | 2018-11-20 | 147 |  | 147 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-03-26 | Online
2056439 | Chelsea | 2150 | 185.6 | PV | 488-H2 | 2015-02-03 | 2015-02-03 | 0 |  | 0 | 2015-03-21 |  | -30061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-15 | 2015-04-27 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2217046 | Chelsea | 2150 | 996 | PV | 14-113H1 | 2017-04-20 | 2017-04-27 | 5 |  | 5 | 2017-05-24 |  | -30625 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-11 | 2017-07-12 | [6 empty] | 0 |  | 0 | 2018-12-28
2273722 | Chelsea | 2150 | 153.2 | PV | 488-H6 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 |  | -30861 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2302133 | Chelsea | 2150 | 66.6 | PV | 488-H2 | 2018-09-26 | 2018-10-01 | 3 |  | 3 | 2018-10-18 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2346218 | Chelsea | 2150 | 1736 | CHP | TBD | 2019-03-20 | 2019-06-03 | 53 |  | 53 | 2019-06-24 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
ESMAEX-00093 | Chelsea | 2150 | 249 | PV & Battery | 488-H2 | 2021-04-30 | 2021-05-18 | [28 empty] | 2022-05-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-00580 | Chelsea | 2150 | 43.2 | PV | 488-H3 | 2021-11-10 | 2021-12-01 | [28 empty] | 2022-01-27 | [12 empty] | 2023-02-07 | Online |  |  | Y
ESMAEX-00581 | Chelsea | 2150 | 43.2 | PV | 488-H7 | 2021-11-10 | 2021-12-01 | [28 empty] | 2022-01-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-00652 | Chelsea | 2150 | 43.2 | PV | 488-H7 | 2021-12-09 | 2021-12-28 | [28 empty] | 2022-01-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-00672 | Chelsea | 2150 | 86.4 | PV | TBD | 2021-12-20 | 2022-01-11 | [28 empty] | 2022-01-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-00744 | Chelsea | 2150 | 250 | Battery | 488-H1 |  | 2022-03-24 | [28 empty] | 2022-04-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-00745 | Chelsea | 2150 | 250 | PV | TBD | 2022-03-08 | 2022-03-24 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-00747 | Chelsea | 2150 | 375 | PV | TBD | 2022-03-08 | 2022-03-24 | [28 empty] | 2022-10-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-00888 | Chelsea | 2150 | 495.8 | PV | TBD |  | 2022-04-14 | [28 empty] | 2022-05-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-00911 | Chelsea | 2150 | 16 | PV & Battery | 488-H7 | 2022-03-14 | 2022-05-13 | [28 empty] | 2022-06-13 | [13 empty] | In Queue |  |  | Y
2373967 | Chelsea | 2150 | 275 | PV & Battery | 488-H2 | 2019-11-08 | 2019-11-26 |  |  |  | 2019-12-12 | [24 empty] | 2020-01-29 | [12 empty] | 2020-11-06 | Online
2391483 | Chelsea | 2150 | 199.8 | PV | TBD | 2020-03-10 | 2020-03-12 |  |  |  | 2020-03-27 | [24 empty] | 2020-04-30 | [13 empty] | Withdrawn
2295249 | Boston | 2163 | 46 | PV | STATION890 | 2018-07-26 | 2018-08-20 | 17 |  | 17 | 2018-09-06 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online |  | Private
2346677 | Boston | 2163 | 43.2 | PV | TBD | 2019-05-31 | 2019-06-12 |  |  |  | 2019-06-26 | [24 empty] | 2019-09-11 | [12 empty] | 2019-12-31 | Online
2355531 | Boston | 2163 | 66.6 | PV | TBD | 2019-07-29 | 2019-08-05 |  |  |  | 2019-08-21 | [24 empty] | 2020-01-31 | [12 empty] | 2021-03-23 | Online
2196194 | Boston | 2163 | 32 | PV | 817-03 | 2016-12-22 | 2016-12-29 | 5 |  | 5 | 2017-01-11 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-02-28 | [6 empty] | 0 |  | 0 | [5 empty] | PRIVATE
2271561 | Boston | 2163 | 56 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-16 |  | -30852 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0
2355098 | Boston | 2163 | 166.6 | PV | TBD | 2019-07-19 | 2019-08-05 |  |  |  | 2019-08-21 | [24 empty] | 2020-02-21 | [12 empty] | 2021-05-24 | Online
ESMAEX-00733 | Boston | 2163 | 43.2 | PV | 831-1107 | 2022-01-18 | 2022-02-14 | [28 empty] | 2022-03-08 | [12 empty] | 2022-08-01 | Online |  |  | Y
4325236 | Fairhaven | 2179 | 300 | PV | TBD | 2020-09-08 | 2020-09-14 |  |  |  | 2020-10-05
2119971 | Stoneham | 2180 | 16.95 | PV | 375H8 | 2016-12-17 | 2016-12-22 | 4 |  | 4 | 2016-01-05 |  | -30268 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-06-27 | Online
2130639 | Stoneham | 2180 | 30.3 | PV | 301-03 | 2016-02-05 | 2016-02-10 | 3 |  | 3 | 2016-02-25 |  | -30305 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-06-01 | [6 empty] | 0 |  | 0 |  |  | 2016-12-14 | Online |  | PRIVATE
2170420 | Stoneham | 2180 | 84 | PV | 375-H7 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-20 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-14 | Online
2316352 | Stoneham | 2180 | 50 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2019-01-03 |  | -31040 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-03 | [7 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
2314500 | Stoneham | 2180 | 72 | PV | 375-H7 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2019-08-07 | Online
2288415 | Stoneham | 2180 | 17.17 | PV | 375-H8 | 2018-07-10 | 2018-07-24 | 10 |  | 10 | 2018-07-25 |  | -30924 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-28 | [7 empty] | 0 |  | 0 |  |  | 2020-01-24 | Online
2357040 | Stoneham | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-16 |  |  |  | 2019-09-05 | [24 empty] | 2019-10-08 | [12 empty] | 2020-04-02 | Online
2381326 | Stoneham | 2180 | 20 | PV & Battery | 375-H8 | 2019-11-18 | 2019-12-26 |  |  |  | 2020-01-13 | [37 empty] | 2020-06-19 | Online
2357591 | Stoneham | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-19 |  |  |  | 2019-09-04 | [24 empty] | 2019-10-08 | [12 empty] | 2020-09-16 | Online
2326872 | Stoneham | 2180 | 200 | PV | 375-H7 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-26 |  | -31078 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
2411309 | Stoneham | 2180 | 10 | PV & Battery | 375-H8 | 2020-07-22 | 2020-08-03 |  |  |  | 2020-08-24 | [24 empty] | 2020-11-09 | [12 empty] | 2021-02-08 | Online
2412543 | Stoneham | 2180 | 15.2 | PV | TBD | 2020-07-22 | 2020-08-14 |  |  |  | 2020-08-31 | [24 empty] | 2020-09-03 | [12 empty] | 2021-03-16 | Online
4841015 | Stoneham | 2180 | 15.2 | PV | 375-H8 | 2020-12-29 | 2021-01-11 |  |  |  | 2021-01-21 | [24 empty] | 2021-02-04 | [12 empty] | 2021-05-17 | Online
2257799 | Stoneham | 2180 | 15.95 | PV | 375-H8 | 2017-12-05 | 2017-12-11 | 4 |  | 4 | 2018-01-09 | 2018-11-01 | 212 |  | 212 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-01 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
2150045 | Stoneham | 2180 | 15.98 | PV | 375-H8 | 2016-05-13 | 2016-05-18 | 3 |  | 3 | 2016-06-02 |  | -30375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-08-10 | [6 empty] | 0 |  | 0 | [5 empty] | PRIVATE
2215757 | Stoneham | 2180 | 16.7 | PV | 375-H8 | 2017-04-14 | 2017-04-24 | 5 |  | 5 | 2017-05-16 |  | -30619 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-25 | [7 empty] | 0 |  | 0
2258388 | Stoneham | 2180 | 17.575 | PV | 375-H8 | 2017-12-18 | 2017-12-21 | 3 |  | 3 | 2018-01-12 |  | -30786 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2312221 | Stoneham | 2180 | 15.98 | PV | 375-H8 | 2018-11-07 | 2018-11-29 | 16 |  | 16 | 2018-12-13 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-01 | [7 empty] | 0 |  | 0
2314501 | Stoneham | 2180 | 150 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
2352776 | Stoneham | 2180 | 166.6 | PV | TBD | 2019-06-21 | 2019-07-17 |  |  |  | 2019-08-02 | [24 empty] | 2019-08-22 | [12 empty] | 2022-04-08 | Online
2397255 | Stoneham | 2180 | 15.2 | PV | TBD | 2020-03-17 | 2020-03-27 |  |  |  | 2020-05-08 | [24 empty] | 2020-07-29 | [13 empty] | Withdrawn
2393943 | Stoneham | 2180 | 486 | PV | TBD | 2020-03-25 | 2020-03-31 |  |  |  | 2020-04-15 | [24 empty] | 2021-01-28
4680468 | Stoneham | 2180 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-01-14 | [13 empty] | Withdrawn
4635296 | Stoneham | 2180 | 180 | PV | TBD | 2020-12-01 | 2020-12-01 |  |  |  | 2020-12-23 | [24 empty] | 2021-01-06 | [13 empty] | Withdrawn
4676006 | Stoneham | 2180 | 150 | PV | TBD | 2020-12-14 | 2020-12-14 |  |  |  | 2021-01-08 | [24 empty] | 2021-01-14 | [12 empty] | 2022-03-11 | Online
4841178 | Stoneham | 2180 | 19 | PV | TBD | 2020-12-29 | 2021-01-06 |  |  |  | 2021-01-25 | [24 empty] | 2021-02-01 | [12 empty] | 2021-08-19 | Online
ESMAEX-01007 | Stoneham | 2180 | 15.2 | PV | 375-H8 | 2022-04-04 | 2022-04-28 | [28 empty] | 2022-05-23 | [12 empty] | 2023-04-28 | Online |  |  | Y
ESMAEX-01174 | Stoneham | 2180 | 1500 | PV & Battery | 375-H8 | 2022-06-03 | 2022-06-22 | [42 empty] | In Queue |  |  | Y
ESMAEX-01425 | Stoneham | 2180 | 18.6 | PV & Battery | 375-H8 | 2022-08-03 | 2022-08-17 | [28 empty] | 2022-09-14 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01739 | Stoneham | 2180 | 7.6 | PV & Battery | 211-H12 | 2022-10-31 | 2022-11-16 | [28 empty] | 2022-12-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01794 | Stoneham | 2180 | 15.2 | PV & Battery | 211-H12 | 2022-11-09 | 2022-12-07 | [28 empty] | 2022-12-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01811 | Stoneham | 2180 | 10 | PV & Battery | 375-H2 | 2022-11-15 | 2022-12-08 | [28 empty] | 2023-01-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-01992 | Stoneham | 2180 | 15.2 | PV & Battery | 375-H8 | 2023-01-10 | 2023-01-31 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02257 | Stoneham | 2180 | 9.6 | Battery | 375-H2 | 2023-03-10 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
2109234 | Milton | 2186 | 32.4 | PV | 496-H7 | 2015-11-06 | 2015-11-30 | 16 |  | 16 | 2015-12-11 |  | -30251 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-06-10 | Online
2195721 | Milton | 2186 | 17.4 | PV | 60-1409H1 | 2016-11-28 | 2016-12-13 | 11 |  | 11 | 2017-01-09 |  | -30531 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-17 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online |  | PRIVATE
2241676 | Milton | 2186 | 21.9 | PV | 362-02 | 2017-10-03 | 2017-10-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-10 | 2017-11-13 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online
2335039 | Milton | 2186 | 61.2 | PV | 496-H2 | 2019-03-28 | 2019-04-01 | 2 |  | 2 | 2019-04-16 |  | -31113 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
2366661 | Milton | 2186 | 18.2 | PV | TBD | 2019-09-23 | 2019-10-21 |  |  |  | 2019-11-01 | [24 empty] | 2019-11-18 | [12 empty] | 2020-03-17 | Online
2395800 | Milton | 2186 | 57.6 | PV | TBD | 2020-02-13 | [29 empty] | 2020-06-23 | [12 empty] | 2020-10-16 | Online
2366684 | Milton | 2186 | 15.2 | PV | 311-11 | 2019-08-29 | [29 empty] | 2020-01-16 | [12 empty] | 2021-02-17 | Online
2144091 | Milton | 2186 | 25.05 | PV | 496-H7 | 2016-03-11 | 2016-04-01 | 15 |  | 15 | 2016-05-02 |  | -30352 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2265246 | Milton | 2186 | 15.2 | PV | 362-02 | 2018-02-09 | 2018-02-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2302387 | Milton | 2186 | 38 | PV | 362-03 | 2018-09-26 | 2018-10-02 | 4 |  | 4 | 2018-10-19 |  | -30986 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-04 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2353541 | Milton | 2186 | 25.2 | PV | 496-H7 | 2019-06-05 | 2019-07-26 |  |  |  | 2019-08-06 | [24 empty] | 2019-08-22 | [12 empty] | 2022-03-07 | Online
2406457 | Milton | 2186 | 21.67 | PV & Battery | 4303 | 2020-06-10 | 2020-06-23 |  |  |  | 2020-07-14 | [24 empty] | 2020-08-07
4380220 | Milton | 2186 | 17.6 | PV & Battery | TBD | 2020-09-22 | 2020-10-05 |  |  |  | 2020-10-21 | [24 empty] | 2021-04-01
4680587 | Milton | 2186 | 16 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-03-09
4983372 | Milton | 2186 | 15.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 |  |  |  | 2021-02-11 | [24 empty] | 2021-03-05 | [12 empty] | 2021-06-24 | Online
4850213 | Milton | 2186 | 23.78 | PV | TBD | 2021-01-07 | 2021-01-07 |  |  |  | 2021-01-28 | [24 empty] | 2021-03-09
4921183 | Milton | 2186 | 15.2 | PV | 311-04 | 2021-01-12 | 2021-01-19 |  |  |  | 2021-02-02 | [24 empty] | 2021-03-05
ESMAEX-00607 | Milton | 2186 | 19.8 | Battery | 496-H2 | 2021-11-18 | 2022-01-06 | [28 empty] | 2022-02-07 | [12 empty] | 2022-12-16 | Online |  |  | Y
ESMAEX-00923 | Milton | 2186 | 15.2 | PV & Battery | 496-H7 | 2022-03-15 | 2022-04-06 | [28 empty] | 2022-04-11 | [12 empty] | 2022-10-27 | Online |  |  | Y
ESMAEX-01160 | Milton | 2186 | 11.52 | PV & Battery | 362-02 | 2022-05-09 | 2022-06-02 | [28 empty] | 2022-06-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01171 | Milton | 2186 | 17.6 | PV & Battery | 496-H7 | 2022-05-11 | 2022-06-09 | [28 empty] | 2022-06-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01368 | Milton | 2186 | 17.6 | PV & Battery | 4309 | 2022-07-12 | 2022-08-15 | [28 empty] | 2022-09-06 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01545 | Milton | 2186 | 13.44 | PV & Battery | 362-05 | 2022-09-06 | 2022-10-07 | [28 empty] | 2022-11-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01781 | Milton | 2186 | 15.2 | PV | 362-05 | 2022-11-08 | 2022-11-29 | [28 empty] | 2022-12-07 | [12 empty] | 2023-03-14 | Online |  |  | Y
ESMAEX-02091 | Milton | 2186 | 16 | PV & Battery | 470-H9 | 2023-01-30 | 2023-02-10 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
2169723 | Boston | 2188 | 72 | PV | 106-H4 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2017-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-11-09 | Online
2297504 | Boston | 2210 | 75 | PV | 323-06 | 2018-08-09 | 2018-09-05 | 19 |  | 19 | 2018-09-20 | 2018-11-02 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-11-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-27 | Online |  | Private
2387593 | Boston | 2210 | 233.3 | PV | TBD | 2019-12-19 | 2020-02-14 |  |  |  | 2020-02-27 | [38 empty] | Withdrawn
ESMAEX-00510 | Boston | 2210 | 2000 | Other | 99-H3 | 2023-01-13 | 2023-02-03 | [42 empty] | In Queue |  |  | N
ESMAEX-00512 | Boston | 2210 | 1400 | Other | 420-154 | 2023-01-13 | 2023-02-07 | [42 empty] | In Queue |  |  | N
ESMAEX-00518 | Boston | 2210 | 1400 | Other | 99-H5 | 2023-01-13 | 2023-02-03 | [42 empty] | In Queue |  |  | N
ESMAEX-01026 | Boston | 2210 | 300 | PV | 385-H12 | 2022-06-17 | 2022-07-13 | [28 empty] | 2022-08-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-01063 | Boston | 2210 | 750 | PV | 99-H6 | 2022-05-12 | 2022-06-08 | [28 empty] | 2023-04-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01096 | Boston | 2210 | 1500 | PV & Battery | 99-H4 | 2022-04-21 | 2022-05-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01950 | Boston | 2210 | 360 | PV & Battery | 99-H3 | 2023-02-24 | 2023-03-21 | [42 empty] | In Queue |  |  | Y
2236713 | Boston | 2215 | 21.9 | PV | 350-H10 | 2017-08-31 | 2017-09-05 | 2 |  | 2 | 2017-09-26 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-08 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
4352975 | Boston | 2215 | 75 | CHP | TBD | 2020-09-24 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2021-04-02 | [12 empty] | 2021-08-19 | Online
ESMAEX-00460 | Boston | 2215 | 120.8 | PV | 350-H12 | 2021-09-30 | 2021-10-18 | [28 empty] | 2021-11-09 | [12 empty] | 2022-08-08 | Online |  |  | Y
ESMAEX-00666 | Boston | 2215 | 116 | PV | TBD | 2021-12-15 | 2022-01-20 | [28 empty] | 2022-02-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01104 | Boston | 2215 | 70 | PV | 329-H9 | 2022-04-24 | 2022-05-23 | [28 empty] | 2022-05-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01105 | Boston | 2215 | 170 | PV | TBD | 2022-04-24 | 2022-05-23 | [28 empty] | 2022-05-23 | [13 empty] | In Queue |  |  | Y
2114406 | Carver | 2330 | 17.5 | PV | 3-83-950 | 2015-11-19 | 2016-01-05 | 33 |  | 33 | 2016-02-11 |  | -30295 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online |  | PRIVATE
2135870 | Carver | 2330 | 34.2 | PV | 3-10-930 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-21 |  | -30322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-09 | 2016-05-12 | [6 empty] | 0 |  | 0 |  |  | 2017-01-20 | Online
2137495 | Carver | 2330 | 1860 | PV | 3-51-980 | 2016-03-08 | 2016-03-08 | 0 |  | 0 | 2016-03-29 |  | -30328 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-15 | 2016-08-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online
2234830 | Carver | 2330 | 21.9 | PV | 3-10-929 | 2017-08-10 | 2017-08-15 | 3 | 0 | 3 | 2017-09-13 |  | -30702 | 6 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-24 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
2221535 | Carver | 2330 | 2000 | PV | 3-10-10 | 2017-05-19 | 2017-05-30 | 6 |  | 6 | 2017-06-21 |  | -30644 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-08-16 | -16 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2019-05-17 | Online
2382007 | Carver | 2330 | 50 | PV | TBD | 2019-12-26 | 2020-01-06 |  |  |  | 2020-01-17 | [24 empty] | 2020-02-07 | [12 empty] | 2021-01-14 | Online
2214971 | Carver | 2330 | 30 | PV | 3-81-950 | 2017-04-13 | 2017-04-21 | 5 |  | 5 | 2017-05-16 |  | -30619 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-05 | 2017-07-14 | [6 empty] | 0 |  | 0
2247816 | Carver | 2330 | 1500 | PV | 3-10-10 | 2017-10-27 | 2017-11-08 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | [7 empty] | 0 |  | 0
2250250 | Carver | 2330 | 8300 | PV & Battery | 3-81-81 | 2017-11-14 | 2017-11-14 | 0 |  | 0 | 2017-12-06 |  | -30760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
2255727 | Carver | 2330 | 5980 | PV & Battery | 3-83-83 | 2017-11-20 | 2017-12-11 | 14 |  | 14 | 2018-01-08 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
2260848 | Carver | 2330 | 6415 | PV | 3-10-917 | 2017-12-11 | 2018-01-02 | 15 |  | 15 | 2018-01-31 |  | -30799 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2272654 | Carver | 2330 | 104.4 | PV | 3-81-81 | 2018-03-16 | 2018-04-03 | 12 |  | 12 | 2018-04-20 |  | -30856 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-18 | [6 empty] | 0 |  | 0 |  |  | 2021-06-18 | Online
2272658 | Carver | 2330 | 2980 | PV & Battery | 3-10-10 | 2018-03-27 | 2018-04-05 | 7 |  | 7 | 2018-04-20 |  | -30856 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0
2277381 | Carver | 2330 | 8980 | PV & Battery | 3-81-81 | 2018-04-06 | 2018-05-04 | 20 |  | 20 | 2018-05-22 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
2281482 | Carver | 2330 | 1000 | PV & Battery | 3-81-950 | 2018-05-18 | 2018-05-30 | 8 |  | 8 | 2018-06-12 |  | -30893 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
2288775 | Carver | 2330 | 5000 | PV & Battery | 3-83-83 | 2018-07-06 | 2018-07-12 | 4 |  | 4 | 2018-07-27 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
2292181 | Carver | 2330 | 2468 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2292181 - A | Carver | 2330 | 2000 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2292181 - B | Carver | 2330 | 466 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2296720 | Carver | 2330 | 3500 | PV | 3-10-10 | 2018-08-27 | 2018-08-29 | 2 |  | 2 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2299346 | Carver | 2330 | 8300 | PV & Battery | 3-51-901 | 2018-09-07 | 2018-09-11 | 2 |  | 2 | 2018-10-02 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5132501 | Carver | 2330 | 3000 | PV & Battery | 3-81-81 | 2018-10-04 | 2018-10-11 | 5 |  | 5 | 2018-10-31 |  | -30994 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2306416 | Carver | 2330 | 1625 | PV | 3-10-929 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2308513 | Carver | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-11-15 | 2018-11-30 | 11 |  | 11 | 2018-11-30 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2314369 | Carver | 2330 | 3500 | PV | 3-81-950 | 2018-11-27 | 2018-12-10 | 9 |  | 9 | 2018-12-28 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2320444 | Carver | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-12-16 | 2018-12-19 | 3 |  | 3 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2321677 | Carver | 2330 | 6500 | PV | 3-10-930 | 2019-01-07 | 2019-01-08 | 1 |  | 1 | 2019-01-23 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2324188 | Carver | 2330 | 2350 | PV | 3-10-930 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-08 |  | -31066 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2326793 | Carver | 2330 | 2000 | PV | 3-10-917 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-25 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2335827 | Carver | 2330 | 2000 | PV & Battery | 3-81-950 | 2019-03-28 | 2019-04-04 | 5 |  | 5 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2338339 | Carver | 2330 | 9500 | PV & Battery | 3-81-950 | 2019-04-08 | 2019-04-30 | 16 |  | 16 | 2019-05-07 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2351984 | Carver | 2330 | 4999 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 |  |  |  | 2019-07-29
2361242 | Carver | 2330 | 4999 | PV & Battery | TBD | 2019-09-04 | 2019-09-11 |  |  |  | 2019-09-27
2361243 | Carver | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-13 |  |  |  | 2019-10-01 | [38 empty] | Withdrawn
2361424 | Carver | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 |  |  |  | 2019-09-27 | [38 empty] | Withdrawn
2361428 | Carver | 2330 | 2000 | PV & Battery | TBD | 2019-09-06 | 2019-09-13 |  |  |  | 2019-10-01 | [38 empty] | Withdrawn
2402730 | Carver | 2330 | 200 | PV | TBD | 2020-05-15 | 2020-06-03 |  |  |  | 2020-06-16 | [24 empty] | 2020-07-29
4377469 | Carver | 2330 | 200 | PV | TBD | 2020-09-18 | 2020-09-30 |  |  |  | 2020-10-21 | [24 empty] | 2021-10-25
4507889 | Carver | 2330 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 |  |  |  | 2020-12-04
4518746 | Carver | 2330 | 5000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 |  |  |  | 2020-11-24
5114629 | Carver | 2330 | 5000 | PV & Battery | TBD | 2020-11-25 | 2021-01-25 |  |  |  | 2021-03-12
4876930 | Carver | 2330 | 15.2 | PV | TBD | 2020-12-16 | 2021-01-11 |  |  |  | 2021-01-28 | [24 empty] | 2021-03-01 | [12 empty] | 2022-08-24 | Online
4706363 | Carver | 2330 | 248 | PV | TBD | 2020-12-30 | 2020-12-30 |  |  |  | 2021-01-25
4849634 | Carver | 2330 | 72 | PV | TBD | 2020-12-30 | 2021-01-06 |  |  |  | 2021-01-25 | [24 empty] | 2021-02-04 | [12 empty] | 2021-06-09 | Online
5001002 | Carver | 2330 | 1992 | PV | TBD | 2021-01-20 | 2021-01-20 |  |  |  | 2021-02-16
5123008 | Carver | 2330 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08
ESMAEX-00583 | Carver | 2330 | 2000 | PV & Battery | 3-10-930 | 2022-01-06 | 2022-02-01 | [42 empty] | In Queue |  |  | Y
ESMAEX-01327 | Carver | 2330 | 100 | PV & Battery | 3-81-81 | 2022-06-27 | 2022-07-13 | [28 empty] | 2022-08-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01387 | Carver | 2330 | 38 | PV | TBD | 2022-07-19 | 2022-08-17 | [28 empty] | 2022-08-25 | [13 empty] | In Queue |  |  | Y
ESMAEX-01753 | Carver | 2330 | 17.7 | PV | 40247 | 2022-11-02 | 2022-11-22 | [28 empty] | 2023-01-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01859 | Carver | 2330 | 15.2 | PV | 40247 | 2022-11-29 | 2023-01-11 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
2378857 | Carver | 2330 | 2500 | PV & Battery | TBD | 2019-11-19 | 2019-12-23 |  |  |  | 2020-01-07
2128036 | Duxbury | 2332 | 20.25 | PV | 3-27-970 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-11 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-13 | Online
2139848 | Duxbury | 2332 | 24.32 | PV | 3-26-903 | 2016-03-17 | 2016-03-28 | 7 |  | 7 | 2016-05-26 |  | -30370 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-09 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | private
2346979 | Duxbury | 2332 | 200 | PV | 3-27-970 | 2019-06-19 | 2019-06-19 |  |  |  | 2019-06-27 | [24 empty] | 2019-09-23 | [12 empty] | 2020-08-05 | Online
2389174 | Duxbury | 2332 | 16.7 | PV | TBD | 2020-02-18 | 2020-02-21 |  |  |  | 2020-03-09 | [24 empty] | 2020-03-31 | [12 empty] | 2020-08-31 | Online
2386320 | Duxbury | 2332 | 66.6 | PV | TBD | 2020-02-03 | 2020-02-03 |  |  |  | 2020-02-19 | [24 empty] | 2020-03-04 | [12 empty] | 2020-10-06 | Online
5193836 | Duxbury | 2332 | 19.5 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 |  |  |  | 2021-03-16 | [24 empty] | 2021-04-09 | [12 empty] | 2021-05-17 | Online
2146377 | Duxbury | 2332 | 28.8 | PV | 3-26-903 | 2016-03-24 | 2016-05-02 | 27 |  | 27 | 2016-05-10 |  | -30358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | PRIVATE
2251155 | Duxbury | 2332 | 300 | PV | 3-26-903 | 2017-11-17 | 2017-11-17 | 0 |  | 0 | 2017-12-12 |  | -30764 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2333489 | Duxbury | 2332 | 20 | PV | 3-26-903 | 2019-03-07 | 2019-03-22 | 11 |  | 11 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2392885 | Duxbury | 2332 | 4000 | PV & Battery | TBD | 2020-03-20 | 2020-03-23 |  |  |  | 2020-04-07
2399108 | Duxbury | 2332 | 25 | PV & Battery | TBD | 2020-04-29 | 2020-05-08 |  |  |  | 2020-05-27 | [24 empty] | 2020-06-23
4389990 | Duxbury | 2332 | 16.24 | PV & Battery | 3-26-903 | 2020-09-30 | 2020-10-05 |  |  |  | 2020-10-21 | [24 empty] | 2020-11-13
4963456 | Duxbury | 2332 | 25.2 | PV | TBD | 2021-01-21 | 2021-01-27 |  |  |  | 2021-02-17 | [24 empty] | 2021-04-28
ESMAEX-00287 | Duxbury | 2332 | 15.2 | PV | 46107 | 2021-08-04 | 2021-08-16 | [28 empty] | 2021-08-24 | [12 empty] | 2021-12-06 | Online |  |  | Y
ESMAEX-00326 | Duxbury | 2332 | 46.2 | PV | 3-27-970 | 2021-08-18 | 2021-09-07 | [28 empty] | 2021-09-09 | [12 empty] | 2022-07-18 | Online |  |  | Y
ESMAEX-00346 | Duxbury | 2332 | 21.44 | PV | 3-24B-24B | 2021-08-25 | 2021-09-13 | [28 empty] | 2021-11-30 | [12 empty] | 2022-04-05 | Online |  |  | Y
ESMAEX-00646 | Duxbury | 2332 | 10 | PV | 46107 | 2021-12-07 | 2021-12-28 | [28 empty] | 2021-12-30 | [12 empty] | 2022-07-18 | Online |  |  | Y
ESMAEX-00807 | Duxbury | 2332 | 11.4 | Battery | 45008 | 2022-02-04 | 2022-03-01 | [28 empty] | 2022-03-07 | [12 empty] | 2022-06-13 | Online |  |  | Y
ESMAEX-01131 | Duxbury | 2332 | 4990 | Battery | 45741 | 2022-10-04 | 2022-11-30 | [42 empty] | In Queue |  |  | Y
ESMAEX-01633 | Duxbury | 2332 | 15.738 | PV | 46107 | 2022-09-27 | 2022-11-30 | [28 empty] | 2022-12-13 | [12 empty] | 2023-02-28 | Online |  |  | Y
ESMAEX-01726 | Duxbury | 2332 | 9.9 | PV & Battery | 46107 | 2022-10-26 | 2022-11-16 | [28 empty] | 2022-11-29 | [12 empty] | 2023-03-22 | Online |  |  | Y
ESMAEX-01845 | Duxbury | 2332 | 11.4 | PV & Battery | 3-27-970 | 2022-11-23 | 2022-12-13 | [28 empty] | 2023-01-23 | [12 empty] | 2023-04-12 | Online |  |  | Y
ESMAEX-01903 | Duxbury | 2332 | 10.5 | PV & Battery | 46107 | 2022-12-08 | 2022-12-29 | [28 empty] | 2023-01-18 | [12 empty] | 2023-04-13 | Online |  |  | Y
ESMAEX-01935 | Duxbury | 2332 | 15 | PV & Battery | 3-27-970 | 2022-12-20 | 2023-01-10 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-02401 | Duxbury | 2332 | 13.2 | PV | 46107 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
4637511 | Manomet | 2345 | 17.4 | PV | TBD | 2020-11-13 | 2020-11-18 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-11 | [12 empty] | 2021-06-21 | Online
ESMAEX-02113 | Lakeville | 2347 | 15.2 | PV & Battery | 2-108-108 | 2023-02-03 | 2023-02-23 | [28 empty] | 2023-02-28 | [13 empty] | In Queue |  |  | Y
2311298 | Plymouth | 2360 | 233.1 | PV | 3-13-13 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-06 |  | -31020 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2106576 | Plymouth | 2360 | 21.07 | PV | 3-14-931 | 2015-10-27 | 2015-10-28 | 1 |  | 1 | 2015-11-17 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-01-29 | [6 empty] | 0 |  | 0 |  |  | 2016-03-10 | Online
2117742 | Plymouth | 2360 | 21.4 | PV | 3-73-27J2 | 2015-12-09 | 2016-12-10 | 262 |  | 262 | 2016-01-04 |  | -30267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-12 | [6 empty] | 0 |  | 0 |  |  | 2016-03-17 | Online
2108966 | Plymouth | 2360 | 23.75 | PV | 3-89-926 | 2015-11-24 | 2015-11-24 | 0 |  | 0 | 2015-12-01 |  | -30243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-07-26 | Online
2131133 | Plymouth | 2360 | 22.575 | PV | 3-71-71 | 2016-02-01 | 2016-02-01 | 0 |  | 0 | 2016-02-29 |  | -30307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-29 | 2016-03-30 | [6 empty] | 0 |  | 0 |  |  | 2016-10-26 | Online
2110218 | Plymouth | 2360 | 394.8 | PV | 3-14-931 | 2015-11-17 | 2015-11-17 | 0 |  | 0 | 2016-01-11 |  | -30272 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-10 | [6 empty] | 0 |  | 0 |  |  | 2016-11-08 | Online |  | PRIVATE
2177087 | Plymouth | 2360 | 32.35 | PV | 3-13-936 | 2016-09-20 | 2016-09-26 | 4 |  | 4 | 2016-10-25 |  | -30478 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-04-05 | Online |  | Private | Y
2170423 | Plymouth | 2360 | 188.42 | PV | 3-14-911 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-20 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
2203287 | Plymouth | 2360 | 208 | PV | 3-14-911 | 2017-01-31 | 2017-02-03 | 3 |  | 3 | 2017-02-28 |  | -30565 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-04-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online |  | PRIVATE | Y
2227360 | Plymouth | 2360 | 18 | PV | 3-89-926 | 2017-06-27 | 2017-07-06 | 6 |  | 6 | 2017-07-27 |  | -30669 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-02 | [6 empty] | 0 |  | 0 |  |  | 2017-12-11 | Online
2213428 | Plymouth | 2360 | 210 | PV & Battery | 3-13-943 | 2017-04-07 | 2017-04-11 | 2 |  | 2 | 2017-05-02 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-20 | 2017-07-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
2245961 | Plymouth | 2360 | 48 | PV | 3-13-936 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-30 | Online
2218005 | Plymouth | 2360 | 1176 | PV | 3-12-12 | 2017-05-08 | 2017-06-13 | 25 |  | 25 | 2017-06-16 | 2017-08-10 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-10 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-22 | Online
2267338 | Plymouth | 2360 | 272 | PV | 3-71-937 | 2017-11-30 | 2018-02-07 | 48 |  | 48 | 2018-03-23 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-04-30 | [6 empty] | 0 |  | 0 |  |  | 2018-08-17 | Online
2238366 | Plymouth | 2360 | 499.5 | PV | 3-14-911 | 2017-05-15 | 2017-09-13 | 84 |  | 84 | 2017-10-04 | 2017-10-17 | 8 | 0 | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2019-02-11 | Online
2257795 | Plymouth | 2360 | 480 | PV | 3-13-943 | 2017-12-12 | 2017-12-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
2334186 | Plymouth | 2360 | 144 | PV | 3-89-89 | 2019-03-20 | 2019-03-26 | 4 |  | 4 | 2019-04-11 |  | -31110 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-11-18 | Online
2365634 | Plymouth | 2360 | 17.6 | PV | TBD | 2019-04-18 | 2019-10-10 | 125 |  | 125 | 2019-10-28 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
2303429 | Plymouth | 2360 | 144 | PV | 3-13-943 | 2018-10-11 | 2018-10-18 | 5 |  | 5 | 2018-10-31 | 2018-11-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-21 | Online |  | Private
2357988 | Plymouth | 2360 | 150 | PV | 3-12-12 | 2019-08-13 | 2019-08-13 |  |  |  | 2019-09-05 | [24 empty] | 2019-11-20 | [12 empty] | 2020-05-18 | Online
2323714 | Plymouth | 2360 | 700 | PV | 3-71-937 | 2019-01-25 | 2019-01-29 | 2 |  | 2 | 2019-02-06 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-05-21 | Online
2375823 | Plymouth | 2360 | 173.46 | PV | TBD | 2019-12-11 | 2019-12-11 |  |  |  | 2019-12-26 | [24 empty] | 2020-01-31 | [12 empty] | 2020-08-05 | Online
2398880 | Plymouth | 2360 | 7.6 | PV & Battery | TBD | 2020-04-29 | 2020-04-29 | 0 |  | 0 | 2020-04-29 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
2399743 | Plymouth | 2360 | 17.6 | PV | 3-72-940 | 2020-05-08 | 2020-05-13 |  |  |  | 2020-06-02 | [24 empty] | 2020-06-23 | [12 empty] | 2020-11-04 | Online
2392993 | Plymouth | 2360 | 144 | PV | TBD | 2020-03-20 | 2020-03-23 |  |  |  | 2020-04-08 | [24 empty] | 2020-05-06 | [12 empty] | 2021-03-05 | Online
4433447 | Plymouth | 2360 | 66.6 | PV | TBD | 2020-10-06 | 2020-10-07 |  |  |  | 2020-11-09 | [24 empty] | 2020-11-25 | [12 empty] | 2021-04-05 | Online
2302150 | Plymouth | 2360 | 133.2 | PV | 3-13-943 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-18 | 2018-11-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2146368 | Plymouth | 2360 | 99.9 | PV | 3-88-924 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2197892 | Plymouth | 2360 | 21.6 | PV | 3-89-926 | 2016-11-16 | 2017-01-05 | 35 |  | 35 | 2017-01-24 |  | -30541 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-08 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2271383 | Plymouth | 2360 | 4986 | PV | 3-89-922 | 2018-03-12 | 2018-03-27 | 11 |  | 11 | 2018-04-13 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2274654 | Plymouth | 2360 | 3750 | PV & Battery | 3-89-89 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
2284556 | Plymouth | 2360 | 250 | PV | 3-13-943 | 2018-06-11 | 2018-06-18 | 5 |  | 5 | 2018-07-02 |  | -30907 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2288600 | Plymouth | 2360 | 780 | PV | 3-73-73 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-26 |  | -30925 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | [7 empty] | 0 |  | 0
2299348 | Plymouth | 2360 | 924 | PV | 3-12-41J1 | 2018-08-17 | 2018-09-12 | 18 |  | 18 | 2018-10-02 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-12-21 | Online
2303219 | Plymouth | 2360 | 199.8 | PV | 3-10-10 | 2018-10-01 | 2018-10-05 | 4 |  | 4 | 2018-10-25 |  | -30990 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2308333 | Plymouth | 2360 | 500 | PV | 3-13-943 | 2018-11-13 | 2018-11-29 | 12 |  | 12 | 2018-11-29 |  | -31015 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2319393 | Plymouth | 2360 | 999 | PV & Battery | 3-73-73 | 2018-12-18 | 2018-12-18 | 0 |  | 0 | 2018-01-09 |  | -30783 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
2320809 | Plymouth | 2360 | 4999 | PV & Battery | 3-73-73 | 2019-01-08 | 2019-01-08 | 0 |  | 0 | 2019-01-17 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
2323317 | Plymouth | 2360 | 26.55 | PV | 3-13-943 | 2019-01-23 |  | -31054 |  | 0 | 2019-02-01 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-25 | [7 empty] | 0 |  | 0
2328025 | Plymouth | 2360 | 630 | PV & Battery | 3-71-937 | 2019-02-19 | 2019-02-19 | 0 |  | 0 | 2019-03-04 |  | -31082 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2328095 | Plymouth | 2360 | 500 | PV & Battery | 3-89-89 | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-03-05 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2335814 | Plymouth | 2360 | 1800 | PV | 3-89-89 | 2019-03-20 | 2019-04-04 | 11 |  | 11 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2337311 | Plymouth | 2360 | 195 | PV | 3-89-89 | 2019-03-26 | 2019-04-01 | 4 |  | 4 | 2019-05-02 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
2304254 | Plymouth | 2360 | 366.6 | PV | 3-13-943 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2338789 | Plymouth | 2360 | 756 | PV | 3-89-89 | 2019-04-09 | 2019-04-25 | 12 |  | 12 | 2019-05-09 |  | -31130 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2341861 | Plymouth | 2360 | 114 | PV | 3-89-89 | 2019-05-20 | 2019-05-21 |  |  |  | 2019-05-30
2343065 | Plymouth | 2360 | 250 | PV & Battery | 3-71-937 | 2019-05-21 | 2019-05-24 |  |  |  | 2019-06-04
2350447 | Plymouth | 2360 | 250 | CHP | 3-73-927 | 2019-06-27 | 2019-07-02 |  |  |  | 2019-07-22
2350809 | Plymouth | 2360 | 49.59 | PV | 3-10-10 | 2019-07-01 | 2019-07-01 |  |  |  | 2019-07-22 | [24 empty] | 2019-09-03
2381703 | Plymouth | 2360 | 249.9 | PV & Battery | TBD | 2019-12-30 | 2019-12-30 |  |  |  | 2020-01-16 | [24 empty] | 2020-08-05 | [13 empty] | Withdrawn
2395947 | Plymouth | 2360 | 5466 | PV & Battery | TBD | 2020-03-27 | 2020-04-15 |  |  |  | 2020-05-04
2396211 | Plymouth | 2360 | 1000 | PV & Battery | TBD | 2020-04-15 | 2020-04-16 |  |  |  | 2020-05-04
2403991 | Plymouth | 2360 | 180 | PV | TBD | 2020-05-18 | 2020-06-11 |  |  |  | 2020-06-29 | [24 empty] | 2021-01-06
2408483 | Plymouth | 2360 | 1000 | PV & Battery | TBD | 2020-06-30 | 2020-07-02 |  |  |  | 2020-07-28
2409661 | Plymouth | 2360 | 10 | PV & Battery | 3-14-934 | 2020-07-15 | 2020-07-15 |  |  |  | 2020-08-04 | [37 empty] | 2023-01-23 | Online
2412755 | Plymouth | 2360 | 17.6 | PV & Battery | TBD | 2020-07-28 | 2020-08-14 |  |  |  | 2020-09-14 | [24 empty] | 2020-09-18
2413390 | Plymouth | 2360 | 21.4 | PV & Battery | TBD | 2020-08-11 |  |  |  |  | 2020-09-03 | [24 empty] | 2020-10-01 | [12 empty] | 2022-03-17 | Online
4506135 | Plymouth | 2360 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 |  |  |  | 2020-11-24
4619716 | Plymouth | 2360 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 |  |  |  | 2020-12-23 | [24 empty] | 2020-12-30
4887324 | Plymouth | 2360 | 17.6 | PV & Battery | TBD | 2020-11-25 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-25 | [12 empty] | 2021-11-18 | Online
4963768 | Plymouth | 2360 | 20 | PV & Battery | TBD | 2020-12-01 | 2021-01-27 |  |  |  | 2021-02-17 | [24 empty] | 2021-05-06 | [12 empty] | 2021-07-12 | Online
4869990 | Plymouth | 2360 | 110 | PV | TBD | 2020-12-31 | 2021-01-11 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-17 | [12 empty] | 2022-02-07 | Online
5414087 | Plymouth | 2360 | 1366.4 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 |  |  |  | 2021-04-09
5243558 | Plymouth | 2360 | 1519.1 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 |  |  |  | 2021-03-24
2132938 | Plymouth | 2360 | 18.92 | PV | 3-71-38J1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5447376 | Plymouth | 2360 | 747 | PV & Battery | TBD | 2021-03-05 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2022-06-10
5518643 | Plymouth | 2360 | 25 | PV & Battery | TBD | 2021-03-05 | 2021-03-05 |  |  |  | 2021-04-21 | [24 empty] | 2021-05-06 | [12 empty] | 2022-02-16 | Online
ESMAEX-00166 | Plymouth | 2360 | 8.7 | PV | 3-90-90 | 2021-06-04 | 2021-07-06 | [28 empty] | 2021-09-08 | [12 empty] | 2022-01-26 | Online |  |  | Y
ESMAEX-00271 | Plymouth | 2360 | 15 | PV & Battery | 3-71-38J1 | 2021-07-28 | 2021-08-12 | [28 empty] | 2021-08-12 | [12 empty] | 2022-01-07 | Online |  |  | Y
ESMAEX-00312 | Plymouth | 2360 | 7.6 | PV & Battery | 3-14-934 | 2021-08-13 | 2021-08-31 | [28 empty] | 2021-09-17 | [12 empty] | 2022-01-27 | Online |  |  | Y
ESMAEX-00603 | Plymouth | 2360 | 17.6 | PV | 3-90-90 | 2021-11-17 | 2022-01-19 | [28 empty] | 2022-03-01 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00613 | Plymouth | 2360 | 4000 | PV | TBD | 2021-12-18 | 2022-02-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-00614 | Plymouth | 2360 | 2000 | PV | TBD | 2021-12-18 | 2022-02-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-00615 | Plymouth | 2360 | 2000 | PV | TBD | 2021-12-18 | 2022-02-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-00635 | Plymouth | 2360 | 72 | PV | 3-12-28J3 | 2021-12-01 | 2021-12-28 | [28 empty] | 2022-03-22 | [12 empty] | 2022-12-12 | Online |  |  | Y
ESMAEX-00724 | Plymouth | 2360 | 43.2 | PV | 3-89-922 | 2022-01-11 | 2022-02-08 | [28 empty] | 2022-03-31 | [12 empty] | 2022-08-24 | Online |  |  | Y
ESMAEX-00822 | Plymouth | 2360 | 40.4 | PV & Battery | 3-90-90 | 2022-02-08 | 2022-02-28 | [28 empty] | 2022-05-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-00844 | Plymouth | 2360 | 10.03 | PV & Battery | 40613 | 2022-02-21 | 2022-03-10 | [28 empty] | 2022-03-31 | [12 empty] | 2022-06-21 | Online |  |  | Y
ESMAEX-00964 | Plymouth | 2360 | 15.2 | PV & Battery | 3-89-925 | 2022-03-24 | 2022-04-12 | [28 empty] | 2022-05-16 | [12 empty] | 2023-04-10 | Online |  |  | Y
ESMAEX-01098 | Plymouth | 2360 | 7 | Battery | 3-73-938 | 2022-04-21 | 2022-05-12 | [28 empty] | 2022-05-16 | [12 empty] | 2023-02-24 | Online |  |  | Y
ESMAEX-01111 | Plymouth | 2360 | 10 | Battery | 3-89-922 | 2022-04-25 | 2022-07-21 | [28 empty] | 2022-08-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01125 | Plymouth | 2360 | 10 | PV | 3-90-90 | 2022-04-29 | 2022-05-18 | [28 empty] | 2022-05-20 | [12 empty] | 2022-11-17 | Online |  |  | Y
ESMAEX-01229 | Plymouth | 2360 | 1500 | PV & Battery | 3-71-937 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01309 | Plymouth | 2360 | 10 | PV & Battery | 3-90-90 | 2022-06-18 | 2022-07-07 | [28 empty] | 2022-07-13 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-01399 | Plymouth | 2360 | 48 | PV & Battery | 3-89-922 | 2022-07-21 | 2022-08-03 | [28 empty] | 2022-08-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-01411 | Plymouth | 2360 | 67.3 | PV | 3-12-932 | 2022-07-25 | 2022-08-10 | [28 empty] | 2022-08-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01601 | Plymouth | 2360 | 22.8 | PV & Battery | 3-71-38J1 | 2022-09-19 | 2022-10-27 | [28 empty] | 2022-12-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01644 | Plymouth | 2360 | 25 | PV | 40247 | 2022-09-29 | 2022-10-18 | [28 empty] | 2022-11-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01665 | Plymouth | 2360 | 16 | PV & Battery | 40980 | 2022-10-06 | 2022-11-30 | [28 empty] | 2022-12-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01680 | Plymouth | 2360 | 25 | PV & Battery | 40247 | 2022-10-12 | 2022-10-27 | [28 empty] | 2022-11-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01759 | Plymouth | 2360 | 249 | PV & Battery | 3-13-943 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01760 | Plymouth | 2360 | 2000 | PV & Battery | 3-71-937 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01761 | Plymouth | 2360 | 499 | PV & Battery | 3-13-943 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01762 | Plymouth | 2360 | 499 | PV & Battery | 3-71-937 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01763 | Plymouth | 2360 | 249 | PV & Battery | 3-13-943 | 2022-12-20 | 2023-01-12 | [42 empty] | In Queue |  |  | Y
ESMAEX-01931 | Plymouth | 2360 | 3.8 | PV & Battery | 40980 | 2022-12-16 | 2023-01-10 | [28 empty] | 2023-01-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01936 | Plymouth | 2360 | 7.6 | PV | 3-14-934 | 2022-12-20 | 2023-01-12 | [28 empty] | 2023-01-18 | [12 empty] | 2023-03-24 | Online |  |  | Y
ESMAEX-01998 | Plymouth | 2360 | 11.4 | PV & Battery | 3-89-922 | 2023-01-11 | 2023-02-06 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02240 | Plymouth | 2360 | 16.9 | PV | 3-71-38J1 | 2023-03-08 | 2023-04-11 | [28 empty] | 2023-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02305 | Plymouth | 2360 | 16.5 | PV | 3-14-931 | 2023-03-24 | 2023-04-11 | [28 empty] | 2023-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02387 | Plymouth | 2360 | 16 | PV | 40247 | 2023-04-18 | 2023-05-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02395 | Plymouth | 2360 | 15.2 | PV | 3-13-936 | 2023-04-20 | [43 empty] | In Queue |  |  | Y
5393125 | Plymouth | 2360 | 499 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2022-03-24
2294151 | Plymouth | 2362 | 133.2 | PV | 3-14-911 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-11-05 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-08-18 | Online |  | Private
2373797 | Plymouth | 2362 | 60 | PV | 3-13-13 | 2019-11-11 | 2019-11-25 |  |  |  | 2019-12-10 | [24 empty] | 2020-02-13
2170680 | Kingston | 2364 | 80 | PV | 3-26-902 | 2016-08-23 | 2016-09-01 | 7 |  | 7 | 2016-09-21 |  | -30454 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-28 | Online |  | PRIVATE
2225512 | Kingston | 2364 | 20.4 | PV | 3-18-36J1 | 2017-06-08 | 2017-06-20 | 8 |  | 8 | 2017-07-17 |  | -30661 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-20 | 2017-07-21 | [6 empty] | 0 |  | 0 |  |  | 2017-09-05 | Online
2247506 | Kingston | 2364 | 23 | PV | 3-18-36J1 | 2017-10-10 | 2017-11-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
2241214 | Kingston | 2364 | 33.3 | PV | 3-17-17 | 2017-09-27 | 2017-10-03 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
2251317 | Kingston | 2364 | 232 | PV | 3-17-17 | 2017-10-15 | 2017-11-21 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-16 | Online
2359696 | Kingston | 2364 | 250 | PV | TBD | 2019-08-23 | 2019-09-03 |  |  |  | 2019-09-17 | [24 empty] | 2019-10-09 | [12 empty] | 2020-02-28 | Online
2296072 | Kingston | 2364 | 3510 | PV | 3/14-14 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-12 |  | -30959 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-24 | Online
2388590 | Kingston | 2364 | 66.6 | PV | TBD | 2020-02-14 | 2020-02-18 |  |  |  | 2020-03-06 | [24 empty] | 2020-04-06 | [12 empty] | 2021-04-16 | Online
2412838 | Kingston | 2364 | 15.2 | PV | 3-51-980 | 2020-07-22 |  |  |  |  | 2020-09-03 | [24 empty] | 2020-09-21 | [12 empty] | 2021-05-13 | Online
2204685 | Kingston | 2364 | 366.4 | PV | 3-26-902 | 2017-02-03 | 2017-02-09 | 4 |  | 4 | 2017-03-08 |  | -30571 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2270295 | Kingston | 2364 | 150 | PV | 3-26-902 | 2018-02-22 | 2018-03-07 | 9 |  | 9 | 2018-04-09 |  | -30847 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0
2311123 | Kingston | 2364 | 1531.8 | PV | 3/14-14 | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2319914 | Kingston | 2364 | 406.5 | PV | 3-26-902 | 2018-12-19 | 2019-01-02 | 10 |  | 10 | 2019-01-11 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-09 | Online
2340663 | Kingston | 2364 | 1800 | PV | 3-17-17 | 2019-04-25 | 2019-05-02 |  |  |  | 2019-05-21 | [37 empty] | 2023-03-30 | Online
2366662 | Kingston | 2364 | 15.3 | PV | 3-15-15 | 2019-09-19 | 2019-10-22 |  |  |  | 2019-11-01 | [24 empty] | 2019-11-29 | [13 empty] | Withdrawn
2378459 | Kingston | 2364 | 320 | PV | 3-17-916 | 2019-11-13 | 2019-11-25 |  |  |  | 2020-01-06 | [24 empty] | 2020-01-28
23815557 | Kingston | 2364 | 19.27 | PV | 3-17-910 | 2019-12-05 | 2019-12-10 |  |  |  | 2020-01-15 | [24 empty] | 2020-02-12
2388537 | Kingston | 2364 | 2760 | PV | TBD | 2020-01-22 | 2020-02-18 |  |  |  | 2020-03-04
2410310 | Kingston | 2364 | 133.2 | PV | TBD | 2020-07-29 | 2020-08-03 |  |  |  | 2020-08-18 | [24 empty] | 2021-06-17
4675384 | Kingston | 2364 | 499 | PV & Battery | TBD | 2020-12-14 | 2020-12-14 |  |  |  | 2021-01-11 | [24 empty] | 2021-02-01
5000850 | Kingston | 2364 | 250 | PV | TBD | 2021-01-14 | 2021-01-20 |  |  |  | 2021-02-16 | [24 empty] | 2021-05-26
5077570 | Kingston | 2364 | 22.8 | PV & Battery | TBD | 2021-01-21 | 2021-02-08 |  |  |  | 2021-03-01 | [24 empty] | 2021-05-06
2138478 | Kingston | 2364 | 16.69 | PV | 3-17-916 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00196 | Kingston | 2364 | 7.6 | PV & Battery | 3-17-910 | 2021-06-21 | 2021-07-08 | [28 empty] | 2021-07-15 | [12 empty] | 2021-09-17 | Online |  |  | Y
ESMAEX-00297 | Kingston | 2364 | 10 | Battery | 3-51-980 | 2021-08-10 | 2021-08-24 | [28 empty] | 2021-09-27 | [12 empty] | 2022-08-15 | Online |  |  | Y
ESMAEX-00856 | Kingston | 2364 | 15.2 | PV & Battery | 3-17-31J1 | 2022-02-24 | 2022-03-21 | [28 empty] | 2022-03-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01095 | Kingston | 2364 | 15.2 | PV & Battery | 3-17-910 | 2022-04-20 | 2022-05-26 | [28 empty] | 2022-06-16 | [12 empty] | 2023-03-07 | Online |  |  | Y
ESMAEX-01725 | Kingston | 2364 | 7.6 | PV & Battery | 3-50-914 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-11-21 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-01798 | Kingston | 2364 | 180 | PV | 46107 | 2022-11-10 | 2022-12-07 | [28 empty] | 2023-02-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01864 | Kingston | 2364 | 15.2 | PV & Battery | 42078 | 2022-11-29 | 2022-12-29 | [28 empty] | 2023-01-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01957 | Kingston | 2364 | 10 | Battery | 3-50-914 | 2023-01-03 | 2023-01-23 | [28 empty] | 2023-01-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-02313 | Kingston | 2364 | 180 | PV | 42811 | 2023-04-11 | [43 empty] | In Queue |  |  | Y
ESMAEX-02406 | Kingston | 2364 | 15.2 | PV | 3-909-909 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
ESMAEX-01431 | Kingston | 2364 | 240 | PV | 46107 | 2022-08-03 | 2022-08-25 | [28 empty] | 2022-12-22 | [13 empty] | In Queue |  |  | Y
5343599 | Milton | 2364 | 125 | PV | TBD | 2021-02-25 | 2021-03-16 |  |  |  | 2021-03-31 | [37 empty] | 2021-09-15 | Online
2316354 | Plympton | 2364 | 4999 | PV & Battery | 3-15-15 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-01-03 |  | -31040 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue
5016871 | South Carver | 2366 | 23.8 | PV & Battery | TBD | 2021-01-25 | 2021-02-05 |  |  |  | 2021-03-11 | [24 empty] | 2021-04-09
2245475 | South Carver | 2366 | 88 | PV | 3-81-81 | 2017-10-23 | 2017-10-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
5287511 | Truro | 2366 | 19.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-28
2202211 | Plymouth | 2367 | 18.6 | PV | 3-51-43J1 | 2017-02-09 | 2017-02-13 | 2 |  | 2 | 2017-02-27 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-10 | [6 empty] | 0 |  | 0 |  |  | 2017-08-09 | Online |  | PRIVATE
2065453a | Plympton | 2367 | 1000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
2065453b | Plympton | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
2065453c | Plympton | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
2388822 | Plympton | 2367 | 15.2 | PV | TBD | 2020-02-10 | 2020-02-21 |  |  |  | 2020-03-06 | [24 empty] | 2020-03-25 | [12 empty] | 2021-05-12 | Online
2279426 | Plympton | 2367 | 2500 | PV & Battery | 3-15-906 | 2018-04-25 | 2018-05-11 | 12 |  | 12 | 2018-06-01 | 2018-11-08 | 114 |  | 114 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2023-02-06 | Online |  | Private
2211077 | Plympton | 2367 | 4950 | PV & Battery | 3-15-901 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-17 |  | -30598 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-11 | 2017-05-11 | -86 |  | 0 | 2017-09-01 | 2017-08-10 | -18 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2279636 | Plympton | 2367 | 4998 | PV & Battery | 3-51-43J1 | 2018-05-04 | 2018-05-17 | 9 |  | 9 | 2018-06-04 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online
2311480 | Plympton | 2367 | 2000 | PV & Battery | 3-51-901 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2327303 | Plympton | 2367 | 2000 | PV | 3-10-930 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-28 |  | -31080 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2370996 | Plympton | 2367 | 1560 | PV | 3-51-980 | 2019-10-24 | 2019-11-07 |  |  |  | 2019-12-03
2400919 | Plympton | 2367 | 149.3 | PV | TBD | 2020-05-20 | 2020-05-20 |  |  |  | 2020-06-04 | [24 empty] | 2020-07-07
4519678 | Plympton | 2367 | 15.2 | PV | TBD | 2020-10-08 | 2020-10-16 |  |  |  | 2020-11-24 | [24 empty] | 2020-12-08 | [13 empty] | Withdrawn
4708506 | Plympton | 2367 | 19 | PV | TBD | 2020-12-29 | 2020-12-30 |  |  |  | 2021-01-19 | [24 empty] | 2021-02-04
5184938 | Plympton | 2367 | 233.2 | PV | TBD | 2021-02-25 | 2021-02-25 |  |  |  | 2021-03-16 | [24 empty] | 2021-06-22
5758591 | Plympton | 2367 | 742 | PV & Battery | TBD | 2021-02-25 | 2021-05-04 |  |  |  | 2021-05-19 | [24 empty] | 2022-04-15
ESMAEX-00081 | Plympton | 2367 | 999 | PV & Battery | 42078 | 2021-04-28 | 2021-06-01 | [42 empty] | In Queue |  |  | Y
ESMAEX-00197 | Plympton | 2367 | 499 | PV | 42078 | 2021-06-21 | 2021-07-27 | [28 empty] | 2022-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01542 | Plympton | 2367 | 15.2 | PV & Battery | 3-50-50 | 2022-09-06 | 2022-09-22 | [28 empty] | 2022-10-05 | [12 empty] | 2023-04-13 | Online |  |  | Y
ESMAEX-01670 | Plympton | 2367 | 17.6 | PV | 3-50-50 | 2022-10-10 | 2022-11-22 | [28 empty] | 2023-01-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01740 | Plympton | 2367 | 15.2 | PV & Battery | 3-50-43J1 | 2022-10-31 | 2022-11-16 | [28 empty] | 2022-11-21 | [12 empty] | 2023-03-16 | Online |  |  | Y
ESMAEX-02277 | Plympton | 2367 | 4999 | PV | 3-51-51 | 2023-03-17 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
2350752 | South Dennis | 2368 | 333 | PV | TBD | 2019-06-24 | 2019-07-01 |  |  |  | 2019-07-19 | [24 empty] | 2019-08-29 | [12 empty] | 2020-12-15 | Online
2395010 | South Dennis | 2368 | 112.5 | PV | TBD | 2020-04-30 | 2020-04-30 |  |  |  | 2020-04-30 | [24 empty] | 2020-06-15 | [12 empty] | 2021-02-12 | Online
2388945 | Newton | 2378 | 2400 | CHP | TBD | 2019-12-20 | 2020-02-20 |  |  |  | 2020-03-09
2360179 | Plymouth | 2381 | 19 | PV | TBD | 2019-07-25 | 2019-09-05 |  |  |  | 2019-09-20 | [38 empty] | Withdrawn
4878244 | Weston | 2393 | 21.4 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-19 | [12 empty] | 2021-07-08 | Online
2214153 | Cambridge | 2412 | 47.5 | PV | 875-1N38A | 2017-03-01 | 2017-04-13 | 31 |  | 31 | 2017-05-05 |  | -30612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-02 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2231852 | Lexington | 2420 | 25 | PV | 533-H3 | 2017-07-07 | 2017-07-27 | 14 |  | 14 | 2017-08-25 |  | -30690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
2355862 | Lexington | 2420 | 22.8 | PV | TBD | 2019-07-25 | 2019-08-06 |  |  |  | 2019-09-05 | [24 empty] | 2019-10-10 | [12 empty] | 2020-07-08 | Online
2387981 | Lexington | 2420 | 20 | PV & Battery | 533-H3 | 2019-12-02 | 2020-02-14 |  |  |  | 2020-03-04 | [24 empty] | 2020-03-11 | [12 empty] | 2020-07-28 | Online
2389932 | Lexington | 2420 | 25 | PV & Battery | TBD | 2020-02-20 | 2020-02-27 |  |  |  | 2020-03-19 | [24 empty] | 2020-03-25 | [12 empty] | 2020-10-20 | Online
2375572 | Lexington | 2420 | 15.2 | PV | TBD | 2019-11-27 | 2019-12-03 |  |  |  | 2019-12-20 | [24 empty] | 2020-01-30 | [12 empty] | 2020-11-13 | Online
2409998 | Lexington | 2420 | 20 | PV & Battery | TBD | 2020-07-15 | 2020-07-20 |  |  |  | 2020-08-10 | [24 empty] | 2020-09-24 | [12 empty] | 2020-12-30 | Online
4874091 | Lexington | 2420 | 25.2 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 |  |  |  | 2021-01-28 | [37 empty] | 2022-01-26 | Online
2389247 | Lexington | 2420 | 10 | PV & Battery | TBD | 2020-01-15 | 2020-02-24 |  |  |  | 2020-03-09 | [24 empty] | 2020-12-24 | [12 empty] | 2021-02-17 | Online
2182387 | Lexington | 2420 | 20 | PV | 391-H11 | 2016-05-23 | 2016-10-18 | 106 |  | 106 | 2016-11-21 |  | -30497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-15 | [6 empty] | 0 |  | 0 |  |  |  | In Queue |  | PRIVATE
2177534 | Lexington | 2420 | 79.2 | PV | 391-H11 | 2016-09-21 | 2016-09-28 | 5 |  | 5 | 2016-10-27 |  | -30480 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2351363 | Lexington | 2420 | 491 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-07-25
2384383 | Lexington | 2420 | 17 | PV & Battery | 320-H5XY | 2020-01-15 | 2020-01-22 |  |  |  | 2020-02-07 | [37 empty] | 2022-03-15 | Online
4621352 | Lexington | 2420 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-04-16 | [12 empty] | 2022-01-05 | Online
4717011 | Lexington | 2420 | 40 | PV & Battery | TBD | 2020-12-30 | 2020-12-31 |  |  |  | 2021-01-19 | [24 empty] | 2021-08-18
5057606 | Lexington | 2420 | 20 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 |  |  |  | 2021-02-24 | [24 empty] | 2021-04-30 | [12 empty] | 2021-08-10 | Online
5122500 | Lexington | 2420 | 30.2 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | [28 empty] | 2021-06-03 | [12 empty] | 2021-10-14 | Online
5403022 | Lexington | 2420 | 250 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08
5403190 | Lexington | 2420 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-10-01
ESMAEX-00282 | Lexington | 2420 | 11.52 | Battery | 533-H9 | 2021-08-03 | 2021-08-26 | [28 empty] | 2021-09-20 | [12 empty] | 2022-06-22 | Online |  |  | Y
ESMAEX-00637 | Lexington | 2420 | 10.03 | PV & Battery | 351-01 | 2021-12-02 | 2021-12-28 | [28 empty] | 2022-01-18 | [12 empty] | 2022-07-20 | Online |  |  | Y
ESMAEX-00692 | Lexington | 2420 | 22.8 | PV & Battery | 533-H9 | 2021-12-23 | 2022-01-13 | [28 empty] | 2022-05-11 | [12 empty] | 2022-09-30 | Online |  |  | Y
ESMAEX-00967 | Lexington | 2420 | 12.4 | PV & Battery | 533-H9 | 2022-03-25 | 2022-04-14 | [28 empty] | 2022-05-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00970 | Lexington | 2420 | 7.6 | PV & Battery | 3406 | 2022-03-26 | 2022-04-14 | [28 empty] | 2022-05-18 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01043 | Lexington | 2420 | 9.3 | PV | 533-H9 | 2022-04-08 | 2022-04-27 | [28 empty] | 2022-05-31 | [12 empty] | 2022-07-12 | Online |  |  | Y
ESMAEX-01142 | Lexington | 2420 | 8.4 | PV | 533-H4 | 2022-05-04 | 2022-05-25 | [28 empty] | 2022-06-27 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01196 | Lexington | 2420 | 34.6 | PV | 533-H4 | 2022-05-19 | 2022-06-08 | [28 empty] | 2022-07-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01235 | Lexington | 2420 | 22.85 | PV & Battery | 391-H11 | 2022-05-30 | 2022-07-21 | [28 empty] | 2022-10-11 | [12 empty] | 2023-03-20 | Online |  |  | Y
ESMAEX-01453 | Lexington | 2420 | 6 | PV | 391-H11 | 2022-08-09 | 2022-08-29 | [28 empty] | 2022-10-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01454 | Lexington | 2420 | 12.672 | PV & Battery | 211-H10 | 2022-08-09 | 2022-09-07 | [28 empty] | 2022-09-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01469 | Lexington | 2420 | 19 | PV & Battery | 533-H9 | 2022-08-15 | 2022-09-15 | [28 empty] | 2022-09-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01526 | Lexington | 2420 | 15.2 | PV & Battery | 533-H9 | 2022-08-30 | 2022-09-15 | [28 empty] | 2022-09-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-01717 | Lexington | 2420 | 73.6 | PV | 3406 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-12-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01807 | Lexington | 2420 | 20.2 | PV & Battery | 351-01 | 2022-11-14 | 2022-12-08 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-02004 | Lexington | 2420 | 15.2 | PV & Battery | 391-H11 | 2023-01-11 | [29 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02034 | Lexington | 2420 | 15.2 | PV & Battery | 391-H11 | 2023-01-17 | 2023-02-10 | [28 empty] | 2023-03-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-02157 | Lexington | 2420 | 15.93 | Battery | 320-H7 | 2023-02-14 | 2023-02-28 | [28 empty] | 2023-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-02265 | Lexington | 2420 | 16.38 | PV | 533-H9 | 2023-03-14 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02270 | Lexington | 2420 | 15.2 | PV | 533-H9 | 2023-03-15 | 2023-04-03 | [42 empty] | In Queue |  |  | Y
2352055 | Lexington | 2420 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-07-29 | [24 empty] | 2019-08-26 | [12 empty] | 2023-02-16 | Online
2094085 | Lexington | 2421 | 815 | PV | 320-H2 | 2015-08-20 | 2015-08-26 | 4 |  | 4 | 2015-09-15 |  | -30188 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-17 | 2015-11-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-08 | Online
2116975 | Lexington | 2421 | 20.35 | PV | 320-H5XY | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-23 |  | -30259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-27 | 2016-04-19 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online |  | PRIVATE
2149011 | Lexington | 2421 | 15.4 | PV | 3408 | 2016-05-16 | 2016-05-18 | 2 |  | 2 | 2016-06-02 |  | -30375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online |  | PRIVATE
2226745 | Lexington | 2421 | 860.6 | PV | 450-H5 | 2017-06-27 | 2017-07-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
2251157 | Lexington | 2421 | 21.11 | PV | 320-H5XY | 2017-11-13 | 2017-11-17 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-25 | Online
2345373 | Lexington | 2421 | 22.95 | PV & Battery | 320-H2 | 2019-05-28 | 2019-06-04 |  |  |  | 2019-06-18 | [37 empty] | 2019-12-31 | Online
2382228 | Lexington | 2421 | 22.72 | PV | 320-H2 | 2019-12-20 | 2020-01-02 |  |  |  | 2020-01-21 | [24 empty] | 2020-02-28 | [12 empty] | 2020-07-27 | Online
2361940 | Lexington | 2421 | 250 | PV | TBD | 2019-09-03 | 2019-09-09 |  |  |  | 2019-10-02 | [24 empty] | 2019-12-18 | [12 empty] | 2020-12-11 | Online
2403259 | Lexington | 2421 | 25.5 | PV & Battery | TBD | 2020-06-03 | 2020-06-05 |  |  |  | 2020-06-23 | [24 empty] | 2020-06-30 | [12 empty] | 2021-01-08 | Online
4490263 | Lexington | 2421 | 24 | PV & Battery | 3401 | 2020-10-15 | 2020-10-21 |  |  |  | 2020-11-17 | [24 empty] | 2020-12-24 | [12 empty] | 2021-01-14 | Online
2311846 | Lexington | 2421 | 1149 | PV & Battery | 533-H1 | 2018-11-27 | 2018-12-11 | 10 |  | 10 | 2018-12-11 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0
2334511 | Lexington | 2421 | 1500 | PV & Battery | 533-H1 | 2019-03-15 | 2019-03-20 | 3 |  | 3 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2351263 | Lexington | 2421 | 110 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-07-25
2352056 | Lexington | 2421 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-07-30 | [37 empty] | 2023-02-16 | Online
2352139 | Lexington | 2421 | 180 | PV | TBD | 2019-07-10 | 2019-07-17 |  |  |  | 2019-07-30 | [24 empty] | 2019-10-28
2352860 | Lexington | 2421 | 297 | PV | TBD | 2019-07-10 | 2019-07-15 |  |  |  | 2019-08-02 | [24 empty] | 2019-08-19 | [12 empty] | 2023-02-16 | Online
2352285 | Lexington | 2421 | 905 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 |  |  |  | 2019-07-31 | [24 empty] | 2019-12-09 | [12 empty] | 2023-02-02 | Online
2352572 | Lexington | 2421 | 247 | PV & Battery | TBD | 2019-07-11 | 2019-07-17 |  |  |  | 2019-08-01 | [37 empty] | 2023-02-16 | Online
2372246 | Lexington | 2421 | 3000 | CHP | 2-1N11 | 2019-11-18 | 2019-11-19 |  |  |  | 2019-12-05
2380929 | Lexington | 2421 | 133.3 | PV | 533-H1 | 2019-12-02 | 2019-12-05 |  |  |  | 2020-01-09 | [24 empty] | 2020-03-02
2381543 | Lexington | 2421 | 130 | PV | 533-H1 | 2019-12-10 | 2019-12-13 |  |  |  | 2020-01-14 | [24 empty] | 2020-03-03
2412478 | Lexington | 2421 | 133.3 | PV | TBD | 2020-05-05 | 2020-08-13 |  |  |  | 2020-08-31 | [24 empty] | 2020-10-30
2407464 | Lexington | 2421 | 19.86 | PV & Battery | 320-H2 | 2020-07-03 | 2020-07-03 |  |  |  | 2020-07-21
2411492 | Lexington | 2421 | 361.5 | PV | TBD | 2020-07-29 | 2020-08-04 |  |  |  | 2020-08-28 | [24 empty] | 2020-11-23 | [12 empty] | 2022-01-19 | Online
2412545 | Lexington | 2421 | 15.2 | PV | TBD | 2020-08-12 | 2020-08-14 |  |  |  | 2020-08-31 | [24 empty] | 2020-11-17
4289037 | Lexington | 2421 | 21.4 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 |  |  |  | 2020-10-05 | [24 empty] | 2021-02-04 | [12 empty] | 2022-05-18 | Online
5058397 | Lexington | 2421 | 20 | PV & Battery | TBD | 2020-11-06 | 2021-02-05 |  |  |  | 2021-02-24 | [37 empty] | 2021-10-08 | Online
4642133 | Lexington | 2421 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-12-01 |  |  |  | 2020-12-29 | [24 empty] | 2021-06-07 | [12 empty] | 2022-10-21 | Online
4708532 | Lexington | 2421 | 17.44 | PV & Battery | TBD | 2020-12-30 | 2020-12-30 |  |  |  | 2021-01-19 | [24 empty] | 2021-05-27
5149929 | Lexington | 2421 | 19.86 | battery | TBD | 2021-02-19 | 2021-02-19 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-01 | [12 empty] | 2023-03-16 | Online
5402282 | Lexington | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-10-01
5403782 | Lexington | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08
5403580 | Lexington | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-09-28
5403662 | Lexington | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 |  |  |  | 2021-04-08
ESMAEX-00010 | Lexington | 2421 | 420 | PV | 320-H5XY | 2021-03-30 | 2021-04-15 | [28 empty] | 2021-07-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-00210 | Lexington | 2421 | 15.2 | PV | 320-H5XY | 2021-06-24 | 2021-07-13 | [28 empty] | 2021-08-03 | [12 empty] | 2021-12-28 | Online |  |  | Y
ESMAEX-00235 | Lexington | 2421 | 33.3 | PV | 34-1352H1 | 2021-07-13 | 2021-08-03 | [28 empty] | 2021-08-12 | [12 empty] | 2022-06-20 | Online |  |  | Y
ESMAEX-00403 | Lexington | 2421 | 21.43 | PV & Battery | 3409 | 2021-09-10 | 2021-11-23 | [28 empty] | 2021-12-09 | [12 empty] | 2022-01-18 | Online |  |  | Y
ESMAEX-00647 | Lexington | 2421 | 8.85 | PV | 320-H2 | 2021-12-08 | 2022-01-20 | [28 empty] | 2022-02-14 | [12 empty] | 2022-11-15 | Online |  |  | Y
ESMAEX-00860 | Lexington | 2421 | 240 | PV | 3402 | 2022-02-25 | 2022-03-10 | [28 empty] | 2022-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-00861 | Lexington | 2421 | 133.3 | PV | 3402 | 2022-02-25 | 2022-03-10 | [28 empty] | 2022-04-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01186 | Lexington | 2421 | 15.3 | PV | 320-H5XY | 2022-05-17 | 2022-06-06 | [28 empty] | 2022-07-07 | [12 empty] | 2023-03-06 | Online |  |  | Y
ESMAEX-01256 | Lexington | 2421 | 19.175 | PV | 320-H5XY | 2022-06-06 | 2022-06-23 | [28 empty] | 2022-07-06 | [12 empty] | 2022-10-28 | Online |  |  | Y
ESMAEX-01355 | Lexington | 2421 | 15.2 | PV & Battery | 320-H2 | 2022-07-08 | 2022-09-14 | [28 empty] | 2022-09-26 | [12 empty] | 2023-03-07 | Online |  |  | Y
ESMAEX-01365 | Lexington | 2421 | 7 | PV & Battery | 320-H5XY | 2022-07-12 | 2022-07-26 | [28 empty] | 2022-09-06 | [12 empty] | 2023-04-03 | Online |  |  | Y
ESMAEX-01497 | Lexington | 2421 | 19.9 | PV & Battery | 3401 | 2022-08-23 | 2022-09-27 | [28 empty] | 2022-11-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01623 | Lexington | 2421 | 15.2 | PV & Battery | 320-H2 | 2022-09-23 | 2022-11-04 | [28 empty] | 2022-12-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01697 | Lexington | 2421 | 22.8 | PV & Battery | 320-H2 | 2022-10-19 | 2022-11-04 | [28 empty] | 2022-12-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01750 | Lexington | 2421 | 15.2 | PV & Battery | 320-H2 | 2022-11-01 | 2022-11-18 | [28 empty] | 2022-12-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01795 | Lexington | 2421 | 15.2 | PV & Battery | 533-H4 | 2022-11-10 | 2022-12-05 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01804 | Lexington | 2421 | 10 | Battery | 320-H2 | 2022-11-14 | 2022-12-08 | [28 empty] | 2023-01-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01916 | Lexington | 2421 | 15.372 | PV | 320-H5XY | 2022-12-12 | 2023-01-10 | [28 empty] | 2023-02-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-02025 | Lexington | 2421 | 15.2 | PV & Battery | 320-H5XY | 2023-01-14 | 2023-02-01 | [28 empty] | 2023-03-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-02229 | Lexington | 2421 | 10 | Battery | 320-H5XY | 2023-03-03 | 2023-03-23 | [42 empty] | In Queue |  |  | Y
2182805 | Brookline | 2445 | 28 | PV | 350-H8 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-22 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-22 | Online |  | PRIVATE | Y
2262436 | Brookline | 2445 | 21.9 | PV | 496-H4 | 2017-10-09 | 2018-01-29 | 78 |  | 78 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2019-01-03 | Online
2289821 | Brookline | 2445 | 17.28 | PV | 350-H3 | 2018-07-18 | 2018-07-19 | 1 |  | 1 | 2018-08-03 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-21 | [7 empty] | 0 |  | 0 |  |  | 2019-03-19 | Online
2181940 | Brookline | 2445 | 89 | PV | 369-07 | 2016-10-20 | 2016-10-25 | 3 |  | 3 | 2016-11-17 |  | -30495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2410954 | Brookline | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 |  |  |  | 2020-08-31
2411200 | Brookline | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 |  |  |  | 2020-08-26
2411957 | Brookline | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 |  |  |  | 2020-08-26 | [24 empty] | 2021-10-19 | [12 empty] | 2021-12-17 | Online
2413980 | Brookline | 2445 | 133.2 | PV | TBD | 2020-08-27 | 2020-08-27 |  |  |  | 2020-09-11 | [24 empty] | 2020-09-24 | [12 empty] | 2022-03-28 | Online
4307751 | Brookline | 2445 | 100 | PV | TBD | 2020-08-27 | 2020-08-27 |  |  |  | 2020-09-29 | [24 empty] | 2020-11-13 | [12 empty] | 2022-12-08 | Online
5447826 | Brookline | 2445 | 25 | PV & Battery | TBD | 2020-12-16 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2021-10-15
ESMAEX-00231 | Brookline | 2445 | 200 | PV | 23N30 | 2021-07-09 | 2021-07-22 | [28 empty] | 2021-10-04 | [12 empty] | 2023-01-06 | Online |  |  | Y
ESMAEX-00299 | Brookline | 2445 | 19.764 | PV | 350-H8 | 2021-08-10 | 2021-08-24 | [28 empty] | 2021-09-20 | [12 empty] | 2021-11-18 | Online |  |  | Y
ESMAEX-00313 | Brookline | 2445 | 7.68 | PV & Battery | 23N30 | 2021-08-13 | 2021-09-08 | [28 empty] | 2021-10-14 | [12 empty] | 2022-05-31 | Online |  |  | Y
ESMAEX-00678 | Brookline | 2445 | 14 | Battery | 350-H3 | 2021-12-20 | 2022-02-08 | [28 empty] | 2022-02-14 | [12 empty] | 2023-03-27 | Online |  |  | Y
ESMAEX-02292 | Brookline | 2445 | 22.8 | PV | 20N28 | 2023-03-21 | 2023-05-03 | [42 empty] | In Queue |  |  | Y
2177319 | Brookline | 2446 | 16.5 | PV | 350-H12 | 2016-09-15 | 2016-09-26 | 7 |  | 7 | 2016-10-26 |  | -30479 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-04-19 | Online |  | PRIVATE
2384381 | Brookline | 2446 | 38.5 | PV | TBD | 2020-01-16 | 2020-01-17 |  |  |  | 2020-02-04 | [24 empty] | 2020-03-19 | [13 empty] | Withdrawn
2414048 | Brookline | 2446 | 200 | PV | TBD | 2020-08-27 | 2020-08-27 |  |  |  | 2020-09-11 | [24 empty] | 2020-09-24 | [12 empty] | 2022-03-28 | Online
ESMAEX-00359 | Brookline | 2446 | 15 | Battery | 4911 | 2021-08-26 | 2021-09-14 | [28 empty] | 2021-10-15 | [12 empty] | 2023-02-07 | Online |  |  | Y
2285721 | Newton | 2446 | 86 | PV | 33-H3 | 2018-06-12 | 2018-06-20 | 6 |  | 6 | 2018-07-09 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2242293 | Waltham | 2451 | 210 | PV | 450-H1 | 2017-10-10 | 2017-10-31 | 15 |  | 15 | 2017-11-02 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-19 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
2319797 | Waltham | 2451 | 106.6 | PV | 3-25-42J2 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
2294156 | Waltham | 2451 | 496 | PV | 320-H3 | 2018-06-05 | 2018-08-15 | 51 |  | 51 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-05-21 | Online |  | Private
2278335 | Waltham | 2451 | 210 | Fuel Cell | 450-H2 | 2018-04-05 | 2018-05-15 | 28 |  | 28 | 2018-05-29 |  | -30883 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-14 | 2018-07-06 | [6 empty] | 0 |  | 0
2314370 | Waltham | 2451 | 40 | PV | 282-H8 | 2018-12-11 |  | -31023 |  | 0 | 2018-12-28 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2323400 | Waltham | 2451 | 480 | PV | 450-H7 | 2019-01-25 |  | -31056 |  | 0 | 2019-02-01 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online
2329018 | Waltham | 2451 | 924 | PV | 450-H7 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-11 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
2336372 | Waltham | 2451 | 166.6 | PV | 450-H7 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2373333 | Waltham | 2451 | 144 | PV | 450-H7 | 2019-11-14 | 2019-11-08 |  |  |  | 2019-11-25 | [24 empty] | 2020-02-27
2374169 | Waltham | 2451 | 250 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 |  |  |  | 2019-12-12 | [24 empty] | 2020-05-18 | [13 empty] | Withdrawn
2380747 | Waltham | 2451 | 16 | Battery | 450-H3 | 2019-11-27 | 2019-12-02 |  |  |  | 2020-01-08 | [38 empty] | Withdrawn
2403624 | Waltham | 2451 | 144 | PV | TBD | 2020-04-15 | 2020-05-26 |  |  |  | 2020-06-29 | [37 empty] | 2022-01-21 | Online
2402126 | Waltham | 2451 | 375 | PV | TBD | 2020-05-28 | 2020-05-28 |  |  |  | 2020-06-12 | [24 empty] | 2021-07-29
2413861 | Waltham | 2451 | 487.5 | PV | TBD | 2020-06-22 | 2020-08-25 |  |  |  | 2020-09-11 | [24 empty] | 2021-12-15
4582227 | Waltham | 2451 | 7.6 | PV | TBD | 2020-10-29 | 2020-11-06 |  |  |  | 2020-12-09 | [37 empty] | 2022-08-04 | Online
4683376 | Waltham | 2451 | 166 | PV | TBD | 2020-12-14 | 2020-12-22 |  |  |  | 2021-02-02 | [24 empty] | 2021-06-02 | [12 empty] | 2023-04-11 | Online
4686399 | Waltham | 2451 | 233 | PV | TBD | 2020-12-14 | 2020-12-22 |  |  |  | 2021-01-11 | [38 empty] | Withdrawn
4887381 | Waltham | 2451 | 466 | PV | TBD | 2020-12-31 | 2021-01-25 |  |  |  | 2021-02-02 | [24 empty] | 2021-06-04 | [12 empty] | 2022-12-30 | Online
ESMAEX-00098 | Waltham | 2451 | 1994 | Internal Combustion Engine | 526-1361H | 2021-05-03 | 2021-05-19 | [28 empty] | 2023-03-24 | [13 empty] | In Queue |  |  | N
ESMAEX-00113 | Waltham | 2451 | 3012 | Internal Combustion Engine | 531-1359H | 2021-05-10 | 2021-06-18 | [42 empty] | In Queue |  |  | N
ESMAEX-00240 | Waltham | 2451 | 233.1 | PV | 282-H5 | 2021-07-14 | 2021-07-26 | [28 empty] | 2021-09-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-00331 | Waltham | 2451 | 100 | PV | 450-H2 | 2021-08-19 | 2021-09-08 | [28 empty] | 2021-09-28 | [12 empty] | 2022-06-22 | Online |  |  | Y
ESMAEX-00761 | Waltham | 2451 | 250 | PV & Battery | 450-H8 | 2022-01-27 | 2022-02-17 | [28 empty] | 2022-04-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01084 | Waltham | 2451 | 17.6 | PV & Battery | 282-H7 | 2022-04-15 | 2022-05-03 | [28 empty] | 2022-05-16 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01801 | Waltham | 2451 | 33.3 | PV & Battery | 450-H7 | 2022-11-11 | 2022-12-13 | [28 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-02402 | Waltham | 2451 | 15.2 | PV | 450-H1 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
2384826 | Waltham | 2451 | 166.6 | PV | TBD | 2019-12-30 | 2020-01-08 |  |  |  | 2020-02-07
2245192 | Waltham | 2451 | 599 | PV | 450-H2 | 2017-10-10 | 2017-10-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0
2147316 | Waltham | 2452 | 16.15 | PV | 33-H2 | 2016-05-13 | 2016-05-16 | 1 |  | 1 | 2016-05-23 |  | -30367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online |  | PRIVATE
2224625 | Waltham | 2452 | 499.5 | PV | 277-1367XYH | 2017-06-28 | 2017-07-03 | 3 |  | 3 | 2017-07-11 |  | -30657 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-21 | Online
2240718 | Waltham | 2452 | 266.4 | PV | 450-H4 | 2017-09-21 | 2017-09-27 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2018-07-06 | Online
2350448 | Waltham | 2452 | 133.2 | PV | TBD | 2019-07-09 | 2019-07-12 |  |  |  | 2019-07-19 | [24 empty] | 2019-09-12 | [12 empty] | 2020-08-24 | Online
2406861 | Waltham | 2452 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-06-29 |  |  |  | 2020-07-20 | [24 empty] | 2020-09-18 | [12 empty] | 2020-11-23 | Online
2175313 | Waltham | 2452 | 18.4 | PV | 282-H7 | 2016-09-15 | 2016-09-19 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2410763 | Waltham | 2452 | 7.6 | PV | 450-H6 | 2020-08-04 | 2020-08-06 |  |  |  | 2020-08-24 | [24 empty] | 2020-11-17 | [12 empty] | 2021-10-20 | Online
5132265 | Waltham | 2452 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 |  |  |  | 2021-03-08
ESMAEX-00348 | Waltham | 2452 | 190 | PV | 467-H6 | 2021-08-25 | 2021-09-21 | [42 empty] | In Queue |  |  | Y
ESMAEX-01259 | Waltham | 2452 | 15.2 | PV & Battery | 450-H4 | 2022-06-07 | 2022-06-24 | [28 empty] | 2022-09-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01440 | Waltham | 2452 | 15.2 | PV | 282-H7 | 2022-08-05 | 2022-08-29 | [28 empty] | 2023-01-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01808 | Waltham | 2452 | 16.82 | PV | 282-H7 | 2022-11-14 | 2022-12-13 | [28 empty] | 2023-01-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-02400 | Waltham | 2452 | 16 | PV | 450-H4 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
4352193 | Sudbury | 2453 | 17.86 | PV & Battery | TBD | 2020-09-18 | 2020-09-24 |  |  |  | 2020-10-15 | [24 empty] | 2021-01-21 | [12 empty] | 2021-04-30 | Online
2134404 | Waltham | 2453 | 16.15 | PV | 3311 | 2016-03-10 | 2016-03-11 | 1 |  | 1 | 2016-03-16 |  | -30319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-08 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-08-02 | Online
2166275 | Waltham | 2453 | 60 | PV | 282-H4 | 2016-08-09 | 2016-08-15 | 4 |  | 4 | 2016-08-30 |  | -30438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online |  | PRIVATE
2167216 | Waltham | 2453 | 73.3 | PV | 33-H1 | 2016-08-09 | 2016-08-16 | 5 |  | 5 | 2016-09-02 |  | -30441 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online
2166276 | Waltham | 2453 | 50 | PV | 282-H9 | 2016-08-09 | 2016-08-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-16 | Online |  | PRIVATE
2180042 | Waltham | 2453 | 30 | PV | 467-H5 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-07 |  | -30487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-28 | 2016-12-13 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
2226333 | Waltham | 2453 | 180 | PV | 282-H8 | 2017-06-01 | 2017-06-20 | 13 |  | 13 | 2017-07-21 |  | -30665 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
2280855 | Waltham | 2453 | 780 | PV & Battery | 386-1356 | 2018-05-03 | 2018-05-22 | 13 |  | 13 | 2018-06-07 |  | -30890 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-10-01 | Online |  | Private
2340383 | Waltham | 2453 | 40 | PV | 311-13 | 2019-04-17 | 2019-04-29 | 8 |  | 8 | 2019-05-28 |  | -31143 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
2338649 | Waltham | 2453 | 99.9 | PV | 33-H3 | 2019-04-17 | 2019-04-23 | 4 |  | 4 | 2019-05-09 |  | -31130 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2377493 | Waltham | 2453 | 80 | PV | TBD | 2019-12-13 | 2019-12-20 |  |  |  | 2020-01-03 | [24 empty] | 2020-02-19 | [12 empty] | 2021-03-01 | Online
2220027 | Waltham | 2453 | 72 | PV | 282-H8 | 2017-05-01 | 2017-05-23 | 16 |  | 16 | 2017-06-13 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-09-18 | [6 empty] | 0 |  | 0
2295857 | Waltham | 2453 | 73.3 | PV | 33-H2 | 2018-08-08 | 2018-08-23 | 11 |  | 11 | 2018-09-11 |  | -30958 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-29 | [7 empty] | 0 |  | 0
2384357 | Waltham | 2453 | 40 | PV | TBD | 2019-06-14 | 2020-01-21 |  |  |  | 2020-02-04 | [24 empty] | 2020-03-02 | [12 empty] | 2021-06-07 | Online
2397225 | Waltham | 2453 | 80 | PV | TBD | 2020-03-20 | 2020-04-23 |  |  |  | 2020-05-14 | [24 empty] | 2020-09-16 | [12 empty] | 2023-03-14 | Online
2397603 | Waltham | 2453 | 46 | PV | TBD | 2020-04-16 | 2020-04-27 |  |  |  | 2020-05-14 | [24 empty] | 2020-10-22
4399358 | Waltham | 2453 | 75 | chp | TBD | 2020-10-05 | 2020-10-05 |  |  |  | 2020-10-22 | [24 empty] | 2021-03-25 | [12 empty] | 2021-08-10 | Online
ESMAEX-00426 | Waltham | 2453 | 7 | PV & Battery | 282-H8 | 2021-09-20 | 2021-10-07 | [28 empty] | 2022-02-07 | [12 empty] | 2023-01-31 | Online |  |  | Y
ESMAEX-00516 | Waltham | 2453 | 7 | PV & Battery | 282-H8 | 2021-10-20 | 2021-11-09 | [28 empty] | 2021-11-19 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01516 | Waltham | 2453 | 73.3 | PV | 33-H2 | 2022-08-26 | 2022-09-22 | [28 empty] | 2022-11-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01660 | Waltham | 2453 | 100 | PV & Battery | 33-H1 | 2022-10-05 | 2022-10-25 | [28 empty] | 2022-12-01 | [13 empty] | In Queue |  |  | Y
2367388 | Waltham | 2453 | 480 | PV | TBD | 2019-09-25 | 2019-10-16 |  |  |  | 2019-11-05 | [24 empty] | 2020-09-24 | [13 empty] | Withdrawn
2381555 | Woburn | 2453 | 748 | PV | TBD | 2019-12-09 | 2019-12-12 |  |  |  | 2020-01-14 | [24 empty] | 2020-04-06
2180952 | Brookline | 2455 | 60 | PV | 506-07 | 2016-09-30 | 2016-10-12 | 8 |  | 8 | 2016-11-30 |  | -30504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-16 | 2016-01-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2166797 | Newton | 2458 | 150 | PV | 467-H14 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-02 |  | -30441 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-03-29 | Online |  | PRIVATE
2258392 | Newton | 2458 | 199.8 | PV | 467-H3 | 2017-12-15 | 2017-12-22 | 5 |  | 5 | 2018-01-12 |  | -30786 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-14 | 2018-03-16 | [6 empty] | 0 |  | 0 |  |  | 2019-01-28 | Online
2394648 | Newton | 2458 | 25 | PV & Battery | TBD | 2020-03-20 | 2020-03-31 |  |  |  | 2020-04-23 | [24 empty] | 2020-04-28 | [12 empty] | 2020-07-06 | Online
4469731 | Newton | 2458 | 19.75 | PV & Battery | 277-05 | 2020-09-18 | 2020-10-05 |  |  |  | 2020-11-12 | [24 empty] | 2021-01-26 | [12 empty] | 2021-04-20 | Online
2370022 | Newton | 2458 | 200 | PV | TBD | 2019-08-29 | 2020-09-16 |  |  |  | 2020-11-22 | [24 empty] | 2020-03-31 | [12 empty] | 2021-05-12 | Online
2285991 | Newton | 2458 | 50 | PV | 292-H1 | 2018-05-31 | 2018-06-26 | 18 |  | 18 | 2018-07-09 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-05 | [6 empty] | 0 |  | 0
2370419 | Newton | 2458 | 100 | PV | TBD | 2019-11-05 | 2019-11-12 |  |  |  | 2019-11-26 | [24 empty] | 2020-12-30 | [13 empty] | Withdrawn
ESMAEX-00454 | Newton | 2458 | 200 | PV | 467-H14 | 2021-09-28 | 2021-10-21 | [28 empty] | 2022-02-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-00716 | Newton | 2458 | 13.05 | PV & Battery | 467-H12 | 2022-01-06 | 2022-01-26 | [28 empty] | 2022-02-28 | [12 empty] | 2022-06-20 | Online |  |  | Y
ESMAEX-01347 | Newton | 2458 | 50 | PV & Battery | 467-H14 | 2022-07-06 | 2022-09-14 | [28 empty] | 2022-09-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01370 | Newton | 2458 | 216 | PV | 467-H5 | 2022-07-12 | 2022-07-26 | [28 empty] | 2022-09-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01371 | Newton | 2458 | 67.3 | PV | 467-H5 | 2022-07-12 | [29 empty] | 2022-09-20 | [13 empty] | In Queue |  |  | Y
2370421 | Newton | 2458 | 62.5 | PV | TBD | 2019-11-04 | 2019-11-12 |  |  |  | 2019-12-04
ESMAEX-00279 | Newtonville | 2458 | 110 | PV | 467-H5 | 2021-08-02 | 2021-08-13 | [28 empty] | 2022-04-06 | [13 empty] | In Queue |  |  | Y
2340114 | Newton | 2459 | 57.6 | PV | 1708 | 2019-05-01 | 2019-05-02 | 1 |  | 1 | 2019-05-17 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2407743 | Newton | 2459 | 20 | PV & Battery | TBD | 2020-06-23 | 2020-07-01 |  |  |  | 2020-07-22 | [24 empty] | 2020-09-21 | [12 empty] | 2021-02-10 | Online
2312220 | Newton | 2459 | 200 | PV | 292-H3 | 2018-11-28 | 2018-11-29 | 1 |  | 1 | 2018-12-13 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 |  |  |  | EXP |  |  |  | 0 |  | 0
2323381 | Newton | 2459 | 1000 | PV | 282-H8 | 2019-01-24 |  | -31055 |  | 0 | 2019-02-01 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
2330355 | Newton | 2459 | 266 | PV | 17-H2 | 2019-03-11 | 2019-03-11 | 0 |  | 0 | 2019-03-19 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
2344792 | Newton | 2459 | 136 | PV | 292-H8 | 2019-04-25 | 2019-05-30 |  |  |  | 2019-06-14 | [24 empty] | 2019-08-01
2345601 | Newton | 2459 | 100 | PV | TBD | 2019-04-25 | 2020-06-04 | [28 empty] | 2020-02-12
2344839 | Newton | 2459 | 146 | PV | TBD | 2019-05-20 | 2019-05-30 |  |  |  | 2019-06-14 | [24 empty] | 2020-02-19
2367956 | Newton | 2459 | 436 | PV | TBD | 2019-07-16 | 2019-10-25 |  |  |  | 2019-11-07 | [24 empty] | 2019-12-26
2368913 | Newton | 2459 | 220 | PV | TBD | 2019-09-20 | 2019-11-01 |  |  |  | 2019-11-18 | [24 empty] | 2020-05-14
2391435 | Newton | 2459 | 0 | Battery | 292-H8 | 2020-01-15 | 2020-03-12 |  |  |  | 2020-03-27 | [38 empty] | Withdrawn
2403398 | Newton | 2459 | 19.84 | PV & Battery | 443-02 | 2020-06-05 | 2020-06-05 |  |  |  | 2020-06-23 | [24 empty] | 2020-06-30 | [13 empty] | Withdrawn
4495812 | Newton | 2459 | 18 | PV & Battery | TBD | 2020-10-16 | 2020-10-22 |  |  |  | 2020-11-19
4658683 | Newton | 2459 | 15 | PV & Battery | 292-H11 | 2020-11-13 | 2020-11-24 |  |  |  | 2021-01-05 | [24 empty] | 2021-02-19 | [12 empty] | 2023-01-06 | Online
4642283 | Newton | 2459 | 28.8 | PV & Battery | 292-H6 | 2020-11-18 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-02-24 | [12 empty] | 2022-03-03 | Online
4708433 | Newton | 2459 | 66.6 | PV | TBD | 2020-12-30 | 2020-12-30 |  |  |  | 2021-01-19 | [24 empty] | 2021-03-12 | [13 empty] | Withdrawn
5392881 | Newton | 2459 | 19.84 | PV & Battery | TBD | 2021-03-17 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-06-09 | [12 empty] | 2021-12-07 | Online
2364472 | Newton | 2459 | 15.2 | PV | TBD | 2019-09-27 | 2019-10-03 |  |  |  | 2019-10-18 | [24 empty] | 2019-12-02 | [12 empty] | 2020-04-07 | Online
ESMAEX-00551 | Newton Center | 2459 | 1.5 | PV & Battery | 292-H8 | 2021-10-28 | 2021-11-23 | [28 empty] | 2022-01-25 | [12 empty] | 2022-04-25 | Online |  |  | Y
ESMAEX-00601 | Newton Center | 2459 | 15.2 | PV | 443-02 | 2021-11-17 | 2022-01-06 | [28 empty] | 2022-01-25 | [12 empty] | 2022-11-30 | Online |  |  | Y
ESMAEX-00688 | Newton Center | 2459 | 25.2 | PV & Battery | 292-H6 | 2021-12-22 | 2022-02-22 | [28 empty] | 2022-02-24 | [12 empty] | 2023-04-11 | Online |  |  | Y
ESMAEX-00889 | Newton Center | 2459 | 480 | PV | 292-H3 | 2022-04-07 | 2022-04-28 | [28 empty] | 2023-04-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-00921 | Newton Center | 2459 | 3.5 | PV | 1709 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-05-11 | [12 empty] | 2022-07-18 | Online |  |  | Y
ESMAEX-00956 | Newton Center | 2459 | 15.2 | PV & Battery | 292-H6 | 2022-03-22 | 2022-04-21 | [28 empty] | 2022-05-05 | [12 empty] | 2023-02-10 | Online |  |  | Y
ESMAEX-00984 | Newton Center | 2459 | 60 | PV | TBD | 2022-03-29 | 2022-04-14 | [28 empty] | 2022-05-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00985 | Newton Center | 2459 | 240 | PV & Battery | 292-H3 | 2022-03-29 | 2022-04-14 | [28 empty] | 2023-04-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01004 | Newton Center | 2459 | 492 | PV & Battery | 292-H11 | 2022-04-27 | 2022-05-12 | [28 empty] | 2023-02-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01094 | Newton Center | 2459 | 240 | PV | 292-H3 | 2022-04-20 | 2022-06-14 | [28 empty] | 2022-09-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01145 | Newton Center | 2459 | 19.398 | PV | 292-H12 | 2022-05-04 | 2022-05-25 | [28 empty] | 2022-06-28 | [12 empty] | 2022-10-21 | Online |  |  | Y
ESMAEX-01338 | Newton Center | 2459 | 67.3 | PV | 443-02 | 2022-06-30 | 2022-07-18 | [28 empty] | 2022-09-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01398 | Newton Center | 2459 | 22.5 | PV & Battery | 292-H6 | 2022-07-21 | 2022-08-03 | [28 empty] | 2022-09-15 | [13 empty] | In Queue |  |  | Y
ESMAEX-01428 | Newton Center | 2459 | 11.136 | PV & Battery | 17-H2 | 2022-08-03 | 2022-10-17 | [28 empty] | 2022-11-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01943 | Newton Center | 2459 | 15.9 | PV & Battery | 292-H11 | 2022-12-22 | 2023-01-12 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02047 | Newton Center | 2459 | 15.2 | PV & Battery | 1708 | 2023-01-20 | 2023-02-10 | [28 empty] | 2023-04-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-02381 | Newton Center | 2459 | 150 | PV | 1709 | 2023-04-14 | [43 empty] | In Queue |  |  | Y
ESMAEX-02382 | Newton Center | 2459 | 150 | PV | 292-H8 | 2023-04-14 | [43 empty] | In Queue |  |  | Y
ESMAEX-02404 | Newton Center | 2459 | 10 | Battery | 1701 | 2023-04-21 | [43 empty] | In Queue |  |  | Y
2319566 | Newton | 2460 | 66.66 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
2340567 | Newton | 2460 | 72 | PV | 282-H8 | 2019-04-26 | 2019-05-01 | 3 |  | 3 | 2019-05-21 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
2344713 | Newton | 2460 | 133 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 | 2019-05-30 | -13 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
2292310 | Newton | 2460 | 90 | PV | 467-H3 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0
2319219 | Newton | 2460 | 206 | PV | 17-H2 | 2018-12-17 | 2018-12-20 | 3 |  | 3 | 2019-01-08 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2319220 | Newton | 2460 | 66.66 | PV | 467-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-08 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2319563 | Newton | 2460 | 233 | PV | 17-1354H1. | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2328535 | Newton | 2460 | 220 | PV | 17-H1 | 2019-01-17 | 2019-02-26 | 28 |  | 28 | 2019-03-07 |  | -31085 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
2333672 | Newton | 2460 | 360 | PV | 282-H8 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-11 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
2344584 | Newton | 2460 | 109 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2344729 | Newton | 2460 | 60 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2344165 | Newton | 2460 | 216 | PV | 282-H8 | 2019-05-20 | 2019-05-30 |  |  |  | 2019-06-10 | [24 empty] | 2019-11-27
2344807 | Newton | 2460 | 109 | PV | 467-H14 | 2019-05-20 | 2019-05-30 |  |  |  | 2019-06-14 | [24 empty] | 2019-09-25
2407737 | Newton | 2460 | 115.2 | PV | TBD | 2020-07-06 | 2020-07-07 |  |  |  | 2020-07-27 | [24 empty] | 2020-09-02 | [12 empty] | 2022-09-09 | Online
ESMAEX-02378 | Newtonville | 2460 | 44.6 | PV | 467-H3 | 2023-04-14 | [43 empty] | In Queue |  |  | Y
2130936 | Newton | 2461 | 57.5 | PV | 369-01 | 2016-02-08 | 2016-02-10 | 2 |  | 2 | 2016-02-29 |  | -30307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-14 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online
2346031 | Newton | 2461 | 145.1 | PV | 292-H1 | 2019-05-29 | 2019-06-07 |  |  |  | 2019-06-24 | [24 empty] | 2019-09-17 | [12 empty] | 2021-03-05 | Online
2133801 | Newton | 2461 | 47.52 | PV | 1701 | 2016-02-19 | 2016-04-07 | 34 |  | 34 | 2016-03-10 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | 2016-04-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2133803 | Newton | 2461 | 41.76 | PV | 467-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-10 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-23 | 2016-05-23 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2349180 | Newton | 2461 | 133.2 | PV | TBD | 2019-06-17 | 2019-06-25 |  |  |  | 2019-07-10 | [24 empty] | 2020-03-04 | [12 empty] | 2021-12-31 | Online
4590939 | Newton | 2461 | 10 | PV & Battery | 292-01 | 2020-11-13 | 2020-11-16 |  |  |  | 2020-12-23
5404188 | Newton | 2461 | 86.4 | PV | TBD | 2021-03-23 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-08-05
5404047 | Newton | 2461 | 158.4 | PV | TBD | 2021-03-23 | 2021-03-23 |  |  |  | 2021-04-08 | [24 empty] | 2021-08-05 | [12 empty] | 2022-06-20 | Online
ESMAEX-00002 | Newton | 2461 | 7.68 | Battery | 292-03 | 2021-03-29 | 2021-04-13 | [28 empty] | 2021-05-26 | [12 empty] | 2021-08-11 | Online |  |  | Y
ESMAEX-00023 | Newton | 2461 | 18.88 | PV & Battery | 292-H5 | 2021-04-02 | 2021-04-20 | [28 empty] | 2021-07-26 | [12 empty] | 2022-01-04 | Online |  |  | Y
ESMAEX-01549 | Newton | 2461 | 6.3 | PV & Battery | 292-H12 | 2022-09-07 | 2022-11-30 | [28 empty] | 2023-01-04 | [12 empty] | 2023-03-28 | Online |  |  | Y
2134029 | Newton | 2462 | 15.2 | PV | 292-H7 | 2016-02-24 | 2016-02-24 | 0 |  | 0 | 2016-03-16 |  | -30319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-04 | 2016-05-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online |  | PRIVATE
2395093 | Newton | 2462 | 17.6 | PV & Battery | TBD | 2020-04-06 | 2020-04-09 |  |  |  | 2020-04-27 | [24 empty] | 2020-06-09 | [12 empty] | 2020-12-15 | Online
ESMAEX-00571 | Newton | 2462 | 9.75 | PV & Battery | 292-H2 | 2021-11-08 | 2021-12-16 | [28 empty] | 2022-01-07 | [12 empty] | 2022-06-09 | Online |  |  | Y
ESMAEX-01405 | Newton | 2462 | 15.2 | PV & Battery | 292-H12 | 2022-07-21 | 2022-09-29 | [28 empty] | 2022-11-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01607 | Newton | 2462 | 34 | PV & Battery | 292-H2 | 2022-09-20 | 2022-10-13 | [28 empty] | 2022-11-22 | [13 empty] | In Queue |  |  | Y
4581647 | Newton | 2464 | 25 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 |  |  |  | 2020-12-09 | [24 empty] | 2021-03-12 | [13 empty] | Withdrawn
ESMAEX-01543 | Newton | 2464 | 15.2 | PV & Battery | 292-H7 | 2022-09-06 | 2022-09-22 | [28 empty] | 2022-10-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01928 | Newton | 2464 | 19 | PV & Battery | 292-H2 | 2022-12-14 | 2023-01-10 | [28 empty] | 2023-01-17 | [13 empty] | In Queue |  |  | Y
2223207 | Newton | 2465 | 17.75 | PV | 292-H12 | 2017-05-22 | 2017-06-02 | 8 |  | 8 | 2017-07-06 |  | -30654 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-24 | 2017-09-13 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online
2366803 | Newton | 2465 | 21.4 | PV | 1713 | 2019-09-25 | 2019-10-22 |  |  |  | 2019-11-05 | [24 empty] | 2019-12-20 | [12 empty] | 2020-08-26 | Online
ESMAEX-01721 | Newton | 2465 | 25.2 | PV & Battery | 277-04 | 2022-10-25 | 2022-11-30 | [28 empty] | 2023-01-03 | [13 empty] | In Queue |  |  | Y
4610357 | West Newton | 2465 | 17.6 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 |  |  |  | 2020-12-17 | [24 empty] | 2020-12-18 | [12 empty] | 2021-11-18 | Online
ESMAEX-00386 | West Newton | 2465 | 17.6 | PV & Battery | 282-H9 | 2021-09-06 | 2021-10-04 | [28 empty] | 2021-11-19 | [12 empty] | 2023-03-07 | Online |  |  | Y
ESMAEX-00727 | West Newton | 2465 | 15.51 | PV & Battery | 316-03 | 2022-01-13 | 2022-02-09 | [28 empty] | 2022-02-24 | [12 empty] | 2022-04-13 | Online |  |  | Y
ESMAEX-01085 | West Newton | 2465 | 7.6 | PV & Battery | 282-H9 | 2022-04-15 | 2022-05-12 | [28 empty] | 2022-05-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01831 | West Newton | 2465 | 31.49 | PV & Battery | 1713 | 2022-11-18 | 2022-12-16 | [28 empty] | 2023-02-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01942 | West Newton | 2465 | 25.62 | PV & Battery | 1713 | 2022-12-22 | 2023-01-10 | [28 empty] | 2023-03-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-02048 | West Newton | 2465 | 15.36 | PV & Battery | 1703 | 2023-01-20 | 2023-02-10 | [28 empty] | 2023-04-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-02154 | West Newton | 2465 | 15.2 | PV & Battery | 282-H9 | 2023-02-13 | 2023-03-02 | [42 empty] | In Queue |  |  | Y
2262433 | Waltham | 2465 | 80.5 | PV | 282-H9 | 2018-01-02 | 2018-01-26 | 18 |  | 18 | 2018-02-09 |  | -30806 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
2145951 | West Newton | 2465 | 21.681 | PV | 282-H9 | 2016-04-26 | 2016-04-29 | 3 |  | 3 | 2016-05-12 |  | -30360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-11 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online |  | PRIVATE | Y
2226368 | West Newton | 2465 | 15.95 | PV | 282-H9 | 2017-06-15 | 2017-06-28 | 9 |  | 9 | 2017-07-20 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-29 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
2350781 | West Newton | 2465 | 100 | PV | 467-H5 | 2019-07-01 | 2019-07-01 |  |  |  | 2019-07-19 | [24 empty] | 2019-09-12 | [12 empty] | 2021-02-23 | Online
ESMAEX-02365 | Auburndale | 2466 | 15.2 | PV | 33-H3 | 2023-04-10 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
ESMAEX-02380 | Auburndale | 2466 | 67.3 | PV | 292-H7 | 2023-04-14 | [43 empty] | In Queue |  |  | Y
2166988 | Newton | 2466 | 57.5 | PV | 292-H7 | 2016-08-18 | 2016-08-22 | 2 |  | 2 | 2016-09-02 |  | -30441 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-03-01 | Online |  | PRIVATE
ESMAEX-01337 | Newton | 2466 | 1000 | PV & Battery | 292-H7 | 2023-02-06 | 2023-02-28 | [42 empty] | In Queue |  |  | Y
2387929 | Brookline | 2467 | 20 | PV & Battery | 496-H5 | 2020-01-16 | 2020-02-14 |  |  |  | 2020-03-04 | [24 empty] | 2020-03-19 | [12 empty] | 2020-03-26 | Online
2136359 | Chestnut Hill | 2467 | 196.24 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online |  | Private | Y
2136357 | Chestnut Hill | 2467 | 324.8 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-03 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online |  | Private | Y
2307511 | Chestnut Hill | 2467 | 496.2 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -31009 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2307513 | Chestnut Hill | 2467 | 499.8 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -31009 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2407979 | Chestnut Hill | 2467 | 36 | PV & Battery | 467-H12 | 2020-07-01 | 2020-07-02 |  |  |  | 2020-07-28 | [24 empty] | 2020-10-30
5333799 | Chestnut Hill | 2467 | 86.4 | PV | TBD | 2021-03-15 | 2021-03-15 |  |  |  | 2021-04-02 | [24 empty] | 2021-09-01
5333163 | Chestnut Hill | 2467 | 100.8 | PV | TBD | 2021-03-15 | 2021-03-15 |  |  |  | 2021-03-31 | [24 empty] | 2021-06-04 | [12 empty] | 2022-04-20 | Online
ESMAEX-00176 | Chestnut Hill | 2467 | 16.57 | PV & Battery | TBD | 2021-06-09 | 2021-06-25 | [28 empty] | 2021-10-07 | [12 empty] | 2022-03-18 | Online |  |  | Y
ESMAEX-00272 | Chestnut Hill | 2467 | 5.16 | Battery | 496-H5 | 2021-07-28 | 2021-08-12 | [28 empty] | 2021-11-04 | [12 empty] | 2022-01-05 | Online |  |  | Y
ESMAEX-00545 | Chestnut Hill | 2467 | 17.6 | PV & Battery | 329-H6 | 2021-10-26 | 2021-11-16 | [28 empty] | 2021-11-16 | [12 empty] | 2022-03-21 | Online |  |  | Y
ESMAEX-00548 | Chestnut Hill | 2467 | 199.8 | PV | 443-08 | 2021-10-27 | 2021-11-17 | [28 empty] | 2021-11-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00907 | Chestnut Hill | 2467 | 8 | Battery | 443-07 | 2022-03-11 | 2022-04-07 | [28 empty] | 2022-06-22 | [12 empty] | 2023-02-07 | Online |  |  | Y
ESMAEX-01000 | Chestnut Hill | 2467 | 15.2 | PV & Battery | 443-07 | 2022-04-01 | 2022-08-15 | [28 empty] | 2022-09-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01030 | Chestnut Hill | 2467 | 25.2 | PV & Battery | 443-08 | 2022-04-07 | 2022-04-28 | [28 empty] | 2022-05-02 | [13 empty] | In Queue |  |  | Y
2304489 | Newton | 2468 | 75.6 | PV | 292-H12 | 2018-10-18 | 2018-11-02 | 11 |  | 11 | 2018-11-02 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-19 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05 | Online |  | Private
2320273 | Newton | 2468 | 133.3 | PV | 17-H2 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-01-14 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-05-04 | Online
2136808 | Newton | 2468 | 109.25 | PV | 292-H12 | 2016-02-25 | 2016-03-02 | 4 |  | 4 | 2016-03-25 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-06 | 2016-07-25 | 2016-07-25 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn
2184406 | Newton | 2468 | 480 | PV | 292-H12 | 2016-10-24 | 2016-10-31 | 5 |  | 5 | 2016-12-02 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-19 | 2017-06-19 |  |  |  | 87 |  |  | 0 |  | 0 |  |  | 2022-05-13 | Online
2344421 | Newton | 2468 | 86 | PV | 292-H12 | 2019-04-25 | 2019-05-30 |  |  |  | 2019-06-12 | [24 empty] | 2019-10-08
4878336 | Newton | 2468 | 35.2 | PV & Battery | TBD | 2020-12-01 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-04-23 | [12 empty] | 2021-10-25 | Online
2406455 | Waban | 2468 | 19.84 | PV & Battery | 292-H12 | 2020-06-23 | 2020-06-23 |  |  |  | 2020-07-14 | [24 empty] | 2020-09-02 | [13 empty] | Withdrawn
ESMAEX-00119 | Waban | 2468 | 10 | Battery | 292-H12 | 2021-05-13 | 2021-06-15 | [28 empty] | 2021-07-20 | [12 empty] | 2022-06-01 | Online |  |  | Y
ESMAEX-00139 | Waban | 2468 | 15 | PV & Battery | 292-H7 | 2021-05-19 | 2021-05-20 | [28 empty] | 2021-07-22 | [12 empty] | 2021-10-08 | Online |  |  | Y
ESMAEX-00218 | Waban | 2468 | 25 | PV & Battery | 1701 | 2021-06-28 | 2021-07-15 | [28 empty] | 2021-09-09 | [12 empty] | 2022-02-01 | Online |  |  | Y
ESMAEX-00301 | Waban | 2468 | 7.67 | PV & Battery | 292-H2 | 2021-08-11 | 2021-08-25 | [28 empty] | 2021-09-15 | [12 empty] | 2022-02-04 | Online |  |  | Y
ESMAEX-00392 | Waban | 2468 | 25.2 | PV & Battery | 292-H12 | 2021-09-08 | 2021-09-23 | [28 empty] | 2021-10-08 | [12 empty] | 2023-03-21 | Online |  |  | Y
ESMAEX-00960 | Waban | 2468 | 23.424 | PV | 292-H12 | 2022-03-23 | 2022-04-12 | [28 empty] | 2022-07-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01132 | Waban | 2468 | 7.68 | Battery | 1701 | 2022-05-02 | 2022-05-18 | [28 empty] | 2022-06-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01446 | Waban | 2468 | 12.078 | PV & Battery | 1701 | 2022-08-08 | 2022-09-01 | [28 empty] | 2022-10-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01585 | Waban | 2468 | 15.2 | PV & Battery | 292-H7 | 2022-09-14 | 2022-10-11 | [28 empty] | 2022-11-29 | [13 empty] | In Queue |  |  | Y
2159493 | Framingham | 2472 | 166.5 | PV | 467-H2 | 2016-06-29 | 2016-07-12 | 9 |  | 9 | 2016-07-25 |  | -30412 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2272442 | Watertown | 2472 | 166.5 | PV | 467-H6 | 2018-03-16 | 2018-03-29 | 9 |  | 9 | 2018-03-29 |  | -30840 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11 | Online
2300922 | Watertown | 2472 | 475.2 | PV | 467-H4 | 2018-09-18 | 2018-09-25 | 5 |  | 5 | 2018-10-11 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | [7 empty] | 0 |  | 0 |  |  | 2019-11-15 | Online |  | Private
2321147 | Watertown | 2472 | 100 | PV | 467-H4 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-18 |  | -31051 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
2346407 | Watertown | 2472 | 133.2 | PV | TBD | 2019-06-06 | 2019-06-10 |  |  |  | 2019-06-25 | [24 empty] | 2019-08-19 | [12 empty] | 2020-11-12 | Online
2385313 | Watertown | 2472 | 43.2 | PV | 282-H8 | 2020-01-22 | 2020-01-28 |  |  |  | 2020-02-14 | [24 empty] | 2020-03-25 | [12 empty] | 2020-12-24 | Online
2366357 | Watertown | 2472 | 480 | PV | TBD | 2019-09-30 | 2019-10-10 |  |  |  | 2019-10-31 | [24 empty] | 2020-03-19 | [12 empty] | 2021-02-12 | Online
2366415 | Watertown | 2472 | 353 | PV | TBD | 2019-09-30 | 2019-10-10 |  |  |  | 2019-10-31 | [24 empty] | 2020-03-19 | [12 empty] | 2021-02-12 | Online
2322219 | Watertown | 2472 | 249.9 | PV | 467-H4 | 2019-01-15 | 2019-01-17 | 2 |  | 2 | 2019-01-28 |  | -31057 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2366405 | Watertown | 2472 | 99.9 | PV | TBD | 2019-09-30 | 2019-10-10 |  |  |  | 2019-10-31 | [38 empty] | Withdrawn
2369438 | Watertown | 2472 | 700 | PV & Battery | TBD | 2019-10-10 | 2019-11-04 | [42 empty] | Withdrawn
2381519 | Watertown | 2472 | 100 | PV | 467-H5 | 2019-12-20 | 2019-12-20 |  |  |  | 2020-01-14 | [24 empty] | 2020-03-03 | [12 empty] | 2021-12-15 | Online
2383645 | Watertown | 2472 | 52.2 | PV | TBD | 2020-01-06 | 2020-01-07 |  |  |  | 2020-01-31 | [24 empty] | 2020-10-22 | [12 empty] | 2022-04-13 | Online
4340848 | Watertown | 2472 | 430.3 | PV | TBD | 2020-09-08 | 2020-09-16 |  |  |  | 2020-10-08 | [24 empty] | 2021-03-24 | [12 empty] | 2023-01-31 | Online
4403448 | Watertown | 2472 | 583.3 | PV & Battery | TBD | 2020-09-22 | 2020-09-30 |  |  |  | 2020-10-22 | [24 empty] | 2021-06-02
4404039 | Watertown | 2472 | 320.8 | PV | TBD | 2020-09-22 | 2020-09-30 |  |  |  | 2020-10-22 | [24 empty] | 2021-06-02
5164450 | Watertown | 2472 | 66.6 | PV | TBD | 2021-02-17 | 2021-02-22 |  |  |  | 2021-03-11 | [24 empty] | 2021-06-03 | [12 empty] | 2021-10-01 | Online
ESMAEX-00420 | Watertown | 2472 | 325 | PV & Battery | 548-193 | 2021-09-17 | 2022-01-11 | [28 empty] | 2022-09-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-00429 | Watertown | 2472 | 492 | PV | 370-1323 | 2021-10-26 | 2021-12-01 | [28 empty] | 2022-05-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00662 | Watertown | 2472 | 10 | Battery | 467-H8 | 2021-12-15 | 2022-01-11 | [28 empty] | 2022-01-20 | [12 empty] | 2022-05-12 | Online |  |  | Y
ESMAEX-00696 | Watertown | 2472 | 400 | PV | 315-H4 | 2022-01-20 | 2022-02-10 | [28 empty] | 2022-04-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00726 | Watertown | 2472 | 646 | PV | 315-H4 | 2022-03-15 | 2022-04-11 | [28 empty] | 2023-03-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-00762 | Watertown | 2472 | 99.9 | PV | 315-H4 | 2022-01-28 | 2022-03-02 | [28 empty] | 2022-04-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00866 | Watertown | 2472 | 160 | PV | TBD | 2022-03-01 | 2022-03-14 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01443 | Watertown | 2472 | 16.83 | PV & Battery | 467-H4 | 2022-08-08 | 2022-09-01 | [28 empty] | 2022-09-21 | [12 empty] | 2023-02-21 | Online |  |  | Y
ESMAEX-01498 | Watertown | 2472 | 492 | PV | 370-1327 | 2022-09-29 | 2022-10-25 | [42 empty] | In Queue |  |  | Y
ESMAEX-01499 | Watertown | 2472 | 492 | PV | 467-H9 | 2022-09-29 | 2022-10-27 | [42 empty] | In Queue |  |  | Y
ESMAEX-02327 | Watertown | 2472 | 27.3 | PV | TBD | 2023-03-31 | 2023-04-17 | [42 empty] | In Queue |  |  | Y
2182807 | Arlington | 2474 | 18 | PV | 5905 | 2016-10-18 | 2016-10-24 | 4 |  | 4 | 2016-11-22 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
2370768 | Arlington | 2474 | 19.86 | PV & Battery | 59-1383H1 | 2019-10-31 | 2019-11-19 |  |  |  | 2019-12-02 | [37 empty] | 2020-06-19 | Online
2392742 | Arlington | 2474 | 17.6 | PV & Battery | TBD | 2020-02-20 | 2020-03-18 |  |  |  | 2020-04-03 | [24 empty] | 2020-05-06 | [12 empty] | 2020-09-11 | Online
5017076 | Arlington | 2474 | 19 | Battery | TBD | 2021-01-21 | 2021-02-05 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-01 | [12 empty] | 2022-10-21 | Online
5308545 | Arlington | 2474 | 4.93 | PV | TBD | 2021-02-23 | 2021-02-23 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-28
5298461 | Arlington | 2474 | 17.68 | Battery | TBD | 2021-03-02 | 2021-03-10 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-21 | [12 empty] | 2022-10-24 | Online
ESMAEX-00304 | Arlington | 2474 | 17.6 | PV & Battery | 211-H3 | 2021-08-12 | 2021-09-15 | [28 empty] | 2021-10-20 | [12 empty] | 2022-06-27 | Online |  |  | Y
ESMAEX-00349 | Arlington | 2474 | 12.6 | PV & Battery | 211-H14 | 2021-08-25 | 2021-09-13 | [28 empty] | 2021-09-23 | [12 empty] | 2023-04-26 | Online |  |  | Y
ESMAEX-00702 | Arlington | 2474 | 17.6 | PV & Battery | 211-H3 | 2022-01-03 | 2022-01-25 | [28 empty] | 2022-01-29 | [12 empty] | 2022-04-15 | Online |  |  | Y
ESMAEX-01803 | Arlington | 2474 | 25.6 | PV & Battery | 211-H11 | 2022-11-11 | 2022-12-13 | [28 empty] | 2023-02-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-02049 | Arlington | 2474 | 16.5 | PV & Battery | 211-H11 | 2023-01-22 | 2023-02-10 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-02087 | Arlington | 2474 | 19.03 | PV | 211-H3 | 2023-01-30 | 2023-02-10 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02286 | Arlington | 2474 | 100 | PV | 59-1393H1 | 2023-03-20 | 2023-04-06 | [42 empty] | In Queue |  |  | Y
ESMAEX-02388 | Arlington | 2474 | 15.2 | Battery | 211-H11 | 2023-04-18 | [43 empty] | In Queue |  |  | Y
2170910 | Arlington | 2475 | 396 | PV | 211-H11 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | 2016-09-22 |  | -30455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2016-12-02 | 7 |  | 7 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 |  |  | 2017-08-04 | Online |  | PRIVATE
2133574 | Arlington | 2476 | 40.32 | PV | 211-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-09 |  | -30314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-15 | 2016-07-12 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online |  | PRIVATE
2375708 | Arlington | 2476 | 15.2 | PV | TBD | 2019-12-03 | 2019-12-10 |  |  |  | 2019-12-20 | [24 empty] | 2020-01-31 | [12 empty] | 2020-08-11 | Online
2375571 | Arlington | 2476 | 275 | PV & Battery | TBD | 2019-11-27 | 2019-12-05 |  |  |  | 2019-12-20 | [24 empty] | 2020-01-28 | [12 empty] | 2020-12-09 | Online
2404735 | Arlington | 2476 | 17.6 | PV & Battery | TBD | 2020-06-10 | 2020-06-15 |  |  |  | 2020-07-06 | [24 empty] | 2020-07-29 | [12 empty] | 2020-12-11 | Online
4519305 | Arlington | 2476 | 17.6 | PV & Battery | TBD | 2020-10-05 | 2020-10-15 |  |  |  | 2020-11-24 | [24 empty] | 2020-11-30 | [12 empty] | 2021-04-30 | Online
2173991 | Arlington | 2476 | 34.5 | PV | 211-H3 | 2016-08-25 | 2016-09-14 | 14 |  | 14 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
5913979 | Arlington | 2476 | 16 | Battery | TBD | 2020-09-14 | [29 empty] | 2021-08-05
4615145 | Arlington | 2476 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 |  |  |  | 2020-12-22 | [24 empty] | 2021-01-06 | [12 empty] | 2022-02-03 | Online
4921387 | Arlington | 2476 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-19 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-09 | [12 empty] | 2021-11-18 | Online
ESMAEX-00151 | Arlington | 2476 | 20 | PV | 320-H7 | 2021-05-27 | 2021-06-18 | [28 empty] | 2021-08-10 | [12 empty] | 2022-01-13 | Online |  |  | Y
ESMAEX-00842 | Arlington | 2476 | 166.5 | PV | 211-H13 | 2022-02-18 | 2022-03-21 | [28 empty] | 2022-04-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-01083 | Arlington | 2476 | 13 | PV & Battery | 320-H7 | 2022-04-15 | 2022-05-03 | [28 empty] | 2022-07-07 | [12 empty] | 2022-10-13 | Online |  |  | Y
ESMAEX-02426 | Arlington | 2476 | 67.3 | PV | 211-H3 | 2023-04-28 | [43 empty] | In Queue |  |  | Y
2202454 | Needham | 2492 | 69 | PV | 342-H5 | 2017-02-13 | 2017-02-13 | 0 |  | 0 | 2017-02-27 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-04-28 |  | YES | EXP |  |  |  | 0 |  | 0 |  |  | 2017-10-10 | Online |  | PRIVATE | Y
2262431 | Needham | 2492 | 18.56 | PV | 148-01 | 2017-12-22 | 2018-01-25 | 23 |  | 23 | 2018-02-09 |  | -30806 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-07 | Online
2330416 | Needham | 2492 | 23.3 | PV | 148-H4 | 2019-02-12 | 2019-03-07 | 17 |  | 17 | 2019-03-19 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-21 | Online
2322796 | Needham | 2492 | 28.8 | PV | 148-H1 | 2019-01-18 | 2019-01-25 | 5 |  | 5 | 2019-01-30 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
2347063 | Needham | 2492 | 57.6 | PV | 148-H4 | 2019-06-13 | 2019-06-17 |  |  |  | 2019-06-27 | [24 empty] | 2019-08-15 | [12 empty] | 2019-12-31 | Online
2406453 | Needham | 2492 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-07-07 |  |  |  | 2020-07-14 | [24 empty] | 2020-09-02 | [12 empty] | 2020-12-16 | Online
2408568 | Needham | 2492 | 17 | PV & Battery | TBD | 2020-07-06 | 2020-07-07 |  |  |  | 2020-07-30 | [24 empty] | 2020-09-02 | [12 empty] | 2021-02-02 | Online
2388633 | Needham | 2492 | 18.8 | PV | 148-06 | 2019-12-02 | 2020-02-19 |  |  |  | 2020-03-06 | [24 empty] | 2020-04-14
2404602 | Needham | 2492 | 19.84 | PV | 148-H2 | 2020-06-22 | 2020-06-22 |  |  |  | 2020-07-06 | [24 empty] | 2020-07-15 | [13 empty] | Withdrawn
4324124 | Needham | 2492 | 144 | PV | TBD | 2020-09-03 | 2020-09-11 |  |  |  | 2020-10-05 | [24 empty] | 2021-03-25
4832256 | Needham | 2492 | 16 | PV | TBD | 2020-12-22 | 2020-12-23 |  |  |  | 2021-01-28 | [24 empty] | 2021-03-17 | [12 empty] | 2021-08-30 | Online
4869810 | Needham | 2492 | 17.04 | PV | TBD | 2020-12-31 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-03-15 | [12 empty] | 2021-08-06 | Online
5077813 | Needham | 2492 | 10 | Battery | TBD | 2021-02-05 | 2021-02-08 |  |  |  | 2021-03-01 | [24 empty] | 2021-04-22 | [13 empty] | Withdrawn
5164886 | Needham | 2492 | 19.84 | battery | TBD | 2021-02-18 | 2021-02-23 |  |  |  | 2021-03-24 | [24 empty] | 2021-06-09 | [12 empty] | 2021-10-26 | Online
5354359 | Needham | 2492 | 20 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-06-01
5355247 | Needham | 2492 | 24.86 | Battery | TBD | 2021-03-17 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-07-01 | [13 empty] | Withdrawn
ESMAEX-00121 | Needham | 2492 | 18.56 | PV | 148-H7 | 2021-05-13 | 2021-05-27 | [28 empty] | 2021-08-24 | [12 empty] | 2021-12-02 | Online |  |  | Y
ESMAEX-00264 | Needham | 2492 | 23.4 | PV | 148-04 | 2021-07-26 | 2021-08-12 | [28 empty] | 2021-08-23 | [12 empty] | 2021-11-29 | Online |  |  | Y
ESMAEX-00393 | Needham | 2492 | 20 | Battery | 148-H4 | 2021-09-08 | 2021-09-24 | [28 empty] | 2021-10-12 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00582 | Needham | 2492 | 11.4 | Battery | 148-H4 | 2021-11-11 | 2021-12-01 | [28 empty] | 2022-01-07 | [12 empty] | 2022-04-26 | Online |  |  | Y
ESMAEX-00656 | Needham | 2492 | 15.707 | PV & Battery | 148-08 | 2021-12-13 | 2021-12-30 | [28 empty] | 2022-02-24 | [12 empty] | 2022-05-24 | Online |  |  | Y
ESMAEX-00720 | Needham | 2492 | 10 | Battery | 148-07 | 2022-01-11 | 2022-02-03 | [28 empty] | 2022-02-11 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00830 | Needham | 2492 | 499.5 | PV & Battery | TBD | 2022-02-11 | 2022-03-10 | [28 empty] | 2022-12-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-01033 | Needham | 2492 | 15.2 | PV & Battery | 148-06 | 2022-04-07 | 2022-04-27 | [28 empty] | 2022-05-16 | [12 empty] | 2023-04-04 | Online |  |  | Y
ESMAEX-01285 | Needham | 2492 | 20 | PV | 148-01 | 2022-06-13 | 2022-07-08 | [28 empty] | 2022-08-25 | [12 empty] | 2022-12-06 | Online |  |  | Y
ESMAEX-01408 | Needham | 2492 | 12.8 | PV & Battery | 148-02 | 2022-07-23 | 2022-08-10 | [28 empty] | 2022-11-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01463 | Needham | 2492 | 20 | PV & Battery | 148-H7 | 2022-08-11 | 2022-09-01 | [28 empty] | 2022-09-13 | [12 empty] | 2023-02-06 | Online |  |  | Y
ESMAEX-01681 | Needham | 2492 | 15.2 | PV | 148-01 | 2022-10-13 | 2022-12-07 | [28 empty] | 2023-04-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01838 | Needham | 2492 | 15.2 | PV & Battery | 148-H4 | 2022-11-21 | 2022-12-16 | [28 empty] | 2023-01-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01871 | Needham | 2492 | 10.99 | PV | 148-H6 | 2022-11-30 | 2022-12-08 | [28 empty] | 2023-01-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-01961 | Needham | 2492 | 39.75 | PV & Battery | 148-H6 | 2023-01-04 | 2023-01-26 | [28 empty] | 2023-02-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-01977 | Needham | 2492 | 16.836 | PV | 148-H4 | 2023-01-06 | 2023-01-31 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02068 | Needham | 2492 | 14.918 | PV | 148-H1 | 2023-01-25 | 2023-02-10 | [28 empty] | 2023-04-24 | [13 empty] | In Queue |  |  | Y
ESMAEX-02177 | Needham | 2492 | 15.2 | Battery | 148-01 | 2023-02-17 | 2023-03-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-02366 | Needham | 2492 | 15.2 | PV | 148-07 | 2023-04-10 | [43 empty] | In Queue |  |  | Y
2139664 | Weston | 2493 | 20.16 | PV | 282-H2 | 2016-03-28 | 2016-03-28 | 0 |  | 0 | 2016-04-07 |  | -30335 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-28 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online |  | PRIVATE
2182191 | Weston | 2493 | 18 | PV | 433-H6 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30496 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online |  | PRIVATE
2190095 | Weston | 2493 | 115 | PV | 282-H1 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-27 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-07-06 | Online
2228145 | Weston | 2493 | 24.82 | PV | 282-H1 | 2017-06-27 | 2017-07-11 | 9 |  | 9 | 2017-08-02 |  | -30673 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-21 | 2017-08-25 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
2365270 | Weston | 2493 | 57.6 | PV | 282-H1 | 2019-10-01 | 2019-10-03 |  |  |  | 2019-10-24 | [25 empty] | 2019-12-11 | [11 empty] | 2020-06-30 | Online
2391087 | Weston | 2493 | 25 | PV & Battery | TBD | 2020-02-25 | 2020-03-09 |  |  |  | 2020-03-25 | [24 empty] | 2020-06-09 | [12 empty] | 2020-07-08 | Online
2187501 | Weston | 2493 | 16.7 | PV | 450-H7 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-08 |  | -30510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
4878172 | Weston | 2493 | 18 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-03-25
4663199 | Weston | 2493 | 35.2 | PV & Battery | TBD | 2020-12-16 | 2020-12-16 |  |  |  | 2021-01-05 | [24 empty] | 2021-06-07 | [12 empty] | 2022-02-22 | Online
5113544 | Weston | 2493 | 33.8 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-22
5247231 | Weston | 2493 | 35.2 | PV | TBD | 2021-03-05 | 2021-03-05 |  |  |  | 2021-03-26 | [24 empty] | 2021-05-05
ESMAEX-00142 | Weston | 2493 | 20 | PV & Battery | 282-H1 | 2021-05-20 | 2021-06-15 | [28 empty] | 2021-06-28 | [12 empty] | 2021-08-24 | Online |  |  | Y
ESMAEX-00743 | Weston | 2493 | 18.148 | PV | 282-H1 | 2022-01-20 | 2022-02-15 | [28 empty] | 2022-03-24 | [12 empty] | 2022-06-29 | Online |  |  | Y
ESMAEX-00949 | Weston | 2493 | 5 | Battery | 282-H1 | 2022-03-20 | 2022-06-20 | [28 empty] | 2022-07-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01079 | Weston | 2493 | 7.6 | PV & Battery | 282-H8 | 2022-04-13 | 2022-05-02 | [28 empty] | 2022-07-05 | [12 empty] | 2023-01-30 | Online |  |  | Y
ESMAEX-01339 | Weston | 2493 | 17.6 | PV | 282-H10 | 2022-06-30 | 2022-07-18 | [28 empty] | 2022-09-14 | [12 empty] | 2023-02-07 | Online |  |  | Y
ESMAEX-01390 | Weston | 2493 | 10 | PV & Battery | 282-H1 | 2022-07-20 | 2022-08-03 | [28 empty] | 2022-09-16 | [12 empty] | 2022-12-08 | Online |  |  | Y
ESMAEX-01484 | Weston | 2493 | 240 | PV & Battery | 33-H3 | 2022-08-18 | 2022-09-09 | [28 empty] | 2022-12-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01490 | Weston | 2493 | 15.3 | PV & Battery | 282-H1 | 2022-08-19 | 2022-09-09 | [28 empty] | 2022-09-28 | [12 empty] | 2022-12-13 | Online |  |  | Y
ESMAEX-01599 | Weston | 2493 | 25 | PV & Battery | 282-H8 | 2022-09-16 | 2022-10-25 | [28 empty] | 2023-04-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01636 | Weston | 2493 | 20.352 | PV & Battery | 282-H10 | 2022-09-27 | 2022-10-27 | [28 empty] | 2022-11-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-01822 | Weston | 2493 | 15.2 | PV & Battery | 342-H1 | 2022-11-16 | 2022-12-08 | [28 empty] | 2023-01-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01873 | Weston | 2493 | 26.6 | PV & Battery | 450-H7 | 2022-11-30 | 2022-12-08 | [28 empty] | 2023-03-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-02328 | Weston | 2493 | 100 | PV | 450-H7 | 2023-03-31 | 2023-04-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-02330 | Weston | 2493 | 50 | PV | 450-H7 | 2023-03-31 | 2023-04-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-02344 | Weston | 2493 | 22.8 | PV | 282-H10 | 2023-04-04 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
2325546 | Weston | 2493 | 200 | PV | 342-H1 | 2019-02-08 |  | -31066 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
2297073 | Needham | 2494 | 99.9 | PV | 148-H4 | 2018-08-30 | 2018-08-31 | 1 |  | 1 | 2018-09-19 | 2018-11-14 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-31 | Online |  | Private
2326325 | Needham | 2494 | 194 | PV | 148-H4 | 2019-02-04 |  | -31062 |  | 0 | 2019-02-22 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2019-09-10 | Online
2342982 | Needham | 2494 | 43.2 | PV | 148-H1 | 2019-05-16 | 2019-05-22 |  |  |  | 2019-06-13 | [24 empty] | 2019-08-22 | [12 empty] | 2020-02-06 | Online
2387570 | Needham | 2494 | 7 | PV & Battery | 148-H4 | 2020-01-06 | 2020-01-16 |  |  |  | 2020-02-27 | [24 empty] | 2020-04-28 | [12 empty] | 2020-07-21 | Online
2382008 | Needham | 2494 | 17 | PV & Battery | 148-08 | 2019-12-05 | 2020-01-06 |  |  |  | 2020-01-17 | [24 empty] | 2020-05-21 | [12 empty] | 2020-08-05 | Online
2176734 | Needham | 2494 | 866 | PV | 148-H6 | 2016-07-13 | 2016-09-23 | 52 |  | 52 | 2016-10-24 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2181939 | Needham | 2494 | 64.8 | PV | 148-H1 | 2016-10-17 | 2016-10-21 | 4 |  | 4 | 2016-11-17 |  | -30495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-07 | 2016-12-15 | [6 empty] | 0 |  | 0
2385802 | Needham | 2494 | 460 | PV | TBD | 2019-12-09 | 2020-01-30 |  |  |  | 2020-02-14 | [24 empty] | 2020-11-05 | [12 empty] | 2023-04-28 | Online
2410747 | Needham | 2494 | 19.57 | PV & Battery | 292-H4 | 2020-07-22 | 2020-07-22 |  |  |  | 2020-08-14
4318615 | Needham | 2494 | 1300 | PV & Battery | TBD | 2020-08-27 | 2020-09-10 |  |  |  | 2020-10-01
4590881 | Needham | 2494 | 17.36 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 |  |  |  | 2020-12-22 | [24 empty] | 2021-04-07
4637344 | Needham | 2494 | 22.6 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 |  |  |  | 2020-12-29 | [24 empty] | 2021-03-03 | [12 empty] | 2022-01-05 | Online
5333657 | Needham | 2494 | 86.4 | PV | TBD | 2021-01-27 | 2021-03-15 |  |  |  | 2021-03-31 | [37 empty] | 2022-03-31 | Online
ESMAEX-00041 | Needham | 2494 | 250 | PV | 148-H7 | 2021-04-13 | 2021-05-11 | [28 empty] | 2021-09-07 | [12 empty] | 2022-06-24 | Online |  |  | Y
ESMAEX-00552 | Needham | 2494 | 750 | PV & Battery | 148-H6 | 2021-12-23 | 2022-01-13 | [28 empty] | 2022-10-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-00560 | Needham | 2494 | 11.4 | Battery | 292-H4 | 2021-11-02 | 2021-11-18 | [28 empty] | 2021-12-02 | [12 empty] | 2022-03-23 | Online |  |  | Y
ESMAEX-00693 | Needham | 2494 | 140 | PV | TBD | 2021-12-23 | 2022-01-13 | [28 empty] | 2022-03-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-00736 | Needham | 2494 | 3.8 | PV & Battery | 148-H4 | 2022-01-18 | 2022-06-20 | [28 empty] | 2022-06-28 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-00927 | Needham | 2494 | 15.2 | PV & Battery | 292-H4 | 2022-03-16 | 2022-04-06 | [28 empty] | 2022-05-12 | [13 empty] | In Queue |  |  | Y
ESMAEX-00931 | Needham | 2494 | 15.2 | PV & Battery | 148-H4 | 2022-03-16 | 2022-04-06 | [28 empty] | 2022-05-11 | [12 empty] | 2023-01-24 | Online |  |  | Y
ESMAEX-01227 | Needham | 2494 | 10 | PV & Battery | 292-H4 | 2022-05-26 | 2022-06-28 | [28 empty] | 2022-10-04 | [12 empty] | 2023-03-07 | Online |  |  | Y
ESMAEX-01629 | Needham | 2494 | 17.6 | PV & Battery | 292-H4 | 2022-09-26 | 2022-10-13 | [28 empty] | 2022-11-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01712 | Needham | 2494 | 5 | Battery | 148-H1 | 2022-10-24 | 2022-11-10 | [28 empty] | 2023-01-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-01738 | Needham | 2494 | 20 | PV & Battery | 148-H1 | 2022-10-28 | 2022-11-18 | [28 empty] | 2023-01-03 | [12 empty] | 2023-04-12 | Online |  |  | Y
ESMAEX-02007 | Needham | 2494 | 15.2 | PV & Battery | 148-H4 | 2023-01-12 | 2023-02-09 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
ESMAEX-02153 | Needham | 2494 | 7.6 | Battery | 148-H1 | 2023-02-13 | 2023-03-02 | [42 empty] | In Queue |  |  | Y
ESMAEX-02181 | Needham | 2494 | 17.5698 | Battery | 148-H7 | 2023-02-21 | 2023-03-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-02248 | Needham | 2494 | 15.2 | PV | 292-H4 | 2023-03-08 | 2023-03-28 | [28 empty] | 2023-04-13 | [13 empty] | In Queue |  |  | Y
2382255 | Needham | 2494 | 17.25 | PV | 148-H4 | 2019-12-09 | 2020-01-02 |  |  |  | 2020-01-21 | [24 empty] | 2020-07-08 | [12 empty] | 2020-11-23 | Online
2232421 | Bourne | 2532 | 36 | PV | 3-89-925 | 2017-07-25 | 2017-07-31 | 4 |  | 4 | 2017-08-30 |  | -30693 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-13 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
2289611 | Bourne | 2532 | 115.2 | PV | 4-86-402 | 2018-07-10 | 2018-07-18 | 6 |  | 6 | 2018-08-02 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
2387476 | Bourne | 2532 | 43.2 | PV | 4-86-402 | 2020-02-10 | 2020-02-13 |  |  |  | 2020-02-26 | [24 empty] | 2020-03-20 | [12 empty] | 2020-06-30 | Online
2152371 | Bourne | 2532 | 566.1 | PV | 3-89-925 | 2016-03-04 | 2016-05-18 | 53 |  | 53 | 2016-06-10 |  | -30381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | 2016-09-01 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2312381 | Bourne | 2532 | 999 | PV | 3-88-88 | 2018-11-21 | 2018-12-03 | 8 |  | 8 | 2018-12-14 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
2322113 | Bourne | 2532 | 1390 | PV | 4-86-402 | 2019-01-07 | 2019-01-16 | 7 |  | 7 | 2019-01-25 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2355532 | Bourne | 2532 | 499 | PV | TBD | 2019-07-29 | 2019-08-06 |  |  |  | 2019-08-21 | [24 empty] | 2021-09-28
2378858 | Bourne | 2532 | 5000 | PV & Battery | TBD | 2019-11-21 | 2019-12-23 |  |  |  | 2020-01-07 | [24 empty] | 2021-10-21
2381610 | Bourne | 2532 | 5000 | PV & Battery | TBD | 2019-12-13 | 2019-12-23 |  |  |  | 2020-01-16 | [24 empty] | 2021-10-21
4991635 | Bourne | 2532 | 19.9 | PV | TBD | 2021-01-21 | 2021-01-26 |  |  |  | 2021-02-17 | [24 empty] | 2021-02-19 | [12 empty] | 2021-06-24 | Online
ESMAEX-00059 | Bourne | 2532 | 499 | PV & Battery | 4-86-86 | 2021-04-16 | 2021-05-14 | [28 empty] | 2022-03-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-00461 | Bourne | 2532 | 39.98 | PV | 4-86-408 | 2021-09-30 | 2021-10-18 | [28 empty] | 2021-12-13 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00619 | Bourne | 2532 | 999 | PV & Battery | 4-86-402 | 2021-11-24 | 2021-12-17 | [42 empty] | In Queue |  |  | Y
ESMAEX-00959 | Bourne | 2532 | 18 | PV & Battery | 4-86-408 | 2022-03-23 | 2022-04-12 | [28 empty] | 2022-08-10 | [12 empty] | 2023-01-26 | Online |  |  | Y
ESMAEX-01091 | Bourne | 2532 | 6 | PV & Battery | 4-86-402 | 2022-04-19 | 2022-05-23 | [28 empty] | 2022-06-27 | [12 empty] | 2023-03-09 | Online |  |  | Y
2239274 | Buzzards Bay | 2532 | 119.9 | PV | 3-88-2J4 | 2017-09-12 | 2017-09-13 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
2173585 | Buzzards Bay | 2532 | 100 | PV | 3-88-2J4 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2356276 | Buzzards Bay | 2532 | 4975 | PV & Battery | TBD | 2019-08-05 | 2019-08-09 |  |  |  | 2019-08-26
2407059 | Buzzards Bay | 2532 | 133.2 | PV | TBD | 2020-04-20 | 2020-06-30 |  |  |  | 2020-07-20 | [24 empty] | 2020-09-18 | [13 empty] | Withdrawn
ESMAEX-00253 | Buzzards Bay | 2532 | 50 | Hydro | 3-84-965 | 2021-07-20 | 2021-08-03 | [28 empty] | 2022-01-04 | [13 empty] | In Queue |  |  | N
ESMAEX-00920 | Buzzards Bay | 2532 | 11.4 | PV | 3-88-88 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-04-11 | [13 empty] | In Queue |  |  | Y
ESMAEX-01254 | Buzzards Bay | 2532 | 6 | Battery | 3-88-2J3 | 2022-06-03 | 2022-06-21 | [28 empty] | 2022-06-23 | [13 empty] | In Queue |  |  | Y
2407949 | Holliston | 2532 | 15.2 | PV | TBD | 2020-07-14 | 2020-07-14 |  |  |  | 2020-07-27 | [24 empty] | 2020-11-05 | [13 empty] | Withdrawn
2263854 | Wareham | 2532 | 4875 | PV | 3-85-928 | 2018-01-26 | 2018-02-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
ESMAEX-00540 | Wareham | 2532 | 196 | PV | 3-83-83 | 2021-10-25 | 2021-11-16 | [28 empty] | 2022-02-20 | [13 empty] | In Queue |  |  | Y
2391363 | Cataumet | 2534 | 29.23 | PV & Battery | 4-78-410 | 2020-02-21 | 2020-03-11 |  |  |  | 2020-03-27 | [24 empty] | 2020-04-14 | [12 empty] | 2020-06-30 | Online
ESMAEX-00875 | Aquinnah | 2535 | 8.7 | PV & Battery | 4-97-226 | 2022-03-03 | 2022-03-22 | [28 empty] | 2022-03-23 | [12 empty] | 2022-08-12 | Online |  |  | Y
2327284 | Chilmark | 2535 | 25 | PV | 4-91-126 | 2019-02-20 | 2019-02-22 | 2 |  | 2 | 2019-02-28 |  | -31080 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0 |  |  | 2019-10-02 | Online
4310270 | Chilmark | 2535 | 166.9 | PV | 4-97-226 | 2020-09-16 | 2020-09-16 |  |  |  | 2020-10-01 | [24 empty] | 2020-02-20 | [12 empty] | 2020-12-22 | Online
2396188 | Chilmark | 2535 | 20.95 | PV | TBD | 2020-04-06 | 2020-04-27 |  |  |  | 2020-05-04 | [24 empty] | 2020-05-21 | [12 empty] | 2021-03-12 | Online
2191358 | Chilmark | 2535 | 65.2 | PV | 4-91-226 | 2016-11-22 | 2016-11-30 | 6 |  | 6 | 2016-12-29 |  | -30525 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0
2271199 | Chilmark | 2535 | 40.35 | PV | 4-97-226 | 2018-02-06 | 2018-03-21 | 31 |  | 31 | 2018-04-12 |  | -30850 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-24 | [6 empty] | 0 |  | 0
2311303 | Chilmark | 2535 | 83.52 | PV | 4-91-126 | 2018-11-21 | 2018-12-06 | 11 |  | 11 | 2018-12-06 |  | -31020 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | 2018-12-27 | [6 empty] | 0 |  | 0 | [5 empty] | Private
2327379 | Chilmark | 2535 | 16.24 | PV | 4-97-220 | 2019-02-20 | 2019-02-20 | 0 |  | 0 | 2019-03-01 |  | -31081 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-08 | [7 empty] | 0 |  | 0
ESMAEX-01041 | Chilmark | 2535 | 15.2 | PV & Battery | 4-97-220 | 2022-04-08 | 2022-04-28 | [28 empty] | 2022-05-06 | [12 empty] | 2022-10-17 | Online |  |  | Y
ESMAEX-01069 | Chilmark | 2535 | 24.3 | PV | 4-97-226 | 2022-04-11 | 2022-04-28 | [28 empty] | 2022-05-06 | [12 empty] | 2022-10-18 | Online |  |  | Y
ESMAEX-01416 | Chilmark | 2535 | 8.26 | PV & Battery | 4-97-226 | 2022-07-28 | 2022-08-15 | [28 empty] | 2022-08-16 | [12 empty] | 2023-04-12 | Online |  |  | Y
ESMAEX-01423 | Chilmark | 2535 | 17.6 | PV & Battery | 4-97-226 | 2022-08-02 | 2022-08-15 | [28 empty] | 2022-08-16 | [12 empty] | 2023-01-24 | Online |  |  | Y
2360385 | East Falmouth | 2536 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-17 | [12 empty] | 2020-06-25 | Online
4290987 | East Falmouth | 2536 | 17.04 | PV | 4-77A-77A | 2020-08-27 | 2020-09-02 |  |  |  | 2020-09-25 | [24 empty] | 2020-10-01 | [12 empty] | 2021-01-21 | Online
2397127 | East Falmouth | 2536 | 18.85 | PV | TBD | 2020-04-23 | 2020-04-27 |  |  |  | 2020-05-11 | [24 empty] | 2020-06-02 | [12 empty] | 2021-03-26 | Online
ESMAEX-00215 | East Falmouth | 2536 | 15.2 | PV | 4-98B-449 | 2021-06-25 | 2021-07-13 | [28 empty] | 2021-09-01 | [12 empty] | 2021-10-08 | Online |  |  | Y
ESMAEX-00864 | East Falmouth | 2536 | 15.93 | PV | 4-76-437 | 2022-02-28 | 2022-04-12 | [28 empty] | 2022-06-30 | [12 empty] | 2022-08-26 | Online |  |  | Y
ESMAEX-00963 | East Falmouth | 2536 | 15.2 | PV & Battery | 4-98B-449 | 2022-03-24 | 2022-04-12 | [28 empty] | 2022-05-31 | [12 empty] | 2023-01-17 | Online |  |  | Y
ESMAEX-01031 | East Falmouth | 2536 | 15.2 | PV & Battery | 4-77A-77A | 2022-04-07 | 2022-04-28 | [28 empty] | 2022-05-31 | [12 empty] | 2023-01-26 | Online |  |  | Y
ESMAEX-01299 | East Falmouth | 2536 | 20 | PV & Battery | 4-98B-449 | 2022-06-16 | 2022-07-13 | [28 empty] | 2022-08-10 | [12 empty] | 2022-11-09 | Online |  |  | Y
2343408 | East Falmouth | 2536 | 36 | PV | 4-98A-98A | 2019-05-29 | 2019-05-29 |  |  |  | 2019-06-05 | [24 empty] | 2019-06-17 | [12 empty] | 2020-03-05 | Online
4304824 | East Falmouth | 2536 | 20 | PV & Battery | TBD | 2020-09-03 | 2020-09-09 |  |  |  | 2020-09-29 | [24 empty] | 2020-12-08 | [12 empty] | 2021-02-12 | Online
2367955 | East Falmouth | 2536 | 134 | PV | TBD | 2019-10-18 | 2019-10-23 |  |  |  | 2019-11-07 | [24 empty] | 2019-12-11 | [12 empty] | 2021-03-05 | Online
2316966 | East Falmouth | 2536 | 4500 | PV | 4-98A-98A | 2018-12-11 | 2018-12-17 | 4 |  | 4 | 2019-01-04 |  | -31041 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online
2317177 | East Falmouth | 2536 | 4000 | PV | 4-98A-98A | 2018-12-12 | 2018-12-17 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-14 | Online
2391234 | East Falmouth | 2536 | 3000 | PV & Battery | TBD | 2020-03-09
2398257 | East Falmouth | 2536 | 500 | PV | TBD | 2020-04-27 | 2020-04-30 |  |  |  | 2020-05-18
4430372 | East Falmouth | 2536 | 198 | PV | TBD | 2020-09-30 | 2020-10-08 |  |  |  | 2020-11-04 | [24 empty] | 2021-01-28
5184793 | East Falmouth | 2536 | 22.32 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 |  |  |  | 2021-03-16 | [24 empty] | 2021-05-05
2187033 | East Falmouth | 2536 | 16.7 | PV | 4-98A-98A | 2016-10-27 | 2016-11-02 | 4 |  | 4 | 2016-12-06 |  | -30508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2016-12-15 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online |  | PRIVATE
2202817 | East Falmouth | 2536 | 109.25 | PV | 4-98A-98A | 2017-01-27 | 2017-02-13 | 11 |  | 11 | 2017-02-27 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | 2017-05-03 | [6 empty] | 0 |  | 0 |  |  | 2017-08-17 | Online |  | Private
2237110 | East Falmouth | 2536 | 159.9 | PV | 4-98B-449 | 2017-09-06 | 2017-09-08 | 2 |  | 2 | 2017-09-28 |  | -30713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-21 | [6 empty] | 0 |  | 0 |  |  | 2018-06-28 | Online
2343832 | East Falmouth | 2536 | 72 | PV | 4-98B-449 | 2019-05-28 | 2019-05-28 |  |  |  | 2019-06-07 | [24 empty] | 2019-06-17 | [12 empty] | 2020-02-14 | Online
2366343 | East Falmouth | 2536 | 39.83 | PV | TBD | 2019-09-27 | 2019-10-09 |  |  |  | 2019-10-31 | [24 empty] | 2019-11-29 | [12 empty] | 2020-03-13 | Online
2172199 | East Falmouth | 2536 | 48 | PV | 4-98A-98A | 2016-07-15 | 2016-09-14 | 43 |  | 43 | 2016-09-29 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
ESMAEX-00319 | East Falmouth | 2536 | 310 | PV | TBD | 2021-11-10 | 2021-12-14 | [28 empty] | 2022-08-19 | [13 empty] | In Queue |  |  | Y
2165668 | Falmouth | 2536 | 90 | PV | 4-98A-98A | 2016-07-29 | 2016-08-09 | 7 |  | 7 | 2016-08-24 |  | -30434 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online |  | PRIVATE | Y
2166111 | Falmouth | 2536 | 100.8 | PV | 4-98A-98A | 2016-07-26 | 2016-08-29 | 24 |  | 24 | 2016-08-29 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2017-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-04-28 | Online
4288338 | Falmouth | 2536 | 33.3 | PV | TBD | 2020-09-01 | 2020-09-03 |  |  |  | 2020-09-25 | [24 empty] | 2020-10-01 | [12 empty] | 2021-03-12 | Online
2228808 | Falmouth | 2536 | 7190 | PV | 4-98A-429 | 2017-06-30 | 2017-07-12 | 7 |  | 7 | 2017-08-04 |  | -30675 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-23 | 2018-01-17 | 249 |  | 249 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
2246979 | Falmouth | 2536 | 1500 | PV | 4-98A-98A | 2017-10-12 | 2017-11-07 | 18 |  | 18 | 2017-11-29 |  | -30755 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-22 | [7 empty] | 0 |  | 0
2303631 | Falmouth | 2536 | 3300 | PV & Battery | 4-98A-98A | 2018-10-08 | 2018-10-12 | 4 |  | 4 | 2018-11-02 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-04 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2322598 | Falmouth | 2536 | 3300 | PV & Battery | 4-98A-98A | 2019-01-17 |  | -31050 |  | 0 | 2019-01-29 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2391172 | Falmouth | 2536 | 4990 | PV & Battery | TBD | 2020-03-09 | [43 empty] | Withdrawn
2394862 | Falmouth | 2536 | 3500 | PV & Battery | TBD | 2020-03-27 | 2020-04-08 |  |  |  | 2020-04-23
2410632 | Falmouth | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-13 |  |  |  | 2020-08-14
2411107 | Falmouth | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-30 |  |  |  | 2020-08-18
2152612 | Falmouth | 2536 | 16.15 | PV | 4-98A-462 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2337408 | Hatchville | 2536 | 28.5 | PV | 4-98A-98A | 2019-02-26 | 2019-04-12 | 33 |  | 33 | 2019-05-02 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
2368537 | Hatchville | 2536 | 20 | PV | TBD | 2019-10-18 | 2019-10-28 |  |  |  | 2019-11-13 | [24 empty] | 2020-01-03 | [13 empty] | Withdrawn
5344212 | Hatchville | 2536 | 44.98 | PV | TBD | 2021-03-15 | 2021-03-17 |  |  |  | 2021-03-31 | [24 empty] | 2021-04-06 | [12 empty] | 2022-01-26 | Online
ESMAEX-00685 | Hatchville | 2536 | 10 | PV | 4-98A-429 | 2021-12-21 | 2022-01-12 | [28 empty] | 2022-05-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01412 | Hatchville | 2536 | 17.6 | PV | 4-98A-98A | 2022-07-27 | 2022-08-10 | [28 empty] | 2022-08-15 | [12 empty] | 2022-11-04 | Online |  |  | Y
ESMAEX-02000 | Hatchville | 2536 | 17.6 | PV & Battery | 4-78-78 | 2023-01-11 | 2023-02-02 | [28 empty] | 2023-02-21 | [13 empty] | In Queue |  |  | Y
2252869 | Milton | 2536 | 19.3 | PV | 4-98B-449 | 2017-11-10 | 2017-11-30 | 13 |  | 13 | 2017-12-21 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-01 | [6 empty] | 0 |  | 0 |  |  | 2018-10-05 | Online
2178798 | Teaticket | 2536 | 228 | PV | 4-76-437 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-02 |  | -30484 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | [7 empty] | 0 |  | 0 |  |  | 2017-12-01 | Online
ESMAEX-01667 | Teaticket | 2536 | 3.8 | PV | 4-98A-98A | 2022-10-07 | 2022-10-27 | [28 empty] | 2022-12-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-00367 | Waquoit | 2536 | 20 | PV & Battery | 4-98B-845 | 2021-08-27 | 2021-09-15 | [28 empty] | 2021-12-10 | [12 empty] | 2022-04-27 | Online |  |  | Y
ESMAEX-00748 | Waquoit | 2536 | 11.52 | PV & Battery | 4-98B-845 | 2022-01-20 | 2022-02-24 | [28 empty] | 2022-03-28 | [12 empty] | 2023-04-28 | Online |  |  | Y
ESMAEX-00397 | East Sandwich | 2537 | 10 | PV & Battery | 4-87A-87A | 2021-09-09 | 2021-09-29 | [28 empty] | 2021-11-03 | [12 empty] | 2022-04-11 | Online |  |  | Y
ESMAEX-00517 | East Sandwich | 2537 | 9.12 | PV & Battery | 4-87B-87B | 2021-10-20 | 2021-11-09 | [28 empty] | 2022-02-24 | [12 empty] | 2022-04-26 | Online |  |  | Y
ESMAEX-01023 | East Sandwich | 2537 | 26.4 | PV & Battery | 4-87A-87A | 2022-04-06 | 2022-04-28 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
2360131 | East Sandwich | 2537 | 4600 | PV | TBD | 2019-08-28 | 2019-09-04 |  |  |  | 2019-10-01
2401361 | East Sandwich | 2537 | 499 | PV | TBD | 2020-05-04 | 2020-05-20 |  |  |  | 2020-06-08
2349579 | East Sandwich | 2537 | 3510 | PV & Battery | 4-87A-471 | 2019-05-30 | 2019-06-26 |  |  |  | 2019-07-12
2349576 | East Sandwich | 2537 | 849.5 | PV & Battery | 4-87A-471 | 2019-05-31 | 2019-06-26 |  |  |  | 2019-07-12
2354511 | East Sandwich | 2537 | 900 | PV | TBD | 2019-06-24 | 2019-07-19 |  |  |  | 2019-08-13 | [38 empty] | Withdrawn
2131316 | Sandwich | 2537 | 15.2 | PV | 4-81B-443 | 2016-02-08 | 2016-02-12 | 4 |  | 4 | 2016-02-29 |  | -30307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-28 | 2016-04-25 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online |  | PRIVATE
4877705 | East Wareham | 2538 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-02-09 | [12 empty] | 2021-10-07 | Online
5132131 | East Wareham | 2538 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 |  |  |  | 2021-03-08
2360402 | East Wareham | 2538 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-14 | [12 empty] | 2020-06-25 | Online
2386584 | East Wareham | 2538 | 30 | PV | 3-84-960 | 2019-12-03 | 2020-02-04 |  |  |  | 2020-02-24 | [24 empty] | 2020-04-16 | [12 empty] | 2020-10-06 | Online
5299014 | East Wareham | 2538 | 19 | PV | TBD | 2021-02-19 | 2021-03-10 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-21 | [12 empty] | 2021-11-12 | Online
5483849 | East Wareham | 2538 | 21.4 | PV | TBD | 2021-03-29 | 2021-04-01 |  |  |  | 2021-04-16 | [24 empty] | 2021-04-21 | [12 empty] | 2021-10-21 | Online
2354403 | East Wareham | 2538 | 15.2 | PV | 3-84-960 | 2019-04-19 | 2019-07-25 | 69 |  | 69 | 2019-08-13 |  | -31198 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
ESMAEX-02012 | East Wareham | 2538 | 480 | PV | 3-84-961 | 2023-02-24 | 2023-03-21 | [42 empty] | In Queue |  |  | Y
ESMAEX-02013 | East Wareham | 2538 | 1000 | PV | 3-84-961 | 2023-03-08 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02014 | East Wareham | 2538 | 360 | PV | 3-84-961 | 2023-02-24 | 2023-03-21 | [42 empty] | In Queue |  |  | Y
ESMAEX-02199 | East Wareham | 2538 | 120 | Battery | 3-84-961 | 2023-02-24 | 2023-03-21 | [28 empty] | 2023-04-26 | [13 empty] | In Queue |  |  | Y
2296718 | Wareham | 2538 | 199.8 | PV | 3-81-81 | 2018-08-23 | 2018-08-29 | 4 |  | 4 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2384553 | Wareham | 2538 | 4995 | PV & Battery | TBD | 2019-12-30 | 2020-01-06 |  |  |  | 2020-02-06
2183002 | Edgartown | 2539 | 21.75 | PV | 4-97-97 | 2016-10-21 | 2016-10-27 | 4 |  | 4 | 2016-11-28 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2016-12-16 | [6 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online |  | PRIVATE
2178416 | Edgartown | 2539 | 21.38 | PV | 4-75-75 | 2016-06-15 | 2016-10-19 | 90 |  | 90 | 2016-11-02 |  | -30484 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online |  | PRIVATE
2187701 | Edgartown | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30511 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-08-03 | Online |  | PRIVATE
2188255 | Edgartown | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-14 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-08-23 | Online |  | PRIVATE
2333814 | Edgartown | 2539 | 24 | PV | TBD | 2019-02-26 | 2019-03-20 | 16 |  | 16 | 2019-04-09 |  | -31108 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
2282055 | Edgartown | 2539 | 466.6 | PV & Battery | 4-97-97 | 2018-05-29 | 2018-05-31 | 2 |  | 2 | 2018-06-15 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
2389485 | Edgartown | 2539 | 22.8 | PV | TBD | 2019-12-26 | 2020-02-25 |  |  |  | 2020-03-11 | [24 empty] | 2020-03-19 | [12 empty] | 2020-11-04 | Online
2306817 | Edgartown | 2539 | 22.4 | PV | 4-99-99 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 | 2018-11-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2247507 | Edgartown | 2539 | 133.2 | PV | 4-97-97 | 2017-10-23 | 2017-11-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
2360354 | Edgartown | 2539 | 286 | PV & Battery | TBD | 2019-08-16 | 2019-09-05 |  |  |  | 2019-09-23 | [24 empty] | 2020-01-29 | [13 empty] | Withdrawn
ESMAEX-00682 | Edgartown | 2539 | 11.21 | PV & Battery | TBD | 2021-12-21 | 2022-02-09 | [28 empty] | 2022-02-16 | [12 empty] | 2022-08-22 | Online |  |  | Y
ESMAEX-00687 | Edgartown | 2539 | 8.12 | PV & Battery | 4-75-123 | 2021-12-22 | 2022-01-12 | [28 empty] | 2022-02-04 | [12 empty] | 2022-07-27 | Online |  |  | Y
ESMAEX-00832 | Edgartown | 2539 | 2500 | PV & Battery | 4-75-223 | 2022-02-14 | 2022-03-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-00891 | Edgartown | 2539 | 29 | PV | 4-75-227 | 2022-03-09 | 2022-05-23 | [28 empty] | 2022-05-31 | [12 empty] | 2023-03-10 | Online |  |  | Y
ESMAEX-01006 | Edgartown | 2539 | 132.48 | PV & Battery | 4-75-75 | 2022-04-04 | 2022-04-20 | [28 empty] | 2022-08-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-01133 | Edgartown | 2539 | 44.37 | PV & Battery | 4-75-227 | 2022-05-02 | 2022-05-24 | [28 empty] | 2022-06-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-01136 | Edgartown | 2539 | 34.2 | PV & Battery | 4-75-75 | 2022-05-03 | 2022-05-31 | [28 empty] | 2022-06-02 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01348 | Edgartown | 2539 | 466.66 | PV & Battery | TBD | 2022-07-06 | 2022-07-08 | [42 empty] | In Queue |  |  | Y
ESMAEX-01415 | Edgartown | 2539 | 16.1 | PV & Battery | TBD | 2022-07-28 | 2022-08-15 | [28 empty] | 2022-08-16 | [12 empty] | 2022-11-15 | Online |  |  | Y
2180040 | Falmouth | 2540 | 16 | PV | 4-72-433 | 2016-09-27 | 2016-10-03 | 4 |  | 4 | 2016-11-07 |  | -30487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online |  | PRIVATE
2313194 | Falmouth | 2540 | 24.84 | PV | 4-98A-98A | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31028 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0 |  |  | 2019-05-02 | Online
2376010 | Falmouth | 2540 | 133.2 | PV | TBD | 2019-12-09 | 2019-12-12 |  |  |  | 2019-12-26 | [24 empty] | 2020-01-15 | [12 empty] | 2020-08-11 | Online
2391570 | Falmouth | 2540 | 24.6 | PV & Battery | 4-107-832 | 2020-03-05 | 2020-03-12 |  |  |  | 2020-03-30 | [37 empty] | 2020-08-31 | Online
2411656 | Falmouth | 2540 | 18.7 | PV & Battery | TBD | 2020-07-15 | 2020-08-03 |  |  |  | 2020-08-24 | [24 empty] | 2020-09-02 | [12 empty] | 2020-10-23 | Online
2355581 | Falmouth | 2540 | 46.08 | PV | TBD | 2019-08-01 | 2019-08-07 |  |  |  | 2019-08-21 | [24 empty] | 2019-09-20 | [12 empty] | 2021-02-24 | Online
2411634 | Falmouth | 2540 | 66.6 | PV | TBD | 2020-08-03 | 2020-08-07 |  |  |  | 2020-08-24 | [24 empty] | 2020-09-02 | [12 empty] | 2021-03-18 | Online
2179819 | Falmouth | 2540 | 32.4 | PV | 4-72-433 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-03 |  | -30485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2219873 | Falmouth | 2540 | 54.88 | PV | 4-72-433 | 2017-05-23 | 2017-05-25 | 2 |  | 2 | 2017-06-13 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | [7 empty] | 0 |  | 0
2317183 | Falmouth | 2540 | 1000 | PV | 4-98A-98A | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2327130 | Falmouth | 2540 | 4980 | PV & Battery | 4-98B-448 | 2019-02-01 | 2019-02-15 | 10 |  | 10 | 2019-02-27 |  | -31079 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2389176 | Falmouth | 2540 | 21.58 | PV & Battery | 4-72-433 | 2019-12-18 | 2020-02-24 |  |  |  | 2020-03-09 | [24 empty] | 2020-04-28
2386189 | Falmouth | 2540 | 34.6 | PV & Battery | 4-78-420 | 2020-01-22 | 2020-02-03 |  |  |  | 2020-02-19 | [24 empty] | 2020-04-17
2389199 | Falmouth | 2540 | 958 | PV & Battery | TBD | 2020-02-18 | 2020-02-24 |  |  |  | 2020-03-09 | [38 empty] | Withdrawn
2411073 | Falmouth | 2540 | 15.2 | PV | 4-76-436 | 2020-06-15 | 2020-07-28 |  |  |  | 2020-08-18
2412337 | Falmouth | 2540 | 122 | PV | TBD | 2020-08-06 | 2020-08-11 |  |  |  | 2020-08-28 | [24 empty] | 2020-10-15 | [12 empty] | 2022-09-15 | Online
5518931 | Falmouth | 2540 | 27.6 | PV & Battery | TBD | 2021-01-26 | 2021-03-19 |  |  |  | 2021-04-21
ESMAEX-00124 | Falmouth | 2540 | 36.54 | PV | TBD | 2021-05-15 | 2021-06-01 | [28 empty] | 2021-08-19 | [12 empty] | 2022-01-10 | Online |  |  | Y
ESMAEX-00132 | Falmouth | 2540 | 5 | PV | 4-76-436 | 2021-05-18 | 2021-06-07 | [28 empty] | 2021-08-05 | [12 empty] | 2021-12-08 | Online |  |  | Y
ESMAEX-00435 | Falmouth | 2540 | 16.82 | PV | 4-76-76 | 2021-09-21 | 2021-11-09 | [28 empty] | 2022-01-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-00604 | Falmouth | 2540 | 19 | PV | 4-98A-98A | 2021-11-18 | 2022-01-04 | [28 empty] | 2022-02-07 | [12 empty] | 2022-05-24 | Online |  |  | Y
ESMAEX-00721 | Falmouth | 2540 | 10 | Battery | 4-76-436 | 2022-01-11 | 2022-02-03 | [28 empty] | 2022-03-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-00764 | Falmouth | 2540 | 9.6 | PV & Battery | 4-72-72 | 2022-01-28 | 2022-02-17 | [28 empty] | 2022-03-16 | [12 empty] | 2022-08-26 | Online |  |  | Y
ESMAEX-00776 | Falmouth | 2540 | 4999.2 | Battery | 4-76-76 | 2022-09-20 | 2022-10-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-00968 | Falmouth | 2540 | 15.2 | PV & Battery | 4-72-72 | 2022-03-25 | 2022-04-13 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01418 | Falmouth | 2540 | 179.3 | PV & Battery | 4-72-72 | 2022-10-25 | 2022-11-16 | [28 empty] | 2022-11-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01422 | Falmouth | 2540 | 17.4 | PV | 4-72-72 | 2022-08-02 | 2022-08-15 | [28 empty] | 2022-08-18 | [12 empty] | 2022-11-30 | Online |  |  | Y
2391457 | Falmouth | 2540 | 15.2 | PV | 4-72-72 | 2020-03-10 | 2020-03-12 |  |  |  | 2020-03-27 | [24 empty] | 2020-04-17
2233739 | Woods Hole | 2540 | 86.4 | PV | 4-72-433 | 2017-08-03 | 2017-08-03 | 0 |  | 0 | 2017-09-08 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-06-08 | Online
2180239 | Bourne | 2542 | 7950 | PV | 4-98A-98A | 2016-10-04 | 2016-10-12 | 6 |  | 6 | 2016-11-07 |  | -30487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-05-11 | -44 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0
2187704 | Sandwich | 2542 | 4700 | Micro Grid | 4-98A-98A | 2016-12-07 | 2016-12-21 | 10 |  | 10 | 2016-12-09 |  | -30511 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-20 | [7 empty] | 0 |  | 0 |  |  | 2019-10-17 | Online
ESMAEX-00827 | Woods Hole | 2543 | 18.99 | PV & Battery | 4-91-91 | 2022-02-10 | 2022-03-11 | [28 empty] | 2022-04-05 | [12 empty] | 2022-08-22 | Online |  |  | Y
ESMAEX-01153 | Woods Hole | 2543 | 7.8 | PV & Battery | 4-91-91 | 2022-05-06 | 2022-05-26 | [28 empty] | 2022-07-13 | [12 empty] | 2023-04-24 | Online |  |  | Y
2336292 | Falmouth | 2556 | 26 | PV | 4-98B-448 | 2019-04-04 | 2019-04-11 | 5 |  | 5 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2366459 | North Falmouth | 2556 | 15.2 | PV | TBD | 2019-08-01 | 2019-10-16 |  |  |  | 2019-11-01 | [24 empty] | 2019-11-29 | [12 empty] | 2020-05-18 | Online
2383638 | North Falmouth | 2556 | 15.2 | PV | 4-78-78 | 2020-01-08 | 2020-01-15 |  |  |  | 2020-01-31 | [24 empty] | 2020-02-13 | [12 empty] | 2020-10-28 | Online
2411670 | North Falmouth | 2556 | 18 | PV & Battery | TBD | 2020-08-04 | 2020-08-10 |  |  |  | 2020-08-24 | [24 empty] | 2020-09-02
ESMAEX-00404 | North Falmouth | 2556 | 25.075 | PV | 4-78-861 | 2021-09-10 | 2021-09-29 | [28 empty] | 2022-01-27 | [12 empty] | 2022-08-30 | Online |  |  | Y
ESMAEX-00539 | North Falmouth | 2556 | 12 | Battery | 4-78-420 | 2021-10-25 | 2021-11-16 | [28 empty] | 2022-02-04 | [12 empty] | 2022-06-29 | Online |  |  | Y
ESMAEX-01123 | North Falmouth | 2556 | 15.29 | Battery | 4-78-420 | 2022-04-28 | 2022-05-18 | [28 empty] | 2022-06-20 | [12 empty] | 2022-08-26 | Online |  |  | Y
2397130 | Oak Bluffs | 2557 | 300 | PV | 4-99-224 | 2020-03-18 | 2020-04-22 |  |  |  | 2020-05-11 | [24 empty] | 2020-09-16 | [12 empty] | 2022-06-07 | Online
2407481 | Oak Bluffs | 2557 | 22 | PV & Battery | TBD | 2020-06-29 | 2020-07-01 |  |  |  | 2020-07-21 | [24 empty] | 2020-08-28
4340257 | Oak Bluffs | 2557 | 233.1 | PV | TBD | 2020-05-26 | 2020-09-15 |  |  |  | 2020-10-08 | [24 empty] | 2021-02-24
2177535 | Oak Bluffs | 2557 | 21.15 | PV | 4-99-224 | 2016-08-25 | 2016-10-19 | 39 |  | 39 | 2016-11-02 |  | -30484 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-03 | Online |  | PRIVATE
2262599 | Oak Bluffs | 2557 | 90 | PV | 4-99-99 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-06 | Online
2295584 | Oak Bluffs | 2557 | 280 | PV & Battery | 4-75-75 | 2018-08-20 | 2018-08-22 | 2 |  | 2 | 2018-09-11 |  | -30958 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
2244459 | Oak Bluffs | 2557 | 20.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2244463 | Oak Bluffs | 2557 | 27.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2311848 | Oak Bluffs | 2557 | 249.8 | PV | 4-75-75 | 2018-11-29 | 2018-12-11 | 8 |  | 8 | 2018-12-11 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0
ESMAEX-00193 | Oak Bluffs | 2557 | 19.92 | PV | 4-99-224 | 2021-06-19 | 2021-07-08 | [28 empty] | 2021-09-08 | [12 empty] | 2021-11-04 | Online |  |  | Y
ESMAEX-00991 | Oak Bluffs | 2557 | 20 | PV | 4-99-225 | 2022-03-30 | 2022-04-15 | [28 empty] | 2022-04-18 | [12 empty] | 2023-01-09 | Online |  |  | Y
ESMAEX-01389 | Oak Bluffs | 2557 | 26.385 | PV & Battery | TBD | 2022-07-20 | 2022-08-03 | [28 empty] | 2022-08-22 | [13 empty] | In Queue |  |  | Y
2210632 | Onset | 2558 | 19.5 | PV | 3-84-17J1 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-13 |  | -30597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-19 | [7 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online |  | PRIVATE
2412247 | Onset | 2558 | 17.6 | PV | TBD | 2020-06-23 | 2020-08-13 |  |  |  | 2020-08-28 | [24 empty] | 2020-09-18 | [12 empty] | 2021-04-05 | Online
ESMAEX-01649 | Onset | 2558 | 10 | Battery | 3-88-17J1 | 2022-10-03 | 2022-12-07 | [28 empty] | 2023-01-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-02152 | Onset | 2558 | 15.988 | Battery | 3-88-17J1 | 2023-02-13 | 2023-03-02 | [28 empty] | 2023-03-07 | [13 empty] | In Queue |  |  | Y
2260502 | Bourne | 2559 | 32 | PV | 4-86-86 | 2017-12-28 | 2018-01-08 | 7 |  | 7 | 2018-01-29 |  | -30797 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
2412341 | Pocasset | 2559 | 999 | PV & Battery | TBD | 2020-08-12 | 2020-08-12 |  |  |  | 2020-08-28
5099887 | Pocasset | 2559 | 20 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 |  |  |  | 2021-03-08 | [24 empty] | 2021-05-13
ESMAEX-00188 | Pocasset | 2559 | 36.83 | PV | 4-81A-406 | 2021-06-15 | 2021-07-01 | [28 empty] | 2021-08-24 | [12 empty] | 2022-02-08 | Online |  |  | Y
2341513 | Sagamore Beach | 2562 | 20 | PV | 3-89-925 | 2019-05-16 | 2019-05-17 |  |  |  | 2019-05-28 | [24 empty] | 2019-06-11 | [12 empty] | 2019-12-17 | Online
ESMAEX-02140 | Sagamore Beach | 2562 | 15.2 | PV & Battery | 3-89-925 | 2023-02-08 | 2023-02-23 | [28 empty] | 2023-02-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-00055 | South Sandwich | 2563 | 250 | PV | 4-87A-87A | 2021-04-14 | 2021-05-03 | [28 empty] | 2021-08-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-00143 | South Sandwich | 2563 | 10 | Battery | 4-71-455 | 2021-05-20 | 2021-06-08 | [28 empty] | 2021-07-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01088 | South Sandwich | 2563 | 15.2 | PV & Battery | 4-81B-440 | 2022-04-16 | 2022-05-03 | [28 empty] | 2022-05-31 | [12 empty] | 2022-11-21 | Online |  |  | Y
2232261 | Sandwich | 2563 | 66.6 | PV | 4-81B-81B | 2017-07-23 | 2017-07-31 | 6 |  | 6 | 2017-08-29 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2018-01-02 | [6 empty] | 0 |  | 0 |  |  | 2018-04-16 | Online
2218204 | Sandwich | 2563 | 70 | PV | 4-81B-443 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30631 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-06 | [6 empty] | 0 |  | 0 |  |  | 2018-04-19 | Online
2360491 | Sandwich | 2563 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-14 | [12 empty] | 2020-06-25 | Online
2284071 | Sandwich | 2563 | 133.2 | PV | 4-81B-443 | 2018-06-04 | 2018-06-14 | 8 |  | 8 | 2018-06-28 |  | -30905 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online |  | Private
2373431 | Sandwich | 2563 | 112.5 | PV | TBD | 2019-11-19 | 2019-11-19 |  |  |  | 2019-12-06 | [24 empty] | 2020-04-06 | [12 empty] | 2021-03-16 | Online
2155836 | Sandwich | 2563 | 109.2 | PV | 4-81B-443 | 2016-06-09 | 2016-06-22 | 9 |  | 9 | 2016-07-01 |  | -30396 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2301106 | Sandwich | 2563 | 133.2 | PV | 4-81B-443 | 2018-09-19 | 2018-09-26 | 5 |  | 5 | 2018-10-12 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2320561 | Sandwich | 2563 | 500 | PV | 4-87A-471 | 2019-01-02 | 2019-01-02 | 0 |  | 0 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0
2331592 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-01-02 | 2019-02-26 | 39 |  | 39 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2323654 | Sandwich | 2563 | 2660 | PV | 4-81B-443 | 2019-01-23 | 2019-01-29 | 4 |  | 4 | 2019-02-04 |  | -31062 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
2334444 | Sandwich | 2563 | 77.5 | PV | 4-81B-443 | 2019-02-19 | 2019-03-28 | 27 |  | 27 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
2330926 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-07 | 2019-03-15 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330392 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330718 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330720 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330360 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330875 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330882 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330923 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2331148 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2331153 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2331348 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2331371 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2331587 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2334390 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-443 | 2019-03-27 | 2019-03-27 | 0 |  | 0 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
2353792 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2354118 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2354162 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2354172 | Sandwich | 2563 | 3250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-12
2355014 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2355016 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2355017 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2355143 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-19
2355015 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-07-29 | 2019-07-29 |  |  |  | 2019-08-19
2370777 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 |  |  |  | 2019-12-02
2372155 | Sandwich | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-11-19 | 2019-11-19 |  |  |  | 2019-12-05
2372267 | Sandwich | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 |  |  |  | 2019-12-06
2374039 | Sandwich | 2563 | 249 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 |  |  |  | 2019-12-12
2378798 | Sandwich | 2563 | 490 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 |  |  |  | 2020-01-06
2392033 | Sandwich | 2563 | 250 | PV | TBD | 2020-02-27 | 2020-03-16 |  |  |  | 2020-04-01 | [24 empty] | 2020-05-21 | [13 empty] | Withdrawn
2396845 | Sandwich | 2563 | 133.3 | PV | TBD | 2020-03-17 | 2020-04-20 |  |  |  | 2020-05-06 | [24 empty] | 2020-05-21
2403120 | Sandwich | 2563 | 90 | PV & Battery | TBD | 2020-05-28 | 2020-06-03 |  |  |  | 2020-06-19 | [24 empty] | 2020-07-29
2410106 | Sandwich | 2563 | 7.6 | PV | 4-81B-443 | 2020-06-23 | 2020-07-28 |  |  |  | 2020-08-14 | [24 empty] | 2020-09-11
2133264 | Sandwich | 2563 | 109.2 | PV | 4-81B-443 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00636 | Falmouth | 2565 | 6.1 | Battery | 4-78-861 | 2021-12-02 | 2021-12-28 | [28 empty] | 2022-02-04 | [12 empty] | 2022-03-22 | Online |  |  | Y
ESMAEX-02383 | Falmouth | 2565 | 15.2 | PV | 4-78-420 | 2023-04-17 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
2403670 | Provincetown | 2567 | 22.89 | PV & Battery | 4-96-675 | 2020-06-03 | 2020-06-10 |  |  |  | 2020-06-29 | [24 empty] | 2020-07-13 | [12 empty] | 2020-08-31 | Online
2127808 | Oak Bluffs | 2568 | 566.1 | PV | 4-75-75 | 2016-01-14 | 2016-01-20 | 4 |  | 4 | 2016-02-08 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-07 | [6 empty] | 0 |  | 0
ESMAEX-00831 | Vineyard Haven | 2568 | 70 | PV | 4-75-75 | 2022-02-12 | 2022-03-03 | [28 empty] | 2022-04-11 | [12 empty] | 2023-03-17 | Online |  |  | Y
ESMAEX-01162 | Vineyard Haven | 2568 | 25 | PV & Battery | TBD | 2022-05-10 | 2022-06-07 | [28 empty] | 2022-06-18 | [12 empty] | 2022-09-02 | Online |  |  | Y
2201898 | Vineyard Haven | 2568 | 166.5 | PV | 4-75-75 | 2017-01-30 | 2017-02-13 | 10 |  | 10 | 2017-02-16 |  | -30558 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-18 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
2285555 | Vineyard Haven | 2568 | 29.75 | PV | 4-97-222 | 2018-06-12 | 2018-06-19 | 5 |  | 5 | 2018-07-06 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-07 | [7 empty] | 0 |  | 0 |  |  | 2018-11-08 | Online
2275151 | Vineyard Haven | 2568 | 5666.1 | PV & Battery | 4-75-75 | 2016-01-19 | 2016-02-08 | 14 |  | 14 | 2016-02-08 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-05-31 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-12-14 | Online
2319568 | Vineyard Haven | 2568 | 43.2 | PV | 4-75-75 | 2018-12-13 | 2018-12-20 | 5 |  | 5 | 2019-01-10 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-04 | [7 empty] | 0 |  | 0 |  |  | 2019-10-29 | Online
4429285 | Vineyard Haven | 2568 | 19.68 | PV | TBD | 2020-08-27 | 2020-10-07 |  |  |  | 2020-11-04 | [24 empty] | 2020-11-13 | [12 empty] | 2021-03-18 | Online
2303430 | Vineyard Haven | 2568 | 23.36 | PV | 3-24B-95 | 2018-10-05 | 2018-10-11 | 4 |  | 4 | 2018-10-31 | 2018-12-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
5392988 | Vineyard Haven | 2568 | 16.26 | PV & Battery | TBD | 2021-03-15 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-10-01 | [12 empty] | 2022-05-03 | Online
ESMAEX-01005 | Vineyard Haven | 2568 | 156.16 | PV & Battery | 4-75-75 | 2022-04-04 | 2022-04-20 | [28 empty] | 2022-05-17 | [13 empty] | In Queue |  |  | Y
2350188 | West Tisbury | 2568 | 20 | PV | TBD | 2019-05-23 | 2019-07-02 |  |  |  | 2019-07-17 | [24 empty] | 2019-09-27 | [12 empty] | 2020-03-11 | Online
2235688 | Barnstable | 2571 | 472 | PV | 4-80B-80B | 2017-07-24 | 2017-10-17 | 59 |  | 59 | 2017-11-06 |  | -30739 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | [7 empty] | 0 |  | 0
2188254 | Wareham | 2571 | 77.6 | PV | 3-84-968 | 2016-09-28 | 2016-12-09 | 52 |  | 52 | 2016-12-14 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | 2017-01-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online |  | PRIVATE
2216193 | Wareham | 2571 | 17.575 | PV | 3-84-963 | 2017-04-14 | 2017-04-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-10-27 | Online
2236093 | Wareham | 2571 | 46.8 | PV | 3-85-964 | 2017-08-07 | 2017-08-29 | 16 |  | 16 | 2017-09-21 |  | -30708 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-27 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
2218205 | Wareham | 2571 | 210 | Fuel Cell | 3-84-961 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30631 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 |  | 2017-06-20 | [5 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
2224664 | Wareham | 2571 | 3300 | PV | 3-85-928 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30658 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -18 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-12-12 | Online
2188543 | Wareham | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20 | Online
2188542 | Wareham | 2571 | 1500 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20 | Online
2188540 | Wareham | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online
2188544 | Wareham | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online
2284066 | Wareham | 2571 | 15.13 | PV | 3-84-963 | 2018-04-23 | 2018-06-13 | 37 |  | 37 | 2018-06-25 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-08-01 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
2358992 | Wareham | 2571 | 16.59 | PV | 3-83-83 | 2018-04-25 | 2018-06-13 | 35 |  | 35 | 2018-06-28 |  | -30905 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-24 | 2018-08-14 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2391934 | Wareham | 2571 | 28.8 | PV | TBD | 2020-03-16 | 2020-03-18 | [28 empty] | 2020-04-16 | [12 empty] | 2020-06-19 | Online
2358028 | Wareham | 2571 | 300 | PV | 3-86-966 | 2019-08-20 | 2019-08-22 |  |  |  | 2019-09-06 | [24 empty] | 2019-10-25 | [12 empty] | 2020-11-18 | Online
2237797 | Wareham | 2571 | 294 | PV | 3-86-966 | 2017-09-06 | 2017-09-11 | 3 |  | 3 | 2017-10-03 | 2017-10-17 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2302380 | Wareham | 2571 | 100 | PV | 8-83-83 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-19 | 2018-11-20 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-20 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2188541 | Wareham | 2571 | 2000 | PV | 3-83-83 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2260144 | Wareham | 2571 | 7310 | PV & Battery | 3-83-83 | 2017-11-16 | 2018-01-11 | 38 |  | 38 | 2018-01-25 |  | -30795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
2258018 | Wareham | 2571 | 15.2 | PV | 3-84-968 | 2017-12-12 | 2017-12-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2260699 | Wareham | 2571 | 8300 | PV & Battery | 3-83-83 | 2018-01-09 | 2018-01-09 | 0 |  | 0 | 2018-01-30 |  | -30798 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
2289380 | Wareham | 2571 | 996 | PV & Battery | 3-84-961 | 2018-06-27 | 2018-07-18 | 15 |  | 15 | 2018-08-02 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2296373 | Wareham | 2571 | 4890 | PV | 3-82-82 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2297500 | Wareham | 2571 | 4890 | PV | 8-83-83 | 2018-08-09 | 2018-09-19 | 29 |  | 29 | 2018-09-20 |  | -30965 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2306600 | Wareham | 2571 | 4999 | PV & Battery | 3-82-82 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2306818 | Wareham | 2571 | 240 | PV | 3-85-955 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -31006 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 | [5 empty] | Public
2322036 | Wareham | 2571 | 2250 | PV | 8-83-83 | 2019-01-04 | 2019-01-07 | 1 |  | 1 | 2019-01-25 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2333726 | Wareham | 2571 | 4500 | PV | 8-83-83 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-09 |  | -31108 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2343539 | Wareham | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-21 | 2019-05-29 |  |  |  | 2019-06-06
2344136 | Wareham | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-24 | 2019-05-30 |  |  |  | 2019-06-10
2353430 | Wareham | 2571 | 5000 | PV & Battery | tbd | 2019-06-04 | 2019-07-23 |  |  |  | 2019-08-05
2349786 | Wareham | 2571 | 5500 | PV & Battery | TBD | 2019-06-21 | 2019-06-28 |  |  |  | 2019-07-15
2366043 | Wareham | 2571 | 499 | Fuel Cell | TBD | 2019-10-15 | 2019-10-15 |  |  |  | 2019-10-29 | [38 empty] | Withdrawn
2371602 | Wareham | 2571 | 166.6 | PV | TBD | 2019-11-08 | 2019-11-15 |  |  |  | 2019-12-04 | [24 empty] | 2020-02-06 | [13 empty] | Withdrawn
2382474 | Wareham | 2571 | 66.6 | PV | 3-84-960 | 2019-12-19 | 2020-01-06 |  |  |  | 2020-01-30 | [24 empty] | 2020-02-12
2395041 | Wareham | 2571 | 216 | PV | TBD | 2020-03-27 | 2020-04-13 |  |  |  | 2020-04-23 | [37 empty] | 2021-09-28 | Online
2403535 | Wareham | 2571 | 149.3 | PV | TBD | 2020-06-10 | 2020-06-10 |  |  |  | 2020-07-20 | [24 empty] | 2020-09-03 | [12 empty] | 2021-07-21 | Online
4659423 | Wareham | 2571 | 4980 | PV & Battery | TBD | 2020-12-07 | 2020-12-14 |  |  |  | 2021-01-25 | [24 empty] | 2021-03-23
ESMAEX-00990 | Wareham | 2571 | 100 | PV & Battery | 3-86-966 | 2022-03-30 | 2022-04-15 | [28 empty] | 2022-05-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-01774 | Wareham | 2571 | 66.6 | PV | 3-86-966 | 2022-11-07 | 2022-11-16 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01836 | Wareham | 2571 | 12.9 | PV | 3-83-83 | 2022-11-21 | 2022-12-13 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-01962 | Wareham | 2571 | 7.6 | PV & Battery | 3-84-84 | 2023-01-05 | 2023-01-26 | [28 empty] | 2023-01-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-02360 | Wareham | 2571 | 2000 | PV | 3-83-83 | 2023-04-08 | 2023-04-18 | [42 empty] | In Queue |  |  | Y
2355009 | Wareham | 2571 | 500 | PV & Battery | 3-84-968 | 2019-07-18 | 2019-07-29 |  |  |  | 2019-08-16 | [24 empty] | 2019-10-15
4323415 | Wareham | 2571 | 200 | PV | TBD | 2020-08-06 | 2020-09-10 |  |  |  | 2020-10-05 | [38 empty] | Withdrawn
2349997 | West Tisbury | 2573 | 19.17 | PV | TBD | 2019-06-26 | 2019-06-28 |  |  |  | 2019-07-17 | [24 empty] | 2019-08-07 | [12 empty] | 2019-12-06 | Online
ESMAEX-00109 | West Falmouth | 2574 | 17.772 | PV & Battery | 4-98A-98A | 2021-05-07 | 2021-06-04 | [28 empty] | 2021-08-11 | [12 empty] | 2021-11-15 | Online |  |  | Y
2288244 | Tisbury | 2575 | 18 | PV | 4-97-222 | 2018-05-25 | 2018-07-10 | 32 |  | 32 | 2018-07-24 |  | -30923 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2018-11-16 | Online
ESMAEX-00446 | West Tisbury | 2575 | 12.98 | PV | 4-97-97 | 2021-09-24 | 2021-11-09 | [28 empty] | 2021-11-22 | [12 empty] | 2022-06-29 | Online |  |  | Y
ESMAEX-00644 | West Tisbury | 2575 | 25.568 | PV & Battery | TBD | 2021-12-07 | 2021-12-29 | [28 empty] | 2022-02-03 | [12 empty] | 2022-11-04 | Online |  |  | Y
ESMAEX-00673 | West Tisbury | 2575 | 20 | PV | 4-97-222 | 2021-12-20 | 2022-01-11 | [28 empty] | 2022-02-04 | [12 empty] | 2022-04-22 | Online |  |  | Y
ESMAEX-01243 | West Tisbury | 2575 | 17.6 | PV & Battery | 4-97-222 | 2022-06-02 | 2022-06-17 | [28 empty] | 2022-10-26 | [12 empty] | 2022-12-01 | Online |  |  | Y
ESMAEX-01340 | West Tisbury | 2575 | 23.6 | PV & Battery | 4-97-97 | 2022-07-01 | 2022-07-21 | [28 empty] | 2022-08-10 | [12 empty] | 2022-12-16 | Online |  |  | Y
ESMAEX-02415 | West Tisbury | 2575 | 19.398 | PV | TBD | 2023-04-25 | [43 empty] | In Queue |  |  | Y
5299167 | West Tisbury | 2575 | 16.225 | PV | TBD | 2021-03-02 | 2021-03-10 |  |  |  | 2021-04-02 | [24 empty] | 2021-05-27 | [12 empty] | 2022-01-26 | Online
2124323 | West Tisbury | 2575 | 33.9 | PV | 4-97-97 | 2016-01-13 | 2016-01-15 | 2 |  | 2 | 2016-01-20 |  | -30279 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-03 | 2016-02-17 | [6 empty] | 0 |  | 0 |  |  | 2016-08-05 | Online
2109230 | West Tisbury | 2575 | 213.2 | PV | 4-97-220 | 2015-11-17 | 2015-11-30 | 9 |  | 9 | 2015-12-01 |  | -30243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-11-30 | Online
2173995 | West Tisbury | 2575 | 22.8 | PV | 4-97-97 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-16 | Online |  | PRIVATE
2173999 | West Tisbury | 2575 | 22.8 | PV | 4-97-226 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online |  | PRIVATE
2103349 | West Tisbury | 2575 | 233.1 | PV | 4-97-220 | 2015-10-15 | 2015-10-23 | 6 |  | 6 | 2015-10-29 |  | -30220 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-12-07 | [7 empty] | 0 |  | 0 | 2017-03-23 | 2017-03-23 | 2017-04-10 | Online |  | PRIVATE
2134027 | West Tisbury | 2575 | 95.4 | PV | 4-97-97 | 2016-02-17 | 2016-02-23 | 4 |  | 4 | 2016-03-11 |  | -30316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-05-10 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | PRIVATE | Y
2279017 | West Tisbury | 2575 | 22.8 | PV | 4-97-222 | 2018-05-03 | 2018-05-16 | 9 |  | 9 | 2018-05-30 |  | -30884 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
2308167 | West Tisbury | 2575 | 22.33 | PV & Battery | 3-24B-95 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 | 2018-12-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-07 | 2018-12-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-09-06 | Online |  | Private
2233942 | West Tisbury | 2575 | 48 | PV | 4-97-220 | 2017-08-02 | 2017-08-08 | 4 |  | 4 | 2017-09-11 |  | -30700 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | [7 empty] | 0 |  | 0
2313933 | West Tisbury | 2575 | 92.4 | PV | 4-97-97 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-24 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0
2385299 | West Tisbury | 2575 | 25 | PV | TBD | 2020-01-22 | 2020-01-28 |  |  |  | 2020-02-14 | [37 empty] | 2021-10-18 | Online
2409477 | West Wareham | 2576 | 7.6 | PV | TBD | 2020-07-01 | 2020-07-16 |  |  |  | 2020-08-04 | [37 empty] | 2022-02-22 | Online
ESMAEX-00219 | West Wareham | 2576 | 15.2 | PV | 3-85-85 | 2021-06-29 | 2021-07-15 | [28 empty] | 2021-08-05 | [12 empty] | 2021-10-22 | Online |  |  | Y
ESMAEX-01200 | West Wareham | 2576 | 15.045 | PV | MID-702 | 2022-05-20 | 2022-06-23 | [28 empty] | 2022-06-27 | [12 empty] | 2023-01-09 | Online |  |  | Y
ESMAEX-01592 | West Wareham | 2576 | 19 | PV | 3-85-85 | 2022-09-15 | 2022-10-03 | [28 empty] | 2022-10-11 | [12 empty] | 2023-03-27 | Online |  |  | Y
2336183 | West Wareham | 2576 | 57.6 | PV | 3-86-86 | 2019-04-10 | 2019-04-10 | 0 |  | 0 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-16 | Online
2402967 | West Wareham | 2576 | 10 | PV & Battery | 3-85-85 | 2020-05-28 | 2020-06-03 |  |  |  | 2020-06-19 | [24 empty] | 2020-06-30 | [12 empty] | 2021-02-02 | Online
2403572 | West Wareham | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-10 |  |  |  | 2020-06-29 | [24 empty] | 2020-09-11
2404678 | West Wareham | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-11 |  |  |  | 2020-07-01 | [24 empty] | 2020-08-03
4350518 | West Wareham | 2576 | 266.3 | PV | TBD | 2020-09-18 | 2020-09-22 |  |  |  | 2020-10-08 | [24 empty] | 2020-11-13 | [12 empty] | 2022-03-30 | Online
2122405 | Wareham | 2576 | 16.5 | PV | 3-86-966 | 2015-12-04 | 2016-01-07 | 24 |  | 24 | 2016-01-11 |  | -30272 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-03-11 | Online
2220029 | Wareham | 2576 | 18 | PV | 3-85-85 | 2017-05-24 | 2017-05-30 | 3 |  | 3 | 2017-06-13 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online
2265247 | Wareham | 2576 | 201.6 | PV | 3-83-83 | 2018-02-05 | 2018-02-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-09 | [6 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
2277865 | Wareham | 2576 | 3300 | PV & Battery | 3-86-966 | 2018-04-25 | 2018-05-08 | 9 |  | 9 | 2018-05-22 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-31 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
2230372 | Wareham | 2576 | 24.5 | PV | 3-85-85 | 2017-07-14 | 2017-07-25 | 7 |  | 7 | 2017-08-16 |  | -30683 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-08 | [6 empty] | 0 |  | 0
2233733 | Wareham | 2576 | 2000 | PV | 3-85-85 | 2017-07-31 | 2017-08-01 | 1 |  | 1 | 2017-09-08 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-26 | 2018-01-23 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
2253372 | Wareham | 2576 | 4320 | PV & Battery | 3-83-83 | 2017-11-10 | 2017-12-07 | 18 |  | 18 | 2017-12-28 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
2278333 | Wareham | 2576 | 201.6 | PV | 3-86-966 | 2018-05-01 | 2018-05-11 | 8 |  | 8 | 2018-05-29 |  | -30883 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-17 | [6 empty] | 0 |  | 0
2282256-A | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30921 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2282256-B | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30921 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2282256-C | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30921 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-A | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-B | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-C | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-D | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-E | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-F | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-G | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287856-H | Wareham | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2286968 | Wareham | 2576 | 2660 | PV & Battery | 3-81-81 | 2018-06-13 | 2018-06-29 | 12 |  | 12 | 2018-07-17 |  | -30918 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
2295852 | Wareham | 2576 | 3000 | PV & Battery | 3-81-81 | 2018-08-16 | 2018-08-23 | 5 |  | 5 | 2018-09-11 |  | -30958 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2300908 | Wareham | 2576 | 4180 | PV & Battery | 3-81-81 | 2018-09-04 | 2018-09-21 | 13 |  | 13 | 2018-10-11 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2371039 | Wareham | 2576 | 100 | PV | TBD | 2019-11-08 | 2019-11-15 |  |  |  | 2019-12-03 | [24 empty] | 2020-03-02 | [13 empty] | Withdrawn
4490547 | Wareham | 2576 | 233.2 | PV | TBD | 2020-10-16 | 2020-10-21 |  |  |  | 2020-11-18
ESMAEX-00089 | Wareham | 2576 | 499.5 | PV | 3-86-966 | 2021-04-30 | 2021-05-19 | [42 empty] | In Queue |  |  | Y
ESMAEX-00675 | Wareham | 2576 | 148.92 | PV | 3-85-928 | 2021-12-20 | 2022-02-08 | [28 empty] | 2022-05-23 | [13 empty] | In Queue |  |  | Y
2395408 | Wareham | 2576 | 470 | PV | TBD | 2020-04-06 | 2020-04-09 |  |  |  | 2020-04-27 | [24 empty] | 2020-06-30 | [13 empty] | Withdrawn
2297083 | Wareham | 2576 | 4075 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2297267 | Wareham | 2576 | 500 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2297503 | Wareham | 2576 | 250 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2170912 | West Wareham | 2576 | 24.5 | PV | 3-85-85 | 2016-08-30 | 2016-09-06 | 5 |  | 5 | 2016-09-22 |  | -30455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2392870 | West Wareham | 2576 | 133.2 | PV | TBD | 2020-03-18 | 2020-03-20 |  |  |  | 2020-04-08 | [24 empty] | 2020-06-15
5149756 | Brewster | 2601 | 13.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-08 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-20 | [12 empty] | 2021-06-16 | Online
2130872 | Hyannis | 2601 | 21.045 | PV | 4-63-521 | 2016-02-09 | 2016-02-12 | 3 |  | 3 | 2016-02-24 |  | -30304 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-06 | 2016-04-27 | [6 empty] | 0 |  | 0 |  |  | 2016-07-28 | Online
2170678 | Hyannis | 2601 | 306.07 | PV | 4-84B-524 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-21 |  | -30454 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-03-28 | Online |  | PRIVATE
2136574 | Hyannis | 2601 | 465 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
2136578 | Hyannis | 2601 | 364 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
2151406 | Hyannis | 2601 | 136.5 | PV | 4-63-521 | 2016-05-12 | 2016-05-31 | 13 |  | 13 | 2016-06-09 |  | -30380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-15 | 2016-08-08 | [6 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
2198079 | Hyannis | 2601 | 38 | PV | 4-63-63 | 2017-01-09 | 2017-01-11 | 2 |  | 2 | 2017-01-24 |  | -30541 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-02-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-01 | Online |  | PRIVATE
2235860 | Hyannis | 2601 | 28.8 | PV | 4-84B-524 | 2017-08-25 | 2017-08-29 | 2 |  | 2 | 2017-09-20 |  | -30707 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-05 | 2018-01-12 | [6 empty] | 0 |  | 0 |  |  | 2018-02-08 | Online
2228337 | Hyannis | 2601 | 997.965 | PV | 4-80B-80B | 2017-06-13 | 2017-07-12 | 20 |  | 20 | 2017-08-03 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19 | Online
2303431 | Hyannis | 2601 | 40 | PV | 4-80B-514 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-10-11 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0 |  |  | 2019-09-06 | Online |  | Private
2329185 | Hyannis | 2601 | 43.6 | PV | 4-63-63 | 2019-02-25 | 2019-02-28 | 3 |  | 3 | 2019-03-12 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-09-23 | Online
2333242 | Hyannis | 2601 | 254.29 | PV | 4-63-63 | 2019-03-14 | 2019-03-19 | 3 |  | 3 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0 |  |  | 2020-01-09 | Online
2361417 | Hyannis | 2601 | 24.78 | PV | 4-63-63 | 2019-09-05 | 2019-09-09 |  |  |  | 2019-09-27 | [24 empty] | 2019-10-18 | [12 empty] | 2020-05-19 | Online
2251318 | Hyannis | 2601 | 250 | PV | 4-63-63 | 2017-11-10 | 2017-11-21 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-08 | Online
2360467 | Hyannis | 2601 | 262.5 | Fuel Cell | 4-84A-520 | 2019-09-04 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-17 | [12 empty] | 2020-06-25 | Online
2363855 | Hyannis | 2601 | 112.1 | PV | TBD | 2019-09-05 | 2019-09-09 |  |  |  | 2019-10-15 | [37 empty] | 2020-08-19 | Online
2350400 | Hyannis | 2601 | 112.5 | PV | TBD | 2019-06-25 | 2019-07-11 |  |  |  | 2019-07-18 | [24 empty] | 2019-08-06 | [12 empty] | 2020-08-31 | Online
2328863 | Hyannis | 2601 | 100 | PV | 4-63-63 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-12 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-18 | Online
2355569 | Hyannis | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 |  |  |  | 2019-08-21 | [24 empty] | 2019-09-20 | [12 empty] | 2021-03-29 | Online
2356386 | Hyannis | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 |  |  |  | 2019-08-27 | [24 empty] | 2019-09-20 | [12 empty] | 2021-03-29 | Online
2166109 | Hyannis | 2601 | 20 | PV | 4-63-63 | 2016-07-13 | 2016-08-15 | 23 |  | 23 | 2016-08-29 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue |  | PRIVATE
2182194 | Hyannis | 2601 | 19 | PV | 4-63-905 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30496 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2288599 | Hyannis | 2601 | 1500 | PV | 4-84B-524 | 2018-05-31 | 2018-07-11 | 29 |  | 29 | 2018-07-26 |  | -30925 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0
2316959 | Hyannis | 2601 | 500 | PV | 4-63-63 | 2018-11-21 | 2018-12-12 | 15 |  | 15 | 2019-01-04 |  | -31041 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330458 | Hyannis | 2601 | 699.9 | PV | 4-63-63 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-03-20 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2022-12-31 | Online
2359768 | Hyannis | 2601 | 17.6 | PV | 4-80B-514 | 2019-05-06 | 2019-09-03 | 86 |  | 86 | 2019-09-17 |  | -31223 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2391270 | Hyannis | 2601 | 133.2 | PV | TBD | 2019-07-26 | 2019-07-29 |  |  |  | 2019-08-16 | [24 empty] | 2020-09-03 | [12 empty] | 2021-06-09 | Online
2371521 | Hyannis | 2601 | 250 | PV | TBD | 2019-09-30 | 2019-10-28 |  |  |  | 2019-12-04 | [24 empty] | 2020-03-13 | [12 empty] | 2021-12-31 | Online
2368753 | Hyannis | 2601 | 200 | PV | TBD | 2019-10-29 | 2019-10-31 |  |  |  | 2019-11-14 | [24 empty] | 2020-02-06 | [12 empty] | 2021-07-19 | Online
2404659 | Hyannis | 2601 | 999 | PV & Battery | TBD | 2020-02-07 | 2020-06-11 |  |  |  | 2020-07-01
2392889 | Hyannis | 2601 | 72 | PV | TBD | 2020-03-17 | 2020-03-20 |  |  |  | 2020-04-08 | [24 empty] | 2020-05-14 | [13 empty] | Withdrawn
2399725 | Hyannis | 2601 | 73.3 | PV | TBD | 2020-04-06 | 2020-05-13 |  |  |  | 2020-06-04 | [24 empty] | 2020-06-23 | [12 empty] | 2022-03-08 | Online
2395561 | Hyannis | 2601 | 50 | PV | 4-80B-80B | 2020-04-08 | [29 empty] | 2020-07-07
2399178 | Hyannis | 2601 | 460 | PV | 4-80B-80B | 2020-04-16 | 2020-04-20 |  |  |  | 2020-05-27 | [24 empty] | 2021-12-15
2407747 | Hyannis | 2601 | 24.07 | PV | TBD | 2020-07-06 | 2020-07-07 |  |  |  | 2020-07-27 | [38 empty] | Withdrawn
2411466 | Hyannis | 2601 | 186 | PV | TBD | 2020-08-06 | 2020-08-06 |  |  |  | 2020-08-24 | [24 empty] | 2020-10-22
2412477 | Hyannis | 2601 | 250 | PV | TBD | 2020-08-12 | 2020-08-12 |  |  |  | 2020-08-28 | [24 empty] | 2021-01-13
4305225 | Hyannis | 2601 | 86.4 | PV | TBD | 2020-08-27 | 2020-09-03 |  |  |  | 2020-09-29 | [23 empty] | 2020-11-13 | [13 empty] | 2021-11-09 | Online
4886864 | Hyannis | 2601 | 7.6 | PV | 4-84A-520 | 2020-12-14 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-02-09 | [12 empty] | 2021-08-25 | Online
4945583 | Hyannis | 2601 | 120 | PV | TBD | 2021-01-12 | 2021-01-21 |  |  |  | 2021-02-05 | [24 empty] | 2021-06-18 | [12 empty] | 2021-12-23 | Online
4983604 | Hyannis | 2601 | 90 | PV | TBD | 2021-01-20 | 2021-01-20 |  |  |  | 2021-02-11 | [24 empty] | 2021-02-19 | [12 empty] | 2021-11-09 | Online
4983194 | Hyannis | 2601 | 51.9 | PV | TBD | 2021-01-20 | 2021-01-20 |  |  |  | 2021-03-11 | [24 empty] | 2021-03-15
5018578 | Hyannis | 2601 | 120 | PV | TBD | 2021-01-21 | 2021-02-05 |  |  |  | 2021-03-01 | [24 empty] | 2021-03-09 | [12 empty] | 2021-12-15 | Online
4936393 | Hyannis | 2601 | 69.25 | PV | TBD | 2021-01-21 |  |  |  |  | 2021-02-11 | [24 empty] | 2021-02-19
4945477 | Hyannis | 2601 | 86.6 | PV | TBD | 2021-01-21 | 2021-01-21 |  |  |  | 2021-02-05 | [24 empty] | 2021-04-22 | [12 empty] | 2022-09-22 | Online
5483911 | Hyannis | 2601 | 400 | PV | TBD | 2021-03-16 | 2021-04-01 |  |  |  | 2021-04-16 | [24 empty] | 2021-09-23
ESMAEX-00203 | Hyannis | 2601 | 30 | Battery | TBD | 2021-06-22 | [43 empty] | In Queue |  |  | Y
ESMAEX-00546 | Hyannis | 2601 | 150 | PV | 4-63-531 | 2021-10-26 | 2021-12-15 | [28 empty] | 2022-07-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00648 | Hyannis | 2601 | 220 | PV | 4-63-521 | 2021-12-08 | 2021-12-30 | [28 empty] | 2022-02-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-00834 | Hyannis | 2601 | 75 | PV | 4-63-521 | 2022-02-15 | 2022-04-15 | [28 empty] | 2022-06-30 | [13 empty] | In Queue |  |  | Y
ESMAEX-01025 | Hyannis | 2601 | 4999.2 | Battery | 4-63-63 | 2023-01-12 | 2023-04-14 | [42 empty] | In Queue |  |  | Y
ESMAEX-01119 | Hyannis | 2601 | 7.6 | PV & Battery | TBD | 2022-04-27 | 2022-05-17 | [28 empty] | 2022-05-31 | [12 empty] | 2022-08-12 | Online |  |  | Y
ESMAEX-01912 | Hyannis | 2601 | 100 | PV & Battery | 4-80B-514 | 2022-12-09 | 2023-01-04 | [28 empty] | 2023-01-23 | [13 empty] | In Queue |  |  | Y
2387744 | Hyannis | 2601 | 115.05 | PV | TBD | 2020-02-10 | 2020-02-13 |  |  |  | 2020-03-02 | [24 empty] | 2020-06-15 | [12 empty] | 2021-02-23 | Online
2399742 | Hyannis | 2601 | 60 | PV | TBD | 2020-04-08 | 2020-05-13 |  |  |  | 2020-06-02 | [24 empty] | 2020-06-23 | [12 empty] | 2022-02-28 | Online
2370582 | Sharon | 2607 | 370 | PV | TBD | 2019-10-07 | 2019-11-12 |  |  |  | 2019-11-29 | [24 empty] | 2020-06-02
2370630 | Sharon | 2607 | 660 | PV | TBD | 2019-10-07 | 2019-11-12 |  |  |  | 2019-11-29
2370666 | Sharon | 2607 | 5000 | PV & Battery | TBD | 2019-10-07 | 2019-11-13 |  |  |  | 2019-11-29 | [24 empty] | 2022-10-11
2173782 | Barnstable | 2630 | 50 | PV | 4-84B-524 | 2016-08-29 | 2016-09-09 | 9 |  | 9 | 2016-10-12 |  | -30469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-03-10 | Online |  | PRIVATE
2214303 | Barnstable | 2630 | 373 | PV | 4-84B-524 | 2017-04-12 | 2017-04-18 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-25 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-04-09 | Online
ESMAEX-02273 | Barnstable | 2630 | 8 | Battery | 4-84B-510 | 2023-03-15 | 2023-04-03 | [28 empty] | 2023-04-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-02399 | Barnstable | 2630 | 10 | PV | 4-84B-510 | 2023-04-20 | [43 empty] | In Queue |  |  | Y
2404275 | Barnstable | 2630 | 3146 | PV & Battery | TBD | 2019-05-26 | 2020-06-15 |  |  |  | 2020-07-01 | [38 empty] | Withdrawn
2386368 | Barnstable | 2630 | 240 | PV | 4-84B-510 | 2020-02-03 | 2020-02-03 |  |  |  | 2020-02-20 | [24 empty] | 2020-06-15
2389479 | Barnstable | 2630 | 66.6 | PV | TBD | 2020-02-24 | 2020-02-25 |  |  |  | 2020-03-11 | [24 empty] | 2020-04-08 | [13 empty] | Withdrawn
2122697 | Brewster | 2631 | 73.2 | PV | 4-89B-89B | 2016-01-05 | 2016-01-08 | 3 |  | 3 | 2016-01-27 |  | -30284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-17 | 2016-02-25 | [6 empty] | 0 |  | 0 |  |  | 2016-07-11 | Online
2226549 | Brewster | 2631 | 19.2 | PV | 4-89B-576 | 2017-06-23 | 2017-06-28 | 3 |  | 3 | 2017-07-24 |  | -30666 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-01 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online
2271201 | Brewster | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-22 | 15 |  | 15 | 2018-04-12 |  | -30850 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
2271377 | Brewster | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-26 | 17 |  | 17 | 2018-04-13 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | [6 empty] | 2018-07-16 | 30916 |  | 30916 |  |  | 2019-05-16 | Online
2324673 | Brewster | 2631 | 25 | PV | 4-95A-597 | 2019-01-28 | 2019-02-01 | 4 |  | 4 | 2019-02-11 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0 |  |  | 2019-07-01 | Online
2325660 | Brewster | 2631 | 24.99 | PV | 4-95B-600 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-15 |  | -31071 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2019-07-15 | Online
2294155 | Brewster | 2631 | 15.2 | PV | 4-89A-553 | 2018-08-02 | 2018-08-15 | 9 |  | 9 | 2018-08-30 |  | -30950 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-04 | Online
2395844 | Brewster | 2631 | 16.28 | PV & Battery | 4-89A-553 | 2020-03-27 | 2020-04-15 |  |  |  | 2020-04-30 | [24 empty] | 2020-05-04 | [12 empty] | 2020-06-04 | Online
2368090 | Brewster | 2631 | 199.8 | PV | 4-95A-597 | 2018-09-12 | 2018-09-20 | 6 |  | 6 | 2018-10-10 |  | -30979 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-14 | [7 empty] | 0 |  | 0 |  |  | 2020-11-10 | Online
2169301 | Brewster | 2631 | 19.25 | PV | 4-89B-576 | 2016-08-18 | 2016-08-24 | 4 |  | 4 | 2016-09-14 |  | -30449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2329348 | Brewster | 2631 | 20 | PV | 4-89B-576 | 2019-02-28 | 2019-03-05 | 3 |  | 3 | 2019-03-13 |  | -31089 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0
2340839 | Brewster | 2631 | 20.01 | PV | 4-89B-618 | 2019-04-12 | 2019-05-14 | 22 |  | 22 | 2019-05-22 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
2348521 | Brewster | 2631 | 480 | PV | TBD | 2019-05-30 | 2019-06-21 |  |  |  | 2019-07-05 | [24 empty] | 2019-11-05 | [12 empty] | 2021-08-12 | Online
2347755 | Brewster | 2631 | 1490 | PV & Battery | TBD | 2019-05-31 | 2019-06-21 |  |  |  | 2019-07-05 | [24 empty] | 2020-09-18 | [12 empty] | 2022-03-22 | Online
2363697 | Brewster | 2631 | 2500 | PV | TBD | 2019-09-06 | 2019-09-25 |  |  |  | 2019-10-10 | [24 empty] | 2022-03-31
2396639 | Brewster | 2631 | 66.6 | PV | TBD | 2020-03-13 | 2020-04-20 |  |  |  | 2020-05-06 | [24 empty] | 2020-08-05 | [13 empty] | Withdrawn
2398609 | Brewster | 2631 | 4999 | PV & Battery | TBD | 2020-04-30 | 2020-04-30 |  |  |  | 2020-05-18
2399192 | Brewster | 2631 | 4999 | PV & Battery | TBD | 2020-05-05 | 2020-05-08 |  |  |  | 2020-05-27
2404421 | Brewster | 2631 | 10 | PV & Battery | 4-95A-597 | 2020-06-15 | 2020-06-29 |  |  |  | 2020-07-01 | [24 empty] | 2020-07-23 | [12 empty] | 2022-03-15 | Online
2411939 | Brewster | 2631 | 57.6 | PV | TBD | 2020-07-22 | 2020-08-06 |  |  |  | 2020-08-26 | [24 empty] | 2020-09-11
ESMAEX-00096 | Brewster | 2631 | 57.6 | PV | 4-89B-946 | 2021-05-03 | 2021-06-11 | [28 empty] | 2021-06-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00334 | Brewster | 2631 | 10 | PV & Battery | 4-628-628 | 2021-08-20 | 2021-09-09 | [28 empty] | 2021-10-26 | [12 empty] | 2022-06-13 | Online |  |  | Y
ESMAEX-01058 | Brewster | 2631 | 25.2 | PV & Battery | 4-89A-553 | 2022-04-08 | 2022-04-28 | [28 empty] | 2022-05-06 | [12 empty] | 2023-01-05 | Online |  |  | Y
ESMAEX-02197 | Brewster | 2631 | 16 | PV & Battery | 4-89B-89B | 2023-02-23 | 2023-03-21 | [28 empty] | 2023-03-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-02212 | Brewster | 2631 | 15.2 | Battery | 4-89B-576 | 2023-02-28 | 2023-03-23 | [28 empty] | 2023-03-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-00650 | East Brewster | 2631 | 100 | PV | 4-89B-618 | 2021-12-09 | 2021-12-30 | [28 empty] | 2022-02-04 | [12 empty] | 2022-08-26 | Online |  |  | Y
ESMAEX-01151 | East Brewster | 2631 | 10 | Battery | 4-89B-577 | 2022-05-05 | 2022-05-26 | [28 empty] | 2022-06-02 | [12 empty] | 2022-09-09 | Online |  |  | Y
ESMAEX-02011 | East Brewster | 2631 | 18 | PV & Battery | 4-89B-577 | 2023-01-12 | 2023-02-28 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
2302867 | Barnstable | 2632 | 66.6 | PV | 4-88-88 | 2018-10-05 | 2018-10-05 | 0 |  | 0 | 2018-10-23 |  | -30988 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2377494 | Centerville | 2632 | 15.2 | PV | TBD | 2019-11-25 | 2019-12-20 |  |  |  | 2020-01-03 | [24 empty] | 2020-01-31 | [12 empty] | 2021-02-02 | Online
2402410 | Centerville | 2632 | 7.6 | PV | 4-82-508 | 2020-05-18 | 2020-06-03 |  |  |  | 2020-06-16 | [24 empty] | 2020-06-24 | [12 empty] | 2021-04-21 | Online
2403564 | Centerville | 2632 | 15.2 | PV | TBD | 2020-04-20 | 2020-06-18 |  |  |  | 2020-06-29 | [24 empty] | 2020-07-07 | [12 empty] | 2021-04-30 | Online
2373813 | Centerville | 2632 | 747 | PV & Battery | tbd | 2019-11-15 | 2019-11-20 |  |  |  | 2019-12-10 | [24 empty] | 2020-04-06
5447504 | Centerville | 2632 | 15.68 | Battery | TBD | 2021-03-29 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2021-04-22 | [12 empty] | 2022-03-17 | Online
ESMAEX-00711 | Centerville | 2632 | 18.25 | PV & Battery | 4-82-894 | 2022-01-05 | 2022-01-25 | [28 empty] | 2022-06-24 | [12 empty] | 2022-10-07 | Online |  |  | Y
ESMAEX-01727 | Centerville | 2632 | 20 | PV | 4-82-894 | 2022-10-26 | 2022-11-16 | [28 empty] | 2022-11-18 | [12 empty] | 2023-03-20 | Online |  |  | Y
2262808 | Chatham | 2633 | 86.4 | PV | 4-95B-940 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-31 | Online
2326896 | Chatham | 2633 | 117.12 | PV & Battery | 4-95A-95A | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-26 |  | -31078 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0 |  |  | 2020-07-01 | Online
2390124 | Chatham | 2633 | 18.7 | PV & Battery | TBD | 2020-02-28 | 2020-03-03 |  |  |  | 2020-03-19 | [24 empty] | 2020-04-14 | [12 empty] | 2020-07-16 | Online
2402094 | Chatham | 2633 | 22.32 | PV | TBD | 2020-05-26 | 2020-05-28 |  |  |  | 2020-06-11 | [24 empty] | 2020-07-06 | [12 empty] | 2020-09-10 | Online
2370503 | Chatham | 2633 | 133.3 | PV | TBD | 2019-11-08 | 2019-11-12 |  |  |  | 2019-11-27 | [24 empty] | 2020-01-21 | [12 empty] | 2021-09-20 | Online
4257166 | Chatham | 2633 | 86.6 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 |  |  |  | 2020-09-17 | [24 empty] | 2020-10-19
5813985 | Chatham | 2633 | 100.8 | PV & Battery | TBD | 2020-08-19 | 2021-05-14 |  |  |  | 2021-05-27 | [24 empty] | 2021-06-08
ESMAEX-00070 | Chatham | 2633 | 22 | PV & Battery | 4-95B-941 | 2021-04-22 | 2021-06-02 | [28 empty] | 2021-06-07 | [12 empty] | 2022-02-01 | Online |  |  | Y
ESMAEX-00138 | Chatham | 2633 | 10.15 | PV | 4-95B-941 | 2021-05-19 | 2021-06-07 | [28 empty] | 2021-06-16 | [12 empty] | 2021-07-27 | Online |  |  | Y
ESMAEX-00542 | Chatham | 2633 | 15.39 | PV | 4-95B-95B | 2021-10-26 | 2021-11-19 | [28 empty] | 2021-11-23 | [12 empty] | 2022-02-08 | Online |  |  | Y
ESMAEX-00586 | Chatham | 2633 | 12 | Battery | 4-95B-95B | 2021-11-15 | 2021-12-07 | [28 empty] | 2021-12-13 | [12 empty] | 2022-03-24 | Online |  |  | Y
ESMAEX-00820 | Chatham | 2633 | 19.14 | PV | 4-95A-606 | 2022-02-07 | 2022-04-07 | [28 empty] | 2022-04-18 | [12 empty] | 2022-07-05 | Online |  |  | Y
ESMAEX-01842 | Chatham | 2633 | 15.2 | PV & Battery | 4-95B-95B | 2022-11-22 | 2022-12-13 | [28 empty] | 2022-12-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02424 | Chatham | 2633 | 15.2 | PV | 4-95B-95B | 2023-04-27 | [43 empty] | In Queue |  |  | Y
4281091 | Aquinnah | 2635 | 54.2 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 |  |  |  | 2020-09-23 | [24 empty] | 2020-11-13
2311617 | Cotuit | 2635 | 17.93 | PV & Battery | 4-88-880 | 2018-11-26 | 2018-12-10 | 10 |  | 10 | 2018-12-10 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-15 | [7 empty] | 0 |  | 0 |  |  | 2019-10-21 | Online |  | Private
2314367 | Cotuit | 2635 | 15.2 | PV | 4-88-880 | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00929 | Cotuit | 2635 | 15.2 | PV & Battery | 4-88-88 | 2022-03-16 | 2022-05-23 | [28 empty] | 2022-05-31 | [12 empty] | 2023-01-03 | Online |  |  | Y
ESMAEX-01014 | Cotuit | 2635 | 15.2 | PV & Battery | 4-88-88 | 2022-04-05 | 2022-04-28 | [28 empty] | 2022-05-31 | [13 empty] | In Queue |  |  | Y
ESMAEX-01741 | Cotuit | 2635 | 15.2 | PV & Battery | 4-88-88 | 2022-10-31 | 2022-11-18 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
2376383 | Cotuit | 2635 | 200 | PV | TBD | 2019-12-12 | 2019-12-16 |  |  |  | 2019-12-31 | [37 empty] | 2022-06-27 | Online
2360391 | Marston Mills | 2635 | 210 | Fuel Cell | 4-88-485 | 2019-09-05 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-16 | [12 empty] | 2020-06-25 | Online
ESMAEX-00283 | Cummaquid | 2637 | 18 | PV | 4-92A-912 | 2021-08-03 | 2021-08-16 | [28 empty] | 2021-10-12 | [12 empty] | 2022-06-24 | Online |  |  | Y
ESMAEX-01616 | Cummaquid | 2637 | 9 | PV | 4-92A-912 | 2022-09-21 | 2022-10-25 | [28 empty] | 2023-01-17 | [13 empty] | In Queue |  |  | Y
2340718 | Dennisport | 2637 | 250 | PV | 4-92B-583 | 2019-04-25 | 2019-04-30 |  |  |  | 2019-05-21 | [24 empty] | 2019-08-26 | [12 empty] | 2020-11-12 | Online
2308172 | Dennis | 2638 | 17.4 | PV | 4-92B-92B | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -31014 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2019-04-30 | Online |  | Private
2395295 | Dennis | 2638 | 16.6 | PV & Battery | 4-90-90 | 2020-03-27 | 2020-04-15 |  |  |  | 2020-04-27 | [24 empty] | 2020-05-04 | [12 empty] | 2020-06-19 | Online
2155620 | Dennis | 2638 | 89.9 | PV | 4-92B-92B | 2016-05-13 | 2016-06-08 | 18 |  | 18 | 2016-06-30 |  | -30395 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-28 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  |  | In Queue
ESMAEX-00336 | Dennis | 2638 | 262.5 | Fuel Cell | 4-92B-92B | 2021-08-20 | 2021-09-08 | [28 empty] | 2021-12-20 | [12 empty] | 2023-01-05 | Online |  |  | N
ESMAEX-00946 | Dennis | 2638 | 17.6 | PV & Battery | 4-89A-549 | 2022-03-18 | 2022-04-07 | [28 empty] | 2022-04-18 | [12 empty] | 2022-07-12 | Online |  |  | Y
2357995 | South Dennis | 2638 | 100 | PV | TBD | 2019-08-01 | 2019-08-09 |  |  |  | 2019-09-06 | [24 empty] | 2019-11-08 | [12 empty] | 2020-09-09 | Online
2146378 | Dennisport | 2639 | 34.77 | PV | 4-85-592 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-01 | 2016-06-24 | [6 empty] | 0 |  | 0 |  |  | 2016-08-11 | Online
2132327 | Dennisport | 2639 | 65.7 | PV | 4-92B-583 | 2016-02-16 | 2016-02-18 | 2 |  | 2 | 2016-03-03 |  | -30310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-10-24 | [6 empty] | 0 |  | 0 |  |  | 2017-03-23 | Online |  | PRIVATE
2297501 | Dennisport | 2639 | 40 | PV | 4-92B-583 | 2018-08-03 | 2018-08-18 | 10 |  | 10 | 2018-09-19 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-05 | Online
4308158 | East Dennis | 2641 | 10 | PV & Battery | 4-89A-552 | 2020-09-15 | 2020-09-15 |  |  |  | 2020-10-05 | [24 empty] | 2021-01-11 | [13 empty] | Withdrawn
2334447 | East Dennis | 2641 | 36 | PV | 4-89A-552 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
2187463 | Eastham | 2642 | 23.04 | PV | 4-94B-956 | 2016-11-15 | 2016-11-17 | 2 |  | 2 | 2016-12-08 |  | -30510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-18 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online |  | PRIVATE
2262994 | Eastham | 2642 | 83 | PV | 4-94b-646 | 2018-01-13 | 2018-02-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
2262807 | Eastham | 2642 | 109.8 | PV | 4-94A-648 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
2372185 | Eastham | 2642 | 37.7 | PV | TBD | 2019-11-13 | 2019-11-20 |  |  |  | 2019-12-05 | [24 empty] | 2020-02-07 | [12 empty] | 2020-07-30 | Online
2384268 | Eastham | 2642 | 10 | PV & Battery | 4-94A-633 | 2019-11-22 | 2020-01-16 |  |  |  | 2020-02-04 | [24 empty] | 2020-03-02
2152613 | Eastham | 2642 | 15.4 | PV | 4-94A-648 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00073 | Eastham | 2642 | 18.41 | PV & Battery | 4-94A-648 | 2021-04-23 | 2021-06-04 | [28 empty] | 2021-06-07 | [12 empty] | 2021-11-02 | Online |  |  | Y
ESMAEX-00276 | Eastham | 2642 | 20 | PV & Battery | 4-94A-648 | 2021-07-30 | 2021-08-16 | [28 empty] | 2021-08-25 | [12 empty] | 2022-03-10 | Online |  |  | Y
ESMAEX-01020 | Eastham | 2642 | 4999.2 | Battery | 4-94B-647 | 2022-11-29 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-01290 | Eastham | 2642 | 3.8 | PV | 4-94A-94A | 2022-06-14 | 2022-08-23 | [28 empty] | 2022-09-06 | [12 empty] | 2023-03-28 | Online |  |  | Y
ESMAEX-01481 | Eastham | 2642 | 7.68 | Battery | 4-94A-648 | 2022-08-18 | 2022-08-18 | [28 empty] | 2022-09-06 | [13 empty] | In Queue |  |  | Y
2404297 | East Orleans | 2643 | 10 | PV & Battery | 4-95B-628 | 2020-05-28 | 2020-06-15 |  |  |  | 2020-06-29 | [24 empty] | 2020-07-13 | [12 empty] | 2020-12-22 | Online
5273198 | Orleans | 2643 | 17.4 | PV | TBD | 2021-03-08 | 2021-03-08 |  |  |  | 2021-03-31 | [24 empty] | 2021-04-30 | [12 empty] | 2021-06-16 | Online
2334165 | Forestdale | 2644 | 4990 | PV | 4-81B-443 | 2019-03-14 | 2019-03-26 | 8 |  | 8 | 2019-04-11 |  | -31110 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
4399952 | Forestdale | 2644 | 15.2 | PV | 4-81B-443 | 2020-09-18 | 2020-09-18 |  |  |  | 2020-09-18 | [24 empty] | 2020-10-09 | [13 empty] | Withdrawn
ESMAEX-00149 | Forestdale | 2644 | 20 | PV & Battery | 4-81B-443 | 2021-05-25 | 2021-06-11 | [28 empty] | 2021-08-05 | [12 empty] | 2022-08-22 | Online |  |  | Y
2291297 | Sandwich | 2644 | 15.2 | PV | 4-81B-443 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-10 |  | -30936 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
2330325 | Sandwich | 2644 | 5000 | PV & Battery | 4-81B-443 | 2019-02-22 | 2019-02-27 | 3 |  | 3 | 2019-03-19 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2351960 | Sandwich | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 |  |  |  | 2019-07-29
2352540 | Sandwich | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 |  |  |  | 2019-07-31
2352680 | Sandwich | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 |  |  |  | 2019-08-01
2349583 | Sandwich | 2644 | 849.5 | PV & Battery | 4-81B-443 | 2019-05-30 | 2019-06-26 |  |  |  | 2019-07-12
2373432 | Sandwich | 2644 | 2500 | PV & Battery | TBD | 2019-10-31 | [43 empty] | Withdrawn
ESMAEX-00305 | Sandwich | 2644 | 60.5 | PV | 4-81B-443 | 2021-08-12 | 2021-09-08 | [28 empty] | 2022-01-03 | [13 empty] | In Queue |  |  | Y
ESMAEX-00111 | East Harwich | 2645 | 20 | Battery | 4-95A-95A | 2021-05-10 | 2021-06-22 | [28 empty] | 2021-08-11 | [12 empty] | 2022-04-06 | Online |  |  | Y
ESMAEX-00737 | East Harwich | 2645 | 19.14 | PV | 4-95A-95A | 2022-01-19 | 2022-02-15 | [28 empty] | 2022-02-16 | [12 empty] | 2022-10-26 | Online |  |  | Y
ESMAEX-00874 | East Harwich | 2645 | 11 | PV & Battery | 4-95A-95A | 2022-03-03 | 2022-03-14 | [28 empty] | 2022-03-22 | [12 empty] | 2022-06-13 | Online |  |  | Y
2143454 | Harwich | 2645 | 16.77 | PV | 4-95A-599 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 |  | -30350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-24 | [6 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online |  | PRIVATE
2176727 | Harwich | 2645 | 30 | PV | 4-89A-556 | 2016-09-19 | 2016-09-21 | 2 |  | 2 | 2016-10-24 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-01 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online |  | PRIVATE
2314368 | Harwich | 2645 | 20 | PV | 4-92B-92B | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-05-21 | Online
2360563 | Harwich | 2645 | 262.5 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-15 | [12 empty] | 2020-06-25 | Online
2391216 | Harwich | 2645 | 23 | PV | TBD | 2020-03-06 | 2020-03-12 |  |  |  | 2020-03-27 | [24 empty] | 2020-05-04 | [12 empty] | 2020-07-28 | Online
2348529 | Harwich | 2645 | 166.5 | PV | 4-95A-95A | 2019-05-31 | 2019-06-26 |  |  |  | 2019-07-05 | [24 empty] | 2019-08-09 | [12 empty] | 2021-01-14 | Online
2291972 | Harwich | 2645 | 30 | PV | 4-92B-92B | 2018-08-02 | 2018-08-07 | 3 |  | 3 | 2018-08-15 | 2018-11-06 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2354467 | Harwich | 2645 | 3750 | PV | TBD | 2019-07-24 | 2019-08-01 |  |  |  | 2019-08-14
2359695 | Harwich | 2645 | 5000 | PV & Battery | TBD | 2019-08-26 | 2019-08-29 |  |  |  | 2019-09-19
2378433 | Harwich | 2645 | 3150 | PV & Battery | TBD | 2019-11-22 | 2019-11-22 |  |  |  | 2020-01-06
5233905 | Harwich | 2645 | 72 | Wind | TBD | 2020-01-22 | 2021-03-02 |  |  |  | 2021-03-30 | [24 empty] | 2021-05-05
2392746 | Harwich | 2645 | 4990 | PV & Battery | TBD | 2020-03-16 | 2020-03-20 |  |  |  | 2020-04-03
2398156 | Harwich | 2645 | 22.2 | PV | 4-95A-95A | 2020-04-27 | 2020-04-29 |  |  |  | 2020-05-18
4999717 | Harwich | 2645 | 213.2 | PV | TBD | 2021-01-12 | 2021-01-20 |  |  |  | 2021-02-17 | [24 empty] | 2021-05-19 | [12 empty] | 2023-04-11 | Online
5132388 | Harwich | 2645 | 20 | Battery | TBD | 2021-02-08 | 2021-02-17 |  |  |  | 2021-03-08 | [24 empty] | 2021-04-22 | [12 empty] | 2021-10-07 | Online
5256465 | Harwich | 2645 | 255 | PV | TBD | 2021-02-18 | 2021-03-05 |  |  |  | 2021-03-24 | [24 empty] | 2021-06-08
ESMAEX-00094 | Harwich | 2645 | 499 | PV & Battery | 4-95A-599 | 2021-05-03 | 2021-05-18 | [42 empty] | In Queue |  |  | Y
ESMAEX-00466 | Harwich | 2645 | 12.68 | PV & Battery | 4-89B-576 | 2021-10-04 | 2021-10-21 | [28 empty] | 2021-10-21 | [12 empty] | 2022-05-04 | Online |  |  | Y
ESMAEX-00217 | North Harwich | 2645 | 10 | Battery | 4-89A-553 | 2021-06-28 | 2021-07-15 | [28 empty] | 2021-07-20 | [12 empty] | 2022-08-09 | Online |  |  | Y
2365636 | North Harwich | 2645 | 23.2 | PV | 4-92B-92B | 2019-10-07 | 2019-10-10 |  |  |  | 2019-10-28 | [24 empty] | 2019-12-05 | [12 empty] | 2020-11-04 | Online
ESMAEX-00821 | Harwichport | 2646 | 15.2 | PV & Battery | 4-95A-95A | 2022-02-08 | 2022-02-28 | [28 empty] | 2022-02-28 | [12 empty] | 2022-11-03 | Online |  |  | Y
ESMAEX-01388 | Harwichport | 2646 | 10 | Battery | 4-85-592 | 2022-07-19 | 2022-08-01 | [28 empty] | 2022-08-10 | [12 empty] | 2022-09-26 | Online |  |  | Y
2279638 | Barnstable | 2648 | 4998 | PV & Battery | 4-88-478 | 2018-05-16 | 2018-05-22 | 4 |  | 4 | 2018-06-04 | 2018-11-08 | 113 |  | 113 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 | [6 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online |  | Private
2298568 | Barnstable | 2648 | 4990 | PV | 4-88-453 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-27 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
ESMAEX-00172 | Marston Mills | 2648 | 20.67 | Battery | 4-88-88 | 2021-06-08 | 2021-06-24 | [28 empty] | 2021-09-09 | [12 empty] | 2021-12-29 | Online |  |  | Y
ESMAEX-00284 | Marston Mills | 2648 | 6 | PV | 4-87A-87A | 2021-08-03 | 2021-08-12 | [28 empty] | 2021-10-12 | [12 empty] | 2022-02-17 | Online |  |  | Y
ESMAEX-02419 | Marston Mills | 2648 | 19.8 | PV | 4-87A-87A | 2023-04-26 | [43 empty] | In Queue |  |  | Y
5113167 | Marston Mills | 2648 | 500 | PV | TBD | 2021-01-06 | 2021-02-10 |  |  |  | 2021-03-12 | [24 empty] | 2022-08-03
5113061 | Marston Mills | 2648 | 433 | PV | TBD | 2021-01-06 | 2021-02-10 |  |  |  | 2021-03-12
4971708 | Marston Mills | 2648 | 11.6 | Battery | TBD | 2021-01-21 | 2021-01-27 |  |  |  | 2021-02-11 | [24 empty] | 2021-04-30 | [13 empty] | Withdrawn
5355181 | Marston Mills | 2648 | 19.84 | Battery | TBD | 2021-03-17 | 2021-03-17 |  |  |  | 2021-04-02 | [24 empty] | 2021-04-21 | [12 empty] | 2022-07-18 | Online
5447070 | Marston Mills | 2648 | 15.2 | PV | TBD | 2021-03-17 | 2021-03-29 |  |  |  | 2021-04-13 | [24 empty] | 2021-04-22
2165396 | Marston Mills | 2648 | 19.6 | PV | 4-88-485 | 2016-07-26 | 2016-08-01 | 4 |  | 4 | 2016-08-24 |  | -30434 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-17 | Online |  | PRIVATE
2381861 | Marston Mills | 2648 | 40 | PV | TBD | 2019-12-19 | 2020-01-02 |  |  |  | 2020-01-16 | [24 empty] | 2020-03-02 | [12 empty] | 2020-12-09 | Online
2395414 | Marston Mills | 2648 | 16.38 | PV | TBD | 2020-04-01 | 2020-04-09 |  |  |  | 2020-04-27 | [24 empty] | 2020-05-04 | [12 empty] | 2020-12-09 | Online
2123807 | Marston Mills | 2648 | 19.3 | PV | 4-88-478 | 2012-01-11 | 2016-01-15 | 1047 |  | 1047 | 2016-01-19 |  | -30278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-10 | 2016-03-15 | [6 empty] | 0 |  | 0
2158112 | Marston Mills | 2648 | 50.4 | PV | 4-88-478 | 2016-05-24 | 2016-06-28 | 25 |  | 25 | 2016-07-14 |  | -30405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue |  | PRIVATE
2145692 | Mashpee | 2649 | 58.9 | PV | 4-88-453 | 2016-02-10 | 2016-04-27 | 55 |  | 55 | 2016-05-11 |  | -30359 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2016-12-05 | Online |  | PRIVATE
2138475 | Mashpee | 2649 | 53.8 | PV | 4-88-455 | 2016-03-28 | 2016-03-30 | 2 |  | 2 | 2016-04-06 |  | -30334 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2019-01-10 | Online
2332061 | Mashpee | 2649 | 254.29 | PV | 4-88-483 | 2019-03-13 | 2019-03-15 | 2 |  | 2 | 2019-03-29 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-03 | Online
2360533 | Mashpee | 2649 | 210 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 |  |  |  | 2019-09-25 | [24 empty] | 2020-01-15 | [12 empty] | 2020-06-25 | Online
2402767 | Mashpee | 2649 | 10 | PV & Battery | 4-452-452 | 2020-05-15 | 2020-06-03 |  |  |  | 2020-06-19 | [24 empty] | 2020-07-07 | [12 empty] | 2020-08-05 | Online
2187699 | Mashpee | 2649 | 496 | PV | 4-88-455 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30511 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
2387970 | Mashpee | 2649 | 499.73 | PV | TBD | 2020-02-10 | 2020-02-13 |  |  |  | 2020-03-04 | [24 empty] | 2020-06-17
2393455 | Mashpee | 2649 | 5000 | PV & Battery | TBD | 2020-02-20 | 2020-03-27 |  |  |  | 2020-04-14
2400260 | Mashpee | 2649 | 1490 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 |  |  |  | 2020-06-02
2400979 | Mashpee | 2649 | 2075 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 |  |  |  | 2020-06-04
2401235 | Mashpee | 2649 | 730 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 |  |  |  | 2020-06-08
2410254 | Mashpee | 2649 | 499 | PV & Battery | TBD | 2020-07-27 | 2020-08-03 |  |  |  | 2020-08-18 | [24 empty] | 2021-01-28
2411961 | Mashpee | 2649 | 750 | PV & Battery | TBD | 2020-07-27 | 2020-08-06 |  |  |  | 2020-08-31
2409915 | Mashpee | 2649 | 245 | PV & Battery | TBD | 2020-08-07 | [29 empty] | 2021-02-05
4632820 | Mashpee | 2649 | 13.8 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 |  |  |  | 2020-12-29 | [37 empty] | 2023-01-23 | Online
4887205 | Mashpee | 2649 | 52.78 | PV | TBD | 2021-01-12 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-03-10 | [12 empty] | 2021-05-27 | Online
4962795 | Mashpee | 2649 | 495 | PV | TBD | 2021-01-21 | 2021-01-26 |  |  |  | 2021-02-11 | [24 empty] | 2021-06-17
2140032 | Mashpee | 2649 | 21.9 | PV | 4-88-483 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5392364 | Mashpee | 2649 | 17.6 | PV & Battery | TBD | 2021-03-12 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-04-28
ESMAEX-00273 | Mashpee | 2649 | 80 | PV | 4-452-452 | 2021-07-28 | 2021-08-13 | [28 empty] | 2021-09-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-00565 | Mashpee | 2649 | 85.76 | PV | 4-71-455 | 2021-11-04 | 2021-11-23 | [28 empty] | 2021-12-30 | [12 empty] | 2022-06-30 | Online |  |  | Y
ESMAEX-01363 | Mashpee | 2649 | 6 | PV | 4-77A-77A | 2022-07-11 | 2022-07-26 | [28 empty] | 2022-08-24 | [12 empty] | 2023-03-20 | Online |  |  | Y
ESMAEX-01835 | Mashpee | 2649 | 17.58 | PV | 4-452-452 | 2022-11-21 | 2022-12-13 | [28 empty] | 2022-12-15 | [12 empty] | 2023-04-04 | Online |  |  | Y
4479289 | North Falmouth | 2649 | 25.81 | PV & Battery | TBD | 2020-10-15 | 2020-10-19 |  |  |  | 2020-11-13 | [24 empty] | 2020-11-25 | [12 empty] | 2021-04-09 | Online
2156004 | Chatham | 2650 | 21.44 | PV | 4-95B-612 | 2016-06-10 | 2016-06-13 | 1 |  | 1 | 2016-07-05 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-13 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online |  | PRIVATE
2354636 | Chatham | 2650 | 24.64 | PV | TBD | 2019-07-16 | 2019-07-22 |  |  |  | 2019-08-14 | [24 empty] | 2019-09-25 | [12 empty] | 2020-02-06 | Online
5174898 | North Chatham | 2650 | 17.6 | battery | TBD | 2021-02-23 | 2021-02-25 |  |  |  | 2021-03-16 | [24 empty] | 2021-05-27 | [12 empty] | 2021-10-15 | Online
ESMAEX-02137 | North Chatham | 2650 | 15.2 | PV & Battery | 4-95B-95B | 2023-02-07 | 2023-03-07 | [28 empty] | 2023-03-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-01694 | North Eastham | 2651 | 16 | PV & Battery | 4-94B-646 | 2022-10-19 | 2022-11-04 | [28 empty] | 2022-11-07 | [12 empty] | 2023-03-23 | Online |  |  | Y
ESMAEX-01951 | North Eastham | 2651 | 15.2 | PV & Battery | 4-94B-647 | 2022-12-29 | [43 empty] | In Queue |  |  | Y
ESMAEX-00507 | North Truro | 2652 | 8 | PV | 4-96-96 | 2021-10-18 | 2021-11-09 | [28 empty] | 2021-12-21 | [12 empty] | 2022-03-07 | Online |  |  | Y
ESMAEX-00585 | North Truro | 2652 | 15.2 | PV & Battery | 4-96-96 | 2021-11-15 | 2022-01-20 | [28 empty] | 2022-02-17 | [12 empty] | 2023-02-02 | Online |  |  | Y
ESMAEX-00740 | North Truro | 2652 | 16.56 | PV | TBD | 2022-01-19 | 2022-02-15 | [28 empty] | 2022-02-25 | [12 empty] | 2022-06-09 | Online |  |  | Y
ESMAEX-00908 | North Truro | 2652 | 24.94 | PV & Battery | 4-96-96 | 2022-03-11 | 2022-04-19 | [28 empty] | 2022-04-21 | [12 empty] | 2022-08-26 | Online |  |  | Y
ESMAEX-00919 | North Truro | 2652 | 28.71 | PV | 4-96-96 | 2022-03-15 | 2022-04-05 | [28 empty] | 2022-04-18 | [12 empty] | 2022-11-15 | Online |  |  | Y
ESMAEX-01332 | North Truro | 2652 | 18.9 | PV | 4-96-96 | 2022-06-29 | 2022-07-21 | [28 empty] | 2022-08-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-01378 | North Truro | 2652 | 10 | Battery | 4-96-96 | 2022-07-15 | 2022-08-02 | [28 empty] | 2022-08-10 | [12 empty] | 2022-10-14 | Online |  |  | Y
ESMAEX-01485 | North Truro | 2652 | 21.6 | PV | 4-96-96 | 2022-08-18 | 2022-09-27 | [28 empty] | 2022-10-21 | [12 empty] | 2023-01-10 | Online |  |  | Y
ESMAEX-01536 | North Truro | 2652 | 17.6 | PV | 4-96-96 | 2022-09-02 | 2022-10-25 | [28 empty] | 2022-10-28 | [13 empty] | In Queue |  |  | Y
ESMAEX-01847 | North Truro | 2652 | 10 | Battery | 4-96-96 | 2022-11-23 | 2022-12-19 | [28 empty] | 2023-01-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01997 | North Truro | 2652 | 10 | Battery | 4-96-96 | 2023-01-10 | 2023-02-02 | [28 empty] | 2023-02-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-02021 | North Truro | 2652 | 15 | Battery | 4-96-96 | 2023-01-13 | 2023-02-01 | [28 empty] | 2023-02-07 | [12 empty] | 2023-04-13 | Online |  |  | Y
ESMAEX-02223 | North Truro | 2652 | 10.25 | PV & Battery | 4-96-96 | 2023-03-02 | 2023-03-23 | [28 empty] | 2023-03-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-02287 | North Truro | 2652 | 15.2 | PV | 4-96-96 | 2023-03-20 | 2023-04-06 | [28 empty] | 2023-04-12 | [13 empty] | In Queue |  |  | Y
4280601 | Truro | 2652 | 35 | PV | TBD | 2020-09-03 | 2020-09-03 |  |  |  | 2020-09-03 | [24 empty] | 2020-11-13 | [12 empty] | 2021-01-28 | Online
2405858 | Truro | 2652 | 4107 | PV & Battery | TBD | 2020-06-23 | 2020-06-23 |  |  |  | 2020-07-13
2172699 | Orleans | 2653 | 33.5 | PV | 4-83-952 | 2016-09-06 | 2016-09-14 | 6 |  | 6 | 2016-10-30 |  | -30481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | [7 empty] | 0 |  | 0 |  |  | 2017-05-18 | Online |  | PRIVATE
2272019 | Orleans | 2653 | 23.1 | PV | 4-83-952 | 2018-03-26 | 2018-03-29 | 3 |  | 3 | 2018-04-17 |  | -30853 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-06-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-20 | Online
2227358 | Orleans | 2653 | 58.6 | PV | 4-83-952 | 2017-06-05 | 2017-06-15 | 8 |  | 8 | 2017-07-27 |  | -30669 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18 | Online
2366434 | Orleans | 2653 | 20 | PV | 4-89B-89B | 2019-09-20 | 2019-10-09 |  |  |  | 2019-10-31 | [24 empty] | 2019-11-25 | [12 empty] | 2020-04-08 | Online
2373810 | Orleans | 2653 | 89.39 | PV | TBD | 2019-05-28 | 2019-06-20 |  |  |  | 2019-07-05 | [24 empty] | 2019-10-07 | [12 empty] | 2020-07-08 | Online
2369981 | Orleans | 2653 | 133.7 | PV | 4-83-952 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-04-15 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-04 | Online
4284906 | Orleans | 2653 | 51.62 | PV | TBD | 2020-08-27 | 2020-09-01 |  |  |  | 2020-09-29 | [24 empty] | 2020-11-13 | [12 empty] | 2021-03-01 | Online
2358998 | Orleans | 2653 | 86 | PV | 4-83-951 | 2019-08-20 | 2019-08-27 |  |  |  | 2019-09-13 | [24 empty] | 2019-10-31
2401009 | Orleans | 2653 | 200 | PV | TBD | 2020-04-30 | 2020-05-18 |  |  |  | 2020-06-04 | [24 empty] | 2020-07-21
2400943 | Orleans | 2653 | 499 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 |  |  |  | 2020-06-04 | [24 empty] | 2021-09-20 | [12 empty] | 2023-01-31 | Online
5174743 | Orleans | 2653 | 18.32 | PV & Battery | TBD | 2021-02-18 | 2021-02-23 |  |  |  | 2021-03-16 | [24 empty] | 2021-04-28
ESMAEX-00303 | Orleans | 2653 | 15.2 | PV & Battery | 4-94A-94A | 2021-08-12 | 2021-09-09 | [28 empty] | 2021-10-20 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-00840 | Orleans | 2653 | 10 | Battery | 4-94A-94A | 2022-02-17 | 2022-03-10 | [28 empty] | 2022-03-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-00851 | Orleans | 2653 | 15.2 | PV & Battery | 4-628-628 | 2022-02-22 | 2022-03-15 | [28 empty] | 2022-03-22 | [12 empty] | 2023-03-16 | Online |  |  | Y
ESMAEX-01147 | Orleans | 2653 | 10 | Battery | TBD | 2022-05-05 | 2022-05-26 | [28 empty] | 2022-06-01 | [12 empty] | 2022-10-05 | Online |  |  | Y
ESMAEX-01596 | Orleans | 2653 | 15.2 | PV & Battery | 4-628-628 | 2022-09-16 | 2022-10-11 | [28 empty] | 2022-10-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-01657 | Orleans | 2653 | 29.76 | PV & Battery | 4-628-628 | 2022-10-03 | 2022-10-19 | [28 empty] | 2022-10-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01973 | Orleans | 2653 | 80 | PV | 4-89B-89B | 2023-01-05 | 2023-02-01 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
2400107 | Sandwich | 2653 | 150 | PV | TBD | 2020-05-08 | 2020-05-18 |  |  |  | 2020-06-02 | [24 empty] | 2020-06-24 | [12 empty] | 2021-03-10 | Online
1253 | Osterville | 2655 | 52 | PV | 4-80A-490 | 2009-04-21 | 2009-04-29 | 6 | 4 | 2 | 2009-04-30 | 2009-05-27 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-05 |  | 2009-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2008-07-30 |  | 2009-07-30 | Online |  | Gov't | N
2216608 | Osterville | 2655 | 18.91 | PV | 4-80A-490 | 2017-04-19 | 2017-04-26 | 5 |  | 5 | 2017-05-22 |  | -30623 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2017-09-12 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03 | Online
2292182 | Osterville | 2655 | 23.04 | PV | 4-80A-892 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2358595 | Osterville | 2655 | 240 | PV | 4-88-491 | 2019-08-14 | 2019-08-27 |  |  |  | 2019-09-11 | [38 empty] | Withdrawn
2389165 | Osterville | 2655 | 23.3 | PV & Battery | 4-80A-490 | 2019-11-04 | 2020-02-21 |  |  |  | 2020-03-09 | [24 empty] | 2020-07-06 | [13 empty] | Withdrawn
ESMAEX-00494 | Osterville | 2655 | 28 | PV & Battery | 4-80A-488 | 2021-10-13 | 2021-11-04 | [28 empty] | 2021-12-23 | [12 empty] | 2022-05-02 | Online |  |  | Y
ESMAEX-01248 | Osterville | 2655 | 18.59 | PV | 4-88-88 | 2022-06-02 | 2022-07-01 | [28 empty] | 2022-08-18 | [12 empty] | 2023-03-22 | Online |  |  | Y
2313435 | Truro | 2655 | 4998 | PV & Battery | 4-96-674 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-19 |  | -31029 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2262605 | Provincetown | 2657 | 276.6 | PV | 4-96-675 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
2397610 | Provincetown | 2657 | 54 | PV | TBD | 2020-04-06 | 2020-04-23 |  |  |  | 2020-05-14 | [24 empty] | 2020-06-09 | [12 empty] | 2020-11-23 | Online
2352065 | Provincetown | 2657 | 325 | PV | TBD | 2019-07-12 |  |  |  |  | 2019-07-31 | [24 empty] | 2019-08-29 | [12 empty] | 2021-01-19 | Online
2384542 | Provincetown | 2657 | 70 | PV | 4-96-675 | 2020-01-15 | 2020-01-22 |  |  |  | 2020-02-06 | [24 empty] | 2020-03-02 | [12 empty] | 2021-03-09 | Online
2350711 | Provincetown | 2657 | 53.76 | PV | TBD | 2019-06-26 | 2019-07-12 |  |  |  | 2019-07-19 | [24 empty] | 2019-08-26 | [13 empty] | Withdrawn
2357992 | Provincetown | 2657 | 30.39 | PV | 4-96-974 | 2019-08-06 | 2019-08-08 |  |  |  | 2019-09-05 | [24 empty] | 2019-09-20
2386275 | Provincetown | 2657 | 28.8 | PV | TBD | 2020-01-30 | 2020-02-03 |  |  |  | 2020-02-19 | [24 empty] | 2020-03-02
2395067 | Provincetown | 2657 | 495.8 | PV | TBD | 2020-04-08 | 2020-04-08 |  |  |  | 2020-04-23 | [38 empty] | Withdrawn
ESMAEX-01414 | Provincetown | 2657 | 12.005 | PV & Battery | 4-675-675 | 2022-07-27 | 2022-08-10 | [28 empty] | 2022-08-15 | [12 empty] | 2023-02-17 | Online |  |  | Y
ESMAEX-01783 | Provincetown | 2657 | 10 | PV & Battery | 4-675-675 | 2022-11-08 | 2022-12-05 | [28 empty] | 2022-12-08 | [13 empty] | In Queue |  |  | Y
ESMAEX-01833 | Provincetown | 2657 | 15.2 | PV & Battery | 4-675-675 | 2022-11-18 | 2022-12-13 | [28 empty] | 2022-12-13 | [13 empty] | In Queue |  |  | Y
2287709 | Vineyard Haven | 2658 | 19.78 | PV | 4-91-228 | 2017-11-03 | 2017-11-03 | 0 |  | 0 | 2017-11-03 | 2018-07-20 | 183 |  | 183 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | [7 empty] | 0 |  | 0 |  |  | 2018-10-10 | Online |  | Private
2243750 | Vineyard Haven | 2658 | 22 | PV | 4-91-228 | 2017-10-16 | 2017-10-18 | 2 |  | 2 | 2017-11-03 |  | -30738 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | 2018-08-09 | [6 empty] | 0 |  | 0 |  |  |  | In Queue
2259526 | Vineyard Haven | 2658 | 20 | PV | 4-91-228 | 2017-10-16 | 2018-01-04 | 56 |  | 56 | 2018-01-25 |  | -30795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
4307156 | West Tisbury | 2658 | 48 | PV | TBD | 2020-09-04 | 2020-09-14 |  |  |  | 2020-10-05 | [24 empty] | 2020-10-15 | [12 empty] | 2021-06-30 | Online
2214785 | Chatham | 2659 | 47 | PV | 4-95A-95A | 2017-04-11 | 2017-04-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online
2374770 | Chatham | 2659 | 25 | PV & Battery | 4-95A-606 | 2019-11-15 | 2019-12-02 |  |  |  | 2019-12-17 | [24 empty] | 2020-01-21 | [12 empty] | 2020-12-07 | Online
2299602 | Chatham | 2659 | 78.2 | PV | 4-95A-95A | 2018-09-12 | 2018-09-19 | 5 |  | 5 | 2018-10-03 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [5 empty] | Private
2354558 | Chatham | 2659 | 1560 | PV | TBD | 2019-06-24
2355012 | Chatham | 2659 | 2500 | PV & Battery | TBD | 2019-07-25 | 2019-07-25 |  |  |  | 2019-08-16 | [24 empty] | 2020-05-29
ESMAEX-00415 | Chatham | 2659 | 180 | PV | 4-95A-95A | 2021-09-16 | 2022-01-19 | [28 empty] | 2022-02-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-00522 | South Chatham | 2659 | 10 | Battery | 4-95A-606 | 2021-10-21 | 2021-11-15 | [28 empty] | 2021-11-22 | [12 empty] | 2022-10-04 | Online |  |  | Y
ESMAEX-00602 | South Chatham | 2659 | 16 | PV | TBD | 2021-11-17 | 2021-12-30 | [28 empty] | 2022-01-27 | [12 empty] | 2023-03-20 | Online |  |  | Y
2392011 | South Chatham | 2659 | 24.92 | PV & Battery | 4-95A-606 | 2020-03-09 | 2020-03-12 |  |  |  | 2020-04-01 | [24 empty] | 2020-05-14
2136807 | Dennis | 2660 | 21.75 | PV | 4-92B-92B | 2016-03-01 | 2016-03-02 | 1 |  | 1 | 2016-03-25 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-19 | 2016-06-22 | [6 empty] | 0 |  | 0
2404237 | Dennis | 2660 | 3176 | PV | TBD | 2020-04-01 | 2020-06-11 |  |  |  | 2020-06-29
2383634 | South Dennis | 2660 | 37.6 | PV | TBD | 2020-01-06 | 2020-01-13 |  |  |  | 2020-01-31 | [24 empty] | 2020-02-12 | [12 empty] | 2020-05-29 | Online
5758561 | South Dennis | 2660 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-05-04 |  |  |  | 2021-05-19 | [24 empty] | 2021-07-01
2259134 | South Dennis | 2660 | 149.5 | PV | 4-92B-92B | 2017-10-23 | 2017-12-28 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-03-12 | Online
2324745 | South Dennis | 2660 | 133.3 | PV | 4-92B-92B | 2019-02-01 | 2019-02-01 | 0 |  | 0 | 2019-02-11 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
2333807 | South Dennis | 2660 | 699.7 | PV | 4-92B-92B | 2019-03-04 | 2019-03-25 | 15 |  | 15 | 2019-04-09 |  | -31108 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
2335447 | South Dennis | 2660 | 133.2 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
2323237 | South Dennis | 2660 | 4951 | PV | tbd | 2019-01-24 | 2019-01-28 | 2 |  | 2 | 2019-01-31 |  | -31060 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
2335454 | South Dennis | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2335459 | South Dennis | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2378744 | South Dennis | 2660 | 30.72 | PV | TBD | 2019-11-20 | 2019-11-26 |  |  |  | 2020-01-06 | [24 empty] | 2020-06-30 | [13 empty] | Withdrawn
2369488 | South Yarmouth | 2661 | 17.23 | PV | 4-92A-562 | 2019-10-16 | 2019-11-04 |  |  |  | 2019-11-20 | [24 empty] | 2019-12-03 | [12 empty] | 2020-02-21 | Online
ESMAEX-02239 | South Orleans | 2662 | 17.4 | PV | 4-628-628 | 2023-03-07 | 2023-04-20 | [28 empty] | 2023-04-27 | [13 empty] | In Queue |  |  | Y
ESMAEX-01608 | South Wellfleet | 2663 | 12.6 | PV & Battery | 4-94B-653 | 2022-09-20 | 2022-10-11 | [28 empty] | 2022-10-20 | [13 empty] | In Queue |  |  | Y
2271202 | Welfleet | 2663 | 48.56 | PV | 4-96-960 | 2018-02-26 | 2018-03-23 | 19 |  | 19 | 2018-04-12 |  | -30850 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-25 | [6 empty] | 0 |  | 0
5298773 | Welfleet | 2663 | 18.16 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 |  |  |  | 2021-04-02 | [24 empty] | 2021-04-28 | [12 empty] | 2021-12-01 | Online
ESMAEX-01089 | South Yarmouth | 2664 | 18.56 | PV | 4-92A-562 | 2022-04-18 | 2022-05-03 | [28 empty] | 2022-05-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01173 | South Yarmouth | 2664 | 79.8 | PV | 4-92A-563 | 2022-05-11 | 2022-06-03 | [28 empty] | 2022-06-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-01232 | South Yarmouth | 2664 | 20.2 | PV & Battery | 4-92A-560 | 2022-05-27 | 2022-06-17 | [28 empty] | 2022-06-27 | [12 empty] | 2023-04-18 | Online |  |  | Y
2355147 | South Yarmouth | 2664 | 264 | PV | TBD | 2019-07-22 | 2019-08-02 |  |  |  | 2019-08-19 | [24 empty] | 2019-09-11 | [12 empty] | 2020-11-04 | Online
2356024 | South Yarmouth | 2664 | 100 | PV | TBD | 2019-08-07 | 2019-08-07 |  |  |  | 2019-08-23 | [37 empty] | 2021-03-10 | Online
2330447 | South Yarmouth | 2664 | 233.64 | PV | 4-90-90 | 2019-02-28 | 2019-03-06 | 4 |  | 4 | 2019-03-19 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2348526 | South Yarmouth | 2664 | 1560 | PV & Battery | 4-92A-563 | 2019-05-30 | 2019-06-26 |  |  |  | 2019-07-05
2353833 | South Yarmouth | 2664 | 756 | PV | TBD | 2019-06-24 | 2019-07-19 |  |  |  | 2019-08-08
2384954 | South Yarmouth | 2664 | 437.5 | PV | TBD | 2019-12-19 | 2020-01-06 |  |  |  | 2020-02-07 | [24 empty] | 2020-06-23 | [12 empty] | 2022-11-08 | Online
2241680 | South Yarmouth | 2664 | 124.47 | PV | 4-92A-562 | 2017-09-27 | 2017-10-03 | 4 |  | 4 | 2017-10-10 |  | -30720 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
2345649 | South Yarmouth | 2664 | 249.9 | PV | TBD | 2019-05-29 | 2019-06-05 |  |  |  | 2019-06-19 | [24 empty] | 2019-07-19 | [12 empty] | 2020-04-21 | Online
2351939 | South Yarmouth | 2664 | 92.16 | PV | TBD | 2019-07-12 | 2019-07-15 |  |  |  | 2019-07-29 | [24 empty] | 2019-08-27 | [12 empty] | 2020-10-16 | Online
2264227 | South Yarmouth | 2664 | 33.6 | PV | 4-92A-562 | 2018-02-07 | 2018-02-12 | 3 |  | 3 | 2018-02-23 |  | -30816 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-21 | [6 empty] | 0 |  | 0
2372266 | South Yarmouth | 2664 | 160 | PV & Battery | TBD | 2019-06-14 | 2019-07-02 |  |  |  | 2019-07-19 | [24 empty] | 2020-04-28
ESMAEX-00060 | South Yarmouth | 2664 | 250 | Battery | TBD | 2021-04-19 | 2021-05-04 | [28 empty] | 2022-03-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00778 | South Yarmouth | 2664 | 4999.2 | Battery | 4-64-558 | 2022-03-09 | [43 empty] | In Queue |  |  | Y
ESMAEX-01140 | South Yarmouth | 2664 | 200 | PV & Battery | 4-92A-562 | 2022-05-03 | 2022-05-31 | [28 empty] | 2022-08-23 | [13 empty] | In Queue |  |  | Y
2264855 | Yarmouth | 2664 | 52.2 | PV | 4-92a-562 | 2018-01-24 | 2018-02-15 | 16 |  | 16 | 2018-02-28 |  | -30819 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
2283640 | Yarmouth | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | 20 |  | 20 | 2018-06-26 |  | -30903 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
2178449 | Yarmouth | 2664 | 127.8 | PV | 4-92a-562 | 2016-09-26 | 2016-10-03 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5243395 | Yarmouth | 2664 | 5325 | PV & Battery | TBD | 2021-02-17 | 2021-03-02 |  |  |  | 2021-03-24
2117763 | Yarmouth | 2664 | 19.3 | PV | 4-90-90 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2262127 | Osterville | 2665 | 36 | PV | 4-80A-892 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-08 |  | -30805 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-08-08 | Online
ESMAEX-02384 | South Truro | 2666 | 16.8 | PV | 4-96-96 | 2023-04-17 | 2023-04-25 | [42 empty] | In Queue |  |  | Y
2172198 | Truro | 2666 | 18.9 | PV | 4-96-674 | 2016-09-07 | 2016-09-09 | 2 |  | 2 | 2016-09-29 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online |  | PRIVATE
2262805 | Truro | 2666 | 80 | PV | 4-96-674 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
4311559 | Truro | 2666 | 15.2 | PV | TBD | 2020-08-07 | 2020-09-03 |  |  |  | 2020-10-01 | [24 empty] | 2020-11-13 | [12 empty] | 2021-04-09 | Online
4658780 | Truro | 2666 | 249.8 | PV | TBD | 2020-11-24 | 2020-11-24 |  |  |  | 2021-01-05 | [24 empty] | 2021-05-26
4621310 | Truro | 2666 | 62.93 | PV | TBD | 2020-12-01 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-02-01 | [12 empty] | 2022-01-18 | Online
4963253 | Truro | 2666 | 17.68 | battery | TBD | 2021-01-21 | 2021-01-27 |  |  |  | 2021-02-11 | [24 empty] | 2021-04-09 | [12 empty] | 2022-02-01 | Online
ESMAEX-00190 | Truro | 2666 | 50 | PV & Battery | 4-96-96 | 2021-06-16 | 2021-07-06 | [28 empty] | 2021-08-26 | [12 empty] | 2022-06-22 | Online |  |  | Y
ESMAEX-01579 | Truro | 2666 | 17.6 | PV & Battery | 4-96-96 | 2022-09-13 | 2022-10-03 | [28 empty] | 2022-10-21 | [13 empty] | In Queue |  |  | Y
4304369 | Welfleet | 2667 | 28.7 | PV & Battery | TBD | 2020-08-04 | 2020-09-08 |  |  |  | 2020-09-29 | [24 empty] | 2020-10-19 | [12 empty] | 2021-02-23 | Online
2407474 | Welfleet | 2667 | 2000 | PV & Battery | TBD | 2020-07-01 | 2020-07-02 |  |  |  | 2020-07-21 | [24 empty] | 2021-05-13
2237326 | Welfleet | 2667 | 17.92 | PV | 4-96-960 | 2017-09-07 | 2017-09-14 | 5 |  | 5 | 2017-09-29 | 2017-10-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-10-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
2281067 | Welfleet | 2667 | 700 | PV | 4-96-677 | 2018-05-18 | 2018-05-23 | 3 |  | 3 | 2018-06-08 |  | -30891 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online
4469232 | Welfleet | 2667 | 23.2 | PV | 4-96-677 | 2020-09-18 | 2020-10-08 |  |  |  | 2020-11-12 | [24 empty] | 2020-12-30 | [12 empty] | 2021-06-04 | Online
ESMAEX-00505 | Welfleet | 2667 | 7.14 | PV | 4-94B-656 | 2021-10-15 | 2021-11-04 | [28 empty] | 2021-11-04 | [12 empty] | 2022-04-13 | Online |  |  | Y
ESMAEX-00624 | Welfleet | 2667 | 23.78 | PV | 4-94B-653 | 2021-11-27 | 2021-12-30 | [28 empty] | 2022-07-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-00664 | Welfleet | 2667 | 8 | Battery | 4-94B-656 | 2021-12-15 | 2022-01-14 | [28 empty] | 2022-02-04 | [12 empty] | 2022-05-23 | Online |  |  | Y
ESMAEX-01100 | Welfleet | 2667 | 21.83 | PV | 4-96-96 | 2022-04-22 | 2022-05-12 | [28 empty] | 2022-05-31 | [12 empty] | 2022-07-21 | Online |  |  | Y
ESMAEX-01591 | Welfleet | 2667 | 18.816 | PV & Battery | 4-94B-94B | 2022-09-15 | 2022-10-03 | [28 empty] | 2022-10-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-01729 | Welfleet | 2667 | 18.9 | PV & Battery | 4-96-96 | 2022-10-26 | 2022-11-16 | [28 empty] | 2022-11-21 | [13 empty] | In Queue |  |  | Y
ESMAEX-02389 | Welfleet | 2667 | 6.4 | Battery | 4-94B-656 | 2023-04-19 | [43 empty] | In Queue |  |  | Y
2243747 | Barnstable | 2668 | 33.6 | PV | 4-82-516 | 2017-10-10 | 2017-10-18 | 6 |  | 6 | 2017-11-03 |  | -30738 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-09-17 | Online
2282058 | Barnstable | 2668 | 44.5 | PV | 4-87B-473 | 2018-05-15 | 2018-06-01 | 13 |  | 13 | 2018-06-15 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-03 | 2018-08-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00730 | West Barnstable | 2668 | 15.36 | PV | 4-87B-87B | 2022-01-16 | 2022-02-10 | [28 empty] | 2022-03-15 | [12 empty] | 2022-05-12 | Online |  |  | Y
5058535 | West Barnstable | 2668 | 20.88 | PV | TBD | 2021-02-05 | 2021-02-05 |  |  |  | 2021-02-24 | [24 empty] | 2021-03-25 | [12 empty] | 2021-06-21 | Online
2383632 | Dennis | 2670 | 20 | PV & Battery | 4-92B-571 | 2020-01-04 | 2020-01-13 |  |  |  | 2020-01-31 | [24 empty] | 2020-02-13 | [12 empty] | 2020-05-21 | Online
ESMAEX-00971 | West Dennis | 2670 | 15.2 | PV | TBD | 2022-03-27 | 2022-04-28 | [28 empty] | 2022-05-04 | [12 empty] | 2023-03-06 | Online |  |  | Y
ESMAEX-00986 | West Dennis | 2670 | 3.8 | PV & Battery | 4-92B-571 | 2022-03-29 | 2022-04-21 | [28 empty] | 2022-05-04 | [13 empty] | In Queue |  |  | Y
2390776 | West Dennis | 2670 | 233.3 | PV | TBD | 2020-03-06 | 2020-03-06 |  |  |  | 2020-03-23 | [38 empty] | Withdrawn
5247195 | West Dennis | 2670 | 5 | battery | TBD | 2021-02-17 | 2021-03-05 |  |  |  | 2021-03-24 | [24 empty] | 2021-04-28
ESMAEX-01185 | West Harwich | 2671 | 17.2 | PV & Battery | 4-85-925 | 2022-05-16 | 2022-07-26 | [28 empty] | 2022-08-10 | [12 empty] | 2022-12-29 | Online |  |  | Y
2374665 | West Harwich | 2671 | 25.6 | PV & Battery | 4-85-592 | 2019-11-22 | 2019-12-02 |  |  |  | 2019-12-17 | [24 empty] | 2020-02-07
ESMAEX-00558 | Hyannisport | 2672 | 10 | Battery | 4-80B-514 | 2021-11-01 | 2021-11-17 | [28 empty] | 2022-02-04 | [12 empty] | 2023-04-26 | Online |  |  | Y
4311398 | West Yarmouth | 2673 | 370 | PV | TBD | 2020-08-18 | 2020-09-03 |  |  |  | 2020-10-01 | [38 empty] | Withdrawn
ESMAEX-00278 | West Yarmouth | 2673 | 170 | Internal Combustion Engine | 4-64-536 | 2021-08-02 | 2021-08-13 | [28 empty] | 2022-02-24 | [13 empty] | In Queue |  |  | N
ESMAEX-00327 | West Yarmouth | 2673 | 22.6 | PV & Battery | 4-64-557 | 2021-08-18 | 2021-09-07 | [28 empty] | 2022-02-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-00719 | West Yarmouth | 2673 | 20.2 | PV & Battery | 4-64-64 | 2022-01-11 | 2022-02-02 | [28 empty] | 2022-02-04 | [12 empty] | 2022-12-05 | Online |  |  | Y
2403438 | West Yarmouth | 2673 | 232 | PV | TBD | 2020-05-18 | 2020-06-08 |  |  |  | 2020-06-23 | [24 empty] | 2020-10-08 | [13 empty] | Withdrawn
4907860 | West Yarmouth | 2673 | 21.75 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 |  |  |  | 2021-02-02 | [24 empty] | 2021-04-22 | [12 empty] | 2022-02-16 | Online
5247359 | West Yarmouth | 2673 | 17.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-24 | [24 empty] | 2021-04-28 | [12 empty] | 2022-05-04 | Online
5483954 | West Yarmouth | 2673 | 160 | PV | TBD | 2021-03-16 | 2021-04-01 |  |  |  | 2021-04-16 | [24 empty] | 2021-04-30 | [12 empty] | 2021-06-15 | Online
2228338 | West Yarmouth | 2673 | 39 | PV | 4-64-536 | 2017-06-26 | 2017-07-12 | 11 |  | 11 | 2017-08-03 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-26 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
2343868 | West Yarmouth | 2673 | 174 | PV & Battery | 4-92A-536 | 2019-05-21 | 2019-05-28 |  |  |  | 2019-06-10 | [24 empty] | 2019-07-26 | [12 empty] | 2020-08-26 | Online
2320835 | West Yarmouth | 2673 | 498 | PV | 4-92A-534 | 2018-12-20 | 2018-12-26 | 4 |  | 4 | 2019-01-17 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
2217600 | Yarmouth | 2673 | 1560 | PV | 4-92A-92A | 2017-05-08 | 2017-06-13 | 25 |  | 25 | 2017-06-13 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
4263458 | Yarmouth | 2673 | 158.4 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 |  |  |  | 2020-10-15 | [24 empty] | 2021-01-26
5057452 | Yarmouth | 2673 | 188 | PV | TBD | 2021-01-27 | 2021-02-05 |  |  |  | 2021-02-24 | [24 empty] | 2021-03-15
5233972 | Yarmouth | 2673 | 187.5 | PV & Battery | TBD | 2021-02-25 | [29 empty] | 2021-05-27
5333868 | Yarmouth | 2673 | 999 | PV & Battery | TBD | 2021-03-02 | 2021-03-15 |  |  |  | 2021-03-31
2263856 | Yarmouth | 2675 | 104.4 | PV | 4-92A-536 | 2018-01-24 | 2018-02-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-06-27 | [6 empty] | 0 |  | 0 |  |  | 2019-11-08 | Online
2236910 | Yarmouth | 2675 | 23.2 | PV | 4-90-541 | 2017-09-01 | 2017-09-06 | 2 |  | 2 | 2017-09-27 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-26 | [6 empty] | 0 |  | 0
5518451 | Hyannisport | 2678 | 28 | Battery | TBD | 2021-04-09 | 2021-04-09 |  |  |  | 2021-04-21 | [24 empty] | 2021-07-01 | [12 empty] | 2022-05-18 | Online
2250466 | Assonet | 2702 | 15.2 | PV | 2-605-605 | 2017-11-14 | 2017-11-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
2368944 | Assonet | 2702 | 15.2 | PV | 2-605-605 | 2019-09-13 | 2019-11-01 | [28 empty] | 2020-03-02 | [12 empty] | 2020-07-08 | Online
4494158 | Assonet | 2702 | 18.85 | PV | TBD | 2020-10-22 | 2020-10-22 |  |  |  | 2020-12-03 | [24 empty] | 2020-12-15 | [12 empty] | 2021-05-05 | Online
2175318 | Assonet | 2702 | 16.7 | PV | 2-605-605 | 2016-09-13 | 2016-09-17 | 3 |  | 3 | 2016-10-17 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2188539 | Assonet | 2702 | 16.7 | PV | 2-605-605 | 2016-11-17 | 2016-11-21 | 2 |  | 2 | 2016-12-15 |  | -30515 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2258821 | Assonet | 2702 | 16.7 | PV | 2-605-605 | 2017-12-18 | 2017-12-28 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2347725 | Assonet | 2702 | 3000 | PV & Battery | TBD | 2019-06-17 | 2019-06-20 |  |  |  | 2019-07-05
2359951 | Assonet | 2702 | 250 | PV | TBD | 2019-09-03 | 2019-09-03 |  |  |  | 2019-09-18 | [24 empty] | 2019-12-16
4556815 | Assonet | 2702 | 15.2 | PV | TBD | 2020-10-15 | 2020-11-04 |  |  |  | 2020-12-04 | [24 empty] | 2020-12-15 | [12 empty] | 2021-12-07 | Online
2129465 | Assonet | 2702 | 16.95 | PV | 2-605-605 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00195 | Assonet | 2702 | 15.2 | PV | 2-605-605 | 2021-06-21 | 2021-08-03 | [28 empty] | 2021-08-11 | [12 empty] | 2022-01-20 | Online |  |  | Y
ESMAEX-00396 | Assonet | 2702 | 149.76 | PV | 2-102-604 | 2021-09-09 | 2021-09-29 | [28 empty] | 2021-11-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-00610 | Assonet | 2702 | 17.25 | PV | 2-605-605 | 2021-11-22 | 2021-12-14 | [28 empty] | 2022-03-02 | [13 empty] | In Queue |  |  | Y
2224661 | Fairhaven | 2702 | 4900 | PV | 2-605-605 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30658 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30682 |  | 30682 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2224890 | Freetown | 2702 | 4900 | PV | 2-102-102 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30658 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30682 |  | 30682 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2274652 | Freetown | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0
2277113 | Freetown | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30875 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2277114 | Freetown | 2702 | 5000 | PV & Battery | 532 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30875 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2320621 | Freetown | 2702 | 4875 | PV | 2-605-605 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2337126 | Freetown | 2702 | 4890 | PV & Battery | 2-605-605 | 2019-04-12 | 2019-04-15 | 1 |  | 1 | 2019-05-01 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
4869709 | Freetown | 2702 | 4999 | PV & Battery | TBD | 2020-12-30 | 2021-01-11 |  |  |  | 2021-01-28
2403584 | Dartmouth | 2714 | 2958 | PV & Battery | 2-543-543 | 2020-02-20 | 2020-06-08 |  |  |  | 2020-06-29
2328085 | East Freetown | 2717 | 27.42 | PV | 2-102-102 | 2019-02-20 | 2019-02-21 | 1 |  | 1 | 2019-03-05 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
2399041 | East Freetown | 2717 | 25 | PV | TBD | 2020-05-07 | 2020-05-07 |  |  |  | 2020-05-27 | [24 empty] | 2020-07-07 | [13 empty] | Withdrawn
4686146 | East Freetown | 2717 | 149.3 | PV | TBD | 2020-12-22 | 2020-12-22 |  |  |  | 2021-01-11 | [24 empty] | 2021-04-22
ESMAEX-00965 | East Freetown | 2717 | 15.2 | PV | 2-108-108 | 2022-03-24 | 2022-04-12 | [28 empty] | 2022-04-15 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-02075 | East Freetown | 2717 | 17.6 | PV | 2-108-108 | 2023-01-26 | 2023-02-15 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-02299 | East Freetown | 2717 | 20 | PV | 2-108-108 | 2023-03-22 | 2023-04-13 | [28 empty] | 2023-04-19 | [13 empty] | In Queue |  |  | Y
2314499 | East Freetown | 2717 | 3300 | PV & Battery | 2-102-604 | 2018-10-19 | 2018-12-14 | 40 |  | 40 | 2018-12-31 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
2373342 | East Freetown | 2717 | 17.6 | PV & Battery | 2-102-602 | 2019-11-07 | 2019-11-22 |  |  |  | 2019-12-10 | [24 empty] | 2020-02-28 | [12 empty] | 2020-06-19 | Online
2395483 | East Freetown | 2717 | 149.3 | PV | TBD | 2020-03-09 | 2020-04-10 |  |  |  | 2020-04-27 | [24 empty] | 2020-06-23 | [12 empty] | 2021-04-22 | Online
2349398 | East Freetown | 2717 | 1750 | PV | TBD | 2019-05-09 | 2019-06-24 |  |  |  | 2019-07-11 | [38 empty] | Withdrawn
2349571 | East Freetown | 2717 | 1000 | PV | TBD | 2019-06-21 | 2019-06-26 |  |  |  | 2019-07-12 | [38 empty] | Withdrawn
2382455 | East Freetown | 2717 | 25 | PV & Battery | TBD | 2020-01-06 | 2020-01-06 |  |  |  | 2020-01-21 | [24 empty] | 2020-01-31 | [13 empty] | Withdrawn
2387969 | East Freetown | 2717 | 15.2 | PV | 2-107-107 | 2020-01-22 | 2020-02-18 |  |  |  | 2020-03-04 | [24 empty] | 2020-03-19 | [13 empty] | Withdrawn
2391908 | East Freetown | 2717 | 25 | PV | TBD | 2020-03-16 | 2020-03-16 |  |  |  | 2020-03-31 | [24 empty] | 2020-08-07 | [12 empty] | 2021-07-08 | Online
2395036 | East Freetown | 2717 | 149.3 | PV | TBD | 2020-03-26 | 2020-04-06 |  |  |  | 2020-04-23 | [24 empty] | 2020-06-09 | [12 empty] | 2021-07-12 | Online
4355122 | East Freetown | 2717 | 61.6 | PV | TBD | 2020-09-25 | 2020-09-25 |  |  |  | 2020-10-15 | [24 empty] | 2020-12-24 | [12 empty] | 2021-11-02 | Online
5141690 | East Freetown | 2717 | 25 | PV | TBD | 2020-12-30 | 2021-02-10 |  |  |  | 2021-03-03 | [24 empty] | 2021-04-28 | [12 empty] | 2021-08-27 | Online
4896804 | East Freetown | 2717 | 25 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 |  |  |  | 2021-02-05 | [24 empty] | 2021-05-13
ESMAEX-00508 | East Freetown | 2717 | 149.76 | PV | 2-108-108 | 2021-10-18 | 2021-11-15 | [28 empty] | 2022-02-09 | [12 empty] | 2023-03-01 | Online |  |  | Y
2139202 | East Freetown | 2717 | 24.32 | PV | 2-102-602 | 2016-03-23 | 2016-04-06 | 10 |  | 10 | 2016-04-06 |  | -30334 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-09 | 2016-06-10 | [6 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | PRIVATE
5415234 | East Freetown | 2717 | 1000 | PV & Battery | 2-102-608 | 2016-12-14 | 2016-12-27 | 9 |  | 9 | 2017-01-19 |  | -30538 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-05-22 | 30622 |  | 30622 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-28 | Online
2301315 | East Freetown | 2717 | 220 | PV | 604 | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-16 |  | -30983 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online |  | Private
2341535 | East Freetown | 2717 | 25 | PV | 2-102-102 | 2019-05-16 | 2019-05-17 |  |  |  | 2019-05-29 | [24 empty] | 2019-07-01 | [12 empty] | 2020-10-22 | Online
2262266 | East Freetown | 2717 | 15.95 | PV | 2-107-107 | 2018-01-16 | 2018-01-23 | 5 |  | 5 | 2018-02-08 |  | -30805 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-28 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2089453 | East Freetown | 2717 | 22.8 | PV | 2-102-102 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00079 | East Freetown | 2717 | 69.2 | PV | 2-102-102 | 2021-04-28 | 2021-05-14 | [28 empty] | 2021-08-03 | [12 empty] | 2023-03-28 | Online |  |  | Y
ESMAEX-00080 | East Freetown | 2717 | 69.2 | PV | 2-102-604 | 2021-04-28 | 2021-05-14 | [28 empty] | 2021-06-10 | [12 empty] | 2023-03-31 | Online |  |  | Y
ESMAEX-01691 | East Freetown | 2717 | 3000 | PV & Battery | 2-108-108 | 2022-11-17 | 2022-12-19 | [42 empty] | In Queue |  |  | Y
2238661 - B | Freetown | 2717 | 4990 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30719 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
2188717 | Freetown | 2717 | 4950 | PV | 2-102-102 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2238661 - A | Freetown | 2717 | 4090 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30719 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2297681 | Freetown | 2717 | 4500 | PV & Battery | 2-108-108 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-21 |  | -30966 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2319218 | Freetown | 2717 | 8360 | PV & Battery | 2-605-605 | 2018-12-07 | 2018-12-18 | 7 |  | 7 | 2019-01-08 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2337174 | Freetown | 2717 | 4890 | PV & Battery | 2-605-605 | 2019-04-16 | 2019-04-17 | 1 |  | 1 | 2019-05-01 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2353838 | Freetown | 2717 | 500 | PV & Battery | TBD | 2019-05-29 | 2019-07-22 |  |  |  | 2019-08-08
2354457 | Freetown | 2717 | 5000 | PV & Battery | TBD | 2019-06-03 | 2019-07-30 |  |  |  | 2019-08-13
2366461 | Freetown | 2717 | 2000 | PV | TBD | 2019-08-14 | 2019-10-16 |  |  |  | 2019-11-01
2360807 | Freetown | 2717 | 1125 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 |  |  |  | 2019-09-25
2384761 | Freetown | 2717 | 2000 | PV & Battery | TBD | 2020-01-07 | 2020-01-08 |  |  |  | 2020-02-06
2400205 | Freetown | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 |  |  |  | 2020-06-02
2401405 | Freetown | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 |  |  |  | 2020-06-08
ESMAEX-01812 | Freetown | 2717 | 148.92 | PV | TBD | 2022-11-15 | 2022-12-08 | [42 empty] | In Queue |  |  | Y
2130412 | Fairhaven | 2719 | 16.4 | PV | 2-221-221 | 2016-02-02 | 2016-02-02 | 0 |  | 0 | 2016-02-23 |  | -30303 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-07 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-07-01 | Online
2202964 | Fairhaven | 2719 | 184 | PV | 2-240-209 | 2017-02-15 | 2017-02-15 | 0 |  | 0 | 2017-02-27 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
2374177 | Fairhaven | 2719 | 200 | PV | 2-220-206 | 2019-11-27 | 2019-11-27 |  |  |  | 2019-12-12 | [24 empty] | 2020-02-28 | [12 empty] | 2021-04-22 | Online
2380743 | Fairhaven | 2719 | 200 | PV | 2-221-221 | 2019-11-27 | 2019-11-27 |  |  |  | 2020-01-08 | [24 empty] | 2020-02-20 | [12 empty] | 2021-04-22 | Online
2201063 | Fairhaven | 2719 | 2000 | PV | 2-221-221 | 2017-01-31 | 2017-01-31 | 0 |  | 0 | 2017-02-13 |  | -30555 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-02-27 | -16 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
2255728 | Fairhaven | 2719 | 3750 | PV | 2-221-221 | 2017-12-04 | 2017-12-11 | 5 |  | 5 | 2018-01-08 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-24 | 2018-04-23 | -3 |  | 0 |  |  | 0 |  | 0 | 2018-09-26 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
2270747 | Fairhaven | 2719 | 8300 | PV & Battery | 2-241-241 | 2018-03-01 | 2018-03-14 | 9 |  | 9 | 2018-04-11 |  | -30849 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2349408 | Fairhaven | 2719 | 2000 | PV & Battery | TBD | 2019-05-28 | 2019-06-26 |  |  |  | 2019-07-12
2403269 | Fairhaven | 2719 | 469.8 | PV | TBD | 2020-03-16 | 2020-06-05 |  |  |  | 2020-06-23 | [24 empty] | 2020-09-29 | [12 empty] | 2022-03-08 | Online
2393958 | Fairhaven | 2719 | 245 | PV | TBD | 2020-03-18 | 2020-03-31 |  |  |  | 2020-04-15 | [24 empty] | 2020-09-18 | [13 empty] | Withdrawn
2408289 | Fairhaven | 2719 | 99.09 | PV | TBD | 2020-07-10 | 2020-07-14 |  |  |  | 2020-07-28 | [24 empty] | 2020-10-19
2410005 | Fairhaven | 2719 | 750 | PV | TBD | 2020-07-22 | 2020-07-22 |  |  |  | 2020-08-10
2412322 | Fairhaven | 2719 | 66.6 | PV | TBD | 2020-08-10 | 2020-08-10 |  |  |  | 2020-08-28 | [24 empty] | 2020-09-11 | [12 empty] | 2021-07-28 | Online
4404592 | Fairhaven | 2719 | 2000 | PV & Battery | TBD | 2020-09-24 | 2020-09-25 |  |  |  | 2020-10-28
5132174 | Fairhaven | 2719 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 |  |  |  | 2021-03-08
ESMAEX-00027 | Fairhaven | 2719 | 223 | Battery | 2-221-221 | 2021-04-02 | 2021-05-21 | [28 empty] | 2021-11-04 | [13 empty] | In Queue |  |  | Y
ESMAEX-00028 | Fairhaven | 2719 | 223 | Battery | 2-220-206 | 2021-04-02 | 2021-05-20 | [28 empty] | 2021-11-03 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-00090 | Fairhaven | 2719 | 499.5 | PV | 2-222-222 | 2021-04-30 | 2021-05-18 | [42 empty] | In Queue |  |  | Y
ESMAEX-00559 | Fairhaven | 2719 | 500 | PV | 2-240-240 | 2021-11-01 | 2021-12-09 | [42 empty] | In Queue |  |  | Y
ESMAEX-00938 | Fairhaven | 2719 | 200 | PV & Battery | 2-230-230 | 2022-06-22 | 2022-07-20 | [28 empty] | 2022-11-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-00939 | Fairhaven | 2719 | 4999.2 | Battery | 2-230-230 | 2022-06-28 | 2022-08-10 | [42 empty] | In Queue |  |  | Y
ESMAEX-01216 | Fairhaven | 2719 | 15.2 | PV | 2-220-201 | 2022-05-24 | 2022-06-15 | [28 empty] | 2022-06-22 | [12 empty] | 2022-10-21 | Online |  |  | Y
ESMAEX-01787 | Fairhaven | 2719 | 100 | PV & Battery | 2-221-221 | 2022-11-09 | 2022-11-29 | [28 empty] | 2022-12-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01927 | Fairhaven | 2719 | 10 | PV & Battery | 2-222-222 | 2022-12-14 | 2023-01-12 | [28 empty] | 2023-03-01 | [13 empty] | In Queue |  |  | Y
ESMAEX-02343 | Fairhaven | 2719 | 50 | PV | 2-220-220 | 2023-04-04 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
2355860 | Fairhaven | 2719 | 100 | PV | TBD | 2019-08-05 | 2019-08-05 |  |  |  | 2019-08-23 | [24 empty] | 2019-10-11 | [12 empty] | 2021-03-12 | Online
2370690 | Westport | 2721 | 3375 | PV | TBD | 2019-10-29 | 2019-11-14 |  |  |  | 2019-11-29
2171654 | Marion | 2738 | 15.2 | PV | 3-85-85 | 2016-09-01 | 2016-09-07 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online |  | PRIVATE
2174858 | Marion | 2738 | 27.72 | PV | 2-304-304 | 2016-09-08 | 2016-09-15 | 5 |  | 5 | 2016-10-14 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online |  | PRIVATE
2305082 | Marion | 2738 | 20.88 | PV | 3-85-969 | 2018-10-19 | 2018-10-19 | 0 |  | 0 | 2018-11-05 | 2018-11-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-29 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-01-09 | Online |  | Private
2270301 | Marion | 2738 | 17.6 | PV | 2-304-304 | 2018-03-08 | 2018-03-09 | 1 |  | 1 | 2018-04-09 |  | -30847 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
2338418 | Marion | 2738 | 99.9 | PV | 3-304-304 | 2019-04-18 | 2019-04-18 | 0 |  | 0 | 2019-05-08 |  | -31129 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
2297682 | Marion | 2738 | 3500 | PV & Battery | 3-85-85 | 2018-08-14 | 2018-09-06 | 17 |  | 17 | 2018-09-21 |  | -30966 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
4668251 | Marion | 2738 | 22.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 |  |  |  | 2021-01-05 | [24 empty] | 2021-01-11 | [12 empty] | 2021-06-30 | Online
5256768 | Marion | 2738 | 25.2 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 |  |  |  | 2021-03-26 | [24 empty] | 2021-04-14
ESMAEX-00063 | Marion | 2738 | 21.21 | PV & Battery | 3-85-85 | 2021-04-21 | 2021-05-07 | [28 empty] | 2021-08-27 | [12 empty] | 2021-11-04 | Online |  |  | Y
ESMAEX-00270 | Marion | 2738 | 22.8 | PV | 3-85-85 | 2021-07-28 | 2021-08-13 | [28 empty] | 2021-11-03 | [12 empty] | 2022-06-17 | Online |  |  | Y
ESMAEX-00590 | Marion | 2738 | 17.6 | PV & Battery | 3-85-85 | 2021-11-16 | 2022-01-20 | [28 empty] | 2022-03-23 | [12 empty] | 2023-01-26 | Online |  |  | Y
ESMAEX-00658 | Marion | 2738 | 22.8 | PV | 3-304-304 | 2021-12-14 | 2022-01-06 | [28 empty] | 2022-03-24 | [12 empty] | 2022-07-18 | Online |  |  | Y
ESMAEX-00725 | Marion | 2738 | 10 | PV & Battery | 3-304-304 | 2022-01-12 | 2022-02-24 | [28 empty] | 2022-03-07 | [12 empty] | 2022-06-28 | Online |  |  | Y
ESMAEX-01255 | Marion | 2738 | 17.568 | PV | TBD | 2022-06-03 | 2022-08-10 | [28 empty] | 2022-08-15 | [12 empty] | 2023-01-20 | Online |  |  | Y
ESMAEX-01896 | Marion | 2738 | 20.65 | PV | 3-304-304 | 2022-12-06 | 2023-05-03 | [42 empty] | In Queue |  |  | Y
ESMAEX-02028 | Marion | 2738 | 17.6 | PV | 3-304-304 | 2023-01-16 | 2023-02-09 | [28 empty] | 2023-04-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-02355 | Marion | 2738 | 15.2 | PV | 3-702-702 | 2023-04-06 | 2023-04-27 | [28 empty] | 2023-05-01 | [13 empty] | In Queue |  |  | Y
2401247 | Marion | 2738 | 700 | PV & Battery | TBD | 2020-04-30 | 2020-05-18 |  |  |  | 2020-06-08
2295586 | Rochester | 2738 | 996 | PV | 3-85-85 | 2018-08-20 | 2018-08-23 | 3 |  | 3 | 2018-09-11 |  | -30958 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2295386 | Wareham | 2738 | 2925 | PV | 3-85-85 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-07 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2330775 | Mattapoisett | 2739 | 4980 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-06 | 9 |  | 9 | 2019-03-29 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Online
2334358 | Mattapoisett | 2739 | 3300 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-27 | 24 |  | 24 | 2019-04-11 |  | -31110 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Online
2375330 | Mattapoisett | 2739 | 28.7 | PV & Battery | 2-301-301 | 2019-11-27 | 2019-12-03 |  |  |  | 2019-12-20 | [24 empty] | 2020-02-28 | [12 empty] | 2020-12-22 | Online
2407746 | Mattapoisett | 2739 | 15.2 | PV | TBD | 2020-07-01 | 2020-07-01 |  |  |  | 2020-07-22 | [24 empty] | 2020-08-03 | [12 empty] | 2021-01-19 | Online
2164627 | Mattapoisett | 2739 | 16.92 | PV | 2-301-301 | 2016-07-05 | 2016-07-27 | 16 |  | 16 | 2016-08-22 |  | -30432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2223989 | Mattapoisett | 2739 | 43.17 | PV | 2-301-301 | 2017-06-02 | 2017-06-08 | 4 |  | 4 | 2017-07-06 |  | -30654 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-26 | 2017-08-17 | [6 empty] | 0 |  | 0
2285553 | Mattapoisett | 2739 | 3560 | PV | 2-302-302 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2285554 | Mattapoisett | 2739 | 4980 | PV & Battery | 2-301-301 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2295025 | Mattapoisett | 2739 | 960 | PV | 2-302-302 | 2018-08-14 | 2018-08-17 | 3 |  | 3 | 2018-09-05 |  | -30954 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online
2327320 | Mattapoisett | 2739 | 2000 | PV | 2-302-302 | 2019-02-12 | 2019-02-14 | 2 |  | 2 | 2019-02-28 |  | -31080 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2329391 | Mattapoisett | 2739 | 4600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-14 |  | -31090 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
2330206 | Mattapoisett | 2739 | 2600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-03-06 | 10 |  | 10 | 2019-03-18 |  | -31092 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
2353656 | Mattapoisett | 2739 | 4999 | PV & Battery | TBD | 2019-07-16 | 2019-07-19 |  |  |  | 2019-08-07
2368538 | Mattapoisett | 2739 | 15.2 | PV | 2-301-301 | 2019-09-10 | 2019-10-28 |  |  |  | 2019-11-13 | [24 empty] | 2020-01-03
2374771 | Mattapoisett | 2739 | 3 Options | PV & Battery | TBD | 2019-11-27 | 2019-12-03 |  |  |  | 2019-12-17 | [38 empty] | Withdrawn
2388535 | Mattapoisett | 2739 | 0 | PV | TBD | 2020-01-30 | 2020-02-18 |  |  |  | 2020-03-04 | [38 empty] | Withdrawn
2410489 | Mattapoisett | 2739 | 5000 | PV & Battery | TBD | 2020-07-29 | 2020-08-04 |  |  |  | 2020-08-17
4490762 | Mattapoisett | 2739 | 5000 | PV & Battery | TBD | 2020-10-16 | 2020-10-21 |  |  |  | 2020-11-18
4619595 | Mattapoisett | 2739 | 2250 | PV & Battery | TBD | 2020-11-06 | 2020-11-25 |  |  |  | 2020-12-21
4717656 | Mattapoisett | 2739 | 2496 | Battery | TBD | 2020-12-22 | 2020-12-22 |  |  |  | 2021-01-19
5193909 | Mattapoisett | 2739 | 148.92 | PV | TBD | 2021-02-25 | 2021-02-25 |  |  |  | 2021-03-18
ESMAEX-00955 | Mattapoisett | 2739 | 478.55 | PV & Battery | 2-304-304 | 2022-03-21 | 2022-04-18 | [28 empty] | 2022-07-05 | [13 empty] | In Queue |  |  | Y
ESMAEX-01333 | Mattapoisett | 2739 | 478.55 | PV | 2-304-304 | 2022-06-29 | 2022-07-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-00189 | Mattapoisett | 2739 | 9 | PV | 2-301-301 | 2021-06-16 | 2021-07-01 | [28 empty] | 2021-09-23 | [12 empty] | 2022-01-10 | Online |  |  | Y
ESMAEX-00200 | Mattapoisett | 2739 | 18.28 | PV | 2-301-301 | 2021-06-22 | 2021-07-27 | [28 empty] | 2021-08-02 | [12 empty] | 2021-12-22 | Online |  |  | Y
ESMAEX-00425 | Mattapoisett | 2739 | 79.75 | PV | 2-304-304 | 2021-09-20 | 2021-10-07 | [28 empty] | 2021-10-12 | [12 empty] | 2022-02-14 | Online |  |  | Y
ESMAEX-00450 | Mattapoisett | 2739 | 17.6 | PV | 2-302-302 | 2021-09-27 | 2021-10-20 | [28 empty] | 2021-10-22 | [12 empty] | 2022-01-05 | Online |  |  | Y
ESMAEX-00458 | Mattapoisett | 2739 | 1472 | PV & Battery | 2-302-302 | 2021-09-29 | 2021-10-15 | [42 empty] | In Queue |  |  | Y
ESMAEX-00485 | Mattapoisett | 2739 | 16.24 | PV | 2-302-302 | 2021-10-09 | 2021-11-03 | [28 empty] | 2021-11-09 | [12 empty] | 2022-02-08 | Online |  |  | Y
ESMAEX-01013 | Mattapoisett | 2739 | 27.6 | PV & Battery | 2-301-305 | 2022-04-05 | 2022-04-21 | [28 empty] | 2022-06-10 | [13 empty] | In Queue |  |  | Y
ESMAEX-01983 | Mattapoisett | 2739 | 19.5 | PV | 2-301-305 | 2023-01-09 | 2023-02-01 | [42 empty] | In Queue |  |  | Y
ESMAEX-02163 | Mattapoisett | 2739 | 5.4 | Battery | 2-302-302 | 2023-02-14 | 2023-03-02 | [42 empty] | In Queue |  |  | Y
2188718 | New Bedford | 2740 | 27 | PV | 2-73-47 | 2016-08-29 | 2016-10-28 | 44 |  | 44 | 2016-12-16 |  | -30516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-23 | Online |  | NO EXPORT | N
2208391 | New Bedford | 2740 | 36 | PV | 2-59-96 | 2017-02-20 | 2017-03-20 | 20 |  | 20 | 2017-04-03 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-02 | 2017-05-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online |  | PRIVATE
2217818 | New Bedford | 2740 | 1070 | PV | 2-151-151 | 2017-05-08 | 2017-06-13 | 25 |  | 25 | 2017-06-16 | 2017-06-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -18 |  | 0 |  |  | 0 |  | 0 | 2018-01-22 | [7 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
2291744 | New Bedford | 2740 | 36 | PV | 2-69-69 | 2018-06-25 | 2018-08-03 | 29 |  | 29 | 2018-08-15 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online |  | Private
2227197 | New Bedford | 2740 | 700 | PV | 2-152-152 | 2017-06-15 | 2017-06-29 | 10 |  | 10 | 2017-07-26 |  | -30668 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | [7 empty] | 0 |  | 0 | 2018-12-21 |  | 2018-12-21 | Online
2295246 | New Bedford | 2740 | 86.4 | PV | 2-49-49 | 2018-08-14 | 2018-08-20 | 4 |  | 4 | 2018-09-06 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
2295579 | New Bedford | 2740 | 150 | PV | 2-70-70 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-11 | 2018-10-24 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | 2018-10-30 | [6 empty] | 0 |  | 0 |  |  | 2019-12-19 | Online |  | Private
2308002 | New Bedford | 2740 | 43.2 | PV | 2-24-182 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 | 2018-12-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-04 | 2018-12-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-20 | Online |  | Private
2351619 | New Bedford | 2740 | 236 | PV | TBD | 2019-07-10 | 2019-07-11 |  |  |  | 2019-07-26 | [24 empty] | 2019-09-20 | [12 empty] | 2020-07-30 | Online
4590471 | New Bedford | 2740 | 20 | PV | TBD | 2020-11-09 | 2020-11-16 |  |  |  | 2020-12-11 | [24 empty] | 2020-12-18 | [12 empty] | 2021-05-14 | Online
2128034 | New Bedford | 2740 | 17.45 | PV | 2.3.96 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-26 | 2016-03-07 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2284288 | New Bedford | 2740 | 250 | PV | 110-110 | 2018-05-29 | 2018-06-14 | 12 |  | 12 | 2018-06-29 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2305081 | New Bedford | 2740 | 199.4 | PV | 2-38-38 | 2018-10-18 | 2018-10-19 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online |  | Public
2333508 | New Bedford | 2740 | 346.5 | PV | 2-137-139 | 2019-03-18 | 2019-03-22 | 4 |  | 4 | 2019-04-09 |  | -31108 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2366447 | New Bedford | 2740 | 1400 | Fuel Cell | TBD | 2019-10-11 | 2019-10-15 |  |  |  | 2019-10-31 | [38 empty] | Withdrawn
2394184 | New Bedford | 2740 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 |  |  |  | 2020-04-16 | [24 empty] | 2020-06-30
2394211 | New Bedford | 2740 | 250 | PV | TBD | 2020-03-20 | 2020-03-31 |  |  |  | 2020-04-16 | [24 empty] | 2020-06-30
4556981 | New Bedford | 2740 | 999 | PV & Battery | TBD | 2020-10-27 | 2020-11-02 |  |  |  | 2020-12-04 | [37 empty] | 2021-09-17 | Online
4991678 | New Bedford | 2740 | 15.2 | PV | TBD | 2021-01-06 | 2021-01-26 |  |  |  | 2021-02-17 | [38 empty] | Withdrawn
2119973 | New Bedford | 2740 | 248.88 | PV | 2-137-139 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
5299345 | New Bedford | 2740 | 120 | PV | TBD | 2021-02-25 | 2021-03-10 |  |  |  | 2021-04-02 | [24 empty] | 2021-04-14 | [12 empty] | 2021-09-30 | Online
ESMAEX-00053 | New Bedford | 2740 | 100 | PV | 2-42-42 | 2021-04-14 | 2021-05-03 | [28 empty] | 2021-08-17 | [13 empty] | In Queue |  |  | Y
ESMAEX-00781 | New Bedford | 2740 | 4999.2 | Battery | 2-110-110 | 2022-11-29 | [43 empty] | In Queue |  |  | Y
ESMAEX-00996 | New Bedford | 2740 | 120 | PV | 2-83-403 | 2022-03-31 | 2022-04-15 | [28 empty] | 2022-05-16 | [13 empty] | In Queue |  |  | Y
ESMAEX-01197 | New Bedford | 2740 | 100 | PV | 2-55-47 | 2022-05-19 | 2022-06-07 | [28 empty] | 2022-06-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-00062 | New Bedford | 2740 | 16.57 | PV & Battery | 2-531-531 | 2021-04-20 | 2021-05-18 | [28 empty] | 2021-06-10 | [12 empty] | 2021-11-10 | Online |  |  | Y
ESMAEX-00418 | New Bedford | 2740 | 50 | PV | 2-73-16 | 2021-09-17 | 2021-10-07 | [28 empty] | 2021-10-08 | [12 empty] | 2022-08-12 | Online |  |  | Y
ESMAEX-00436 | New Bedford | 2740 | 75 | Internal Combustion Engine | 2-67-28 | 2021-09-21 | 2021-10-07 | [28 empty] | 2021-10-27 | [12 empty] | 2022-12-12 | Online |  |  | N
ESMAEX-00437 | New Bedford | 2740 | 75 | Internal Combustion Engine | 18663 | 2021-09-21 | 2021-10-07 | [28 empty] | 2021-10-27 | [12 empty] | 2022-12-12 | Online |  |  | N
ESMAEX-02150 | Watertown | 2742 | 120 | PV | TBD | 2023-02-13 | 2023-03-02 | [42 empty] | In Queue |  |  | Y
2176279 | Acushnet | 2743 | 15.36 | PV | 2-241-241 | 2016-09-20 | 2016-09-20 | 0 |  | 0 | 2016-10-21 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-08 | 2016-12-09 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online |  | PRIVATE
2320833 | Acushnet | 2743 | 21.34 | PV & Battery | 2-241-241 | 2018-04-06 | 2018-12-26 | 188 |  | 188 | 2019-01-17 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-01 | Online
2157905 | Acushnet | 2743 | 144.4 | PV | 2-231-231 | 2016-05-27 | 2016-06-27 | 21 |  | 21 | 2016-07-14 |  | -30405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2271557 | Acushnet | 2743 | 9878 | PV & Battery | 2-106-160 | 2018-03-19 | 2018-03-28 | 7 |  | 7 | 2018-04-16 |  | -30852 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
2274401 | Acushnet | 2743 | 4990 | PV & Battery | 2-241-241 | 2018-04-04 | 2018-04-16 | 8 |  | 8 | 2018-05-02 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2277380 | Acushnet | 2743 | 8980 | PV & Battery | 2-241-241 | 2018-04-11 | 2018-05-04 | 17 |  | 17 | 2018-05-22 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2299606 | Acushnet | 2743 | 4950 | PV & Battery | 2-241-241 | 2018-09-07 | 2018-09-20 | 9 |  | 9 | 2018-10-03 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2301817 | Acushnet | 2743 | 5000 | PV | 2-241-241 | 2018-09-26 | 2018-09-28 | 2 |  | 2 | 2018-10-17 |  | -30984 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2304486 | Acushnet | 2743 | 3060 | PV & Battery | 2-241-238 | 2018-10-15 | 2018-10-18 | 3 |  | 3 | 2018-11-02 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2331299 | Acushnet | 2743 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31098 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2342846 | Acushnet | 2743 | 2640 | PV & Battery | 2-241-241 | 2019-04-10 | 2019-05-31 | 37 |  | 37 | 2019-06-04 |  | -31148 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2340380 | Acushnet | 2743 | 2999 | PV & Battery | 2-241-241 | 2019-04-12 | 2019-04-30 |  |  |  | 2019-05-21
2352175 | Acushnet | 2743 | 84 | PV | TBD | 2019-07-18 | 2019-07-18 |  |  |  | 2019-07-30 | [24 empty] | 2019-10-21
2355146 | Acushnet | 2743 | 4995 | PV & Battery | TBD | 2019-07-24 | 2019-08-01 |  |  |  | 2019-08-19
2358231 | Acushnet | 2743 | 22 | PV | 2-231-231 | 2019-08-22 | 2019-08-26 |  |  |  | 2019-09-06 | [24 empty] | 2019-10-21 | [12 empty] | 2021-10-14 | Online
2399839 | Acushnet | 2743 | 5000 | PV | TBD | 2019-09-13 | 2020-05-13 |  |  |  | 2020-05-29
2392113 | Acushnet | 2743 | 4000 | PV & Battery | TBD | 2020-03-12 | 2020-03-18 |  |  |  | 2020-04-03 | [38 empty] | Withdrawn
2394461 | Acushnet | 2743 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 |  |  |  | 2020-04-20 | [24 empty] | 2022-05-17 | [12 empty] | 2022-05-17 | Online
2414312 | Acushnet | 2743 | 1220 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 |  |  |  | 2020-10-05
2414387 | Acushnet | 2743 | 610 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 |  |  |  | 2020-09-14
4287867 | Acushnet | 2743 | 610 | PV & Battery | TBD | 2020-09-01 | 2020-09-03 |  |  |  | 2020-09-24
4556908 | Acushnet | 2743 | 500 | PV & Battery | TBD | 2020-11-02 | 2020-11-02 |  |  |  | 2020-12-04 | [24 empty] | 2020-04-20
4590902 | Acushnet | 2743 | 61.6 | PV | TBD | 2020-11-16 | 2020-11-16 |  |  |  | 2020-12-23 | [24 empty] | 2021-01-20 | [12 empty] | 2021-08-24 | Online
4702589 | Acushnet | 2743 | 4990 | PV & Battery | TBD | 2020-12-17 | 2020-12-29 |  |  |  | 2021-01-13
5113369 | Acushnet | 2743 | 17.6 | PV & Battery | TBD | 2020-12-17 | 2021-02-16 |  |  |  | 2021-03-08 | [24 empty] | 2021-03-25 | [12 empty] | 2021-06-07 | Online
4907766 | Acushnet | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 |  |  |  | 2021-02-17 | [24 empty] | 2021-04-22
4907809 | Acushnet | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 |  |  |  | 2021-02-05 | [24 empty] | 2021-04-22
ESMAEX-00573 | Acushnet | 2743 | 15.2 | PV | 2-241-241 | 2021-11-09 | 2021-12-07 | [28 empty] | 2021-12-15 | [12 empty] | 2022-08-23 | Online |  |  | Y
ESMAEX-01310 | Acushnet | 2743 | 11.52 | Battery | 2-241-238 | 2022-06-20 | 2022-07-07 | [28 empty] | 2022-08-15 | [12 empty] | 2022-12-19 | Online |  |  | Y
ESMAEX-01336 | Acushnet | 2743 | 9.3 | PV & Battery | 2-241-237 | 2022-06-30 | 2022-07-18 | [28 empty] | 2022-07-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-02031 | Acushnet | 2743 | 4999 | PV & Battery | 2-241-241 | 2023-01-17 | 2023-02-21 | [42 empty] | In Queue |  |  | Y
2329466 | Mattapoisett | 2743 | 4980 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-15 |  | -31091 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
2331280 | Acushnet | 2744 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31098 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2146760 | New Bedford | 2744 | 499.5 | PV | 2-69-52 | 2016-05-08 | 2016-05-09 | 1 |  | 1 | 2016-05-22 |  | -30366 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online
2270504 | New Bedford | 2744 | 599.4 | PV | 2-54-54 | 2018-01-22 | 2018-03-14 | 37 |  | 37 | 2018-04-09 |  | -30847 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-15 | 2018-06-22 | [6 empty] | 0 |  | 0 |  |  | 2019-07-19 | Online
2295385 | New Bedford | 2744 | 233.1 | PV | 2-41-41 | 2018-08-06 | 2018-09-04 | 21 |  | 21 | 2018-09-07 | 2018-11-20 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-11-27 | Online
2399048 | New Bedford | 2744 | 15.2 | PV | TBD | 2020-05-05 | 2020-05-13 |  |  |  | 2020-05-27 | [24 empty] | 2020-06-09 | [12 empty] | 2021-02-09 | Online
2370785 | New Bedford | 2744 | 150 | PV | TBD | 2019-11-07 | 2019-11-19 |  |  |  | 2019-12-02 | [24 empty] | 2020-01-30 | [12 empty] | 2021-05-18 | Online
5355312 | New Bedford | 2744 | 480 | PV | 2-7-7 | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | 2018-10-10 | [6 empty] | 0 |  | 0 | [5 empty] | Private
2334371 | New Bedford | 2744 | 180 | PV | 2-137-139 | 2019-01-31 | 2019-03-27 | 39 |  | 39 | 2019-04-11 |  | -31110 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-07-29 | Online
ESMAEX-02066 | New Bedford | 2744 | 200 | PV | 45346 | 2023-03-15 | 2023-04-13 | [42 empty] | In Queue |  |  | Y
ESMAEX-02331 | New Bedford | 2744 | 10 | PV | 12457 | 2023-03-31 | 2023-04-19 | [42 empty] | In Queue |  |  | Y
2179799 | New Bedford | 2745 | 208 | PV | 2-82-82 | 2016-10-09 | 2016-10-12 | 3 |  | 3 | 2016-11-03 |  | -30485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | 2016-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | Private
2196803 | New Bedford | 2745 | 296 | PV | 2-101-101 | 2016-12-28 | 2016-12-30 | 2 |  | 2 | 2016-01-17 |  | -30276 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-17 | [6 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online
2197507 | New Bedford | 2745 | 496 | PV | 2-152-152 | 2016-12-21 | 2016-12-30 | 7 |  | 7 | 2017-01-19 |  | -30538 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-09 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online
2219644 | New Bedford | 2745 | 336 | PV | 2-88-18 | 2017-05-19 | 2017-05-22 | 1 |  | 1 | 2017-06-08 |  | -30635 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-06-26 | [6 empty] | 0 |  | 0 |  |  | 2017-12-29 | Online
2227188 | New Bedford | 2745 | 499.05 | PV | 2-107-107 | 2017-06-16 | 2017-07-10 | 15 |  | 15 | 2017-07-26 |  | -30668 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2017-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
2314371 | New Bedford | 2745 | 100 | PV | 2-137-139 | 2018-12-12 | 2018-12-12 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-08 | Online
2386391 | New Bedford | 2745 | 30 | PV | 2-137-137 | 2019-12-03 | 2020-02-04 |  |  |  | 2020-02-25 | [24 empty] | 2020-03-24 | [12 empty] | 2020-09-25 | Online
2351223 | New Bedford | 2745 | 499.5 | PV | TBD | 2019-07-01 | 2019-07-08 |  |  |  | 2019-07-23 | [24 empty] | 2020-06-19 | [12 empty] | 2020-11-04 | Online
2366298 | New Bedford | 2745 | 200 | PV | 2-79-404 | 2019-09-25 | 2019-10-09 |  |  |  | 2019-10-31 | [37 empty] | 2020-11-13 | Online
2268420 | New Bedford | 2745 | 120 | PV | 2-104-104 | 2018-02-21 | 2018-03-15 | 16 |  | 16 | 2018-03-28 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online |  | Private
2268649 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2268650 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2268651 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2268866 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2268869 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2269021 | New Bedford | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
2394787 | New Bedford | 2745 | 100 | PV | TBD | 2020-04-06 | 2020-04-08 |  |  |  | 2020-04-23 | [37 empty] | 2020-12-22 | Online
4582294 | New Bedford | 2745 | 17.6 | PV & Battery | 2-104-104 | 2020-10-21 | 2020-11-09 |  |  |  | 2020-12-09 | [24 empty] | 2020-12-15 | [12 empty] | 2021-04-06 | Online
2227939 | New Bedford | 2745 | 632.7 | PV | 2-83-83 | 2017-06-30 | 2017-07-07 | 4 |  | 4 | 2017-08-01 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-11-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2298790 | New Bedford | 2745 | 1220 | PV | 2-107-107 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-28 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2333666 | New Bedford | 2745 | 22.8 | PV | 2-87-135 | 2019-03-13 | 2019-03-25 | 8 |  | 8 | 2019-04-08 |  | -31107 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
2334473 & 2334854 | New Bedford | 2745 | 695.6 | PV | TBD | 2019-03-25 | 2020-03-29 | 264 |  | 264 | 2020-04-16 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 | [7 empty] | 0 |  | 0
2340125 | New Bedford | 2745 | 200 | PV | 2-137-139 | 2019-04-18 | 2019-05-08 | 14 |  | 14 | 2019-05-20 |  | -31137 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-19 | Online
2351638 | New Bedford | 2745 | 466.6 | PV | TBD | 2019-07-08 | 2019-07-11 |  |  |  | 2019-07-26 | [38 empty] | Withdrawn
2370116 | New Bedford | 2745 | 100 | PV | TBD | 2019-11-22 | 2019-11-22 |  |  |  | 2019-11-25 | [24 empty] | 2020-04-06 | [13 empty] | Withdrawn
2394463 | New Bedford | 2745 | 133.3 | PV | TBD | 2020-03-18 | 2020-03-31 |  |  |  | 2020-04-20 | [24 empty] | 2020-04-28 | [12 empty] | 2022-02-28 | Online
2407717 | New Bedford | 2745 | 500 | PV & Battery | TBD | 2020-06-01 | 2020-07-13 |  |  |  | 2020-07-22 | [24 empty] | 2022-03-11
4607301 | New Bedford | 2745 | 2125 | PV | TBD | 2020-11-18 | 2020-12-01 |  |  |  | 2020-12-17
5256352 | New Bedford | 2745 | 445 | PV | TBD | 2021-02-18 | 2021-03-05 |  |  |  | 2021-03-24 | [24 empty] | 2021-06-21
ESMAEX-00049 | New Bedford | 2745 | 166.6 | PV | 2-82-82 | 2021-04-14 | 2021-05-12 | [28 empty] | 2021-06-10 | [12 empty] | 2022-04-19 | Online |  |  | Y
ESMAEX-00322 | New Bedford | 2745 | 249.9 | PV | 2-79-404 | 2021-08-17 | 2021-09-02 | [28 empty] | 2022-02-22 | [13 empty] | In Queue |  |  | Y
ESMAEX-00900 | New Bedford | 2745 | 999 | PV | 2-79-404 | 2022-04-06 | 2022-05-04 | [42 empty] | In Queue |  |  | Y
ESMAEX-01001 | New Bedford | 2745 | 199.8 | PV & Battery | 2-82-18 | 2022-06-06 | 2022-06-21 | [42 empty] | In Queue |  |  | Y
ESMAEX-01374 | New Bedford | 2745 | 17.568 | PV | 2-102-608 | 2022-07-13 | 2022-08-01 | [28 empty] | 2022-08-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00009 | New Bedford | 2745 | 73.3 | PV | 2-104-104 | 2021-03-30 | 2021-04-15 | [28 empty] | 2021-06-08 | [12 empty] | 2021-09-22 | Online |  |  | Y
ESMAEX-00250 | New Bedford | 2745 | 15.2 | PV | 2-106-160 | 2021-07-20 | 2021-08-03 | [28 empty] | 2021-08-11 | [12 empty] | 2022-02-01 | Online |  |  | Y
ESMAEX-00340 | New Bedford | 2745 | 50 | PV | 2-103-103 | 2021-08-23 | 2021-09-09 | [28 empty] | 2021-09-13 | [12 empty] | 2022-05-20 | Online |  |  | Y
ESMAEX-01034 | New Bedford | 2745 | 15.2 | PV & Battery | 2-106-161 | 2022-04-07 | 2022-04-28 | [28 empty] | 2022-05-06 | [13 empty] | In Queue |  |  | Y
ESMAEX-01737 | New Bedford | 2745 | 10 | PV & Battery | 2-105-105 | 2022-10-28 | 2022-12-13 | [28 empty] | 2023-01-05 | [13 empty] | In Queue |  |  | Y
2175669 | New Bedford | 2746 | 180 | PV | 2-24-11 | 2016-09-16 | 2016-09-19 | 1 |  | 1 | 2016-10-18 |  | -30473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-25 | 2017-03-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online
2345033 | New Bedford | 2746 | 496 | PV | 2-83-403 | 2017-02-01 | 2017-02-17 | 12 |  | 12 | 2017-02-28 |  | -30565 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
2303220 | New Bedford | 2746 | 86.4 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-05-10 | Online |  | Private
2303221 | New Bedford | 2746 | 57.6 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-29 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-30 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-08-23 | Online |  | Public
2305084 | New Bedford | 2746 | 428 | PV | 2-80-401 | 2018-10-18 | 2018-10-19 | 1 |  | 1 | 2018-11-05 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online |  | Public
2363245 | New Bedford | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 |  |  |  | 2019-10-22 | [38 empty] | Withdrawn
2363249 | New Bedford | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 |  |  |  | 2019-10-22 | [24 empty] | 2020-06-23
2363671 | New Bedford | 2746 | 200 | PV | TBD | 2019-09-23 | 2019-09-25 |  |  |  | 2019-10-22 | [24 empty] | 2020-05-14
2412695 | New Bedford | 2746 | 250 | PV | TBD | 2019-12-30 | 2020-01-21 |  |  |  | 2020-09-07 | [24 empty] | 2020-02-28
2401687 | New Bedford | 2746 | 499 | PV | TBD | 2020-05-18 | 2020-05-20 |  |  |  | 2020-06-10 | [24 empty] | 2020-12-05
2402897 | New Bedford | 2746 | 499 | PV | TBD | 2020-05-28 | 2020-06-01 |  |  |  | 2020-06-19 | [24 empty] | 2020-12-24
4579621 | New Bedford | 2746 | 93.45 | PV | TBD | 2020-10-29 | 2020-11-10 |  |  |  | 2020-12-09 | [24 empty] | 2020-12-15 | [12 empty] | 2021-09-13 | Online
ESMAEX-00153 | New Bedford | 2746 | 120 | PV | 2-82-82 | 2021-05-27 | 2021-06-11 | [28 empty] | 2021-08-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00154 | New Bedford | 2746 | 120 | PV | 2-82-82 | 2021-05-27 | 2021-06-11 | [28 empty] | 2021-08-18 | [13 empty] | In Queue |  |  | Y
ESMAEX-00976 | New Bedford | 2746 | 480 | PV | 2-81-81 | 2022-06-08 | 2022-08-15 | [28 empty] | 2022-11-09 | [13 empty] | In Queue |  |  | Y
ESMAEX-01949 | New Bedford | 2746 | 400 | PV | 2-83-83 | 2023-03-06 | 2023-03-23 | [42 empty] | In Queue |  |  | Y
2123114 | Acton | 2747 | 17.6 | PV | 416-H4 | 2016-01-04 | 2016-01-05 | 1 |  | 1 | 2016-01-13 |  | -30274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-03-03 | [6 empty] | 0 |  | 0 |  |  | 2016-03-24 | Online
2264231 | Dartmouth | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 | 2018-02-23 |  | -30816 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
2264232 | Dartmouth | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-04 | Online
2219177 | Dartmouth | 2747 | 2300 | PV | 2-543-543 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-06 |  | -30633 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-07-27 | 30668 |  | 30668 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-29 | Online
2296559 | Dartmouth | 2747 | 4990 | PV | 2-103-103 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-03 | Online
2210401 | Dartmouth | 2747 | 20.35 | PV | 274-H3 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-12 |  | -30596 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-30 | 2017-06-30 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2234626 | Dartmouth | 2747 | 594 | PV | 2-532-532 | 2017-08-08 | 2017-08-11 | 3 |  | 3 | 2017-09-13 |  | -30702 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-11-15 | 30745 |  | 30745 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2239746 | Dartmouth | 2747 | 997.7 | PV | 2-543-543 | 2017-09-11 | 2017-09-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
2269612 | Dartmouth | 2747 | 1000 | PV | 2-532-532 | 2018-02-02 | 2018-03-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-31 | [7 empty] | 0 |  | 0
2269896 | Dartmouth | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30845 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2270084 | Dartmouth | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30845 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2273508 | Dartmouth | 2747 | 4999 | PV | 2-107-107 | 2018-04-04 | 2018-04-11 | 5 |  | 5 | 2018-04-26 |  | -30860 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-22 | 2018-12-18 | [6 empty] | 0 |  | 0
2298981 | Dartmouth | 2747 | 185 | PV & Battery | 2-525-525 | 2018-08-31 | 2018-09-10 | 6 |  | 6 | 2018-10-01 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0
2305846 | Dartmouth | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2305925 | Dartmouth | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online |  | Private
2323875 | Dartmouth | 2747 | 699.3 | PV | 2-528-528 | 2019-01-17 | 2019-01-22 | 3 |  | 3 | 2019-02-08 |  | -31066 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2341496 | Dartmouth | 2747 | 1000 | PV & Battery | 2-528-528 | 2019-02-25 | 2019-05-16 | 58 |  | 58 | 2019-05-28 |  | -31143 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2334531 | Dartmouth | 2747 | 1000 | PV | 2-528-528 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-12 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2343563 | Dartmouth | 2747 | 6000 | PV | 2-528-528 | 2019-05-06 | 2019-05-29 | 17 |  | 17 | 2019-06-06 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2354849 | Dartmouth | 2747 | 5000 | PV & Battery | TBD | 2019-05-09 | 2019-07-26 |  |  |  | 2019-08-15 | [38 empty] | Withdrawn
4581517 | Dartmouth | 2747 | 200 | PV | TBD | 2020-11-04 | 2020-11-06 |  |  |  | 2020-12-09 | [24 empty] | 2021-05-13 | [12 empty] | 2022-03-15 | Online
4972223 | Dartmouth | 2747 | 200 | PV | TBD | 2021-03-02 | 2021-03-02 |  |  |  | 2021-03-02
ESMAEX-00238 | Dartmouth | 2747 | 148.92 | PV | 2-532-532 | 2021-07-13 | 2021-07-28 | [28 empty] | 2021-09-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-00291 | Dartmouth | 2747 | 499 | PV & Battery | 2-541-541 | 2021-08-06 | 2021-08-24 | [28 empty] | 2022-09-07 | [13 empty] | In Queue |  |  | Y
ESMAEX-00455 | Dartmouth | 2747 | 100 | PV | 2-532-532 | 2021-09-28 | 2022-02-03 | [28 empty] | 2022-06-20 | [13 empty] | In Queue |  |  | Y
ESMAEX-00627 | Dartmouth | 2747 | 4000 | PV & Battery | 2-541-542 | 2021-12-31 | 2022-01-25 | [42 empty] | In Queue |  |  | Y
ESMAEX-00715 | Dartmouth | 2747 | 20000 | Battery | 2-531-531 | 2022-02-16 | 2022-03-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-01400 | Dartmouth | 2747 | 22800 | Battery | 2-531-531 | 2022-08-22 | 2022-12-05 | [42 empty] | In Queue |  |  | Y
ESMAEX-01401 | Dartmouth | 2747 | 22800 | Battery | 2-531-531 | 2022-08-22 | 2022-12-05 | [42 empty] | In Queue |  |  | Y
ESMAEX-01402 | Dartmouth | 2747 | 22800 | Battery | 2-531-531 | 2022-08-22 | 2022-12-05 | [42 empty] | In Queue |  |  | Y
ESMAEX-02043 | Dartmouth | 2747 | 15.2 | PV | TBD | 2023-01-19 | [43 empty] | In Queue |  |  | Y
2351639 | North Dartmouth | 2747 | 150 | PV | TBD | 2019-07-12 | 2019-07-12 |  |  |  | 2019-07-26 | [24 empty] | 2019-08-22 | [12 empty] | 2020-10-16 | Online
2398168 | North Dartmouth | 2747 | 15.2 | PV | 2-532-532 | 2020-03-16 | 2020-04-30 |  |  |  | 2020-05-18 | [24 empty] | 2020-05-28 | [12 empty] | 2021-05-21 | Online
2412130 | North Dartmouth | 2747 | 15.2 | PV | TBD | 2020-07-27 | 2020-08-07 |  |  |  | 2020-08-26 | [24 empty] | 2020-09-03
4615175 | North Dartmouth | 2747 | 35.2 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 |  |  |  | 2020-12-22 | [24 empty] | 2021-01-11 | [12 empty] | 2022-06-17 | Online
4869494 | North Dartmouth | 2747 | 18.6 | PV | TBD | 2021-01-07 | 2021-01-11 |  |  |  | 2021-01-28 | [24 empty] | 2021-04-06 | [12 empty] | 2021-07-28 | Online
ESMAEX-00102 | North Dartmouth | 2747 | 86.4 | PV | 2-533-503 | 2021-05-05 | 2021-05-20 | [28 empty] | 2021-06-10 | [12 empty] | 2022-02-03 | Online |  |  | Y
ESMAEX-00410 | North Dartmouth | 2747 | 15.2 | PV | 2-531-531 | 2021-09-14 | 2021-11-16 | [28 empty] | 2021-11-22 | [12 empty] | 2022-07-12 | Online |  |  | Y
ESMAEX-00480 | North Dartmouth | 2747 | 86.4 | PV | 2-532-532 | 2021-10-07 | 2021-11-09 | [28 empty] | 2021-11-16 | [12 empty] | 2022-07-08 | Online |  |  | Y
ESMAEX-00544 | North Dartmouth | 2747 | 57.6 | PV | 2-532-532 | 2021-10-26 | 2021-11-16 | [28 empty] | 2021-12-22 | [12 empty] | 2022-08-16 | Online |  |  | Y
ESMAEX-00589 | North Dartmouth | 2747 | 20 | PV | 2-532-532 | 2021-11-15 | 2021-12-07 | [28 empty] | 2021-12-15 | [12 empty] | 2022-06-28 | Online |  |  | Y
ESMAEX-01179 | North Dartmouth | 2747 | 10 | PV & Battery | 2-541-541 | 2022-05-13 | 2022-06-06 | [28 empty] | 2022-06-07 | [12 empty] | 2022-11-09 | Online |  |  | Y
ESMAEX-01395 | North Dartmouth | 2747 | 19 | PV & Battery | 2-528-528 | 2022-07-21 | 2022-08-23 | [28 empty] | 2022-09-29 | [13 empty] | In Queue |  |  | Y
ESMAEX-02064 | North Dartmouth | 2747 | 10 | Battery | 2-541-541 | 2023-01-24 | 2023-02-14 | [28 empty] | 2023-02-23 | [13 empty] | In Queue |  |  | Y
2322528 | North Dartmouth | 2747 | 720 | PV | 2-541-541 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-29 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
2340119 | North Dartmouth | 2747 | 999 | PV & Battery | 2-541-541 | 2019-03-21 | 2019-05-07 | 33 |  | 33 | 2019-05-17 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2390961 | North Dartmouth | 2747 | 150 | PV | TBD | 2020-03-09 | 2020-03-09 |  |  |  | 2020-03-23 | [24 empty] | 2020-04-14 | [12 empty] | 2021-07-19 | Online
2402135 | North Dartmouth | 2747 | 149.3 | PV | TBD | 2020-05-28 | 2020-05-28 |  |  |  | 2020-06-12 | [24 empty] | 2020-11-23
2270087 | North Dartmouth | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-31 | [7 empty] | 0 |  | 0
2117201 | North Dartmouth | 2747 | 19.3 | PV | 2-107-107 | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-24 |  | -30260 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2016-01-03 | Online |  | PRIVATE
2157001 | North Dartmouth | 2747 | 16.25 | PV | 2-541-541 | 2016-06-01 | 2016-06-20 | 13 |  | 13 | 2016-07-07 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-09-12 | [6 empty] | 0 |  | 0 |  |  | 2016-09-26 | Online |  | PRIVATE
2168995 | North Dartmouth | 2747 | 40 | PV | 2-541-542 | 2016-07-28 | 2016-08-29 | 22 |  | 22 | 2016-09-13 |  | -30448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-30 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online |  | PRIVATE | Y
2184042 | North Dartmouth | 2747 | 22 | PV | 2-523-523 | 2016-07-21 | 2016-10-28 | 71 |  | 71 | 2016-12-01 |  | -30505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-13 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online |  | PRIVATE
2178419 | North Dartmouth | 2747 | 499.5 | PV | 2-533-530 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-01 |  | -30483 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-02 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online
2223159 | North Dartmouth | 2747 | 100.8 | PV | 2-532-532 | 2017-05-22 | 2017-05-31 | 6 |  | 6 | 2017-06-30 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
2217262 | North Dartmouth | 2747 | 210 | Fuel Cell | 2-531-531 | 2017-05-02 | 2017-05-02 | 0 |  | 0 | 2017-05-25 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
2308643 | North Dartmouth | 2747 | 18.15 | PV | 2-532-532 | 2018-11-16 | 2018-12-03 | 11 |  | 11 | 2018-12-03 | 2018-12-06 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-24 | Online |  | Private
2360141 | North Dartmouth | 2747 | 200 | PV | TBD | 2019-09-03 | 2019-09-03 |  |  |  | 2019-09-19 | [24 empty] | 2019-12-16 | [12 empty] | 2021-05-12 | Online
2193440 | North Dartmouth | 2747 | 15.2 | PV | 2-107-107 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-01-04 |  | -30267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2193439 | North Dartmouth | 2747 | 15.34 | PV | 2-541-541 | 2016-11-30 | 2016-12-05 | 3 |  | 3 | 2016-01-04 |  | -30267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2352731 | North Dartmouth | 2747 | 516 | PV | TBD | 2019-06-24 | 2019-07-19 |  |  |  | 2019-08-02 | [24 empty] | 2020-02-24 | [13 empty] | Withdrawn
ESMAEX-00463 | North Dartmouth | 2747 | 4990 | PV & Battery | 2-107-107 | 2021-11-10 | 2021-12-14 | [42 empty] | In Queue |  |  | Y
ESMAEX-01978 | North Dartmouth | 2747 | 250 | PV | 2-70-502 | 2023-01-06 | 2023-02-02 | [28 empty] | 2023-03-09 | [13 empty] | In Queue |  |  | Y
2241682 | Dartmouth | 2748 | 22.8 | PV | 2-528-528 | 2017-10-02 | 2017-10-10 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-09 | Online
2290691 | Dartmouth | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | 4 |  | 4 | 2018-08-07 |  | -30933 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-06 | 2018-09-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online |  | Private
2308512 | Dartmouth | 2748 | 17.4 | PV | 2-528-528 | 2018-11-14 | 2018-11-30 | 12 |  | 12 | 2018-11-30 | 2018-12-11 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 | 2018-12-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-30 | Online |  | Private
2341375 | Dartmouth | 2748 | 200 | PV | 2-528-528 | 2019-05-09 | 2019-05-16 |  |  |  | 2019-05-28
5273833 | Dartmouth | 2748 | 15 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 |  |  |  | 2021-03-23 | [24 empty] | 2021-04-14 | [12 empty] | 2021-09-08 | Online
5447348 | Dartmouth | 2748 | 27.28 | PV & Battery | TBD | 2021-03-17 | [42 empty] | 2021-10-14 | Online
ESMAEX-00893 | Dartmouth | 2748 | 220 | PV | 2-53-65 | 2022-03-10 | 2022-05-31 | [28 empty] | 2022-07-19 | [13 empty] | In Queue |  |  | Y
ESMAEX-01244 | Dartmouth | 2748 | 500 | PV | 2-53-65 | 2022-10-04 | 2022-10-27 | [42 empty] | In Queue |  |  | Y
ESMAEX-01745 | Dartmouth | 2748 | 210 | PV | 2-60-63 | 2022-11-01 | 2022-12-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-01746 | Dartmouth | 2748 | 195 | PV | TBD | 2022-11-01 | 2022-12-07 | [42 empty] | In Queue |  |  | Y
ESMAEX-01747 | Dartmouth | 2748 | 210 | PV | 2-60-63 | 2022-11-01 | 2022-12-07 | [42 empty] | In Queue |  |  | Y
5273781 | Lincoln | 2748 | 15.2 | PV | TBD | 2021-03-09 | 2021-03-09 |  |  |  | 2021-03-23 | [24 empty] | 2021-12-06 | [12 empty] | 2021-06-15 | Online
2180485 | North Dartmouth | 2748 | 39.6 | PV | 2-524-524 | 2016-09-22 | 2016-10-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-08 | Online |  | PRIVATE
4698354 | South Dartmouth | 2748 | 15.2 | PV | TBD | 2020-12-14 | 2020-12-29 |  |  |  | 2021-01-13 | [24 empty] | 2021-03-09 | [12 empty] | 2021-12-07 | Online
4870032 | South Dartmouth | 2748 | 18 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-03-25
ESMAEX-00600 | South Dartmouth | 2748 | 48.03 | PV & Battery | 2-524-524 | 2021-11-17 | 2022-01-05 | [28 empty] | 2022-01-10 | [12 empty] | 2022-09-09 | Online |  |  | Y
ESMAEX-00785 | South Dartmouth | 2748 | 22.8 | PV | 2-524-524 | 2022-02-01 | 2022-02-24 | [28 empty] | 2022-03-21 | [12 empty] | 2022-07-19 | Online |  |  | Y
ESMAEX-00863 | South Dartmouth | 2748 | 4.64 | PV | 2-528-528 | 2022-02-28 | 2022-03-11 | [28 empty] | 2022-04-14 | [12 empty] | 2022-10-12 | Online |  |  | Y
ESMAEX-01228 | South Dartmouth | 2748 | 15.2 | PV | 2-528-528 | 2022-05-26 | 2022-06-28 | [28 empty] | 2022-07-05 | [12 empty] | 2022-10-27 | Online |  |  | Y
ESMAEX-01780 | South Dartmouth | 2748 | 17.6 | PV | 2-53-65 | 2022-11-08 | 2022-11-16 | [28 empty] | 2022-11-17 | [12 empty] | 2023-02-13 | Online |  |  | Y
ESMAEX-02044 | South Dartmouth | 2748 | 6.59 | PV & Battery | 2-2-505 | 2023-01-20 | 2023-02-07 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02046 | South Dartmouth | 2748 | 10 | Battery | 2-528-528 | 2023-01-20 | 2023-02-10 | [28 empty] | 2023-02-23 | [13 empty] | In Queue |  |  | Y
ESMAEX-02072 | South Dartmouth | 2748 | 3.8 | PV & Battery | 2-2-505 | 2023-01-25 | 2023-02-09 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
2398833 | South Dartmouth | 2748 | 20.8 | PV & Battery | 2-53-65 | 2020-04-30 | 2020-05-05 |  |  |  | 2020-05-20
4632856 | South Dartmouth | 2748 | 43.92 | PV | TBD | 2020-12-07 | 2020-12-07 |  |  |  | 2020-12-29 | [24 empty] | 2021-01-06 | [12 empty] | 2021-07-15 | Online
5392200 | South Dartmouth | 2748 | 21.4 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 |  |  |  | 2021-04-08 | [24 empty] | 2021-04-28 | [13 empty] | Withdrawn
ESMAEX-00890 | South Dartmouth | 2748 | 220 | PV | 2-53-65 | 2022-03-08 | 2022-03-24 | [28 empty] | 2022-04-25 | [12 empty] | 2023-01-04 | Online |  |  | Y
2181937 | South Dartmouth | 2748 | 57.6 | PV | 2-2-505 | 2016-10-04 | 2016-10-20 | 12 |  | 12 | 2016-11-17 |  | -30495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-21 | Online |  | PRIVATE
2268194 | Westport | 2748 | 5000 | PV & Battery | 2-523-523 | 2018-02-15 | 2018-02-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0
2274408 | Freetown | 2770 | 1000 | PV | 3-703-703 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-02 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2292307 | Rochester | 2770 | 16.7 | PV | 3-702-702 | 2018-08-08 | 2018-08-15 | 5 |  | 5 | 2018-08-16 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-21 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online |  | Private
2325833 | Rochester | 2770 | 20 | PV | 3-703-703 | 2019-02-06 | 2019-02-11 | 3 |  | 3 | 2019-02-20 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online
2336283 | Rochester | 2770 | 17.52 | PV | 3-85-85 | 2019-04-09 | 2019-04-11 | 2 |  | 2 | 2019-04-25 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-11 | Online
2313788 | Rochester | 2770 | 496.6 | PV | 3-85-85 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
4489081 | Rochester | 2770 | 22 | PV | TBD | 2020-10-15 | 2020-10-19 |  |  |  | 2020-11-17 | [24 empty] | 2020-10-25 | [12 empty] | 2021-02-09 | Online
2260703 - A | Rochester | 2770 | 2000 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30799 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
2311484 | Rochester | 2770 | 19 | PV | 3-703-703 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 | 2018-12-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2131315 | Rochester | 2770 | 15.2 | PV | 3-702-702 | 2016-02-04 | 2016-02-12 | 6 |  | 6 | 2016-02-29 |  | -30307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-20 | 2016-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2170422 | Rochester | 2770 | 21.9 | PV | 5-702-702 | 2016-08-25 | 2016-08-29 | 2 |  | 2 | 2016-09-20 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2189508 | Rochester | 2770 | 3300 | PV | 3-702-702 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-28 |  | -30524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-04 | [7 empty] | 0 |  | 0
2260703 - B | Rochester | 2770 | 540 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30799 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2278508 | Rochester | 2770 | 3345 | PV & Battery | 3-702-702 | 2018-05-14 | 2018-05-15 | 1 |  | 1 | 2018-05-29 |  | -30883 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2290690 | Rochester | 2770 | 4000 | PV | 3-702-702 | 2018-07-18 | 2018-07-23 | 3 |  | 3 | 2018-08-07 |  | -30933 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2296372 | Rochester | 2770 | 4998 | PV & Battery | 3-703-703 | 2018-08-14 | 2018-08-24 | 8 |  | 8 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
pp02295853 | Rochester | 2770 | 2000 | PV & Battery | 3-85-85 | 2021-01-17 | 2021-01-17 | 0 |  | 0 | 2021-03-22 |  | -31617 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2298768 | Rochester | 2770 | 1782 | PV | 3-702-702 | 2018-08-28 | 2018-09-07 | 8 |  | 8 | 2018-09-28 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2299343 | Rochester | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-06 | 2018-09-11 | 3 |  | 3 | 2018-10-02 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2299350 | Rochester | 2770 | 1250 | PV & Battery | 5-702-702 | 2018-09-06 | 2018-09-12 | 4 |  | 4 | 2018-10-02 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2300058 | Rochester | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30975 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2300060 | Rochester | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30975 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2300709 | Rochester | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-10 |  | -30979 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2302146 | Rochester | 2770 | 1000 | PV & Battery | 3-702-702 | 2018-09-20 | 2018-09-21 | 1 |  | 1 | 2018-10-18 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2306598 | Rochester | 2770 | 1750 | PV | 3-703-703 | 2018-10-31 | 2018-11-15 | 11 |  | 11 | 2018-11-15 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2307638 | Rochester | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2328012 | Rochester | 2770 | 15000 | PV | 3-85-85 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-03-04 |  | -31082 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
ISO NE | Rochester | 2770 | 15000 | PV & Battery | 3-703-703 | 2018-12-18 | 2018-12-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2320446 | Rochester | 2770 | 2900 | PV | 3-703-703 | 2018-12-21 | 2018-12-26 | 3 |  | 3 | 2019-01-15 |  | -31048 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2320623 | Rochester | 2770 | 4890 | PV & Battery | 3-703-703 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2335506 | Rochester | 2770 | 25 | PV | 3-702-702 | 2019-03-20 | 2019-04-02 | 9 |  | 9 | 2019-05-03 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2363427 | Rochester | 2770 | 3500 | PV & Battery | TBD | 2019-09-19 | 2019-09-24 |  |  |  | 2019-10-09
2369465 | Rochester | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 |  |  |  | 2019-11-20 | [24 empty] | 2020-04-06 | [13 empty] | Withdrawn
2369675 | Rochester | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 |  |  |  | 2019-11-29 | [24 empty] | 2020-04-06
2381700 | Rochester | 2770 | 21.4 | PV | TBD | 2019-11-06 | 2019-12-30 |  |  |  | 2020-01-16 | [24 empty] | 2020-02-12 | [13 empty] | Withdrawn
2408783 | Rochester | 2770 | 4999 | PV & Battery | TBD | 2020-07-07 | 2020-07-13 |  |  |  | 2020-07-30
4590784 | Rochester | 2770 | 20 | PV | TBD | 2020-11-06 | 2020-11-13 |  |  |  | 2020-12-11 | [24 empty] | 2020-12-24 | [12 empty] | 2021-06-11 | Online
4669412 | Rochester | 2770 | 149.3 | PV | TBD | 2020-12-01 | 2020-12-14 |  |  |  | 2021-01-05 | [24 empty] | 2021-01-14 | [13 empty] | Withdrawn
4921323 | Rochester | 2770 | 25.2 | PV & Battery | TBD | 2020-12-14 | 2021-01-20 |  |  |  | 2021-02-02 | [24 empty] | 2021-07-26
4869940 | Rochester | 2770 | 250 | PV | TBD | 2020-12-31 | 2021-01-11 |  |  |  | 2021-02-02 | [24 empty] | 2021-04-22
2083435 | Rochester | 2770 | 20.52 | PV | 3-702-702 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
ESMAEX-00421 | Rochester | 2770 | 20 | PV | 3-702-702 | 2021-09-17 | 2021-10-07 | [28 empty] | 2022-02-08 | [12 empty] | 2022-07-06 | Online |  |  | Y
ESMAEX-00574 | Rochester | 2770 | 10.03 | PV | 3-703-703 | 2021-11-09 | 2021-11-23 | [28 empty] | 2021-12-30 | [12 empty] | 2022-03-03 | Online |  |  | Y
ESMAEX-01778 | Rochester | 2770 | 15.2 | PV & Battery | 3-702-702 | 2022-11-08 | 2022-11-16 | [28 empty] | 2022-11-21 | [12 empty] | 2023-03-16 | Online |  |  | Y
ESMAEX-02342 | Rochester | 2770 | 15.3 | PV | 3-702-702 | 2023-04-04 | 2023-04-20 | [42 empty] | In Queue |  |  | Y
ESMAEX-02368 | Rochester | 2770 | 4999 | PV | TBD | 2023-04-11 | [43 empty] | In Queue |  |  | Y
ESMAEX-02409 | Rochester | 2770 | 4999 | PV | TBD | 2023-04-24 | [43 empty] | In Queue |  |  | Y
ESMAEX-02412 | Rochester | 2770 | 4999 | PV | TBD | 2023-04-24 | [43 empty] | In Queue |  |  | Y
2289828 | Westport | 2770 | 4498 | PV & Battery | 2-532-532 | 2018-04-30 | 2018-07-20 | 59 |  | 59 | 2018-08-15 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2247819 | Wareham | 2777 | 8300 | PV & Battery | 3-83-83 | 2017-11-09 | 2017-11-23 | 9 |  | 9 | 2017-12-06 |  | -30760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-12-16 | Online
2097455 | Westport | 2790 | 32.85 | PV | 2-523-523 | 2015-09-22 | 2015-09-24 | 2 |  | 2 | 2015-10-02 |  | -30201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-10-29 | 2015-11-30 | [6 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online |  | Private | Y
2190239 | Westport | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online |  | PRIVATE
2227530 | Westport | 2790 | 480 | PV | 2-523-523 | 2017-05-09 | 2017-06-28 | 35 |  | 35 | 2017-07-31 |  | -30671 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
2346438 | Westport | 2790 | 20 | PV | TBD | 2019-05-29 | 2019-06-10 |  |  |  | 2019-06-25 | [24 empty] | 2019-08-09 | [12 empty] | 2019-11-04 | Online
2308001 | Westport | 2790 | 37.8 | PV | 2-532-532 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
2319812 | Westport | 2790 | 22.1 | PV | 2-532-532 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
2243995 | Westport | 2790 | 2400 | PV | 2-532-532 | 2017-10-04 | 2017-10-13 | 6 |  | 6 | 2017-11-06 |  | -30739 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-04-12 | 30849 |  | 30849 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-14 | Online
2406662 | Westport | 2790 | 19 | PV | 2-523-523 | 2020-06-09 | 2020-06-29 |  |  |  | 2020-07-20 | [24 empty] | 2020-07-27 | [12 empty] | 2021-04-05 | Online
2237335 | Westport | 2790 | 268 | PV | 2-532-532 | 2017-09-06 | 2017-09-14 | 6 |  | 6 | 2017-09-29 | 2017-10-16 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-12-27 | [6 empty] | 0 |  | 0
2190240 | Westport | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2200167 | Westport | 2790 | 15.2 | PV | 2-523-523 | 2017-01-11 | 2017-01-20 | 6 |  | 6 | 2017-02-08 |  | -30552 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2228336 | Westport | 2790 | 2000 | PV | 2-524-524 | 2017-07-03 | 2017-07-11 | 5 |  | 5 | 2017-08-03 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 |  | -30691 |  | 0 |  |  | 0 |  | 0 | 2017-12-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2274155 | Westport | 2790 | 4500 | PV | 2-532-532 | 2018-03-02 | 2018-04-15 | 30 |  | 30 | 2018-05-01 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
2274649 | Westport | 2790 | 8300 | PV & Battery | 2-523-523 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
2277112 | Westport | 2790 | 8300 | PV & Battery | 2-522-522 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30875 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
2281069 | Westport | 2790 | 995 | Gas Turbine | 2-523-523 | 2018-05-16 | 2018-05-30 | 10 |  | 10 | 2018-06-08 |  | -30891 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2283036 | Westport | 2790 | 2000 | PV | 2-523-523 | 2018-05-23 | 2018-06-13 | 15 |  | 15 | 2018-06-21 |  | -30900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2285715 | Westport | 2790 | 2200 | PV & Battery | 33-H3 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-09 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2287931 | Westport | 2790 | 4950 | PV | 2-522-522 | 2018-06-29 | 2018-07-03 | 2 |  | 2 | 2018-07-23 |  | -30922 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
2291742 | Westport | 2790 | 500 | PV | 2-522-522 | 2018-07-23 | 2018-07-27 | 4 |  | 4 | 2018-08-14 |  | -30938 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2297080 | Westport | 2790 | 1000 | PV | 2-532-532 | 2018-08-20 | 2018-08-31 | 9 |  | 9 | 2018-09-19 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2296371 | Westport | 2790 | 2000 | PV | 2-532-532 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-18 |  | -30963 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2304259 | Westport | 2790 | 5000 | PV & Battery | 2-523-523 | 2018-10-02 | 2018-10-18 | 12 |  | 12 | 2018-11-01 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2307639 | Westport | 2790 | 1500 | PV | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2307641 | Westport | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private
2313433 | Westport | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-29 | 2018-12-04 | 3 |  | 3 | 2018-12-19 |  | -31029 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2323699 | Westport | 2790 | 72 | PV | 2-532-532 | 2019-01-22 | 2019-01-31 | 7 |  | 7 | 2019-02-05 |  | -31063 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
2381437 | Westport | 2790 | 4000 | PV & Battery | TBD | 2019-11-19 | 2019-12-30 |  |  |  | 2020-01-14
2383646 | Westport | 2790 | 4000 | PV & Battery | TBD | 2019-12-20 | 2020-01-08 |  |  |  | 2020-02-04
4887097 | Westport | 2790 | 23.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 |  |  |  | 2021-02-05 | [24 empty] | 2021-04-30
ESMAEX-00104 | Westport | 2790 | 20 | PV | 2-532-532 | 2021-05-05 | 2021-06-04 | [28 empty] | 2021-06-16 | [12 empty] | 2021-09-24 | Online |  |  | Y
ESMAEX-00628 | Westport | 2790 | 23.7 | PV & Battery | 2-522-522 | 2021-11-29 | 2021-12-29 | [28 empty] | 2022-01-14 | [13 empty] | In Queue |  |  | Y
ESMAEX-00630 | Westport | 2790 | 10 | Battery | 2-523-523 | 2021-11-30 | 2022-01-20 | [28 empty] | 2022-01-25 | [12 empty] | 2022-04-13 | Online |  |  | Y
ESMAEX-00886 | Westport | 2790 | 5.12 | Battery | 2-523-523 | 2022-03-07 | 2022-07-01 | [28 empty] | 2022-07-06 | [12 empty] | 2023-01-09 | Online |  |  | Y
ESMAEX-01953 | Westport | 2790 | 7.6 | PV & Battery | 2-523-523 | 2023-01-03 | 2023-01-23 | [28 empty] | 2023-02-13 | [13 empty] | In Queue |  |  | Y
ESMAEX-02358 | Westport | 2790 | 1350 | PV | TBD | 2023-04-08 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
ESMAEX-02359 | Westport | 2790 | 1200 | PV | TBD | 2023-04-08 | 2023-04-11 | [42 empty] | In Queue |  |  | Y
4696273 | Mattapoisett | 2793 | 2500 | PV & Battery | TBD | 2020-11-04 | 2020-11-25 |  |  |  | 2021-01-13
2305372 | Winchester | 2890 | 50 | PV | 211-H10 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30998 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online |  | Private
2196392 | Rochester | 3180 | 3180 | PV | 3-702-702 | 2016-12-12 | 2016-12-15 | 3 |  | 3 | 2017-01-12 |  | -30534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-26 | 2017-06-22 | -260 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | [7 empty] | 0 |  | 0 | [6 empty] | Y
2350166 | Rochester | 3180 | 0 | PV & Battery | 3-702-702 | 2019-07-03 | 2019-07-10 |  |  |  | 2019-07-17 | [38 empty] | Withdrawn
2363669 | Harwich | 6245 | 210 | PV | 4-95A-597 | 2019-09-13 | 2019-09-19 |  |  |  | 2019-10-09 | [24 empty] | 2019-12-02 | [12 empty] | 2021-07-21 | Online
2298087 | Marion | 17054 | 462 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2298090 | Marion | 17054 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2298091 | Marion | 17054 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2298092 | Marion | 17054 | 1254 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30969 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2206239 | Arlington | 20474 | 16.45 | PV | 211-H11 | 2017-03-01 | 2017-03-03 | 2 |  | 2 | 2017-03-17 |  | -30578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | PRIVATE
2399599 | Harwich | 2645 | 240 | PV | TBD | 2020-04-29 | 2020-05-13 |  |  |  | 2020-05-29 | [24 empty] | 2020-07-21
2171656 | Hopkinton |  | 433 | PV | 126-H1 | 2016-09-01 | 2016-09-06 | 3 |  | 3 | 2016-09-29 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | 2016-11-17 | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  |  | In Queue
1651 | South Dartmouth |  | 1650 | Wind | 2-53-65 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | Y
2238 | Plymouth | 1606 | 95 | PV | 3-12-12 | 2012-08-29 | 2012-09-05 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-09-21 | Private | Y
2015313 | Framingham | 1701 | 500 | PV | 433-H11 | 2014-07-22 | 2014-07-23 | 1 | 0 | 1 | 2014-07-25 | 2014-08-05 | 7 | 73 | -66 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2015-01-27 | 2015-06-19 | No | EXP | 30 | 2015-05-27 | 2015-05-27 | 0 |  | 0 |  | 2015-06-16 | 2015-07-08 | Online |  | Private
2012062 | Framingham | 1701 | 500 | PV | 278-H2 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-06 | 2015-03-02 | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-02 | 2015-09-21 | Online |  | Gov't
2043236 | Framingham | 1701 | 524 | PV | 433-H3 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-19 | 2015-03-05 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 | 2015-09-14 | 2016-01-15 | No | EXP | 30 | 2015-10-30 | 2015-10-30 | 0 |  | 0 |  | 2016-02-03 | 2016-01-15 | Online |  | Private
2054091 | Framingham | 1701 | 322 | PV | 433-H3 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | 2015-02-11 |  | -30034 | 145 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-14 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-07-23 | Online |  | Private
2051390 | Framingham | 1701 | 17.6 | PV | 433-H4 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2154503 | Framingham | 1701 | 105 | PV | 433-H3 | 2016-06-22 | 2016-06-23 | 1 | 2 | -1 | 2016-06-28 | 2016-07-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2154699 | Framingham | 1701 | 105 | PV | 433-H3 | 2016-06-23 | 2016-06-24 | 1 | 2 | -1 | 2016-07-05 | 2016-07-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2328190 | Framingham | 1701 | 57 | PV | TBD | 2019-03-05 | 2019-11-25 | 183 | 182 | 1 | 2019-11-25 | 2019-12-10 | 10 | 0 | 10 | [17 empty] | 0 | 0 | 0 | 2019-12-20 |  | 2019-10-06 | No | EXP | 30 | [7 empty] | 2022-11-21 | Online |  | Private | N
2398893 | Framingham | 1701 | 0 |  | TBD | 2020-05-20 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-28 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1297 | Framingham | 1701 | 100 | PV | 433-H4 | 2009-06-10 | 2009-06-11 | 1 | 1 | 0 | 2009-06-11 | 2009-07-01 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online |  | Private | Y
1636 | Framingham | 1701 | 2000 | Diesel | Sta 175 | 2010-06-16 | 2010-06-18 | 2 | 2 | 0 | 2010-06-18 | 2010-07-21 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-08 |  | 2010-11-10 | Online |  | Private | Y
1737 | Framingham | 1701 | 82 | PV | 455-H5 | 2010-12-20 | 2011-01-05 | 12 | 11 | 1 | 2011-01-05 | 2011-02-02 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online |  | Gov't | Y
1738 | Framingham | 1701 | 26 | PV | 455-H5 | 2010-12-20 | 2011-01-26 | 27 | 25 | 2 | 2011-01-26 | 2011-03-01 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-03 |  | 2011-04-21 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  | 2011-12-29 | Online |  | Private | Y
2288 | Framingham | 1701 | 25 | PV | 433-H4 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-11-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-24 | Online |  | Private | Y
2443 | Framingham | 1701 | 75 | Natural Gas | 342-H4 | 2013-09-20 | 2013-09-30 | 6 | 4 | 2 | 2013-10-01 |  | -29678 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-29 | Online |  | Private | Y
2408 | Framingham | 1701 | 46 | PV | 455-H5 | 2013-06-20 | 2013-08-20 | 43 | 41 | 2 | 2013-08-20 |  | -29648 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-03 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online |  | Private | Y
1708 | Framingham | 1701 | 500 | PV | 433-H4 | 2010-10-26 | 2010-10-28 | 2 | 0 | 2 | 2010-11-08 | 2010-11-24 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-29 |  | 2010-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1716 | Framingham | 1701 | 50 | PV | 342-H4 | 2010-11-15 | 2010-11-22 | 5 | 2 | 3 | 2010-11-24 | 2010-12-16 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2010-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1873 | Framingham | 1701 | 225 | PV | 433-H8 | 2011-08-03 | 2012-09-10 | 288 | 287 | 1 | 2012-09-10 |  | -29402 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2431 | Framingham | 1701 | 250 | PV | 433-H4 | 2013-08-13 | 2013-08-30 | 13 | 11 | 2 | 2013-08-30 |  | -29656 | 0 | 0 | 2013-11-07 | 2013-11-25 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1316 | Framingham | 1701 | 75 | PV | 274-H4 | 2009-06-23 | 2009-07-01 | 6 | 6 | 0 | 2009-07-02 |  | -28570 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-06-23 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1985681 | Framingham | 1702 | 27.6 | PV | 240-H4 | 2014-01-30 | 2014-01-30 | 0 | 0 | 0 | 2014-02-05 | 2014-02-26 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-20 | 2014-08-25 | 2014-09-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-08-22 | 2014-08-22 | Online |  | Private
2006363 | Framingham | 1702 | 120 | PV | 274-H4 | 2014-05-16 | 2014-06-03 | 12 | 0 | 12 | 2014-06-06 | 2014-07-01 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 |  | 2015-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-11-21 | Online |  | Private
2029290 | Framingham | 1702 | 42.5 | PV | 240-H4 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-31 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-27 | Online |  | Private
2072250 | Framingham | 1702 | 4279 | PV | 274-H4 | 2015-05-29 | 2015-05-30 | 1 | 0 | 1 | 2015-06-05 | 2016-01-27 | 168 | 158 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-23 | 2016-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-18 | Online |  | Private
2131138 | Framingham | 1702 | 60 | WIND | 240-H4 | 2016-02-26 | 2016-02-29 | 1 | 0 | 1 | 2016-03-03 | 2016-04-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-10-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2137840 | Framingham | 1702 | 219 | PV | 455-H5 | 2016-03-31 | 2016-04-01 | 1 | 0 | 1 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-12 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2399085 | Framingham | 1702 | 22 | PV | TBD | 2020-05-21 |  | 2 | 0 | 2 | 2020-05-26 | 2020-06-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-29 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2052167 | Framingham | 1702 | 15.2 | PV | 455-H3 | 2015-01-29 | 2015-01-29 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2411344 | Framingham | 1702 | 573 | PV | TBD | 2020-08-18 | 2020-09-09 | 15 | 0 | 15 | 2020-09-14 |  | 77 | 0 | 77 | [20 empty] | 2021-03-25 |  | 2020-12-01 | TBD |  | 30 | [8 empty] | In Queue |  | Gov't
1534 | Framingham | 1702 | 63 | PV | 240-H4 | 2009-12-16 | 2009-12-22 | 4 | 2 | 2 | 2009-12-23 | 2010-01-04 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-11 |  | 2010-03-11 | Online |  | Private | Y
1469 | Framingham | 1702 | 20 | PV | 2404 | 2009-10-13 | 2009-10-23 | 8 | 7 | 1 | 2009-10-23 | 2009-12-16 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-11-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-02 |  | 2010-06-02 | Online |  | Private | N
1588 | Framingham | 1702 | 60 | Natural Gas | 2401 | 2010-03-12 | 2010-03-24 | 8 | 8 | 0 | 2010-03-25 | 2010-04-07 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-10 |  | 2010-06-10 | Online |  | Private | Y
1966 | Framingham | 1702 | 725 | PV | 2408 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-01-31 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Gov't | Y
2144 | Framingham | 1702 | 500 | PV | 455-H6 | 2012-06-01 | 2012-06-14 | 9 | 7 | 2 | 2012-06-14 | 2012-07-19 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-26 | Online |  | Private | Y
2302 | Framingham | 1702 | 4400 | PV | 274-H4 | 2012-11-13 | 2012-11-19 | 4 | 3 | 1 | 2012-11-19 | 2013-02-06 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Online |  | Private | Y
2289 | Framingham | 1702 | 20 | PV | 278-H1 | 2012-10-26 | 2012-11-29 | 24 | 24 | 0 | 2012-11-29 | 2013-02-06 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-29 | Online |  | Private | Y
2291 | Framingham | 1702 | 20 | PV | 455-H5 | 2012-10-31 | 2012-11-27 | 19 | 19 | 0 | 2012-11-27 | 2012-12-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-13 | Online |  | Private | Y
2338 | Framingham | 1702 | 190 | PV | 240-H3 | 2013-01-28 | 2013-01-29 | 1 | 0 | 1 | 2013-01-29 | 2013-02-11 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-11 |  | 2013-02-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online |  | Private | Y
2337 | Framingham | 1702 | 150 | PV | 433-H8 | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-02-27 | 2013-04-08 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-05 | Online |  | Private | Y
2404 | Framingham | 1702 | 18 | PV | 433-H12 | 2013-06-17 | 2013-06-19 | 2 | 1 | 1 | 2013-06-19 | 2013-08-13 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-17 | Online |  | Private | Y
2439 | Framingham | 1702 | 40 | PV | 433-H8 | 2013-09-16 | 2013-10-02 | 12 | 12 | 0 | 2013-10-02 |  | -29679 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-10-21 | Online | 2013-12-09 | Private | Y
1977 | Framingham | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-22 | 1 | 0 | 1 | 2011-11-23 | 2012-01-03 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  |  | Withdrawn |  | Private | Y
1945 | Framingham | 1702 | 875 | PV | 274-H1 | 2011-10-20 | 2011-10-21 | 1 | 1 | 0 | 2011-10-21 | 2012-01-19 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  |  | Withdrawn |  | Private | Y
1943 | Framingham | 1702 | 750 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1944 | Framingham | 1702 | 875 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1976 | Framingham | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-28 | 5 | 4 | 1 | 2011-11-28 | 2012-01-23 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2416 | Framingham | 1702 | 1000 | PV | 455-H6 | 2013-07-09 | 2013-07-22 | 9 | 7 | 2 | 2013-07-25 |  | -29630 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-21 |  | 2013-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2432 | Framingham | 1702 | 1364 | PV | 278-H2 | 2013-08-21 | 2013-08-30 | 7 | 6 | 1 | 2013-08-30 |  | -29656 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-15 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2034 | Bedford | 1703 | 13 | PV | 533-H8 | 2012-01-16 | 2012-02-02 | 13 | 5 | 8 | 2012-02-02 | 2012-03-16 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | 131 | 0 | 131 |  |  | 0 | 0 | 0 | 2014-07-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-05-28 | Gov't | N
2013623 | Acton | 1720 | 126 | PV | 416-H9 | 2014-07-18 | 2014-07-22 | 2 | 0 | 2 | 2014-07-28 | 2014-07-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-10 | Online |  | Private
2014462 | Acton | 1720 | 81 | PV | 416-H1 | 2014-07-23 | 2014-07-28 | 3 | 0 | 3 | 2014-08-19 | 2014-10-01 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 |  | 2015-10-01 | TBD | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2015-09-17 | 2015-09-17 | Online |  | Gov't
2144430 | Acton | 1720 | 18 | PV | 416-H4 | 2016-05-02 | 2016-05-03 | 1 | 0 | 1 | 2016-05-13 | 2016-05-27 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-01 |  | 2016-12-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-31 | Online |  | Private
2250671 | Acton | 1720 | 66 | PV | 416-H4 | 2017-11-08 | 2017-11-17 | 7 |  | 7 | 2017-12-08 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-30 | Online
2090728 | Acton | 1720 | 420 | PV | 416-H4 | 2015-08-14 | 2015-09-01 | 12 | 0 | 12 | 2015-09-01 | 2015-09-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2093910 | Acton | 1720 | 1940 | PV | 416-H1 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-08 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2114164 | Acton | 1720 | 17 | PV | 416-H8 | 2015-12-09 | 2015-12-11 | 2 | 0 | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2084724 | Acton | 1720 | 2000 | PV | 416-H2 | 2015-07-29 | 2015-08-03 | 3 | 0 | 3 | 2015-08-05 | 2016-01-20 | 120 | 108 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-22 | No | EXP | 30 | 2016-05-11 |  | -30359 |  | 0 |  | 2016-06-08 |  | Withdrawn |  | Private | N
2093456 | Acton | 1720 | 750 | PV | 416-H1 | 2015-09-10 | 2015-09-14 | 2 | 0 | 2 | 2015-09-15 | 2016-01-26 | 95 | 54 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-07-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2134405 | Acton | 1720 | 990 | PV | 416-H4 | 2016-03-15 | 2016-04-20 | 26 | 39 | -13 | 2016-03-22 | 2016-05-13 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2102432 | Acton | 1720 | 830 | PV | 416-H1 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-27 | 2016-08-01 | 199 | 26 | 173 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 |  | 2016-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2407706 | Acton | 1720 | 15 | PV & Battery | 416-H4 | 2020-07-21 |  | 12 | 0 | 12 | 2020-08-06 | 2020-11-12 | 67 | 0 | 67 | [20 empty] | 2020-10-21 |  | 2020-12-30 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2136976 | Acton | 1720 | 990 | PV | 416-H4 | 2016-03-28 | 2016-03-29 | 1 | 0 | 1 | 2016-03-29 |  | -30328 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-04-27 | Private
2158995 | Acton | 1720 | 294 | PV | 416-H4 | 2016-07-18 | 2016-07-25 | 5 | 0 | 5 | 2016-07-28 |  | -30415 | 14 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-02 | Private
2284261 | Acton | 1720 | 0 |  | TBD | 2018-06-28 |  | 449 | 0 | 449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-11-23 | TBD | TBD | [9 empty] | Withdrawn |  | Private
1788 | Acton | 1720 | 142 | PV | 416-H5 | 2011-04-01 | 2011-04-08 | 5 | 3 | 2 | 2011-04-08 | 2011-05-17 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-04-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-18 |  | 2011-09-07 | Online |  | Gov't | Y
1853 | Acton | 1720 | 128 | PV | 416-H9 | 2011-07-20 | 2011-07-27 | 5 | 5 | 0 | 2011-07-27 | 2011-09-16 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-15 | Online |  | Private | Y
1787 | Acton | 1720 | 24 | PV | 416-H2 | 2011-04-01 | 2011-04-12 | 7 | 5 | 2 | 2011-04-12 | 2011-05-11 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online |  | Private | Y
1931 | Acton | 1720 | 42 | PV | 416-H9 | 2011-10-04 | 2011-10-04 | 0 | 0 | 0 | 2011-10-05 | 2012-01-05 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-06 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-15 | Online |  | Private | Y
2061 | Acton | 1720 | 12 | PV | 416-H8 | 2012-02-27 | 2012-02-29 | 2 | 2 | 0 | 2012-02-29 | 2012-03-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-08 | 2013-08-24 | 315 | 0 | 315 |  |  | 0 | 0 | 0 | 2013-04-08 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-10-02 | 2013-10-02 | 2013-10-04 | Online |  | Gov't | Y
2056 | Acton | 1720 | 1500 | PV | 416-H4 | 2012-02-21 | 2012-03-05 | 9 | 7 | 2 | 2012-03-05 | 2012-04-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-03-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online |  | Gov't | Y
1634 | Acton | 1720 | 60 | PV | 416-H4 | 2010-06-09 | 2010-06-10 | 1 | 0 | 1 | 2010-06-10 | 2010-07-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-30 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1988954 | Ashland | 01721 | 80 | PV | 274-1429H1 | 2014-02-05 | 2014-02-24 | 13 | 0 | 13 | 2014-02-28 | 2014-02-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-11 |  | 2014-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-09-11 | Online |  | Private | N
2039760 | Ashland | 01721 | 200 | PV | 274-1429H1 | 2014-12-04 | 2015-01-23 | 36 | 0 | 36 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 |  | 2015-07-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online |  | Private
2038832 | Ashland | 01721 | 200 | PV | 274-1429H1 | 2014-12-03 | 2015-01-02 | 22 | 0 | 22 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 |  | 2015-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online |  | Private
2052252 | Ashland | 01721 | 2413 | PV | 274-H1 | 2015-01-30 | 2015-01-30 | 0 | 0 | 0 | 2015-02-04 | 2015-02-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-09 |  | 2015-09-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
2125198 | Ashland | 01721 | 90 | PV | 519-175H1 | 2016-01-25 | 2016-01-26 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-10 | Online |  | Private
2071026 | Ashland | 01721 | 498 | PV | 519-175H1 | 2015-05-20 | 2015-05-22 | 2 | 0 | 2 | 2015-05-27 | 2015-06-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-07-09 | 2015-12-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online |  | Private
2071030 | Ashland | 01721 | 186 | PV | 274-1429H1 | 2015-05-20 | 2015-05-26 | 4 | 0 | 4 | 2015-05-28 | 2015-07-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2016-02-29 | 2016-12-27 | No | EXP | 30 | 2016-02-23 |  | -30303 | 0 | 0 |  |  | 2017-02-23 | Online |  | Private
2078781 | Ashland | 01721 | 183.287 | PV | 274-1429H1 | 2015-07-02 | 2015-07-06 | 2 | 0 | 2 | 2015-07-08 | 2015-07-29 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-17 | 2015-09-30 | 2015-11-06 | No | EXP | 30 | 2015-10-20 | 2015-10-20 | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private | N
2197716 | Ashland | 01721 | 728 | PV | TBD | 2017-01-19 |  | 175 | 0 | 175 |  |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 |  | 2017-09-29 | 2018-05-30 | TBD |  | 30 | 2018-04-05 | 2018-04-05 |  |  |  |  | 2018-06-14 | 2018-06-15 | Online |  | Private
2035449 | Ashland | 01721 | 3756 | PV | 274-1429H1 | 2014-11-10 | 2014-11-18 | 6 | 61 | -55 | 2014-11-14 | 2015-01-09 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-12-01 | 2015-12-14 | 9 | 0 | 9 | 2015-05-13 | 2016-02-29 | 2016-08-12 | No | STD | 60 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2054585 | Ashland | 01721 | 21.2 | PV | 519-175H1 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 | 2015-02-17 | 2015-03-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-31 |  | 2016-04-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2071039 | Ashland | 01721 | 728 | PV | 455-H3 | 2015-05-21 | 2015-06-10 | 14 | 0 | 14 | 2015-06-11 | 2015-08-26 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2147605 | Ashland | 01721 | 728 | PV | 3-10-929 | 2016-05-18 | 2016-05-19 | 1 | 0 | 1 | 2016-07-14 | 2016-07-29 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2015-08-18 | 2016-12-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2114171 | Ashland | 01721 | 17 | PV | 519-175H1 | 2015-12-14 | 2015-12-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2296607 | Ashland | 01721 | 4450 | PV | TBD | 2018-09-14 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 |  |  | 2019-12-31 | TBD |  | 30 | 2019-10-30 | 2019-10-30 | [6 empty] | In Queue |  | Private
1736 | Ashland | 1721 | 500 | PV | 274-H1 | 2010-12-20 | 2011-01-05 | 12 | 11 | 1 | 2011-01-05 | 2011-02-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online |  | Gov't | Y
1580 | Ashland | 1721 | 21 | PV | 274-1429H1 | 2010-02-11 | 2010-02-24 | 9 | 5 | 4 | 2010-02-25 | 2010-03-25 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | N
2041 | Ashland | 1721 | 500 | PV | 274-H1 | 2012-01-31 | 2012-02-17 | 13 | 12 | 1 | 2012-02-17 | 2012-03-21 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-21 |  | 2012-12-21 | Online |  | Private | Y
2039 | Ashland | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online |  | Private | N
1781 | Ashland | 1721 | 30 | PV | 519-175H1 | 2011-03-15 | 2011-09-26 | 139 | 139 | 0 | 2011-09-26 | 2011-10-28 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1975 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 4 | 1 | 2011-11-28 | 2012-01-23 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1970 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1971 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1972 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1973 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1974 | Ashland | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2040 | Ashland | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  | -29314 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2127134 | Bedford | 01730 | 370 | PV | 322-1397H1 | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-07-20 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2133471 | Bedford | 01730 | 312 | PV | 487-1376H1 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 |  | -30318 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-12 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1353 | Bedford | 1730 | 142 | PV | 512-1399H | 2009-07-22 | 2009-07-22 | 0 | 0 | 0 | 2009-07-30 | 2009-09-03 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-01-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online |  | Private | Y
1426 | Bedford | 1730 | 75 | Natural Gas | 533-H7 | 2009-09-08 | 2009-09-16 | 6 | 5 | 1 | 2009-09-16 | 2009-12-09 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-09 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-23 | Online |  | Private | N
1979 | Bedford | 1730 | 500 | PV | 533-H8 | 2011-11-23 | 2011-12-06 | 9 | 7 | 2 | 2011-12-08 | 2012-01-26 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-06-29 | Online |  | Private | Y
1782 | Bedford | 1730 | 51 | PV | 592-70H | 2011-03-15 | 2011-03-18 | 3 | 2 | 1 | 2011-03-18 | 2011-04-29 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 |  | 2011-12-08 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-08-02 | Online |  | Gov't | N
2321 | Bedford | 1730 | 24 | PV | 533-H8 | 2012-12-18 | 2012-12-20 | 2 | 1 | 1 | 2013-03-26 | 2013-04-16 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-06 | Online |  | Private | Y
2395 | Bedford | 1730 | 500 | PV | 391-H10 | 2013-06-04 |  | -29593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1513 | Needham | 1730 | 75 | Natural Gas | 148-H1 | 2009-11-19 | 2009-11-19 | 0 | 0 | 0 | 2009-11-20 | 2009-12-22 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2010-01-28 | Online |  | Private | Y
2337464 | Bedford | 1730 | 35 | CHP | 322-05 | 2019-04-01 | 2019-04-22 | 15 |  | 15 | 2019-05-03 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
2135 | Lincoln | 1733 | 11 | PV | 282-H1 | 2012-05-17 | 2012-05-17 | 0 | 0 | 0 | 2012-05-22 | 2012-06-15 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-20 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online |  | Private | Y
2232 | Lincoln | 1733 | 13 | PV | 320-H6 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2013-06-26 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2014-06-24 |  |  | In Queue |  | Gov't | Y
2134241 | Carlisle | 01741 | 39 | PV | 512-1399H1 | 2016-03-11 | 2016-03-12 | 1 | 0 | 1 | 2016-03-22 | 2016-06-16 | 62 | 40 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-16 | Online |  | Private | Y
2136139 | Carlisle | 01741 | 17 | PV | 512-1399H1 | 2016-03-21 | 2016-03-25 | 4 | 0 | 4 | 2016-03-31 | 2016-06-14 | 53 | 22 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-21 | 2016-09-08 | 2016-10-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-18 | Online |  | Private
2089685 | Carlisle | 01741 | 216 | PV | 512-1399H1 | 2015-08-24 | 2015-08-27 | 3 | 0 | 3 | 2015-08-31 | 2015-09-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-24 |  | 2016-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2133263 | Carlisle | 01741 | 22 | PV | 533-H8 | 2016-03-04 | 2016-03-07 | 1 | 0 | 1 | 2016-03-15 | 2016-05-17 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-10-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2286 | Carlisle | 1741 | 14 | PV | 512-1399H1 | 2012-10-25 | 2012-11-01 | 5 | 4 | 1 | 2012-11-01 | 2012-12-04 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-14 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-25 | Online |  | Private | Y
1922 | Carlisle | 1741 | 11 | PV | 512-1399H1 | 2011-09-29 | 2011-10-21 | 16 | 15 | 1 | 2011-10-24 | 2012-01-30 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-05-25 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online |  | Gov't | Y
2021094 | Holliston | 01746 | 500 | PV | 65-H2 | 2014-08-27 | 2014-08-28 | 1 | 0 | 1 | 2014-09-04 | 2014-10-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 |  | 2017-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online |  | Private
2021069 | Holliston | 01746 | 185 | PV | 65-H2 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-10-15 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 | 2014-12-05 | 2014-12-31 | No | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  | 2015-02-18 | 2015-02-27 | Online |  | Private
2015374 | Holliston | 01746 | 300 | PV | 65-H7 | 2014-07-24 | 2014-08-19 | 18 | 0 | 18 | 2014-08-04 | 2014-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-17 | 2014-11-03 | 2015-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-08 | Online |  | Private
2027916 | Holliston | 01746 | 42 | PV | 274-H3 | 2014-10-01 | 2014-12-09 | 49 | 0 | 49 | 2014-12-09 | 2014-12-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 |  | 2015-03-01 | TBD | EXP | 30 | 2015-03-02 | 2015-03-02 | 0 |  | 0 |  |  | 2015-07-28 | Online |  | Private
2074665 | Holliston | 01746 | 20 | PV | 274-H5 | 2015-06-10 | 2015-06-12 | 2 | 0 | 2 | 2015-06-17 | 2015-08-26 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 |  | 2016-01-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-19 | Online |  | Private | N
2115036 | Holliston | 01746 | 21 | PV | 274-H1 | 2015-12-16 | 2015-12-18 | 2 | 0 | 2 | 2015-12-22 | 2016-01-14 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-20 |  | 2016-07-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online |  | Private
2093131 | Holliston | 01746 | 990 | PV | 65-H2 | 2015-09-09 | 2015-09-10 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online |  | Private
2397865 | Holliston | 01746 | 200 | PV | TBD | 2020-05-13 | 2020-05-13 | 1 | 0 | 1 | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 | [20 empty] | 2020-05-13 |  | 2020-12-18 | TBD | EXP | 30 | [7 empty] | 2021-03-19 | Online |  | Private
2008170 | Holliston | 01746 | 17 | PV | 274-H5 | 2014-06-11 | 2014-06-12 | 1 | 0 | 1 | 2014-06-16 | 2014-07-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 | 2014-09-22 | 2014-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2096409 | Holliston | 01746 | 476 | PV | 274-H1 | 2015-09-25 | 2015-09-28 | 1 | 0 | 1 | 2015-09-30 | 2015-11-20 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-01-21 | 2016-06-30 | No | EXP | 30 | 2016-04-07 | 2016-04-07 | 0 |  | 0 |  | 2016-06-24 |  | Withdrawn |  | Private
2051070 | Holliston | 01746 | 2000 | PV | 130-H1 | 2015-01-21 | 2015-01-21 | 0 | 64 | 0 | 2015-01-23 | 2016-01-19 | 257 | 66 | 191 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2016-12-31 | No | COMP | 160 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private
2125460 | Holliston | 01746 | 432 | PV | 274-H1 | 2016-01-25 | 2016-01-26 | 1 | 0 | 1 | 2016-01-28 | 2016-03-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-30 |  | 2016-08-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2044550 | Holliston | 01746 | 15.2 | PV | 65-H2 | 2014-12-26 | 2014-12-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Gov't
2061089 | Holliston | 01746 | 28 | PV | 65-H5 | 2015-03-31 | 2015-04-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2364171 | Holliston | 01746 | 0 |  | TBD | 2019-10-15 |  | 125 | 0 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-22 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2412335 | Holliston | 01746 | 20 | PV | TBD | 2020-08-26 | 2020-08-31 | 3 | 0 | 3 | 2020-09-14 |  | 77 | 0 | 77 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-01 | TBD | TBD | 30 | [8 empty] | In Queue |  | Private
1624 | Holliston | 1746 | 50 | PV | 274-H3 | 2010-05-17 | 2010-05-26 | 7 | 7 | 0 | 2010-05-26 | 2010-06-15 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2011-02-24 | Online |  | Private | Y
2112 | Holliston | 1746 | 18 | PV | 65-H5 | 2012-04-23 | 2012-05-24 | 23 | 21 | 2 | 2012-05-24 | 2012-06-23 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
2262 | Holliston | 1746 | 3000 | PV | 3-88-2J2 | 2012-09-28 | 2012-09-28 | 0 | 0 | 0 | 2012-10-17 | 2012-12-05 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-11 | Online |  | Gov't | Y
2389 | Holliston | 1746 | 1000 | PV | 65-1325H | 2013-05-20 | 2013-07-02 | 31 | 30 | 1 | 2013-07-02 | 2013-07-10 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-06-07 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-07-09 | Online |  | Private | Y
2279 | Holliston | 1746 | 15 | PV | 65-H5 | 2012-10-15 | 2012-11-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-12-23 | Online |  | Private | Y
2412 | Holliston | 1746 | 2000 | PV | 130-H1 | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 128 | 0 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29573 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2099 | West Roxbury | 1746 | 60 | PV | 468-01 | 2012-04-13 | 2012-08-29 | 98 | 96 | 2 | 2012-08-29 | 2012-10-04 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-03 | Online |  | Private | Y
2033025 | Hopkinton | 01748 | 15.2 | PV | 65-H6 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-01-12 | Online |  | Private
2051301 | Hopkinton | 01748 | 31 | PV | 65-H2 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-03-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 | 2015-04-20 | 2015-08-26 | TBD | EXP | 30 | 2015-05-18 | 2015-05-18 | 0 |  | 0 |  |  | 2015-09-04 | Online |  | Private
2096675 | Hopkinton | 01748 | 170 | PV | 126-H1 | 2015-09-28 | 2015-09-30 | 2 | 0 | 2 | 2015-10-05 | 2015-10-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-05 |  | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online |  | Private
2161144 | Hopkinton | 01748 | 252 | PV | 126-H1 | 2016-07-29 | 2016-08-02 | 2 | 0 | 2 | 2016-08-05 | 2016-08-19 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-12 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online | 2016-08-22 | Private
2037342 | Hopkinton | 01748 | 3000 | PV | 65-H6 | 2014-11-21 | 2015-02-10 | 57 | 0 | 57 | 2014-11-24 | 2015-04-01 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
2057252 | Hopkinton | 01748 | 308 | PV | 126-H2 | 2015-03-21 | 2015-05-06 | 33 | 5 | 28 | 2015-05-12 |  | -30098 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 | [7 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online |  | Private
2126313 | Hopkinton | 01748 | 6 | PV | 65-H6 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-30 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 |  | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2286172 | Hopkinton | 01748 | 100 | PV | TBD | 2018-07-10 | 2018-07-11 | 1 | 0 | 1 | 2018-07-13 | 2018-07-18 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-19 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2380935 | Hopkinton | 01748 | 250 | PV | TBD | 2020-01-08 | 2020-01-09 | 1 | 0 | 1 | 2020-01-10 | 2020-05-08 | 78 | 4 | 74 | [20 empty] | 2020-05-27 |  | 2020-08-12 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2017615 | Hopkinton | 01748 | 342 | PV | 126-H4 | 2014-08-06 | 2014-08-15 | 7 | 0 | 7 | 2014-09-24 |  | -29934 |  | 0 |  |  | 0 | 0 | 0 | 2014-08-15 | 2014-10-04 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-23 |  | 2015-03-17 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2107469 | Hopkinton | 01748 | 87 | PV | 65-H7 | 2015-11-18 | 2015-11-19 | 1 | 0 | 1 | 2015-11-20 |  | -30236 | 187 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-23 | Private
2136142 | Hopkinton | 01748 | 2000 | PV | 126-H1 | 2016-03-23 | 2016-05-12 | 36 | 0 | 36 | 2016-03-31 |  | -30330 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2246432 | Hopkinton | 01748 | 15.2 | PV | 65-H6 | 2017-10-16 | 2017-10-26 | 8 |  | 8 | 2017-11-21 |  | -30750 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-02 | [6 empty] | 0 |  | 0
2358327 | Hopkinton | 01748 | 2770 | PV | TBD | 2019-09-06 |  | 151 | 0 | 151 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-16 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2407210 | Hopkinton | 01748 | 480 | PV | TBD | 2020-07-17 | 2020-07-20 | 1 | 0 | 1 | 2020-07-22 |  | 104 | 104 | 0 | [20 empty] | 2021-11-22 |  | 2020-12-15 | TBD |  | 30 | [8 empty] | In Queue | 2020-08-04 | Private
1347 | Hopkinton | 1748 | 82 | PV | 65-H7 | 2009-07-03 | 2009-07-07 | 2 | 0 | 2 | 2009-07-08 | 2009-08-05 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-23 |  | 2009-09-23 | Online |  | Private | N
1346 | Hopkinton | 1748 | 177 | PV | 65-H7 | 2009-06-30 | 2009-06-30 | 0 | 0 | 0 | 2009-07-01 | 2009-08-03 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-13 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-10-08 | Online |  | Private | N
1337 | Hopkinton | 1748 | 2000 | Other | 126-H1 | 2009-06-29 | 2009-06-30 | 1 | 1 | 0 | 2009-06-30 | 2009-07-16 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online |  | Private | Y
1612 | Hopkinton | 1748 | 29 | PV | 126-H1 | 2010-04-26 | 2010-05-11 | 11 | 11 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-22 | Online |  | Private | Y
1679 | Hopkinton | 1748 | 20 | PV | 126-H1 | 2010-09-15 | 2010-09-22 | 5 | 4 | 1 | 2010-09-22 | 2010-10-14 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-12-15 | Online |  | Gov't | Y
1665 | Hopkinton | 1748 | 36 | PV | 65-H7 | 2010-08-18 | 2010-08-27 | 7 | 6 | 1 | 2010-08-27 | 2010-10-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2011-01-19 | Online |  | Private | Y
1825 | Hopkinton | 1748 | 69 | PV | 65-1325H3 | 2011-05-31 | 2011-06-14 | 10 | 6 | 4 | 2011-06-14 | 2011-09-14 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2011-12-06 | Online |  | Private | Y
1877 | Hopkinton | 1748 | 1000 | Natural Gas | 455-H3 | 2011-08-09 | 2011-08-10 | 1 | 1 | 0 | 2011-08-10 | 2011-09-14 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-15 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-04 |  | 2012-04-11 | Online |  | Private | Y
2322 | Hopkinton | 1748 | 190 | PV | 126-H1 | 2012-12-19 | 2012-12-21 | 2 | 1 | 1 | 2013-04-08 | 2013-04-24 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-24 | Online |  | Private | Y
2458 | Hopkinton | 1748 | 85 | PV | 126-H1 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29697 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online |  | Private | Y
1938 | Hopkinton | 1748 | 30 | PV | 65-H6 | 2011-10-13 | 2011-10-19 | 4 | 3 | 1 | 2011-10-20 | 2012-01-30 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 | 2012-07-27 | 80 | 0 | 80 |  |  | 0 | 0 | 0 | 2013-08-12 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-29 | Online |  | Private | Y
1698 | Hopkinton | 1748 | 2250 | Natural Gas | 455-H3 | 2010-09-01 | 2010-11-12 | 52 | 26 | 26 | 2010-11-18 | 2010-12-23 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2375 | Hopkinton | 1748 | 4000 | PV | 126-H1 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1932 | Hopkinton | 1748 | 200 | PV | 519-175H1 | 2011-10-06 |  | -29160 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2459 | Hopkinton | 1748 | 18 | PV | 126-H1 | 2013-10-21 | 2013-11-01 | 9 | 9 | 0 | 2013-11-01 |  | -29701 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-12-04 | Private | Y
2051324 | Maynard | 01754 | 15.2 | PV | 355-05 | 2015-01-21 | 2015-01-22 | 1 | 0 | 1 | 2015-01-23 | 2015-02-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-09-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2127819 | Maynard | 01754 | 750 | PV | STA207 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2160866 | Maynard | 01754 | 576 | PV | 416-H3 | 2016-07-28 | 2016-08-01 | 2 | 0 | 2 | 2016-08-05 |  | -30421 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-09 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-11 | Private
1961 | Maynard | 1754 | 1000 | PV | 416-H6 | 2011-11-09 | 2011-11-15 | 4 | 3 | 1 | 2011-11-21 | 2012-01-03 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-30 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2068895 | Natick | 01760 | 19 | PV | 240-H5 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-05-27 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-01 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online |  | Private
2001342 | Natick | 01760 | 520 | PV | 433-H10 | 2014-01-30 | 2014-03-27 | 40 | 0 | 40 | 2014-05-14 | 2014-06-25 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 |  | 2014-12-17 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-24 | 2015-12-28 | Online |  | Private | Y
2071934 | Natick | 01760 | 148 | PV | 240-H5 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 | 2015-06-03 | 2015-06-24 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2016-01-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online |  | Private
2043228 | Natick | 01760 | 211 | PV | 23-H1 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-22 | 2015-03-18 | 62 | 27 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-18 |  | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-15 | 2016-01-15 | Online |  | Private
2024912 | Natick | 01760 | 264 | PV | 433-H9 | 2014-08-27 | 2014-09-15 | 13 | 0 | 13 | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-02 | 2015-04-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-21 | Online |  | Private
2094705 | Natick | 01760 | 75 | PV | 433-H11 | 2015-09-16 | 2015-09-21 | 3 | 0 | 3 | 2015-09-23 | 2015-10-07 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-06 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online |  | Private
2085006 | Natick | 01760 | 492 | PV | 433-H9 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-19 | Online |  | Private
2001305 | Natick | 01760 | 580 | PV | 433-H10 | 2014-05-05 | 2014-05-06 | 1 | 0 | 1 | 2014-05-07 | 2014-09-23 | 99 | 131 | -32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-29 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-03 | Online |  | Private
2001314 | Natick | 01760 | 620 | PV | 433-H9 | 2014-03-24 | 2014-05-05 | 30 | 0 | 30 | 2014-05-07 | 2014-11-26 | 145 | 132 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-30 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-28 | 2016-06-03 | Online |  | Private
2104785 | Natick | 01760 | 36 | PV | 433-H11 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-25 | Online |  | Private
2151948 | Natick | 01760 | 75 | Natural Gas | 433-H7 | 2016-06-07 | 2016-06-09 | 2 | 38 | -36 | 2016-06-14 |  | -30383 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-29 | 2016-01-03 | 2017-01-17 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | 2016-06-28 | Private
2148247 | Natick | 01760 | 280 | PV | 433-H7 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-30 | 2016-07-25 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-08-24 | 2016-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online |  | Private
2120155 | Natick | 01760 | 457 | PV | 240-H1 | 2016-01-05 | 2016-01-08 | 3 | 0 | 3 | 2016-01-11 | 2016-01-11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-21 |  | 2016-08-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-06 | Online |  | Gov't
2120194 | Natick | 01760 | 120 | PV | 23-H1 | 2016-01-06 | 2016-01-08 | 2 | 0 | 2 | 2016-01-11 | 2016-02-10 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-11 | 2016-02-11 | 2016-08-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
1998808 | Natick | 01760 | 150 | Natural Gas | 23-1339H1 | 2014-04-29 | 2014-04-30 | 1 | 0 | 1 | 2014-05-13 | 2014-08-20 | 71 | 64 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-19 | 2016-03-11 | 2014-12-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2059455 | Natick | 01760 | 240 | PV | 433-H7 | 2015-03-23 | 2015-03-23 | 0 | 0 | 0 | 2015-03-31 | 2015-04-22 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-15 |  | 2015-10-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2060976 | Natick | 01760 | 500 | PV | 408-1433 | 2015-03-31 | 2015-03-31 | 0 | 0 | 0 | 2015-04-03 | 2015-04-23 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-30 |  | 2015-11-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2097431 | Natick | 01760 | 207 | PV | 433-H7 | 2015-10-01 | 2015-10-02 | 1 | 0 | 1 | 2015-10-05 | 2015-10-27 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2178429 | Natick | 01760 | 458 | PV | TBD | 2016-10-31 |  | 1 | 0 | 1 | 2016-11-04 | 2017-08-17 | 195 | 188 | 7 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-06-09 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Gov't
2321334 | Natick | 01760 | 32.4 | PV | TBD | 2019-01-18 |  | 1 | 0 | 1 | 2019-01-22 | 2019-03-05 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-26 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2366478 | Natick | 01760 | 250 | PV | TBD | 2019-10-31 |  | 1 | 0 | 1 | 2019-11-05 | 2020-07-01 | 160 | 13 | 147 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-10 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2410982 | Natick | 01760 | 497 | PV | 240-H1 | 2020-08-17 | 2020-09-29 | 29 | 0 | 29 | 2020-09-29 | 2020-10-07 | 6 | 0 | 6 | [22 empty] | 2020-12-01 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2397836 | Natick | 01760 | 330 | PV | TBD | 2020-05-12 |  | 162 | 0 | 162 | 2020-05-18 |  | 0 | 0 | 0 | [22 empty] | 2020-12-17 | TBD |  | 30 | [7 empty] | 2022-04-25 | Online |  | Private
2183910 | Natick | 01760 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1892 | Natick | 1760 | 100 | PV | 240-H5 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-19 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | N
1898 | Natick | 1760 | 260 | PV | 433-H5 | 2011-08-30 | 2011-10-05 | 26 | 25 | 1 | 2011-10-05 | 2011-12-02 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online |  | Private | Y
2111 | Natick | 1760 | 50 | PV | 240-H2 | 2012-04-23 | 2012-06-11 | 35 | 33 | 2 | 2012-06-11 | 2012-07-06 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-19 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-10 | Online |  | Private | Y
2110 | Natick | 1760 | 260 | PV | 240-H1 | 2012-04-23 | 2012-04-27 | 4 | 2 | 2 | 2012-04-27 | 2012-06-25 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-06 | Online |  | Gov't | Y
2197 | Natick | 1760 | 14 | PV | 433-H5 | 2012-08-01 | 2012-08-23 | 16 | 14 | 2 | 2012-08-23 | 2012-11-19 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-29 | Online |  | Gov't | Y
1818 | Natick | 1760 | 175 | PV | 433-H12 | 2011-05-23 | 2011-05-31 | 6 | 3 | 3 | 2011-05-31 | 2011-07-23 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-25 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-24 | Online |  | Private | Y
2436 | Natick | 1760 | 550 | PV | 433-H10 | 2013-09-10 | 2013-09-13 | 3 | 3 | 0 | 2013-09-13 |  | -29666 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-06 | Online |  | Private | Y
2353437 | Natick | 1760 | 496 | PV | 240-H1 | 2017-06-28 | 2017-06-28 | [28 empty] | 2018-04-03 | [12 empty] | 2020-10-28 | Online
1838 | Natick | 1760 | 332 | Natural Gas | 433-H7 | 2011-06-24 | 2011-06-28 | 2 | 2 | 0 | 2011-06-28 | 2011-08-15 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1893 | Natick | 1760 | 90 | PV | 433-H5 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 115 | 0 | 115 |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2091 | Natick | 1760 | 14 | PV | 240-H1 | 2012-03-30 | 2012-04-03 | 2 | 0 | 2 | 2012-04-13 | 2012-05-23 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2042113 | Sherborn | 01770 | 29 | PV | 240-H1 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-18 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-15 | 2015-01-14 | 2015-05-22 | No | EXP | 30 | 2015-05-08 | 2015-05-08 | 0 |  | 0 |  |  | 2015-05-29 | Online |  | Private
2146567 | Sherborn | 01770 | 19 | PV | 274-H2 | 2016-05-12 | 2016-05-18 | 4 | 0 | 4 | 2016-05-26 | 2016-06-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-08 | Online |  | Private
1870 | Sherborn | 1770 | 60 | PV | 240-H6 | 2011-07-28 | 2011-08-01 | 2 | 1 | 1 | 2011-08-01 | 2011-09-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-29 |  | 2011-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-02-03 | Online |  | Private | Y
2445 | Sherborn | 1770 | 19 | PV | 130-H2 | 2013-09-23 | 2013-09-30 | 5 | 2 | 3 | 2013-10-04 |  | -29681 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online |  | Private | Y
1793 | Sherborn | 1770 | 16 | PV | 240-H1 | 2011-04-20 | 2011-08-24 | 90 | 89 | 1 | 2011-08-24 | 2012-03-12 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-03 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2011-10-03 | Private | N
2073959 | Lincoln | 01773 | 112 | PV | 320-H8 | 2015-06-09 | 2015-06-11 | 2 | 0 | 2 | 2015-06-15 | 2015-06-25 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-12-18 | 2016-01-20 | TBD | EXP | 30 | 2015-12-28 | 2015-12-28 | 0 |  | 0 |  |  | 2016-01-29 | Online |  | Private
2073947 | Lincoln | 01773 | 84 | PV | 320-H8 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-10 | 2015-07-17 | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-30 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-18 | Online |  | Private | N
2245650 | Lincoln | 01773 | 199.8 | PV | 320-H6 | 2017-09-26 | 2017-11-02 | 26 |  | 26 | 2018-11-16 |  | -31006 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-03 | 2018-02-15 | [6 empty] | 0 |  | 0 |  |  | 2018-10-04 | Online
2102041 | Lincoln | 01773 | 20 | PV | 320-H1 | 2015-10-21 | 2015-10-22 | 1 | 0 | 1 | 2015-10-23 | 2015-10-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2271 | Lincoln | 1773 | 14 | PV | 282-H1 | 2012-10-02 | 2012-10-24 | 16 | 16 | 0 | 2012-10-24 | 2012-12-04 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-28 | Online |  | Private | Y
2295 | Lincoln | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2012-12-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
2311 | Lincoln | 1773 | 10 | PV | 320-H6 | 2012-12-03 | 2012-12-13 | 8 | 6 | 2 | 2012-12-27 | 2013-02-12 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Online |  | Private | Y
2307 | Lincoln | 1773 | 12 | PV | 320-H8 | 2012-11-27 | 2012-12-04 | 5 | 5 | 0 | 2012-12-04 | 2013-02-12 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-02 | Online |  | Private | Y
2293 | Lincoln | 1773 | 11 | PV | 320-H1 | 2012-10-31 | 2012-11-27 | 19 | 19 | 0 | 2012-11-27 | 2013-01-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online |  | Private | Y
2294 | Lincoln | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2013-04-22 | 2013-04-26 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-05 | Online |  | Private | Y
2339 | Lincoln | 1773 | 9 | PV | 320-H8 | 2013-01-28 | 2013-03-12 | 31 | 30 | 1 | 2013-03-13 | 2013-04-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-17 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-12 | 2013-08-12 | 2013-08-16 | Online |  | Private | N
2272 | Lincoln | 1773 | 12 | PV | 320-H6 | 2012-10-02 | 2012-11-13 | 30 | 30 | 0 | 2012-11-13 | 2012-12-26 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  | 2012-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-09 | Online |  | Private | Y
2292 | Lincoln | 1773 | 12 | PV | 320-H8 | 2012-10-31 | 2012-11-30 | 22 | 22 | 0 | 2012-11-30 | 2013-01-15 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2329 | Lincoln | 1773 | 11 | PV | 320-H6 | 2013-01-21 | 2013-01-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-05-07 | Gov't | Y
2099532 | Sudbury | 01776 | 42 | PV | 342-H2 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2015-11-16 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2134239 | Sudbury | 01776 | 600 | PV | 342-H2 | 2016-03-10 | 2016-03-11 | 1 | 0 | 1 | 2016-03-21 | 2016-04-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2134028 | Sudbury | 01776 | 112 | PV | 342-H2 | 2016-03-09 | 2016-03-10 | 1 | 0 | 1 | 2016-03-21 | 2016-04-06 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2264 | Sudbury | 1776 | 12 | PV | 342-H8 | 2012-09-29 | 2012-11-07 | 28 | 27 | 1 | 2012-11-07 | 2012-12-26 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-11 |  | 2012-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online |  | Private | Y
2046 | Sudbury | 1776 | 18 | PV | 342-H2 | 2012-01-24 | 2012-02-22 | 21 | 9 | 12 | 2012-02-22 | 2012-03-19 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-28 | Online |  | Private | Y
2346 | Sudbury | 1776 | 41 | PV | 342-H7 | 2013-03-26 | 2013-04-01 | 4 | 0 | 4 | 2013-04-01 | 2013-05-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
2176 | Sudbury | 1776 | 1333 | PV | 342-H3 | 2012-07-26 | 2012-08-15 | 14 | 14 | 0 | 2012-08-16 | 2012-09-28 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-14 |  | 2012-08-06 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online |  | Gov't | Y
2417 | Sudbury | 1776 | 980 | PV | 416-H4 | 2013-07-03 | 2013-08-20 | 34 | 28 | 6 | 2013-08-20 |  | -29648 | 0 | 0 | 2013-09-16 |  | -29667 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-05-19 | Online |  | Private | Y
1920 | Sudbury | 1776 | 95 | PV | 342-H5 | 2011-05-23 | 2011-05-31 | 6 | 3 | 3 | 2011-05-31 | 2011-07-23 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-06 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2265 | Sudbury | 1776 | 12 | PV | 342-H2 | 2012-09-29 | 2012-10-17 | 13 | 12 | 1 | 2012-10-17 | 2012-12-05 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2341 | Sudbury | 1776 | 12 | PV | 342-H8 | 2013-01-31 | 2013-02-06 | 4 | 3 | 1 | 2013-02-27 | 2013-04-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2281 | Sudbury | 1776 | 12 | PV | 342-H8 | 2012-10-18 | 2012-11-29 | 30 | 30 | 0 | 2012-11-29 |  | -29460 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-07 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2052009 | Wayland | 01778 | 42 | PV | 433-H6 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-06 | Online |  | Private
2050518 | Wayland | 01778 | 113 | PV | 433-H6 | 2015-01-16 | 2015-01-19 | 1 | 0 | 1 | 2015-01-21 | 2015-02-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-03 | Online |  | Private
2038683 | Wayland | 01778 | 131 | PV | 342-H1 | 2014-12-02 | 2015-01-02 | 23 | 0 | 23 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 | 2016-03-11 | 2016-08-15 | No | EXP | 30 | 2016-03-24 |  | -30325 |  | 0 |  |  | 2016-04-14 | Online |  | Private
2059441 | Wayland | 01778 | 217 | PV | 433-H6 | 2015-03-19 | 2015-03-20 | 1 | 0 | 1 | 2015-07-23 | 2015-07-30 | 5 | 85 | -80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-22 | 2016-06-30 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-29 | Online |  | Private
2059403 | Wayland | 01778 | 207 | PV | 342-H3 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-06-22 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-18 | 2016-01-11 | 2016-07-29 | TBD | EXP | 30 | 2016-04-29 |  | -30351 |  | 0 |  |  | 2016-12-30 | Online |  | Gov't
2059369 | Wayland | 01778 | 176 | PV | 342-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-05-18 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online |  | Private
2212763 | Wayland | 01778 | 15.2 | PV | 342-H1 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
1973375 | Wayland | 01778 | 200 | PV | 342-H3 | 2013-12-10 | 2013-12-10 | 0 | 0 | 0 | 2013-12-11 | 2013-12-19 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-27 | 2013-12-31 | 2014-07-18 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2013-12-27 |  | Withdrawn |  | Private
1984570 | Wayland | 01778 | 225 | PV | 342-H3 | 2014-01-21 | 2014-04-30 | 71 | 0 | 71 | 2014-01-24 | 2014-02-14 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 | 2014-05-13 | 2014-08-26 | TBD | EXP | 30 | 2014-05-16 | 2014-05-16 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1989963 | Wayland | 01778 | 20 | PV | 342-H1 | 2014-02-28 | 2014-09-20 | 145 | 0 | 145 | 2014-03-05 | 2014-04-03 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-11-03 | 2015-06-05 | 154 | 9 | 145 | 2015-11-16 | 2015-11-25 | 7 | 0 | 7 | 2015-03-04 | 2016-04-20 | 2016-11-01 | No | STD | 60 | 2016-05-27 |  | -30371 |  | 0 |  |  |  | In Queue |  | PRIVATE | N
2059432 | Wayland | 01778 | 500 | PV | 278-H2 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-23 | 2015-05-19 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2429 | Wayland | 01778 | 325 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29652 | 0 | 0 | 2013-09-24 | 2013-10-28 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-12-02 | Gov't | Y
2430 | Natick | 1778 | 225 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Gov't | Y
2461 | Sudbury | 1778 | 225 | PV | 342-H3 | 2013-10-28 | 2013-11-13 | 12 | 12 | 0 | 2013-11-13 |  | -29709 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-05-14 | 43 | 0 | 43 |  |  | 0 | 0 | 0 | 2014-06-09 |  | 2014-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2129 | Wayland | 1778 | 150 | PV | 342-H1 | 2012-05-11 |  | -29316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2012-11-16 | Online |  | Gov't | Y
2270 | Wayland | 1778 | 17 | PV | 342-H1 | 2012-10-02 | 2012-11-07 | 26 | 26 | 0 | 2012-11-14 | 2012-12-20 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-31 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-14 | Online |  | Private | Y
2263 | Wayland | 1778 | 13 | PV | 342-H1 | 2012-09-29 | 2012-10-17 | 13 | 12 | 1 | 2012-10-17 | 2012-12-05 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
2266 | Wayland | 1778 | 12 | PV | 342-H9 | 2012-10-01 | 2012-11-28 | 42 | 41 | 1 | 2012-11-28 | 2013-01-03 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-09 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online |  | Private | Y
2268 | Wayland | 1778 | 10 | PV | 342-H1 | 2012-10-01 | 2012-10-24 | 17 | 16 | 1 | 2012-10-24 | 2013-01-15 | 59 | 26 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 |  | 2012-10-22 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online |  | Private | Y
2356 | Wayland | 1778 | 10 | PV | 278-H2 | 2013-03-06 | 2013-03-13 | 5 | 2 | 3 | 2013-03-15 | 2013-04-24 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-18 | Online |  | Private | Y
2296 | Wayland | 1778 | 12 | PV | 342-H1 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2013-02-06 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-23 | Online |  | Private | Y
2297 | Wayland | 1778 | 11 | PV | 342-H1 | 2012-11-02 | 2012-11-07 | 3 | 3 | 0 | 2012-11-27 | 2013-01-22 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-11-14 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online |  | Private | Y
2142 | Wayland | 1778 | 19 | PV | 278-H2 | 2012-05-30 | 2012-06-20 | 15 | 13 | 2 | 2012-06-20 | 2012-07-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-23 | Online |  | Gov't | Y
2282 | Wayland | 1778 | 11 | PV | 342-H1 | 2012-10-22 | 2012-11-07 | 12 | 12 | 0 | 2012-11-07 | 2012-12-14 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-06-26 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 2013-08-14 |  | 2012-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online |  | Gov't | Y
2312 | Wayland | 1778 | 18 | PV | 342-H3 | 2012-12-04 | 2012-12-11 | 5 | 1 | 4 | 2012-12-11 | 2013-02-12 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-24 | Online |  | Gov't | Y
1906 | Wayland | 1778 | 12 | PV | 342-H1 | 2011-09-01 | 2011-09-08 | 5 | 4 | 1 | 2011-09-08 | 2011-11-15 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1916 | Wayland | 1778 | 60 | PV | 342-H3 | 2011-09-17 |  | -29146 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2177 | Wayland | 1778 | 12 | PV | 278-H2 | 2012-07-30 |  | -29372 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2273 | Wayland | 1778 | 14 | PV | 278-H2 | 2012-10-02 | 2012-11-21 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-03-19 | Private | Y
2319 | Wayland | 1778 | 11 | PV | 342-H1 | 2012-12-14 |  | -29471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2027532 | Woburn | 01801 | 278.4 | PV | 375-H9 | 2014-09-30 | 2014-10-02 | 2 | 0 | 2 | 2014-10-03 | 2014-10-06 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-14 |  | 2015-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-22 | Online |  | Private
2073317 | Woburn | 01801 | 100 | PV | 211-H8 | 2015-06-03 | 2016-03-02 | 195 |  | 195 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-03-02 | Online |  | Private
2143665 | Woburn | 01801 | 140 | PV | 211-H5 | 2016-04-27 | 2016-04-29 | 2 | 0 | 2 | 2016-04-29 | 2016-06-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-09 | Online |  | Private
2098750 | Woburn | 01801 | 252 | PV | 211-H5 | 2015-10-06 | 2015-10-08 | 2 | 0 | 2 | 2015-10-12 | 2016-02-18 | 93 | 18 | 75 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-06 | 2016-05-13 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-12 | Online |  | Private
2087191 | Woburn | 01801 | 29 | PV | 211-H2 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-18 | 2015-10-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2017-01-05 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online |  | PRIVATE | N
2135024 | Woburn | 01801 | 378 | PV | 375-H4 | 2016-03-15 | 2016-03-18 | 3 | 0 | 3 | 2016-03-28 | 2016-05-16 | 35 | 28 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 | 2016-06-08 | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-09 | Online |  | Private
2083212 | Woburn | 01801 | 263 | PV | 325-03 | 2015-07-21 | 2015-07-22 | 1 | 3 | -2 | 2015-07-24 | 2015-09-02 | 28 | 194 | -166 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-16 | 2016-01-06 | 2016-02-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online |  | Gov't | Y
2143667 | Woburn | 01801 | 112 | PV | 211-H5 | 2016-04-27 | 2016-05-20 | 17 | 0 | 17 | 2016-05-26 | 2016-08-17 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-23 | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-05 | Online |  | Private | Y
2130638 | Woburn | 01801 | 50 | PV | 375-H4 | 2016-02-24 | 2016-04-08 | 32 | 0 | 32 | 2016-04-25 | 2016-05-04 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-07-25 | 2016-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-18 | Online |  | Private
2064809 | Woburn | 01801 | 2640 | PV | 375-H6 | 2015-04-21 | 2015-04-28 | 5 | 49 | -44 | 2015-05-05 | 2015-07-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-12 | 2015-09-15 | 2015-11-25 | No | EXP | 30 | 2015-12-11 | 2015-12-11 | 0 |  | 0 |  | 2015-12-22 | 2017-06-15 | Online |  | Private
2126828 | Woburn | 01801 | 168 | PV | 375-H3 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-16 | Online |  | Private
2239974 | Woburn | 01801 | 57.5 | PV | 4W5-H1 | 2017-09-07 | 2017-09-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-07-20 | Online
2082549 | Woburn | 01801 | 495 | PV | 375-H3 | 2015-07-21 | 2015-07-22 | 1 | 0 | 1 | 2015-07-24 | 2015-09-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-29 | 2016-05-30 | 2016-02-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-03-29 | Online |  | Private
1976701 | Woburn | 01801 | 1000 | PV | 375-H14 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-10-15 | 215 | 297 | -82 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-03 | 2015-05-20 | 2015-09-27 | No | EXP | 30 | 2014-10-14 | 2014-10-14 | 0 |  | 0 |  | 2015-10-20 |  | Withdrawn |  | Gov't
2070813 | Woburn | 01801 | 662 | PV | 211-H5 | 2015-05-19 | 2015-05-27 | 6 | 0 | 6 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2015-06-25 | 2015-12-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2059849 | Woburn | 01801 | 65 | PV | 211-H2 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-06-04 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-14 | 2016-02-05 | 2015-10-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2072460 | Woburn | 01801 | 225 | PV | 375-H6 | 2015-06-01 | 2015-06-04 | 3 | 0 | 3 | 2015-06-08 | 2015-07-01 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-29 | 2015-10-23 | 2016-03-17 | TBD | EXP | 30 | 2016-01-15 | 2016-01-15 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2083306 | Woburn | 01801 | 265 | PV | 211-H10 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-08-12 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2083239 | Woburn | 01801 | 454 | PV | 211-H5 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-09-05 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-25 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2085086 | Woburn | 01801 | 336 | PV | 258-1394H2 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2100120 | Woburn | 01801 | 480 | PV | 258-1394H2 | 2015-10-14 | 2015-10-15 | 1 | 0 | 1 | 2015-10-19 | 2016-01-08 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-13 |  | 2016-05-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2099592 | Woburn | 01801 | 84 | PV | 211-01 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2016-01-25 | 73 | 57 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-14 |  | 2016-05-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2100528 | Woburn | 01801 | 40 | PV | 258-1394H4 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2016-01-25 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2085091 | Woburn | 01801 | 377 | PV | 258-1394H2 | 2015-07-30 | 2015-08-04 | 3 | 0 | 3 | 2015-08-06 | 2016-01-26 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-26 |  | 2017-02-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2100110 | Woburn | 01801 | 360 | PV | 258-1394H2 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-12 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2085252 | Woburn | 01801 | 624 | PV | 375-H12 | 2015-07-31 | 2015-08-01 | 1 | 0 | 1 | 2015-08-07 | 2016-03-23 | 163 | 142 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2106588 | Woburn | 01801 | 85 | PV | 375-H3 | 2015-11-13 | 2015-11-17 | 2 | 0 | 2 | 2015-11-18 | 2016-03-25 | 92 | 34 | 58 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-27 |  | 2016-06-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2126923 | Woburn | 01801 | 726 | PV | 375-H14 | 2016-02-02 | 2016-02-02 | 0 | 0 | 0 | 2016-02-08 | 2016-05-06 | 64 | 35 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2140339 | Woburn | 01801 | 480 | PV | 375-H6 | 2016-04-11 | 2016-04-25 | 10 | 0 | 10 | 2016-04-28 | 2016-07-13 | 54 | 49 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2016-11-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2187229 | Woburn | 01801 | 180 | PV | TBD | 2016-12-06 |  | 1 | 0 | 1 | 2016-12-09 | 2017-03-03 | 56 | 0 | 56 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-06 |  | 2017-07-14 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Gov't
2068626 | Woburn | 01801 | 300 | PV | 375-H11 | 2015-05-07 | 2015-05-12 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2080949 | Woburn | 01801 | 696 | PV | 375-H4 | 2015-07-16 | 2015-07-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2134403 | Woburn | 01801 | 200 | PV | 375-H6 | 2016-03-11 | 2016-03-16 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2016-03-21 | Private
2157251 | Woburn | 01801 | 499 | PV | 375-H3 | 2016-07-08 | 2016-07-11 | 1 | 0 | 1 | 2016-07-13 |  | -30404 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-16 | TBD | TBD | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2384521 | Woburn | 01801 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-09-08 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
945 | Woburn | 1801 | 95 | PV | 375-H11 | 2009-10-15 | 2009-10-15 | 0 |  | 0 | 2008-10-15 | 2008-10-30 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2008-11-13 | [7 empty] | 0 |  | 0 | 2009-02-11 |  | 2009-02-11 | Online |  |  | Y
1245 | Woburn | 1801 | 26 | PV | 375-H6 | 2009-04-08 | 2009-04-16 | 6 | 4 | 2 | 2009-04-16 | 2009-05-19 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-26 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2009-09-03 | Online |  | Private | Y
1468 | Woburn | 1801 | 101 | PV | 375-H11 | 2009-10-09 | 2009-10-23 | 10 | 7 | 3 | 2009-10-23 | 2009-11-13 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2009-10-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-16 | Online |  | Private | Y
1246 | Woburn | 1801 | 30 | PV | 375-H6 | 2009-04-13 | 2009-04-17 | 4 | 1 | 3 | 2009-04-22 | 2009-06-02 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-04 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2009-12-22 | Online |  | Gov't | N
1590 | Woburn | 1801 | 30 | PV | 375-H9 | 2010-03-19 | 2010-03-23 | 2 | 2 | 0 | 2010-03-24 | 2010-04-07 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2010-05-03 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-05 |  | 2010-08-05 | Online |  | Private | Y
1666 | Woburn | 1801 | 60 | PV | 375-H11 | 2010-08-20 | 2010-09-01 | 8 | 8 | 0 | 2010-09-01 | 2010-10-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-13 |  | 2010-10-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-04-27 | Online |  | Private | Y
1483 | Woburn | 1801 | 45 | PV | 375-H6 | 2009-10-21 | 2009-10-27 | 4 | 3 | 1 | 2009-10-27 | 2009-12-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2010-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-11 |  | 2012-02-06 | Online |  | Gov't | Y
2023 | Woburn | 1801 | 90 | PV | 375-H4 | 2012-01-18 | 2012-01-24 | 4 | 3 | 1 | 2012-01-24 | 2012-02-22 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-05 |  | 2012-04-11 | Online |  | Private | Y
2309 | Woburn | 1801 | 60 | PV | 375-H6 | 2012-11-28 | 2012-12-27 | 21 | 19 | 2 | 2012-12-27 | 2013-02-25 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-06 |  | 2013-01-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online |  | Private | Y
2340 | Woburn | 1801 | 336 | Natural Gas | 301-1386H | 2013-01-29 | 2013-02-06 | 6 | 4 | 2 | 2013-02-13 | 2013-04-24 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2013-02-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online |  | Private | Y
2450 | Woburn | 1801 | 50 | PV | 211-H2 | 2013-10-09 | 2013-10-16 | 5 | 3 | 2 | 2013-10-18 |  | -29691 | 0 | 0 | 2013-12-02 |  | -29722 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-13 |  | 2013-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-04 | Online |  | Private | Y
2123 | Woburn | 1801 | 288 | PV | 375-H1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2170 | Woburn | 1801 | 485 | PV | 375-H4 | 2012-07-20 | 2012-07-31 | 7 | 5 | 2 | 2012-08-01 | 2012-09-17 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  | 2012-08-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-11-15 |  |  | Withdrawn |  | Private | Y
2248 | Woburn | 1801 | 12 | PV | 211-H5 | 2012-09-04 | 2012-09-11 | 5 | 3 | 2 | 2012-09-11 | 2012-11-14 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2010 | Woburn | 1801 | 50 | PV | 211-H8 | 2011-12-28 |  | -29219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
593 | Woburn | 1801 | 75 | Capacitor | 211-H7XY |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2007-05-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | N
2026226 | Burlington | 01803 | 500 | PV | 391-H9 | 2014-09-25 | 2014-09-25 | 0 | 0 | 0 | 2014-09-29 | 2015-07-21 | 211 | 195 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2015-11-18 | 2016-06-16 | No | EXP | 30 | 2016-05-16 | 2016-05-16 | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2094742 | Burlington | 01803 | 100 | PV | 211-H13 | 2015-09-17 | 2015-09-21 | 2 | 0 | 2 | 2015-09-23 | 2016-01-19 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-04-07 | 2016-06-24 | No | EXP | 30 | 2016-05-18 |  | -30364 |  | 0 |  | 2015-10-14 |  | In Queue |  | Private | N
2127236 | Burlington | 01803 | 170 | PV | 211-H13 | 2016-02-04 | 2016-02-05 | 1 | 0 | 1 | 2016-02-15 | 2016-07-11 | 105 | 91 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2099699 | Burlington | 01803 | 360 | PV | 391-H15 | 2015-10-08 | 2015-10-14 | 4 | 1 | 3 | 2015-10-16 | 2016-08-01 | 206 | 0 | 206 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1977755 | Burlington | 01803 | 500 | PV | 391-H12 | 2013-12-19 | 2013-12-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2123809 | Burlington | 01803 | 672 | PV | 391-H16 | 2016-01-20 | 2016-01-22 | 2 | 0 | 2 | 2016-01-27 |  | -30284 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-08-25 | No | TBD | 160 |  |  | 0 |  | 0 |  |  |  | In Queue
2411056 | Burlington | 01803 | 500 | PV | TBD | 2020-08-17 | 2020-08-17 | 1 | 0 | 1 | 2020-08-25 |  | 89 | 65 | 24 | [22 empty] | 2020-12-30 | TBD |  | 30 | [8 empty] | In Queue | 2020-09-30 | Private
2347 | Burlington | 1803 | 351 | PV | 391-H12 | 2013-02-08 | 2013-05-14 | 67 | 50 | 17 | 2013-06-24 | 2013-07-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-11 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
2435 | Burlington | 1803 | 232 | PV | 391-H5 | 2013-09-03 | 2013-11-22 | 58 | 57 | 1 | 2013-11-22 |  | -29716 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-12 | 2014-12-04 | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-04 | Online |  | Private | Y
2161 | Burlington | 1805 | 3000 | Natural Gas | 541-1377H | 2012-07-13 | 2012-07-25 | 8 | 7 | 1 | 2012-07-25 | 2012-11-06 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-23 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2327102 | Burlington | 1805 | 5274.6 | PV & Battery | 541-1377H | 2019-01-22 | 2019-02-15 | 18 |  | 18 | 2019-02-27 |  | -31079 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
1868 | Marshfield | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-07-28 | 1 | 0 | 1 | 2011-07-28 | 2011-09-07 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  |  | Withdrawn |  | Private | Y
1866 | Marshfield | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1867 | Marshfield | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1865 | Marshfield | 1845 | 3000 | PV | 3-21-34J1 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2409982 | Winchester | 01890 | 18 | PV & Battery | TBD | 2020-08-07 | 2020-08-10 | 1 | 0 | 1 | 2020-08-13 | 2020-08-13 | 0 | 0 | 0 | [20 empty] | 2020-08-25 | 2020-08-31 | 2020-12-15 | TBD | EXP | 30 | [7 empty] | 2022-02-03 | Online |  | Private
2358 | Winchester | 1890 | 11 | PV | 211-H7XY | 2013-03-15 | 2013-10-09 | 148 | 146 | 2 | 2013-10-10 |  | -29685 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-04-11 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
1928 | Winchester | 1890 | 17 | PV | 211-H4 | 2011-09-30 | 2012-04-06 | 135 |  | 135 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-05-29 | Private | N
1987709 | Bellingham | 02019 | 52.5 | PV | 65-H4 | 2014-02-12 | 2014-02-14 | 2 | 0 | 2 | 2014-02-14 | 2014-03-06 | 14 | 28 | -14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-29 |  | 2014-09-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-07-18 | Online |  | Private
2032500 | Bellingham | 02019 | 480 | PV | 65-H4 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-03 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-05 | 2014-11-21 | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online |  | Private
2068158 | Bellingham | 02019 | 497 | PV | 65-H4 | 2015-05-06 | 2015-05-07 | 1 | 0 | 1 | 2015-07-01 | 2015-07-07 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-09 | 2016-09-12 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | Online |  | Private
2037449 | Bellingham | 02019 | 480 | PV | 65-H4 | 2014-11-25 | 2014-12-08 | 9 | 0 | 9 | 2014-12-02 | 2015-02-14 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-21 |  | -30345 | 1 | 0 |  |  | 0 | 0 | 0 | 2015-07-31 |  | 2015-07-03 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2037441 | Bellingham | 02019 | 480 | PV | 65-H4 | 2014-11-21 | 2015-02-10 | 57 | 0 | 57 | 2014-11-24 | 2015-03-26 | 88 | 0 | 88 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2061830 | Bellingham | 02019 | 1976 | PV | 65-H4 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-20 | 2015-05-04 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-11 | 2015-09-07 | 2015-11-09 | TBD | EXP | 30 | 2015-10-16 | 2015-10-16 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2082060 | Bellingham | 02019 | 990 | PV | 65-H4 | 2015-07-17 | 2015-07-20 | 1 | 0 | 1 | 2015-07-23 | 2015-08-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2016-02-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2096445 | Bellingham | 02019 | 984 | PV | 65-H4 | 2015-09-28 | 2015-09-30 | 2 | 2 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-12 | 2016-10-11 | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1344 | Bellingham | 2019 | 75 | PV | 65-H4 | 2009-06-30 | 2009-07-01 | 1 | 1 | 0 | 2009-07-01 | 2009-07-29 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-08 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-10-15 | Online |  | Private | N
1952 | Bellingham | 2019 | 5800 | PV | 65-H4 | 2011-10-27 | 2011-11-01 | 3 | 1 | 2 | 2011-11-02 | 2011-12-19 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-20 |  | 2011-11-04 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-10 | Online |  | Private | Y
1933 | Bellingham | 2019 | 5800 | PV | 65-H4 | 2011-10-06 | 2011-10-12 | 4 | 3 | 1 | 2011-10-12 | 2011-11-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-14 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2012-02-28 | Online |  | Private | Y
1909 | Bellingham | 2019 | 600 | PV | 65-H4 | 2011-09-09 | 2011-09-15 | 4 | 3 | 1 | 2011-09-15 | 2011-10-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1987 | Bellingham | 2019 | 2000 | PV | 65-H4 | 2011-12-01 | 2011-12-07 | 4 | 3 | 1 | 2011-12-07 | 2012-02-09 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-16 |  |  | Withdrawn |  | Private | Y
1985 | Bellingham | 2019 | 2000 | PV | 65-H4 | 2011-11-30 | 2012-02-22 | 60 | 58 | 2 | 2012-02-29 | 2012-05-26 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2276 | Bellingham | 2019 | 1000 | PV | 65-H4 | 2012-10-03 | 2012-10-12 | 7 | 6 | 1 | 2012-10-12 | 2012-12-04 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-31 |  |  |  |  | Private | Y
2274 | Bellingham | 2019 | 1000 | PV | 65-H4 | 2012-10-02 | 2012-11-06 | 25 | 23 | 2 | 2012-11-06 | 2013-01-17 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-11-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-01 | 2013-04-01 |  |  |  | Private | Y
1986 | Bellingham | 2019 | 2000 | PV | 65-H4 | 2011-11-30 |  | -29199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2022875 | Canton | 02021 | 170 | PV | 470-H8 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-09 | 2014-09-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-26 | 2014-09-29 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-19 | Online |  | Private
2044274 | Canton | 02021 | 18.9 | PV | 269-1320H1 | 2014-12-26 | 2014-12-26 | 0 | 0 | 0 | 2015-01-01 | 2015-01-08 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 |  | 2015-08-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-03-26 | Online |  | Private
2050531 | Canton | 02021 | 95 | PV | 470-H4 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-07-07 | 2015-07-31 | TBD | EXP | 30 | 2015-07-28 | 2015-07-28 | 0 |  | 0 |  |  | 2015-08-18 | Online |  | Private
2022843 | Canton | 02021 | 300 | PV | 470-H7 | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-22 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 | 2014-10-02 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-06 | Online |  | Private
2007950 | Canton | 02021 | 980 | PV | 470-H7 | 2014-06-11 | 2014-06-11 | 1 | 0 | 1 | 2014-06-13 | 2014-10-07 | 77 | 46 | 31 | [10 empty] | 2014-10-24 | 2015-01-14 | 55 | 0 | 55 | 2015-08-31 | 2015-10-13 | 30 | 0 | 30 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 |  |  |  |  | 2016-07-19 | 2016-07-19 | Online |  | Private | N
2128797 | Canton | 02021 | 19 | PV | 470-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-09 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-07-12 | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
2141085 | Canton | 02021 | 252 | PV | 470-H11 | 2016-04-14 | 2016-04-20 | 4 | 0 | 4 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-11-02 | 2016-11-17 | 2016-11-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-16 | Online |  | Private
2115399 | Canton | 02021 | 432 | PV | 470-H11 | 2015-12-17 | 2015-12-18 | 1 | 21 | -20 | 2015-12-22 | 2016-02-03 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-05-04 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-19 | Online |  | Private
2264634 | Canton | 02021 | 700 | PV | 470-H7 | 2014-06-12 | 2014-06-12 | 0 | 0 | 0 | 2014-06-16 | 2014-06-24 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-12-23 | Online |  | Private
2025700 | Canton | 02021 | 85 | PV | 470-H11 | 2014-09-19 | 2014-09-20 | 1 | 0 | 1 | 2014-09-22 | 2014-10-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-20 |  | 2015-04-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2093030 | Canton | 02021 | 990 | PV | 470-H7 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2015-10-13 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-17 | 2016-03-09 | 2016-05-27 | No | EXP | 30 | 2016-02-24 |  | -30304 |  | 0 |  |  |  | In Queue |  | Private
2131137 | Canton | 02021 | 496 | PV | 470-H8 | 2016-02-25 | 2016-02-29 | 2 | 0 | 2 | 2016-03-03 | 2016-03-18 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-18 |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2139666 | Canton | 02021 | 192 | PV | 470-H7 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 | 2016-04-20 | 2016-06-20 | 43 | 6 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-28 | 2016-08-24 | 2016-11-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2184049 | Canton | 02021 | 660 | PV | TBD | 2016-11-30 |  | 2 | 0 | 2 | 2016-12-08 | 2016-12-23 | 11 | 8 | 3 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | No | EXP | 30 | [8 empty] | Withdrawn |  | Private
2105434 | Canton | 02021 | 630 | PV | 269-1320H1 | 2015-11-05 | 2015-11-09 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2116306 | Canton | 02021 | 396 | PV | 470-H4 | 2015-12-18 | 2015-12-22 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2145484 | Canton | 02021 | 780 | PV | 269-1320H1 | 2016-05-05 | 2016-05-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2246191 | Canton | 02021 | 24 | PV | 470-H9 | 2017-10-10 | 2017-10-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
1695 | Canton | 2021 | 261.45 | PV | 470-H4 | 2010-10-01 | 2010-10-18 | 11 | 10 | 1 | 2010-10-20 | 2011-01-04 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-09-01 | Online |  | Private | Y
1899 | Canton | 2021 | 46 | PV | 269-1321H2 | 2011-08-31 | 2011-09-02 | 2 | 2 | 0 | 2011-09-02 | 2011-10-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-03 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-05 | Online |  | Private | Y
2014 | Canton | 2021 | 120 | PV | 470-H10 | 2012-01-05 | 2012-02-02 | 20 | 17 | 3 | 2012-02-02 | 2012-03-20 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-22 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-04-20 |  | 2012-05-04 | Online |  | Private | Y
1790 | Canton | 2021 | 100 | PV | 470-H7 | 2011-04-08 | 2011-04-12 | 2 | 1 | 1 | 2011-04-12 | 2011-05-16 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | Y
1730 | Canton | 2021 | 950 | PV | 470-H4 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2012-08-03 | Online |  | Gov't | N
1726 | Canton | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
1727 | Canton | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
1728 | Canton | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
1729 | Canton | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online |  | Gov't | N
2089 | Canton | 2021 | 14 | PV | 269-1320H1 | 2012-03-29 | 2012-04-03 | 3 | 1 | 2 | 2012-04-05 | 2012-06-12 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-15 |  | 2012-06-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-07 | Online |  | Gov't | Y
2148 | Canton | 2021 | 200 | PV | 470-H11 | 2012-06-05 | 2012-06-08 | 3 | 0 | 3 | 2012-06-08 | 2012-08-30 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online |  | Private | Y
2247 | Canton | 2021 | 237 | PV | 135-1319H1 | 2012-09-05 | 2012-09-10 | 3 | 3 | 0 | 2012-09-10 | 2012-11-25 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-04 | Online |  | Private | Y
2147 | Canton | 2021 | 260 | PV | 470-H11 | 2012-06-01 | 2012-08-06 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2013-08-06 | Online | 2012-09-24 | Private | Y
2012 | Canton | 2021 | 14 | PV | 269-1320H1 | 2012-01-05 | 2012-01-17 | 8 | 5 | 3 | 2012-01-24 | 2012-04-26 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-30 |  | 2012-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online |  | Gov't | Y
2009 | Canton | 2021 | 360 | PV | 470-H6 | 2012-01-03 | 2012-01-11 | 6 | 5 | 1 | 2012-01-12 | 2012-02-16 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-05 |  | 2013-08-13 | Online |  | Gov't | Y
1083 | Canton | 2021 | 39 | PV | 470-H7 | 2009-01-06 | 2009-01-13 | 5 | 4 | 1 | 2009-01-13 | 2009-01-29 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-01-12 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2013 | Canton | 2021 | 225 | PV | 269-1321H2 | 2012-01-05 | 2012-01-17 | 8 | 5 | 3 | 2012-01-27 | 2012-03-19 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1806 | Canton | 2021 | 50 | PV | 470-H8 | 2011-05-09 |  | -29052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2460 | Canton | 2021 | 60 | PV | 269-1320H1 | 2013-10-24 |  | -29695 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-10-24 | Private | Y
2047 | Roxbury Crossing | 2021 | 96 | PV | 483-H6 | 2011-11-15 | 2012-03-08 | 82 | 20 | 62 | 2012-03-08 | 2012-04-09 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-06-12 | Online |  | Private | Y
1573 | Canton | 2021 | 155 | PV | 470-H10 | 2010-02-04 | 2010-02-25 | 15 | 15 | 0 | 2010-02-25 | 2010-03-30 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-14 |  | 2010-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2011-05-09 | Private | Y
2154886 | Dedham | 02026 | 189.2 | PV | 20-H5 | 2016-06-24 | 2016-06-27 | 1 | 0 | 1 | 2016-07-04 | 2016-07-26 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-03 | 2016-08-03 | 2017-02-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-30 | Online |  | Private
2099070 | Dedham | 02026 | 765 | PV | 20-H2 | 2015-10-07 | 2015-10-08 | 1 | 0 | 1 | 2015-10-14 | 2016-05-02 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-04 | Online |  | Private
2124992 | Dedham | 02026 | 1740 | PV | 344-1413H1 | 2016-01-21 | 2016-01-25 | 2 | 0 | 2 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-11-16 | Online |  | Private
2063144 | Dedham | 02026 | 210 | PV | 469-H4 | 2015-04-09 | 2015-04-16 | 5 | 0 | 5 | 2015-04-20 | 2015-04-22 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2035957 | Dedham | 02026 | 150 | Natural Gas | 13-H1 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | 2015-02-10 | 2015-09-01 | 145 | 112 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-06-24 | No | COMP | 160 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2135559 | Dedham | 02026 | 112 | PV | 20-H5 | 2016-03-18 | 2016-03-21 | 1 | 0 | 1 | 2016-03-28 | 2016-05-24 | 41 | 28 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-10-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2034950 | Dedham | 02026 | 794 | PV | 20-H5 | 2014-11-10 | 2014-11-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2135868 | Dedham | 02026 | 84 | PV | 20-H1 | 2016-03-18 | 2016-03-30 | 8 | 0 | 8 | 2016-03-30 |  | -30329 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-25 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2412699 | Dedham | 02026 | 4990 | PV | TBD | 2020-08-31 | 2020-09-09 | 6 | 0 | 6 | [10 empty] | 2020-09-14 |  | 77 | 62 | 15 | [12 empty] | 2020-12-30 | TBD |  | 60 | [8 empty] | In Queue | 2020-10-05 | Private
1388 | Dedham | 2026 | 400 | Natural Gas | 20-H5 | 2009-07-13 | 2009-08-06 | 18 | 4 | 14 | 2009-08-06 | 2009-09-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-02 |  | 2009-10-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online |  | Private | N
1516 | Dedham | 2026 | 167 | PV | 13-H1 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2010-01-08 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-12-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-07-22 |  | 2010-07-22 | Online |  | Gov't | Y
1754 | Dedham | 2026 | 26 | PV | 20-H1 | 2011-01-21 | 2011-01-25 | 2 | 1 | 1 | 2011-01-25 | 2011-04-01 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online |  | Gov't | N
1755 | Dedham | 2026 | 120 | PV | 20-H5 | 2011-01-21 | 2011-02-08 | 12 | 8 | 4 | 2011-02-08 | 2011-03-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-30 |  | 2012-05-30 | Online |  | Private | N
1799 | Dedham | 2026 | 100 | PV | 344-07 | 2011-04-27 | 2011-05-12 | 11 | 9 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-29 | Online |  | Private | Y
1826 | Dedham | 2026 | 150 | PV | 344-07 | 2011-06-01 | 2011-07-06 | 25 | 21 | 4 | 2011-07-06 | 2011-08-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-21 |  | 2011-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-22 |  | 2013-01-22 | Online |  | Private | Y
1390 | Dedham | 2026 | 75 | PV | 20-H5 | 2009-06-19 | 2009-08-03 | 31 | 0 | 31 | 2009-08-03 | 2009-09-09 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-02-28 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1802 | Dedham | 2026 | 250 | PV | 20-H8 | 2011-04-29 | 2011-05-12 | 9 | 7 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2462 | Dedham | 2026 | 1750 | PV | 20-H3 | 2013-10-25 | 2014-03-05 | 93 |  | 93 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2007317 | Dover | 02030 | 20.2 | PV | 456-H5 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 | 2014-06-11 | 2014-06-23 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-25 | 2014-10-01 | 2015-01-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online |  | Private
2157192 | Dover | 02030 | 21 | PV | 456-H5 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-15 | 2016-08-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2017-02-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-02 | Online |  | Private
2019996 | Dover | 02030 | 21.2 | PV | 456-H5 | 2014-08-19 | 2014-08-20 | 1 | 0 | 1 | 2014-08-20 | 2014-09-26 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2016-08-18 | 2015-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
2117764 | Dover | 02030 | 1000 | PV | 456-H4 | 2015-12-30 | 2016-01-01 | 2 | 0 | 2 | 2016-01-06 | 2016-05-31 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-08-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2138477 | Dover | 02030 | 282 | PV | 456-H5 | 2016-04-06 | 2016-04-07 | 1 | 0 | 1 | 2016-04-25 | 2016-06-13 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2115395 | Dover | 02030 | 20 | PV | 456-H5 | 2015-12-16 | 2015-12-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
1978 | Dover | 2030 | 16 | PV | 456-H5 | 2011-11-23 | 2011-12-01 | 6 | 4 | 2 | 2011-12-01 | 2012-02-04 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-12 |  | 2012-02-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-06-29 | Online |  | Private | Y
2306 | Dover | 2030 | 12 | PV | 456-H5 | 2012-11-26 | 2012-12-05 | 7 | 3 | 4 | 2012-12-05 | 2013-02-06 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2013-01-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online |  | Private | Y
2452 | Dover | 2030 | 20 | PV | 456-H3 | 2013-10-15 | 2013-10-21 | 4 | 3 | 1 | 2013-10-21 |  | -29692 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
2134 | Dover | 2030 | 13 | PV | 456-H3 | 2012-05-16 | 2012-06-01 | 12 | 12 | 0 | 2012-06-01 | 2012-07-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-07-18 | Private | Y
2230 | Dover | 2030 | 23 | PV | 456-H5 | 2012-08-24 |  | -29391 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1637 | Framingham | 2030 | 110 | PV | 2410 | 2010-06-17 | 2010-06-25 | 6 | 6 | 0 | 2010-07-01 | 2010-08-18 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-13 |  | 2010-10-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-10-14 |  | 2011-10-14 | Online |  | Private | Y
2018681 | East Walpole | 02032 | 325.6 | PV | 135-1301 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-15 | 2014-08-28 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 |  | 2015-03-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-13 | Online |  | Private | N
2137 | East Walpole | 2032 | 360 | PV | 135-1319H1 | 2012-05-21 | 2012-11-26 | 135 |  | 135 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | Y
1984064 | Marshfield | 02050 | 18.5 | PV | 3-25-976 | 2014-01-20 | 2014-01-21 | 1 | 0 | 1 | 2014-01-20 | 2014-01-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2002502 | Marshfield | 02050 | 9 | PV | 3-24B-915 | 2014-02-14 | 2014-05-02 | 55 | 0 | 55 | 2014-05-19 | 2014-05-28 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-30 |  | 2014-12-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1293 | Marshfield | 2050 | 135 | PV | 3-25-908 | 2009-05-28 | 2009-06-01 | 2 | 1 | 1 | 2009-06-02 | 2009-06-29 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-06 |  | 2009-08-06 | Online |  | Private | Y
1803 | Marshfield | 2050 | 100 | PV | 3-24-915 | 2011-05-03 | 2011-05-10 | 5 | 2 | 3 | 2011-05-10 | 2011-06-13 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-13 |  | 2011-06-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-29 | Online |  | Private | Y
2171 | Marshfield | 2050 | 82 | PV | 3-24A-24A | 2012-07-24 | 2012-10-22 | 64 | 64 | 0 | 2012-10-22 | 2013-02-10 | 79 | 0 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 |  | -29526 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2094 | Marshfield | 2050 | 334 | PV | 3-25-908 | 2012-04-04 | 2012-04-06 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-05-04 | Private | Y
2060105 | Medfield | 02052 | 196 | PV | 456-H2 | 2015-03-31 | 2015-04-01 | 1 | 0 | 1 | 2015-04-03 | 2015-09-21 | 121 | 117 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2412922 | Medfield | 02052 | 250 | PV | TBD | 2020-09-01 | 2020-09-03 | 2 | 0 | 2 | 2020-09-14 | 2020-11-25 | 51 | 0 | 51 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-12-14 |  | 2020-12-31 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2051 | Medfield | 2052 | 20 | PV | 456-H3 | 2012-02-09 | 2012-03-27 | 33 | 31 | 2 | 2012-03-28 | 2012-05-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-25 |  | 2012-06-26 | Online |  | Private | Y
2344 | Millis | 2052 | 1000 | PV | 65-H1 | 2013-02-05 | 2013-03-06 | 21 | 19 | 2 | 2013-03-21 | 2013-04-24 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2013-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2286612 | Medway | 02053 | 180 | PV | 65-H3 | 2018-07-12 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 |  |  | 2019-02-21 | TBD |  | 30 | [7 empty] | 2019-07-30 | Online |  | Private
1785 | Medway | 2053 | 350 | PV | 65-H3 | 2011-03-30 | 2011-04-29 | 22 | 20 | 2 | 2011-04-29 | 2011-06-16 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-29 |  | 2011-09-13 | Online |  | Gov't | Y
2397 | Medway | 2053 | 103 | PV | 65-H3 | 2013-06-05 | 2013-06-07 | 2 | 2 | 0 | 2013-10-10 | 2013-10-23 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-06 | Online |  | Private | Y
1910 | Medway | 2053 | 600 | PV | 65-H2 | 2011-09-12 | 2011-09-20 | 6 | 6 | 0 | 2011-09-20 | 2011-10-24 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 | 2012-06-20 | 98 | 0 | 98 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1989 | Medway | 2053 | 2000 | Other | 65-H2 | 2011-12-06 | 2011-12-12 | 4 | 2 | 2 | 2011-12-13 | 2012-02-14 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-04-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2398 | Medway | 2053 | 50 | PV | 65-H2 | 2013-06-10 |  | -29597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-06-10 | Private | Y
1536 | Medway | 2053 | 134 | PV | 65-H5 | 2009-12-17 | 2010-01-05 | 13 | 11 | 2 | 2010-01-05 | 2010-01-25 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-04-08 | Online |  | Private | Y
2049284 | Millis | 02054 | 300 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-01-30 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-11 | Online |  | Private
2049131 | Millis | 02054 | 42 | PV | 146-H10 | 2015-01-09 | 2015-01-12 | 1 | 0 | 1 | 2015-01-15 | 2015-03-26 | 50 | 15 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 | 2015-03-31 | 2015-07-23 | No | EXP | 30 | 2015-06-15 |  | -30122 |  | 0 |  | 2015-09-11 | 2015-09-11 | Online |  | Private
2049734 | Millis | 02054 | 75 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-03-31 | 53 | 40 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 | 2015-06-02 | 2015-09-30 | TBD | EXP | 30 | 2015-07-15 | 2015-07-15 | 0 |  | 0 |  | 2015-09-28 | 2015-09-28 | Online |  | Private
2048757 | Millis | 02054 | 131 | PV | 146-H10 | 2015-01-07 | 2015-01-08 | 1 | 0 | 1 | 2015-01-12 | 2015-03-31 | 56 | 2 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-14 | 2015-04-14 | 2015-08-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-18 | 2015-12-18 | Online |  | Private
2072811 | Millis | 02054 | 1002 | PV | 65-H3 | 2015-06-02 | 2015-06-03 | 1 | 0 | 1 | 2015-06-05 | 2015-07-06 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-24 | 2015-12-10 | 2016-01-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-11-01 | Online |  | Private
2065662 | Millis | 02054 | 2000 | PV | 65-H1 | 2015-04-24 | 2015-04-29 | 3 | 0 | 3 | 2015-04-30 | 2015-05-11 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-04 |  | 2015-12-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2057504 | Millis | 02054 | 296 | PV | 65-H3 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-03-13 | Private
2151 | Millis | 2054 | 135 | PV | 146-H10 | 2012-06-07 | 2012-09-27 | 80 | 75 | 5 | 2012-09-27 | 2012-10-04 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2367 | Millis | 2054 | 500 | PV | 146-H10 | 2013-03-21 | 2013-04-10 | 14 | 5 | 9 | 2013-04-10 | 2013-04-24 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-18 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 |  | Withdrawn |  | Private | Y
2028128 | Norfolk | 02056 | 22 | PV | 146-H3 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-14 | 2014-11-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online |  | Private
2026963 | Norfolk | 02056 | 499 | PV | 146-H3 | 2014-09-25 | 2014-09-26 | 1 | 0 | 1 | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-05-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-28 | Online |  | Private
2106809 | Norfolk | 02056 | 186.5 | PV | 146-H3 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-16 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-24 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-14 | Online |  | Private
2070139 | Norfolk | 02056 | 475 | PV | 146-H3 | 2015-05-19 | 2015-05-21 | 2 | 0 | 2 | 2015-05-25 | 2015-08-03 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2015-12-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1219 | Norfolk | 2056 | 95 | PV | 146-H2 | 2009-03-24 | 2009-03-30 | 4 | 3 | 1 | 2009-03-30 | 2009-04-30 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-06-23 | Online |  | Private | Y
1653 | Norfolk | 2056 | 82 | PV | 146-H9 | 2010-07-19 | 2010-08-06 | 14 | 14 | 0 | 2010-08-09 | 2010-09-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-03 |  | 2010-07-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-06-12 |  | 2011-07-14 | Online |  | Gov't | N
1655 | Norfolk | 2056 | 142 | PV | 146-H2 | 2010-07-23 | 2010-08-13 | 15 | 15 | 0 | 2010-08-18 | 2010-09-23 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-02-08 |  | 2012-02-08 | Online |  | Gov't | Y
2007 | Norfolk | 2056 | 45 | PV | 146-H3 | 2011-12-28 | 2012-01-03 | 4 | 0 | 4 | 2012-01-03 | 2012-02-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online |  | Private | Y
1846 | Norfolk | 2056 | 1375 | PV | 65-H1 | 2011-07-06 | 2011-07-07 | 1 | 0 | 1 | 2011-07-07 | 2011-08-25 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Gov't | N
2132 | Norfolk | 2056 | 14 | PV | 146-H3 | 2012-05-16 | 2012-06-27 | 30 | 30 | 0 | 2012-06-27 | 2012-07-31 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-06-18 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-07 |  | 2012-12-07 | Online |  | Gov't | Y
2352 | Norfolk | 2056 | 82 | PV | 65-H1 | 2013-02-22 | 2013-03-06 | 8 | 5 | 3 | 2013-03-07 | 2013-04-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-05-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-08 | Online |  | Private | Y
1988 | Norfolk | 2056 | 270 | PV | 146-H3 | 2011-12-01 | 2011-12-09 | 6 | 4 | 2 | 2011-12-15 | 2012-02-10 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2070 | Norfolk | 2056 | 5000 | PV | 65-H1 | 2012-03-09 | 2012-03-15 | 4 | 3 | 1 | 2012-03-15 | 2012-04-21 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 | 2013-03-25 | 180 | 0 | 180 |  |  | 0 | 0 | 0 |  |  | 2012-11-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2075 | Norfolk | 2056 | 82 | PV | 146-H9 | 2012-03-22 | 2012-04-26 | 25 | 22 | 3 | 2012-04-26 | 2012-06-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2396 | Norfolk | 2056 | 1000 | PV | 146-H3 | 2013-06-05 | 2013-06-10 | 3 | 3 | 0 | 2013-10-01 | 2013-10-23 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2402 | Norfolk | 2056 | 1000 | PV | 146-H3 | 2013-06-07 | 2013-07-10 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-08-26 | Gov't | Y
2425 | Norfolk | 2056 | 266 | PV | 146-H3 | 2013-07-29 | 2013-08-02 | 4 | 3 | 1 | 2013-08-05 |  | -29637 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-13 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2049971 | Sharon | 02067 | 15.8 | PV | 470-H3 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-22 | Online |  | Private
1167 | Sharon | 2067 | 20 | PV | 146-H7 | 2009-02-10 | 2010-07-08 | 367 | 366 | 1 | 2010-07-08 | 2010-08-02 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-17 |  | 2009-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Gov't | Y
2022 | Sharon | 2067 | 999 | PV | 146-H1 | 2012-01-17 | 2012-03-20 | 45 | 44 | 1 | 2012-03-20 | 2012-04-11 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-11 |  | 2012-07-03 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-09 | Online |  | Gov't | Y
2438 | Sharon | 2067 | 185 | PV | 146-H1 | 2013-09-12 | 2013-10-30 | 34 | 33 | 1 | 2013-10-30 |  | -29699 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-02 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online |  | Private | Y
1848 | Sharon | 2067 | 30 | PV | 470-H12 | 2011-07-13 | 2011-08-02 | 14 | 14 | 0 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2013-09-19 | 447 | 0 | 447 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-03-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online |  | Gov't | N
2018960 | South Walpole | 02071 | 85 | PV | 146-H3 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-19 | 2014-09-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-03 |  | 2015-03-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-20 | Online |  | Private
2134146 | South Walpole | 02071 | 0 |  | TBD | 2016-03-10 | 2016-03-10 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-17 | No | TBD | 30 | [8 empty] | Withdrawn |  | Private | N
2121 | Walpole | 2071 | 1398.22 | PV | 146-H9 | 2012-05-02 | 2012-05-04 | 2 | 2 | 0 | 2012-05-04 | 2012-07-09 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-08-10 |  | 2015-02-03 | Online |  | Gov't | Y
2120 | Walpole | 2071 | 1000 | PV | 146-H9 | 2012-05-01 | 2012-05-07 | 4 | 3 | 1 | 2012-05-08 | 2012-07-27 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online |  | Private | Y
2079372 | Walpole | 02081 | 153 | PV | 146-H3 | 2015-07-02 | 2015-07-09 | 5 | 0 | 5 | 2015-07-10 | 2015-07-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-16 |  | 2016-02-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-13 | Online |  | Private
2061451 | Walpole | 02081 | 2280 | PV | 146-H6 | 2015-04-02 | 2015-04-03 | 1 | 0 | 1 |  |  | 0 | 76 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2015-11-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-06-26 | Online |  | Private | N
2334218 | Walpole | 02081 | 32.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 28 | 0 | 28 | [20 empty] | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 | [7 empty] | 2021-02-04 | Online |  | Private
2334252 | Walpole | 02081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 28 | 0 | 28 | [20 empty] | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 | [7 empty] | 2021-02-04 | Online |  | Gov't
2334255 | Walpole | 02081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 28 | 0 | 28 | [20 empty] | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 | [7 empty] | 2021-02-04 | Online |  | Gov't
2334411 | Walpole | 02081 | 142 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-18 | 2019-05-30 | 29 | 0 | 29 | [20 empty] | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 | [7 empty] | 2021-02-09 | Online |  | Gov't
2333782 | Walpole | 02081 | 34.2 | PV | 146-H4 | 2019-04-08 | 2019-04-12 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 28 | 0 | 28 | [17 empty] | 0 | 0 | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2334415 | Walpole | 02081 | 129.6 | PV | TBD | 2019-04-11 |  | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-06-04 | 2020-01-08 | 2019-11-18 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Gov't
2334212 | Walpole | 02081 | 37.8 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-18 | 2019-05-31 | 30 | 0 | 30 | [20 empty] | 2019-06-04 | 2019-06-18 | 2020-06-04 | No | EXP | 30 | [8 empty] | In Queue |  | Private | N
2334039 | Walpole | 02081 | 131.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-06-15 | 40 | 0 | 40 | [20 empty] | 2019-06-18 | 2020-06-09 | 2020-10-31 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2036754 | Walpole | 02081 | 138 | PV | 146-H3 | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-11 |  | -30163 | 172 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 |  | 2016-03-14 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2334013 | Walpole | 02081 | 400 | PV | TBD | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 | [10 empty] | 2019-04-19 | 2020-06-03 | 279 | 0 | 279 | [5 empty] | 2020-11-17 | 2020-11-20 | 4 | 0 | 4 | 2020-02-21 | 2020-12-29 | 2021-01-15 | No |  | 60 | 2020-02-10 | [6 empty] | 2021-05-24 | Online |  | Private | N
2093 | Medfield | 2081 | 41 | PV | 146-H6 | 2012-04-03 | 2012-04-10 | 5 | 3 | 2 | 2012-04-10 | 2012-05-09 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-21 | Online |  | Private | Y
1589 | Walpole | 2081 | 104 | PV | 146-H6 | 2010-03-12 | 2010-03-26 | 10 | 10 | 0 | 2010-03-26 | 2010-04-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-14 | Online |  | Private | Y
1658 | Walpole | 2081 | 28 | PV | 2-105-105 | 2010-07-30 | 2010-08-17 | 12 | 12 | 0 | 2010-08-17 | 2010-10-01 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-29 | Online |  | Private | Y
1654 | Walpole | 2081 | 95 | PV | 146-H4 | 2010-07-19 | 2010-08-06 | 14 | 14 | 0 | 2010-08-09 | 2010-10-04 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-16 |  | 2011-03-21 | Online |  | Gov't | Y
2246 | Walpole | 2081 | 300 | PV | 4-85-592 | 2012-09-05 | 2012-09-26 | 15 | 15 | 0 | 2012-09-26 | 2012-12-18 | 59 | 46 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online |  | Private | Y
2434 | Walpole | 2081 | 24 | PV | 456-H1 | 2013-09-03 | 2013-09-11 | 6 | 5 | 1 | 2013-09-11 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-28 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online |  | Private | Y
1248 | Walpole | 2081 | 75 | PV | 146-H4 | 2009-04-10 | 2009-05-05 | 17 | 10 | 7 | 2009-05-05 | 2009-06-08 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2400 | Walpole | 2081 | 49 | PV | 146-H3 | 2013-06-12 | 2013-07-30 | 34 | 33 | 1 | 2013-07-30 |  | -29633 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-05-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2161690 | Westwood | 02090 | 164 | PV | 456-H4 | 2016-07-16 | 2016-08-09 | 17 | 0 | 17 | 2016-08-03 |  | -30419 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-09-14 | 2017-03-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online |  | Private
2165129 | Westwood | 02090 | 138 | PV | 456-H4 | 2016-07-14 | 2016-07-28 | 10 | 0 | 10 | 2016-08-22 |  | -30432 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-29 | 2017-03-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-25 | Online |  | Gov't
2161143 | Westwood | 02090 | 161 | PV | 469-H2 | 2016-07-29 | 2016-08-01 | 1 | 0 | 1 | 2016-08-05 |  | -30421 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-16 | 2016-09-23 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-27 | Online |  | Private
2059020 | Westwood | 02090 | 40 | PV | 456-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-04-14 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-01 | 2016-06-06 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2327596 | Westwood | 02090 | 0 |  | TBD | 2019-03-01 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-10-04 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1828 | Westwood | 2090 | 150 | Natural Gas | 148-H3 | 2011-06-13 | 2011-06-27 | 10 | 10 | 0 | 2011-06-27 | 2011-08-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-15 |  | 2011-07-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-07 | Online |  | Private | Y
2362 | Westwood | 2090 | 17 | PV | 148-H3 | 2013-03-25 | 2013-03-29 | 4 | 2 | 2 | 2013-04-02 | 2013-04-24 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-26 | Online |  | Private | Y
2449 | Westwood | 2090 | 20 | PV | 456-H1 | 2013-10-09 | 2013-10-15 | 4 | 2 | 2 | 2013-10-17 |  | -29690 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online |  | Private | Y
1710 | Boston | 2108 | 16 | PV | 2-1N45 | 2010-10-27 | 2010-11-09 | 9 | 5 | 4 | 2010-11-09 | 2010-12-07 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-15 | Online |  | Private | Y
2006387 | Boston | 02109 | 45 | PV | 3009 | 2014-05-19 | 2014-06-05 | 13 | 0 | 13 | 2014-06-12 | 2014-10-23 | 95 | 45 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-01-14 | No | EXP | 30 | 2015-01-12 | 2015-01-12 | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2385 | Boston | 2109 | 35 | PV | 3009 | 2013-05-10 | 2013-05-21 | 7 | 3 | 4 | 2013-05-23 | 2013-06-26 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | N
1198 | Roxbury | 2109 | 35 | PV | 323-05 | 2009-03-15 | 2009-04-02 | 14 | 11 | 3 | 2017-11-03 | 2009-05-05 | -2212 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-05 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-20 | Online |  | Gov't | Y
2115948 | Boston | 02110 | 75 | Natural Gas | 12-1N82N | 2015-12-17 | 2015-12-17 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2016-02-01 | Private
1484 | Boston | 2110 | 30 | PV | 528-129H | 2009-10-21 | 2009-11-09 | 13 | 11 | 2 | 2009-11-10 | 2009-12-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-11-06 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-18 |  | 2010-02-18 | Online |  | Private | Y
2138 | Boston | 2114 | 555 | Natural Gas | 2-1N11 | 2012-05-22 |  | -29323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2089121 | Boston | 02115 | 128 | PV | 492-1N14S | 2015-08-20 | 2015-08-20 | 0 | 0 | 0 | 2015-08-20 | 2015-08-25 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-10 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online |  | Private
2409588 | Boston | 02115 | 180 | PV | TBD | 2020-08-03 | 2020-08-04 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | [22 empty] | 2020-12-31 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2351 | Boston | 2115 | 5750 | Natural Gas | 335-1141 | 2013-02-21 | 2013-02-27 | 4 | 3 | 1 | 2013-02-28 | 2013-04-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1852 | Acushnet | 2116 | 1000 | PV | 2-241-241 | 2011-07-14 | 2011-07-20 | 4 | 4 | 0 | 2011-07-20 | 2011-08-25 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1851 | Acushnet | 2116 | 1000 | PV | 2-241-241 | 2011-07-07 | 2011-09-09 | 46 | 42 | 4 | 2011-09-09 | 2011-10-24 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1644 | Boston | 2116 | 195 | Natural Gas | 71-1N35 | 2010-07-09 | 2010-07-13 | 2 | 2 | 0 | 2010-07-13 | 2010-10-04 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
2009215 | Boston | 02118 | 75 | Natural Gas | 385-H17 | 2014-06-16 | 2014-06-20 | 4 | 0 | 4 | 2014-06-26 | 2014-07-08 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online |  | Gov't
2048937 | Boston | 02118 | 85 | Natural Gas | 318-10 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 2015-01-13 | 2015-01-29 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-29 | Online |  | Private
2062878 | Boston | 02118 | 100 | PV | 2-543-543 | 2015-04-08 | 2015-04-21 | 9 | 0 | 9 | 2015-04-23 | 2015-07-17 | 61 | 59 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-22 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-25 | Online |  | Private
2066533 | Boston | 02118 | 48 | PV | 385-H15 | 2015-04-28 | 2015-05-19 | 15 | 11 | 4 | 2015-05-20 | 2015-06-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-24 | 2015-06-24 | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-07-12 | 2016-07-22 | Online |  | Private
2088913 | Boston | 02118 | 75 | Natural Gas | 106-H4 | 2015-08-19 | 2015-08-21 | 2 | 0 | 2 | 2015-08-25 | 2015-12-15 | 80 | 72 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-21 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online |  | Private
2044564 | Boston | 02118 | 2000 | Natural Gas | 4910 | 2014-12-31 | 2014-12-31 | 0 | 0 | 0 | 2015-01-06 | 2015-01-07 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-08 | 2015-01-08 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-09 | Online |  | Private | N
2066237 | Boston | 02118 | 96 | PV | 528-129H | 2015-04-28 | 2015-04-29 | 1 | 0 | 1 | 2015-04-29 | 2015-06-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-21 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 |  | Withdrawn |  | Gov't
2147800 | Boston | 02118 | 336 | PV | 106-H4 | 2016-05-19 | 2016-05-20 | 1 | 0 | 1 | 2016-05-23 | 2016-08-10 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-15 | 2016-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1628 | Boston | 2118 | 177 | PV | 323-02 | 2010-05-27 | 2010-06-01 | 3 | 3 | 0 | 2010-06-01 | 2010-07-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-03 | Online |  | Private | Y
2345 | Boston | 2118 | 60 | PV | 323-02 | 2013-02-04 | 2013-04-01 | 40 | 36 | 4 | 2013-04-02 | 2013-05-13 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-27 |  | 2013-03-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online |  | Private | Y
2140 | Boston | 2118 | 60 | Natural Gas | 528-129H | 2012-05-23 | 2012-09-19 | 85 | 84 | 1 | 2012-09-19 | 2013-01-07 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-11 | Online |  | Gov't | Y
1498 | Boston | 2118 | 6600 | Natural Gas | 376-90 | 2009-11-09 |  | -28662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2084347 | Roxbury | 02119 | 27 | PV | 323-05 | 2015-07-27 | 2015-07-31 | 4 | 0 | 4 | 2015-08-04 | 2015-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-20 | 2015-08-19 | 2016-03-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online |  | Private
2051417 | Roxbury | 02119 | 42 | PV | 323-05 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | 2015-01-29 | 2015-03-30 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-25 | 2015-09-09 | 11 | 0 | 11 | 2015-03-25 | 2015-09-24 | 2016-04-01 | No | COMP | 160 | 2015-11-19 | 2015-11-19 | 0 |  | 0 |  | 2016-05-23 | 2016-09-28 | Online |  | Private
2089776 | Roxbury | 02119 | 33 | PV | 106-H5 | 2015-08-26 | 2015-08-27 | 1 | 44 | -43 | 2015-08-31 | 2015-12-21 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
1623 | Boston | 2119 | 242 | PV | 106-H4 | 2010-05-12 | 2010-05-25 | 9 | 9 | 0 | 2010-05-25 | 2010-06-22 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-09 |  | 2010-09-09 | Online |  | Private | Y
1884 | Boston | 2119 | 75 | PV | 323-05 | 2011-08-18 | 2011-08-25 | 5 | 5 | 0 | 2011-08-26 | 2011-10-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-04 |  | 2011-10-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-27 |  | 2012-07-06 | Online |  | Private | Y
2419 | Boston | 2119 | 50 | PV | 385-H19 | 2013-07-09 | 2013-07-12 | 3 | 1 | 2 | 2013-07-12 | 2013-08-26 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-15 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-09 | Online |  | Private | Y
2418 | Boston | 2119 | 36 | PV | 385-H1 | 2013-07-03 | 2013-08-20 | 34 | 28 | 6 | 2013-08-20 |  | -29648 | 0 | 0 | 2013-09-16 |  | -29667 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-24 | Online |  | Private | Y
2052 | Boston | 2119 | 18 | PV | 106-1N18H1 | 2012-02-12 |  | -29251 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1957 | Roxbury | 2119 | 75 | Natural Gas | 106-1N18H1 | 2011-11-01 | 2011-11-28 | 19 | 18 | 1 | 2011-11-28 | 2012-01-23 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-25 |  | 2011-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-21 | Online |  | Private | Y
1750 | Roxbury | 2119 | 75 | PV | 483-H3 | 2011-01-07 | 2011-03-22 | 52 | 51 | 1 | 2011-03-22 | 2011-04-06 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-05-24 | Online |  | Private | Y
1830 | Roxbury | 2119 | 150 | PV | 52-1487H1 | 2011-06-13 | 2011-06-24 | 9 | 9 | 0 | 2011-06-24 | 2011-07-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-07-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2088902 | Roxbury | 02120 | 75 | Natural Gas | 106-H8 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online |  | Private
1992441 | Roxbury | 02120 | 75 | Natural Gas | 5201 | 2014-03-18 | 2014-10-08 | 146 |  | 146 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-05-20 | Private
2148650 | Roxbury | 02120 | 936 | PV | 483-H6 | 2016-05-25 | 2016-05-31 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Gov't
2141087 | Dorchester | 02121 | 57 | PV | 106-H2 | 2016-04-15 | 2016-04-27 | 8 | 0 | 8 | 2016-04-27 | 2016-05-13 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-16 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2141870 | Dorchester | 02121 | 48 | PV | 106-H2 | 2016-04-21 | 2016-04-22 | 1 | 0 | 1 | 2016-05-12 | 2016-06-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2247148 | Dorchester | 02121 | 57.6 | PV | 483-H3 | 2017-10-20 | 2017-10-27 | 5 |  | 5 | 2017-11-29 |  | -30755 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
2409 | Boston | 2121 | 60 | PV | 323-02 | 2013-06-25 | 2013-06-27 | 2 | 2 | 0 | 2013-06-27 | 2013-08-26 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-05 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | Online |  | Private | Y
1608 | Dorchester | 2121 | 36 | PV | 143-151H1 | 2010-04-21 | 2010-06-07 | 33 | 33 | 0 | 2010-06-07 | 2010-07-13 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online |  | Gov't | Y
2466 | Dorchester | 2121 | 27 | PV | 483-H3 | 2013-10-29 | 2013-11-18 | 14 | 12 | 2 | 2013-11-19 |  | -29713 | 0 | 0 | 2013-12-05 | 2014-01-10 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-28 |  | 2013-12-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-25 | Online |  | Private | Y
2025617 | Dorchester | 02122 | 56 | PV | 466-1482H1 | 2014-09-18 | 2014-09-18 | 0 | 0 | 0 | 2014-09-22 | 2014-10-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-16 | 2014-10-17 | 2015-04-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online |  | Private
2156003 | Dorchester | 02122 | 170 | PV | 496-H1XY | 2016-07-01 | 2016-07-05 | 2 | 0 | 2 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-07-26 | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-01 | Online |  | Private
2015660 | Dorchester | 02122 | 89 | PV | 6702 | 2014-07-30 | 2014-08-01 | 2 | 0 | 2 | 2014-08-05 | 2014-08-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-09-29 | 2015-04-17 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 2015-03-10 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1554 | Boston | 2122 | 170 | PV | 106-H4 | 2010-01-08 | 2010-01-28 | 14 | 12 | 2 | 2010-01-28 | 2010-03-09 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-31 |  | 2010-03-31 | Online |  | Gov't | N
1609 | Dorchester | 2122 | 45 | PV | 466-1481H1 | 2010-04-23 | 2010-05-17 | 16 | 16 | 0 | 2010-05-18 | 2010-06-14 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-10 | Online |  | Gov't | Y
1440 | Dorchester | 2122 | 1240 | PV | 466-1482H1 | 2009-09-25 | 2009-09-30 | 3 | 2 | 1 | 2009-09-30 | 2009-10-16 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-23 |  | 2009-09-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2012-01-17 | Online |  |  | N
2240 | Dorchester | 2122 | 95 | PV | 511-1498H1 | 2012-08-28 | 2012-09-12 | 11 | 3 | 8 | 2012-09-12 | 2013-04-29 | 163 | 0 | 163 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-01-06 | Online |  | Private | Y
1724 | Dorchester | 2122 | 100 | PV | 466-1482H1 | 2010-12-03 | 2010-12-15 | 8 | 3 | 5 | 2010-12-16 | 2011-02-02 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2411 | Dorchester | 2122 | 85 | PV | 511-1498H1 | 2013-06-26 | 2013-06-28 | 2 | 1 | 1 | 2013-07-02 | 2013-08-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2174 | West Dennis | 2122 | 75 | PV | 4-92B-92B | 2012-07-25 | 2012-11-30 | 92 | 92 | 0 | 2012-11-30 | 2012-12-20 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 2013-05-05 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-05 | Online |  | Gov't | Y
2326537 | Dorchester | 2122 | 52.2 | PV | 466-1482H1 | 2019-02-07 |  | -31065 |  | 0 | 2019-02-22 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-08 | Online
2125462 | Dorchester | 02124 | 300 | PV | 311-07 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 | 2016-02-01 | 2016-02-19 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 |  | 2016-09-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-19 | Online |  | Private
2142846 | Dorchester | 02124 | 57 | PV | 106-H2 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 | 2016-05-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1283 | Dorchester | 2124 | 45 | PV | 496-H8 | 2009-05-21 | 2009-05-28 | 5 | 1 | 4 | 2009-05-29 | 2009-06-24 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-09-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-30 |  | 2009-12-30 | Online |  | Private | N
2100 | Dorchester | 2124 | 60 | Natural Gas | 511-1495H | 2012-04-13 | 2012-08-29 | 98 | 96 | 2 | 2012-08-29 | 2012-10-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Private | Y
2085514 | Dorchester | 02125 | 4600 | Natural Gas | 511-1497H | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 | 2015-08-11 | 2015-09-15 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2355449 | Dorchester | 02125 | 366.3 | PV | TBD | 2019-08-19 |  | 1 | 0 | 1 | 2019-08-22 | 2019-11-01 | 48 | 40 | 8 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-30 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
1847 | Boston | 2125 | 82 | PV | 511-1497H | 2011-07-11 | 2011-07-20 | 7 | 7 | 0 | 2011-07-20 | 2011-09-09 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | Online |  | Gov't | Y
1546 | Dorchester | 2125 | 75 | Natural Gas | 483-08 | 2010-01-06 | 2010-01-27 | 15 | 12 | 3 | 2010-01-27 | 2010-04-14 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-09 | Online |  | Private | N
1804 | Dorchester | 2125 | 250 | PV | 106-H2 | 2011-05-03 | 2011-05-09 | 4 | 1 | 3 | 2011-05-09 | 2011-05-10 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-27 | Online |  | Gov't | Y
1641 | Dorchester | 2125 | 197 | PV | 483-01 | 2010-06-29 | 2010-07-02 | 3 | 3 | 0 | 2010-10-01 |  | -28896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
1616 | Boston | 2126 | 11 | PV | 496-H8 | 2010-04-30 | 2010-05-12 | 8 | 8 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-05-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-26 |  | 2011-05-09 | Online |  | Gov't | Y
1645 | Mattapan | 2126 | 38 | PV | 311-05 | 2010-07-09 | 2010-07-14 | 3 | 3 | 0 | 2010-07-14 | 2010-08-24 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-06 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
1646 | Mattapan | 2126 | 14 | PV | 311-05 | 2010-07-09 | 2010-07-14 | 3 | 3 | 0 | 2010-07-14 | 2010-08-24 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online |  | Private | Y
1647 | Mattapan | 2126 | 15 | PV | 311-05 | 2010-07-13 | 2010-07-22 | 7 | 7 | 0 | 2010-07-22 | 2010-09-10 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-31 |  | 2012-01-31 | Online |  | Gov't | N
2158505 | South Boston | 02127 | 500 | PV | 106-H1 | 2016-07-15 | 2016-07-25 | 6 | 0 | 6 | 2016-07-25 |  | -30412 | 16 | 0 | 2016-08-31 |  | -30439 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-24 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2158507 | South Boston | 02127 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1816 | Boston | 2127 | 28 | PV | 385-H1 | 2011-05-26 | 2011-05-26 | 0 | 0 | 0 | 2011-05-26 | 2011-07-08 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-30 |  | 2011-10-04 | Online |  | Private | Y
1814 | Boston | 2127 | 50 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | 14 | 12 | 2 | 2011-06-06 | 2011-07-11 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2011-12-22 | Online |  | Private | Y
1815 | Boston | 2127 | 28 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | 14 | 10 | 4 | 2011-06-06 | 2011-07-07 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-08 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2012-01-09 | Online |  | Private | Y
2108 | South Boston | 2127 | 75 | Natural Gas | 106-H3 | 2012-04-19 | 2012-04-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2013-01-22 |  | 2013-01-22 | Online |  | Private | Y
2360 | South Boston | 2127 | 142 | PV | 106-H1 | 2013-03-21 | 2013-04-12 | 16 | 14 | 2 | 2013-04-17 | 2013-05-28 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-11-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1494 | Boston | 2127 | 7200 | Natural Gas | 515-193H | 2009-11-03 | 2009-11-10 | 5 | 5 | 0 | 2009-11-10 | 2009-11-25 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-04 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-02 |  | 2010-02-02 | Online |  | Private | N
2063964 | East Boston | 02128 | 499 | PV | 108-196H1 | 2015-04-16 | 2015-04-16 | 0 | 0 | 0 | 2015-05-01 | 2015-05-28 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2015-11-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-29 | 2017-04-06 | Online |  | Private | N
2006940 | East Boston | 02128 | 750 | PV | 108-196H1 | 2014-06-06 | 2014-06-09 | 1 | 0 | 1 | 2014-06-11 | 2014-06-30 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 |  | 2015-01-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2010040 | East Boston | 02128 | 552 | PV | 108-196H1 | 2014-06-26 | 2014-07-01 | 3 | 0 | 3 | 2014-07-03 | 2014-07-08 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-08 | 2014-10-06 | 2015-02-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1976430 | East Boston | 02128 | 100 | PV | 488-H4 | 2013-12-11 | 2013-12-12 | 1 | 0 | 1 | 2013-12-17 | 2015-03-10 | 320 | 3 | 317 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-21 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2063933 | East Boston | 02128 | 499 | PV | 108-196H1 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-07-07 | 60 | 28 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-07 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2162392 | East Boston | 02128 | 72 | PV | 488-H8 | 2016-08-04 | 2016-08-09 | 3 | 0 | 3 | 2016-08-11 |  | -30425 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-16 |  | 2017-03-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2396083 | East Boston | 02128 | 1700 | Steam Turbine | TBD | 2020-05-01 |  | 1 | 0 | 1 | 2020-05-01 |  | 169 | 0 | 169 | [22 empty] | 2020-12-08 | TBD |  | 30 | [8 empty] | In Queue |  | Gov't
1581 | Boston | 2128 | 200 | PV | 592-70H | 2010-02-18 | 2010-02-23 | 3 | 3 | 0 | 2010-02-24 | 2010-04-20 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online |  | Gov't | Y
1885 | Boston | 2128 | 75 | PV | 108-196H1 | 2011-08-17 | 2011-08-22 | 3 | 1 | 2 | 2011-08-22 | 2011-09-12 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-05-15 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2014-06-09 | 2014-06-09 | 2014-06-16 | Online |  | Gov't | Y
1706 | East Boston | 2128 | 82 | PV | 592-72XY | 2010-10-20 | 2010-11-04 | 11 | 9 | 2 | 2010-11-08 | 2010-12-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-20 |  | 2010-11-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-02-14 | Online |  | Private | Y
1791 | East Boston | 2128 | 345 | PV | 592-72XY | 2011-04-08 | 2011-10-27 | 144 | 142 | 2 | 2011-10-28 | 2011-12-06 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-07 |  | 2011-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-12 |  |  |  |  | Private | Y
2101 | East Boston | 2128 | 60 | Natural Gas | MC-8 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Private | Y
2017443 | Charlestown | 02129 | 391 | PV | 10-H1 | 2014-08-05 | 2014-08-11 | 4 | 0 | 4 | 2014-08-15 | 2014-11-21 | 70 | 34 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-04-11 | 2016-04-14 | 3 | 0 | 3 | 2015-03-26 | 2016-07-28 | 2016-12-15 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2123364 | Charlestown | 02129 | 30 | PV | 250-H5 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-01-27 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-01 | 2016-08-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2140031 | Charlestown | 02129 | 288 | PV | 10-H1 | 2016-04-11 | 2016-04-12 | 1 | 0 | 1 | 2016-04-25 | 2016-05-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-11-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2380 | Boston | 2129 | 75 | Natural Gas | 530-178 | 2013-05-01 | 2013-05-06 | 3 | 3 | 0 | 2013-05-06 | 2013-06-18 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-27 | Online |  | Private | Y
1574 | Charlestown | 2129 | 555 | Diesel | 10-H1 | 2010-02-16 | 2010-02-17 | 1 | 1 | 0 | 2010-02-17 | 2010-03-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-04-12 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online |  | Gov't | Y
1709 | Charlestown | 2129 | 30 | Wind | 287-148H1 | 2010-10-27 | 2010-11-23 | 19 | 17 | 2 | 2010-11-23 | 2011-01-21 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2010-11-25 | No | STD |  |  |  | 0 | 0 | 0 | 2011-09-22 |  | 2011-09-30 | Online |  | Gov't | N
1638 | Charlestown | 2129 | 1500 | Wind | 387-148H1 | 2010-06-28 | 2010-07-02 | 4 | 4 | 0 | 2010-07-07 | 2010-08-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-10-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-11-01 | Online |  | Gov't | Y
1794 | Charlestown | 2129 | 250 | Natural Gas | 250-H3 | 2011-04-25 | 2011-04-27 | 2 | 1 | 1 | 2011-05-02 | 2011-06-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-17 | Online |  | Private | Y
2467 | Charlestown | 2129 | 11 | PV | 10-H2 | 2013-11-08 | 2013-11-14 | 4 | 1 | 3 | 2013-11-15 |  | -29711 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-19 |  | 2013-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-14 | Online |  | Private | Y
1994005 | Jamaica Plain | 02130 | 34.2 | PV | 284-1300H1 | 2014-03-26 | 2014-04-01 | 4 | 0 | 4 | 2014-04-01 | 2014-04-23 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-15 | 2014-11-03 | 2014-10-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online |  | Private | N
2005440 | Jamaica Plain | 02130 | 1640 | Natural Gas | 496-H4 | 2014-05-30 | 2015-05-16 | 250 | 0 | 250 | 2014-06-05 | 2015-01-19 | 162 | 148 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-01-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-30 | Online
2143903 | Jamaica Plain | 02130 | 30 | PV | 284-07 | 2016-04-28 | 2016-05-03 | 3 | 0 | 3 | 2016-05-13 | 2016-05-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-26 | 2016-06-02 | 2016-12-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-02 | Online |  | Private
2083371 | Jamaica Plain | 02130 | 28 | PV | 496-H4 | 2015-07-23 | 2015-07-24 | 1 | 0 | 1 | 2015-07-28 | 2015-08-07 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2016-03-15 | 2016-08-25 | TBD | EXP | 30 | 2016-08-04 | 2016-08-04 | 0 |  | 0 |  |  |  | In Queue |  | Private
2103067 | Jamaica Plain | 02130 | 17 | PV | 554-79H1 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-13 | 115 | 0 | 115 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2402933 | Jamaica Plain | 02130 | 1489 | PV | TBD | 2020-06-17 | 2020-06-19 | 2 | 0 | 2 | 2020-06-29 |  | 128 | 128 | 0 | [22 empty] | 2020-12-15 | No |  | 30 | [8 empty] | In Queue | 2020-06-30 | Private
1330 | Jamaica Plain | 2130 | 150 | Natural Gas | 284-1360H2 | 2009-06-23 | 2009-06-25 | 2 | 2 | 0 | 2009-06-25 | 2009-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-11-24 | Online |  | Private | Y
1510 | Jamaica Plain | 2130 | 75 | Natural Gas | 350-H2 | 2009-10-16 | 2009-11-18 | 23 | 0 | 23 | 2009-11-19 | 2009-12-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-02-01 | Online |  | Private | Y
1792 | Jamaica Plain | 2130 | 30 | PV | 284-1360H2 | 2011-04-12 | 2011-04-15 | 3 | 2 | 1 | 2011-04-15 | 2011-05-18 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-23 |  | 2011-06-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-08-25 | Online |  | Private | Y
1667 | Jamaica Plain | 2130 | 75 | PV | 350-H2 | 2010-08-23 | 2011-08-01 | 245 | 245 | 0 | 2011-08-01 | 2011-09-06 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-02-24 | Online |  | Gov't | Y
1771 | Jamaica Plain | 2130 | 30 | PV | 396-01 | 2011-02-17 | 2011-04-22 | 46 | 45 | 1 | 2011-04-22 | 2011-06-22 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-31 |  | 2012-07-31 | Online |  | Private | Y
1800 | Jamaica Plain | 2130 | 100 | PV | 496-H4 | 2011-04-29 | 2011-05-12 | 9 | 8 | 1 | 2011-05-13 | 2011-09-28 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-18 |  | 2013-01-18 | Online |  | Private | Y
2379 | Jamaica Plain | 2130 | 60 | PV | 396 | 2013-05-01 | 2013-05-14 | 9 | 9 | 0 | 2013-05-16 | 2013-06-27 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Gov't | N
2042 | Jamaica Plain | 2130 | 100 | PV | 284-1300H1 | 2012-02-01 | 2012-02-13 | 8 | 7 | 1 | 2012-02-13 | 2012-03-20 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | 67 | 0 | 67 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-23 | Online |  | Gov't | N
1759 | Roslindale | 2131 | 26 | PV | 13-H1 | 2011-02-01 | 2011-02-11 | 8 | 6 | 2 | 2011-02-11 | 2011-04-05 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-06 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-03 |  | 2011-08-04 | Online |  | Private | Y
1904 | Roslindale | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-06 | 3 | 3 | 0 | 2011-09-06 | 2011-11-29 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-03 |  | 2012-04-03 | Online |  | Private | Y
1907 | Roslindale | 2131 | 35 | PV | 1310 | 2011-09-02 | 2011-10-25 | 37 | 35 | 2 | 2011-10-25 | 2012-05-10 | 142 | 0 | 142 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-14 | Online |  | Gov't | Y
1901 | Roslindale | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-17 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1903 | Roslindale | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-17 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1902 | Roslindale | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-22 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2127824 | West Roxbury | 02132 | 40 | PV | 468-01 | 2016-02-05 | 2016-02-08 | 1 | 0 | 1 | 2016-02-10 | 2016-03-01 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2145690 | West Roxbury | 02132 | 684 | PV | 374-04 | 2016-05-06 | 2016-05-11 | 3 | 0 | 3 | 2016-05-16 |  | -30362 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 2016-12-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2160263 | West Roxbury | 02132 | 250 | Natural Gas | 374-2215 | 2016-07-25 | 2016-07-27 | 2 | 0 | 2 | 2016-08-01 |  | -30417 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-18 | 2016-09-09 | 2017-03-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
1626 | West Roxbury | 2132 | 37 | PV | 374-04 | 2010-05-21 | 2010-05-25 | 2 | 2 | 0 | 2010-05-25 | 2010-06-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-07-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-08-13 | Online |  | Private | Y
2077 | West Roxbury | 2132 | 100 | PV | 468-01 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2012-09-13 | Online |  | Private | Y
2301 | West Roxbury | 2132 | 60 | PV | 468-01 | 2012-11-09 | 2012-11-16 | 5 | 2 | 3 | 2012-11-16 | 2013-03-18 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2012919 | Allston | 02134 | 90 | PV | 548-92H3 | 2014-07-15 | 2014-07-22 | 5 | 0 | 5 | 2014-08-04 | 2014-07-29 | -6 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 | 2014-10-27 | 2015-02-23 | No | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2014-12-19 | 2015-01-02 | Online |  | Private | N
2246186 | Allston | 02134 | 66.6 | PV | 3614 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-27 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-27 | Online
2225 | Allston | 2134 | 354 | PV | 467-H11 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-11-19 | 66 | 21 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-14 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Gov't | Y
1715 | Boston | 2134 | 75 | Natural Gas | 329-H1 | 2010-11-10 | 2010-11-19 | 7 | 4 | 3 | 2010-11-23 | 2010-12-23 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-19 | 2011-04-19 | 2011-04-21 | Online |  | Private | Y
677 | Allston | 2134 | 4300 | Natural Gas | 341-82 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2007-11-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | N
2128801 | Brighton | 02135 | 111 | PV | 329-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 |  | -30300 | 129 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-19 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online | 2016-02-18 | Private
2155327 | Brighton | 02135 | 75 | PV | 315-H11 | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 | 2016-07-25 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 |  | 2017-02-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-07 | Online |  | Private
1982906 | Brighton | 02135 | 75 | Natural Gas | 467-H13 | 2014-01-16 | 2014-01-16 | 0 | 0 | 0 | 2014-01-24 | 2014-02-07 | 10 | 0 | 10 | 2014-02-20 | 2014-03-24 | 22 | 0 | 22 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-27 | 2014-04-17 | 2014-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2133578 | Brighton | 02135 | 48 | PV | 329-H7 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-13 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1630 | Brighton | 2135 | 75 | Natural Gas | 329-H7 | 2010-06-01 | 2010-06-03 | 2 | 2 | 0 | 2010-06-03 | 2010-07-07 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-06-21 | Online |  | Private | Y
1995 | Brighton | 2135 | 75 | Natural Gas | 329-H3 | 2011-12-13 | 2011-12-16 | 3 | 2 | 1 | 2011-12-20 | 2012-02-02 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-03-16 | Online |  | Private | Y
1384 | Brighton | 2135 | 16 | PV | 329-H5 | 2009-07-23 | 2009-07-29 | 4 | 0 | 4 | 2009-07-29 | 2009-08-14 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-18 |  | 2009-07-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1383 | Brighton | 2135 | 58 | PV | 329-H5 | 2009-07-24 | 2009-07-30 | 4 | 3 | 1 | 2009-07-30 | 2009-08-20 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1752 | Brighton | 2135 | 14 | PV | 315-H5 | 2011-01-14 |  | -28971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2126908 | Hyde Park | 02136 | 168 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2016-03-18 | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-02 | Online |  | Private
1990011 | Hyde Park | 02136 | 3190 | PV | 496-H2 | 2014-02-28 | 2014-03-06 | 4 | 0 | 4 | 2014-03-10 | 2014-04-29 | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 |  | 2014-10-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-28 | Online |  | Gov't | Y
2126921 | Hyde Park | 02136 | 192 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online |  | Private
2126922 | Hyde Park | 02136 | 288 | PV | 344-1411H2 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-05-19 | 74 | 31 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-12 | 2017-04-18 |  | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online |  | Private
2128422 | Hyde Park | 02136 | 540 | PV | 344-1413H1 | 2016-02-09 | 2016-02-10 | 1 | 0 | 1 | 2016-02-12 | 2016-02-22 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 | 2016-06-06 | 2016-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2110822 | Hyde Park | 02136 | 1200 | PV | 344-07 | 2015-12-03 | 2015-12-04 | 1 | 0 | 1 | 2015-12-08 | 2016-07-18 | 159 | 86 | 73 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2184405 | Hyde Park | 02136 | 510 | PV | TBD | 2016-12-01 |  | 1 | 0 | 1 | 2016-12-06 | 2016-12-23 | 13 | 2 | 11 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-11 | No | EXP | 30 | [8 empty] | Withdrawn |  | Private
2377419 | Hyde Park | 02136 | 0 |  | TBD | 2020-01-02 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-06 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2340378 | Waltham | 02136 | 0 |  | TBD | 2019-05-17 |  | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-26 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2373 | Dedham | 2136 | 2000 | PV | 344-1413H1 | 2013-04-19 | 2013-04-29 | 6 | 3 | 3 | 2013-04-30 | 2013-06-18 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online |  | Private | Y
1919 | Hyde Park | 2136 | 177 | PV | 496-H2 | 2011-09-21 | 2011-09-26 | 3 | 3 | 0 | 2011-09-26 | 2011-11-07 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-27 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-23 | Online |  | Private | Y
2021 | Hyde Park | 2136 | 975 | PV | 344-07 | 2012-01-16 | 2012-01-24 | 6 | 5 | 1 | 2012-01-27 | 2012-04-06 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2087199 | Cambridge | 02138 | 171.1 | PV | 828-1105 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2015-08-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-27 | 2015-08-26 | 2016-03-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-26 | Online |  | Private
2340888 | Cambridge | 02138 | 66.6 | PV | 819-1NE4 | 2019-05-21 | 2019-05-22 | 1 | 0 | 1 | 2019-05-23 | 2019-06-18 | 17 | 0 | 17 | [20 empty] | 2019-06-18 |  | 2019-12-30 | TBD | EXP | 30 | [7 empty] | 2020-12-16 | Online |  | Private
2135260 | Cambridge | 02138 | 405 | PV | 819-1NB3 | 2016-03-16 | 2016-03-17 | 1 | 0 | 1 | 2016-03-22 | 2016-04-20 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1503 | Cambridge | 2138 | 66 | PV | 827-31 | 2009-11-13 | 2009-11-20 | 5 | 4 | 1 | 2009-11-20 | 2010-01-04 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2010-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-16 | Online |  | Private | N
1673 | Cambridge | 2138 | 75 | PV | 828-1104H1 | 2010-09-09 | 2010-09-17 | 6 | 5 | 1 | 2010-09-17 | 2010-10-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-10 | Online |  | Gov't | Y
1711 | Cambridge | 2138 | 250 | PV | 828-1104H1 | 2010-11-02 | 2010-11-10 | 6 | 5 | 1 | 2010-11-18 | 2010-12-16 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2011-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2011-06-16 | Online |  | Gov't | N
2451 | Cambridge | 2138 | 70 | PV | 827-31 | 2013-10-15 | 2013-10-23 | 6 | 5 | 1 | 2013-10-23 |  | -29694 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  | 2013-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-11 | Online |  | Private | Y
743 | Cambridge | 2138 | 8 | PV | 819-1NE6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | N
2051340 | Cambridge | 02139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-30 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-07 | Online |  | Private
2041623 | Cambridge | 02139 | 22.8 | PV | 814-12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 |  | 2015-07-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-05 | Online |  | Private | N
2041620 | Cambridge | 02139 | 22.8 | PV | 815-10 | 2014-12-08 | 2015-01-02 | 19 | 0 | 19 | 2015-01-02 | 2015-02-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-03 |  | 2015-07-15 | TBD | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  |  | 2015-06-12 | Online |  | Private
2051393 | Cambridge | 02139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-24 | Online |  | Private
2066481 | Cambridge | 02139 | 568 | PV | 817-05 | 2015-04-28 | 2015-05-05 | 5 | 0 | 5 | 2015-05-07 | 2015-05-27 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-27 |  | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-24 | Online |  | Private
2124635 | Cambridge | 02139 | 4400 | Natural Gas | 831-1110 | 2016-01-06 | 2016-01-07 | 1 | 0 | 1 | 2016-01-27 |  | -30284 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-06-07 | 2017-08-11 |  | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2020-12-14 | Online |  | Private
2002879 | Cambridge | 02139 | 802 | PV | 817-05 | 2014-05-15 | 2014-05-16 | 1 | 0 | 1 | 2014-05-19 | 2014-06-10 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-07-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2115956 | Cambridge | 02139 | 1000 | Natural Gas | 875-1N35B | 2015-12-18 | 2015-12-19 | 1 | 0 | 1 | 2015-12-24 | 2016-01-18 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2130635 | Cambridge | 02139 | 27 | PV | 815-10 | 2016-02-23 | 2016-03-09 | 11 | 0 | 11 | 2016-03-15 | 2016-06-23 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-15 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2324814 | Cambridge | 02139 | 44000 | CHP | 831-1314 | 2019-02-12 | 2019-02-19 | 4 | 0 | 4 | [10 empty] | 2019-02-19 | 2019-03-04 | 9 | 0 | 9 | [7 empty] | 0 | 0 | 0 |  |  | 2020-06-30 | No |  | 60 | [8 empty] | In Queue |  | Private
1756 | Cambridge | 2139 | 150 | Natural Gas | 831-1324 | 2011-01-24 | 2011-02-01 | 6 | 3 | 3 | 2011-02-01 | 2011-04-14 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-15 |  | 2011-02-20 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-05-31 | Online |  | Private | Y
1437 | Cambridge | 2139 | 30 | PV | 814-14 | 2009-09-15 | 2009-09-28 | 9 | 9 | 0 | 2009-09-28 | 2010-10-26 | 281 | 0 | 281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-12 |  | 2010-03-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-26 | Online |  | Private | N
1705 | Cambridge | 2139 | 1500 | Natural Gas | 813-36 | 2010-10-18 | 2011-04-04 | 120 | 118 | 2 | 2011-04-04 | 2011-05-11 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online |  | Gov't | Y
1769 | Cambridge | 2139 | 82 | PV | 831-1324 | 2011-02-14 | 2011-03-07 | 15 | 14 | 1 | 2011-03-07 | 2011-04-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-05-21 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2013-01-24 | Online |  | Private | Y
2280 | Cambridge | 2139 | 7500 | Natural Gas | 817-48 | 2012-10-17 | 2012-10-25 | 6 | 5 | 1 | 2012-10-26 | 2013-02-06 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online |  | Private | Y
1668 | Cambridge | 2139 | 30 | PV | 819-1NB2 | 2010-08-20 | 2010-09-15 | 18 | 17 | 1 | 2010-09-15 | 2010-10-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2012-12-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
1289 | Cambridge | 2139 | 75 | PV | 817-02 | 2009-05-19 | 2009-06-04 | 12 | 5 | 7 | 2009-06-05 | 2011-10-22 | 620 | 0 | 620 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-24 |  | 2009-12-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2290 | Cambridge | 2139 | 14 | PV | 817-03 | 2012-10-26 | 2013-01-07 | 51 | 51 | 0 | 2013-01-11 | 2013-02-10 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
582 | Cambridge | 2139 | 21500 | Natural Gas | 811-36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 1998-01-01 | Online |  |  | N
2130419 | Cambridge | 02140 | 36 | PV | 824-26 | 2016-02-23 | 2016-02-26 | 3 | 0 | 3 | 2016-03-03 | 2016-03-15 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-23 | Online |  | Private
2135869 | Cambridge | 02140 | 270 | PV | 828-1NA9 | 2016-03-21 | 2016-03-29 | 6 | 0 | 6 | 2016-04-04 | 2016-04-06 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-05-22 | [7 empty] | 0 |  | 0 | [5 empty] | Private
2065777 | Cambridge | 02140 | 36 | PV | 826-20 | 2015-04-24 | 2015-04-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1633 | Cambridge | 2140 | 41 | PV | 826-28 | 2010-06-09 | 2010-06-18 | 7 | 6 | 1 | 2010-06-18 | 2010-07-28 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-30 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-14 |  | 2010-12-14 | Online |  | Gov't | Y
2003 | Cambridge | 2140 | 85 | Natural Gas | 825-20 | 2011-12-16 | 2011-12-20 | 2 | 0 | 2 | 2011-12-27 | 2012-03-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-23 | Online |  | Private | N
2004 | Cambridge | 2140 | 85 | Natural Gas | 825-20 | 2011-12-20 | 2011-12-23 | 3 | 1 | 2 | 2011-12-27 | 2012-03-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-10-10 |  | 2012-10-10 | Online |  | Private | Y
2376 | Cambridge | 2140 | 28 | PV | 825-26 | 2013-04-30 | 2013-06-19 | 36 | 36 | 0 | 2013-06-20 | 2013-07-10 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-08 | Online |  | Private | Y
2378 | Cambridge | 2140 | 35 | PV | 825-26 | 2013-04-30 | 2013-05-06 | 4 | 4 | 0 | 2013-05-20 | 2013-06-26 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-24 | Online |  | Private | Y
2406 | Cambridge | 2140 | 40 | PV | 824-25 | 2013-06-18 | 2013-06-24 | 4 | 2 | 2 | 2013-06-24 | 2013-08-26 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-01 |  | -29678 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-09 |  | 2013-12-15 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Gov't | Y
1723 | Cambridge | 2141 | 28 | PV | 820-15 | 2010-12-07 | 2010-12-15 | 6 | 3 | 3 | 2010-12-16 | 2011-02-10 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-16 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-20 |  | 2011-05-04 | Online |  | Private | Y
1544 | Cambridge | 2141 | 29 | PV | 811-37 | 2010-01-05 | 2010-06-30 | 126 | 123 | 3 | 2010-06-30 | 2010-09-10 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-06-01 |  | 2011-06-01 | Online |  | Gov't | N
1918 | Cambridge | 2141 | 38 | Natural Gas | 812-16 | 2011-09-20 | 2011-09-21 | 1 | 0 | 1 | 2011-09-21 | 2012-01-30 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-04 | Online |  | Private | Y
1994170 | Cambridge | 02142 | 75 | Natural Gas | 875-1328 | 2014-01-22 | 2014-03-27 | 46 | 0 | 46 | 2014-03-31 | 2014-04-02 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-15 | 2014-09-03 | 2014-10-31 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online |  | Private
1629 | Cambridge | 2142 | 75 | Natural Gas | 875-1N35B | 2010-05-27 | 2010-06-02 | 4 | 4 | 0 | 2010-06-02 | 2010-07-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-08 |  | 2010-09-02 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-18 |  | 2010-11-18 | Online |  | Private | Y
1631 | Cambridge | 2142 | 85 | Natural Gas | 875-1N39A | 2010-06-01 | 2010-06-04 | 3 | 3 | 0 | 2010-06-04 | 2010-07-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-07 | Online |  | Private | Y
1956 | Cambridge | 2142 | 75 | Natural Gas | 875-1N25A | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2011-11-30 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
1929 | Cambridge | 2142 | 5750 | Natural Gas | 831-1301 | 2011-10-03 | 2011-10-04 | 1 | 1 | 0 | 2011-10-04 | 2011-11-08 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-06-27 | Online |  | Gov't | N
2150 | Cambridge | 2142 | 1966 | Natural Gas | 814-17 | 2012-06-11 | 2012-07-26 | 33 | 30 | 3 | 2012-07-27 | 2012-08-31 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-04 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-29 | Online |  | Gov't | Y
2104944 | Somerville | 02143 | 996 | PV | 387-148H2 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2250669 | Somerville | 02143 | 150 | PV | 387-148H2 | 2017-11-10 | 2017-11-14 | 2 |  | 2 | 2017-12-08 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-26 | 2018-03-12 | [6 empty] | 0 |  | 0
1505 | Somerville | 2143 | 75 | Natural Gas | 250-1N81H1 | 2009-11-13 | 2009-11-17 | 2 | 1 | 1 | 2009-11-17 | 2009-12-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-11-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-11 |  | 2010-02-11 | Online |  | Private | Y
1780 | Somerville | 2143 | 120 | PV | 250-1N39H1 | 2011-03-10 | 2011-04-28 | 35 | 34 | 1 | 2011-04-28 | 2011-06-16 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-19 |  | 2012-06-19 | Online |  | Private | Y
1203 | Somerville | 2143 | 48 | PV | 250-1N81H1 | 2009-03-15 | 2009-03-18 | 3 | 0 | 3 | 2009-03-19 |  | -28495 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
2428 | Somerville | 2143 | 85 | PV | 250-1N35H2 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29652 | 0 | 0 | 2013-09-24 |  | -29673 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2097809 | Somerville | 02144 | 20 | PV | 227-51H2 | 2015-10-05 | 2015-10-06 | 1 | 0 | 1 | 2015-10-12 | 2016-03-17 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1226 | Somerville | 2144 | 85 | Natural Gas | 250-1N81H1 | 2009-03-30 | 2009-11-02 | 155 | 152 | 3 | 2009-11-02 | 2009-11-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-16 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-08 | Online |  | Private | N
1606 | Somerville | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-06-07 | 33 | 33 | 0 | 2010-06-07 | 2010-07-13 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online |  | Gov't | N
1605 | Somerville | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-25 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
1604 | Somerville | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-30 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
2027112 | Somerville | 02145 | 50 | PV | 14N26 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | 2014-10-01 | 2014-11-21 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-08 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-21 | 2014-12-24 | Online |  | Private
2084293 | Somerville | 02145 | 54 | PV | 250-1N81H1 | 2015-07-27 | 2015-07-28 | 1 | 0 | 1 | 2015-07-31 | 2015-08-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-10 | Online |  | Private
2043499 | Somerville | 02145 | 50 | PV | 585-114H4 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-23 | Online |  | Private
2094631 | Somerville | 02145 | 24 | PV | 250-H4XY | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-10-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-14 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-30 | Online |  | Private
2132326 | Somerville | 02145 | 84 | PV | 227-52H3 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-05-14 | 47 | 32 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-31 | 2016-06-03 | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-14 | Online |  | Private
2093280 | Somerville | 02145 | 999 | PV | 250-H3 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-10 |  | -30185 |  | 0 |  |  | 0 | 0 | 0 | 2015-09-15 | 2015-10-16 | 23 | 2 | 21 | 2016-02-19 |  | -30301 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 | 2016-02-04 | [6 empty] | 0 |  | 0 |  |  | 2017-05-02 | Online |  | Private | N
2131317 | Somerville | 02145 | 56 | PV | 227-51H2 | 2016-02-29 |  | -30307 | 0 | 0 | 2016-03-03 | 2016-05-27 | 61 | 48 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2141311 | Somerville | 02145 | 18 | PV | 250-H4XY | 2016-04-18 | 2016-04-20 | 2 | 0 | 2 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-15 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2406866 | Somerville | 02145 | 23 | PV | TBD | 2020-07-15 | 2020-07-20 | 3 | 0 | 3 | 2020-08-04 | 2020-08-21 | 13 | 0 | 13 | [20 empty] | 2020-08-25 | 2020-09-10 | 2020-12-15 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2136141 | Somerville | 02145 | 499.5 | PV | 250-H4XY | 2016-03-21 | 2016-03-23 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2016-03-31 | Private
1512 | Somerville | 2145 | 198 | PV | 250-1N81H1 | 2009-11-17 | 2009-11-23 | 4 | 2 | 2 | 2009-11-24 | 2009-12-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online |  | Private | N
2304 | Somerville | 2145 | 42 | PV | 250-1N90H2 | 2012-11-19 | 2012-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2125197 | Chelsea | 02150 | 491 | PV | 488-H2 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-02-19 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-28 | Online |  | Private
2056434 | Chelsea | 02150 | 394.4 | PV | 488-H2 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-28 |  | 2016-09-30 | TBD | EXP | 30 | 2016-03-02 |  | -30309 |  | 0 |  |  |  | Withdrawn |  | Private
1171 | Chelsea | 2150 | 44 | PV | 488-H3 | 2009-02-11 | 2009-04-29 | 55 | 54 | 1 | 2009-04-29 | 2009-05-22 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-27 |  | 2009-03-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-02 |  | 2009-07-02 | Online |  | Private | Y
1652 | Chelsea | 2150 | 175 | PV | 488-H2 | 2010-07-19 | 2010-08-30 | 30 | 30 | 0 | 2010-08-31 | 2010-12-14 | 75 | 0 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2011-02-08 | Online |  | Gov't | Y
2060 | Chelsea | 2150 | 30 | PV | 488-H2 | 2012-02-24 | 2012-06-26 | 87 | 86 | 1 | 2012-06-26 | 2012-07-31 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-01 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online |  | Private | Y
1762 | Chelsea | 2150 | 39 | PV | 488-H2 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online |  | Gov't | N
1265 | Chelsea | 2150 | 60 | PV | 488-H6 | 2009-04-29 | 2009-06-09 | 29 | 27 | 2 | 2009-06-15 | 2009-07-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-11-30 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2384 | Chelsea | 2150 | 50 | PV | 488-H7 | 2013-05-08 | 2013-05-16 | 6 | 5 | 1 | 2013-05-21 | 2013-09-05 | 77 | 0 | 77 | 2013-09-13 | 2013-09-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-17 |  | 2013-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1204 | Winthrop | 2152 | 1200 | Wind | TRM-PTC | 2009-03-20 | 2009-03-23 | 1 | 0 | 1 | 2009-03-24 | 2009-04-17 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-06 |  | 2009-05-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-06-18 | Online |  | Gov't | N
1507 | Waltham | 2154 | 60 | Natural Gas | 33-H2 | 2009-11-16 | 2009-11-19 | 3 | 2 | 1 | 2009-11-19 | 2009-12-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-04 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online |  | Gov't | Y
2008179 | Stoneham | 02180 | 15.9 | PV | 375-H8 | 2014-06-11 | 2014-06-17 | 4 | 0 | 4 | 2014-06-20 | 2014-09-10 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-11 | 2014-09-11 | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-11 | Online |  | Private | N
2176517 | Stoneham | 02180 | 0 | PV | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-20 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1779 | Stoneham | 2180 | 72 | PV | 375-H7 | 2011-03-10 | 2011-05-12 | 45 | 44 | 1 | 2011-05-13 | 2011-07-08 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2013-01-28 | Online |  | Private | Y
2093526 | Milton | 02186 | 512 | PV | 496-H1XY | 2015-09-11 | 2015-09-15 | 2 | 0 | 2 | 2015-09-18 | 2015-10-26 | 26 | 205 | -179 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2015-10-27 | Private
2158997 | Milton | 02186 | 30 | PV | 362-1209H1 | 2016-07-18 | 2016-07-20 | 2 | 0 | 2 | 2016-07-28 | 2016-08-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-15 |  | 2017-02-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1401 | Milton | 2186 | 2000 | Wind | 496-H7 | 2009-08-10 | 2009-10-14 | 47 | 47 | 0 | 2009-10-14 | 2009-11-04 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-05 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-03-02 | Online |  | Private | Y
1770 | Milton | 2186 | 200 | PV | 4306 | 2011-02-11 | 2011-02-28 | 11 | 9 | 2 | 2011-02-28 | 2011-03-25 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-06-07 | Online |  | Private | Y
1789 | Milton | 2186 | 60 | PV | 362-05 | 2011-04-05 | 2011-05-06 | 23 | 23 | 0 | 2011-05-09 | 2011-06-29 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-06 |  | 2011-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online |  | Private | Y
1812 | Milton | 2186 | 400 | PV | 496-H7 | 2011-05-16 | 2011-05-31 | 11 | 9 | 2 | 2011-06-01 | 2011-07-20 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-21 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-24 | Online |  | Gov't | N
1813 | Milton | 2186 | 200 | PV | 4303 | 2011-05-17 | 2011-06-06 | 14 | 13 | 1 | 2011-06-06 | 2011-07-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-15 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-25 | Online |  | Private | Y
1811 | Milton | 2186 | 100 | PV | 496-H7 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-09-13 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-27 | Online |  | Gov't | N
1810 | Milton | 2186 | 75 | PV | 311-04 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-07-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | Online |  | Gov't | N
1725 | Milton | 2186 | 26 | PV | 496-H7 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-03 | Online |  | Gov't | N
1600 | Milton | 2186 | 60 | PV | 362-02 | 2010-04-21 |  | -28779 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | N
1703 | Milton | 2186 | 2000 | Wind | 362-02 | 2010-10-07 |  | -28900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1277 | Milton | 2186 | 75 | Natural Gas | 496-H2 | 2009-05-14 | 2009-06-18 | 25 | 24 | 1 | 2009-06-18 | 2009-07-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-15 | Online |  | Private | Y
2105436 | South Boston | 02210 | 2280 | PV | 106-H1 | 2015-11-10 | 2015-11-11 | 1 | 0 | 1 | 2015-11-18 | 2016-04-19 | 109 | 24 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online |  | Private
2157900 | South Boston | 02210 | 456 | PV | 385-H18 | 2016-06-09 | 2016-06-22 | 9 | 0 | 9 | 2016-07-14 |  | -30405 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-23 | 2017-02-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-07-20 | Online |  | Private
1720 | Boston | 2210 | 200 | PV | 385-H15 | 2010-11-18 | 2010-12-06 | 12 | 10 | 2 | 2010-12-07 | 2010-12-28 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-26 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-08 | Online | 2021-12-29 | Private | Y
1718 | Boston | 2210 | 125 | PV | 385-H10 | 2010-11-16 | 2010-11-24 | 6 | 3 | 3 | 2010-11-30 | 2010-12-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Online | 2021-12-29 | Private | Y
1719 | Boston | 2210 | 200 | PV | 385-H5 | 2010-11-16 | 2010-11-24 | 6 | 2 | 4 | 2010-11-30 | 2011-01-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Online | 2021-12-29 | Private | Y
2386 | Boston | 2210 | 75 | Natural Gas | 385-H4 | 2013-05-17 | 2013-06-10 | 16 | 15 | 1 | 2013-06-10 | 2013-07-16 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-21 |  | 2013-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-30 | Online |  | Private | Y
2163 | Boston | 2210 | 250 | Natural Gas | 385-H5 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-11 | 2013-12-11 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2218 | Boston | 2210 | 500 | PV | 385-H12 | 2012-08-14 |  | -29383 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2151408 | Boston | 02215 | 367 | PV | 350-H5 | 2016-06-03 | 2016-06-04 | 1 | 0 | 1 | 2016-06-09 | 2016-06-21 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1949 | Boston | 2215 | 225 | PV | 329-H4 | 2011-10-27 | 2011-10-28 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | Y
2133 | Boston | 2218 | 102 | PV | 574-70H | 2012-05-14 | 2012-06-01 | 14 | 12 | 2 | 2012-06-01 | 2012-07-13 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-19 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-24 | Online |  | Private | Y
1701 | Boston | 2222 | 28 | PV | 2-1N43 | 2010-10-18 | 2010-10-19 | 1 | 1 | 0 | 2010-10-19 | 2010-10-29 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-21 |  | 2010-10-25 | Online |  | Private | Y
2106584 | Carver | 02330 | 28 | PV | 3-10-929 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-09 |  | 2016-06-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online |  | Private | N
2147609 | Carver | 02330 | 20 | PV | 3-10-929 | 2016-05-18 | 2016-05-23 | 3 | 0 | 3 | 2016-05-26 | 2016-08-19 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-22 | 2017-01-19 | 2016-12-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online |  | Private | N
2051273 | Carver | 02330 | 1500 | PV | 3-10-930 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-23 |  | -30021 | 395 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2017-01-25 |  | -30542 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-02 | 2015-05-14 | 2015-08-26 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online | 2015-01-27 | Private
2158976 | Carver | 02330 | 0 | PV | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD | TBD | 30 | [6 empty] | 2018-04-30 | 2018-04-30 | Online |  | Private
2093250 | Carver | 02330 | 990 | PV | 3-10-929 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2016-03-19 | 134 | 37 | 97 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 |  | 2016-04-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-01-23 | Online |  | Private
2116312 | Carver | 02330 | 2000 | PV | 3-10-929 | 2015-12-18 | 2015-12-22 | 2 | 0 | 2 | 2015-12-30 |  | -30264 | 155 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2019-02-28 | Online | 2016-01-11 | Private
1972386 | Carver | 02330 | 5000 | PV | 3-83-83 | 2013-12-02 | 2013-12-03 | 1 | 0 | 1 | 2013-12-05 | 2013-12-27 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2014-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2114902 | Carver | 02330 | 499 | PV | 3-10-929 | 2015-12-14 | 2015-12-22 | 6 | 0 | 6 | 2015-12-23 | 2015-12-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-10 | 2016-07-04 | 2016-07-21 | TBD | EXP | 30 | 2016-07-06 | 2016-07-06 | 0 |  | 0 |  |  |  | In Queue |  | Private
2135263 | Carver | 02330 | 490 | PV | 3-81-950 | 2016-03-17 | 2016-03-18 | 1 | 0 | 1 | 2016-03-28 | 2016-04-18 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-06 |  | 2016-10-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2328021 | Carver | 02330 | 499 | PV | TBD | 2019-03-04 | 2019-03-07 | 3 | 0 | 3 | 2019-03-07 | 2019-03-20 | 7 | 0 | 7 | [17 empty] | 0 | 0 | 0 |  | 2019-04-17 | 2020-10-16 | No | EXP | 30 | 2020-10-14 | [7 empty] | In Queue |  | Private
2361932 | Carver | 02330 | 2000 | PV & Battery | TBD | 2019-10-01 |  | 1 | 0 | 1 | 2019-10-10 | 2019-10-24 | 9 | 8 | 1 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2107748 | Carver | 02330 | 5966 | PV & Battery | 3-83-83 | 2015-11-19 | 2015-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online | 2015-11-25 | Private
2281481 | Carver | 02330 | 2000 | PV & Battery | TBD | 2018-06-11 | 2018-06-12 | 1 | 0 | 1 | [10 empty] | 2018-06-13 |  | 484 | 135 | 349 | [7 empty] | 0 | 0 | 0 | 2019-05-20 |  | 2019-06-28 | No |  | 60 | [8 empty] | In Queue |  | Private
2296366 | Carver | 02330 | 4650 | PV | TBD | 2018-09-12 | 2018-09-18 | 4 | 0 | 4 | 2018-09-18 |  | 569 | 569 | 0 | [17 empty] | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 | [8 empty] | In Queue | 2018-09-20 | Private
2338333 | Carver | 02330 | 0 |  | TBD | 2019-05-06 |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-12 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2361931 | Carver | 02330 | 0 |  | TBD | 2019-10-01 |  | 134 | 0 | 134 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2158504 | Carver | 02330 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1955 | Carver | 2330 | 225 | PV | 3-10-917 | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2011-12-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
2105 | Carver | 2330 | 833 | PV | 3-10-929 | 2012-04-17 | 2012-04-19 | 2 | 1 | 1 | 2012-04-19 | 2012-05-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 | 2013-04-12 | 210 | 0 | 210 |  |  | 0 | 0 | 0 | 2013-11-15 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-07-01 | Online |  | Private | Y
2327 | Carver | 2330 | 2000 | PV | 433-H8 | 2013-01-08 | 2013-01-11 | 3 | 3 | 0 | 2013-01-16 | 2013-02-12 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-01-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-06-13 | 2013-06-13 | 2016-10-04 | Online |  | Private | Y
1819 | Carver | 2330 | 833 | PV | 3-10-930 | 2011-05-25 | 2011-08-22 | 63 | 58 | 5 | 2011-08-22 | 2011-10-24 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2012-01-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1959 | Carver | 2330 | 21 | PV | 3-11-11 | 2011-11-04 | 2011-11-14 | 6 | 5 | 1 | 2011-11-14 | 2012-01-31 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2122 | Carver | 2330 | 95 | PV | 3-10-930 | 2012-05-04 | 2012-05-16 | 8 | 8 | 0 | 2012-05-22 | 2012-08-03 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-22 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-08-22 | Private | Y
1951 | Carver | 2330 | 150 | PV | 3-10-917 | 2011-10-24 |  | -29172 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2355 | Carver | 2330 | 250 | PV | 3-51-901 | 2013-03-06 | 2013-03-06 | 0 | 0 | 0 | 2013-03-08 |  | -29531 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-05-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2427 | Carver | 2330 | 5000 | PV | 3-10-930 | 2013-08-13 | 2013-08-22 | 7 | 6 | 1 | 2013-08-22 |  | -29650 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-03 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-09-03 | Private | Y
2045 | Plymouth | 2330 | 2000 | PV | 3-10-10 | 2012-01-25 | 2012-03-01 | 26 | 16 | 10 | 2012-03-01 | 2012-04-25 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-25 |  | 2012-01-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  |  | Withdrawn |  | Private | Y
2143 | Duxbury | 2331 | 500 | PV | 3-26-903 | 2012-06-04 | 2012-06-19 | 11 | 10 | 1 | 2012-06-19 | 2012-11-30 | 118 | 0 | 118 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-10-02 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-26 |  | 2014-06-23 | Online |  | Gov't | Y
2069125 | Duxbury | 02332 | 16 | PV | 3-23-981 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-07-09 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-06 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-20 | 2016-01-25 | Online |  | Private
2117204 | Duxbury | 02332 | 360 | PV | 3-27-970 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-08-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2117207 | Duxbury | 02332 | 480 | PV | 3-26-903 | 2015-12-24 | 2015-12-29 | 3 | 13 | -10 | 2016-01-05 |  | -30268 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-08-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1921 | Carver | 2346 | 1000 | PV | 930 | 2011-09-22 | 2011-09-28 | 4 | 1 | 3 | 2011-09-28 | 2011-10-28 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1997 | Carver | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
1998 | Carver | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
1999 | Carver | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
2000 | Carver | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
2002 | Carver | 2355 | 200 | PV | 3-10-10 | 2011-12-16 | 2011-12-20 | 2 | 0 | 2 | 2011-12-27 | 2012-03-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2001 | Carver | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-03-12 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2009028 | Plymouth | 02360 | 20 | PV | 3-89-926 | 2014-06-13 | 2014-06-17 | 2 | 0 | 2 | 2014-06-20 | 2014-08-15 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-09 | 2014-11-17 | Online |  | Private
2020496 | Plymouth | 02360 | 92.8 | PV | 3-14-911 | 2014-08-25 | 2014-08-28 | 3 | 0 | 3 | 2014-08-28 | 2014-11-10 | 52 | 16 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-17 |  | 2015-04-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2015-01-02 | Online |  | Private
2018969 | Plymouth | 02360 | 50 | PV | 4-81A-406 | 2014-08-19 | 2014-08-19 | 0 | 0 | 0 | 2014-08-21 | 2014-09-08 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-16 | 2015-03-02 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2015-03-30 | Online |  | Private
2029298 | Plymouth | 02360 | 30.9 | PV | 3-89-926 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-31 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online |  | Private
1977739 | Plymouth | 02360 | 600 | PV | 3-13-943 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-01-15 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | 2014-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-01-02 | 2015-10-21 | Online |  | GOV'T
2053997 | Plymouth | 02360 | 112 | PV | 3-13-936 | 2015-02-05 | 2015-02-05 | 0 | 0 | 0 | 2015-02-10 | 2015-03-26 | 32 | 2 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-09-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-09 | 2016-03-29 | Online |  | Private
2133265 | Plymouth | 02360 | 66 | PV | 3-12-12 | 2016-03-07 | 2016-03-10 | 3 | 0 | 3 | 2016-03-15 | 2016-04-25 | 29 | 24 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 | 2016-07-25 | 2016-10-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-03 | Online |  | Private
2082435 | Plymouth | 02360 | 79 | PV | 3-12-12 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2016-02-10 | 144 | 50 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-01 | 2016-05-25 | 2016-10-14 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online |  | Private
2140340 | Plymouth | 02360 | 364.3 | PV | 3-89-922 | 2016-04-12 | 2016-04-13 | 1 | 0 | 1 | 2016-04-18 | 2016-05-02 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-13 | 2016-12-22 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-24 | Online |  | Private
2132061 | Plymouth | 02360 | 2000 | PV | 3-89-925 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-06-02 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 |  | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
2099704 | Plymouth | 02360 | 996 | PV | 31313 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-19 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-09-06 | Online |  | Private
2251494 | Plymouth | 02360 | 20 | PV | 40613 | 2017-11-15 | 2017-11-21 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
2054256 | Plymouth | 02360 | 1000 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 |  | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-10-03 | Online |  | Private
1988060 | Plymouth | 02360 | 38 | PV | 3-12-41J1 | 2014-02-18 | 2014-07-10 | 102 | 0 | 102 | 2014-02-19 | 2014-04-07 | 33 | 1 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-04 | 2016-01-05 | 2016-10-07 | Yes | EXP | 30 | 2016-07-22 |  | -30411 |  | 0 |  |  |  | In Queue |  | Private | N
2035699 | Plymouth | 02360 | 993.6 | PV | 3-89-926 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | 2014-11-18 | 2014-11-19 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-05 |  | 2015-06-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2029874 | Plymouth | 02360 | 225 | Natural Gas | 3-13-943 | 2014-10-09 | 2014-10-10 | 1 | 0 | 1 | 2014-10-27 | 2014-11-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-10 |  | 2015-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2036912 | Plymouth | 02360 | 960 | PV | 3-12-12 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2014-12-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-06-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-01 |  | Withdrawn |  | Private
2021322 | Plymouth | 02360 | 500 | PV | 3-12-12 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-04 | 2015-01-30 | 106 | 0 | 106 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-05 |  | 2015-04-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2054376 | Plymouth | 02360 | 500 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 | 2015-02-19 | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2036219 | Plymouth | 02360 | 4000 | PV | 3-14-934 | 2014-11-18 | 2014-12-16 | 20 | 0 | 20 | 2014-12-16 | 2015-02-23 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 | 2015-08-25 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2056169 | Plymouth | 02360 | 100 | PV | 3-14-911 | 2015-02-26 | 2015-02-26 | 0 | 0 | 0 | 2015-03-04 | 2015-03-10 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-27 |  | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2059927 | Plymouth | 02360 | 500 | PV | 3-12-12 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-04-21 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 |  | 2015-10-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2090094 | Plymouth | 02360 | 4999 | PV | 3-012-012 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-08-31 | 2015-10-14 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-03 |  | 2016-11-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2129461 | Plymouth | 02360 | 308 | PV | 3-71-71 | 2016-02-17 | 2016-02-18 | 1 | 0 | 1 | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-25 |  | 2016-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2103303 | Plymouth | 02360 | 5976 | PV | 3-73-73 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-05 | 109 | 15 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2114928 | Plymouth | 02360 | 57 | PV | 3-89-922 | 2015-12-14 | 2015-12-15 | 1 | 0 | 1 | 2015-12-16 | 2016-04-26 | 94 | 74 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-07-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2096227 | Plymouth | 02360 | 4000 | PV | 3-88-924 | 2015-09-25 | 2015-09-26 | 1 | 0 | 1 | 2015-09-30 | 2016-04-28 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2129459 | Plymouth | 02360 | 840 | PV | 3-12-12 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 | 2016-05-18 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-08-02 | 2016-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2336042 | Plymouth | 02360 | 366 | PV | TBD | 2019-04-23 | 2019-04-23 | 1 | 0 | 1 | 2019-04-23 | 2019-05-22 | 21 | 0 | 21 | [20 empty] | 2019-05-23 | 2020-09-02 | 2019-11-29 | TBD | EXP | 30 | [7 empty] | 2023-03-28 | Online |  | Private
2072210 | Plymouth | 02360 | 112 | PV | 3-12-12 | 2015-05-28 | 2015-06-01 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2099348 | Plymouth | 02360 | 420 | PV | 3-12-12 | 2015-10-08 | 2015-10-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2135261 | Plymouth | 02360 | 2000 | PV | 3-89-922 | 2016-03-16 | 2016-03-31 | 11 | 0 | 11 | 2016-04-07 |  | -30335 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2240998 | Plymouth | 02360 | 0 |  | TBD | 2017-10-18 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-25 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2287723 | Plymouth | 02360 | 780 | PV | TBD | 2018-07-19 |  | 435 | 0 | 435 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-28 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2335156 | Plymouth | 02360 | 0 |  | TBD | 2019-04-16 |  | 352 | 0 | 352 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-21 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2242294 | Plymouth | 02360 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-05 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2245196 | Plymouth | 02360 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2237 | Barnstable | 2360 | 11 | PV | 4-82-518 | 2012-08-29 | 2012-10-16 | 34 | 34 | 0 | 2012-10-16 | 2013-01-30 | 76 | 65 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1252 | Plymouth | 2360 | 750 | Wind | 3-71-937 | 2009-04-17 | 2009-04-22 | 3 | 0 | 3 | 2009-04-22 | 2009-05-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-18 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-08-05 | Online |  | Private | Y
1290 | Plymouth | 2360 | 750 | Wind | 3-14-911 | 2009-05-26 | 2009-06-02 | 5 | 2 | 3 | 2009-06-02 | 2009-06-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-29 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-09-17 | Online |  | Private | N
1696 | Plymouth | 2360 | 95 | PV | 3-14-911 | 2010-10-07 | 2010-10-20 | 9 | 4 | 5 | 2010-10-20 | 2010-12-23 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-10-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-04-08 | Online |  | Private | Y
1751 | Plymouth | 2360 | 49 | PV | 3-13-936 | 2011-01-17 | 2011-01-28 | 9 | 8 | 1 | 2011-01-28 | 2011-03-15 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online |  | Private | Y
1856 | Plymouth | 2360 | 190 | PV | 3-12-12 | 2011-07-22 | 2011-07-28 | 4 | 4 | 0 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
1547 | Plymouth | 2360 | 250 | PV | 3-13-943 | 2010-01-06 | 2010-03-03 | 40 | 37 | 3 | 2010-03-03 | 2010-03-25 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  | 2010-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-22 |  | 2012-03-30 | Online |  | Private | Y
2036 | Plymouth | 2360 | 500 | PV | 3-89-89 | 2012-01-27 | 2012-02-07 | 7 | 7 | 0 | 2012-02-07 | 2012-04-20 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-23 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-17 | Online |  | Private | Y
1240 | Plymouth | 2360 | 1670 | Wind | 3-71-71 | 2009-04-08 | 2009-04-16 | 6 | 4 | 2 | 2009-04-16 | 2009-05-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2012-11-08 | Online |  | Private | N
2267 | Plymouth | 2360 | 12 | PV | 3-11-11 | 2012-10-01 | 2012-11-28 | 42 | 41 | 1 | 2012-11-28 | 2013-01-15 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online |  | Private | Y
2285 | Plymouth | 2360 | 75 | PV | 3-14-911 | 2012-10-25 | 2012-11-06 | 8 | 8 | 0 | 2012-11-06 | 2013-01-30 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online |  | Private | Y
2299 | Plymouth | 2360 | 132 | PV | 3-89-925 | 2012-11-06 | 2012-11-27 | 15 | 15 | 0 | 2012-11-27 | 2013-03-18 | 79 | 0 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-12-27 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-24 | Online |  | Private | Y
2221 | Plymouth | 2360 | 649.74 | PV | 3-13-13 | 2012-08-15 | 2012-08-17 | 2 | 1 | 1 | 2012-08-17 | 2012-09-20 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online |  | Private | Y
2254 | Plymouth | 2360 | 361 | PV | 3-14-911 | 2012-09-17 | 2012-09-20 | 3 | 2 | 1 | 2012-09-20 | 2012-10-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-10 | 2013-09-19 | 94 | 0 | 94 | 2013-09-26 |  | -29675 | 0 | 0 | 2013-12-09 |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online |  | Private | N
2433 | Plymouth | 2360 | 75 | PV | 3-13-943 | 2013-08-22 | 2013-08-27 | 3 | 0 | 3 | 2013-08-27 |  | -29653 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-23 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online |  | Private | Y
2283 | Plymouth | 2360 | 4260 | PV | 3-71-71 | 2012-10-23 | 2012-10-25 | 2 | 2 | 0 | 2012-10-26 | 2012-12-18 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online |  | Gov't | Y
2048 | Plymouth | 2360 | 11 | PV | 3-89-925 | 2012-01-02 | 2012-03-26 | 60 | 31 | 29 | 2012-03-26 | 2012-04-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 | 2013-01-17 | 111 | 0 | 111 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
2313 | Plymouth | 2360 | 333 | PV | 3-13-943 | 2012-12-05 | 2012-12-13 | 6 | 1 | 5 | 2012-12-13 | 2013-02-12 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-26 |  | 2013-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-14 | Online |  | Gov't | Y
2155/2249 | Plymouth | 2360 | 4750 | PV | 3-89-89 | 2012-06-20 | 2012-07-09 | 13 | 4 | 9 | 2012-07-18 | 2012-08-27 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-28 |  | 2012-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-02 | Online |  | Gov't | Y
2106 | Plymouth | 2360 | 500 | PV | 3-11-11 | 2012-04-18 | 2012-04-25 | 5 | 4 | 1 | 2012-04-25 | 2012-07-09 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-10 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-12 | Online |  | Private | Y
2354 | Plymouth | 2360 | 85 | PV | 3-73-927 | 2013-03-04 | 2013-05-30 | 63 | 62 | 1 | 2013-05-30 | 2013-07-02 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-26 |  | 2013-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-08-11 | Online |  | Gov't | Y
1992 | Plymouth | 2360 | 2000 | Wind | 3-89-925 | 2011-12-08 | 2011-12-13 | 3 | 0 | 3 | 2011-12-15 | 2012-01-03 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  | 2011-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2016-08-10 | Online |  | Gov't | Y
2102 | Plymouth | 2360 | 2000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online |  | Private | Y
2103 | Plymouth | 2360 | 4000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online |  | Private | Y
2104 | Plymouth | 2360 | 1500 | Wind | 3-89-925 | 2012-04-18 | 2012-04-20 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-08-10 | Online | 2013-07-24 | Private | Y
1500 | Plymouth | 2360 | 1650 | Wind | 3-89-926 | 2009-11-10 | 2009-11-12 | 2 | 2 | 0 | 2009-11-12 | 2009-12-23 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-21 |  |  | Withdrawn |  | Private | N
1393 | Plymouth | 2360 | 1670 | Wind | 3-89-926 | 2009-08-07 | 2009-12-17 | 94 | 93 | 1 | 2009-12-18 | 2010-09-21 | 197 | 0 | 197 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-04 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-10 |  |  | Withdrawn |  | Gov't | N
1537 | Plymouth | 2360 | 30 | PV | 3-73-938 | 2009-12-22 | 2010-10-19 | 215 | 215 | 0 | 2010-10-19 | 2010-10-20 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-10-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2035 | Plymouth | 2360 | 2000 | PV | 3-89-89 | 2012-01-16 | 2012-02-02 | 13 | 5 | 8 | 2012-02-02 | 2012-03-16 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | 131 | 0 | 131 |  |  | 0 | 0 | 0 | 2014-04-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-05-28 | Gov't | Y
2078 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2079 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2080 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2081 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2082 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2083 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2084 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2085 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2086 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2118 | Plymouth | 2360 | 1000 | PV | 3311 | 2012-04-27 | 2012-05-01 | 2 | 2 | 0 | 2012-05-03 | 2012-06-12 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2119 | Plymouth | 2360 | 2000 | PV | 3-89-926 | 2012-05-01 | 2012-05-07 | 4 | 3 | 1 | 2012-05-08 | 2012-07-27 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2087 | Plymouth | 2360 | 1000 | PV | 3-89-925 | 2012-03-30 | 2012-04-05 | 4 | 4 | 0 | 2012-07-03 | 2012-08-14 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-03-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2162 | Plymouth | 2360 | 142 | PV | 3-13-936 | 2012-07-10 | 2012-07-18 | 6 | 1 | 5 | 2012-07-18 | 2012-08-24 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-08-28 | Private | Y
2158 | Plymouth | 2360 | 2000 | PV | 3-89-89 | 2012-06-27 | 2012-08-16 | 36 | 29 | 7 | 2012-08-16 | 2012-09-17 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-18 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
2157 | Plymouth | 2360 | 2000 | PV | 3-89-89 | 2012-06-20 | 2012-08-16 | 41 | 33 | 8 | 2012-08-16 | 2012-09-21 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2318 | Plymouth | 2360 | 333 | PV | 3-13-943 | 2012-12-14 | 2012-12-27 | 9 | 9 | 0 | 2012-12-27 | 2013-01-29 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2013-01-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2284 | Plymouth | 2360 | 75 | PV | 3-14-911 | 2012-10-19 |  | -29431 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
658 | Plymouth | 2360 | 4500 | Wind | 3-89-926 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | N
2023232 | Kingston | 02364 | 21.5 | PV | 3-15-15 | 2014-09-18 |  |  | 0 | 0 | 2014-09-10 | 2014-10-01 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 |  | 2015-04-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-23 | 2014-12-31 | Online |  | Private
2018246 | Kingston | 02364 | 142.5 | PV | 3-15-15 | 2014-08-11 | 2014-08-15 | 4 | 0 | 4 | 2014-09-24 | 2014-10-02 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-10 |  | 2015-03-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-08-17 | 2015-08-18 | Online |  | PRIVATE
2140338 | Kingston | 02364 | 50 | PV | 3-17-17 | 2016-04-11 | 2016-04-12 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-28 | Online |  | Private
2143458 | Kingston | 02364 | 48 | PV | 3-17-910 | 2016-04-26 | 2016-04-28 | 2 | 0 | 2 | 2016-05-02 | 2016-05-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-16 | 2016-09-08 | 2016-12-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online |  | Private
2020238 | Kingston | 02364 | 668 | PV | 3-909-909 | 2014-08-21 | 2014-08-25 | 2 | 0 | 2 | 2014-08-25 | 2014-09-15 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 | 2015-07-15 | 2015-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-08 | Online |  | Private
2117310 | Kingston | 02364 | 600 | PV | 3-26-902 | 2015-12-29 | 2015-12-30 | 1 | 2 | -1 | 2016-01-05 | 2016-07-19 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-12-31 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-19 | Online |  | Private
2402374 | Kingston | 02364 | 499 | PV | TBD | 2020-06-15 | 2020-06-16 | 1 | 0 | 1 | 2020-06-30 |  | 128 | 0 | 128 | [22 empty] | 2020-12-20 | TBD |  | 30 | [8 empty] | In Queue |  | Private
1531 | Kingston | 2364 | 100 | Wind | 3-17-913 | 2009-12-16 | 2010-01-18 | 23 | 22 | 1 | 2010-01-18 | 2010-02-12 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-22 |  | 2009-12-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-07 |  | 2010-04-07 | Online |  | Private | Y
1656 | Kingston | 2364 | 6000 | Wind | 3-17-913 | 2010-07-27 | 2010-08-17 | 15 | 14 | 1 | 2010-08-17 | 2010-10-01 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-28 | Online |  | Gov't | Y
1833 | Kingston | 2364 | 2100 | Wind | 3-17-913 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-09-16 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-21 | Online |  | Gov't | Y
2015 | Kingston | 2364 | 60 | PV | 3-17-913 | 2012-01-02 | 2012-02-01 | 22 | 16 | 6 | 2012-02-01 | 2012-03-02 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-05 |  | 2012-02-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-03 | Online |  | Private | Y
2097 | Kingston | 2364 | 11 | PV | 3-909-909 | 2012-04-11 | 2012-04-12 | 1 | 1 | 0 | 2012-04-12 | 2012-05-04 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-04 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-05 | Online |  | Private | Y
2348 | Kingston | 2364 | 33 | PV | 3-26-902 | 2013-02-08 | 2013-03-06 | 18 | 18 | 0 | 2013-03-11 | 2013-05-10 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2013-11-08 | Online |  | Private | Y
2457 | Kingston | 2364 | 19 | PV | 3-17-910 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29697 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
1776 | Kingston | 2364 | 1000 | PV | 3-17-913 | 2011-03-07 | 2011-03-07 | 0 | 0 | 0 | 2011-03-07 | 2011-04-28 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  |  | Withdrawn |  | Gov't | N
2401 | Plympton | 2364 | 4000 | PV | 3-15-901 | 2013-06-12 | 2013-08-20 | 49 | 48 | 1 | 2013-08-21 |  | -29649 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-11 | 2013-11-23 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 2014-05-09 |  | 2013-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2082491 | Plympton | 02367 | 990 | PV | 3-51-901 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2015-08-06 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 | 2016-02-10 | 2016-02-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-09 | Online |  | Private
1988677 | Plympton | 02367 | 840 | PV | 3-15-906 | 2014-01-30 | 2014-02-20 | 15 | 0 | 15 | 2014-03-07 | 2014-03-12 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-09-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-12-19 | Online |  | Private
2099482 | Plympton | 02367 | 880 | PV | 3-51-901 | 2015-10-08 | 2015-10-21 | 9 | 0 | 9 | 2015-10-27 | 2015-11-17 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-01 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2122696 | Plympton | 02367 | 24 | PV | 3-51-901 | 2016-01-13 | 2016-01-15 | 2 | 0 | 2 | 2016-01-18 | 2016-02-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-23 |  | 2016-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2137254 | Plympton | 02367 | 972 | PV | 3-51-901 | 2016-03-29 | 2016-03-30 | 1 | 0 | 1 | 2016-04-07 | 2016-05-18 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2016-11-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2065453 | Plympton | 02367 | 5000 | PV | 3-51-DSS | 2015-04-23 | 2015-04-24 | 1 | 0 | 1 | 2015-05-04 | 2016-05-24 | 276 | 256 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2159738 | Plympton | 02367 | 1000 | PV | TBD | 2016-07-21 |  | 312 | 0 | 312 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-02 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2262995 | Plympton | 02367 | 2310 | PV & Battery | TBD | 2018-02-13 | 2018-02-27 | 9 | 0 | 9 | [10 empty] | 2018-03-05 | 2018-08-24 | 115 | 96 | 19 | [7 empty] | 0 | 0 | 0 | 2018-08-28 |  | 2020-03-30 | TBD |  | 60 | [8 empty] | In Queue |  | Private
2394682 | Plympton | 02367 | 4975 | PV | TBD | 2020-04-20 |  | 178 | 0 | 178 | 2020-04-25 |  | 0 | 0 | 0 | [22 empty] | 2020-11-24 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2241681 | Plympton | 02367 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-31 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2315 | Plympton | 2367 | 12 | PV | 3-51-901 | 2012-12-12 | 2012-12-20 | 6 | 4 | 2 | 2012-12-20 | 2013-02-12 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2013-03-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-01 | Online |  | Private | Y
2062 | Plympton | 2367 | 4000 | PV | 3-51-901 | 2012-02-27 | 2012-02-29 | 2 | 2 | 0 | 2012-02-29 | 2012-03-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2063 | Plympton | 2367 | 2000 | PV | 3-51-901 | 2012-02-29 | 2012-03-05 | 3 | 3 | 0 | 2012-03-05 | 2012-04-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-08 |  |  | Withdrawn |  | Private | Y
2124 | Plympton | 2367 | 1500 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2125 | Plympton | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2126 | Plympton | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2127 | Plympton | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-08 | 2012-05-15 | 5 | 5 | 0 | 2012-05-15 | 2012-07-03 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-02-11 | 78 | 0 | 78 |  |  | 0 | 0 | 0 | 2013-05-10 |  | 2012-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
2342 | Plympton | 2367 | 1000 | PV | 3-10-930 | 2013-01-31 |  | -29505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2448 | Plympton | 2367 | 24 | PV | 3-51-901 | 2013-10-04 | 2013-10-10 | 4 | 2 | 2 | 2013-10-11 |  | -29686 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-01 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1947 | Marion | 2378 | 39 | PV | 3-85-957 | 2011-10-20 | 2011-10-28 | 6 | 6 | 0 | 2011-10-31 | 2012-01-30 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-07-11 | 136 | 0 | 136 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2009611 | Lexington | 02420 | 135 | PV | 533-H3 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-27 | 2014-06-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-02 | 2014-12-10 | Online |  | Private
2009605 | Lexington | 02420 | 135 | PV | 391-H11 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online |  | Gov't
2009631 | Lexington | 02420 | 40 | PV | 3403 | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-02 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-03 | 2014-10-01 | 2015-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-19 | Online |  | Private
2068862 | Lexington | 02420 | 19 | PV | 391-H11 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-26 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-29 | 2015-05-29 | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-05 | Online |  | Private
2027027 | Lexington | 02420 | 15 | PV | 391-H3 | 2014-09-26 | 2014-09-27 | 1 | 0 | 1 | 2014-09-30 | 2014-10-21 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2253 | Lexington | 2420 | 18 | PV | 391-H3 | 2012-09-17 | 2012-09-19 | 2 | 1 | 1 | 2012-10-04 | 2013-03-18 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-13 | 2013-12-13 | 2013-12-20 | Online |  | Private | Y
2437 | Lexington | 2420 | 32 | PV | 391-H11 | 2013-09-10 | 2013-09-11 | 1 | 0 | 1 | 2013-09-11 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-16 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-18 | Online |  | Private | Y
2009625 | Lexington | 02421 | 171 | PV | 320-H5XY | 2014-06-20 | 2014-06-26 | 4 | 0 | 4 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-23 | Online |  | Private
2009595 | Lexington | 02421 | 388 | PV | 320-H5XY | 2014-06-16 | 2014-06-20 | 4 | 0 | 4 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online |  | Gov't | N
2009615 | Lexington | 02421 | 79 | PV | 320-H5XY | 2014-06-20 | 2014-06-27 | 5 | 0 | 5 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-16 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online |  | Private
2069155 | Lexington | 02421 | 319 | PV | 320-H5XY | 2015-05-15 | 2015-05-16 | 1 | 47 | -46 | 2015-05-18 | 2015-08-11 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-19 | Online |  | Private
1989453 | Lexington | 02421 | 25.9 | PV | 533-H1 | 2014-02-11 | 2014-02-26 | 11 | 0 | 11 | 2014-03-14 | 2014-03-20 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-04-11 | 2014-08-07 | 84 | 7 | 77 | 2015-05-04 | 2015-05-07 | 3 | 0 | 3 | 2014-08-04 | 2015-05-11 | 2015-11-30 | No | STD | 60 | 2015-09-30 | 2015-09-30 | 0 |  | 0 |  | 2016-03-01 | 2016-03-01 | Online |  | Private | N
2052550 | Lexington | 02421 | 2964 | PV | 533-H2 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2016-12-04 | 2015-09-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-15 | Online |  | Gov't
2247317 | Lexington | 02421 | 840 | PV | TBD | 2017-11-29 | 2017-11-30 | 1 | 0 | 1 | 2017-12-05 | 2018-02-09 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-12-28 |  | 2018-07-09 | TBD | EXP | 30 | [7 empty] | 2017-12-29 | Online
2036677 | Lexington | 02421 | 15.75 | PV | TBD | 2014-11-17 |  | 31 | 0 | 31 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-14 |  | 2015-06-25 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2123559 | Lexington | 02421 | 720 | PV | 2-1N11 | 2016-01-15 | 2016-01-19 | 2 | 7 | -5 | 2016-01-21 | 2016-03-21 | 42 | 9 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-06 |  | 2016-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2137830 | Lexington | 02421 | 360 | PV | 320-H4 | 2016-03-30 | 2016-04-01 | 2 | 0 | 2 | 2016-04-07 | 2016-05-31 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-30 |  | 2016-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2054352 | Lexington | 02421 | 15.9 | PV | 320-H2 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-11 |  | -30034 | 115 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-15 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2333267 | Lexington | 02421 | 0 |  | TBD | 2019-04-04 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-08 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2352782 | Lexington | 02421 | 330 | PV | TBD | 2019-08-01 |  | 176 | 0 | 176 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-12 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2303 | Lexington | 2421 | 11 | PV | 3409 | 2012-11-04 | 2012-11-20 | 12 | 4 | 8 | 2012-11-20 | 2012-12-20 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2012-04-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Gov't | Y
2305 | Lexington | 2421 | 10 | PV | 320-H5XY | 2012-11-21 | 2012-11-28 | 5 | 5 | 0 | 2012-11-28 | 2012-12-20 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online |  | Private | Y
2244 | Lexington | 2421 | 56 | PV | 320-H5XY | 2012-08-30 | 2012-09-11 | 8 | 5 | 3 | 2012-09-11 | 2013-01-07 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-23 | 2013-04-23 | 2013-04-23 | Online |  | Gov't | Y
2442 | Lexington | 2421 | 46 | PV | 3402 | 2013-09-19 | 2013-10-24 | 25 | 24 | 1 | 2013-10-24 |  | -29695 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-07 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2014-04-08 | 2014-04-08 | 2014-04-08 | Online |  | Private | Y
1495 | Lexington | 2421 | 150 | Natural Gas | 3401 | 2009-11-05 | 2009-11-17 | 8 | 8 | 0 | 2009-11-17 |  | -28668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | n/a | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2236 | Lexington | 2421 | 260 | PV | 533-H2 | 2012-08-29 |  | -29394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1796 | Brookline | 2446 | 75 | Natural Gas | 350-H12 | 2011-04-27 | 2011-05-19 | 16 | 15 | 1 | 2011-05-19 | 2011-07-13 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-08 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-08 | Online |  | Gov't | N
2444 | Brookline | 2446 | 46 | PV | 329-H7 | 2013-09-23 | 2013-10-01 | 6 | 5 | 1 | 2013-10-04 |  | -29681 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online |  | Private | Y
2089144 | Waltham | 02451 | 96 | PV | 450-H8 | 2015-08-21 | 2015-08-24 | 1 | 0 | 1 | 2015-08-26 | 2015-09-22 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-23 |  | 2016-03-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-05 | Online |  | Private
2068489 | Waltham | 02451 | 96 | PV | 450-H8 | 2015-05-07 | 2015-05-11 | 2 | 0 | 2 | 2015-05-14 | 2015-06-22 | 27 | 1 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-01 |  | 2015-12-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-22 | 2016-01-25 | Online |  | Private
2094179 | Waltham | 02451 | 1200 | Natural Gas | 373-1358 | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-09-28 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2016-02-25 | 2016-03-30 | TBD | EXP | 30 | 2016-02-25 | 2016-02-25 | 0 |  | 0 |  |  | 2016-04-14 | Online |  | Private
2088991 | Waltham | 02451 | 175 | PV | 282-H6 | 2015-08-20 | 2015-08-21 | 1 | 98 | -97 | 2015-08-25 | 2016-04-05 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-17 | Online |  | Private
1980806 | Waltham | 02451 | 1000 | PV | 526-1361H | 2014-01-03 | 2014-01-03 | 0 | 0 | 0 | 2014-02-04 | 2014-02-04 | 0 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-31 | 2014-06-05 | 2014-09-30 | No | EXP | 30 | 2014-09-04 | 2014-09-04 | 0 |  | 0 |  | 2014-09-25 |  | Withdrawn |  | Gov't
2009878 | Waltham | 02451 | 675 | PV | 531-1359H | 2014-06-24 | 2014-06-24 | 0 | 0 | 0 | 2014-07-01 | 2014-07-29 | 20 | 308 | -288 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2064568 | Waltham | 02451 | 500 | PV | 363-1369 | 2015-04-17 | 2015-04-17 | 0 | 37 | 0 | 2015-04-24 | 2015-07-01 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-02 |  | 2015-11-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2135867 | Waltham | 02451 | 270 | PV | 450-H8 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | 2016-05-24 | 2016-08-10 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-10-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2093779 | Waltham | 02451 | 1000 | PV | 450-H3 | 2015-09-14 | 2015-09-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2137498 | Waltham | 02451 | 290 | PV | 450-H3 | 2016-03-30 | 2016-03-31 | 1 | 0 | 1 | 2016-04-07 |  | -30335 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-11-04 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-06 | Private
2246565 | Waltham | 02451 | 366.3 | PV | 282-H5 | 2017-08-11 | 2017-10-27 | 53 |  | 53 | 2017-11-29 |  | -30755 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2245194 | Waltham | 02451 | 632.7 | PV | 282-H5 | 2017-08-15 | 2017-10-27 | 51 |  | 51 | 2017-11-21 |  | -30750 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
2245190 | Waltham | 02451 | 599 | PV | TBD | 2017-11-13 |  | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
692 | Newton | 2451 | 75 | Natural Gas | 292-H7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2011-07-22 | Online |  |  | N
1144 | Waltham | 2451 | 235 | PV | 450-H7 | 2009-02-09 | 2009-02-19 | 8 | 7 | 1 | 2009-02-19 | 2009-03-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-03-30 |  | 2009-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-04-23 |  | 2009-04-09 | Online |  |  | N
1835 | Waltham | 2451 | 130 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-25 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | Y
2441 | Waltham | 2451 | 60 | PV | 282-H1 | 2013-09-16 | 2013-09-20 | 4 | 1 | 3 | 2013-09-20 |  | -29671 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Private | Y
2349 | Waltham | 2451 | 120 | PV | 282-H5 | 2013-02-11 | 2013-02-14 | 3 | 0 | 3 | 2013-02-27 | 2013-04-09 | 29 | 2 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-16 | Online |  | Private | Y
2410 | Waltham | 2451 | 750 | PV | 320-H3 | 2013-06-24 | 2013-07-01 | 5 | 2 | 3 | 2013-07-01 | 2013-08-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online |  | Private | Y
2162221 | Waltham | 02452 | 380 | PV | 277-1367 | 2016-08-03 | 2016-08-09 | 4 | 0 | 4 | 2016-08-11 |  | -30425 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-19 | 2016-09-29 | 2017-03-15 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-12 | Private
1565 | Bourne | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-29 | 2010-02-02 | 2 | 0 | 2 | 2010-02-02 | 2010-03-25 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-02-22 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1562 | Bourne | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1563 | Bourne | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1564 | Bourne | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1834 | Waltham | 2452 | 395 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-25 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | Y
1872 | Waltham | 2452 | 310 | PV | 450-H6 | 2011-08-02 | 2011-08-09 | 5 | 4 | 1 | 2011-08-09 | 2011-09-26 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-29 | Online |  | Private | Y
1836 | Waltham | 2452 | 75 | PV | 282-H2 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-28 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-29 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-09 | Online |  | Gov't | Y
1805 | Waltham | 2452 | 182 | PV | 3316 | 2011-05-05 | 2011-10-20 | 120 | 118 | 2 | 2011-10-21 | 2011-12-19 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  | 2012-04-06 | Online |  | Gov't | Y
1930 | Waltham | 2452 | 666 | PV | 450-H1 | 2011-10-03 | 2011-10-05 | 2 | 2 | 0 | 2011-10-05 | 2011-11-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-06-06 | Online |  | Private | Y
2277 | Waltham | 2452 | 12 | PV | 33-H2 | 2012-10-03 | 2012-10-12 | 7 | 6 | 1 | 2012-10-12 | 2013-01-15 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-01 | Online |  | Private | Y
2101013 | Waltham | 02453 | 126 | PV | 467-H8 | 2015-10-20 | 2015-10-21 | 1 | 0 | 1 | 2015-10-27 | 2016-03-31 | 112 | 102 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-16 | Online |  | PRIVATE
1994357 | Waltham | 02453 | 75 | Natural Gas | 33-H1 | 2014-04-20 | 2014-04-22 | 2 | 0 | 2 | 2014-05-12 | 2014-05-23 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-29 |  | 2014-11-28 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-18 |  | Withdrawn |  | Gov't
2157007 | Waltham | 02453 | 180 | PV | 33-H3 | 2016-07-06 | 2016-07-07 | 1 | 0 | 1 | 2016-07-14 |  | -30405 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2016-08-04 | Private
1509 | Waltham | 2453 | 272 | PV | 282-H8 | 2009-10-16 | 2009-11-17 | 22 | 0 | 22 | 2009-11-24 | 2009-12-22 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online |  | Private | N
2018 | Waltham | 2453 | 30 | PV | 3311 | 2012-01-10 | 2012-01-18 | 6 | 4 | 2 | 2012-01-18 | 2012-02-24 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2011-12-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-23 | Online |  | Private | Y
1876 | Waltham | 2453 | 30 | PV | 467-H5 | 2011-08-08 | 2011-08-09 | 1 | 0 | 1 | 2011-08-10 | 2011-09-23 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-09 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-07 | 2012-08-07 | 2012-08-07 | Online |  | Private | N
1837 | Waltham | 2453 | 75 | PV | 467-H5 | 2011-06-23 | 2011-08-05 | 31 | 31 | 0 | 2011-08-05 | 2011-08-23 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-06 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-09 | Online |  | Private | Y
1084 | Waltham | 2454 | 1200 | Diesel | 386-1356 | 2009-01-28 | 2009-02-25 | 20 | 19 | 1 | 2009-02-25 | 2009-04-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-07 |  | 2009-07-07 | Online |  | Private | N
2000080 | Newton | 02458 | 100 | PV | 467-H3 | 2014-03-20 | 2014-03-27 | 5 | 0 | 5 | 2014-05-06 | 2014-05-08 | 2 | 0 | 2 | 2014-05-13 | 2014-05-28 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2017-10-31 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2324 | Newton | 2458 | 13 | PV | 277-05 | 2012-12-28 | 2013-01-24 | 19 | 19 | 0 | 2013-01-24 | 2013-04-17 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-05-02 | 2013-05-02 | 2013-05-02 | Online |  | Private | Y
2414 | Newton | 2458 | 57 | PV | 467-H5 | 2013-07-08 | 2013-10-29 | 81 | 80 | 1 | 2013-11-05 |  | -29703 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2415 | Newton | 2458 | 62 | PV | 467-H3 | 2013-07-08 | 2013-07-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-09-16 | Private | Y
2034511 | Newton | 02459 | 36 | PV | 292-H3 | 2014-11-05 | 2015-01-20 | 54 | 0 | 54 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-21 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-28 | Online |  | Private
2129052 | Newton | 02459 | 104 | PV | 292-H8 | 2016-02-12 | 2016-02-13 | 1 | 0 | 1 | 2016-02-23 | 2016-05-27 | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2016-05-31 | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-09 | Online |  | Private
2136579 | Newton | 02459 | 240 | PV | 292-H8 | 2016-03-24 | 2016-04-04 | 7 | 0 | 7 | 2016-04-04 | 2016-04-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 | 2016-04-05 | 2016-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
2134030 | Newton | 02459 | 159 | PV | 292-H2 | 2016-03-10 | 2016-03-14 | 2 | 0 | 2 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-10-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2408881 | Newton | 02459 | 10 | PV | 1709 | 2020-07-30 | 2020-09-10 | 29 | 0 | 29 | 2020-09-10 |  | 78 | 0 | 78 | [20 empty] | 2021-05-06 |  | 2020-12-30 | TBD |  | 30 | [7 empty] | 2022-02-15 | Online |  | Private
1511 | Newton | 2459 | 36 | PV | 467-H5 | 2009-10-18 | 2009-11-18 | 23 | 0 | 23 | 2009-12-03 | 2010-01-08 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-06 |  | 2010-05-06 | Online |  | Private | Y
2235 | Newton | 2459 | 200 | PV | 292-H8 | 2012-08-27 | 2012-08-30 | 3 | 3 | 0 | 2013-09-06 | 2013-10-10 | 24 | 228 | -204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online |  | Gov't | Y
2160 | Newton Center | 2459 | 11 | PV | 467-H12 | 2012-07-02 | 2012-08-15 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-04-29 | Gov't | Y
2154090 | Newton | 02460 | 75 | PV | 467-H5 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-27 | 2016-06-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-27 |  | 2017-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1611 | Newton | 2460 | 30 | PV | 17-H1 | 2010-04-23 | 2010-05-10 | 11 | 11 | 0 | 2010-08-26 | 2010-09-21 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-14 |  | 2010-05-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-20 |  | 2010-10-22 | Online |  | Private | Y
2252 | Newton | 2460 | 20 | PV | 282-H9 | 2012-09-17 | 2012-09-18 | 1 | 1 | 0 | 2012-09-18 | 2012-10-10 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-26 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online |  | Private | Y
2233 | Newton | 2460 | 260 | PV | 17-H1 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-11-25 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-24 | Online |  | Gov't | Y
2131753 | Newton | 02461 | 492 | PV | 292-H2 | 2016-03-01 | 2016-03-29 | 20 | 0 | 20 | 2016-03-29 | 2016-05-12 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 | 2016-05-12 | 2016-10-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
2234 | Newton | 2461 | 100 | PV | 433-02 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-09-27 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-05 | 2012-09-01 | -133 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online |  | Gov't | Y
2250 | Newton | 2461 | 50 | PV | 292-H11 | 2012-09-06 | 2013-05-10 | 176 | 175 | 1 | 2013-05-10 | 2013-06-18 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
2253263 | Newton | 02465 | 24.95 | PV | 282-H9 | 2017-10-30 | 2017-12-05 | 25 |  | 25 | 2018-12-27 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11 | Online
2348530 | Newton | 02465 | 20 | PV & Battery | 282-H9 | 2019-05-31 | 2019-06-20 |  |  |  | 2019-07-05 | [24 empty] | 2019-11-18 | [12 empty] | 2020-01-22 | Online
2131 | Newton | 2465 | 11 | PV | 1707 | 2012-05-15 | 2012-05-25 | 8 | 8 | 0 | 2012-05-29 | 2012-07-13 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-14 | Online |  | Private | Y
2042189 | Newton | 02466 | 16.4 | PV | 292-H12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-02-17 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-04 | Online |  | Private
2148462 | Newton | 02466 | 1800 | PV | 33-H3 | 2016-05-24 | 2016-05-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online | 2016-06-06 | Private
2095914 | Brookline | 02467 | 32 | PV | 496-H4 | 2015-09-24 | 2015-09-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2096 | Brookline | 2467 | 111 | PV | 369-07 | 2012-04-10 | 2012-05-24 | 32 | 31 | 1 | 2012-05-24 | 2012-07-18 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-07-24 | Online |  | Private | Y
2095 | Brookline | 2467 | 51 | PV | 369-07 | 2012-04-04 | 2012-04-06 | 2 | 0 | 2 | 2012-04-06 | 2012-05-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-08-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-06-29 | Private | Y
1436 | Newton | 2467 | 400 | Natural Gas | 467-H14 | 2009-09-08 | 2010-03-01 | 124 | 123 | 1 | 2010-03-01 | 2010-04-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-26 |  | 2010-05-26 | Online |  | Gov't | Y
2130935 | Newton | 02468 | 36 | PV | 292-H12 | 2016-02-25 | 2016-02-26 | 1 | 0 | 1 | 2016-03-03 | 2016-06-06 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-19 | Online |  | Private
2139847 | Newton | 02468 | 982 | PV | 292-H2 | 2016-04-08 | 2016-04-09 | 1 | 0 | 1 | 2016-04-19 | 2016-05-04 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-25 |  | 2016-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2154091 | Watertown | 02472 | 432 | PV | 467-H6 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-28 | 2016-08-03 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-08-24 | 2017-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-23 | Online |  | Private
2130080 | Watertown | 02472 | 216 | PV | 467-H6 | 2016-02-19 | 2016-02-22 | 1 | 0 | 1 | 2016-02-25 | 2016-03-01 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 | 2016-03-02 | 2016-09-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online |  | Private
2070884 | Watertown | 02472 | 156 | PV | 467-H9 | 2015-05-20 | 2015-05-26 | 4 | 45 | -41 | 2015-05-28 | 2015-07-22 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2015-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2131752 | Watertown | 02472 | 125 | PV | 467-H2 | 2016-02-29 | 2016-03-02 | 2 | 0 | 2 | 2016-03-03 | 2016-05-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1610 | Watertown | 2472 | 34 | PV | 467-H9 | 2010-04-23 | 2010-05-24 | 21 | 21 | 0 | 2010-05-25 | 2010-07-09 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-09 |  | 2010-08-09 | Online |  | Gov't | Y
1990 | Watertown | 2472 | 120 | PV | 467-H6 | 2011-12-08 | 2011-12-13 | 3 | 3 | 0 | 2011-12-15 | 2012-01-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online |  | Private | Y
1435 | Watertown | 2472 | 500 | PV | 467-H9 | 2009-09-08 | 2009-10-30 | 38 | 37 | 1 | 2009-10-30 | 2009-12-08 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Private | N
1582 | Watertown | 2472 | 28 | PV | 467-H8 | 2010-02-08 |  | -28727 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2053837 | Arlington | 02474 | 74 | PV | 59-1383H1 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-03-09 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 |  | 2015-09-09 | TBD | EXP | 30 | 2015-03-05 | 2015-03-05 | 0 |  | 0 |  |  | 2015-11-18 | Online |  | Gov't
2073733 | Arlington | 02474 | 92 | PV | 59-1383H1 | 2015-06-03 | 2015-10-28 | 105 | 87 | 18 | 2015-10-28 | 2015-10-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-11-02 | 2016-01-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-28 | 2015-12-08 | Online |  | Private | N
2053868 | Arlington | 02474 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
1380 | Arlington | 2474 | 52 | PV | 320-H7 | 2009-07-24 | 2009-07-30 | 4 | 3 | 1 | 2009-07-30 | 2009-08-20 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-26 |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2055516 | Arlington | 02476 | 56 | PV | 320-H7 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | 2015-02-27 | 2015-03-04 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-03-05 | 2015-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
2053824 | Arlington | 02476 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-18 | Online |  | Gov't
2053847 | Arlington | 02476 | 74 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-19 | Online |  | Gov't
2073753 | Arlington | 02476 | 69 | PV | 351-1385H1 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-09 | 2015-07-30 | 37 | 34 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private | N
2053835 | Arlington | 02476 | 176 | PV | 211-H3 | 2015-02-03 | 2015-02-04 | 1 | 0 | 1 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2129730 | Arlington | 02476 | 115 | PV | 320-H7 | 2016-02-17 | 2016-02-19 | 2 | 0 | 2 | 2016-02-25 | 2016-04-26 | 43 | 27 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-02 |  | 2016-09-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2090065 | Arlington | 02476 | 118 | PV | 320-H7 | 2015-08-26 | 2015-08-27 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2377 | Arlington | 2476 | 34 | PV | 5905 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-23 | Online |  | Private | Y
1989732 | Needham | 02492 | 3120 | PV | 148-H1 | 2014-02-14 | 2014-02-28 | 10 | 0 | 10 | 2014-03-04 | 2014-03-12 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-10-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-23 | Online |  | Gov't | Y
1694 | Needham | 2492 | 15 | PV | 148-H1 | 2010-10-01 | 2010-10-19 | 12 | 11 | 1 | 2010-10-20 | 2010-12-08 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-30 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-08-22 |  | 2011-09-08 | Online |  | Private | Y
2196 | Needham | 2492 | 14 | PV | 148-01 | 2012-08-02 | 2012-08-13 | 7 | 7 | 0 | 2012-08-14 | 2012-10-18 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-25 |  | 2012-09-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-10 | Online |  | Private | Y
2317 | Needham | 2492 | 12 | PV | 148-03 | 2012-12-14 |  | -29471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2387 | Roxbury | 2492 | 32 | PV | 483-H6 | 2013-05-20 | 2013-05-31 | 9 | 9 | 0 | 2013-05-31 | 2013-06-26 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2055868 | Weston | 02493 | 1795 | PV | 450-H7 | 2015-02-24 | 2015-03-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-15 | Online |  | Private | Y
2145203 | Weston | 02493 | 20 | PV | 282-H10 | 2016-05-04 | 2016-05-05 | 1 | 0 | 1 | 2016-05-11 | 2016-05-24 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 |  | 2016-12-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-13 | Online |  | Private
2140569 | Weston | 02493 | 246 | PV | 433-H6 | 2016-04-14 | 2016-04-20 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2016-04-27 | Private
2159240 | Weston | 02493 | 20 | PV | 282-H1 | 2016-07-19 | 2016-07-20 | 1 | 0 | 1 | 2016-07-28 |  | -30415 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-01-30 |  | 2017-02-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-08-10 | Private
1234 | Weston | 2493 | 95 | PV | 282-H10 | 2009-04-06 | 2009-05-05 | 21 | 20 | 1 | 2009-05-05 | 2009-06-08 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-23 |  | 2009-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-11-20 | Online |  | Private | N
1717 | Weston | 2493 | 300 | PV | 282-H3 | 2010-11-16 | 2010-11-24 | 6 | 3 | 3 | 2010-11-30 | 2011-01-21 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  |  | Withdrawn |  | Private | Y
1400 | Weston | 2493 | 200 | Hydro | 282-H8 | 2009-08-07 | 2010-01-15 | 115 | 114 | 1 | 2010-01-15 |  | -28711 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-05-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
2153 | Weston | 2493 | 60 | PV | 450-H7 | 2012-06-18 | 2012-07-20 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-08-29 | Private | Y
2363 | Weston | 2493 | 20 | PV | 342-H1 | 2013-02-04 |  | -29507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-03-27 | Private | Y
2156671 | Needham | 02494 | 90 | PV | 148-H7 | 2016-07-05 | 2016-07-06 | 1 | 0 | 1 | 2016-07-14 | 2016-08-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-23 | 2016-08-25 | 2017-02-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-07 | Online |  | Private
2126109 | Needham | 02494 | 828 | PV | 148-H6 | 2016-01-29 | 2016-02-01 | 1 | 0 | 1 | 2016-02-04 | 2016-02-22 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 |  | 2016-09-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | Online |  | Private
2135025 | Needham | 02494 | 150 | PV | 148-H1 | 2016-03-16 | 2016-03-17 | 1 | 11 | -10 | 2016-04-04 | 2016-06-14 | 51 | 5 | 46 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2084378 | Needham | 02494 | 40 | PV | 148-H7 | 2015-07-28 | 2015-08-05 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-08-13 | Private
1596 | Needham | 2494 | 78 | PV | 292-H10 | 2010-03-31 | 2010-04-01 | 1 | 1 | 0 | 2010-04-01 | 2010-05-11 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-12 |  | 2010-05-21 | No | STD |  |  |  | 0 | 0 | 0 | 2010-10-15 |  | 2010-10-15 | Online |  | Private | Y
2424 | Needham | 2494 | 30 | PV | 148-H7 | 2013-07-25 |  | -29630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2154 | Marshfield | 2500 | 14 | PV | 3-25-25 | 2012-06-20 | 2012-08-16 | 41 | 33 | 8 | 2012-08-16 | 2012-12-14 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-15 | 2012-12-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 2013-06-05 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-06 | Online |  | Gov't | Y
2043278 | Bourne | 02532 | 650 | PV | 4-86-402 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 | 2015-02-02 | 2015-03-01 | No | EXP | 30 | 2015-03-26 | 2015-03-26 | 0 |  | 0 |  |  | 2015-12-31 | Online |  | Private
2101008 | Bourne | 02532 | 468 | PV | 4-86-402 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-20 | 2015-10-20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2017-04-03 |  | 2017-04-11 | Online |  | Private
2025848 | Bourne | 02532 | 499 | PV | 3-89-925 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | 2014-09-30 | 2014-11-10 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-30 |  | Withdrawn |  | Private
2098326 | Bourne | 02532 | 4800 | Natural Gas | 4-81A-81A | 2015-10-05 | 2015-10-09 | 4 | 0 | 4 | 2015-10-14 | 2015-10-20 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2015-11-11 | 2016-06-15 | TBD | EXP | 30 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2127227 | Bourne | 02532 | 1000 | PV | 4-98A-98A | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-04-04 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 |  | 2016-09-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2133572 | Buzzards Bay | 02532 | 66 | PV | 3-90-10J2 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 | 2016-06-07 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-12 | 2016-12-19 | 2016-10-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online |  | Private
2034325 | Buzzards Bay | 02532 | 104 | PV | 3-88-2J4 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | 2014-11-07 | 2014-11-12 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1550 | Bourne | 2532 | 27 | PV | 4-81A-81A | 2010-01-11 | 2010-01-27 | 12 | 9 | 3 | 2010-01-27 | 2010-03-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-05 |  | 2010-05-05 | Online |  | Private | N
1572 | Bourne | 2532 | 143 | PV | 4-86-402 | 2010-02-04 | 2010-02-12 | 6 | 6 | 0 | 2010-02-16 | 2010-03-29 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-29 |  | 2010-04-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online |  | Private | Y
1615 | Bourne | 2532 | 50 | Wind | 4-79-79 | 2010-04-29 | 2010-05-10 | 7 | 7 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-05-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-29 |  | 2010-09-29 | Online |  | Gov't | Y
1669 | Bourne | 2532 | 2000 | Wind | 4-81A-81A | 2010-08-24 | 2010-08-30 | 4 | 4 | 0 | 2010-09-01 | 2010-10-21 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-24 |  | 2011-03-25 | Online |  | Private | Y
2017 | Bourne | 2532 | 250 | PV | 4-86-86 | 2011-11-08 | 2012-02-08 | 66 | 20 | 46 | 2012-02-08 | 2012-03-19 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Gov't | Y
2008 | Bourne | 2532 | 14 | PV | 3-84-961 | 2011-12-28 | 2012-01-12 | 11 | 7 | 4 | 2012-01-16 | 2012-05-09 | 82 | 0 | 82 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online |  | Gov't | Y
2336 | Bourne | 2532 | 1680 | Wind | 4-81A-81A | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-03-01 | 2013-08-26 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Gov't | N
2180 | Bourne | 2532 | 425 | PV | 4-86-402 | 2013-05-01 | 2013-05-03 | 2 | 0 | 2 | 2013-05-03 | 2013-06-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 | 2013-09-19 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-15 | Online |  | Gov't | Y
1583 | Bourne | 2532 | 1500 | Wind | 3-88-923 | 2010-03-01 | 2010-03-02 | 1 | 1 | 0 | 2010-03-03 | 2010-03-05 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-29 |  |  | Withdrawn |  | Gov't | Y
1555 | Bourne | 2532 | 28 | PV | 3-88-923 | 2010-01-15 | 2010-06-10 | 104 | 103 | 1 | 2010-06-18 | 2010-07-14 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1491 | Bourne | 2532 | 600 | Wind | 4-86-402 | 2009-10-30 | 2009-12-04 | 25 | 24 | 1 | 2009-12-07 | 2010-11-30 | 256 | 0 | 256 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  |  | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2011-01-31 | Private | N
1880 | Bourne | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1881 | Bourne | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1882 | Bourne | 2532 | 2000 | Wind | 3-88-923 | 2011-08-16 | 2011-08-30 | 10 | 10 | 0 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | -29223 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
2071 | Bourne | 2532 | 1785 | PV | 4-86-402 | 2012-03-12 | 2012-03-23 | 9 | 9 | 0 | 2012-03-23 | 2012-05-10 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-18 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1643 | Bourne | 2532 | 15000 | Wind | 4-81A-81A | 2010-07-07 |  | -28834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2413 | Bourne | 2532 | 1680 | Wind | 4-81A-81A | 2013-07-08 | 2013-10-29 | 81 |  | 81 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-11-18 | Private | Y
2141 | Buzzards Bay | 2532 | 96 | PV | 3-84-965 | 2012-05-22 | 2012-06-29 | 28 | 26 | 2 | 2012-06-29 | 2012-08-06 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-12-10 | Online |  | Private | Y
2195 | Buzzards Bay | 2532 | 35 | PV | 3-88-88 | 2012-08-02 | 2012-08-06 | 2 | 2 | 0 | 2012-08-08 | 2012-09-11 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-08-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-25 | Online |  | Private | Y
2179 | Buzzards Bay | 2532 | 21 | PV | 3-89-925 | 2012-07-30 | 2012-10-22 | 60 | 59 | 1 | 2012-12-18 | 2013-01-22 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-01-31 | Gov't | Y
2178 | Buzzards Bay | 2532 | 50 | PV | 3-88-88 | 2012-07-30 |  | -29372 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1642 | Plymouth | 2532 | 10000 | Wind | 221 | 2010-06-29 | 2010-07-02 | 3 | 3 | 0 | 2010-10-01 |  | -28896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
1450 | Bourne | 2534 | 100 | PV | 4-78-409 | 2009-10-06 | 2009-10-09 | 3 | 0 | 3 | 2009-10-09 | 2009-10-29 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-11-09 | Online |  | Gov't | Y
1981127 | Chilmark | 02535 | 95 | PV | 4-97-126 | 2014-01-08 | 2014-01-08 | 0 | 0 | 0 | 2014-01-14 | 2014-02-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-10 |  | 2014-08-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online |  | Private
2033372 | Chilmark | 02535 | 195.2 | PV | 4-97-126 | 2014-11-03 | 2014-11-03 | 0 | 0 | 0 | 2014-11-06 | 2014-11-24 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-06-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2372255 | Chilmark | 02535 | 0 |  | TBD | 2019-12-04 |  | 1 | 0 | 1 | 2019-12-19 | 2020-01-27 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-02-20 | 2020-10-01 | 2020-07-10 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
1739 | Chilmark | 2535 | 68 | Wind | 4-97-226 | 2010-12-21 | 2011-01-04 | 10 | 6 | 4 | 2011-01-04 | 2011-02-28 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-06-09 | Online |  | Gov't | Y
1934 | Chilmark | 2535 | 62 | PV | 4-97-220 | 2011-10-10 | 2011-10-12 | 2 | 1 | 1 | 2011-10-20 | 2012-01-20 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
1713 | Chilmark | 2535 | 88 | PV | 4-97-226 | 2010-11-10 | 2010-11-16 | 4 | 1 | 3 | 2010-11-19 | 2010-12-20 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-11-26 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-03-21 |  | 2013-03-21 | Online |  | Gov't | N
2422 | Chilmark | 2535 | 17 | PV | 4-97-126 | 2013-07-15 | 2013-08-12 | 20 | 18 | 2 | 2013-08-12 | 2013-09-11 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online |  | Gov't | Y
2343 | Chilmark | 2535 | 12 | PV | 4-97-226 | 2013-02-01 | 2013-02-07 | 4 | 1 | 3 | 2013-03-06 | 2013-04-09 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | -29759 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2381 | Chilmark | 2535 | 27 | PV | 4-97-126 | 2013-04-17 | 2013-05-08 | 15 | 5 | 10 | 2013-05-17 | 2013-06-26 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2468 | Chilmark | 2535 | 42 | PV | 4-91-220 | 2014-11-18 | 2015-01-02 | 33 | 0 | 33 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2016-03-11 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2392 | Chilmark | 2535 | 23 | PV | 4-97-226 | 2013-05-24 |  | -29586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2426 | Chilmark | 2535 | 17 | PV | 4-97-226 | 2013-08-06 |  | -29638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Gov't | Y
2051319 | Falmouth | 02536 | 56 | PV | 4-76-436 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
2102531 | Falmouth | 02536 | 48 | PV | 4-98A-98A | 2015-10-26 | 2015-10-29 | 3 | 0 | 3 | 2015-10-29 | 2016-02-12 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-14 | Online |  | Private
1985442 | Falmouth | 02536 | 90 | PV | 4-98A-98A | 2014-01-28 | 2014-01-30 | 2 | 0 | 2 | 2014-01-30 | 2014-02-05 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-09-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2132336 | Falmouth | 02536 | 185 | PV | 4-92B-583 | 2016-03-03 | 2016-07-14 | 95 | 0 | 95 | 2016-07-14 | 2016-07-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-20 | 2016-10-24 | 2016-10-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2128032 | Falmouth | 02536 | 16.7 | PV | 4-98B-845 | 2016-02-09 | 2016-02-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-03-09 | Private
2394867 | Falmouth | 02536 | 3500 | PV | TBD | 2020-04-21 |  | 177 | 0 | 177 |  |  | 0 | 0 | 0 | [22 empty] | 2020-11-25 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2395855 | Falmouth | 02536 | 4990 | PV | TBD | 2020-04-29 | 2020-04-30 | 1 | 0 | 1 | 2020-04-30 |  | 170 | 169 | 1 | [22 empty] | 2020-12-04 | TBD |  | 30 | [8 empty] | In Queue | 2020-05-01 | Private
2395998 | Falmouth | 02536 | 3000 | PV | TBD | 2020-04-30 | 2020-05-01 | 1 | 0 | 1 |  |  | 169 | 169 | 0 | [22 empty] | 2020-12-07 | TBD |  | 30 | [8 empty] | In Queue | 2020-05-01 | Private
1982667 | Hatchville | 02536 | 48 | PV | 4-98B-448 | 2014-01-09 | 2014-01-09 | 0 | 0 | 0 | 2014-01-15 | 2014-02-05 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-16 |  | 2014-09-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-05-16 | 2014-05-16 | Online |  | Private
2024739 | Hatchville | 02536 | 3000 | PV | 4-98A-98A | 2014-09-16 |  |  | 0 | 0 | 2014-09-18 | 2014-10-01 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2015-04-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-21 | 2017-04-06 | Online |  | Gov't
2136806 | Hatchville | 02536 | 15.4 | PV | 4-98A-98A | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-29 | 2016-04-04 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-05 | 2016-06-16 | 2016-11-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online |  | Private
2124636 | Hatchville | 02536 | 1500 | PV | 4-98A-98A | 2016-01-21 | 2016-01-22 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-02-16 | Private
2160717 | Hatchville | 02536 | 98 | PV | 4-98A-98A | 2016-07-27 | 2016-08-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2395965 | Hatchville | 02536 | 3300 | PV | TBD | 2020-04-30 | 2020-04-30 | 1 | 0 | 1 | 2020-04-30 |  | 170 | 169 | 1 | [22 empty] | 2020-12-07 | TBD |  | 30 | [8 empty] | In Queue | 2020-05-01 | Private
2335 | East Falmouth | 2536 | 54 | PV | 4-98A-98A | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 128 | 0 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29573 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online |  | Gov't | Y
1506 | East Falmouth | 2536 | 40 | PV | 4-98A-98A | 2009-11-16 | 2009-11-17 | 1 | 0 | 1 | 2009-11-17 | 2009-12-23 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-07-07 | Online |  | Private | N
1741 | East Falmouth | 2536 | 97 | PV | 4-98A-98A | 2011-01-03 | 2011-01-04 | 1 | 1 | 0 | 2011-01-04 | 2011-01-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-10 |  | 2013-01-03 | Online |  | Gov't | Y
2243 | East Falmouth | 2536 | 11 | PV | 4-98B-449 | 2012-08-31 | 2012-09-06 | 4 | 4 | 0 | 2012-09-06 | 2012-10-05 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-13 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-30 | 2013-01-30 | 2013-01-30 | Online |  | Gov't | Y
2456 | East Falmouth | 2536 | 90 | PV | 4-98A-98A | 2013-10-18 | 2013-10-24 | 4 | 3 | 1 | 2013-12-16 |  | -29732 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
2455 | East Falmouth | 2536 | 85 | PV | 4-77A-450 | 2013-10-17 |  | -29690 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-10-18 | Private | Y
1465 | Falmouth | 2536 | 67 | PV | 4-80B-523 | 2009-10-06 | 2009-10-23 | 13 | 10 | 3 | 2009-10-23 | 2009-11-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-21 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-04 | Online |  | Gov't | N
1594 | Falmouth | 2536 | 50 | PV | 4-76-437 | 2010-03-25 | 2010-04-01 | 5 | 5 | 0 | 2010-04-01 | 2010-05-07 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2010-05-30 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2012-02-14 | Online |  | Gov't | Y
2020 | Falmouth | 2536 | 750 | PV | 4-98A-98A | 2012-01-16 | 2012-02-27 | 30 | 30 | 0 | 2012-02-27 | 2012-04-30 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-11 |  | 2012-07-13 | Online |  | Private | Y
1697 | Falmouth | 2536 | 95 | PV | 4-98A-98A | 2010-10-01 | 2010-10-22 | 15 | 13 | 2 | 2010-10-22 | 2011-02-22 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1820 | East Falmouth | 2536 | 225 | Wind | 4-98A-98A | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  |  | Withdrawn |  | Private | N
1189 | Falmouth | 2536 | 1650 | Wind | 4-98A-98A | 2009-03-10 | 2009-03-10 | 0 | 0 | 0 | 2009-03-10 | 2009-04-10 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-21 | Online |  | Private | N
2135023 | Sandwich | 02537 | 984 | PV | 4-87A-471 | 2016-03-15 | 2016-03-16 | 1 | 0 | 1 | 2016-03-23 | 2016-05-16 | 38 | 1 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-06-17 | 2016-10-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2155321 | Sandwich | 02537 | 468 | PV | 4-81B-81B | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 |  | -30397 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 2016-09-08 | 30444 | 0 | 30444 |  |  | 0 | 0 | 0 | 2016-12-19 |  | 2017-02-07 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2184 | East Sandwich | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-08-22 | 17 | 16 | 1 | 2012-08-22 | 2012-09-24 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-29 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2194 | East Sandwich | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-10-23 | 61 | 59 | 2 | 2012-10-23 | 2013-01-03 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1598 | Sandwich | 2537 | 29 | PV | 4-87A-471 | 2010-04-09 | 2010-04-16 | 5 | 5 | 0 | 2010-04-20 | 2010-05-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-27 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-12-16 | Online |  | Gov't | N
2076 | Sandwich | 2537 | 6000 | PV | 4-81B-443 | 2012-03-26 | 2012-04-25 | 22 | 21 | 1 | 2012-04-25 | 2012-06-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-07 |  | 2012-05-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-09-12 | Online |  | Gov't | Y
2314 | Sandwich | 2537 | 28 | PV | 4-87B-473 | 2012-12-12 | 2012-12-17 | 3 | 2 | 1 | 2012-12-17 | 2013-02-06 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-11 |  | 2013-01-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online |  | Private | Y
1991204 | Wareham | 02538 | 100 | PV | 3-84-961 | 2014-03-14 | 2014-03-14 | 0 | 0 | 0 | 2014-03-20 | 2014-03-31 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-28 | 2014-05-05 | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-01 | 2015-05-01 | Online |  | Private
2051455 | Wareham | 02538 | 2000 | PV | 3-84-961 | 2015-01-22 | 2015-01-22 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online |  | Private
2116332 | Wareham | 02538 | 7450 | PV | 3-84-961 | 2015-12-22 | 2016-01-15 | 18 | 0 | 18 | 2016-01-15 | 2016-04-16 | 65 | 54 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
2226 | Wareham | 2538 | 4000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2227 | Wareham | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2228 | Wareham | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2229 | Wareham | 2538 | 1000 | PV | 3-83-83 | 2012-08-20 | 2012-08-27 | 5 | 5 | 0 | 2012-08-27 | 2012-10-09 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-25 | No | EXP |  |  |  | 0 | 0 | 0 |  | 2013-03-11 |  |  |  | Private | Y
2120504 | Edgartown | 02539 | 36 | PV | 4-97-97 | 2016-01-11 | 2016-01-26 | 11 | 0 | 11 | 2016-01-26 | 2016-01-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2016-06-25 | TBD | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  | 2016-06-08 | Online |  | Private
2005414 | Edgartown | 02539 | 80 | PV | 4-75-123 | 2014-05-30 | 2015-05-07 | 244 | 0 | 244 | 2014-06-05 | 2014-12-29 | 147 | 148 | -1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2015-01-08 | No | STD | 60 |  |  | 0 |  | 0 |  | 2016-06-23 | 2016-06-30 | Online |  | Private | N
2007907 | Edgartown | 02539 | 18.7 | PV | 4-75-123 | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-10-07 | 82 | 46 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | 58 | 0 | 58 | 2015-08-31 | 2015-10-13 | 31 | 0 | 31 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online |  | Private | N
2062416 | Edgartown | 02539 | 56 | PV | 4-97-97 | 2015-04-07 | 2015-04-07 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-07-21 | 2016-08-29 | Online |  | Private | N
2128645 | Edgartown | 02539 | 72 | PV | 4-97-97 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-31 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 |  | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-22 | Online |  | Private
2130081 | Edgartown | 02539 | 170 | PV | 4-97-97 | 2016-02-22 | 2016-02-23 | 1 | 0 | 1 | 2016-03-03 | 2016-03-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-25 |  | 2016-09-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-26 | Online |  | Private
2123548 | Edgartown | 02539 | 36 | PV | 4-97-97 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-03-14 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-12 | 2016-08-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online |  | Private
2245195 | Edgartown | 02539 | 74.4 | PV | 4-97-97 | 2017-10-18 | 2017-10-23 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-04 | Online
2291054 | Edgartown | 02539 | 19.6 | PV | 4-99-99 | 2018-05-31 | 2018-07-25 | 39 |  | 39 | 2018-08-09 |  | -30935 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0
863 | Edgartown | 2539 | 68 | Wind | 4-75-75 | 2009-01-05 | 2009-05-14 | 93 | 70 | 23 | 2009-05-14 | 2009-06-16 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2008-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-14 |  | 2009-08-13 | Online |  | Private | Y
1661 | Edgartown | 2539 | 42 | PV | 4-99-223 | 2010-08-03 | 2010-08-12 | 7 | 5 | 2 | 2010-08-18 | 2010-10-06 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-13 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Online |  | Gov't | Y
1761 | Edgartown | 2539 | 55 | Wind | 4-97-97 | 2011-02-03 | 2011-02-07 | 2 | 1 | 1 | 2011-02-07 | 2011-03-31 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-01 |  | 2011-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-28 |  | 2011-05-04 | Online |  | Private | Y
1674 | Edgartown | 2539 | 15 | PV | 4-99-99 | 2010-09-13 | 2010-09-22 | 7 | 7 | 0 | 2011-01-24 | 2011-03-25 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-25 |  | 2010-03-28 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-05-19 | Online |  | Private | Y
1967 | Edgartown | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-01-31 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Private | Y
1968 | Edgartown | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-02-01 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online |  | Private | Y
1887 | Edgartown | 2539 | 1083 | PV | 4-97-97 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 234 | 0 | 234 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Gov't | Y
2390 | Edgartown | 2539 | 26 | PV | 4-75-75 | 2013-05-21 | 2013-05-28 | 5 | 5 | 0 | 2013-05-28 | 2013-07-01 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-08 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online |  | Private | Y
2365 | Edgartown | 2539 | 266 | PV | 4-97-97 | 2013-03-26 | 2013-10-03 | 137 | 133 | 4 | 2013-10-04 |  | -29681 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online |  | Private | Y
1886 | Edgartown | 2539 | 1083 | PV | 4-97-227 | 2011-08-22 | 2011-08-22 | 0 | 0 | 0 | 2011-08-23 | 2011-09-12 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-06-20 | 151 | 0 | 151 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online |  | Gov't | Y
1917 | Edgartown | 2539 | 1500 | PV | 4-97-97 | 2011-09-15 | 2011-09-20 | 3 | 1 | 2 | 2011-09-21 | 2011-11-07 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-08 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1953 | Edgartown | 2539 | 12 | PV | 4-75-227 | 2011-10-28 | 2011-11-01 | 2 | 1 | 1 | 2011-11-01 | 2011-11-29 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1335 | Edgartown | 2539 | 5 | Wind | 4-75-75 | 2009-06-22 |  | -28562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2011 | Edgartown | 2539 | 1250 | PV | 4-97-97 | 2011-12-15 | 2012-01-09 | 17 | 0 | 17 | 2012-01-10 |  | -29228 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2366 | Edgartown | 2539 | 18 | PV | 4-75-123 | 2013-03-28 | 2013-04-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-07-22 | Private | Y
2062098 | Falmouth | 02540 | 56 | PV | 4-76-436 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-22 | 2015-04-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 | 2015-04-23 | 2015-11-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-04 | Online |  | Private
2233941 | Falmouth | 02540 | 33.3 | PV | 4-72-433 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-08 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
2402100 | Falmouth | 02540 | 133 | PV | TBD | 2020-06-11 | 2020-06-15 | 2 | 0 | 2 | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | [20 empty] | 2020-06-15 | 2020-07-06 | 2020-12-15 | No | EXP | 30 | [7 empty] | 2020-08-19 | Online |  | Private
2012720 | Falmouth | 02540 | 47.8 | PV | 4-107-830 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-16 |  | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2093955 | Falmouth | 02540 | 19 | PV | 4-76-436 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-16 | 2015-09-28 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 | 2015-10-30 | 2016-01-20 | TBD | EXP | 30 | 2016-01-04 | 2016-01-04 | 0 |  | 0 |  | 2016-01-26 |  | Withdrawn |  | Private
2125878 | Falmouth | 02540 | 250 | PV | 10494/020 | 2016-01-28 | 2016-01-29 | 1 | 0 | 1 | 2016-02-01 | 2016-06-06 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-20 |  | 2016-09-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2396002 | Falmouth | 02540 | 958 | PV | TBD | 2020-04-30 |  | 170 | 0 | 170 |  |  | 0 | 0 | 0 | [22 empty] | 2020-12-07 | TBD |  | 30 | [8 empty] | In Queue |  | Private
1526 | East Falmouth | 2540 | 20 | PV | 4-98A-98A | 2009-12-02 | 2009-12-15 | 9 | 9 | 0 | 2009-12-16 |  | -28689 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
744 | Falmouth | 2540 | 1545 | Wind | 4-98A-98A | 2009-01-15 | 2009-01-15 | 0 |  | 0 | 2009-01-15 | 2009-03-13 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-04-29 | [7 empty] | 0 |  | 0 |  |  | 2010-03-23 | Online |  |  | Y
1681 | Falmouth | 2540 | 75 | PV | 4-72-72 | 2010-09-21 | 2010-09-28 | 5 | 4 | 1 | 2010-10-04 | 2010-11-15 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-02 |  | 2010-12-02 | Online |  | Gov't | Y
1595 | Falmouth | 2540 | 1650 | Wind | 4-98A-98A | 2010-03-29 | 2010-04-01 | 3 | 3 | 0 | 2010-04-01 | 2010-04-20 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-14 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-15 |  | 2012-02-14 | Online |  | Private | N
2067 | Falmouth | 2540 | 70 | PV | 4-98A-461 | 2012-03-06 | 2012-03-08 | 2 | 2 | 0 | 2012-03-08 | 2012-04-09 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-10 | Online |  | Private | Y
2391 | Falmouth | 2540 | 60 | PV | 4-76-437 | 2013-04-16 | 2013-05-22 | 26 | 23 | 3 | 2013-05-22 | 2013-06-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-13 | Online |  | Private | Y
2394 | Falmouth | 2540 | 25 | PV | 4-107-830 | 2013-05-31 | 2013-06-26 | 18 | 18 | 0 | 2013-07-01 | 2013-08-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-26 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online |  | Private | Y
2420 | Falmouth | 2540 | 40 | PV | 4-76-76 | 2013-07-09 | 2013-10-02 | 61 | 58 | 3 | 2013-10-08 | 2013-12-11 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-10 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-03 | Online |  | Private | Y
2090 | Falmouth | 2540 | 26 | PV | 4-107-830 | 2012-03-30 | 2012-04-05 | 4 | 2 | 2 | 2012-04-05 | 2012-05-14 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1692 | Bourne | 2542 | 3000 | Wind | 3-88-923 | 2010-09-28 | 2010-10-01 | 3 | 0 | 3 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Gov't | Y
557 | Sandwich | 2542 | 1500 | Wind | 4-81A-81A | 2009-01-12 | 2009-01-12 | 0 | 8 | 0 | 2009-02-18 |  | -28474 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-24 | 2009-06-24 |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2009-12-22 | Online |  | Private | N
990 | Woods Hole | 2543 | 10 | Wind | 4-91-434 | 2009-02-17 | 2009-02-17 | 0 |  | 0 | 2009-02-17 | 2009-03-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-03-03 | [7 empty] | 0 |  | 0 | 2009-04-30 |  | 2009-05-07 | Online |  |  | Y
2094911 | MONUMENT BEACH | 02553 | 496 | PV | 4-86-408 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-23 | 2016-04-12 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-09 | 2016-02-09 | 2016-05-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-30 | Online |  | Private
1683 | North Falmouth | 2556 | 43 | PV | 4-78-420 | 2010-09-20 | 2010-09-30 | 8 | 2 | 6 | 2010-10-01 | 2010-11-05 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-10-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-25 |  | 2011-02-02 | Online |  | Private | Y
2055949 | Oak Bluffs | 02557 | 2000 | PV | 4-75-75 | 2015-02-24 | 2015-02-25 | 1 | 0 | 1 | 2015-02-27 | 2015-04-27 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2392014 | Oak Bluffs | 02557 | 1500 | PV | TBD | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 2020-04-08 |  | 186 | 179 | 7 | [22 empty] | 2020-11-03 | TBD |  | 30 | [8 empty] | In Queue | 2020-04-17 | Private
1413 | Oak Bluffs | 2557 | 39 | PV | 4-99-221 | 2009-08-25 | 2010-03-30 | 155 | 153 | 2 | 2010-03-30 | 2011-03-09 | 246 | 0 | 246 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-12 |  | 2011-04-15 | Online |  | Private | Y
2359 | Oak Bluffs | 2557 | 260 | PV | 4-75-75 | 2013-03-18 | 2013-03-25 | 5 | 0 | 5 | 2013-03-25 | 2013-04-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online |  | Private | Y
2200 | Oak Bluffs | 2557 | 100 | PV | 4-75-75 | 2012-08-03 |  | -29376 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2381115 | Onset | 02558 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-13 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2002111 | Pocasset | 02559 | 248.4 | PV | 4-86-86 | 2014-02-05 | 2014-04-22 | 54 | 0 | 54 | 2014-05-16 | 2014-05-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-20 | 2014-08-14 | 2014-12-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-10-23 | Online |  | Private
2029122 | Pocasset | 02559 | 55.2 | PV | 4-81A-406 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-08 | 2014-11-12 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-09 | 2015-01-15 | 2015-04-30 | No | EXP | 30 | 2015-03-09 | 2015-03-09 | 0 |  | 0 |  | 2015-04-27 | 2015-04-27 | Online |  | Private | N
2029376 | Pocasset | 02559 | 34.2 | PV | 4-81A-406 | 2014-10-09 | 2014-10-09 | 0 | 0 | 0 | 2014-10-17 | 2015-05-20 | 153 | 115 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-03 |  | 2015-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-02 | 2016-03-02 | Online |  | Gov't | N
2102746 | Pocasset | 02559 | 27 | PV | 4-81A-81A | 2015-10-27 | 2015-10-29 | 2 | 0 | 2 | 2015-11-02 | 2015-12-29 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-15 | 2016-02-10 | 2016-07-15 | TBD | EXP | 30 | 2016-06-09 | 2016-06-09 | 0 |  | 0 |  |  | 2016-07-22 | Online |  | Private
2124995 | Sagamore Beach | 02562 | 150 | PV | 3-89-925 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-03-22 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-02-17 | 2016-08-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online |  | Private | N
2223 | Sagamore Beach | 2562 | 250 | PV | 3-89-925 | 2012-07-17 | 2012-08-21 | 25 | 3 | 22 | 2012-08-21 | 2012-09-24 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  | 2012-10-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-04 |  | 2014-09-09 | Online |  | Private | Y
2091380 | Sandwich | 02563 | 1476 | PV | 4-81A-439 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-08 | Online | 2015-09-28 | Private
2407070 | Sandwich | 02563 | 499 | PV | TBD | 2020-07-16 | 2020-07-20 | 2 | 0 | 2 | 2020-08-04 |  | 104 | 100 | 4 | [22 empty] | 2020-12-15 | TBD |  | 30 | [8 empty] | In Queue | 2020-08-10 | Private
2044 | Sandwich | 2563 | 1500 | PV | 4-81B-443 | 2012-02-03 | 2012-02-21 | 12 | 11 | 1 | 2012-02-21 | 2012-03-16 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-13 | 2012-06-27 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 2012-06-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2043 | Sandwich | 2563 | 3500 | PV | 4-81B-443 | 2012-02-01 | 2012-02-13 | 8 | 7 | 1 | 2012-02-13 | 2012-03-20 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1923 | Tisbury | 2568 | 1083 | PV | 4-91-91 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 | 2012-05-09 | 77 | 0 | 77 |  |  | 0 | 0 | 0 | 2013-11-19 |  | 2012-08-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-25 | Online |  | Gov't | Y
2334 | Tisbury | 2568 | 500 | PV | 4-91-91 | 2013-01-24 |  | -29500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2050 | Vineyard Haven | 2568 | 135 | PV | 4-75-75 | 2012-02-10 | 2012-02-22 | 8 | 7 | 1 | 2012-02-22 | 2012-03-30 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-10 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
2113 | Vineyard Haven | 2568 | 19 | PV | 4-75-75 | 2012-04-23 | 2012-05-01 | 6 | 4 | 2 | 2012-05-01 | 2012-06-05 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-28 | Online |  | Gov't | Y
2222 | Vineyard Haven | 2568 | 12 | PV | 4-91-122 | 2012-08-07 | 2012-08-27 | 14 | 7 | 7 | 2012-08-27 | 2012-10-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-09 | Online |  | Private | Y
2190 | Vineyard Haven | 2568 | 50 | PV | 4-97-228 | 2012-07-30 | 2012-08-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-17 | Online |  | Gov't | N
1675 | Vineyard Haven | 2568 | 72 | PV | 4-91-222 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2069 | West Tisbury | 2568 | 31 | PV | 4-97-97 | 2012-03-05 | 2012-04-03 | 21 | 19 | 2 | 2012-04-03 | 2012-06-26 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2145 | West Tisbury | 2568 | 13 | PV | 4-97-220 | 2012-05-23 | 2012-09-27 | 91 | 82 | 9 | 2012-09-27 | 2012-10-04 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 | 2013-01-29 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2189 | West Tisbury | 2568 | 850 | PV | 4-91-220 | 2012-07-30 | 2012-10-23 | 61 | 59 | 2 | 2013-04-08 | 2013-05-03 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2023726 | Wareham | 02571 | 324.8 | PV | 3-86-966 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | 2014-09-18 | 2014-10-10 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-08 |  | 2015-04-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2014-12-23 | Online |  | Private
2051382 | Wareham | 02571 | 56 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-02-18 | 2015-08-26 | TBD | EXP | 30 | 2015-03-19 | 2015-03-19 | 0 |  | 0 |  |  | 2015-03-27 | Online |  | Private
2029884 | Wareham | 02571 | 60 | PV | 3-86-966 | 2014-10-21 | 2014-10-21 | 0 | 0 | 0 | 2014-10-23 | 2014-12-22 | 42 | 39 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-23 | 2015-06-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-12 | 2015-04-22 | Online |  | Private
1972361 | Wareham | 02571 | 5000 | PV | 3-83-83 | 2013-11-25 | 2013-12-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2015-12-29 | 2016-04-19 | Online |  | Gov't
2035472 | Wareham | 02571 | 999 | PV | 3-85-955 | 2014-11-12 | 2014-11-13 | 1 | 0 | 1 | 2014-11-14 | 2015-01-12 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-12-29 | 2015-06-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  | 2016-08-29 | Online |  | Private
2092960 | Wareham | 02571 | 5500 | PV | 3-82-82 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online | 2016-04-25 | Private
2051336 | Wareham | 02571 | 150 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 | 2015-02-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
2062402 | Wareham | 02571 | 17 | PV | 3-84-84 | 2015-04-06 | 2015-04-16 | 8 | 0 | 8 | 2015-04-20 | 2015-04-21 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-22 | 2015-04-22 | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2128802 | Wareham | 02571 | 1992 | PV | 3-83-966 | 2016-02-12 | 2016-02-16 | 2 | 0 | 2 | 2016-02-23 | 2016-03-08 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 |  | 2016-09-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn
2132937 | Wareham | 02571 | 150 | PV | 3-84-84 | 2016-03-04 | 2016-03-08 | 2 | 0 | 2 | 2016-03-15 | 2016-03-22 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 | 2016-09-01 | 2016-10-11 | No | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  |  | In Queue |  | Private
2024196 | Wareham | 02571 | 2000 | PV | 3-84-84 | 2014-08-13 | 2014-09-16 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2077939 | Wareham | 02571 | 200 | PV | 3-84-961 | 2015-06-30 | 2015-07-06 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2093002 | Wareham | 02571 | 4000 | PV | 3-83-83 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2209835 | Wareham | 02571 | 0 |  | TBD | 2017-04-06 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2018-05-01 | 2018-03-31 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2323953 | Wareham | 02571 | 2000 | PV | 3-82-82 | 2019-02-06 |  | 475 | 0 | 475 | [12 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 2020-01-24 | TBD |  | 60 | [8 empty] | In Queue |  | Private
2333746 | Wareham | 02571 | 4500 | PV | TBD | 2019-04-08 | 2019-04-09 | 1 | 0 | 1 | 2019-04-10 |  | 433 | 427 | 6 | [17 empty] | 0 | 0 | 0 |  |  | 2020-06-30 | TBD |  | 30 | [8 empty] | In Queue | 2019-04-18 | Private
2359588 | Wareham | 02571 | 5000 | PV | TBD | 2019-09-16 | 2019-09-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | [22 empty] | 2020-04-24 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2361120 | Wareham | 02571 | 0 |  | TBD | 2019-09-25 |  | 138 | 0 | 138 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-05 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2393736 | Wareham | 02571 | 8500 | PV | TBD | 2020-04-13 | 2020-12-21 | 174 | 0 | 174 | 2020-12-21 |  | 9 | 0 | 9 | [22 empty] | 2022-05-01 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2393742 | Wareham | 02571 | 8500 | PV | TBD | 2020-04-13 |  | 183 | 0 | 183 |  |  | 0 | 0 | 0 | [22 empty] | 2022-03-01 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2247812 | Wareham | 02571 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-07-11 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1678 | Wareham | 2571 | 2300 | Wind | 3-83-966 | 2010-09-15 | 2010-09-20 | 3 | 2 | 1 | 2010-09-20 | 2010-10-20 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-11-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-12-23 | Online |  | Private | Y
1587 | Wareham | 2571 | 4398 | PV | 3-83-83 | 2010-03-03 | 2010-03-08 | 3 | 3 | 0 | 2010-03-08 | 2011-04-15 | 289 | 0 | 289 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-01-28 | Online |  | Private | Y
1772 | Wareham | 2571 | 875 | PV | 3-86-966 | 2011-02-24 | 2011-03-16 | 14 | 13 | 1 | 2011-03-16 | 2011-04-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2012-07-31 | Online |  | Private | Y
2128 | Wareham | 2571 | 583 | PV | 4-83-83 | 2012-05-10 | 2012-06-11 | 22 | 22 | 0 | 2012-06-11 | 2012-07-23 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-27 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-27 | Online |  | Private | Y
2130 | Wareham | 2571 | 583 | PV | 3-83-83 | 2012-05-11 | 2012-05-14 | 1 | 0 | 1 | 2012-05-14 | 2012-07-09 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-07-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1676 | Wareham | 2571 | 11500 | Wind | 3-83-966 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1677 | Wareham | 2571 | 4600 | Wind | 3-85-928 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2350 | Wareham | 2571 | 1000 | PV | 3-83-83 | 2013-02-22 | 2013-02-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-06-17 | Private | Y
2002682 | West Tisbury | 02575 | 204 | PV | 4-97-220 | 2014-05-14 | 2014-05-15 | 1 | 0 | 1 | 2014-06-18 | 2015-06-15 | 258 | 243 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't
2114 | Aquinnah | 2575 | 54 | PV | 4-97-126 | 2012-04-21 | 2012-04-30 | 6 | 3 | 3 | 2012-04-30 | 2012-06-11 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-09-19 | 236 | 0 | 236 |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-12 | Online |  | Gov't | Y
2068 | Oak Bluffs | 2575 | 13 | PV | 4-99-99 | 2012-03-01 | 2012-03-06 | 3 | 0 | 3 | 2012-03-07 | 2012-04-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1172 | West Tisbury | 2575 | 5 | Wind | 4-97-222 | 2009-02-17 | 2009-03-16 | 19 |  | 19 | 2017-10-17 |  | -30725 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-05-27 | 2009-05-27 | [6 empty] | 0 |  | 0 |  |  | 2009-07-08 | Online
2098 | West Tisbury | 2575 | 13 | PV | 4-97-226 | 2012-04-12 | 2012-06-27 | 54 | 54 | 0 | 2012-06-27 | 2012-08-07 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online |  | Private | Y
2287 | West Tisbury | 2575 | 26 | PV | 4-97-220 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2012-12-12 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online |  | Private | Y
2388 | West Tisbury | 2575 | 15 | PV | 4-97-97 | 2013-05-17 | 2013-05-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-09 | Online |  | Private | Y
1879 | West Tisbury | 2575 | 5 | Wind | 4-97-97 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1969 | West Tisbury | 2575 | 250 | PV | 4-91-91 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2198 | West Tisbury | 2575 | 34 | PV | 4-97-97 | 2012-08-03 | 2012-09-13 | 29 | 29 | 0 | 2012-09-13 | 2012-12-20 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-01-08 | Gov't | Y
2374 | West Tisbury | 2575 | 15 | PV | 4-97-97 | 2013-04-24 | 2013-05-01 | 5 | 3 | 2 | 2013-05-01 | 2013-06-27 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2009038 | Wareham | 02576 | 18 | PV | 3-85-85 | 2014-06-13 | 2014-06-18 | 3 | 0 | 3 | 2014-06-27 | 2014-07-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 | 2014-09-03 | 2015-01-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-02-04 | 2016-02-04 | Online |  | Private
2102456 | Wareham | 02576 | 600 | PV | 3-85-85 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-28 | 2016-01-29 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 | 2016-03-08 | 2017-01-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-16 | Online
2071689 | Wareham | 02576 | 1800 | PV | 3-85-85 | 2015-05-27 | 2015-05-28 | 1 | 0 | 1 | 2015-05-28 | 2015-06-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-10 |  | 2016-01-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-17 | Online |  | Private
2011256 | Wareham | 02576 | 42 | PV | 3-86-966 | 2014-06-26 | 2014-07-03 | 5 | 0 | 5 | 2014-08-04 | 2014-10-06 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 | 2015-02-05 | 2015-10-01 | TBD | EXP | 30 | 2015-01-30 |  | -30026 |  | 0 |  | 2015-09-23 |  | Withdrawn |  | Gov't
2086312 | Wareham | 02576 | 1440 | PV | 3-85-928 | 2015-08-05 | 2015-08-07 | 2 | 0 | 2 | 2015-08-11 | 2015-09-15 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2282256 | Wareham | 02576 | 1497 | PV | TBD | 2018-06-15 |  | 24 | 0 | 24 | 2018-09-22 | 2018-09-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-01-25 | No | EXP | 30 | [8 empty] | Withdrawn |  | Private
2287856 | Wareham | 02576 | 3992 | PV | TBD | 2018-07-20 |  | 1 | 0 | 1 | 2018-09-22 | 2018-09-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-03-01 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2050542 | Wareham | 02576 | 23.6 | PV | 3-85-928 | 2015-01-20 | 2015-01-20 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2346531 | Wareham | 02576 | 4980 | PV | TBD | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | 2019-06-27 |  | 378 | 371 | 7 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-02-03 | TBD | TBD | 30 | [8 empty] | In Queue | 2019-07-09 | Private
2410816 | Wareham | 02576 | 0 |  | TBD | 2020-08-14 |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2030-12-20 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1821 | Wareham | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
1822 | Wareham | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
1823 | Wareham | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online |  | Private | N
1824 | Wareham | 2576 | 500 | PV | 3-86-86 | 2011-06-01 | 2011-06-08 | 5 | 3 | 2 | 2011-06-08 | 2011-06-16 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-17 | Online |  | Private | Y
2074 | Wareham | 2576 | 1000 | PV | 3-83-83 | 2012-03-19 | 2012-04-19 | 23 | 21 | 2 | 2012-04-19 | 2012-05-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2156 | West Wareham | 2576 | 60 | PV | 3-86-966 | 2012-06-20 | 2012-08-16 | 41 | 33 | 8 | 2012-08-16 | 2012-09-21 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2071355 | Hyannis | 02601 | 144 | PV | 4-80B-523 | 2015-05-21 | 2015-06-25 | 25 | 0 | 25 | 2015-07-01 | 2015-08-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online |  | Private
2105424 | Hyannis | 02601 | 96 | PV | 4-84A-520 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-11-27 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-04 | 2016-02-12 | 2016-03-31 | TBD | EXP | 30 | 2016-03-31 | 2016-03-31 | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private
2012789 | Hyannis | 02601 | 252 | PV | 4-84B-524 | 2014-07-03 | 2014-07-10 | 5 | 0 | 5 | 2014-07-16 | 2014-08-25 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 | 2014-09-03 | 2015-02-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 |  | Withdrawn |  | Private
2108876 | Hyannis | 02601 | 120 | PV | 4-84B-524 | 2015-12-03 | 2015-12-04 | 1 | 18 | -17 | 2015-12-08 | 2016-01-25 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2134025 | Hyannis | 02601 | 72 | PV | 4-84B-524 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2151036 | Hyannis | 02601 | 38 | PV | 4-63-63 | 2016-06-02 | 2016-06-08 | 4 | 0 | 4 | 2016-06-14 | 2016-06-30 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2017-01-11 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2071356 | Hyannis | 02601 | 120 | PV | 4-84B-524 | 2015-05-26 | 2015-06-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-06-23 | Private | N
2369838 | Hyannis | 02601 | 975 | PV | TBD | 2019-11-20 | 2019-11-27 | 5 | 0 | 5 | 2019-11-28 |  | 272 | 264 | 8 | [22 empty] | 2020-06-29 | TBD |  | 30 | [8 empty] | In Queue | 2019-12-10 | Private
1618 | Barnstable | 2601 | 131 | PV | 4-80B-514 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
2192 | Barnstable | 2601 | 1250 | PV | 4-80B-80B | 2012-07-30 | 2012-12-17 | 100 |  | 100 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2193 | Barnstable | 2601 | 1750 | PV | 4-80B-80B | 2012-07-30 |  | -29372 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1294 | Hyannis | 2601 | 27 | PV | 4-63-521 | 2009-05-29 | 2009-06-02 | 2 | 0 | 2 | 2009-06-03 | 2009-06-30 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-10-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-02-04 | Online |  | Private | N
1187 | Hyannis | 2601 | 105 | Natural Gas | 4-80B-80B | 2009-02-25 | 2009-02-26 | 1 | 0 | 1 | 2009-03-04 | 2009-04-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-30 |  | 2009-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2010-07-21 | Online |  | Private | N
1591 | Hyannis | 2601 | 259 | PV | 4-84B-524 | 2010-03-22 | 2010-03-24 | 2 | 2 | 0 | 2010-07-30 | 2010-10-08 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-03-09 |  | 2010-08-05 | Online |  | Private | Y
1602 | Hyannis | 2601 | 60 | PV | 4-80B-80B | 2010-04-21 | 2010-05-18 | 19 | 19 | 0 | 2010-05-18 | 2010-06-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online |  | Private | Y
1625 | Hyannis | 2601 | 25 | PV | 4-80B-523 | 2010-05-18 | 2010-05-25 | 5 | 5 | 0 | 2010-05-25 | 2010-06-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online |  | Private | Y
1617 | Hyannis | 2601 | 14 | PV | 4-63-905 | 2010-05-03 | 2010-05-12 | 7 | 7 | 0 | 2010-05-12 | 2010-06-11 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online |  | Gov't | Y
1601 | Hyannis | 2601 | 48 | PV | 4-80B-80B | 2010-04-21 | 2010-04-21 | 0 | 0 | 0 | 2010-05-18 | 2010-06-15 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-07 |  | 2010-10-07 | Online |  | Private | Y
1603 | Hyannis | 2601 | 40 | PV | 4-84B-524 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-10 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online |  | Private | N
1545 | Hyannis | 2601 | 200 | Wind | 4-80B-523 | 2010-01-05 | 2010-01-12 | 5 | 2 | 3 | 2010-01-12 | 2010-02-16 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-10 |  | 2010-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-26 |  | 2011-04-28 | Online |  | Private | N
1722 | Hyannis | 2601 | 43 | PV | 4-80B-80B | 2010-12-01 | 2010-12-13 | 8 | 7 | 1 | 2010-12-13 | 2011-01-12 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-14 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-27 |  | 2011-05-27 | Online |  | Private | Y
1648 | Hyannis | 2601 | 766 | PV | 4-80B-523 | 2010-07-14 | 2010-07-28 | 10 | 10 | 0 | 2010-08-02 | 2010-09-10 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2012-01-31 | Online |  | Gov't | Y
1936 | Hyannis | 2601 | 50 | PV | 4-84B-524 | 2011-10-07 | 2011-10-12 | 3 | 1 | 2 | 2011-10-13 | 2011-11-19 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-04-17 |  | 2012-04-19 | Online |  | Private | Y
1757 | Hyannis | 2601 | 82 | PV | 4-63-521 | 2011-01-31 | 2011-08-16 | 141 | 140 | 1 | 2011-08-16 | 2011-11-18 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2012-06-27 | Online |  | Private | Y
2058 | Hyannis | 2601 | 26 | PV | 4-84A-520 | 2012-02-23 | 2012-02-27 | 2 | 1 | 1 | 2012-02-28 | 2012-03-19 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online |  | Private | Y
1946 | Hyannis | 2601 | 475.2 | PV | 4-80B-80B | 2011-10-20 | 2011-10-20 | 0 | 0 | 0 | 2011-10-21 | 2011-12-22 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-18 |  | 2012-07-13 | Online |  | Private | Y
2088 | Hyannis | 2601 | 110 | PV | 4-80B-514 | 2012-03-29 | 2012-05-02 | 24 | 23 | 1 | 2012-05-02 | 2012-06-13 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-14 |  | 2012-03-30 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online |  | Private | Y
1875 | Hyannis | 2601 | 1238 | PV | 4-80B-80-B | 2011-08-04 | 2011-08-09 | 3 | 2 | 1 | 2011-08-09 | 2011-09-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-08-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-27 | Online |  | Private | Y
1935 | Hyannis | 2601 | 35 | PV | 4-84B-524 | 2011-10-10 | 2011-10-12 | 2 | 1 | 1 | 2011-10-20 | 2012-01-20 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
2159 | Hyannis | 2601 | 60 | PV | 4-63-905 | 2012-06-28 | 2012-07-24 | 18 | 12 | 6 | 2012-07-24 | 2012-08-28 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-31 |  | 2012-08-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-08 | Online |  | Private | Y
2185 | Hyannis | 2601 | 500 | PV | 4-80B-514 | 2012-07-30 | 2012-08-22 | 17 | 16 | 1 | 2012-08-22 | 2012-11-16 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-20 | Online |  | Gov't | Y
2423 | Hyannis | 2601 | 750 | PV | 4-84B-510 | 2013-07-22 | 2013-07-25 | 3 | 2 | 1 | 2013-07-26 |  | -29631 | 0 | 0 | 2013-09-11 | 2013-10-08 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-10 |  | 2013-10-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online |  | Gov't | Y
1984 | Hyannis | 2601 | 46 | PV | 4-84B-524 | 2011-11-30 | 2012-02-22 | 60 | 58 | 2 | 2012-02-29 | 2012-05-26 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2202 | Hyannis | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2203 | Hyannis | 2601 | 1000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2204 | Hyannis | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-12-27 | 103 | 103 | 0 | 2012-12-27 | 2013-01-29 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | -29663 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2181 | Hyannis | 2601 | 4500 | PV | 4-84B-524 | 2012-07-30 |  | -29372 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
PP02407747 | Hyannis | 02601` | 19.92 | PV | TBD | 2020-10-15 | 2020-11-12 |  |  |  | 2021-01-05 | [24 empty] | 2020-12-06 | [12 empty] | 2021-07-28 | Online
1963 | Barnstable | 2630 | 14 | PV | 4-82-518 | 2011-11-10 | 2011-11-18 | 6 | 4 | 2 | 2011-11-22 | 2012-01-31 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | 142 | 0 | 142 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
2043623 | Brewster | 02631 | 132 | PV | 4-89A-553 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 | 2014-12-29 | 2015-01-06 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2015-02-05 | 2015-04-01 | TBD | EXP | 30 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 2015-04-07 | Online |  | Private
2116973 | Brewster | 02631 | 82 | PV | 4-89A-553 | 2015-12-22 | 2015-12-23 | 1 | 0 | 1 | 2015-12-29 | 2015-12-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 |  | 2016-07-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-21 | Online |  | Private
2087387 | Brewster | 02631 | 111 | PV | 4-95A-597 | 2015-08-14 | 2015-08-15 | 1 | 0 | 1 | 2015-08-21 | 2015-12-15 | 82 | 53 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2396597 | Brewster | 02631 | 86.4 | PV | TBD | 2020-05-04 |  | 2 | 0 | 2 | 2020-05-06 | 2020-05-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-05-13 | 2020-05-12 | 2020-12-09 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Gov't
1177 | Brewster | 2631 | 10 | Wind | 4-89B-89B | 2009-02-25 | 2009-02-26 | 1 | 0 | 1 | 2009-02-26 | 2009-04-14 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-07-09 | Online |  | Private | N
1520 | Brewster | 2631 | 101 | PV | 4-89B-573 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2009-12-23 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online |  | Gov't | Y
1640 | Brewster | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-29 | 2010-07-06 | 5 | 5 | 0 | 2010-07-06 | 2010-08-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-10-14 | Online |  | Gov't | N
1635 | Brewster | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-16 | 2010-08-13 | 42 | 42 | 0 | 2010-08-19 | 2011-01-28 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-17 |  | 2011-02-17 | Online |  | Private | N
1774 | Brewster | 2631 | 2 | PV | 4-89B-577 | 2011-02-24 | 2011-03-16 | 14 | 13 | 1 | 2011-03-16 | 2011-03-28 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-31 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2011-05-20 | Online |  | Private | Y
1950 | Brewster | 2631 | 1785 | PV | 4-95B-600 | 2011-10-24 | 2011-10-25 | 1 | 0 | 1 | 2011-10-25 | 2011-11-30 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-03-15 | Online |  | Private | Y
2016 | Brewster | 2631 | 11 | PV | 4-89B-576 | 2012-01-06 | 2012-01-11 | 3 | 0 | 3 | 2012-01-11 | 2012-02-06 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-27 |  | 2012-03-10 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Private | Y
2269 | Brewster | 2631 | 16 | PV | 4-89B-89B | 2012-10-02 | 2012-10-24 | 16 | 16 | 0 | 2012-10-24 | 2012-12-12 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-13 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-05 | Online |  | Private | Y
1912 | Brewster | 2631 | 1083 | PV | 4-89A-553 | 2011-09-09 | 2011-09-20 | 7 | 6 | 1 | 2011-09-20 | 2011-10-18 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | 137 | 0 | 137 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online |  | Gov't | Y
1775 | Brewster | 2631 | 21 | PV | 4-89B-577 | 2011-03-03 | 2011-03-07 | 2 | 1 | 1 | 2011-03-07 | 2011-05-24 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1871 | Brewster | 2631 | 310 | PV | 4-95B-600 | 2011-08-02 | 2011-08-04 | 2 | 2 | 0 | 2011-08-04 | 2011-09-08 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  |  |  |  | Gov't | N
2205 | Brewster | 2631 | 750 | PV | 4-89B-576 | 2012-08-06 | 2012-12-14 | 94 | 94 | 0 | 2012-12-21 | 2013-01-29 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | -29663 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2323 | Brewster | 2631 | 16 | PV | 4-89B-946 | 2012-12-26 | 2012-12-27 | 1 | 1 | 0 | 2012-12-27 | 2013-02-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-02-21 | Private | Y
1522 | Brewster | 2631 | 101 | PV | 4-89B-573 | 2009-12-03 | 2009-12-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
1773 | Brewster | 2631 | 15 | PV | 4-89B-577 | 2011-02-24 |  | -29000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2206 | Brewster | 2631 | 3000 | PV | 4-95B-600 | 2012-08-07 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2207 | Brewster | 2631 | 1000 | PV | 4-95B-600 | 2012-08-07 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2275 | Brewster | 2631 | 25 | PV | 4-89B-945 | 2012-10-02 |  | -29418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2065805 | Centerville | 02632 | 17.4 | PV | 4-82-508 | 2015-04-27 | 2015-05-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-07-27 | Private
1817 | Chatham | 2633 | 21 | PV | 4-95B-941 | 2011-05-25 | 2011-06-06 | 8 | 7 | 1 | 2011-06-06 | 2011-06-16 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-06-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-28 | Online |  | Gov't | Y
1778 | Chatham | 2633 | 31 | PV | 4-95A-608 | 2011-03-10 | 2011-04-15 | 26 | 25 | 1 | 2011-04-15 | 2011-06-14 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-06-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-06 | Online |  | Private | Y
1911 | Chatham | 2633 | 1500 | PV | 4-95B-606 | 2011-09-12 | 2011-10-21 | 29 | 29 | 0 | 2011-10-24 | 2012-01-27 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-09 | 2012-06-20 | 73 | 0 | 73 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-29 | Online |  | Gov't | Y
2188 | Chatham | 2633 | 868 | PV | 4-95B-95B | 2012-07-30 | 2012-10-23 | 61 | 59 | 2 | 2012-10-23 | 2012-12-20 | 42 | 2 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-03-20 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 2013-07-30 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-12-31 | Online |  | Gov't | Y
1908 | Chatham | 2633 | 50 | PV | 4-95A-606 | 2011-09-09 | 2011-09-15 | 4 | 3 | 1 | 2011-09-15 | 2011-10-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2152205 | Cotuit | 02635 | 1992 | PV | 4-88-880 | 2016-06-08 | 2016-06-13 | 3 | 0 | 3 | 2016-06-14 |  | -30383 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30457 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-28 |  | 2017-01-18 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-17 | Private
2153294 | Cotuit | 02635 | 1992 | PV | 4-88-880 | 2016-06-15 | 2016-06-16 | 1 | 0 | 1 | 2016-06-27 |  | -30392 | 37 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30457 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2016-09-28 | 2017-01-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-29 | Private
2037 | Cotuit | 2635 | 12 | PV | 4-88-485 | 2012-01-23 | 2012-01-30 | 5 | 1 | 4 | 2012-01-30 | 2012-02-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online |  | Private | Y
2440 | Cotuit | 2635 | 30 | PV | 4-71-455 | 2013-09-18 | 2013-09-20 | 2 | 2 | 0 | 2013-09-20 |  | -29671 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-13 | Online |  | Private | Y
2054 | Dennis | 2638 | 1250 | PV | 4-92B-92B | 2012-02-13 | 2012-02-24 | 9 | 5 | 4 | 2012-08-23 | 2012-09-21 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-01 |  | 2012-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Withdrawn |  | Private | Y
2053 | Dennis | 2638 | 1250 | PV | 4-92B-92B | 2012-02-12 |  | -29251 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2045155 | Dennisport | 02639 | 72 | PV | 4-92B-583 | 2015-01-06 | 2015-01-08 | 2 | 0 | 2 | 2015-01-12 | 2015-01-29 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-25 | Online |  | Private
2128423 | Dennisport | 02639 | 72 | PV | 4-92B-572 | 2016-02-10 | 2016-02-11 | 1 | 0 | 1 | 2016-02-15 | 2016-02-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-23 | Online |  | Private
2031909 | Dennisport | 02639 | 72 | PV | 4-92B-583 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2132335 | Dennisport | 02639 | 40 | PV | 4-92B-583 | 2016-03-02 | 2016-03-03 | 1 | 22 | -21 | 2016-04-25 | 2016-05-13 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
1485 | Dennisport | 2639 | 33 | PV | 4-92B-583 | 2009-10-29 | 2009-11-03 | 3 | 3 | 0 | 2009-11-03 | 2009-11-13 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2011-04-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
2031577 | Dennis | 02641 | 16.1 | PV | 4-89A-552 | 2014-10-22 | 2014-10-23 | 1 | 0 | 1 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private | N
1508 | Eastham | 2642 | 80 | PV | 4-94B-646 | 2009-11-13 | 2009-11-17 | 2 | 0 | 2 | 2009-12-03 | 2009-12-21 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-24 |  | 2010-02-24 | Online |  | Private | Y
1521 | Eastham | 2642 | 101 | PV | 4-94A-648 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2010-01-28 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-16 |  | 2010-07-16 | Online |  | Gov't | Y
1915 | Eastham | 2642 | 500 | PV | 4-94B-646 | 2011-09-15 | 2011-09-21 | 4 | 4 | 0 | 2011-09-21 | 2011-10-14 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-17 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-02-16 | Online |  | Private | Y
2032 | Eastham | 2642 | 210 | PV | 4-94B-94B | 2012-01-19 | 2012-02-02 | 10 | 8 | 2 | 2012-02-02 | 2012-03-02 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online |  | Private | Y
2033 | Eastham | 2642 | 220 | PV | 4-94B-94B | 2012-01-23 | 2012-01-26 | 3 | 2 | 1 | 2012-01-26 | 2012-02-22 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  | 2011-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-20 | Online |  | Private | Y
2199 | Eastham | 2642 | 500 | PV | 4-94B-646 | 2012-08-03 |  | -29376 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2055988 | Forestdale | 02644 | 15.8 | PV | 4-81B-443 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | 2015-03-02 | 2015-03-05 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-29 | Online |  | Private
2403701 | Forestdale | 02644 | 0 |  | TBD | 2020-06-24 |  | 3 | 0 | 3 | 2020-06-30 | 2020-07-13 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-08-12 | 2020-09-14 | 2020-12-02 | No | EXP | 30 | [8 empty] | Withdrawn |  | Private
2182 | Forestdale | 2644 | 100 | PV | 4-81B-443 | 2012-07-30 | 2012-11-06 | 71 | 70 | 1 | 2012-11-06 | 2012-12-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-15 | Online |  | Gov't | Y
2391210 | Harwich | 02645 | 23 | PV | TBD | 2020-03-24 |  | 197 | 0 | 197 |  |  | 0 | 0 | 0 | [22 empty] | 2020-10-27 | TBD |  | 30 | [8 empty] | In Queue |  | Private
1571 | Harwich | 2645 | 104 | PV | 4-95A-95A | 2010-02-01 | 2010-02-04 | 3 | 1 | 2 | 2010-02-04 | 2010-03-12 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-22 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-14 | Online |  | Gov't | Y
1897 | Harwich | 2645 | 36 | PV | 4-89A-556 | 2011-08-29 | 2011-08-30 | 1 | 1 | 0 | 2011-08-30 | 2011-11-09 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-14 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online |  | Gov't | N
1891 | Harwich | 2645 | 36 | PV | 4-89A-556 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-19 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-05 | Online |  | Gov't | Y
1808 | Harwich | 2645 | 32 | PV | 4-95A-599 | 2011-05-13 | 2011-06-03 | 15 | 13 | 2 | 2011-06-03 | 2011-06-15 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2012-07-14 | 29360 | 0 | 29360 |  |  | 0 | 0 | 0 | 2012-12-19 |  |  | TBD | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2013-02-06 | Online |  | Private | N
2278 | Harwich | 2645 | 13 | PV | 4-95A-597 | 2012-10-04 | 2012-10-31 | 19 | 18 | 1 | 2012-10-31 | 2012-12-11 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online |  | Private | Y
1913 | Harwich | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2011-09-20 | 7 | 6 | 1 | 2011-09-20 | 2011-10-18 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | 137 | 0 | 137 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1914 | Harwich | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2012-02-21 | 117 | 116 | 1 | 2012-02-21 | 2012-04-02 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2257 | Harwich | 2645 | 4000 | PV | 4-89A-89A | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2054472 | Harwichport | 02646 | 15.2 | PV | 4-95A-95A | 2015-02-10 | 2015-02-11 | 1 | 0 | 1 | 2015-02-13 | 2015-02-19 | 4 | 47 | -43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2063694 | Harwichport | 02646 | 40 | PV | 4-85-592 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-05-16 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2016-06-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2129905 | Marston Mills | 02648 | 4400 | PV | 4-88-478 | 2016-02-18 | 2016-02-19 | 1 | 73 | -72 | 2016-02-22 | 2016-03-21 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-15 |  | -30341 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-10-03 | 2016-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2016-05-09 | Private
2186 | Marston Mills | 2648 | 61 | PV | 4-88-88 | 2012-07-30 | 2012-10-16 | 56 |  | 56 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-01-15 | Gov't | Y
2042191 | Mashpee | 02649 | 11.4 | PV | 4-77A-454 | 2014-12-16 | 2014-12-17 | 1 | 0 | 1 | 2014-12-19 | 2015-03-30 | 71 | 36 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-16 | 2015-05-27 | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2095832 | Mashpee | 02649 | 264 | PV | 4-88-455 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-28 | 2015-10-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2015-12-02 | 2016-01-29 | TBD | EXP | 30 | 2015-12-30 | 2015-12-30 | 0 |  | 0 | [5 empty] | Private
2089388 | Mashpee | 02649 | 90 | PV | 4-88-455 | 2015-08-24 | 2015-08-26 | 2 | 0 | 2 | 2015-08-28 | 2015-10-26 | 41 | 11 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2096431 | Mashpee | 02649 | 371 | PV | 4-77A-454 | 2015-09-25 | 2015-09-28 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
1613 | Mashpee | 2649 | 192 | PV | 4-88-453 | 2010-04-28 | 2010-05-03 | 3 | 3 | 0 | 2010-05-03 | 2010-06-30 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-07-16 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-08 |  | 2011-03-08 | Online |  | Gov't | N
1798 | Mashpee | 2649 | 270 | PV | 4-77A-454 | 2011-04-27 | 2011-05-13 | 12 | 10 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-05-23 | Online |  | Private | Y
2325 | Mashpee | 2649 | 18 | PV | 4-71-455 | 2013-01-02 | 2013-01-09 | 5 | 3 | 2 | 2013-01-10 | 2013-04-29 | 77 | 0 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-02 |  | 2013-05-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online |  | Private | Y
2049 | Mashpee | 2649 | 1500 | PV | 4-88-455 | 2012-02-06 | 2012-02-15 | 7 | 3 | 4 | 2012-02-16 | 2012-03-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-06-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
2382 | Mashpee | 2649 | 5000 | PV | 4-88-453 | 2013-05-02 | 2013-05-31 | 21 | 19 | 2 | 2013-06-01 | 2013-07-10 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1597 | Mashpee | 2649 | 141 | PV | 4-88-453 | 2010-04-02 | 2010-04-09 | 5 | 5 | 0 | 2010-04-09 | 2010-04-20 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-30 |  | 2010-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2010-07-21 |  | 2010-07-21 | Online |  | Private | Y
2102528 | Chatham | 02650 | 88 | PV | 4-95A-608 | 2015-10-23 | 2015-10-24 | 1 | 0 | 1 | 2015-10-27 | 2016-04-19 | 125 | 112 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2090556 | Chatham | 02650 | 296 | PV | 4-95A-608 | 2015-08-28 | 2015-09-01 | 2 | 0 | 2 | 2015-09-02 |  | -30179 | 241 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-07 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-09-03 | Gov't
2045149 | Truro | 02652 | 16 | PV | 4-96-674 | 2014-12-31 | 2015-01-02 | 2 | 0 | 2 | 2015-01-02 | 2015-01-09 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-12 | 2015-01-12 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-11 | Online |  | Private
2108546 | Truro | 02652 | 30 | PV | 4-96-674 | 2015-11-25 | 2015-11-26 | 1 | 0 | 1 | 2015-12-03 | 2015-12-07 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 | 2017-11-28 | 2016-07-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-10 | Online |  | Private
2397176 | Truro | 02652 | 35 | PV | TBD | 2020-05-07 |  | 2 | 0 | 2 | 2020-06-25 | 2020-06-26 | 16 | 15 | 1 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-07-15 |  | 2020-12-14 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2006 | North Truro | 2652 | 39 | PV | 4-96-674 | 2011-12-21 | 2011-12-22 | 1 | 0 | 1 | 2012-04-09 | 2012-05-18 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-20 | Online |  | Private | Y
2063168 | Orleans | 02653 | 100 | PV | 4-89B-618 | 2015-04-13 | 2015-04-14 | 1 | 0 | 1 | 2015-04-16 | 2015-04-22 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online |  | Private
2152923 | Orleans | 02653 | 300 | PV | 4-83-952 | 2016-06-13 | 2016-06-15 | 2 | 0 | 2 | 2016-06-20 | 2016-06-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-27 |  | 2017-01-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-18 | Online |  | Private
2251495 | Orleans | 02653 | 64 | PV | 4-94A-633 | 2017-10-15 | 2017-11-17 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
2384945 | Orleans | 02653 | 60 | PV | TBD | 2020-02-06 | 2020-02-11 | 3 | 0 | 3 | 2020-02-11 | 2020-02-12 | 1 | 0 | 1 | [20 empty] | 2020-03-02 | 2020-03-02 | 2020-09-10 | TBD | EXP | 30 | [7 empty] | 2020-10-06 | Online |  | Private
2331027 | Orleans | 02653 | 133.3 | PV | TBD | 2019-03-22 |  | 16 | 0 | 16 | 2019-04-17 | 2019-05-04 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-04-15 | 2019-11-21 | 2019-10-28 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
1402 | Orleans | 2653 | 85 | PV | 4-94A-632 | 2009-08-17 | 2009-08-24 | 5 | 3 | 2 | 2009-08-25 | 2009-09-16 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-08-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-12-17 | Online |  | Private | Y
1742 | Orleans | 2653 | 16 | PV | 4-94A-633 | 2011-01-05 | 2011-01-13 | 6 | 4 | 2 | 2011-01-13 | 2011-02-28 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-02-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-11 |  | 2011-05-11 | Online |  | Private | Y
2019 | Orleans | 2653 | 11 | PV | 4-95B-600 | 2012-01-13 | 2012-01-18 | 3 | 2 | 1 | 2012-01-24 | 2012-03-29 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  | 2012-07-13 | Online |  | Private | Y
2217 | Orleans | 2653 | 500 | PV | 4-95B-95B | 2012-08-10 | 2012-09-25 | 32 | 30 | 2 | 2012-09-25 | 2012-10-25 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2332 | South Sandwich | 2653 | 2250 | PV | 2-87A-475 | 2013-01-21 | 2013-01-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-05-09 | Gov't | Y
2022522 | Wianno | 02655 | 32.8 | PV | 4-80A-892 | 2014-09-04 | 2014-09-04 | 0 | 0 | 0 | 2015-02-13 | 2015-04-01 | 33 | 107 | -74 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-04-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-06 |  | Withdrawn |  | Private
2074867 | Wianno | 02655 | 44 | PV | 4-80A-892 | 2015-06-19 | 2015-06-25 | 4 | 0 | 4 | 2015-06-24 |  | -30129 | 290 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-01-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-06-26 | Private
1964 | Barnstable | 2655 | 2000 | PV | 4-80A-80A | 2011-11-10 | 2011-11-18 | 6 | 4 | 2 | 2011-11-22 | 2012-01-31 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | 142 | 0 | 142 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Gov't | Y
1965 | Barnstable | 02655____ | 1681 | PV | 4-88-88 | 2011-11-14 | 2011-11-21 | 5 | 4 | 1 | 2011-11-23 | 2012-02-29 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-11-21 |  | 2014-09-02 | Online |  | Gov't | N
2062144 | Provincetown | 02657 | 27 | PV | 4-96-675 | 2015-04-06 | 2015-04-13 | 5 | 0 | 5 | 2015-04-16 | 2015-04-23 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 |  | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-08 | Online |  | Private
2104946 | Provincetown | 02657 | 124 | PV | 4-96-674 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-12-07 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 | 2015-12-07 | 2016-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-21 | Online |  | Private
2105431 | Provincetown | 02657 | 100 | PV | 4-96-676 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2016-02-18 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-14 |  | 2016-06-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2104938 | Provincetown | 02657 | 168 | PV | 4-96-674 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2016-04-18 | 115 | 46 | 69 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1978458 | Provincetown | 02657 | 20 | PV | 4-96-676 | 2013-12-23 | 2013-12-24 | 1 | 0 | 1 | 2013-12-31 | 2016-06-08 | 636 | 604 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-31 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2066548 | Provincetown | 02657 | 30 | PV | 4-96-676 | 2015-05-05 | 2015-05-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2358697 | Provincetown | 02657 | 0 |  | TBD | 2019-09-10 |  | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-20 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2025 | Provincetown | 2657 | 34 | PV | 4-96-675 | 2012-01-18 | 2012-01-23 | 3 | 0 | 3 | 2012-01-30 | 2012-02-22 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-09-06 | Online |  | Private | Y
2201 | Provincetown | 2657 | 50 | PV | 4-96-675 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2183 | Provincetown | 2657 | 135 | PV | 4-96-675 | 2012-07-30 |  | -29372 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2007346 | Chatham | 02659 | 50 | PV | 4-95A-95A | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-06-17 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-18 | 2014-10-01 | 2015-01-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online |  | Private
2009828 | Chatham | 02659 | 60 | PV | 4-95A-95A | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-24 |  | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-31 | 2015-04-08 | Online |  | Private
2004834 | Chatham | 02659 | 44 | PV | 4-95A-95A | 2014-03-20 | 2014-05-13 | 38 | 0 | 38 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-10 | 2014-11-19 | 2015-06-30 | TBD | EXP | 30 | 2015-07-17 | 2015-07-17 | 0 |  | 0 |  |  | 2015-07-28 | Online |  | Private
2055020 | Dennis | 02660 | 56 | PV | 4-92B-92B | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online |  | Private
2055023 | Dennis | 02660 | 70 | PV | 4-92B-92B | 2015-02-18 | 2015-02-19 | 1 | 0 | 1 | 2015-02-23 | 2015-02-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-09-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online |  | Gov't
2022973 | Dennis | 02660 | 75 | PV | 4-92B-92B | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-29 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-29 | 2014-10-06 | 2015-04-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online |  | Private
2094068 | Dennis | 02660 | 300 | PV | 4-92B-92B | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 | 2016-06-06 | 2016-11-18 | No | EXP | 30 | 2016-06-06 |  | -30377 |  | 0 |  | 2016-06-06 | 2016-01-26 | Online |  | Private
2055761 | Dennis | 02660 | 15.2 | PV | 4-92B-572 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-15 |  | In Queue |  | Private | N
1569 | Dennis | 2660 | 150 | PV | 4-92B-92B | 2010-02-01 | 2010-02-04 | 3 | 1 | 2 | 2010-02-04 | 2010-03-03 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-15 |  | 2010-07-15 | Online |  | Gov't | Y
1650 | Dennis | 2660 | 82 | PV | 4-92B-92B | 2010-07-15 | 2010-08-05 | 15 | 14 | 1 | 2010-08-05 | 2010-10-14 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-12-06 | Online |  | Private | Y
1649 | Dennis | 2660 | 30 | PV | 4-92B-92B | 2010-07-14 | 2010-07-29 | 11 | 11 | 0 | 2010-07-30 | 2010-10-12 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2011-01-21 | Online |  | Private | Y
1712 | Dennis | 2660 | 1250 | PV | 4-92B-92B | 2010-11-08 | 2010-11-19 | 9 | 8 | 1 | 2010-11-23 | 2011-01-14 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-20 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-25 |  | 2011-05-25 | Online |  | Gov't | Y
2066 | Dennis | 2660 | 1250 | PV | 4-92B-92B | 2012-03-02 | 2012-03-23 | 15 | 14 | 1 | 2012-03-23 | 2012-05-25 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-25 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-22 | Online |  | Private | Y
2116 | Dennis | 2660 | 1250 | PV | 4-92B-92B | 2012-04-25 | 2012-05-01 | 4 | 3 | 1 | 2012-05-01 | 2012-06-05 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  | 2012-07-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-01-07 | Private | Y
2115 | Dennis | 2660 | 2500 | PV | 4-92B-92B | 2012-04-21 | 2012-04-30 | 6 | 3 | 3 | 2012-04-30 | 2012-06-11 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 |  | -29434 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1662 | South Dennis | 2660 | 100 | Wind | 4-92B-92B | 2010-08-06 | 2010-08-19 | 9 | 5 | 4 | 2010-08-19 | 2010-09-21 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-01 | Online |  | Gov't | N
2167 | South Dennis | 2660 | 500 | PV | 4-89A-553 | 2012-07-18 | 2012-07-27 | 7 | 5 | 2 | 2012-07-27 | 2012-12-18 | 102 | 8 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 | 2013-09-11 | 138 | 0 | 138 |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-11-19 | Online |  | Gov't | Y
2245 | Harwich | 2661 | 20 | PV | 320-H5XY | 2012-09-05 | 2012-12-05 | 65 | 65 | 0 | 2012-12-05 | 2013-02-01 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-05 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-02-21 | 2013-02-21 | 2013-02-21 | Online |  | Private | Y
1176 | Orleans | 2662 | 10 | Wind | 4-95B-600 | 2009-02-17 | 2010-05-12 | 321 | 320 | 1 | 2010-05-12 | 2010-06-22 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2009-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2108544 | Welfleet | 02663 | 50 | PV | 4-94B-653 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-11-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-03 | 2016-06-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online |  | Gov't
2024 | South Wellfleet | 2663 | 60 | PV | 4-94B-653 | 2012-01-19 | 2012-02-06 | 12 | 12 | 0 | 2012-02-06 | 2012-03-19 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-05-25 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online |  | Private | Y
2350641 | Bass River | 02664 | 180 | PV | TBD | 2019-07-18 |  | 1 | 0 | 1 | 2019-07-23 | 2019-08-17 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-09-05 |  | 2020-02-27 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2036990 | Yarmouth | 02664 | 0 | PV | TBD | 2014-11-19 | 2014-11-19 | 1 | 0 | 1 | 2014-12-12 | 2014-12-16 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-27 | 2015-06-29 | No | EXP | 30 | 2015-02-23 | 2015-02-23 |  |  | 0 |  | 2015-03-06 | 2015-03-06 | Online |  | Gov't
2038201 | Yarmouth | 02664 | 40 | PV | 4-92A-562 | 2014-12-02 | 2014-12-23 | 15 | 0 | 15 | 2014-12-23 | 2015-02-26 | 47 | 35 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-07-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-19 | Online |  | Private
2032033 | Yarmouth | 02664 | 42 | PV | 4-92A-562 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-11-14 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 | 2015-02-18 | 2015-06-15 | TBD | EXP | 30 | 2015-05-21 | 2015-05-21 | 0 |  | 0 |  | 2015-07-08 | 2015-07-13 | Online |  | Private
2350705 | Yarmouth | 02664 | 187.5 | PV | TBD | 2019-07-19 | 2019-07-19 | 1 | 0 | 1 | 2019-07-23 | 2019-09-06 | 33 | 22 | 11 | [20 empty] | 2019-09-20 | 2019-10-10 | 2020-02-28 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2038 | South Yarmouth | 2664 | 100 | PV | 4-90-90 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online |  | Private | N
2175 | South Yarmouth | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-08-06 | 8 | 8 | 0 | 2012-08-06 | 2012-09-11 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-08-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-10-24 | 2013-10-24 | 2015-03-05 | Online |  | Gov't | Y
2173 | South Yarmouth | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-10-31 | 70 | 70 | 0 | 2012-10-31 | 2013-03-08 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-14 | Online |  | Gov't | Y
1627 | Yarmouth | 2664 | 183 | PV | 4-64-558 | 2010-05-24 | 2010-05-26 | 2 | 2 | 0 | 2010-05-27 | 2010-06-30 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-05-04 | Online |  | Private | N
1740 | Yarmouth | 2664 | 266 | PV | 4-92B-563 | 2010-12-29 | 2011-01-13 | 11 | 9 | 2 | 2011-01-13 | 2011-03-25 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-07-18 |  |  |  |  | Private | Y
2020127 | Truro | 02666 | 1000 | PV | 4-96-96 | 2014-08-20 | 2014-08-25 | 3 | 0 | 3 | 2014-08-25 |  | -29912 |  | 0 |  |  | 0 | 0 | 0 | 2014-10-21 | 2015-01-09 | 58 | 120 | -62 | 2015-07-02 | 2015-07-10 | 6 | 3 | 3 | 2016-03-10 | 2016-03-31 | 15 | 0 | 15 | 2015-07-08 | 2016-04-25 | 2016-12-02 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1657 | Welfleet | 2667 | 28 | PV | 4-96-677 | 2010-07-29 | 2010-08-17 | 13 | 13 | 0 | 2010-08-17 | 2010-10-14 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-18 |  | 2011-02-18 | Online |  | Private | Y
1527 | Welfleet | 2667 | 1650 | Wind | 4-94B-653 | 2009-11-30 | 2009-12-17 | 13 | 6 | 7 | 2009-12-18 | 2010-01-25 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-05 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1639 | Welfleet | 2667 | 52 | PV | 4-94B-653 | 2010-06-22 | 2010-07-16 | 18 | 19 | -1 | 2010-07-16 | 2010-08-30 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2322818 | Barnstable | 02668 | 17.92 | PV | 4-87B-473 | 2019-01-30 | 2019-01-30 | 1 | 0 | 1 | 2019-02-01 | 2019-02-26 | 16 | 0 | 16 | [17 empty] | 0 | 0 | 0 | 2019-02-26 | 2019-03-01 | 2019-09-05 | TBD | EXP | 30 | [7 empty] | 2019-07-16 | Online |  | Private
2055 | West Barnstable | 2668 | 581 | PV | 4-82-516 | 2012-02-17 | 2012-02-23 | 4 | 4 | 0 | 2012-02-23 | 2012-05-08 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-11 | 2012-09-19 | 72 | 0 | 72 |  |  | 0 | 0 | 0 | 2012-10-04 |  | 2012-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-23 | 2013-12-23 | 2012-10-11 | Online |  | Gov't | Y
2308 | West Barnstable | 2668 | 40 | PV | 4-87B-473 | 2012-11-28 | 2012-12-11 | 9 | 9 | 0 | 2012-12-11 | 2013-01-30 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online |  | Private | Y
1272 | West Barnstable | 2668 | 600 | Wind | 4-82-516 | 2009-05-07 | 2009-06-08 | 22 | 22 | 0 | 2009-06-08 | 2009-07-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-14 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-15 |  | 2011-02-16 | Online |  | Gov't | N
1784 | West Dennis | 2670 | 30 | PV | 4-92B-571 | 2011-03-28 | 2011-04-06 | 7 | 5 | 2 | 2011-04-06 | 2011-06-03 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-10 |  | 2011-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-16 | Online |  | Private | N
1987679 | Harwich | 02671 | 23 | PV | 4-92B-572 | 2014-02-10 | 2014-02-11 | 1 | 0 | 1 | 2014-02-11 | 2014-02-28 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-13 | 2014-04-15 | 2014-09-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-29 | Online |  | Private | Y
2094563 | Harwich | 02671 | 72 | PV | 4-85-592 | 2015-09-16 | 2015-09-17 | 1 | 0 | 1 | 2015-09-22 | 2015-10-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-15 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
1869 | Wareham | 2671 | 30 | PV | 3-86-966 | 2011-07-28 | 2011-07-28 | 0 | 0 | 0 | 2011-07-28 | 2011-09-07 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online |  | Private | Y
2259 | West Harwich | 2671 | 11 | PV | 4-85-925 | 2012-09-26 | 2012-10-12 | 12 | 12 | 0 | 2012-10-16 | 2013-01-30 | 76 | 36 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 94 | 0 | 94 | 2013-09-26 |  | -29675 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-19 | Online |  | Gov't | Y
2258 | West Harwich | 2671 | 11 | PV | 4-85-925 | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2331 | West Yarmouth | 2673 | 1000 | PV | 2-92A-92A | 2013-01-23 | 2013-01-28 | 3 | 0 | 3 | 2013-04-22 | 2013-05-28 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2330 | West Yarmouth | 2673 | 1000 | PV | 2-92A-92A | 2013-01-21 |  | -29497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2333 | West Yarmouth | 2673 | 500 | PV | 2-92A-92A | 2013-01-21 | 2013-02-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-06-03 | Gov't | Y
2168 | West Yarmouth | 2673 | 750 | PV | 4-92A-92A | 2012-07-18 | 2012-07-27 | 7 | 5 | 2 | 2012-07-27 | 2013-01-10 | 119 | 0 | 119 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-27 | Online |  | Gov't | Y
2172 | West Yarmouth | 2673 | 750 | PV | 4-92A-92A | 2012-07-25 | 2012-11-30 | 92 | 92 | 0 | 2012-11-30 | 2013-02-07 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 2013-06-19 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2239 | West Yarmouth | 2673 | 150 | PV | 4-92A-536 | 2012-08-30 | 2012-10-03 | 24 | 24 | 0 | 2012-10-03 | 2013-03-18 | 118 | 0 | 118 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2169 | West Yarmouth | 2673 | 200 | PV | 4-92A-92A | 2012-07-20 | 2012-07-26 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-09-14 | Private | Y
2044156 | Yarmouthport | 02675 | 57 | PV | 4-92A-92A | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 | 2014-12-29 | 2015-01-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-30 | 2015-01-29 | 2015-06-19 | No | EXP | 30 | 2015-05-20 | 2015-05-20 | 0 |  | 0 |  |  | 2015-06-17 | Online |  | Private
1962 | Yarmouth | 2675 | 75 | PV | 4-92A-92A | 2011-11-09 | 2011-11-15 | 4 | 3 | 1 | 2011-11-15 | 2012-02-14 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-27 |  | 2012-03-27 | Online |  | Private | Y
2051972 | Assonet | 02702 | 24.1 | PV | 2-605-605 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-24 | Online |  | Private
2148246 | Assonet | 02702 | 432 | PV | 2-605-605 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-24 |  | -30368 | 58 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-14 |  | 2016-12-30 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-10-23 | Online | 2016-05-30 | Private
2079393 | Assonet | 02702 | 20 | PV | 2-605-605 | 2015-07-09 | 2015-07-16 | 5 | 0 | 5 | 2015-07-20 | 2015-08-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2016-02-12 | 2016-06-30 | No | EXP | 30 | 2016-08-10 |  | -30424 |  | 0 |  |  |  | In Queue |  | Private
2106271 | Assonet | 02702 | 1992 | PV | 2-605-605 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-02 | 10 | 0 | 10 |  |  | 0 | 4 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2086459 | Assonet | 02702 | 1440 | PV | 2-605-605 | 2013-11-25 | 2013-12-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-20 |  | Withdrawn
2102530 | Assonet | 02702 | 1992 | PV | 2-605-605 | 2015-10-23 | 2015-10-24 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2103346 | Assonet | 02702 | 984 | PV | 2-605-605 | 2015-10-29 | 2015-11-04 | 4 | 0 | 4 | 2015-11-03 |  | -30223 | 199 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-04 | Private
2330491 | Assonet | 02702 | 4890 | PV & Battery | TBD | 2019-03-19 | 2019-03-20 | 1 | 0 | 1 | 2019-03-26 |  | 444 | 439 | 5 | [17 empty] | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 | [8 empty] | In Queue | 2019-04-02 | Private
2339086 | Assonet | 02702 | 4498 | PV | TBD | 2019-05-10 | 2019-05-10 | 1 | 0 | 1 | [10 empty] | 2019-05-14 |  | 409 | 409 | 0 | [12 empty] | 2019-12-18 | TBD |  | 60 | [8 empty] | In Queue | 2019-05-14 | Private
1760 | Assonet | 2702 | 11 | PV | 2-605-605 | 2011-02-03 | 2011-03-16 | 29 | 29 | 0 | 2011-03-16 | 2011-03-25 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-30 |  | 2011-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-16 | Online |  | Private | N
2107 | Assonet | 2702 | 13 | PV | 2-605-605 | 2012-04-19 | 2012-04-20 | 1 | 0 | 1 | 2012-04-24 | 2012-06-04 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-01 |  | 2012-09-21 | Online |  | Private | Y
2353 | Assonet | 2702 | 142 | PV | 2-605-605 | 2013-02-26 | 2013-03-28 | 22 | 20 | 2 | 2013-04-01 | 2013-04-24 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-31 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online |  | Private | Y
2447 | Assonet | 2702 | 10 | PV | 2-605-605 | 2013-10-02 | 2013-10-07 | 3 | 0 | 3 | 2013-10-10 |  | -29685 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-19 | Online |  | Private | Y
2092 | Assonet | 2702 | 12 | PV | 2-605-605 | 2012-04-04 | 2012-04-05 | 1 | 0 | 1 | 2012-04-09 | 2012-05-22 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2251 | Assonet | 2702 | 500 | PV | 2-605-605 | 2012-09-14 | 2012-09-24 | 6 | 6 | 0 | 2012-09-24 | 2012-12-12 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2191 | Assonet | 2702 | 1500 | PV | 2-606-605 | 2012-07-30 | 2012-12-17 | 100 |  | 100 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Gov't | Y
2372 | Freetown | 2702 | 4999 | PV | 2-102-102 | 2013-04-12 | 2013-06-14 | 45 | 43 | 2 | 2013-06-17 | 2013-07-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-11-27 | 55 | 11 | 44 |  |  | 0 | 0 | 0 | 2014-03-13 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2031 | Dartmouth | 2714 | 1000 | PV | 2-541-541 | 2012-01-19 | 2012-02-02 | 10 | 8 | 2 | 2012-02-02 | 2012-03-02 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online |  | Private | Y
2027 | Dartmouth | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 24 | 21 | 3 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2028 | Dartmouth | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 24 | 21 | 3 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2029 | Dartmouth | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 24 | 21 | 3 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2030 | Dartmouth | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 24 | 21 | 3 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2052538 | East Freetown | 02717 | 17.4 | PV | 2-102-102 | 2014-11-05 | 2014-11-12 | 5 |  | 5 | 2015-02-03 |  | -30028 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-02-09 | 2015-02-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2016-02-12 | Online |  | Private | N
2056337 | East Freetown | 02717 | 52 | PV | 2-102-602 | 2015-02-27 | 2015-02-27 | 0 | 0 | 0 | 2015-03-04 | 2015-03-30 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-13 |  | 2015-10-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online |  | Private
2113074 | East Freetown | 02717 | 2000 | PV | 2-102-604 | 2015-12-09 | 2015-12-11 | 2 |  | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2018-12-12 | 2018-12-13 | 2018-12-13 | Online |  | Private
2041172 | East Freetown | 02717 | 1137 | Natural Gas | 2-606-606 | 2014-12-08 | 2015-01-02 | 19 | 0 | 19 | 2015-01-02 | 2015-01-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-26 |  | 2015-07-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2108032 | East Freetown | 02717 | 4000 | PV | 2-102-102 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-12-08 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-23 | 2016-06-24 | No | EXP | 30 | 2016-04-08 | 2016-04-08 | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2086294 | East Freetown | 02717 | 1440 | PV | 2-102-604 | 2015-08-06 | 2015-08-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-09-28 | Private
2200961 | East Freetown | 02717 | 0 |  | TBD | 2017-02-09 |  | 174 | 0 | 174 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-09-15 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2238661 | East Freetown | 02717 | 1156 | PV & Battery | TBD | 2017-10-04 | 2017-10-06 | 2 | 0 | 2 | [10 empty] | 2017-10-11 | 2019-05-16 | 400 | 333 | 67 | [5 empty] | 2019-06-25 | 2019-07-10 | 11 | 0 | 11 | 2019-02-25 | 2019-08-01 | 2020-03-01 | No |  | 60 | 2020-01-30 | [7 empty] | In Queue |  | Private | N
2361432 | East Freetown | 02717 | 4000 | PV | TBD | 2019-09-26 | 2019-10-02 | 4 | 0 | 4 | 2019-10-07 |  | 308 | 298 | 10 | [22 empty] | 2020-05-06 | TBD |  | 30 | [8 empty] | In Queue | 2019-10-22 | Private
1883 | East Freetown | 2717 | 1000 | PV | 604 | 2011-08-18 | 2011-08-25 | 5 | 5 | 0 | 2011-08-26 | 2011-10-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2012-03-08 | Online |  | Private | Y
1844 | East Freetown | 2717 | 2000 | PV | 2-102-102 | 2011-07-01 | 2011-07-08 | 5 | 3 | 2 | 2011-07-08 | 2011-08-05 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-15 | Online |  | Gov't | Y
1843 | East Freetown | 2717 | 1723 | PV | 2-102-102 | 2011-07-01 | 2011-07-18 | 11 | 11 | 0 | 2011-07-18 | 2011-07-25 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | 47 | 0 | 47 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Gov't | Y
1896 | East Freetown | 2717 | 1000 | PV | 2-102-604 | 2011-08-25 | 2011-08-29 | 2 | 0 | 2 | 2011-08-29 | 2011-10-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2015-03-20 | Online |  | Private | Y
1895 | East Freetown | 2717 | 2984 | PV | 2-108-108 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 115 | 0 | 115 |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-20 | Online |  | Gov't | Y
1894 | East Freetown | 2717 | 1000 | PV | 604 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 115 | 0 | 115 |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online |  | Private | Y
1614 | Freetown | 2717 | 82 | PV | 2-102-102 | 2010-04-28 | 2010-05-03 | 3 | 3 | 0 | 2010-05-03 | 2010-07-08 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-22 |  | 2011-03-25 | Online |  | Gov't | Y
1855 | Freetown | 2717 | 2000 | PV | 2-102-102 | 2011-07-21 | 2011-09-20 | 43 | 43 | 0 | 2011-09-20 | 2011-10-29 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-31 |  | 2011-08-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-13 | Online |  | Private | Y
1827 | Freetown | 2717 | 1304.16 | PV | 2-102-604 | 2011-06-07 | 2011-06-15 | 6 | 6 | 0 | 2011-06-15 | 2011-08-05 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-11-29 |  | 2013-01-22 | Online |  | Private | N
2109 | Freetown | 2717 | 648.98 | PV | 2-102-604 | 2012-04-21 | 2012-05-01 | 7 | 5 | 2 | 2012-05-01 | 2012-06-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-22 | Online |  | Gov't | Y
1849 | Freetown | 2717 | 4200 | PV | 2-102-102 | 2011-07-13 | 2011-08-02 | 14 | 14 | 0 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | -29223 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1850 | Freetown | 2717 | 2000 | PV | 2-102-102 | 2011-07-07 | 2011-09-09 | 46 | 42 | 4 | 2011-09-09 | 2011-10-24 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1948 | Freetown | 2717 | 1785 | PV | 2-102-604 | 2011-10-07 | 2011-11-21 | 31 | 21 | 10 | 2011-11-21 | 2012-02-28 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2011-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-05-07 | Private | Y
2215 | Freetown | 2717 | 1500 | PV | 2-102-102 | 2012-08-13 | 2012-08-13 | 0 | 0 | 0 | 2012-08-13 | 2012-09-18 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2220 | Freetown | 2717 | 1500 | PV | 2-102-102 | 2012-08-16 | 2012-08-21 | 3 | 3 | 0 | 2012-08-22 | 2012-10-19 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-06-12 | 2013-06-12 |  | Withdrawn |  | Private | Y
2219 | Freetown | 2717 | 1500 | PV | 2-102-102 | 2012-08-14 |  | -29383 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2093189 | Fairhaven | 02719 | 2000 | PV | 2-221-221 | 2015-09-09 | 2015-09-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-05 | Online |  | Private
2247327 | Fairhaven | 02719 | 53.3 | PV | 2-240-240 | 2017-10-24 | 2017-11-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
2408049 | Fairhaven | 02719 | 99 | PV | TBD | 2020-07-23 | 2020-07-27 | 2 | 0 | 2 | 2020-08-04 | 2020-08-19 | 11 | 0 | 11 | [20 empty] | 2020-10-19 |  | 2020-10-31 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2336099 | Fairhaven | 02719 | 5000 | PV | TBD | 2019-04-23 | 2019-04-25 | 2 | 0 | 2 | [10 empty] | 2019-04-25 |  | 421 | 256 | 165 | [10 empty] | 2021-10-21 |  | 2020-06-30 | TBD |  | 60 | [8 empty] | In Queue | 2020-04-18 | Private
1797 | Fairhaven | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-04-25 | 2011-05-31 | 26 | 23 | 3 | 2011-05-31 | 2011-07-11 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-12 |  | 2011-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1807 | Fairhaven | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-05-09 | 2011-05-11 | 2 | 1 | 1 | 2011-05-11 | 2011-06-27 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-28 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-10-12 |  | 2011-10-12 | Online |  | Private | Y
1994 | Fairhaven | 2719 | 60 | PV | 2-220-201 | 2011-12-13 | 2011-12-14 | 1 | 0 | 1 | 2011-12-15 | 2012-01-16 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online |  | Private | N
1663 | Fairhaven | 2719 | 1500 | Wind | 2-220-220 | 2010-08-06 | 2010-08-13 | 5 | 1 | 4 | 2010-08-18 | 2010-09-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-05-01 | Online |  | Gov't | N
1664 | Fairhaven | 2719 | 1500 | Wind | 2-220-220 | 2010-08-17 | 2010-08-25 | 6 | 5 | 1 | 2010-08-26 | 2010-10-27 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2012-05-03 | Online |  | Gov't | Y
1671 | Fairhaven | 2719 | 100 | PV | 2-220-201 | 2010-08-24 | 2010-08-26 | 2 | 2 | 0 | 2010-08-26 | 2010-10-06 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-02 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-05-29 | Online |  | Private | N
1993 | Fairhaven | 2719 | 120 | PV | 2-220-201 | 2011-12-08 | 2011-12-13 | 3 | 0 | 3 | 2011-12-15 | 2012-01-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online |  | Private | Y
1714 | Fairhaven | 2719 | 577.28 | PV | 2-222-222 | 2010-11-12 | 2010-12-02 | 14 | 13 | 1 | 2010-12-03 | 2011-02-03 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-21 | Online |  | Private | N
1585 | Fairhaven | 2719 | 85 | PV | 2-221-221 | 2010-03-01 | 2010-03-08 | 5 | 4 | 1 | 2010-08-02 | 2010-08-30 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | N
1702 | Fairhaven | 2719 | 30 | PV | 2-220-201 | 2010-10-15 | 2010-10-25 | 6 | 4 | 2 | 2010-10-26 | 2010-12-22 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1960 | Fairhaven | 2719 | 1000 | PV | 2-220-220 | 2011-11-04 | 2011-11-08 | 2 | 1 | 1 | 2011-11-08 | 2012-01-30 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2026 | Fairhaven | 2719 | 66 | PV | 2-240-240 | 2012-01-18 | 2012-02-21 | 24 | 21 | 3 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1991 | Fairhaven | 2719 | 82 | PV | 2-220-201 | 2011-12-05 | 2011-12-09 | 4 | 0 | 4 | 2012-11-13 | 2013-04-09 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Private | N
2029145 | Marion | 02738 | 783 | PV | 3-85-85 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-16 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-27 | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-27 | Online |  | Private
2062768 | Marion | 02738 | 882 | PV | 3-85-85 | 2015-04-08 | 2015-04-22 | 10 | 3 | 7 | 2015-04-24 | 2015-05-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-20 | Online |  | Private
2057875 | Marion | 02738 | 482 | PV | 2-304-304 | 2015-03-12 | 2015-03-12 | 0 | 0 | 0 | 2015-03-17 | 2015-04-03 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 |  | 2015-10-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2032055 | Marion | 02738 | 250 | PV | 3-304-304 | 2014-10-27 | 2014-11-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2059 | Marion | 2738 | 18 | PV | 3-85-969 | 2012-02-24 | 2012-03-13 | 12 | 12 | 0 | 2012-03-13 | 2012-04-23 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-31 |  | 2012-06-26 | Online |  | Private | Y
2083555 | Mattapoisett | 02739 | 60 | PV | 2-304-304 | 2015-07-27 | 2015-07-29 | 2 | 0 | 2 | 2015-07-30 | 2015-07-30 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-05 | Online |  | Private
1992844 | Mattapoisett | 02739 | 2000 | PV | 2-301-301 | 2014-03-18 | 2014-10-10 | 148 |  | 148 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-27 | Online | 2015-03-12 | Private
1978822 | Mattapoisett | 02739 | 750 | PV | 2-301-301 | 2014-01-02 | 2014-01-02 | 0 | 106 | 0 | 2014-01-03 | 2015-01-07 | 263 | 139 | 124 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2051498 | Mattapoisett | 02739 | 2500 | PV | 2-304-304 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-04 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-06 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2051477 | Mattapoisett | 02739 | 2250 | PV | 2-304-304 | 2015-01-22 | 2015-01-23 | 1 | 0 | 1 | 2015-02-19 | 2015-03-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-27 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2098384 | Mattapoisett | 02739 | 25 | WIND | 2-301-301 | 2015-10-05 | 2015-10-09 | 4 | 73 | -69 | 2015-10-14 | 2016-06-14 | 174 | 0 | 174 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
1992854 | Mattapoisett | 02739 | 2000 | PV | 2-306-306 | 2014-03-18 | 2014-11-07 | 168 |  | 168 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-05-20 | Private
1992858 | Mattapoisett | 02739 | 1000 | PV | 2-306-306 | 2014-03-25 |  | -29803 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2229139 | Mattapoisett | 02739 | 0 |  | TBD | 2017-08-07 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-03-16 | No | TBD | 30 | [8 empty] | Withdrawn |  | Private | N
2160656 | Mattapoisett | 02739 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1670 | Mattapoisett | 2739 | 164 | PV | 2-304-304 | 2010-08-24 | 2010-08-26 | 2 | 2 | 0 | 2010-08-26 | 2010-10-01 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-21 | Online |  | Private | Y
1743 | Mattapoisett | 2739 | 60 | PV | 2-301-301 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1937 | Mattapoisett | 2739 | 82 | PV | 2-304-304 | 2011-10-12 | 2011-10-12 | 0 | 0 | 0 | 2011-10-12 | 2011-11-29 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-15 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-15 | Online |  | Private | Y
1832 | Mattapoisett | 2739 | 82 | PV | 2-304-304 | 2011-06-20 | 2011-06-30 | 8 | 7 | 1 | 2011-06-30 | 2011-08-01 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2011-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online |  | Gov't | N
2261 | Mattapoisett | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-11-27 | 44 | 44 | 0 | 2012-11-27 | 2013-02-06 | 51 | 11 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-05-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 2014-02-25 |  | 2013-10-15 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-18 | Online |  | Private | Y
2260 | Mattapoisett | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-10-12 | 12 | 12 | 0 | 2012-10-16 | 2013-01-30 | 76 | 36 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 94 | 0 | 94 | 2013-09-26 |  | -29675 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Gov't | N
2407 | Mattapoisett | 2739 | 4500 | PV | 2-302-302 | 2013-06-19 | 2013-07-01 | 8 | 7 | 1 | 2013-07-03 | 2013-08-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-24 |  | 2013-08-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
2463 | Mattapoisett | 2739 | 4000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 93 |  | 93 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | Y
2464 | Mattapoisett | 2739 | 1000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 93 |  | 93 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | Y
2465 | Mattapoisett | 2739 | 1000 | PV | 2-302-302 | 2013-10-30 | 2013-11-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online |  | Private | Y
2034765 | New Bedford | 02740 | 30.9 | PV | 2-89-14 | 2014-11-05 | 2014-11-06 | 1 | 0 | 1 | 2014-11-10 | 2014-12-10 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-12 | 2015-05-12 | Online |  | Private
2136975 | New Bedford | 02740 | 468 | PV | 2-110-110 | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-31 |  | -30330 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-01 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online | 2016-04-20 | Private
2203288 | New Bedford | 02740 | 496 | PV | TBD | 2017-02-27 |  | 1 | 0 | 1 | 2017-03-01 | 2017-04-07 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-29 |  | 2017-10-02 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2286967 | New Bedford | 02740 | 28 | PV | TBD | 2018-07-16 | 2018-07-24 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-25 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2117 | Marion | 2740 | 1000 | PV | 3-85-85 | 2012-04-27 | 2012-05-01 | 2 | 2 | 0 | 2012-05-03 | 2012-06-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1303 | New Bedford | 2740 | 44 | PV | 2-103-103 | 2009-06-18 | 2009-09-10 | 60 | 60 | 0 | 2009-09-10 | 2009-10-02 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-31 |  | 2009-12-31 | Online |  | Gov't | N
1548 | New Bedford | 2740 | 39 | PV | 2-38-38 | 2010-01-08 | 2010-02-01 | 16 | 12 | 4 | 2010-02-01 | 2010-03-03 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-02-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-04-21 | Online |  | Private | Y
1749 | New Bedford | 2740 | 56 | PV | 2-6-10 | 2011-01-07 | 2011-03-01 | 37 | 36 | 1 | 2011-03-01 | 2011-03-02 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-12 |  | 2011-05-12 | Online |  | Private | Y
1831 | New Bedford | 2740 | 200 | PV | 2-220-9 | 2011-06-13 | 2011-07-29 | 34 | 30 | 4 | 2011-07-29 | 2011-08-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-16 | Online |  | Private | Y
1744 | New Bedford | 2740 | 88 | PV | 2-38-38 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1745 | New Bedford | 2740 | 14 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1746 | New Bedford | 2740 | 42 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1747 | New Bedford | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1748 | New Bedford | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online |  | Gov't | Y
1858 | New Bedford | 2740 | 50 | PV | 2-73-16 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
1954 | New Bedford | 2740 | 50 | PV | 2-5-5 | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2012-01-26 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-08-24 |  | 2012-08-24 | Online |  | Private | Y
2369 | New Bedford | 2740 | 500 | PV | 2-59-59 | 2013-03-26 | 2013-04-08 | 9 | 0 | 9 | 2013-04-12 | 2013-04-24 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-02 | Online |  | Private | Y
2241 | New Bedford | 2740 | 190 | PV | 2-81-94 | 2012-08-21 | 2012-09-07 | 13 | 6 | 7 | 2012-09-07 | 2012-09-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-31 |  | 2012-10-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-09-11 | 2013-10-11 | Online |  | Private | Y
2242 | New Bedford | 2740 | 225 | PV | 2-84-84 | 2012-08-22 | 2012-09-07 | 12 | 5 | 7 | 2012-09-07 | 2012-11-16 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-11 | Online |  | Private | Y
2405 | New Bedford | 2740 | 100 | PV | 2-38-38 | 2013-06-18 | 2013-06-24 | 4 | 3 | 1 | 2013-06-26 | 2013-07-10 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-15 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-04 | Online |  | Private | Y
2421 | New Bedford | 2740 | 75 | Natural Gas | 2-67-14 | 2013-07-11 | 2013-07-23 | 8 | 6 | 2 | 2013-07-24 | 2013-08-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-11-18 | Online |  | Private | Y
1592 | New Bedford | 2740 | 1600 | PV | 4-107-107 | 2010-03-22 | 2010-03-31 | 7 | 7 | 0 | 2010-03-31 | 2010-07-02 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-04-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2065 | New Bedford | 2740 | 60 | PV | 2-5-5 | 2010-11-02 | 2010-11-10 | 6 | 5 | 1 | 2010-11-18 | 2010-12-16 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1939 | New Bedford | 2740 | 1500 | PV | 2-70-502 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1863 | New Bedford | 2740 | 108 | PV | 2-71-71 | 2011-07-26 | 2011-07-28 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2011-08-31 | Private | Y
1680 | Watertown | 2742 | 50 | PV | 467-H4 | 2010-09-21 | 2010-09-28 | 5 | 4 | 1 | 2010-10-04 | 2010-11-10 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-19 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-11-30 | Online |  | Private | Y
2035823 | Acushnet | 02743 | 43.6 | PV | 2-106-160 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | 2014-12-24 | 2015-02-24 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-04-21 | 2015-04-24 | Online |  | Private
1984711 | Acushnet | 02743 | 40 | PV | 2-241-241 | 2014-01-27 | 2014-05-06 | 71 | 0 | 71 | 2014-06-25 | 2014-08-22 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2014-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-26 | Online |  | Private
2051046 | Acushnet | 02743 | 1904 | PV | 2-241-238 | 2015-01-20 | 2015-01-21 | 1 | 0 | 1 | 2015-01-27 | 2015-09-03 | 157 | 152 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-04-29 | Online |  | Private
2051285 | Acushnet | 02743 | 4000 | PV | 2-241-238 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-27 | 2015-02-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-05-19 |  | -30103 | 0 | 0 |  |  | 0 |  | 0 | 2015-10-02 |  |  |  | STD |  |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2058670 | Acushnet | 02743 | 1000 | PV | 2-241-241 | 2015-03-17 | 2015-03-17 | 0 | 0 | 0 | 2015-03-24 | 2015-04-10 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-17 | 2019-08-21 | 2015-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2057145 | Acushnet | 02743 | 18 | PV | 2-241-237 | 2015-03-04 | 2015-03-09 | 3 | 49 | -46 | 2015-06-03 | 2015-07-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 |  | 2015-10-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2077489 | Acushnet | 02743 | 1080 | PV | 2-241-241 | 2015-06-25 | 2015-06-30 | 3 | 0 | 3 | 2015-07-02 | 2015-07-30 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-02-02 | No | EXP | 30 |  |  | 0 |  | 0 | [5 empty] | Private
2088074 | Acushnet | 02743 | 4000 | PV | 2-241-238 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-17 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2092123 | Acushnet | 02743 | 2000 | PV | 2-241-238 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2015-11-09 | 41 | 29 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-09-29 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2086776 | Acushnet | 02743 | 1000 | PV | 2-241-241 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2016-01-13 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2019-08-21 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2116976 | Acushnet | 02743 | 16 | PV | 2-241-237 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2053880 | Acushnet | 02743 | 1995 | PV | 2-241-238 | 2015-02-04 | 2017-03-15 | 547 |  | 547 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private
2086742 | Acushnet | 02743 | 1990 | PV | 2-241-241 | 2015-08-07 | 2015-08-17 | 6 | 0 | 6 | 2015-09-28 |  | -30197 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-03-17 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | 2016-04-27 | Private
2092115 | Acushnet | 02743 | 2000 | PV | 2-241-238 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-09-28 | Private
2129053 | Acushnet | 02743 | 168 | PV | 2-231-231 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 |  | -30300 | 74 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-09-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2270749 | Acushnet | 02743 | 5000 | PV | TBD | 2018-04-09 | 2018-04-11 | 2 | 0 | 2 | 2018-04-11 |  | 681 | 681 | 0 | [17 empty] | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 | [8 empty] | In Queue | 2018-04-12 | Private
2285552 | Acushnet | 02743 | 2000 | PV | TBD | 2018-07-05 | 2018-07-06 | 1 | 0 | 1 | 2018-07-06 |  | 619 | 619 | 0 | [17 empty] | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 | [8 empty] | In Queue | 2018-07-11 | Private
2301808 | Acushnet | 02743 | 5000 | PV | TBD | 2018-10-16 | 2018-10-17 | 1 | 0 | 1 | [10 empty] | 2018-10-18 | 2019-12-18 | 180 | 41 | 139 | [7 empty] | 0 | 0 | 0 | 2019-06-13 |  | 2020-06-30 | TBD |  | 60 | [7 empty] | 2021-09-23 | Online |  | Private
2364982 | Acushnet | 02743 | 500 | PV & Battery | TBD | 2019-10-21 | 2019-10-22 | 1 | 0 | 1 | [10 empty] | 2019-10-25 |  | 295 | 86 | 209 | [10 empty] | 2020-04-20 |  | 2020-12-31 | TBD |  | 60 | [7 empty] | 2022-02-09 | Online |  | Private
2203266 | Acushnet | 02743 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-10-02 | No | TBD | 30 | [8 empty] | Withdrawn |  | Private | N
1682 | Acushnet | 2743 | 20 | PV | 2-241-237 | 2010-09-21 | 2010-09-28 | 5 | 3 | 2 | 2010-10-04 | 2010-11-22 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-08 | Online |  | Private | Y
1809 | Acushnet | 2743 | 1142.68 | PV | 2-241-238 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-07-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2013-02-06 | Online |  | Gov't | Y
2403 | Acushnet | 2743 | 500 | PV | 2-240-240 | 2013-06-17 | 2013-06-20 | 3 | 2 | 1 | 2013-06-24 | 2013-07-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2017-01-06 | Online |  | Private | Y
1942 | Acushnet | 2743 | 2000 | PV | 2-242-242 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1940 | Acushnet | 2743 | 2000 | PV | 2-241-241 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1941 | Acushnet | 2743 | 2000 | PV | 2-240-240 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2164 | Acushnet | 2743 | 2000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2165 | Acushnet | 2743 | 1000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2166 | Acushnet | 2743 | 2000 | PV | 2-241-327 | 2012-07-18 | 2012-07-25 | 5 | 3 | 2 | 2012-07-27 | 2012-11-18 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2399 | Acushnet | 2743 | 750 | PV | 2-231-231 | 2013-06-10 | 2013-06-20 | 8 | 7 | 1 | 2013-06-26 | 2013-07-23 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-25 |  | 2013-07-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2090242 | New Bedford | 02744 | 843 | PV | 2-7-95 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-09-02 | 2015-10-27 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-04-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-04 | Online |  | Private
2130836 | New Bedford | 02744 | 144 | PV | 2-69-69 | 2016-02-24 | 2016-02-29 | 3 | 0 | 3 | 2016-03-15 | 2016-03-23 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2339509 | New Bedford | 02744 | 113 | PV | TBD | 2019-05-13 | 2019-05-17 | 4 | 0 | 4 | 2019-05-27 | 2020-06-16 | 262 | 0 | 262 | [20 empty] | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
1632 | New Bedford | 2744 | 177 | PV | 2-6-17 | 2010-06-04 | 2010-07-26 | 36 | 36 | 0 | 2010-08-26 | 2010-10-15 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-03-01 | Online |  | Gov't | Y
1860 | New Bedford | 2744 | 110 | PV | 2-7-34 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-31 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-31 |  | 2011-10-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | Y
1874 | New Bedford | 2744 | 310 | PV | 12457 | 2011-08-04 | 2011-09-28 | 39 | 39 | 0 | 2011-09-28 | 2011-11-02 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 | 2012-10-15 | 226 | 0 | 226 |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-12-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-09-27 | 2012-10-02 |  |  |  | Private | Y
2003173 | New Bedford | 02745 | 810 | Natural Gas | 2-107-107 | 2014-03-10 | 2014-05-12 | 45 | 0 | 45 | 2014-06-06 | 2014-06-17 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-19 | 2014-08-11 | 2015-01-05 | TBD | EXP | 30 | 2014-10-01 | 2014-10-01 | 0 |  | 0 |  |  | 2014-10-10 | Online |  | Private
2005461 | New Bedford | 02745 | 2000 | Natural Gas | 2-101-101 | 2014-05-14 | 2014-06-03 | 14 | 0 | 14 | 2014-06-06 | 2014-06-10 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 | 2014-09-12 | 2015-01-12 | TBD | EXP | 30 | 2014-10-09 | 2014-10-09 | 0 |  | 0 |  | 2014-11-05 | 2014-11-18 | Online |  | Private
2017870 | New Bedford | 02745 | 2000 | Natural Gas | 2-101-101 | 2014-08-07 | 2014-08-15 | 6 | 0 | 6 | 2014-09-24 | 2014-09-24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-30 | 2014-10-06 | 2015-03-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online |  | Private | N
2037115 | New Bedford | 02745 | 300 | PV | 2-104-104 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2015-02-23 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-23 | 2015-06-02 | 2015-06-29 | No | EXP | 30 | 2015-07-06 | 2015-07-06 | 0 |  | 0 |  | 2015-07-14 | 2015-07-17 | Online |  | Private
2049774 | New Bedford | 02745 | 200 | PV | 2-104-104 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-01 | Online |  | Private
2164917 | New Bedford | 02745 | 272 | PV | 2-103-103 | 2016-07-22 | 2016-07-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online |  | Private
2062901 | New Bedford | 02745 | 40 | PV | 2-88-18 | 2015-04-09 | 2015-04-15 | 4 | 0 | 4 | 2015-04-16 | 2015-07-07 | 58 | 23 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-08 |  | 2015-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2102526 | New Bedford | 02745 | 928 | PV | 2-88-88 | 2015-10-23 | 2015-10-26 | 1 | 0 | 1 | 2015-10-28 | 2016-02-10 | 75 | 57 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2273298 | New Bedford | 02745 | 1384 | PV | TBD | 2018-04-24 | 2018-04-25 | 1 | 0 | 1 | 2018-05-04 | 2018-10-03 | 89 | 0 | 89 | [17 empty] | 0 | 0 | 0 | 2018-07-10 | 2019-04-30 | 2020-02-28 | TBD | EXP | 30 | 2020-02-27 | [7 empty] | In Queue |  | Private
2339571 | New Bedford | 02745 | 129.6 | PV | TBD | 2019-05-13 | 2019-05-22 | 7 | 0 | 7 | 2019-05-27 | 2020-09-17 | 326 | 0 | 326 | [20 empty] | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 | [8 empty] | In Queue |  | Gov't
2037121 | New Bedford | 02745 | 266 | PV | 2-104-104 | 2014-11-20 | 2014-11-24 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2129733 | New Bedford | 02745 | 496 | PV | 2-103-103 | 2016-02-18 | 2016-03-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-03-17 | Private
2334473 | New Bedford | 02745 | 496 | PV | TBD | 2019-04-12 | 2019-04-16 | 2 | 0 | 2 | [10 empty] | 2019-04-18 | 2020-09-08 | 427 | 319 | 108 | [10 empty] | 2020-10-05 |  | 2020-06-30 | TBD |  | 60 | [8 empty] | In Queue | 2019-09-20 | Private
2334854 | New Bedford | 02745 | 199.8 | PV | 2-137-139 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | 2019-04-18 |  | 427 | 379 | 48 | [20 empty] | 2020-10-05 |  | 2020-06-30 | TBD |  | 30 | [8 empty] | In Queue | 2019-06-26 | Private
2339580 | New Bedford | 02745 | 0 |  | TBD | 2019-05-13 |  | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-19 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2298 | Acushnet | 2745 | 425 | PV | 2-86-86 | 2012-11-06 | 2012-11-08 | 2 | 2 | 0 | 2012-11-08 | 2013-03-18 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-13 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online |  | Private | Y
2255 | Acushnet | 2745 | 750 | PV | 221 | 2012-09-18 | 2012-12-27 | 72 | 70 | 2 | 2013-11-13 |  | -29709 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-29 |  | -29806 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 |  | 2013-07-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | In Queue |  | Gov't | Y
1659 | New Bedford | 2745 | 16 | PV | 2-105-105 | 2010-08-02 | 2010-08-16 | 10 | 10 | 0 | 2010-08-16 | 2010-10-06 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | Online |  | Private | Y
1857 | New Bedford | 2745 | 110 | PV | 2-105-105 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online |  | Gov't | N
1829 | New Bedford | 2745 | 26 | PV | 2-106-160 | 2011-05-31 | 2011-06-14 | 10 | 1 | 9 | 2011-06-14 | 2011-08-08 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2012-01-11 | Online |  | Private | Y
2316 | New Bedford | 2745 | 100 | PV | 2-103-103 | 2012-12-13 | 2012-12-21 | 6 | 5 | 1 | 2012-12-21 | 2013-02-06 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online |  | Private | Y
2152 | New Bedford | 2745 | 1750 | PV | 2-102-102 | 2012-06-18 | 2012-10-23 | 91 | 89 | 2 | 2012-10-23 | 2012-11-27 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online |  | Private | Y
2328 | New Bedford | 2745 | 345 | PV | 240-H3 | 2013-01-15 | 2013-01-22 | 5 | 1 | 4 | 2013-01-28 | 2013-03-08 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2013-03-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-13 | Online |  | Private | Y
1996 | New Bedford | 2745 | 135 | PV | 2-104-104 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 94 | 0 | 94 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online |  | Private | Y
1864 | New Bedford | 2745 | 625 | PV | 2-59-59 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 214 | 0 | 214 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 | [5 empty] | Private | Y
1854 | New Bedford | 2745 | 250 | PV | 2-82-82 | 2011-07-20 | 2011-08-02 | 9 | 8 | 1 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 115 | 0 | 115 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1859 | New Bedford | 2745 | 50 | PV | 2-79-79 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-09-16 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2011-09-19 | Gov't | Y
2320 | New Bedford | 2745 | 100 | PV | 2-103-103 | 2012-12-17 | 2013-01-24 | 28 | 26 | 2 | 2013-01-24 | 2013-03-18 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-22 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-03-25 | Private | Y
2146 | New Bedford | 2745 | 1750 | PV | 2-102-102 | 2012-06-01 | 2012-08-07 | 47 | 45 | 2 | 2013-03-12 | 2013-04-09 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2013-04-13 | Private | Y
2361 | New Bedford | 2745 | 2000 | PV | 4-??-103 | 2013-01-29 | 2013-03-25 | 39 | 0 | 39 | 2013-03-25 | 2013-04-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1980 | New Bedford | 2745 | 30 | PV | 2-79-79 | 2011-11-30 | 2011-12-01 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [5 empty] | Private | Y
2149 | New Bedford | 2745 | 100 | PV | 2-103-103 | 2012-06-06 | 2012-06-08 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2256 | New Bedford | 2745 | 5000 | PV | 2-102-604 | 2012-09-19 |  | -29409 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2034871 | New Bedford | 02746 | 600 | PV | 2-83-403 | 2014-11-06 | 2014-11-07 | 1 | 0 | 1 | 2014-12-12 | 2015-03-30 | 76 | 65 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-12 | Online |  | Private
2041158 | New Bedford | 02746 | 18 | PV | 2-84-133 | 2014-12-04 | 2015-01-13 | 28 | 0 | 28 | 2015-01-13 | 2015-02-21 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-02-23 | 2015-06-29 | 90 | 0 | 90 |  |  | 0 | 0 | 0 | 2015-04-29 |  | 2015-07-13 | TBD | STD | 60 |  |  | 0 |  | 0 |  | 2015-12-17 | 2015-12-17 | Online |  | PRIVATE
2096734 | New Bedford | 02746 | 157 | PV | 2-87-135 | 2015-10-01 | 2015-10-02 | 1 | 8 | -7 | 2015-10-16 | 2015-11-02 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-05 | 2016-10-09 |  | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 | 2016-04-29 | Online |  | Private | Y
2097474 | New Bedford | 02746 | 360 | PV | 2-134-134 | 2015-10-02 | 2015-10-05 | 1 | 0 | 1 | 2015-10-07 | 2015-10-29 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-10-30 | 2016-05-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-03 | Online |  | Private
2119974 | New Bedford | 02746 | 280 | PV | 2-80-80 | 2016-01-05 | 2016-01-08 | 3 | 5 | -2 | 2016-01-11 | 2016-02-09 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-23 | 2016-03-28 | 2016-08-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online |  | Private
2093470 | New Bedford | 02746 | 990 | PV | 2-38-38 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-15 | 2015-10-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-28 | 2017-05-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2339584 | New Bedford | 02746 | 369.6 | PV | 2-89-181 | 2019-05-13 | 2019-05-21 | 6 | 0 | 6 | 2019-05-27 | 2019-11-13 | 118 | 0 | 118 | [22 empty] | 2020-03-20 | TBD | EXP | 30 | [8 empty] | In Queue |  | Gov't
2384474 | New Bedford | 02746 | 133 | PV | TBD | 2020-02-04 | 2020-02-07 | 3 | 0 | 3 | 2020-02-13 | 2020-02-28 | 10 | 0 | 10 | [20 empty] | 2020-02-28 |  | 2020-09-08 | TBD | EXP | 30 | [8 empty] | In Queue |  | Private
2339142 | New Bedford | 02746 | 355 | PV | TBD | 2019-05-10 | 2019-05-17 | 5 | 0 | 5 | 2019-05-27 |  | 400 | 0 | 400 | [20 empty] | 2020-04-17 |  | 2020-03-30 | TBD |  | 30 | [8 empty] | In Queue |  | Gov't
1845 | New Bedford | 2746 | 177 | PV | 2-84-15 | 2011-07-04 | 2011-07-05 | 1 | 0 | 1 | 2011-07-05 | 2011-08-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2011-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online |  | Private | Y
1861 | New Bedford | 2746 | 50 | PV | 2-83-403 | 2011-07-25 | 2011-07-28 | 3 | 2 | 1 | 2011-07-29 | 2011-09-09 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-26 |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online |  | Private | Y
2005 | New Bedford | 2746 | 287.35 | PV | 2-24-182 | 2011-12-20 | 2011-12-22 | 2 | 0 | 2 | 2011-12-22 | 2012-01-11 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2015-02-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-10-10 | Online |  | Private | Y
2393 | New Bedford | 2746 | 1000 | PV | 2-7-34 | 2013-05-28 | 2013-06-18 | 15 | 13 | 2 | 2013-06-19 | 2013-10-29 | 94 | 1 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-30 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2357 | New Bedford | 2746 | 50 | PV | 2-82-82 | 2013-03-07 |  | -29530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2020964 | Dartmouth | 02747 | 232 | PV | 2-532-532 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-09-17 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-25 | 2014-10-31 | 2014-12-15 | TBD | EXP | 30 | 2014-12-12 | 2014-12-12 | 0 |  | 0 |  |  | 2014-12-17 | Online |  | Private
2042098 | Dartmouth | 02747 | 17.5 | PV | 2-533-533 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-22 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-04 | Online |  | Private
2065135 | Dartmouth | 02747 | 239.4 | PV | 2-532-532 | 2015-04-21 | 2015-04-22 | 1 | 0 | 1 | 2015-04-24 | 2015-06-15 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2015-08-26 | 2015-11-25 | No | EXP | 30 | 2015-09-16 | 2015-09-16 | 0 |  | 0 |  | 2015-12-22 | 2016-02-28 | Online |  | Private
2107468 | Dartmouth | 02747 | 72 | PV | 2-543-543 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-03 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online |  | Gov't
2157191 | Dartmouth | 02747 | 150 | Natural Gas | 2-541-542 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-14 |  | -30405 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-22 | 2017-02-15 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-31 | Online |  | Gov't
2264640 | Dartmouth | 02747 | 1500 | PV | 2-107-107 | 2018-02-26 | 2018-02-27 | 1 | 0 | 1 | [10 empty] | 2018-02-28 | 2020-05-04 | 379 | 122 | 257 | [7 empty] | 0 | 0 | 0 | 2018-10-12 |  | 2019-06-14 | TBD |  | 60 | [6 empty] | 2019-06-11 | 2019-06-11 | Online |  | Private
2024047 | Dartmouth | 02747 | 301.6 | PV | 2-531-531 | 2014-09-11 | 2014-09-12 | 1 | 0 | 1 | 2014-09-19 | 2015-01-16 | 85 | 53 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-04-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2054857 | Dartmouth | 02747 | 800 | PV | 2-533-530 | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2137247 | Dartmouth | 02747 | 1000 | PV | 2-532-532 | 2016-03-28 | 2016-03-28 | 0 | 0 | 0 | 2016-03-29 | 2016-04-28 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2138143 | Dartmouth | 02747 | 18 | PV | 2-532-532 | 2016-04-01 | 2016-04-05 | 2 | 0 | 2 | 2016-04-11 | 2016-06-22 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-29 |  | 2016-11-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2102045 | Dartmouth | 02747 | 98 | PV | 2-543-543 | 2015-10-23 | 2015-10-24 | 1 | 0 | 1 | 2015-11-03 | 2016-06-27 | 169 | 157 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2065189 | Dartmouth | 02747 | 360 | PV | 2-532-532 | 2015-04-22 | 2015-07-28 | 69 | 60 | 9 | 2015-08-03 | 2016-08-01 | 260 | 63 | 197 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-07 |  | 2015-11-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2051325 | Dartmouth | 02747 | 360 | PV | 2-532-532 | 2015-01-21 | 2015-01-21 | 0 |  | 0 | 2015-01-27 |  | -30023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-03 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2058198 | Dartmouth | 02747 | 17 | PV | 2-532-532 | 2015-03-16 | 2015-03-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-03-24 | Private
2076812 | Dartmouth | 02747 | 4500 | PV | 2-532-532 | 2015-06-23 | 2015-06-29 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-07-03 | Private
2342977 | Dartmouth | 02747 | 0 | PV | TBD | 2019-06-03 |  | 218 | 0 | 218 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-10 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
1470 | Dartmouth | 2747 | 95 | PV | 2-532-532 | 2009-10-16 | 2009-10-23 | 5 | 1 | 4 | 2009-10-23 | 2009-11-30 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-03 |  | 2009-11-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-20 |  | 2010-06-02 | Online |  | Private | Y
1622 | Dartmouth | 2747 | 2150 | Natural Gas | 2-525-525 | 2010-05-07 | 2010-05-11 | 2 | 2 | 0 | 2010-05-12 | 2010-06-22 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-23 |  | 2010-11-23 | Online |  | Gov't | N
1707 | Dartmouth | 2747 | 33 | PV | 2-543-543 | 2010-10-24 | 2010-11-16 | 17 | 16 | 1 | 2010-11-16 | 2010-11-29 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-22 |  | 2010-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-28 | Online |  | Private | Y
1783 | Dartmouth | 2747 | 600 | Wind | 2-525-525 | 2011-03-21 | 2011-03-21 | 0 | 0 | 0 | 2011-03-21 | 2011-03-30 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-01 | Online |  | Private | Y
1753 | Dartmouth | 2747 | 600 | Wind | 2-525-525 | 2011-01-20 | 2011-02-01 | 8 | 7 | 1 | 2011-02-01 | 2011-03-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online |  | Gov't | Y
1735 | Dartmouth | 2747 | 82 | PV | 2-525-525 | 2010-12-15 | 2010-12-21 | 4 | 1 | 3 | 2010-12-21 | 2011-01-25 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-03-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-18 | Online |  | Private | N
1731 | Dartmouth | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
1732 | Dartmouth | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
1733 | Dartmouth | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
1734 | Dartmouth | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online |  | Gov't | N
1672 | Dartmouth | 2747 | 1000 | PV | 2-532-532 | 2010-08-26 | 2010-09-02 | 5 | 4 | 1 | 2010-09-02 | 2010-11-29 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-29 |  | 2012-05-25 | Online |  | Private | Y
1862 | Dartmouth | 2747 | 2000 | PV | 2-541-541 | 2011-07-26 | 2011-07-28 | 2 | 2 | 0 | 2011-07-29 | 2011-08-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2012-07-05 | Online |  | Gov't | N
1890 | Dartmouth | 2747 | 1146 | PV | 2-107-107 | 2011-08-23 | 2011-08-29 | 4 | 4 | 0 | 2011-08-29 | 2011-10-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2013-03-27 | Online |  | Private | Y
1888 | Dartmouth | 2747 | 1146 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 234 | 0 | 234 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Private | Y
1889 | Dartmouth | 2747 | 1000 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 234 | 0 | 234 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online |  | Private | Y
1924 | Dartmouth | 2747 | 2750 | PV | 2-541-541 | 2011-09-30 | 2011-10-04 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2014-03-24 | Online |  | Gov't | Y
1768 | Dartmouth | 2747 | 1000 | PV | 2-525-525 | 2011-02-11 | 2011-02-28 | 11 | 10 | 1 | 2011-02-28 | 2011-04-07 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  |  | Withdrawn |  | Gov't | Y
1763 | Dartmouth | 2747 | 4560 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1764 | Dartmouth | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1765 | Dartmouth | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1766 | Dartmouth | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1767 | Dartmouth | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 348 | 0 | 348 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | N
1927 | Dartmouth | 2747 | 2000 | PV | 2-532-532 | 2011-10-03 | 2011-10-04 | 1 | 1 | 0 | 2011-10-04 | 2011-11-23 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1925 | Dartmouth | 2747 | 4000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | -29237 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1926 | Dartmouth | 2747 | 2000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | -29237 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
1983 | Dartmouth | 2747 | 1000 | PV | 2-533-533 | 2011-11-30 | 2011-12-15 | 11 | 9 | 2 | 2011-12-15 | 2012-03-07 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-07 |  | 2011-12-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-15 |  |  | Withdrawn |  | Private | Y
1981 | Dartmouth | 2747 | 4400 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | 1 | 1 | 0 | 2011-12-01 | 2012-03-12 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | -29765 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1982 | Dartmouth | 2747 | 2000 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | 1 | 1 | 0 | 2011-12-01 | 2012-03-12 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | -29765 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2073 | Dartmouth | 2747 | 16 | PV | 2-543-543 | 2012-03-14 | 2012-04-09 | 18 | 16 | 2 | 2012-04-09 | 2012-06-11 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 |  | -29346 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2136 | Dartmouth | 2747 | 276 | PV | 2-543-543 | 2012-05-21 | 2012-05-21 | 0 | 0 | 0 | 2012-05-22 | 2012-08-02 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2212 | Dartmouth | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | 9 | 9 | 0 | 2012-08-23 | 2012-10-01 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2213 | Dartmouth | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-10-12 | 47 | 47 | 0 | 2012-10-12 | 2012-11-30 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-04 | 2013-09-11 | 178 | 0 | 178 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2208 | Dartmouth | 2747 | 500 | PV | 2-543-543 | 2012-08-06 | 2012-11-07 | 67 | 66 | 1 | 2012-11-07 | 2013-01-22 | 54 | 13 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-04 | 2013-07-25 | 80 | 0 | 80 |  |  | 0 | 0 | 0 | 2013-08-05 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2209 | Dartmouth | 2747 | 3500 | PV | 2-532-532 | 2012-08-07 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2210 | Dartmouth | 2747 | 1000 | PV | 2-543-543 | 2012-08-07 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
2211 | Dartmouth | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
2364 | Dartmouth | 2747 | 17 | PV | 2-543-543 | 2013-03-27 | 2013-04-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2013-08-16 | Private | Y
1958 | North Dartmouth | 2747 | 125 | PV | 2-541-541 | 2011-11-04 | 2011-11-04 | 0 | 0 | 0 | 2011-11-04 | 2011-12-19 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online |  | Private | Y
2216 | North Dartmouth | 2747 | 100 | PV | 2-543-543 | 2012-08-10 | 2012-08-15 | 3 | 2 | 1 | 2012-08-15 | 2012-09-20 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-06 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online |  | Gov't | Y
2300 | North Dartmouth | 2747 | 20 | PV | 2-528-528 | 2012-10-31 | 2012-11-14 | 10 | 0 | 10 | 2012-11-14 | 2013-01-04 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online |  | Gov't | Y
2310 | North Dartmouth | 2747 | 13 | PV | 2-524-524 | 2012-12-03 | 2012-12-27 | 18 | 16 | 2 | 2012-12-27 | 2013-02-12 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-07 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-20 | Online |  | Private | Y
2383 | North Dartmouth | 2747 | 75 | PV | 2-532-532 | 2013-05-07 | 2013-05-16 | 7 | 6 | 1 | 2013-05-17 | 2013-06-26 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-25 | Online |  | Private | Y
2368 | North Dartmouth | 2747 | 225 | PV | 2-543-543 | 2013-04-03 | 2013-04-26 | 17 | 14 | 3 | 2013-05-01 | 2013-06-18 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Private | Y
2454 | North Dartmouth | 2747 | 25 | PV | 2-531-531 | 2013-10-18 | 2013-11-01 | 10 | 10 | 0 | 2013-11-01 |  | -29701 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-31 | Online |  | Private | Y
2446 | North Dartmouth | 2747 | 383 | PV | 2-531-530 | 2013-09-23 | 2013-09-27 | 4 | 1 | 3 | 2013-10-01 |  | -29678 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-10-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online |  | Private | Y
1593 | North Dartmouth | 2747 | 1500 | PV | 2-541-541 | 2010-03-23 | 2010-03-26 | 3 | 3 | 0 | 2010-03-26 | 2010-05-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-10 |  | 2010-03-26 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-09 |  |  |  |  | Private | Y
1900 | North Dartmouth | 2747 | 17 | PV | 2-72-501 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-22 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2326 | North Dartmouth | 2747 | 134 | PV | 2-533-503 | 2013-01-04 | 2013-01-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Gov't | Y
1986041 | Dartmouth | 02748 | 21 | PV | 2-524-524 | 2014-02-10 | 2014-05-16 | 69 |  | 69 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-08-19 | Online |  | Private
2064782 | Dartmouth | 02748 | 20 | PV | 2-528-528 | 2015-04-17 | 2015-04-23 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-28 | Online |  | Private
2049963 | Dartmouth | 02748 | 17.8 | PV | 2-2-505 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-02-06 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2072760 | Dartmouth | 02748 | 100 | PV | 2-528-528 | 2015-06-01 | 2015-06-05 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2016-06-14 | Private
2090751 | Dartmouth | 02748 | 18 | PV | 2-524-524 | 2015-09-01 | 2015-09-02 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue |  | Private | N
1535 | Dartmouth | 2748 | 32 | PV | 2-532-532 | 2009-12-17 | 2010-01-12 | 18 | 16 | 2 | 2010-01-12 | 2010-02-11 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-12 |  | 2010-02-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-03-25 | Online |  | Gov't | N
1684 | Dartmouth | 2748 | 95 | PV | 2-524-524 | 2010-09-27 | 2010-10-14 | 13 | 9 | 4 | 2010-10-14 | 2010-12-03 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-03-10 | Online |  | Private | Y
1842 | Dartmouth | 2748 | 50 | PV | 2-524-524 | 2011-07-01 | 2011-07-18 | 11 | 11 | 0 | 2011-07-18 | 2011-07-25 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | 47 | 0 | 47 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online |  | Gov't | Y
1777 | Dartmouth | 2748 | 1000 | PV | 2-528-528 | 2011-03-08 | 2011-04-15 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Private | Y
1559 | South Dartmouth | 2748 | 3340 | Wind | 2-531-531 | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2010-01-22 | Online |  | Private | Y
1541 | South Dartmouth | 2748 | 750 | Wind | 2-528-528 | 2010-01-04 | 2010-01-07 | 3 | 1 | 2 | 2010-01-07 | 2010-02-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2010-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2010-04-01 | Online |  | Private | Y
1686 | South Dartmouth | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
1687 | South Dartmouth | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
1689 | South Dartmouth | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
1690 | South Dartmouth | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
1693 | South Dartmouth | 2748 | 17 | PV | 2-53-65 | 2010-09-27 | 2010-10-14 | 13 | 9 | 4 | 2010-10-15 | 2010-11-22 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-08 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-04 | Online |  | Private | Y
1691 | South Dartmouth | 2748 | 14 | PV | 2-53-65 | 2010-09-24 | 2010-11-02 | 27 | 23 | 4 | 2010-11-02 | 2010-12-16 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-29 |  | 2011-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-11-08 |  | 2011-11-08 | Online |  | Gov't | N
2064 | West Wareham | 2756 | 30 | PV | 3-86-966 | 2012-03-01 | 2012-03-08 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2012-03-28 | Private | Y
2370 | Westport | 2767 | 82 | PV | 2-522-522 | 2013-04-12 | 2013-04-17 | 3 | 1 | 2 | 2013-04-25 | 2013-06-18 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-24 |  | 2013-06-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-13 | Online |  | Private | Y
2056499 | Rochester | 02770 | 2500 | PV | 3-703-703 | 2015-02-27 | 2015-02-27 | 62 | 62 | 1 | 2015-03-05 | 2015-07-02 | 63 | 0 | 63 | [17 empty] | 0 | 0 | 0 | 2015-07-28 | 2016-09-12 | 2016-12-16 | TBD | EXP | 30 | 2016-03-02 | 2016-03-02 |  |  |  |  | 2017-01-13 | 2017-01-13 | Online |  | Private
2114929 | Rochester | 02770 | 392 | PV | 3-702-702 | 2015-12-15 | 2015-12-15 | 0 | 1 | 0 | 2015-12-18 | 2016-01-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 | 2016-05-25 | 2016-07-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online |  | Private
2056449 | Rochester | 02770 | 840 | PV | 3-702-702 | 2015-03-03 | 2015-03-03 | 0 | 0 | 0 | 2015-03-06 | 2015-03-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online |  | Private
2135262 | Rochester | 02770 | 260 | PV | 3-702-702 | 2016-03-16 | 2016-03-22 | 4 | 0 | 4 | 2016-03-22 |  | -30323 | 97 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2017-01-24 | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-03-08 | Online |  | Private | N
2090360 | Rochester | 02770 | 1000 | PV | 3-702-702 | 2015-08-27 | 2015-08-28 | 1 | 0 | 1 | 2015-08-31 | 2015-11-23 | 60 | 53 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-22 |  | 2016-04-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-14 | Online |  | Private
2016902 | Rochester | 02770 | 2000 | PV | 3-703-703 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | 2014-08-11 | 2014-12-02 | 81 | 60 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-17 | 2015-09-08 | 2016-03-15 | No | EXP | 30 | 2016-01-28 | 2016-01-28 | 0 |  | 0 |  | 2016-04-14 |  | Withdrawn |  | Private | N
2037775 | Rochester | 02770 | 1500 | PV | 3-702-702 | 2014-11-28 | 2014-12-23 | 17 | 0 | 17 | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2103577 | Rochester | 02770 | 3000 | PV | 3-702-702 | 2015-11-03 | 2015-11-03 | 0 | 0 | 0 | 2015-11-09 | 2015-11-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-31 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2092354 | Rochester | 02770 | 2000 | PV | 3-702-702 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2016-04-06 | 148 | 130 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  | Private
2246980 | Rochester | 02770 | 1000 | PV | 3-85-85 | 2017-10-27 | 2017-11-07 | 7 |  | 7 | 2017-11-29 | 2018-11-06 | 243 |  | 243 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | STD |  |  |  | 0 |  | 0 | [5 empty] | Private
2269022 | Rochester | 02770 | 1250 | PV | TBD | 2018-03-30 |  | 1 | 0 | 1 | 2018-04-02 | 2020-07-20 | 572 | 572 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD | EXP | 30 | [8 empty] | Withdrawn |  | Private
2092534 | Rochester | 02770 | 1000 | PV | 3-702-702 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2016-06-17 | Private
2103573 | Rochester | 02770 | 2000 | PV | 3-703-703 | 2015-10-29 | 2015-11-04 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-11-04 | Private
2258583 | Rochester | 02770 | 7415 | PV | TBD | 2018-01-12 | 2018-01-17 | 2 | 0 | 2 | [10 empty] | 2018-01-17 | 2020-01-07 | 384 | 234 | 150 | [7 empty] | 0 | 0 | 0 | 2019-05-17 |  | 2019-06-28 | No |  | 60 | [7 empty] | 2023-01-19 | Online |  | Private | N
2259340 | Rochester | 02770 | 3320 | PV | TBD | 2018-01-18 |  | 1 | 0 | 1 | [7 empty] | 0 | 0 | 0 | 2018-01-23 | 2019-09-30 | 236 | 160 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-05-07 |  | 2019-06-30 | No | TBD | 60 | [8 empty] | Withdrawn |  | Private
2260703 | Rochester | 02770 | 2540 | PV | TBD | 2018-01-29 | 2018-01-31 | 2 | 0 | 2 | [10 empty] | 2018-01-31 |  | 727 | 394 | 333 | [7 empty] | 0 | 0 | 0 |  |  | 2020-03-20 | No |  | 60 | [8 empty] | In Queue |  | Private
2260702 | Rochester | 02770 | 540 | PV | TBD | 2018-01-29 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-09-04 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2264857 | Rochester | 02770 | 4650 | PV | TBD | 2018-02-27 | 2018-03-01 | 2 | 0 | 2 | [10 empty] | 2018-03-05 |  | 708 | 660 | 48 | [7 empty] | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 60 | [8 empty] | In Queue | 2018-05-11 | Private
2296978 | Rochester | 02770 | 0 |  | TBD | 2018-09-17 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-04-26 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2395209 | Rochester | 02770 | 999 | PV | TBD | 2020-04-23 | 2020-04-27 | 2 | 0 | 2 | 2020-04-28 |  | 172 | 0 | 172 | [22 empty] | 2020-11-30 | TBD |  | 30 | [8 empty] | In Queue |  | Private
2393720 | Rochester | 02770 | 0 |  | TBD |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-11-17 | TBD | TBD | 30 | [8 empty] | Withdrawn |  | Private
2224 | Rochester | 2770 | 17 | PV | 3-702-702 | 2012-08-16 | 2012-08-17 | 1 | 1 | 0 | 2012-10-12 | 2013-01-15 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1386 | Roslindale | 2771 | 30 | PV | 496-H3 | 2009-07-14 | 2009-08-13 | 22 | 10 | 12 | 2009-08-13 | 2009-09-15 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-16 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2010-01-07 |  | 2010-01-07 | Online |  | Private | N
2247147 | Wareham | 02777 | 26.35 | PV | 3-85-85 | 2017-10-20 | 2017-10-26 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
2059968 | Westport | 02790 | 21 | PV | 2-523-523 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | 2015-04-09 | 2015-05-01 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-08 | 2015-05-08 | 2015-10-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online |  | Private
2107466 | Westport | 02790 | 36 | PV | 2-523-523 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-11-30 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online |  | Private
2068650 | Westport | 02790 | 2550 | PV | 2-522-522 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-19 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-05 |  | 2015-12-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-01 | Online |  | Private | Y
2101010 | Westport | 02790 | 19 | PV | 2-523-523 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2015-11-23 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-11 | 2016-01-11 | 2016-04-15 | No | EXP | 30 | 2016-03-11 |  | -30316 |  | 0 |  |  | 2016-12-07 | Online |  | Private | N
2061122 | Westport | 02790 | 2000 | PV | 2-532-532 | 2015-04-01 | 2015-04-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-09-27 | Online |  | Private
2033167 | Westport | 02790 | 30 | PV | 2-532-532 | 2014-10-30 | 2014-12-18 | 35 | 0 | 35 | 2014-12-29 | 2015-01-12 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private
2051411 | Westport | 02790 | 16.3 | PV | 2-523-523 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-10 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 |  | 2015-08-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Private | N
2129051 | Westport | 02790 | 25 | PV | 2-532-532 | 2016-02-12 | 2016-02-17 | 3 | 0 | 3 | 2016-02-23 | 2016-05-26 | 67 | 63 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-27 |  | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  | Gov't
2085492 | Westport | 02790 | 2000 | PV | 2-524-524 | 2015-07-31 | 2015-08-04 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | 2015-08-17 | Gov't
2110823 | Westport | 02790 | 1000 | PV | 2-523-523 | 2015-12-07 | 2015-12-08 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | In Queue | 2015-12-16 | Private
2246192 | Westport | 02790 | 21.95 | PV | 2-532-532 | 2017-10-11 | 2017-10-23 | 8 |  | 8 | 2017-11-20 |  | -30749 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
2277378 | Westport | 02790 | 4875 | PV & Battery | TBD | 2018-05-17 | 2018-05-22 | 3 | 0 | 3 | [10 empty] | 2018-05-22 | 2018-12-26 | 148 | 148 | 0 | [7 empty] | 0 | 0 | 0 | 2018-10-22 |  | 2020-12-30 | TBD |  | 60 | [8 empty] | In Queue |  | Private
1685 | Dartmouth | 2790 | 70 | PV | 2-523-523 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online |  | Private | Y
1514 | Westport | 2790 | 34 | PV | 2-523-523 | 2009-11-20 | 2009-12-03 | 9 | 9 | 0 | 2009-12-03 | 2010-01-28 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-02 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-13 |  | 2010-05-13 | Online |  | Private | Y
1619 | Westport | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
1620 | Westport | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online |  | Private | Y
2057 | Westport | 2790 | 20 | PV | 2-524-524 | 2012-02-21 | 2012-03-01 | 7 | 5 | 2 | 2012-03-01 | 2012-05-21 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online |  | Private | Y
1621 | Westport | 2790 | 10 | Wind | 2-523-523 | 2010-05-07 | 2011-10-03 | 366 | 366 | 0 | 2011-10-03 | 2011-11-09 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-08-28 | 2013-08-28 | 2013-09-19 | Online |  | Gov't | N
2453 | Westport | 2790 | 100 | PV | 2-532-532 | 2013-10-16 | 2013-10-18 | 2 | 0 | 2 | 2013-10-21 |  | -29692 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-14 | Online |  | Private | Y
2231 | Westport | 2790 | 500 | PV | 2-523-523 | 2012-08-24 | 2012-09-06 | 9 | 8 | 1 | 2012-09-06 | 2012-11-26 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-09-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
2214 | Westport | 2790 | 500 | PV | 2-523-523 | 2012-08-09 |  | -29380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Gov't | Y
1660 | Westport | 2791 | 7 | PV | 2-523-523 | 2010-08-01 | 2010-08-13 | 10 | 7 | 3 | 2010-08-16 | 2010-10-06 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-16 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-16 | Online |  | Private | Y
2072 | Milton | 4101 | 190 | PV | 362-05 | 2012-03-13 | 2012-03-20 | 5 | 5 | 0 | 2012-03-20 | 2012-04-26 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-27 |  | 2012-04-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | In Queue | 2012-04-27 | Private | Y
1839 | Holliston | 7146 | 1750 | PV | 274-H2 | 2011-06-24 | 2011-07-29 | 25 | 23 | 2 | 2011-07-29 | 2011-09-16 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Private | Y
1700 | Dorchester | 21222 | 65 | Natural Gas | 466-1482H1 | 2009-10-01 | 2010-11-09 | 288 | 19 | 269 | 2010-11-09 | 2010-12-08 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-13 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-03-04 |  | 2011-03-07 | Online |  | Gov't | N
2371 | Dartmouth | 94402 | 19 | PV | 2-533-533 | 2013-04-10 | 2013-04-30 | 14 | 10 | 4 | 2013-04-30 |  | -29568 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Gov't | Y
2258582 | Boston |  | 992 | PV | 344-1413H1 | 2017-12-22 | 2018-01-03 | 7 |  | 7 | 2018-01-17 |  | -30789 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
2352975 | Carver |  | 1250 | PV & Battery | TBD | 2019-07-12 | 2019-07-19 |  |  |  | 2019-08-05
2399437 | South Dennis |  | 15.2 | PV | TBD | 2020-04-01 | 2020-05-18 |  |  |  | 2020-06-16 | [24 empty] | 2020-06-23 | [12 empty] | 2021-03-16 | Online
2408369 | Welfleet |  | 0 |  | TBD | [44 empty] | Withdrawn
2239531 | Plympton |  | 4695 | PV & Battery | TBD | 2017-09-17 | 2017-09-17 |  |  |  | 2017-09-17 | [24 empty] | 2019-02-14 | [12 empty] | 2020-12-21 | Online