NSTAR | Rochester | 2224 | 2770 | 17 | PV | 3-702-702 | 2012-08-16 | 2012-08-17 | 1 | 1 | 0 | 2012-10-12 | 2013-01-15 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Allston | 2225 | 2134 | 354 | PV | 467-H11 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-11-19 | 64 | 21 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-14 |  | 2013-08-29 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs and NSTARwork completion | [5 empty] | Gov't | Y
NSTAR | Wareham | 2226 | 2538 | 4000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Wareham | 2227 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Wareham | 2228 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Wareham | 2229 | 2538 | 1000 | PV | 3-83-83 | 2012-08-20 | 2012-08-27 | 5 | 5 | 0 | 2012-08-27 | 2012-10-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  | 2013-03-11 | [7 empty] | Private | Y
NSTAR | Dover | 2230 | 2030 | 23 | PV | 456-H5 | 2012-08-24 |  | -29386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Westport | 2231 | 2790 | 500 | PV | 2-523-523 | 2012-08-24 | 2012-09-06 | 8 | 8 | 0 | 2012-09-06 | 2012-11-26 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-09-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Lincoln | 2232 | 1733 | 13 | PV | 320-H6 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2013-06-26 | 204 | 0 | 204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 | 2014-06-24 |  |  | Awaiting Witness test | [5 empty] | Gov't | Y
NSTAR | Newton | 2233 | 2460 | 260 | PV | 17-H1 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-11-25 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-06-24 | Online | [5 empty] | Gov't | Y
NSTAR | Newton | 2234 | 2461 | 100 | PV | 433-02 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-09-27 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-05 | 2012-09-01 | -126 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | Standard |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online | [5 empty] | Gov't | Y
NSTAR | Newton | 2235 | 2459 | 200 | PV | 292-H8 | 2012-08-27 | 2012-08-30 | 3 | 3 | 0 | 2013-09-06 | 2013-10-10 | 24 | 228 | -204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online | [5 empty] | Gov't | Y
NSTAR | Lexington | 2236 | 2421 | 260 | PV | 533-H2 | 2012-08-29 |  | -29389 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Barnstable | 2237 | 2360 | 11 | PV | 4-82-518 | 2012-08-29 | 2012-10-16 | 32 | 34 | -2 | 2012-10-16 | 2013-01-30 | 72 | 65 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Plymouth | 2238 | 2360 | 95 | PV | 3-12-12 | 2012-08-29 | 2012-09-05 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs |  |  |  |  | 2012-09-21 | Private | Y
NSTAR | West Yarmouth | 2239 | 2673 | 150 | PV | 4-92A-536 | 2012-08-30 | 2012-10-03 | 23 | 24 | -1 | 2012-10-03 | 2013-03-18 | 112 | 0 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-08-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Dorchester | 2240 | 2122 | 95 | PV | 511-1498H1 | 2012-08-28 | 2012-09-12 | 10 | 3 | 7 | 2012-09-12 | 2013-04-29 | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-10-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-01-06 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2241 | 2740 | 190 | PV | 2-81-94 | 2012-08-21 | 2012-09-07 | 12 | 6 | 6 | 2012-09-07 | 2012-09-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-31 |  | 2012-10-30 | Yes | Expedited |  |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-09-11 | 2013-10-11 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2242 | 2740 | 225 | PV | 2-84-84 | 2012-08-22 | 2012-09-07 | 11 | 5 | 6 | 2012-09-07 | 2012-11-16 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-10-11 | Online | [5 empty] | Private | Y
NSTAR | East Falmouth | 2243 | 2536 | 11 | PV | 4-98B-449 | 2012-08-31 | 2012-09-06 | 3 | 4 | -1 | 2012-09-06 | 2012-10-05 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-13 |  | 2012-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-01-30 | 2013-01-30 | 2013-01-30 | Online | [5 empty] | Gov't | Y
NSTAR | Lexington | 2244 | 2421 | 56 | PV | 320-H5XY | 2012-08-30 | 2012-09-11 | 7 | 5 | 2 | 2012-09-11 | 2013-01-07 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-04-23 | 2013-04-23 | 2013-04-23 | Online | [5 empty] | Gov't | Y
NSTAR | Harwich | 2245 | 2661 | 20 | PV | 320-H5XY | 2012-09-05 | 2012-12-05 | 63 | 65 | -2 | 2012-12-05 | 2013-02-01 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-05 |  | 2012-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-02-21 | 2013-02-21 | 2013-02-21 | Online | [5 empty] | Private | Y
NSTAR | Walpole | 2246 | 2081 | 300 | PV | 4-85-592 | 2012-09-05 | 2012-09-26 | 15 | 15 | 0 | 2012-09-26 | 2012-12-18 | 57 | 46 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-10 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online | [5 empty] | Private | Y
NSTAR | Canton | 2247 | 2021 | 237 | PV | 135-1319H1 | 2012-09-05 | 2012-09-10 | 3 | 3 | 0 | 2012-09-10 | 2012-11-25 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-02-04 | Online | [5 empty] | Private | Y
NSTAR | Woburn | 2248 | 1801 | 12 | PV | 211-H5 | 2012-09-04 | 2012-09-11 | 5 | 3 | 2 | 2012-09-11 | 2012-11-14 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-15 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Newton | 2250 | 2461 | 50 | PV | 292-H11 | 2012-09-06 | 2013-05-10 | 169 | 175 | -6 | 2013-05-10 | 2013-06-18 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | N
NSTAR | Assonett | 2251 | 2702 | 500 | PV | 2-605-605 | 2012-09-14 | 2012-09-24 | 6 | 6 | 0 | 2012-09-24 | 2012-12-12 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Newton | 2252 | 2460 | 20 | PV | 282-H9 | 2012-09-17 | 2012-09-18 | 1 | 1 | 0 | 2012-09-18 | 2012-10-10 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-26 |  | 2012-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online | [5 empty] | Private | Y
NSTAR | Lexington | 2253 | 2420 | 18 | PV | 391-H3 | 2012-09-17 | 2012-09-19 | 2 | 1 | 1 | 2012-10-04 | 2013-03-18 | 111 | 0 | 111 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-12-13 | 2013-12-13 | 2013-12-20 | Online | [5 empty] | Private | Y
NSTAR | Plymouth | 2254 | 2360 | 361 | PV | 3-14-911 | 2012-09-17 | 2012-09-20 | 3 | 2 | 1 | 2012-09-20 | 2012-10-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-10 | 2013-09-19 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-12-09 |  | 2013-01-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online | [5 empty] | Private | N
NSTAR | Acusnet | 2255 | 2745 | 750 | PV | 221 | 2012-09-18 | 2012-12-27 | 69 | 70 | -1 | 2013-11-13 |  | -29690 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-29 |  | -29781 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 |  | 2013-07-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage | [5 empty] | Gov't | Y
NSTAR | New Bedford | 2256 | 2745 | 5000 | PV | 2-102-604 | 2012-09-19 |  | -29403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Harwich | 2257 | 2645 | 4000 | PV | 4-89A-89A | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 77 | 0 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | West Harwich | 2258 | 2671 | 11 | PV | 4-85-925 | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 77 | 0 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | West Harwich | 2259 | 2671 | 11 | PV | 4-85-925 | 2012-09-26 | 2012-10-12 | 11 | 12 | -1 | 2012-10-16 | 2013-01-30 | 72 | 36 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  | 2014-09-19 | Online | [5 empty] | Gov't | Y
NSTAR | Mattapoisett | 2260 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-10-12 | 11 | 12 | -1 | 2012-10-16 | 2013-01-30 | 72 | 36 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | [5 empty] | Gov't | N
NSTAR | Mattapoisett | 2261 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-11-27 | 42 | 44 | -2 | 2012-11-27 | 2013-02-06 | 48 | 11 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 2014-02-25 |  | 2013-10-15 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  | 2014-09-18 | Online | [5 empty] | Private | Y
NSTAR | Holliston | 2262 | 1746 | 3000 | PV | 3-88-2J2 | 2012-09-28 | 2012-09-28 | 0 | 0 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-10-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-12-11 | Online | [5 empty] | Gov't | Y
NSTAR | Wayland | 2263 | 1778 | 13 | PV | 342-H1 | 2012-09-29 | 2012-10-17 | 12 | 12 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | [5 empty] | Private | Y
NSTAR | Sudbury | 2264 | 1776 | 12 | PV | 342-H8 | 2012-09-29 | 2012-11-07 | 27 | 27 | 0 | 2012-11-07 | 2012-12-26 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-11 |  | 2012-11-07 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online | [5 empty] | Private | Y
NSTAR | Sudbury | 2265 | 1776 | 12 | PV | 342-H2 | 2012-09-29 | 2012-10-17 | 12 | 12 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Wayland | 2266 | 1778 | 12 | PV | 342-H9 | 2012-10-01 | 2012-11-28 | 40 | 41 | -1 | 2012-11-28 | 2013-01-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-09 |  | 2012-10-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online | [5 empty] | Private | Y
NSTAR | Plymouth | 2267 | 2360 | 12 | PV | 3-11-11 | 2012-10-01 | 2012-11-28 | 40 | 41 | -1 | 2012-11-28 | 2013-01-15 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2268 | 1778 | 10 | PV | 342-H1 | 2012-10-01 | 2012-10-24 | 16 | 16 | 0 | 2012-10-24 | 2013-01-15 | 56 | 26 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 |  | 2012-10-22 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online | [5 empty] | Private | Y
NSTAR | Brewster | 2269 | 2631 | 16 | PV | 4-89B-89B | 2012-10-02 | 2012-10-24 | 15 | 16 | -1 | 2012-10-24 | 2012-12-12 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-13 |  | 2012-10-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-05 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2270 | 1778 | 17 | PV | 342-H1 | 2012-10-02 | 2012-11-07 | 25 | 26 | -1 | 2012-11-14 | 2012-12-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-31 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-14 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2271 | 1773 | 14 | PV | 282-H1 | 2012-10-02 | 2012-10-24 | 15 | 16 | -1 | 2012-10-24 | 2012-12-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-02-28 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2272 | 1773 | 12 | PV | 320-H6 | 2012-10-02 | 2012-11-13 | 29 | 30 | -1 | 2012-11-13 | 2012-12-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  | 2012-10-25 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-09 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2273 | 1778 | 14 | PV | 278-H2 | 2012-10-02 | 2012-11-21 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs |  |  |  |  | 2013-03-19 | Private | Y
NSTAR | Bellingham | 2274 | 2019 | 1000 | PV | 65-H4 | 2012-10-02 | 2012-11-06 | 24 | 23 | 1 | 2012-11-06 | 2013-01-17 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-11-20 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-04-01 | 2013-04-01 | [7 empty] | Private | Y
NSTAR | Brewster | 2275 | 2631 | 25 | PV | 4-89B-945 | 2012-10-02 |  | -29412 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Bellingham | 2276 | 2019 | 1000 | PV | 65-H4 | 2012-10-03 | 2012-10-12 | 6 | 6 | 0 | 2012-10-12 | 2012-12-04 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-01-31 | [8 empty] | Private | Y
NSTAR | Waltham | 2277 | 2452 | 12 | PV | 33-H2 | 2012-10-03 | 2012-10-12 | 6 | 6 | 0 | 2012-10-12 | 2013-01-15 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-03-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-01 | Online | [5 empty] | Private | Y
NSTAR | Harwich | 2278 | 2645 | 13 | PV | 4-95A-597 | 2012-10-04 | 2012-10-31 | 18 | 18 | 0 | 2012-10-31 | 2012-12-11 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-11-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | [5 empty] | Private | Y
NSTAR | Holliston | 2279 | 1746 | 15 | PV | 65-H5 | 2012-10-15 | 2012-11-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-12-23 | Online | [5 empty] | Private | Y
NSTAR | Cambridge | 2280 | 2139 | 7500 | Natural Gas | 817-48 | 2012-10-17 | 2012-10-25 | 6 | 5 | 1 | 2012-10-26 | 2013-02-06 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-05 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online | [5 empty] | Private | Y
NSTAR | Sudbury | 2281 | 1776 | 12 | PV | 342-H8 | 2012-10-18 | 2012-11-29 | 29 | 30 | -1 | 2012-11-29 |  | -29452 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-07 | Withdrawn |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Wayland | 2282 | 1778 | 11 | PV | 342-H1 | 2012-10-22 | 2012-11-07 | 12 | 12 | 0 | 2012-11-07 | 2012-12-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-06-26 | 96 | 0 | 96 |  |  | 0 | 0 | 0 | 2013-08-14 |  | 2012-12-15 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online | [5 empty] | Gov't | Y
NSTAR | Plymouth | 2283 | 2360 | 4260 | PV | 3-71-71 | 2012-10-23 | 2012-10-25 | 2 | 2 | 0 | 2012-10-26 | 2012-12-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online | [5 empty] | Gov't | Y
NSTAR | Plymouth | 2284 | 2360 | 75 | PV | 3-14-911 | 2012-10-19 |  | -29424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Plymouth | 2285 | 2360 | 75 | PV | 3-14-911 | 2012-10-25 | 2012-11-06 | 8 | 8 | 0 | 2012-11-06 | 2013-01-30 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2012-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online | [5 empty] | Private | Y
NSTAR | Carlisle | 2286 | 1741 | 14 | PV | 512-1399H1 | 2012-10-25 | 2012-11-01 | 5 | 4 | 1 | 2012-11-01 | 2012-12-04 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-14 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-02-25 | Online | [5 empty] | Private | Y
NSTAR | West Tisbury | 2287 | 2575 | 26 | PV | 4-97-220 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2012-12-12 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2288 | 1701 | 25 | PV | 433-H4 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-11-26 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-06-24 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2289 | 1702 | 20 | PV | 278-H1 | 2012-10-26 | 2012-11-29 | 23 | 24 | -1 | 2012-11-29 | 2013-02-06 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-04-29 | Online | [5 empty] | Private | Y
NSTAR | Cambridge | 2290 | 2139 | 14 | PV | 817-03 | 2012-10-26 | 2013-01-07 | 48 | 51 | -3 | 2013-01-11 | 2013-02-10 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-12-27 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Framingham | 2291 | 1702 | 20 | PV | 455-H5 | 2012-10-31 | 2012-11-27 | 18 | 19 | -1 | 2012-11-27 | 2012-12-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-13 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2292 | 1773 | 12 | PV | 320-H8 | 2012-10-31 | 2012-11-30 | 21 | 22 | -1 | 2012-11-30 | 2013-01-15 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Lincoln | 2293 | 1773 | 11 | PV | 320-H1 | 2012-10-31 | 2012-11-27 | 18 | 19 | -1 | 2012-11-27 | 2013-01-15 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2294 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2013-04-22 | 2013-04-26 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-11-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-06-05 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2295 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2012-12-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2296 | 1778 | 12 | PV | 342-H1 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2013-02-06 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-29 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-23 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2297 | 1778 | 11 | PV | 342-H1 | 2012-11-02 | 2012-11-07 | 3 | 3 | 0 | 2012-11-27 | 2013-01-22 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-11-14 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online | [5 empty] | Private | Y
NSTAR | Acusnet | 2298 | 2745 | 425 | PV | 2-86-86 | 2012-11-06 | 2012-11-08 | 2 | 2 | 0 | 2012-11-08 | 2013-03-18 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-13 |  | 2012-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online | [5 empty] | Private | Y
NSTAR | Plymouth | 2299 | 2360 | 132 | PV | 3-89-925 | 2012-11-06 | 2012-11-27 | 14 | 15 | -1 | 2012-11-27 | 2013-03-18 | 75 | 0 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-12-27 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-24 | Online | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2300 | 2747 | 20 | PV | 2-528-528 | 2012-10-31 | 2012-11-14 | 10 | 0 | 10 | 2012-11-14 | 2013-01-04 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online | [5 empty] | Gov't | Y
NSTAR | West Roxbury | 2301 | 2132 | 60 | PV | 468-01 | 2012-11-09 | 2012-11-16 | 5 | 2 | 3 | 2012-11-16 | 2013-03-18 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-01-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Framingham | 2302 | 1702 | 4400 | PV | 274-H4 | 2012-11-13 | 2012-11-19 | 4 | 3 | 1 | 2012-11-19 | 2013-02-06 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-21 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Withdrawn | [5 empty] | Private | Y
NSTAR | Lexington | 2303 | 2421 | 11 | PV | 3409 | 2012-11-04 | 2012-11-20 | 12 | 4 | 8 | 2012-11-20 | 2012-12-20 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2012-04-01 | TBD | Expedited |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online | [5 empty] | Gov't | Y
NSTAR | Somerville | 2304 | 2145 | 42 | PV | 250-1N90H2 | 2012-11-19 | 2012-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Lexington | 2305 | 2421 | 10 | PV | 320-H5XY | 2012-11-21 | 2012-11-28 | 4 | 5 | -1 | 2012-11-28 | 2012-12-20 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-27 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online | [5 empty] | Private | Y
NSTAR | Dover | 2306 | 2030 | 12 | PV | 456-H5 | 2012-11-26 | 2012-12-05 | 7 | 3 | 4 | 2012-12-05 | 2013-02-06 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2013-01-07 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2307 | 1773 | 12 | PV | 320-H8 | 2012-11-27 | 2012-12-04 | 5 | 5 | 0 | 2012-12-04 | 2013-02-12 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-26 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-02 | Online | [5 empty] | Private | Y
NSTAR | West Barnstable | 2308 | 2668 | 40 | PV | 4-87B-473 | 2012-11-28 | 2012-12-11 | 9 | 9 | 0 | 2012-12-11 | 2013-01-30 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online | [5 empty] | Private | Y
NSTAR | Woburn | 2309 | 1801 | 60 | PV | 375-H6 | 2012-11-28 | 2012-12-27 | 20 | 19 | 1 | 2012-12-27 | 2013-02-25 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-06 |  | 2013-01-02 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2310 | 2747 | 13 | PV | 2-524-524 | 2012-12-03 | 2012-12-27 | 17 | 16 | 1 | 2012-12-27 | 2013-02-12 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-07 |  | 2013-02-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-20 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2311 | 1773 | 10 | PV | 320-H6 | 2012-12-03 | 2012-12-13 | 8 | 6 | 2 | 2012-12-27 | 2013-02-12 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Online | [5 empty] | Private | Y
NSTAR | Wayland | 2312 | 1778 | 18 | PV | 342-H3 | 2012-12-04 | 2012-12-11 | 5 | 1 | 4 | 2012-12-11 | 2013-02-12 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-10-24 | Online | [5 empty] | Gov't | Y
NSTAR | Plymouth | 2313 | 2360 | 333 | PV | 3-13-943 | 2012-12-05 | 2012-12-13 | 6 | 1 | 5 | 2012-12-13 | 2013-02-12 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-26 |  | 2013-04-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-10-14 | Online | [5 empty] | Gov't | Y
NSTAR | Sandwich | 2314 | 2537 | 28 | PV | 4-87B-473 | 2012-12-12 | 2012-12-17 | 3 | 2 | 1 | 2012-12-17 | 2013-02-06 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-11 |  | 2013-01-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online | [5 empty] | Private | Y
NSTAR | Plympton | 2315 | 2367 | 12 | PV | 3-51-901 | 2012-12-12 | 2012-12-20 | 6 | 4 | 2 | 2012-12-20 | 2013-02-12 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2013-03-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-01 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2316 | 2745 | 100 | PV | 2-103-103 | 2012-12-13 | 2012-12-21 | 6 | 5 | 1 | 2012-12-21 | 2013-02-06 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-22 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online | [5 empty] | Private | Y
NSTAR | Needham | 2317 | 2492 | 12 | PV | 148-03 | 2012-12-14 |  | -29463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Plymouth | 2318 | 2360 | 333 | PV | 3-13-943 | 2012-12-14 | 2012-12-27 | 8 | 9 | -1 | 2012-12-27 | 2013-01-29 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2013-01-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Wayland | 2319 | 1778 | 11 | PV | 342-H1 | 2012-12-14 |  | -29463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | New Bedford | 2320 | 2745 | 100 | PV | 2-103-103 | 2012-12-17 | 2013-01-24 | 25 | 26 | -1 | 2013-01-24 | 2013-03-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-22 |  | 2012-12-20 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-03-25 | Private | Y
NSTAR | Bedford | 2321 | 1730 | 24 | PV | 533-H8 | 2012-12-18 | 2012-12-20 | 2 | 1 | 1 | 2013-03-26 | 2013-04-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-24 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-06 | Online | [5 empty] | Private | Y
NSTAR | Hopkinton | 2322 | 1748 | 190 | PV | 126-H1 | 2012-12-19 | 2012-12-21 | 2 | 1 | 1 | 2013-04-08 | 2013-04-24 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-19 |  | 2012-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-24 | Online | [5 empty] | Private | Y
NSTAR | Brewster | 2323 | 2631 | 16 | PV | 4-89B-946 | 2012-12-26 | 2012-12-27 | 1 | 1 | 0 | 2012-12-27 | 2013-02-10 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-02-21 | Private | Y
NSTAR | Newton | 2324 | 2458 | 13 | PV | 277-05 | 2012-12-28 | 2013-01-24 | 17 | 19 | -2 | 2013-01-24 | 2013-04-17 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-12-20 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-05-02 | 2013-05-02 | 2013-05-02 | Online | [5 empty] | Private | Y
NSTAR | Mashpee | 2325 | 2649 | 18 | PV | 4-71-455 | 2013-01-02 | 2013-01-09 | 5 | 3 | 2 | 2013-01-10 | 2013-04-29 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-02 |  | 2013-05-15 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2326 | 2747 | 134 | PV | 2-533-503 | 2013-01-04 | 2013-01-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage | [5 empty] | Gov't | Y
NSTAR | Carver | 2327 | 2330 | 2000 | PV | 433-H8 | 2013-01-08 | 2013-01-11 | 3 | 3 | 0 | 2013-01-16 | 2013-02-12 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-01-30 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-06-13 | 2013-06-13 | 2016-10-04 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2328 | 2745 | 345 | PV | 240-H3 | 2013-01-15 | 2013-01-22 | 4 | 1 | 3 | 2013-01-28 | 2013-03-08 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2013-03-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-06-13 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2329 | 1773 | 11 | PV | 320-H6 | 2013-01-21 | 2013-01-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs |  |  |  |  | 2013-05-07 | Gov't | Y
NSTAR | West Yarmouth | 2330 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-21 |  | -29486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | West Yarmouth | 2331 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-23 | 2013-01-28 | 3 | 0 | 3 | 2013-04-22 | 2013-05-28 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | South Sandwich | 2332 | 2653 | 2250 | PV | 2-87A-475 | 2013-01-21 | 2013-01-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for the Study of a Nearby System |  |  |  |  | 2013-05-09 | Gov't | Y
NSTAR | West Yarmouth | 2333 | 2673 | 500 | PV | 2-92A-92A | 2013-01-21 | 2013-02-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement |  |  |  |  | 2013-06-03 | Gov't | Y
NSTAR | Tisbury | 2334 | 2568 | 500 | PV | 4-91-91 | 2013-01-24 |  | -29489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | East Falmouth | 2335 | 2536 | 54 | PV | 4-98A-98A | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29560 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | [5 empty] | Gov't | Y
NSTAR | Bourne | 2336 | 2532 | 1680 | Wind | 4-81A-81A | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-03-01 | 2013-08-26 | 122 | 0 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-06-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | [5 empty] | Gov't | N
NSTAR | Framingham | 2337 | 1702 | 150 | PV | 433-H8 | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-02-27 | 2013-04-08 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-06-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-05 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2338 | 1702 | 190 | PV | 240-H3 | 2013-01-28 | 2013-01-29 | 1 | 0 | 1 | 2013-01-29 | 2013-02-11 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-11 |  | 2013-02-20 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online | [5 empty] | Private | Y
NSTAR | Lincoln | 2339 | 1773 | 9 | PV | 320-H8 | 2013-01-28 | 2013-03-12 | 30 | 30 | 0 | 2013-03-13 | 2013-04-29 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-17 |  | 2013-02-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-08-12 | 2013-08-12 | 2013-08-16 | Online | [5 empty] | Private | N
NSTAR | Woburn | 2340 | 1801 | 336 | Natural Gas | 301-1386H | 2013-01-29 | 2013-02-06 | 6 | 4 | 2 | 2013-02-13 | 2013-04-24 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2013-02-14 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online | [5 empty] | Private | Y
NSTAR | Sudbury | 2341 | 1776 | 12 | PV | 342-H8 | 2013-01-31 | 2013-02-06 | 4 | 3 | 1 | 2013-02-27 | 2013-04-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-12-15 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Plympton | 2342 | 2367 | 1000 | PV | 3-10-930 | 2013-01-31 |  | -29494 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Chilmark | 2343 | 2535 | 12 | PV | 4-97-226 | 2013-02-01 | 2013-02-07 | 4 | 1 | 3 | 2013-03-06 | 2013-04-09 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | -29736 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Millis | 2344 | 2052 | 1000 | PV | 65-H1 | 2013-02-05 | 2013-03-06 | 20 | 19 | 1 | 2013-03-21 | 2013-04-24 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2013-05-21 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Boston | 2345 | 2118 | 60 | PV | 323-02 | 2013-02-04 | 2013-04-01 | 39 | 36 | 3 | 2013-04-02 | 2013-05-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-27 |  | 2013-03-15 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online | [5 empty] | Private | Y
NSTAR | Sudbury | 2346 | 1776 | 41 | PV | 342-H7 | 2013-03-26 | 2013-04-01 | 4 | 0 | 4 | 2013-04-01 | 2013-05-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-23 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | [5 empty] | Private | Y
NSTAR | Burlington | 2347 | 1803 | 351 | PV | 391-H12 | 2013-02-08 | 2013-05-14 | 65 | 50 | 15 | 2013-06-24 | 2013-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-11 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | [5 empty] | Private | Y
NSTAR | Kingston | 2348 | 2364 | 33 | PV | 3-26-902 | 2013-02-08 | 2013-03-06 | 17 | 18 | -1 | 2013-03-11 | 2013-05-10 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  |  | TBD |  |  |  |  | 0 | 0 | 0 |  |  | 2013-11-08 | Online | [5 empty] | Private | Y
NSTAR | Waltham | 2349 | 2451 | 120 | PV | 282-H5 | 2013-02-11 | 2013-02-14 | 3 | 0 | 3 | 2013-02-27 | 2013-04-09 | 29 | 2 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2013-08-29 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  | 2014-05-16 | Online | [5 empty] | Private | Y
NSTAR | Wareham | 2350 | 2571 | 1000 | PV | 3-83-83 | 2013-02-22 | 2013-02-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for Customer's Response / Revised Docs |  |  |  |  | 2013-06-17 | Private | Y
NSTAR | Boston | 2351 | 2115 | 5750 | Natural Gas | 335-1141 | 2013-02-21 | 2013-02-27 | 4 | 3 | 1 | 2013-02-28 | 2013-04-24 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Norfolk | 2352 | 2056 | 82 | PV | 65-H1 | 2013-02-22 | 2013-03-06 | 8 | 5 | 3 | 2013-03-07 | 2013-04-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-05-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-08 | Online | [5 empty] | Private | Y
NSTAR | Assonett | 2353 | 2702 | 142 | PV | 2-605-605 | 2013-02-26 | 2013-03-28 | 22 | 20 | 2 | 2013-04-01 | 2013-04-24 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-31 |  | 2013-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online | [5 empty] | Private | Y
NSTAR | Plymouth | 2354 | 2360 | 85 | PV | 3-73-927 | 2013-03-04 | 2013-05-30 | 61 | 62 | -1 | 2013-05-30 | 2013-07-02 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-26 |  | 2013-06-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-08-11 | Online | [5 empty] | Gov't | Y
NSTAR | Carver | 2355 | 2330 | 250 | PV | 3-51-901 | 2013-03-06 | 2013-03-06 | 0 | 0 | 0 | 2013-03-08 |  | -29519 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-05-15 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Wayland | 2356 | 1778 | 10 | PV | 278-H2 | 2013-03-06 | 2013-03-13 | 5 | 2 | 3 | 2013-03-15 | 2013-04-24 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-05-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-07-18 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2357 | 2746 | 50 | PV | 2-82-82 | 2013-03-07 |  | -29518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Winchester | 2358 | 1890 | 11 | PV | 211-H7XY | 2013-03-15 | 2013-10-09 | 143 | 146 | -3 | 2013-10-10 |  | -29668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-04-11 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | Y
NSTAR | Oak Bluffs | 2359 | 2557 | 260 | PV | 4-75-75 | 2013-03-18 | 2013-03-25 | 5 | 0 | 5 | 2013-03-25 | 2013-04-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-06-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | Y
NSTAR | South Boston | 2360 | 2127 | 142 | PV | 106-H1 | 2013-03-21 | 2013-04-12 | 16 | 14 | 2 | 2013-04-17 | 2013-05-28 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-11-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | New Bedford | 2361 | 2745 | 2000 | PV | 4-??-103 | 2013-01-29 | 2013-03-25 | 38 | 0 | 38 | 2013-03-25 | 2013-04-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Westwood | 2362 | 2090 | 17 | PV | 148-H3 | 2013-03-25 | 2013-03-29 | 4 | 2 | 2 | 2013-04-02 | 2013-04-24 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-30 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-06-26 | Online | [5 empty] | Private | Y
NSTAR | Weston | 2363 | 2493 | 20 | PV | 342-H1 | 2013-02-04 |  | -29496 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2013-03-27 | Private | Y
NSTAR | Dartmouth | 2364 | 2747 | 17 | PV | 2-543-543 | 2013-03-27 | 2013-04-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Detailed Study Stage |  |  |  |  | 2013-08-16 | Private | Y
NSTAR | Edgartown | 2365 | 2539 | 266 | PV | 4-97-97 | 2013-03-26 | 2013-10-03 | 132 | 133 | -1 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-04-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online | [5 empty] | Private | Y
NSTAR | Edgartown | 2366 | 2539 | 18 | PV | 4-75-123 | 2013-03-28 | 2013-04-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-07-22 | Private | Y
NSTAR | Millis | 2367 | 2054 | 500 | PV | 146-H10 | 2013-03-21 | 2013-04-10 | 14 | 5 | 9 | 2013-04-10 | 2013-04-24 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-18 |  | 2013-06-30 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 |  | Withdrawn | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2368 | 2747 | 225 | PV | 2-543-543 | 2013-04-03 | 2013-04-26 | 16 | 14 | 2 | 2013-05-01 | 2013-06-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-01 | No | Expedited |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2369 | 2740 | 500 | PV | 2-59-59 | 2013-03-26 | 2013-04-08 | 9 | 0 | 9 | 2013-04-12 | 2013-04-24 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-10-02 | Online | [5 empty] | Private | Y
NSTAR | Westport | 2370 | 2767 | 82 | PV | 2-522-522 | 2013-04-12 | 2013-04-17 | 2 | 1 | 1 | 2013-04-25 | 2013-06-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-24 |  | 2013-06-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-13 | Online | [5 empty] | Private | Y
NSTAR | Dartmouth | 2371 | 2747 | 19 | PV | 2-533-533 | 2013-04-10 | 2013-04-30 | 13 | 10 | 3 | 2013-04-30 |  | -29555 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-01 | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Freetown | 2372 | 2702 | 4999 | PV | 2-102-102 | 2013-04-12 | 2013-06-14 | 43 | 43 | 0 | 2013-06-17 | 2013-07-26 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-11-27 | 53 | 11 | 42 |  |  | 0 | 0 | 0 | 2014-03-13 |  |  | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Dedham | 2373 | 2136 | 2000 | PV | 344-1413H1 | 2013-04-19 | 2013-04-29 | 6 | 3 | 3 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-08-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online | [5 empty] | Private | Y
NSTAR | West Tisbury | 2374 | 2575 | 15 | PV | 4-97-97 | 2013-04-24 | 2013-05-01 | 5 | 3 | 2 | 2013-05-01 | 2013-06-27 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Hopkinton | 2375 | 1748 | 4000 | PV | 126-H1 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Cambridge | 2376 | 2140 | 28 | PV | 825-26 | 2013-04-30 | 2013-06-19 | 34 | 36 | -2 | 2013-06-20 | 2013-07-10 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-07-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-10-08 | Online | [5 empty] | Private | Y
NSTAR | Arlington | 2377 | 2476 | 34 | PV | 5905 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-04-23 | Online | [5 empty] | Private | Y
NSTAR | Cambridge | 2378 | 2140 | 35 | PV | 825-26 | 2013-04-30 | 2013-05-06 | 4 | 4 | 0 | 2013-05-20 | 2013-06-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-09-16 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-03-24 | Online | [5 empty] | Private | Y
NSTAR | Jamaica Plain | 2379 | 2130 | 60 | PV | 396 | 2013-05-01 | 2013-05-14 | 9 | 9 | 0 | 2013-05-16 | 2013-06-27 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  | 2013-08-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online | [5 empty] | Gov't | N
NSTAR | Boston | 2380 | 2129 | 75 | Natural Gas | 530-178 | 2013-05-01 | 2013-05-06 | 3 | 3 | 0 | 2013-05-06 | 2013-06-18 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-06-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-11-27 | Online | [5 empty] | Private | Y
NSTAR | Chilmark | 2381 | 2535 | 27 | PV | 4-97-126 | 2013-04-17 | 2013-05-08 | 15 | 5 | 10 | 2013-05-17 | 2013-06-26 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-06-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Mashpee | 2382 | 2649 | 5000 | PV | 4-88-453 | 2013-05-02 | 2013-05-31 | 20 | 19 | 1 | 2013-06-01 | 2013-07-10 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-15 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2383 | 2747 | 75 | PV | 2-532-532 | 2013-05-07 | 2013-05-16 | 7 | 6 | 1 | 2013-05-17 | 2013-06-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-07-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-25 | Online | [5 empty] | Private | Y
NSTAR | Chelsea | 2384 | 2150 | 50 | PV | 488-H7 | 2013-05-08 | 2013-05-16 | 6 | 5 | 1 | 2013-05-21 | 2013-09-05 | 73 | 0 | 73 | 2013-09-13 | 2013-09-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-17 |  | 2013-08-01 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Boston | 2385 | 2109 | 35 | PV | 3009 | 2013-05-10 | 2013-05-21 | 7 | 3 | 4 | 2013-05-23 | 2013-06-26 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | N
NSTAR | Boston | 2386 | 2210 | 75 | Natural Gas | 385-H4 | 2013-05-17 | 2013-06-10 | 15 | 15 | 0 | 2013-06-10 | 2013-07-16 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-21 |  | 2013-07-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-30 | Online | [5 empty] | Private | Y
NSTAR | Roxbury | 2387 | 2492 | 32 | PV | 483-H6 | 2013-05-20 | 2013-05-31 | 8 | 9 | -1 | 2013-05-31 | 2013-06-26 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-08-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | West Tisbury | 2388 | 2575 | 15 | PV | 4-97-97 | 2013-05-17 | 2013-05-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-09 | Online | [5 empty] | Private | Y
NSTAR | Holliston | 2389 | 1746 | 1000 | PV | 65-1325H | 2013-05-20 | 2013-07-02 | 29 | 30 | -1 | 2013-07-02 | 2013-07-10 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-06-07 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-07-09 | Online | [5 empty] | Private | Y
NSTAR | Edgartown | 2390 | 2539 | 26 | PV | 4-75-75 | 2013-05-21 | 2013-05-28 | 4 | 5 | -1 | 2013-05-28 | 2013-07-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-08 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | [5 empty] | Private | Y
NSTAR | Falmouth | 2391 | 2540 | 60 | PV | 4-76-437 | 2013-04-16 | 2013-05-22 | 26 | 23 | 3 | 2013-05-22 | 2013-06-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-08-13 | Online | [5 empty] | Private | Y
NSTAR | Chilmark | 2392 | 2535 | 23 | PV | 4-97-226 | 2013-05-24 |  | -29573 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | New Bedford | 2393 | 2746 | 1000 | PV | 2-7-34 | 2013-05-28 | 2013-06-18 | 14 | 13 | 1 | 2013-06-19 | 2013-10-29 | 91 | 1 | 90 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-30 |  | 2013-08-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Falmouth | 2394 | 2540 | 25 | PV | 4-107-830 | 2013-05-31 | 2013-06-26 | 17 | 18 | -1 | 2013-07-01 | 2013-08-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-26 |  | 2013-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online | [5 empty] | Private | Y
NSTAR | Bedford | 2395 | 1730 | 500 | PV | 391-H10 | 2013-06-04 |  | -29579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Norfolk | 2396 | 2056 | 1000 | PV | 146-H3 | 2013-06-05 | 2013-06-10 | 3 | 3 | 0 | 2013-10-01 | 2013-10-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Medway | 2397 | 2053 | 103 | PV | 65-H3 | 2013-06-05 | 2013-06-07 | 2 | 2 | 0 | 2013-10-10 | 2013-10-23 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-06 | Online | [5 empty] | Private | Y
NSTAR | Medway | 2398 | 2053 | 50 | PV | 65-H2 | 2013-06-10 |  | -29583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2013-06-10 | Private | Y
NSTAR | Acusnet | 2399 | 2743 | 750 | PV | 2-231-231 | 2013-06-10 | 2013-06-20 | 7 | 7 | 0 | 2013-06-26 | 2013-07-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-25 |  | 2013-07-20 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Walpole | 2400 | 2081 | 49 | PV | 146-H3 | 2013-06-12 | 2013-07-30 | 32 | 33 | -1 | 2013-07-30 |  | -29617 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-05-01 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Plympton | 2401 | 2364 | 4000 | PV | 3-15-901 | 2013-06-12 | 2013-08-20 | 47 | 48 | -1 | 2013-08-21 |  | -29633 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-11 | 2013-11-23 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 2014-05-09 |  | 2013-12-01 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Norfolk | 2402 | 2056 | 1000 | PV | 146-H3 | 2013-06-07 | 2013-07-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Response and/or Cost Estimates from Eng |  |  |  |  | 2013-08-26 | Gov't | Y
NSTAR | Acusnet | 2403 | 2743 | 500 | PV | 2-240-240 | 2013-06-17 | 2013-06-20 | 3 | 2 | 1 | 2013-06-24 | 2013-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2017-01-06 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2404 | 1702 | 18 | PV | 433-H12 | 2013-06-17 | 2013-06-19 | 2 | 1 | 1 | 2013-06-19 | 2013-08-13 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  | 2013-10-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-06-17 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2405 | 2740 | 100 | PV | 2-38-38 | 2013-06-18 | 2013-06-24 | 4 | 3 | 1 | 2013-06-26 | 2013-07-10 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-15 |  | 2013-08-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-11-04 | Online | [5 empty] | Private | Y
NSTAR | Cambridge | 2406 | 2140 | 40 | PV | 824-25 | 2013-06-18 | 2013-06-24 | 4 | 2 | 2 | 2013-06-24 | 2013-08-26 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-09 |  | 2013-12-15 | No | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage C&P | [5 empty] | Gov't | Y
NSTAR | Mattapoisett | 2407 | 2739 | 4500 | PV | 2-302-302 | 2013-06-19 | 2013-07-01 | 8 | 7 | 1 | 2013-07-03 | 2013-08-07 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-24 |  | 2013-08-15 | Yes | Expedited |  |  |  | 0 | 0 | 0 | [9 empty] | Private | Y
NSTAR | Framingham | 2408 | 1701 | 46 | PV | 455-H5 | 2013-06-20 | 2013-08-20 | 42 | 41 | 1 | 2013-08-20 |  | -29632 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-03 |  | 2013-09-09 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online | [5 empty] | Private | Y
NSTAR | Boston | 2409 | 2121 | 60 | PV | 323-02 | 2013-06-25 | 2013-06-27 | 2 | 2 | 0 | 2013-06-27 | 2013-08-26 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-05 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | Online | [5 empty] | Private | Y
NSTAR | Waltham | 2410 | 2451 | 750 | PV | 320-H3 | 2013-06-24 | 2013-07-01 | 5 | 2 | 3 | 2013-07-01 | 2013-08-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online | [5 empty] | Private | Y
NSTAR | Dorchester | 2411 | 2122 | 85 | PV | 511-1498H1 | 2013-06-26 | 2013-06-28 | 2 | 1 | 1 | 2013-07-02 | 2013-08-26 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Holliston | 2412 | 1746 | 2000 | PV | 130-H1 | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29560 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Bourne | 2413 | 2532 | 1680 | Wind | 4-81A-81A | 2013-07-08 | 2013-10-29 | 79 |  | 79 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs |  |  |  |  | 2013-11-18 | Private | Y
NSTAR | Newton | 2414 | 2458 | 57 | PV | 467-H5 | 2013-07-08 | 2013-10-29 | 79 | 80 | -1 | 2013-11-05 |  | -29685 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Newton | 2415 | 2458 | 62 | PV | 467-H3 | 2013-07-08 | 2013-07-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs |  |  |  |  | 2013-09-16 | Private | Y
NSTAR | Framingham | 2416 | 1702 | 1000 | PV | 455-H6 | 2013-07-09 | 2013-07-22 | 9 | 7 | 2 | 2013-07-25 |  | -29614 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29657 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-21 |  | 2013-11-30 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Sudbury | 2417 | 1776 | 980 | PV | 416-H4 | 2013-07-03 | 2013-08-20 | 33 | 28 | 5 | 2013-08-20 |  | -29632 | 0 | 0 | 2013-09-16 |  | -29650 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-05-19 | Online | [5 empty] | Private | Y
NSTAR | Boston | 2418 | 2119 | 36 | PV | 385-H1 | 2013-07-03 | 2013-08-20 | 33 | 28 | 5 | 2013-08-20 |  | -29632 | 0 | 0 | 2013-09-16 |  | -29650 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-04-24 | Online | [5 empty] | Private | Y
NSTAR | Boston | 2419 | 2119 | 50 | PV | 385-H19 | 2013-07-09 | 2013-07-12 | 3 | 1 | 2 | 2013-07-12 | 2013-08-26 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-15 |  | 2013-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-09 | Online | [5 empty] | Private | Y
NSTAR | Falmouth | 2420 | 2540 | 40 | PV | 4-76-76 | 2013-07-09 | 2013-10-02 | 60 | 58 | 2 | 2013-10-08 | 2013-12-11 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-10 |  | 2013-10-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-03-03 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2421 | 2740 | 75 | Natural Gas | 2-67-14 | 2013-07-11 | 2013-07-23 | 8 | 6 | 2 | 2013-07-24 | 2013-08-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-09-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-11-18 | Online | [5 empty] | Private | Y
NSTAR | Chilmark | 2422 | 2535 | 17 | PV | 4-97-126 | 2013-07-15 | 2013-08-12 | 20 | 18 | 2 | 2013-08-12 | 2013-09-11 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29657 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | Standard |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online | [5 empty] | Gov't | Y
NSTAR | Hyannis | 2423 | 2601 | 750 | PV | 4-84B-510 | 2013-07-22 | 2013-07-25 | 3 | 2 | 1 | 2013-07-26 |  | -29615 | 0 | 0 | 2013-09-11 | 2013-10-08 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-10 |  | 2013-10-01 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online | [5 empty] | Gov't | Y
NSTAR | Needham | 2424 | 2494 | 30 | PV | 148-H7 | 2013-07-25 |  | -29614 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Norfolk | 2425 | 2056 | 266 | PV | 146-H3 | 2013-07-29 | 2013-08-02 | 4 | 3 | 1 | 2013-08-05 |  | -29621 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-13 |  | 2013-08-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Chilmark | 2426 | 2535 | 17 | PV | 4-97-226 | 2013-08-06 |  | -29622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage | [5 empty] | Gov't | Y
NSTAR | Carver | 2427 | 2330 | 5000 | PV | 3-10-930 | 2013-08-13 | 2013-08-22 | 7 | 6 | 1 | 2013-08-22 |  | -29634 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-03 |  | 2013-10-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-09-03 | Private | Y
NSTAR | Somerville | 2428 | 2143 | 85 | PV | 250-1N35H2 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29636 | 0 | 0 | 2013-09-24 |  | -29656 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Wayland | 2429 | 1778 | 325 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29636 | 0 | 0 | 2013-09-24 | 2013-10-28 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-12-02 | Gov't | Y
NSTAR | Natick | 2430 | 1778 | 225 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Construction Stage | [5 empty] | Gov't | Y
NSTAR | Framingham | 2431 | 1701 | 250 | PV | 433-H4 | 2013-08-13 | 2013-08-30 | 13 | 11 | 2 | 2013-08-30 |  | -29640 | 0 | 0 | 2013-11-07 | 2013-11-25 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Gov't | Y
NSTAR | Framingham | 2432 | 1702 | 1364 | PV | 278-H2 | 2013-08-21 | 2013-08-30 | 7 | 6 | 1 | 2013-08-30 |  | -29640 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-15 |  | 2013-10-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Plymouth | 2433 | 2360 | 75 | PV | 3-13-943 | 2013-08-22 | 2013-08-27 | 3 | 0 | 3 | 2013-08-27 |  | -29637 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-23 |  | 2013-10-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online | [5 empty] | Private | Y
NSTAR | Walpole | 2434 | 2081 | 24 | PV | 456-H1 | 2013-09-03 | 2013-09-11 | 6 | 5 | 1 | 2013-09-11 |  | -29647 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-28 |  | 2014-06-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online | [5 empty] | Private | Y
NSTAR | Burlington | 2435 | 1803 | 232 | PV | 391-H5 | 2013-09-03 | 2013-11-22 | 56 | 57 | -1 | 2013-11-22 |  | -29697 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-12 | 2014-12-04 | 2014-06-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-12-04 | Online | [5 empty] | Private | Y
NSTAR | Natick | 2436 | 1760 | 550 | PV | 433-H10 | 2013-09-10 | 2013-09-13 | 3 | 3 | 0 | 2013-09-13 |  | -29649 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-10-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-12-06 | Online | [5 empty] | Private | Y
NSTAR | Lexington | 2437 | 2420 | 32 | PV | 391-H11 | 2013-09-10 | 2013-09-11 | 1 | 0 | 1 | 2013-09-11 |  | -29647 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-16 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-07-18 | Online | [5 empty] | Private | Y
NSTAR | Sharon | 2438 | 2067 | 185 | PV | 146-H1 | 2013-09-12 | 2013-10-30 | 33 | 33 | 0 | 2013-10-30 |  | -29681 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-02 |  | 2013-11-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2439 | 1702 | 40 | PV | 433-H8 | 2013-09-16 | 2013-10-02 | 12 | 12 | 0 | 2013-10-02 |  | -29662 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-10-21 | Awaiting Completion Docs |  |  |  |  | 2013-12-09 | Private | Y
NSTAR | Cotuit | 2440 | 2635 | 30 | PV | 4-71-455 | 2013-09-18 | 2013-09-20 | 2 | 2 | 0 | 2013-09-20 |  | -29654 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-13 | Online | [5 empty] | Private | Y
NSTAR | Waltham | 2441 | 2451 | 60 | PV | 282-H1 | 2013-09-16 | 2013-09-20 | 4 | 1 | 3 | 2013-09-20 |  | -29654 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | [5 empty] | Private | Y
NSTAR | Lexington | 2442 | 2421 | 46 | PV | 3402 | 2013-09-19 | 2013-10-24 | 24 | 24 | 0 | 2013-10-24 |  | -29677 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-07 |  | 2013-12-15 | No | Expedited |  |  |  | 0 | 0 | 0 | 2014-04-08 | 2014-04-08 | 2014-04-08 | Online | [5 empty] | Private | Y
NSTAR | Framingham | 2443 | 1701 | 75 | Natural Gas | 342-H4 | 2013-09-20 | 2013-09-30 | 6 | 4 | 2 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-29 | Online | [5 empty] | Private | Y
NSTAR | Brookline | 2444 | 2446 | 46 | PV | 329-H7 | 2013-09-23 | 2013-10-01 | 6 | 5 | 1 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online | [5 empty] | Private | Y
NSTAR | Sherborn | 2445 | 1770 | 19 | PV | 130-H2 | 2013-09-23 | 2013-09-30 | 5 | 2 | 3 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2014-06-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2446 | 2747 | 383 | PV | 2-531-530 | 2013-09-23 | 2013-09-27 | 4 | 1 | 3 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-10-10 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online | [5 empty] | Private | Y
NSTAR | Assonett | 2447 | 2702 | 10 | PV | 2-605-605 | 2013-10-02 | 2013-10-07 | 3 | 0 | 3 | 2013-10-10 |  | -29668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-10-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-19 | Online | [5 empty] | Private | Y
NSTAR | Plympton | 2448 | 2367 | 24 | PV | 3-51-901 | 2013-10-04 | 2013-10-10 | 4 | 2 | 2 | 2013-10-11 |  | -29669 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-01 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Westwood | 2449 | 2090 | 20 | PV | 456-H1 | 2013-10-09 | 2013-10-15 | 3 | 2 | 1 | 2013-10-17 |  | -29672 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-11-22 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online | [5 empty] | Private | Y
NSTAR | Woburn | 2450 | 1801 | 50 | PV | 211-H2 | 2013-10-09 | 2013-10-16 | 4 | 3 | 1 | 2013-10-18 |  | -29673 | 0 | 0 | 2013-12-02 |  | -29702 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-13 |  | 2013-11-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-04-04 | Online | [5 empty] | Private | Y
NSTAR | Cambridge | 2451 | 2138 | 70 | PV | 827-31 | 2013-10-15 | 2013-10-23 | 6 | 5 | 1 | 2013-10-23 |  | -29676 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  | 2013-11-29 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-03-11 | Online | [5 empty] | Private | Y
NSTAR | Dover | 2452 | 2030 | 20 | PV | 456-H3 | 2013-10-15 | 2013-10-21 | 4 | 3 | 1 | 2013-10-21 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | Y
NSTAR | Westport | 2453 | 2790 | 100 | PV | 2-532-532 | 2013-10-16 | 2013-10-18 | 2 | 0 | 2 | 2013-10-21 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-12-15 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-14 | Online | [5 empty] | Private | Y
NSTAR | North Dartmouth | 2454 | 2747 | 25 | PV | 2-531-531 | 2013-10-18 | 2013-11-01 | 10 | 10 | 0 | 2013-11-01 |  | -29683 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2013-12-31 | Online | [5 empty] | Private | Y
NSTAR | East Falmouth | 2455 | 2536 | 85 | PV | 4-77A-450 | 2013-10-17 |  | -29672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2013-10-18 | Private | Y
NSTAR | East Falmouth | 2456 | 2536 | 90 | PV | 4-98A-98A | 2013-10-18 | 2013-10-24 | 4 | 3 | 1 | 2013-12-16 |  | -29712 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-11-30 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | Y
NSTAR | Kingston | 2457 | 2364 | 19 | PV | 3-17-910 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29679 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | [5 empty] | Private | Y
NSTAR | Hopkinton | 2458 | 1748 | 85 | PV | 126-H1 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29679 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online | [5 empty] | Private | Y
NSTAR | Hopkinton | 2459 | 1748 | 18 | PV | 126-H1 | 2013-10-21 | 2013-11-01 | 9 | 9 | 0 | 2013-11-01 |  | -29683 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-12-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs |  |  |  |  | 2013-12-04 | Private | Y
NSTAR | Canton | 2460 | 2021 | 60 | PV | 269-1320H1 | 2013-10-24 |  | -29677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2013-10-24 | Private | Y
NSTAR | Sudbury | 2461 | 1778 | 225 | PV | 342-H3 | 2013-10-28 | 2013-11-13 | 11 | 12 | -1 | 2013-11-13 |  | -29690 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-05-14 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 2014-06-09 |  | 2014-04-01 | Yes | Standard |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Dedham | 2462 | 2026 | 1750 | PV | 20-H2, 20-H3 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Mattapoisett | 2463 | 2739 | 4000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage | [5 empty] | Private | Y
NSTAR | Mattapoisett | 2464 | 2739 | 1000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage | [5 empty] | Private | Y
NSTAR | Mattapoisett | 2465 | 2739 | 1000 | PV | 2-302-302 | 2013-10-30 | 2013-11-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | Y
NSTAR | Dorchester | 2466 | 2121 | 27 | PV | 483-H3 | 2013-10-29 | 2013-11-18 | 13 | 12 | 1 | 2013-11-19 |  | -29694 | 0 | 0 | 2013-12-05 | 2014-01-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-28 |  | 2013-12-23 | Yes | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-06-25 | Online | [5 empty] | Private | Y
NSTAR | Charlestown | 2467 | 2129 | 11 | PV | 10-H2 | 2013-11-08 | 2013-11-14 | 3 | 1 | 2 | 2013-11-15 |  | -29692 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-19 |  | 2013-12-25 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-02-14 | Online | [5 empty] | Private | Y
NSTAR | Chilmark | 2468 | 2535 | 42 | PV | 4-91-220 | 2014-11-18 | 2015-01-02 | 31 | 0 | 31 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2016-03-11 | 2015-06-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 1972361 | 2571 | 5000 | PV | 3-83-83 | 2013-11-25 | 2013-12-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2015-12-29 | 2016-04-19 | Online | [5 empty] | Gov't
NSTAR | Carver | 1972386 | 2330 | 5000 | PV | 3-83-83 | 2013-12-02 | 2013-12-03 | 1 | 0 | 1 | 2013-12-05 | 2013-12-27 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2014-07-10 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wayland | 1973375 | 1778 | 200 | PV | 342-H3 | 2013-12-10 | 2013-12-10 | 0 | 0 | 0 | 2013-12-11 | 2013-12-19 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-27 | 2013-12-31 | 2014-07-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2013-12-27 |  | Withdrawn | [5 empty] | Private
NSTAR | East Boston | 1976430 | 2128 | 100 | PV | 488-H4 | 2013-12-11 | 2013-12-12 | 1 | 0 | 1 | 2013-12-17 | 2015-03-10 | 306 | 3 | 303 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-21 | No | Standard | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Woburn | 1976701 | 1801 | 1000 | PV | 375-H14 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-10-15 | 204 | 297 | -93 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-03 | 2015-05-20 | 2015-09-27 | No | Expedited | 30 | 2014-10-14 | 2014-10-14 | 0 |  | 0 |  | 2015-10-20 |  | Withdrawn | [5 empty] | Gov't
NSTAR | Plymouth | 1977739 | 2360 | 600 | PV | 3-13-943 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-01-15 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | 2014-07-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-01-02 | 2015-10-21 | Online | [5 empty] | GOV'T
NSTAR | Burlington | 1977755 | 1803 | 500 | PV | 391-H12 | 2013-12-19 | 2013-12-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Provincetown | 1978458 | 2657 | 20 | PV | 4-96-676 | 2013-12-23 | 2013-12-24 | 1 | 0 | 1 | 2013-12-31 | 2016-06-08 | 623 | 604 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-31 | TBD |  | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Mattapoisett | 1978822 | 2739 | 750 | PV | 2-301-301 | 2014-01-02 | 2014-01-02 | 0 | 106 | 0 | 2014-01-03 | 2015-01-07 | 251 | 139 | 112 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Waltham | 1980806 | 2451 | 1000 | PV | 526-1361H | 2014-01-03 | 2014-01-03 | 0 | 0 | 0 | 2014-02-04 | 2014-02-04 | 0 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-31 | 2014-06-05 | 2014-09-30 | No | Expedited | 30 | 2014-09-04 | 2014-09-04 | 0 |  | 0 |  | 2014-09-25 |  | Withdrawn | [5 empty] | Gov't
NSTAR | Chilmark | 1981127 | 2535 | 95 | PV | 4-97-126 | 2014-01-08 | 2014-01-08 | 0 | 0 | 0 | 2014-01-14 | 2014-02-05 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-10 |  | 2014-08-14 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online | [5 empty] | Private
NSTAR | Hatchville | 1982667 | 2536 | 48 | PV | 4-98B-448 | 2014-01-09 | 2014-01-09 | 0 | 0 | 0 | 2014-01-15 | 2014-02-05 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-16 |  | 2014-09-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-05-16 | 2014-05-16 | Online | [5 empty] | Private
NSTAR | Brighton | 1982906 | 2135 | 75 | Natural Gas | 467-H13 | 2014-01-16 | 2014-01-16 | 0 | 0 | 0 | 2014-01-24 | 2014-02-07 | 10 | 0 | 10 | 2014-02-20 | 2014-03-24 | 21 | 0 | 21 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-27 | 2014-04-17 | 2014-08-22 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Marshfield | 1984064 | 2050 | 18.5 | PV | 3-25-976 | 2014-01-20 | 2014-01-21 | 1 | 0 | 1 | 2014-01-20 | 2014-01-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-08-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wayland | 1984570 | 1778 | 225 | PV | 342-H3 | 2014-01-21 | 2014-04-30 | 68 | 0 | 68 | 2014-01-24 | 2014-02-14 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 | 2014-05-13 | 2014-08-26 | TBD | Expedited | 30 | 2014-05-16 | 2014-05-16 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acusnet | 1984711 | 2743 | 40 | PV | 2-241-241 | 2014-01-27 | 2014-05-06 | 68 | 0 | 68 | 2014-06-25 | 2014-08-22 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2014-09-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-26 | Online | [5 empty] | Private
NSTAR | Falmouth | 1985442 | 2536 | 90 | PV | 4-98A-98A | 2014-01-28 | 2014-01-30 | 2 | 0 | 2 | 2014-01-30 | 2014-02-05 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-09-03 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Framingham | 1985681 | 1702 | 27.6 | PV | 240-H4 | 2014-01-30 | 2014-01-30 | 0 | 0 | 0 | 2014-02-05 | 2014-02-26 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-20 | 2014-08-25 | 2014-09-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-08-22 | 2014-08-22 | Online | [5 empty] | Private
NSTAR | Dartmouth | 1986041 | 2748 | 21 | PV | 2-524-524 | 2014-02-10 | 2014-05-16 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-08-19 | Online | [5 empty] | Private
NSTAR | Harwich | 1987679 | 2671 | 23 | PV | 4-92B-572 | 2014-02-10 | 2014-02-11 | 1 | 0 | 1 | 2014-02-11 | 2014-02-28 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-13 | 2014-04-15 | 2014-09-16 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-29 | Online | [5 empty] | Private | Y
NSTAR | Bellingham | 1987709 | 2019 | 52.5 | PV | 65-H4 | 2014-02-12 | 2014-02-14 | 2 | 0 | 2 | 2014-02-14 | 2014-03-06 | 13 | 28 | -15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-29 |  | 2014-09-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-07-18 | Online | [5 empty] | Private
NSTAR | Plymouth | 1988060 | 2360 | 38 | PV | 3-12-41J1 | 2014-02-18 | 2014-07-10 | 97 | 0 | 97 | 2014-02-19 | 2014-04-07 | 32 | 1 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-04 | 2016-01-05 | 2016-10-07 | Yes | Expedited | 30 | 2016-07-22 |  | -30377 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private | N
NSTAR | Plympton | 1988677 | 2367 | 840 | PV | 3-15-906 | 2014-01-30 | 2014-02-20 | 14 | 0 | 14 | 2014-03-07 | 2014-03-12 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-09-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-12-19 | Online | [5 empty] | Private
NSTAR | Ashland | 1988954 | 1721 | 80 | PV | 274-1429H1 | 2014-02-05 | 2014-02-24 | 12 | 0 | 12 | 2014-02-28 | 2014-02-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-11 |  | 2014-09-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-09-11 | Online | [5 empty] | Private | N
NSTAR | Lexington | 1989453 | 2421 | 25.9 | PV | 533-H1 | 2014-02-11 | 2014-02-26 | 10 | 0 | 10 | 2014-03-14 | 2014-03-20 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-04-11 | 2014-08-07 | 80 | 7 | 73 | 2015-05-04 | 2015-05-07 | 3 | 0 | 3 | 2014-08-04 | 2015-05-11 | 2015-11-30 | No | Standard | 60 | 2015-09-30 | 2015-09-30 | 0 |  | 0 |  | 2016-03-01 | 2016-03-01 | Online | [5 empty] | Private | N
NSTAR | Needham | 1989732 | 2492 | 3120 | PV | 148-H1 | 2014-02-14 | 2014-02-28 | 9 | 0 | 9 | 2014-03-04 | 2014-03-12 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-10-03 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-23 | Online | [5 empty] | Gov't | Y
NSTAR | Wayland | 1989963 | 1778 | 20 | PV | 342-H1 | 2014-02-28 | 2014-09-20 | 139 | 0 | 139 | 2014-03-05 | 2014-04-03 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-11-03 | 2015-06-05 | 151 | 9 | 142 | 2015-11-16 | 2015-11-25 | 7 | 0 | 7 | 2015-03-04 | 2016-04-20 | 2016-11-01 | No | Standard | 60 | 2016-05-27 |  | -30337 |  | 0 |  |  |  | Online | [5 empty] | PRIVATE | N
NSTAR | Hyde Park | 1990011 | 2136 | 3190 | PV | 496-H2 | 2014-02-28 | 2014-03-06 | 4 | 0 | 4 | 2014-03-10 | 2014-04-29 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 |  | 2014-10-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-28 | Online | [5 empty] | Gov't | Y
NSTAR | Wareham | 1991204 | 2538 | 100 | PV | 3-84-961 | 2014-03-14 | 2014-03-14 | 0 | 0 | 0 | 2014-03-20 | 2014-03-31 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-28 | 2014-05-05 | 2015-01-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-05-01 | 2015-05-01 | Online | [5 empty] | Private
NSTAR | Roxbury | 1992441 | 2120 | 75 | Natural Gas | 5201 | 2014-03-18 | 2014-10-08 | 141 |  | 141 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-05-20 | Private
NSTAR | Mattapoisett | 1992844 | 2739 | 2000 | PV | 2-301-301 | 2014-03-18 | 2014-10-10 | 143 |  | 143 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-27 | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-03-12 | Private
NSTAR | Mattapoisett | 1992854 | 2739 | 2000 | PV | 2-306-306 | 2014-03-18 | 2014-11-07 | 162 |  | 162 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-05-20 | Private
NSTAR | Mattapoisett | 1992858 | 2739 | 1000 | PV | 2-306-306 | 2014-03-25 |  | -29778 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Jamaica Plain | 1994005 | 2130 | 34.2 | PV | 284-1300H1 | 2014-03-26 | 2014-04-01 | 4 | 0 | 4 | 2014-04-01 | 2014-04-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-15 | 2014-11-03 | 2014-10-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online | [5 empty] | Private | N
NSTAR | Cambridge | 1994170 | 2142 | 75 | Natural Gas | 875-1328 | 2014-01-22 | 2014-03-27 | 44 | 0 | 44 | 2014-03-31 | 2014-04-02 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-15 | 2014-09-03 | 2014-10-31 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online | [5 empty] | Private
NSTAR | Waltham | 1994357 | 2453 | 75 | Natural Gas | 33-H1 | 2014-04-20 | 2014-04-22 | 1 | 0 | 1 | 2014-05-12 | 2014-05-23 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-29 |  | 2014-11-28 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-02-18 |  | Withdrawn | [5 empty] | Gov't
NSTAR | Natick | 1998808 | 1760 | 150 | Natural Gas | 23-1339H1 | 2014-04-29 | 2014-04-30 | 1 | 0 | 1 | 2014-05-13 | 2014-08-20 | 68 | 64 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-19 | 2016-03-11 | 2014-12-05 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2000080 | 2458 | 100 | PV | 467-H3 | 2014-03-20 | 2014-03-27 | 5 | 0 | 5 | 2014-05-06 | 2014-05-08 | 2 | 0 | 2 | 2014-05-13 | 2014-05-28 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2017-10-31 | No | Standard | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Walpole | 2000815 | 2071 | 3450 | PV | 146-H3 | 2014-03-13 | 2014-03-13 | 0 |  | 0 | 2014-03-13 |  | -29771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-01 | 2015-09-01 | [6 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online
NSTAR | Natick | 2001305 | 1760 | 580 | PV | 433-H10 | 2014-05-05 | 2014-05-06 | 1 | 0 | 1 | 2014-05-07 | 2014-09-23 | 95 | 131 | -36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-29 | 2014-12-11 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-06-03 | Online | [5 empty] | Private
NSTAR | Natick | 2001314 | 1760 | 620 | PV | 433-H9 | 2014-03-24 | 2014-05-05 | 29 | 0 | 29 | 2014-05-07 | 2014-11-26 | 139 | 132 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-30 | 2014-12-11 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-12-28 | 2016-06-03 | Online | [5 empty] | Private
NSTAR | Natick | 2001342 | 1760 | 520 | PV | 433-H10 | 2014-01-30 | 2014-03-27 | 38 | 0 | 38 | 2014-05-14 | 2014-06-25 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 |  | 2014-12-17 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-10-24 | 2015-12-28 | Online | [5 empty] | Private | Y
NSTAR | Pocasset | 2002111 | 2559 | 248.4 | PV | 4-86-86 | 2014-02-05 | 2014-04-22 | 51 | 0 | 51 | 2014-05-16 | 2014-05-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-20 | 2014-08-14 | 2014-12-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-10-23 | Online | [5 empty] | Private
NSTAR | Marshfield | 2002502 | 2050 | 9 | PV | 3-24B-915 | 2014-02-14 | 2014-05-02 | 52 | 0 | 52 | 2014-05-19 | 2014-05-28 | 6 | 7 | -1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-30 |  | 2014-12-19 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | West Tisbury | 2002682 | 2575 | 204 | PV | 4-97-220 | 2014-05-14 | 2014-05-15 | 1 | 0 | 1 | 2014-06-18 | 2015-06-15 | 252 | 243 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-05-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Cambridge | 2002879 | 2139 | 802 | PV | 817-05 | 2014-05-15 | 2014-05-16 | 1 | 0 | 1 | 2014-05-19 | 2014-06-10 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-07-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2003173 | 2745 | 810 | Natural Gas | 2-107-107 | 2014-03-10 | 2014-05-12 | 43 | 0 | 43 | 2014-06-06 | 2014-06-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-19 | 2014-08-11 | 2015-01-05 | TBD | Expedited | 30 | 2014-10-01 | 2014-10-01 | 0 |  | 0 |  |  | 2014-10-10 | Online | [5 empty] | Private
NSTAR | Chatham | 2004834 | 2659 | 44 | PV | 4-95A-95A | 2014-03-20 | 2014-05-13 | 37 | 0 | 37 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-10 | 2014-11-19 | 2015-06-30 | TBD | Expedited | 30 | 2015-07-17 | 2015-07-17 | 0 |  | 0 |  |  | 2015-07-28 | Online | [5 empty] | Private
NSTAR | Edgartown | 2005414 | 2539 | 80 | PV | 4-75-123 | 2014-05-30 | 2015-05-07 | 237 | 0 | 237 | 2014-06-05 | 2014-12-29 | 140 | 148 | -8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2015-01-08 | No | Standard | 60 |  |  | 0 |  | 0 |  | 2016-06-23 | 2016-06-30 | Online | [5 empty] | Private | N
NSTAR | Jamaica Plain | 2005440 | 2130 | 1640 | Natural Gas | 496-H4 | 2014-05-30 | 2015-05-16 | 243 | 0 | 243 | 2014-06-05 | 2015-01-19 | 155 | 148 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-01-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-06-30 | Online
NSTAR | New Bedford | 2005461 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-05-14 | 2014-06-03 | 13 | 0 | 13 | 2014-06-06 | 2014-06-10 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 | 2014-09-12 | 2015-01-12 | TBD | Expedited | 30 | 2014-10-09 | 2014-10-09 | 0 |  | 0 |  | 2014-11-05 | 2014-11-18 | Withdrawn | [5 empty] | Private
NSTAR | Framingham | 2006363 | 1702 | 120 | PV | 274-H4 | 2014-05-16 | 2014-06-03 | 11 | 0 | 11 | 2014-06-06 | 2014-07-01 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 |  | 2015-01-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-11-21 | Online | [5 empty] | Private
NSTAR | Boston | 2006387 | 2109 | 45 | PV | 3009 | 2014-05-19 | 2014-06-05 | 12 | 0 | 12 | 2014-06-12 | 2014-10-23 | 91 | 45 | 46 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-01-14 | No | Expedited | 30 | 2015-01-12 | 2015-01-12 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | East Boston | 2006940 | 2128 | 750 | PV | 108-196H1 | 2014-06-06 | 2014-06-09 | 1 | 0 | 1 | 2014-06-11 | 2014-06-30 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 |  | 2015-01-16 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Dover | 2007317 | 2030 | 20.2 | PV | 456-H5 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 | 2014-06-11 | 2014-06-23 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-25 | 2014-10-01 | 2015-01-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online | [5 empty] | Private
NSTAR | Chatham | 2007346 | 2659 | 50 | PV | 4-95A-95A | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-06-17 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-18 | 2014-10-01 | 2015-01-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online | [5 empty] | Private
NSTAR | Edgartown | 2007907 | 2539 | 18.7 | PV | 4-75-123 | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-10-07 | 79 | 46 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | 55 | 0 | 55 | 2015-08-31 | 2015-10-13 | 31 | 0 | 31 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | Standard | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online | [5 empty] | Private | N
NSTAR | Canton | 2007950 | 2021 | 980 | PV | 470-H7 | 2014-06-11 | 2014-06-11 | 0 | 0 | 0 | 2014-06-13 | 2014-10-07 | 79 | 46 | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | 55 | 0 | 55 | 2015-08-31 | 2015-10-13 | 31 | 0 | 31 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | Standard | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online | [5 empty] | Private | N
NSTAR | Holliston | 2008170 | 1746 | 17 | PV | 274-H5 | 2014-06-11 | 2014-06-12 | 1 | 0 | 1 | 2014-06-16 | 2014-07-07 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 | 2014-09-22 | 2014-09-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Stoneham | 2008179 | 2180 | 15.9 | PV | 375-H8 | 2014-06-11 | 2014-06-17 | 3 | 0 | 3 | 2014-06-20 | 2014-09-10 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-11 | 2014-09-11 | 2015-01-26 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-11 | Online | [5 empty] | Private | N
NSTAR | Plymouth | 2009028 | 2360 | 20 | PV | 3-89-926 | 2014-06-13 | 2014-06-17 | 1 | 0 | 1 | 2014-06-20 | 2014-08-15 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2015-01-26 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-10-09 | 2014-11-17 | Online | [5 empty] | Private
NSTAR | Wareham | 2009038 | 2576 | 18 | PV | 3-85-85 | 2014-06-13 | 2014-06-18 | 2 | 0 | 2 | 2014-06-27 | 2014-07-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 | 2014-09-03 | 2015-01-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-02-04 | 2016-02-04 | Online | [5 empty] | Private
NSTAR | Boston | 2009215 | 2118 | 75 | Natural Gas | 385-H17 | 2014-06-16 | 2014-06-20 | 3 | 0 | 3 | 2014-06-26 | 2014-07-08 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online | [5 empty] | Gov't
NSTAR | Lexington | 2009595 | 2421 | 388 | PV | 320-H5XY | 2014-06-16 | 2014-06-20 | 3 | 0 | 3 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online | [5 empty] | Gov't | N
NSTAR | Lexington | 2009605 | 2420 | 135 | PV | 391-H11 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online | [5 empty] | Gov't
NSTAR | Lexington | 2009611 | 2420 | 135 | PV | 533-H3 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-27 | 2014-06-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-02 | 2014-12-10 | Online | [5 empty] | Private
NSTAR | Lexington | 2009615 | 2421 | 79 | PV | 320-H5XY | 2014-06-20 | 2014-06-27 | 5 | 0 | 5 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-16 | 2015-01-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online | [5 empty] | Private
NSTAR | Lexington | 2009625 | 2421 | 171 | PV | 320-H5XY | 2014-06-20 | 2014-06-26 | 4 | 0 | 4 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-23 | Online | [5 empty] | Private
NSTAR | Lexington | 2009631 | 2420 | 40 | PV | 3403 | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-02 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-03 | 2014-10-01 | 2015-01-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-02-19 | Online | [5 empty] | Private
NSTAR | Chatham | 2009828 | 2659 | 60 | PV | 4-95A-95A | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-24 |  | 2015-01-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-03-31 | 2015-04-08 | Online | [5 empty] | Private
NSTAR | Waltham | 2009878 | 2451 | 675 | PV | 531-1359H | 2014-06-24 | 2014-06-24 | 0 | 0 | 0 | 2014-07-01 | 2014-07-29 | 19 | 308 | -289 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | East Boston | 2010040 | 2128 | 552 | PV | 108-196H1 | 2014-06-26 | 2014-07-01 | 3 | 0 | 3 | 2014-07-03 | 2014-07-08 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-08 | 2014-10-06 | 2015-02-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2011256 | 2576 | 42 | PV | 3-86-966 | 2014-06-26 | 2014-07-03 | 5 | 0 | 5 | 2014-08-04 | 2014-10-06 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 | 2015-02-05 | 2015-10-01 | TBD | Expedited | 30 | 2015-01-30 |  | -29992 |  | 0 |  | 2015-09-23 |  | Withdrawn | [5 empty] | Gov't
NSTAR | Framingham | 2012062 | 1701 | 500 | PV | 278-H2 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-06 | 2015-03-02 | 2015-02-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-03-02 | 2015-09-21 | Online | [5 empty] | Gov't
NSTAR | Falmouth | 2012720 | 2540 | 47.8 | PV | 4-107-830 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-16 |  | 2015-02-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hyannis | 2012789 | 2601 | 252 | PV | 4-84B-524 | 2014-07-03 | 2014-07-10 | 4 | 0 | 4 | 2014-07-16 | 2014-08-25 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 | 2014-09-03 | 2015-02-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-31 |  | Withdrawn | [5 empty] | Private
NSTAR | Allston | 2012919 | 2134 | 90 | PV | 548-92H3 | 2014-07-15 | 2014-07-22 | 5 | 0 | 5 | 2014-08-04 | 2014-07-29 | -6 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 | 2014-10-27 | 2015-02-23 | No | Expedited | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2014-12-19 | 2015-01-02 | Online | [5 empty] | Private | N
NSTAR | Acton | 2013623 | 1720 | 126 | PV | 416-H9 | 2014-07-18 | 2014-07-22 | 2 | 0 | 2 | 2014-07-28 | 2014-07-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-08-10 | Online | [5 empty] | Private
NSTAR | Acton | 2014462 | 1720 | 81 | PV | 416-H1 | 2014-07-23 | 2014-07-28 | 3 | 0 | 3 | 2014-08-19 | 2014-10-01 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 |  | 2015-10-01 | TBD | Expedited | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2015-09-17 | 2015-09-17 | Online | [5 empty] | Gov't
NSTAR | Framingham | 2015313 | 1701 | 500 | PV | 433-H11 | 2014-07-22 | 2014-07-23 | 1 | 0 | 1 | 2014-07-25 | 2014-08-05 | 7 | 73 | -66 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2015-01-27 | 2015-06-19 | No | Expedited | 30 | 2015-05-27 | 2015-05-27 | 0 |  | 0 |  | 2015-06-16 | 2015-07-08 | Online | [5 empty] | Private
NSTAR | Holliston | 2015374 | 1746 | 300 | PV | 65-H7 | 2014-07-24 | 2014-08-19 | 18 | 0 | 18 | 2014-08-04 | 2014-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-17 | 2014-11-03 | 2015-03-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-07-08 | Online | [5 empty] | Private
NSTAR | Dorchester | 2015660 | 2122 | 89 | PV | 6702 | 2014-07-30 | 2014-08-01 | 2 | 0 | 2 | 2014-08-05 | 2014-08-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-09-29 | 2015-04-17 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 2015-03-10 | No | Standard | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2016902 | 2770 | 2000 | PV | 3-703-703 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | 2014-08-11 | 2014-12-02 | 77 | 60 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-17 | 2015-09-08 | 2016-03-15 | No | Expedited | 30 | 2016-01-28 | 2016-01-28 | 0 |  | 0 |  | 2016-04-14 |  | Withdrawn | [5 empty] | Private | N
NSTAR | Charlestown | 2017443 | 2129 | 391 | PV | 10-H1 | 2014-08-05 | 2014-08-11 | 4 | 0 | 4 | 2014-08-15 | 2014-11-21 | 67 | 34 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-04-11 | 2016-04-14 | 3 | 0 | 3 | 2015-03-26 | 2016-07-28 | 2016-12-15 | No | Standard | 60 |  |  | 0 |  | 0 |  |  |  | Field Com | [5 empty] | Private | N
NSTAR | Hopkinton | 2017615 | 1748 | 342 | PV | 126-H4 | 2014-08-06 | 2014-08-15 | 7 | 0 | 7 | 2014-09-24 |  | -29904 |  | 0 |  |  | 0 | 0 | 0 | 2014-08-15 | 2014-10-04 | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-23 |  | 2015-03-17 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2017870 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-08-07 | 2014-08-15 | 6 | 0 | 6 | 2014-09-24 | 2014-09-24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-30 | 2014-10-06 | 2015-03-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online | [5 empty] | Private | N
NSTAR | Kingston | 2018246 | 2364 | 142.5 | PV | 3-15-15 | 2014-08-11 | 2014-08-15 | 4 | 0 | 4 | 2014-09-24 | 2014-10-02 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-10 |  | 2015-03-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-08-17 | 2015-08-18 | Online | [5 empty] | PRIVATE
NSTAR | East Walpole | 2018681 | 2032 | 325.6 | PV | 135-1301 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-15 | 2014-08-28 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 |  | 2015-03-23 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-08-13 | Online | [5 empty] | Private | N
NSTAR | South Walpole | 2018960 | 2071 | 85 | PV | 146-H3 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-19 | 2014-09-09 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-03 |  | 2015-03-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-20 | Online | [5 empty] | Private
NSTAR | Plymouth | 2018969 | 2360 | 50 | PV | 4-81A-406 | 2014-08-19 | 2014-08-19 | 0 | 0 | 0 | 2014-08-21 | 2014-09-08 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-16 | 2015-03-02 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2015-03-30 | Online | [5 empty] | Private
NSTAR | Dover | 2019996 | 2030 | 21.2 | PV | 456-H5 | 2014-08-19 | 2014-08-20 | 1 | 0 | 1 | 2014-08-20 | 2014-09-26 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2016-08-18 | 2015-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee | [5 empty] | Gov't
NSTAR | Truro | 2020127 | 2666 | 1000 | PV | 4-96-96 | 2014-08-20 | 2014-08-25 | 3 | 0 | 3 | 2014-08-25 |  | -29883 |  | 0 |  |  | 0 | 0 | 0 | 2014-10-21 | 2015-01-09 | 55 | 120 | -65 | 2015-07-02 | 2015-07-10 | 6 | 3 | 3 | 2016-03-10 | 2016-03-31 | 15 | 0 | 15 | 2015-07-08 | 2016-04-25 | 2016-12-02 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Kingston | 2020238 | 2364 | 668 | PV | 3-909-909 | 2014-08-21 | 2014-08-25 | 2 | 0 | 2 | 2014-08-25 | 2014-09-15 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 | 2015-07-15 | 2015-04-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-08 | Online | [5 empty] | Private
NSTAR | Plymouth | 2020496 | 2360 | 92.8 | PV | 3-14-911 | 2014-08-25 | 2014-08-28 | 3 | 0 | 3 | 2014-08-28 | 2014-11-10 | 50 | 16 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-17 |  | 2015-04-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2015-01-02 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2020964 | 2747 | 232 | PV | 2-532-532 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-09-17 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-25 | 2014-10-31 | 2014-12-15 | TBD | Expedited | 30 | 2014-12-12 | 2014-12-12 | 0 |  | 0 |  |  | 2014-12-17 | Online | [5 empty] | Private
NSTAR | Holliston | 2021069 | 1746 | 185 | PV | 65-H2 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-10-15 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 | 2014-12-05 | 2014-12-31 | No | Expedited | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  | 2015-02-18 | 2015-02-27 | Online | [5 empty] | Private
NSTAR | Holliston | 2021094 | 1746 | 500 | PV | 65-H2 | 2014-08-27 | 2014-08-28 | 1 | 0 | 1 | 2014-09-04 | 2014-10-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 |  | 2017-01-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online | [5 empty] | Private
NSTAR | Plymouth | 2021322 | 2360 | 500 | PV | 3-12-12 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-04 | 2015-01-30 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-05 |  | 2015-04-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wianno | 2022522 | 2655 | 32.8 | PV | 4-80A-892 | 2014-09-04 | 2014-09-04 | 0 | 0 | 0 | 2015-02-13 | 2015-04-01 | 33 | 107 | -74 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-04-14 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-10-06 |  | Withdrawn | [5 empty] | Private
NSTAR | Canton | 2022843 | 2021 | 300 | PV | 470-H7 | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-22 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 | 2014-10-02 | 2015-04-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-06 | Online | [5 empty] | Private
NSTAR | Canton | 2022875 | 2021 | 170 | PV | 470-H8 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-09 | 2014-09-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-26 | 2014-09-29 | 2015-04-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-19 | Online | [5 empty] | Private
NSTAR | Dennis | 2022973 | 2660 | 75 | PV | 4-92B-92B | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-29 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-29 | 2014-10-06 | 2015-04-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online | [5 empty] | Private
NSTAR | Kingston | 2023232 | 2364 | 21.5 | PV | 3-15-15 | 2014-09-18 |  | -29900 | 0 | 0 | 2014-09-10 | 2014-10-01 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 |  | 2015-04-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-23 | 2014-12-31 | Online | [5 empty] | Private
NSTAR | Wareham | 2023726 | 2571 | 324.8 | PV | 3-86-966 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | 2014-09-18 | 2014-10-10 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-08 |  | 2015-04-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2014-12-23 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2024047 | 2747 | 301.6 | PV | 2-531-531 | 2014-09-11 | 2014-09-12 | 1 | 0 | 1 | 2014-09-19 | 2015-01-16 | 81 | 53 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-04-22 | TBD | Standard | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2024196 | 2571 | 2000 | PV | 3-84-84 | 2014-08-13 | 2014-09-16 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hatchville | 2024739 | 2536 | 3000 | PV | 4-98A-98A | 2014-09-16 |  | -29898 | 0 | 0 | 2014-09-18 | 2014-10-01 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2015-04-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-01-21 | 2017-04-06 | Online | [5 empty] | Gov't
NSTAR | Natick | 2024912 | 1760 | 264 | PV | 433-H9 | 2014-08-27 | 2014-09-15 | 12 | 0 | 12 | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-02 | 2015-04-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-21 | Online | [5 empty] | Private
NSTAR | Dorchester | 2025617 | 2122 | 56 | PV | 466-1482H1 | 2014-09-18 | 2014-09-18 | 0 | 0 | 0 | 2014-09-22 | 2014-10-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-16 | 2014-10-17 | 2015-04-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online | [5 empty] | Private
NSTAR | Canton | 2025700 | 2021 | 85 | PV | 470-H11 | 2014-09-19 | 2014-09-20 | -1 | 0 | 0 | 2014-09-22 | 2014-10-20 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-20 |  | 2015-04-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Bourne | 2025848 | 2532 | 499 | PV | 3-89-925 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | 2014-09-30 | 2014-11-10 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-05-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-03-30 |  | Withdrawn | [5 empty] | Private
NSTAR | Burlington | 2026226 | 1803 | 500 | PV | 391-H9 | 2014-09-25 | 2014-09-25 | 0 | 0 | 0 | 2014-09-29 | 2015-07-21 | 207 | 195 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2015-11-18 | 2016-06-16 | No | Expedited | 30 | 2016-05-16 | 2016-05-16 | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Norfolk | 2026963 | 2056 | 499 | PV | 146-H3 | 2014-09-25 | 2014-09-26 | 1 | 0 | 1 | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-05-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-28 | Online | [5 empty] | Private
NSTAR | Lexington | 2027027 | 2420 | 15 | PV | 391-H3 | 2014-09-26 | 2014-09-27 | -1 | 0 | 0 | 2014-09-30 | 2014-10-21 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Somerville | 2027112 | 2145 | 50 | PV | 14N26 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | 2014-10-01 | 2014-11-21 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2014-11-21 | 2014-12-24 | Online | [5 empty] | Private
NSTAR | Woburn | 2027532 | 1801 | 278.4 | PV | 375-H9 | 2014-09-30 | 2014-10-02 | 2 | 0 | 2 | 2014-10-03 | 2014-10-06 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-14 |  | 2015-05-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2014-12-22 | Online | [5 empty] | Private
NSTAR | Holliston | 2027916 | 1746 | 42 | PV | 274-H3 | 2014-10-01 | 2014-12-09 | 46 | 0 | 46 | 2014-12-09 | 2014-12-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 |  | 2015-03-01 | TBD | Expedited | 30 | 2015-03-02 | 2015-03-02 | 0 |  | 0 |  |  | 2015-07-28 | Online | [5 empty] | Private
NSTAR | Norfolk | 2028128 | 2056 | 22 | PV | 146-H3 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-14 | 2014-11-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online | [5 empty] | Private
NSTAR | Pocasset | 2029122 | 2559 | 55.2 | PV | 4-81A-406 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-08 | 2014-11-12 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-09 | 2015-01-15 | 2015-04-30 | No | Expedited | 30 | 2015-03-09 | 2015-03-09 | 0 |  | 0 |  | 2015-04-27 | 2015-04-27 | Online | [5 empty] | Private | N
NSTAR | Marion | 2029145 | 2738 | 783 | PV | 3-85-85 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-16 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-27 | 2015-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-04-27 | Online | [5 empty] | Private
NSTAR | Framingham | 2029290 | 1702 | 42.5 | PV | 240-H4 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-17 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-31 |  | 2015-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-27 | Online | [5 empty] | Private
NSTAR | Plymouth | 2029298 | 2360 | 30.9 | PV | 3-89-926 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-31 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online | [5 empty] | Private
NSTAR | Pocasset | 2029376 | 2559 | 34.2 | PV | 4-81A-406 | 2014-10-09 | 2014-10-09 | 0 | 0 | 0 | 2014-10-17 | 2015-05-20 | 150 | 115 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-03 |  | 2015-05-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-03-02 | 2016-03-02 | Online | [5 empty] | Gov't | N
NSTAR | Plymouth | 2029874 | 2360 | 225 | Natural Gas | 3-13-943 | 2014-10-09 | 2014-10-10 | 1 | 0 | 1 | 2014-10-27 | 2014-11-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-10 |  | 2015-05-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2029884 | 2571 | 60 | PV | 3-86-966 | 2014-10-21 | 2014-10-21 | 0 | 0 | 0 | 2014-10-23 | 2014-12-22 | 40 | 39 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-23 | 2015-06-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-03-12 | 2015-04-22 | Online | [5 empty] | Private
NSTAR | Dennis | 2031577 | 2641 | 16.1 | PV | 4-89A-552 | 2014-10-22 | 2014-10-23 | 1 | 0 | 1 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Dennisport | 2031909 | 2639 | 72 | PV | 4-92B-583 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Yarmouth | 2032033 | 2664 | 42 | PV | 4-92A-562 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-11-14 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 | 2015-02-18 | 2015-06-15 | TBD | Expedited | 30 | 2015-05-21 | 2015-05-21 | 0 |  | 0 |  | 2015-07-08 | 2015-07-13 | Online | [5 empty] | Private
NSTAR | Marion | 2032055 | 2738 | 250 | PV | 3-304-304 | 2014-10-27 | 2014-11-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Bellingham | 2032500 | 2019 | 480 | PV | 65-H4 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-03 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-05 | 2014-11-21 | 2015-06-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online | [5 empty] | Private
NSTAR | Hopkinton | 2033025 | 1748 | 15.2 | PV | 65-H6 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-06-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-01-12 | Online | [5 empty] | Private
NSTAR | Westport | 2033167 | 2790 | 30 | PV | 2-532-532 | 2014-10-30 | 2014-12-18 | 33 | 0 | 33 | 2014-12-29 | 2015-01-12 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights | [5 empty] | Private
NSTAR | Chilmark | 2033372 | 2535 | 195.2 | PV | 4-97-126 | 2014-11-03 | 2014-11-03 | 0 | 0 | 0 | 2014-11-06 | 2014-11-24 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-06-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Buzzards Bay | 2034325 | 2532 | 104 | PV | 3-88-2J4 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | 2014-11-07 | 2014-11-12 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-06-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2034511 | 2459 | 36 | PV | 292-H3 | 2014-11-05 | 2015-01-20 | 51 | 0 | 51 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-21 |  | 2015-06-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-04-28 | Online | [5 empty] | Private
NSTAR | New Bedford | 2034765 | 2740 | 30.9 | PV | 2-89-14 | 2014-11-05 | 2014-11-06 | 1 | 0 | 1 | 2014-11-10 | 2014-12-10 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-06-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-05-12 | 2015-05-12 | Online | [5 empty] | Private
NSTAR | New Bedford | 2034871 | 2746 | 600 | PV | 2-83-403 | 2014-11-06 | 2014-11-07 | 1 | 0 | 1 | 2014-12-12 | 2015-03-30 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-17 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-12 | Online | [5 empty] | Private
NSTAR | Dedham | 2034950 | 2026 | 794 | PV | 20-H5 | 2014-11-10 | 2014-11-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Ashland | 2035449 | 1721 | 3756 | PV | 274-1429H1 | 2014-11-10 | 2014-11-18 | 5 | 61 | -56 | 2014-11-14 | 2015-01-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-12-01 | 2015-12-14 | 9 | 0 | 9 | 2015-05-13 | 2016-02-29 | 2016-08-12 | No | Standard | 60 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Wareham | 2035472 | 2571 | 999 | PV | 3-85-955 | 2014-11-12 | 2014-11-13 | 1 | 0 | 1 | 2014-11-14 | 2015-01-12 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-12-29 | 2015-06-22 | TBD | Standard | 60 |  |  | 0 |  | 0 |  |  | 2016-08-29 | Online | [5 empty] | Private
NSTAR | Plymouth | 2035699 | 2360 | 993.6 | PV | 3-89-926 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | 2014-11-18 | 2014-11-19 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-05 |  | 2015-06-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acusnet | 2035823 | 2743 | 43.6 | PV | 2-106-160 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | 2014-12-24 | 2015-02-24 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-04-21 | 2015-04-24 | Online | [5 empty] | Private
NSTAR | Dedham | 2035957 | 2026 | 150 | Natural Gas | 13-H1 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | 2015-02-10 | 2015-09-01 | 145 | 112 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-06-24 | No |  | 160 |  |  | 0 |  | 0 |  |  |  | Screening | [5 empty] | Private
NSTAR | Plymouth | 2036219 | 2360 | 4000 | PV | 3-14-934 | 2014-11-18 | 2014-12-16 | 19 | 0 | 19 | 2014-12-16 | 2015-02-23 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 | 2015-08-25 | 2015-06-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Lexington | 2036677 | 2421 | 15.75 | PV | TBD | 2014-11-17 |  | -29940 | 0 | 0 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-14 |  | 2015-06-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Walpole | 2036754 | 2081 | 138 | PV | 146-H3 | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-11 |  | -30129 | 172 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 |  | 2016-03-14 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Plymouth | 2036912 | 2360 | 960 | PV | 3-12-12 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2014-12-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-06-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-07-01 |  | Withdrawn | [5 empty] | Private
NSTAR | Yarmouth | 2036990 | 2664 | - | PV | TBD | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-12-12 | 2014-12-16 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-27 | 2015-06-29 | No | Expedited | 30 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  | 2015-03-06 | 2015-03-06 | Online | [5 empty] | Gov't
NSTAR | New Bedford | 2037115 | 2745 | 300 | PV | 2-104-104 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2015-02-23 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-23 | 2015-06-02 | 2015-06-29 | No | Expedited | 30 | 2015-07-06 | 2015-07-06 | 0 |  | 0 |  | 2015-07-14 | 2015-07-17 | Online | [5 empty] | Private
NSTAR | New Bedford | 2037121 | 2745 | 266 | PV | 2-104-104 | 2014-11-20 | 2014-11-24 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hopkinton | 2037342 | 1748 | 3000 | PV | 65-H6 | 2014-11-21 | 2015-02-10 | 55 | 0 | 55 | 2014-11-24 | 2015-04-01 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | Private
NSTAR | Bellingham | 2037441 | 2019 | 480 | PV | 65-H4 | 2014-11-21 | 2015-02-10 | 55 | 0 | 55 | 2014-11-24 | 2015-03-26 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Bellingham | 2037449 | 2019 | 480 | PV | 65-H4 | 2014-11-25 | 2014-12-08 | 8 | 0 | 8 | 2014-12-02 | 2015-02-14 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-21 |  | -30311 | 1 | 0 |  |  | 0 | 0 | 0 | 2015-07-31 |  | 2015-07-03 | TBD |  | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2037775 | 2770 | 1500 | PV | 3-702-702 | 2014-11-28 | 2014-12-23 | 17 | 0 | 17 | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Yarmouth | 2038201 | 2664 | 40 | PV | 4-92A-562 | 2014-12-02 | 2014-12-23 | 15 | 0 | 15 | 2014-12-23 | 2015-02-26 | 46 | 35 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-07-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-19 | Online | [5 empty] | Private
NSTAR | Wayland | 2038683 | 1778 | 131 | PV | 342-H1 | 2014-12-02 | 2015-01-02 | 22 | 0 | 22 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 | 2016-03-11 | 2016-08-15 | No | Expedited | 30 | 2016-03-24 |  | -30291 |  | 0 |  |  | 2016-04-14 | Online | [5 empty] | Private
NSTAR | Ashland | 2038832 | 1721 | 200 | PV | 274-1429H1 | 2014-12-03 | 2015-01-02 | 21 | 0 | 21 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 |  | 2015-07-10 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online | [5 empty] | Private
NSTAR | Ashland | 2039760 | 1721 | 200 | PV | 274-1429H1 | 2014-12-04 | 2015-01-23 | 35 | 0 | 35 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 |  | 2015-07-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online | [5 empty] | Private
NSTAR | New Bedford | 2041158 | 2746 | 18 | PV | 2-84-133 | 2014-12-04 | 2015-01-13 | 27 | 0 | 27 | 2015-01-13 | 2015-02-21 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-02-23 | 2015-06-29 | 90 | 0 | 90 |  |  | 0 | 0 | 0 | 2015-04-29 |  | 2015-07-13 | TBD | Standard | 60 |  |  | 0 |  | 0 |  | 2015-12-17 | 2015-12-17 | Online | [5 empty] | PRIVATE
NSTAR | East Freetown | 2041172 | 2717 | 1137 | Natural Gas | 2-606-606 | 2014-12-08 | 2015-01-02 | 18 | 0 | 18 | 2015-01-02 | 2015-01-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-26 |  | 2015-07-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2041620 | 2139 | 22.8 | PV | 815-10 | 2014-12-08 | 2015-01-02 | 18 | 0 | 18 | 2015-01-02 | 2015-02-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-03 |  | 2015-07-15 | TBD | Expedited | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  |  | 2015-06-12 | Online | [5 empty] | Private
NSTAR | Cambridge | 2041623 | 2139 | 22.8 | PV | 814-12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 |  | 2015-07-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-05 | Online | [5 empty] | Private | N
NSTAR | Dartmouth | 2042098 | 2747 | 17.5 | PV | 2-533-533 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-22 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-07-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-02-04 | Online | [5 empty] | Private
NSTAR | Sherborn | 2042113 | 1770 | 29 | PV | 240-H1 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-18 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-15 | 2015-01-14 | 2015-05-22 | No | Expedited | 30 | 2015-05-08 | 2015-05-08 | 0 |  | 0 |  |  | 2015-05-29 | Online | [5 empty] | Private
NSTAR | Newton | 2042189 | 2466 | 16.4 | PV | 292-H12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-02-17 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-07-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-08-04 | Online | [5 empty] | Private
NSTAR | Mashpee | 2042191 | 2649 | 11.4 | PV | 4-77A-454 | 2014-12-16 | 2014-12-17 | 1 | 0 | 1 | 2014-12-19 | 2015-03-30 | 70 | 36 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-16 | 2015-05-27 | 2015-07-23 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2043228 | 1760 | 211 | PV | 23-H1 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-22 | 2015-03-18 | 61 | 27 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-18 |  | 2015-07-23 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-01-15 | 2016-01-15 | Online | [5 empty] | Private
NSTAR | Framingham | 2043236 | 1701 | 524 | PV | 433-H3 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-19 | 2015-03-05 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 | 2015-09-14 | 2016-01-15 | No | Expedited | 30 | 2015-10-30 | 2015-10-30 | 0 |  | 0 |  | 2016-02-03 | 2016-01-15 | Online | [5 empty] | Private
NSTAR | Bourne | 2043278 | 2532 | 650 | PV | 4-86-402 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 | 2015-02-02 | 2015-03-01 | No | Expedited | 30 | 2015-03-26 | 2015-03-26 | 0 |  | 0 |  |  | 2015-12-31 | Online | [5 empty] | Private
NSTAR | Somerville | 2043499 | 2145 | 50 | PV | 585-114H4 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-23 | Online | [5 empty] | Private
NSTAR | Brewster | 2043623 | 2631 | 132 | PV | 4-89A-553 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 | 2014-12-29 | 2015-01-06 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2015-02-05 | 2015-04-01 | TBD | Expedited | 30 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 2015-04-07 | Online | [5 empty] | Private
NSTAR | Yarmouthport | 2044156 | 2675 | 57 | PV | 4-92A-92A | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 | 2014-12-29 | 2015-01-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-30 | 2015-01-29 | 2015-06-19 | No | Expedited | 30 | 2015-05-20 | 2015-05-20 | 0 |  | 0 |  |  | 2015-06-17 | Online | [5 empty] | Private
NSTAR | Canton | 2044274 | 2021 | 18.9 | PV | 269-1320H1 | 2014-12-26 | 2014-12-26 | 0 | 0 | 0 | 2015-01-01 | 2015-01-08 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 |  | 2015-08-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-03-26 | Online | [5 empty] | Private
NSTAR | Holliston | 2044550 | 1746 | 15.2 | PV | 65-H2 | 2014-12-26 | 2014-12-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Gov't
NSTAR | Boston | 2044564 | 2118 | 2000 | Natural Gas | 4910 | 2014-12-31 | 2014-12-31 | 0 | 0 | 0 | 2015-01-06 | 2015-01-07 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-08 | 2015-01-08 | 2015-08-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-09 | Online | [5 empty] | Private | N
NSTAR | Truro | 2045149 | 2652 | 16 | PV | 4-96-674 | 2014-12-31 | 2015-01-02 | 2 | 0 | 2 | 2015-01-02 | 2015-01-09 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-12 | 2015-01-12 | 2015-08-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-11 | Online | [5 empty] | Private
NSTAR | Dennisport | 2045155 | 2639 | 72 | PV | 4-92B-583 | 2015-01-06 | 2015-01-08 | 2 | 0 | 2 | 2015-01-12 | 2015-01-29 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-25 | Online | [5 empty] | Private
NSTAR | Millis | 2048757 | 2054 | 131 | PV | 146-H10 | 2015-01-07 | 2015-01-08 | 1 | 0 | 1 | 2015-01-12 | 2015-03-31 | 56 | 2 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-14 | 2015-04-14 | 2015-08-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-12-18 | 2015-12-18 | Online | [5 empty] | Private
NSTAR | Boston | 2048937 | 2118 | 85 | Natural Gas | 318-10 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 2015-01-13 | 2015-01-29 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-06-29 | Online | [5 empty] | Private
NSTAR | Millis | 2049131 | 2054 | 42 | PV | 146-H10 | 2015-01-09 | 2015-01-12 | 1 | 0 | 1 | 2015-01-15 | 2015-03-26 | 50 | 15 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 | 2015-03-31 | 2015-07-23 | No | Expedited | 30 | 2015-06-15 |  | -30088 |  | 0 |  | 2015-09-11 | 2015-09-11 | Online | [5 empty] | Private
NSTAR | Millis | 2049284 | 2054 | 300 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-01-30 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-11 | Online | [5 empty] | Private
NSTAR | Millis | 2049734 | 2054 | 75 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-03-31 | 53 | 40 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 | 2015-06-02 | 2015-09-30 | TBD | Expedited | 30 | 2015-07-15 | 2015-07-15 | 0 |  | 0 |  | 2015-09-28 | 2015-09-28 | Online | [5 empty] | Private
NSTAR | New Bedford | 2049774 | 2745 | 200 | PV | 2-104-104 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-01 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2049963 | 2748 | 17.8 | PV | 2-2-505 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-02-06 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Sharon | 2049971 | 2067 | 15.8 | PV | 470-H3 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-07-22 | Withdrawn | [5 empty] | Private
NSTAR | Wayland | 2050518 | 1778 | 113 | PV | 433-H6 | 2015-01-16 | 2015-01-19 | 1 | 0 | 1 | 2015-01-21 | 2015-02-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-03 | Online | [5 empty] | Private
NSTAR | Canton | 2050531 | 2021 | 95 | PV | 470-H4 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-07-07 | 2015-07-31 | TBD | Expedited | 30 | 2015-07-28 | 2015-07-28 | 0 |  | 0 |  |  | 2015-08-18 | Online | [5 empty] | Private
NSTAR | Wareham | 2050542 | 2576 | 23.6 | PV | 3-85-928 | 2015-01-20 | 2015-01-20 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | [5 empty] | Private | N
NSTAR | Acusnet | 2051046 | 2743 | 1904 | PV | 2-241-238 | 2015-01-20 | 2015-01-21 | 1 | 0 | 1 | 2015-01-27 | 2015-09-03 | 157 | 152 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2020-04-29 | Online | [5 empty] | Private
NSTAR | Holliston | 2051070 | 1746 | 2000 | PV | 130-H1 | 2015-01-21 | 2015-01-21 | 0 | 64 | 0 | 2015-01-23 | 2016-01-19 | 257 | 66 | 191 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2016-12-31 | No |  | 160 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2051273 | 2330 | 1500 | PV | 3-10-930 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-23 |  | -29987 | 395 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2017-01-25 |  | -30510 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-02 | 2015-05-14 | 2015-08-26 | TBD |  | 160 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online |  |  |  |  | 2015-01-27 | Private
NSTAR | Acusnet | 2051285 | 2743 | 4000 | PV | 2-241-238 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-27 | 2015-02-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-05-19 |  | -30069 | 0 | 0 |  |  | 0 |  | 0 | 2015-10-02 |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hopkinton | 2051301 | 1748 | 31 | PV | 65-H2 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-03-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 | 2015-04-20 | 2015-08-26 | TBD | Expedited | 30 | 2015-05-18 | 2015-05-18 | 0 |  | 0 |  |  | 2015-09-04 | Online | [5 empty] | Private
NSTAR | Falmouth | 2051319 | 2536 | 56 | PV | 4-76-436 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | [5 empty] | Private
NSTAR | Maynard | 2051324 | 1754 | 15.2 | PV | 355-05 | 2015-01-21 | 2015-01-22 | 1 | 0 | 1 | 2015-01-23 | 2015-02-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-09-24 | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2051325 | 2747 | 360 | PV | 2-532-532 | 2015-01-21 | 2015-01-21 | 0 |  | 0 | 2015-01-27 |  | -29989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-03 |  | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2051336 | 2571 | 150 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 | 2015-02-24 | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Witness Test Awaiting Cust Response/Doc | [5 empty] | Gov't
NSTAR | Cambridge | 2051340 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-30 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-04-07 | Online | [5 empty] | Private
NSTAR | Wareham | 2051382 | 2571 | 56 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-02-18 | 2015-08-26 | TBD | Expedited | 30 | 2015-03-19 | 2015-03-19 | 0 |  | 0 |  |  | 2015-03-27 | Online | [5 empty] | Private
NSTAR | Framingham | 2051390 | 1701 | 17.6 | PV | 433-H4 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Cambridge | 2051393 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-24 | Online | [5 empty] | Private
NSTAR | Westport | 2051411 | 2790 | 16.3 | PV | 2-523-523 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-10 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 |  | 2015-08-26 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private | N
NSTAR | Roxbury | 2051417 | 2119 | 42 | PV | 323-05 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | 2015-01-29 | 2015-03-30 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-25 | 2015-09-09 | 11 | 0 | 11 | 2015-03-25 | 2015-09-24 | 2016-04-01 | No |  | 160 | 2015-11-19 | 2015-11-19 | 0 |  | 0 |  | 2016-05-23 | 2016-09-28 | Online | [5 empty] | Private
NSTAR | Wareham | 2051455 | 2538 | 2000 | PV | 3-84-961 | 2015-01-22 | 2015-01-22 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online | [5 empty] | Private
NSTAR | Mattapoisett | 2051477 | 2739 | 2250 | PV | 2-304-304 | 2015-01-22 | 2015-01-23 | 1 | 0 | 1 | 2015-02-19 | 2015-03-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-27 | TBD |  | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Mattapoisett | 2051498 | 2739 | 2500 | PV | 2-304-304 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-04 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-06 |  | 2015-08-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Assonett | 2051972 | 2702 | 24.1 | PV | 2-605-605 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-08-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-07-24 | Online | [5 empty] | Private
NSTAR | Wayland | 2052009 | 1778 | 42 | PV | 433-H6 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-09-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-05-06 | Online | [5 empty] | Private
NSTAR | Framingham | 2052167 | 1702 | 15.2 | PV | 455-H3 | 2015-01-29 | 2015-01-29 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Ashland | 2052252 | 1721 | 2413 | PV | 274-H1 | 2015-01-30 | 2015-01-30 | 0 | 0 | 0 | 2015-02-04 | 2015-02-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-09 |  | 2015-09-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | [5 empty] | Private
NSTAR | East Freetown | 2052538 | 2717 | 17.4 | PV | 2-102-102 | 2014-11-05 | 2014-11-12 | 4 |  | 4 | 2015-02-03 |  | -29994 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-02-09 | 2015-02-12 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2016-02-12 | Online | [5 empty] | Private | N
NSTAR | Lexington | 2052550 | 2421 | 2964 | PV | 533-H2 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2016-12-04 | 2015-09-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-15 | Online | [5 empty] | Gov't
NSTAR | Arlington | 2053824 | 2476 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-18 | Online | [5 empty] | Gov't
NSTAR | Arlington | 2053835 | 2476 | 176 | PV | 211-H3 | 2015-02-03 | 2015-02-04 | 1 | 0 | 1 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Arlington | 2053837 | 2474 | 74 | PV | 59-1383H1 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-03-09 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 |  | 2015-09-09 | TBD | Expedited | 30 | 2015-03-05 | 2015-03-05 | 0 |  | 0 |  |  | 2015-11-18 | Online | [5 empty] | Gov't
NSTAR | Arlington | 2053847 | 2476 | 74 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-19 | Online | [5 empty] | Gov't
NSTAR | Arlington | 2053868 | 2474 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee/ Agreement | [5 empty] | Private
NSTAR | Acusnet | 2053880 | 2743 | 1995 | PV | 2-241-238 | 2015-02-04 | 2017-03-15 | 550 |  | 550 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | impact study | [5 empty] | Private
NSTAR | Plymouth | 2053997 | 2360 | 112 | PV | 3-13-936 | 2015-02-05 | 2015-02-05 | 0 | 0 | 0 | 2015-02-10 | 2015-03-26 | 32 | 2 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-09-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-07-09 | 2016-03-29 | Online | [5 empty] | Private
NSTAR | Framingham | 2054091 | 1701 | 322 | PV | 433-H3 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | 2015-02-11 |  | -30000 | 145 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-14 | TBD |  | 160 |  |  | 0 |  | 0 |  |  | 2017-07-23 | Online | [5 empty] | Private
NSTAR | Plymouth | 2054256 | 2360 | 1000 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 |  | 2015-09-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-10-03 | Online | [5 empty] | Private
NSTAR | Lexington | 2054352 | 2421 | 15.9 | PV | 320-H2 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-11 |  | -30000 | 115 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-15 | TBD |  | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Plymouth | 2054376 | 2360 | 500 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 | 2015-02-19 | 2015-09-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | hold - cluster | [5 empty] | Private
NSTAR | Harwichport | 2054472 | 2646 | 15.2 | PV | 4-95A-95A | 2015-02-10 | 2015-02-11 | 1 | 0 | 1 | 2015-02-13 | 2015-02-19 | 4 | 47 | -43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Ashland | 2054585 | 1721 | 21.2 | PV | 519-175H1 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 | 2015-02-17 | 2015-03-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-31 |  | 2016-04-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2054857 | 2747 | 800 | PV | 2-533-530 | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dennis | 2055020 | 2660 | 56 | PV | 4-92B-92B | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online | [5 empty] | Private
NSTAR | Dennis | 2055023 | 2660 | 70 | PV | 4-92B-92B | 2015-02-18 | 2015-02-19 | 1 | 0 | 1 | 2015-02-23 | 2015-02-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-09-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online | [5 empty] | Gov't
NSTAR | Arlington | 2055516 | 2476 | 56 | PV | 320-H7 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | 2015-02-27 | 2015-03-04 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-03-05 | 2015-09-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | [5 empty] | Private
NSTAR | Dennis | 2055761 | 2660 | 15.2 | PV | 4-92B-572 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-15 |  | Construction | [5 empty] | Private | N
NSTAR | Weston | 2055868 | 2493 | 1795 | PV | 450-H7 | 2015-02-24 | 2015-03-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-15 | Online | [5 empty] | Private | Y
NSTAR | Oak Bluffs | 2055949 | 2557 | 2000 | PV | 4-75-75 | 2015-02-24 | 2015-02-25 | 1 | 0 | 1 | 2015-02-27 | 2015-04-27 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Forestdale | 2055988 | 2644 | 15.8 | PV | 4-81B-443 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | 2015-03-02 | 2015-03-05 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-09-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-29 | Online | [5 empty] | Private
NSTAR | Plymouth | 2056169 | 2360 | 100 | PV | 3-14-911 | 2015-02-26 | 2015-02-26 | 0 | 0 | 0 | 2015-03-04 | 2015-03-10 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-27 |  | 2015-12-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | East Freetown | 2056337 | 2717 | 52 | PV | 2-102-602 | 2015-02-27 | 2015-02-27 | 0 | 0 | 0 | 2015-03-04 | 2015-03-30 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-13 |  | 2015-10-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online | [5 empty] | Private
NSTAR | Chelsea | 2056434 | 2150 | 394.4 | PV | 488-H2 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-28 |  | 2016-09-30 | TBD | Expedited | 30 | 2016-03-02 |  | -30275 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Chelsea | 2056439 | 2150 | 185.6 | PV | 488-H2 | 2015-02-03 | 2015-02-03 | 0 |  | 0 | 2015-03-21 |  | -30027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-15 | 2015-04-27 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2056449 | 2770 | 840 | PV | 3-702-702 | 2015-03-03 | 2015-03-03 | 0 | 0 | 0 | 2015-03-06 | 2015-03-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-10-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online | [5 empty] | Private
NSTAR | Rochester | 2056499 | 2770 | 2500 | PV | 3-703-703 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | 85 | 0 | 85 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-07-28 | 2016-09-12 | 2016-12-16 | TBD | Expedited | 30 | 2016-03-02 | 2016-03-02 | 0 |  | 0 |  | 2017-01-13 | 2017-01-13 | Online | [5 empty] | Private
NSTAR | Acusnet | 2057145 | 2743 | 18 | PV | 2-241-237 | 2015-03-04 | 2015-03-09 | 3 | 49 | -46 | 2015-06-03 | 2015-07-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 |  | 2015-10-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Hopkinton | 2057252 | 1748 | 308 | PV | 126-H2 | 2015-03-21 | 2015-05-06 | 33 | 5 | 28 | 2015-05-12 |  | -30064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 | [7 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online | [5 empty] | Private
NSTAR | Millis | 2057504 | 2054 | 296 | PV | 65-H3 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-03-13 | Private
NSTAR | Marion | 2057875 | 2738 | 482 | PV | 2-304-304 | 2015-03-12 | 2015-03-12 | 0 | 0 | 0 | 2015-03-17 | 2015-04-03 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 |  | 2015-10-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2058198 | 2747 | 17 | PV | 2-532-532 | 2015-03-16 | 2015-03-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-03-24 | Private
NSTAR | Acusnet | 2058670 | 2743 | 1000 | PV | 2-241-241 | 2015-03-17 | 2015-03-17 | 0 | 0 | 0 | 2015-03-24 | 2015-04-10 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-17 | 2019-08-21 | 2015-10-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | Westwood | 2059020 | 2090 | 40 | PV | 456-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-04-14 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-01 | 2016-06-06 | 2015-10-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Wayland | 2059369 | 1778 | 176 | PV | 342-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-05-18 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online | [5 empty] | Private
NSTAR | Wayland | 2059403 | 1778 | 207 | PV | 342-H3 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-06-22 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-18 | 2016-01-11 | 2016-07-29 | TBD | Expedited | 30 | 2016-04-29 |  | -30317 |  | 0 |  |  | 2016-12-30 | Online | [5 empty] | Gov't
NSTAR | Wayland | 2059432 | 1778 | 500 | PV | 278-H2 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-23 | 2015-05-19 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Wayland | 2059441 | 1778 | 217 | PV | 433-H6 | 2015-03-19 | 2015-03-20 | 1 | 0 | 1 | 2015-07-23 | 2015-07-30 | 5 | 85 | -80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-22 | 2016-06-30 | 2015-10-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-29 | Online | [5 empty] | Private
NSTAR | Natick | 2059455 | 1760 | 240 | PV | 433-H7 | 2015-03-23 | 2015-03-23 | 0 | 0 | 0 | 2015-03-31 | 2015-04-22 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-15 |  | 2015-10-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Woburn | 2059849 | 1801 | 65 | PV | 211-H2 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-06-04 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-14 | 2016-02-05 | 2015-10-28 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Plymouth | 2059927 | 2360 | 500 | PV | 3-12-12 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-04-21 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 |  | 2015-10-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2059968 | 2790 | 21 | PV | 2-523-523 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | 2015-04-09 | 2015-05-01 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-08 | 2015-05-08 | 2015-10-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online | [5 empty] | Private
NSTAR | Medfield | 2060105 | 2052 | 196 | PV | 456-H2 | 2015-03-31 | 2015-04-01 | 1 | 0 | 1 | 2015-04-03 | 2015-09-21 | 121 | 117 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2060976 | 1760 | 500 | PV | 408-1433 | 2015-03-31 | 2015-03-31 | 0 | 0 | 0 | 2015-04-03 | 2015-04-23 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-30 |  | 2015-11-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Holliston | 2061089 | 1746 | 28 | PV | 65-H5 | 2015-03-31 | 2015-04-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Westport | 2061122 | 2790 | 2000 | PV | 2-532-532 | 2015-04-01 | 2015-04-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-09-27 | Online | [5 empty] | Private
NSTAR | Walpole | 2061451 | 2081 | 2280 | PV | 146-H6 | 2015-04-02 | 2015-04-03 | 1 | 0 | 1 |  |  | 0 | 76 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2015-11-06 | No |  | 30 |  |  | 0 |  | 0 |  |  | 2017-06-26 | Online | [5 empty] | Private | N
NSTAR | Bellingham | 2061830 | 2019 | 1976 | PV | 65-H4 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-20 | 2015-05-04 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-11 | 2015-09-07 | 2015-11-09 | TBD | Expedited | 30 | 2015-10-16 | 2015-10-16 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Falmouth | 2062098 | 2540 | 56 | PV | 4-76-436 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-22 | 2015-04-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 | 2015-04-23 | 2015-11-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-04 | Online | [5 empty] | Private
NSTAR | Provincetown | 2062144 | 2657 | 27 | PV | 4-96-675 | 2015-04-06 | 2015-04-13 | 5 | 0 | 5 | 2015-04-16 | 2015-04-23 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 |  | 2015-11-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-06-08 | Online | [5 empty] | Private
NSTAR | Wareham | 2062402 | 2571 | 17 | PV | 3-84-84 | 2015-04-06 | 2015-04-16 | 8 | 0 | 8 | 2015-04-20 | 2015-04-21 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-22 | 2015-04-22 | 2015-11-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Meter | [5 empty] | Private
NSTAR | Edgartown | 2062416 | 2539 | 56 | PV | 4-97-97 | 2015-04-07 | 2015-04-07 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-07-21 | 2016-08-29 | Online | [5 empty] | Private | N
NSTAR | Marion | 2062768 | 2738 | 882 | PV | 3-85-85 | 2015-04-08 | 2015-04-22 | 10 | 3 | 7 | 2015-04-24 | 2015-05-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2015-11-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-07-20 | Online | [5 empty] | Private
NSTAR | Boston | 2062878 | 2118 | 100 | PV | 2-543-543 | 2015-04-08 | 2015-04-21 | 9 | 0 | 9 | 2015-04-23 | 2015-07-17 | 61 | 59 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-22 |  | 2015-11-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-02-25 | Online | [5 empty] | Private
NSTAR | New Bedford | 2062901 | 2745 | 40 | PV | 2-88-18 | 2015-04-09 | 2015-04-15 | 4 | 0 | 4 | 2015-04-16 | 2015-07-07 | 58 | 23 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-08 |  | 2015-11-16 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Dedham | 2063144 | 2026 | 210 | PV | 469-H4 | 2015-04-09 | 2015-04-16 | 5 | 0 | 5 | 2015-04-20 | 2015-04-22 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Orleans | 2063168 | 2653 | 100 | PV | 4-89B-618 | 2015-04-13 | 2015-04-14 | 1 | 0 | 1 | 2015-04-16 | 2015-04-22 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | [5 empty] | Private
NSTAR | Harwichport | 2063694 | 2646 | 40 | PV | 4-85-592 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-05-16 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2016-06-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | East Boston | 2063933 | 2128 | 499 | PV | 108-196H1 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-07-07 | 60 | 28 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-07 |  | 2016-11-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | East Boston | 2063964 | 2128 | 499 | PV | 108-196H1 | 2015-04-16 | 2015-04-16 | 0 | 0 | 0 | 2015-05-01 | 2015-05-28 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2015-11-23 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-12-29 | 2017-04-06 | Online | [5 empty] | Private | N
NSTAR | Waltham | 2064568 | 2451 | 500 | PV | 363-1369 | 2015-04-17 | 2015-04-17 | 0 | 37 | 0 | 2015-04-24 | 2015-07-01 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-02 |  | 2015-11-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Dartmouth | 2064782 | 2748 | 20 | PV | 2-528-528 | 2015-04-17 | 2015-04-23 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-28 | Online | [5 empty] | Private
NSTAR | Woburn | 2064809 | 1801 | 2640 | PV | 375-H6 | 2015-04-21 | 2015-04-28 | 5 | 49 | -44 | 2015-05-05 | 2015-07-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-12 | 2015-09-15 | 2015-11-25 | No | Expedited | 30 | 2015-12-11 | 2015-12-11 | 0 |  | 0 |  | 2015-12-22 | 2017-06-15 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2065135 | 2747 | 239.4 | PV | 2-532-532 | 2015-04-21 | 2015-04-22 | 1 | 0 | 1 | 2015-04-24 | 2015-06-15 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2015-08-26 | 2015-11-25 | No | Expedited | 30 | 2015-09-16 | 2015-09-16 | 0 |  | 0 |  | 2015-12-22 | 2016-02-28 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2065189 | 2747 | 360 | PV | 2-532-532 | 2015-04-22 | 2015-07-28 | 69 | 60 | 9 | 2015-08-03 | 2016-08-01 | 260 | 63 | 197 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-07 |  | 2015-11-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee | [5 empty] | Private | N
NSTAR | Plympton | 2065453 | 2367 | 5000 | PV | 3-51-DSS | 2015-04-23 | 2015-04-24 | 1 | 0 | 1 | 2015-05-04 | 2016-05-24 | 276 | 256 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Millis | 2065662 | 2054 | 2000 | PV | 65-H1 | 2015-04-24 | 2015-04-29 | 3 | 0 | 3 | 2015-04-30 | 2015-05-11 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-04 |  | 2015-12-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2065777 | 2140 | 36 | PV | 826-20 | 2015-04-24 | 2015-04-25 | -1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Centerville | 2065805 | 2632 | 17.4 | PV | 4-82-508 | 2015-04-27 | 2015-05-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2015-07-27 | Private
NSTAR | Boston | 2066237 | 2118 | 96 | PV | 528-129H | 2015-04-28 | 2015-04-29 | 1 | 0 | 1 | 2015-04-29 | 2015-06-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-21 |  | 2016-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-03-10 |  | Withdrawn | [5 empty] | Gov't
NSTAR | Cambridge | 2066481 | 2139 | 568 | PV | 817-05 | 2015-04-28 | 2015-05-05 | 5 | 0 | 5 | 2015-05-07 | 2015-05-27 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-27 |  | 2015-12-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-03-24 | Withdrawn | [5 empty] | Private
NSTAR | Boston | 2066533 | 2118 | 48 | PV | 385-H15 | 2015-04-28 | 2015-05-19 | 15 | 11 | 4 | 2015-05-20 | 2015-06-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-24 | 2015-06-24 | 2015-12-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-07-12 | 2016-07-22 | Online | [5 empty] | Private
NSTAR | Provincetown | 2066548 | 2657 | 30 | PV | 4-96-676 | 2015-05-05 | 2015-05-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Bellingham | 2068158 | 2019 | 497 | PV | 65-H4 | 2015-05-06 | 2015-05-07 | 1 | 0 | 1 | 2015-07-01 | 2015-07-07 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-09 | 2016-09-12 |  | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | ISA Received/Signed | [5 empty] | Private
NSTAR | Waltham | 2068489 | 2451 | 96 | PV | 450-H8 | 2015-05-07 | 2015-05-11 | 2 | 0 | 2 | 2015-05-14 | 2015-06-22 | 27 | 1 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-01 |  | 2015-12-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-01-22 | 2016-01-25 | Online | [5 empty] | Private
NSTAR | Woburn | 2068626 | 1801 | 300 | PV | 375-H11 | 2015-05-07 | 2015-05-12 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private | N
NSTAR | Westport | 2068650 | 2790 | 2550 | PV | 2-522-522 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-19 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-05 |  | 2015-12-15 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-01 | Online | [5 empty] | Private | Y
NSTAR | Lexington | 2068862 | 2420 | 19 | PV | 391-H11 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-26 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-29 | 2015-05-29 | 2015-12-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-08-05 | Online | [5 empty] | Private
NSTAR | Natick | 2068895 | 1760 | 19 | PV | 240-H5 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-05-27 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-01 |  | 2015-12-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online | [5 empty] | Private
NSTAR | Duxbury | 2069125 | 2332 | 16 | PV | 3-23-981 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-07-09 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-06 |  | 2015-12-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-01-20 | 2016-01-25 | Online | [5 empty] | Private
NSTAR | Lexington | 2069155 | 2421 | 319 | PV | 320-H5XY | 2015-05-15 | 2015-05-16 | -1 | 47 | 0 | 2015-05-18 | 2015-08-11 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-19 | Online | [5 empty] | Private
NSTAR | Norfolk | 2070139 | 2056 | 475 | PV | 146-H3 | 2015-05-19 | 2015-05-21 | 2 | 0 | 2 | 2015-05-25 | 2015-08-03 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2015-12-24 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Woburn | 2070813 | 1801 | 662 | PV | 211-H5 | 2015-05-19 | 2015-05-27 | 6 | 0 | 6 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2015-06-25 | 2015-12-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Watertown | 2070884 | 2472 | 156 | PV | 467-H9 | 2015-05-20 | 2015-05-26 | 4 | 45 | -41 | 2015-05-28 | 2015-07-22 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2015-12-28 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Ashland | 2071026 | 1721 | 498 | PV | 519-175H1 | 2015-05-20 | 2015-05-22 | 2 | 0 | 2 | 2015-05-27 | 2015-06-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-07-09 | 2015-12-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | [5 empty] | Private
NSTAR | Ashland | 2071030 | 1721 | 186 | PV | 274-1429H1 | 2015-05-20 | 2015-05-26 | 4 | 0 | 4 | 2015-05-28 | 2015-07-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2016-02-29 | 2016-12-27 | No | Expedited | 30 | 2016-02-23 |  | -30269 | 0 | 0 |  |  | 2017-02-23 | Online | [5 empty] | Private
NSTAR | Ashland | 2071039 | 1721 | 728 | PV | 455-H3 | 2015-05-21 | 2015-06-10 | 14 | 0 | 14 | 2015-06-11 | 2015-08-26 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Hyannis | 2071355 | 2601 | 144 | PV | 4-80B-523 | 2015-05-21 | 2015-06-25 | 25 | 0 | 25 | 2015-07-01 | 2015-08-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online | [5 empty] | Private
NSTAR | Hyannis | 2071356 | 2601 | 120 | PV | 4-84B-524 | 2015-05-26 | 2015-06-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info |  |  |  |  | 2015-06-23 | Private | N
NSTAR | Wareham | 2071689 | 2576 | 1800 | PV | 3-85-85 | 2015-05-27 | 2015-05-28 | 1 | 0 | 1 | 2015-05-28 | 2015-06-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-10 |  | 2016-01-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-01-17 | Online | [5 empty] | Private
NSTAR | Natick | 2071934 | 1760 | 148 | PV | 240-H5 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 | 2015-06-03 | 2015-06-24 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2016-01-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online | [5 empty] | Private
NSTAR | Plymouth | 2072210 | 2360 | 112 | PV | 3-12-12 | 2015-05-28 | 2015-06-01 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Framingham | 2072250 | 1702 | 4279 | PV | 274-H4 | 2015-05-29 | 2015-05-30 | -1 | 0 | 0 | 2015-06-05 | 2016-01-27 | 168 | 158 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-23 | 2016-01-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-18 | Online | [5 empty] | Private
NSTAR | Woburn | 2072460 | 1801 | 225 | PV | 375-H6 | 2015-06-01 | 2015-06-04 | 3 | 0 | 3 | 2015-06-08 | 2015-07-01 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-29 | 2015-10-23 | 2016-03-17 | TBD | Expedited | 30 | 2016-01-15 | 2016-01-15 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2072760 | 2748 | 100 | PV | 2-528-528 | 2015-06-01 | 2015-06-05 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Impct Stdy:Awaiting Customers Response/Doc |  |  |  |  | 2016-06-14 | Private
NSTAR | Millis | 2072811 | 2054 | 1002 | PV | 65-H3 | 2015-06-02 | 2015-06-03 | 1 | 0 | 1 | 2015-06-05 | 2015-07-06 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-24 | 2015-12-10 | 2016-01-08 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-11-01 | Online | [5 empty] | Private
NSTAR | Woburn | 2073317 | 1801 | 100 | PV | 211-H8 | 2015-06-03 | 2016-03-02 | 195 |  | 195 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-03-02 | Online | [5 empty] | Private
NSTAR | Arlington | 2073733 | 2474 | 92 | PV | 59-1383H1 | 2015-06-03 | 2015-10-28 | 105 | 87 | 18 | 2015-10-28 | 2015-10-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-11-02 | 2016-01-11 | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2015-10-28 | 2015-12-08 | Online | [5 empty] | Private | N
NSTAR | Arlington | 2073753 | 2476 | 69 | PV | 351-1385H1 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-09 | 2015-07-30 | 37 | 34 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-01-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online | [5 empty] | Private | N
NSTAR | Lincoln | 2073947 | 1773 | 84 | PV | 320-H8 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-10 | 2015-07-17 | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-30 |  | 2016-01-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-05-18 | Online | [5 empty] | Private | N
NSTAR | Lincoln | 2073959 | 1773 | 112 | PV | 320-H8 | 2015-06-09 | 2015-06-11 | 2 | 0 | 2 | 2015-06-15 | 2015-06-25 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-12-18 | 2016-01-20 | TBD | Expedited | 30 | 2015-12-28 | 2015-12-28 | 0 |  | 0 |  |  | 2016-01-29 | Online | [5 empty] | Private
NSTAR | Holliston | 2074665 | 1746 | 20 | PV | 274-H5 | 2015-06-10 | 2015-06-12 | 2 | 0 | 2 | 2015-06-17 | 2015-08-26 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 |  | 2016-01-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-02-19 | Online | [5 empty] | Private | N
NSTAR | Wianno | 2074867 | 2655 | 44 | PV | 4-80A-892 | 2015-06-19 | 2015-06-25 | 4 | 0 | 4 | 2015-06-24 |  | -30095 | 290 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-01-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-06-26 | Private
NSTAR | Dartmouth | 2076812 | 2747 | 4500 | PV | 2-532-532 | 2015-06-23 | 2015-06-29 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-07-03 | Private
NSTAR | Acusnet | 2077489 | 2743 | 1080 | PV | 2-241-241 | 2015-06-25 | 2015-06-30 | 3 | 0 | 3 | 2015-07-02 | 2015-07-30 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-02-02 | No | Expedited | 30 |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | Wareham | 2077939 | 2571 | 200 | PV | 3-84-961 | 2015-06-30 | 2015-07-06 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Ashland | 2078781 | 1721 | 183.287 | PV | 274-1429H1 | 2015-07-02 | 2015-07-06 | 2 | 0 | 2 | 2015-07-08 | 2015-07-29 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-17 | 2015-09-30 | 2015-11-06 | No | Expedited | 30 | 2015-10-20 | 2015-10-20 | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | Private | N
NSTAR | Walpole | 2079372 | 2081 | 153 | PV | 146-H3 | 2015-07-02 | 2015-07-09 | 5 | 0 | 5 | 2015-07-10 | 2015-07-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-16 |  | 2016-02-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-13 | Online | [5 empty] | Private
NSTAR | Assonett | 2079393 | 2702 | 20 | PV | 2-605-605 | 2015-07-09 | 2015-07-16 | 5 | 0 | 5 | 2015-07-20 | 2015-08-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2016-02-12 | 2016-06-30 | No | Expedited | 30 | 2016-08-10 |  | -30390 |  | 0 |  |  |  | Construction | [5 empty] | Private
NSTAR | Woburn | 2080949 | 1801 | 696 | PV | 375-H4 | 2015-07-16 | 2015-07-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private | N
NSTAR | Bellingham | 2082060 | 2019 | 990 | PV | 65-H4 | 2015-07-17 | 2015-07-20 | 1 | 0 | 1 | 2015-07-23 | 2015-08-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2016-02-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2082435 | 2360 | 79 | PV | 3-12-12 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2016-02-10 | 144 | 50 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-01 | 2016-05-25 | 2016-10-14 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online | [5 empty] | Private
NSTAR | Plympton | 2082491 | 2367 | 990 | PV | 3-51-901 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2015-08-06 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 | 2016-02-10 | 2016-02-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-09 | Online | [5 empty] | Private
NSTAR | Woburn | 2082549 | 1801 | 495 | PV | 375-H3 | 2015-07-21 | 2015-07-22 | 1 | 0 | 1 | 2015-07-24 | 2015-09-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-29 | 2016-05-30 | 2016-02-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2019-03-29 | Online | [5 empty] | Private
NSTAR | Woburn | 2083212 | 1801 | 263 | PV | 325-03 | 2015-07-21 | 2015-07-22 | 1 | 3 | -2 | 2015-07-24 | 2015-09-02 | 28 | 194 | -166 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-16 | 2016-01-06 | 2016-02-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online | [5 empty] | Gov't | Y
NSTAR | Woburn | 2083239 | 1801 | 454 | PV | 211-H5 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-09-05 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-25 |  | 2016-03-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Woburn | 2083306 | 1801 | 265 | PV | 211-H10 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-08-12 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 |  | 2016-03-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Jamaica Plain | 2083371 | 2130 | 28 | PV | 496-H4 | 2015-07-23 | 2015-07-24 | 1 | 0 | 1 | 2015-07-28 | 2015-08-07 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2016-03-15 | 2016-08-25 | TBD | Expedited | 30 | 2016-08-04 | 2016-08-04 | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Rochester | 2083435 | 2770 | 20.52 | PV | 3-702-702 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2083555 | 2739 | 60 | PV | 2-304-304 | 2015-07-27 | 2015-07-29 | 2 | 0 | 2 | 2015-07-30 | 2015-07-30 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-03-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-05-05 | Online | [5 empty] | Private
NSTAR | Somerville | 2084293 | 2145 | 54 | PV | 250-1N81H1 | 2015-07-27 | 2015-07-28 | 1 | 0 | 1 | 2015-07-31 | 2015-08-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 |  | 2016-03-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-11-10 | Online | [5 empty] | Private
NSTAR | Roxbury | 2084347 | 2119 | 27 | PV | 323-05 | 2015-07-27 | 2015-07-31 | 4 | 0 | 4 | 2015-08-04 | 2015-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-20 | 2015-08-19 | 2016-03-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online | [5 empty] | Private
NSTAR | Needham | 2084378 | 2494 | 40 | PV | 148-H7 | 2015-07-28 | 2015-08-05 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-08-13 | Private
NSTAR | Acton | 2084724 | 1720 | 2000 | PV | 416-H2 | 2015-07-29 | 2015-08-03 | 3 | 0 | 3 | 2015-08-05 | 2016-01-20 | 120 | 108 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-22 | No | Expedited | 30 | 2016-05-11 |  | -30325 |  | 0 |  | 2016-06-08 |  | Withdrawn | [5 empty] | Private | N
NSTAR | Natick | 2085006 | 1760 | 492 | PV | 433-H9 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-05-19 | Online | [5 empty] | Private
NSTAR | Woburn | 2085086 | 1801 | 336 | PV | 258-1394H2 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Woburn | 2085091 | 1801 | 377 | PV | 258-1394H2 | 2015-07-30 | 2015-08-04 | 3 | 0 | 3 | 2015-08-06 | 2016-01-26 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-26 |  | 2017-02-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Woburn | 2085252 | 1801 | 624 | PV | 375-H12 | 2015-07-31 | 2015-08-01 | -1 | 0 | 0 | 2015-08-07 | 2016-03-23 | 163 | 142 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2085492 | 2790 | 2000 | PV | 2-524-524 | 2015-07-31 | 2015-08-04 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-08-17 | Gov't
NSTAR | Dorchester | 2085514 | 2125 | 4600 | Natural Gas | 511-1497H | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 | 2015-08-11 | 2015-09-15 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | East Freetown | 2086294 | 2717 | 1440 | PV | 2-102-604 | 2015-08-06 | 2015-08-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-09-28 | Private
NSTAR | Wareham | 2086312 | 2576 | 1440 | PV | 3-85-928 | 2015-08-05 | 2015-08-07 | 2 | 0 | 2 | 2015-08-11 | 2015-09-15 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Assonett | 2086459 | 2702 | 1440 | PV | 2-605-605 | 2013-11-25 | 2013-12-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-20 |  | Withdrawn
NSTAR | Acusnet | 2086742 | 2743 | 1990 | PV | 2-241-241 | 2015-08-07 | 2015-08-17 | 6 | 0 | 6 | 2015-09-28 |  | -30163 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-03-17 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2016-04-27 | Private
NSTAR | Acusnet | 2086776 | 2743 | 1000 | PV | 2-241-241 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2016-01-13 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2019-08-21 | 2016-03-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | [5 empty] | Private | N
NSTAR | Woburn | 2087191 | 1801 | 29 | PV | 211-H2 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-18 | 2015-10-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2017-01-05 | 2016-03-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online | [5 empty] | PRIVATE | N
NSTAR | Cambridge | 2087199 | 2138 | 171.1 | PV | 828-1105 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2015-08-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-27 | 2015-08-26 | 2016-03-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-26 | Online | [5 empty] | Private
NSTAR | Brewster | 2087387 | 2631 | 111 | PV | 4-95A-597 | 2015-08-14 | 2015-08-15 | -1 | 0 | 0 | 2015-08-21 | 2015-12-15 | 82 | 53 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acusnet | 2088074 | 2743 | 4000 | PV | 2-241-238 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-17 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2016-03-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Roxbury | 2088902 | 2120 | 75 | Natural Gas | 106-H8 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 | 2015-10-09 | 2016-03-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online | [5 empty] | Private
NSTAR | Boston | 2088913 | 2118 | 75 | Natural Gas | 106-H4 | 2015-08-19 | 2015-08-21 | 2 | 0 | 2 | 2015-08-25 | 2015-12-15 | 80 | 72 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-21 | 2015-10-09 | 2016-03-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online | [5 empty] | Private
NSTAR | Waltham | 2088991 | 2451 | 175 | PV | 282-H6 | 2015-08-20 | 2015-08-21 | 1 | 98 | -97 | 2015-08-25 | 2016-04-05 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-17 | Online | [5 empty] | Private
NSTAR | Boston | 2089121 | 2115 | 128 | PV | 492-1N14S | 2015-08-20 | 2015-08-20 | 0 | 0 | 0 | 2015-08-20 | 2015-08-25 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-10 |  | 2016-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online | [5 empty] | Private
NSTAR | Waltham | 2089144 | 2451 | 96 | PV | 450-H8 | 2015-08-21 | 2015-08-24 | 1 | 0 | 1 | 2015-08-26 | 2015-09-22 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-23 |  | 2016-03-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-01-05 | Online | [5 empty] | Private
NSTAR | Mashpee | 2089388 | 2649 | 90 | PV | 4-88-455 | 2015-08-24 | 2015-08-26 | 2 | 0 | 2 | 2015-08-28 | 2015-10-26 | 41 | 11 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Dover | 2089416 | 2030 | 27.75 | PV | 456-H3 | 2015-07-31 | 2015-08-11 | 7 |  | 7 | 2015-08-24 |  | -30138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-06-15 | [6 empty] | 0 |  | 0 |  |  | 2016-09-15 | Online
NSTAR | East Freetown | 2089453 | 2717 | 22.8 | PV | 2-102-102 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2089685 | 1741 | 216 | PV | 512-1399H1 | 2015-08-24 | 2015-08-27 | 3 | 0 | 3 | 2015-08-31 | 2015-09-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-24 |  | 2016-04-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Roxbury | 2089776 | 2119 | 33 | PV | 106-H5 | 2015-08-26 | 2015-08-27 | 1 | 44 | -43 | 2015-08-31 | 2015-12-21 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-05 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Arlington | 2090065 | 2476 | 118 | PV | 320-H7 | 2015-08-26 | 2015-08-27 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2090094 | 2360 | 4999 | PV | 3-012-012 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-08-31 | 2015-10-14 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-03 |  | 2016-11-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2090242 | 2744 | 843 | PV | 2-7-95 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-09-02 | 2015-10-27 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-04-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-04 | Online | [5 empty] | Private
NSTAR | Rochester | 2090360 | 2770 | 1000 | PV | 3-702-702 | 2015-08-27 | 2015-08-28 | 1 | 0 | 1 | 2015-08-31 | 2015-11-23 | 60 | 53 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-22 |  | 2016-04-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-12-14 | Customer Cost | [5 empty] | Private
NSTAR | Chatham | 2090556 | 2650 | 296 | PV | 4-95A-608 | 2015-08-28 | 2015-09-01 | 2 | 0 | 2 | 2015-09-02 |  | -30145 | 241 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-07 | TBD |  | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-09-03 | Gov't
NSTAR | Acton | 2090728 | 1720 | 420 | PV | 416-H4 | 2015-08-14 | 2015-09-01 | 12 | 0 | 12 | 2015-09-01 | 2015-09-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | [5 empty] | Private
NSTAR | Dartmouth | 2090751 | 2748 | 18 | PV | 2-524-524 | 2015-09-01 | 2015-09-02 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Sandwich | 2091380 | 2563 | 1476 | PV | 4-81A-439 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-08 | Online |  |  |  |  | 2015-09-28 | Private
NSTAR | Acusnet | 2092115 | 2743 | 2000 | PV | 2-241-238 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-09-28 | Private
NSTAR | Acusnet | 2092123 | 2743 | 2000 | PV | 2-241-238 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2015-11-09 | 41 | 29 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-09-29 |  |  | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2092354 | 2770 | 2000 | PV | 3-702-702 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2016-04-06 | 148 | 130 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2092534 | 2770 | 1000 | PV | 3-702-702 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-06-17 | Private
NSTAR | Wareham | 2092960 | 2571 | 5500 | PV | 3-82-82 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online |  |  |  |  | 2016-04-25 | Private
NSTAR | Wareham | 2093002 | 2571 | 4000 | PV | 3-83-83 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Canton | 2093030 | 2021 | 990 | PV | 470-H7 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2015-10-13 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-17 | 2016-03-09 | 2016-05-27 | No | Expedited | 30 | 2016-02-24 |  | -30270 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Holliston | 2093131 | 1746 | 990 | PV | 65-H2 | 2015-09-09 | 2015-09-10 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online | [5 empty] | Private
NSTAR | Fairhaven | 2093189 | 2719 | 2000 | PV | 2-221-221 | 2015-09-09 | 2015-09-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-05 | Online | [5 empty] | Private
NSTAR | Carver | 2093250 | 2330 | 990 | PV | 3-10-929 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2016-03-19 | 134 | 37 | 97 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 |  | 2016-04-19 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2019-01-23 | Online | [5 empty] | Private
NSTAR | Somerville | 2093280 | 2145 | 999 | PV | 250-H3 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-10 |  | -30151 |  | 0 |  |  | 0 | 0 | 0 | 2015-09-15 | 2015-10-16 | 23 | 2 | 21 | 2016-02-19 |  | -30267 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 | 2016-02-04 | [6 empty] | 0 |  | 0 |  |  | 2017-05-02 | Online | [5 empty] | Private | N
NSTAR | Acton | 2093456 | 1720 | 750 | PV | 416-H1 | 2015-09-10 | 2015-09-14 | 2 | 0 | 2 | 2015-09-15 | 2016-01-26 | 95 | 54 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-07-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2093470 | 2746 | 990 | PV | 2-38-38 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-15 | 2015-10-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-28 | 2017-05-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Milton | 2093526 | 2186 | 512 | PV | 496-H1XY | 2015-09-11 | 2015-09-15 | 2 | 0 | 2 | 2015-09-18 | 2015-10-26 | 26 | 205 | -179 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-10-27 | Private
NSTAR | Waltham | 2093779 | 2451 | 1000 | PV | 450-H3 | 2015-09-14 | 2015-09-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Acton | 2093910 | 1720 | 1940 | PV | 416-H1 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-08 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Falmouth | 2093955 | 2540 | 19 | PV | 4-76-436 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-16 | 2015-09-28 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 | 2015-10-30 | 2016-01-20 | TBD | Expedited | 30 | 2016-01-04 | 2016-01-04 | 0 |  | 0 |  | 2016-01-26 |  | Withdrawn | [5 empty] | Private
NSTAR | Dennis | 2094068 | 2660 | 300 | PV | 4-92B-92B | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 | 2016-06-06 | 2016-11-18 | No | Expedited | 30 | 2016-06-06 |  | -30343 |  | 0 |  | 2016-06-06 | 2016-01-26 | Online | [5 empty] | Private
NSTAR | Lexington | 2094085 | 2421 | 815 | PV | 320-H2 | 2015-08-20 | 2015-08-26 | 4 |  | 4 | 2015-09-15 |  | -30154 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-17 | 2015-11-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-08 | Online
NSTAR | Waltham | 2094179 | 2451 | 1200 | Natural Gas | 373-1358 | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-09-28 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2016-02-25 | 2016-03-30 | TBD | Expedited | 30 | 2016-02-25 | 2016-02-25 | 0 |  | 0 |  |  | 2016-04-14 | Online | [5 empty] | Private
NSTAR | Harwich | 2094563 | 2671 | 72 | PV | 4-85-592 | 2015-09-16 | 2015-09-17 | 1 | 0 | 1 | 2015-09-22 | 2015-10-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-15 |  | 2016-04-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Somerville | 2094631 | 2145 | 24 | PV | 250-H4XY | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-10-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-14 |  | 2016-04-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-03-30 | Online | [5 empty] | Private
NSTAR | Natick | 2094705 | 1760 | 75 | PV | 433-H11 | 2015-09-16 | 2015-09-21 | 3 | 0 | 3 | 2015-09-23 | 2015-10-07 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-06 |  | 2016-04-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online | [5 empty] | Private
NSTAR | Burlington | 2094742 | 1803 | 100 | PV | 211-H13 | 2015-09-17 | 2015-09-21 | 2 | 0 | 2 | 2015-09-23 | 2016-01-19 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-04-07 | 2016-06-24 | No | Expedited | 30 | 2016-05-18 |  | -30330 |  | 0 |  | 2015-10-14 |  | Awaiting Completion Docs | [5 empty] | Private | N
NSTAR | Monument Beach | 2094911 | 2553 | 496 | PV | 4-86-408 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-23 | 2016-04-12 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-09 | 2016-02-09 | 2016-05-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-30 | Online | [5 empty] | Private
NSTAR | Mashpee | 2095832 | 2649 | 264 | PV | 4-88-455 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-28 | 2015-10-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2015-12-02 | 2016-01-29 | TBD | Expedited | 30 | 2015-12-30 | 2015-12-30 | 0 |  | 0 | [9 empty] | Private
NSTAR | Brookline | 2095914 | 2467 | 32 | PV | 496-H4 | 2015-09-24 | 2015-09-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage | [5 empty] | Private
NSTAR | Woburn | 2096036 | 1801 | 499.8 | PV | 375-H12 | 2015-09-04 | 2015-09-09 | 3 |  | 3 | 2015-09-24 |  | -30161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-25 | 2015-11-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-10 | Online | [5 empty] | PRIVATE
NSTAR | Plymouth | 2096227 | 2360 | 4000 | PV | 3-88-924 | 2015-09-25 | 2015-09-26 | -1 | 0 | 0 | 2015-09-30 | 2016-04-28 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Holliston | 2096409 | 1746 | 476 | PV | 274-H1 | 2015-09-25 | 2015-09-28 | 1 | 0 | 1 | 2015-09-30 | 2015-11-20 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-01-21 | 2016-06-30 | No | Expedited | 30 | 2016-04-07 | 2016-04-07 | 0 |  | 0 |  | 2016-06-24 |  | Withdrawn | [5 empty] | Private
NSTAR | Mashpee | 2096431 | 2649 | 371 | PV | 4-77A-454 | 2015-09-25 | 2015-09-28 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Bellingham | 2096445 | 2019 | 984 | PV | 65-H4 | 2015-09-28 | 2015-09-30 | 2 | 2 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-12 | 2016-10-11 | 2016-05-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hopkinton | 2096675 | 1748 | 170 | PV | 126-H1 | 2015-09-28 | 2015-09-30 | 2 | 0 | 2 | 2015-10-05 | 2015-10-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-05 |  | 2016-05-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online | [5 empty] | Private
NSTAR | New Bedford | 2096734 | 2746 | 157 | PV | 2-87-135 | 2015-10-01 | 2015-10-02 | 1 | 8 | -7 | 2015-10-16 | 2015-11-02 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-05 | 2016-10-09 |  | No | Expedited | 30 |  |  | 0 |  | 0 |  | 2016-03-10 | 2016-04-29 | Online | [5 empty] | Private | Y
NSTAR | Natick | 2097431 | 1760 | 207 | PV | 433-H7 | 2015-10-01 | 2015-10-02 | 1 | 0 | 1 | 2015-10-05 | 2015-10-27 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Westport | 2097455 | 2790 | 32.85 | PV | 2-523-523 | 2015-09-22 | 2015-09-24 | 2 |  | 2 | 2015-10-02 |  | -30167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-10-29 | 2015-11-30 | [6 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online | [5 empty] | Private | Y
NSTAR | New Bedford | 2097474 | 2746 | 360 | PV | 2-134-134 | 2015-10-02 | 2015-10-05 | 1 | 0 | 1 | 2015-10-07 | 2015-10-29 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-10-30 | 2016-05-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-03 | Online | [5 empty] | Private
NSTAR | Somerville | 2097809 | 2144 | 20 | PV | 227-51H2 | 2015-10-05 | 2015-10-06 | 1 | 0 | 1 | 2015-10-12 | 2016-03-17 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-13 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Bourne | 2098326 | 2532 | 4800 | Natural Gas | 4-81A-81A | 2015-10-05 | 2015-10-09 | 4 | 0 | 4 | 2015-10-14 | 2015-10-20 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2015-11-11 | 2016-06-15 | TBD | Expedited | 30 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Mattapoisett | 2098384 | 2739 | 25 | WIND | 2-301-301 | 2015-10-05 | 2015-10-09 | 4 | 73 | -69 | 2015-10-14 | 2016-06-14 | 174 | 0 | 174 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-05-13 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Woburn | 2098750 | 1801 | 252 | PV | 211-H5 | 2015-10-06 | 2015-10-08 | 2 | 0 | 2 | 2015-10-12 | 2016-02-18 | 93 | 18 | 75 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-06 | 2016-05-13 | 2016-11-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-12 | Online | [5 empty] | Private
NSTAR | Dedham | 2099070 | 2026 | 765 | PV | 20-H2 | 2015-10-07 | 2015-10-08 | 1 | 0 | 1 | 2015-10-14 | 2016-05-02 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-04 | Online | [5 empty] | Private
NSTAR | Plymouth | 2099348 | 2360 | 420 | PV | 3-12-12 | 2015-10-08 | 2015-10-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plympton | 2099482 | 2367 | 880 | PV | 3-51-901 | 2015-10-08 | 2015-10-21 | 9 | 0 | 9 | 2015-10-27 | 2015-11-17 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-01 |  | 2016-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sudbury | 2099532 | 1776 | 42 | PV | 342-H2 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2015-11-16 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 |  | 2016-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Woburn | 2099592 | 1801 | 84 | PV | 211-01 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2016-01-25 | 73 | 57 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-14 |  | 2016-05-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Burlington | 2099699 | 1803 | 360 | PV | 391-H15 | 2015-10-08 | 2015-10-14 | 4 | 1 | 3 | 2015-10-16 | 2016-08-01 | 206 | 0 | 206 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-05-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2099704 | 2360 | 996 | PV | 31313 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-19 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-09-06 | Online | [5 empty] | Private
NSTAR | Woburn | 2100110 | 1801 | 360 | PV | 258-1394H2 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-12 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-05-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Woburn | 2100120 | 1801 | 480 | PV | 258-1394H2 | 2015-10-14 | 2015-10-15 | 1 | 0 | 1 | 2015-10-19 | 2016-01-08 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-13 |  | 2016-05-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Woburn | 2100528 | 1801 | 40 | PV | 258-1394H4 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2016-01-25 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Bourne | 2101008 | 2532 | 468 | PV | 4-86-402 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-20 | 2015-10-20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 |  | 2016-05-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 | 2017-04-03 |  | 2017-04-11 | Online | [5 empty] | Private
NSTAR | Westport | 2101010 | 2790 | 19 | PV | 2-523-523 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2015-11-23 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-11 | 2016-01-11 | 2016-04-15 | No | Expedited | 30 | 2016-03-11 |  | -30282 |  | 0 |  |  | 2016-12-07 | Online | [5 empty] | Private | N
NSTAR | Waltham | 2101013 | 2453 | 126 | PV | 467-H8 | 2015-10-20 | 2015-10-21 | 1 | 0 | 1 | 2015-10-27 | 2016-03-31 | 112 | 102 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-16 | Online | [5 empty] | PRIVATE
NSTAR | Medway | 2101737 | 2053 | 504 | PV | 65-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2102041 | 1773 | 20 | PV | 320-H1 | 2015-10-21 | 2015-10-22 | 1 | 0 | 1 | 2015-10-23 | 2015-10-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Dartmouth | 2102045 | 2747 | 98 | PV | 2-543-543 | 2015-10-23 | 2015-10-24 | -1 | 0 | 0 | 2015-11-03 | 2016-06-27 | 169 | 157 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acton | 2102432 | 1720 | 830 | PV | 416-H1 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-27 | 2016-08-01 | 199 | 26 | 173 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 |  | 2016-06-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | [5 empty] | Private
NSTAR | Wareham | 2102456 | 2576 | 600 | PV | 3-85-85 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-28 | 2016-01-29 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 | 2016-03-08 | 2017-01-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | New Bedford | 2102526 | 2745 | 928 | PV | 2-88-88 | 2015-10-23 | 2015-10-26 | 1 | 0 | 1 | 2015-10-28 | 2016-02-10 | 75 | 57 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Chatham | 2102528 | 2650 | 88 | PV | 4-95A-608 | 2015-10-23 | 2015-10-24 | -1 | 0 | 0 | 2015-10-27 | 2016-04-19 | 125 | 112 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Assonett | 2102530 | 2702 | 1992 | PV | 2-605-605 | 2015-10-23 | 2015-10-24 | -1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Falmouth | 2102531 | 2536 | 48 | PV | 4-98A-98A | 2015-10-26 | 2015-10-29 | 3 | 0 | 3 | 2015-10-29 | 2016-02-12 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-07-14 | Online | [5 empty] | Private
NSTAR | Pocasset | 2102746 | 2559 | 27 | PV | 4-81A-81A | 2015-10-27 | 2015-10-29 | 2 | 0 | 2 | 2015-11-02 | 2015-12-29 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-15 | 2016-02-10 | 2016-07-15 | TBD | Expedited | 30 | 2016-06-09 | 2016-06-09 | 0 |  | 0 |  |  | 2016-07-22 | Online | [5 empty] | Private
NSTAR | Canton | 2102821 | 2021 | 324.6 | PV | 470-H8 | 2015-10-09 | 2016-10-16 | 265 |  | 265 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-25 | 2016-05-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online | [5 empty] | PRIVATE
NSTAR | Jamaica Plain | 2103067 | 2130 | 17 | PV | 554-79H1 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-13 | 115 | 0 | 115 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Plymouth | 2103303 | 2360 | 5976 | PV | 3-73-73 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-05 | 109 | 15 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Assonett | 2103346 | 2702 | 984 | PV | 2-605-605 | 2015-10-29 | 2015-11-04 | 4 | 0 | 4 | 2015-11-03 |  | -30189 | 199 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-11-04 | Private
NSTAR | West Tisbury | 2103349 | 2575 | 233.1 | PV | 4-97-220 | 2015-10-15 | 2015-10-23 | 6 |  | 6 | 2015-10-29 |  | -30186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-12-07 | [7 empty] | 0 |  | 0 | 2017-03-23 | 2017-03-23 | 2017-04-10 | Online | [5 empty] | PRIVATE
NSTAR | Rochester | 2103573 | 2770 | 2000 | PV | 3-703-703 | 2015-10-29 | 2015-11-04 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-11-04 | Private
NSTAR | Rochester | 2103577 | 2770 | 3000 | PV | 3-702-702 | 2015-11-03 | 2015-11-03 | 0 | 0 | 0 | 2015-11-09 | 2015-11-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-31 |  | 2016-06-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2104785 | 1760 | 36 | PV | 433-H11 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-10-25 | Online | [5 empty] | Private
NSTAR | Provincetown | 2104938 | 2657 | 168 | PV | 4-96-674 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2016-04-18 | 115 | 46 | 69 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 |  | 2016-06-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage | [5 empty] | Private
NSTAR | Somerville | 2104944 | 2143 | 996 | PV | 387-148H2 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | Provincetown | 2104946 | 2657 | 124 | PV | 4-96-674 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-12-07 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 | 2015-12-07 | 2016-06-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-03-21 | Online | [5 empty] | Private
NSTAR | Hyannis | 2105424 | 2601 | 96 | PV | 4-84A-520 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-11-27 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-04 | 2016-02-12 | 2016-03-31 | TBD | Expedited | 30 | 2016-03-31 | 2016-03-31 | 0 |  | 0 |  |  | 2016-04-26 | Online | [5 empty] | Private
NSTAR | Provincetown | 2105431 | 2657 | 100 | PV | 4-96-676 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2016-02-18 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-14 |  | 2016-06-15 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Canton | 2105434 | 2021 | 630 | PV | 269-1320H1 | 2015-11-05 | 2015-11-09 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | South Boston | 2105436 | 2210 | 2280 | PV | 106-H1 | 2015-11-10 | 2015-11-11 | 1 | 0 | 1 | 2015-11-18 | 2016-04-19 | 109 | 24 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online | [5 empty] | Private
NSTAR | Assonett | 2106271 | 2702 | 1992 | PV | 2-605-605 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-02 | 10 | 0 | 10 |  |  | 0 | 4 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2106576 | 2360 | 21.07 | PV | 3-14-931 | 2015-10-27 | 2015-10-28 | 1 |  | 1 | 2015-11-17 |  | -30199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-01-29 | [6 empty] | 0 |  | 0 |  |  | 2016-03-10 | Online
NSTAR | Carver | 2106584 | 2330 | 28 | PV | 3-10-929 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-09 |  | 2016-06-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online | [5 empty] | Private | N
NSTAR | Woburn | 2106588 | 1801 | 85 | PV | 375-H3 | 2015-11-13 | 2015-11-17 | 2 | 0 | 2 | 2015-11-18 | 2016-03-25 | 92 | 34 | 58 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-27 |  | 2016-06-22 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Norfolk | 2106809 | 2056 | 186.5 | PV | 146-H3 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-16 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-24 |  | 2016-06-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-14 | Online | [5 empty] | Private
NSTAR | Westport | 2107466 | 2790 | 36 | PV | 2-523-523 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-11-30 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2107468 | 2747 | 72 | PV | 2-543-543 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-03 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 |  | 2016-06-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online | [5 empty] | Gov't
NSTAR | Hopkinton | 2107469 | 1748 | 87 | PV | 65-H7 | 2015-11-18 | 2015-11-19 | 1 | 0 | 1 | 2015-11-20 |  | -30202 | 187 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2015-11-23 | Private
NSTAR | Carver | 2107748 | 2330 | 5966 | PV & Battery | 3-83-83 | 2015-11-19 | 2015-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online |  |  |  |  | 2015-11-25 | Private
NSTAR | East Freetown | 2108032 | 2717 | 4000 | PV | 2-102-102 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-12-08 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-23 | 2016-06-24 | No | Expedited | 30 | 2016-04-08 | 2016-04-08 | 0 |  | 0 |  |  |  | Meter | [5 empty] | Private | N
NSTAR | Wellfleet | 2108544 | 2663 | 50 | PV | 4-94B-653 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-11-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-03 | 2016-06-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online | [5 empty] | Gov't
NSTAR | Truro | 2108546 | 2652 | 30 | PV | 4-96-674 | 2015-11-25 | 2015-11-26 | 1 | 0 | 1 | 2015-12-03 | 2015-12-07 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 | 2017-11-28 | 2016-07-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-01-10 | Online | [5 empty] | Private
NSTAR | Hyannis | 2108876 | 2601 | 120 | PV | 4-84B-524 | 2015-12-03 | 2015-12-04 | 1 | 18 | -17 | 2015-12-08 | 2016-01-25 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Plymouth | 2108966 | 2360 | 23.75 | PV | 3-89-926 | 2015-11-24 | 2015-11-24 | 0 |  | 0 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-07-26 | Online
NSTAR | West Tisbury | 2109230 | 2575 | 213.2 | PV | 4-97-220 | 2015-11-17 | 2015-11-30 | 9 |  | 9 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-11-30 | Online
NSTAR | Cambridge | 2109233 | 2138 | 26.6 | PV | 821-05 | 2015-11-10 | 2015-11-10 | 0 |  | 0 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-11 | 2016-01-19 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Milton | 2109234 | 2186 | 32.4 | PV | 496-H7 | 2015-11-06 | 2015-11-30 | 16 |  | 16 | 2015-12-11 |  | -30217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-06-10 | Online
NSTAR | Plymouth | 2110218 | 2360 | 394.8 | PV | 3-14-931 | 2015-11-17 | 2015-11-17 | 0 |  | 0 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-10 | [6 empty] | 0 |  | 0 |  |  | 2016-11-08 | Online | [5 empty] | PRIVATE
NSTAR | Hyde Park | 2110822 | 2136 | 1200 | PV | 344-07 | 2015-12-03 | 2015-12-04 | 1 | 0 | 1 | 2015-12-08 | 2016-07-18 | 159 | 86 | 73 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2110823 | 2790 | 1000 | PV | 2-523-523 | 2015-12-07 | 2015-12-08 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2015-12-16 | Private
NSTAR | East Freetown | 2113074 | 2717 | 2000 | PV | 2-102-604 | 2015-12-09 | 2015-12-11 | 2 |  | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 | 2018-12-12 | 2018-12-13 | 2018-12-13 | Online | [5 empty] | Private
NSTAR | Sudbury | 2114162 | 1776 | 15.5 | PV | 342-H7 | 2015-10-19 | 2015-10-20 | 1 |  | 1 | 2015-12-11 |  | -30217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-15 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Acton | 2114164 | 1720 | 17 | PV | 416-H8 | 2015-12-09 | 2015-12-11 | 2 | 0 | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Ashland | 2114171 | 1721 | 17 | PV | 519-175H1 | 2015-12-14 | 2015-12-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2114406 | 2330 | 17.5 | PV | 3-83-950 | 2015-11-19 | 2016-01-05 | 33 |  | 33 | 2016-02-11 |  | -30261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online | [5 empty] | PRIVATE
NSTAR | Carver | 2114902 | 2330 | 499 | PV | 3-10-929 | 2015-12-14 | 2015-12-22 | 6 | 0 | 6 | 2015-12-23 | 2015-12-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-10 | 2016-07-04 | 2016-07-21 | TBD | Expedited | 30 | 2016-07-06 | 2016-07-06 | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Plymouth | 2114928 | 2360 | 57 | PV | 3-89-922 | 2015-12-14 | 2015-12-15 | 1 | 0 | 1 | 2015-12-16 | 2016-04-26 | 94 | 74 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-07-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Rochester | 2114929 | 2770 | 392 | PV | 3-702-702 | 2015-12-15 | 2015-12-15 | 0 | 1 | 0 | 2015-12-18 | 2016-01-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 | 2016-05-25 | 2016-07-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | [5 empty] | Private
NSTAR | Holliston | 2115036 | 1746 | 21 | PV | 274-H1 | 2015-12-16 | 2015-12-18 | 2 | 0 | 2 | 2015-12-22 | 2016-01-14 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-20 |  | 2016-07-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online | [5 empty] | Private
NSTAR | Dover | 2115395 | 2030 | 20 | PV | 456-H5 | 2015-12-16 | 2015-12-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | [5 empty] | Private | N
NSTAR | Canton | 2115399 | 2021 | 432 | PV | 470-H11 | 2015-12-17 | 2015-12-18 | 1 | 21 | -20 | 2015-12-22 | 2016-02-03 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-05-04 |  | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-19 | Online | [5 empty] | Private
NSTAR | Boston | 2115948 | 2110 | 75 | Natural Gas | 12-1N82N | 2015-12-17 | 2015-12-17 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2016-02-01 | Private
NSTAR | Cambridge | 2115956 | 2139 | 1000 | Natural Gas | 875-1N35B | 2015-12-18 | 2015-12-19 | -1 | 0 | 0 | 2015-12-24 | 2016-01-18 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Canton | 2116306 | 2021 | 396 | PV | 470-H4 | 2015-12-18 | 2015-12-22 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | [5 empty] | Private
NSTAR | Carver | 2116312 | 2330 | 2000 | PV | 3-10-929 | 2015-12-18 | 2015-12-22 | 2 | 0 | 2 | 2015-12-30 |  | -30230 | 155 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2019-02-28 | Online |  |  |  |  | 2016-01-11 | Private
NSTAR | Wareham | 2116332 | 2538 | 7450 | PV | 3-84-961 | 2015-12-22 | 2016-01-15 | 18 | 0 | 18 | 2016-01-15 | 2016-04-16 | 65 | 54 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Brewster | 2116973 | 2631 | 82 | PV | 4-89A-553 | 2015-12-22 | 2015-12-23 | 1 | 0 | 1 | 2015-12-29 | 2015-12-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 |  | 2016-07-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-21 | Online | [5 empty] | Private
NSTAR | Lexington | 2116975 | 2421 | 20.35 | PV | 320-H5XY | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-23 |  | -30225 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-27 | 2016-04-19 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online | [5 empty] | PRIVATE
NSTAR | Acusnet | 2116976 | 2743 | 16 | PV | 2-241-237 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | North Dartmouth | 2117201 | 2747 | 19.3 | PV | 2-107-107 | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-24 |  | -30226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2016-01-03 | Online | [5 empty] | PRIVATE
NSTAR | Duxbury | 2117204 | 2332 | 360 | PV | 3-27-970 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-08-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Duxbury | 2117207 | 2332 | 480 | PV | 3-26-903 | 2015-12-24 | 2015-12-29 | 3 | 13 | -10 | 2016-01-05 |  | -30234 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-08-02 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Kingston | 2117310 | 2364 | 600 | PV | 3-26-902 | 2015-12-29 | 2015-12-30 | 1 | 2 | -1 | 2016-01-05 | 2016-07-19 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-12-31 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-19 | Online | [5 empty] | Private
NSTAR | Plymouth | 2117742 | 2360 | 21.4 | PV | 3-73-27J2 | 2015-12-09 | 2016-12-10 | 262 |  | 262 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-12 | [6 empty] | 0 |  | 0 |  |  | 2016-03-17 | Online
NSTAR | Woburn | 2117752 | 1810 | 42.3 | PV | 211-H2 | 2015-12-01 | 2015-12-28 | 19 |  | 19 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Yarmouth | 2117763 | 2664 | 19.3 | PV | 4-90-90 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2117764 | 2030 | 1000 | PV | 456-H4 | 2015-12-30 | 2016-01-01 | 2 | 0 | 2 | 2016-01-06 | 2016-05-31 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-08-05 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Boston | 2117954 | 2118 | 587 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2117955 | 2118 | 471 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2119971 | 2180 | 16.95 | PV | 375H8 | 2016-12-17 | 2016-12-22 | 4 |  | 4 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-06-27 | Online
NSTAR | New Bedford | 2119973 | 2740 | 248.88 | PV | 2-137-139 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2119974 | 2746 | 280 | PV | 2-80-80 | 2016-01-05 | 2016-01-08 | 3 | 5 | -2 | 2016-01-11 | 2016-02-09 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-23 | 2016-03-28 | 2016-08-10 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online | [5 empty] | Private
NSTAR | Natick | 2120155 | 1760 | 457 | PV | 240-H1 | 2016-01-05 | 2016-01-08 | 3 | 0 | 3 | 2016-01-11 | 2016-01-11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-21 |  | 2016-08-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-06 | Online | [5 empty] | Gov't
NSTAR | Natick | 2120191 | 1760 | 24.8 | PV | 2302 | 2016-12-22 | 2016-12-26 | 2 |  | 2 | 2016-01-08 |  | -30237 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-28 | 2016-01-28 | [6 empty] | 0 |  | 0
NSTAR | Natick | 2120194 | 1760 | 120 | PV | 23-H1 | 2016-01-06 | 2016-01-08 | 2 | 0 | 2 | 2016-01-11 | 2016-02-10 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-11 | 2016-02-11 | 2016-08-11 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | Private
NSTAR | Edgartown | 2120504 | 2539 | 36 | PV | 4-97-97 | 2016-01-11 | 2016-01-26 | 11 | 0 | 11 | 2016-01-26 | 2016-01-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2016-06-25 | TBD | Expedited | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  | 2016-06-08 | Online | [5 empty] | Private
NSTAR | Woburn | 2120505 | 1801 | 16.7 | PV | 375-H11 | 2015-11-05 | 2015-11-08 | 1 |  | 1 | 2016-01-08 |  | -30237 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-23 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | [5 empty] | PRIVATE
NSTAR | Wareham | 2122405 | 2576 | 16.5 | PV | 3-86-966 | 2015-12-04 | 2016-01-07 | 24 |  | 24 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-03-11 | Online
NSTAR | Sharon | 2122406 | 2067 | 17.5 | PV | 470-h12 | 2015-12-02 | 2016-01-07 | 26 |  | 26 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-12 | 2016-03-23 | [6 empty] | 0 |  | 0 |  |  | 2016-04-29 | Online
NSTAR | Maynard | 2122407 | 1754 | 32.85 | PV | 416-H6 | 2016-12-21 | 2017-01-05 | 11 |  | 11 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-10-21 | Online
NSTAR | Framingham | 2122694 | 1701 | 328.75 | CHP | 433-H1 | 2016-01-04 | 2016-03-16 | 52 |  | 52 | 2016-01-12 |  | -30239 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-10-19 | [6 empty] | 0 |  | 0 |  |  | 2017-04-04 | Online | [5 empty] | NO EXPORT
NSTAR | Plympton | 2122696 | 2367 | 24 | PV | 3-51-901 | 2016-01-13 | 2016-01-15 | 2 | 0 | 2 | 2016-01-18 | 2016-02-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-23 |  | 2016-08-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | [5 empty] | Private
NSTAR | Brewster | 2122697 | 2631 | 73.2 | PV | 4-89B-89B | 2016-01-05 | 2016-01-08 | 3 |  | 3 | 2016-01-27 |  | -30250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-17 | 2016-02-25 | [6 empty] | 0 |  | 0 |  |  | 2016-07-11 | Online
NSTAR | Acton | 2123114 | 2747 | 17.6 | PV | 416-H4 | 2016-01-04 | 2016-01-05 | 1 |  | 1 | 2016-01-13 |  | -30240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-03-03 | [6 empty] | 0 |  | 0 |  |  | 2016-03-24 | Online
NSTAR | Marshfield | 2123118 | 2050 | 19.35 | PV | 3-25-42J2 | 2016-12-23 | 2017-01-11 | 13 |  | 13 | 2017-01-15 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-10 | 2016-02-11 | [6 empty] | 0 |  | 0
NSTAR | Charlestown | 2123364 | 2129 | 30 | PV | 250-H5 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-01-27 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-01 | 2016-08-19 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Edgartown | 2123548 | 2539 | 36 | PV | 4-97-97 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-03-14 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-12 | 2016-08-19 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | [5 empty] | Private
NSTAR | Lexington | 2123559 | 2421 | 720 | PV | 2-1N11 | 2016-01-15 | 2016-01-19 | 2 | 7 | -5 | 2016-01-21 | 2016-03-21 | 42 | 9 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-06 |  | 2016-08-22 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private | N
NSTAR | Marston Mills | 2123807 | 2648 | 19.3 | PV | 4-88-478 | 2012-01-11 | 2016-01-15 | 1013 |  | 1013 | 2016-01-19 |  | -30244 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-10 | 2016-03-15 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2123809 | 1803 | 672 | PV | 391-H16 | 2016-01-20 | 2016-01-22 | 2 | 0 | 2 | 2016-01-27 |  | -30250 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-08-25 | No |  | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review
NSTAR | West Tisbury | 2124323 | 2575 | 33.9 | PV | 4-97-97 | 2016-01-13 | 2016-01-15 | 2 |  | 2 | 2016-01-20 |  | -30245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-03 | 2016-02-17 | [6 empty] | 0 |  | 0 |  |  | 2016-08-05 | Online
NSTAR | Cambridge | 2124635 | 2139 | 4400 | Natural Gas | 831-1110 | 2016-01-06 | 2016-01-07 | 1 | 0 | 1 | 2016-01-27 |  | -30250 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-06-07 | 2017-08-11 |  | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2020-12-14 | Online | [5 empty] | Private
NSTAR | Hatchville | 2124636 | 2536 | 1500 | PV | 4-98A-98A | 2016-01-21 | 2016-01-22 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-02-16 | Private
NSTAR | Dedham | 2124992 | 2026 | 1740 | PV | 344-1413H1 | 2016-01-21 | 2016-01-25 | 2 | 0 | 2 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 |  |  | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-11-16 | Online | [5 empty] | Private
NSTAR | Sagamore Beach | 2124995 | 2562 | 150 | PV | 3-89-925 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-03-22 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-02-17 | 2016-08-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online | [5 empty] | Private | N
NSTAR | Chelsea | 2125197 | 2150 | 491 | PV | 488-H2 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-02-19 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-04-28 | Online | [5 empty] | Private
NSTAR | Ashland | 2125198 | 1721 | 90 | PV | 519-175H1 | 2016-01-25 | 2016-01-26 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-10 | Online | [5 empty] | Private
NSTAR | Holliston | 2125460 | 1746 | 432 | PV | 274-H1 | 2016-01-25 | 2016-01-26 | 1 | 0 | 1 | 2016-01-28 | 2016-03-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-30 |  | 2016-08-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Dorchester | 2125462 | 2124 | 300 | PV | 311-07 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 | 2016-02-01 | 2016-02-19 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 |  | 2016-09-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-10-19 | Online | [5 empty] | Private
NSTAR | Bedford | 2125698 | 1730 | 16.7 | PV | 533-H8 | 2016-12-31 | 2017-01-06 | 5 |  | 5 | 2017-01-27 |  | -30512 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-11 | 2016-03-14 | [6 empty] | 0 |  | 0 |  |  | 2016-09-06 | Online | [5 empty] | PRIVATE
NSTAR | Falmouth | 2125878 | 2540 | 250 | PV | 10494/020 | 2016-01-28 | 2016-01-29 | 1 | 0 | 1 | 2016-02-01 | 2016-06-06 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-20 |  | 2016-09-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Needham | 2126109 | 2494 | 828 | PV | 148-H6 | 2016-01-29 | 2016-02-01 | 1 | 0 | 1 | 2016-02-04 | 2016-02-22 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 |  | 2016-09-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | [6 empty] | Private
NSTAR | Hyde Park | 2126261 | 2136 | 5 | PV | 6006 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2126313 | 1748 | 6 | PV | 65-H6 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-30 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 |  | 2016-09-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Woburn | 2126828 | 1801 | 168 | PV | 375-H3 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2017-04-18 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-02-16 | Online | [5 empty] | Private
NSTAR | Hyde Park | 2126908 | 2136 | 168 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2016-03-18 | 2016-09-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-02 | Online | [5 empty] | Private
NSTAR | Hyde Park | 2126921 | 2136 | 192 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2017-04-18 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online | [5 empty] | Private
NSTAR | Hyde Park | 2126922 | 2136 | 288 | PV | 344-1411H2 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-05-19 | 74 | 31 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-12 | 2017-04-18 |  | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online | [5 empty] | Private
NSTAR | Woburn | 2126923 | 1801 | 726 | PV | 375-H14 | 2016-02-02 | 2016-02-02 | 0 | 0 | 0 | 2016-02-08 | 2016-05-06 | 64 | 35 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-09-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Bedford | 2127134 | 1730 | 370 | PV | 322-1397H1 | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-07-20 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Bourne | 2127227 | 2532 | 1000 | PV | 4-98A-98A | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-04-04 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 |  | 2016-09-08 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Burlington | 2127236 | 1803 | 170 | PV | 211-H13 | 2016-02-04 | 2016-02-05 | 1 | 0 | 1 | 2016-02-15 | 2016-07-11 | 105 | 91 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Millis | 2127532 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127571 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127590 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127594 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127596 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127597 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Oak Bluffs | 2127808 | 2568 | 566.1 | PV | 4-75-75 | 2016-01-14 | 2016-01-20 | 4 |  | 4 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-07 | [6 empty] | 0 |  | 0
NSTAR | Maynard | 2127819 | 1754 | 750 | PV | STA207 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | West Roxbury | 2127824 | 2132 | 40 | PV | 468-01 | 2016-02-05 | 2016-02-08 | 1 | 0 | 1 | 2016-02-10 | 2016-03-01 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Falmouth | 2128032 | 2536 | 16.7 | PV | 4-98B-845 | 2016-02-09 | 2016-02-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-03-09 | Private
NSTAR | New Bedford | 2128034 | 2740 | 17.45 | PV | 2.3.96 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-26 | 2016-03-07 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2128036 | 2332 | 20.25 | PV | 3-27-970 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-11 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-13 | Online
NSTAR | Hyde Park | 2128422 | 2136 | 540 | PV | 344-1413H1 | 2016-02-09 | 2016-02-10 | 1 | 0 | 1 | 2016-02-12 | 2016-02-22 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 | 2016-06-06 | 2016-09-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dennisport | 2128423 | 2639 | 72 | PV | 4-92B-572 | 2016-02-10 | 2016-02-11 | 1 | 0 | 1 | 2016-02-15 | 2016-02-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-09-16 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-23 | Online | [5 empty] | Private
NSTAR | Edgartown | 2128645 | 2539 | 72 | PV | 4-97-97 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-31 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 |  | 2016-09-19 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-09-22 | Online | [5 empty] | Private
NSTAR | Woburn | 2128688 | 1801 | 53 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2128797 | 2021 | 19 | PV | 470-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-09 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-07-12 | 2016-09-19 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | [5 empty] | Private
NSTAR | Brighton | 2128801 | 2135 | 111 | PV | 329-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 |  | -30266 | 129 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-19 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online |  |  |  |  | 2016-02-18 | Private
NSTAR | Wareham | 2128802 | 2571 | 1992 | PV | 3-83-966 | 2016-02-12 | 2016-02-16 | 2 | 0 | 2 | 2016-02-23 | 2016-03-08 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 |  | 2016-09-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2129051 | 2790 | 25 | PV | 2-532-532 | 2016-02-12 | 2016-02-17 | 3 | 0 | 3 | 2016-02-23 | 2016-05-26 | 67 | 63 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-27 |  | 2016-09-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Gov't
NSTAR | Newton | 2129052 | 2459 | 104 | PV | 292-H8 | 2016-02-12 | 2016-02-13 | -1 | 0 | 0 | 2016-02-23 | 2016-05-27 | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2016-05-31 | 2016-09-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-09 | Online | [5 empty] | Private
NSTAR | Acusnet | 2129053 | 2743 | 168 | PV | 2-231-231 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 |  | -30266 | 74 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-09-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Plymouth | 2129459 | 2360 | 840 | PV | 3-12-12 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 | 2016-05-18 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-08-02 | 2016-09-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2129461 | 2360 | 308 | PV | 3-71-71 | 2016-02-17 | 2016-02-18 | 1 | 0 | 1 | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-25 |  | 2016-09-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Assonett | 2129465 | 2702 | 16.95 | PV | 2-605-605 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 2129730 | 2476 | 115 | PV | 320-H7 | 2016-02-17 | 2016-02-19 | 2 | 0 | 2 | 2016-02-25 | 2016-04-26 | 43 | 27 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-02 |  | 2016-09-22 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | New Bedford | 2129733 | 2745 | 496 | PV | 2-103-103 | 2016-02-18 | 2016-03-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-03-17 | Private
NSTAR | Marston Mills | 2129905 | 2648 | 4400 | PV | 4-88-478 | 2016-02-18 | 2016-02-19 | 1 | 73 | -72 | 2016-02-22 | 2016-03-21 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-15 |  | -30307 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-10-03 | 2016-12-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-05-09 | Private
NSTAR | Framingham | 2129908 | 1701 | 1250 | PV | 203-1348H3 | 2016-02-01 | 2016-02-04 | 3 |  | 3 | 2016-02-19 |  | -30267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  | 2017-12-18 | Online
NSTAR | Watertown | 2130080 | 2472 | 216 | PV | 467-H6 | 2016-02-19 | 2016-02-22 | 1 | 0 | 1 | 2016-02-25 | 2016-03-01 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 | 2016-03-02 | 2016-09-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online | [5 empty] | Private
NSTAR | Edgartown | 2130081 | 2539 | 170 | PV | 4-97-97 | 2016-02-22 | 2016-02-23 | 1 | 0 | 1 | 2016-03-03 | 2016-03-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-25 |  | 2016-09-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-10-26 | Online | [5 empty] | Private
NSTAR | Canton | 2130083 | 2021 | 495.72 | PV | 470-H11 | 2016-01-12 | 2016-01-24 | 8 |  | 8 | 2016-02-23 |  | -30269 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2016-06-10 | 30346 |  | 30346 |  |  | 0 |  | 0 | 2017-07-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2130412 | 2719 | 16.4 | PV | 2-221-221 | 2016-02-02 | 2016-02-02 | 0 |  | 0 | 2016-02-23 |  | -30269 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-07 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-07-01 | Online
NSTAR | Cambridge | 2130419 | 2140 | 36 | PV | 824-26 | 2016-02-23 | 2016-02-26 | 3 | 0 | 3 | 2016-03-03 | 2016-03-15 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 |  | 2016-09-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-05-23 | Online | [5 empty] | Private
NSTAR | Cambridge | 2130635 | 2139 | 27 | PV | 815-10 | 2016-02-23 | 2016-03-09 | 11 | 0 | 11 | 2016-03-15 | 2016-06-23 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-15 |  | 2016-09-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | [5 empty] | Private
NSTAR | Woburn | 2130638 | 1801 | 50 | PV | 375-H4 | 2016-02-24 | 2016-04-08 | 32 | 0 | 32 | 2016-04-25 | 2016-05-04 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-07-25 | 2016-09-29 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-04-18 | Online | [5 empty] | Private
NSTAR | Stoneham | 2130639 | 2180 | 30.3 | PV | 301-03 | 2016-02-05 | 2016-02-10 | 3 |  | 3 | 2016-02-25 |  | -30271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-06-01 | [6 empty] | 0 |  | 0 |  |  | 2016-12-14 | Online | [5 empty] | PRIVATE
NSTAR | New Bedford | 2130836 | 2744 | 144 | PV | 2-69-69 | 2016-02-24 | 2016-02-29 | 3 | 0 | 3 | 2016-03-15 | 2016-03-23 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-09-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hyannis | 2130872 | 2601 | 21.045 | PV | 4-63-521 | 2016-02-09 | 2016-02-12 | 3 |  | 3 | 2016-02-24 |  | -30270 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-06 | 2016-04-27 | [6 empty] | 0 |  | 0 |  |  | 2016-07-28 | Online
NSTAR | Newton | 2130935 | 2468 | 36 | PV | 292-H12 | 2016-02-25 | 2016-02-26 | 1 | 0 | 1 | 2016-03-03 | 2016-06-06 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-19 | Online | [5 empty] | Private
NSTAR | Newton | 2130936 | 2461 | 57.5 | PV | 369-01 | 2016-02-08 | 2016-02-10 | 2 |  | 2 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-14 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online
NSTAR | Dover | 2130937 | 2030 | 16.7 | PV | 456-H5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2131133 | 2360 | 22.575 | PV | 3-71-71 | 2016-02-01 | 2016-02-01 | 0 |  | 0 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-29 | 2016-03-30 | [6 empty] | 0 |  | 0 |  |  | 2016-10-26 | Online
NSTAR | Canton | 2131137 | 2021 | 496 | PV | 470-H8 | 2016-02-25 | 2016-02-29 | 2 | 0 | 2 | 2016-03-03 | 2016-03-18 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-18 |  | 2016-09-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Framingham | 2131138 | 1702 | 60 | WIND | 240-H4 | 2016-02-26 | 2016-02-29 | 1 | 0 | 1 | 2016-03-03 | 2016-04-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-10-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Rochester | 2131315 | 2770 | 15.2 | PV | 3-702-702 | 2016-02-04 | 2016-02-12 | 6 |  | 6 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-20 | 2016-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2131316 | 2537 | 15.2 | PV | 4-81B-443 | 2016-02-08 | 2016-02-12 | 4 |  | 4 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-28 | 2016-04-25 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online | [5 empty] | PRIVATE
NSTAR | Somerville | 2131317 | 2145 | 56 | PV | 227-51H2 | 2016-02-29 |  | -30273 | 0 | 0 | 2016-03-03 | 2016-05-27 | 61 | 48 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Watertown | 2131752 | 2472 | 125 | PV | 467-H2 | 2016-02-29 | 2016-03-02 | 2 | 0 | 2 | 2016-03-03 | 2016-05-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 |  | 2016-10-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Newton | 2131753 | 2461 | 492 | PV | 292-H2 | 2016-03-01 | 2016-03-29 | 20 | 0 | 20 | 2016-03-29 | 2016-05-12 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 | 2016-05-12 | 2016-10-05 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | [5 empty] | Private
NSTAR | Plymouth | 2132061 | 2360 | 2000 | PV | 3-89-925 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-06-02 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 |  | 2016-10-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | Private
NSTAR | Somerville | 2132326 | 2145 | 84 | PV | 227-52H3 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-05-14 | 47 | 32 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-31 | 2016-06-03 | 2016-10-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-14 | Online | [5 empty] | Private
NSTAR | Dennisport | 2132327 | 2639 | 65.7 | PV | 4-92B-583 | 2016-02-16 | 2016-02-18 | 2 |  | 2 | 2016-03-03 |  | -30276 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-10-24 | [6 empty] | 0 |  | 0 |  |  | 2017-03-23 | Online | [5 empty] | PRIVATE
NSTAR | Dennisport | 2132335 | 2639 | 40 | PV | 4-92B-583 | 2016-03-02 | 2016-03-03 | 1 | 22 | -21 | 2016-04-25 | 2016-05-13 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Falmouth | 2132336 | 2536 | 185 | PV | 4-92B-583 | 2016-03-03 | 2016-07-14 | 95 | 0 | 95 | 2016-07-14 | 2016-07-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-20 | 2016-10-24 | 2016-10-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2132937 | 2571 | 150 | PV | 3-84-84 | 2016-03-04 | 2016-03-08 | 2 | 0 | 2 | 2016-03-15 | 2016-03-22 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 | 2016-09-01 | 2016-10-11 | No | Expedited | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  |  | ISA Received/Signed | [5 empty] | Private
NSTAR | Plymouth | 2132938 | 2360 | 18.92 | PV | 3-71-38J1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2133263 | 1741 | 22 | PV | 533-H8 | 2016-03-04 | 2016-03-07 | 1 | 0 | 1 | 2016-03-15 | 2016-05-17 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-10-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Sandwich | 2133264 | 2563 | 109.2 | PV | 4-81B-443 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2133265 | 2360 | 66 | PV | 3-12-12 | 2016-03-07 | 2016-03-10 | 3 | 0 | 3 | 2016-03-15 | 2016-04-25 | 29 | 24 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 | 2016-07-25 | 2016-10-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-03 | Online | [5 empty] | Private
NSTAR | Bedford | 2133471 | 1730 | 312 | PV | 487-1376H1 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 |  | -30284 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-12 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private
NSTAR | Buzzards Bay | 2133572 | 2532 | 66 | PV | 3-90-10J2 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 | 2016-06-07 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-12 | 2016-12-19 | 2016-10-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | Private
NSTAR | Arlington | 2133574 | 2476 | 40.32 | PV | 211-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-09 |  | -30280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-15 | 2016-07-12 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online | [5 empty] | PRIVATE
NSTAR | Ashland | 2133577 | 1721 | 756.4 | PV | 274-H5 | 2016-02-07 | 2016-02-22 | 11 |  | 11 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-16 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Brighton | 2133578 | 2135 | 48 | PV | 329-H7 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-13 |  | 2016-10-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2133801 | 2461 | 47.52 | PV | 1701 | 2016-02-19 | 2016-04-07 | 34 |  | 34 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | 2016-04-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2133803 | 2461 | 41.76 | PV | 467-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-23 | 2016-05-23 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2133805 | 2143 | 23.04 | PV | 250-1N90H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2134025 | 2601 | 72 | PV | 4-84B-524 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-10-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | West Tisbury | 2134027 | 2575 | 95.4 | PV | 4-97-97 | 2016-02-17 | 2016-02-23 | 4 |  | 4 | 2016-03-11 |  | -30282 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-05-10 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | [5 empty] | PRIVATE | Y
NSTAR | Sudbury | 2134028 | 1776 | 112 | PV | 342-H2 | 2016-03-09 | 2016-03-10 | 1 | 0 | 1 | 2016-03-21 | 2016-04-06 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2134029 | 2462 | 15.2 | PV | 292-H7 | 2016-02-24 | 2016-02-24 | 0 |  | 0 | 2016-03-16 |  | -30285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-04 | 2016-05-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online | [5 empty] | PRIVATE
NSTAR | Newton | 2134030 | 2459 | 159 | PV | 292-H2 | 2016-03-10 | 2016-03-14 | 2 | 0 | 2 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-10-17 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | South Walpole | 2134146 | 2071 | - |  | TBD | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-17 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Sudbury | 2134239 | 1776 | 600 | PV | 342-H2 | 2016-03-10 | 2016-03-11 | 1 | 0 | 1 | 2016-03-21 | 2016-04-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Carlisle | 2134241 | 1741 | 39 | PV | 512-1399H1 | 2016-03-11 | 2016-03-12 | -1 | 0 | 0 | 2016-03-22 | 2016-06-16 | 62 | 40 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-16 | Online | [5 empty] | Private | Y
NSTAR | Woburn | 2134403 | 1801 | 200 | PV | 375-H6 | 2016-03-11 | 2016-03-16 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2016-03-21 | Private
NSTAR | Waltham | 2134404 | 2453 | 16.15 | PV | 3311 | 2016-03-10 | 2016-03-11 | 1 |  | 1 | 2016-03-16 |  | -30285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-08 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-08-02 | Online
NSTAR | Acton | 2134405 | 1720 | 990 | PV | 416-H4 | 2016-03-15 | 2016-04-20 | 26 | 39 | -13 | 2016-03-22 | 2016-05-13 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-10-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sandwich | 2135023 | 2537 | 984 | PV | 4-87A-471 | 2016-03-15 | 2016-03-16 | 1 | 0 | 1 | 2016-03-23 | 2016-05-16 | 38 | 1 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-06-17 | 2016-10-20 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Rights | [5 empty] | Private
NSTAR | Woburn | 2135024 | 1801 | 378 | PV | 375-H4 | 2016-03-15 | 2016-03-18 | 3 | 0 | 3 | 2016-03-28 | 2016-05-16 | 35 | 28 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 | 2016-06-08 | 2016-10-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-09 | Online | [5 empty] | Private
NSTAR | Needham | 2135025 | 2494 | 150 | PV | 148-H1 | 2016-03-16 | 2016-03-17 | 1 | 11 | -10 | 2016-04-04 | 2016-06-14 | 51 | 5 | 46 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2135260 | 2138 | 405 | PV | 819-1NB3 | 2016-03-16 | 2016-03-17 | 1 | 0 | 1 | 2016-03-22 | 2016-04-20 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2135261 | 2360 | 2000 | PV | 3-89-922 | 2016-03-16 | 2016-03-31 | 11 | 0 | 11 | 2016-04-07 |  | -30301 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2135262 | 2770 | 260 | PV | 3-702-702 | 2016-03-16 | 2016-03-22 | 4 | 0 | 4 | 2016-03-22 |  | -30289 | 97 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2017-01-24 | 2016-10-21 | No |  | 30 |  |  | 0 |  | 0 |  |  | 2017-03-08 | Online | [5 empty] | Private | N
NSTAR | Carver | 2135263 | 2330 | 490 | PV | 3-81-950 | 2016-03-17 | 2016-03-18 | 1 | 0 | 1 | 2016-03-28 | 2016-04-18 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-06 |  | 2016-10-24 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | [5 empty] | Private
NSTAR | Dedham | 2135559 | 2026 | 112 | PV | 20-H5 | 2016-03-18 | 2016-03-21 | 1 | 0 | 1 | 2016-03-28 | 2016-05-24 | 41 | 28 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-10-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Waltham | 2135867 | 2451 | 270 | PV | 450-H8 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | 2016-05-24 | 2016-08-10 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-10-25 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dedham | 2135868 | 2026 | 84 | PV | 20-H1 | 2016-03-18 | 2016-03-30 | 8 | 0 | 8 | 2016-03-30 |  | -30295 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-25 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | [5 empty] | Private | N
NSTAR | Cambridge | 2135869 | 2140 | 270 | PV | 828-1NA9 | 2016-03-21 | 2016-03-29 | 6 | 0 | 6 | 2016-04-04 | 2016-04-06 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-05-22 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Carver | 2135870 | 2330 | 34.2 | PV | 3-10-930 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-21 |  | -30288 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-09 | 2016-05-12 | [6 empty] | 0 |  | 0 |  |  | 2017-01-20 | Online
NSTAR | Carlisle | 2136139 | 1741 | 17 | PV | 512-1399H1 | 2016-03-21 | 2016-03-25 | 4 | 0 | 4 | 2016-03-31 | 2016-06-14 | 53 | 22 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-21 | 2016-09-08 | 2016-10-26 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-18 | Online | [5 empty] | Private
NSTAR | Somerville | 2136141 | 2145 | 499.5 | PV | 250-H4XY | 2016-03-21 | 2016-03-23 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2016-03-31 | Private
NSTAR | Hopkinton | 2136142 | 1748 | 2000 | PV | 126-H1 | 2016-03-23 | 2016-05-12 | 36 | 0 | 36 | 2016-03-31 |  | -30296 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-28 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Chestnut Hill | 2136357 | 2467 | 324.8 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-03 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online | [5 empty] | Private | Y
NSTAR | Chestnut Hill | 2136359 | 2467 | 196.24 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online | [5 empty] | Private | Y
NSTAR | Hyannis | 2136574 | 2601 | 465 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Hyannis | 2136578 | 2601 | 364 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Newton | 2136579 | 2459 | 240 | PV | 292-H8 | 2016-03-24 | 2016-04-04 | 7 | 0 | 7 | 2016-04-04 | 2016-04-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 | 2016-04-05 | 2016-10-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | [5 empty] | Private
NSTAR | Hatchville | 2136806 | 2536 | 15.4 | PV | 4-98A-98A | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-29 | 2016-04-04 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-05 | 2016-06-16 | 2016-11-01 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online | [5 empty] | Private
NSTAR | Dennis | 2136807 | 2660 | 21.75 | PV | 4-92B-92B | 2016-03-01 | 2016-03-02 | 1 |  | 1 | 2016-03-25 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-19 | 2016-06-22 | [6 empty] | 0 |  | 0
NSTAR | Newton | 2136808 | 2468 | 109.25 | PV | 292-H12 | 2016-02-25 | 2016-03-02 | 4 |  | 4 | 2016-03-25 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-06 | 2016-07-25 | 2016-07-25 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2136975 | 2740 | 468 | PV | 2-110-110 | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-31 |  | -30296 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online |  |  |  |  | 2016-04-20 | Private
NSTAR | Acton | 2136976 | 1720 | 990 | PV | 416-H4 | 2016-03-28 | 2016-03-29 | 1 | 0 | 1 | 2016-03-29 |  | -30294 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-04-27 | Private
NSTAR | Dartmouth | 2137247 | 2747 | 1000 | PV | 2-532-532 | 2016-03-28 | 2016-03-28 | 0 | 0 | 0 | 2016-03-29 | 2016-04-28 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plympton | 2137254 | 2367 | 972 | PV | 3-51-901 | 2016-03-29 | 2016-03-30 | 1 | 0 | 1 | 2016-04-07 | 2016-05-18 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2016-11-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Design Approval | [5 empty] | Private
NSTAR | Jamaica Plain | 2137255 | 2130 | 21.9 | PV | 496-H4 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-29 |  | -30294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-30 | 2016-04-08 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | [5 empty] | PRIVATE
NSTAR | Carver | 2137495 | 2330 | 1860 | PV | 3-51-980 | 2016-03-08 | 2016-03-08 | 0 |  | 0 | 2016-03-29 |  | -30294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-15 | 2016-08-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online
NSTAR | Dorchester | 2137497 | 2121 | 57.6 | PV | 106-H2 | 2016-02-15 | 2016-02-26 | 9 |  | 9 | 2016-04-01 |  | -30297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2137498 | 2451 | 290 | PV | 450-H3 | 2016-03-30 | 2016-03-31 | 1 | 0 | 1 | 2016-04-07 |  | -30301 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-11-04 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-06-06 | Private
NSTAR | Lexington | 2137830 | 2421 | 360 | PV | 320-H4 | 2016-03-30 | 2016-04-01 | 2 | 0 | 2 | 2016-04-07 | 2016-05-31 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-30 |  | 2016-11-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Framingham | 2137840 | 1702 | 219 | PV | 455-H5 | 2016-03-31 | 2016-04-01 | 1 | 0 | 1 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-12 |  | 2016-11-07 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2138143 | 2747 | 18 | PV | 2-532-532 | 2016-04-01 | 2016-04-05 | 2 | 0 | 2 | 2016-04-11 | 2016-06-22 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-29 |  | 2016-11-08 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private | N
NSTAR | Mashpee | 2138475 | 2649 | 53.8 | PV | 4-88-455 | 2016-03-28 | 2016-03-30 | 2 |  | 2 | 2016-04-06 |  | -30300 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2019-01-10 | Online
NSTAR | Dover | 2138477 | 2030 | 282 | PV | 456-H5 | 2016-04-06 | 2016-04-07 | 1 | 0 | 1 | 2016-04-25 | 2016-06-13 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Kingston | 2138478 | 2364 | 16.69 | PV | 3-17-916 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2139202 | 2717 | 24.32 | PV | 2-102-602 | 2016-03-23 | 2016-04-06 | 10 |  | 10 | 2016-04-06 |  | -30300 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-09 | 2016-06-10 | [6 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | [5 empty] | PRIVATE
NSTAR | Bedford | 2139203 | 1730 | 21.9 | PV | 322-05 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2139413 | 1760 | 16.2 | PV | 240-H1 | 2016-03-20 | 2016-03-28 | 6 |  | 6 | 2016-04-07 |  | -30301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-22 | 2016-07-11 | [6 empty] | 0 |  | 0
NSTAR | Weston | 2139664 | 2493 | 20.16 | PV | 282-H2 | 2016-03-28 | 2016-03-28 | 0 |  | 0 | 2016-04-07 |  | -30301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-28 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online | [5 empty] | PRIVATE
NSTAR | Canton | 2139666 | 2021 | 192 | PV | 470-H7 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 | 2016-04-20 | 2016-06-20 | 43 | 6 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-28 | 2016-08-24 | 2016-11-15 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | [5 empty] | Private
NSTAR | Newton | 2139847 | 2468 | 982 | PV | 292-H2 | 2016-04-08 | 2016-04-09 | -1 | 0 | 0 | 2016-04-19 | 2016-05-04 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-25 |  | 2016-11-16 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | [5 empty] | Private
NSTAR | Duxbury | 2139848 | 2332 | 24.32 | PV | 3-26-903 | 2016-03-17 | 2016-03-28 | 7 |  | 7 | 2016-05-26 |  | -30336 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-09 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | [5 empty] | private
NSTAR | Charlestown | 2140031 | 2129 | 288 | PV | 10-H1 | 2016-04-11 | 2016-04-12 | 1 | 0 | 1 | 2016-04-25 | 2016-05-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-11-17 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Mashpee | 2140032 | 2649 | 21.9 | PV | 4-88-483 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2140033 | 1776 | 15.75 | PV | 342-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2140338 | 2364 | 50 | PV | 3-17-17 | 2016-04-11 | 2016-04-12 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-28 | Online | [5 empty] | Private
NSTAR | Woburn | 2140339 | 1801 | 480 | PV | 375-H6 | 2016-04-11 | 2016-04-25 | 10 | 0 | 10 | 2016-04-28 | 2016-07-13 | 54 | 49 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2016-11-17 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | [5 empty] | Private
NSTAR | Plymouth | 2140340 | 2360 | 364.3 | PV | 3-89-922 | 2016-04-12 | 2016-04-13 | 1 | 0 | 1 | 2016-04-18 | 2016-05-02 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-13 | 2016-12-22 | 2016-11-18 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-24 | Online | [5 empty] | Private
NSTAR | Weston | 2140569 | 2493 | 246 | PV | 433-H6 | 2016-04-14 | 2016-04-20 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs |  |  |  |  | 2016-04-27 | Private
NSTAR | Burlington | 2140576 | 1803 | 16.72 | PV | 391-H6 | 2016-03-29 | 2016-04-05 | 5 |  | 5 | 2016-04-14 |  | -30306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-12 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140849 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140850 | 2121 | 43.2 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2140851 | 2121 | 43.2 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2141085 | 2021 | 252 | PV | 470-H11 | 2016-04-14 | 2016-04-20 | 4 | 0 | 4 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-11-02 | 2016-11-17 | 2016-11-22 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-16 | Online | [5 empty] | Private
NSTAR | Dorchester | 2141087 | 2121 | 57 | PV | 106-H2 | 2016-04-15 | 2016-04-27 | 8 | 0 | 8 | 2016-04-27 | 2016-05-13 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-16 |  | 2016-11-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Somerville | 2141311 | 2145 | 18 | PV | 250-H4XY | 2016-04-18 | 2016-04-20 | 2 | 0 | 2 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-15 |  | 2016-11-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | [5 empty] | Private
NSTAR | Dorchester | 2141870 | 2121 | 48 | PV | 106-H2 | 2016-04-21 | 2016-04-22 | 1 | 0 | 1 | 2016-05-12 | 2016-06-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dorchester | 2141880 | 2121 | 30.4 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2141881 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142397 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142398 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142654 | 2121 | 26.6 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142655 | 2121 | 28.8 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Sudbury | 2142844 | 1776 | 21.6 | PV | 342-h8 | 2016-04-11 | 2016-04-19 | 6 |  | 6 | 2016-04-25 |  | -30313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-10 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142845 | 2121 | 45.6 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142846 | 2124 | 57 | PV | 106-H2 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 | 2016-05-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dorchester | 2143232 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2143233 | 2121 | 26.6 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Harwich | 2143454 | 2645 | 16.77 | PV | 4-95A-599 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 |  | -30316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-24 | [6 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online | [5 empty] | PRIVATE
NSTAR | Kingston | 2143458 | 2364 | 48 | PV | 3-17-910 | 2016-04-26 | 2016-04-28 | 2 | 0 | 2 | 2016-05-02 | 2016-05-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-16 | 2016-09-08 | 2016-12-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | [5 empty] | Private
NSTAR | Woburn | 2143665 | 1801 | 140 | PV | 211-H5 | 2016-04-27 | 2016-04-29 | 2 | 0 | 2 | 2016-04-29 | 2016-06-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-11-09 | Online | [5 empty] | Private
NSTAR | Woburn | 2143667 | 1801 | 112 | PV | 211-H5 | 2016-04-27 | 2016-05-20 | 17 | 0 | 17 | 2016-05-26 | 2016-08-17 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-23 | 2016-12-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-04-05 | Online | [5 empty] | Private | Y
NSTAR | Natick | 2143668 | 1760 | 16.25 | PV | 433-H5 | 2016-04-05 | 2016-04-11 | 4 |  | 4 | 2016-04-29 |  | -30317 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-16 | 2010-06-03 | [6 empty] | 0 |  | 0 |  |  | 2016-09-19 | Online | [5 empty] | PRIVATE
NSTAR | Carlisle | 2143902 | 1741 | 17.4 | PV | 512-1399h1 | 2016-04-10 | 2016-04-11 | 1 |  | 1 | 2016-05-02 |  | -30318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-27 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online
NSTAR | Jamaica Plain | 2143903 | 2130 | 30 | PV | 284-07 | 2016-04-28 | 2016-05-03 | 3 | 0 | 3 | 2016-05-13 | 2016-05-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-26 | 2016-06-02 | 2016-12-06 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-02 | Online | [5 empty] | Private
NSTAR | Milton | 2144091 | 2186 | 25.05 | PV | 496-H7 | 2016-03-11 | 2016-04-01 | 15 |  | 15 | 2016-05-02 |  | -30318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2144430 | 1720 | 18 | PV | 416-H4 | 2016-05-02 | 2016-05-03 | 1 | 0 | 1 | 2016-05-13 | 2016-05-27 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-01 |  | 2016-12-08 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-08-31 | Online | [5 empty] | Private
NSTAR | Weston | 2145203 | 2493 | 20 | PV | 282-H10 | 2016-05-04 | 2016-05-05 | 1 | 0 | 1 | 2016-05-11 | 2016-05-24 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 |  | 2016-12-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-07-13 | Online | [5 empty] | Private
NSTAR | Canton | 2145484 | 2021 | 780 | PV | 269-1320H1 | 2016-05-05 | 2016-05-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | [5 empty] | Private
NSTAR | West Roxbury | 2145690 | 2132 | 684 | PV | 374-04 | 2016-05-06 | 2016-05-11 | 3 | 0 | 3 | 2016-05-16 |  | -30328 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 2016-12-14 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Mashpee | 2145692 | 2649 | 58.9 | PV | 4-88-453 | 2016-02-10 | 2016-04-27 | 55 |  | 55 | 2016-05-11 |  | -30325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2016-12-05 | Online | [5 empty] | PRIVATE
NSTAR | Woburn | 2145950 | 1801 | 43.009 | PV | 211-H5 | 2016-04-20 | 2016-05-02 | 8 |  | 8 | 2016-05-12 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-31 | 2016-09-06 | 2016-09-06 | [5 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online | [5 empty] | PRIVATE
NSTAR | West Newton | 2145951 | 2465 | 21.681 | PV | 282-H9 | 2016-04-26 | 2016-04-29 | 3 |  | 3 | 2016-05-12 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-11 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online | [5 empty] | PRIVATE | Y
NSTAR | Woburn | 2146188 | 1801 | 15.2 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2146368 | 2360 | 99.9 | PV | 3-88-924 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2146377 | 2332 | 28.8 | PV | 3-26-903 | 2016-03-24 | 2016-05-02 | 27 |  | 27 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | PRIVATE
NSTAR | Dennisport | 2146378 | 2639 | 34.77 | PV | 4-85-592 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-01 | 2016-06-24 | [6 empty] | 0 |  | 0 |  |  | 2016-08-11 | Online
NSTAR | Sherborn | 2146567 | 1770 | 19 | PV | 274-H2 | 2016-05-12 | 2016-05-18 | 4 | 0 | 4 | 2016-05-26 | 2016-06-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-08 | Online | [5 empty] | Private
NSTAR | New Bedford | 2146760 | 2744 | 499.5 | PV | 2-69-52 | 2016-05-08 | 2016-05-09 | 1 |  | 1 | 2016-05-22 |  | -30332 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online
NSTAR | Waltham | 2147316 | 2452 | 16.15 | PV | 33-H2 | 2016-05-13 | 2016-05-16 | 1 |  | 1 | 2016-05-23 |  | -30333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online | [5 empty] | PRIVATE
NSTAR | Ashland | 2147605 | 1721 | 728 | PV | 3-10-929 | 2016-05-18 | 2016-05-19 | 1 | 0 | 1 | 2016-07-14 | 2016-07-29 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2015-08-18 | 2016-12-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Field Com | [5 empty] | Private
NSTAR | Carver | 2147609 | 2330 | 20 | PV | 3-10-929 | 2016-05-18 | 2016-05-23 | 3 | 0 | 3 | 2016-05-26 | 2016-08-19 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-22 | 2017-01-19 | 2016-12-27 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online | [5 empty] | Private | N
NSTAR | Boston | 2147800 | 2118 | 336 | PV | 106-H4 | 2016-05-19 | 2016-05-20 | 1 | 0 | 1 | 2016-05-23 | 2016-08-10 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-15 | 2016-12-28 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed | [5 empty] | Private
NSTAR | Assonett | 2148246 | 2702 | 432 | PV | 2-605-605 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-24 |  | -30334 | 58 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-14 |  | 2016-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-10-23 | Online |  |  |  |  | 2016-05-30 | Private
NSTAR | Natick | 2148247 | 1760 | 280 | PV | 433-H7 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-30 | 2016-07-25 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-08-24 | 2016-12-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online | [5 empty] | Private
NSTAR | Newton | 2148462 | 2466 | 1800 | PV | 33-H3 | 2016-05-24 | 2016-05-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online |  |  |  |  | 2016-06-06 | Private
NSTAR | Roxbury | 2148650 | 2120 | 936 | PV | 483-H6 | 2016-05-25 | 2016-05-31 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [5 empty] | Gov't
NSTAR | Sherborn | 2148838 | 1770 | 23.1 | PV | 274-H3 | 2016-05-03 | 2016-05-18 | 11 |  | 11 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-07 | [7 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online | [5 empty] | PRIVATE
NSTAR | Lexington | 2149011 | 2421 | 15.4 | PV | 3408 | 2016-05-16 | 2016-05-18 | 2 |  | 2 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online | [5 empty] | PRIVATE
NSTAR | Stoneham | 2150045 | 2180 | 15.98 | PV | 375-H8 | 2016-05-13 | 2016-05-18 | 3 |  | 3 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-08-10 | [6 empty] | 0 |  | 0 | [9 empty] | PRIVATE
NSTAR | Hyannis | 2151036 | 2601 | 38 | PV | 4-63-63 | 2016-06-02 | 2016-06-08 | 4 | 0 | 4 | 2016-06-14 | 2016-06-30 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2017-01-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | Bedford | 2151037 | 1730 | 288 | PV | 391-H8 | 2016-05-23 | 2016-05-31 | 6 |  | 6 | 2016-06-07 |  | -30344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-12 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online | [5 empty] | Private
NSTAR | Hyannis | 2151406 | 2601 | 136.5 | PV | 4-63-521 | 2016-05-12 | 2016-05-31 | 13 |  | 13 | 2016-06-09 |  | -30346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-15 | 2016-08-08 | [6 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | Boston | 2151408 | 2215 | 367 | PV | 350-H5 | 2016-06-03 | 2016-06-04 | -1 | 0 | 0 | 2016-06-09 | 2016-06-21 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-01-12 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2151948 | 1760 | 75 | Natural Gas | 433-H7 | 2016-06-07 | 2016-06-09 | 2 | 38 | -36 | 2016-06-14 |  | -30349 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-29 | 2016-01-03 | 2017-01-17 | No |  | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online |  |  |  |  | 2016-06-28 | Private
NSTAR | Cotuit | 2152205 | 2635 | 1992 | PV | 4-88-880 | 2016-06-08 | 2016-06-13 | 3 | 0 | 3 | 2016-06-14 |  | -30349 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30423 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-28 |  | 2017-01-18 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-06-17 | Private
NSTAR | Bourne | 2152371 | 2532 | 566.1 | PV | 3-89-925 | 2016-03-04 | 2016-05-18 | 53 |  | 53 | 2016-06-10 |  | -30347 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | 2016-09-01 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2152612 | 2536 | 16.15 | PV | 4-98A-462 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Eastham | 2152613 | 2642 | 15.4 | PV | 4-94A-648 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2152922 | 1801 | 49.14 | PV | 533-H7 | 2016-05-10 | 2016-06-02 | 17 |  | 17 | 2016-06-15 |  | -30350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online | [5 empty] | PRIVATE
NSTAR | Orleans | 2152923 | 2653 | 300 | PV | 4-83-952 | 2016-06-13 | 2016-06-15 | 2 | 0 | 2 | 2016-06-20 | 2016-06-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-27 |  | 2017-01-23 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-07-18 | Online | [5 empty] | Private
NSTAR | Cotuit | 2153294 | 2635 | 1992 | PV | 4-88-880 | 2016-06-15 | 2016-06-16 | 1 | 0 | 1 | 2016-06-27 |  | -30358 | 37 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30423 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2016-09-28 | 2017-01-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-06-29 | Private
NSTAR | Newton | 2154090 | 2460 | 75 | PV | 467-H5 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-27 | 2016-06-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-27 |  | 2017-01-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Online | [5 empty] | Private
NSTAR | Watertown | 2154091 | 2472 | 432 | PV | 467-H6 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-28 | 2016-08-03 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-08-24 | 2017-01-30 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-06-23 | Online | [5 empty] | Private
NSTAR | Framingham | 2154503 | 1701 | 105 | PV | 433-H3 | 2016-06-22 | 2016-06-23 | 1 | 2 | -1 | 2016-06-28 | 2016-07-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Framingham | 2154699 | 1701 | 105 | PV | 433-H3 | 2016-06-23 | 2016-06-24 | 1 | 2 | -1 | 2016-07-05 | 2016-07-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Dedham | 2154886 | 2026 | 189.2 | PV | 20-H5 | 2016-06-24 | 2016-06-27 | 1 | 0 | 1 | 2016-07-04 | 2016-07-26 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-03 | 2016-08-03 | 2017-02-03 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-30 | Online | [5 empty] | Private
NSTAR | Sandwich | 2155321 | 2537 | 468 | PV | 4-81B-81B | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 |  | -30363 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 2016-09-08 | 30410 | 0 | 30410 |  |  | 0 | 0 | 0 | 2016-12-19 |  | 2017-02-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Sent ISA | [5 empty] | Private
NSTAR | Brighton | 2155327 | 2135 | 75 | PV | 315-H11 | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 | 2016-07-25 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 |  | 2017-02-07 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-07 | Online | [5 empty] | Private
NSTAR | Dennis | 2155620 | 2638 | 89.9 | PV | 4-92B-92B | 2016-05-13 | 2016-06-08 | 18 |  | 18 | 2016-06-30 |  | -30361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-28 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  |  | isa received/signed
NSTAR | Sandwich | 2155836 | 2563 | 109.2 | PV | 4-81B-443 | 2016-06-09 | 2016-06-22 | 9 |  | 9 | 2016-07-01 |  | -30362 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2156003 | 2122 | 170 | PV | 496-H1XY | 2016-07-01 | 2016-07-05 | 2 | 0 | 2 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-07-26 | 2016-09-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-02-01 | Online | [5 empty] | Private
NSTAR | Chatham | 2156004 | 2650 | 21.44 | PV | 4-95B-612 | 2016-06-10 | 2016-06-13 | 1 |  | 1 | 2016-07-05 |  | -30364 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-13 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online | [5 empty] | PRIVATE
NSTAR | Needham | 2156671 | 2494 | 90 | PV | 148-H7 | 2016-07-05 | 2016-07-06 | 1 | 0 | 1 | 2016-07-14 | 2016-08-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-23 | 2016-08-25 | 2017-02-13 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-03-07 | Online | [5 empty] | Private
NSTAR | North Dartmouth | 2157001 | 2747 | 16.25 | PV | 2-541-541 | 2016-06-01 | 2016-06-20 | 13 |  | 13 | 2016-07-07 |  | -30366 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-09-12 | [6 empty] | 0 |  | 0 |  |  | 2016-09-26 | Online | [5 empty] | PRIVATE
NSTAR | Waltham | 2157007 | 2453 | 180 | PV | 33-H3 | 2016-07-06 | 2016-07-07 | 1 | 0 | 1 | 2016-07-14 |  | -30371 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-14 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Online |  |  |  |  | 2016-08-04 | Private
NSTAR | Dartmouth | 2157191 | 2747 | 150 | Natural Gas | 2-541-542 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-14 |  | -30371 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-22 | 2017-02-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-01-31 | Online | [5 empty] | Gov't
NSTAR | Dover | 2157192 | 2030 | 21 | PV | 456-H5 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-15 | 2016-08-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2017-02-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2016-12-02 | Online | [5 empty] | Private
NSTAR | Woburn | 2157251 | 1801 | 499 | PV | 375-H3 | 2016-07-08 | 2016-07-11 | 1 | 0 | 1 | 2016-07-13 |  | -30370 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-16 | TBD |  | 30 |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | South Boston | 2157900 | 2210 | 456 | PV | 385-H18 | 2016-06-09 | 2016-06-22 | 9 | 0 | 9 | 2016-07-14 |  | -30371 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-23 | 2017-02-21 | No |  | 30 |  |  | 0 |  | 0 |  |  | 2017-07-20 | Online | [5 empty] | Private
NSTAR | Acusnet | 2157905 | 2743 | 144.4 | PV | 2-231-231 | 2016-05-27 | 2016-06-27 | 21 |  | 21 | 2016-07-14 |  | -30371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2158112 | 2648 | 50.4 | PV | 4-88-478 | 2016-05-24 | 2016-06-28 | 25 |  | 25 | 2016-07-14 |  | -30371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | [5 empty] | PRIVATE
NSTAR | South Boston | 2158329 | 2127 | 486.2 | PV | 385-H17 | 2016-05-11 | 2016-05-16 | 3 |  | 3 | 2016-06-08 |  | -30345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2158504 | 2330 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | South Boston | 2158505 | 2127 | 500 | PV | 106-H1 | 2016-07-15 | 2016-07-25 | 6 | 0 | 6 | 2016-07-25 |  | -30378 | 16 | 0 | 2016-08-31 |  | -30405 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | South Boston | 2158507 | 2127 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2158976 | 2330 | - | PV | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD |  | 30 |  |  | 0 |  | 0 |  | 2018-04-30 | 2018-04-30 | Online | [5 empty] | Private
NSTAR | Acton | 2158995 | 1720 | 294 | PV | 416-H4 | 2016-07-18 | 2016-07-25 | 5 | 0 | 5 | 2016-07-28 |  | -30381 | 14 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-08-02 | Private
NSTAR | Milton | 2158997 | 2186 | 30 | PV | 362-1209H1 | 2016-07-18 | 2016-07-20 | 2 | 0 | 2 | 2016-07-28 | 2016-08-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-15 |  | 2017-02-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | [5 empty] | Private
NSTAR | Weston | 2159240 | 2493 | 20 | PV | 282-H1 | 2016-07-19 | 2016-07-20 | 1 | 0 | 1 | 2016-07-28 |  | -30381 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-01-30 |  | 2017-02-28 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-08-10 | Private
NSTAR | Framingham | 2159493 | 2472 | 166.5 | PV | 467-H2 | 2016-06-29 | 2016-07-12 | 9 |  | 9 | 2016-07-25 |  | -30378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 2159738 | 2367 | 1000 | PV | TBD | 2016-07-21 |  | -30376 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-02 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | West Roxbury | 2160263 | 2132 | 250 | Natural Gas | 374-2215 | 2016-07-25 | 2016-07-27 | 2 | 0 | 2 | 2016-08-01 |  | -30383 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-18 | 2016-09-09 | 2017-03-06 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed | [5 empty] | Gov't
NSTAR | Westwood | 2160448 | 2090 | 126.5 | PV | 456-h1 | 2016-07-14 | 2016-07-18 | 2 |  | 2 | 2016-07-27 |  | -30380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-02 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2017-04-27 | Online
NSTAR | Mattapoisett | 2160656 | 2739 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hatchville | 2160717 | 2536 | 98 | PV | 4-98A-98A | 2016-07-27 | 2016-08-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Maynard | 2160866 | 1754 | 576 | PV | 416-H3 | 2016-07-28 | 2016-08-01 | 2 | 0 | 2 | 2016-08-05 |  | -30387 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-09 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-08-11 | Private
NSTAR | Westwood | 2161143 | 2090 | 161 | PV | 469-H2 | 2016-07-29 | 2016-08-01 | 1 | 0 | 1 | 2016-08-05 |  | -30387 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-16 | 2016-09-23 | 2017-03-10 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-04-27 | Online | [5 empty] | Private
NSTAR | Hopkinton | 2161144 | 1748 | 252 | PV | 126-H1 | 2016-07-29 | 2016-08-02 | 2 | 0 | 2 | 2016-08-05 | 2016-08-19 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-12 | 2017-03-10 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online |  |  |  |  | 2016-08-22 | Private
NSTAR | Westwood | 2161690 | 2090 | 164 | PV | 456-H4 | 2016-07-16 | 2016-08-09 | 17 | 0 | 17 | 2016-08-03 |  | -30385 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-09-14 | 2017-03-14 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online | [5 empty] | Private
NSTAR | Waltham | 2162221 | 2452 | 380 | PV | 277-1367 | 2016-08-03 | 2016-08-09 | 4 | 0 | 4 | 2016-08-11 |  | -30391 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-19 | 2016-09-29 | 2017-03-15 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2016-08-12 | Private
NSTAR | East Boston | 2162392 | 2128 | 72 | PV | 488-H8 | 2016-08-04 | 2016-08-09 | 3 | 0 | 3 | 2016-08-11 |  | -30391 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-16 |  | 2017-03-16 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Ashland | 2162591 | 1721 | 148.9 | PV | 274-H1 | 2016-07-18 | 2016-07-25 | 5 |  | 5 | 2016-08-09 |  | -30389 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 2164625 | 2019 | 497.5 | PV | 65-H4 | 2016-06-10 | 2016-07-25 | 31 |  | 31 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-12 | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-07-28 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Mattapoisett | 2164627 | 2739 | 16.92 | PV | 2-301-301 | 2016-07-05 | 2016-07-27 | 16 |  | 16 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | New Bedford | 2164917 | 2745 | 272 | PV | 2-103-103 | 2016-07-22 | 2016-07-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | [5 empty] | Private
NSTAR | Westwood | 2165129 | 2090 | 138 | PV | 456-H4 | 2016-07-14 | 2016-07-28 | 10 | 0 | 10 | 2016-08-22 |  | -30398 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-29 | 2017-03-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2017-04-25 | Online | [5 empty] | Gov't
NSTAR | Roxbury | 2165132 | 2119 | 57.6 | PV | 106-H5 | 2016-07-11 | 2016-07-28 | 13 |  | 13 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Roxbury | 2165395 | 2119 | 115.2 | PV | 106-H4 | 2016-07-13 | 2016-08-01 | 13 |  | 13 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2165396 | 2648 | 19.6 | PV | 4-88-485 | 2016-07-26 | 2016-08-01 | 4 |  | 4 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-17 | Online | [5 empty] | PRIVATE
NSTAR | Falmouth | 2165668 | 2536 | 90 | PV | 4-98A-98A | 2016-07-29 | 2016-08-09 | 7 |  | 7 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online | [5 empty] | PRIVATE | Y
NSTAR | Framingham | 2165880 | 1701 | 30 | PV | 4-98A-98A | 2016-07-22 | 2016-08-09 | 12 |  | 12 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | [7 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online | [5 empty] | PRIVATE
NSTAR | Westwood | 2165893 | 2090 | 266.4 | PV | 456-H1 | 2016-08-05 | 2016-08-12 | 5 |  | 5 | 2016-08-26 |  | -30402 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2017-10-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-21 | Online | [5 empty] | PRIVATE | Y
NSTAR | Hyannis | 2166109 | 2601 | 20 | PV | 4-63-63 | 2016-07-13 | 2016-08-15 | 23 |  | 23 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | [5 empty] | PRIVATE
NSTAR | Falmouth | 2166111 | 2536 | 100.8 | PV | 4-98A-98A | 2016-07-26 | 2016-08-29 | 24 |  | 24 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2017-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-04-28 | Online
NSTAR | Waltham | 2166275 | 2453 | 60 | PV | 282-H4 | 2016-08-09 | 2016-08-15 | 4 |  | 4 | 2016-08-30 |  | -30404 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online | [5 empty] | PRIVATE
NSTAR | Waltham | 2166276 | 2453 | 50 | PV | 282-H9 | 2016-08-09 | 2016-08-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-16 | Online | [5 empty] | PRIVATE
NSTAR | Dedham | 2166557 | 2026 | 525 | PV | 344-1413H1 | 2016-07-20 | 2016-08-22 | 23 |  | 23 | 2016-08-30 |  | -30404 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-20 |  | -30441 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | [7 empty] | 0 |  | 0 |  |  |  | isa sent
NSTAR | Dorchester | 2166559 | 2124 | 20 | PV | 511-1497H3 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-22 | 2016-09-23 | [6 empty] | 0 |  | 0 |  |  | 2017-06-02 | Online | [5 empty] | PRIVATE
NSTAR | Cambridge | 2166793 | 2140 | 22.8 | PV | 825-27 | 2016-08-03 | 2016-08-04 | 1 |  | 1 | 2016-09-01 |  | -30406 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-21 | [6 empty] | 0 |  | 0 |  |  | 2017-01-03 | Online | [5 empty] | PRIVATE
NSTAR | Newton | 2166797 | 2458 | 150 | PV | 467-H14 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-03-29 | Online | [5 empty] | PRIVATE
NSTAR | Newton | 2166988 | 2466 | 57.5 | PV | 292-H7 | 2016-08-18 | 2016-08-22 | 2 |  | 2 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-03-01 | Online | [5 empty] | PRIVATE
NSTAR | Cambridge | 2166994 | 2140 | 115.2 | PV | 825-26 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2167216 | 2453 | 73.3 | PV | 33-H1 | 2016-08-09 | 2016-08-16 | 5 |  | 5 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online
NSTAR | Allston | 2168053 | 2134 | 60 | PV | 329-H7 | 2016-08-17 | 2016-08-22 | 3 |  | 3 | 2016-09-07 |  | -30410 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-02 | Online | [5 empty] | PRIVATE
NSTAR | Boston | 2168059 | 2118 | 75 | PV | 323-06 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-07 |  | -30410 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Bedford | 2168512 | 1731 | 2805 | PV | 320-H6 | 2016-09-01 | 2016-09-07 | 4 |  | 4 | 2016-09-12 |  | -30413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2168736 | 1760 | 21.9 | PV | 240-H2 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-09-12 |  | -30413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2016-11-29 | Online | [5 empty] | PRIVATE | Y
NSTAR | Sudbury | 2168989 | 1776 | 20 | PV | 342-H7 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-13 |  | -30414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online | [5 empty] | PRIVATE
NSTAR | North Dartmouth | 2168995 | 2747 | 40 | PV | 2-541-542 | 2016-07-28 | 2016-08-29 | 22 |  | 22 | 2016-09-13 |  | -30414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-30 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | [5 empty] | PRIVATE | Y
NSTAR | Brewster | 2169301 | 2631 | 19.25 | PV | 4-89B-576 | 2016-08-18 | 2016-08-24 | 4 |  | 4 | 2016-09-14 |  | -30415 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Somerville | 2169544 | 2143 | 45 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  | 2019-02-05 | isa sent | [5 empty] | PRIVATE
NSTAR | Somerville | 2169546 | 2143 | 105 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-09 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-18 | Online
NSTAR | Cambridge | 2169551 | 2139 | 57.6 | PV | 814-13 | 2016-09-02 | 2016-09-07 | 3 |  | 3 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-06 | Online | [5 empty] | PRIVATE
NSTAR | Boston | 2169723 | 2188 | 72 | PV | 106-H4 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30417 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2017-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-11-09 | Online
NSTAR | Brighton | 2169751 | 2135 | 64 | PV | 467-H12 | 2016-08-17 | 2016-08-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2169753 | 2128 | 167 | PV | 108-196H1 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30417 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Stoneham | 2170420 | 2180 | 84 | PV | 375-H7 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-14 | Online
NSTAR | Hopkinton | 2170421 | 1748 | 22.7 | PV | 126-H1 | 2016-08-29 | 2016-08-31 | 2 |  | 2 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-01-05 | Online | [5 empty] | PRIVATE
NSTAR | Rochester | 2170422 | 2770 | 21.9 | PV | 5-702-702 | 2016-08-25 | 2016-08-29 | 2 |  | 2 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Plymouth | 2170423 | 2360 | 188.42 | PV | 3-14-911 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Hyannis | 2170678 | 2601 | 306.07 | PV | 4-84B-524 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-21 |  | -30420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-03-28 | Online | [5 empty] | PRIVATE
NSTAR | Kingston | 2170680 | 2364 | 80 | PV | 3-26-902 | 2016-08-23 | 2016-09-01 | 7 |  | 7 | 2016-09-21 |  | -30420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-28 | Online | [5 empty] | PRIVATE
NSTAR | Acton | 2170908 | 1720 | 21.9 | PV | 416-H4 | 2016-08-25 | 2016-09-01 | 5 |  | 5 | 2016-07-22 |  | -30377 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | [5 empty] | PRIVATE
NSTAR | Arlington | 2170910 | 2475 | 396 | PV | 211-H11 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | 2016-09-22 |  | -30421 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2016-12-02 | 7 |  | 7 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 |  |  | 2017-08-04 | Online | [5 empty] | PRIVATE
NSTAR | West Wareham | 2170912 | 2576 | 24.5 | PV | 3-85-85 | 2016-08-30 | 2016-09-06 | 5 |  | 5 | 2016-09-22 |  | -30421 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Framingham | 2171111 | 1701 | 1760 | PV | 455-H7 | 2016-07-29 | 2016-09-07 | 28 |  | 28 | 2016-09-23 |  | -30422 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-22 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2018-04-30 | Online
NSTAR | Acton | 2171112 | 1720 | 39.1 | PV | 416-H5 | 2016-08-22 | 2016-09-06 | 11 |  | 11 | 2016-09-23 |  | -30422 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Marion | 2171654 | 2738 | 15.2 | PV | 3-85-85 | 2016-09-01 | 2016-09-07 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online | [5 empty] | PRIVATE
NSTAR | Woburn | 2171655 | 1888 | 466.2 | PV | 375-H3 | 2016-06-01 | 2016-09-07 | 70 |  | 70 | 2016-09-28 |  | -30425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 |  | -30545 |  | 0 |  |  | 0 |  | 0 | 2017-08-18 | 2017-08-23 | [6 empty] | 0 |  | 0 |  |  | 2018-02-26 | Online
NSTAR | Hopkinton | 2171656 | 1748 | 433 | PV | 126-H1 | 2016-09-01 | 2016-09-06 | 3 |  | 3 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | 2016-11-17 | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  |  | WO Request
NSTAR | Acton | 2171989 | 1720 | 40 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Acton | 2171992 | 1720 | 52.9 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Truro | 2172198 | 2666 | 18.9 | PV | 4-96-674 | 2016-09-07 | 2016-09-09 | 2 |  | 2 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online | [5 empty] | PRIVATE
NSTAR | East Falmouth | 2172199 | 2536 | 48 | PV | 4-98A-98A | 2016-07-15 | 2016-09-14 | 43 |  | 43 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Acton | 2172398 | 1720 | 101 | PV | 416-H9 | 2016-08-18 | 2016-09-07 | 14 |  | 14 | 2016-10-03 |  | -30428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2172403 | 2140 | 66.6 | PV | 824-28 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-03 |  | -30428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-02 | 2016-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-06-26 | Online
NSTAR | Orleans | 2172699 | 2653 | 33.5 | PV | 4-83-952 | 2016-09-06 | 2016-09-14 | 6 |  | 6 | 2016-10-30 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | [7 empty] | 0 |  | 0 |  |  | 2017-05-18 | Online | [5 empty] | PRIVATE
NSTAR | East Boston | 2173575 | 2128 | 75 | CHP | 488-H8 | 2016-09-12 | 2016-10-04 | 16 |  | 16 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2016-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-02-10 | Online | [5 empty] | NO EXPORT
NSTAR | Buzzards Bay | 2173585 | 2532 | 100 | PV | 3-88-2J4 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2173782 | 2630 | 50 | PV | 4-84B-524 | 2016-08-29 | 2016-09-09 | 9 |  | 9 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-03-10 | Online | [5 empty] | PRIVATE
NSTAR | Arlington | 2173991 | 2476 | 34.5 | PV | 211-H3 | 2016-08-25 | 2016-09-14 | 14 |  | 14 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Natick | 2173993 | 1760 | 126 | PV | 240-H2 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | ISA SENT
NSTAR | West Tisbury | 2173995 | 2575 | 22.8 | PV | 4-97-97 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-16 | Online | [5 empty] | PRIVATE
NSTAR | West Tisbury | 2173999 | 2575 | 22.8 | PV | 4-97-226 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online | [5 empty] | PRIVATE
NSTAR | Framingham | 2174568 | 1701 | 165 | PV | 433-H3 | 2016-09-09 | 2016-09-15 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Walpole | 2174571 | 2081 | 135 | PV | 2611 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marion | 2174858 | 2738 | 27.72 | PV | 2-304-304 | 2016-09-08 | 2016-09-15 | 5 |  | 5 | 2016-10-14 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online | [5 empty] | PRIVATE
NSTAR | Framingham | 2175097 | 1702 | 180 | PV | 240-H4 | 2016-09-28 | 2016-10-03 | 3 |  | 3 | 2016-10-14 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2175313 | 2452 | 18.4 | PV | 282-H7 | 2016-09-15 | 2016-09-19 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Assonett | 2175318 | 2702 | 16.7 | PV | 2-605-605 | 2016-09-13 | 2016-09-17 | 3 |  | 3 | 2016-10-17 |  | -30438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | New Bedford | 2175669 | 2746 | 180 | PV | 2-24-11 | 2016-09-16 | 2016-09-19 | 1 |  | 1 | 2016-10-18 |  | -30439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-25 | 2017-03-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online
NSTAR | Acusnet | 2176279 | 2743 | 15.36 | PV | 2-241-241 | 2016-09-20 | 2016-09-20 | 0 |  | 0 | 2016-10-21 |  | -30442 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-08 | 2016-12-09 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online | [5 empty] | PRIVATE
NSTAR | Stoneham | 2176517 | 2180 | - | PV | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Holliston | 2176549 | 1746 | 36 | PV | 274-H3 | 2016-09-09 | 2016-09-23 | 10 |  | 10 | 2016-10-21 |  | -30442 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online | [5 empty] | PRIVATE
NSTAR | Harwich | 2176727 | 2645 | 30 | PV | 4-89A-556 | 2016-09-19 | 2016-09-21 | 2 |  | 2 | 2016-10-24 |  | -30443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-01 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online | [5 empty] | PRIVATE
NSTAR | Needham | 2176734 | 2494 | 866 | PV | 148-H6 | 2016-07-13 | 2016-09-23 | 52 |  | 52 | 2016-10-24 |  | -30443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2177085 | 2145 | 210 | PV | 210-1N81H1 | 2016-08-19 | 2016-09-23 | 25 |  | 25 | 2016-10-25 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2177087 | 2360 | 32.35 | PV | 3-13-936 | 2016-09-20 | 2016-09-26 | 4 |  | 4 | 2016-10-25 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-04-05 | Online | [5 empty] | Private | Y
NSTAR | Brookline | 2177319 | 2446 | 16.5 | PV | 350-H12 | 2016-09-15 | 2016-09-26 | 7 |  | 7 | 2016-10-26 |  | -30445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-04-19 | Online | [5 empty] | PRIVATE
NSTAR | Lexington | 2177534 | 2420 | 79.2 | PV | 391-H11 | 2016-09-21 | 2016-09-28 | 5 |  | 5 | 2016-10-27 |  | -30446 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2177535 | 2557 | 21.15 | PV | 4-99-224 | 2016-08-25 | 2016-10-19 | 39 |  | 39 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-03 | Online | [5 empty] | PRIVATE
NSTAR | Medway | 2177856 | 2053 | 180 | PV | 65-H3 | 2016-09-30 | 2016-10-26 | 18 |  | 18 | 2016-10-28 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2178416 | 2539 | 21.38 | PV | 4-75-75 | 2016-06-15 | 2016-10-19 | 90 |  | 90 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online | [5 empty] | PRIVATE
NSTAR | North Dartmouth | 2178419 | 2747 | 499.5 | PV | 2-533-530 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-01 |  | -30449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-02 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online
NSTAR | Natick | 2178429 | 1760 | 458 | PV | TBD | 2016-10-31 |  | -30448 | 0 | 0 | 2016-11-04 | 2017-08-17 | 204 | 188 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-06-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Somerville | 2178439 | 2143 | 30.24 | PV | 250-1N90H2 | 2016-09-20 | 2016-09-29 | 7 |  | 7 | 2016-11-01 |  | -30449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online | [5 empty] | PRIVATE | Y
NSTAR | Yarmouth | 2178449 | 2664 | 127.8 | PV | 4-92a-562 | 2016-09-26 | 2016-10-03 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Teaticket | 2178798 | 2536 | 228 | PV | 4-76-437 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | [7 empty] | 0 |  | 0 |  |  | 2017-12-01 | Online
NSTAR | New Bedford | 2179799 | 2745 | 208 | PV | 2-82-82 | 2016-10-09 | 2016-10-12 | 3 |  | 3 | 2016-11-03 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | 2016-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | [5 empty] | Private
NSTAR | Falmouth | 2179819 | 2540 | 32.4 | PV | 4-72-433 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-03 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Falmouth | 2180040 | 2540 | 16 | PV | 4-72-433 | 2016-09-27 | 2016-10-03 | 4 |  | 4 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | [5 empty] | PRIVATE
NSTAR | Waltham | 2180042 | 2453 | 30 | PV | 467-H5 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-28 | 2016-12-13 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online | [5 empty] | PRIVATE
NSTAR | Bourne | 2180239 | 2542 | 7950 | PV | 4-98A-98A | 2016-10-04 | 2016-10-12 | 6 |  | 6 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-05-11 | -46 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2180242 | 1760 | 252 | PV | 240-H1 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-03 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2180244 | 1730 | 5198 | CHP | 319-1377 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | 2180484 | 2052 | 70 | PV | 146-H2 | 2016-11-07 | 2016-11-07 | 0 |  | 0 | 2016-11-09 |  | -30455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online | [5 empty] | GOV'T
NSTAR | North Dartmouth | 2180485 | 2748 | 39.6 | PV | 2-524-524 | 2016-09-22 | 2016-10-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-08 | Waiting for ISA | [5 empty] | PRIVATE
NSTAR | Framingham | 2180488 | 1702 | 50 | PV | 2408 | 2016-09-19 | 2016-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-17 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online | [5 empty] | PRIVATE
NSTAR | Brookline | 2180952 | 2455 | 60 | PV | 506-07 | 2016-09-30 | 2016-10-12 | 8 |  | 8 | 2016-11-30 |  | -30470 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-16 | 2016-01-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Walpole | 2180956 | 2081 | 28.8 | PV | 146-H3 | 2016-10-05 | 2016-10-17 | 8 |  | 8 | 2016-11-10 |  | -30456 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online | [5 empty] | PRIVATE
NSTAR | Framingham | 2181138 | 1702 | 51 | PV | 278-H1 | 2016-09-19 | 2016-10-12 | 17 |  | 17 | 2016-11-14 |  | -30458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-04-10 | [6 empty] | 0 |  | 0 |  |  | 2017-09-20 | Online | [5 empty] | PRIVATE
NSTAR | Holliston | 2181140 | 1746 | 42 | PV | 274-H3 | 2016-10-13 | 2016-10-21 | 6 | 7 | -1 | 2016-11-14 |  | -30458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | [7 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online | [5 empty] | PRIVATE
NSTAR | Bedford | 2181646 | 1731 | 430 | PV | 319-1378 | 2016-10-11 | 2016-10-18 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-22 | Online
NSTAR | Holliston | 2181649 | 1746 | 32.5 | PV | 130-H1 | 2016-10-06 | 2016-10-19 | 9 |  | 9 | 2016-11-16 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-03-13 | Online | [5 empty] | PRIVATE
NSTAR | Dedham | 2181650 | 2026 | 150 | CHP | 20-H5 | 2016-10-14 | 2016-10-19 | 3 |  | 3 | 2016-11-16 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online
NSTAR | South Dartmouth | 2181937 | 2748 | 57.6 | PV | 2-2-505 | 2016-10-04 | 2016-10-20 | 12 |  | 12 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-21 | Online | [5 empty] | PRIVATE
NSTAR | Needham | 2181939 | 2494 | 64.8 | PV | 148-H1 | 2016-10-17 | 2016-10-21 | 4 |  | 4 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-07 | 2016-12-15 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2181940 | 2445 | 89 | PV | 369-07 | 2016-10-20 | 2016-10-25 | 3 |  | 3 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sherborn | 2181941 | 1770 | 35.6 | PV | 274-H2 | 2016-10-11 | 2016-10-17 | 4 |  | 4 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Weston | 2182191 | 2493 | 18 | PV | 433-H6 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online | [5 empty] | PRIVATE
NSTAR | Hyannis | 2182194 | 2601 | 19 | PV | 4-63-905 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Westwood | 2182386 | 2090 | 480 | PV | 469-H3 | 2016-09-15 | 2016-10-18 | 23 |  | 23 | 2016-11-21 |  | -30463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Lexington | 2182387 | 2420 | 20 | PV | 391-H11 | 2016-05-23 | 2016-10-18 | 106 |  | 106 | 2016-11-21 |  | -30463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-15 | [6 empty] | 0 |  | 0 |  |  |  | isa sent | [5 empty] | PRIVATE
NSTAR | Canton | 2182736 | 2021 | 980 | PV | 470-H7 | 2014-06-17 | 2014-06-17 | 0 |  | 0 | 2017-06-30 |  | -30622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-20 | 2014-10-14 | -6 |  | 0 |  |  | 0 |  | 0 | 2016-09-09 | 2016-09-09 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2182805 | 2445 | 28 | PV | 350-H8 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-22 | Online | [5 empty] | PRIVATE | Y
NSTAR | Framingham | 2182806 | 1702 | 648 | PV | 240-H6 | 2016-10-03 | 2016-11-18 | 34 |  | 34 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 2182807 | 2474 | 18 | PV | 5905 | 2016-10-18 | 2016-10-24 | 4 |  | 4 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | [5 empty] | PRIVATE
NSTAR | Acton | 2182998 | 1720 | 288 | PV | 416-H4 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-23 |  | -30465 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2183002 | 2539 | 21.75 | PV | 4-97-97 | 2016-10-21 | 2016-10-27 | 4 |  | 4 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2016-12-16 | [6 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online | [5 empty] | PRIVATE
NSTAR | Natick | 2183182 | 1760 | 94.52 | PV | 240-H5 | 2016-10-18 | 2016-10-27 | 7 |  | 7 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | Framingham | 2183183 | 1702 | 220 | Battery | 455-H5 | 2016-10-28 | 2016-11-14 | 11 |  | 11 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2183910 | 1760 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | North Dartmouth | 2184042 | 2747 | 22 | PV | 2-523-523 | 2016-07-21 | 2016-10-28 | 71 |  | 71 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-13 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | [5 empty] | PRIVATE
NSTAR | Westwood | 2184045 | 2090 | 2310 | PV | 344-1412H1 | 2016-10-21 | 2016-10-31 | 6 |  | 6 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-20 | 2017-05-18 | 20 |  | 20 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 2184047 | 1776 | 17.4 | PV | 342-H7 | 2016-10-25 | 2016-10-31 | 4 |  | 4 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | [5 empty] | PRIVATE
NSTAR | Westwood | 2184048 | 2090 | 30.14 | PV | 148-H3 | 2016-10-24 | 2016-11-15 | 16 |  | 16 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Canton | 2184049 | 2021 | 660 | PV | TBD | 2016-11-30 |  | -30470 | 0 | 0 | 2016-12-08 | 2016-12-23 | 11 | 8 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2184402 | 1760 | 720 | PV | 433-H12 | 2016-10-17 | 2016-10-31 | 10 |  | 10 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Cambridge | 2184403 | 2140 | 2442 | PV | 828-1375 | 2016-10-24 | 2017-10-31 | 266 |  | 266 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 |  | -30559 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyde Park | 2184405 | 2136 | 510 | PV | TBD | 2016-12-01 |  | -30471 | 0 | 0 | 2016-12-06 | 2016-12-23 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-11 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2184406 | 2468 | 480 | PV | 292-H12 | 2016-10-24 | 2016-10-31 | 5 |  | 5 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-19 | 2017-06-19 |  |  |  | 87 |  |  | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Dedham | 2184658 | 2026 | 66.6 | PV | 374-04 | 2016-10-31 | 2016-11-01 | 1 |  | 1 | 2016-12-05 |  | -30473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | East Falmouth | 2187033 | 2536 | 16.7 | PV | 4-98A-98A | 2016-10-27 | 2016-11-02 | 4 |  | 4 | 2016-12-06 |  | -30474 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2016-12-15 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online | [5 empty] | PRIVATE
NSTAR | Woburn | 2187229 | 1801 | 180 | PV | TBD | 2016-12-06 |  | -30474 | 0 | 0 | 2016-12-09 | 2017-03-03 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-06 |  | 2017-07-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Hopkinton | 2187300 | 1748 | 2820 | PV | 455=H3 | 2016-11-18 | 2016-11-18 | 0 |  | 0 | 2016-12-07 |  | -30475 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2187307 | 2138 | 23.4 | PV | 821-05 | 2016-11-21 | 2016-11-28 | 5 |  | 5 | 2016-12-07 |  | -30475 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | 2017-02-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online | [5 empty] | PRIVATE
NSTAR | Eastham | 2187463 | 2642 | 23.04 | PV | 4-94B-956 | 2016-11-15 | 2016-11-17 | 2 |  | 2 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-18 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online | [5 empty] | PRIVATE
NSTAR | Cambridge | 2187497 | 2139 | 60 | CHP | 831-1NC7 | 2016-10-31 | 2016-11-05 | 4 |  | 4 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-26 | ISA Received | [5 empty] | PRIVATE
NSTAR | Winchester | 2187499 | 1890 | 60 | PV | 211-H4 | 2016-11-07 | 2016-11-09 | 2 |  | 2 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Weston | 2187501 | 2493 | 16.7 | PV | 450-H7 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Woburn | 2187695 | 1801 | 15.875 | PV | 211-H8 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online | [5 empty] | PRIVATE
NSTAR | Mashpee | 2187699 | 2649 | 496 | PV | 4-88-455 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Edgartown | 2187701 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-08-03 | Online | [5 empty] | PRIVATE
NSTAR | Sandwich | 2187704 | 2542 | 4700 | Micro Grid | 4-98A-98A | 2016-12-07 | 2016-12-21 | 10 |  | 10 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-20 | [7 empty] | 0 |  | 0 |  |  | 2019-10-17 | Online
NSTAR | Wareham | 2188254 | 2571 | 77.6 | PV | 3-84-968 | 2016-09-28 | 2016-12-09 | 52 |  | 52 | 2016-12-14 |  | -30480 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | 2017-01-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online | [5 empty] | PRIVATE
NSTAR | Edgartown | 2188255 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-14 |  | -30480 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-08-23 | Online | [5 empty] | PRIVATE
NSTAR | Assonett | 2188539 | 2702 | 16.7 | PV | 2-605-605 | 2016-11-17 | 2016-11-21 | 2 |  | 2 | 2016-12-15 |  | -30481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Wareham | 2188540 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11
NSTAR | Wareham | 2188541 | 2571 | 2000 | PV | 3-83-83 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2188542 | 2571 | 1500 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20 | Online
NSTAR | Wareham | 2188543 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20
NSTAR | Wareham | 2188544 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online
NSTAR | Hopkinton | 2188716 | 1748 | 990 | PV | 126-H1 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-04 | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2188717 | 2717 | 4950 | PV | 2-102-102 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2188718 | 2740 | 27 | PV | 2-73-47 | 2016-08-29 | 2016-10-28 | 44 |  | 44 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-23 | Online | [5 empty] | NO EXPORT | N
NSTAR | Wayland | 2189506 | 1778 | 93.275 | PV | 342-H3 | 2016-11-09 | 2016-11-22 | 9 |  | 9 | 2016-12-28 |  | -30490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-26 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online
NSTAR | Rochester | 2189508 | 2770 | 3300 | PV | 3-702-702 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-28 |  | -30490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-04 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2189509 | 1748 | 2120 | PV | 126-H2 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-04-18 | Online
NSTAR | Weston | 2190095 | 2493 | 115 | PV | 282-H1 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-27 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-07-06 | Online
NSTAR | Bellingham | 2190097 | 2019 | 16.09 | PV | 65-H4 | 2016-11-22 | 2016-11-30 | 6 |  | 6 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-28 | [7 empty] | 0 |  | 0 |  |  | 2017-09-18 | Online | [5 empty] | PRIVATE
NSTAR | Westport | 2190239 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online | [5 empty] | PRIVATE
NSTAR | Westport | 2190240 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Chilmark | 2191358 | 2535 | 65.2 | PV | 4-91-226 | 2016-11-22 | 2016-11-30 | 6 |  | 6 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2191380 | 1801 | 86.4 | PV | 325-01 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-30 | 2017-04-06 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2017-09-08 | Online | [5 empty] | PRIVATE
NSTAR | Hopkinton | 2191381 | 1748 | 28.8 | PV | 65-H6 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-06-21 | Online | [5 empty] | PRIVATE
NSTAR | Natick | 2191567 | 1760 | 20 | PV | 240-H5 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-30 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-06-27 | Online | [5 empty] | PRIVATE
NSTAR | Holliston | 2191568 | 1746 | 47.7 | PV | 65-H2 | 2016-12-02 | 2016-12-05 | 1 |  | 1 | 2016-12-30 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | 2017-02-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online | [5 empty] | PRIVATE
NSTAR | North Dartmouth | 2193439 | 2747 | 15.34 | PV | 2-541-541 | 2016-11-30 | 2016-12-05 | 3 |  | 3 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | North Dartmouth | 2193440 | 2747 | 15.2 | PV | 2-107-107 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Burlington | 2193629 | 1803 | 19.75 | PV | 391-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-03-29 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online | [5 empty] | PRIVATE
NSTAR | West Roxbury | 2193924 | 2132 | 300 | CHP | 496-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2017-01-06 |  | -30497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-27 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-01-24 | Online
NSTAR | Canton | 2195719 | 2021 | 128 | PV | 470-H4 | 2016-12-09 | 2016-12-13 | 2 |  | 2 | 2017-01-09 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20
NSTAR | Milton | 2195721 | 2186 | 17.4 | PV | 60-1409H1 | 2016-11-28 | 2016-12-13 | 11 |  | 11 | 2017-01-09 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-17 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online | [5 empty] | PRIVATE
NSTAR | Cambridge | 2195978 | 2138 | 42 | PV | 828-1NC8 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online | [5 empty] | PRIVATE
NSTAR | Cambridge | 2195981 | 2138 | 214.2 | PV | 821-05 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online
NSTAR | Boston | 2196194 | 2163 | 32 | PV | 817-03 | 2016-12-22 | 2016-12-29 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-02-28 | [6 empty] | 0 |  | 0 | [9 empty] | PRIVATE
NSTAR | Woburn | 2196195 | 1801 | 119.9 | PV | 375-H3 | 2016-12-16 | 2016-12-27 | 7 |  | 7 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-05-16 |  |  | Expedited |  |  |  | 0 |  | 0 | [9 empty] | PRIVATE | Y
NSTAR | Rochester | 2196392 | 2770 | 3180 | PV | 3-702-702 | 2016-12-12 | 2016-12-15 | 3 |  | 3 | 2017-01-12 |  | -30501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-26 | 2017-06-22 | -265 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | [7 empty] | 0 |  | 0 | [10 empty] | Y
NSTAR | Sherborn | 2196661 | 1770 | 75 | PV | 240-H1 | 2016-12-16 | 2016-12-28 | 8 |  | 8 | 2017-01-13 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-01-19 | [6 empty] | 0 |  | 0 |  |  | 2017-05-24 | Online
NSTAR | New Bedford | 2196803 | 2745 | 296 | PV | 2-101-101 | 2016-12-28 | 2016-12-30 | 2 |  | 2 | 2016-01-17 |  | -30242 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-17 | [6 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | New Bedford | 2197507 | 2745 | 496 | PV | 2-152-152 | 2016-12-21 | 2016-12-30 | 7 |  | 7 | 2017-01-19 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-09 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online
NSTAR | Ashland | 2197716 | 1721 | 728 | PV |  | 2017-01-19 |  | -30506 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2017-09-29 | 2018-05-30 | TBD |  | 30 | 2018-04-05 | 2018-04-05 | 0 |  | 0 |  | 2018-06-14 | 2018-06-15 | Online | [5 empty] | Private
NSTAR | Natick | 2197718 | 1760 | 737 | PV | 339-1345H | 2016-12-21 | 2017-01-05 | 11 |  | 11 | 2017-01-20 |  | -30507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2197892 | 2360 | 21.6 | PV | 3-89-926 | 2016-11-16 | 2017-01-05 | 36 |  | 36 | 2017-01-24 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-08 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Hyannis | 2198079 | 2601 | 38 | PV | 4-63-63 | 2017-01-09 | 2017-01-11 | 2 |  | 2 | 2017-01-24 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-02-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-01 | Online | [5 empty] | PRIVATE
NSTAR | Holliston | 2198478 | 1746 | 110 | Battery | 274-H3 | 2016-12-01 | 2017-01-12 | 30 |  | 30 | 2017-01-27 |  | -30512 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | [5 empty] | N/A | N
NSTAR | Natick | 2199089 | 1760 | 16.78 | PV | 433-H5 | 2017-01-11 | 2017-01-18 | 5 |  | 5 | 2017-01-31 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | [5 empty] | PRIVATE
NSTAR | Woburn | 2199093 | 1801 | 8.35 | PV | 211-H2 | 2017-01-17 | 2017-01-20 | 3 |  | 3 | 2017-01-31 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Canton | 2199637 | 2021 | 16.7 | PV | 470-H11 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-01 |  | -30515 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 | [9 empty] | PRIVATE
NSTAR | Burlington | 2199843 | 1803 | 182.65 | PV | 391-H15 | 2017-01-11 | 2017-01-18 | 5 |  | 5 | 2017-02-02 |  | -30516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-21 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-24 | Online
NSTAR | Walpole | 2200165 | 2081 | 16.7 | PV | 146-H9 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-08 |  | -30520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-04-24 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online | [5 empty] | PRIVATE
NSTAR | Westport | 2200167 | 2790 | 15.2 | PV | 2-523-523 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-08 |  | -30520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Sudbury | 2200633 | 1776 | 96 | PV | 342-H2 | 2017-02-09 | 2017-02-09 | 0 |  | 0 | 2017-02-10 |  | -30522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-31 | 2017-04-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-25 | Online | [5 empty] | P2 | N
NSTAR | Dedham | 2200785 | 2026 | 153.2 | PV | 20-H1 | 2017-01-24 | 2017-01-25 | 1 |  | 1 | 2017-02-09 |  | -30521 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2200960 | 1776 | 16.2 | PV | 375-H2 | 2017-01-24 | 2017-01-27 | 3 |  | 3 | 2017-02-10 |  | -30522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | East Freetown | 2200961 | 2717 | - |  | TBD | 2017-02-09 |  | -30521 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-09-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Fairhaven | 2201063 | 2719 | 2000 | PV | 2-221-221 | 2017-01-31 | 2017-01-31 | 0 |  | 0 | 2017-02-13 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-02-27 | -16 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Sudbury | 2201274 | 1776 | 21.4 | PV | 342-H5 | 2017-02-03 | 2017-02-08 | 3 |  | 3 | 2017-02-14 |  | -30524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-06-06 | Online | [5 empty] | PRIVATE
NSTAR | Vineyard Haven | 2201898 | 2568 | 166.5 | PV | 4-75-75 | 2017-01-30 | 2017-02-13 | 10 |  | 10 | 2017-02-16 |  | -30526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-18 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Plymouth | 2202211 | 2367 | 18.6 | PV | 3-51-43J1 | 2017-02-09 | 2017-02-13 | 2 |  | 2 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-10 | [6 empty] | 0 |  | 0 |  |  | 2017-08-09 | Online | [5 empty] | PRIVATE
NSTAR | Needham | 2202454 | 2492 | 69 | PV | 342-H5 | 2017-02-13 | 2017-02-13 | 0 |  | 0 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-04-28 |  | YES | Expedited |  |  |  | 0 |  | 0 |  |  | 2017-10-10 | Online | [5 empty] | PRIVATE | Y
NSTAR | East Falmouth | 2202817 | 2536 | 109.25 | PV | 4-98A-98A | 2017-01-27 | 2017-02-13 | 11 |  | 11 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | 2017-05-03 | [6 empty] | 0 |  | 0 |  |  | 2017-08-17 | Online | [5 empty] | Private
NSTAR | Fairhaven | 2202964 | 2719 | 184 | PV | 2-240-209 | 2017-02-15 | 2017-02-15 | 0 |  | 0 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Acusnet | 2203266 | 2743 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-10-02 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Plymouth | 2203287 | 2360 | 208 | PV | 3-14-911 | 2017-01-31 | 2017-02-03 | 3 |  | 3 | 2017-02-28 |  | -30534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-04-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online | [5 empty] | PRIVATE | Y
NSTAR | New Bedford | 2203288 | 2740 | 496 | PV | TBD | 2017-02-27 |  | -30533 | 0 | 0 | 2017-03-01 | 2017-04-07 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-29 |  | 2017-10-02 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hopkinton | 2203698 | 1748 | 1980 | PV | 126-H4 | 2015-08-14 | 2015-08-14 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-03-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Woburn | 2204382 | 1801 | 17.4 | PV | 211-H10 | 2017-02-17 | 2017-02-23 | 4 |  | 4 | 2017-03-06 |  | -30538 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Kingston | 2204685 | 2364 | 366.4 | PV | 3-26-902 | 2017-02-03 | 2017-02-09 | 4 |  | 4 | 2017-03-08 |  | -30540 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2205487 | 1801 | 17.4 | PV | 211-H5 | 2017-02-17 | 2017-02-23 | 4 |  | 4 | 2017-03-16 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-27 | 2017-03-28 | [6 empty] | 0 |  | 0 |  |  | 2017-11-15 | Online | [5 empty] | PRIVATE
NSTAR | West Roxbury | 2205777 | 2132 | 300 | Fuel Cell & Battery | 496-H3 | 2017-02-09 | 2017-02-27 | 12 |  | 12 | 2017-03-16 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-27 | 2017-11-03 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Arlington | 2206239 | 2474 | 16.45 | PV | 211-H11 | 2017-03-01 | 2017-03-03 | 2 |  | 2 | 2017-03-17 |  | -30547 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Westwood | 2206500 | 2090 | 20 | PV | 148-H3 | 2017-02-28 | 2017-03-06 | 4 |  | 4 | 2017-03-20 |  | -30548 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-25 | 2017-04-26 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online | [5 empty] | PRIVATE
NSTAR | Boston | 2206844 | 2130 | 75 | CHP | 536-76H2 | 2016-12-08 | 2017-03-08 | 64 |  | 64 | 2017-04-11 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-24 | Online
NSTAR | Woburn | 2207029 | 1801 | 576 | PV | 258-1394H2 | 2017-03-09 | 2017-03-10 | 1 |  | 1 | 2017-03-23 |  | -30551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-17 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Cambridge | 2207242 | 2139 | 75 | CHP | 817-03 | 2017-03-08 | 2017-03-20 | 8 |  | 8 | 2017-03-23 |  | -30551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-06-21 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2207411 | 2142 | 35 | CHP | 875-1328 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-09-07 | Online | [5 empty] | PRIVATE | Y
NSTAR | Cambridge | 2207804 | 2142 | 35 | CHP | 875-1343 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  | NO | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-12-26 | [6 empty] | PRIVATE
NSTAR | Canton | 2207988 | 2021 | 19.8 | PV | 269-1320H1 | 2017-03-06 | 2017-03-20 | 10 |  | 10 | 2017-03-30 |  | -30556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | New Bedford | 2208391 | 2740 | 36 | PV | 2-59-96 | 2017-02-20 | 2017-03-20 | 20 |  | 20 | 2017-04-03 |  | -30558 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-02 | 2017-05-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online | [5 empty] | PRIVATE
NSTAR | Natick | 2208547 | 1760 | 449.5 | PV | 433-H5 | 2017-02-10 | 2017-03-23 | 29 |  | 29 | 2017-04-06 |  | -30561 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE | N
NSTAR | Natick | 2209451 | 1760 | 466.2 | PV | 433-H12 | 2017-02-10 | 2017-03-23 | 29 |  | 29 | 2017-04-06 |  | -30561 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE | N
NSTAR | Wareham | 2209835 | 2571 | - |  | TBD | 2017-04-06 |  | -30561 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2018-05-01 | 2018-03-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2210401 | 2747 | 20.35 | PV | 274-H3 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-12 |  | -30565 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-30 | 2017-06-30 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Onset | 2210632 | 2558 | 19.5 | PV | 3-84-17J1 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-13 |  | -30566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-19 | [7 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online | [5 empty] | PRIVATE
NSTAR | Plympton | 2211077 | 2367 | 4950 | PV & Battery | 3-15-901 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-17 |  | -30568 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-11 | 2017-05-11 | -89 |  | 0 | 2017-09-01 | 2017-08-10 | -18 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2211409 | 2129 | 403.2 | PV & Battery | 5-208H/22-208 | 2017-03-16 | 2017-04-01 | 11 |  | 11 | 2017-04-18 |  | -30569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-06 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2018-02-13 | Online
NSTAR | Woburn | 2211603 | 1801 | 20.35 | PV | 211-H8 | 2017-03-30 | 2017-04-10 | 7 |  | 7 | 2017-04-24 |  | -30573 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | PRIVATE
NSTAR | Millis | 2211983 | 2054 | 350.4 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30572 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2211985 | 2054 | 175.2 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30572 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2212591 | 2090 | 858 | PV | 469-H6 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-26 |  | -30575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2212756 | 2021 | 330 | PV | 470-H1 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-28 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -46 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-26 | Online
NSTAR | Wayland | 2212763 | 1778 | 15.2 | PV | 342-H1 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Woburn | 2212768 | 1801 | 16.7 | PV | 211-H13 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-01 | 2017-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20 | Online
NSTAR | Burlington | 2212942 | 1803 | 16.95 | PV | 391-H7 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-28 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-27 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2213109 | 1803 | 176.4 | PV | 211-H13 | 2017-03-10 | 2017-04-11 | 22 |  | 22 | 2017-05-01 |  | -30578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2213428 | 2360 | 210 | PV & Battery | 3-13-943 | 2017-04-07 | 2017-04-11 | 2 |  | 2 | 2017-05-02 |  | -30579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-20 | 2017-07-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Cambridge | 2214153 | 2412 | 47.5 | PV | 875-1N38A | 2017-03-01 | 2017-04-13 | 31 |  | 31 | 2017-05-05 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-02 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2214303 | 2630 | 373 | PV | 4-84B-524 | 2017-04-12 | 2017-04-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-25 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-04-09 | Online
NSTAR | Lincoln | 2214304 | 1773 | 24 | PV | 320-H8 | 2017-04-12 | 2017-04-18 | 4 |  | 4 | 2017-05-05 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-07 | 2017-06-20 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Canton | 2214562 | 2021 | 462 | PV | 470-H11 | 2017-04-13 | 2017-04-14 | 1 |  | 1 | 2017-05-08 |  | -30583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -46 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2018-12-27 |  | 2018-12-28 | Online
NSTAR | Cambridge | 2214784 | 2139 | 14.4 | PV | 831-1NC7 | 2017-03-31 | 2017-04-11 | 7 |  | 7 | 2017-05-09 |  | -30584 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-25 | 2018-03-01 | [6 empty] | 0 |  | 0 |  |  | 2018-09-07 | Online
NSTAR | Chatham | 2214785 | 2659 | 47 | PV | 4-95A-95A | 2017-04-11 | 2017-04-18 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | Carver | 2214971 | 2330 | 30 | PV | 3-81-950 | 2017-04-13 | 2017-04-21 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-05 | 2017-07-14 | [6 empty] | 0 |  | 0
NSTAR | Walpole | 2215756 | 2081 | 19.15 | PV | 146-H3 | 2017-04-14 | 2017-04-24 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2215757 | 2180 | 16.7 | PV | 375-H8 | 2017-04-14 | 2017-04-24 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-25 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2216193 | 2571 | 17.575 | PV | 3-84-963 | 2017-04-14 | 2017-04-24 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-10-27 | Online
NSTAR | Osterville | 2216608 | 2655 | 18.91 | PV | 4-80A-490 | 2017-04-19 | 2017-04-26 | 5 |  | 5 | 2017-05-22 |  | -30593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2017-09-12 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03
NSTAR | Chelsea | 2217046 | 2150 | 996 | PV | 14-113H1 | 2017-04-20 | 2017-04-27 | 5 |  | 5 | 2017-05-24 |  | -30595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-11 | 2017-07-12 | [6 empty] | 0 |  | 0 | 2018-12-28
NSTAR | Burlington | 2217047 | 1803 | 180 | PV | 346-1395H1 | 2017-04-21 | 2017-05-01 | 6 |  | 6 | 2017-05-24 |  | -30595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2217262 | 2747 | 210 | Fuel Cell | 2-531-531 | 2017-05-02 | 2017-05-02 | 0 |  | 0 | 2017-05-25 |  | -30596 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Woburn | 2217434 | 1801 | 224.25 | PV | 375-H4 | 2017-05-01 | 2017-05-02 | 1 |  | 1 | 2017-05-26 |  | -30597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-22 | Online
NSTAR | Cambridge | 2217599 | 2141 | 153.2 | PV | 875-1N36B | 2017-04-25 | 2017-05-03 | 6 |  | 6 | 2017-05-30 |  | -30599 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-25 | 2017-08-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Yarmouth | 2217600 | 2673 | 1560 | PV | 4-92A-92A | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2217818 | 2740 | 1070 | PV | 2-151-151 | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-16 | 2017-06-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -19 |  | 0 |  |  | 0 |  | 0 | 2018-01-22 | [7 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Westwood | 2218004 | 2090 | 302 | PV | 469-H6 | 2017-05-09 | 2017-05-16 | 5 |  | 5 | 2017-06-16 |  | -30612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-04 | 30646 |  | 30646 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-02 |  |  | Standard |  |  |  | 0 |  | 0 |  |  | 2018-10-29 | Online | [5 empty] | Private
NSTAR | Plymouth | 2218005 | 2360 | 1176 | PV | 3-12-12 | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-16 | 2017-08-10 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-10 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-22 | Online
NSTAR | Sandwich | 2218204 | 2563 | 70 | PV | 4-81B-443 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-06 | [6 empty] | 0 |  | 0 |  |  | 2018-04-19 | Online
NSTAR | Wareham | 2218205 | 2571 | 210 | Fuel Cell | 3-84-961 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 1900-04-05 | 2017-06-20 | [5 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Norfolk | 2218206 | 2056 | 72 | PV | 146-H3 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-10-06 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2218766 | 1748 | 16.7 | PV | 65-H6 | 2017-05-15 | 2017-05-22 | 5 |  | 5 | 2017-06-05 |  | -30603 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2219177 | 2747 | 2300 | PV | 2-543-543 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-06 |  | -30604 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-07-27 | 30640 |  | 30640 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-29 | Online
NSTAR | Roxbury | 2219411 | 2119 | 24 | PV | 483-H6 | 2017-05-13 | 2017-05-22 | 6 |  | 6 | 2017-06-07 |  | -30605 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-17 | 2017-09-20 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | New Bedford | 2219644 | 2745 | 336 | PV | 2-88-18 | 2017-05-19 | 2017-05-22 | 1 |  | 1 | 2017-06-08 |  | -30606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-06-26 | [6 empty] | 0 |  | 0 |  |  | 2017-12-29 | Online
NSTAR | Falmouth | 2219873 | 2540 | 54.88 | PV | 4-72-433 | 2017-05-23 | 2017-05-25 | 2 |  | 2 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2220027 | 2453 | 72 | PV | 282-H8 | 2017-05-01 | 2017-05-23 | 16 |  | 16 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-09-18 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2220029 | 2576 | 18 | PV | 3-85-85 | 2017-05-24 | 2017-05-30 | 4 |  | 4 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online
NSTAR | Dorchester | 2220311 | 2124 | 45.15 | PV | 483-H7 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-07-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-23 | Online | [5 empty] | PRIVATE
NSTAR | Ashland | 2220527 | 1721 | 4450 | PV | 274-1429H1 | 2017-05-16 | 2017-05-22 | 4 |  | 4 | 2017-06-15 |  | -30611 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-29 | 2017-09-21 | -8 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2221535 | 2330 | 2000 | PV | 3-10-10 | 2017-05-19 | 2017-05-30 | 7 |  | 7 | 2017-06-21 |  | -30615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-08-16 | -17 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2019-05-17 | Online
NSTAR | North Dartmouth | 2223159 | 2747 | 100.8 | PV | 2-532-532 | 2017-05-22 | 2017-05-31 | 7 |  | 7 | 2017-06-30 |  | -30622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Newton | 2223207 | 2465 | 17.75 | PV | 292-H12 | 2017-05-22 | 2017-06-02 | 9 |  | 9 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-24 | 2017-09-13 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online
NSTAR | Dedham | 2223211 | 2026 | 135 | CHP | 20-H6 | 2017-05-26 | 2017-06-05 | 6 |  | 6 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2223213 | 2053 | 20 | PV | 65-H5 | 2017-05-16 | 2017-06-05 | 14 |  | 14 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-04 | 2017-08-09 | [6 empty] | 0 |  | 0 |  |  | 2017-10-02 | Online
NSTAR | Woburn | 2223988 | 2116 | 602 | PV | 375-H9 | 2017-06-05 | 2017-06-07 | 2 |  | 2 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2223989 | 2739 | 43.17 | PV | 2-301-301 | 2017-06-02 | 2017-06-08 | 4 |  | 4 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-26 | 2017-08-17 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2223990 | 1720 | 167 | PV | 416-H4 | 2017-06-07 | 2017-06-15 | 6 |  | 6 | 2017-07-07 |  | -30627 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2224177 | 2054 | 17.1 | PV | 65-H1 | 2017-06-01 | 2017-06-19 | 12 |  | 12 | 2017-07-10 |  | -30628 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-08 | 2017-10-04 | [6 empty] | 0 |  | 0 |  |  | 2018-01-03 | Online
NSTAR | West Roxbury | 2224405 | 2132 | 498 | PV | 496-H3 | 2017-06-09 | 2017-06-19 | 6 |  | 6 | 2017-07-10 |  | -30628 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2224625 | 2452 | 499.5 | PV | 277-1367XYH | 2017-06-28 | 2017-07-03 | 3 |  | 3 | 2017-07-11 |  | -30629 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-21 | Online
NSTAR | Fairhaven | 2224661 | 2702 | 4900 | PV | 2-605-605 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2224664 | 2571 | 3300 | PV | 3-85-928 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -19 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-12-12 | Online
NSTAR | Freetown | 2224890 | 2702 | 4900 | PV | 2-102-102 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2225509 | 2125 | 210 | Fuel Cell | 106-H4 | 2017-06-15 | 2017-06-19 | 2 |  | 2 | 2017-07-17 |  | -30633 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2019-04-04 | Online
NSTAR | Kingston | 2225512 | 2364 | 20.4 | PV | 3-18-36J1 | 2017-06-08 | 2017-06-20 | 8 |  | 8 | 2017-07-17 |  | -30633 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-20 | 2017-07-21 | [6 empty] | 0 |  | 0 |  |  | 2017-09-05 | Online
NSTAR | Waltham | 2226333 | 2453 | 180 | PV | 282-H8 | 2017-06-01 | 2017-06-20 | 13 |  | 13 | 2017-07-21 |  | -30637 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Dorchester | 2226367 | 2021 | 56.35 | PV | 143-109H4 | 2017-06-12 | 2017-06-28 | 12 |  | 12 | 2017-07-20 |  | -30636 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | West Newton | 2226368 | 2465 | 15.95 | PV | 282-H9 | 2017-06-15 | 2017-06-28 | 9 |  | 9 | 2017-07-20 |  | -30636 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-29 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Brewster | 2226549 | 2631 | 19.2 | PV | 4-89B-576 | 2017-06-23 | 2017-06-28 | 3 |  | 3 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-01 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online
NSTAR | Framingham | 2226553 | 1702 | 120 | PV | 240-H4 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Natick | 2226744 | 1760 | 497 | PV | 240-H1 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-05-01 | [6 empty] | 0 |  | 0
NSTAR | Lexington | 2226745 | 2421 | 860.6 | PV | 450-H5 | 2017-06-27 | 2017-07-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | New Bedford | 2227188 | 2745 | 499.05 | PV | 2-107-107 | 2017-06-16 | 2017-07-10 | 16 |  | 16 | 2017-07-26 |  | -30640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2017-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | New Bedford | 2227197 | 2740 | 700 | PV | 2-152-152 | 2017-06-15 | 2017-06-29 | 10 |  | 10 | 2017-07-26 |  | -30640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | [7 empty] | 0 |  | 0 | 2018-12-21 |  | 2018-12-21
NSTAR | Maynard | 2227357 | 1754 | 3516 | PV | 416-H6 | 2017-06-22 | 2017-07-06 | 10 |  | 10 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-19 | 2018-02-20 | -21 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Orleans | 2227358 | 2653 | 58.6 | PV | 4-83-952 | 2017-06-05 | 2017-06-15 | 8 |  | 8 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Plymouth | 2227360 | 2360 | 18 | PV | 3-89-926 | 2017-06-27 | 2017-07-06 | 7 |  | 7 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-02 | [6 empty] | 0 |  | 0 |  |  | 2017-12-11 | Online
NSTAR | Westport | 2227530 | 2790 | 480 | PV | 2-523-523 | 2017-05-09 | 2017-06-28 | 36 |  | 36 | 2017-07-31 |  | -30643 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | New Bedford | 2227939 | 2745 | 632.7 | PV | 2-83-83 | 2017-06-30 | 2017-07-07 | 5 |  | 5 | 2017-08-01 |  | -30644 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-11-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2227941 | 1702 | 1095.78 | PV | 240-H6 | 2017-06-26 | 2017-07-06 | 8 |  | 8 | 2017-08-01 |  | -30644 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Weston | 2228145 | 2493 | 24.82 | PV | 282-H1 | 2017-06-27 | 2017-07-11 | 10 |  | 10 | 2017-08-02 |  | -30645 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-21 | 2017-08-25 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Westport | 2228336 | 2790 | 2000 | PV | 2-524-524 | 2017-07-03 | 2017-07-11 | 6 |  | 6 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 |  | -30663 |  | 0 |  |  | 0 |  | 0 | 2017-12-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2228337 | 2601 | 997.965 | PV | 4-80B-80B | 2017-06-13 | 2017-07-12 | 21 |  | 21 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | West Yarmouth | 2228338 | 2673 | 39 | PV | 4-64-536 | 2017-06-26 | 2017-07-12 | 12 |  | 12 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-26 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Falmouth | 2228808 | 2536 | 7190 | PV | 4-98A-429 | 2017-06-30 | 2017-07-12 | 8 |  | 8 | 2017-08-04 |  | -30647 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-23 | 2018-01-17 | 257 |  | 257 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
NSTAR | Mattapoisett | 2229139 | 2739 | - |  | TBD | 2017-08-07 |  | -30648 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-03-16 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | N
NSTAR | Dorchester | 2229211 | 2121 | 40.7 | PV | 483-H2 | 2017-07-10 | 2017-07-17 | 5 |  | 5 | 2017-08-08 |  | -30649 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dover | 2229213 | 2030 | 28 | PV | 456-H3 | 2017-07-07 | 2017-07-19 | 8 |  | 8 | 2017-08-08 |  | -30649 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2229434 | 1746 | 44 | PV | 130-H1 | 2017-07-18 | 2017-07-21 | 3 |  | 3 | 2017-08-09 |  | -30650 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-23 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Norfolk | 2229611 | 2056 | 34.5 | PV | 146-H3 | 2017-07-11 | 2017-07-19 | 6 |  | 6 | 2017-08-10 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Holliston | 2229612 | 1746 | 15.2 | PV | 130-H1 | 2017-06-16 | 2017-07-19 | 23 |  | 23 | 2017-08-10 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-01 | Online
NSTAR | Acton | 2229787 | 1720 | 22.8 | PV | 416-H4 | 2017-07-10 | 2017-07-24 | 10 |  | 10 | 2017-08-11 |  | -30652 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2229788 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-11 |  | -30652 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Natick | 2229922 | 1760 | 466.2 | PV | 433-H10 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-04 | 2018-01-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online | [5 empty] | Private
NSTAR | Natick | 2229933 | 1760 | 466.2 | PV | 433-H14 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-02 | 2017-01-08 | -281 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | 2018-11-29 |  |  | Standard |  |  |  | 0 |  | 0 |  |  | 2019-11-20 | Online
NSTAR | Dorchester | 2229935 | 2124 | 24 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-30 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Wareham | 2230372 | 2576 | 24.5 | PV | 3-85-85 | 2017-07-14 | 2017-07-25 | 7 |  | 7 | 2017-08-16 |  | -30655 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-08 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2230376 | 1748 | 3960 | PV | 126-H2 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-16 |  | -30655 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2230557 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2230560 | 2081 | 590 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-17 |  | -30656 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dorchester | 2230829 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-18 |  | -30657 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231017 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-21 |  | -30658 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231474 | 2121 | 32.85 | PV | 143-109H4 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-23 |  | -30660 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231481 | 2124 | 30 | PV | 143-109H4 | 2017-07-18 | 2017-07-26 | 6 |  | 6 | 2017-08-23 |  | -30660 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231678 | 2121 | 36 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2017-12-04 | Online
NSTAR | Dorchester | 2231683 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Walpole | 2231849 | 2081 | 402 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2231851 | 2081 | 362 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Lexington | 2231852 | 2420 | 25 | PV | 533-H3 | 2017-07-07 | 2017-07-27 | 14 |  | 14 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Sandwich | 2232261 | 2563 | 66.6 | PV | 4-81B-81B | 2017-07-23 | 2017-07-31 | 6 |  | 6 | 2017-08-29 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2018-01-02 | [6 empty] | 0 |  | 0 |  |  | 2018-04-16 | Online
NSTAR | Dorchester | 2232263 | 2124 | 48 | PV | 483-H7 | 2017-07-27 | 2017-07-31 | 2 |  | 2 | 2017-08-29 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Bourne | 2232421 | 2532 | 36 | PV | 3-89-925 | 2017-07-25 | 2017-07-31 | 4 |  | 4 | 2017-08-30 |  | -30665 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-13 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Dorchester | 2232422 | 2124 | 43.2 | PV | 483-H5 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-08-30 |  | -30665 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online
NSTAR | Dorchester | 2232784 | 2124 | 72 | PV | 483-H4 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-09-05 |  | -30669 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-22 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03 | Online
NSTAR | Walpole | 2233507 | 2081 | 336 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-06 |  | -30670 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2233722 | 2081 | 368 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2019-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-07-03 | Online
NSTAR | Walpole | 2233726 | 2081 | 662 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Wareham | 2233733 | 2576 | 2000 | PV | 3-85-85 | 2017-07-31 | 2017-08-01 | 1 |  | 1 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-26 | 2018-01-23 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Woods Hole | 2233739 | 2540 | 86.4 | PV | 4-72-433 | 2017-08-03 | 2017-08-03 | 0 |  | 0 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-06-08 | Online
NSTAR | Falmouth | 2233941 | 2540 | 33.3 | PV | 4-72-433 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | West Tisbury | 2233942 | 2575 | 48 | PV | 4-97-220 | 2017-08-02 | 2017-08-08 | 4 |  | 4 | 2017-09-11 |  | -30673 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2234087 | 2081 | 24 | PV | 456-H1 | 2017-08-01 | 2017-08-15 | 10 |  | 10 | 2017-09-12 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-17 | 2017-10-17 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2234091 | 2081 | 782 | PV | 146-H1 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-12 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2234593 | 2081 | 132 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-09-13 |  | -30675 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dartmouth | 2234626 | 2747 | 594 | PV | 2-532-532 | 2017-08-08 | 2017-08-11 | 3 |  | 3 | 2017-09-13 |  | -30675 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-11-15 | 30719 |  | 30719 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2234823 | 1721 | 1080 | PV | 274-1429H1 | 2017-08-02 | 2017-08-15 | 9 |  | 9 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2234830 | 2330 | 21.9 | PV | 3-10-929 | 2017-08-10 | 2017-08-15 | 3 | 0 | 3 | 2017-09-13 |  | -30675 | 6 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-24 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Woburn | 2234836 | 1801 | 16.7 | PV | 375-H12 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-12-05 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2234838 | 1801 | 16.7 | PV | 375-H14 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2235080 | 2131 | 180 | PV | 385-H15 | 2017-07-06 | 2017-08-15 | 28 |  | 28 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2235082 | 1748 | 59 | PV | 126-H2 | 2017-08-01 | 2017-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-23 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-04-11 | Online
NSTAR | Barnstable | 2235087 | 2090 | 3720 | PV | 4-88-453 | 2017-08-17 | 2017-08-18 | 1 |  | 1 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-26 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2235287 | 1802 | 42 | PV | 240-H3 | 2017-08-16 | 2017-08-22 | 4 |  | 4 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2018-05-29 | Online
NSTAR | Barnstable | 2235688 | 2571 | 472 | PV | 4-80B-80B | 2017-07-24 | 2017-10-17 | 61 |  | 61 | 2017-11-06 |  | -30713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2235692 | 2134 | 133.2 | PV | 250-1N39H1 | 2017-08-22 | 2017-08-28 | 4 |  | 4 | 2017-10-19 |  | -30701 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-16 | 2017-10-19 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Hyannis | 2235860 | 2601 | 28.8 | PV | 4-84B-524 | 2017-08-25 | 2017-08-29 | 2 |  | 2 | 2017-09-20 |  | -30680 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-05 | 2018-01-12 | [6 empty] | 0 |  | 0 |  |  | 2018-02-08 | Online
NSTAR | Wareham | 2236093 | 2571 | 46.8 | PV | 3-85-964 | 2017-08-07 | 2017-08-29 | 16 |  | 16 | 2017-09-21 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-27 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Natick | 2236094 | 1760 | 51.75 | PV | 433-H9 | 2017-08-29 | 2017-08-30 | 1 |  | 1 | 2017-09-21 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-10-25 | [6 empty] | 0 |  | 0 |  |  | 2018-03-23 | Online
NSTAR | Canton | 2236306 | 2021 | 208 | PV | 470-H11 | 2017-08-24 | 2017-08-30 | 4 |  | 4 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2236312 | 2126 | 30.5 | PV | 311-12 | 2017-08-31 | 2017-08-31 | 0 |  | 0 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Ashland | 2236318 | 1721 | 92 | PV | 274-1429H1 | 2017-08-31 | 2017-09-01 | 1 |  | 1 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2236710 | 2026 | 170 | PV | 20-H6 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-07 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2019-06-25 | Online
NSTAR | Boston | 2236712 | 2115 | 15.2 | PV | 2-1N45 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-18 | 2017-12-19 | [6 empty] | 0 |  | 0 |  |  | 2018-04-24 | Online
NSTAR | Boston | 2236713 | 2215 | 21.9 | PV | 350-H10 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-08 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Yarmouth | 2236910 | 2675 | 23.2 | PV | 4-90-541 | 2017-09-01 | 2017-09-06 | 3 |  | 3 | 2017-09-27 |  | -30685 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-26 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2236911 | 1803 | 27.9 | PV | 346-1395H1 | 2017-09-01 | 2017-09-06 | 3 |  | 3 | 2017-09-27 |  | -30685 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2237110 | 2536 | 159.9 | PV | 4-98B-449 | 2017-09-06 | 2017-09-08 | 2 |  | 2 | 2017-09-28 |  | -30686 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-21 | [6 empty] | 0 |  | 0 |  |  | 2018-06-28 | Online
NSTAR | Wellfleet | 2237326 | 2667 | 17.92 | PV | 4-96-960 | 2017-09-07 | 2017-09-14 | 5 |  | 5 | 2017-09-29 | 2017-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-10-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Westport | 2237335 | 2790 | 268 | PV | 2-532-532 | 2017-09-06 | 2017-09-14 | 6 |  | 6 | 2017-09-29 | 2017-10-16 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-12-27 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2237797 | 2571 | 294 | PV | 3-86-966 | 2017-09-06 | 2017-09-11 | 3 |  | 3 | 2017-10-03 | 2017-10-17 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marshfield | 2237799 | 2050 | 27.5 | PV | 3-25-42J2 | 2017-08-22 | 2017-09-13 | 16 |  | 16 | 2017-10-03 |  | -30689 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-11 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Plymouth | 2238366 | 2360 | 499.5 | PV | 3-14-911 | 2017-05-15 | 2017-09-13 | 87 |  | 87 | 2017-10-04 | 2017-10-17 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2019-02-11
NSTAR | Hopkinton | 2238660 | 1748 | 7520 | PV | 126-H2 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-05 |  | -30691 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2238661 | 2717 | 1156 | PV & Battery |  | 2017-10-04 | 2017-10-06 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2019-05-16 | 416 | 333 | 83 |  |  | 0 |  | 0 | 2019-06-25 | 2019-07-10 | 11 | 0 | 11 | 2019-02-25 | 2019-08-01 | 2020-03-01 | No |  | 60 | 2020-01-30 |  | -31296 |  | 0 |  |  |  | In Queue | [5 empty] | Private | N
NSTAR | Cambridge | 2238845 | 2139 | 1330 | PV | 875-1312 | 2017-06-02 | 2017-10-05 | 89 |  | 89 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-09 | 2018-01-05 | -4 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online | [5 empty] | Public
NSTAR | Buzzards Bay | 2239274 | 2532 | 119.9 | PV | 3-88-2J4 | 2017-09-12 | 2017-09-13 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Plympton | 2239531 | 2367 | 4695 | PV & Battery | TBD | 2017-09-17 | 2017-09-17 | 0 |  | 0 | 2017-09-17 |  | -30677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-21 | Online
NSTAR | Brighton | 2239744 | 2134 | 7500 | CHP |  | 2017-10-04 | 2017-10-04 | 0 |  | 0 | 2017-10-13 |  | -30697 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-26 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Dartmouth | 2239746 | 2747 | 997.7 | PV | 2-543-543 | 2017-09-11 | 2017-09-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2239974 | 1801 | 57.5 | PV | 4W5-H1 | 2017-09-07 | 2017-09-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-07-20 | Online
NSTAR | Roslindale | 2240297 | 2131 | 338 | PV | 496-H4 | 2017-09-12 | 2017-09-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Waltham | 2240718 | 2452 | 266.4 | PV | 450-H4 | 2017-09-21 | 2017-09-27 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2018-07-06 | Online
NSTAR | Plymouth | 2240998 | 2360 | - |  | TBD | 2017-10-18 |  | -30700 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sharon | 2241001 | 2067 | 272 | PV | 146-H1 | 2017-10-04 | 2017-10-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-28 | 2018-08-30 | [6 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online | [5 empty] | Private
NSTAR | Acton | 2241211 | 1720 | 22.8 | PV | 416-H8 | 2017-09-22 | 2017-09-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-28 | 2017-12-05 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2241214 | 2364 | 33.3 | PV | 3-17-17 | 2017-09-27 | 2017-10-03 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Milton | 2241676 | 2186 | 21.9 | PV | 362-02 | 2017-10-03 | 2017-10-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-10 | 2017-11-13 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online
NSTAR | South Yarmouth | 2241680 | 2664 | 124.47 | PV | 4-92A-562 | 2017-09-27 | 2017-10-03 | 4 |  | 4 | 2017-10-10 |  | -30694 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Plympton | 2241681 | 2367 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2241682 | 2748 | 22.8 | PV | 2-528-528 | 2017-10-02 | 2017-10-10 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-09 | Online
NSTAR | Framingham | 2242066 | 1702 | 20 | PV | 455-H5 | 2017-08-30 | 2017-10-11 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2242067 | 1748 | 299.7 | PV | 126-H1 | 2017-09-29 | 2017-10-10 | 7 |  | 7 | 2017-11-02 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private | Y
NSTAR | Waltham | 2242293 | 2451 | 210 | PV | 450-H1 | 2017-10-10 | 2017-10-31 | 15 |  | 15 | 2017-11-02 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-19 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Plymouth | 2242294 | 2360 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-05 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Roxbury | 2242468 | 2119 | 15.5 | PV | 52-148H1 | 2017-09-13 | 2017-10-17 | 24 |  | 24 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-29 | 2017-12-07 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Framingham | 2243010 | 1702 | 256 | PV | 455-H4 | 2017-10-04 | 2017-10-18 | 10 |  | 10 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-08-06 | Online
NSTAR | Barnstable | 2243747 | 2668 | 33.6 | PV | 4-82-516 | 2017-10-10 | 2017-10-18 | 6 |  | 6 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-09-17 | Online
NSTAR | Vineyard Haven | 2243750 | 2658 | 22 | PV | 4-91-228 | 2017-10-16 | 2017-10-18 | 2 |  | 2 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | 2018-08-09 | [6 empty] | 0 |  | 0 |  |  |  | Revised ISA/WO (2287709)
NSTAR | Westport | 2243995 | 2790 | 2400 | PV | 2-532-532 | 2017-10-04 | 2017-10-13 | 7 |  | 7 | 2017-11-06 |  | -30713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-04-12 | 30825 |  | 30825 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-14 | Online
NSTAR | Oak Bluffs | 2244459 | 2557 | 20.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2244463 | 2557 | 27.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2244680 | 2139 | 33.3 | PV | 814-13 | 2017-10-17 | 2017-10-19 | 2 |  | 2 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2244684 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | West Roxbury | 2244833 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Waltham | 2245190 | 2451 | 599 | PV | TBD | 2017-11-13 |  | -30718 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Waltham | 2245192 | 2451 | 599 | PV | 450-H2 | 2017-10-10 | 2017-10-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2245194 | 2451 | 632.7 | PV | 282-H5 | 2017-08-15 | 2017-10-27 | 53 |  | 53 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2245195 | 2539 | 74.4 | PV | 4-97-97 | 2017-10-18 | 2017-10-23 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-04 | Online
NSTAR | Plymouth | 2245196 | 2360 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | South Carver | 2245475 | 2366 | 88 | PV | 3-81-81 | 2017-10-23 | 2017-10-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Ashland | 2245647 | 1721 | 773.6 | PV | 274-H1 | 2017-11-02 | 2017-11-02 | 0 |  | 0 | 2017-11-16 |  | -30721 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2245650 | 1773 | 199.8 | PV | 320-H6 | 2017-09-26 | 2017-11-02 | 27 |  | 27 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-03 | 2018-02-15 | [6 empty] | 0 |  | 0 |  |  | 2018-10-04 | Online
NSTAR | Plymouth | 2245961 | 2360 | 48 | PV | 3-13-936 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-30 | Online
NSTAR | Allston | 2246186 | 2134 | 66.6 | PV | 3614 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-27 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-27 | Online
NSTAR | Canton | 2246191 | 2021 | 24 | PV | 470-H9 | 2017-10-10 | 2017-10-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2246192 | 2790 | 21.95 | PV | 2-532-532 | 2017-10-11 | 2017-10-23 | 8 |  | 8 | 2017-11-20 |  | -30723 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Boston | 2246431 | 2128 | 978 | PV | 108-195H1 | 2017-10-31 | 2017-11-03 | 3 |  | 3 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | 2018-03-02 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2246432 | 1748 | 15.2 | PV | 65-H6 | 2017-10-16 | 2017-10-26 | 8 |  | 8 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-02 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2246565 | 2451 | 366.3 | PV | 282-H5 | 2017-08-11 | 2017-10-27 | 55 |  | 55 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2246979 | 2536 | 1500 | PV | 4-98A-98A | 2017-10-12 | 2017-11-07 | 18 |  | 18 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-22 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2246980 | 2770 | 1000 | PV | 3-85-85 | 2017-10-27 | 2017-11-07 | 7 |  | 7 | 2017-11-29 | 2018-11-06 | 244 |  | 244 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | Standard |  |  |  | 0 |  | 0 | [9 empty] | Private
NSTAR | Wareham | 2247147 | 2571 | 26.35 | PV | 3-85-85 | 2017-10-20 | 2017-10-26 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2247148 | 2121 | 57.6 | PV | 483-H3 | 2017-10-20 | 2017-10-27 | 5 |  | 5 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2247317 | 2421 | 840 | PV | TBD | 2017-11-29 | 2017-11-30 | 1 | 0 | 1 | 2017-12-05 | 2018-02-09 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-12-28 |  | 2018-07-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2017-12-29 | Withdrawn
NSTAR | Fairhaven | 2247327 | 2719 | 53.3 | PV | 2-240-240 | 2017-10-24 | 2017-11-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2247506 | 2364 | 23 | PV | 3-18-36J1 | 2017-10-10 | 2017-11-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Edgartown | 2247507 | 2539 | 133.2 | PV | 4-97-97 | 2017-10-23 | 2017-11-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Wareham | 2247812 | 2571 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-07-11 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2247816 | 2330 | 1500 | PV | 3-10-10 | 2017-10-27 | 2017-11-08 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2247819 | 2571 | 8300 | PV & Battery | 3-83-83 | 2017-11-09 | 2017-11-23 | 10 |  | 10 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-12-16 | Online
NSTAR | Hopkinton | 2249982 | 1748 | 84 | PV | 126-H4 | 2017-10-19 | 2017-10-19 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-08 | Online
NSTAR | Canton | 2250080 | 2021 | 964 | PV | 470-H10 | 2017-10-18 | 2017-11-15 | 20 |  | 20 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-07-23 | Online
NSTAR | Burlington | 2250081 | 1803 | 34.8 | PV | 391-H2 | 2017-11-09 | 2017-11-14 | 3 |  | 3 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-03-22 | [6 empty] | 0 |  | 0 |  |  | 2018-06-07 | Online
NSTAR | Carver | 2250250 | 2330 | 8300 | PV & Battery | 3-81-81 | 2017-11-14 | 2017-11-14 | 0 |  | 0 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Somerville | 2250465 | 2144 | 100.8 | PV | 1604 | 2017-11-14 | 2017-11-29 | 11 |  | 11 | 2017-12-07 |  | -30736 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Assonett | 2250466 | 2702 | 15.2 | PV | 2-605-605 | 2017-11-14 | 2017-11-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Somerville | 2250669 | 2143 | 150 | PV | 387-148H2 | 2017-11-10 | 2017-11-14 | 2 |  | 2 | 2017-12-08 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-26 | 2018-03-12 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2250671 | 1720 | 66 | PV | 416-H4 | 2017-11-08 | 2017-11-17 | 7 |  | 7 | 2017-12-08 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-30 | Online
NSTAR | Duxbury | 2251155 | 2332 | 300 | PV | 3-26-903 | 2017-11-17 | 2017-11-17 | 0 |  | 0 | 2017-12-12 |  | -30739 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2251157 | 2421 | 21.11 | PV | 320-H5XY | 2017-11-13 | 2017-11-17 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-25 | Online
NSTAR | Kingston | 2251317 | 2364 | 232 | PV | 3-17-17 | 2017-10-15 | 2017-11-21 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-16 | Online
NSTAR | Hyannis | 2251318 | 2601 | 250 | PV | 4-63-63 | 2017-11-10 | 2017-11-21 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-08 | Online
NSTAR | Plymouth | 2251494 | 2360 | 20 | PV | 40613 | 2017-11-15 | 2017-11-21 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Orleans | 2251495 | 2653 | 64 | PV | 4-94A-633 | 2017-10-15 | 2017-11-17 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Natick | 2252677 | 1760 | 1700 | CHP | 23-1339H2 | 2017-12-01 | 2017-12-19 | 12 |  | 12 | 2017-12-20 |  | -30745 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2252869 | 2536 | 19.3 | PV | 4-98B-449 | 2017-11-10 | 2017-11-30 | 14 |  | 14 | 2017-12-21 |  | -30746 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-01 | [6 empty] | 0 |  | 0 |  |  | 2018-10-05 | Online
NSTAR | Millis | 2253053 | 2054 | 46 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 4 |  | 4 | 2017-12-22 |  | -30747 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-21 | 2018-03-27 | [6 empty] | 0 |  | 0
NSTAR | Millis | 2253054 | 2054 | 40.25 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2253056 | 2021 | 432.9 | PV | 470-H4 | 2017-11-24 | 2017-12-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Newton | 2253263 | 2465 | 24.95 | PV | 282-H9 | 2017-10-30 | 2017-12-05 | 26 |  | 26 | 2018-12-27 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Somerville | 2253264 | 2144 | 52.2 | PV | 1604 | 2017-11-10 | 2017-12-12 | 22 |  | 22 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Wareham | 2253372 | 2576 | 4320 | PV & Battery | 3-83-83 | 2017-11-10 | 2017-12-07 | 19 |  | 19 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2253373 | 2144 | 72 | PV | 1604 | 2017-11-10 | 2017-12-07 | 19 |  | 19 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Somerville | 2253374 | 2144 | 50.4 | PV | 1604 | 2017-11-10 | 2017-12-12 | 22 |  | 22 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Hopkinton | 2255236 | 1748 | 18 | PV | 126-H1 | 2017-11-30 | 2017-12-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-03 | Online
NSTAR | Norfolk | 2255237 | 2056 | 152 | PV | 146-H3 | 2017-12-08 | 2017-12-18 | 6 |  | 6 | 2018-01-03 |  | -30755 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-08-15 | Online
NSTAR | Bedford | 2255723 | 1730 | 138 | PV | 533-H7 | 2017-12-01 | 2017-12-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2255727 | 2330 | 5980 | PV & Battery | 3-83-83 | 2017-11-20 | 2017-12-11 | 15 |  | 15 | 2018-01-08 |  | -30758 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Fairhaven | 2255728 | 2719 | 3750 | PV | 2-221-221 | 2017-12-04 | 2017-12-11 | 5 |  | 5 | 2018-01-08 |  | -30758 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-24 | 2018-04-23 | -3 |  | 0 |  |  | 0 |  | 0 | 2018-09-26 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Plymouth | 2257795 | 2360 | 480 | PV | 3-13-943 | 2017-12-12 | 2017-12-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Stoneham | 2257799 | 2180 | 15.95 | PV | 375-H8 | 2017-12-05 | 2017-12-11 | 4 |  | 4 | 2018-01-09 | 2018-11-01 | 212 |  | 212 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2258018 | 2571 | 15.2 | PV | 3-84-968 | 2017-12-12 | 2017-12-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2258119 | 2136 | 19.6 | PV | 60-1409H1 | 2017-12-13 | 2017-12-18 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2258239 | 2081 | 218.5 | PV | 146-H1 | 2017-10-31 | 2017-12-18 | 34 |  | 34 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2258388 | 2180 | 17.575 | PV | 375-H8 | 2017-12-18 | 2017-12-21 | 3 |  | 3 | 2018-01-12 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2258392 | 2458 | 199.8 | PV | 467-H3 | 2017-12-15 | 2017-12-22 | 5 |  | 5 | 2018-01-12 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-14 | 2018-03-16 | [6 empty] | 0 |  | 0 |  |  | 2019-01-28 | Online
NSTAR | Boston | 2258582 | 2136 | 992 | PV | 344-1413H1 | 2017-12-22 | 2018-01-03 | 8 |  | 8 | 2018-01-17 |  | -30765 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Rochester | 2258583 | 2770 | 7415 | PV |  | 2018-01-12 | 2018-01-17 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-17 | 2020-01-07 | 514 | 234 | 280 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-17 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  | 2023-01-19 | Online | [5 empty] | Private | N
NSTAR | Assonett | 2258821 | 2702 | 16.7 | PV | 2-605-605 | 2017-12-18 | 2017-12-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2258823 | 2130 | 23 | PV | 284-02 | 2017-12-21 | 2017-12-28 | 5 |  | 5 | 2018-01-17 |  | -30765 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2259134 | 2660 | 149.5 | PV | 4-92B-92B | 2017-10-23 | 2017-12-28 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-03-12
NSTAR | Allston | 2259136 | 2134 | 99.9 | PV | 456-H3 | 2017-12-02 | 2017-12-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Rochester | 2259340 | 2770 | 3320 | PV | TBD | 2018-01-18 |  | -30766 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-01-23 | 2019-09-30 | 439 | 160 | 279 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-05-07 |  | 2019-06-30 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2259341 | 2138 | 13.6 | PV & Battery | 821-22 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-22 |  | -30768 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0
NSTAR | Vineyard Haven | 2259526 | 2658 | 20 | PV | 4-91-228 | 2017-10-16 | 2018-01-04 | 58 |  | 58 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2259745 | 2139 | 76.6 | PV | 814-13 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-03-05 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2259746 | 2122 | 51.75 | PV | 466-1481H1 | 2017-12-12 | 2018-01-03 | 16 |  | 16 | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-14 | 2018-03-28 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | Cambridge | 2259916 | 2138 | 53.3 | PV | 830-11 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-24 |  | -30770 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-04-19 | [6 empty] | 0 |  | 0
NSTAR | Lincoln | 2260143 | 1773 | 43.8 | PV | 320-H1 | 2017-10-16 | 2018-01-03 | 57 |  | 57 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-27 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Wareham | 2260144 | 2571 | 7310 | PV & Battery | 3-83-83 | 2017-11-16 | 2018-01-11 | 40 |  | 40 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2260285 | 1760 | 40.25 | PV | 433-H5 | 2017-12-28 | 2017-12-28 | 0 |  | 0 | 2018-01-26 |  | -30772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-04-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Woburn | 2260286 | 1801 | 23.4 | PV | 325-03 | 2017-12-26 | 2018-01-05 | 8 |  | 8 | 2018-01-26 |  | -30772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bourne | 2260502 | 2559 | 32 | PV | 4-86-86 | 2017-12-28 | 2018-01-08 | 7 |  | 7 | 2018-01-29 |  | -30773 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Hopkinton | 2260503 | 1748 | 4000 | PV | 126-H4 | 2017-12-19 | 2018-01-09 | 15 |  | 15 | 2018-01-29 |  | -30773 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2260699 | 2571 | 8300 | PV & Battery | 3-83-83 | 2018-01-09 | 2018-01-09 | 0 |  | 0 | 2018-01-30 |  | -30774 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2260702 | 2770 | 540 | PV | TBD | 2018-01-29 |  | -30773 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-09-04 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2260703 | 2770 | 2540 | PV |  | 2018-01-29 | 2018-01-31 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 |  | -30775 | 394 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-20 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Carver | 2260848 | 2330 | 6415 | PV | 3-10-917 | 2017-12-11 | 2018-01-02 | 16 |  | 16 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2261351 | 1801 | 15.2 | PV | 375-H12 | 2018-01-03 | 2018-01-29 | 18 |  | 18 | 2018-02-01 |  | -30776 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | [7 empty] | 0 |  | 0 |  |  | 2019-09-27 | Online
NSTAR | Canton | 2261355 | 2021 | 288 | PV | 269-1321H2 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-01 | 2018-11-20 | 208 |  | 208 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 | [6 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online | [5 empty] | Private
NSTAR | Acton | 2261525 | 1720 | 143.2 | PV | 416-H4 | 2017-06-07 | 2018-01-11 | 156 |  | 156 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Sudbury | 2261526 | 1776 | 29.58 | PV | 342-H7 | 2017-12-04 | 2018-01-19 | 34 |  | 34 | 2018-02-02 |  | -30777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-23 | [6 empty] | 0 |  | 0 |  |  | 2018-07-24 | Online
NSTAR | Wayland | 2261527 | 1778 | 15.2 | PV | 433-H6 | 2017-12-12 | 2018-01-19 | 28 |  | 28 | 2018-02-02 |  | -30777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Medway | 2261707 | 2053 | 22.95 | PV | 65-H5 | 2017-12-14 | 2018-01-19 | 26 |  | 26 | 2018-02-06 |  | -30779 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Osterville | 2262127 | 2665 | 36 | PV | 4-80A-892 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-08-08 | Online
NSTAR | Millis | 2262130 | 2054 | 97.75 | PV | 146-H10 | 2017-12-01 | 2018-01-23 | 37 |  | 37 | 2018-02-07 |  | -30780 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-09 | [6 empty] | 0 |  | 0 |  |  | 2018-09-12 | Online
NSTAR | East Freetown | 2262266 | 2717 | 15.95 | PV | 2-107-107 | 2018-01-16 | 2018-01-23 | 5 |  | 5 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-28 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2262268 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-14 | Online
NSTAR | Maynard | 2262282 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2262431 | 2492 | 18.56 | PV | 148-01 | 2017-12-22 | 2018-01-25 | 24 |  | 24 | 2018-02-09 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-07 | Online
NSTAR | Waltham | 2262433 | 2465 | 80.5 | PV | 282-H9 | 2018-01-02 | 2018-01-26 | 18 |  | 18 | 2018-02-09 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Brookline | 2262436 | 2445 | 21.9 | PV | 496-H4 | 2017-10-09 | 2018-01-29 | 80 |  | 80 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2019-01-03 | Online
NSTAR | Natick | 2262597 | 1760 | 37.5 | PV | 433-H12 | 2018-01-16 | 2018-01-29 | 9 |  | 9 | 2018-02-12 |  | -30783 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Oak Bluffs | 2262599 | 2557 | 90 | PV | 4-99-99 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Provincetown | 2262605 | 2657 | 276.6 | PV | 4-96-675 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Truro | 2262805 | 2666 | 80 | PV | 4-96-674 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Eastham | 2262807 | 2642 | 109.8 | PV | 4-94A-648 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | Chatham | 2262808 | 2633 | 86.4 | PV | 4-95B-940 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-31
NSTAR | Sherborn | 2262993 | 1770 | 110 | PV | 274-H4 | 2017-11-17 | 2018-02-01 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-25 | 2018-06-29 | [6 empty] | 0 |  | 0 |  |  | 2018-04-25
NSTAR | Eastham | 2262994 | 2642 | 83 | PV | 4-94b-646 | 2018-01-13 | 2018-02-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Plympton | 2262995 | 2367 | 2310 | PV & Battery |  | 2018-02-13 | 2018-02-27 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 | 2018-08-24 | 124 | 96 | 28 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-08-28 |  | 2020-03-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Wareham | 2263854 | 2532 | 4875 | PV | 3-85-928 | 2018-01-26 | 2018-02-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2263856 | 2675 | 104.4 | PV | 4-92A-536 | 2018-01-24 | 2018-02-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-06-27 | [6 empty] | 0 |  | 0 |  |  | 2019-11-08 | Online
NSTAR | West Roxbury | 2263857 | 2132 | 588 | PV | 496-H3 | 2018-02-01 | 2018-02-05 | 2 |  | 2 | 2018-02-05 |  | -30778 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Framingham | 2264047 | 1702 | 125 | PV | 2410 | 2018-01-16 | 2018-02-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | [7 empty] | 0 |  | 0 |  |  | 2019-04-22 | Online
NSTAR | Boston | 2264049 | 2118 | 109.25 | PV | 318-10 | 2018-02-02 | 2018-02-08 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-18 | [6 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2264227 | 2664 | 33.6 | PV | 4-92A-562 | 2018-02-07 | 2018-02-12 | 3 |  | 3 | 2018-02-23 |  | -30792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-21 | [6 empty] | 0 |  | 0
NSTAR | Dartmouth | 2264231 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 | 2018-02-23 |  | -30792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Dartmouth | 2264232 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-04
NSTAR | Cambridge | 2264395 | 2140 | 466.2 | PV | 828-1382 | 2018-02-02 | 2018-02-15 | 9 |  | 9 | 2018-02-26 | 2018-03-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-23 | 2018-06-14 |  |  | Expedited |  |  |  | 0 |  | 0 | 2018-11-19 | 2018-11-19 | 2018-11-20 | Online
NSTAR | Canton | 2264634 | 2021 | 700 | PV | 470-H7 | 2014-06-12 | 2014-06-12 | 0 | 0 | 0 | 2014-06-16 | 2014-06-24 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-21 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2019-12-23 | Online | [5 empty] | Private
NSTAR | Dartmouth | 2264640 | 2747 | 1500 | PV | 2-107-107 | 2018-02-26 | 2018-02-27 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | 2020-05-04 | 568 | 122 | 446 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-12 |  | 2019-06-14 | TBD |  | 60 |  |  | 0 |  | 0 |  | 2019-06-11 | 2019-06-11 | Online | [5 empty] | Private
NSTAR | Woburn | 2264643 | 1801 | 50 | PV | 211-H6 | 2018-01-26 | 2018-02-15 | 14 |  | 14 | 2018-02-27 |  | -30794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | 2018-05-18 | [6 empty] | 0 |  | 0 |  |  | 2018-10-19
NSTAR | Yarmouth | 2264855 | 2664 | 52.2 | PV | 4-92a-562 | 2018-01-24 | 2018-02-15 | 16 |  | 16 | 2018-02-28 |  | -30795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Rochester | 2264857 | 2770 | 4650 | PV |  | 2018-02-27 | 2018-03-01 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 |  | -30798 | 660 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2018-05-11 | Private
NSTAR | Walpole | 2265026 | 2032 | 2370 | PV | 146-H6 | 2018-02-16 | 2018-04-03 | 32 |  | 32 | 2018-03-01 |  | -30796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-03-01 | 30795 |  | 30795 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2265032 | 2118 | 30 | PV | 323-175H | 2018-02-02 | 2018-08-23 | 144 |  | 144 | 2018-08-23 |  | -30921 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 2265246 | 2186 | 15.2 | PV | 362-02 | 2018-02-09 | 2018-02-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2265247 | 2576 | 201.6 | PV | 3-83-83 | 2018-02-05 | 2018-02-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-09 | [6 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Cambridge | 2267013 | 2138 | 100.8 | PV | 829-19 | 2018-01-09 | 2018-02-20 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-05 | Online
NSTAR | Cambridge | 2267217 | 2138 | 66.6 | PV | 814-13 | 2018-02-08 | 2018-02-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Plymouth | 2267338 | 2360 | 272 | PV | 3-71-937 | 2017-11-30 | 2018-02-07 | 49 |  | 49 | 2018-03-23 |  | -30812 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-04-30 | [6 empty] | 0 |  | 0 |  |  | 2018-08-17 | Online
NSTAR | Boston | 2267381 | 2135 | 75 | Gas Turbine | 548-193 | 2017-12-21 | 2018-02-21 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-08-27 | Online
NSTAR | Somerville | 2267712 | 2143 | 42 | PV | 250-1N81H1 | 2018-02-14 | 2018-02-28 | 10 |  | 10 | 2018-03-23 |  | -30812 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-07-17 | Online
NSTAR | Dorchester | 2267902 | 2121 | 43.2 | PV | 483-H5 | 2018-02-28 | 2018-02-28 | 0 |  | 0 | 2018-03-26 |  | -30813 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | Westport | 2268194 | 2748 | 5000 | PV & Battery | 2-523-523 | 2018-02-15 | 2018-02-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2268196 | 2056 | 66.6 | PV | 146-H3 | 2018-02-21 | 2018-02-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0 |  |  | 2018-12-04 | Online
NSTAR | New Bedford | 2268420 | 2745 | 120 | PV | 2-104-104 | 2018-02-21 | 2018-03-15 | 16 |  | 16 | 2018-03-28 |  | -30815 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online | [5 empty] | Private
NSTAR | New Bedford | 2268649 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268650 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268651 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268866 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268869 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2269021 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Rochester | 2269022 | 2770 | 1250 | PV | TBD | 2018-03-30 |  | -30817 | 0 | 0 | 2018-04-02 | 2020-07-20 | 600 | 572 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sudbury | 2269609 | 1776 | 240 | PV | 342-H5 | 2018-02-21 | 2018-03-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-10 | [6 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Dartmouth | 2269612 | 2747 | 1000 | PV | 2-532-532 | 2018-02-02 | 2018-03-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-31 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2269886 | 2030 | 25 | PV | 456-H5 | 2018-02-23 | 2018-03-06 | 7 |  | 7 | 2018-04-04 |  | -30820 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2018-07-19 | Online
NSTAR | Dartmouth | 2269896 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30821 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2270084 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30821 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2270087 | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-31 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2270295 | 2364 | 150 | PV | 3-26-902 | 2018-02-22 | 2018-03-07 | 9 |  | 9 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0
NSTAR | Marion | 2270301 | 2738 | 17.6 | PV | 2-304-304 | 2018-03-08 | 2018-03-09 | 1 |  | 1 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | New Bedford | 2270504 | 2744 | 599.4 | PV | 2-54-54 | 2018-01-22 | 2018-03-14 | 37 |  | 37 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-15 | 2018-06-22 | [6 empty] | 0 |  | 0 |  |  | 2019-07-19 | Online
NSTAR | Fairhaven | 2270747 | 2719 | 8300 | PV & Battery | 2-241-241 | 2018-03-01 | 2018-03-14 | 9 |  | 9 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2270749 | 2743 | 5000 | PV |  | 2018-04-09 | 2018-04-11 | 2 | 0 | 2 | 2018-04-11 |  | -30825 | 681 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2018-04-12 | Private
NSTAR | Millis | 2270750 | 2054 | 199.8 | PV | 65-H1 | 2018-02-23 | 2018-03-16 | 15 |  | 15 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Framingham | 2270751 | 1702 | 528 | PV | 519-175H1 | 2018-01-31 | 2018-03-21 | 35 |  | 35 | 2018-04-11 | 2018-11-29 | 166 |  | 166 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-29 |  |  | Standard |  |  |  | 0 |  | 0 |  |  | 2021-06-28 | Online | [5 empty] | Private
NSTAR | Acton | 2271183 | 1720 | 5040 | PV & Battery | 416-H9 | 2018-03-01 | 2018-03-21 | 14 |  | 14 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Chilmark | 2271199 | 2535 | 40.35 | PV | 4-97-226 | 2018-02-06 | 2018-03-21 | 31 |  | 31 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-24 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271201 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-22 | 15 |  | 15 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Wellfleet | 2271202 | 2663 | 48.56 | PV | 4-96-960 | 2018-02-26 | 2018-03-23 | 19 |  | 19 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271377 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-26 | 17 |  | 17 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | [6 empty] | 2018-07-16 | 30892 |  | 30892 |  |  | 2019-05-16 | Online
NSTAR | Walpole | 2271379 | 2081 | 480 | PV | 146-H6 | 2018-03-16 | 2018-03-26 | 6 |  | 6 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2271383 | 2360 | 4986 | PV | 3-89-922 | 2018-03-12 | 2018-03-27 | 11 |  | 11 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2271557 | 2743 | 9878 | PV & Battery | 2-106-160 | 2018-03-19 | 2018-03-28 | 7 |  | 7 | 2018-04-16 |  | -30828 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2271561 | 2163 | 56 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-16 |  | -30828 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2272015 | 2138 | 16 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2272017 | 2138 | 32 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-27
NSTAR | Orleans | 2272019 | 2653 | 23.1 | PV | 4-83-952 | 2018-03-26 | 2018-03-29 | 3 |  | 3 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-06-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-20 | Online
NSTAR | Watertown | 2272442 | 2472 | 166.5 | PV | 467-H6 | 2018-03-16 | 2018-03-29 | 9 |  | 9 | 2018-03-29 |  | -30816 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Acton | 2272445 | 1720 | 2100 | PV & Battery | 416-H2 | 2018-03-23 | 2018-04-04 | 8 |  | 8 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Hopkinton | 2272446 | 1748 | 19 | PV | 130-H1 | 2018-03-01 | 2018-04-03 | 23 |  | 23 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-05 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Carver | 2272654 | 2330 | 104.4 | PV | 3-81-81 | 2018-03-16 | 2018-04-03 | 12 |  | 12 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-18 | [6 empty] | 0 |  | 0 |  |  | 2021-06-18 | Online
NSTAR | Holliston | 2272656 | 1746 | 7.6 | PV | 274-H3 | 2018-04-04 | 2018-04-09 | 3 |  | 3 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Carver | 2272658 | 2330 | 2980 | PV & Battery | 3-10-10 | 2018-03-27 | 2018-04-05 | 7 |  | 7 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2272821 | 1748 | 86.25 | PV | 4-92A-558 | 2018-03-29 | 2018-04-09 | 7 |  | 7 | 2018-04-23 |  | -30833 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Hopkinton | 2272822 | 1748 | 86.25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-23 |  | -30833 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273069 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2273079 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273089 | 1748 | 25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | New Bedford | 2273298 | 2745 | 1384 | PV |  | 2018-04-24 | 2018-04-25 | 1 | 0 | 1 | 2018-05-04 | 2018-10-03 | 108 | 0 | 108 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-07-10 | 2019-04-30 | 2020-02-28 | TBD | Expedited | 30 | 2020-02-27 |  | -31316 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Dartmouth | 2273508 | 2747 | 4999 | PV | 2-107-107 | 2018-04-04 | 2018-04-11 | 5 |  | 5 | 2018-04-26 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-22 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273509 | 2021 | 240 | PV | 269-1321H2 | 2018-02-20 | 2018-04-12 | 37 |  | 37 | 2018-04-26 | 2018-04-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-12-13 | [6 empty] | 0 |  | 0
NSTAR | Chelsea | 2273722 | 2150 | 153.2 | PV | 488-H6 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 |  | -30837 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | 2273723 | 2150 | 196.6 | PV | 488-H7 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 | 2018-11-20 | 147 |  | 147 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-27 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | Hopkinton | 2273879 | 1748 | 74 | PV | 65-H6 | 2018-03-30 | 2018-04-11 | 8 |  | 8 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273880 | 2021 | 610 | PV | 470-H1 | 2018-04-05 | 2018-04-12 | 5 |  | 5 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-03-12 | Online
NSTAR | Woburn | 2274149 | 1801 | 180 | PV | 375-H10 | 2016-10-26 | 2016-11-02 | 5 |  | 5 | 2016-12-06 |  | -30474 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2018-08-23 | Online
NSTAR | Framingham | 2274154 | 1702 | 198 | PV | 2411 | 2018-04-13 | 2018-04-17 | 2 |  | 2 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | [7 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Westport | 2274155 | 2790 | 4500 | PV | 2-532-532 | 2018-03-02 | 2018-04-15 | 30 |  | 30 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2274401 | 2743 | 4990 | PV & Battery | 2-241-241 | 2018-04-04 | 2018-04-16 | 8 |  | 8 | 2018-05-02 |  | -30840 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2274408 | 2770 | 1000 | PV | 3-703-703 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-02 |  | -30840 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | 2274649 | 2790 | 8300 | PV & Battery | 2-523-523 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Freetown | 2274652 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2274654 | 2360 | 3750 | PV & Battery | 3-89-89 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Vineyard Haven | 2275151 | 2568 | 5666.1 | PV & Battery | 4-75-75 | 2016-01-19 | 2016-02-08 | 14 |  | 14 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-05-31 |  |  | Standard |  |  |  | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Wayland | 2275155 | 1778 | 16.32 | PV | 342-H1 | 2018-04-17 | 2018-04-24 | 5 |  | 5 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-06 | 2018-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Dorchester | 2275333 | 2122 | 64 | PV | 466-1481H1 | 2018-04-12 | 2018-04-27 | 11 |  | 11 | 2018-05-07 |  | -30843 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Norfolk | 2275667 | 2056 | 15.2 | PV | 146-H3 | 2018-04-09 | 2018-04-24 | 11 |  | 11 | 2018-05-08 |  | -30844 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Somerville | 2276155 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30846 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2276157 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30846 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2276786 | 1701 | 15.8 | PV | 433-H8 | 2018-03-01 | 2018-04-27 | 41 |  | 41 | 2018-05-15 |  | -30849 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2276951 | 1773 | 250 | PV | 320-H1 | 2018-04-26 | 2018-05-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-31 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2277112 | 2790 | 8300 | PV & Battery | 2-522-522 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2277113 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2277114 | 2702 | 5000 | PV & Battery | 532 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2277378 | 2790 | 4875 | PV & Battery |  | 2018-05-17 | 2018-05-22 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-12-26 | 156 | 148 | 8 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-22 |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Acusnet | 2277380 | 2743 | 8980 | PV & Battery | 2-241-241 | 2018-04-11 | 2018-05-04 | 17 |  | 17 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2277381 | 2330 | 8980 | PV & Battery | 3-81-81 | 2018-04-06 | 2018-05-04 | 20 |  | 20 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2277865 | 2576 | 3300 | PV & Battery | 3-86-966 | 2018-04-25 | 2018-05-08 | 9 |  | 9 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-31 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Woburn | 2277867 | 1801 | 130 | PV | 258-1394-H1 | 2018-03-07 | 2018-05-10 | 46 |  | 46 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-09 | 2018-08-22 | [6 empty] | 0 |  | 0 |  |  | 2018-09-24 | Online
NSTAR | Wareham | 2278333 | 2576 | 201.6 | PV | 3-86-966 | 2018-05-01 | 2018-05-11 | 8 |  | 8 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-17 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2278335 | 2451 | 210 | Fuel Cell | 450-H2 | 2018-04-05 | 2018-05-15 | 28 |  | 28 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-14 | 2018-07-06 | [6 empty] | 0 |  | 0
NSTAR | Rochester | 2278508 | 2770 | 3345 | PV & Battery | 3-702-702 | 2018-05-14 | 2018-05-15 | 1 |  | 1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2279017 | 2575 | 22.8 | PV | 4-97-222 | 2018-05-03 | 2018-05-16 | 9 |  | 9 | 2018-05-30 |  | -30860 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Medway | 2279222 | 2053 | 27.72 | PV | 65-H5 | 2018-04-26 | 2018-05-16 | 14 |  | 14 | 2018-05-31 |  | -30861 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2279224 | 1776 | 249.8 | PV | 342-H2 | 2018-05-11 | 2018-05-16 | 3 |  | 3 | 2018-05-31 |  | -30861 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0
NSTAR | Medfield | 2279225 | 2052 | 264 | PV | 456-H2 | 2018-05-07 | 2018-05-11 | 4 |  | 4 | 2018-06-05 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-06-05 | Online
NSTAR | Wayland | 2279425 | 1778 | 21.9 | PV | 342-H1 | 2018-05-04 | 2018-05-16 | 8 |  | 8 | 2018-06-01 |  | -30862 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-07 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-03-11
NSTAR | Plympton | 2279426 | 2367 | 2500 | PV & Battery | 3-15-906 | 2018-04-25 | 2018-05-11 | 12 |  | 12 | 2018-06-01 | 2018-11-08 | 114 |  | 114 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 |  |  | Standard |  |  |  | 0 |  | 0 |  |  | 2023-02-06 | Online | [5 empty] | Private
NSTAR | Plympton | 2279636 | 2367 | 4998 | PV & Battery | 3-51-43J1 | 2018-05-04 | 2018-05-17 | 9 |  | 9 | 2018-06-04 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online
NSTAR | Barnstable | 2279638 | 2648 | 4998 | PV & Battery | 4-88-478 | 2018-05-16 | 2018-05-22 | 4 |  | 4 | 2018-06-04 | 2018-11-08 | 113 |  | 113 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 | [6 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | [5 empty] | Private
NSTAR | Cambridge | 2280401 | 2142 | 35 | CHP | 875-1399 | 2018-05-15 | 2018-05-22 | 5 |  | 5 | 2018-06-05 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-18 | [6 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Waltham | 2280855 | 2453 | 780 | PV & Battery | 386-1356 | 2018-05-03 | 2018-05-22 | 13 |  | 13 | 2018-06-07 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-10-01 | Online | [5 empty] | Private
NSTAR | Acton | 2280862 | 1720 | 1496 | PV & Battery | 416-H1 | 2018-03-01 | 2018-05-23 | 59 |  | 59 | 2018-06-07 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 2281067 | 2667 | 700 | PV | 4-96-677 | 2018-05-18 | 2018-05-23 | 3 |  | 3 | 2018-06-08 |  | -30867 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online
NSTAR | Westport | 2281069 | 2790 | 995 | Gas Turbine | 2-523-523 | 2018-05-16 | 2018-05-30 | 10 |  | 10 | 2018-06-08 |  | -30867 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2281481 | 2330 | 2000 | PV & Battery |  | 2018-06-11 | 2018-06-12 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 |  | -30870 | 135 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-20 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Carver | 2281482 | 2330 | 1000 | PV & Battery | 3-81-950 | 2018-05-18 | 2018-05-30 | 8 |  | 8 | 2018-06-12 |  | -30869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2282055 | 2539 | 466.6 | PV & Battery | 4-97-97 | 2018-05-29 | 2018-05-31 | 2 |  | 2 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Framingham | 2282056 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2282057 | 2138 | 28.8 | PV | 825-18 | 2018-05-29 | 2018-06-01 | 3 |  | 3 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | [7 empty] | 0 |  | 0 |  |  | 2019-02-04 | [6 empty] | Private
NSTAR | Barnstable | 2282058 | 2668 | 44.5 | PV | 4-87B-473 | 2018-05-15 | 2018-06-01 | 13 |  | 13 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-03 | 2018-08-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2282066 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256 | 2576 | 1497 | PV | TBD | 2018-06-15 |  | -30872 | 0 | 0 | 2018-09-22 | 2018-09-28 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-01-25 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Medfield | 2282637 | 2052 | 240 | PV | 456-H2 | 2018-05-30 | 2018-06-04 | 3 |  | 3 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | 2018-08-23 | [6 empty] | 0 |  | 0 |  |  | 2019-06-10 | Online
NSTAR | Ashland | 2282638 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282639 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | 3 |  | 3 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2282640 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282847 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2283031 | 2130 | 38 | PV | 350-H11 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-21 |  | -30876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 |  |  | 2019-01-22 | Online
NSTAR | Westport | 2283036 | 2790 | 2000 | PV | 2-523-523 | 2018-05-23 | 2018-06-13 | 15 |  | 15 | 2018-06-21 |  | -30876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2283230 | 2081 | 486.6 | PV | 146-H1 | 2018-06-05 | 2018-06-13 | 6 |  | 6 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Walpole | 2283639 | 2081 | 7499 | PV & Battery | 456-H1 | 2018-06-01 | 2018-06-13 | 8 |  | 8 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2283640 | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | 20 |  | 20 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Wareham | 2284066 | 2571 | 15.13 | PV | 3-84-963 | 2018-04-23 | 2018-06-13 | 37 |  | 37 | 2018-06-25 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-08-01 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Ashland | 2284070 | 1721 | 100 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | 3 |  | 3 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2284071 | 2563 | 133.2 | PV | 4-81B-443 | 2018-06-04 | 2018-06-14 | 8 |  | 8 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online | [5 empty] | Private
NSTAR | Acton | 2284261 | 1720 | - |  | TBD | 2018-06-28 |  | -30881 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-11-23 | TBD |  |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2284288 | 2740 | 250 | PV | 110-110 | 2018-05-29 | 2018-06-14 | 12 |  | 12 | 2018-06-29 |  | -30882 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2284555 | 1776 | 25 | PV | 342-H7 | 2018-05-31 | 2018-06-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Plymouth | 2284556 | 2360 | 250 | PV | 3-13-943 | 2018-06-11 | 2018-06-18 | 5 |  | 5 | 2018-07-02 |  | -30883 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2285552 | 2743 | 2000 | PV |  | 2018-07-05 | 2018-07-06 | 1 | 0 | 1 | 2018-07-06 |  | -30887 | 619 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2018-07-11 | Private
NSTAR | Mattapoisett | 2285553 | 2739 | 3560 | PV | 2-302-302 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2285554 | 2739 | 4980 | PV & Battery | 2-301-301 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Vineyard Haven | 2285555 | 2568 | 29.75 | PV | 4-97-222 | 2018-06-12 | 2018-06-19 | 5 |  | 5 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-07 | [7 empty] | 0 |  | 0 |  |  | 2018-11-08 | Online
NSTAR | Westport | 2285715 | 2790 | 2200 | PV & Battery | 33-H3 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2285721 | 2446 | 86 | PV | 33-H3 | 2018-06-12 | 2018-06-20 | 6 |  | 6 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2285991 | 2458 | 50 | PV | 292-H1 | 2018-05-31 | 2018-06-26 | 18 |  | 18 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-05 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2286172 | 1748 | 100 | PV | TBD | 2018-07-10 | 2018-07-11 | 1 | 0 | 1 | 2018-07-13 | 2018-07-18 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-19 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Medway | 2286612 | 2053 | 180 | PV | 65-H3 | 2018-07-12 |  | -30891 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2019-07-30 | Online | [5 empty] | Private
NSTAR | Bedford | 2286613 | 1730 | 52.2 | PV | 533-H7 | 2018-06-21 | 2018-06-27 | 4 |  | 4 | 2018-07-13 |  | -30892 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-10 | [7 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Hopkinton | 2286965 | 1748 | 100 | PV | 3-86-966 | 2018-05-23 | 2018-06-27 | 25 |  | 25 | 2018-07-11 | 2018-12-10 | 108 |  | 108 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-10-16 | Online | [5 empty] | Private
NSTAR | New Bedford | 2286967 | 2740 | 28 | PV | TBD | 2018-07-16 | 2018-07-24 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2286968 | 2576 | 2660 | PV & Battery | 3-81-81 | 2018-06-13 | 2018-06-29 | 12 |  | 12 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2286970 | 1701 | 21.68 | PV | 342-H4 | 2018-05-15 | 2018-06-29 | 33 |  | 33 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Wayland | 2286971 | 1778 | 208 | PV | 433-H6 | 2018-06-29 | 2018-06-29 | 0 |  | 0 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2287284 | 1701 | 249.8 | PV | 278-H1 | 2018-06-06 | 2018-06-29 | 17 |  | 17 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-09-21 | [6 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Boston | 2287285 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-02 | Online
NSTAR | Woburn | 2287543 | 1801 | 1310 | PV | 375-H1 | 2018-07-02 | 2018-07-03 | 1 |  | 1 | 2018-07-19 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Boston | 2287544 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Vineyard Haven | 2287709 | 2658 | 19.78 | PV | 4-91-228 | 2017-11-03 | 2017-11-03 | 0 |  | 0 | 2017-11-03 | 2018-07-20 | 185 |  | 185 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | [7 empty] | 0 |  | 0 |  |  | 2018-10-10 | Online | [5 empty] | Private
NSTAR | Plymouth | 2287723 | 2360 | 780 | PV | TBD | 2018-07-19 |  | -30896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-28 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2287856 | 2576 | 3992 | PV | TBD | 2018-07-20 |  | -30897 | 0 | 0 | 2018-09-22 | 2018-09-28 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-03-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2287931 | 2790 | 4950 | PV | 2-522-522 | 2018-06-29 | 2018-07-03 | 2 |  | 2 | 2018-07-23 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2288242 | 1801 | 942 | PV | 146-H1 | 2018-07-10 | 2018-07-10 | 0 |  | 0 | 2018-07-24 |  | -30899 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0
NSTAR | Tisbury | 2288244 | 2575 | 18 | PV | 4-97-222 | 2018-05-25 | 2018-07-10 | 32 |  | 32 | 2018-07-24 |  | -30899 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2018-11-16 | Online
NSTAR | Stoneham | 2288415 | 2180 | 17.17 | PV | 375-H8 | 2018-07-10 | 2018-07-24 | 10 |  | 10 | 2018-07-25 |  | -30900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-28 | [7 empty] | 0 |  | 0 |  |  | 2020-01-24 | Online
NSTAR | Hyannis | 2288599 | 2601 | 1500 | PV | 4-84B-524 | 2018-05-31 | 2018-07-11 | 29 |  | 29 | 2018-07-26 |  | -30901 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2288600 | 2360 | 780 | PV | 3-73-73 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-26 |  | -30901 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2288772 | 1803 | 17.49 | PV | 391-H6 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2288774 | 1720 | 999 | PV | 416-H4 | 2018-06-20 | 2018-07-12 | 16 |  | 16 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2020-09-30
NSTAR | Carver | 2288775 | 2330 | 5000 | PV & Battery | 3-83-83 | 2018-07-06 | 2018-07-12 | 4 |  | 4 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Norfolk | 2288776 | 2056 | 250 | PV | 146-H3 | 2018-06-07 | 2018-07-12 | 25 |  | 25 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-09-07 | Online
NSTAR | Holliston | 2288918 | 1746 | 66.6 | PV | 65-H9 | 2018-07-13 | 2018-07-16 | 1 |  | 1 | 2018-07-30 |  | -30903 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-06 | [6 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online
NSTAR | Holliston | 2289154 | 1746 | 17.28 | PV | 274-H3 | 2018-04-10 | 2018-07-17 | 70 |  | 70 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-05-11 | Online
NSTAR | Woburn | 2289155 | 1801 | 15.34 | PV | 211-H10 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Burlington | 2289156 | 1803 | 15.2 | PV | 391-H7 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-11-25 | Online
NSTAR | Wareham | 2289380 | 2571 | 996 | PV & Battery | 3-84-961 | 2018-06-27 | 2018-07-18 | 15 |  | 15 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2289611 | 2532 | 115.2 | PV | 4-86-402 | 2018-07-10 | 2018-07-18 | 6 |  | 6 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Brookline | 2289821 | 2445 | 17.28 | PV | 350-H3 | 2018-07-18 | 2018-07-19 | 1 |  | 1 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-21 | [7 empty] | 0 |  | 0 |  |  | 2019-03-19 | Online
NSTAR | Cambridge | 2289823 | 2138 | 510 | Fuel Cell | 819-1NC3 | 2018-06-12 | 2018-07-20 | 28 |  | 28 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 | 2018-12-20 |  | 2018-12-21
NSTAR | Westport | 2289828 | 2770 | 4498 | PV & Battery | 2-532-532 | 2018-04-30 | 2018-07-20 | 59 |  | 59 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290339 | 1720 | 300 | PV | 416-H4 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290347 | 1720 | 360 | PV | 416-H9 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2290688 | 1801 | 16.42 | PV | 211-H8 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2290690 | 2770 | 4000 | PV | 3-702-702 | 2018-07-18 | 2018-07-23 | 3 |  | 3 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2290691 | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | 4 |  | 4 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-06 | 2018-09-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online | [5 empty] | Private
NSTAR | Bedford | 2290881 | 1731 | 1645 | PV & Battery | 320-H6 | 2018-07-19 | 2018-07-24 | 3 |  | 3 | 2018-08-08 |  | -30910 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2290885 | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | 44 |  | 44 | 2018-08-08 |  | -30910 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Edgartown | 2291054 | 2539 | 19.6 | PV | 4-99-99 | 2018-05-31 | 2018-07-25 | 39 |  | 39 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0
NSTAR | Chelsea | 2291056 | 2150 | 33.3 | PV | 488-H7 | 2018-07-20 | 2018-07-25 | 3 |  | 3 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | 2018-10-03 | [6 empty] | 0 |  | 0 |  |  | 2019-11-07 | Online
NSTAR | Woburn | 2291058 | 1801 | 15.2 | PV | 391-H11 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2018-10-24 | [6 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Norfolk | 2291293 | 2056 | 996 | PV | 146-H3 | 2018-07-24 | 2018-07-26 | 2 |  | 2 | 2018-08-10 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2291296 | 1801 | 16.56 | PV | 375-H14 | 2018-05-22 | 2018-07-26 | 47 |  | 47 | 2018-08-10 | 2018-12-10 | 86 |  | 86 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2291297 | 2644 | 15.2 | PV | 4-81B-443 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-10 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Westport | 2291742 | 2790 | 500 | PV | 2-522-522 | 2018-07-23 | 2018-07-27 | 4 |  | 4 | 2018-08-14 |  | -30914 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2291743 | 2124 | 86 | PV | 311-12 | 2018-07-27 | 2018-08-02 | 4 |  | 4 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-06-19 | Online | [5 empty] | Private
NSTAR | New Bedford | 2291744 | 2740 | 36 | PV | 2-69-69 | 2018-06-25 | 2018-08-03 | 29 |  | 29 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online | [5 empty] | Private
NSTAR | Harwich | 2291972 | 2645 | 30 | PV | 4-92B-92B | 2018-08-02 | 2018-08-07 | 3 |  | 3 | 2018-08-15 | 2018-11-06 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Bellingham | 2292179 | 2019 | 6310 | PV & Battery | 65-H4 | 2018-08-03 | 2018-08-07 | 2 |  | 2 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2021-11-30 | Online
NSTAR | Carver | 2292181 | 2330 | 2468 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2292182 | 2655 | 23.04 | PV | 4-80A-892 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Rochester | 2292307 | 2770 | 16.7 | PV | 3-702-702 | 2018-08-08 | 2018-08-15 | 5 |  | 5 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-21 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online | [5 empty] | Private
NSTAR | Newton | 2292310 | 2460 | 90 | PV | 467-H3 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2293955 | 1720 | 17.56 | PV | 416-H4 | 2018-07-20 | 2018-08-10 | 15 |  | 15 | 2018-08-29 |  | -30925 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-23 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  | 2019-04-05 | Online | [5 empty] | Private
NSTAR | Allston | 2294148 | 2134 | 70 | PV | 548-92H3 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-31 | 2018-11-16 | [6 empty] | 0 |  | 0
NSTAR | Plymouth | 2294151 | 2362 | 133.2 | PV | 3-14-911 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-11-05 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 | 2018-12-05 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-08-18 | Online | [5 empty] | Private
NSTAR | Barnstable | 2294153 | 1801 | 22.8 | PV | 4-81B-443 | 2018-07-24 | 2018-08-15 | 16 |  | 16 | 2018-08-30 | 2018-11-02 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-12-17 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-06-04 | Online | [5 empty] | Private
NSTAR | Brewster | 2294155 | 2631 | 15.2 | PV | 4-89A-553 | 2018-08-02 | 2018-08-15 | 9 |  | 9 | 2018-08-30 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-04 | Online
NSTAR | Waltham | 2294156 | 2451 | 496 | PV | 320-H3 | 2018-06-05 | 2018-08-15 | 51 |  | 51 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-05-21 | [6 empty] | Private
NSTAR | Mattapoisett | 2295025 | 2739 | 960 | PV | 2-302-302 | 2018-08-14 | 2018-08-17 | 3 |  | 3 | 2018-09-05 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online
NSTAR | Natick | 2295244 | 1760 | 180 | PV | 433-H12 | 2018-08-09 | 2018-08-17 | 6 |  | 6 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2295246 | 2740 | 86.4 | PV | 2-49-49 | 2018-08-14 | 2018-08-20 | 4 |  | 4 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Boston | 2295249 | 2163 | 46 | PV | STATION890 | 2018-07-26 | 2018-08-20 | 17 |  | 17 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online | [5 empty] | Private
NSTAR | Cambridge | 2295384 | 2138 | 80.5 | PV | 821-05 | 2018-07-31 | 2018-08-20 | 14 |  | 14 | 2018-09-07 | 2018-11-09 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-12-26
NSTAR | New Bedford | 2295385 | 2744 | 233.1 | PV | 2-41-41 | 2018-08-06 | 2018-09-04 | 21 |  | 21 | 2018-09-07 | 2018-11-20 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-11-27
NSTAR | Wareham | 2295386 | 2738 | 2925 | PV | 3-85-85 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-07 |  | -30932 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2295579 | 2740 | 150 | PV | 2-70-70 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-11 | 2018-10-24 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | 2018-10-30 | [6 empty] | 0 |  | 0 |  |  | 2019-12-19 | Online | [5 empty] | Private
NSTAR | Oak Bluffs | 2295584 | 2557 | 280 | PV & Battery | 4-75-75 | 2018-08-20 | 2018-08-22 | 2 |  | 2 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Rochester | 2295586 | 2738 | 996 | PV | 3-85-85 | 2018-08-20 | 2018-08-23 | 3 |  | 3 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2295850 | 1721 | 22.95 | PV | 455-H3 | 2018-08-23 | 2018-08-23 | 0 |  | 0 | 2018-09-12 | 2018-11-05 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2295852 | 2576 | 3000 | PV & Battery | 3-81-81 | 2018-08-16 | 2018-08-23 | 5 |  | 5 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2295857 | 2453 | 73.3 | PV | 33-H2 | 2018-08-08 | 2018-08-23 | 11 |  | 11 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-29 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2296072 | 2364 | 3510 | PV | 3/14-14 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-12 |  | -30935 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-24 | Online
NSTAR | Carver | 2296366 | 2330 | 4650 | PV |  | 2018-09-12 | 2018-09-18 | 4 | 0 | 4 | 2018-09-18 |  | -30939 | 569 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2018-09-20 | Private
NSTAR | Westport | 2296371 | 2790 | 2000 | PV | 2-532-532 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2296372 | 2770 | 4998 | PV & Battery | 3-703-703 | 2018-08-14 | 2018-08-24 | 8 |  | 8 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2296373 | 2571 | 4890 | PV | 3-82-82 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Dartmouth | 2296559 | 2747 | 4990 | PV | 2-103-103 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-03 | Online
NSTAR | Framingham | 2296563 | 1702 | 15.2 | PV | 274-H1 | 2018-08-02 | 2018-08-29 | 19 |  | 19 | 2018-09-18 | 2018-11-15 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-11-16 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sandwich | 2296564 | 2563 | 4890 | PV & Battery | 4-81B-443 | 2018-07-24 | 2018-08-29 | 26 |  | 26 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2296607 | 1721 | 4450 | PV |  | 2018-09-14 |  | -30937 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-31 | TBD |  | 30 | 2019-10-30 | 2019-10-30 | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Wareham | 2296718 | 2538 | 199.8 | PV | 3-81-81 | 2018-08-23 | 2018-08-29 | 4 |  | 4 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2296720 | 2330 | 3500 | PV | 3-10-10 | 2018-08-27 | 2018-08-29 | 2 |  | 2 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2296721 | 2120 | 27 | PV | 5203 | 2018-06-25 | 2018-08-30 | 48 |  | 48 | 2018-09-18 | 2018-11-02 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-04-09 | Online | [5 empty] | Private
NSTAR | Rochester | 2296978 | 2770 | - |  | TBD | 2018-09-17 |  | -30938 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-04-26 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Needham | 2297073 | 2494 | 99.9 | PV | 148-H4 | 2018-08-30 | 2018-08-31 | 1 |  | 1 | 2018-09-19 | 2018-11-14 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-15 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-12-31 | Online | [5 empty] | Private
NSTAR | Westport | 2297080 | 2790 | 1000 | PV | 2-532-532 | 2018-08-20 | 2018-08-31 | 9 |  | 9 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297083 | 2576 | 4075 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2297267 | 2576 | 500 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297500 | 2571 | 4890 | PV | 8-83-83 | 2018-08-09 | 2018-09-19 | 29 |  | 29 | 2018-09-20 |  | -30941 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2297501 | 2639 | 40 | PV | 4-92B-583 | 2018-08-03 | 2018-08-18 | 10 |  | 10 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-05
NSTAR | Wareham | 2297503 | 2576 | 250 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2297504 | 2210 | 75 | PV | 323-06 | 2018-08-09 | 2018-09-05 | 19 |  | 19 | 2018-09-20 | 2018-11-02 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-11-07 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-12-27 | [6 empty] | Private
NSTAR | Freetown | 2297681 | 2717 | 4500 | PV & Battery | 2-108-108 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-21 |  | -30942 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2297682 | 2738 | 3500 | PV & Battery | 3-85-85 | 2018-08-14 | 2018-09-06 | 17 |  | 17 | 2018-09-21 |  | -30942 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298087 | 1754 | 462 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298090 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 2298091 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298092 | 1754 | 1254 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2298285 | 1720 | 490 | PV | 416-H4 | 2018-07-10 | 2018-09-06 | 42 |  | 42 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2298289 | 1730 | 72 | PV | 533-H5 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2298290 | 1801 | 924 | PV | 258-1394-H1 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Woburn | 2298553 | 1801 | 490 | PV | 258-1394H8 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 |  | -30946 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online
NSTAR | Burlington | 2298565 | 1803 | 990 | PV | 391-H16 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | Expedited |  |  |  | 0 |  | 0
NSTAR | Burlington | 2298567 | 1803 | 990 | PV | 391-H9 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Barnstable | 2298568 | 2648 | 4990 | PV | 4-88-453 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-27 |  | -30946 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2298768 | 2770 | 1782 | PV | 3-702-702 | 2018-08-28 | 2018-09-07 | 8 |  | 8 | 2018-09-28 |  | -30947 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2298783 | 1746 | 31 | PV | 130-H1 | 2018-08-30 | 2018-09-07 | 6 |  | 6 | 2018-09-28 | 2018-12-06 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-03-06
NSTAR | New Bedford | 2298790 | 2745 | 1220 | PV | 2-107-107 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-28 |  | -30947 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2298981 | 2747 | 185 | PV & Battery | 2-525-525 | 2018-08-31 | 2018-09-10 | 6 |  | 6 | 2018-10-01 |  | -30948 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2299343 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-06 | 2018-09-11 | 3 |  | 3 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2299346 | 2330 | 8300 | PV & Battery | 3-51-901 | 2018-09-07 | 2018-09-11 | 2 |  | 2 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2299348 | 2360 | 924 | PV | 3-12-41J1 | 2018-08-17 | 2018-09-12 | 18 |  | 18 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-12-21 | Online
NSTAR | Rochester | 2299350 | 2770 | 1250 | PV & Battery | 5-702-702 | 2018-09-06 | 2018-09-12 | 4 |  | 4 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2299602 | 2659 | 78.2 | PV | 4-95A-95A | 2018-09-12 | 2018-09-19 | 5 |  | 5 | 2018-10-03 |  | -30950 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Acusnet | 2299606 | 2743 | 4950 | PV & Battery | 2-241-241 | 2018-09-07 | 2018-09-20 | 9 |  | 9 | 2018-10-03 |  | -30950 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300058 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30951 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2300060 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30951 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300709 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2300908 | 2576 | 4180 | PV & Battery | 3-81-81 | 2018-09-04 | 2018-09-21 | 13 |  | 13 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Woburn | 2300919 | 1801 | 15.2 | PV | 211-H13 | 2018-09-07 | 2018-09-25 | 12 |  | 12 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  | 2020-03-24 | Online | [5 empty] | Private
NSTAR | Watertown | 2300922 | 2472 | 475.2 | PV | 467-H4 | 2018-09-18 | 2018-09-25 | 5 |  | 5 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | [7 empty] | 0 |  | 0 |  |  | 2019-11-15 | Online | [5 empty] | Private
NSTAR | Sandwich | 2301106 | 2563 | 133.2 | PV | 4-81B-443 | 2018-09-19 | 2018-09-26 | 5 |  | 5 | 2018-10-12 |  | -30957 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cambridge | 2301108 | 2142 | 63.3 | PV | 831-1336XY | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-12 | 2018-11-14 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-28 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-12-22 | Online | [5 empty] | Private
NSTAR | East Freetown | 2301315 | 2717 | 220 | PV | 604 | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-16 |  | -30959 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online | [5 empty] | Private
NSTAR | Acusnet | 2301808 | 2743 | 5000 | PV |  | 2018-10-16 | 2018-10-17 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2019-12-18 | 304 | 41 | 263 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-06-13 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2021-09-23 | Online | [5 empty] | Private
NSTAR | Acusnet | 2301817 | 2743 | 5000 | PV | 2-241-241 | 2018-09-26 | 2018-09-28 | 2 |  | 2 | 2018-10-17 |  | -30960 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Chelsea | 2302133 | 2150 | 66.6 | PV | 488-H2 | 2018-09-26 | 2018-10-01 | 3 |  | 3 | 2018-10-18 |  | -30961 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2302146 | 2770 | 1000 | PV & Battery | 3-702-702 | 2018-09-20 | 2018-09-21 | 1 |  | 1 | 2018-10-18 |  | -30961 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Plymouth | 2302150 | 2360 | 133.2 | PV | 3-13-943 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-18 | 2018-11-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2302380 | 2571 | 100 | PV | 8-83-83 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-19 | 2018-11-20 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-20 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Milton | 2302387 | 2186 | 38 | PV | 362-03 | 2018-09-26 | 2018-10-02 | 4 |  | 4 | 2018-10-19 |  | -30962 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-04 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Canton | 2302390 | 2021 | 3992 | PV | 269-1321H | 2018-09-28 | 2018-10-03 | 3 |  | 3 | 2018-10-19 |  | -30962 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online | [5 empty] | Private
NSTAR | Barnstable | 2302867 | 2632 | 66.6 | PV | 4-88-88 | 2018-10-05 | 2018-10-05 | 0 |  | 0 | 2018-10-23 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Plymouth | 2303219 | 2360 | 199.8 | PV | 3-10-10 | 2018-10-01 | 2018-10-05 | 4 |  | 4 | 2018-10-25 |  | -30966 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2303220 | 2746 | 86.4 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-21 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2021-05-10 | Online | [5 empty] | Private
NSTAR | New Bedford | 2303221 | 2746 | 57.6 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-29 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-30 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2021-08-23 | Online | [5 empty] | Public
NSTAR | Natick | 2303427 | 1760 | 100 | PV & Battery | 240-H3 | 2018-10-11 | 2018-10-18 | 5 |  | 5 |  | 2018-11-26 | 30987 |  | 30987 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-27 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-04-22 | Online | [5 empty] | Private
NSTAR | Plymouth | 2303429 | 2360 | 144 | PV | 3-13-943 | 2018-10-11 | 2018-10-18 | 5 |  | 5 | 2018-10-31 | 2018-11-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-04-21 | Online | [5 empty] | Private
NSTAR | Vineyard Haven | 2303430 | 2568 | 23.36 | PV | 3-24B-95 | 2018-10-05 | 2018-10-11 | 4 |  | 4 | 2018-10-31 | 2018-12-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hyannis | 2303431 | 2601 | 40 | PV | 4-80B-514 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0 |  |  | 2019-09-06 | Online | [5 empty] | Private
NSTAR | Natick | 2303432 | 1760 | 366.6 | PV | 433-H9 | 2018-10-05 | 2018-10-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Falmouth | 2303631 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2018-10-08 | 2018-10-12 | 4 |  | 4 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-04 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Woburn | 2304049 | 1801 | 15.2 | PV | 375-H14 | 2018-10-09 | 2018-10-12 | 3 |  | 3 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Canton | 2304052 | 2021 | 496.2 | PV | 269-1321H | 2018-10-12 | 2018-10-12 | 0 |  | 0 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2020-12-08 | Online | [5 empty] | Private
NSTAR | Plymouth | 2304254 | 2360 | 366.6 | PV | 3-13-943 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Canton | 2304257 | 2021 | 350 | PV | 470-h7 | 2018-10-10 | 2018-10-18 | 6 |  | 6 | 2018-11-01 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2304259 | 2790 | 5000 | PV & Battery | 2-523-523 | 2018-10-02 | 2018-10-18 | 12 |  | 12 | 2018-11-01 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acusnet | 2304486 | 2743 | 3060 | PV & Battery | 2-241-238 | 2018-10-15 | 2018-10-18 | 3 |  | 3 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Newton | 2304489 | 2468 | 75.6 | PV | 292-H12 | 2018-10-18 | 2018-11-02 | 11 |  | 11 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-19 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05 | Online | [5 empty] | Private
NSTAR | Framingham | 2304490 | 1701 | 43.2 | PV | 433-H2 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online | [5 empty] | Private
NSTAR | New Bedford | 2305081 | 2740 | 199.4 | PV | 2-38-38 | 2018-10-18 | 2018-10-19 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | [5 empty] | Public
NSTAR | Marion | 2305082 | 2738 | 20.88 | PV | 3-85-969 | 2018-10-19 | 2018-10-19 | 0 |  | 0 | 2018-11-05 | 2018-11-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-29 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2018-01-09 | Online | [5 empty] | Private
NSTAR | New Bedford | 2305084 | 2746 | 428 | PV | 2-80-401 | 2018-10-18 | 2018-10-19 | 1 |  | 1 | 2018-11-05 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | [5 empty] | Public
NSTAR | Winchester | 2305372 | 2890 | 50 | PV | 211-H10 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online | [5 empty] | Private
NSTAR | Winchester | 2305374 | 1890 | 60 | PV | 211-H1 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online | [5 empty] | Private
NSTAR | Roslindale | 2305544 | 2131 | 336 | PV & Battery | 496-H4 | 2018-10-24 | 2018-11-07 | 10 |  | 10 | 2018-11-07 | 2018-11-14 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-14 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-12-04 | Online | [5 empty] | Private
NSTAR | Jamaica Plain | 2305731 | 2130 | 60 | PV | 284-02 | 2018-10-19 | 2018-11-08 | 14 |  | 14 | 2018-11-08 | 2018-11-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-12-14 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-02-26 | Online | [5 empty] | Private
NSTAR | Burlington | 2305732 | 1803 | 400 | PV | 391-H5 | 2018-11-06 | 2018-11-08 | 2 |  | 2 | 2018-11-08 |  | -30976 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Burlington | 2305734 | 1803 | 800 | PV | 391-H5 | 2018-10-25 | 2018-11-08 | 10 |  | 10 | 2018-11-08 |  | -30976 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Dartmouth | 2305846 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -30977 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Dartmouth | 2305925 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -30977 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online | [5 empty] | Private
NSTAR | Holliston | 2306412 | 1746 | 490 | PV | 274-H3 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2306416 | 2330 | 1625 | PV | 3-10-929 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Rochester | 2306598 | 2770 | 1750 | PV | 3-703-703 | 2018-10-31 | 2018-11-15 | 11 |  | 11 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Wareham | 2306600 | 2571 | 4999 | PV & Battery | 3-82-82 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Norfolk | 2306602 | 2056 | 15.2 | PV | 146-H9 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Lincoln | 2306816 | 1773 | 86.4 | PV | 320-H1 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-23 | Online | [5 empty] | Private
NSTAR | Edgartown | 2306817 | 2539 | 22.4 | PV | 4-99-99 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 | 2018-11-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2306818 | 2571 | 240 | PV | 3-85-955 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 | [9 empty] | Public
NSTAR | Framingham | 2307344 | 1702 | 57.6 | PV | 24-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -30984 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-12-13 | Online | [5 empty] | Private
NSTAR | Framingham | 2307346 | 1701 | 81 | PV | 278-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -30984 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Chestnut Hill | 2307511 | 2467 | 496.2 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Chestnut Hill | 2307513 | 2467 | 499.8 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Rochester | 2307638 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Westport | 2307639 | 2790 | 1500 | PV | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Somerville | 2307640 | 2145 | 250 | PV & Battery | 250-H4XY | 2018-11-08 | 2018-11-23 | 11 |  | 11 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Westport | 2307641 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Woburn | 2307642 | 1801 | 208.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online | [5 empty] | Private
NSTAR | Woburn | 2308000 | 1801 | 333.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Westport | 2308001 | 2790 | 37.8 | PV | 2-532-532 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | New Bedford | 2308002 | 2740 | 43.2 | PV | 2-24-182 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 | 2018-12-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-04 | 2018-12-21 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-12-20 | Online | [5 empty] | Private
NSTAR | West Tisbury | 2308167 | 2575 | 22.33 | PV & Battery | 3-24B-95 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 | 2018-12-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-07 | 2018-12-07 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-09-06 | Online | [5 empty] | Private
NSTAR | Boston | 2308171 | 2114 | 50 | CHP | 274-H3 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -30990 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online | [5 empty] | Private
NSTAR | Dennis | 2308172 | 2638 | 17.4 | PV | 4-92B-92B | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -30990 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2019-04-30 | Online | [5 empty] | Private
NSTAR | Boston | 2308328 | 2115 | 1600 | PV & Battery | 528-169H | 2018-11-27 |  | -30989 |  | 0 | 2018-12-26 |  | -31010 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Plymouth | 2308333 | 2360 | 500 | PV | 3-13-943 | 2018-11-13 | 2018-11-29 | 12 |  | 12 | 2018-11-29 |  | -30991 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Hopkinton | 2308334 | 1748 | 2000 | PV & Battery | 126-H4 | 2018-11-14 | 2018-11-29 | 11 |  | 11 | 2018-11-29 |  | -30991 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dartmouth | 2308512 | 2748 | 17.4 | PV | 2-528-528 | 2018-11-14 | 2018-11-30 | 12 |  | 12 | 2018-11-30 | 2018-12-11 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 | 2018-12-12 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2019-04-30 | Online | [5 empty] | Private
NSTAR | Carver | 2308513 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-11-15 | 2018-11-30 | 11 |  | 11 | 2018-11-30 |  | -30992 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Somerville | 2308642 | 2145 | 600 | Fuel Cell | 250-H4XY | 2018-11-15 | 2018-12-03 | 12 |  | 12 | 2018-12-03 |  | -30993 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online | [5 empty] | Private
NSTAR | North Dartmouth | 2308643 | 2747 | 18.15 | PV | 2-532-532 | 2018-11-16 | 2018-12-03 | 11 |  | 11 | 2018-12-03 | 2018-12-06 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 | 2018-12-11 |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-12-24 | Online | [5 empty] | Private
NSTAR | Kingston | 2311123 | 2364 | 1531.8 | PV | 3/14-14 | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Marshfield | 2311127 | 2050 | 2112 | PV | 3-24A-24A | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online | [5 empty] | Private
NSTAR | Framingham | 2311128 | 1702 | 492 | PV | 455-H2 | 2018-12-05 | 2018-12-05 | 0 |  | 0 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Canton | 2311297 | 2021 | 225 | PV | 470-H7 | 2018-11-14 | 2018-11-21 | 5 |  | 5 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Plymouth | 2311298 | 2360 | 233.1 | PV | 3-13-13 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2311303 | 2535 | 83.52 | PV | 4-91-126 | 2018-11-21 | 2018-12-06 | 11 |  | 11 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | 2018-12-27 | [6 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Woburn | 2311476 | 1801 | 249.8 | PV | 211-H2 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-08 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online | [5 empty] | Private
NSTAR | Plympton | 2311480 | 2367 | 2000 | PV & Battery | 3-51-901 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Natick | 2311483 | 1760 | 180 | PV | 433-H10 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online | [5 empty] | Private
NSTAR | Rochester | 2311484 | 2770 | 19 | PV | 3-703-703 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 | 2018-12-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Cotuit | 2311617 | 2635 | 17.93 | PV & Battery | 4-88-880 | 2018-11-26 | 2018-12-10 | 10 |  | 10 | 2018-12-10 |  | -30998 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-15 | [7 empty] | 0 |  | 0 |  |  | 2019-10-21 | Online | [5 empty] | Private
NSTAR | Lexington | 2311846 | 2421 | 1149 | PV & Battery | 533-H1 | 2018-11-27 | 2018-12-11 | 10 |  | 10 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2311847 | 2050 | 115.44 | PV | 3-24A-24A | 2018-11-28 | 2018-12-11 | 9 |  | 9 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Oak Bluffs | 2311848 | 2557 | 249.8 | PV | 4-75-75 | 2018-11-29 | 2018-12-11 | 8 |  | 8 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2312220 | 2459 | 200 | PV | 292-H3 | 2018-11-28 | 2018-11-29 | 1 |  | 1 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0
NSTAR | Stoneham | 2312221 | 2180 | 15.98 | PV | 375-H8 | 2018-11-07 | 2018-11-29 | 16 |  | 16 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-01 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2312223 | 2067 | 660 | PV & Battery | 146-H7 | 2018-10-25 | 2018-12-03 | 27 |  | 27 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  |  |  | 2020-09-30
NSTAR | Roxbury | 2312379 | 2119 | 199.8 | PV | 106-H4 | 2018-12-03 | 2018-12-03 | 0 |  | 0 | 2018-12-14 |  | -31002 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Bourne | 2312381 | 2532 | 999 | PV | 3-88-88 | 2018-11-21 | 2018-12-03 | 8 |  | 8 | 2018-12-14 |  | -31002 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Falmouth | 2313194 | 2540 | 24.84 | PV | 4-98A-98A | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0 |  |  | 2019-05-02 | Online
NSTAR | Roxbury | 2313198 | 2119 | 36 | PV | 106-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Westport | 2313433 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-29 | 2018-12-04 | 3 |  | 3 | 2018-12-19 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2313435 | 2655 | 4998 | PV & Battery | 4-96-674 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-19 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2313788 | 2770 | 496.6 | PV | 3-85-85 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Boston | 2313793 | 2128 | 250 | PV | 488-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Canton | 2313802 | 2021 | 100 | PV | 269-1320H1 | 2018-12-04 | 2018-12-06 | 2 |  | 2 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Hyde Park | 2313809 | 2136 | 15.2 | PV | 441-06 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2313811 | 1749 | 31.7 | PV | 386-1356 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2313933 | 2575 | 92.4 | PV | 4-97-97 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-24 |  | -31008 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0
NSTAR | East Boston | 2314366 | 2128 | 79.2 | PV | 592-72XY |  | 2018-12-07 | 30996 |  | 30996 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cotuit | 2314367 | 2635 | 15.2 | PV | 4-88-880 | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2314368 | 2645 | 20 | PV | 4-92B-92B | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-05-21 | Online
NSTAR | Carver | 2314369 | 2330 | 3500 | PV | 3-81-950 | 2018-11-27 | 2018-12-10 | 9 |  | 9 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2314370 | 2451 | 40 | PV | 282-H8 | 2018-12-11 |  | -30999 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2314371 | 2745 | 100 | PV | 2-137-139 | 2018-12-12 | 2018-12-12 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-08
NSTAR | East Freetown | 2314499 | 2717 | 3300 | PV & Battery | 2-102-604 | 2018-10-19 | 2018-12-14 | 40 |  | 40 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Stoneham | 2314500 | 2180 | 72 | PV | 375-H7 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2019-08-07 | Online
NSTAR | Stoneham | 2314501 | 2180 | 150 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2316352 | 2180 | 50 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-03 | [7 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Plympton | 2316354 | 2364 | 4999 | PV & Battery | 3-15-15 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2316355 | 1748 | 6310 | PV & Battery | 533-H7 | 2018-12-20 | 2018-12-20 | 0 |  | 0 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2316959 | 2601 | 500 | PV | 4-63-63 | 2018-11-21 | 2018-12-12 | 15 |  | 15 | 2019-01-04 |  | -31017 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2316966 | 2536 | 4500 | PV | 4-98A-98A | 2018-12-11 | 2018-12-17 | 4 |  | 4 | 2019-01-04 |  | -31017 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online
NSTAR | East Falmouth | 2317177 | 2536 | 4000 | PV | 4-98A-98A | 2018-12-12 | 2018-12-17 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-14 | Online
NSTAR | Sudbury | 2317182 | 1766 | 499.99 | PV | 342-H2 | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31018 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2317183 | 2540 | 1000 | PV | 4-98A-98A | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31018 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2319218 | 2717 | 8360 | PV & Battery | 2-605-605 | 2018-12-07 | 2018-12-18 | 7 |  | 7 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319219 | 2460 | 206 | PV | 17-H2 | 2018-12-17 | 2018-12-20 | 3 |  | 3 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319220 | 2460 | 66.66 | PV | 467-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2319393 | 2360 | 999 | PV & Battery | 3-73-73 | 2018-12-18 | 2018-12-18 | 0 |  | 0 | 2018-01-09 |  | -30759 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2319563 | 2460 | 233 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2319566 | 2460 | 66.66 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Holliston | 2319567 | 1746 | 1640 | PV | 274-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Vineyard Haven | 2319568 | 2568 | 43.2 | PV | 4-75-75 | 2018-12-13 | 2018-12-20 | 5 |  | 5 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-04 | [7 empty] | 0 |  | 0 |  |  | 2019-10-29
NSTAR | Marshfield | 2319796 | 2050 | 15.2 | PV | 3-25-42J2 | 2018-12-11 | 2018-12-21 | 8 |  | 8 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online
NSTAR | Waltham | 2319797 | 2451 | 106.6 | PV | 3-25-42J2 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Westport | 2319812 | 2790 | 22.1 | PV | 2-532-532 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Kingston | 2319914 | 2364 | 406.5 | PV | 3-26-902 | 2018-12-19 | 2019-01-02 | 10 |  | 10 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-09 | Online
NSTAR | Newton | 2320273 | 2468 | 133.3 | PV | 17-H2 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-01-14 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-05-04 | Online
NSTAR | Dover | 2320293 | 2030 | 19.8 | PV | 456-H1 | 2018-12-26 | 2019-01-07 | 8 |  | 8 | 2019-01-14 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-05 | [7 empty] | 0 |  | 0 |  |  | 2019-07-22 | Online
NSTAR | Wareham | 2320442 | 2571 | 5000 | PV | 8-83-83 | 2018-12-12 | 2018-12-21 | 7 |  | 7 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2320444 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-12-16 | 2018-12-19 | 3 |  | 3 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2320445 | 2021 | 3240 | PV | 269-1320H1 | 2018-12-19 | 2018-12-26 | 5 |  | 5 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2320446 | 2770 | 2900 | PV | 3-703-703 | 2018-12-21 | 2018-12-26 | 3 |  | 3 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2320561 | 2563 | 500 | PV | 4-87A-471 | 2019-01-02 | 2019-01-02 | 0 |  | 0 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2320621 | 2702 | 4875 | PV | 2-605-605 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2320623 | 2770 | 4890 | PV & Battery | 3-703-703 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2320809 | 2360 | 4999 | PV & Battery | 3-73-73 | 2019-01-08 | 2019-01-08 | 0 |  | 0 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2320829 | 2026 | 399.6 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online
NSTAR | Acusnet | 2320833 | 2743 | 21.34 | PV & Battery | 2-241-241 | 2018-04-06 | 2018-12-26 | 188 |  | 188 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-01 | Online
NSTAR | West Yarmouth | 2320835 | 2673 | 498 | PV | 4-92A-534 | 2018-12-20 | 2018-12-26 | 4 |  | 4 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 2321103 | 1773 | 20 | PV & Battery | 320-H6 | 2018-12-20 | 2019-01-08 | 13 |  | 13 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 | [7 empty] | 0 |  | 0 |  |  | 2019-09-03 | Online
NSTAR | Watertown | 2321147 | 2472 | 100 | PV | 467-H4 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Dedham | 2321149 | 2026 | 199.8 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-11-07 | Online
NSTAR | Dedham | 2321151 | 2026 | 119 | PV | 20-H6 | 2018-12-19 | 2018-12-28 | 7 |  | 7 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2321334 | 1760 | 32.4 | PV | TBD | 2019-01-18 |  | -31027 | 0 | 0 | 2019-01-22 | 2019-03-05 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-26 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2321677 | 2330 | 6500 | PV | 3-10-930 | 2019-01-07 | 2019-01-08 | 1 |  | 1 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2321814 | 2021 | 132 | PV | 269-1320H1 | 2018-12-18 | 2019-01-09 | 16 |  | 16 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-29 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2321912 | 1760 | 72 | PV | 433-H10 | 2019-01-15 | 2019-01-15 | 0 |  | 0 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Wareham | 2322036 | 2571 | 2250 | PV | 8-83-83 | 2019-01-04 | 2019-01-07 | 1 |  | 1 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2322113 | 2532 | 1390 | PV | 4-86-402 | 2019-01-07 | 2019-01-16 | 7 |  | 7 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2322158 | 1721 | 346.2 | PV | 455-H3 | 2018-12-19 | 2019-01-16 | 20 |  | 20 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Woburn | 2322181 | 1801 | 15.2 | PV | 375-H12 | 2018-12-28 | 2019-01-16 | 13 |  | 13 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | Watertown | 2322219 | 2472 | 249.9 | PV | 467-H4 | 2019-01-15 | 2019-01-17 | 2 |  | 2 | 2019-01-28 |  | -31033 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2322394 | 2026 | 499.5 | PV | 20-H5 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-28 |  | -31033 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online
NSTAR | Mattapoisett | 2322525 | 2739 | 115.2 | PV | 2-302-302 | 2019-01-15 | 2019-01-17 | 2 |  | 2 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2020-01-10 | Online
NSTAR | North Dartmouth | 2322528 | 2747 | 720 | PV | 2-541-541 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2322577 | 2136 | 60 | PV | 344-08 | 2019-01-18 | 2019-01-18 | 0 |  | 0 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Falmouth | 2322598 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2019-01-17 |  | -31026 |  | 0 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2322632 | 1720 | 242 | PV | 416-H4 | 2019-01-18 |  | -31027 |  | 0 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2322689 | 2134 | 57.6 | PV | 456-H3 | 2019-01-04 | 2019-01-09 | 3 |  | 3 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Needham | 2322796 | 2492 | 28.8 | PV | 148-H1 | 2019-01-18 | 2019-01-25 | 5 |  | 5 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Barnstable | 2322818 | 2668 | 17.92 | PV | 4-87B-473 | 2019-01-30 | 2019-01-30 | 0 | 0 | 0 | 2019-02-01 | 2019-02-26 | 17 | 0 | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-02-26 | 2019-03-01 | 2019-09-05 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2019-07-16 | Online | [5 empty] | Private
NSTAR | Dorchester | 2322890 | 2122 | 260 | PV & Battery | 483-H7 | 2019-01-02 |  | -31015 |  | 0 | 2019-01-31 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | South Dennis | 2323237 | 2660 | 4951 | PV | tbd | 2019-01-24 | 2019-01-28 | 2 |  | 2 | 2019-01-31 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323317 | 2360 | 26.55 | PV | 3-13-943 | 2019-01-23 |  | -31030 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2323381 | 2459 | 1000 | PV | 282-H8 | 2019-01-24 |  | -31031 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2323400 | 2451 | 480 | PV | 450-H7 | 2019-01-25 |  | -31032 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online
NSTAR | Dorchester | 2323443 | 2124 | 15.2 | PV | 483-H2 | 2019-01-07 | 2019-01-14 | 5 |  | 5 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-24 | Online
NSTAR | Sandwich | 2323654 | 2563 | 2660 | PV | 4-81B-443 | 2019-01-23 | 2019-01-29 | 4 |  | 4 | 2019-02-04 |  | -31038 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2323699 | 2790 | 72 | PV | 2-532-532 | 2019-01-22 | 2019-01-31 | 7 |  | 7 | 2019-02-05 |  | -31039 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323714 | 2360 | 700 | PV | 3-71-937 | 2019-01-25 | 2019-01-29 | 2 |  | 2 | 2019-02-06 |  | -31040 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-05-21 | Online
NSTAR | Ashland | 2323862 | 1721 | 500 | PV | 455-H3 | 2019-01-07 | 2019-01-11 | 4 |  | 4 | 2019-02-05 |  | -31039 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2323875 | 2747 | 699.3 | PV | 2-528-528 | 2019-01-17 | 2019-01-22 | 3 |  | 3 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2323953 | 2571 | 2000 | PV | 3-82-82 | 2019-02-06 |  | -31040 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-24 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Carver | 2324188 | 2330 | 2350 | PV | 3-10-930 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Boston | 2324396 | 2128 | 115.2 | PV | 488-H5 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Canton | 2324409 | 2021 | 299.7 | PV | 269-1320H1 | 2019-01-17 |  | -31026 |  | 0 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2324659 | 1701 | 4980 | PV & Battery | 2-605-605 | 2018-12-27 | 2019-02-01 | 26 |  | 26 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2324673 | 2631 | 25 | PV | 4-95A-597 | 2019-01-28 | 2019-02-01 | 4 |  | 4 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0 |  |  | 2019-07-01 | Online
NSTAR | South Dennis | 2324745 | 2660 | 133.3 | PV | 4-92B-92B | 2019-02-01 | 2019-02-01 | 0 |  | 0 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Cambridge | 2324814 | 2139 | 44000 | CHP | 831-1314 | 2019-02-12 | 2019-02-19 | 5 | 0 | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | 2019-03-04 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Woburn | 2325016 | 1801 | 243.1 | PV | 375-H3 | 2018-12-26 | 2019-02-07 | 31 |  | 31 | 2019-02-13 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-16 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | Acton | 2325167 | 1720 | 43.2 | PV | 416-H2 | 2019-02-07 | 2019-02-07 | 0 |  | 0 | 2019-02-14 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Framingham | 2325422 | 1702 | 240 | PV | 433-H8 | 2019-01-14 | 2019-01-14 | 0 |  | 0 | 2019-02-15 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Weston | 2325546 | 2493 | 200 | PV | 342-H1 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Brewster | 2325660 | 2631 | 24.99 | PV | 4-95B-600 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-15 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2019-07-15 | Online
NSTAR | Framingham | 2325768 | 1702 | 996 | PV | 240-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2325785 | 1801 | 216 | PV | 375-H14 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Woburn | 2325824 | 1801 | 250 | PV | 211-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Rochester | 2325833 | 2770 | 20 | PV | 3-703-703 | 2019-02-06 | 2019-02-11 | 3 |  | 3 | 2019-02-20 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online
NSTAR | East Walpole | 2326033 | 2032 | 2370 | PV | 2-102-604 | 2019-01-29 | 2019-02-11 | 9 |  | 9 | 2019-02-20 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-07-20 | Online
NSTAR | Boston | 2326176 | 2130 | 37.8 | PV | 528-169H | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Dorchester | 2326311 | 2125 | 1516 | PV | 466-1481H1 | 2019-01-28 |  | -31033 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2326325 | 2494 | 194 | PV | 148-H4 | 2019-02-04 |  | -31038 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2019-09-10 | Online
NSTAR | Dorchester | 2326537 | 2122 | 52.2 | PV | 466-1482H1 | 2019-02-07 |  | -31041 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-08 | Online
NSTAR | Carver | 2326793 | 2330 | 2000 | PV | 3-10-917 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2326814 | 1801 | 233.1 | PV | 211-H6 | 2019-02-12 | 2019-02-12 | 0 |  | 0 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Hopkinton | 2326836 | 1748 | 206 | PV | 126-H2 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Stoneham | 2326872 | 2180 | 200 | PV | 375-H7 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-26 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Chatham | 2326896 | 2633 | 117.12 | PV & Battery | 4-95A-95A | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-26 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0 |  |  | 2020-07-01 | Online
NSTAR | Burlington | 2327102 | 1805 | 5274.6 | PV & Battery | 541-1377H | 2019-01-22 | 2019-02-15 | 18 |  | 18 | 2019-02-27 |  | -31055 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2327130 | 2540 | 4980 | PV & Battery | 4-98B-448 | 2019-02-01 | 2019-02-15 | 10 |  | 10 | 2019-02-27 |  | -31055 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2327251 | 2138 | 86.4 | PV | 831-1336XY | 2019-02-14 | 2019-02-22 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Chilmark | 2327284 | 2535 | 25 | PV | 4-91-126 | 2019-02-20 | 2019-02-22 | 2 |  | 2 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0 |  |  | 2019-10-02 | Online
NSTAR | Plympton | 2327303 | 2367 | 2000 | PV | 3-10-930 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2327320 | 2739 | 2000 | PV | 2-302-302 | 2019-02-12 | 2019-02-14 | 2 |  | 2 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2327357 | 2114 | 50 | PV | 528-169H | 2019-02-14 | 2019-02-14 | 0 |  | 0 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Chilmark | 2327379 | 2535 | 16.24 | PV | 4-97-220 | 2019-02-20 | 2019-02-20 | 0 |  | 0 | 2019-03-01 |  | -31057 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-08 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2327596 | 2090 | - |  | TBD | 2019-03-01 |  | -31057 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-10-04 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Rochester | 2328012 | 2770 | 15000 | PV | 3-85-85 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2328021 | 2330 | 499 | PV |  | 2019-03-04 | 2019-03-07 | 3 | 0 | 3 | 2019-03-07 | 2019-03-20 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2019-04-17 | 2020-10-16 | No | Expedited | 30 | 2020-10-14 |  | -31480 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Plymouth | 2328025 | 2360 | 630 | PV & Battery | 3-71-937 | 2019-02-19 | 2019-02-19 | 0 |  | 0 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2328085 | 2717 | 27.42 | PV | 2-102-102 | 2019-02-20 | 2019-02-21 | 1 |  | 1 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Plymouth | 2328095 | 2360 | 500 | PV & Battery | 3-89-89 | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2328177 | 1760 | 32.4 | PV | 433-H10 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Framingham | 2328190 | 1701 | 57 | PV |  | 2019-03-05 | 2019-11-25 | 189 | 182 | 7 | 2019-11-25 | 2019-12-10 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-12-20 |  | 2019-10-06 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2022-11-21 | Online | [5 empty] | Private | N
NSTAR | Boston | 2328228 | 2134 | 180 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-08 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online
NSTAR | Roxbury Crossing | 2328268 | 2120 | 72 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-06 |  | -31060 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2328535 | 2460 | 220 | PV | 17-H1 | 2019-01-17 | 2019-02-26 | 28 |  | 28 | 2019-03-07 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Norfolk | 2328724 | 2056 | 195 | PV | 146-H9 | 2019-02-14 | 2019-02-19 | 3 |  | 3 | 2019-03-08 |  | -31062 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2328863 | 2601 | 100 | PV | 4-63-63 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-18 | Online
NSTAR | Waltham | 2329018 | 2451 | 924 | PV | 450-H7 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-11 |  | -31063 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2329096 | 2021 | 1100 | PV | 269-1320H1 | 2019-02-06 | 2019-02-28 | 16 |  | 16 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2329126 | 2131 | 20.7 | PV | 468-02 | 2019-01-04 | 2019-02-27 | 38 |  | 38 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2019-08-05 | Online
NSTAR | Hyannis | 2329185 | 2601 | 43.6 | PV | 4-63-63 | 2019-02-25 | 2019-02-28 | 3 |  | 3 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-09-23 | Online
NSTAR | Sherborn | 2329192 | 1770 | 34.78 | PV | 240-H1 | 2019-02-15 | 2019-02-26 | 7 |  | 7 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Brewster | 2329348 | 2631 | 20 | PV | 4-89B-576 | 2019-02-28 | 2019-03-05 | 3 |  | 3 | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329391 | 2739 | 4600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-14 |  | -31066 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329466 | 2743 | 4980 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-15 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330206 | 2739 | 2600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-03-06 | 10 |  | 10 | 2019-03-18 |  | -31068 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2330259 | 1801 | 233.2 | PV | 375-H3 | 2019-03-05 | 2019-03-08 | 3 |  | 3 | 2019-03-18 |  | -31068 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-12 | Online
NSTAR | Sandwich | 2330325 | 2644 | 5000 | PV & Battery | 4-81B-443 | 2019-02-22 | 2019-02-27 | 3 |  | 3 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2330355 | 2459 | 266 | PV | 17-H2 | 2019-03-11 | 2019-03-11 | 0 |  | 0 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sandwich | 2330360 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330392 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2330416 | 2492 | 23.3 | PV | 148-H4 | 2019-02-12 | 2019-03-07 | 17 |  | 17 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-21
NSTAR | South Yarmouth | 2330447 | 2664 | 233.64 | PV | 4-90-90 | 2019-02-28 | 2019-03-06 | 4 |  | 4 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2330458 | 2601 | 699.9 | PV | 4-63-63 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-03-20 |  | -31070 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2022-12-31 | Online
NSTAR | Assonett | 2330491 | 2702 | 4890 | PV & Battery |  | 2019-03-19 | 2019-03-20 | 1 | 0 | 1 | 2019-03-26 |  | -31074 | 439 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-04-02 | Private
NSTAR | Winchester | 2330512 | 1890 | 37.8 | PV | 211-H1 | 2019-03-01 | 2019-03-11 | 6 |  | 6 | 2019-03-22 |  | -31072 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09 | Online
NSTAR | Sandwich | 2330718 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330720 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330775 | 2739 | 4980 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-06 | 9 |  | 9 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | Roslindale | 2330819 | 2131 | 42.8 | PV | 1312 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-22 |  | -31072 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05
NSTAR | Sandwich | 2330875 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330882 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330923 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330926 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-07 | 2019-03-15 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2330941 | 2081 | 250 | PV | 146-H1 | 2019-03-08 | 2019-03-13 | 3 |  | 3 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2331027 | 2653 | 133.3 | PV | TBD | 2019-03-22 |  | -31072 | 0 | 0 | 2019-04-17 | 2019-05-04 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-04-15 | 2019-11-21 | 2019-10-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Sandwich | 2331148 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331153 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331280 | 2744 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331299 | 2743 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331348 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331371 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2331457 | 2118 | 1000 | PV & Battery | 4912 | 2019-02-11 | 2019-03-14 | 23 |  | 23 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2331587 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331592 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-01-02 | 2019-02-26 | 39 |  | 39 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2331739 | 2142 | 75 | PV | 875-1N35B | 2019-02-14 | 2019-03-15 | 21 |  | 21 | 2019-03-28 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Walpole | 2331931 | 2081 | 407 | PV | 146-H1 | 2019-01-11 | 2019-03-15 | 45 |  | 45 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2332061 | 2649 | 254.29 | PV | 4-88-483 | 2019-03-13 | 2019-03-15 | 2 |  | 2 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-03 | Online
NSTAR | Ashland | 2333111 | 1721 | 250 | PV & Battery | 455-H3 | 2019-03-05 | 2019-03-18 | 9 |  | 9 | 2019-04-04 |  | -31081 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2333220 | 1721 | 250 | PV | 455-H3 | 2019-01-11 | 2019-03-18 | 46 |  | 46 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2333229 | 1760 | 407 | PV & Battery | 433-H10 | 2019-01-17 | 2019-03-18 | 42 |  | 42 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2333242 | 2601 | 254.29 | PV | 4-63-63 | 2019-03-14 | 2019-03-19 | 3 |  | 3 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0 |  |  | 2020-01-09 | Online
NSTAR | Dorchester | 2333256 | 2124 | 240 | PV | 466-1481H1 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2333267 | 2421 | - |  | TBD | 2019-04-04 |  | -31081 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Duxbury | 2333489 | 2332 | 20 | PV | 3-26-903 | 2019-03-07 | 2019-03-22 | 11 |  | 11 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333508 | 2740 | 346.5 | PV | 2-137-139 | 2019-03-18 | 2019-03-22 | 4 |  | 4 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333666 | 2745 | 22.8 | PV | 2-87-135 | 2019-03-13 | 2019-03-25 | 8 |  | 8 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Newton | 2333672 | 2460 | 360 | PV | 282-H8 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-11 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Wareham | 2333726 | 2571 | 4500 | PV | 8-83-83 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2333746 | 2571 | 4500 | PV |  | 2019-04-08 | 2019-04-09 | 1 | 0 | 1 | 2019-04-10 |  | -31085 | 427 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-04-18 | Private
NSTAR | South Boston | 2333766 | 2127 | 172.8 | PV | 106-H3 | 2019-03-05 | 2019-03-25 | 14 |  | 14 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Walpole | 2333782 | 2081 | 34.2 | PV | 146-H4 | 2019-04-08 | 2019-04-12 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | South Dennis | 2333807 | 2660 | 699.7 | PV | 4-92B-92B | 2019-03-04 | 2019-03-25 | 15 |  | 15 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Edgartown | 2333814 | 2539 | 24 | PV | TBD | 2019-02-26 | 2019-03-20 | 16 |  | 16 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Walpole | 2334013 | 2081 | 400 | PV |  | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-19 | 2020-06-03 | 293 | 0 | 293 |  |  | 0 |  | 0 | 2020-11-17 | 2020-11-20 | 3 | 0 | 3 | 2020-02-21 | 2020-12-29 | 2021-01-15 | No |  | 60 | 2020-02-10 |  | -31303 |  | 0 |  |  | 2021-05-24 | Online | [5 empty] | Private | N
NSTAR | Walpole | 2334039 | 2081 | 131.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-06-15 | 40 | 0 | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | 2020-06-09 | 2020-10-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Forestdale | 2334165 | 2644 | 4990 | PV | 4-81B-443 | 2019-03-14 | 2019-03-26 | 8 |  | 8 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2334186 | 2360 | 144 | PV | 3-89-89 | 2019-03-20 | 2019-03-26 | 4 |  | 4 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-11-18 | Online
NSTAR | Walpole | 2334212 | 2081 | 37.8 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-18 | 2019-05-31 | 31 | 0 | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-04 | 2019-06-18 | 2020-06-04 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private | N
NSTAR | Walpole | 2334218 | 2081 | 32.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | [5 empty] | Private
NSTAR | Walpole | 2334252 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | [5 empty] | Gov't
NSTAR | Walpole | 2334255 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | [5 empty] | Gov't
NSTAR | Mattapoisett | 2334358 | 2739 | 3300 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-27 | 24 |  | 24 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | New Bedford | 2334371 | 2744 | 180 | PV | 2-137-139 | 2019-01-31 | 2019-03-27 | 39 |  | 39 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-07-29 | Online
NSTAR | Sandwich | 2334390 | 2563 | 250 | PV & Battery | 4-81B-443 | 2019-03-27 | 2019-03-27 | 0 |  | 0 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2334399 | 1730 | 200 | PV | 322-05 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2334411 | 2081 | 142 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-18 | 2019-05-30 | 30 | 0 | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2021-02-09 | Online | [5 empty] | Gov't
NSTAR | Walpole | 2334415 | 2081 | 129.6 | PV | TBD | 2019-04-11 |  | -31086 | 0 | 0 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-06-04 | 2020-01-08 | 2019-11-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Sandwich | 2334444 | 2563 | 77.5 | PV | 4-81B-443 | 2019-02-19 | 2019-03-28 | 27 |  | 27 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | East Dennis | 2334447 | 2641 | 36 | PV | 4-89A-552 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | Sudbury | 2334450 | 1776 | 15.2 | PV & Battery | 342-H5 | 2019-03-29 | 2019-04-12 | 10 |  | 10 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Walpole | 2334456 | 2081 | 1000 | PV & Battery | 146-H1 | 2019-03-15 | 2019-03-28 | 9 |  | 9 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 | 2745 | 496 | PV |  | 2019-04-12 | 2019-04-16 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-18 | 2020-09-08 | 363 | 319 | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-09-20 | Private
NSTAR | Lexington | 2334511 | 2421 | 1500 | PV & Battery | 533-H1 | 2019-03-15 | 2019-03-20 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2334531 | 2747 | 1000 | PV | 2-528-528 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334854 | 2745 | 199.8 | PV | 2-137-139 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | 2019-04-18 |  | -31091 | 379 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-06-26 | Private
NSTAR | Milton | 2335039 | 2186 | 61.2 | PV | 496-H2 | 2019-03-28 | 2019-04-01 | 2 |  | 2 | 2019-04-16 |  | -31089 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Plymouth | 2335156 | 2360 | - |  | TBD | 2019-04-16 |  | -31089 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Norfolk | 2335261 | 2056 | 50 | PV | 146-H9 | 2019-04-01 | 2019-04-01 | 0 |  | 0 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-05 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Jamaica Plain | 2335383 | 2130 | 432.9 | PV | 496-H4 | 2019-04-02 | 2019-04-02 | 0 |  | 0 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-01 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2335440 | 1760 | 150 | CHP | 433-H7 | 2019-03-26 | 2019-04-02 | 5 |  | 5 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-02-18 | Online
NSTAR | South Dennis | 2335447 | 2660 | 133.2 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | South Dennis | 2335454 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2335459 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2335506 | 2770 | 25 | PV | 3-702-702 | 2019-03-20 | 2019-04-02 | 9 |  | 9 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2335814 | 2360 | 1800 | PV | 3-89-89 | 2019-03-20 | 2019-04-04 | 11 |  | 11 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2335827 | 2330 | 2000 | PV & Battery | 3-81-950 | 2019-03-28 | 2019-04-04 | 5 |  | 5 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2336013 | 2021 | 200.4 | PV | 269-1320H1 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | Plymouth | 2336042 | 2360 | 366 | PV |  | 2019-04-23 | 2019-04-23 | 0 | 0 | 0 | 2019-04-23 | 2019-05-22 | 21 | 0 | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | 2020-09-02 | 2019-11-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2023-03-28 | Online | [5 empty] | Private
NSTAR | Cambridge | 2336049 | 2142 | 35 | CHP | 875-1N25A | 2019-03-12 | 2019-04-08 | 19 |  | 19 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2336071 | 2056 | 4990 | PV & Battery | 146-H9 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 2336099 | 2719 | 5000 | PV |  | 2019-04-23 | 2019-04-25 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-25 |  | -31096 | 256 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-04-18 | Private
NSTAR | West Wareham | 2336183 | 2576 | 57.6 | PV | 3-86-86 | 2019-04-10 | 2019-04-10 | 0 |  | 0 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-16 | Online
NSTAR | Rochester | 2336283 | 2770 | 17.52 | PV | 3-85-85 | 2019-04-09 | 2019-04-11 | 2 |  | 2 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-11 | Online
NSTAR | Falmouth | 2336292 | 2556 | 26 | PV | 4-98B-448 | 2019-04-04 | 2019-04-11 | 5 |  | 5 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Natick | 2336317 | 1760 | 366.6 | PV | 433-H5 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2336372 | 2451 | 166.6 | PV | 450-H7 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2336465 | 1741 | 496 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-26 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2337102 | 1741 | 484 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-30 |  | -31099 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-26 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Freetown | 2337126 | 2702 | 4890 | PV & Battery | 2-605-605 | 2019-04-12 | 2019-04-15 | 1 |  | 1 | 2019-05-01 |  | -31100 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2337174 | 2717 | 4890 | PV & Battery | 2-605-605 | 2019-04-16 | 2019-04-17 | 1 |  | 1 | 2019-05-01 |  | -31100 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2337311 | 2360 | 195 | PV | 3-89-89 | 2019-03-26 | 2019-04-01 | 4 |  | 4 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 2337320 | 2135 | 250 | PV | 467-H12 | 2019-03-29 | 2019-04-03 | 3 |  | 3 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2337333 | 2021 | 133.6 | PV | 269-1320H1 | 2019-02-11 | 2019-04-08 | 40 |  | 40 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | Hatchville | 2337408 | 2536 | 28.5 | PV | 4-98A-98A | 2019-02-26 | 2019-04-12 | 33 |  | 33 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2337464 | 1730 | 35 | CHP | 322-05 | 2019-04-01 | 2019-04-22 | 15 |  | 15 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Brighton | 2337496 | 2135 | 86.6 | PV | 329-H2 | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Somerville | 2338222 | 2145 | 99.9 | PV | 250-H4XY | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-06 |  | -31103 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Ashland | 2338277 | 1721 | 19 | PV | 519-175H1 | 2019-04-17 | 2019-04-18 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Carver | 2338333 | 2330 | - |  | TBD | 2019-05-06 |  | -31103 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-12 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2338339 | 2330 | 9500 | PV & Battery | 3-81-950 | 2019-04-08 | 2019-04-30 | 16 |  | 16 | 2019-05-07 |  | -31104 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2338418 | 2738 | 99.9 | PV | 3-304-304 | 2019-04-18 | 2019-04-18 | 0 |  | 0 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | East Boston | 2338574 | 2128 | 43.2 | PV | 488-H5 | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | East Boston | 2338586 | 2128 | 28.8 | PV | 592-72XY | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1900-01-03 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Waltham | 2338649 | 2453 | 99.9 | PV | 33-H3 | 2019-04-17 | 2019-04-23 | 4 |  | 4 | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Framingham | 2338764 | 1702 | 15.2 | PV | 455-H5 | 2019-01-04 | 2019-04-19 | 75 |  | 75 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Plymouth | 2338789 | 2360 | 756 | PV | 3-89-89 | 2019-04-09 | 2019-04-25 | 12 |  | 12 | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Assonett | 2339086 | 2702 | 4498 | PV |  | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 |  | -31109 | 409 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2019-12-18 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-05-14 | Private
NSTAR | New Bedford | 2339142 | 2746 | 355 | PV |  | 2019-05-10 | 2019-05-17 | 5 | 0 | 5 | 2019-05-27 |  | -31118 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 |  | 2020-03-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Gov't
NSTAR | New Bedford | 2339509 | 2744 | 113 | PV |  | 2019-05-13 | 2019-05-17 | 4 | 0 | 4 | 2019-05-27 | 2020-06-16 | 276 | 0 | 276 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Sharon | 2339541 | 2067 | 57.6 | PV | 146-H7 | 2019-04-23 | 2019-04-25 | 2 |  | 2 | 2019-05-14 |  | -31109 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-29 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | New Bedford | 2339571 | 2745 | 129.6 | PV |  | 2019-05-13 | 2019-05-22 | 7 | 0 | 7 | 2019-05-27 | 2020-09-17 | 343 | 0 | 343 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Gov't
NSTAR | New Bedford | 2339580 | 2745 | - |  | TBD | 2019-05-13 |  | -31108 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-19 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | New Bedford | 2339584 | 2746 | 369.6 | PV | 2-89-181 | 2019-05-13 | 2019-05-21 | 6 | 0 | 6 | 2019-05-27 | 2019-11-13 | 122 | 0 | 122 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-03-20 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Gov't
NSTAR | Woburn | 2339665 | 1801 | 66.6 | PV | 375-H1 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Hyde Park | 2339703 | 2136 | 40 | PV | 311-13 | 2019-04-19 | 2019-04-29 | 6 |  | 6 | 2019-05-14 |  | -31109 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Westwood | 2339939 | 2090 | 60 | PV | 20-H3 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-16 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Newton | 2340114 | 2459 | 57.6 | PV | 1708 | 2019-05-01 | 2019-05-02 | 1 |  | 1 | 2019-05-17 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | North Dartmouth | 2340119 | 2747 | 999 | PV & Battery | 2-541-541 | 2019-03-21 | 2019-05-07 | 33 |  | 33 | 2019-05-17 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2340125 | 2745 | 200 | PV | 2-137-139 | 2019-04-18 | 2019-05-08 | 14 |  | 14 | 2019-05-20 |  | -31113 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-19 | Online
NSTAR | Boston | 2340373 | 2118 | 60 | PV | 323-78H1 | 2019-04-19 | 2019-04-30 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Waltham | 2340378 | 2136 | - |  | TBD | 2019-05-17 |  | -31112 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-26 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Acusnet | 2340380 | 2743 | 2999 | PV & Battery | 2-241-241 | 2019-04-12 | 2019-04-30 | 12 |  | 12 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2340383 | 2453 | 40 | PV | 311-13 | 2019-04-17 | 2019-04-29 | 8 |  | 8 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Newton | 2340567 | 2460 | 72 | PV | 282-H8 | 2019-04-26 | 2019-05-01 | 3 |  | 3 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Lincoln | 2340569 | 1773 | 38 | PV | 320-H8 | 2019-04-22 | 2019-05-01 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Kingston | 2340663 | 2364 | 1800 | PV | 3-17-17 | 2019-04-25 | 2019-05-02 | 5 |  | 5 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-03-30 | Online
NSTAR | Walpole | 2340703 | 2071 | 99.9 | PV | 146-H1 | 2019-05-01 | 2019-05-03 | 2 |  | 2 | 2019-05-23 |  | -31116 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2340718 | 2637 | 250 | PV | 4-92B-583 | 2019-04-25 | 2019-04-30 | 3 |  | 3 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Dover | 2340724 | 2030 | 20.2 | PV | 456-H5 | 2019-04-11 | 2019-05-06 | 17 |  | 17 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Dedham | 2340807 | 2026 | 20 | PV | 148-H3 | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-03-27 | Online
NSTAR | Brewster | 2340839 | 2631 | 20.01 | PV | 4-89B-618 | 2019-04-12 | 2019-05-14 | 22 |  | 22 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2340888 | 2138 | 66.6 | PV | 819-1NE4 | 2019-05-21 | 2019-05-22 | 1 | 0 | 1 | 2019-05-23 | 2019-06-18 | 18 | 0 | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 |  | 2019-12-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2020-12-16 | Online | [5 empty] | Private
NSTAR | Woburn | 2340946 | 1801 | 480 | PV | TBD | 2019-05-08 | 2019-05-14 | 4 |  | 4 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-18 | Online
NSTAR | Cambridge | 2341088 | 2138 | 20.4 | PV | 831-1336XY | 2019-04-17 | 2019-05-15 | 20 |  | 20 | 2019-05-23 |  | -31116 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Woburn | 2341172 | 1801 | 166.5 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-08 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2341237 | 1801 | 249.8 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2341375 | 2748 | 200 | PV | 2-528-528 | 2019-05-09 | 2019-05-16 | 5 |  | 5 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2341496 | 2747 | 1000 | PV & Battery | 2-528-528 | 2019-02-25 | 2019-05-16 | 58 |  | 58 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sagamore Beach | 2341513 | 2562 | 20 | PV | 3-89-925 | 2019-05-16 | 2019-05-17 | 1 |  | 1 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | East Freetown | 2341535 | 2717 | 25 | PV | 2-102-102 | 2019-05-16 | 2019-05-17 | 1 |  | 1 | 2019-05-29 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-01 | [7 empty] | 0 |  | 0 |  |  | 2020-10-22 | Online
NSTAR | Sharon | 2341555 | 2067 | 20.35 | PV | 470-H12 | 2019-04-22 | 2019-05-17 | 19 |  | 19 | 2019-05-29 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Norfolk | 2341849 | 2056 | 1000 | PV | 146-H9 | 2019-05-16 | 2019-05-20 | 2 |  | 2 | 2019-05-30 |  | -31121 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2341861 | 2360 | 114 | PV | 3-89-89 | 2019-05-20 | 2019-05-21 | 1 |  | 1 | 2019-05-30 |  | -31121 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2341981 | 2050 | 31.5 | PV & Battery | 3-25-42J2 | 2019-04-18 | 2019-05-21 | 23 |  | 23 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2342846 | 2743 | 2640 | PV & Battery | 2-241-241 | 2019-04-10 | 2019-05-31 | 37 |  | 37 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2342972 | 1741 | 18.7 | PV | 512-1399h1 | 2019-05-16 | 2019-05-24 | 6 |  | 6 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-12 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Dartmouth | 2342977 | 2747 | - | PV | TBD | 2019-06-03 |  | -31123 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-10 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Needham | 2342982 | 2494 | 43.2 | PV | 148-H1 | 2019-05-16 | 2019-05-22 | 4 |  | 4 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Plymouth | 2343065 | 2360 | 250 | PV & Battery | 3-71-937 | 2019-05-21 | 2019-05-24 | 3 |  | 3 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2343104 | 1748 | 8485 | PV & Battery | 533-H7 | 2019-05-16 | 2019-05-24 | 6 |  | 6 | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343408 | 2536 | 36 | PV | 4-98A-98A | 2019-05-29 | 2019-05-29 | 0 |  | 0 | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-03-05 | Online
NSTAR | Wareham | 2343539 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-21 | 2019-05-29 | 6 |  | 6 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2343563 | 2747 | 6000 | PV | 2-528-528 | 2019-05-06 | 2019-05-29 | 17 |  | 17 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2343564 | 1801 | 50 | PV | 211-H2 | 2019-05-14 | 2019-05-22 | 6 |  | 6 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-16 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21
NSTAR | Cambridge | 2343568 | 2140 | 32.4 | PV | 824-26 | 2019-05-13 | 2019-05-22 | 7 |  | 7 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2343632 | 1801 | 66.6 | PV | 211-H6 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-01-20 | Online
NSTAR | Cambridge | 2343786 | 2138 | 924 | PV | 831-1336XY | 2019-05-21 | 2019-05-30 | 7 |  | 7 | 2019-06-07 |  | -31127 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343832 | 2536 | 72 | PV | 4-98B-449 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-07 |  | -31127 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online
NSTAR | West Yarmouth | 2343868 | 2673 | 174 | PV & Battery | 4-92A-536 | 2019-05-21 | 2019-05-28 | 5 |  | 5 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-26 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Wareham | 2344136 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-24 | 2019-05-30 | 4 |  | 4 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2344165 | 2460 | 216 | PV | 282-H8 | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344421 | 2468 | 86 | PV | 292-H12 | 2019-04-25 | 2019-05-30 | 25 |  | 25 | 2019-06-12 |  | -31130 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344584 | 2460 | 109 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344713 | 2460 | 133 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 | 2019-05-30 | -13 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344729 | 2460 | 60 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344792 | 2459 | 136 | PV | 292-H8 | 2019-04-25 | 2019-05-30 | 25 |  | 25 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344807 | 2460 | 109 | PV | 467-H14 | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344839 | 2459 | 146 | PV | TBD | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2344916 | 2119 | 52.2 | PV | TBD | 2019-05-16 | 2019-05-31 | 11 |  | 11 | 2019-06-19 |  | -31135 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | New Bedford | 2345033 | 2746 | 496 | PV | 2-83-403 | 2017-02-01 | 2017-02-17 | 12 |  | 12 | 2017-02-28 |  | -30534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31
NSTAR | Cambridge | 2345372 | 2138 | 330 | PV | TBD | 2019-05-21 | 2019-06-03 | 9 |  | 9 | 2019-06-18 |  | -31134 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2345373 | 2421 | 22.95 | PV & Battery | 320-H2 | 2019-05-28 | 2019-06-04 | 5 |  | 5 | 2019-06-18 |  | -31134 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2345601 | 2459 | 100 | PV | TBD | 2019-04-25 | 2020-06-04 | 290 |  | 290 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2345649 | 2664 | 249.9 | PV | TBD | 2019-05-29 | 2019-06-05 | 5 |  | 5 | 2019-06-19 |  | -31135 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-19 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Canton | 2345712 | 2021 | 688 | PV & Battery | 269-1320H1 | 2019-04-26 | 2019-06-06 | 29 |  | 29 | 2019-06-20 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2345953 | 2021 | 250 | PV | TBD | 2019-05-30 | 2019-06-07 | 6 |  | 6 | 2019-06-20 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-02 | Online
NSTAR | Newton | 2346031 | 2461 | 145.1 | PV | 292-H1 | 2019-05-29 | 2019-06-07 | 7 |  | 7 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Chelsea | 2346218 | 2150 | 1736 | CHP | TBD | 2019-03-20 | 2019-06-03 | 53 |  | 53 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Canton | 2346246 | 2021 | 100 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2346323 | 2119 | 37.8 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Watertown | 2346407 | 2472 | 133.2 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-25 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Westport | 2346438 | 2790 | 20 | PV | TBD | 2019-05-29 | 2019-06-10 | 8 |  | 8 | 2019-06-25 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Boston | 2346459 | 2125 | 133.2 | PV | 321-02 | 2019-06-07 | 2019-06-11 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Wareham | 2346531 | 2576 | 4980 | PV | TBD | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | 2019-06-27 |  | -31141 | 371 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-02-03 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-07-09 | Private
NSTAR | Boston | 2346677 | 2163 | 43.2 | PV | TBD | 2019-05-31 | 2019-06-12 | 8 |  | 8 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Hopkinton | 2346774 | 1748 | 480 | PV | TBD | 2019-05-23 | 2019-06-13 | 15 |  | 15 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2346835 | 2120 | 57.6 | PV | TBD | 2019-06-10 | 2019-06-13 | 3 |  | 3 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Sharon | 2346951 | 2067 | 50 | PV | 470-H3 | 2019-05-07 | 2019-06-14 | 28 |  | 28 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online
NSTAR | Duxbury | 2346979 | 2332 | 200 | PV | 3-27-970 | 2019-06-19 | 2019-06-19 | 0 |  | 0 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-23 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Needham | 2347063 | 2492 | 57.6 | PV | 148-H4 | 2019-06-13 | 2019-06-17 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Boston | 2347214 | 2115 | 57.6 | PV | TBD | 2019-06-12 | 2019-06-14 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2347229 | 1773 | 17.4 | PV | 320-H6 | 2019-05-31 | 2019-06-14 | 10 |  | 10 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Acton | 2347245 | 1720 | 60 | PV | 416-H8 | 2019-06-06 | 2019-06-17 | 7 |  | 7 | 2019-06-28 |  | -31142 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Assonett | 2347725 | 2702 | 3000 | PV & Battery | TBD | 2019-06-17 | 2019-06-20 | 3 |  | 3 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2347755 | 2631 | 1490 | PV & Battery | TBD | 2019-05-31 | 2019-06-21 | 15 |  | 15 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22
NSTAR | Walpole | 2348516 | 2081 | 17.5 | PV | TBD | 2019-06-17 | 2019-06-21 | 4 |  | 4 | 2019-07-08 |  | -31148 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Brewster | 2348521 | 2631 | 480 | PV | TBD | 2019-05-30 | 2019-06-21 | 16 |  | 16 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-08-12 | Online
NSTAR | South Yarmouth | 2348526 | 2664 | 1560 | PV & Battery | 4-92A-563 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2348529 | 2645 | 166.5 | PV | 4-95A-95A | 2019-05-31 | 2019-06-26 | 18 |  | 18 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Newton | 2348530 | 2465 | 20 | PV & Battery | 282-H9 | 2019-05-31 | 2019-06-20 | 14 |  | 14 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-01-22 | Online
NSTAR | Ashland | 2348725 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-12 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Ashland | 2348729 | 1721 | 144 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-05-04 | Online
NSTAR | Woburn | 2349171 | 1801 | 333 | PV | TBD | 2019-06-21 | 2019-06-24 | 1 |  | 1 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2349180 | 2461 | 133.2 | PV | TBD | 2019-06-17 | 2019-06-25 | 6 |  | 6 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Ashland | 2349389 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-11 |  | -31151 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | East Freetown | 2349398 | 2717 | 1750 | PV | TBD | 2019-05-09 | 2019-06-24 | 32 |  | 32 | 2019-07-11 |  | -31151 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2349404 | 1890 | 108 | PV | 211-H4 | 2019-06-21 | 2019-06-26 | 3 |  | 3 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Fairhaven | 2349408 | 2719 | 2000 | PV & Battery | TBD | 2019-05-28 | 2019-06-26 | 21 |  | 21 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2349571 | 2717 | 1000 | PV | TBD | 2019-06-21 | 2019-06-26 | 3 |  | 3 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Sandwich | 2349576 | 2537 | 849.5 | PV & Battery | 4-87A-471 | 2019-05-31 | 2019-06-26 | 18 |  | 18 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2349579 | 2537 | 3510 | PV & Battery | 4-87A-471 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2349583 | 2644 | 849.5 | PV & Battery | 4-81B-443 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2349777 | 1701 | 57.6 | PV | TBD | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Roxbury | 2349780 | 2119 | 37.8 | PV | tbd | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Wareham | 2349786 | 2571 | 5500 | PV & Battery | TBD | 2019-06-21 | 2019-06-28 | 5 |  | 5 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Tisbury | 2349997 | 2573 | 19.17 | PV | TBD | 2019-06-26 | 2019-06-28 | 2 |  | 2 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Framingham | 2350003 | 1701 | 72 | PV | 433-H8 | 2019-06-24 | 2019-07-08 | 10 |  | 10 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-13 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350004 | 1773 | 107.84 | PV & Battery | 320-H8 | 2019-02-11 | 2019-07-10 | 107 |  | 107 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350022 | 1773 | 17.6 | PV | 320-H6 | 2019-05-31 | 2019-07-03 | 23 |  | 23 | 2019-07-16 |  | -31154 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2350124 | 1720 | 999 | PV | TBD | 2019-07-02 | 2019-07-09 | 5 |  | 5 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2350166 | 2770 | 1000 | PV & Battery | 3-702-702 | 2019-07-03 | 2019-07-10 | 5 |  | 5 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2350185 | 2119 | 25 | PV | 106-1N31H4 | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Natick | 2350187 | 1760 | 466.6 | PV | TBD | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | West Tisbury | 2350188 | 2568 | 20 | PV | TBD | 2019-05-23 | 2019-07-02 | 28 |  | 28 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0 |  |  | 2020-03-11 | Online
NSTAR | Hyannis | 2350400 | 2601 | 112.5 | PV | TBD | 2019-06-25 | 2019-07-11 | 12 |  | 12 | 2019-07-18 |  | -31156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Plymouth | 2350447 | 2360 | 250 | CHP | 3-73-927 | 2019-06-27 | 2019-07-02 | 3 |  | 3 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2350448 | 2452 | 133.2 | PV | TBD | 2019-07-09 | 2019-07-12 | 3 |  | 3 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2020-08-24 | Online
NSTAR | Bass River | 2350641 | 2664 | 180 | PV | TBD | 2019-07-18 |  | -31156 | 0 | 0 | 2019-07-23 | 2019-08-17 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-09-05 |  | 2020-02-27 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Yarmouth | 2350705 | 2664 | 187.5 | PV |  | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 2019-07-23 | 2019-09-06 | 33 | 22 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | 2019-10-10 | 2020-02-28 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Provincetown | 2350711 | 2657 | 53.76 | PV | TBD | 2019-06-26 | 2019-07-12 | 12 |  | 12 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2350752 | 2368 | 333 | PV | TBD | 2019-06-24 | 2019-07-01 | 5 |  | 5 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | West Newton | 2350781 | 2465 | 100 | PV | 467-H5 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23
NSTAR | Plymouth | 2350809 | 2360 | 49.59 | PV | 3-10-10 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2351221 | 1803 | 999 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | New Bedford | 2351223 | 2745 | 499.5 | PV | TBD | 2019-07-01 | 2019-07-08 | 5 |  | 5 | 2019-07-23 |  | -31159 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Lexington | 2351263 | 2421 | 110 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2351363 | 2420 | 491 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2351364 | 1746 | 4999 | PV & Battery | TBD | 2019-07-05 | 2019-07-10 | 3 |  | 3 | 2019-07-23 |  | -31159 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2351423 | 2026 | 22.8 | PV | 20-H7 | 2019-07-08 | 2019-07-10 | 2 |  | 2 | 2019-07-24 |  | -31160 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | New Bedford | 2351619 | 2740 | 236 | PV | TBD | 2019-07-10 | 2019-07-11 | 1 |  | 1 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Boston | 2351637 | 2115 | 43.2 | PV | TBD | 2019-06-27 | 2019-07-11 | 10 |  | 10 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2351638 | 2745 | 466.6 | PV | TBD | 2019-07-08 | 2019-07-11 | 3 |  | 3 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2351639 | 2747 | 150 | PV | TBD | 2019-07-12 | 2019-07-12 | 0 |  | 0 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Medfield | 2351919 | 2052 | 1280 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | 3 |  | 3 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2351939 | 2664 | 92.16 | PV | TBD | 2019-07-12 | 2019-07-15 | 1 |  | 1 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Sandwich | 2351960 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2351984 | 2330 | 4999 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | 2 |  | 2 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352055 | 2420 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Lexington | 2352056 | 2421 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Provincetown | 2352065 | 2657 | 325 | PV | TBD | 2019-07-12 |  | -31152 |  | 0 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Lexington | 2352139 | 2421 | 180 | PV | TBD | 2019-07-10 | 2019-07-17 | 5 |  | 5 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2352175 | 2743 | 84 | PV | TBD | 2019-07-18 | 2019-07-18 | 0 |  | 0 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2352275 | 2139 | 694 | PV & Battery | 831-1118 | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352285 | 2421 | 905 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | 2 |  | 2 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Medfield | 2352302 | 2052 | 766.6 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | 3 |  | 3 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2352308 | 2053 | 250 | PV | TBD | 2019-06-26 | 2019-07-16 | 14 |  | 14 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Cambridge | 2352522 | 2139 | 460 | PV & Battery | 831-1304 | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2352540 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352572 | 2421 | 247 | PV & Battery | TBD | 2019-07-11 | 2019-07-17 | 4 |  | 4 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Dorchester | 2352639 | 2124 | 199.8 | PV | TBD | 2019-07-01 | 2019-07-17 | 12 |  | 12 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2352680 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2352731 | 2747 | 516 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2352774 | 1801 | 100 | PV | 211-H6 | 2019-07-18 | 2019-07-19 | 1 |  | 1 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Stoneham | 2352776 | 2180 | 166.6 | PV | TBD | 2019-06-21 | 2019-07-17 | 18 |  | 18 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-08 | Online
NSTAR | Lexington | 2352782 | 2421 | 330 | PV | TBD | 2019-08-01 |  | -31166 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-12 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Lexington | 2352860 | 2421 | 297 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Medfield | 2352954 | 2052 | 150 | PV | TBD | 2019-07-18 | 2019-07-22 | 2 |  | 2 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-09-13 | Online
NSTAR | Carver | 2352975 | 2330 | 1250 | PV & Battery | TBD | 2019-07-12 | 2019-07-19 | 5 |  | 5 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2353430 | 2571 | 5000 | PV & Battery | tbd | 2019-06-04 | 2019-07-23 | 35 |  | 35 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2353437 | 1760 | 496 | PV | 240-H1 | 2017-06-28 | 2017-06-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Roxbury | 2353454 | 2120 | 66.6 | PV | TBD | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Milton | 2353541 | 2186 | 25.2 | PV | 496-H7 | 2019-06-05 | 2019-07-26 | 37 |  | 37 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online
NSTAR | Mattapoisett | 2353656 | 2739 | 4999 | PV & Battery | TBD | 2019-07-16 | 2019-07-19 | 3 |  | 3 | 2019-08-07 |  | -31170 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2353669 | 2139 | 133.2 | PV | TBD | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2353792 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2353830 | 1803 | 43.2 | PV | TBD | 2019-07-16 | 2019-07-19 | 3 |  | 3 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | South Yarmouth | 2353833 | 2664 | 756 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2353838 | 2717 | 500 | PV & Battery | TBD | 2019-05-29 | 2019-07-22 | 38 |  | 38 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2354057 | 2120 | 43.2 | PV | TBD | 2019-07-09 | 2019-07-24 | 11 |  | 11 | 2019-08-09 |  | -31172 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-03-30
NSTAR | Sandwich | 2354118 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354162 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354172 | 2563 | 3250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-12 |  | -31173 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Roxbury | 2354364 | 2120 | 22.8 | PV | 52-1499H2 | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-12 |  | -31173 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | East Wareham | 2354403 | 2538 | 15.2 | PV | 3-84-960 | 2019-04-19 | 2019-07-25 | 69 |  | 69 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Freetown | 2354457 | 2717 | 5000 | PV & Battery | TBD | 2019-06-03 | 2019-07-30 | 41 |  | 41 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2354467 | 2645 | 3750 | PV | TBD | 2019-07-24 | 2019-08-01 | 6 |  | 6 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2354511 | 2537 | 900 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2354558 | 2659 | 1560 | PV | TBD | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2354628 | 2139 | 594.6 | PV & Battery | 831-1301 | 2019-06-18 | 2019-07-19 | 23 |  | 23 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2354633 | 1801 | 100 | PV | 375-H14 | 2019-07-18 | 2019-07-19 | 1 |  | 1 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Chatham | 2354636 | 2650 | 24.64 | PV | TBD | 2019-07-16 | 2019-07-22 | 4 |  | 4 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Boston | 2354844 | 2120 | 43.2 | PV | TBD | 2019-07-10 | 2019-07-24 | 10 |  | 10 | 2019-08-15 |  | -31176 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2354849 | 2747 | 5000 | PV & Battery | TBD | 2019-05-09 | 2019-07-26 | 56 |  | 56 | 2019-08-15 |  | -31176 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2355009 | 2571 | 500 | PV & Battery | 3-84-968 | 2019-07-18 | 2019-07-29 | 7 |  | 7 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 2355012 | 2659 | 2500 | PV & Battery | TBD | 2019-07-25 | 2019-07-25 | 0 |  | 0 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2355014 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355015 | 2563 | 250 | PV & Battery | TBD | 2019-07-29 | 2019-07-29 | 0 |  | 0 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355016 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355017 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2355098 | 2163 | 166.6 | PV | TBD | 2019-07-19 | 2019-08-05 | 11 |  | 11 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-24 | Online
NSTAR | Sandwich | 2355143 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2355146 | 2743 | 4995 | PV & Battery | TBD | 2019-07-24 | 2019-08-01 | 6 |  | 6 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2355147 | 2664 | 264 | PV | TBD | 2019-07-22 | 2019-08-02 | 9 |  | 9 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Boston | 2355397 | 2127 | 275 | PV & Battery | 293-09 | 2019-07-12 | 2019-08-05 | 16 |  | 16 | 2019-08-20 |  | -31179 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-14 | Online
NSTAR | Dorchester | 2355449 | 2125 | 366.3 | PV | TBD | 2019-08-19 |  | -31178 | 0 | 0 | 2019-08-22 | 2019-11-01 | 51 | 40 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Boston | 2355531 | 2163 | 66.6 | PV | TBD | 2019-07-29 | 2019-08-05 | 5 |  | 5 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-03-23 | Online
NSTAR | Bourne | 2355532 | 2532 | 499 | PV | TBD | 2019-07-29 | 2019-08-06 | 6 |  | 6 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2355569 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Falmouth | 2355581 | 2540 | 46.08 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-24 | Online
NSTAR | Boston | 2355610 | 2115 | 100 | PV | 493-1411H | 2019-08-07 | 2019-08-08 | 1 |  | 1 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | Bellingham | 2355844 | 2019 | 250 | PV | TBD | 2019-07-15 | 2019-08-06 | 16 |  | 16 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-19 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2355854 | 1720 | 750 | PV | tbd | 2019-07-30 | 2019-08-05 | 4 |  | 4 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-12 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Fairhaven | 2355860 | 2719 | 100 | PV | TBD | 2019-08-05 | 2019-08-05 | 0 |  | 0 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Burlington | 2355861 | 1821 | 1000 | PV & Battery | TBD | 2019-07-30 | 2019-08-01 | 2 |  | 2 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2355862 | 2420 | 22.8 | PV | TBD | 2019-07-25 | 2019-08-06 | 8 |  | 8 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Sudbury | 2355864 | 1776 | 15.2 | PV | TBD | 2019-07-31 | 2019-08-06 | 4 |  | 4 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-13 | Online
NSTAR | Boston | 2355992 | 2119 | 43.2 | PV | TBD | 2019-07-10 | 2019-08-09 | 22 |  | 22 | 2019-08-26 |  | -31183 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-05-13 | Online
NSTAR | South Yarmouth | 2356024 | 2664 | 100 | PV | TBD | 2019-08-07 | 2019-08-07 | 0 |  | 0 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Buzzards Bay | 2356276 | 2532 | 4975 | PV & Battery | TBD | 2019-08-05 | 2019-08-09 | 4 |  | 4 | 2019-08-26 |  | -31183 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2356386 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-27 |  | -31184 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Medway | 2356387 | 2053 | 500 | PV | TBD | 2019-08-08 | 2019-08-15 | 5 |  | 5 | 2019-08-28 |  | -31185 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Burlington | 2356435 | 1803 | 130 | PV | 391-H2 | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-27 |  | -31184 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Stoneham | 2356835 | 1757 | 86.4 | PV | TBD | 2019-08-14 | 2019-08-19 | 3 |  | 3 | 2019-08-29 |  | -31186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Stoneham | 2357040 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-16 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Hopkinton | 2357587 | 1748 | 2770 | PV & Battery | 126-H2 | 2019-08-15 | 2020-08-16 | 261 |  | 261 | 2020-09-06 |  | -31452 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2357591 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-19 | 3 |  | 3 | 2019-09-04 |  | -31190 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-16 | Online
NSTAR | Norfolk | 2357740 | 2056 | 100.8 | PV | TBD | 2019-08-20 | 2019-08-20 | 0 |  | 0 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2357988 | 2360 | 150 | PV | 3-12-12 | 2019-08-13 | 2019-08-13 | 0 |  | 0 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Provincetown | 2357992 | 2657 | 30.39 | PV | 4-96-974 | 2019-08-06 | 2019-08-08 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 2357995 | 2638 | 100 | PV | TBD | 2019-08-01 | 2019-08-09 | 6 |  | 6 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | Wareham | 2358028 | 2571 | 300 | PV | 3-86-966 | 2019-08-20 | 2019-08-22 | 2 |  | 2 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0 |  |  | 2020-11-18 | Online
NSTAR | Sherborn | 2358191 | 1770 | 17.6 | PV & Battery | TBD | 2019-08-07 | 2019-08-13 | 4 |  | 4 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-02-25 | Online
NSTAR | Boston | 2358194 | 2121 | 20 | PV | TBD | 2019-07-10 | 2019-08-09 | 22 |  | 22 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Acusnet | 2358231 | 2743 | 22 | PV | 2-231-231 | 2019-08-22 | 2019-08-26 | 2 |  | 2 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Hopkinton | 2358327 | 1748 | 2770 | PV | TBD | 2019-09-06 |  | -31192 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-16 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Framingham | 2358332 | 1749 | 216 | PV | TBD | 2019-08-19 | 2019-08-21 | 2 |  | 2 | 2019-09-09 |  | -31193 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Dorchester | 2358592 | 2124 | 45.4 | PV | 511-1498H1 | 2019-08-26 | 2019-08-26 | 0 |  | 0 | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Osterville | 2358595 | 2655 | 240 | PV | 4-88-491 | 2019-08-14 | 2019-08-27 | 9 |  | 9 | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Provincetown | 2358697 | 2657 | - |  | TBD | 2019-09-10 |  | -31194 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2358992 | 2571 | 16.59 | PV | 3-83-83 | 2018-04-25 | 2018-06-13 | 35 |  | 35 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-24 | 2018-08-14 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Orleans | 2358998 | 2653 | 86 | PV | 4-83-951 | 2019-08-20 | 2019-08-27 | 5 |  | 5 | 2019-09-13 |  | -31197 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2359000 | 2143 | 2400 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2020-09-30 | Online
NSTAR | Somerville | 2359001 | 2143 | 600 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2359588 | 2571 | 5000 | PV |  | 2019-09-16 | 2019-09-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-04-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Harwich | 2359695 | 2645 | 5000 | PV & Battery | TBD | 2019-08-26 | 2019-08-29 | 3 |  | 3 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2359696 | 2364 | 250 | PV | TBD | 2019-08-23 | 2019-09-03 | 7 |  | 7 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Framingham | 2359697 | 1701 | 43.2 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2359768 | 2601 | 17.6 | PV | 4-80B-514 | 2019-05-06 | 2019-09-03 | 86 |  | 86 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2359934 | 1720 | 100 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2359951 | 2702 | 250 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-18 |  | -31200 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0
NSTAR | East Sandwich | 2360131 | 2537 | 4600 | PV | TBD | 2019-08-28 | 2019-09-04 | 5 |  | 5 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2360135 | 2143 | 1200 | CHP | TBD | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | North Dartmouth | 2360141 | 2747 | 200 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Woburn | 2360146 | 1801 | 240 | PV | TBD | 2019-08-29 | 2019-09-04 | 4 |  | 4 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-10-29 | Online
NSTAR | Cambridge | 2360150 | 2141 | 125 | CHP | TBD | 2019-08-05 | 2019-09-05 | 23 |  | 23 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2360179 | 2381 | 19 | PV | TBD | 2019-07-25 | 2019-09-05 | 30 |  | 30 | 2019-09-20 |  | -31202 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2360354 | 2539 | 286 | PV & Battery | TBD | 2019-08-16 | 2019-09-05 | 14 |  | 14 | 2019-09-23 |  | -31203 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Falmouth | 2360385 | 2536 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Marston Mills | 2360391 | 2635 | 210 | Fuel Cell | 4-88-485 | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | East Wareham | 2360402 | 2538 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Hyannis | 2360467 | 2601 | 262.5 | Fuel Cell | 4-84A-520 | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Sandwich | 2360491 | 2563 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Mashpee | 2360533 | 2649 | 210 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Harwich | 2360563 | 2645 | 262.5 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Freetown | 2360807 | 2717 | 1125 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 2360809 | 2053 | 500 | PV | 65-H2 | 2019-08-22 | 2019-09-09 | 12 |  | 12 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2361120 | 2571 | - |  | TBD | 2019-09-25 |  | -31205 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-05 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2361242 | 2330 | 4999 | PV & Battery | TBD | 2019-09-04 | 2019-09-11 | 5 |  | 5 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2361243 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-13 | 6 |  | 6 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2361417 | 2601 | 24.78 | PV | 4-63-63 | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-18 | [7 empty] | 0 |  | 0 |  |  | 2020-05-19 | Online
NSTAR | Carver | 2361424 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2361428 | 2330 | 2000 | PV & Battery | TBD | 2019-09-06 | 2019-09-13 | 5 |  | 5 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2361432 | 2717 | 4000 | PV |  | 2019-09-26 | 2019-10-02 | 4 | 0 | 4 | 2019-10-07 |  | -31213 | 298 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-05-06 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-10-22 | Private
NSTAR | Hopkinton | 2361481 | 1748 | 333.3 | PV | TBD | 2019-09-03 | 2019-09-12 | 7 |  | 7 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2361879 | 1890 | 25.2 | PV & Battery | 211-H3 | 2019-09-03 | 2019-09-17 | 10 |  | 10 | 2019-10-02 |  | -31210 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Carver | 2361931 | 2330 | - |  | TBD | 2019-10-01 |  | -31209 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Carver | 2361932 | 2330 | 2000 | PV & Battery | TBD | 2019-10-01 |  | -31209 | 0 | 0 | 2019-10-10 | 2019-10-24 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Lexington | 2361940 | 2421 | 250 | PV | TBD | 2019-09-03 | 2019-09-09 | 4 |  | 4 | 2019-10-02 |  | -31210 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-18 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Foxboro | 2362818 | 2035 | 3900 | PV | TBD | 2019-09-18 | 2019-09-23 | 3 |  | 3 | 2019-10-08 |  | -31214 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2363245 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2363249 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2363427 | 2770 | 3500 | PV & Battery | TBD | 2019-09-19 | 2019-09-24 | 3 |  | 3 | 2019-10-09 |  | -31215 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2363669 | 2645 | 210 | PV | 4-95A-597 | 2019-09-13 | 2019-09-19 | 4 |  | 4 | 2019-10-09 |  | -31215 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | New Bedford | 2363671 | 2746 | 200 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2363676 | 2030 | 17.6 | PV & Battery | TBD | 2019-09-20 | 2019-09-26 | 4 |  | 4 | 2019-10-10 |  | -31216 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2019-01-08 | Online
NSTAR | Brewster | 2363697 | 2631 | 2500 | PV | TBD | 2019-09-06 | 2019-09-25 | 13 |  | 13 | 2019-10-10 |  | -31216 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2363855 | 2601 | 112.1 | PV | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-10-15 |  | -31219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-19 | Online
NSTAR | Natick | 2363856 | 1760 | 66 | PV & Battery | 433-H9 | 2019-08-22 | 2019-09-30 | 27 |  | 27 | 2019-10-15 |  | -31219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Holliston | 2364171 | 1746 | - |  | TBD | 2019-10-15 |  | -31219 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-22 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Holliston | 2364172 | 1746 | 240 | PV | TBD | 2019-09-09 | 2019-09-26 | 13 |  | 13 | 2019-10-16 |  | -31220 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Newton | 2364472 | 2459 | 15.2 | PV | TBD | 2019-09-27 | 2019-10-03 | 4 |  | 4 | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Dedham | 2364473 | 2026 | 125 | PV & Battery | 20-H8 | 2019-07-30 | 2019-10-03 | 47 |  | 47 | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Acusnet | 2364982 | 2743 | 500 | PV & Battery |  | 2019-10-21 | 2019-10-22 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 |  | -31227 | 86 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2022-02-09 | Online | [5 empty] | Private
NSTAR | Weston | 2365270 | 2493 | 57.6 | PV | 282-H1 | 2019-10-01 | 2019-10-03 | 2 |  | 2 | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2019-12-11 | [6 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Framingham | 2365418 | 1701 | 199.8 | PV | TBD | 2019-09-27 | 2019-10-09 | 8 |  | 8 | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2365634 | 2360 | 17.6 | PV | TBD | 2019-04-18 | 2019-10-10 | 125 |  | 125 | 2019-10-28 |  | -31228 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Lincoln | 2365635 | 1773 | 1831.4 | PV & Battery | 320-H8 | 2019-09-13 | 2019-10-28 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0
NSTAR | North Harwich | 2365636 | 2645 | 23.2 | PV | 4-92B-92B | 2019-10-07 | 2019-10-10 | 3 |  | 3 | 2019-10-28 |  | -31228 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Wareham | 2366043 | 2571 | 499 | Fuel Cell | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2366044 | 1760 | 43.2 | PV | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2366164 | 2114 | 66 | PV | TBD | 2019-08-23 | 2019-10-10 | 34 |  | 34 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2366298 | 2745 | 200 | PV | 2-79-404 | 2019-09-25 | 2019-10-09 | 10 |  | 10 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | East Falmouth | 2366343 | 2536 | 39.83 | PV | TBD | 2019-09-27 | 2019-10-09 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-13
NSTAR | Watertown | 2366357 | 2472 | 480 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Watertown | 2366405 | 2472 | 99.9 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 2366415 | 2472 | 353 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Orleans | 2366434 | 2653 | 20 | PV | 4-89B-89B | 2019-09-20 | 2019-10-09 | 13 |  | 13 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0 |  |  | 2020-04-08 | Online
NSTAR | Natick | 2366438 | 1760 | 100 | PV | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2366447 | 2740 | 1400 | Fuel Cell | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Falmouth | 2366459 | 2556 | 15.2 | PV | TBD | 2019-08-01 | 2019-10-16 | 54 |  | 54 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Marshfield | 2366460 | 2050 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | 3 |  | 3 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2366461 | 2717 | 2000 | PV | TBD | 2019-08-14 | 2019-10-16 | 45 |  | 45 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2366478 | 1760 | 250 | PV | TBD | 2019-10-31 |  | -31231 | 0 | 0 | 2019-11-05 | 2020-07-01 | 171 | 13 | 158 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Milton | 2366661 | 2186 | 18.2 | PV | TBD | 2019-09-23 | 2019-10-21 | 20 |  | 20 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Kingston | 2366662 | 2364 | 15.3 | PV | 3-15-15 | 2019-09-19 | 2019-10-22 | 23 |  | 23 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2366684 | 2186 | 15.2 | PV | 311-11 | 2019-08-29 |  | -31186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Woburn | 2366729 | 1801 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | 3 |  | 3 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Newton | 2366803 | 2465 | 21.4 | PV | 1713 | 2019-09-25 | 2019-10-22 | 19 |  | 19 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Waltham | 2367388 | 2453 | 480 | PV | TBD | 2019-09-25 | 2019-10-16 | 15 |  | 15 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2367405 | 1890 | 15.2 | PV | 211-H10 | 2019-08-28 | 2019-10-16 | 35 |  | 35 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Boston | 2367475 | 2116 | 1150 | CHP | TBD | 2019-09-25 | 2019-10-18 | 17 |  | 17 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brighton | 2367836 | 2135 | 456 | PV | TBD | 2019-10-07 | 2019-10-22 | 11 |  | 11 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Sherborn | 2367897 | 1770 | 22.8 | PV | 240-H1 | 2019-10-18 | 2019-10-24 | 4 |  | 4 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | East Falmouth | 2367955 | 2536 | 134 | PV | TBD | 2019-10-18 | 2019-10-23 | 3 |  | 3 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Newton | 2367956 | 2459 | 436 | PV | TBD | 2019-07-16 | 2019-10-25 | 73 |  | 73 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-26 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2368084 | 1773 | 129.6 | PV | TBD | 2019-10-28 | 2019-10-28 | 0 |  | 0 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brewster | 2368090 | 2631 | 199.8 | PV | 4-95A-597 | 2018-09-12 | 2018-09-20 | 6 |  | 6 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-14 | [7 empty] | 0 |  | 0 |  |  | 2020-11-10 | Online
NSTAR | Lincoln | 2368534 | 1773 | 23.7 | PV | 282-H1 | 2019-08-05 | 2019-10-28 | 60 |  | 60 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Hatchville | 2368537 | 2536 | 20 | PV | TBD | 2019-10-18 | 2019-10-28 | 6 |  | 6 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2368538 | 2739 | 15.2 | PV | 2-301-301 | 2019-09-10 | 2019-10-28 | 34 |  | 34 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368571 | 2067 | 499 | PV & Battery | TBD | 2019-10-24 | 2019-10-29 | 3 |  | 3 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368605 | 2067 | 999 | PV | TBD | 2019-09-05 | 2019-10-29 | 38 |  | 38 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 2368750 | 1890 | 35.2 | PV | TBD | 2019-10-18 | 2019-10-29 | 7 |  | 7 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-02 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Hyannis | 2368753 | 2601 | 200 | PV | TBD | 2019-10-29 | 2019-10-31 | 2 |  | 2 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Charlestown | 2368889 | 2129 | 250 | PV | TBD | 2019-10-22 | 2019-10-25 | 3 |  | 3 | 2019-11-18 |  | -31243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2368913 | 2459 | 220 | PV | TBD | 2019-09-20 | 2019-11-01 | 30 |  | 30 | 2019-11-18 |  | -31243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2368944 | 2702 | 15.2 | PV | 2-605-605 | 2019-09-13 | 2019-11-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Watertown | 2369438 | 2472 | 700 | PV & Battery | TBD | 2019-10-10 | 2019-11-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2369465 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2019-11-20 |  | -31245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Yarmouth | 2369488 | 2661 | 17.23 | PV | 4-92A-562 | 2019-10-16 | 2019-11-04 | 13 |  | 13 | 2019-11-20 |  | -31245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-03 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Rochester | 2369675 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2369838 | 2601 | 975 | PV |  | 2019-11-20 | 2019-11-27 | 5 | 0 | 5 | 2019-11-28 |  | -31251 | 264 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-06-29 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2019-12-10 | Private
NSTAR | Dorchester | 2369846 | 2122 | 66.6 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2369848 | 1770 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-22 |  | -31247 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Orleans | 2369981 | 2653 | 133.7 | PV | 4-83-952 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-04 | Online
NSTAR | Canton | 2370020 | 2021 | 133.2 | PV | TBD | 2019-11-07 | 2019-11-08 | 1 |  | 1 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370022 | 2458 | 200 | PV | TBD | 2019-08-29 | 2020-09-16 | 274 |  | 274 | 2020-11-22 |  | -31507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Wayland | 2370024 | 1778 | 80 | PV | TBD | 2019-10-28 | 2019-11-08 | 9 |  | 9 | 2019-11-22 |  | -31247 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | New Bedford | 2370116 | 2745 | 100 | PV | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2370417 | 1746 | 437.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370419 | 2458 | 100 | PV | TBD | 2019-11-05 | 2019-11-12 | 5 |  | 5 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2370420 | 2129 | 100 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2370421 | 2458 | 62.5 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chatham | 2370503 | 2633 | 133.3 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Marshfield | 2370516 | 2050 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2370546 | 2021 | 495.8 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2370560 | 1746 | 499 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2370575 | 2081 | 312.5 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370582 | 2607 | 370 | PV | TBD | 2019-10-07 | 2019-11-12 | 26 |  | 26 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2370583 | 1721 | 125 | PV | TBD | 2019-10-31 | 2019-11-12 | 8 |  | 8 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2370630 | 2607 | 660 | PV | TBD | 2019-10-07 | 2019-11-12 | 26 |  | 26 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370666 | 2607 | 5000 | PV & Battery | TBD | 2019-10-07 | 2019-11-13 | 27 |  | 27 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2370690 | 2721 | 3375 | PV | TBD | 2019-10-29 | 2019-11-14 | 12 |  | 12 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 2370768 | 2474 | 19.86 | PV & Battery | 59-1383H1 | 2019-10-31 | 2019-11-19 | 13 |  | 13 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2370777 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2370785 | 2744 | 150 | PV | TBD | 2019-11-07 | 2019-11-19 | 8 |  | 8 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2021-05-18 | Online
NSTAR | Plympton | 2370996 | 2367 | 1560 | PV | 3-51-980 | 2019-10-24 | 2019-11-07 | 10 |  | 10 | 2019-12-03 |  | -31254 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2371039 | 2576 | 100 | PV | TBD | 2019-11-08 | 2019-11-15 | 5 |  | 5 | 2019-12-03 |  | -31254 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2371521 | 2601 | 250 | PV | TBD | 2019-09-30 | 2019-10-28 | 20 |  | 20 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Canton | 2371598 | 2021 | 325 | Natural Gas | 269-1321H2 | 2019-11-14 | 2019-11-14 | 0 |  | 0 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2371602 | 2571 | 166.6 | PV | TBD | 2019-11-08 | 2019-11-15 | 5 |  | 5 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2372155 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2372185 | 2642 | 37.7 | PV | TBD | 2019-11-13 | 2019-11-20 | 5 |  | 5 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Framingham | 2372222 | 1702 | 250 | PV | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2372246 | 2421 | 3000 | CHP | 2-1N11 | 2019-11-18 | 2019-11-19 | 1 |  | 1 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2372255 | 2535 | - |  | TBD | 2019-12-04 |  | -31255 | 0 | 0 | 2019-12-19 | 2020-01-27 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-02-20 | 2020-10-01 | 2020-07-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Dedham | 2372263 | 2026 | 15.2 | PV | TBD | 2019-11-06 | 2019-11-18 | 8 |  | 8 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | South Yarmouth | 2372266 | 2664 | 160 | PV & Battery | TBD | 2019-06-14 | 2019-07-02 | 12 |  | 12 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2372267 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2373333 | 2451 | 144 | PV | 450-H7 | 2019-11-14 | 2019-11-08 | -6 |  | 0 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-27 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 2373342 | 2717 | 17.6 | PV & Battery | 2-102-602 | 2019-11-07 | 2019-11-22 | 11 |  | 11 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2373431 | 2563 | 112.5 | PV | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Sandwich | 2373432 | 2644 | 2500 | PV & Battery | TBD | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2373744 | 1748 | 15.2 | PV | 126-H1 | 2019-11-18 | 2019-11-21 | 3 |  | 3 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2373797 | 2362 | 60 | PV | 3-13-13 | 2019-11-11 | 2019-11-25 | 10 |  | 10 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2373810 | 2653 | 89.39 | PV | TBD | 2019-05-28 | 2019-06-20 | 17 |  | 17 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Centerville | 2373813 | 2632 | 747 | PV & Battery | tbd | 2019-11-15 | 2019-11-20 | 3 |  | 3 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2373814 | 2144 | 133.2 | PV | TBD | 2019-11-18 | 2019-11-27 | 7 |  | 7 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Chelsea | 2373967 | 2150 | 275 | PV & Battery | 488-H2 | 2019-11-08 | 2019-11-26 | 12 |  | 12 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Sandwich | 2374039 | 2563 | 249 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2374058 | 2067 | 200 | PV | 146-H1 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Waltham | 2374169 | 2451 | 250 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2374177 | 2719 | 200 | PV | 2-220-206 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Medfield | 2374353 | 2052 | 17.6 | PV & Battery | TBD | 2019-11-21 | 2019-12-02 | 7 |  | 7 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | West Harwich | 2374665 | 2671 | 25.6 | PV & Battery | 4-85-592 | 2019-11-22 | 2019-12-02 | 6 |  | 6 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2374769 | 2120 | 55.8 | PV | TBD | 2019-12-02 | 2019-12-02 | 0 |  | 0 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Chatham | 2374770 | 2659 | 25 | PV & Battery | 4-95A-606 | 2019-11-15 | 2019-12-02 | 11 |  | 11 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-07 | Online
NSTAR | Mattapoisett | 2374771 | 2739 | - | PV & Battery | TBD | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2375330 | 2739 | 28.7 | PV & Battery | 2-301-301 | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Arlington | 2375571 | 2476 | 275 | PV & Battery | TBD | 2019-11-27 | 2019-12-05 | 6 |  | 6 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Lexington | 2375572 | 2420 | 15.2 | PV | TBD | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Woburn | 2375623 | 1801 | 150 | PV | TBD | 2019-12-02 | 2019-12-05 | 3 |  | 3 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2375708 | 2476 | 15.2 | PV | TBD | 2019-12-03 | 2019-12-10 | 5 |  | 5 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Plymouth | 2375823 | 2360 | 173.46 | PV | TBD | 2019-12-11 | 2019-12-11 | 0 |  | 0 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Falmouth | 2376010 | 2540 | 133.2 | PV | TBD | 2019-12-09 | 2019-12-12 | 3 |  | 3 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Carlisle | 2376068 | 1741 | 17.6 | PV | 512-1399H1 | 2019-10-22 | 2019-12-11 | 36 |  | 36 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0
NSTAR | Cotuit | 2376383 | 2635 | 200 | PV | TBD | 2019-12-12 | 2019-12-16 | 2 |  | 2 | 2019-12-31 |  | -31274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Bedford | 2376385 | 1730 | 25 | PV & Battery | 533-H8 | 2019-12-11 | 2019-12-19 | 6 |  | 6 | 2019-12-31 |  | -31274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Burlington | 2377387 | 1803 | 19.57 | PV & Battery | TBD | 2019-11-22 | 2019-11-26 | 2 |  | 2 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2377419 | 2136 | - |  | TBD | 2020-01-02 |  | -31276 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-06 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wayland | 2377433 | 1778 | 20 | PV & Battery | 342-H1 | 2019-11-07 | 2019-11-22 | 11 |  | 11 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2377476 | 2125 | 72 | PV | TBD | 2019-10-18 | 2019-11-22 | 25 |  | 25 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2377493 | 2453 | 80 | PV | TBD | 2019-12-13 | 2019-12-20 | 5 |  | 5 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Centerville | 2377494 | 2632 | 15.2 | PV | TBD | 2019-11-25 | 2019-12-20 | 19 |  | 19 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Harwich | 2378433 | 2645 | 3150 | PV & Battery | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2378459 | 2364 | 320 | PV | 3-17-916 | 2019-11-13 | 2019-11-25 | 8 |  | 8 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2378471 | 1702 | 15.2 | PV | 274-H1 | 2019-12-02 | 2019-12-12 | 8 |  | 8 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Medway | 2378489 | 2053 | 230 | PV | TBD | 2019-11-20 | 2019-12-13 | 17 |  | 17 | 2020-01-23 |  | -31291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | South Dennis | 2378744 | 2660 | 30.72 | PV | TBD | 2019-11-20 | 2019-11-26 | 4 |  | 4 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2378798 | 2563 | 490 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Roxbury | 2378813 | 2132 | 43.2 | PV | TBD | 2019-12-11 | 2019-12-19 | 6 |  | 6 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Carver | 2378857 | 2330 | 2500 | PV & Battery | TBD | 2019-11-19 | 2019-12-23 | 24 |  | 24 | 2020-01-07 |  | -31279 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2378858 | 2532 | 5000 | PV & Battery | TBD | 2019-11-21 | 2019-12-23 | 22 |  | 22 | 2020-01-07 |  | -31279 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2380743 | 2719 | 200 | PV | 2-221-221 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Waltham | 2380747 | 2451 | 16 | Battery | 450-H3 | 2019-11-27 | 2019-12-02 | 3 |  | 3 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2380929 | 2421 | 133.3 | PV | 533-H1 | 2019-12-02 | 2019-12-05 | 3 |  | 3 | 2020-01-09 |  | -31281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2380935 | 1748 | 250 | PV |  | 2020-01-08 | 2020-01-09 | 1 | 0 | 1 | 2020-01-10 | 2020-05-08 | 85 | 4 | 81 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 |  | 2020-08-12 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Onset | 2381115 | 2558 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-13 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Marshfield | 2381120 | 2048 | 4600 | PV & Battery | TBD | 2019-12-18 | 2019-12-26 | 6 |  | 6 | 2020-01-10 |  | -31282 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2381326 | 2180 | 20 | PV & Battery | 375-H8 | 2019-11-18 | 2019-12-26 | 28 |  | 28 | 2020-01-13 |  | -31283 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Westport | 2381437 | 2790 | 4000 | PV & Battery | TBD | 2019-11-19 | 2019-12-30 | 29 |  | 29 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | 2381519 | 2472 | 100 | PV | 467-H5 | 2019-12-20 | 2019-12-20 | 0 |  | 0 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Lexington | 2381543 | 2421 | 130 | PV | 533-H1 | 2019-12-10 | 2019-12-13 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2381555 | 2453 | 748 | PV | TBD | 2019-12-09 | 2019-12-12 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2381556 | 2136 | 19 | PV | 60-1409H1 | 2019-10-31 | 2019-12-02 | 22 |  | 22 | 2020-01-15 |  | -31285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Walpole | 2381558 | 2032 | 23.8 | PV | TBD | 2019-12-11 | 2019-12-16 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2381571 | 1801 | 3623 | PV | TBD | 2019-12-05 | 2019-12-09 | 2 |  | 2 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-24 | [7 empty] | 0 |  | 0
NSTAR | Bourne | 2381610 | 2532 | 5000 | PV & Battery | TBD | 2019-12-13 | 2019-12-23 | 6 |  | 6 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2381700 | 2770 | 21.4 | PV | TBD | 2019-11-06 | 2019-12-30 | 38 |  | 38 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2381703 | 2360 | 249.9 | PV & Battery | TBD | 2019-12-30 | 2019-12-30 | 0 |  | 0 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2381861 | 2648 | 40 | PV | TBD | 2019-12-19 | 2020-01-02 | 10 |  | 10 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Carver | 2382007 | 2330 | 50 | PV | TBD | 2019-12-26 | 2020-01-06 | 7 |  | 7 | 2020-01-17 |  | -31287 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Needham | 2382008 | 2494 | 17 | PV & Battery | 148-08 | 2019-12-05 | 2020-01-06 | 22 |  | 22 | 2020-01-17 |  | -31287 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Lexington | 2382228 | 2421 | 22.72 | PV | 320-H2 | 2019-12-20 | 2020-01-02 | 9 |  | 9 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Needham | 2382255 | 2494 | 17.25 | PV | 148-H4 | 2019-12-09 | 2020-01-02 | 18 |  | 18 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | East Freetown | 2382455 | 2717 | 25 | PV & Battery | TBD | 2020-01-06 | 2020-01-06 | 0 |  | 0 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2382474 | 2571 | 66.6 | PV | 3-84-960 | 2019-12-19 | 2020-01-06 | 12 |  | 12 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2383462 | 2053 | 15.2 | PV | 130-H2 | 2019-12-18 | 2019-12-20 | 2 |  | 2 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 2383471 | 1741 | 17.6 | PV & Battery | 512-1399H1 | 2019-12-13 | 2020-01-13 | 21 |  | 21 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hyde Park | 2383520 | 2136 | 333.2 | PV | TBD | 2020-01-02 | 2020-01-13 | 7 |  | 7 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Dennis | 2383632 | 2670 | 20 | PV & Battery | 4-92B-571 | 2020-01-04 | 2020-01-13 | 6 |  | 6 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-05-21
NSTAR | South Dennis | 2383634 | 2660 | 37.6 | PV | TBD | 2020-01-06 | 2020-01-13 | 5 |  | 5 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | North Falmouth | 2383638 | 2556 | 15.2 | PV | 4-78-78 | 2020-01-08 | 2020-01-15 | 5 |  | 5 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Watertown | 2383645 | 2472 | 52.2 | PV | TBD | 2020-01-06 | 2020-01-07 | 1 |  | 1 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Westport | 2383646 | 2790 | 4000 | PV & Battery | TBD | 2019-12-20 | 2020-01-08 | 13 |  | 13 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2384268 | 2642 | 10 | PV & Battery | 4-94A-633 | 2019-11-22 | 2020-01-16 | 39 |  | 39 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2384357 | 2453 | 40 | PV | TBD | 2019-06-14 | 2020-01-21 | 157 |  | 157 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marshfield | 2384377 | 2050 | 16.2 | PV | 3-24A-971 | 2019-09-18 | 2019-12-11 | 60 |  | 60 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Brookline | 2384381 | 2446 | 38.5 | PV | TBD | 2020-01-16 | 2020-01-17 | 1 |  | 1 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2384383 | 2420 | 17 | PV & Battery | 320-H5XY | 2020-01-15 | 2020-01-22 | 5 |  | 5 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | New Bedford | 2384474 | 2746 | 133 | PV |  | 2020-02-04 | 2020-02-07 | 3 | 0 | 3 | 2020-02-13 | 2020-02-28 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 |  | 2020-09-08 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Woburn | 2384521 | 1801 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-09-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Provincetown | 2384542 | 2657 | 70 | PV | 4-96-675 | 2020-01-15 | 2020-01-22 | 5 |  | 5 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hopkinton | 2384545 | 1748 | 111.5 | PV & Battery | 126-H2 | 2019-12-10 | 2020-01-02 | 17 |  | 17 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-31
NSTAR | Wareham | 2384553 | 2538 | 4995 | PV & Battery | TBD | 2019-12-30 | 2020-01-06 | 5 |  | 5 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2384624 | 1702 | 440 | PV | TBD | 2020-01-21 | 2020-01-23 | 2 |  | 2 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-12 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Freetown | 2384761 | 2717 | 2000 | PV & Battery | TBD | 2020-01-07 | 2020-01-08 | 1 |  | 1 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2384826 | 2451 | 166.6 | PV | TBD | 2019-12-30 | 2020-01-08 | 7 |  | 7 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2384945 | 2653 | 60 | PV |  | 2020-02-06 | 2020-02-11 | 3 | 0 | 3 | 2020-02-11 | 2020-02-12 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | 2020-03-02 | 2020-09-10 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2020-10-06 | Online | [5 empty] | Private
NSTAR | South Yarmouth | 2384954 | 2664 | 437.5 | PV | TBD | 2019-12-19 | 2020-01-06 | 12 |  | 12 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online
NSTAR | Walpole | 2384980 | 2081 | 30.2 | PV & Battery | 146-H4 | 2020-01-10 | 2020-01-26 | 10 |  | 10 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Dorchester | 2384991 | 2122 | 100 | PV & Battery | 6702 | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-11 |  | -31304 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Burlington | 2385267 | 1803 | 19.76 | PV | 346-1395H1 | 2020-01-17 | 2020-01-27 | 6 |  | 6 | 2020-02-11 |  | -31304 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | West Tisbury | 2385299 | 2575 | 25 | PV | TBD | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-18 | Online
NSTAR | Watertown | 2385313 | 2472 | 43.2 | PV | 282-H8 | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Westwood | 2385414 | 2090 | 25 | PV & Battery | 469-H2 | 2020-01-21 | 2020-01-28 | 5 |  | 5 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Acton | 2385734 | 1720 | 200 | PV | TBD | 2019-12-12 | 2020-01-31 | 36 |  | 36 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2385800 | 1702 | 187.5 | PV | TBD | 2020-01-30 | 2020-01-30 | 0 |  | 0 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-12 | Online
NSTAR | Needham | 2385802 | 2494 | 460 | PV | TBD | 2019-12-09 | 2020-01-30 | 38 |  | 38 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online
NSTAR | Falmouth | 2386189 | 2540 | 34.6 | PV & Battery | 4-78-420 | 2020-01-22 | 2020-02-03 | 8 |  | 8 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2386275 | 2657 | 28.8 | PV | TBD | 2020-01-30 | 2020-02-03 | 2 |  | 2 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 2386320 | 2332 | 66.6 | PV | TBD | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Barnstable | 2386368 | 2630 | 240 | PV | 4-84B-510 | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2386391 | 2745 | 30 | PV | 2-137-137 | 2019-12-03 | 2020-02-04 | 45 |  | 45 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Ashland | 2386559 | 1721 | 10 | PV & Battery | 274-H1 | 2020-01-23 | 2020-02-04 | 8 |  | 8 | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Wareham | 2386584 | 2538 | 30 | PV | 3-84-960 | 2019-12-03 | 2020-02-04 | 45 |  | 45 | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Dedham | 2386594 | 2026 | 10 | PV & Battery | 20-H7 | 2020-01-29 | 2020-02-04 | 4 |  | 4 | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2387342 | 1746 | 4999 | PV & Battery | TBD | 2019-12-26 | 2020-02-06 | 30 |  | 30 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-12-05 | Online
NSTAR | Marshfield | 2387378 | 2050 | 15.1 | PV | 3-24B-24B | 2019-12-23 | 2020-02-06 | 33 |  | 33 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Bourne | 2387476 | 2532 | 43.2 | PV | 4-86-402 | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-02-26 |  | -31315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Winchester | 2387543 | 1890 | 20 | PV | 211-H10 | 2020-04-14 | 2020-02-21 | -39 |  | 0 | 2020-03-02 |  | -31318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Needham | 2387570 | 2494 | 7 | PV & Battery | 148-H4 | 2020-01-06 | 2020-01-16 | 8 |  | 8 | 2020-02-27 |  | -31316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Boston | 2387593 | 2210 | 233.3 | PV | TBD | 2019-12-19 | 2020-02-14 | 41 |  | 41 | 2020-02-27 |  | -31316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2387744 | 2601 | 115.05 | PV | TBD | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-03-02 |  | -31318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | Brookline | 2387929 | 2467 | 20 | PV & Battery | 496-H5 | 2020-01-16 | 2020-02-14 | 21 |  | 21 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | East Freetown | 2387969 | 2717 | 15.2 | PV | 2-107-107 | 2020-01-22 | 2020-02-18 | 19 |  | 19 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2387970 | 2649 | 499.73 | PV | TBD | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-17 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2387981 | 2420 | 20 | PV & Battery | 533-H3 | 2019-12-02 | 2020-02-14 | 54 |  | 54 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | Walpole | 2388024 | 2021 | 20 | PV | TBD | 2020-02-06 | 2020-02-14 | 6 |  | 6 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Mattapoisett | 2388535 | 2739 | 800 | PV | TBD | 2020-01-30 | 2020-02-18 | 13 |  | 13 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388537 | 2364 | 2760 | PV | TBD | 2020-01-22 | 2020-02-18 | 19 |  | 19 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2388583 | 2125 | 366.3 | PV | TBD | 2020-02-18 | 2020-02-18 | 0 |  | 0 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388590 | 2364 | 66.6 | PV | TBD | 2020-02-14 | 2020-02-18 | 2 |  | 2 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Winchester | 2388617 | 1890 | 17.6 | PV & Battery | TBD | 2020-01-16 | 2020-02-19 | 24 |  | 24 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-12 | Online
NSTAR | Needham | 2388633 | 2492 | 18.8 | PV | 148-06 | 2019-12-02 | 2020-02-19 | 57 |  | 57 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2388772 | 2125 | 121.22 | PV | TBD | 2020-02-10 | 2020-02-19 | 7 |  | 7 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Plympton | 2388822 | 2367 | 15.2 | PV | TBD | 2020-02-10 | 2020-02-21 | 9 |  | 9 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Framingham | 2388879 | 1702 | 400 | PV | TBD | 2020-01-21 | 2020-02-24 | 24 |  | 24 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Newton | 2388945 | 2378 | 2400 | CHP | TBD | 2019-12-20 | 2020-02-20 | 44 |  | 44 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2389165 | 2655 | 23.3 | PV & Battery | 4-80A-490 | 2019-11-04 | 2020-02-21 | 79 |  | 79 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2389174 | 2332 | 16.7 | PV | TBD | 2020-02-18 | 2020-02-21 | 3 |  | 3 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Falmouth | 2389176 | 2540 | 21.58 | PV & Battery | 4-72-433 | 2019-12-18 | 2020-02-24 | 48 |  | 48 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2389199 | 2540 | 958 | PV & Battery | TBD | 2020-02-18 | 2020-02-24 | 4 |  | 4 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2389233 | 1776 | 20 | PV & Battery | TBD | 2020-02-07 | 2020-02-24 | 11 |  | 11 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-10-08 | Online
NSTAR | Ashland | 2389241 | 1721 | 20 | Battery | 519-175H1 | 2020-01-15 | 2020-02-24 | 28 |  | 28 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2389247 | 2420 | 10 | PV & Battery | TBD | 2020-01-15 | 2020-02-24 | 28 |  | 28 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Wayland | 2389401 | 1778 | 20 | PV | TBD | 2020-02-20 | 2020-02-25 | 3 |  | 3 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Boston | 2389473 | 2135 | 1150 | PV & Battery | TBD | 2020-01-29 | 2020-02-25 | 19 |  | 19 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | Natick | 2389477 | 1760 | 133.2 | PV | TBD | 2020-03-03 | 2020-03-04 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online
NSTAR | Barnstable | 2389479 | 2630 | 66.6 | PV | TBD | 2020-02-24 | 2020-02-25 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2389481 | 1890 | 17.6 | PV & Battery | 211-H1 | 2020-02-20 | 2020-02-25 | 3 |  | 3 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Edgartown | 2389485 | 2539 | 22.8 | PV | TBD | 2019-12-26 | 2020-02-25 | 43 |  | 43 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Acton | 2389509 | 1720 | 27 | Battery | 416-H4 | 2020-02-21 | 2020-02-25 | 2 |  | 2 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2389511 | 2067 | 480 | PV | TBD | 2020-02-24 | 2020-02-25 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online
NSTAR | Lexington | 2389932 | 2420 | 25 | PV & Battery | TBD | 2020-02-20 | 2020-02-27 | 5 |  | 5 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-10-20 | Online
NSTAR | Chatham | 2390124 | 2633 | 18.7 | PV & Battery | TBD | 2020-02-28 | 2020-03-03 | 2 |  | 2 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-07-16 | Online
NSTAR | Boston | 2390327 | 2118 | 557.5 | PV & Battery | 4912 | 2020-02-10 | 2020-03-06 | 19 |  | 19 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Bellingham | 2390335 | 2019 | 15.2 | PV | 65-H4 | 2020-03-05 | 2020-03-09 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2390546 | 1702 | 100 | PV | TBD | 2020-03-02 | 2020-03-04 | 2 |  | 2 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 2390669 | 1778 | 17.6 | PV & Battery | 342-H1 | 2020-02-25 | 2020-03-05 | 7 |  | 7 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 2390776 | 2670 | 233.3 | PV | TBD | 2020-03-06 | 2020-03-06 | 0 |  | 0 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2390944 | 2090 | 10 | PV & Battery | 148-H3 | 2020-02-18 | 2020-03-10 | 15 |  | 15 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | North Dartmouth | 2390961 | 2747 | 150 | PV | TBD | 2020-03-09 | 2020-03-09 | 0 |  | 0 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Weston | 2391087 | 2493 | 25 | PV & Battery | TBD | 2020-02-25 | 2020-03-09 | 9 |  | 9 | 2020-03-25 |  | -31335 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Falmouth | 2391172 | 2536 | 4990 | PV & Battery | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2391210 | 2645 | 23 | PV |  | 2020-03-24 |  | -31334 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-10-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Harwich | 2391216 | 2645 | 23 | PV | TBD | 2020-03-06 | 2020-03-12 | 4 |  | 4 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | East Falmouth | 2391234 | 2536 | 3000 | PV & Battery | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2391270 | 2601 | 133.2 | PV | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Cataumet | 2391363 | 2534 | 29.23 | PV & Battery | 4-78-410 | 2020-02-21 | 2020-03-11 | 13 |  | 13 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Newton | 2391435 | 2459 | - | Battery | 292-H8 | 2020-01-15 | 2020-03-12 | 41 |  | 41 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2391457 | 2540 | 15.2 | PV | 4-72-72 | 2020-03-10 | 2020-03-12 | 2 |  | 2 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2391467 | 1746 | 20 | PV & Battery | TBD | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chelsea | 2391483 | 2150 | 199.8 | PV | TBD | 2020-03-10 | 2020-03-12 | 2 |  | 2 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2391527 | 1776 | 17.6 | PV & Battery | 342-H7 | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Falmouth | 2391570 | 2540 | 24.6 | PV & Battery | 4-107-832 | 2020-03-05 | 2020-03-12 | 5 |  | 5 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Holliston | 2391752 | 1746 | 200 | PV | TBD | 2020-02-27 | 2020-03-16 | 12 |  | 12 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2391763 | 1730 | 15.2 | PV | TBD | 2020-01-15 | 2020-03-16 | 43 |  | 43 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2391862 | 1803 | 19.12 | PV & Battery | TBD | 2020-03-09 | 2020-03-16 | 5 |  | 5 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-28 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | East Freetown | 2391908 | 2717 | 25 | PV | TBD | 2020-03-16 | 2020-03-16 | 0 |  | 0 | 2020-03-31 |  | -31339 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2391934 | 2571 | 28.8 | PV | TBD | 2020-03-16 | 2020-03-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | South Chatham | 2392011 | 2659 | 24.92 | PV & Battery | 4-95A-606 | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2392014 | 2557 | 1500 | PV |  | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 2020-04-08 |  | -31345 | 179 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-03 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-04-17 | Private
NSTAR | Sandwich | 2392033 | 2563 | 250 | PV | TBD | 2020-02-27 | 2020-03-16 | 12 |  | 12 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2392113 | 2743 | 4000 | PV & Battery | TBD | 2020-03-12 | 2020-03-18 | 4 |  | 4 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2392127 | 2054 | 250 | PV | TBD | 2020-03-18 | 2020-03-18 | 0 |  | 0 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2392184 | 1730 | 20 | PV | 533-H8 | 2020-03-17 | 2020-03-18 | 1 |  | 1 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2392188 | 2132 | 344.8 | PV & Battery | TBD | 2020-03-05 | 2020-03-18 | 9 |  | 9 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | Walpole | 2392586 | 2081 | 2000 | PV & Battery | TBD | 2020-03-06 | 2020-03-20 | 10 |  | 10 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2392595 | 1760 | 456 | PV & Battery | TBD | 2020-03-05 | 2020-03-20 | 11 |  | 11 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Marshfield | 2392617 | 2050 | 500 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2392719 | 2050 | 250 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Online
NSTAR | Natick | 2392730 | 1760 | 180 | PV | TBD | 2020-03-02 | 2020-03-20 | 14 |  | 14 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Arlington | 2392742 | 2474 | 17.6 | PV & Battery | TBD | 2020-02-20 | 2020-03-18 | 19 |  | 19 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Harwich | 2392746 | 2645 | 4990 | PV & Battery | TBD | 2020-03-16 | 2020-03-20 | 4 |  | 4 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2392870 | 2576 | 133.2 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2392879 | 2134 | 36 | CHP | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-07 |  | -31344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Duxbury | 2392885 | 2332 | 4000 | PV & Battery | TBD | 2020-03-20 | 2020-03-23 | 1 |  | 1 | 2020-04-07 |  | -31344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2392889 | 2601 | 72 | PV | TBD | 2020-03-17 | 2020-03-20 | 3 |  | 3 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2392993 | 2360 | 144 | PV | TBD | 2020-03-20 | 2020-03-23 | 1 |  | 1 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Mashpee | 2393455 | 2649 | 5000 | PV & Battery | TBD | 2020-02-20 | 2020-03-27 | 26 |  | 26 | 2020-04-14 |  | -31349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2393720 | 2770 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-11-17 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Wareham | 2393736 | 2571 | 8500 | PV |  | 2020-04-13 | 2020-12-21 | 180 | 0 | 180 | 2020-12-21 |  | -31528 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-05-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Wareham | 2393742 | 2571 | 8500 | PV |  | 2020-04-13 |  | -31348 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-03-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Stoneham | 2393943 | 2180 | 486 | PV | TBD | 2020-03-25 | 2020-03-31 | 4 |  | 4 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2393958 | 2719 | 245 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2394000 | 1741 | 19.5 | PV | TBD | 2020-01-17 | 2020-03-31 | 52 |  | 52 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Charlestown | 2394014 | 2129 | 4990 | PV | TBD | 2020-03-27 | 2020-03-31 | 2 |  | 2 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2394160 | 2081 | 1000 | PV | TBD | 2020-03-27 | 2020-04-01 | 3 |  | 3 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394184 | 2740 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394211 | 2740 | 250 | PV | TBD | 2020-03-20 | 2020-03-31 | 7 |  | 7 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2394461 | 2743 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-17 | Online
NSTAR | New Bedford | 2394463 | 2745 | 133.3 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Boston | 2394534 | 2109 | 750 | CHP | TBD | 2020-04-06 | 2020-04-06 | 0 |  | 0 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2394648 | 2458 | 25 | PV & Battery | TBD | 2020-03-20 | 2020-03-31 | 7 |  | 7 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Plympton | 2394682 | 2367 | 4975 | PV |  | 2020-04-20 |  | -31353 | 0 | 0 | 2020-04-25 |  | -31357 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | New Bedford | 2394787 | 2745 | 100 | PV | TBD | 2020-04-06 | 2020-04-08 | 2 |  | 2 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Falmouth | 2394862 | 2536 | 3500 | PV & Battery | TBD | 2020-03-27 | 2020-04-08 | 8 |  | 8 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2394867 | 2536 | 3500 | PV |  | 2020-04-21 |  | -31354 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | South Dennis | 2395010 | 2368 | 112.5 | PV | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-04-30 |  | -31361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | East Freetown | 2395036 | 2717 | 149.3 | PV | TBD | 2020-03-26 | 2020-04-06 | 7 |  | 7 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Wareham | 2395041 | 2571 | 216 | PV | TBD | 2020-03-27 | 2020-04-13 | 11 |  | 11 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-28 | Online
NSTAR | Provincetown | 2395067 | 2657 | 495.8 | PV | TBD | 2020-04-08 | 2020-04-08 | 0 |  | 0 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2395093 | 2462 | 17.6 | PV & Battery | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Boston | 2395099 | 2134 | 40 | PV | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Canton | 2395122 | 2021 | 15.2 | PV | TBD | 2020-03-18 | 2020-04-09 | 16 |  | 16 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Rochester | 2395209 | 2770 | 999 | PV |  | 2020-04-23 | 2020-04-27 | 2 | 0 | 2 | 2020-04-28 |  | -31359 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Dennis | 2395295 | 2638 | 16.6 | PV & Battery | 4-90-90 | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Acton | 2395297 | 1720 | 240 | PV | TBD | 2020-04-08 | 2020-04-15 | 5 |  | 5 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Wareham | 2395408 | 2576 | 470 | PV | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2395414 | 2648 | 16.38 | PV | TBD | 2020-04-01 | 2020-04-09 | 6 |  | 6 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Boston | 2395480 | 2136 | 99.9 | PV | TBD | 2020-04-06 | 2020-04-13 | 5 |  | 5 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2395483 | 2717 | 149.3 | PV | TBD | 2020-03-09 | 2020-04-10 | 24 |  | 24 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Hyannis | 2395561 | 2601 | 50 | PV | 4-80B-80B | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2395617 | 2118 | 484 | PV | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2395659 | 1701 | 57.6 | PV | TBD | 2020-04-20 | 2020-04-20 | 0 |  | 0 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Milton | 2395800 | 2186 | 57.6 | PV | TBD | 2020-02-13 |  | -31306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Brewster | 2395844 | 2631 | 16.28 | PV & Battery | 4-89A-553 | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-04-30 |  | -31361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Falmouth | 2395855 | 2536 | 4990 | PV |  | 2020-04-29 | 2020-04-30 | 1 | 0 | 1 | 2020-04-30 |  | -31361 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-04 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-05-01 | Private
NSTAR | Plymouth | 2395947 | 2360 | 5466 | PV & Battery | TBD | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hatchville | 2395965 | 2536 | 3300 | PV |  | 2020-04-30 | 2020-04-30 | 0 | 0 | 0 | 2020-04-30 |  | -31361 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-05-01 | Private
NSTAR | Falmouth | 2395998 | 2536 | 3000 | PV |  | 2020-04-30 | 2020-05-01 | 1 | 0 | 1 |  |  | 0 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-05-01 | Private
NSTAR | Falmouth | 2396002 | 2540 | 958 | PV |  | 2020-04-30 |  | -31361 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | East Boston | 2396083 | 2128 | 1700 | Steam Turbine |  | 2020-05-01 |  | -31362 | 0 | 0 | 2020-05-01 |  | -31362 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Gov't
NSTAR | Framingham | 2396140 | 1702 | 400 | PV | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 2396188 | 2535 | 20.95 | PV | TBD | 2020-04-06 | 2020-04-27 | 15 |  | 15 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Plymouth | 2396211 | 2360 | 1000 | PV & Battery | TBD | 2020-04-15 | 2020-04-16 | 1 |  | 1 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2396597 | 2631 | 86.4 | PV | TBD | 2020-05-04 |  | -31363 | 0 | 0 | 2020-05-06 | 2020-05-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-05-13 | 2020-05-12 | 2020-12-09 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Gov't
NSTAR | Brewster | 2396639 | 2631 | 66.6 | PV | TBD | 2020-03-13 | 2020-04-20 | 26 |  | 26 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2396686 | 1746 | 14 | Battery | 274-H5 | 2020-02-18 | 2020-04-20 | 44 |  | 44 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2396845 | 2563 | 133.3 | PV | TBD | 2020-03-17 | 2020-04-20 | 24 |  | 24 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2397127 | 2536 | 18.85 | PV | TBD | 2020-04-23 | 2020-04-27 | 2 |  | 2 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-26 | Online
NSTAR | Oak Bluffs | 2397130 | 2557 | 300 | PV | 4-99-224 | 2020-03-18 | 2020-04-22 | 25 |  | 25 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online
NSTAR | Hopkinton | 2397168 | 1748 | 3900 | PV & Battery | TBD | 2020-02-10 | 2020-04-23 | 53 |  | 53 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2397176 | 2652 | 35 | PV | TBD | 2020-05-07 |  | -31366 | 0 | 0 | 2020-06-25 | 2020-06-26 | 1 | 15 | -14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-07-15 |  | 2020-12-14 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Natick | 2397214 | 1760 | 13.92 | PV | 240-H1 | 2020-03-09 | 2020-04-22 | 32 |  | 32 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Waltham | 2397225 | 2453 | 80 | PV | TBD | 2020-03-20 | 2020-04-23 | 24 |  | 24 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Online
NSTAR | Stoneham | 2397255 | 2180 | 15.2 | PV | TBD | 2020-03-17 | 2020-03-27 | 8 |  | 8 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2397442 | 2030 | 17.7 | PV | 456-H3 | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Waltham | 2397603 | 2453 | 46 | PV | TBD | 2020-04-16 | 2020-04-27 | 7 |  | 7 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2397610 | 2657 | 54 | PV | TBD | 2020-04-06 | 2020-04-23 | 13 |  | 13 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Framingham | 2397729 | 1702 | 240 | PV | TBD | 2020-04-23 | 2020-04-27 | 2 |  | 2 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2397818 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397824 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397836 | 1760 | 330 | PV |  | 2020-05-12 |  | -31369 | 0 | 0 | 2020-05-18 |  | -31373 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-17 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-04-25 | Online | [5 empty] | Private
NSTAR | Holliston | 2397865 | 1746 | 200 | PV |  | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-13 |  | 2020-12-18 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2021-03-19 | Online | [5 empty] | Private
NSTAR | Canton | 2397898 | 2021 | 499 | PV & Battery | TBD | 2020-04-29 | 2020-04-30 | 1 |  | 1 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2398079 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2398156 | 2645 | 22.2 | PV | 4-95A-95A | 2020-04-27 | 2020-04-29 | 2 |  | 2 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2398168 | 2747 | 15.2 | PV | 2-532-532 | 2020-03-16 | 2020-04-30 | 33 |  | 33 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Natick | 2398175 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2398227 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-04-29 |  | -31360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | East Falmouth | 2398257 | 2536 | 500 | PV | TBD | 2020-04-27 | 2020-04-30 | 3 |  | 3 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2398274 | 1748 | 24.28 | PV | TBD | 2020-04-09 | 2020-04-29 | 14 |  | 14 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Cambridge | 2398561 | 2138 | 200 | PV | TBD | 2020-03-27 | 2020-04-30 | 24 |  | 24 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brewster | 2398609 | 2631 | 4999 | PV & Battery | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2398639 | 1773 | 43.2 | PV | 240-H1 | 2020-04-15 | 2020-05-04 | 13 |  | 13 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | Somerville | 2398711 | 2143 | 211 | PV | TBD | 2020-05-05 | 2020-05-08 | 3 |  | 3 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Lincoln | 2398773 | 1773 | 86.4 | PV | TBD | 2020-04-15 | 2020-05-04 | 13 |  | 13 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | South Dartmouth | 2398833 | 2748 | 20.8 | PV & Battery | 2-53-65 | 2020-04-30 | 2020-05-05 | 3 |  | 3 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2398880 | 2360 | 7.6 | PV & Battery | TBD | 2020-04-29 | 2020-04-29 | 0 |  | 0 | 2020-04-29 |  | -31360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Framingham | 2398893 | 1701 | - |  | TBD | 2020-05-20 |  | -31375 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-28 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Holliston | 2399007 | 1746 | 300 | PV | TBD | 2020-04-20 | 2020-05-13 | 17 |  | 17 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2399041 | 2717 | 25 | PV | TBD | 2020-05-07 | 2020-05-07 | 0 |  | 0 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2399048 | 2744 | 15.2 | PV | TBD | 2020-05-05 | 2020-05-13 | 6 |  | 6 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Framingham | 2399085 | 1702 | 22 | PV | TBD | 2020-05-21 |  | -31376 | 0 | 0 | 2020-05-26 | 2020-06-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-29 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Duxbury | 2399108 | 2332 | 25 | PV & Battery | TBD | 2020-04-29 | 2020-05-08 | 7 |  | 7 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2399178 | 2601 | 460 | PV | 4-80B-80B | 2020-04-16 | 2020-04-20 | 2 |  | 2 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2399192 | 2631 | 4999 | PV & Battery | TBD | 2020-05-05 | 2020-05-08 | 3 |  | 3 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2399437 | 2660 | 15.2 | PV | TBD | 2020-04-01 | 2020-05-18 | 33 |  | 33 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Natick | 2399566 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2399596 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2399599 | 2645 | 240 | PV | TBD | 2020-04-29 | 2020-05-13 | 10 |  | 10 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2399607 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Hyannis | 2399725 | 2601 | 73.3 | PV | TBD | 2020-04-06 | 2020-05-13 | 27 |  | 27 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Hyannis | 2399742 | 2601 | 60 | PV | TBD | 2020-04-08 | 2020-05-13 | 25 |  | 25 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Plymouth | 2399743 | 2360 | 17.6 | PV | 3-72-940 | 2020-05-08 | 2020-05-13 | 3 |  | 3 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Cambridge | 2399827 | 2141 | 60 | CHP | TBD | 2020-02-04 | 2020-05-13 | 71 |  | 71 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online
NSTAR | Acusnet | 2399839 | 2743 | 5000 | PV | TBD | 2019-09-13 | 2020-05-13 | 173 |  | 173 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 2399904 | 2030 | 35.2 | PV | TBD | 2020-05-05 | 2020-05-13 | 6 |  | 6 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Sandwich | 2400107 | 2653 | 150 | PV | TBD | 2020-05-08 | 2020-05-18 | 6 |  | 6 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Freetown | 2400205 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | 14 |  | 14 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | 2400260 | 2649 | 1490 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plympton | 2400919 | 2367 | 149.3 | PV | TBD | 2020-05-20 | 2020-05-20 | 0 |  | 0 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2400943 | 2653 | 499 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Natick | 2400946 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Mashpee | 2400979 | 2649 | 2075 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2401009 | 2653 | 200 | PV | TBD | 2020-04-30 | 2020-05-18 | 12 |  | 12 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2401149 | 2132 | 149.8 | PV | TBD | 2020-04-27 | 2020-05-26 | 21 |  | 21 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2401235 | 2649 | 730 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2401247 | 2738 | 700 | PV & Battery | TBD | 2020-04-30 | 2020-05-18 | 12 |  | 12 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2401361 | 2537 | 499 | PV | TBD | 2020-05-04 | 2020-05-20 | 12 |  | 12 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2401405 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | 14 |  | 14 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2401687 | 2746 | 499 | PV | TBD | 2020-05-18 | 2020-05-20 | 2 |  | 2 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-05 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2401948 | 1746 | 216 | PV | TBD | 2020-05-15 | 2020-05-26 | 7 |  | 7 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Lincoln | 2401979 | 1773 | 22.6 | PV & Battery | TBD | 2020-05-18 | 2020-05-28 | 8 |  | 8 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Chatham | 2402094 | 2633 | 22.32 | PV | TBD | 2020-05-26 | 2020-05-28 | 2 |  | 2 | 2020-06-11 |  | -31391 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-10 | Online
NSTAR | Falmouth | 2402100 | 2540 | 133 | PV |  | 2020-06-11 | 2020-06-15 | 2 | 0 | 2 | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | 2020-07-06 | 2020-12-15 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2020-08-19 | Online | [5 empty] | Private
NSTAR | Waltham | 2402126 | 2451 | 375 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-29 | [7 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2402135 | 2747 | 149.3 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2402181 | 2132 | 226.9 | PV | TBD | 2020-04-27 | 2020-05-26 | 21 |  | 21 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2402255 | 1721 | 10 | PV & Battery | TBD | 2020-05-26 | 2020-06-01 | 4 |  | 4 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Kingston | 2402374 | 2364 | 499 | PV |  | 2020-06-15 | 2020-06-16 | 1 | 0 | 1 | 2020-06-30 |  | -31404 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Centerville | 2402410 | 2632 | 7.6 | PV | 4-82-508 | 2020-05-18 | 2020-06-03 | 12 |  | 12 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-04-21
NSTAR | Carver | 2402730 | 2330 | 200 | PV | TBD | 2020-05-15 | 2020-06-03 | 13 |  | 13 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2402767 | 2649 | 10 | PV & Battery | 4-452-452 | 2020-05-15 | 2020-06-03 | 13 |  | 13 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | New Bedford | 2402897 | 2746 | 499 | PV | TBD | 2020-05-28 | 2020-06-01 | 2 |  | 2 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2402933 | 2130 | 1489 | PV |  | 2020-06-17 | 2020-06-19 | 2 | 0 | 2 | 2020-06-29 |  | -31403 | 128 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-06-30 | Private
NSTAR | West Wareham | 2402967 | 2576 | 10 | PV & Battery | 3-85-85 | 2020-05-28 | 2020-06-03 | 4 |  | 4 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Sandwich | 2403120 | 2563 | 90 | PV & Battery | TBD | 2020-05-28 | 2020-06-03 | 4 |  | 4 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2403255 | 1801 | 63.3 | PV | TBD | 2020-06-01 | 2020-06-04 | 3 |  | 3 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2403259 | 2421 | 25.5 | PV & Battery | TBD | 2020-06-03 | 2020-06-05 | 2 |  | 2 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-01-08 | Online
NSTAR | Fairhaven | 2403269 | 2719 | 469.8 | PV | TBD | 2020-03-16 | 2020-06-05 | 59 |  | 59 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Newton | 2403398 | 2459 | 19.84 | PV & Battery | 443-02 | 2020-06-05 | 2020-06-05 | 0 |  | 0 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 2403403 | 2130 | 10 | PV & Battery | 284-1300H1 | 2020-05-20 | 2020-06-08 | 13 |  | 13 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 2403438 | 2673 | 232 | PV | TBD | 2020-05-18 | 2020-06-08 | 15 |  | 15 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2403475 | 1730 | 31 | PV & Battery | TBD | 2020-06-01 | 2020-06-08 | 5 |  | 5 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Wareham | 2403535 | 2571 | 149.3 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Centerville | 2403564 | 2632 | 15.2 | PV | TBD | 2020-04-20 | 2020-06-18 | 43 |  | 43 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | West Wareham | 2403572 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2403584 | 2714 | 2958 | PV & Battery | 2-543-543 | 2020-02-20 | 2020-06-08 | 77 |  | 77 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2403624 | 2451 | 144 | PV | TBD | 2020-04-15 | 2020-05-26 | 29 |  | 29 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-21 | Online
NSTAR | Provincetown | 2403670 | 2567 | 22.89 | PV & Battery | 4-96-675 | 2020-06-03 | 2020-06-10 | 5 |  | 5 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Forestdale | 2403701 | 2644 | - |  | TBD | 2020-06-24 |  | -31400 | 0 | 0 | 2020-06-30 | 2020-07-13 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-08-12 | 2020-09-14 | 2020-12-02 | No | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Medway | 2403742 | 2053 | 25.75 | PV | TBD | 2019-10-09 | 2020-06-10 | 175 |  | 175 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2403835 | 1776 | 200 | PV | TBD | 2020-04-16 | 2020-06-10 | 39 |  | 39 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Plymouth | 2403991 | 2360 | 180 | PV | TBD | 2020-05-18 | 2020-06-11 | 18 |  | 18 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Dennis | 2404237 | 2660 | 3176 | PV | TBD | 2020-04-01 | 2020-06-11 | 51 |  | 51 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Barnstable | 2404275 | 2630 | 3146 | PV & Battery | TBD | 2019-05-26 | 2020-06-15 | 276 |  | 276 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Orleans | 2404297 | 2643 | 10 | PV & Battery | 4-95B-628 | 2020-05-28 | 2020-06-15 | 12 |  | 12 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Boston | 2404393 | 2126 | 129.6 | PV | TBD | 2020-06-08 | 2020-06-15 | 5 |  | 5 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0
NSTAR | Millis | 2404399 | 2054 | 2500 | PV & Battery | TBD | 2020-06-03 | 2020-06-15 | 8 |  | 8 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2404421 | 2631 | 10 | PV & Battery | 4-95A-597 | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Wayland | 2404425 | 1778 | 10 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2404430 | 1748 | 15.2 | PV | 126-H1 | 2020-06-02 | 2020-06-29 | 19 |  | 19 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Framingham | 2404459 | 1702 | 61.2 | PV | TBD | 2020-04-30 | 2020-06-10 | 29 |  | 29 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Needham | 2404602 | 2492 | 19.84 | PV | 148-H2 | 2020-06-22 | 2020-06-22 | 0 |  | 0 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2404607 | 1746 | 21 | PV & Battery | 274-H5 | 2020-06-10 | 2020-06-23 | 9 |  | 9 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Hyannis | 2404659 | 2601 | 999 | PV & Battery | TBD | 2020-02-07 | 2020-06-11 | 89 |  | 89 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2404678 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-11 | 1 |  | 1 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2404735 | 2476 | 17.6 | PV & Battery | TBD | 2020-06-10 | 2020-06-15 | 3 |  | 3 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Jamaica Plain | 2404933 | 2130 | 1360 | PV | TBD | 2020-04-16 | 2020-06-02 | 33 |  | 33 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2404942 | 2143 | 22.8 | PV | TBD | 2020-06-15 | 2020-06-22 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Cambridge | 2405400 | 2139 | 16 | PV & Battery | 817-03 | 2020-06-15 | 2020-06-22 | 5 |  | 5 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2405461 | 1701 | 365 | PV | TBD | 2020-06-01 | 2020-07-06 | 25 |  | 25 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0
NSTAR | Truro | 2405858 | 2652 | 4107 | PV & Battery | TBD | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-13 |  | -31413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2406412 | 1748 | 250 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-15 |  | -31415 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2406453 | 2492 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-07-07 | 16 |  | 16 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Waban | 2406455 | 2468 | 19.84 | PV & Battery | 292-H12 | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2406457 | 2186 | 21.67 | PV & Battery | 4303 | 2020-06-10 | 2020-06-23 | 9 |  | 9 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 2406653 | 1776 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2406660 | 1701 | 17.6 | PV & Battery | TBD | 2020-06-15 | 2020-06-15 | 0 |  | 0 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-07-01 | Online
NSTAR | Bedford | 2406661 | 1730 | 21 | PV & Battery | 322-1397H1 | 2020-06-23 | 2020-06-29 | 4 |  | 4 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Westport | 2406662 | 2790 | 19 | PV | 2-523-523 | 2020-06-09 | 2020-06-29 | 14 |  | 14 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Waltham | 2406861 | 2452 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-06-29 | 12 |  | 12 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Somerville | 2406866 | 2145 | 23 | PV |  | 2020-07-15 | 2020-07-20 | 3 | 0 | 3 | 2020-08-04 | 2020-08-21 | 13 | 0 | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-09-10 | 2020-12-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Buzzards Bay | 2407059 | 2532 | 133.2 | PV | TBD | 2020-04-20 | 2020-06-30 | 51 |  | 51 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2407070 | 2563 | 499 | PV |  | 2020-07-16 | 2020-07-20 | 2 | 0 | 2 | 2020-08-04 |  | -31429 | 100 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-08-10 | Private
NSTAR | Hopkinton | 2407210 | 1748 | 480 | PV |  | 2020-07-17 | 2020-07-20 | 1 | 0 | 1 | 2020-07-22 |  | -31420 | 104 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-08-04 | Private
NSTAR | Lexington | 2407464 | 2421 | 19.86 | PV & Battery | 320-H2 | 2020-07-03 | 2020-07-03 | 0 |  | 0 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wellfleet | 2407474 | 2667 | 2000 | PV & Battery | TBD | 2020-07-01 | 2020-07-02 | 1 |  | 1 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2407481 | 2557 | 22 | PV & Battery | TBD | 2020-06-29 | 2020-07-01 | 2 |  | 2 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2407609 | 2053 | 1476 | PV & Battery | TBD | 2020-07-06 | 2020-07-09 | 3 |  | 3 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2407667 | 1770 | 17.4 | PV | TBD | 2020-07-10 | 2020-07-10 | 0 |  | 0 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Acton | 2407706 | 1720 | 15 | PV & Battery | 416-H4 | 2020-07-21 |  | -31419 | 0 | 0 | 2020-08-06 | 2020-11-12 | 70 | 0 | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-21 |  | 2020-12-30 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | New Bedford | 2407717 | 2745 | 500 | PV & Battery | TBD | 2020-06-01 | 2020-07-13 | 30 |  | 30 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-11 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2407737 | 2460 | 115.2 | PV | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online
NSTAR | Newton | 2407743 | 2459 | 20 | PV & Battery | TBD | 2020-06-23 | 2020-07-01 | 6 |  | 6 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | Mattapoisett | 2407746 | 2739 | 15.2 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Hyannis | 2407747 | 2601 | 24.07 | PV | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2407835 | 2143 | 22.8 | PV | TBD | 2020-06-02 | 2020-07-07 | 25 |  | 25 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Holliston | 2407949 | 2532 | 15.2 | PV | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chestnut Hill | 2407979 | 2467 | 36 | PV & Battery | 467-H12 | 2020-07-01 | 2020-07-02 | 1 |  | 1 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2408018 | 1701 | 22 | PV & Battery | TBD | 2020-07-01 | 2020-07-03 | 2 |  | 2 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Fairhaven | 2408049 | 2719 | 99 | PV |  | 2020-07-23 | 2020-07-27 | 2 | 0 | 2 | 2020-08-04 | 2020-08-19 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 |  | 2020-10-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Wayland | 2408090 | 1778 | 17.6 | PV & Battery | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2408258 | 1701 | 245 | PV & Battery | TBD | 2020-07-15 | 2020-07-17 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2408289 | 2719 | 99.09 | PV | TBD | 2020-07-10 | 2020-07-14 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 2408369 | 2667 | - |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2408400 | 1746 | 499 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2408483 | 2360 | 1000 | PV & Battery | TBD | 2020-06-30 | 2020-07-02 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2408542 | 1730 | 25 | PV & Battery | 533-H5 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Needham | 2408568 | 2492 | 17 | PV & Battery | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Ashland | 2408580 | 1721 | 7 | PV & Battery | 519-175H1 | 2020-06-05 | 2020-07-13 | 26 |  | 26 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 2408582 | 1760 | 43.2 | PV | TBD | 2020-05-28 | 2020-07-07 | 28 |  | 28 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Rochester | 2408783 | 2770 | 4999 | PV & Battery | TBD | 2020-07-07 | 2020-07-13 | 4 |  | 4 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2408881 | 2459 | 10 | PV | 1709 | 2020-07-30 | 2020-09-10 | 30 | 0 | 30 | 2020-09-10 |  | -31456 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-02-15 | Online | [5 empty] | Private
NSTAR | Marshfield | 2409029 | 2050 | 7.6 | PV | 3-24B-915 | 2020-05-26 | 2020-07-07 | 30 |  | 30 | 2020-08-03 |  | -31428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-12 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Acton | 2409041 | 1702 | 15.6 | PV & Battery | 416-H5 | 2020-07-11 | 2020-07-15 | 3 |  | 3 | 2020-08-03 |  | -31428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Cambridge | 2409461 | 2140 | 14 | PV & Battery | 825-27 | 2020-06-11 | 2020-07-16 | 25 |  | 25 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | West Wareham | 2409477 | 2576 | 7.6 | PV | TBD | 2020-07-01 | 2020-07-16 | 11 |  | 11 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Orleans | 2409513 | 2145 | 245 | PV | TBD | 2020-07-15 | 2020-07-16 | 1 |  | 1 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2409582 | 1746 | 250 | PV | TBD | 2020-07-08 | 2020-07-14 | 4 |  | 4 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2409588 | 2115 | 180 | PV |  | 2020-08-03 | 2020-08-04 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Canton | 2409650 | 2021 | 21.4 | PV & Battery | TBD | 2020-07-20 | 2020-07-20 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Plymouth | 2409661 | 2360 | 10 | PV & Battery | 3-14-934 | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | Hopkinton | 2409830 | 1748 | 5000 | PV & Battery | TBD | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2409880 | 1803 | 95.5 | PV | TBD | 2020-07-22 | 2020-07-23 | 1 |  | 1 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2409915 | 2649 | 245 | PV & Battery | TBD | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-05 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2409919 | 2128 | 57.6 | PV | TBD | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-03-22 | Online
NSTAR | Burlington | 2409940 | 1803 | 20.4 | PV & Battery | 346-1395H1 | 2020-06-29 | 2020-07-28 | 21 |  | 21 | 2020-08-11 |  | -31434 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Winchester | 2409982 | 1890 | 18 | PV & Battery |  | 2020-08-07 | 2020-08-10 | 1 | 0 | 1 | 2020-08-13 | 2020-08-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-08-31 | 2020-12-15 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  | 2022-02-03 | Online | [5 empty] | Private
NSTAR | Lexington | 2409998 | 2420 | 20 | PV & Battery | TBD | 2020-07-15 | 2020-07-20 | 3 |  | 3 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Fairhaven | 2410005 | 2719 | 750 | PV | TBD | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2410106 | 2563 | 7.6 | PV | 4-81B-443 | 2020-06-23 | 2020-07-28 | 25 |  | 25 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2410160 | 2115 | 180 | PV | TBD | 2020-07-28 | 2020-07-29 | 1 |  | 1 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2410254 | 2649 | 499 | PV & Battery | TBD | 2020-07-27 | 2020-08-03 | 5 |  | 5 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2410310 | 2364 | 133.2 | PV | TBD | 2020-07-29 | 2020-08-03 | 3 |  | 3 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online
NSTAR | Mattapoisett | 2410489 | 2739 | 5000 | PV & Battery | TBD | 2020-07-29 | 2020-08-04 | 4 |  | 4 | 2020-08-17 |  | -31438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2410632 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-13 | 5 |  | 5 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2410727 | 2021 | 249.8 | PV | 470-H7 | 2020-07-29 | 2020-07-29 | 0 |  | 0 | 2020-07-29 |  | -31425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Natick | 2410746 | 1760 | 10 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2410747 | 2494 | 19.57 | PV & Battery | 292-H4 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2410763 | 2452 | 7.6 | PV | 450-H6 | 2020-08-04 | 2020-08-06 | 2 |  | 2 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Wareham | 2410816 | 2576 | - |  | TBD | 2020-08-14 |  | -31437 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2030-12-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | [5 empty] | Private
NSTAR | Brookline | 2410954 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2410982 | 1760 | 497 | PV | 240-H1 | 2020-08-17 | 2020-09-29 | 31 | 0 | 31 | 2020-09-29 | 2020-10-07 | 6 | 0 | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Woburn | 2411000 | 1801 | 15.2 | PV | TBD | 2020-06-08 | 2020-07-28 | 36 |  | 36 | 2020-08-17 |  | -31438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-20 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2411056 | 1803 | 500 | PV |  | 2020-08-17 | 2020-08-17 | 0 | 0 | 0 | 2020-08-25 |  | -31444 | 65 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-09-30 | Private
NSTAR | Falmouth | 2411073 | 2540 | 15.2 | PV | 4-76-436 | 2020-06-15 | 2020-07-28 | 31 |  | 31 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2411107 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-30 | 18 |  | 18 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2411131 | 1730 | 25 | PV & Battery | TBD | 2020-07-22 | 2020-08-03 | 8 |  | 8 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Brookline | 2411200 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Stoneham | 2411309 | 2180 | 10 | PV & Battery | 375-H8 | 2020-07-22 | 2020-08-03 | 8 |  | 8 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Framingham | 2411344 | 1702 | 573 | PV |  | 2020-08-18 | 2020-09-09 | 16 | 0 | 16 | 2020-09-14 |  | -31458 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Gov't
NSTAR | Hyannis | 2411466 | 2601 | 186 | PV | TBD | 2020-08-06 | 2020-08-06 | 0 |  | 0 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2411491 | 2536 | - | PV & Battery | TBD | 2020-07-06 | 2020-07-03 | -3 |  | 0 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2411492 | 2421 | 361.5 | PV | TBD | 2020-07-29 | 2020-08-04 | 4 |  | 4 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Falmouth | 2411634 | 2540 | 66.6 | PV | TBD | 2020-08-03 | 2020-08-07 | 4 |  | 4 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Falmouth | 2411656 | 2540 | 18.7 | PV & Battery | TBD | 2020-07-15 | 2020-08-03 | 13 |  | 13 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Wayland | 2411668 | 1778 | 23.01 | PV | TBD | 2020-07-22 | 2020-08-07 | 12 |  | 12 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | North Falmouth | 2411670 | 2556 | 18 | PV & Battery | TBD | 2020-08-04 | 2020-08-10 | 4 |  | 4 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2411939 | 2631 | 57.6 | PV | TBD | 2020-07-22 | 2020-08-06 | 11 |  | 11 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2411957 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Mashpee | 2411961 | 2649 | 750 | PV & Battery | TBD | 2020-07-27 | 2020-08-06 | 8 |  | 8 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2412130 | 2747 | 15.2 | PV | TBD | 2020-07-27 | 2020-08-07 | 9 |  | 9 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2412133 | 2050 | 15.2 | PV | TBD | 2020-08-06 | 2020-08-07 | 1 |  | 1 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2412211 | 2090 | 3104.5 | PV & Battery | TBD | 2020-08-07 | 2020-08-11 | 2 |  | 2 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2412218 | 2125 | 19 | PV & Battery | 483-01 | 2020-07-29 | 2020-08-11 | 9 |  | 9 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Onset | 2412247 | 2558 | 17.6 | PV | TBD | 2020-06-23 | 2020-08-13 | 37 |  | 37 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Fairhaven | 2412322 | 2719 | 66.6 | PV | TBD | 2020-08-10 | 2020-08-10 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Holliston | 2412335 | 1746 | 20 | PV | TBD | 2020-08-26 | 2020-08-31 | 3 | 0 | 3 | 2020-09-14 |  | -31458 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Falmouth | 2412337 | 2540 | 122 | PV | TBD | 2020-08-06 | 2020-08-11 | 3 |  | 3 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Online
NSTAR | Pocasset | 2412341 | 2559 | 999 | PV & Battery | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2412477 | 2601 | 250 | PV | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2412478 | 2421 | 133.3 | PV | TBD | 2020-05-05 | 2020-08-13 | 72 |  | 72 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2412543 | 2180 | 15.2 | PV | TBD | 2020-07-22 | 2020-08-14 | 17 |  | 17 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Lexington | 2412545 | 2421 | 15.2 | PV | TBD | 2020-08-12 | 2020-08-14 | 2 |  | 2 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2412573 | 2021 | 2660 | PV & Battery | TBD | 2020-07-29 | 2020-08-17 | 13 |  | 13 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2412636 | 2140 | 19.12 | PV | TBD | 2020-08-12 | 2020-08-17 | 3 |  | 3 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | New Bedford | 2412695 | 2746 | 250 | PV | TBD | 2019-12-30 | 2020-01-21 | 16 |  | 16 | 2020-09-07 |  | -31453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2412699 | 2026 | 4990 | PV |  | 2020-08-31 | 2020-09-09 | 7 | 0 | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 |  | -31458 | 62 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue |  |  |  |  | 2020-10-05 | Private
NSTAR | Plymouth | 2412755 | 2360 | 17.6 | PV & Battery | TBD | 2020-07-28 | 2020-08-14 | 13 |  | 13 | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2412838 | 2364 | 15.2 | PV | 3-51-980 | 2020-07-22 |  | -31420 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Medfield | 2412922 | 2052 | 250 | PV | TBD | 2020-09-01 | 2020-09-03 | 2 | 0 | 2 | 2020-09-14 | 2020-11-25 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-12-14 |  | 2020-12-31 | TBD | Expedited | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Norfolk | 2412929 | 2056 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2413383 | 1746 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2413389 | 1720 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2413390 | 2360 | 21.4 | PV & Battery | TBD | 2020-08-11 |  | -31434 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Carlisle | 2413532 | 1741 | 17.6 | PV & Battery | TBD | 2020-08-12 | 2020-08-18 | 4 |  | 4 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | Waltham | 2413861 | 2451 | 487.5 | PV | TBD | 2020-06-22 | 2020-08-25 | 46 |  | 46 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2413980 | 2445 | 133.2 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Hyde Park | 2414035 | 2136 | 15.2 | PV | TBD | 2020-08-04 | 2020-08-18 | 10 |  | 10 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Brookline | 2414048 | 2446 | 200 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acusnet | 2414312 | 2743 | 1220 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2414387 | 2743 | 610 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | 6 |  | 6 | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4253275 | 2130 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | 14 |  | 14 | 2020-09-17 |  | -31461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 4257166 | 2633 | 86.6 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-09-17 |  | -31461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 4258230 | 2136 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | 14 |  | 14 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Yarmouth | 4263458 | 2673 | 158.4 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4280601 | 2652 | 35 | PV | TBD | 2020-09-03 | 2020-09-03 | 0 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-01-28 | Online
NSTAR | Burlington | 4280698 | 1803 | 30.2 | PV & Battery | TBD | 2020-07-22 | 2020-08-18 | 19 |  | 19 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Aquinnah | 4281091 | 2635 | 54.2 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-09-23 |  | -31465 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 4284906 | 2653 | 51.62 | PV | TBD | 2020-08-27 | 2020-09-01 | 3 |  | 3 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Acusnet | 4287867 | 2743 | 610 | PV & Battery | TBD | 2020-09-01 | 2020-09-03 | 2 |  | 2 | 2020-09-24 |  | -31466 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 4288338 | 2536 | 33.3 | PV | TBD | 2020-09-01 | 2020-09-03 | 2 |  | 2 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Lexington | 4289037 | 2421 | 21.4 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | East Falmouth | 4290987 | 2536 | 17.04 | PV | 4-77A-77A | 2020-08-27 | 2020-09-02 | 4 |  | 4 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Dover | 4296074 | 2030 | 200 | PV | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4304369 | 2667 | 28.7 | PV & Battery | TBD | 2020-08-04 | 2020-09-08 | 25 |  | 25 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | East Falmouth | 4304824 | 2536 | 20 | PV & Battery | TBD | 2020-09-03 | 2020-09-09 | 4 |  | 4 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Hyannis | 4305225 | 2601 | 86.4 | PV | TBD | 2020-08-27 | 2020-09-03 | 5 |  | 5 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Woburn | 4305278 | 1801 | 111.5 | PV & Battery | TBD | 2020-09-08 | 2020-09-11 | 3 |  | 3 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | West Tisbury | 4307156 | 2658 | 48 | PV | TBD | 2020-09-04 | 2020-09-14 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Sudbury | 4307664 | 1776 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-09-15 | 68 |  | 68 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 4307751 | 2445 | 100 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online
NSTAR | East Dennis | 4308158 | 2641 | 10 | PV & Battery | 4-89A-552 | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 4310270 | 2535 | 166.9 | PV | 4-97-226 | 2020-09-16 | 2020-09-16 | 0 |  | 0 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | West Yarmouth | 4311398 | 2673 | 370 | PV | TBD | 2020-08-18 | 2020-09-03 | 12 |  | 12 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 4311559 | 2666 | 15.2 | PV | TBD | 2020-08-07 | 2020-09-03 | 19 |  | 19 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Acton | 4312709 | 1720 | 15.2 | PV | TBD | 2020-08-27 | 2020-09-03 | 5 |  | 5 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 4314087 | 1721 | 27.6 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 4318460 | 1741 | 30.2 | PV & Battery | TBD | 2020-09-01 | 2020-09-10 | 7 |  | 7 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Needham | 4318615 | 2494 | 1300 | PV & Battery | TBD | 2020-08-27 | 2020-09-10 | 10 |  | 10 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 4323415 | 2571 | 200 | PV | TBD | 2020-08-06 | 2020-09-10 | 25 |  | 25 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 4324124 | 2492 | 144 | PV | TBD | 2020-09-03 | 2020-09-11 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4325211 | 2030 | 20 | PV | 456-H5 | 2020-09-11 | 2020-09-18 | 5 |  | 5 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4325236 | 2179 | 300 | PV | TBD | 2020-09-08 | 2020-09-14 | 4 |  | 4 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | 4336889 | 1778 | 20 | PV & Battery | TBD | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 4340257 | 2557 | 233.1 | PV | TBD | 2020-05-26 | 2020-09-15 | 80 |  | 80 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4340848 | 2472 | 430.3 | PV | TBD | 2020-09-08 | 2020-09-16 | 6 |  | 6 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Millis | 4345313 | 2054 | 19 | PV | TBD | 2020-09-14 | 2020-09-18 | 4 |  | 4 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Wareham | 4350518 | 2576 | 266.3 | PV | TBD | 2020-09-18 | 2020-09-22 | 2 |  | 2 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Online
NSTAR | Canton | 4350632 | 2021 | 35.2 | PV & Battery | TBD | 2020-09-08 | 2020-09-22 | 10 |  | 10 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4351141 | 2030 | 20.22 | PV & Battery | 456-H5 | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Bedford | 4352135 | 1730 | 100.8 | PV | TBD | 2020-09-10 | 2020-09-24 | 10 |  | 10 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-12 | Online
NSTAR | Sudbury | 4352193 | 2453 | 17.86 | PV & Battery | TBD | 2020-09-18 | 2020-09-24 | 4 |  | 4 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Boston | 4352975 | 2215 | 75 | CHP | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | East Freetown | 4355122 | 2717 | 61.6 | PV | TBD | 2020-09-25 | 2020-09-25 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Online
NSTAR | Allston | 4367936 | 2134 | 125 | PV & Battery | TBD | 2020-09-18 | 2020-09-25 | 5 |  | 5 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4371445 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372220 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372438 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Carver | 4377469 | 2330 | 200 | PV | TBD | 2020-09-18 | 2020-09-30 | 8 |  | 8 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4380220 | 2186 | 17.6 | PV & Battery | TBD | 2020-09-22 | 2020-10-05 | 9 |  | 9 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 4389990 | 2332 | 16.24 | PV & Battery | 3-26-903 | 2020-09-30 | 2020-10-05 | 3 |  | 3 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Natick | 4397054 | 1760 | 100 | PV | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-15 | Withdrawn
NSTAR | Waltham | 4399358 | 2453 | 75 | chp | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Forestdale | 4399952 | 2644 | 15.2 | PV | 4-81B-443 | 2020-09-18 | 2020-09-18 | 0 |  | 0 | 2020-09-18 |  | -31462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 4403448 | 2472 | 583.3 | PV & Battery | TBD | 2020-09-22 | 2020-09-30 | 6 |  | 6 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4404039 | 2472 | 320.8 | PV | TBD | 2020-09-22 | 2020-09-30 | 6 |  | 6 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4404592 | 2719 | 2000 | PV & Battery | TBD | 2020-09-24 | 2020-09-25 | 1 |  | 1 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4406125 | 2139 | 77.8 | PV | TBD | 2020-09-30 | 2020-09-30 | 0 |  | 0 | 2020-10-23 |  | -31487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Sherborn | 4425381 | 1770 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 4425492 | 2132 | 15.2 | PV | TBD | 2020-09-24 | 2020-10-07 | 9 |  | 9 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 4427690 | 1760 | 25 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Vineyard Haven | 4429285 | 2568 | 19.68 | PV | TBD | 2020-08-27 | 2020-10-07 | 29 |  | 29 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | East Falmouth | 4430372 | 2536 | 198 | PV | TBD | 2020-09-30 | 2020-10-08 | 6 |  | 6 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4433447 | 2360 | 66.6 | PV | TBD | 2020-10-06 | 2020-10-07 | 1 |  | 1 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Somerville | 4467249 | 2143 | 250 | PV | TBD | 2020-10-19 | 2020-10-19 | 0 |  | 0 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 4468058 | 2067 | 19 | PV | TBD | 2020-10-07 | 2020-10-15 | 6 |  | 6 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4469232 | 2667 | 23.2 | PV | 4-96-677 | 2020-09-18 | 2020-10-08 | 14 |  | 14 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-04
NSTAR | Newton | 4469731 | 2458 | 19.75 | PV & Battery | 277-05 | 2020-09-18 | 2020-10-05 | 11 |  | 11 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Medway | 4470535 | 2053 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-19 | 8 |  | 8 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-08 | Online
NSTAR | Canton | 4470982 | 2021 | 245 | PV | TBD | 2020-10-08 | 2020-10-19 | 7 |  | 7 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0
NSTAR | North Falmouth | 4479289 | 2649 | 25.81 | PV & Battery | TBD | 2020-10-15 | 2020-10-19 | 2 |  | 2 | 2020-11-13 |  | -31502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Somerville | 4487617 | 2145 | 250 | PV | TBD | 2020-10-15 | 2020-10-15 | 0 |  | 0 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Sharon | 4488554 | 2067 | 18.75 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  | 2021-06-03 | Online
NSTAR | Rochester | 4489081 | 2770 | 22 | PV | TBD | 2020-10-15 | 2020-10-19 | 2 |  | 2 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-25 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Jamaica Plain | 4489427 | 2130 | 400 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Lexington | 4490263 | 2421 | 24 | PV & Battery | 3401 | 2020-10-15 | 2020-10-21 | 4 |  | 4 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Wareham | 4490547 | 2576 | 233.2 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4490762 | 2739 | 5000 | PV & Battery | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4492827 | 2030 | 36 | PV & Battery | TBD | 2020-10-15 | 2020-10-21 | 4 |  | 4 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 4493355 | 2050 | 19.6 | PV & Battery | 3-25-25 | 2020-10-21 | 2020-10-22 | 1 |  | 1 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 4494158 | 2702 | 18.85 | PV | TBD | 2020-10-22 | 2020-10-22 | 0 |  | 0 | 2020-12-03 |  | -31516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Newton | 4495812 | 2459 | 18 | PV & Battery | TBD | 2020-10-16 | 2020-10-22 | 4 |  | 4 | 2020-11-19 |  | -31506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 4500410 | 2121 | 16.8 | PV | TBD | 2020-10-07 | 2020-10-27 | 14 |  | 14 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Canton | 4503033 | 2021 | 200 | PV | TBD | 2020-10-21 | 2020-10-22 | 1 |  | 1 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4506135 | 2360 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 4506942 | 2143 | 53.6 | PV & Battery | TBD | 2020-10-19 | 2020-10-27 | 6 |  | 6 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | Carver | 4507889 | 2330 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4518746 | 2330 | 5000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 4519305 | 2476 | 17.6 | PV & Battery | TBD | 2020-10-05 | 2020-10-15 | 8 |  | 8 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Walpole | 4519566 | 2081 | 15.2 | PV | TBD | 2020-09-14 | 2020-10-15 | 23 |  | 23 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Plympton | 4519678 | 2367 | 15.2 | PV | TBD | 2020-10-08 | 2020-10-16 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 4529021 | 2021 | 166.5 | PV | 269-1321H2 | 2020-09-28 | 2020-09-28 | 0 |  | 0 | 2020-09-28 |  | -31468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2021-11-15 | Online | [5 empty] | Private
NSTAR | Framingham | 4532766 | 1701 | 16.4 | PV | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Westwood | 4533474 | 2090 | 20 | PV & Battery | TBD | 2020-11-16 | 2020-11-18 | 2 |  | 2 | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-12 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 4534965 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-01 |  | -31514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | 4535505 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-01 |  | -31514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 4550665 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0
NSTAR | Boston | 4550829 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4551603 | 2120 | 43.2 | PV | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Assonett | 4556815 | 2702 | 15.2 | PV | TBD | 2020-10-15 | 2020-11-04 | 14 |  | 14 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 4556854 | 1773 | 20 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Acusnet | 4556908 | 2743 | 500 | PV & Battery | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4556981 | 2740 | 999 | PV & Battery | TBD | 2020-10-27 | 2020-11-02 | 4 |  | 4 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-17
NSTAR | Woburn | 4557000 | 1801 | 57.6 | PV | TBD | 2020-10-27 | 2020-11-04 | 6 |  | 6 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Sherborn | 4557126 | 1770 | 18.6 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4562972 | 2130 | 75 | CHP | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Dedham | 4575161 | 2026 | 4990 | PV & Battery | TBD | 2020-05-07 |  | -31366 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Norfolk | 4578744 | 2056 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-08 |  | -31519 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | New Bedford | 4579621 | 2746 | 93.45 | PV | TBD | 2020-10-29 | 2020-11-10 | 8 |  | 8 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-13 | Online
NSTAR | Medfield | 4581063 | 2052 | 17.6 | PV | 456-H5 | 2020-09-18 | 2020-11-04 | 33 |  | 33 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-09-14 | Online
NSTAR | Bellingham | 4581275 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4581293 | 2067 | 15.2 | PV | TBD | 2020-11-06 | 2020-11-09 | 1 |  | 1 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Dartmouth | 4581517 | 2747 | 200 | PV | TBD | 2020-11-04 | 2020-11-06 | 2 |  | 2 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Newton | 4581647 | 2464 | 25 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Walpole | 4581720 | 2071 | 20 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0 |  |  | 2021-06-25 | Online
NSTAR | Westwood | 4581827 | 2090 | 20 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4582227 | 2451 | 7.6 | PV | TBD | 2020-10-29 | 2020-11-06 | 6 |  | 6 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | New Bedford | 4582294 | 2745 | 17.6 | PV & Battery | 2-104-104 | 2020-10-21 | 2020-11-09 | 13 |  | 13 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-04-06 | Online
NSTAR | Medfield | 4589421 | 2052 | 200 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4590471 | 2740 | 20 | PV | TBD | 2020-11-09 | 2020-11-16 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Walpole | 4590656 | 2081 | 10 | PV & Battery | 146-H3 | 2020-11-06 | 2020-11-13 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4590784 | 2770 | 20 | PV | TBD | 2020-11-06 | 2020-11-13 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Needham | 4590881 | 2494 | 17.36 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-07 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4590902 | 2743 | 61.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Newton | 4590939 | 2461 | 10 | PV & Battery | 292-01 | 2020-11-13 | 2020-11-16 | 1 |  | 1 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 4606031 | 1730 | 20 | PV & Battery | TBD | 2020-11-18 | 2020-11-24 | 4 |  | 4 | 2020-12-15 |  | -31524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 4606031 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | New Bedford | 4607301 | 2745 | 2125 | PV | TBD | 2020-11-18 | 2020-12-01 | 9 |  | 9 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 4607939 | 1748 | 19.72 | PV | TBD | 2020-11-24 | 2020-12-01 | 5 |  | 5 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-19 | Online
NSTAR | West Newton | 4610357 | 2465 | 17.6 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Maynard | 4614920 | 1754 | 86.4 | PV | TBD | 2020-11-13 | 2020-11-16 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29
NSTAR | Burlington | 4615024 | 1803 | 58.2 | PV | TBD | 2020-11-02 | 2020-11-18 | 12 |  | 12 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Holliston | 4615055 | 1746 | 19.8 | PV & Battery | TBD | 2020-11-18 | 2020-11-19 | 1 |  | 1 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Dorchester | 4615111 | 2124 | 15.2 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 4615145 | 2476 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online
NSTAR | North Dartmouth | 4615175 | 2747 | 35.2 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online
NSTAR | Sudbury | 4619003 | 1776 | 5 | Battery | 342-H4 | 2020-11-06 | 2020-11-24 | 12 |  | 12 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4619474 | 1701 | 17.6 | PV & Battery | 278-H1 | 2020-11-09 | 2020-11-24 | 11 |  | 11 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Framingham | 4619506 | 1702 | 205 | PV | TBD | 2020-11-18 | 2020-11-24 | 4 |  | 4 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 4619563 | 1890 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-24 | 7 |  | 7 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Mattapoisett | 4619595 | 2739 | 2250 | PV & Battery | TBD | 2020-11-06 | 2020-11-25 | 13 |  | 13 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4619617 | 2067 | 20 | PV & Battery | TBD | 2020-10-29 | 2020-11-25 | 19 |  | 19 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Sudbury | 4619695 | 1776 | 23.8 | PV & Battery | TBD | 2020-11-06 | 2020-11-24 | 12 |  | 12 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4619716 | 2360 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | 8 |  | 8 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4621310 | 2666 | 62.93 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Online
NSTAR | Lexington | 4621352 | 2420 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-16 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Mashpee | 4632820 | 2649 | 13.8 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | South Dartmouth | 4632856 | 2748 | 43.92 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-15 | Online
NSTAR | Medfield | 4635189 | 2052 | 25 | PV & Battery | TBD | 2020-11-25 | 2020-12-14 | 13 |  | 13 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Stoneham | 4635296 | 2180 | 180 | PV | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 4635371 | 2090 | 20 | PV & Battery | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Westwood | 4636581 | 2090 | 25.2 | PV & Battery | TBD | 2020-11-25 | 2020-12-07 | 8 |  | 8 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Needham | 4637344 | 2494 | 22.6 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Sharon | 4637394 | 2067 | 18.5 | PV | TBD | 2020-11-13 | 2020-11-18 | 3 |  | 3 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Manomet | 4637511 | 2345 | 17.4 | PV | TBD | 2020-11-13 | 2020-11-18 | 3 |  | 3 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Marshfield | 4637609 | 2050 | 13.8 | PV & Battery | 3-22-973 | 2020-10-29 |  | -31491 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Cambridge | 4637828 | 2140 | 75 | CHP | TBD | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15
NSTAR | Boston | 4637851 | 2135 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | 8 |  | 8 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4637906 | 1701 | 250 | PV | TBD | 2020-11-25 | 2020-11-25 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4642133 | 2421 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-12-01 | 12 |  | 12 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | North Cambridge | 4642185 | 2140 | 19.57 | PV & Battery | TBD | 2020-11-06 | 2020-12-01 | 17 |  | 17 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | West Roxbury | 4642220 | 2132 | 15.2 | PV | TBD | 2020-11-25 | 2020-12-01 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 4642283 | 2459 | 28.8 | PV & Battery | 292-H6 | 2020-11-18 | 2020-12-07 | 13 |  | 13 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Somerville | 4642301 | 2145 | 201.6 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Millis | 4642384 | 2054 | 15.2 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Newton | 4658683 | 2459 | 15 | PV & Battery | 292-H11 | 2020-11-13 | 2020-11-24 | 7 |  | 7 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online
NSTAR | Truro | 4658780 | 2666 | 249.8 | PV | TBD | 2020-11-24 | 2020-11-24 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 4659394 | 2090 | 95.8 | PV | TBD | 2020-11-06 | 2020-12-14 | 26 |  | 26 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Wareham | 4659423 | 2571 | 4980 | PV & Battery | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 4659441 | 1803 | 23.49 | PV | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Watertown | 4659469 | 2122 | 57.6 | PV | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Acton | 4659513 | 1720 | 4980 | PV & Battery | TBD | 2020-11-25 | 2020-12-15 | 14 |  | 14 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4661337 | 2030 | 20 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Weston | 4663199 | 2493 | 35.2 | PV & Battery | TBD | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Holliston | 4664449 | 1746 | 10 | Battery | TBD | 2020-11-16 | 2020-12-14 | 20 |  | 20 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4664554 | 2030 | 19.84 | PV & Battery | 456-H5 | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4665887 | 1720 | 17.6 | PV & Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acton | 4668063 | 1720 | 25.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Winchester | 4668160 | 1890 | 25 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marion | 4668251 | 2738 | 22.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Marshfield | 4668327 | 2050 | 18 | PV | TBD | 2020-12-17 | 2020-12-17 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4669412 | 2770 | 149.3 | PV | TBD | 2020-12-01 | 2020-12-14 | 9 |  | 9 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 4675384 | 2364 | 499 | PV & Battery | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4676006 | 2180 | 150 | PV | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-08 |  | -31542 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Wayland | 4676256 | 1778 | 20 | PV | TBD | 2020-11-25 | 2020-12-14 | 13 |  | 13 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Roslindale | 4677350 | 2131 | 18 | PV & Battery | 496-H8 | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 4680348 | 2124 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | 38 |  | 38 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Online
NSTAR | Stoneham | 4680468 | 2180 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | 38 |  | 38 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 4680531 | 1748 | 35.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 4680587 | 2186 | 16 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4680617 | 1770 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Hopkinton | 4683322 | 1748 | 20 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Waltham | 4683376 | 2451 | 166 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Mattapan | 4683605 | 2126 | 7.6 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-22 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4685975 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-22 | 19 |  | 19 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 4686146 | 2717 | 149.3 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4686399 | 2451 | 233 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 4696273 | 2793 | 2500 | PV & Battery | TBD | 2020-11-04 | 2020-11-25 | 15 |  | 15 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 4698222 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-29 | 24 |  | 24 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | South Dartmouth | 4698354 | 2748 | 15.2 | PV | TBD | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 4698431 | 1760 | 7.6 | PV | 240-H3 | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 4698540 | 2081 | 495 | PV | TBD | 2020-11-13 | 2020-12-29 | 32 |  | 32 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4701003 | 2030 | 20.92 | PV | 456-H5 | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 4702589 | 2743 | 4990 | PV & Battery | TBD | 2020-12-17 | 2020-12-29 | 8 |  | 8 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4706363 | 2330 | 248 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 4707682 | 2026 | 66.6 | PV | 20-H1 | 2020-12-01 | 2020-12-30 | 21 |  | 21 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-20 | Online
NSTAR | Newton | 4708433 | 2459 | 66.6 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 4708506 | 2367 | 19 | PV | TBD | 2020-12-29 | 2020-12-30 | 1 |  | 1 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4708532 | 2421 | 17.44 | PV & Battery | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4708871 | 1720 | 2495 | Battery | TBD | 2020-12-29 | 2020-12-29 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4713423 | 2139 | 75 | CHP | 831-1394 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Holliston | 4713490 | 1746 | 20 | PV & Battery | TBD | 2020-07-29 | 2020-08-10 | 8 |  | 8 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Lincoln | 4713513 | 1773 | 14 | Battery | 320-H8 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Medfield | 4714661 | 2052 | 250 | PV | TBD | 2020-08-14 |  | -31437 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4717011 | 2420 | 40 | PV & Battery | TBD | 2020-12-30 | 2020-12-31 | 1 |  | 1 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4717656 | 2739 | 2496 | Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4832256 | 2492 | 16 | PV | TBD | 2020-12-22 | 2020-12-23 | 1 |  | 1 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Walpole | 4833200 | 2081 | 15.2 | PV | TBD | 2020-12-23 | 2020-12-23 | 0 |  | 0 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4841015 | 2180 | 15.2 | PV | 375-H8 | 2020-12-29 | 2021-01-11 | 9 |  | 9 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Stoneham | 4841178 | 2180 | 19 | PV | TBD | 2020-12-29 | 2021-01-06 | 6 |  | 6 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | Canton | 4849001 | 2021 | 53.2 | PV | TBD | 2021-01-04 | 2021-01-07 | 3 |  | 3 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Carver | 4849634 | 2330 | 72 | PV | TBD | 2020-12-30 | 2021-01-06 | 5 |  | 5 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Milton | 4850213 | 2186 | 23.78 | PV | TBD | 2021-01-07 | 2021-01-07 | 0 |  | 0 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 4850477 | 1776 | 35.2 | PV & Battery | TBD | 2020-12-24 | 2020-12-24 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 4869494 | 2747 | 18.6 | PV | TBD | 2021-01-07 | 2021-01-11 | 2 |  | 2 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Freetown | 4869709 | 2702 | 4999 | PV & Battery | TBD | 2020-12-30 | 2021-01-11 | 8 |  | 8 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4869810 | 2492 | 17.04 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Rochester | 4869940 | 2770 | 250 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4869990 | 2360 | 110 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | South Dartmouth | 4870032 | 2748 | 18 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | 17 |  | 17 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4874091 | 2420 | 25.2 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | 17 |  | 17 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Carver | 4876930 | 2330 | 15.2 | PV | TBD | 2020-12-16 | 2021-01-11 | 18 |  | 18 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | East Wareham | 4877705 | 2538 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Acton | 4878009 | 1720 | 20 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-23 | Online
NSTAR | West Somerville | 4878069 | 2144 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878172 | 2493 | 18 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878244 | 2393 | 21.4 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Newton | 4878336 | 2468 | 35.2 | PV & Battery | TBD | 2020-12-01 | 2021-01-11 | 29 |  | 29 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-23 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Sudbury | 4878402 | 1776 | 20 | PV & Battery | TBD | 2021-01-11 | 2021-01-11 | 0 |  | 0 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 4878461 | 1803 | 20 | PV & Battery | 391-H7 | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | North Acton | 4886788 | 1720 | 57.6 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Hyannis | 4886864 | 2601 | 7.6 | PV | 4-84A-520 | 2020-12-14 | 2021-01-12 | 21 |  | 21 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | East Walpole | 4886981 | 2032 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-12 | 21 |  | 21 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Westwood | 4887029 | 2090 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | 10 |  | 10 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Westport | 4887097 | 2790 | 23.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | 10 |  | 10 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 4887205 | 2649 | 52.78 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-10 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Plymouth | 4887324 | 2360 | 17.6 | PV & Battery | TBD | 2020-11-25 | 2021-01-12 | 34 |  | 34 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Waltham | 4887381 | 2451 | 466 | PV | TBD | 2020-12-31 | 2021-01-25 | 17 |  | 17 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-30 | Online
NSTAR | Wayland | 4894418 | 1778 | 16.78 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2022-05-16 | Online
NSTAR | Bedford | 4896010 | 1730 | 15.2 | PV | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | East Freetown | 4896804 | 2717 | 25 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907766 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907809 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 4907860 | 2673 | 21.75 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Medway | 4920759 | 2053 | 29.5 | PV | TBD | 2020-12-30 | 2021-01-19 | 14 |  | 14 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Medway | 4920922 | 2053 | 19.75 | PV | TBD | 2020-12-30 | 2021-01-19 | 14 |  | 14 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4921183 | 2186 | 15.2 | PV | 311-04 | 2021-01-12 | 2021-01-19 | 5 |  | 5 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4921323 | 2770 | 25.2 | PV & Battery | TBD | 2020-12-14 | 2021-01-20 | 27 |  | 27 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 4921387 | 2476 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-19 | 15 |  | 15 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Sharon | 4921508 | 2067 | 13.8 | PV & Battery | TBD | 2020-12-14 |  | -31523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online
NSTAR | Hyannis | 4936393 | 2601 | 69.25 | PV | TBD | 2021-01-21 |  | -31551 |  | 0 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 4936614 | 2134 | 43.2 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4937121 | 1703 | 21.83 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Hyannis | 4945477 | 2601 | 86.6 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Online
NSTAR | Hyannis | 4945583 | 2601 | 120 | PV | TBD | 2021-01-12 | 2021-01-21 | 7 |  | 7 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Mashpee | 4962795 | 2649 | 495 | PV | TBD | 2021-01-21 | 2021-01-26 | 3 |  | 3 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4963253 | 2666 | 17.68 | battery | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Duxbury | 4963456 | 2332 | 25.2 | PV | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4963535 | 1770 | 15.2 | PV & Battery | TBD | 2020-11-24 | 2021-01-27 | 46 |  | 46 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 4963768 | 2360 | 20 | PV & Battery | TBD | 2020-12-01 | 2021-01-27 | 41 |  | 41 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Walpole | 4963817 | 2081 | 10 | PV & Battery | TBD | 2020-12-14 | 2021-01-27 | 32 |  | 32 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-18 | Online
NSTAR | Marston Mills | 4971708 | 2648 | 11.6 | Battery | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 4972029 | 1778 | 10 | Battery | TBD | 2021-01-27 | 2021-01-28 | 1 |  | 1 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Acton | 4972089 | 1720 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-01-27 | 37 |  | 37 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 4972223 | 2747 | 200 | PV | TBD | 2021-03-02 | 2021-03-02 | 0 |  | 0 | 2021-03-02 |  | -31579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 4983194 | 2601 | 51.9 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4983372 | 2186 | 15.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | 16 |  | 16 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Hyannis | 4983604 | 2601 | 90 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Sudbury | 4983699 | 1776 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-20 | 27 |  | 27 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4983727 | 2067 | 16.48 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | 16 |  | 16 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Bourne | 4991635 | 2532 | 19.9 | PV | TBD | 2021-01-21 | 2021-01-26 | 3 |  | 3 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | New Bedford | 4991678 | 2740 | 15.2 | PV | TBD | 2021-01-06 | 2021-01-26 | 14 |  | 14 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 4999717 | 2645 | 213.2 | PV | TBD | 2021-01-12 | 2021-01-20 | 6 |  | 6 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Kingston | 5000850 | 2364 | 250 | PV | TBD | 2021-01-14 | 2021-01-20 | 4 |  | 4 | 2021-02-16 |  | -31569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Carver | 5001002 | 2330 | 1992 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-16 |  | -31569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Carver | 5016871 | 2366 | 23.8 | PV & Battery | TBD | 2021-01-25 | 2021-02-05 | 9 |  | 9 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5017076 | 2474 | 19 | Battery | TBD | 2021-01-21 | 2021-02-05 | 11 |  | 11 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | Carlisle | 5017153 | 1741 | 35.2 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | 8 |  | 8 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 5018578 | 2601 | 120 | PV | TBD | 2021-01-21 | 2021-02-05 | 11 |  | 11 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Holliston | 5025553 | 1746 | 120 | PV | TBD | 2020-12-31 | 2021-02-05 | 26 |  | 26 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | Canton | 5057342 | 2021 | 7.6 | PV | TBD | 2021-01-27 | 2021-02-05 | 7 |  | 7 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Yarmouth | 5057452 | 2673 | 188 | PV | TBD | 2021-01-27 | 2021-02-05 | 7 |  | 7 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5057606 | 2420 | 20 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | 8 |  | 8 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Lexington | 5058397 | 2421 | 20 | PV & Battery | TBD | 2020-11-06 | 2021-02-05 | 65 |  | 65 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online
NSTAR | West Barnstable | 5058535 | 2668 | 20.88 | PV | TBD | 2021-02-05 | 2021-02-05 | 0 |  | 0 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Kingston | 5077570 | 2364 | 22.8 | PV & Battery | TBD | 2021-01-21 | 2021-02-08 | 12 |  | 12 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5077813 | 2492 | 10 | Battery | TBD | 2021-02-05 | 2021-02-08 | 1 |  | 1 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5077946 | 1722 | 466.6 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5077981 | 1722 | 233.2 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078034 | 1722 | 200 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078087 | 1722 | 100 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087787 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087888 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087946 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088024 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088121 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088220 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088274 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088314 | 1720 | 500 | PV | TBD | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097801 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097909 | 1720 | 1000 | PV & Battery | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 5099394 | 1801 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Hopkinton | 5099581 | 1848 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Westwood | 5099732 | 2090 | 15.2 | PV | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0
NSTAR | Pocasset | 5099887 | 2559 | 20 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acton | 5103412 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5112763 | 1748 | 166.6 | PV | TBD | 2021-02-10 | 2021-02-10 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marston Mills | 5113061 | 2648 | 433 | PV | TBD | 2021-01-06 | 2021-02-10 | 25 |  | 25 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marston Mills | 5113167 | 2648 | 500 | PV | TBD | 2021-01-06 | 2021-02-10 | 25 |  | 25 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 5113369 | 2743 | 17.6 | PV & Battery | TBD | 2020-12-17 | 2021-02-16 | 43 |  | 43 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Winchester | 5113444 | 1890 | 18 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Weston | 5113544 | 2493 | 33.8 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 5113610 | 1701 | 35.2 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5113674 | 1721 | 22.6 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Wayland | 5113728 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 5113853 | 2021 | 18 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2021-04-20 | [6 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Carver | 5114629 | 2330 | 5000 | PV & Battery | TBD | 2020-11-25 | 2021-01-25 | 43 |  | 43 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5122500 | 2420 | 30.2 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Ashland | 5122724 | 1721 | 250 | PV | TBD | 2021-02-08 | 2021-02-16 | 6 |  | 6 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5122828 | 1746 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 5123008 | 2330 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 5123184 | 2050 | 2000 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 5123430 | 2054 | 5000 | PV & Battery | TBD | 2020-12-31 | 2021-01-25 | 17 |  | 17 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5123449 | 1748 | 100 | PV | TBD | 2021-01-19 | 2021-01-20 | 1 |  | 1 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Holliston | 5131879 | 1746 | 150 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5131937 | 1721 | 200 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5132026 | 1746 | 466.6 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 5132026 | [7 empty] | 0 |  | 0 |  |  | 2022-08-03 | Online
NSTAR | East Wareham | 5132131 | 2538 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 5132174 | 2719 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 5132265 | 2452 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 5132388 | 2645 | 20 | Battery | TBD | 2021-02-08 | 2021-02-17 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Carver | 5132501 | 2330 | 3000 | PV & Battery | 3-81-81 | 2018-10-04 | 2018-10-11 | 5 |  | 5 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Sharon | 5132549 | 2067 | 30 | PV & Battery | TBD | 2020-10-15 | 2021-02-17 | 89 |  | 89 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 5140433 | 1746 | 100 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140517 | 1746 | 133.2 | PV | TBD | 2021-02-18 |  | -31571 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140889 | 1746 | 150 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5141509 | 1720 | 1125 | PV & Battery | TBD | 2020-12-31 | 2021-02-05 | 26 |  | 26 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5141690 | 2717 | 25 | PV | TBD | 2020-12-30 | 2021-02-10 | 30 |  | 30 | 2021-03-03 |  | -31580 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-27 | Online
NSTAR | Brewster | 5149756 | 2601 | 13.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-08 | 1 |  | 1 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-20 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5149891 | 1720 | 84 | PV | TBD | 2021-02-10 | 2021-02-19 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-05 | Online
NSTAR | Lexington | 5149929 | 2421 | 19.86 | battery | TBD | 2021-02-19 | 2021-02-19 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online
NSTAR | Natick | 5158094 | 1760 | 26.4 | PV & Battery | TBD | 2021-02-19 | 2021-03-01 | 6 |  | 6 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Watertown | 5164450 | 2472 | 66.6 | PV | TBD | 2021-02-17 | 2021-02-22 | 3 |  | 3 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-01 | Online
NSTAR | Wayland | 5164657 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | 10 |  | 10 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Sudbury | 5164789 | 1776 | 36 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | 10 |  | 10 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 5164886 | 2492 | 19.84 | battery | TBD | 2021-02-18 | 2021-02-23 | 3 |  | 3 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-26 | Online
NSTAR | Ashland | 5174138 | 1721 | 199.8 | PV | TBD | 2021-02-23 |  | -31574 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-06 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marshfield | 5174339 | 2050 | 172 | PV | TBD | 2021-02-17 | 2021-02-23 | 4 |  | 4 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01
NSTAR | Orleans | 5174743 | 2653 | 18.32 | PV & Battery | TBD | 2021-02-18 | 2021-02-23 | 3 |  | 3 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | North Chatham | 5174898 | 2650 | 17.6 | battery | TBD | 2021-02-23 | 2021-02-25 | 2 |  | 2 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | East Falmouth | 5184793 | 2536 | 22.32 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | 4 |  | 4 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5184938 | 2367 | 233.2 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-22 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 5193836 | 2332 | 19.5 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | 4 |  | 4 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Mattapoisett | 5193909 | 2739 | 148.92 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-18 |  | -31591 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 5202637 | 2653 | 262.5 | Fuel Cell | TBD | 2021-02-26 | 2021-02-26 | 0 |  | 0 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Sharon | 5215247 | 2067 | 30.2 | PV & Battery | TBD | 2020-12-14 |  | -31523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Harwich | 5233905 | 2645 | 72 | Wind | TBD | 2020-01-22 | 2021-03-02 | 289 |  | 289 | 2021-03-30 |  | -31599 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5233972 | 2673 | 187.5 | PV & Battery | TBD | 2021-02-25 |  | -31576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5243395 | 2664 | 5325 | PV & Battery | TBD | 2021-02-17 | 2021-03-02 | 9 |  | 9 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5243558 | 2360 | 1519.1 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | 5 |  | 5 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5243871 | 2021 | 499 | PV & Battery | TBD | 2020-12-30 | 2021-03-02 | 44 |  | 44 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5244434 | 1754 | 495.3 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 5247195 | 2670 | 5 | battery | TBD | 2021-02-17 | 2021-03-05 | 12 |  | 12 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5247213 | 1760 | 17.6 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | 10 |  | 10 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Weston | 5247231 | 2493 | 35.2 | PV | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5247359 | 2673 | 17.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Online
NSTAR | New Bedford | 5256352 | 2745 | 445 | PV | TBD | 2021-02-18 | 2021-03-05 | 11 |  | 11 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0
NSTAR | Harwich | 5256465 | 2645 | 255 | PV | TBD | 2021-02-18 | 2021-03-05 | 11 |  | 11 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5256556 | 1754 | 774.3 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 5256604 | 1754 | 1400.5 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Walpole | 5256722 | 2032 | 15.2 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Marion | 5256768 | 2738 | 25.2 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 5256844 | 2135 | 43.2 | PV | TBD | 2021-02-03 | 2021-03-05 | 22 |  | 22 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Natick | 5273003 | 1760 | 19.86 | Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Orleans | 5273198 | 2643 | 17.4 | PV | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5273453 | 1720 | 30.2 | PV & Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5273636 | 2021 | 20 | PV & Battery | TBD | 2021-03-02 | 2021-03-08 | 4 |  | 4 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Online
NSTAR | Lincoln | 5273781 | 2748 | 15.2 | PV | TBD | 2021-03-09 | 2021-03-09 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Dartmouth | 5273833 | 2748 | 15 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | 10 |  | 10 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sharon | 5286859 | 2067 | 15.2 | PV | TBD | 2020-10-15 | 2021-03-02 | 98 |  | 98 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 5287061 | 2130 | 18 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 5287511 | 2366 | 19.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 5287647 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 5298461 | 2474 | 17.68 | Battery | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Online
NSTAR | Wellfleet | 5298773 | 2663 | 18.16 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5299014 | 2538 | 19 | PV | TBD | 2021-02-19 | 2021-03-10 | 13 |  | 13 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-11-12 | Online
NSTAR | West Tisbury | 5299167 | 2575 | 16.225 | PV | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | New Bedford | 5299345 | 2740 | 120 | PV | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Onset | 5308165 | 2053 | 33.3 | PV | TBD | 2021-02-12 | 2021-02-24 | 8 |  | 8 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Online
NSTAR | Arlington | 5308545 | 2474 | 4.93 | PV | TBD | 2021-02-23 | 2021-02-23 | 0 |  | 0 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5317803 | 1803 | 35.2 | PV & Battery | TBD | 2020-12-14 | 2021-03-12 | 64 |  | 64 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0
NSTAR | Chestnut Hill | 5333163 | 2467 | 100.8 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-20 | Online
NSTAR | West Barnstable | 5333489 | 2668 | 450 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5333657 | 2494 | 86.4 | PV | TBD | 2021-01-27 | 2021-03-15 | 33 |  | 33 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-31 | Online
NSTAR | Chestnut Hill | 5333799 | 2467 | 86.4 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5333868 | 2673 | 999 | PV & Battery | TBD | 2021-03-02 | 2021-03-15 | 9 |  | 9 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 5343412 | 1776 | 400 | PV | TBD | 2021-03-16 | 2021-03-15 | -3 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0
NSTAR | Milton | 5343599 | 2364 | 125 | PV | TBD | 2021-02-25 | 2021-03-16 | 13 |  | 13 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Natick | 5343911 | 1760 | 10 | Battery | TBD | 2021-03-12 | 2021-03-16 | 2 |  | 2 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online
NSTAR | Hatchville | 5344212 | 2536 | 44.98 | PV | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Needham | 5354359 | 2492 | 20 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-01 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5354616 | 1860 | 17.6 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Hopkinton | 5354874 | 1748 | 240 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 5354925 | 1748 | 233.2 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online
NSTAR | Marston Mills | 5355181 | 2648 | 19.84 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online
NSTAR | Needham | 5355247 | 2492 | 24.86 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 5355312 | 2744 | 480 | PV | 2-7-7 | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | 2018-10-10 | [6 empty] | 0 |  | 0 | [9 empty] | Private
NSTAR | Acton | 5367340 | 1720 | 199.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377708 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-07 |  | -31605 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377796 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-06 |  | -31604 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dartmouth | 5392200 | 2748 | 21.4 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 5392364 | 2649 | 17.6 | PV & Battery | TBD | 2021-03-12 | 2021-03-22 | 6 |  | 6 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 5392588 | 2136 | 16 | PV | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 5392648 | 2125 | 15.2 | PV | TBD | 2021-02-12 | 2021-03-22 | 26 |  | 26 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-10 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 5392760 | 2067 | 250 | PV | TBD | 2021-03-16 | 2021-03-22 | 4 |  | 4 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 5392843 | 2026 | 250 | PV | TBD | 2021-03-17 | 2021-03-22 | 3 |  | 3 | 2021-05-04 |  | -31624 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0
NSTAR | Newton | 5392881 | 2459 | 19.84 | PV & Battery | TBD | 2021-03-17 | 2021-03-22 | 3 |  | 3 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Vineyard Haven | 5392988 | 2568 | 16.26 | PV & Battery | TBD | 2021-03-15 | 2021-03-22 | 5 |  | 5 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | Framingham | 5393050 | 1701 | 10 | Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5393125 | 2360 | 499 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393165 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393188 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5402282 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403022 | 2420 | 250 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403190 | 2420 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403580 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403662 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403782 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 5403892 | 1803 | 52.2 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 5404047 | 2461 | 158.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online
NSTAR | Newton | 5404188 | 2461 | 86.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 5414087 | 2360 | 1366.4 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | 5 |  | 5 | 2021-04-09 |  | -31607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5415234 | 2717 | 1000 | PV & Battery | 2-102-608 | 2016-12-14 | 2016-12-27 | 9 |  | 9 | 2017-01-19 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-05-22 | 30592 |  | 30592 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-28 | Online
NSTAR | Marston Mills | 5447070 | 2648 | 15.2 | PV | TBD | 2021-03-17 | 2021-03-29 | 8 |  | 8 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5447224 | 1760 | 16.24 | PV | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5447287 | 1803 | 17.6 | Battery | TBD | 2021-03-17 | 2021-03-29 | 8 |  | 8 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 5447348 | 2748 | 27.28 | PV & Battery | TBD | 2021-03-17 |  | -31590 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Plymouth | 5447376 | 2360 | 747 | PV & Battery | TBD | 2021-03-05 | 2021-03-29 | 16 |  | 16 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-10 | [7 empty] | 0 |  | 0
NSTAR | Centerville | 5447504 | 2632 | 15.68 | Battery | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brookline | 5447826 | 2445 | 25 | PV & Battery | TBD | 2020-12-16 | 2021-03-29 | 73 |  | 73 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0
NSTAR | East Walpole | 5483759 | 2032 | 26.4 | PV & Battery | TBD | 2021-03-29 | 2021-04-01 | 3 |  | 3 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5483849 | 2538 | 21.4 | PV | TBD | 2021-03-29 | 2021-04-01 | 3 |  | 3 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-21 | Online
NSTAR | Hyannis | 5483911 | 2601 | 400 | PV | TBD | 2021-03-16 | 2021-04-01 | 12 |  | 12 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5483954 | 2673 | 160 | PV | TBD | 2021-03-16 | 2021-04-01 | 12 |  | 12 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Hyannisport | 5518451 | 2678 | 28 | Battery | TBD | 2021-04-09 | 2021-04-09 | 0 |  | 0 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Plymouth | 5518643 | 2360 | 25 | PV & Battery | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Falmouth | 5518931 | 2540 | 27.6 | PV & Battery | TBD | 2021-01-26 | 2021-03-19 | 38 |  | 38 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 5530688 | 2130 | 199.8 | PV | TBD | 2020-07-01 | 2021-04-06 | 199 |  | 199 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | Somerville | 5540752 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-15 | 9 |  | 9 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 5566155 | 1748 | 1000 | PV | TBD | 2021-03-17 | 2021-04-13 | 19 |  | 19 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 5577223 | 2026 | 86.4 | PV | TBD | 2021-02-25 | 2021-04-12 | 32 |  | 32 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Framingham | 5587228 | 1702 | 167.32 | PV | TBD | 2021-04-13 | 2021-04-14 | 1 |  | 1 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1932-09-13 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 5608635 | 2081 | 15.2 | PV | TBD | 2020-09-08 | 2021-04-16 | 158 |  | 158 | 2021-05-05 |  | -31625 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 5758561 | 2660 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-05-04 | 106 |  | 106 | 2021-05-19 |  | -31635 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5758591 | 2367 | 742 | PV & Battery | TBD | 2021-02-25 | 2021-05-04 | 48 |  | 48 | 2021-05-19 |  | -31635 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 5813985 | 2633 | 100.8 | PV & Battery | TBD | 2020-08-19 | 2021-05-14 | 192 |  | 192 | 2021-05-27 |  | -31641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5913979 | 2476 | 16 | Battery | TBD | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Hatchville | 9568068 | 2536 | 4000 | PV & Battery |  | 2020-08-19 | 2020-08-24 | 3 | 0 | 3 | 2020-09-16 |  | -31460 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | [5 empty] | Private
NSTAR | Kingston | 23815557 | 2364 | 19.27 | PV | 3-17-910 | 2019-12-05 | 2019-12-10 | 3 |  | 3 | 2020-01-15 |  | -31285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 2065453a | 2367 | 1000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | [5 empty] | Private
NSTAR | Plympton | 2065453b | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | [5 empty] | Private
NSTAR | Plympton | 2065453c | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | [5 empty] | Private
NSTAR | Canton | 2093030b | 2021 | 990 | PV | 470-H7 | 2015-08-31 | 2015-09-04 | 4 |  | 4 | 2015-09-09 |  | -30150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  |  | Cust Docs
NSTAR | Plymouth | 2155/2249 | 2360 | 4750 | PV | 3-89-89 | 2012-06-20 | 2012-07-09 | 12 | 4 | 8 | 2012-07-18 | 2012-08-27 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-28 |  | 2012-06-01 | No | Expedited |  |  |  | 0 | 0 | 0 |  |  | 2014-12-02 | Online | [5 empty] | Gov't | Y
NSTAR | Freetown | 2238661 - A | 2717 | 4090 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2238661 - B | 2717 | 4990 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Rochester | 2260703 - A | 2770 | 2000 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-30
NSTAR | Rochester | 2260703 - B | 2770 | 540 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2287285-B | 2125 | 500 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-19 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2287856-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-D | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-E | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-F | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-G | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-H | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2292181 - A | 2330 | 2000 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2292181 - B | 2330 | 466 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 & 2334854 | 2745 | 695.6 | PV | TBD | 2019-03-25 | 2020-03-29 | 264 |  | 264 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 24-9982 | 1701 | 22 | PV & Battery | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | ISO NE | 2770 | 15000 | PV & Battery | 3-703-703 | 2018-12-18 | 2018-12-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | MULTIPLE WOS | 2081 | 2167.6 | PV | 146-H4 | 2019-01-14 | 2019-03-28 | 53 |  | 53 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | pp02295853 | 2770 | 2000 | PV & Battery | 3-85-85 | 2021-01-17 | 2021-01-17 | 0 |  | 0 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | PP02407747 | 2601 | 19.92 | PV | TBD | 2020-10-15 | 2020-11-12 | 20 |  | 20 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Provincetown | TBD | 2657 | 28.13 | PV | TBD | 2019-08-06 | 2019-08-08 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2019-01-06 | Online
NSTAR | Ashland | TBD | 1721 | 4450 | PV | TBD | 2017-05-08 | 2017-05-25 | 13 |  | 13 | 2017-06-15 |  | -30611 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Dedham | TBD | 2026 | 20 | PV | TBD | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Wareham | TBD | 2571 | 1750 | PV & Battery | 416-H1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-02-12 | Withdrawn
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Lincoln | TBD | 1773 | 109.6 | PV & Battery | 416-H1 | 2018-01-10 |  | -30760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-16 | 2018-03-14 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-23 | 2018-03-14 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 27.48 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 15 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Weston | TBD | 2493 | 21.6 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Provincetown | TBD | 2657 | 10 | PV & Battery | 4-96-675 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rcohester | TBD | 2770 | 22.6 | PV & Battery | 3-702-702 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 18.35 | PV & Battery | 416-H1 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Darmouth | TBD | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 8300 | PV & Battery | 416-H1 | 2018-03-01 | 2018-03-14 | 9 |  | 9 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | TBD | 1773 | 17.6 | PV & Battery | 416-H1 | 2018-03-16 |  | -30807 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 153.2 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 196.6 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | TBD | 2472 | 166.5 | PV | 467-H6 | 2018-03-29 | 2018-03-29 | 0 |  | 0 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 10 | PV & Battery | 2-241-241 | 2018-04-04 |  | -30820 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 9878 | PV & Battery | 416-H1 | 2018-04-06 |  | -30822 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | TBD | 2122 | 64 | PV | 416-H1 | 2018-04-12 | 2018-04-27 | 11 |  | 11 | 2018-05-07 |  | -30843 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2538 | 7.6 | PV | 416-H1 | 2018-04-19 |  | -30831 |  | 0 | 2018-04-18 |  | -30830 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 5 | PV | 342-H4 | 2018-04-26 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | TBD | 2770 | 4200 | PV & Battery | 4-80B-514 | 2018-04-30 | 2018-07-20 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Yarmouth | TBD | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV | 416-H1 | 2018-05-18 | 2018-05-30 | 8 |  | 8 | 2018-06-12 |  | -30869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 995 | PV & Battery | 416-H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 300 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 660 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 360 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 4000 | PV | 4-80B-514 | 2018-07-18 | 2018-07-23 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 685 | PV | 2-41-41 | 2018-08-06 | 2018-08-09 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2142 | 63.3 | PV | 416-H1 | 2018-09-24 | 2018-09-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 143.2 | PV | TBD | 2019-01-24 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennis | TBD | 2660 | 4951 | PV | TBD | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 43.2 | PV | TBD | 2019-02-07 |  | -31041 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4980 | PV & Battery | TBD | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2492 | 23.5 | PV | TBD | 2019-02-12 |  | -31044 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 81 | PV | TBD | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 699.9 | PV | TBD | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.485 | PV | TBD | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | TBD | 2739 | 5000 | PV | TBD | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2702 | 4500 | PV & Battery | tbd | 2019-04-10 |  | -31085 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2745 | 5000 | PV | TBD | 2019-04-26 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2138 | 66.6 | PV | TBD | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Newton | TBD | 2465 | 20 | PV & Battery | TBD | 2019-05-31 |  | -31122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 25.2 | PV & Battery | TBD | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | TBD | 1803 | 15.2 | PV | TBD | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | TBD | 2710 | 100 | PV | TBD | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 25.2 | PV | TBD | 2019-08-07 |  | -31170 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | TBD | 2666 | 16.4 | PV | TBD | 2019-08-28 |  | -31185 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4000 | PV & Battery | TBD | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 998 | PV | TBD | 2019-10-11 |  | -31217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | TBD | 2067 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 15.2 | PV | TBD | 2019-10-21 |  | -31223 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.2 | PV | TBD | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 19 | PV | TBD | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 180.96 | PV | TBD | 2019-11-04 |  | -31233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Onset | TBD | 2558 | 25 | PV & Battery | TBD | 2019-11-21 |  | -31246 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 2000 | PV & Battery | TBD | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 19.27 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 330 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2494 | 3623 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | TBD | 2453 | 748 | PV | TBD | 2019-12-09 |  | -31258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 15.2 | PV | TBD | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | TBD | 2421 | 130 | PV | TBD | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Walpole | TBD | 2032 | 23.8 | PV | TBD | 2019-12-11 |  | -31260 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 |  | -31265 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 | 2019-12-23 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2130 | 37.8 | PV | TBD | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2120 | 200 | PV | TBD | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Falmouth | TBD | 2556 | 15.2 | PV | TBD | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 1500 | PV & Battery | TBD | 2020-01-23 |  | -31291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 6 | PV | TBD | 2020-01-28 |  | -31294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 20 | Battery | TBD | 2020-01-28 |  | -31294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 14 | Battery | TBD | 2020-01-29 |  | -31295 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | TBD | 2081 | 16 | PV | TBD | 2020-02-13 |  | -31306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2714 | 2958 | Battery | TBD | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | TBD | 1778 | 29 | Battery | TBD | 2020-02-21 |  | -31312 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 15.2 | PV | TBD | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | TBD | 2649 | 153.85 | PV | TBD | 2020-03-03 |  | -31319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | TBD | 2026 | 108.375 | PV | TBD | 2020-03-03 |  | -31319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sagamore Beach | TBD | 2561 | 150.45 | PV | TBD | 2020-03-05 |  | -31321 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | - | PV | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 8.5 | PV | TBD | 2020-03-20 |  | -31332 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | TBD | 2645 | 175.9 | PV | TBD | 2020-03-25 | 2020-05-15 | 37 |  | 37 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 9999 | PV & Battery | TBD | 2020-04-09 | 2020-04-15 | 4 |  | 4 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 400 | PV | TBD | 2020-04-09 | 2020-04-17 | 6 |  | 6 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 999 | PV & Battery | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 15.2 | PV | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 90 | Battery | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 15.2 | PV | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 5000 | PV & Battery | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | TBD | 2019 | 4990 | PV & Battery | TBD | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-15 |  | -31393 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 499 | PV & Battery | TBD | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | TBD | 2030 | 15.2 | PV | TBD | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 573 | PV & Battery | TBD | 2020-07-29 |  | -31425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 610 | Battery | TBD | 2020-08-19 |  | -31440 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Aquinnah | TBD | 2635 | 144.8 | PV & Battery | TBD | 2020-08-19 |  | -31440 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | TBD | 1770 | 39 | PV & Battery | TBD | 2020-08-25 |  | -31444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 4000 | PV & Battery | TBD | 2020-09-02 |  | -31450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 2875 | PV | TBD | 2020-09-18 |  | -31462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2740 | 250 | PV | TBD | 2020-09-22 |  | -31464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 200 | PV | TBD | 2020-10-27 |  | -31489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 5 | battery | TBD | 2020-11-06 |  | -31497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 20.5 | Battery | TBD | 2020-11-13 |  | -31502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 16.19 | PV | TBD | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 149.3 | PV | TBD | 2020-12-07 |  | -31518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 17.6 | PV & Battery | TBD | 2020-12-07 |  | -31518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 15.2 | PV | TBD | 2020-12-31 |  | -31536 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | TBD | 1757 | 180 | PV | TBD | 2021-01-20 |  | -31550 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 18.5 | PV | TBD | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 3000 | PV & Battery | TBD | 2021-01-27 |  | -31555 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 15 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | TBD | 2021 | 16 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 2000 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 4990 | PV & Battery | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2144 | 170.4 | PV | TBD | 2021-02-18 |  | -31571 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | TBD | 2474 | 15.2 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | TBD | 2364 | 1 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Centerville | TBD | 2632 | 15.2 | PV | TBD | 2021-02-25 |  | -31576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 15 | PV | TBD | 2021-03-02 |  | -31579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Auburndale | TBD | 2466 | 10 | Battery | TBD | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 500 | PV | TBD | 2021-03-19 |  | -31592 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 1500 | PV | TBD | 2021-03-29 |  | -31598 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | ESMAEX-00027 | 02719 | 300 | Battery | 2-221-221 | 2021-04-02 | 2021-05-21 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-11 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Fairhaven | ESMAEX-00028 | 02719 | 223 | Battery | 2-220-206 | 2021-04-02 | 2021-05-20 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Newton Highlands | ESMAEX-00002 | 02461 | 7.68 | Battery | 292-H14 | 2021-03-29 | 2021-04-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-11 | Online | [11 empty] | 20
NSTAR | Brewster | ESMAEX-00097 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [12 empty] | STA_975 Orleans
NSTAR | Canton | ESMAEX-00034 | 02021 | 250 | Solar | 470-H11 | 2021-04-07 | 2021-05-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-26 | Online | [12 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-00010 | 02421 | 420 | Solar | 320-H5XY | 2021-03-30 | 2021-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [12 empty] | STA_320 Lexington
NSTAR | New Bedford | ESMAEX-00009 | 02745 | 73.3 | Solar | 2-104-104 | 2021-03-30 | 2021-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Marion | ESMAEX-00063 | 02738 | 21.21 | Solar & Battery | 3-85-85 | 2021-04-21 | 2021-05-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Plymouth | ESMAEX-00166 | 02360 | 8.7 | Solar | 3-90-90 | 2021-06-04 | 2021-07-06 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | South Sandwich | ESMAEX-00143 | 02563 | 10 | Battery | 4-455-455 | 2021-05-20 | 2021-06-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Newton Highlands | ESMAEX-00023 | 02461 | 18.88 | Solar & Battery | 292-H5 | 2021-04-02 | 2021-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0 |  |  | 2022-01-04 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-00020 | 02081 | 20 | Solar & Battery | 146-H4 | 2021-04-01 | 2021-04-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-09 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online | [12 empty] | STA_146 Walpole
NSTAR | Mattapoisett | ESMAEX-00425 | 02739 | 79.75 | Solar | 2-304-304 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-14 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Brighton | ESMAEX-00030 | 02135 | 150 | Internal Combustion Engine | 467-H12 | 2021-04-06 | 2021-05-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [12 empty] | STA_467 Watertown
NSTAR | New Bedford | ESMAEX-00049 | 02745 | 166.6 | Solar | 2-82-82 | 2021-04-14 | 2021-05-12 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-19 | Online | [12 empty] | STA_612 Acushnet
NSTAR | Acton | ESMAEX-00032 | 01720 | 3800 | Solar & Battery | 416-H8 | 2021-04-07 | 2021-04-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [9 empty] | 2021 ASO Batch 1 |  |  | STA_416 Maynard
NSTAR | Needham | ESMAEX-00041 | 02494 | 250 | Solar | 148-H7 | 2021-04-13 | 2021-05-11 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Online | [12 empty] | STA_148 Needham
NSTAR | South Yarmouth | ESMAEX-00060 | 02664 | 250 | Battery |  | 2021-04-19 | 2021-05-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Online | [11 empty] | 250
NSTAR | Jamaica Plain | ESMAEX-00065 | 02130 | 30 | Solar | 396-1050H4 | 2021-04-21 | 2021-05-11 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Online
NSTAR | Holliston | ESMAEX-00058 | 01746 | 133.2 | Solar | 65-H2 | 2021-04-16 | 2021-05-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-12-07 | Online | [12 empty] | STA_065 Medway
NSTAR | New Bedford | ESMAEX-00053 | 02740 | 100 | Solar | 2-42-42 | 2021-04-14 | 2021-05-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Bourne | ESMAEX-00059 | 02532 | 499 | Solar & Battery | 4-86-86 | 2021-04-16 | 2021-05-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | Waquoit | ESMAEX-00367 | 02536 | 20 | Solar & Battery | 4-77B-456 | 2021-08-27 | 2021-09-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Online
NSTAR | South Sandwich | ESMAEX-00055 | 02563 | 250 | Solar | 4-87A-87A | 2021-04-14 | 2021-05-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | Brewster | ESMAEX-00096 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [12 empty] | STA_975 Orleans
NSTAR | Eastham | ESMAEX-00073 | 02642 | 18.41 | Solar & Battery | 4-94A-94A | 2021-04-23 | 2021-06-04 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Online | [12 empty] | STA_975 Orleans
NSTAR | New Bedford | ESMAEX-00062 | 02740 | 16.57 | Solar & Battery | 2-531-531 | 2021-04-20 | 2021-05-18 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2021-11-10 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Acton | ESMAEX-00071 | 01720 | 16.23 | Solar | 416-H9 | 2021-04-23 | 2021-05-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | [11 empty] | 10 | STA_416 Maynard
NSTAR | Chatham | ESMAEX-00070 | 02633 | 22 | Solar & Battery | 4-95B-941 | 2021-04-22 | 2021-06-02 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [11 empty] | 11.52 | STA_975 Orleans
NSTAR | Plympton | ESMAEX-00081 | 02367 | 999 | Solar & Battery | 3-15-15 | 2021-04-28 | 2021-06-01 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process
NSTAR | East Freetown | ESMAEX-00079 | 02717 | 69.2 | Solar | 2-102-102 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | East Freetown | ESMAEX-00080 | 02717 | 69.2 | Solar | 2-102-604 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Woburn | ESMAEX-00082 | 01801 | 17.4 | Solar | 533-H9 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Holliston | ESMAEX-00101 | 01746 | 140 | Solar | 65-H2 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-18 | Online | [12 empty] | STA_065 Medway
NSTAR | Eastham | ESMAEX-00276 | 02642 | 20 | Solar & Battery | 4-94A-94A | 2021-07-30 | 2021-08-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Online | [12 empty] | STA_975 Orleans
NSTAR | Falmouth | ESMAEX-00132 | 02540 | 5 | Solar | 4-76-436 | 2021-05-18 | 2021-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | West Falmouth | ESMAEX-00109 | 02574 | 17.772 | Solar & Battery | 4-98A-98A | 2021-05-07 | 2021-06-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2021-11-15 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Waltham | ESMAEX-00098 | 02451 | 1994 | Internal Combustion Engine | 526-1361H | 2021-05-03 | 2021-05-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online | [9 empty] | 2021 ASO Batch 1 |  | 0 | STA_450 Trapelo Road
NSTAR | East Harwich | ESMAEX-00111 | 02645 | 20 | Battery | 4-95A-95A | 2021-05-10 | 2021-06-22 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | North Cambridge | ESMAEX-00182 | 02140 | 22.8 | Solar | 824-25 | 2021-06-13 | 2021-06-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | [12 empty] | STA_828 Alewife
NSTAR | North Dartmouth | ESMAEX-00102 | 02747 | 86.4 | Solar | 2-533-503 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Westport | ESMAEX-00104 | 02790 | 20 | Solar | 2-532-532 | 2021-05-05 | 2021-06-04 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Needham | ESMAEX-00121 | 02492 | 18.56 | Solar | 148-H7 | 2021-05-13 | 2021-05-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-02 | Online | [12 empty] | STA_148 Needham
NSTAR | Framingham | ESMAEX-00105 | 01701 | 16 | Solar | 342-H4 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-00122 | 01760 | 251.3 | Solar | 433-H12 | 2021-05-13 | 2021-05-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Dorchester | ESMAEX-00108 | 02124 | 15.2 | Solar | 496-H8 | 2021-05-06 | 2021-05-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Waltham | ESMAEX-00113 | 02451 | 3012 | Internal Combustion Engine | 531-1359H | 2021-05-10 | 2021-06-18 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2021 ASO Batch 1 |  |  | STA_450 Trapelo Road
NSTAR | Brighton | ESMAEX-00117 | 02135 | 100 | Solar | 329-H6 | 2021-05-11 | 2021-06-11 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [12 empty] | STA_329 Brighton
NSTAR | South Boston | ESMAEX-00116 | 02127 | 100 | Solar | 385-H1 | 2021-05-11 | 2021-06-11 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [12 empty] | STA_385D K Street
NSTAR | Waban | ESMAEX-00119 | 02468 | 10 | Battery | 292-H2 | 2021-05-13 | 2021-06-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-01 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Marshfield | ESMAEX-00129 | 02050 | 499 | Solar & Battery | 3-24B-915 | 2021-05-17 | 2021-06-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [7 empty] | ESMAEX-00129 studied W/ESMAEX-00147 |  | 2021 ASO - SEMA |  |  | STA_738 Duxbury
NSTAR | Arlington | ESMAEX-00151 | 02476 | 20 | Solar | 320-H7 | 2021-05-27 | 2021-06-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Online | [12 empty] | STA_320 Lexington
NSTAR | Chatham | ESMAEX-00138 | 02633 | 10.15 | Solar | 4-95B-941 | 2021-05-19 | 2021-06-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-27 | Online | [12 empty] | STA_975 Orleans
NSTAR | Falmouth | ESMAEX-00124 | 02540 | 36.54 | Solar | 4-72-72 | 2021-05-15 | 2021-06-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Online | [12 empty] | STA_933 Falmouth
NSTAR | Weston | ESMAEX-00142 | 02493 | 20 | Solar & Battery | 282-H1 | 2021-05-20 | 2021-06-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online | [12 empty] | STA_282 Waltham
NSTAR | Ashland | ESMAEX-00148 | 01721 | 75 | Solar | 274-H1 | 2021-05-24 | 2021-06-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Waban | ESMAEX-00139 | 02468 | 15 | Solar & Battery | 292-H7 | 2021-05-19 | 2021-05-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Woburn | ESMAEX-00141 | 01801 | 20 | Solar & Battery | 391-H11 | 2021-05-20 | 2021-06-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online | [12 empty] | STA_391 Burlington
NSTAR | Forestdale | ESMAEX-00149 | 02644 | 20 | Solar & Battery | 4-81B-443 | 2021-05-25 | 2021-06-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [8 empty] | Cape |  |  | 9.6 | STA_916 Sandwich
NSTAR | Hopkinton | ESMAEX-00145 | 01748 | 250 | Solar | 126-H1 | 2021-05-21 | 2021-05-26 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-03 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-00380 | 01801 | 216 | Solar | 375-H6 | 2021-09-02 | 2021-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-00175 | 01803 | 499.5 | Solar | 391-H12 | 2021-06-08 | 2021-06-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Online | [12 empty] | STA_391 Burlington
NSTAR | North Harwich | ESMAEX-00217 | 02645 | 10 | Battery | 4-89A-89A | 2021-06-28 | 2021-07-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-09 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Winchester | ESMAEX-00169 | 01890 | 2.03 | Solar | 211-H7XY | 2021-06-07 | 2021-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | [12 empty] | STA_211 Woburn
NSTAR | Mattapan | ESMAEX-00192 | 02126 | 78.8 | Solar | 496-H8 | 2021-06-18 | 2021-07-27 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-00174 | 01803 | 233.1 | Solar | 391-H12 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-06-03 | Online | [12 empty] | STA_391 Burlington
NSTAR | Marstons Mills | ESMAEX-00172 | 02648 | 20.67 | Battery | 4-88-88 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-29 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Sudbury | ESMAEX-00171 | 01776 | 34.2 | Solar | 342-H8 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Online | [11 empty] | 0 | STA_342 Sudbury
NSTAR | Burlington | ESMAEX-01605 | 01803 | 43.2 | Solar | 346-1395H1 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Online | [12 empty] | STA_391 Burlington
NSTAR | Carlisle | ESMAEX-00234 | 01741 | 15 | Battery | 533-H8 | 2021-07-12 | 2021-07-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-10-06 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Plymouth | ESMAEX-00822 | 02360 | 40.4 | Solar & Battery | 3-90-90 | 2022-02-08 | 2022-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Chestnut Hill | ESMAEX-00176 | 02467 | 16.57 | Solar & Battery | 467-H12 | 2021-06-09 | 2021-06-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-18 | Online | [11 empty] | 16.58 | STA_467 Watertown
NSTAR | Plympton | ESMAEX-00197 | 02367 | 499 | Solar | 3-15-15 | 2021-06-21 | 2021-07-27 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 499
NSTAR | Pocasset | ESMAEX-00188 | 02559 | 36.83 | Solar |  | 2021-06-15 | 2021-07-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online
NSTAR | Medway | ESMAEX-00184 | 02053 | 22 | Solar & Battery | 65-H3 | 2021-06-14 | 2021-06-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [11 empty] | 12 | STA_065 Medway
NSTAR | Mattapoisett | ESMAEX-00189 | 02739 | 9 | Solar | 2-306-306 | 2021-06-16 | 2021-07-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Truro | ESMAEX-00190 | 02666 | 50 | Solar & Battery | 4-96-96 | 2021-06-16 | 2021-07-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [11 empty] | 30 | STA_976 Wellfleet
NSTAR | Oak Bluffs | ESMAEX-00193 | 02557 | 19.92 | Solar | 4-99-224 | 2021-06-19 | 2021-07-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Kingston | ESMAEX-00196 | 02364 | 7.6 | Solar & Battery | 3-18-18 | 2021-06-21 | 2021-07-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Online
NSTAR | Walpole | ESMAEX-00191 | 02081 | 15.2 | Solar | 456-H1 | 2021-06-17 | 2021-07-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Online | [12 empty] | STA_456 Dover
NSTAR | Assonett | ESMAEX-00195 | 02702 | 15.2 | Solar | 2-606-606 | 2021-06-21 | 2021-08-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-01-20 | Online | [12 empty] | STA_661 Bell Rock
NSTAR | Bedford | ESMAEX-00211 | 01730 | 17.6 | Solar | 322-1397H1 | 2021-06-24 | 2021-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-05 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Mattapoisett | ESMAEX-00200 | 02739 | 18.28 | Solar | 2-306-306 | 2021-06-22 | 2021-07-27 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2021-12-22 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Cambridge | ESMAEX-00251 | 02139 | 129.6 | Solar | 875-1328 | 2021-07-20 | 2021-09-24 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [12 empty] | STA_875 East Cambridge
NSTAR | Hopkinton | ESMAEX-00228 | 01748 | 20 | Solar | 65-H7 | 2021-07-06 | 2021-07-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online | [12 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-00206 | 01773 | 17.6 | Solar | 320-H8 | 2021-06-23 | 2021-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-29 | Online | [12 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00235 | 02421 | 33.3 | Solar | 34-1352H1 | 2021-07-13 | 2021-08-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online | [12 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00210 | 02421 | 15.2 | Solar | 320-H5XY | 2021-06-24 | 2021-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [12 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-00213 | 01760 | 12.6 | Solar & Battery | 240-H6 | 2021-06-25 | 2021-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [12 empty] | STA_240 Framingham
NSTAR | East Falmouth | ESMAEX-00215 | 02536 | 15.2 | Solar | 4-98B-449 | 2021-06-25 | 2021-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Waban | ESMAEX-00218 | 02468 | 25 | Solar & Battery | 1701 | 2021-06-28 | 2021-07-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Dover | ESMAEX-00293 | 02030 | 3.8 | Solar | 456-H5 | 2021-08-09 | 2021-08-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-15 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [12 empty] | STA_456 Dover
NSTAR | Sudbury | ESMAEX-00259 | 01776 | 20 | Solar | 342-H6 | 2021-07-22 | 2021-08-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Online | [12 empty] | STA_342 Sudbury
NSTAR | West Wareham | ESMAEX-00219 | 02576 | 15.2 | Solar | 3-85-85 | 2021-06-29 | 2021-07-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-10-22 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Framingham | ESMAEX-00222 | 01701 | 9.8 | Solar & Battery | 342-H4 | 2021-07-01 | 2021-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Lincoln | ESMAEX-00226 | 01773 | 12.6 | Solar & Battery | 320-H6 | 2021-07-02 | 2021-07-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online | [12 empty] | STA_320 Lexington
NSTAR | Dartmouth | ESMAEX-00238 | 02747 | 148.92 | Solar | 2-532-532 | 2021-07-13 | 2021-07-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Westwood | ESMAEX-00265 | 02090 | 76 | Solar | 148-H3 | 2021-07-26 | 2021-08-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [12 empty] | STA_148 Needham
NSTAR | Arlington | ESMAEX-00304 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2021-08-12 | 2021-09-15 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online | [12 empty] | STA_211 Woburn
NSTAR | Maynard | ESMAEX-00232 | 01754 | 17.8 | Solar & Battery | 355-04 | 2021-07-12 | 2021-08-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [11 empty] | 0 | STA_416 Maynard
NSTAR | Brookline | ESMAEX-00231 | 02445 | 200 | Solar | 350-H8 | 2021-07-09 | 2021-07-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Sandwich | ESMAEX-00305 | 02644 | 60.5 | Solar |  | 2021-08-12 | 2021-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online
NSTAR | Needham | ESMAEX-00264 | 02492 | 23.4 | Solar | 148-04 | 2021-07-26 | 2021-08-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-11-29 | Online | [12 empty] | STA_148 Needham
NSTAR | Plymouth | ESMAEX-00570 | 02360 | 10 | Battery | 3-71-71 | 2021-11-05 | 2021-12-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-06 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Framingham | ESMAEX-00236 | 01701 | 4999 | Battery | 433-H2 | 2021-08-31 | 2021-09-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2023 ASO Batch 1 |  | 4999 | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-00252 | 01778 | 80 | Solar | 342-H3 | 2021-07-20 | 2021-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-00240 | 02451 | 233.1 | Solar |  | 2021-07-14 | 2021-07-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-24 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online
NSTAR | Burlington | ESMAEX-00302 | 01803 | 19.825 | Solar | 375-H14 | 2021-08-11 | 2021-09-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Carlisle | ESMAEX-00267 | 01741 | 18.18 | Solar | 512-1399H1 | 2021-07-27 | 2021-08-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Dennis | ESMAEX-00336 | 02638 | 262.5 | Fuel Cell | 4-92B-92B | 2021-08-20 | 2021-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online | [8 empty] | Cape |  |  | 100 | STA_968 Harwich
NSTAR | Allston | ESMAEX-00263 | 02134 | 133.2 | Solar | 329-H5 | 2021-07-23 | 2021-08-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online | [12 empty] | STA_329 Brighton
NSTAR | Sherborn | ESMAEX-00285 | 01770 | 19.7 | Solar | 130-H2 | 2021-08-04 | 2021-08-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-07 | Online | [12 empty] | STA_130 Holliston
NSTAR | Sherborn | ESMAEX-00248 | 01770 | 5.7 | Battery | 240-H1 | 2021-07-19 | 2021-08-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-02-18 | Online | [12 empty] | STA_240 Framingham
NSTAR | Maynard | ESMAEX-00247 | 01754 | 16.4 | Solar | 416-H1 | 2021-07-19 | 2021-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-02-02 | Online | [12 empty] | STA_416 Maynard
NSTAR | New Bedford | ESMAEX-00250 | 02745 | 15.2 | Solar | 2-106-160 | 2021-07-20 | 2021-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Burlington | ESMAEX-00337 | 01803 | 138.4 | Solar | 391-H9 | 2021-08-23 | 2021-09-21 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_391 Burlington
NSTAR | Roslindale | ESMAEX-00257 | 02131 | 10 | Battery | 516-06 | 2021-07-21 | 2021-08-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Online | [12 empty] | STA_110 Baker Street
NSTAR | West Yarmouth | ESMAEX-00278 | 02673 | 170 | Internal Combustion Engine |  | 2021-08-02 | 2021-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-04 | Online | [11 empty] | 0
NSTAR | Lexington | ESMAEX-00282 | 02420 | 11.52 | Battery | 533-H9 | 2021-08-03 | 2021-08-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Mashpee | ESMAEX-00273 | 02649 | 80 | Solar | 4-452-452 | 2021-07-28 | 2021-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Westwood | ESMAEX-00274 | 02090 | 24 | Solar & Battery | 148-H3 | 2021-07-29 | 2021-09-17 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Online | [12 empty] | STA_148 Needham
NSTAR | Brookline | ESMAEX-00313 | 02445 | 7.68 | Solar & Battery | 23N30 | 2021-08-13 | 2021-09-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Online | [12 empty] | STA_329 Brighton
NSTAR | Brookline | ESMAEX-00299 | 02445 | 19.764 | Solar | 350-H8 | 2021-08-10 | 2021-08-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Marion | ESMAEX-00270 | 02738 | 22.8 | Solar | 3-85-85 | 2021-07-28 | 2021-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Bellingham | ESMAEX-00298 | 02019 | 4947 | Battery | 65-H4 | 2021-08-10 | 2021-10-18 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [9 empty] | 2023 ASO Batch 1 |  |  | STA_065 Medway
NSTAR | Plymouth | ESMAEX-00271 | 02360 | 15 | Solar & Battery | 3-71-71 | 2021-07-28 | 2021-08-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-01-07 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Chestnut Hill | ESMAEX-00272 | 02467 | 5.16 | Battery | 496-H5 | 2021-07-28 | 2021-08-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Orleans | ESMAEX-00303 | 02653 | 15.2 | Solar & Battery | 4-94A-94A | 2021-08-12 | 2021-09-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [12 empty] | STA_975 Orleans
NSTAR | Acton | ESMAEX-00320 | 01720 | 66.6 | Solar | 416-H9 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_416 Maynard
NSTAR | Cummaquid | ESMAEX-00283 | 02637 | 18 | Solar | 4-92A-92A | 2021-08-03 | 2021-08-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Dedham | ESMAEX-00280 | 02026 | 86.4 | Solar | 148-H3 | 2021-08-02 | 2021-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-05 | Online | [12 empty] | STA_148 Needham
NSTAR | Marstons Mills | ESMAEX-00284 | 02648 | 6 | Solar | 4-87A-87A | 2021-08-03 | 2021-08-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | New Bedford | ESMAEX-00322 | 02745 | 249.9 | Solar | 2-79-404 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_612 Acushnet
NSTAR | Duxbury | ESMAEX-00287 | 02332 | 15.2 | Solar | 3-26-26 | 2021-08-04 | 2021-08-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
NSTAR | Dover | ESMAEX-00288 | 02030 | 10 | Battery | 456-H5 | 2021-08-05 | 2021-08-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-21 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [12 empty] | STA_456 Dover
NSTAR | Kingston | ESMAEX-00297 | 02364 | 10 | Battery | 3-51-980 | 2021-08-10 | 2021-08-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-15 | Online | [8 empty] | Plymouth |  |  |  | STA_727 Brook Street
NSTAR | Needham | ESMAEX-00393 | 02492 | 20 | Battery | 148-H4 | 2021-09-08 | 2021-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [12 empty] | STA_148 Needham
NSTAR | Norfolk | ESMAEX-00292 | 02056 | 15.29 | Solar & Battery | 65-H1 | 2021-08-09 | 2021-09-24 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Online | [12 empty] | STA_065 Medway
NSTAR | Hopkinton | ESMAEX-00317 | 01748 | 15.2 | Solar | 126-H2 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Waban | ESMAEX-00301 | 02468 | 7.67 | Solar & Battery | 292-H2 | 2021-08-11 | 2021-08-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Winchester | ESMAEX-00318 | 01890 | 17.58 | Solar & Battery | 211-07 | 2021-08-17 | 2021-10-15 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-14 | Online | [12 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-00315 | 02067 | 250 | Solar | 146-H1 | 2021-08-16 | 2021-09-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [11 empty] | 250 | STA_146 Walpole
NSTAR | New Bedford | ESMAEX-00340 | 02745 | 50 | Solar | 2-103-103 | 2021-08-23 | 2021-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online
NSTAR | Cambridge | ESMAEX-01118 | 02139 | 21.4 | Solar | 820-45 | 2022-04-26 | 2022-05-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [12 empty] | STA_402 Newton Street
NSTAR | Acton | ESMAEX-00365 | 01720 | 110.8 | Solar | 416-H8 | 2021-08-27 | 2021-09-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-15 | Online | [12 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-00473 | 01760 | 9.516 | Solar & Battery | 433-H12 | 2021-10-05 | 2021-10-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Dover | ESMAEX-00316 | 02030 | 12.685 | Solar & Battery | 456-H5 | 2021-08-16 | 2021-09-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online | [12 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-00312 | 02360 | 7.6 | Solar & Battery | 3-14-934 | 2021-08-13 | 2021-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-17 | [7 empty] | 0 |  | 0 |  |  | 2022-01-27 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Marshfield | ESMAEX-00495 | 02050 | 5.51 | Solar & Battery | 3-22-33J2 | 2021-10-13 | 2021-11-24 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-19 | Online | [12 empty] | STA_739 Marshfield
NSTAR | Carlisle | ESMAEX-00310 | 01741 | 15.2 | Solar & Battery | 512-1399H1 | 2021-08-13 | 2021-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2022-11-29 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-00607 | 02186 | 19.8 | Battery | 496-H2 | 2021-11-18 | 2022-01-06 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Cambridge | ESMAEX-00308 | 02138 | 17.6 | Solar & Battery | 825-18 | 2021-08-13 | 2021-10-21 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online | [12 empty] | STA_828 Alewife
NSTAR | Wayland | ESMAEX-00424 | 01778 | 7.68 | Battery | 278-H2 | 2021-09-20 | 2021-11-09 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-05-26 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Waltham | ESMAEX-00331 | 02451 | 100 | Solar | 450-H2 | 2021-08-19 | 2021-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | East Falmouth | ESMAEX-00319 | 02536 | 310 | Solar |  | 2021-11-10 | 2021-12-14 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online
NSTAR | Hopkinton | ESMAEX-00321 | 01748 | 17.6 | Solar & Battery | 126-H2 | 2021-08-17 | 2022-06-01 | 206 |  | 206 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Sherborn | ESMAEX-00323 | 01770 | 20 | Solar & Battery | 240-H1 | 2021-08-17 | 2021-10-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [11 empty] | 10 | STA_240 Framingham
NSTAR | Duxbury | ESMAEX-00326 | 02332 | 46.2 | Solar | 3-23-23 | 2021-08-18 | 2021-09-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Acton | ESMAEX-00328 | 01720 | 20 | Solar | 416-H8 | 2021-08-18 | 2021-09-22 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online | [12 empty] | STA_416 Maynard
NSTAR | Millis | ESMAEX-00379 | 02054 | 27.13 | Battery | 146-H10 | 2021-09-02 | 2021-09-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online | [12 empty] | STA_146 Walpole
NSTAR | Sherborn | ESMAEX-00335 | 01770 | 24.19 | Solar | 274-H2 | 2021-08-20 | 2021-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Brewster | ESMAEX-00334 | 02631 | 10 | Solar & Battery | 4-628-628 | 2021-08-20 | 2021-09-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online | [12 empty] | STA_975 Orleans
NSTAR | Duxbury | ESMAEX-00346 | 02332 | 21.44 | Solar | 3-24B-24B | 2021-08-25 | 2021-09-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Medfield | ESMAEX-00339 | 02052 | 17.68 | Solar & Battery | 146-H2 | 2021-08-23 | 2021-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online | [12 empty] | STA_146 Walpole
NSTAR | Lincoln | ESMAEX-00406 | 01773 | 21.65 | Solar & Battery | 320-H8 | 2021-09-13 | 2021-09-29 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online | [12 empty] | STA_320 Lexington
NSTAR | Canton | ESMAEX-00422 | 02021 | 16 | Solar | 470-H11 | 2021-09-17 | 2022-02-01 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online | [12 empty] | STA_470 Canton
NSTAR | Burlington | ESMAEX-00344 | 01803 | 17.6 | Solar & Battery | 346-1395H1 | 2021-08-24 | 2021-09-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Online | [12 empty] | STA_391 Burlington
NSTAR | Cambridge | ESMAEX-00350 | 02138 | 17.6 | Solar & Battery | 830-11 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Online | [12 empty] | STA_828 Alewife
NSTAR | Norfolk | ESMAEX-00345 | 02056 | 17.68 | Solar & Battery | 146-H3 | 2021-08-24 | 2021-09-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-14 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Online | [12 empty] | STA_146 Walpole
NSTAR | Sharon | ESMAEX-00352 | 02067 | 20.2 | Solar & Battery | 146-H7 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online | [12 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-00416 | 01720 | 19.79 | Battery | 416-H4 | 2021-09-16 | 2021-10-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Online | [12 empty] | STA_416 Maynard
NSTAR | Arlington | ESMAEX-00349 | 02474 | 12.6 | Solar & Battery | 211-H14 | 2021-08-25 | 2021-09-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [12 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-00359 | 02446 | 15 | Battery | 4911 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Charlestown | ESMAEX-00488 | 02129 | 86.5 | Solar |  | 2021-10-12 | 2021-11-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2023-12-05 | Online
NSTAR | Acton | ESMAEX-00360 | 01720 | 17.6 | Solar & Battery | 416-H4 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Online | [12 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-00357 | 02067 | 498 | Solar | 146-H1 | 2021-10-02 | 2021-11-15 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 498 | STA_146 Walpole
NSTAR | Medway | ESMAEX-00399 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [12 empty] | STA_065 Medway
NSTAR | Medway | ESMAEX-00398 | 02053 | 43.2 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-10 | Online | [12 empty] | STA_065 Medway
NSTAR | Bourne | ESMAEX-00461 | 02532 | 39.98 | Solar | 4-86-408 | 2021-09-30 | 2021-10-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | Acton | ESMAEX-00373 | 01720 | 21.4 | Solar & Battery | 416-H9 | 2021-08-31 | 2021-09-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Online | [12 empty] | STA_416 Maynard
NSTAR | Watertown | ESMAEX-00420 | 02472 | 325 | Solar & Battery | 240-H5 | 2021-09-17 | 2022-01-11 | 82 |  | 82 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Medway | ESMAEX-00400 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [12 empty] | STA_065 Medway
NSTAR | Holliston | ESMAEX-00378 | 01746 | 19 | Solar | 130-H1 | 2021-09-01 | 2021-09-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [12 empty] | STA_130 Holliston
NSTAR | East Sandwich | ESMAEX-00397 | 02537 | 10 | Solar & Battery | 4-87A-87A | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-04-11 | Online | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | West Newton | ESMAEX-00386 | 02465 | 17.6 | Solar & Battery | 282-H9 | 2021-09-06 | 2021-10-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [12 empty] | STA_282 Waltham
NSTAR | Lincoln | ESMAEX-00376 | 01773 | 52.8 | Solar & Battery | 320-H8 | 2021-09-01 | 2021-09-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Online | [12 empty] | STA_320 Lexington
NSTAR | Waltham | ESMAEX-00389 | 02452 | 150 | Solar | 33-H2 | 2021-09-07 | 2021-11-22 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [12 empty] | STA_282 Waltham
NSTAR | Waban | ESMAEX-00392 | 02468 | 25.2 | Solar & Battery | 292-H12 | 2021-09-08 | 2021-09-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-00388 | 01720 | 9.6 | Solar & Battery | 416-H2 | 2021-09-07 | 2021-09-21 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-10 | Online | [12 empty] | STA_416 Maynard
NSTAR | Westwood | ESMAEX-00440 | 02090 | 25.37 | Solar & Battery | 456-H1 | 2021-09-22 | 2021-12-07 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Online | [12 empty] | STA_456 Dover
NSTAR | East Boston | ESMAEX-00411 | 02128 | 75 | Internal Combustion Engine | 488-H5 | 2021-09-14 | 2021-09-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Assonett | ESMAEX-00396 | 02702 | 149.76 | Solar | 2-102-604 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Norfolk | ESMAEX-00391 | 02056 | 13.15 | Battery | 146-H3 | 2021-09-08 | 2021-09-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [12 empty] | STA_146 Walpole
NSTAR | Framingham | ESMAEX-00438 | 01702 | 21.28 | Solar & Battery | 455-H5 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [12 empty] | STA_455 West Framingham
NSTAR | North Falmouth | ESMAEX-00404 | 02556 | 25.075 | Solar | 4-78-861 | 2021-09-10 | 2021-09-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-30 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Brighton | ESMAEX-00405 | 02135 | 100 | Solar | 329-H2 | 2021-09-10 | 2021-09-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-17 | Online | [12 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-00408 | 02118 | 100 | Solar | 106-H4 | 2021-09-13 | 2021-11-16 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Lexington | ESMAEX-00403 | 02421 | 21.43 | Solar & Battery | 3409 | 2021-09-10 | 2021-11-23 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Online
NSTAR | Westwood | ESMAEX-00414 | 02090 | 20 | Solar & Battery | 469-H2 | 2021-09-16 | 2021-10-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-08 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online
NSTAR | Hopkinton | ESMAEX-00412 | 01748 | 27.6 | Solar & Battery | 126-H4 | 2021-09-14 | 2021-10-26 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | North Dartmouth | ESMAEX-00410 | 02747 | 15.2 | Solar | 2-531-531 | 2021-09-14 | 2021-11-16 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Chatham | ESMAEX-00415 | 02659 | 180 | Solar | 4-95A-95A | 2021-09-16 | 2022-01-19 | 89 |  | 89 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Kingston | ESMAEX-00445 | 02364 | 100 | Solar | 3-14-14 | 2021-09-23 | 2021-10-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-24 | [7 empty] | 0 |  | 0 |  |  | 2023-11-17 | Online
NSTAR | New Bedford | ESMAEX-00418 | 02740 | 50 | Solar | 2-73-73 | 2021-09-17 | 2021-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Waltham | ESMAEX-00426 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online | [12 empty] | STA_282 Waltham
NSTAR | Boston | ESMAEX-00460 | 02215 | 120.8 | Solar | 350-H12 | 2021-09-30 | 2021-10-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Framingham | ESMAEX-00419 | 01701 | 17.6 | Solar & Battery | 433-H8 | 2021-09-17 | 2021-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [12 empty] | STA_433 Speen Street
NSTAR | North Falmouth | ESMAEX-00539 | 02556 | 12 | Battery | 4-78-420 | 2021-10-25 | 2021-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Rochester | ESMAEX-00421 | 02770 | 20 | Solar | 3-702-702 | 2021-09-17 | 2021-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Dover | ESMAEX-00428 | 02030 | 30 | Solar & Battery | 456-H5 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online | [12 empty] | STA_456 Dover
NSTAR | Watertown | ESMAEX-00429 | 02472 | 492 | Solar |  | 2021-10-26 | 2021-12-01 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online
NSTAR | West Tisbury | ESMAEX-00446 | 02575 | 12.98 | Solar | 4-97-97 | 2021-09-24 | 2021-11-09 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Falmouth | ESMAEX-00435 | 02540 | 16.82 | Solar | 4-76-76 | 2021-09-21 | 2021-11-09 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Newton | ESMAEX-00454 | 02458 | 200 | Solar | 467-H14 | 2021-09-28 | 2021-10-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_467 Watertown
NSTAR | New Bedford | ESMAEX-00436 | 02740 | 75 | Internal Combustion Engine | 2-67-28 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online | [12 empty] | STA_611 Pine Street
NSTAR | New Bedford | ESMAEX-00437 | 02740 | 75 | Internal Combustion Engine | 2-4-51 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online
NSTAR | Burlington | ESMAEX-00464 | 01803 | 15.2 | Solar & Battery | 391-H6 | 2021-10-01 | 2021-12-28 | 62 |  | 62 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online | [12 empty] | STA_391 Burlington
NSTAR | North Dartmouth | ESMAEX-00480 | 02747 | 86.4 | Solar | 2-532-532 | 2021-10-07 | 2021-11-09 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Dartmouth | ESMAEX-00455 | 02747 | 100 | Solar |  | 2021-09-28 | 2022-02-03 | 92 |  | 92 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online
NSTAR | Mattapoisett | ESMAEX-00450 | 02739 | 17.6 | Solar | 2-302-302 | 2021-09-27 | 2021-10-20 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Roxbury | ESMAEX-00513 | 02119 | 52.2 | Solar | 52-1499H4 | 2021-10-19 | 2021-11-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online
NSTAR | Sharon | ESMAEX-00457 | 02067 | 420 | Solar | 470-H12 | 2021-09-29 | 2021-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [12 empty] | STA_470 Canton
NSTAR | West Tisbury | ESMAEX-00644 | 02575 | 25.568 | Solar & Battery |  | 2021-12-07 | 2021-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Online
NSTAR | Bedford | ESMAEX-00465 | 01730 | 12.6 | Solar & Battery | 533-H8 | 2021-10-03 | 2021-11-16 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-00506 | 01702 | 316.6 | Solar | 24-H1 | 2021-10-15 | 2021-11-23 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Online | [12 empty] | STA_240 Framingham
NSTAR | Marion | ESMAEX-00658 | 02738 | 22.8 | Solar | 3-304-304 | 2021-12-14 | 2022-01-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Dedham | ESMAEX-00467 | 02026 | 17.6 | Solar & Battery | 20-H3 | 2021-10-04 | 2021-11-09 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Harwich | ESMAEX-00466 | 02645 | 12.68 | Solar & Battery | 4-89B-576 | 2021-10-04 | 2021-10-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Online | [12 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-00472 | 01760 | 10.248 | Solar & Battery | 240-H1 | 2021-10-05 | 2021-10-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [12 empty] | STA_240 Framingham
NSTAR | Edgartown | ESMAEX-00682 | 02539 | 11.21 | Solar & Battery |  | 2021-12-21 | 2022-02-09 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Osterville | ESMAEX-00494 | 02655 | 28 | Solar & Battery | 4-80A-80A | 2021-10-13 | 2021-11-04 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Online | [12 empty] | STA_920 Oak Street
NSTAR | Hopkinton | ESMAEX-00478 | 01748 | 19.77 | Solar | 126-H1 | 2021-10-06 | 2021-11-18 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Wellfleet | ESMAEX-00505 | 02667 | 7.14 | Solar | 4-94B-656 | 2021-10-15 | 2021-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-00486 | 01801 | 109.8 | Solar | 211-H2 | 2021-10-10 | 2021-11-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online | [12 empty] | STA_211 Woburn
NSTAR | Chestnut Hill | ESMAEX-00548 | 02467 | 199.8 | Solar | 443-08 | 2021-10-27 | 2021-11-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Walpole | ESMAEX-00498 | 02081 | 15.8 | Solar | 456-H1 | 2021-10-13 | 2021-11-16 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [12 empty] | STA_456 Dover
NSTAR | Mattapoisett | ESMAEX-00485 | 02739 | 16.24 | Solar | 2-302-302 | 2021-10-09 | 2021-11-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Dover | ESMAEX-00500 | 02030 | 26 | Solar | 456-H5 | 2021-10-14 | 2021-11-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online | [12 empty] | STA_456 Dover
NSTAR | East Freetown | ESMAEX-00508 | 02717 | 149.76 | Solar | 2-108-108 | 2021-10-18 | 2021-11-15 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | North Truro | ESMAEX-00507 | 02652 | 8 | Solar | 4-96-96 | 2021-10-18 | 2021-11-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Hyde Park | ESMAEX-00537 | 02136 | 30.45 | Solar | 60-1409H1 | 2021-10-21 | 2021-11-15 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Dover | ESMAEX-00547 | 02030 | 7.678 | Solar & Battery | 456-H5 | 2021-10-27 | 2021-11-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Online | [12 empty] | STA_456 Dover
NSTAR | Natick | ESMAEX-00514 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-10-19 | 2022-01-25 | 70 |  | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online | [12 empty] | STA_240 Framingham
NSTAR | Dorchester | ESMAEX-00561 | 02125 | 43.2 | Solar | 106-1N31H1 | 2021-11-02 | 2021-11-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Waltham | ESMAEX-00516 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-10-20 | 2021-11-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [12 empty] | STA_282 Waltham
NSTAR | East Sandwich | ESMAEX-00517 | 02537 | 9.12 | Solar & Battery | 4-87B-87B | 2021-10-20 | 2021-11-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | South Chatham | ESMAEX-00522 | 02659 | 10 | Battery | 4-95A-606 | 2021-10-21 | 2021-11-15 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-04 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Wellfleet | ESMAEX-00664 | 02667 | 8 | Battery | 4-94B-94B | 2021-12-15 | 2022-01-14 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Hyannis | ESMAEX-00546 | 02601 | 150 | Solar | 4-63-531 | 2021-10-26 | 2021-12-15 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Hyannis Port | ESMAEX-00558 | 02672 | 10 | Battery | 4-80B-80B | 2021-11-01 | 2021-11-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Natick | ESMAEX-00563 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-11-03 | 2021-11-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [12 empty] | STA_240 Framingham
NSTAR | South Dartmouth | ESMAEX-00600 | 02748 | 48.03 | Solar & Battery | 2-524-524 | 2021-11-17 | 2022-01-05 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Wareham | ESMAEX-00540 | 02532 | 196 | Solar | 3-83-83 | 2021-10-25 | 2021-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Ashland | ESMAEX-00557 | 01721 | 250 | Solar | 274-H5 | 2021-11-01 | 2021-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_274 Sherborn
NSTAR | Chatham | ESMAEX-00542 | 02633 | 15.39 | Solar | 4-95B-95B | 2021-10-26 | 2021-11-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online | [12 empty] | STA_975 Orleans
NSTAR | North Dartmouth | ESMAEX-00544 | 02747 | 57.6 | Solar | 2-532-532 | 2021-10-26 | 2021-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-08-16 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Chestnut Hill | ESMAEX-00545 | 02467 | 17.6 | Solar & Battery | 329-H6 | 2021-10-26 | 2021-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-03-21 | Online | [12 empty] | STA_329 Brighton
NSTAR | Newton Center | ESMAEX-00551 | 02459 | 1.5 | Solar & Battery | 292-H8 | 2021-10-28 | 2021-11-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-25 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Needham | ESMAEX-00830 | 02492 | 480 | Solar & Battery | 148-H1 | 2022-02-11 | 2022-03-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | Needham | ESMAEX-00552 | 02494 | 750 | Solar & Battery | 148-H6 | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Online | [11 empty] | 750 | STA_148 Needham
NSTAR | Burlington | ESMAEX-00554 | 01803 | 20 | Solar & Battery | 391-H7 | 2021-10-28 | 2021-11-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-21 | Online | [12 empty] | STA_391 Burlington
NSTAR | Needham | ESMAEX-00560 | 02494 | 11.4 | Battery | 292-H4 | 2021-11-02 | 2021-11-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-02 | [7 empty] | 0 |  | 0 |  |  | 2022-03-23 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-00572 | 02081 | 400 | Solar | 146-H8 | 2021-11-08 | 2021-11-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Online | [12 empty] | STA_146 Walpole
NSTAR | Mashpee | ESMAEX-00565 | 02649 | 85.76 | Solar | 4-455-455 | 2021-11-04 | 2021-11-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [12 empty] | STA_946 Mashpee
NSTAR | Canton | ESMAEX-00562 | 02021 | 8.56 | Solar & Battery | 470-H8 | 2021-11-02 | 2021-11-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-14 | Online | [12 empty] | STA_470 Canton
NSTAR | Newton Lower Falls | ESMAEX-00571 | 02462 | 9.75 | Solar & Battery | 292-H2 | 2021-11-08 | 2021-12-16 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Dover | ESMAEX-00566 | 02030 | 10 | Battery | 148-H2 | 2021-11-05 | 2021-11-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Online | [12 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-00589 | 02747 | 20 | Solar | 2-532-532 | 2021-11-15 | 2021-12-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Carlisle | ESMAEX-00596 | 01741 | 14 | Battery | 512-1399H1 | 2021-11-17 | 2021-12-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [11 empty] | 14 | STA_533 Hartwell Avenue
NSTAR | Acusnet | ESMAEX-00573 | 02743 | 15.2 | Solar | 2-241-241 | 2021-11-09 | 2021-12-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-08-23 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Rochester | ESMAEX-00574 | 02770 | 10.03 | Solar | 3-703-703 | 2021-11-09 | 2021-11-23 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Dover | ESMAEX-00576 | 02030 | 16.225 | Solar | 456-H5 | 2021-11-10 | 2021-11-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [12 empty] | STA_456 Dover
NSTAR | Needham | ESMAEX-00582 | 02492 | 11.4 | Battery | 148-H4 | 2021-11-11 | 2021-12-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Online | [12 empty] | STA_148 Needham
NSTAR | Chelsea | ESMAEX-00580 | 02150 | 43.2 | Solar | 488-H3 | 2021-11-10 | 2021-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Chelsea | ESMAEX-00581 | 02150 | 43.2 | Solar | 488-H7 | 2021-11-10 | 2021-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Chatham | ESMAEX-00586 | 02633 | 12 | Battery | 4-95B-95B | 2021-11-15 | 2021-12-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-24 | Online | [12 empty] | STA_975 Orleans
NSTAR | Marshfield | ESMAEX-00584 | 02050 | 9 | Battery | 3-27-970 | 2021-11-15 | 2021-12-17 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Carver | ESMAEX-02467 | 02330 | 4990 | Solar | 3-10-10 | 2023-06-26 | 2023-07-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth | 2024 SEMA/Cape ASO Study | Phase 2 - In Process | 4990 | STA_737 West Pond
NSTAR | North Truro | ESMAEX-00585 | 02652 | 15.2 | Solar & Battery | 4-96-96 | 2021-11-15 | 2022-01-20 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Marion | ESMAEX-00590 | 02738 | 17.6 | Solar & Battery | 3-85-85 | 2021-11-16 | 2022-01-20 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Newton Center | ESMAEX-00601 | 02459 | 15.2 | Solar | 443-02 | 2021-11-17 | 2022-01-06 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Holliston | ESMAEX-00605 | 01746 | 80 | Solar | 274-H3 | 2021-11-18 | 2021-12-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Falmouth | ESMAEX-00604 | 02540 | 19 | Solar | 4-78-78 | 2021-11-18 | 2022-01-04 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Assonett | ESMAEX-00610 | 02702 | 17.25 | Solar | 2-605-605 | 2021-11-22 | 2021-12-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_661 Bell Rock
NSTAR | Cambridge | ESMAEX-00597 | 02138 | 34.2 | Solar | 821-05 | 2021-11-17 | 2021-12-30 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2023-09-01 | Online | [12 empty] | STA_831 Putnam
NSTAR | South Chatham | ESMAEX-00602 | 02659 | 16 | Solar |  | 2021-11-17 | 2021-12-30 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online
NSTAR | Plymouth | ESMAEX-00603 | 02360 | 17.6 | Solar | 3-90-90 | 2021-11-17 | 2022-01-19 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Canton | ESMAEX-00606 | 02021 | 140 | Solar | 470-H4 | 2021-11-18 | 2022-01-13 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online | [12 empty] | STA_470 Canton
NSTAR | Westport | ESMAEX-00630 | 02790 | 10 | Battery | 2-523-523 | 2021-11-30 | 2022-01-20 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | South Dartmouth | ESMAEX-00890 | 02748 | 220 | Solar | 2-53-65 | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-01-04 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Cambridge | ESMAEX-00638 | 02139 | 14.79 | Solar | 817-46 | 2021-12-03 | 2022-01-03 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Online | [12 empty] | STA_831 Putnam
NSTAR | Lexington | ESMAEX-00637 | 02420 | 10.03 | Solar & Battery | 391-H11 | 2021-12-02 | 2021-12-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online | [12 empty] | STA_391 Burlington
NSTAR | Silver Beach | ESMAEX-00636 | 02565 | 6.1 | Battery | 4-78-861 | 2021-12-02 | 2021-12-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Plymouth | ESMAEX-00635 | 02360 | 72 | Solar | 3-12-28J3 | 2021-12-01 | 2021-12-28 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Hopkinton | ESMAEX-00621 | 01748 | 20 | Solar & Battery | 126-H4 | 2021-11-24 | 2021-12-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Bedford | ESMAEX-00622 | 01730 | 17.4 | Solar | 533-H8 | 2021-11-24 | 2021-12-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Wellfleet | ESMAEX-00624 | 02667 | 23.78 | Solar | 4-94B-653 | 2021-11-27 | 2021-12-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-25 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Sharon | ESMAEX-00626 | 02067 | 7.6 | Solar & Battery | 470-H12 | 2021-11-28 | 2021-12-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2023-04-14 | Online | [12 empty] | STA_470 Canton
NSTAR | Westwood | ESMAEX-00667 | 02090 | 18 | Solar & Battery | 456-H4 | 2021-12-16 | 2022-01-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [11 empty] | 5 | STA_456 Dover
NSTAR | Chelsea | ESMAEX-00672 | 02150 | 86.4 | Solar | 488-H7 | 2021-12-20 | 2022-01-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [12 empty] | STA_488 Chelsea
NSTAR | East Brewster | ESMAEX-00650 | 02631 | 100 | Solar |  | 2021-12-09 | 2021-12-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online
NSTAR | Boston | ESMAEX-00733 | 02163 | 43.2 | Solar | 831-1107 | 2022-01-18 | 2022-02-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Online | [12 empty] | STA_831 Putnam
NSTAR | Hyannis | ESMAEX-00648 | 02601 | 220 | Solar | 4-63-521 | 2021-12-08 | 2021-12-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Sharon | ESMAEX-00641 | 02067 | 9.15 | Solar & Battery | 470-H12 | 2021-12-03 | 2021-12-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online | [12 empty] | STA_470 Canton
NSTAR | West Barnstable | ESMAEX-00730 | 02668 | 15.36 | Solar | 4-87B-87B | 2022-01-16 | 2022-02-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Lexington | ESMAEX-00647 | 02421 | 8.85 | Solar | 320-H2 | 2021-12-08 | 2022-01-20 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [12 empty] | STA_320 Lexington
NSTAR | Brookline | ESMAEX-00678 | 02445 | 14 | Battery | 350-H3 | 2021-12-20 | 2022-02-08 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | North Truro | ESMAEX-00740 | 02652 | 16.56 | Solar |  | 2022-01-19 | 2022-02-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online
NSTAR | Duxbury | ESMAEX-00646 | 02332 | 10 | Solar | 3-26-26 | 2021-12-07 | 2021-12-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online
NSTAR | Hatchville | ESMAEX-00685 | 02536 | 10 | Solar | 4-98A-429 | 2021-12-21 | 2022-01-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Westwood | ESMAEX-00703 | 02090 | 16.054 | Solar | 148-H3 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Online | [12 empty] | STA_148 Needham
NSTAR | Needham | ESMAEX-00656 | 02492 | 15.707 | Solar & Battery | 148-08 | 2021-12-13 | 2021-12-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [12 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-00651 | 01776 | 199.9 | Solar | 342-H2 | 2021-12-09 | 2021-12-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-28 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-00654 | 02125 | 98 | Solar | 483-H3 | 2021-12-10 | 2021-12-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Hyde Park | ESMAEX-00655 | 02136 | 3.8 | Solar | 441-02 | 2021-12-10 | 2021-12-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-29 | Online | [12 empty] | STA_441 Wilmont Street
NSTAR | Hopkinton | ESMAEX-00676 | 01748 | 7.6 | Solar & Battery | 126-H3 | 2021-12-20 | 2022-01-20 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-04-21 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Watertown | ESMAEX-00662 | 02472 | 10 | Battery | 467-H8 | 2021-12-15 | 2022-01-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online | [12 empty] | STA_467 Watertown
NSTAR | Boston | ESMAEX-00666 | 02215 | 116 | Solar |  | 2021-12-15 | 2022-01-20 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online
NSTAR | Marshfield | ESMAEX-00683 | 02050 | 17.7 | Solar | 3-24A-34J1 | 2021-12-21 | 2022-01-11 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-08-29 | Online | [12 empty] | STA_739 Marshfield
NSTAR | Canton | ESMAEX-00665 | 02021 | 15.2 | Solar | 470-H10 | 2021-12-15 | 2022-01-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online | [12 empty] | STA_470 Canton
NSTAR | Boston | ESMAEX-00669 | 02124 | 130 | Solar | 496-H8 | 2021-12-17 | 2022-01-20 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Dover | ESMAEX-00704 | 02030 | 16.403 | Solar | 456-H5 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [12 empty] | STA_456 Dover
NSTAR | Needham | ESMAEX-00693 | 02494 | 140 | Solar |  | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online
NSTAR | West Tisbury | ESMAEX-00673 | 02575 | 20 | Solar |  | 2021-12-20 | 2022-01-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-22 | Online
NSTAR | Falmouth | ESMAEX-00721 | 02540 | 10 | Battery | 4-76-436 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-21 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Canton | ESMAEX-00681 | 02021 | 4999.2 | Battery | 470-H4 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 4999.2 | STA_470 Canton
NSTAR | Edgartown | ESMAEX-00687 | 02539 | 8.12 | Solar & Battery |  | 2021-12-22 | 2022-01-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Newton Center | ESMAEX-00688 | 02459 | 25.2 | Solar & Battery | 292-H6 | 2021-12-22 | 2022-02-22 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Millis | ESMAEX-00686 | 02054 | 498 | Solar & Battery | 456-H2 | 2023-01-26 | 2023-02-08 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-00692 | 02420 | 22.8 | Solar & Battery | 533-H9 | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-09-30 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Watertown | ESMAEX-00696 | 02472 | 400 | Solar | 315-H4 | 2022-01-20 | 2022-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | Framingham | ESMAEX-00697 | 01702 | 11.5 | Solar & Battery | 519-175H1 | 2021-12-28 | 2022-01-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Dover | ESMAEX-01930 | 02030 | 15.37 | Solar | 456-H3 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Online | [12 empty] | STA_456 Dover
NSTAR | Arlington | ESMAEX-00702 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Online | [12 empty] | STA_211 Woburn
NSTAR | Boston | ESMAEX-00722 | 02118 | 43.2 | Solar |  | 2022-01-11 | 2022-03-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online
NSTAR | Westwood | ESMAEX-00709 | 02090 | 480 | Solar | 469-H6 | 2022-05-11 | 2022-07-21 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_469 Ellis Avenue
NSTAR | South Boston | ESMAEX-00753 | 02127 | 28.8 | Solar | 385-H19 | 2022-01-24 | 2022-02-28 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [12 empty] | STA_385D K Street
NSTAR | West Yarmouth | ESMAEX-00719 | 02673 | 20.2 | Solar & Battery | 4-64-64 | 2022-01-11 | 2022-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-05 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Centerville | ESMAEX-00711 | 02632 | 18.25 | Solar & Battery | 4-82-82 | 2022-01-05 | 2022-01-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Newton | ESMAEX-00716 | 02458 | 13.05 | Solar & Battery | 467-H12 | 2022-01-06 | 2022-01-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online | [12 empty] | STA_467 Watertown
NSTAR | Hopkinton | ESMAEX-00809 | 01748 | 24.78 | Solar | 126-H4 | 2022-02-04 | 2022-03-18 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online | [11 empty] | 20 | STA_126 Hopkinton
NSTAR | West Newton | ESMAEX-00727 | 02465 | 15.51 | Solar & Battery | 316-03 | 2022-01-13 | 2022-02-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [12 empty] | STA_282 Waltham
NSTAR | Marion | ESMAEX-00725 | 02738 | 10 | Solar & Battery | 3-304-304 | 2022-01-12 | 2022-02-24 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Plymouth | ESMAEX-00724 | 02360 | 43.2 | Solar | 3-89-922 | 2022-01-11 | 2022-02-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Needham | ESMAEX-00720 | 02492 | 10 | Battery | 148-07 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [12 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-00723 | 01776 | 21.4 | Solar & Battery | 342-H8 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-03-14 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Huntington | ESMAEX-01101 | 01050 | 4250 | Solar & Battery | 19J5 | 2022-05-12 | 2022-05-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process |  | 19J BLANDFORD
NSTAR | Watertown | ESMAEX-00726 | 02472 | 636 | Solar | 370-1323 | 2022-03-15 | 2022-04-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | Westwood | ESMAEX-00757 | 02090 | 15.2 | Solar & Battery | 456-H4 | 2022-01-25 | 2022-02-17 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online | [12 empty] | STA_456 Dover
NSTAR | Weston | ESMAEX-00743 | 02493 | 18.148 | Solar | 282-H1 | 2022-01-20 | 2022-02-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [12 empty] | STA_282 Waltham
NSTAR | Edgartown | ESMAEX-01133 | 02539 | 44.37 | Solar |  | 2022-05-02 | 2022-05-24 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online
NSTAR | North Cambridge | ESMAEX-00732 | 02140 | 6.38 | Solar & Battery | 824-28 | 2022-01-18 | 2022-02-22 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Online | [12 empty] | STA_828 Alewife
NSTAR | Allston | ESMAEX-00729 | 02134 | 40 | Solar | 315-H8 | 2022-01-14 | 2022-02-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online
NSTAR | East Harwich | ESMAEX-00737 | 02645 | 19.14 | Solar | 4-95A-95A | 2022-01-19 | 2022-02-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-10-26 | Technical Review | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Needham | ESMAEX-00736 | 02494 | 3.8 | Solar & Battery | 148-H4 | 2022-01-18 | 2022-06-20 | 109 |  | 109 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_148 Needham
NSTAR | Lincoln | ESMAEX-00811 | 01773 | 7.68 | Battery | 320-H6 | 2022-02-04 | 2022-02-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-11-16 | Online | [12 empty] | STA_320 Lexington
NSTAR | Chelsea | ESMAEX-00744 | 02150 | 250 | Battery | 488-H1 | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Edgartown | ESMAEX-00891 | 02539 | 29 | Solar | 4-75-227 | 2022-03-09 | 2022-05-23 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Chelsea | ESMAEX-00745 | 02150 | 250 | Solar |  | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Chelsea | ESMAEX-00747 | 02150 | 375 | Solar |  | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-10-23 | Online
NSTAR | Cambridge | ESMAEX-00913 | 02139 | 9.15 | Solar & Battery | 816-02 | 2022-03-14 | 2022-04-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-25 | Online | [12 empty] | STA_831 Putnam
NSTAR | Waquoit | ESMAEX-00748 | 02536 | 11.52 | Solar & Battery | 4-77B-456 | 2022-01-20 | 2022-02-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online
NSTAR | East Harwich | ESMAEX-00874 | 02645 | 11 | Solar & Battery | 4-95A-95A | 2022-03-03 | 2022-03-14 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Roxbury Crossing | ESMAEX-00802 | 02120 | 43.2 | Solar | 52-1499H4 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online
NSTAR | Chatham | ESMAEX-00820 | 02633 | 19.14 | Solar | 4-95A-606 | 2022-02-07 | 2022-04-07 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-05 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Sherborn | ESMAEX-00922 | 01770 | 15.705 | Solar | 274-H2 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Carlisle | ESMAEX-00767 | 01741 | 15.95 | Solar | 512-1399H1 | 2022-01-31 | 2022-02-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Falmouth | ESMAEX-00764 | 02540 | 9.6 | Solar & Battery | 4-72-72 | 2022-01-28 | 2022-02-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Chestnut Hill | ESMAEX-00907 | 02467 | 8 | Battery | 443-07 | 2022-03-11 | 2022-04-07 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Cambridge | ESMAEX-00758 | 02142 | 133.2 | Solar | 875-1392 | 2022-01-26 | 2022-04-19 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-27 | Online | [12 empty] | STA_875 East Cambridge
NSTAR | Waltham | ESMAEX-00761 | 02451 | 250 | Solar & Battery | 450-H8 | 2022-01-27 | 2022-02-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_450 Trapelo Road
NSTAR | Chelsea | ESMAEX-00888 | 02150 | 495.8 | Solar | 488-H6 | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Watertown | ESMAEX-00762 | 02472 | 99.9 | Solar | 315-H4 | 2022-01-28 | 2022-03-02 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | South Dartmouth | ESMAEX-00785 | 02748 | 22.8 | Solar | 2-524-524 | 2022-02-01 | 2022-02-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Boston | ESMAEX-00770 | 02131 | 250 | Solar | 496-H8 | 2022-03-04 | 2022-03-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Boston | ESMAEX-00772 | 02124 | 480 | Solar | 483-H1 | 2022-03-14 | 2022-03-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-24 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Falmouth | ESMAEX-00776 | 02540 | 4999.2 | Battery | 4-76-76 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Cape Group Phase II | Cape | 2024 SEMA/Cape ASO Study | Phase 2 - In Process |  | STA_933 Falmouth
NSTAR | Springfield | ESMAEX-00777 | 01118 | 4999.2 | Battery | 20A21 | 2023-01-18 | 2023-02-17 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [10 empty] | Sequential Study - In Process | 4.9998 | 20A BRECKWOOD
NSTAR | Duxbury | ESMAEX-00807 | 02332 | 11.4 | Battery | 3-23-23 | 2022-02-04 | 2022-03-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online
NSTAR | Woods Hole | ESMAEX-00827 | 02543 | 18.99 | Solar & Battery | 4-91-91 | 2022-02-10 | 2022-03-11 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Mattapan | ESMAEX-00796 | 02126 | 250 | Solar | 311-09 | 2022-08-04 | 2022-09-09 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Framingham | ESMAEX-00801 | 01701 | 20 | Solar | 455-H1 | 2022-02-03 | 2022-02-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Harwichport | ESMAEX-00821 | 02646 | 15.2 | Solar | 4-95A-95A | 2022-02-08 | 2022-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-11-03 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Arlington | ESMAEX-00842 | 02476 | 166.5 | Solar | 211-H13 | 2022-02-18 | 2022-03-21 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [12 empty] | STA_211 Woburn
NSTAR | Walpole | ESMAEX-00804 | 02081 | 133.3 | Solar | 146-H4 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Online | [12 empty] | STA_146 Walpole
NSTAR | East Walpole | ESMAEX-00805 | 02032 | 100 | Solar | 146-H8 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Online | [12 empty] | STA_146 Walpole
NSTAR | Hopkinton | ESMAEX-00841 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-17 | 2022-03-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-00808 | 02090 | 11 | Solar & Battery | 456-H4 | 2022-02-04 | 2022-02-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Online | [12 empty] | STA_456 Dover
NSTAR | East Falmouth | ESMAEX-00864 | 02536 | 15.93 | Solar | 4-76-437 | 2022-02-28 | 2022-04-12 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Edgartown | ESMAEX-00832 | 02539 | 2490 | Solar & Battery | 4-75-223 | 2022-02-14 | 2022-03-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | Cape Group Phase II | Cape | 2024 SEMA/Cape ASO Study | Phase 2 - In Process |  | STA_933 Falmouth
NSTAR | Ashland | ESMAEX-01234 | 01721 | 120 | Solar | 274-1429H | 2022-05-27 | 2022-07-21 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Winchester | ESMAEX-00825 | 01890 | 19 | Solar | 211-H4 | 2022-02-09 | 2022-02-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [12 empty] | STA_211 Woburn
NSTAR | Sherborn | ESMAEX-00824 | 01770 | 13.275 | Solar | 274-H2 | 2022-02-09 | 2022-03-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Westport | ESMAEX-00886 | 02790 | 5.12 | Battery | 2-523-523 | 2022-03-07 | 2022-07-01 | 84 |  | 84 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Hyannis | ESMAEX-00834 | 02601 | 75 | Solar | 4-63-521 | 2022-02-15 | 2022-04-15 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Vineyard Haven | ESMAEX-00831 | 02568 | 70 | Solar | 4-75-75 | 2022-02-12 | 2022-03-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-17 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Marshfield | ESMAEX-00838 | 02050 | 4999.2 | Battery | 3-22-973 | 2022-03-16 | 2022-05-23 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2024 SEMA/Cape ASO Study |  |  | STA_739 Marshfield
NSTAR | Lexington | ESMAEX-00860 | 02421 | 240 | Solar | 3402 | 2022-02-25 | 2022-03-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [12 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00861 | 02421 | 133.3 | Solar | 3402 | 2022-02-25 | 2022-03-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_320 Lexington
NSTAR | Watertown | ESMAEX-00866 | 02472 | 160 | Solar |  | 2022-03-01 | 2022-03-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online
NSTAR | Dennis | ESMAEX-00946 | 02638 | 17.6 | Solar & Battery | 4-89A-89A | 2022-03-18 | 2022-04-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Hopkinton | ESMAEX-00843 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-21 | 2022-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-00844 | 02360 | 10.03 | Solar & Battery | 3-11-11 | 2022-02-21 | 2022-03-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-06-21 | Online
NSTAR | Orleans | ESMAEX-00851 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-02-22 | 2022-03-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online | [12 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-00918 | 02139 | 84.6 | Solar | 820-15 | 2022-03-15 | 2022-05-31 | 55 |  | 55 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [12 empty] | STA_402 Newton Street
NSTAR | Mattapan | ESMAEX-00867 | 02126 | 60 | Solar | 311-1403H1 | 2022-03-01 | 2022-03-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Medway | ESMAEX-00859 | 02053 | 10.25 | Solar & Battery | 65-H3 | 2022-02-25 | 2022-03-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-25 | Online | [12 empty] | STA_065 Medway
NSTAR | South Dartmouth | ESMAEX-00863 | 02748 | 4.64 | Solar | 2-528-528 | 2022-02-28 | 2022-03-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-12 | Online
NSTAR | Newton Center | ESMAEX-00889 | 02459 | 480 | Solar | 292-H3 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2025-09-29 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Newton Center | ESMAEX-00984 | 02459 | 60 | Solar |  | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-22 | Online
NSTAR | Sudbury | ESMAEX-00872 | 01776 | 15.2 | Solar & Battery | 342-H2 | 2022-03-02 | 2022-04-18 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-00885 | 02128 | 249.9 | Solar | 152-87H | 2022-03-07 | 2022-03-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Aquinnah | ESMAEX-00875 | 02535 | 8.7 | Solar & Battery | 4-97-97 | 2022-03-03 | 2022-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Newton Center | ESMAEX-00985 | 02459 | 240 | Solar | 292-H3 | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Bedford | ESMAEX-00877 | 01730 | 16.104 | Solar | 533-H5 | 2022-03-04 | 2022-03-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Woburn | ESMAEX-00880 | 01801 | 15.2 | Solar | 325-03 | 2022-03-04 | 2022-03-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_211 Woburn
NSTAR | Lincoln | ESMAEX-00912 | 01773 | 9.216 | Solar | 320-H6 | 2022-03-14 | 2022-03-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online | [12 empty] | STA_320 Lexington
NSTAR | Medway | ESMAEX-00887 | 02053 | 6 | Solar | 65-H3 | 2022-03-07 | 2022-03-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online | [12 empty] | STA_065 Medway
NSTAR | Chilmark | ESMAEX-01041 | 02535 | 15.2 | Solar & Battery | 4-97-97 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-00951 | 01702 | 240 | Solar |  | 2022-03-21 | 2022-05-24 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Online
NSTAR | Milton | ESMAEX-00923 | 02186 | 15.2 | Solar & Battery | 362-1209H2 | 2022-03-15 | 2022-04-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Cambridge | ESMAEX-01252 | 02142 | 100 | Solar | 875-1N39A | 2022-06-02 | 2022-06-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-27 | Online | [12 empty] | STA_875 East Cambridge
NSTAR | Lincoln | ESMAEX-00917 | 01773 | 15.36 | Solar | 320-H6 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Online | [12 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-00899 | 01760 | 86.5 | Solar | 433-H11 | 2022-03-11 | 2022-03-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Medway | ESMAEX-00895 | 02053 | 14.46 | Solar | 65-H5 | 2022-03-10 | 2022-03-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [12 empty] | STA_065 Medway
NSTAR | Bellingham | ESMAEX-00901 | 02019 | 15.2 | Solar & Battery | 65-H4 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-22 | Online | [12 empty] | STA_065 Medway
NSTAR | Medway | ESMAEX-00902 | 02053 | 25.2 | Solar | 65-H3 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online | [12 empty] | STA_065 Medway
NSTAR | New Bedford | ESMAEX-00900 | 02745 | 999 | Solar & Battery | 2-79-404 | 2022-04-06 | 2022-05-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 999 | STA_612 Acushnet
NSTAR | Wayland | ESMAEX-00903 | 01778 | 12.6 | Solar | 433-H2 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-01033 | 02492 | 15.2 | Solar & Battery | 148-06 | 2022-04-07 | 2022-04-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_148 Needham
NSTAR | North Truro | ESMAEX-00908 | 02652 | 24.94 | Solar |  | 2022-03-11 | 2022-04-19 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online
NSTAR | Cotuit | ESMAEX-00929 | 02635 | 15.2 | Solar & Battery | 4-88-88 | 2022-03-16 | 2022-05-23 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Weston | ESMAEX-00949 | 02493 | 5 | Battery | 282-H1 | 2022-03-20 | 2022-06-20 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [12 empty] | STA_282 Waltham
NSTAR | North Truro | ESMAEX-00919 | 02652 | 28.71 | Solar | 4-96-96 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Framingham | ESMAEX-00916 | 01702 | 3.8 | Solar | 455-H5 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-00940 | 01702 | 10 | Solar & Battery | 455-H5 | 2022-03-17 | 2022-04-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Buzzards Bay | ESMAEX-00920 | 02532 | 11.4 | Solar | 3-88-88 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Newton Center | ESMAEX-00921 | 02459 | 3.5 | Solar | 1709 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Sudbury | ESMAEX-00945 | 01776 | 43.2 | Solar | 342-H2 | 2022-03-18 | 2022-04-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-00927 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2022-03-16 | 2022-04-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Needham | ESMAEX-00931 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2022-03-16 | 2022-04-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_148 Needham
NSTAR | Holliston | ESMAEX-00936 | 01746 | 4.93 | Solar | 274-H3 | 2022-03-17 | 2022-04-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Waltham | ESMAEX-01801 | 02451 | 33.3 | Solar | 450-H7 | 2022-11-11 | 2022-12-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Natick | ESMAEX-00935 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-03-17 | 2022-04-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [12 empty] | STA_240 Framingham
NSTAR | Fairhaven | ESMAEX-00938 | 02719 | 200 | Solar | 2-230-230 | 2022-06-22 | 2022-07-20 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_612 Acushnet
NSTAR | Boston | ESMAEX-00953 | 02118 | 51.9 | Solar | 218-80H1 | 2022-03-21 | 2022-04-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [12 empty] | STA_250 Mystic
NSTAR | Canton | ESMAEX-00947 | 02021 | 7.6 | Solar & Battery | 470-H10 | 2022-03-19 | 2022-04-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online | [12 empty] | STA_470 Canton
NSTAR | Newton Center | ESMAEX-00956 | 02459 | 15.2 | Solar & Battery | 292-H6 | 2022-03-22 | 2022-04-21 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Arlington | ESMAEX-01083 | 02476 | 13 | Solar & Battery | 320-H7 | 2022-04-15 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-13 | Online | [12 empty] | STA_320 Lexington
NSTAR | Bourne | ESMAEX-00959 | 02532 | 18 | Solar | 4-86-408 | 2022-03-23 | 2022-04-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | West Dennis | ESMAEX-00986 | 02670 | 3.8 | Solar & Battery | 4-92B-92B | 2022-03-29 | 2022-04-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Acton | ESMAEX-00962 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2022-03-24 | 2022-04-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [12 empty] | STA_416 Maynard
NSTAR | Waban | ESMAEX-00960 | 02468 | 23.424 | Solar | 292-H2 | 2022-03-23 | 2022-04-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-00967 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-03-25 | 2022-04-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | East Falmouth | ESMAEX-00963 | 02536 | 15.2 | Solar & Battery | 4-98B-449 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Plymouth | ESMAEX-00964 | 02360 | 15.2 | Solar & Battery | 3-89-925 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Canton | ESMAEX-00961 | 02021 | 250 | Solar | 269-1320H1 | 2022-06-06 | 2022-06-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Online | [12 empty] | STA_470 Canton
NSTAR | Allston | ESMAEX-00972 | 02134 | 34.6 | Solar | 315-H3 | 2022-03-28 | 2022-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | Carlisle | ESMAEX-00987 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2022-03-29 | 2022-05-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Falmouth | ESMAEX-00968 | 02540 | 15.2 | Solar & Battery | 4-72-72 | 2022-03-25 | 2022-04-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Marshfield | ESMAEX-00974 | 02050 | 7.6 | Solar & Battery | 3-24A-974 | 2022-03-28 | 2022-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online | [12 empty] | STA_739 Marshfield
NSTAR | East Freetown | ESMAEX-00965 | 02717 | 15.2 | Solar | 2-108-108 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-00970 | 02420 | 7.6 | Solar & Battery | 3406 | 2022-03-26 | 2022-04-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | West Dennis | ESMAEX-00971 | 02670 | 15.2 | Solar & Battery |  | 2022-03-27 | 2022-04-28 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online
NSTAR | Marion | ESMAEX-01255 | 02738 | 17.568 | Solar |  | 2022-06-03 | 2022-08-10 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | New Bedford | ESMAEX-00976 | 02746 | 480 | Solar | 2-81-81 | 2022-06-08 | 2022-08-15 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_612 Acushnet
NSTAR | Edgartown | ESMAEX-01006 | 02539 | 132.48 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-30 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Vineyard Haven | ESMAEX-01005 | 02568 | 156.16 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Oak Bluffs | ESMAEX-00991 | 02557 | 20 | Solar | 4-99-225 | 2022-03-30 | 2022-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | New Bedford | ESMAEX-00996 | 02740 | 120 | Solar | 2-83-403 | 2022-03-31 | 2022-04-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Online | [12 empty] | STA_612 Acushnet
NSTAR | Boston | ESMAEX-00995 | 02118 | 250 | Solar |  | 2022-06-15 | 2022-08-01 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online
NSTAR | Walpole | ESMAEX-00997 | 02081 | 10 | Solar | 146-H4 | 2022-03-31 | 2022-05-26 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Online | [12 empty] | STA_146 Walpole
NSTAR | Newton Center | ESMAEX-01398 | 02459 | 22.5 | Solar & Battery | 292-H6 | 2022-07-21 | 2022-08-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-01000 | 02467 | 15.2 | Solar | 443-07 | 2022-04-01 | 2022-08-15 | 96 |  | 96 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [12 empty] | STA_110 Baker Street
NSTAR | East Walpole | ESMAEX-01003 | 02032 | 17.6 | Solar & Battery | 146-H4 | 2022-04-04 | 2022-04-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_146 Walpole
NSTAR | Winchester | ESMAEX-01017 | 01890 | 15.2 | Solar & Battery | 211-H10 | 2022-04-06 | 2022-04-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [11 empty] | 0 | STA_211 Woburn
NSTAR | Westwood | ESMAEX-01082 | 02090 | 20.2 | Solar & Battery | 148-H3 | 2022-04-15 | 2022-05-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [12 empty] | STA_148 Needham
NSTAR | Newton Center | ESMAEX-01004 | 02459 | 492 | Solar | 292-H11 | 2022-04-27 | 2022-05-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-10-30 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Newton Center | ESMAEX-01094 | 02459 | 240 | Solar | 292-H3 | 2022-04-20 | 2022-06-14 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_292 Newton Highlands
NSTAR | Stoneham | ESMAEX-01007 | 02180 | 15.2 | Solar | 375-H8 | 2022-04-04 | 2022-04-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Acton | ESMAEX-01055 | 01720 | 12.6 | Solar & Battery | 416-H9 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online | [12 empty] | STA_416 Maynard
NSTAR | South Yarmouth | ESMAEX-01089 | 02664 | 18.56 | Solar | 4-92A-92A | 2022-04-18 | 2022-05-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Westwood | ESMAEX-01016 | 02090 | 15.2 | Solar | 148-H3 | 2022-04-06 | 2022-05-23 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [12 empty] | STA_148 Needham
NSTAR | Lexington | ESMAEX-01043 | 02420 | 9.3 | Solar | 533-H9 | 2022-04-08 | 2022-04-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Chestnut Hill | ESMAEX-01030 | 02467 | 25.2 | Solar & Battery | 443-08 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Holliston | ESMAEX-01022 | 01746 | 15.2 | Solar & Battery | 65-H5 | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Online | [12 empty] | STA_065 Medway
NSTAR | East Sandwich | ESMAEX-01023 | 02537 | 26.4 | Solar & Battery | 4-87A-87A | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Online | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | East Walpole | ESMAEX-01027 | 02032 | 15.2 | Solar & Battery | 146-H4 | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [12 empty] | STA_146 Walpole
NSTAR | East Falmouth | ESMAEX-01031 | 02536 | 15.2 | Solar & Battery | 4-77A-77A | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | New Bedford | ESMAEX-01034 | 02745 | 15.2 | Solar & Battery | 2-106-161 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-05-11 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Boston | ESMAEX-01026 | 02210 | 300 | Solar | 385-H12 | 2022-06-17 | 2022-07-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [12 empty] | STA_385D K Street
NSTAR | Sherborn | ESMAEX-01028 | 01770 | 30 | Solar | 240-H1 | 2022-04-07 | 2022-04-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-18 | Online | [12 empty] | STA_240 Framingham
NSTAR | Brewster | ESMAEX-01058 | 02631 | 25.2 | Solar & Battery | 4-89A-89A | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Boston | ESMAEX-01105 | 02215 | 170 | Solar | 508-91 | 2022-04-24 | 2022-05-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Online | [12 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-01104 | 02215 | 70 | Solar | 329-H9 | 2022-04-24 | 2022-05-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Online | [12 empty] | STA_329 Brighton
NSTAR | East Falmouth | ESMAEX-01299 | 02536 | 20 | Solar & Battery | 4-98B-449 | 2022-06-16 | 2022-07-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Natick | ESMAEX-01038 | 01760 | 15.2 | Solar & Battery | 240-H5 | 2022-04-07 | 2022-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [12 empty] | STA_240 Framingham
NSTAR | Norfolk | ESMAEX-01039 | 02056 | 21 | Solar & Battery | 146-H10 | 2022-04-07 | 2022-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Online | [11 empty] | 15.2 | STA_146 Walpole
NSTAR | Canton | ESMAEX-01296 | 02021 | 20.2 | Solar & Battery | 470-H9 | 2022-06-15 | 2022-07-13 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Online | [12 empty] | STA_470 Canton
NSTAR | Stoneham | ESMAEX-01052 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Dorchester | ESMAEX-01137 | 02125 | 43.5 | Solar | 483-H3 | 2022-05-03 | 2022-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Dorchester | ESMAEX-01138 | 02125 | 31.7 | Solar | 6703 | 2022-05-03 | 2022-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Sharon | ESMAEX-01049 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online | [12 empty] | STA_470 Canton
NSTAR | Carlisle | ESMAEX-01086 | 01741 | 17.9 | Solar | 512-1399H1 | 2022-04-16 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Roxbury | ESMAEX-01062 | 02119 | 50 | Solar | 510-77H3 | 2022-04-11 | 2022-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Wellfleet | ESMAEX-01100 | 02667 | 21.83 | Solar | 4-96-96 | 2022-04-22 | 2022-05-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Allston | ESMAEX-01066 | 02134 | 480 | Solar | 508-91 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [12 empty] | STA_329 Brighton
NSTAR | Hopkinton | ESMAEX-01067 | 01748 | 250 | Solar | 65-H7 | 2022-05-11 | 2022-06-22 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [12 empty] | STA_065 Medway
NSTAR | Chilmark | ESMAEX-01069 | 02535 | 24.3 | Solar | 4-97-97 | 2022-04-11 | 2022-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-18 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Hopkinton | ESMAEX-01068 | 01748 | 120 | Solar | 126-H2 | 2022-05-11 | 2022-06-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Sharon | ESMAEX-01113 | 02067 | 8.85 | Solar & Battery | 146-H7 | 2022-04-26 | 2022-05-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [12 empty] | STA_146 Walpole
NSTAR | Boston | ESMAEX-01155 | 02119 | 30.16 | Solar | 396-1050H | 2022-05-06 | 2022-06-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Orleans | ESMAEX-01147 | 02653 | 10 | Battery | 4-89B-89B | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-05 | Online | [12 empty] | STA_975 Orleans
NSTAR | Weston | ESMAEX-01079 | 02493 | 7.6 | Solar & Battery | 282-H8 | 2022-04-13 | 2022-05-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Online | [12 empty] | STA_282 Waltham
NSTAR | South Sandwich | ESMAEX-01088 | 02563 | 15.2 | Solar & Battery | 4-81B-81B | 2022-04-16 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-11-21 | Online | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | Holliston | ESMAEX-01080 | 01746 | 15.18 | Solar | 65-H5 | 2022-04-14 | 2022-05-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Online | [12 empty] | STA_065 Medway
NSTAR | Waltham | ESMAEX-01084 | 02451 | 17.6 | Solar & Battery | 282-H7 | 2022-04-15 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_282 Waltham
NSTAR | Kingston | ESMAEX-01095 | 02364 | 15.2 | Solar & Battery | 3-18-18 | 2022-04-20 | 2022-05-26 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online
NSTAR | Bourne | ESMAEX-01091 | 02532 | 6 | Solar & Battery | 4-86-86 | 2022-04-19 | 2022-05-23 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | Plymouth | ESMAEX-01125 | 02360 | 10 | Solar | 3-90-90 | 2022-04-29 | 2022-05-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-20 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Plymouth | ESMAEX-01098 | 02360 | 7 | Battery | 3-73-938 | 2022-04-21 | 2022-05-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-02-24 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Westwood | ESMAEX-01786 | 02090 | 10 | Solar & Battery | 148-H3 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [12 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-01115 | 01803 | 6.4 | Battery | 391-H7 | 2022-04-26 | 2022-05-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online | [11 empty] | 0 | STA_391 Burlington
NSTAR | Plymouth | ESMAEX-01111 | 02360 | 10 | Battery | 3-89-922 | 2022-04-25 | 2022-07-21 | 63 |  | 63 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Natick | ESMAEX-01103 | 01760 | 18.29 | Solar | 433-H7 | 2022-04-22 | 2022-05-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-15 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Cambridge | ESMAEX-01099 | 02138 | 10 | Solar & Battery | 827-21 | 2022-04-21 | 2022-06-02 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_828 Alewife
NSTAR | Acton | ESMAEX-01112 | 01720 | 17 | Solar & Battery | 416-H8 | 2022-04-25 | 2022-05-26 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_416 Maynard
NSTAR | Framingham | ESMAEX-01108 | 01702 | 480 | Solar | 455-H5 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Vineyard Haven | ESMAEX-01162 | 02568 | 25 | Solar |  | 2022-05-10 | 2022-06-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-09-02 | Online
NSTAR | South Yarmouth | ESMAEX-01232 | 02664 | 20.2 | Solar & Battery | 4-92A-560 | 2022-05-27 | 2022-06-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Marion | ESMAEX-01896 | 02738 | 20.65 | Solar | 3-304-304 | 2022-12-06 | 2023-05-03 | 106 |  | 106 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Mattapan | ESMAEX-01121 | 02126 | 24.78 | Solar | 441-02 | 2022-04-27 | 2022-05-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [12 empty] | STA_441 Wilmont Street
NSTAR | Hyannis | ESMAEX-01119 | 02601 | 7.6 | Solar & Battery |  | 2022-04-27 | 2022-05-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online
NSTAR | North Falmouth | ESMAEX-01123 | 02556 | 15.29 | Battery | 4-78-420 | 2022-04-28 | 2022-05-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Wayland | ESMAEX-01143 | 01778 | 10.248 | Solar & Battery | 342-H1 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Holliston | ESMAEX-01124 | 01746 | 19.99 | Solar & Battery | 65-H2 | 2022-04-28 | 2022-05-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Online | [12 empty] | STA_065 Medway
NSTAR | Jamaica Plain | ESMAEX-01150 | 02130 | 50 | Solar | 284-1430H | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2025-06-02 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Framingham | ESMAEX-01130 | 01702 | 67.3 | Solar | 455-H5 | 2022-04-29 | 2022-05-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [12 empty] | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-01197 | 02740 | 100 | Solar | 2-55-47 | 2022-05-19 | 2022-06-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Duxbury | ESMAEX-01131 | 02332 | 4990 | Battery | 3-25-25 | 2022-10-04 | 2022-11-30 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2024 SEMA/Cape ASO Study |  | 4990 | STA_738 Duxbury
NSTAR | Lincoln | ESMAEX-01144 | 01773 | 25.828 | Solar | 320-H6 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online | [12 empty] | STA_320 Lexington
NSTAR | Newton Center | ESMAEX-01145 | 02459 | 19.398 | Solar | 292-H12 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Edgartown | ESMAEX-01136 | 02539 | 34.2 | Solar | 4-75-75 | 2022-05-03 | 2022-05-31 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | Cape |  |  | 0 | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-01142 | 02420 | 8.4 | Solar | 533-H4 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | East Brewster | ESMAEX-01151 | 02631 | 10 | Battery | 4-89B-577 | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online | [12 empty] | STA_975 Orleans
NSTAR | Hopkinton | ESMAEX-01154 | 01748 | 140 | Solar | 65-H7 | 2022-05-06 | 2022-06-14 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-20 | Online | [12 empty] | STA_065 Medway
NSTAR | Walpole | ESMAEX-01156 | 02081 | 250 | Solar | 146-H6 | 2022-05-06 | 2022-06-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Burlington | ESMAEX-01213 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-05-24 | 2022-06-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-07 | Online | [12 empty] | STA_391 Burlington
NSTAR | East Boston | ESMAEX-01170 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [12 empty] | STA_488 Chelsea
NSTAR | East Walpole | ESMAEX-01149 | 02032 | 9.74 | Solar & Battery | 146-H4 | 2022-05-05 | 2022-05-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [12 empty] | STA_146 Walpole
NSTAR | South Yarmouth | ESMAEX-01173 | 02664 | 79.8 | Solar | 4-92A-563 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Carlisle | ESMAEX-01172 | 01741 | 16.24 | Solar | 533-H8 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [11 empty] | 7.68 | STA_533 Hartwell Avenue
NSTAR | Sudbury | ESMAEX-01152 | 01776 | 15.2 | Solar | 342-H2 | 2022-05-05 | 2022-06-29 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Online | [11 empty] | 15.2 | STA_342 Sudbury
NSTAR | Westwood | ESMAEX-01177 | 02090 | 15.045 | Solar | 456-H1 | 2022-05-12 | 2022-06-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online | [12 empty] | STA_456 Dover
NSTAR | Woods Hole | ESMAEX-01153 | 02543 | 7.8 | Solar & Battery | 4-91-91 | 2022-05-06 | 2022-05-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-24 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Wayland | ESMAEX-01157 | 01778 | 24.192 | Solar | 342-H1 | 2022-05-09 | 2022-06-03 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [12 empty] | STA_342 Sudbury
NSTAR | East Boston | ESMAEX-01169 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-01178 | 01760 | 160 | Solar | 23-H1 | 2022-05-13 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [12 empty] | STA_240 Framingham
NSTAR | Bedford | ESMAEX-01215 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-05-24 | 2022-06-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-01160 | 02186 | 11.52 | Solar & Battery | 362-02 | 2022-05-09 | 2022-06-02 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Stoneham | ESMAEX-01174 | 02180 | 1500 | Solar & Battery | 375-H8 | 2022-06-03 | 2022-06-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2023 ASO Batch 1 |  |  | STA_375 Dragon Court
NSTAR | West Wareham | ESMAEX-01200 | 02576 | 15.045 | Solar | MID-702 | 2022-05-20 | 2022-06-23 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online
NSTAR | Ashland | ESMAEX-01167 | 01721 | 29.5 | Solar & Battery | 274-H5 | 2022-05-11 | 2022-06-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Acusnet | ESMAEX-01310 | 02743 | 11.52 | Battery | 2-241-241 | 2022-06-20 | 2022-07-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-19 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Lexington | ESMAEX-01196 | 02420 | 34.6 | Solar | 533-H4 | 2022-05-19 | 2022-06-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | North Dartmouth | ESMAEX-01179 | 02747 | 10 | Solar & Battery | 2-541-541 | 2022-05-13 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Boston | ESMAEX-01202 | 02128 | 100 | Solar | 108-195H4 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-15 | Online | [12 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-01201 | 02128 | 100 | Solar | 108-195H1 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Canton | ESMAEX-01176 | 02021 | 15.2 | Solar & Battery | 470-H8 | 2022-05-12 | 2022-07-21 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online | [12 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-01233 | 01773 | 24.78 | Solar | 320-H6 | 2022-05-27 | 2022-06-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [12 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-01181 | 01701 | 16.512 | Solar | 278-H2 | 2022-05-15 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online | [12 empty] | STA_278 Saxonville
NSTAR | West Harwich | ESMAEX-01185 | 02671 | 17.2 | Solar & Battery | 4-85-925 | 2022-05-16 | 2022-07-26 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | South Dartmouth | ESMAEX-01228 | 02748 | 15.2 | Solar | 2-528-528 | 2022-05-26 | 2022-06-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online
NSTAR | Hopkinton | ESMAEX-01184 | 01748 | 16.4 | Solar & Battery | 130-H1 | 2022-05-16 | 2022-06-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [12 empty] | STA_130 Holliston
NSTAR | Lexington | ESMAEX-01186 | 02421 | 15.3 | Solar | 320-H5XY | 2022-05-17 | 2022-06-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online | [12 empty] | STA_320 Lexington
NSTAR | Dover | ESMAEX-01238 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2022-06-01 | 2022-07-13 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [12 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-01194 | 02090 | 25 | Solar | 148-H3 | 2022-05-18 | 2022-06-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Online | [12 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-01193 | 01776 | 15.2 | Solar & Battery | 342-H4 | 2022-05-18 | 2022-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Jamaica Plain | ESMAEX-01195 | 02130 | 3.8 | Solar | 496-H4 | 2022-05-18 | 2022-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [11 empty] | 3.84 | STA_496 Hyde Park
NSTAR | Carlisle | ESMAEX-01198 | 01741 | 15.2 | Solar | 533-H8 | 2022-05-19 | 2022-06-17 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Sharon | ESMAEX-01212 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-05-23 | 2022-06-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-03 | Online | [12 empty] | STA_470 Canton
NSTAR | Winchester | ESMAEX-01203 | 01890 | 9.984 | Solar & Battery | 211-H6 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [12 empty] | STA_211 Woburn
NSTAR | Bellingham | ESMAEX-01253 | 02019 | 20 | Solar | 65-H4 | 2022-06-02 | 2022-06-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Online | [12 empty] | STA_065 Medway
NSTAR | Lexington | ESMAEX-01256 | 02421 | 19.175 | Solar | 320-H5XY | 2022-06-06 | 2022-06-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-28 | Online | [12 empty] | STA_320 Lexington
NSTAR | Holliston | ESMAEX-01204 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-05-20 | 2022-06-17 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Burlington | ESMAEX-01211 | 01803 | 10.03 | Solar & Battery | 346-1395H1 | 2022-05-23 | 2022-06-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-07 | Online | [12 empty] | STA_391 Burlington
NSTAR | Fairhaven | ESMAEX-01216 | 02719 | 15.2 | Solar | 2-220-201 | 2022-05-24 | 2022-06-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Lincoln | ESMAEX-01217 | 01773 | 14.455 | Solar & Battery | 320-H8 | 2022-05-25 | 2022-06-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [12 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-01235 | 02420 | 22.85 | Solar & Battery | 391-H11 | 2022-05-30 | 2022-07-21 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [12 empty] | STA_391 Burlington
NSTAR | Wayland | ESMAEX-01225 | 01778 | 16 | Solar | 342-H1 | 2022-05-26 | 2022-06-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Dedham | ESMAEX-01226 | 02026 | 999 | Solar | 20-H1 | 2022-07-19 | 2022-08-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | Needham | ESMAEX-01227 | 02494 | 10 | Solar & Battery | 292-H4 | 2022-05-26 | 2022-06-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Natick | ESMAEX-01236 | 01760 | 6.6 | Solar & Battery | 433-H12 | 2022-05-31 | 2022-06-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Westwood | ESMAEX-01242 | 02090 | 486 | Solar | 456-H4 | 2022-12-05 | 2023-01-26 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 499 | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-01231 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-05-27 | 2022-06-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Carlisle | ESMAEX-01237 | 01741 | 7.2 | Battery | 533-H8 | 2022-06-01 | 2022-06-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [11 empty] | 7.68 | STA_533 Hartwell Avenue
NSTAR | Maynard | ESMAEX-01239 | 01754 | 430 | Solar | 416-H6 | 2023-01-04 | 2023-02-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Online | [12 empty] | STA_416 Maynard
NSTAR | West Tisbury | ESMAEX-01243 | 02575 | 17.6 | Solar & Battery | 4-97-97 | 2022-06-02 | 2022-06-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-12-01 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Dartmouth | ESMAEX-01244 | 02748 | 500 | Solar | 2-53-65 | 2022-10-04 | 2022-10-27 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Osterville | ESMAEX-01248 | 02655 | 18.59 | Solar | 4-88-88 | 2022-06-02 | 2022-07-01 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Bedford | ESMAEX-01278 | 01730 | 7.08 | Solar & Battery |  | 2022-06-10 | 2022-07-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online
NSTAR | Buzzards Bay | ESMAEX-01254 | 02532 | 6 | Battery | 3-88-2J3 | 2022-06-03 | 2022-06-21 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | West Somerville | ESMAEX-01294 | 02144 | 8.418 | Solar & Battery | 250-H6 | 2022-06-14 | 2022-07-13 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [12 empty] | STA_250 Mystic
NSTAR | Maynard | ESMAEX-01262 | 01754 | 62.5 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Newton Center | ESMAEX-01338 | 02459 | 67.3 | Solar | 443-02 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Waltham | ESMAEX-01259 | 02452 | 15.2 | Solar & Battery | 450-H4 | 2022-06-07 | 2022-06-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Lexington | ESMAEX-01497 | 02421 | 15.2 | Solar & Battery | 3401 | 2022-08-23 | 2022-09-27 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [11 empty] | 19.9 | STA_320 Lexington
NSTAR | Acton | ESMAEX-01260 | 01720 | 17.6 | Solar & Battery | 416-H4 | 2022-06-07 | 2022-06-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_416 Maynard
NSTAR | Carver | ESMAEX-01387 | 02330 | 38 | Solar | 3-11-11 | 2022-07-19 | 2022-08-17 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online
NSTAR | Maynard | ESMAEX-01263 | 01754 | 125 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-01264 | 01754 | 33.3 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-01266 | 01754 | 125 | Solar | 416-H6 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_416 Maynard
NSTAR | Maynard | ESMAEX-01267 | 01754 | 487.5 | Solar | 342-H8 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-01315 | 02134 | 200 | Solar | 329-H2 | 2022-06-21 | 2022-07-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-27 | Online | [12 empty] | STA_329 Brighton
NSTAR | Dorchester | ESMAEX-01305 | 02125 | 499 | Solar | 106-H2 | 2022-06-17 | 2022-07-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-02 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Carlisle | ESMAEX-01275 | 01741 | 21.4 | Solar | 512-1399H1 | 2022-06-09 | 2022-06-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-01283 | 02090 | 16.5 | Solar | 456-H1 | 2022-06-10 | 2022-07-18 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-28 | Online | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01312 | 02420 | 11.4 | Solar & Battery |  | 2022-06-20 | 2022-07-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online
NSTAR | Sharon | ESMAEX-01683 | 02067 | 230 | Other | 146-H1 | 2022-10-14 | 2022-11-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Online | [11 empty] | 230 | STA_146 Walpole
NSTAR | Needham | ESMAEX-01285 | 02492 | 20 | Solar | 148-01 | 2022-06-13 | 2022-07-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online | [12 empty] | STA_148 Needham
NSTAR | Eastham | ESMAEX-01290 | 02642 | 3.8 | Solar | 4-94A-94A | 2022-06-14 | 2022-08-23 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online | [12 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-01331 | 01760 | 15.2 | Solar | 433-H12 | 2022-06-28 | 2022-09-29 | 67 |  | 67 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Chilmark | ESMAEX-01416 | 02535 | 8.26 | Solar & Battery | 4-97-97 | 2022-07-28 | 2022-08-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Burlington | ESMAEX-01320 | 01803 | 15.3 | Solar | 391-H7 | 2022-06-24 | 2022-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online | [12 empty] | STA_391 Burlington
NSTAR | Plymouth | ESMAEX-01309 | 02360 | 10 | Solar & Battery | 3-90-90 | 2022-06-18 | 2022-07-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Dover | ESMAEX-01313 | 02030 | 38.904 | Solar & Battery | 456-H5 | 2022-06-21 | 2022-10-25 | 90 |  | 90 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Online | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01526 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-08-30 | 2022-09-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Green Harbor | ESMAEX-01300 | 02041 | 103.68 | Solar | 3-27-970 | 2024-01-09 | 2024-01-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-08 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Ashland | ESMAEX-01362 | 01721 | 15.2 | Solar & Battery | 274-H6 | 2022-07-11 | 2022-08-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online
NSTAR | Lincoln | ESMAEX-01394 | 01773 | 22.6 | Solar & Battery | 320-H8 | 2022-07-20 | 2022-08-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-23 | Online | [12 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-01355 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-07-08 | 2022-09-14 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [12 empty] | STA_320 Lexington
NSTAR | Arlington | ESMAEX-02499 | 02476 | 133.3 | Solar | 211-H3 | 2023-05-21 | 2023-08-24 | 69 |  | 69 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-01322 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2022-06-24 | 2022-07-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_470 Canton
NSTAR | Medway | ESMAEX-01321 | 02053 | 19.032 | Solar | 65-H2 | 2022-06-24 | 2022-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online | [12 empty] | STA_065 Medway
NSTAR | Brighton | ESMAEX-01433 | 02135 | 100 | Solar | 315-H1 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | Edgartown | ESMAEX-01415 | 02539 | 16.1 | Solar |  | 2022-07-28 | 2022-08-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online
NSTAR | Newton | ESMAEX-01347 | 02458 | 50 | Solar | 467-H14 | 2022-07-06 | 2022-09-14 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Online | [12 empty] | STA_467 Watertown
NSTAR | Carver | ESMAEX-01327 | 02330 | 100 | Solar | 3-81-81 | 2022-06-27 | 2022-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | West Tisbury | ESMAEX-01340 | 02575 | 23.6 | Solar & Battery | 4-97-97 | 2022-07-01 | 2022-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Edgartown | ESMAEX-01348 | 02539 | 466.66 | Solar & Battery |  | 2022-07-06 | 2022-07-08 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | [11 empty] | 466.66
NSTAR | Weston | ESMAEX-01339 | 02493 | 17.6 | Solar | 282-H10 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [12 empty] | STA_282 Waltham
NSTAR | Acusnet | ESMAEX-01336 | 02743 | 9.3 | Solar & Battery | 2-241-241 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Ashland | ESMAEX-01359 | 01721 | 240 | Solar | 274-1429H1 | 2022-07-11 | 2022-07-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Dover | ESMAEX-01373 | 02030 | 150 | Solar | 456-H5 | 2022-07-13 | 2022-08-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-07-02 | Online | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01365 | 02421 | 7 | Solar & Battery | 320-H5XY | 2022-07-12 | 2022-07-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online | [12 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-01342 | 01701 | 6 | Solar | 278-H1 | 2022-07-01 | 2022-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Online | [11 empty] | 6 | STA_278 Saxonville
NSTAR | Charlestown | ESMAEX-01343 | 02129 | 4999 | Battery | 250-H3 | 2022-09-23 | 2022-10-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [9 empty] | 2023 ASO Batch 1 |  |  | STA_250 Mystic
NSTAR | Burlington | ESMAEX-01364 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-07-12 | 2022-08-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-27 | Online | [12 empty] | STA_391 Burlington
NSTAR | Woburn | ESMAEX-01344 | 01801 | 7.38 | Solar & Battery | 211-H8 | 2022-07-05 | 2022-07-21 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [12 empty] | STA_211 Woburn
NSTAR | New Bedford | ESMAEX-01374 | 02745 | 17.57 | Solar | 2-102-608 | 2022-07-13 | 2022-08-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Oak Bluffs | ESMAEX-01389 | 02557 | 26.385 | Solar | 4-99-224 | 2022-07-20 | 2022-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online | [12 empty] | STA_933 Falmouth
NSTAR | Natick | ESMAEX-01354 | 01760 | 17.6 | Solar | 433-H7 | 2022-07-08 | 2022-07-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Mashpee | ESMAEX-01363 | 02649 | 6 | Solar | 4-77A-77A | 2022-07-11 | 2022-07-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | North Truro | ESMAEX-01378 | 02652 | 10 | Battery | 4-96-96 | 2022-07-15 | 2022-08-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Milton | ESMAEX-01368 | 02186 | 17.6 | Solar | 4309 | 2022-07-12 | 2022-08-15 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Carlisle | ESMAEX-01437 | 01741 | 20.2 | Solar & Battery | 512-1399H1 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-10 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Harwichport | ESMAEX-01388 | 02646 | 10 | Battery | 4-85-592 | 2022-07-19 | 2022-08-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Westwood | ESMAEX-01503 | 02090 | 15.2 | Solar & Battery | 456-H1 | 2022-08-23 | 2022-09-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [12 empty] | STA_456 Dover
NSTAR | Milton | ESMAEX-01508 | 02186 | 19 | Solar & Battery | 362-1209H2 | 2022-08-24 | 2022-09-22 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-03 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Framingham | ESMAEX-01377 | 01702 | 200 | Solar |  | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [11 empty] | 200
NSTAR | Boston | ESMAEX-01603 | 02130 | 100 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Norfolk | ESMAEX-01417 | 02056 | 20.2 | Solar & Battery | 146-H10 | 2022-07-29 | 2022-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Online | [12 empty] | STA_146 Walpole
NSTAR | Boston | ESMAEX-01900 | 02125 | 34.6 | Solar | 106-1N31H1 | 2022-12-07 | 2023-01-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-01407 | 02119 | 120 | Solar | 106-1N31H6 | 2022-07-22 | 2022-08-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online
NSTAR | Framingham | ESMAEX-01386 | 01702 | 200 | Solar | 455-H4 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Weston | ESMAEX-01390 | 02493 | 10 | Solar & Battery | 282-H1 | 2022-07-20 | 2022-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online | [11 empty] | 10 | STA_282 Waltham
NSTAR | Bedford | ESMAEX-01393 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-07-20 | 2022-09-29 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-06-27 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-01659 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2022-10-05 | 2022-11-10 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [12 empty] | STA_342 Sudbury
NSTAR | North Dartmouth | ESMAEX-01395 | 02747 | 19 | Solar | 2-528-528 | 2022-07-21 | 2022-08-23 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online
NSTAR | Plymouth | ESMAEX-01399 | 02360 | 48 | Solar | 3-89-922 | 2022-07-21 | 2022-08-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Framingham | ESMAEX-01409 | 01702 | 200 | Solar | 455-H4 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Plymouth | ESMAEX-01411 | 02360 | 67.3 | Solar | 3-12-932 | 2022-07-25 | 2022-08-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Provincetown | ESMAEX-01414 | 02657 | 12.005 | Solar & Battery | 4-675-675 | 2022-07-27 | 2022-08-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Hatchville | ESMAEX-01412 | 02536 | 17.6 | Solar | 4-78-78 | 2022-07-27 | 2022-08-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Medfield | ESMAEX-01442 | 02052 | 19.8 | Solar | 456-H3 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online | [12 empty] | STA_456 Dover
NSTAR | Watertown | ESMAEX-01443 | 02472 | 16.83 | Solar & Battery | 467-H4 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-21 | Online | [12 empty] | STA_467 Watertown
NSTAR | Dorchester | ESMAEX-01505 | 02125 | 72 | Solar | 483-H1 | 2022-08-24 | 2022-09-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Falmouth | ESMAEX-01418 | 02540 | 178.2 | Solar | 4-72-72 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-09 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Hopkinton | ESMAEX-01424 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2022-08-02 | 2022-08-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Framingham | ESMAEX-01419 | 01702 | 200 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-30 | Online | [11 empty] | 200 | STA_455 West Framingham
NSTAR | Dover | ESMAEX-01420 | 02030 | 17.6 | Solar | 456-H5 | 2022-08-01 | 2022-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online | [12 empty] | STA_456 Dover
NSTAR | Chilmark | ESMAEX-01423 | 02535 | 17.6 | Solar & Battery | 4-97-97 | 2022-08-02 | 2022-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Falmouth | ESMAEX-01422 | 02540 | 17.4 | Solar | 4-72-72 | 2022-08-02 | 2022-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Stoneham | ESMAEX-01425 | 02180 | 18.6 | Solar | 375-H8 | 2022-08-03 | 2022-08-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Framingham | ESMAEX-01432 | 01701 | 15.2 | Solar | 455-H1 | 2022-08-03 | 2022-09-27 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Kingston | ESMAEX-01431 | 02364 | 240 | Solar | 3-26-26 | 2022-08-03 | 2022-08-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Dedham | ESMAEX-01429 | 02026 | 270 | Solar | 13-H1 | 2022-08-03 | 2022-08-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-27 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Dedham | ESMAEX-01430 | 02026 | 150 | Solar | 20-H1 | 2022-08-03 | 2022-08-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-10-03 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Westwood | ESMAEX-01541 | 02090 | 15.2 | Solar & Battery | 469-H2 | 2022-09-02 | 2022-10-11 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | Waban | ESMAEX-01446 | 02468 | 12.078 | Solar & Battery | 277-04 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [12 empty] | STA_467 Watertown
NSTAR | Hopkinton | ESMAEX-01458 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-08-10 | 2022-09-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-01436 | 02360 | 15.2 | Solar | 3-90-10J2 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online | [8 empty] | Plymouth |  |  | 15.2 | STA_715 Valley
NSTAR | Wayland | ESMAEX-01496 | 01778 | 22.8 | Solar & Battery | 342-H3 | 2022-08-22 | 2022-09-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-01440 | 02452 | 15.2 | Solar | 282-H7 | 2022-08-05 | 2022-08-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [11 empty] | 15.2 | STA_282 Waltham
NSTAR | Framingham | ESMAEX-01441 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [11 empty] | 250 | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-01453 | 02420 | 6 | Solar | 391-H11 | 2022-08-09 | 2022-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [11 empty] | 6 | STA_391 Burlington
NSTAR | Needham | ESMAEX-01463 | 02492 | 20 | Solar | 148-H7 | 2022-08-11 | 2022-09-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-06 | Online | [12 empty] | STA_148 Needham
NSTAR | East Boston | ESMAEX-01610 | 02128 | 69.2 | Solar | 488-H8 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Medfield | ESMAEX-01452 | 02052 | 8.7 | Solar & Battery | 456-H2 | 2022-08-09 | 2022-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Online | [12 empty] | STA_456 Dover
NSTAR | Woburn | ESMAEX-01459 | 01801 | 6 | Solar | 375-H6 | 2022-08-10 | 2022-09-01 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [11 empty] | 6 | STA_375 Dragon Court
NSTAR | Hopkinton | ESMAEX-01464 | 01748 | 250 | Solar | 126-H1 | 2022-09-09 | 2022-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01467 | 01720 | 250 | Solar | 416-H9 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Online | [12 empty] | STA_416 Maynard
NSTAR | Framingham | ESMAEX-01470 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [11 empty] | 250 | STA_455 West Framingham
NSTAR | Wayland | ESMAEX-01471 | 01778 | 16 | Solar | 278-H2 | 2022-08-15 | 2022-09-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [11 empty] | 16 | STA_278 Saxonville
NSTAR | Sharon | ESMAEX-01472 | 02067 | 19 | Solar | 470-H3 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Online | [12 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-01487 | 01748 | 220 | Solar | 126-H1 | 2022-08-19 | 2022-09-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Weston | ESMAEX-01490 | 02493 | 15.3 | Solar & Battery | 282-H1 | 2022-08-19 | 2022-09-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [12 empty] | STA_282 Waltham
NSTAR | Orleans | ESMAEX-01657 | 02653 | 29.76 | Solar & Battery | 4-628-628 | 2022-10-03 | 2022-10-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-06 | Online | [11 empty] | 15.36 | STA_975 Orleans
NSTAR | Woburn | ESMAEX-01491 | 01801 | 217.3 | Solar | 375-H3 | 2022-08-19 | 2022-09-27 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Eastham | ESMAEX-01481 | 02642 | 7.68 | Battery | 4-94A-94A | 2022-08-18 | 2022-08-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [12 empty] | STA_975 Orleans
NSTAR | North Truro | ESMAEX-01485 | 02652 | 21.6 | Solar | 4-96-96 | 2022-08-18 | 2022-09-27 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-01-10 | Compliances Documents | [12 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-01493 | 01801 | 237.5 | Solar | 375-H3 | 2022-08-19 | 2022-09-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Wayland | ESMAEX-01531 | 01778 | 19.398 | Solar | 342-H1 | 2022-09-01 | 2022-10-25 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Watertown | ESMAEX-01498 | 02472 | 492 | Solar | 370-1327 | 2022-09-29 | 2022-10-25 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [12 empty] | STA_467 Watertown
NSTAR | Waltham | ESMAEX-01660 | 02453 | 90 | Solar | 33-H1 | 2022-10-05 | 2022-10-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Watertown | ESMAEX-01499 | 02472 | 492 | Solar | 305-1422H2 | 2022-09-29 | 2022-10-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-21 | Online
NSTAR | Plympton | ESMAEX-01542 | 02367 | 15.2 | Solar & Battery | 3-50-50 | 2022-09-06 | 2022-09-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online | [8 empty] | Plymouth |  |  |  | STA_727 Brook Street
NSTAR | Waltham | ESMAEX-01516 | 02453 | 73.3 | Solar | 33-H2 | 2022-08-26 | 2022-09-22 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [12 empty] | STA_282 Waltham
NSTAR | Newton Upper Falls | ESMAEX-01543 | 02464 | 15.2 | Solar & Battery | 292-H7 | 2022-09-06 | 2022-09-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Framingham | ESMAEX-01509 | 01701 | 17.1 | Solar | 455-H1 | 2022-08-25 | 2022-09-22 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Green Harbor | ESMAEX-01684 | 02041 | 20.2 | Solar & Battery | 3-27-970 | 2022-10-17 | 2022-11-23 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Online | [11 empty] | 0 | STA_738 Duxbury
NSTAR | Sudbury | ESMAEX-01513 | 01776 | 17.6 | Solar | 342-H6 | 2022-08-25 | 2022-09-22 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-05-09 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Hopkinton | ESMAEX-01537 | 01748 | 250 | Solar | 65-H7 | 2022-09-02 | 2022-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [12 empty] | STA_065 Medway
NSTAR | Wayland | ESMAEX-01521 | 01778 | 20.2 | Solar & Battery | 342-H3 | 2022-08-29 | 2022-09-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-01525 | 02492 | 15.2 | Solar | 148-H4 | 2022-08-30 | 2022-09-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online | [12 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-01528 | 01803 | 32.85 | Solar | 391-H2 | 2022-08-30 | 2022-09-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_391 Burlington
NSTAR | Marshfield | ESMAEX-01540 | 02050 | 3.8 | Solar | 3-25-42J2 | 2022-09-02 | 2022-09-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-30 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Hopkinton | ESMAEX-01619 | 01748 | 16.2 | Solar | 126-H1 | 2022-09-22 | 2022-10-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Hopkinton | ESMAEX-01538 | 01748 | 250 | Solar | 126-H2 | 2022-09-02 | 2022-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01534 | 01720 | 100 | Solar | 416-H4 | 2022-11-21 | 2023-01-30 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Online | [12 empty] | STA_416 Maynard
NSTAR | Waban | ESMAEX-01585 | 02468 | 15.2 | Solar & Battery | 292-H7 | 2022-09-14 | 2022-10-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Milton | ESMAEX-01545 | 02186 | 13.44 | Solar | 362-1209H2 | 2022-09-06 | 2022-10-07 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-01553 | 01760 | 19.8 | Solar | 240-H5 | 2022-09-08 | 2022-09-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [12 empty] | STA_240 Framingham
NSTAR | Newton Highlands | ESMAEX-01549 | 02461 | 6.3 | Solar & Battery | 292-H12 | 2022-09-07 | 2022-11-30 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Woburn | ESMAEX-01562 | 01801 | 210 | Solar | 375-H9 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Winchester | ESMAEX-01673 | 01890 | 17.6 | Solar & Battery | 211-H1 | 2022-10-11 | 2022-11-10 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [12 empty] | STA_211 Woburn
NSTAR | Bedford | ESMAEX-01548 | 01730 | 15.744 | Solar & Battery | 533-H7 | 2022-09-07 | 2022-10-27 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-01560 | 02090 | 15.2 | Solar | 456-H4 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Online | [12 empty] | STA_456 Dover
NSTAR | Duxbury | ESMAEX-01633 | 02332 | 15.738 | Solar | 3-26-26 | 2022-09-27 | 2022-11-30 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online
NSTAR | Plymouth | ESMAEX-01601 | 02360 | 22.8 | Solar & Battery | 3-71-38J1 | 2022-09-19 | 2022-10-27 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-03 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Weston | ESMAEX-01636 | 02493 | 20.352 | Solar | 282-H10 | 2022-09-27 | 2022-10-27 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [12 empty] | STA_282 Waltham
NSTAR | Lexington | ESMAEX-01804 | 02421 | 10 | Battery | 320-H2 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [12 empty] | STA_320 Lexington
NSTAR | Hopkinton | ESMAEX-01692 | 01748 | 15.2 | Solar & Battery | 455-H8 | 2022-10-18 | 2022-11-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Norfolk | ESMAEX-01589 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-09-14 | 2022-09-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [12 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-01911 | 02138 | 30 | Solar | 831-1111 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [12 empty] | STA_831 Putnam
NSTAR | Truro | ESMAEX-01579 | 02666 | 17.6 | Solar & Battery | 4-96-96 | 2022-09-13 | 2022-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Cambridge | ESMAEX-01703 | 02138 | 30 | Solar | 819-1NB2 | 2022-10-21 | 2022-11-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [12 empty] | STA_402 Newton Street
NSTAR | Boston | ESMAEX-01604 | 02130 | 86.4 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Weston | ESMAEX-01599 | 02493 | 25 | Solar & Battery | 282-H8 | 2022-09-16 | 2022-10-25 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Online | [12 empty] | STA_282 Waltham
NSTAR | Wellfleet | ESMAEX-01591 | 02667 | 18.816 | Solar | 4-94B-94B | 2022-09-15 | 2022-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Orleans | ESMAEX-01596 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-09-16 | 2022-10-11 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Online | [12 empty] | STA_975 Orleans
NSTAR | West Wareham | ESMAEX-01592 | 02576 | 19 | Solar | 3-85-85 | 2022-09-15 | 2022-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Hopkinton | ESMAEX-01627 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-26 | 2022-10-27 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  | 2023-02-15 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Lincoln | ESMAEX-01664 | 01773 | 19.845 | Solar | 320-H8 | 2022-10-06 | 2022-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [12 empty] | STA_320 Lexington
NSTAR | Newton Lower Falls | ESMAEX-01607 | 02462 | 34 | Solar & Battery | 292-H2 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-01623 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-09-23 | 2022-11-04 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [12 empty] | STA_320 Lexington
NSTAR | Acton | ESMAEX-01611 | 01720 | 15.3 | Solar | 416-H5 | 2022-09-21 | 2022-12-29 | 71 |  | 71 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [12 empty] | STA_416 Maynard
NSTAR | Cummaquid | ESMAEX-01616 | 02637 | 9 | Solar | 4-92A-92A | 2022-09-21 | 2022-10-25 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Natick | ESMAEX-01617 | 01760 | 250 | Solar | 433-H5 | 2022-10-14 | 2022-11-23 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-01624 | 01803 | 18.9 | Solar | 391-H6 | 2022-09-23 | 2022-10-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_391 Burlington
NSTAR | Framingham | ESMAEX-01634 | 01701 | 17.92 | Solar | 433-H3 | 2022-09-27 | 2022-10-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Walpole | ESMAEX-01628 | 02081 | 10 | Solar | 2607 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Online | [12 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-01629 | 02494 | 17.6 | Solar | 292-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Online | [11 empty] | 17.6 | STA_292 Newton Highlands
NSTAR | Wayland | ESMAEX-01825 | 01778 | 19.5 | Solar | 342-H1 | 2022-11-17 | 2023-01-04 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Dover | ESMAEX-01630 | 02030 | 9 | Solar | 456-H5 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-21 | Online | [12 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-01644 | 02360 | 25 | Solar | 3-10-10 | 2022-09-29 | 2022-10-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online
NSTAR | Burlington | ESMAEX-01653 | 01803 | 15.2 | Solar & Battery | 346-1395H1 | 2022-10-03 | 2022-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Online | [12 empty] | STA_391 Burlington
NSTAR | Sherborn | ESMAEX-01663 | 01770 | 15.2 | Solar & Battery | 274-H2 | 2022-10-06 | 2022-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-01646 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-29 | 2022-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01648 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-09-30 | 2022-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online | [12 empty] | STA_416 Maynard
NSTAR | Onset | ESMAEX-01649 | 02558 | 10 | Battery | 3-88-17J1 | 2022-10-03 | 2022-12-07 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online
NSTAR | Natick | ESMAEX-01796 | 01760 | 16.2 | Solar | 2304 | 2022-11-10 | 2022-12-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Online | [12 empty] | STA_240 Framingham
NSTAR | Framingham | ESMAEX-01655 | 01702 | 15.2 | Solar | 24-H1 | 2022-10-03 | 2022-10-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Online | [11 empty] | 15.2 | STA_240 Framingham
NSTAR | Acton | ESMAEX-01714 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [12 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-01661 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2022-10-05 | 2022-11-29 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [12 empty] | STA_146 Walpole
NSTAR | Fairhaven | ESMAEX-01787 | 02719 | 100 | Solar | 2-221-221 | 2022-11-09 | 2022-11-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Plymouth | ESMAEX-01665 | 02360 | 16 | Solar | 3-12-12 | 2022-10-06 | 2022-11-30 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online
NSTAR | Bedford | ESMAEX-01779 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Edgartown | ESMAEX-01669 | 02539 | 37.6 | Solar | 4-75-75 | 2022-10-07 | 2022-10-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Westwood | ESMAEX-01668 | 02090 | 15.2 | Solar | 456-H1 | 2022-10-07 | 2022-10-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [12 empty] | STA_456 Dover
NSTAR | Plympton | ESMAEX-01670 | 02367 | 17.6 | Solar | 3-50-50 | 2022-10-10 | 2022-11-22 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [8 empty] | Plymouth |  |  | 17.6 | STA_727 Brook Street
NSTAR | Maynard | ESMAEX-01675 | 02067 | 250 | Solar | 416-H6 | 2022-10-11 | 2022-11-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-01854 | 01760 | 19.8 | Solar | 240-H1 | 2022-11-28 | 2022-12-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [12 empty] | STA_240 Framingham
NSTAR | Plymouth | ESMAEX-01680 | 02360 | 25 | Solar | 3-10-10 | 2022-10-12 | 2022-10-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online
NSTAR | Needham | ESMAEX-01681 | 02492 | 15.2 | Solar & Battery | 391-H11 | 2022-10-13 | 2022-12-07 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-12-20 | Online | [12 empty] | STA_148 Needham
NSTAR | Kingston | ESMAEX-01725 | 02364 | 7.6 | Solar & Battery | 3-50-914 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [8 empty] | Plymouth |  |  |  | STA_727 Brook Street
NSTAR | Wayland | ESMAEX-01892 | 01778 | 17.6 | Solar | 342-H1 | 2022-12-06 | 2022-12-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Ashland | ESMAEX-01685 | 01721 | 19.92 | Solar & Battery | 455-H3 | 2022-10-17 | 2022-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-05 | Online | [11 empty] | 19.92 | STA_455 West Framingham
NSTAR | Sharon | ESMAEX-01690 | 02067 | 16.47 | Solar | 470-H12 | 2022-10-17 | 2022-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [12 empty] | STA_470 Canton
NSTAR | Woburn | ESMAEX-01720 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | East Freetown | ESMAEX-01691 | 02717 | 2000 | Solar & Battery | 2-108-108 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | New Bedford | 2024 SEMA/Cape ASO Study | Hold In Queue | 1500 | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-01807 | 02420 | 20.2 | Solar & Battery | 391-H11 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [12 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-01716 | 01720 | 15.2 | Solar & Battery | 512-1399H1 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | North Eastham | ESMAEX-01694 | 02651 | 16 | Solar | 4-94B-646 | 2022-10-19 | 2022-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [11 empty] | 15.36 | STA_976 Wellfleet
NSTAR | Boston | ESMAEX-01699 | 02132 | 483 | Solar |  | 2022-10-19 | 2022-11-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online
NSTAR | Lexington | ESMAEX-01697 | 02421 | 22.8 | Solar & Battery | 320-H2 | 2022-10-19 | 2022-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Online | [12 empty] | STA_320 Lexington
NSTAR | Sudbury | ESMAEX-01711 | 01776 | 17.6 | Solar & Battery | 342-H7 | 2022-10-24 | 2022-11-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-01706 | 01741 | 10 | Battery | 512-1399H1 | 2022-10-21 | 2022-11-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-15 | Online | [11 empty] | 0 | STA_533 Hartwell Avenue
NSTAR | Plympton | ESMAEX-01740 | 02367 | 15.2 | Solar & Battery | 3-50-43J1 | 2022-10-31 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online
NSTAR | East Freetown | ESMAEX-01966 | 02717 | 10 | Battery | 2-108-108 | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-01717 | 02420 | 57 | Solar | 3406 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online
NSTAR | Hopkinton | ESMAEX-01718 | 01748 | 15.2 | Solar | 126-H4 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Natick | ESMAEX-01929 | 01760 | 10 | Battery | 433-H10 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-18 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Hyannis | ESMAEX-01723 | 02601 | 166.6 | Solar | 4-64-64 | 2022-10-25 | 2022-12-16 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Walpole | ESMAEX-01722 | 02081 | 22.2 | Solar | 2606 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [12 empty] | STA_146 Walpole
NSTAR | Duxbury | ESMAEX-01726 | 02332 | 9.9 | Solar & Battery | 3-26-26 | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online
NSTAR | Centerville | ESMAEX-01727 | 02632 | 20 | Solar | 4-82-82 | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Wellfleet | ESMAEX-01729 | 02667 | 18.9 | Solar |  | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-08 | Online
NSTAR | Dover | ESMAEX-01734 | 02030 | 20 | Solar | 456-H5 | 2022-10-27 | 2022-11-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-18 | Online | [11 empty] | 20 | STA_456 Dover
NSTAR | Stoneham | ESMAEX-01739 | 02180 | 7.6 | Solar & Battery | 211-H12 | 2022-10-31 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [12 empty] | STA_211 Woburn
NSTAR | Dedham | ESMAEX-01768 | 02026 | 15.2 | Solar & Battery | 456-H4 | 2022-11-04 | 2022-11-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [12 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-01757 | 01748 | 12.9 | Solar | 126-H2 | 2022-11-03 | 2022-12-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-19 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Burlington | ESMAEX-01736 | 01803 | 21.12 | Solar | 391-H6 | 2022-10-28 | 2023-03-22 | 103 |  | 103 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [12 empty] | STA_391 Burlington
NSTAR | New Bedford | ESMAEX-01737 | 02745 | 10 | Solar | 2-105-105 | 2022-10-28 | 2022-12-13 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Needham | ESMAEX-01738 | 02494 | 20 | Solar & Battery | 148-H1 | 2022-10-28 | 2022-11-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [11 empty] | 10 | STA_148 Needham
NSTAR | Dartmouth | ESMAEX-01745 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Dartmouth | ESMAEX-01746 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Dartmouth | ESMAEX-01747 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Sherborn | ESMAEX-01775 | 01770 | 9.7 | Solar | 130-H2 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Online | [12 empty] | STA_130 Holliston
NSTAR | North Dartmouth | ESMAEX-01771 | 02747 | 15.2 | Solar & Battery | 2-541-541 | 2022-11-04 | 2022-11-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Walpole | ESMAEX-01784 | 02081 | 15.2 | Solar | 146-H4 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-25 | Online | [12 empty] | STA_146 Walpole
NSTAR | Carver | ESMAEX-01753 | 02330 | 17.7 | Solar | 3-10-10 | 2022-11-02 | 2022-11-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Online
NSTAR | Westwood | ESMAEX-01974 | 02090 | 120 | Solar | 469-H4 | 2023-01-05 | 2023-02-23 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online
NSTAR | Sudbury | ESMAEX-01756 | 01776 | 16 | Solar | 342-H8 | 2022-11-02 | 2022-11-16 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Weston | ESMAEX-01822 | 02493 | 15.2 | Solar & Battery | 342-H1 | 2022-11-16 | 2022-12-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Mashpee | ESMAEX-01765 | 02649 | 15.2 | Solar & Battery | 4-77B-454 | 2022-11-03 | 2022-11-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Online
NSTAR | West Somerville | ESMAEX-01788 | 02144 | 27.57 | Solar & Battery | 1603 | 2022-11-09 | 2022-12-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [11 empty] | 13.57 | STA_828 Alewife
NSTAR | Hyannis | ESMAEX-01970 | 02601 | 100 | Solar | 4-84B-524 | 2023-01-05 | 2023-01-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Hopkinton | ESMAEX-01843 | 01748 | 18 | Solar | 126-H3 | 2022-11-23 | 2023-02-03 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Orleans | ESMAEX-01973 | 02653 | 80 | Solar | 4-89B-89B | 2023-01-05 | 2023-02-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Online | [12 empty] | STA_975 Orleans
NSTAR | Canton | ESMAEX-01770 | 02021 | 35.2 | Solar & Battery | 470-H7 | 2022-11-04 | 2022-11-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Online | [12 empty] | STA_470 Canton
NSTAR | Carlisle | ESMAEX-01773 | 01741 | 15.2 | Solar | 533-H8 | 2022-11-07 | 2022-12-05 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-05-25 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Wareham | ESMAEX-01774 | 02571 | 66.6 | Solar | 3-86-966 | 2022-11-07 | 2022-11-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Kingston | ESMAEX-01798 | 02364 | 180 | Solar | 3-17-17 | 2022-11-10 | 2022-12-07 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-16 | Online
NSTAR | South Dartmouth | ESMAEX-01780 | 02748 | 17.6 | Solar | 2-53-65 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-13 | Online | [11 empty] | 17.6 | STA_611 Pine Street
NSTAR | Norfolk | ESMAEX-01782 | 02056 | 12.6 | Solar & Battery | 65-H1 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [12 empty] | STA_065 Medway
NSTAR | Milton | ESMAEX-01781 | 02186 | 15.2 | Solar | 362-1209H2 | 2022-11-08 | 2022-11-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Online | [11 empty] | 15.2 | STA_496 Hyde Park
NSTAR | Rochester | ESMAEX-01778 | 02770 | 15.2 | Solar | 3-702-702 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online | [8 empty] | Marion-Fairhaven |  |  | 15.2 | STA_745 Rochester
NSTAR | Hopkinton | ESMAEX-01884 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-12-02 | 2022-12-19 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Natick | ESMAEX-01785 | 01760 | 13.8 | Solar | 240-H1 | 2022-11-08 | 2022-12-08 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Online | [12 empty] | STA_240 Framingham
NSTAR | Hopkinton | ESMAEX-01910 | 01748 | 20 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-01795 | 02421 | 15.2 | Solar & Battery | 533-H4 | 2022-11-10 | 2022-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Freetown | ESMAEX-01812 | 02717 | 249 | Solar | 2-108-108 | 2022-11-15 | 2022-12-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_636 Industrial Park
NSTAR | Sherborn | ESMAEX-01944 | 01770 | 18.66 | Solar | 274-H2 | 2022-12-23 | 2023-01-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Burlington | ESMAEX-01805 | 01803 | 15.2 | Solar & Battery | 391-H7 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [12 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-01885 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2022-12-02 | 2023-01-12 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Stoneham | ESMAEX-01811 | 02180 | 10 | Solar & Battery | 375-H2 | 2022-11-15 | 2022-12-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Dover | ESMAEX-01827 | 02030 | 19.58 | Solar | 456-H3 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_456 Dover
NSTAR | Roslindale | ESMAEX-01858 | 02131 | 6 | Solar & Battery | 496-H5 | 2022-11-29 | 2022-12-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | West Newton | ESMAEX-01831 | 02465 | 31.49 | Solar | 1713 | 2022-11-18 | 2022-12-16 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-01829 | 02081 | 20.06 | Solar | 146-H4 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [12 empty] | STA_146 Walpole
NSTAR | Chatham | ESMAEX-01842 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2022-11-22 | 2022-12-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online | [11 empty] | 10 | STA_975 Orleans
NSTAR | Sharon | ESMAEX-01863 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online | [12 empty] | STA_146 Walpole
NSTAR | Holliston | ESMAEX-01856 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Mashpee | ESMAEX-01835 | 02649 | 17.58 | Solar | 4-452-452 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Framingham | ESMAEX-01837 | 01701 | 20.2 | Solar & Battery | 455-H1 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Online | [11 empty] | 15.36 | STA_455 West Framingham
NSTAR | Wareham | ESMAEX-01836 | 02571 | 12.9 | Solar | 3-83-83 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Sudbury | ESMAEX-01932 | 01776 | 17.568 | Solar | 342-H7 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-01838 | 02492 | 15.2 | Solar & Battery | 148-H4 | 2022-11-21 | 2022-12-16 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [12 empty] | STA_148 Needham
NSTAR | Kingston | ESMAEX-01864 | 02364 | 15.2 | Solar & Battery | 3-15-15 | 2022-11-29 | 2022-12-29 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online
NSTAR | Needham | ESMAEX-01871 | 02492 | 4.35 | Solar | 148-H6 | 2022-11-30 | 2022-12-08 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online | [12 empty] | STA_148 Needham
NSTAR | Wayland | ESMAEX-01851 | 01778 | 187.3 | Solar | 342-H3 | 2022-11-28 | 2022-12-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Duxbury | ESMAEX-01845 | 02332 | 11.4 | Solar & Battery | 3-23-23 | 2022-11-23 | 2022-12-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Norfolk | ESMAEX-01848 | 02056 | 19.2 | Solar | 65-H1 | 2022-11-26 | 2022-12-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Online | [12 empty] | STA_065 Medway
NSTAR | Marshfield | ESMAEX-01850 | 02050 | 10 | Solar & Battery | 3-25-42J2 | 2022-11-28 | 2022-12-29 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Canton | ESMAEX-02179 | 02021 | 240 | Solar | 470-H10 | 2023-02-21 | 2023-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [12 empty] | STA_470 Canton
NSTAR | Westwood | ESMAEX-01853 | 02090 | 15.2 | Solar | 456-H4 | 2022-11-28 | 2022-12-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Online | [12 empty] | STA_456 Dover
NSTAR | West Tisbury | ESMAEX-02077 | 02575 | 30.975 | Solar |  | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-05-05 | Online | [8 empty] | Cape
NSTAR | Carver | ESMAEX-01859 | 02330 | 15.2 | Solar | 3-10-10 | 2022-11-29 | 2023-01-11 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online
NSTAR | Holliston | ESMAEX-01868 | 01746 | 15.2 | Solar | 130-H1 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [12 empty] | STA_130 Holliston
NSTAR | Hopkinton | ESMAEX-01908 | 01748 | 16 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-30 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Burlington | ESMAEX-01870 | 01803 | 22.272 | Solar | 391-H6 | 2022-11-30 | 2023-02-06 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [11 empty] | 22.272 | STA_391 Burlington
NSTAR | Framingham | ESMAEX-01939 | 01701 | 16.104 | Solar | 455-H1 | 2022-12-21 | 2023-01-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-01876 | 01701 | 20 | Solar | 455-H4 | 2022-12-01 | 2022-12-29 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Sharon | ESMAEX-01922 | 02067 | 15.2 | Solar | 146-H7 | 2022-12-14 | 2023-01-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Online | [12 empty] | STA_146 Walpole
NSTAR | Walpole | ESMAEX-01947 | 02081 | 15.2 | Solar & Battery | 456-H1 | 2022-12-27 | 2023-01-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online | [12 empty] | STA_456 Dover
NSTAR | Canton | ESMAEX-01889 | 02021 | 17.28 | Solar | 470-H8 | 2022-12-04 | 2022-12-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online | [12 empty] | STA_470 Canton
NSTAR | Norfolk | ESMAEX-01898 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-12-07 | 2022-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [12 empty] | STA_146 Walpole
NSTAR | South Dartmouth | ESMAEX-02046 | 02748 | 10 | Battery | 2-528-528 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-22 | Online
NSTAR | Acton | ESMAEX-01948 | 01720 | 10 | Battery | 416-H5 | 2022-12-27 | 2023-01-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [12 empty] | STA_416 Maynard
NSTAR | Medfield | ESMAEX-01891 | 02052 | 17.6 | Solar | 146-H6 | 2022-12-06 | 2022-12-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [12 empty] | STA_146 Walpole
NSTAR | Duxbury | ESMAEX-01903 | 02332 | 10.5 | Solar & Battery | 3-26-26 | 2022-12-08 | 2022-12-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online
NSTAR | Westwood | ESMAEX-01895 | 02090 | 15.2 | Solar | 148-H3 | 2022-12-06 | 2023-01-23 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [12 empty] | STA_148 Needham
NSTAR | Acton | ESMAEX-01902 | 01720 | 16.5 | Solar | 416-H1 | 2022-12-07 | 2022-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [12 empty] | STA_416 Maynard
NSTAR | East Wareham | ESMAEX-02002 | 02538 | 7.6 | Solar | 3-82-82 | 2023-01-11 | 2024-07-31 | 405 |  | 405 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Online | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Wayland | ESMAEX-02352 | 01778 | 15 | Battery | 342-H1 | 2023-04-06 | 2023-05-09 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-05-17 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Mattapoisett | ESMAEX-01983 | 02739 | 19.5 | Solar | 2-301-305 | 2023-01-09 | 2023-02-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Carlisle | ESMAEX-01906 | 01741 | 17.6 | Solar & Battery | 533-H8 | 2022-12-08 | 2023-01-04 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Lexington | ESMAEX-02025 | 02421 | 15.2 | Solar & Battery | 320-H5XY | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Online | [12 empty] | STA_320 Lexington
NSTAR | Hyannis | ESMAEX-01912 | 02601 | 100 | Solar | 4-80B-514 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Lexington | ESMAEX-01916 | 02421 | 15.372 | Solar | 320-H5XY | 2022-12-12 | 2023-01-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [12 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-01914 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [12 empty] | STA_240 Framingham
NSTAR | Kingston | ESMAEX-01957 | 02364 | 10 | Battery | 3-50-914 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [8 empty] | Plymouth |  |  |  | STA_727 Brook Street
NSTAR | Woburn | ESMAEX-01993 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2023-01-10 | 2023-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Fairhaven | ESMAEX-01927 | 02719 | 10 | Solar & Battery | 2-222-222 | 2022-12-14 | 2023-01-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Wayland | ESMAEX-01921 | 01778 | 15 | Battery | 278-H2 | 2022-12-13 | 2023-01-11 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Duxbury | ESMAEX-01935 | 02332 | 15 | Solar & Battery | 3-23-23 | 2022-12-20 | 2023-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Newton Upper Falls | ESMAEX-01928 | 02464 | 19 | Solar | 292-H2 | 2022-12-14 | 2023-01-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Westwood | ESMAEX-01972 | 02090 | 200 | Solar | 456-H5 | 2023-01-05 | 2023-03-08 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online | [12 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-01971 | 02090 | 240 | Solar | 469-H4 | 2023-01-05 | 2023-02-09 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online
NSTAR | Plymouth | ESMAEX-01931 | 02360 | 3.8 | Solar | 3-12-12 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Online
NSTAR | Harwichport | ESMAEX-01990 | 02646 | 39.6 | Solar |  | 2023-01-10 | 2023-02-01 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-27 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Online | [8 empty] | Cape
NSTAR | Marshfield | ESMAEX-02182 | 02050 | 15.2 | Solar | 3-25-25 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online
NSTAR | Plymouth | ESMAEX-01936 | 02360 | 7.6 | Solar | 3-14-934 | 2022-12-20 | 2023-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-24 | Online | [8 empty] | Plymouth |  |  | 7.6 | STA_737 West Pond
NSTAR | Acton | ESMAEX-01956 | 01720 | 16.104 | Solar | 416-H8 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [12 empty] | STA_416 Maynard
NSTAR | West Newton | ESMAEX-01942 | 02465 | 25.62 | Solar | 1713 | 2022-12-22 | 2023-01-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Wareham | ESMAEX-01962 | 02571 | 7.6 | Solar & Battery | 3-84-84 | 2023-01-05 | 2023-01-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-30 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Dedham | ESMAEX-01940 | 02026 | 15.2 | Solar | 344-1412H1 | 2022-12-21 | 2023-01-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Newton Center | ESMAEX-01943 | 02459 | 15.9 | Solar | 292-H11 | 2022-12-22 | 2023-01-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-18 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-02060 | 02081 | 15.2 | Solar & Battery | 146-H6 | 2023-01-23 | 2023-02-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Online | [12 empty] | STA_146 Walpole
NSTAR | South Dartmouth | ESMAEX-02044 | 02748 | 6.59 | Solar & Battery | 2-2-505 | 2023-01-20 | 2023-02-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-25 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Needham | ESMAEX-01961 | 02492 | 39.75 | Solar & Battery | 148-H6 | 2023-01-04 | 2023-01-26 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Online | [12 empty] | STA_148 Needham
NSTAR | Medfield | ESMAEX-02005 | 02052 | 17.934 | Solar | 146-H2 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-11 | Online | [12 empty] | STA_146 Walpole
NSTAR | Westport | ESMAEX-01953 | 02790 | 7.6 | Solar & Battery | 2-523-523 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Sharon | ESMAEX-01965 | 02067 | 19.845 | Solar | LINE48C | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online
NSTAR | Acton | ESMAEX-02092 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-31 | 2023-02-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [12 empty] | STA_416 Maynard
NSTAR | Needham | ESMAEX-01977 | 02492 | 16.836 | Solar | 148-H4 | 2023-01-06 | 2023-01-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [12 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-01978 | 02747 | 250 | Solar | 2-70-502 | 2023-01-06 | 2023-02-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online
NSTAR | Hopkinton | ESMAEX-02001 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Walpole | ESMAEX-02019 | 02081 | 15.3 | Solar | 146-H8 | 2023-01-13 | 2023-01-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [12 empty] | STA_146 Walpole
NSTAR | Bedford | ESMAEX-02061 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2023-01-23 | 2023-02-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-01963 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-05 | 2023-02-07 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Holliston | ESMAEX-01967 | 01746 | 15.2 | Solar | 274-H1 | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Milton | ESMAEX-02890 | 02186 | 19.8 | Solar | 470-H9 | 2023-09-21 | 2023-09-20 | -3 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [12 empty] | STA_470 Canton
NSTAR | Waltham | ESMAEX-03217 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-03216 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Roslindale | ESMAEX-01975 | 02131 | 7.6 | Solar & Battery | 496-H6 | 2023-01-06 | 2023-02-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Stoneham | ESMAEX-01992 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2023-01-10 | 2023-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Wayland | ESMAEX-02023 | 01778 | 15.2 | Solar | 342-H1 | 2023-01-13 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-18 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-01998 | 02360 | 11.4 | Solar & Battery | 3-89-922 | 2023-01-11 | 2023-02-06 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Ashland | ESMAEX-02081 | 01721 | 87 | Solar | 455-H3 | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-26 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-02004 | 02420 | 15.2 | Solar & Battery | 391-H11 | 2023-01-11 |  | -32065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [12 empty] | STA_391 Burlington
NSTAR | Hatchville | ESMAEX-02000 | 02536 | 17.6 | Solar | 4-78-78 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-09-06 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Needham | ESMAEX-02007 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2023-01-12 | 2023-02-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [12 empty] | STA_148 Needham
NSTAR | Newton Center | ESMAEX-02047 | 02459 | 15.2 | Solar & Battery | 1708 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | North Truro | ESMAEX-02021 | 02652 | 15 | Battery | 4-96-96 | 2023-01-13 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Hopkinton | ESMAEX-02110 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-02-03 | 2023-02-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | East Brewster | ESMAEX-02011 | 02631 | 18 | Solar | 4-89B-577 | 2023-01-12 | 2023-02-28 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Online | [12 empty] | STA_975 Orleans
NSTAR | East Wareham | ESMAEX-02014 | 02538 | 360 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  | 360 | STA_714 Wareham
NSTAR | Canton | ESMAEX-02029 | 02021 | 18.585 | Solar | 269-1320H1 | 2023-01-16 | 2023-02-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [12 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-02035 | 02052 | 15.2 | Solar & Battery | 146-H2 | 2023-01-17 | 2023-02-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online | [12 empty] | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02026 | 02056 | 17.6 | Solar | 146-H3 | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-09-26 | Online | [12 empty] | STA_146 Walpole
NSTAR | Natick | ESMAEX-02027 | 01760 | 16.4 | Solar | 240-H5 | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Online | [12 empty] | STA_240 Framingham
NSTAR | Acusnet | ESMAEX-02031 | 02743 | 4999 | Solar & Battery | 2-241-241 | 2023-01-17 | 2023-02-21 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven | 2024 SEMA/Cape ASO Study | Phase 2 - Executed ISA | 4999 | STA_624 Wing Lane
NSTAR | Medway | ESMAEX-02114 | 02053 | 10 | Battery | 65-H3 | 2023-02-04 | 2023-02-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [12 empty] | STA_065 Medway
NSTAR | Sharon | ESMAEX-02057 | 02067 | 20.2 | Solar & Battery | 470-H3 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-17 | Online | [12 empty] | STA_470 Canton
NSTAR | Needham | ESMAEX-02068 | 02492 | 8.027 | Solar | 148-H1 | 2023-01-25 | 2023-02-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-30 | Online | [12 empty] | STA_148 Needham
NSTAR | West Roxbury | ESMAEX-02076 | 02132 | 100 | Solar | 496-H3 | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Arlington | ESMAEX-02049 | 02474 | 16.5 | Solar | 211-H11 | 2023-01-22 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [12 empty] | STA_211 Woburn
NSTAR | Freetown | ESMAEX-02038 | 02717 | 4980 | Solar & Battery | 2-102-608 | 2023-05-16 | 2023-06-27 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | New Bedford | 2024 SEMA/Cape ASO Study | Hold In Queue |  | STA_636 Industrial Park
NSTAR | Walpole | ESMAEX-02041 | 02081 | 15.2 | Solar & Battery | 2601 | 2023-01-19 | 2023-02-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Online | [12 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02100 | 01801 | 35.1 | Solar | 211-H5 | 2023-02-01 | 2023-02-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [12 empty] | STA_211 Woburn
NSTAR | West Newton | ESMAEX-02048 | 02465 | 15.36 | Solar | 1703 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Natick | ESMAEX-02053 | 01760 | 19.84 | Solar | 433-H7 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-02054 | 01778 | 15.2 | Solar | 278-H2 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Allston | ESMAEX-02105 | 02134 | 66.6 | Solar | 315-H3 | 2023-02-02 | 2023-03-21 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-13 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | North Dartmouth | ESMAEX-02064 | 02747 | 10 | Battery | 2-541-541 | 2023-01-24 | 2023-02-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | New Bedford | ESMAEX-02066 | 02744 | 200 | Solar | 2-24-24 | 2023-03-15 | 2023-04-13 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_611 Pine Street
NSTAR | Acton | ESMAEX-02070 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-25 | 2023-02-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | East Freetown | ESMAEX-02075 | 02717 | 17.6 | Solar | 2-108-108 | 2023-01-26 | 2023-02-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Online | [8 empty] | Cape |  |  | 17.6 | STA_636 Industrial Park
NSTAR | North Dartmouth | ESMAEX-02083 | 02747 | 312.5 | Solar | 2-543-543 | 2023-07-28 | 2023-08-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Online | [8 empty] | Dartmouth-Westport |  |  | 25 | STA_651 Cross Road
NSTAR | Jamaica Plain | ESMAEX-02135 | 02130 | 10 | Battery | 284-1300H1 | 2023-02-07 | 2023-03-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Canton | ESMAEX-03358 | 02021 | 100 | Solar | 470-H7 | 2024-01-12 | 2024-01-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Milton | ESMAEX-02091 | 02186 | 16 | Solar | 470-H9 | 2023-01-30 | 2023-02-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [11 empty] | 16 | STA_470 Canton
NSTAR | Sharon | ESMAEX-02117 | 02067 | 100 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_470 Canton
NSTAR | Boston | ESMAEX-02098 | 02115 | 15.2 | Solar & Battery | 5202 | 2023-02-01 | 2023-02-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Wayland | ESMAEX-02245 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Bedford | ESMAEX-02097 | 01730 | 19.96 | Solar | 533-H7 | 2023-02-01 | 2023-02-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Sharon | ESMAEX-02126 | 02067 | 60 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-02108 | 02052 | 15.2 | Solar & Battery | 456-H2 | 2023-02-02 | 2023-02-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Online | [12 empty] | STA_456 Dover
NSTAR | New Bedford | ESMAEX-02331 | 02744 | 10 | Solar & Battery | 2-25-25 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Online
NSTAR | Cambridge | ESMAEX-02373 | 02139 | 20.06 | Solar | 814-12 | 2023-04-13 | 2023-04-24 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Online | [12 empty] | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-02188 | 02138 | 9.6 | Battery | 823-21 | 2023-02-22 | 2023-03-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [12 empty] | STA_828 Alewife
NSTAR | East Wareham | ESMAEX-02199 | 02538 | 120 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  | 120 | STA_714 Wareham
NSTAR | Walpole | ESMAEX-02431 | 02081 | 100 | Solar | 146-H8 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [12 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02432 | 01801 | 75 | Solar | 375-H6 | 2023-04-29 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-31 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Walpole | ESMAEX-02129 | 02081 | 19.52 | Solar | 146-H4 | 2023-02-07 | 2023-03-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [12 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-02157 | 02420 | 19 | Solar | 320-H7 | 2023-02-14 | 2023-02-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Online | [12 empty] | STA_320 Lexington
NSTAR | Needham | ESMAEX-02177 | 02492 | 15.2 | Solar | 148-01 | 2023-02-17 | 2023-03-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-05 | Online | [12 empty] | STA_148 Needham
NSTAR | Onset | ESMAEX-02152 | 02558 | 1.28 | Battery | 3-88-17J1 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online
NSTAR | Wayland | ESMAEX-02136 | 01778 | 16.2 | Solar | 278-H2 | 2023-02-07 | 2023-02-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Sagamore Beach | ESMAEX-02140 | 02562 | 15.2 | Solar & Battery | 3-89-925 | 2023-02-08 | 2023-02-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Watertown | ESMAEX-02150 | 02472 | 120 | Solar | 470-H10 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Online | [12 empty] | STA_470 Canton
NSTAR | Winchester | ESMAEX-02166 | 01890 | 220 | Solar | 211-H13 | 2023-02-15 | 2023-03-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-22 | Online | [12 empty] | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-02353 | 02139 | 19.18 | Solar | 817-03 | 2023-04-06 | 2023-04-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Online | [12 empty] | STA_831 Putnam
NSTAR | Sharon | ESMAEX-02167 | 02067 | 15.2 | Solar | 146-H1 | 2023-02-16 | 2023-03-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-15 | Online | [12 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-02153 | 02494 | 7.6 | Solar | 148-H1 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online | [12 empty] | STA_148 Needham
NSTAR | Dover | ESMAEX-02209 | 02030 | 25.2 | Solar | 456-H5 | 2023-02-27 | 2023-03-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [12 empty] | STA_456 Dover
NSTAR | West Newton | ESMAEX-02154 | 02465 | 15.2 | Solar & Battery | 282-H9 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_282 Waltham
NSTAR | Hopkinton | ESMAEX-02183 | 01748 | 15.2 | Solar | 455-H8 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Woburn | ESMAEX-02186 | 01801 | 150 | Solar | 211-H2 | 2023-02-22 | 2023-04-04 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-06 | Online | [12 empty] | STA_211 Woburn
NSTAR | North Truro | ESMAEX-02223 | 02652 | 10.25 | Solar & Battery | 4-96-96 | 2023-03-02 | 2023-03-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-29 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Westport | ESMAEX-02358 | 02790 | 1350 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Online | [11 empty] | 1350
NSTAR | Millis | ESMAEX-02169 | 01742 | 499 | Battery | 146-H10 | 2023-02-16 | 2023-04-20 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 499 | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02208 | 02056 | 200 | Solar | 65-H1 | 2023-02-27 | 2023-03-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_065 Medway
NSTAR | Framingham | ESMAEX-02172 | 01702 | 15.2 | Solar & Battery | 240-H4 | 2023-02-17 | 2023-03-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [12 empty] | STA_240 Framingham
NSTAR | Acton | ESMAEX-02180 | 01720 | 199.9 | Solar | 416-H8 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_416 Maynard
NSTAR | Acton | ESMAEX-02173 | 01720 | 960 | Solar | 416-H9 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_416 Maynard
NSTAR | Needham | ESMAEX-02181 | 02494 | 17.5698 | Solar | 148-H7 | 2023-02-21 | 2023-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Online | [12 empty] | STA_148 Needham
NSTAR | Westwood | ESMAEX-02213 | 02090 | 18.3 | Solar | 456-H1 | 2023-02-28 | 2023-03-21 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online | [12 empty] | STA_456 Dover
NSTAR | Acton | ESMAEX-02187 | 01720 | 160 | Solar & Battery | 416-H5 | 2023-02-22 | 2023-03-30 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-01-19 | ISA Agreement | [12 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-02229 | 02421 | 10 | Battery | 320-H5XY | 2023-03-03 | 2023-03-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-09 | Online | [12 empty] | STA_320 Lexington
NSTAR | Woburn | ESMAEX-02195 | 01801 | 166.6 | Solar & Battery | 211-H2 | 2023-02-23 | 2023-03-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [12 empty] | STA_211 Woburn
NSTAR | Holliston | ESMAEX-02203 | 01746 | 120 | Solar | 65-H2 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2024-07-23 | Online | [12 empty] | STA_065 Medway
NSTAR | Bellingham | ESMAEX-02191 | 02019 | 6 | Solar | 65-H4 | 2023-02-22 | 2023-03-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Online | [11 empty] | 6 | STA_065 Medway
NSTAR | Brewster | ESMAEX-02197 | 02631 | 16 | Solar & Battery | 4-89B-89B | 2023-02-23 | 2023-03-21 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-03 | Online | [11 empty] | 6 | STA_975 Orleans
NSTAR | Sharon | ESMAEX-02207 | 02067 | 19 | Solar | 470-H3 | 2023-02-27 | 2023-03-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [12 empty] | STA_470 Canton
NSTAR | Brewster | ESMAEX-02212 | 02631 | 15.2 | Solar | 4-89B-576 | 2023-02-28 | 2023-03-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Online | [12 empty] | STA_975 Orleans
NSTAR | Needham | ESMAEX-02248 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2023-03-08 | 2023-03-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Medfield | ESMAEX-02218 | 02052 | 100 | Solar | 456-H2 | 2023-03-23 | 2023-04-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [12 empty] | STA_456 Dover
NSTAR | Medfield | ESMAEX-02219 | 02052 | 480 | Solar | 456-H2 | 2023-03-24 | 2023-04-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | Medfield | ESMAEX-02220 | 02052 | 250 | Solar | 146-H2 | 2023-03-24 | 2023-04-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02255 | 01801 | 117.3 | Solar | 375-H14 | 2023-03-09 | 2023-04-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | New Bedford | ESMAEX-02224 | 02746 | 996 | Solar & Battery | 2-83-403 | 2023-08-08 | 2023-09-20 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 999 | STA_612 Acushnet
NSTAR | North Dartmouth | ESMAEX-02225 | 02747 | 999 | Solar & Battery | 2-543-543 | 2023-08-08 | 2023-09-26 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Dartmouth-Westport |  |  | 999 | STA_651 Cross Road
NSTAR | Rochester | ESMAEX-03301 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth | 2024 SEMA/Cape ASO Study | Phase 2 - In Process |  | STA_713 Tremont
NSTAR | Plymouth | ESMAEX-02240 | 02360 | 16.9 | Solar | 3-71-38J1 | 2023-03-08 | 2023-04-11 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Medway | ESMAEX-02234 | 02053 | 16.4 | Solar & Battery | 65-H2 | 2023-03-05 | 2023-03-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [12 empty] | STA_065 Medway
NSTAR | Natick | ESMAEX-02242 | 01760 | 16.47 | Solar | 240-H1 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_240 Framingham
NSTAR | Rochester | ESMAEX-02237 | 02770 | 4980 | Solar & Battery | 3-702-702 | 2023-06-02 | 2023-06-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven | 2024 SEMA/Cape ASO Study | Phase 2 - Executed ISA | 0 | STA_745 Rochester
NSTAR | South Orleans | ESMAEX-02239 | 02662 | 17.4 | Solar | 4-628-628 | 2023-03-07 | 2023-04-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [12 empty] | STA_975 Orleans
NSTAR | Edgartown | ESMAEX-02243 | 02539 | 15 | Solar | 4-75-75 | 2023-03-08 | 2024-08-15 | 376 |  | 376 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-02247 | 01701 | 15.3 | Solar | 342-H4 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Winchester | ESMAEX-02249 | 01890 | 8.4 | Solar | 211-H3 | 2023-03-08 | 2023-03-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-03 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-02271 | 02139 | 7.6 | Solar | 817-01 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-12 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Online | [12 empty] | STA_831 Putnam
NSTAR | Stoneham | ESMAEX-02257 | 02180 | 9.6 | Battery | 375-H2 | 2023-03-10 | 2023-04-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Marstons Mills | ESMAEX-02419 | 02648 | 4.8 | Solar | 4-87A-87A | 2023-04-26 | 2023-05-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | Plymouth | ESMAEX-02305 | 02360 | 16.5 | Solar | 3-14-931 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Boston | ESMAEX-02263 | 02127 | 34.6 | Solar | 385-H1 | 2023-03-14 | 2023-04-20 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Online | [12 empty] | STA_385D K Street
NSTAR | Acton | ESMAEX-02268 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-03-14 | 2023-04-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-07 | Online | [12 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-02270 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Barnstable | ESMAEX-02273 | 02630 | 8 | Battery | 4-84B-510 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-02 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Plympton | ESMAEX-02277 | 02367 | 5559.66 | Solar & Battery | 3-51-51 | 2023-03-17 | 2023-04-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth | 2024 SEMA/Cape ASO Study | Phase 2 - In Process | 4999 | STA_727 Brook Street
NSTAR | Framingham | ESMAEX-02275 | 01701 | 15.2 | Solar | 455-H1 | 2023-03-16 | 2023-04-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online | [11 empty] | 15.2 | STA_455 West Framingham
NSTAR | Arlington | ESMAEX-02286 | 02474 | 100 | Solar | 59-1393H1 | 2023-03-20 | 2023-04-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [12 empty] | STA_211 Woburn
NSTAR | Westwood | ESMAEX-02297 | 02090 | 16.47 | Solar | 469-H2 | 2023-03-22 | 2023-04-03 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online
NSTAR | Jamaica Plain | ESMAEX-02338 | 02130 | 19.47 | Solar | 350-H2 | 2023-04-03 | 2023-04-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Canton | ESMAEX-02281 | 02021 | 19 | Solar | 470-H9 | 2023-03-17 | 2023-04-25 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_470 Canton
NSTAR | Sharon | ESMAEX-02282 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2023-03-17 | 2023-04-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-30 | Online | [12 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-02291 | 01748 | 15.2 | Solar | 455-H8 | 2023-03-21 | 2023-04-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Brookline | ESMAEX-02292 | 02445 | 20 | Solar | 20N28 | 2023-03-21 | 2023-05-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Online | [12 empty] | STA_329 Brighton
NSTAR | Canton | ESMAEX-02293 | 02021 | 19 | Solar | 470-H6 | 2023-03-21 | 2023-04-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [12 empty] | STA_470 Canton
NSTAR | South Dartmouth | ESMAEX-02398 | 02748 | 34.6 | Solar | 2-60-63 | 2023-04-20 | 2023-05-08 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Technical Review | [12 empty] | STA_611 Pine Street
NSTAR | Canton | ESMAEX-02308 | 02021 | 100 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Online | [12 empty] | STA_470 Canton
NSTAR | Canton | ESMAEX-02310 | 02021 | 70 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online | [12 empty] | STA_470 Canton
NSTAR | East Freetown | ESMAEX-02299 | 02717 | 20 | Solar & Battery | 2-108-108 | 2023-03-22 | 2023-04-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Lincoln | ESMAEX-02319 | 01773 | 10 | Battery | 320-H6 | 2023-03-29 | 2023-04-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [12 empty] | STA_320 Lexington
NSTAR | Wayland | ESMAEX-02332 | 01778 | 18.3 | Solar | 342-H3 | 2023-04-01 | 2023-04-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Roxbury | ESMAEX-02371 | 02119 | 67.3 | Solar | 52-1487H1 | 2023-04-12 | 2023-05-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Westport | ESMAEX-02359 | 02790 | 1200 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Online | [11 empty] | 1200
NSTAR | Kingston | ESMAEX-02313 | 02364 | 180 | Solar | 3-14-14 | 2023-04-11 | 2023-05-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Holliston | ESMAEX-02318 | 01746 | 7.4 | Battery | 65-H5 | 2023-03-28 | 2023-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online | [11 empty] | 7.4 | STA_065 Medway
NSTAR | Dorchester | ESMAEX-02420 | 02125 | 480 | Solar | 511-1495H1 | 2023-04-26 | 2023-05-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Weston | ESMAEX-02328 | 02493 | 100 | Solar | 450-H7 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Truro | ESMAEX-02713 | 02652 | 50 | Solar | 4-96-96 | 2023-07-26 | 2023-08-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Woods Hole | ESMAEX-02335 | 02543 | 40 | Solar | 4-91-91 | 2023-04-03 | 2023-04-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Holliston | ESMAEX-02333 | 01746 | 20 | Solar & Battery | 130-H1 | 2023-04-03 | 2023-04-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_130 Holliston
NSTAR | Westwood | ESMAEX-02337 | 02090 | 360 | Solar | 148-H3 | 2023-06-27 | 2023-08-22 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [12 empty] | STA_148 Needham
NSTAR | Lincoln | ESMAEX-02346 | 01773 | 20 | Solar | 320-H8 | 2023-04-05 | 2023-04-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online | [11 empty] | 20 | STA_320 Lexington
NSTAR | Marion | ESMAEX-02355 | 02738 | 15.2 | Solar & Battery | 3-702-702 | 2023-04-06 | 2023-04-27 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-01 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Lincoln | ESMAEX-02341 | 01773 | 11.52 | Solar | 342-H1 | 2023-04-04 | 2023-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Rochester | ESMAEX-02342 | 02770 | 14.5 | Solar | 3-702-702 | 2023-04-04 | 2023-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Sharon | ESMAEX-02345 | 02067 | 18.5 | Solar | LINE48C | 2023-04-05 | 2023-04-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online
NSTAR | Canton | ESMAEX-02349 | 02021 | 15.3 | Solar | 269-1320H1 | 2023-04-05 | 2023-04-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [12 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-02347 | 01754 | 7.6 | Solar | 416-H6 | 2023-04-05 | 2023-04-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [12 empty] | STA_416 Maynard
NSTAR | Ashland | ESMAEX-02538 | 01721 | 22.8 | Solar & Battery | 274-H5 | 2023-05-30 | 2023-06-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02356 | 01748 | 19.9 | Solar & Battery | 126-H4 | 2023-04-06 | 2023-04-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [11 empty] | 19.9 | STA_126 Hopkinton
NSTAR | Needham | ESMAEX-02366 | 02492 | 15.2 | Solar & Battery | 148-07 | 2023-04-10 | 2023-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [12 empty] | STA_148 Needham
NSTAR | Hopkinton | ESMAEX-02363 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-04-10 | 2023-04-25 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-02364 | 01720 | 16.8 | Solar | 416-H5 | 2023-04-10 | 2023-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Online | [12 empty] | STA_416 Maynard
NSTAR | Rochester | ESMAEX-02368 | 02770 | 4999 | Solar & Battery | 3-703-703 | 2023-04-11 | 2023-09-20 | 116 |  | 116 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven | 2024 SEMA/Cape ASO Study | Phase 2 - Executed ISA | 4999 | STA_745 Rochester
NSTAR | Auburndale | ESMAEX-02380 | 02466 | 67.3 | Solar | 292-H7 | 2023-04-14 | 2023-05-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | West Roxbury | ESMAEX-02372 | 02132 | 15.3 | Solar | 468-06 | 2023-04-13 | 2023-05-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [12 empty] | STA_110 Baker Street
NSTAR | West Newton | ESMAEX-02376 | 02465 | 15.2 | Solar & Battery | 33-H3 | 2023-04-13 | 2023-05-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [12 empty] | STA_282 Waltham
NSTAR | Dover | ESMAEX-02379 | 02030 | 17.6 | Solar | 148-H3 | 2023-04-14 | 2023-05-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-20 | Online | [11 empty] | 17.6 | STA_148 Needham
NSTAR | Lincoln | ESMAEX-02476 | 01773 | 15.2 | Solar & Battery | 320-H6 | 2023-05-15 | 2023-05-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [12 empty] | STA_320 Lexington
NSTAR | Duxbury | ESMAEX-02401 | 02332 | 13.2 | Solar & Battery | 3-26-26 | 2023-04-21 | 2023-05-25 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-22 | Online
NSTAR | Plymouth | ESMAEX-02387 | 02360 | 16 | Solar | 3-10-10 | 2023-04-18 | 2023-05-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Online | [11 empty] | 16
NSTAR | Boston | ESMAEX-02427 | 02119 | 50 | Solar | 52-1487H1 | 2023-04-28 | 2023-05-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-07 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Wellfleet | ESMAEX-02389 | 02667 | 6.4 | Battery | 4-94B-94B | 2023-04-19 | 2023-05-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-18 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Wayland | ESMAEX-02392 | 01778 | 100 | Solar | 433-H2 | 2023-05-26 | 2023-06-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Cambridge | ESMAEX-02574 | 02139 | 28.8 | Solar | 819-1NE4 | 2023-06-12 | 2023-07-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [12 empty] | STA_402 Newton Street
NSTAR | Natick | ESMAEX-02403 | 01760 | 15 | Battery | 433-H5 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2023-09-22 | Online | [11 empty] | 20 | STA_433 Speen Street
NSTAR | Waltham | ESMAEX-02400 | 02452 | 16 | Solar | 450-H4 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Online | [11 empty] | 16 | STA_450 Trapelo Road
NSTAR | Waltham | ESMAEX-02402 | 02451 | 15.2 | Solar | 450-H1 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Kingston | ESMAEX-02406 | 02364 | 15.2 | Solar | 3-909-909 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [8 empty] | Plymouth |  |  |  | STA_735 Kingston
NSTAR | Norfolk | ESMAEX-02429 | 02056 | 15 | Battery | 65-H1 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online | [12 empty] | STA_065 Medway
NSTAR | Somerville | ESMAEX-02814 | 02143 | 25.37 | Solar | 13N14 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-05 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_250 Mystic
NSTAR | Sharon | ESMAEX-02413 | 02067 | 250 | Solar | 470-H12 | 2023-05-17 | 2023-06-27 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Waban | ESMAEX-02444 | 02468 | 25.2 | Solar & Battery | 292-H2 | 2023-05-04 | 2023-05-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Medway | ESMAEX-02416 | 02053 | 15.2 | Solar | 65-H3 | 2023-04-26 | 2023-05-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Online | [12 empty] | STA_065 Medway
NSTAR | Framingham | ESMAEX-02417 | 01701 | 17.4 | Solar | 342-H2 | 2023-04-26 | 2023-05-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Chatham | ESMAEX-02424 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2023-04-27 | 2023-05-16 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [12 empty] | STA_975 Orleans
NSTAR | Arlington | ESMAEX-02426 | 02476 | 67.3 | Solar | 211-H3 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [12 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-02460 | 02445 | 12.54 | Solar & Battery | 350-H8 | 2023-05-08 | 2023-05-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Sharon | ESMAEX-02433 | 02067 | 480 | Solar | 146-H1 | 2023-08-04 | 2023-08-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-02439 | 02421 | 15.2 | Solar | 320-H2 | 2023-05-02 | 2023-05-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-07-31 | Online | [12 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-02478 | 01760 | 4.4 | Solar & Battery | 23-H1 | 2023-05-15 | 2023-06-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [12 empty] | STA_240 Framingham
NSTAR | Holliston | ESMAEX-02449 | 01746 | 19.98 | Solar | 65-H5 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [12 empty] | STA_065 Medway
NSTAR | Wareham | ESMAEX-02441 | 02738 | 2000 | Solar & Battery | 3-85-85 | 2023-08-08 | 2023-09-26 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth | 2024 SEMA/Cape ASO Study | Phase 2 - In Process | 2000 | STA_713 Tremont
NSTAR | Ashland | ESMAEX-02440 | 01721 | 15.2 | Solar & Battery | 455-H3 | 2023-05-03 | 2023-05-18 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Newton Highlands | ESMAEX-02447 | 02461 | 17.9 | Solar | 292-H16 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-29 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online
NSTAR | Norfolk | ESMAEX-02445 | 02056 | 15.2 | Solar | 65-H1 | 2023-05-04 | 2023-05-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [11 empty] | 15.2 | STA_065 Medway
NSTAR | Westport | ESMAEX-02446 | 02790 | 199 | Solar & Battery | 2-523-523 | 2023-05-04 | 2023-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Lexington | ESMAEX-02454 | 02421 | 15.2 | Solar | 533-H1 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-02455 | 01748 | 15.2 | Solar | 455-H8 | 2023-05-06 | 2023-05-30 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Medfield | ESMAEX-02453 | 02052 | 19.584 | Solar | 456-H3 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_456 Dover
NSTAR | Norfolk | ESMAEX-02461 | 02056 | 15.2 | Solar & Battery | 146-H9 | 2023-05-08 | 2023-06-06 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Online | [12 empty] | STA_146 Walpole
NSTAR | Framingham | ESMAEX-02481 | 01701 | 6.39 | Battery | 433-H4 | 2023-05-16 | 2023-05-31 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [11 empty] | 6.39 | STA_433 Speen Street
NSTAR | Sherborn | ESMAEX-02464 | 01770 | 210 | Solar | 240-H1 | 2023-05-09 | 2023-05-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_240 Framingham
NSTAR | Sherborn | ESMAEX-02465 | 01770 | 15.2 | Solar | 274-H2 | 2023-05-09 | 2023-05-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [11 empty] | 15.2 | STA_274 Sherborn
NSTAR | Sherborn | ESMAEX-02468 | 01770 | 10 | Solar | 274-H2 | 2023-05-09 | 2023-06-06 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02469 | 01748 | 15.2 | Solar | 126-H1 | 2023-05-10 | 2023-05-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Framingham | ESMAEX-02474 | 01701 | 14.1 | Solar | 342-H4 | 2023-05-11 | 2023-05-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [12 empty] | STA_342 Sudbury
NSTAR | South Truro | ESMAEX-02472 | 02666 | 17.82 | Solar | 4-96-669 | 2023-05-11 | 2023-06-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Marshfield | ESMAEX-02518 | 02050 | 20 | Solar & Battery | 3-25-42J2 | 2023-05-25 | 2023-06-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Carver | ESMAEX-02477 | 02330 | 14.976 | Solar | 3-51-980 | 2023-05-15 | 2023-06-02 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-08 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [8 empty] | Plymouth |  |  |  | STA_727 Brook Street
NSTAR | Milton | ESMAEX-02654 | 02186 | 48 | Solar | 362-1209H2 | 2023-07-10 | 2023-08-14 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Duxbury | ESMAEX-02487 | 02332 | 15.2 | Solar | 3-26-26 | 2023-05-17 | 2023-05-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online
NSTAR | Framingham | ESMAEX-02491 | 01701 | 17.1 | Solar | 342-H4 | 2023-05-18 | 2023-07-26 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [12 empty] | STA_342 Sudbury
NSTAR | North Eastham | ESMAEX-02498 | 02651 | 82.01 | Solar | 4-94A-94A | 2023-05-19 | 2023-06-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-22 | Online | [12 empty] | STA_975 Orleans
NSTAR | Rochester | ESMAEX-02567 | 02770 | 15.3 | Solar | 3-703-703 | 2023-06-07 | 2023-07-11 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-12 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Medway | ESMAEX-02505 | 02053 | 17.6 | Solar | 65-H1 | 2023-05-22 | 2023-06-06 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [11 empty] | 17.6 | STA_065 Medway
NSTAR | Bedford | ESMAEX-02555 | 01730 | 15.2 | Solar | 533-H8 | 2023-06-05 | 2023-06-30 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Acton | ESMAEX-02510 | 01720 | 17.1 | Solar | 416-H8 | 2023-05-23 | 2023-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-24 | Online | [12 empty] | STA_416 Maynard
NSTAR | Holliston | ESMAEX-02509 | 01746 | 15.36 | Solar | 274-H3 | 2023-05-23 | 2023-07-05 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02533 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2023-05-26 | 2023-06-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2025-02-14 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Carver | ESMAEX-02592 | 02330 | 50 | Solar | 3-10-10 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Allston | ESMAEX-02602 | 02134 | 100 | Solar | 329-H5 | 2023-06-22 | 2023-07-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [12 empty] | STA_329 Brighton
NSTAR | Medway | ESMAEX-02513 | 02053 | 18 | Solar | 65-H1 | 2023-05-24 | 2023-06-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-21 | Online | [11 empty] | 18 | STA_065 Medway
NSTAR | Acton | ESMAEX-02516 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2023-05-24 | 2023-06-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [12 empty] | STA_416 Maynard
NSTAR | Canton | ESMAEX-02587 | 02021 | 25.5 | Solar | 470-H9 | 2023-06-15 | 2023-07-11 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Online | [12 empty] | STA_470 Canton
NSTAR | Milton | ESMAEX-02558 | 02186 | 22.4 | Solar | 496-H7 | 2023-06-06 | 2023-06-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | North Dartmouth | ESMAEX-02519 | 02747 | 200 | Solar | 2-543-543 | 2023-05-25 | 2023-06-19 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Canton | ESMAEX-02521 | 02021 | 15.2 | Solar | 470-H1 | 2023-05-25 | 2023-06-19 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [11 empty] | 15.2 | STA_470 Canton
NSTAR | Dedham | ESMAEX-02526 | 02026 | 250 | Solar |  | 2023-07-06 | 2023-07-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | East Orleans | ESMAEX-02525 | 02643 | 6 | Solar | 4-628-628 | 2023-05-26 | 2023-06-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Online | [11 empty] | 6 | STA_975 Orleans
NSTAR | Dedham | ESMAEX-02527 | 02026 | 120 | Solar | 456-H4 | 2023-07-10 | 2023-07-25 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-02612 | 02360 | 50 | Solar | 3-12-932 | 2023-06-23 | 2023-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-09 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Hopkinton | ESMAEX-02530 | 01748 | 22.8 | Solar & Battery | 126-H4 | 2023-05-26 | 2023-06-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-06-19 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-02565 | 01801 | 150 | Solar | 211-H2 | 2023-06-07 | 2023-07-13 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [12 empty] | STA_211 Woburn
NSTAR | Woburn | ESMAEX-02537 | 01801 | 10 | Battery | 211-H6 | 2023-05-30 | 2023-06-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Online | [11 empty] | 0 | STA_211 Woburn
NSTAR | Truro | ESMAEX-02539 | 02666 | 17.16 | Solar & Battery | 4-96-96 | 2023-05-30 | 2023-06-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-02563 | 01801 | 240 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [12 empty] | STA_211 Woburn
NSTAR | Woburn | ESMAEX-02564 | 01801 | 200 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_211 Woburn
NSTAR | Medway | ESMAEX-02561 | 02053 | 200 | Solar | 65-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-15 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Online | [12 empty] | STA_065 Medway
NSTAR | Canton | ESMAEX-02545 | 02021 | 16 | Solar | 470-H9 | 2023-06-01 | 2023-06-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online | [12 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-02544 | 02421 | 100 | Solar | 320-H5XY | 2023-07-07 | 2023-07-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-30 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Online | [12 empty] | STA_320 Lexington
NSTAR | Dedham | ESMAEX-02550 | 02026 | 200 | Solar | 20-H5 | 2023-06-02 | 2023-06-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | South Dartmouth | ESMAEX-02553 | 02748 | 20.1 | Solar | 2-528-528 | 2023-06-02 | 2023-07-11 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-19 | Online
NSTAR | Carlisle | ESMAEX-02569 | 01741 | 15.36 | Solar | 533-H8 | 2023-06-08 | 2023-07-21 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Dennisport | ESMAEX-02976 | 02639 | 18 | Solar | 4-92B-583 | 2023-09-28 | 2023-12-27 | 64 |  | 64 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Cambridge | ESMAEX-02674 | 02138 | 200 | Solar | 831-1332 | 2023-07-13 | 2023-08-04 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_831 Putnam
NSTAR | Stoneham | ESMAEX-02566 | 02180 | 20 | Solar | 375-H8 | 2023-06-07 | 2023-06-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Brighton | ESMAEX-02717 | 02135 | 200 | Solar | 467-H9 | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Online | [12 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-02581 | 01760 | 7.6 | Solar & Battery | 240-H3 | 2023-06-14 | 2023-07-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online | [12 empty] | STA_240 Framingham
NSTAR | Dover | ESMAEX-02577 | 02030 | 7.6 | Solar & Battery | 456-H5 | 2023-06-12 | 2023-07-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [12 empty] | STA_456 Dover
NSTAR | Burlington | ESMAEX-02572 | 01803 | 25.728 | Solar | 375-H6 | 2023-06-09 | 2023-07-11 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Rochester | ESMAEX-02576 | 02770 | 20 | Solar | 3-703-703 | 2023-06-12 | 2023-07-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Newton | ESMAEX-02600 | 02458 | 16 | Solar | 277-05 | 2023-06-21 | 2023-07-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-06 | Online | [12 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-02579 | 01760 | 14 | Battery | 433-H5 | 2023-06-13 | 2023-07-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Marshfield | ESMAEX-02608 | 02050 | 10 | Battery | 3-25-25 | 2023-06-23 | 2023-07-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online
NSTAR | Chestnut Hill | ESMAEX-02642 | 02467 | 100 | Solar | 292-H5 | 2023-07-06 | 2023-07-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-02646 | 02467 | 62.5 | Solar | 292-H5 | 2023-07-07 | 2023-07-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-02586 | 02467 | 19 | Solar | 350-H7 | 2023-06-14 | 2023-07-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Needham | ESMAEX-02589 | 02494 | 15.2 | Solar | 148-H1 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [12 empty] | STA_148 Needham
NSTAR | Westwood | ESMAEX-02676 | 02090 | 15.36 | Solar | 148-H3 | 2023-07-15 | 2023-08-22 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [12 empty] | STA_148 Needham
NSTAR | Hopkinton | ESMAEX-02590 | 01748 | 19.968 | Solar | 126-H4 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Duxbury | ESMAEX-02595 | 02332 | 16.64 | Solar | 3-27-970 | 2023-06-20 | 2023-09-20 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_738 Duxbury
NSTAR | Marshfield | ESMAEX-02616 | 02050 | 19 | Solar | 3-24B-915 | 2023-06-26 | 2023-07-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-02596 | 02420 | 25 | Solar | 533-H9 | 2023-06-20 | 2023-07-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-01 | [7 empty] | 0 |  | 0 |  |  | 2024-05-13 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Cambridge | ESMAEX-02718 | 02138 | 60 | Solar |  | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Online
NSTAR | Boston | ESMAEX-02755 | 02115 | 120 | Solar | 452-1401 | 2023-08-04 | 2023-08-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Wayland | ESMAEX-02601 | 01778 | 20 | Solar | 342-H1 | 2023-06-22 | 2023-07-05 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online | [12 empty] | STA_342 Sudbury
NSTAR | East Wareham | ESMAEX-02609 | 02538 | 10 | Battery | 3-82-82 | 2023-06-23 | 2023-07-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Medfield | ESMAEX-02607 | 02052 | 30 | Solar | 456-H3 | 2023-06-23 | 2023-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [12 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-02615 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-06-26 | 2023-07-20 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-18 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Sharon | ESMAEX-02618 | 02067 | 3.9 | Solar | 470-H12 | 2023-06-27 | 2023-08-09 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Online | [11 empty] | 0 | STA_470 Canton
NSTAR | West Wareham | ESMAEX-02629 | 02576 | 10 | Solar | 3-86-966 | 2023-06-29 | 2023-07-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Cambridge | ESMAEX-02620 | 02139 | 7.6 | Solar | 817-01 | 2023-06-27 | 2023-06-27 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [12 empty] | STA_831 Putnam
NSTAR | Holliston | ESMAEX-02636 | 01746 | 11.712 | Solar & Battery | 274-H3 | 2023-07-05 | 2023-07-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Online | [12 empty] | STA_274 Sherborn
NSTAR | South Chatham | ESMAEX-02644 | 02659 | 10 | Battery | 4-95A-95A | 2023-07-07 | 2023-07-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Online | [12 empty] | STA_968 Harwich
NSTAR | Weston | ESMAEX-02628 | 02493 | 19.72 | Solar | 282-H10 | 2023-06-29 | 2023-07-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [12 empty] | STA_282 Waltham
NSTAR | Canton | ESMAEX-02627 | 02021 | 18.1 | Solar & Battery | 269-1320H1 | 2023-06-28 | 2023-07-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [12 empty] | STA_470 Canton
NSTAR | Bedford | ESMAEX-02635 | 01730 | 196.99 | Solar | 533-H3 | 2023-06-30 | 2023-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-23 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-02633 | 02090 | 13.056 | Solar | 456-H4 | 2023-06-30 | 2023-07-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-21 | Online | [12 empty] | STA_456 Dover
NSTAR | East Walpole | ESMAEX-02657 | 02032 | 15.2 | Solar | 146-H4 | 2023-07-10 | 2023-07-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [12 empty] | STA_146 Walpole
NSTAR | Carlisle | ESMAEX-02745 | 01741 | 16 | Solar | 512-1399H1 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Rochester | ESMAEX-03936 | 02770 | 20 | Solar | 3-703-703 | 2024-07-30 | 2024-08-13 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Lexington | ESMAEX-02875 | 02421 | 19.8 | Solar | 320-H2 | 2023-08-29 | 2023-10-16 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Online | [12 empty] | STA_320 Lexington
NSTAR | North Dartmouth | ESMAEX-02645 | 02747 | 200 | Solar | 2-541-541 | 2023-10-06 | 2023-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Framingham | ESMAEX-02648 | 01702 | 15.2 | Solar | 455-H3 | 2023-07-07 | 2023-07-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Mashpee | ESMAEX-02660 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-11 | 2023-08-14 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Arlington | ESMAEX-02707 | 02476 | 150 | Solar |  | 2023-07-24 | 2023-08-23 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Meter
NSTAR | Norfolk | ESMAEX-02658 | 02056 | 140 | Solar | 146-H3 | 2023-07-28 | 2023-08-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [12 empty] | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02659 | 02056 | 100 | Solar | 146-H3 | 2023-07-28 | 2023-08-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Mashpee | ESMAEX-02671 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-13 | 2023-08-14 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Arlington | ESMAEX-02664 | 02476 | 4.39 | Solar | 211-H11 | 2023-07-12 | 2023-07-25 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-07 | Online | [12 empty] | STA_211 Woburn
NSTAR | Winchester | ESMAEX-02667 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-13 | 2023-07-26 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [12 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-02678 | 02445 | 200 | Solar | 350-H7 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Arlington | ESMAEX-02686 | 02474 | 20 | Solar | 59-1383H1 | 2023-07-18 | 2023-08-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-07-26 | Online | [12 empty] | STA_211 Woburn
NSTAR | Stoneham | ESMAEX-02677 | 02180 | 180 | Solar | 375-H2 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | New Bedford | ESMAEX-02876 | 02745 | 199 | Solar | 2-102-102 | 2023-08-29 | 2023-09-19 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_636 Industrial Park
NSTAR | Winchester | ESMAEX-02690 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-19 | 2023-09-20 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online | [12 empty] | STA_211 Woburn
NSTAR | Sandwich | ESMAEX-02681 | 02563 | 200 | Solar | 4-81A-81A | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | Westwood | ESMAEX-02680 | 02090 | 17.28 | Solar | 456-H4 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [12 empty] | STA_456 Dover
NSTAR | Dorchester | ESMAEX-02751 | 02122 | 10 | Battery | 511-1498H1 | 2023-08-04 | 2023-08-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Wellfleet | ESMAEX-02803 | 02667 | 17.4 | Battery | 4-94B-94B | 2023-10-27 | 2023-09-06 | -39 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-09 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Lincoln | ESMAEX-02827 | 01773 | 25.8 | Solar & Battery | 320-H6 | 2023-08-17 | 2023-09-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [12 empty] | STA_320 Lexington
NSTAR | Needham | ESMAEX-02783 | 02492 | 15.2 | Solar | 148-H4 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-08-23 | Online | [12 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-02687 | 01803 | 17.4 | Solar | 391-H6 | 2023-07-19 | 2023-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online | [12 empty] | STA_391 Burlington
NSTAR | West Newton | ESMAEX-02688 | 02465 | 16 | Solar | 316-05 | 2023-07-19 | 2023-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online | [11 empty] | 16 | STA_282 Waltham
NSTAR | Duxbury | ESMAEX-02693 | 02332 | 19 | Solar | 3-24B-24B | 2023-07-20 | 2023-08-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-21 | Online | [11 empty] | 19 | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-02703 | 02420 | 15.2 | Solar | 533-H9 | 2023-07-21 | 2023-08-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Burlington | ESMAEX-03180 | 01803 | 240 | Solar | 391-H16 | 2023-11-20 | 2023-12-18 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [12 empty] | STA_391 Burlington
NSTAR | Westwood | ESMAEX-02705 | 02090 | 15.2 | Solar | 148-H3 | 2023-07-24 | 2023-08-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online | [12 empty] | STA_148 Needham
NSTAR | Medway | ESMAEX-02825 | 02341 | 27.3 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online | [12 empty] | STA_065 Medway
NSTAR | Boston | ESMAEX-03169 | 02119 | 67.3 | Solar | 396-1050H4 | 2023-11-17 | 2024-01-31 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Burlington | ESMAEX-02781 | 01803 | 15.68 | Solar | 346-1395H1 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Online | [12 empty] | STA_391 Burlington
NSTAR | Medway | ESMAEX-02824 | 02053 | 50 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_065 Medway
NSTAR | Carlisle | ESMAEX-02813 | 01741 | 7.8 | Solar & Battery | 512-1399H1 | 2023-08-15 | 2023-09-25 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-06 | [7 empty] | 0 |  | 0 |  |  | 2024-06-24 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Kingston | ESMAEX-02711 | 02364 | 18.3 | Solar | 3-18-18 | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth
NSTAR | Ashland | ESMAEX-02740 | 01721 | 200 | Solar | 274-H1 | 2023-08-01 | 2023-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-02 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Chatham | ESMAEX-02734 | 02633 | 19.14 | Solar | 4-95B-95B | 2023-08-01 | 2023-08-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Online | [12 empty] | STA_975 Orleans
NSTAR | Needham | ESMAEX-02722 | 02492 | 20.2 | Solar & Battery | 148-02 | 2023-07-28 | 2023-08-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Online | [12 empty] | STA_148 Needham
NSTAR | Winchester | ESMAEX-02730 | 01890 | 200 | Fuel Cell | 211-H1 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Burlington | ESMAEX-02733 | 01803 | 1500 | Fuel Cell | 391-H13 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_391 Burlington
NSTAR | Hyannis | ESMAEX-02732 | 02601 | 200 | Fuel Cell | 4-63-521 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Cambridge | ESMAEX-02731 | 02138 | 550 | Fuel Cell | 819-1NB5 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_402 Newton Street
NSTAR | Arlington | ESMAEX-02744 | 02474 | 13 | Solar & Battery | 211-H11 | 2023-08-01 | 2023-08-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Online | [12 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-02724 | 02067 | 15.2 | Solar | 146-H8 | 2023-07-28 | 2023-08-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online | [12 empty] | STA_146 Walpole
NSTAR | Jamaica Plain | ESMAEX-02726 | 02130 | 10 | Battery | 284-07 | 2023-07-30 | 2023-08-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 0 | STA_350 Colburn Street
NSTAR | Dover | ESMAEX-02728 | 02030 | 10 | Battery | 456-H3 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online | [11 empty] | 0 | STA_456 Dover
NSTAR | Lincoln | ESMAEX-02729 | 01773 | 699.3 | Solar | 320-H6 | 2023-11-01 | 2024-01-10 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-04016 | 02210 | 80 | Solar | 99-H2 | 2024-08-29 | 2024-10-10 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [12 empty] | STA_099 Seafood Way
NSTAR | Millis | ESMAEX-02772 | 02054 | 17.28 | Battery | 65-H1 | 2023-08-08 | 2023-08-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [12 empty] | STA_065 Medway
NSTAR | Cambridge | ESMAEX-03392 | 02139 | 30 | Solar | 816-04 | 2024-01-29 | 2024-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  | 2025-04-03 | Online | [12 empty] | STA_831 Putnam
NSTAR | Holliston | ESMAEX-02739 | 01746 | 480 | Solar | 274-H1 | 2023-09-01 | 2023-09-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Lincoln | ESMAEX-02747 | 01773 | 15.2 | Solar & Battery | 320-H8 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [12 empty] | STA_320 Lexington
NSTAR | Sharon | ESMAEX-03046 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2023-10-12 | 2023-10-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [12 empty] | STA_470 Canton
NSTAR | Framingham | ESMAEX-02919 | 01701 | 60 | Solar | 433-H4 | 2023-09-14 | 2023-09-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-02779 | 02492 | 200 | Fuel Cell | 148-03 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_148 Needham
NSTAR | Dover | ESMAEX-02746 | 02030 | 15.2 | Solar | 456-H5 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [12 empty] | STA_456 Dover
NSTAR | Newton Center | ESMAEX-02760 | 02459 | 8.7 | Solar & Battery | 369-06 | 2023-08-07 | 2023-08-30 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-02748 | 02420 | 19 | Solar | 351-01 | 2023-08-03 | 2023-08-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Technical Review | [12 empty] | STA_351 East Lexington
NSTAR | East Freetown | ESMAEX-02750 | 02717 | 15.744 | Solar | 2-108-108 | 2023-08-03 | 2023-08-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | East Cambridge | ESMAEX-02775 | 02141 | 1550 | Fuel Cell | 875-1N23B | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_875 East Cambridge
NSTAR | Burlington | ESMAEX-02777 | 01803 | 200 | Fuel Cell | 391-H6 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_391 Burlington
NSTAR | Newtonville | ESMAEX-02776 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Walpole | ESMAEX-02761 | 02081 | 15.2 | Solar & Battery | 146-H4 | 2023-08-07 | 2023-09-06 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [12 empty] | STA_146 Walpole
NSTAR | Hopkinton | ESMAEX-02857 | 01748 | 15.2 | Solar | 455-H8 | 2023-08-23 | 2023-09-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Acton | ESMAEX-02796 | 01720 | 19.39 | Solar | 416-H5 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-11-13 | Online | [12 empty] | STA_416 Maynard
NSTAR | Carlisle | ESMAEX-02762 | 01741 | 17.1 | Solar | 512-1399H1 | 2023-08-07 | 2023-09-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Brookline | ESMAEX-02771 | 02446 | 15.36 | Solar | 315-H8 | 2023-08-08 | 2023-09-08 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online
NSTAR | Newtonville | ESMAEX-02784 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Needham | ESMAEX-02807 | 02494 | 9.6 | Solar & Battery | 148-H4 | 2023-08-14 | 2023-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Online | [12 empty] | STA_148 Needham
NSTAR | Sherborn | ESMAEX-02805 | 01770 | 20 | Solar | 456-H5 | 2023-08-14 | 2023-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Technical Review | [12 empty] | STA_456 Dover
NSTAR | Holliston | ESMAEX-02786 | 01746 | 10 | Solar & Battery | 130-H1 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online | [12 empty] | STA_130 Holliston
NSTAR | Weston | ESMAEX-02793 | 02493 | 15.2 | Solar | 282-H10 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [12 empty] | STA_282 Waltham
NSTAR | Hopkinton | ESMAEX-02800 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-02879 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-08-31 | 2023-09-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-02801 | 01701 | 10 | Battery | 342-H9 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [11 empty] | 0 | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-02802 | 02451 | 5 | Battery | 450-H1 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [11 empty] | 0 | STA_450 Trapelo Road
NSTAR | Sharon | ESMAEX-02810 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2023-08-14 | 2023-09-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-05 | Online | [12 empty] | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02831 | 02056 | 15.2 | Solar | 146-H10 | 2023-08-17 | 2023-09-11 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-29 | Online | [12 empty] | STA_146 Walpole
NSTAR | Lincoln | ESMAEX-02816 | 01773 | 15 | Solar & Battery | 282-H1 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [12 empty] | STA_282 Waltham
NSTAR | West Roxbury | ESMAEX-02817 | 02132 | 18.88 | Solar | 496-H6 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-18 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Canton | ESMAEX-02820 | 02021 | 10.368 | Solar | 269-1321H2 | 2023-08-16 | 2023-10-06 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [12 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-02832 | 01748 | 120 | Solar | 126-H2 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Mattapoisett | ESMAEX-02840 | 02739 | 4980 | Solar & Battery | 2-301-301 | 2023-09-27 | 2023-10-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven | 2024 SEMA/Cape ASO Study | Phase 2 - Executed ISA | 4980 | STA_646 Crystal Spring
NSTAR | Weston | ESMAEX-02842 | 02493 | 19 | Solar | 342-H1 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Norfolk | ESMAEX-02844 | 02056 | 15.2 | Solar & Battery | 65-H1 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online | [12 empty] | STA_065 Medway
NSTAR | Newton | ESMAEX-03544 | 02459 | 20 | Solar | 1701 | 2024-03-18 | 2024-04-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [11 empty] | 19.9 | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-02850 | 02420 | 15.2 | Solar | 533-H9 | 2023-08-21 | 2023-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-02848 | 01701 | 7.6 | Solar | 433-H3 | 2023-08-21 | 2023-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-17 | Online | [11 empty] | 7.6 | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-02851 | 01803 | 17.6 | Solar | 391-H7 | 2023-08-22 | 2023-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-21 | Online | [11 empty] | 20 | STA_391 Burlington
NSTAR | Auburndale | ESMAEX-02860 | 02466 | 5 | Battery | 292-H7 | 2023-08-23 | 2023-09-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [11 empty] | 0 | STA_292 Newton Highlands
NSTAR | Dedham | ESMAEX-02865 | 02026 | 60 | Solar |  | 2023-08-25 | 2023-09-26 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-08 | Online
NSTAR | Wayland | ESMAEX-02868 | 01778 | 17.1 | Solar | 342-H1 | 2023-08-25 | 2023-09-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-02931 | 01741 | 19.8 | Solar | 512-1399H1 | 2023-09-18 | 2023-10-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | East Boston | ESMAEX-03210 | 02128 | 60 | Solar | 488-H8 | 2023-12-01 | 2023-12-27 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-02873 | 01760 | 13.05 | Solar | 240-H1 | 2023-08-28 | 2023-09-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [12 empty] | STA_240 Framingham
NSTAR | Burlington | ESMAEX-02884 | 01803 | 16.8 | Solar | 346-1395H1 | 2023-09-01 | 2023-10-23 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [12 empty] | STA_391 Burlington
NSTAR | Needham | ESMAEX-02980 | 02492 | 19.8 | Solar & Battery | 148-H1 | 2023-09-28 | 2023-10-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-14 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [11 empty] | 20 | STA_148 Needham
NSTAR | Framingham | ESMAEX-02877 | 01702 | 20 | Solar | 240-H6 | 2023-08-29 | 2023-09-20 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-16 | Online | [12 empty] | STA_240 Framingham
NSTAR | Arlington | ESMAEX-02886 | 02474 | 50 | Solar | 59-1393H1 | 2023-09-01 | 2023-09-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Framingham | ESMAEX-02932 | 01701 | 15.2 | Solar | 433-H8 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [11 empty] | 13.62 | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-02896 | 01778 | 15.2 | Solar | 342-H1 | 2023-09-07 | 2023-09-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Brookline | ESMAEX-02917 | 02445 | 16.2 | Solar | 350-H3 | 2023-09-13 | 2023-09-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_350 Colburn Street
NSTAR | Boston | ESMAEX-03020 | 02210 | 300 | Solar | 99-H2 | 2023-10-04 | 2023-12-07 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_099 Seafood Way
NSTAR | East Walpole | ESMAEX-03053 | 02032 | 15.2 | Solar | 146-H4 | 2023-10-16 | 2023-11-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [12 empty] | STA_146 Walpole
NSTAR | Acusnet | ESMAEX-02898 | 02743 | 1.5 | Solar & Battery | 2-230-230 | 2023-09-08 | 2023-09-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [12 empty] | STA_612 Acushnet
NSTAR | Hopkinton | ESMAEX-02905 | 01748 | 199 | Solar | 126-H2 | 2023-09-11 | 2023-09-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-03061 | 02090 | 10 | Battery | 148-H3 | 2023-10-17 | 2023-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Online | [12 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-02929 | 02747 | 15.2 | Solar | 2-70-502 | 2023-09-18 | 2023-10-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online
NSTAR | Holliston | ESMAEX-02911 | 01746 | 20 | Solar & Battery | 130-H2 | 2023-09-12 | 2023-09-19 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [12 empty] | STA_130 Holliston
NSTAR | East Walpole | ESMAEX-02934 | 02032 | 15.2 | Solar | 146-H4 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Online | [12 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-02909 | 02186 | 16.53 | Solar & Battery | 496-H7 | 2023-09-12 | 2023-09-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Waltham | ESMAEX-02936 | 02452 | 15.2 | Solar | 450-H4 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Falmouth | ESMAEX-02922 | 02540 | 15 | Battery | 4-72-72 | 2023-09-15 | 2023-09-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-03028 | 01701 | 10 | Battery | 278-H2 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-01-26 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Westwood | ESMAEX-02926 | 02090 | 10 | Battery | 469-H2 | 2023-09-15 | 2023-10-16 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online
NSTAR | Sharon | ESMAEX-02920 | 02067 | 15.04 | Solar | 146-H7 | 2023-09-14 | 2023-10-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Online | [12 empty] | STA_146 Walpole
NSTAR | Dover | ESMAEX-02930 | 02030 | 5 | Battery | 456-H5 | 2023-09-18 | 2023-10-20 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Online | [12 empty] | STA_456 Dover
NSTAR | Duxbury | ESMAEX-03167 | 02332 | 30 | Solar | 3-23-23 | 2023-11-17 | 2023-12-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Walpole | ESMAEX-02955 | 02081 | 15.2 | Solar | 146-H6 | 2023-09-26 | 2023-10-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online | [12 empty] | STA_146 Walpole
NSTAR | Duxbury | ESMAEX-02921 | 02332 | 14 | Battery | 3-24B-24B | 2023-09-15 | 2023-12-04 | 56 |  | 56 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-06 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Fairhaven | ESMAEX-02923 | 02719 | 15 | Battery | 2-230-230 | 2023-09-15 | 2023-10-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-05-19 | Online | [12 empty] | STA_612 Acushnet
NSTAR | Hopkinton | ESMAEX-02925 | 01748 | 11.4 | Solar | 274-H5 | 2023-09-15 | 2023-09-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Online | [11 empty] | 11.4 | STA_274 Sherborn
NSTAR | Canton | ESMAEX-02959 | 02021 | 15.2 | Solar & Battery | 269-1321H2 | 2023-09-26 | 2023-10-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-30 | Online | [12 empty] | STA_470 Canton
NSTAR | Roxbury | ESMAEX-03017 | 02119 | 20 | Solar | 143-151H1 | 2023-10-04 | 2023-11-15 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Westwood | ESMAEX-02933 | 02090 | 19.968 | Solar | 148-H3 | 2023-09-19 | 2023-10-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [12 empty] | STA_148 Needham
NSTAR | Plymouth | ESMAEX-02947 | 02360 | 77.3 | Solar | 3-13-943 | 2023-09-22 | 2024-08-15 | 234 |  | 234 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Dover | ESMAEX-03003 | 02030 | 16.2 | Solar | 456-H3 | 2023-10-03 | 2023-10-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Online | [12 empty] | STA_456 Dover
NSTAR | Charlestown | ESMAEX-02954 | 02129 | 80 | Solar | 218-80H | 2023-09-25 | 2023-10-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [12 empty] | STA_250 Mystic
NSTAR | Natick | ESMAEX-02998 | 01760 | 15.2 | Solar | 433-H7 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-02951 | 01803 | 66.6 | Solar | 375-H6 | 2023-09-22 | 2023-10-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-13 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Lincoln | ESMAEX-02995 | 01773 | 3.8 | Solar & Battery | 320-H6 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [12 empty] | STA_320 Lexington
NSTAR | Walpole | ESMAEX-02997 | 02081 | 7.6 | Solar | 146-H4 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-02991 | 02492 | 20.1 | Solar | 148-01 | 2023-09-29 | 2023-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [12 empty] | STA_148 Needham
NSTAR | Waltham | ESMAEX-02956 | 02453 | 10 | Solar | 467-H5 | 2023-09-26 | 2023-10-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [12 empty] | STA_467 Watertown
NSTAR | Edgartown | ESMAEX-03023 | 02539 | 400 | Battery |  | 2023-10-25 | 2024-01-03 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 400
NSTAR | Winchester | ESMAEX-03063 | 01890 | 72.2 | Solar | 211-H11 | 2023-10-18 | 2023-10-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [12 empty] | STA_211 Woburn
NSTAR | Watertown | ESMAEX-02986 | 02472 | 16.47 | Solar | 467-H8 | 2023-09-29 | 2023-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Online | [12 empty] | STA_467 Watertown
NSTAR | Ashland | ESMAEX-02960 | 01721 | 10 | Solar | 519-175H1 | 2023-09-26 | 2023-10-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-26 | [7 empty] | 0 |  | 0 |  |  | 2025-10-27 | Online | [11 empty] | 10 | STA_274 Sherborn
NSTAR | Brookline | ESMAEX-02973 | 02467 | 35 | Internal Combustion Engine |  | 2023-09-27 | 2023-10-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Framingham | ESMAEX-02985 | 01702 | 250 | Solar | 240-H3 | 2023-10-27 | 2023-11-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 250 | STA_240 Framingham
NSTAR | Cambridge | ESMAEX-03070 | 02138 | 12.3 | Solar & Battery | 817-09 | 2023-10-19 | 2023-12-18 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [12 empty] | STA_831 Putnam
NSTAR | Chelsea | ESMAEX-03001 | 02150 | 30.4 | Solar | 488-H6 | 2023-10-02 | 2023-11-13 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online | [12 empty] | STA_488 Chelsea
NSTAR | East Freetown | ESMAEX-02989 | 02717 | 10 | Solar | 2-108-108 | 2023-09-29 | 2023-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Online | [8 empty] | Cape |  |  | 10 | STA_636 Industrial Park
NSTAR | New Bedford | ESMAEX-02994 | 02745 | 999 | Solar & Battery | 2-151-151 | 2023-09-29 | 2023-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | New Bedford |  | Hold In Queue | 999 | STA_636 Industrial Park
NSTAR | Burlington | ESMAEX-02999 | 01803 | 15.8 | Solar | 391-H7 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Online | [11 empty] | 15.8 | STA_391 Burlington
NSTAR | Natick | ESMAEX-03007 | 01760 | 17.28 | Solar | 240-H1 | 2023-10-03 | 2023-10-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online | [12 empty] | STA_240 Framingham
NSTAR | Boston | ESMAEX-03016 | 02210 | 999 | Solar & Battery | 151-140H | 2023-12-22 | 2024-01-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 999 | STA_385D K Street
NSTAR | Newtonville | ESMAEX-03021 | 02460 | 20 | Solar & Battery | 277-04 | 2023-10-04 | 2023-10-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Technical Review | [12 empty] | STA_467 Watertown
NSTAR | Jamaica Plain | ESMAEX-03407 | 02130 | 15 | Battery | 496-H4 | 2024-02-01 | 2024-02-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Sharon | ESMAEX-03027 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2023-10-05 | 2023-10-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [12 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03030 | 02139 | 487.5 | Solar | 828-1369 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_828 Alewife
NSTAR | Cambridge | ESMAEX-03029 | 02139 | 375 | Solar | 828-1370 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_828 Alewife
NSTAR | Arlington | ESMAEX-03265 | 02474 | 21.66 | Solar & Battery | 211-H11 | 2023-12-12 | 2024-01-29 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online | [11 empty] | 10 | STA_211 Woburn
NSTAR | Maynard | ESMAEX-03032 | 01754 | 19.5 | Solar | 416-H6 | 2023-10-09 | 2023-11-27 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Online | [12 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-03037 | 01760 | 20 | Solar | 240-H5 | 2023-10-11 | 2023-11-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [11 empty] | 20 | STA_240 Framingham
NSTAR | Sharon | ESMAEX-03038 | 02067 | 23.36 | Solar | 470-H12 | 2023-10-11 | 2023-11-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-05 | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-03043 | 01748 | 18.816 | Solar | 126-H1 | 2023-10-12 | 2023-11-02 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-03161 | 01801 | 20 | Battery | 211-H13 | 2023-11-15 | 2023-12-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Online | [12 empty] | STA_211 Woburn
NSTAR | Burlington | ESMAEX-03049 | 01803 | 20.8 | Solar | 391-H7 | 2023-10-13 | 2023-11-02 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-03055 | 01748 | 15.2 | Solar | 126-H2 | 2023-10-16 | 2023-11-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Carlisle | ESMAEX-03054 | 01741 | 17.6 | Battery | 533-H8 | 2023-10-16 | 2023-11-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-03079 | 01701 | 18.9 | Solar | 342-H5 | 2023-10-23 | 2023-11-08 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Rochester | ESMAEX-03058 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth | 2024 SEMA/Cape ASO Study | Phase 2 - In Process |  | STA_713 Tremont
NSTAR | Framingham | ESMAEX-03059 | 01701 | 20 | Solar | 342-H4 | 2023-10-17 | 2023-10-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Canton | ESMAEX-03069 | 02021 | 5 | Solar & Battery | 269-1321H2 | 2023-10-19 | 2023-11-20 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [12 empty] | STA_470 Canton
NSTAR | Framingham | ESMAEX-03071 | 01701 | 498 | Solar | 455-H1 | 2023-10-19 | 2024-01-31 | 74 |  | 74 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Carlisle | ESMAEX-03073 | 01741 | 15.7 | Solar | 533-H8 | 2023-10-19 | 2023-11-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Weston | ESMAEX-03077 | 02493 | 16.25 | Solar | 282-H10 | 2023-10-22 | 2023-11-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [12 empty] | STA_282 Waltham
NSTAR | Wayland | ESMAEX-03076 | 01778 | 1 | Battery | 342-H1 | 2023-10-20 | 2023-11-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Jamaica Plain | ESMAEX-03273 | 02130 | 16.8 | Solar | 496-H4 | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Hopkinton | ESMAEX-03177 | 01748 | 15.2 | Solar | 126-H4 | 2023-11-20 | 2024-01-23 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-03078 | 01720 | 250 | Solar | 416-H8 | 2024-02-26 | 2024-03-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_416 Maynard
NSTAR | Hopkinton | ESMAEX-03178 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-11-20 | 2024-01-23 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-03084 | 02090 | 19 | Solar | 456-H1 | 2023-11-07 | 2023-11-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [12 empty] | STA_456 Dover
NSTAR | Burlington | ESMAEX-03155 | 01803 | 15.2 | Solar | 391-H7 | 2023-11-15 | 2023-12-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [12 empty] | STA_391 Burlington
NSTAR | Sherborn | ESMAEX-03091 | 01770 | 5 | Battery | 130-H2 | 2023-10-26 | 2023-11-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [12 empty] | STA_130 Holliston
NSTAR | Roxbury | ESMAEX-03130 | 02119 | 100 | Solar | 396-05 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-31 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Truro | ESMAEX-03089 | 02666 | 9.9 | Solar | 4-96-96 | 2023-10-25 | 2023-11-07 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Milton | ESMAEX-03133 | 02186 | 15.2 | Solar | 4303 | 2023-11-08 | 2023-12-06 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Sharon | ESMAEX-03110 | 02067 | 15 | Battery | 470-H12 | 2023-11-02 | 2023-11-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [12 empty] | STA_470 Canton
NSTAR | Wayland | ESMAEX-03100 | 01778 | 50 | Solar | 342-H3 | 2023-10-31 |  | -32274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Bedford | ESMAEX-03098 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2023-10-30 | 2023-11-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-27 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-03149 | 01760 | 240 | Solar | 433-H11 | 2023-11-14 | 2023-12-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 240 | STA_433 Speen Street
NSTAR | Rochester | ESMAEX-03258 | 02770 | 56.14 | Solar | 3-702-702 | 2023-12-07 | 2023-12-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Acton | ESMAEX-03154 | 01720 | 23 | Solar & Battery | 416-H5 | 2023-11-15 | 2023-12-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Online | [11 empty] | 4.8 | STA_416 Maynard
NSTAR | Framingham | ESMAEX-03102 | 01701 | 19.2 | Solar | 278-H2 | 2023-10-31 | 2023-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Acton | ESMAEX-03122 | 01720 | 14 | Battery | 416-H2 | 2023-11-07 | 2023-11-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-09 | [7 empty] | 0 |  | 0 |  |  | 2024-04-02 | Online | [12 empty] | STA_416 Maynard
NSTAR | West Newton | ESMAEX-03116 | 02465 | 20.125 | Battery | 282-H9 | 2023-11-03 | 2023-11-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-16 | Online | [11 empty] | 20 | STA_282 Waltham
NSTAR | Acton | ESMAEX-03134 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-20 | Online | [11 empty] | 19.92 | STA_416 Maynard
NSTAR | Hyannis | ESMAEX-03114 | 02601 | 499.5 | Solar | 4-84B-524 | 2023-12-06 | 2024-01-17 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 499.5 | STA_961 Hyannis Junction
NSTAR | Hyannis | ESMAEX-03148 | 02601 | 150 | Solar | 4-84B-524 | 2023-11-14 | 2023-12-12 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 150 | STA_961 Hyannis Junction
NSTAR | Arlington | ESMAEX-03117 | 02474 | 67.3 | Solar | 211-H3 | 2023-11-03 | 2023-11-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Boston | ESMAEX-03135 | 02111 | 24.4 | Solar | 514-1N25S | 2024-08-14 | 2023-12-18 | -174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [12 empty] | STA_514 Kingston Street
NSTAR | Cambridge | ESMAEX-03146 | 02139 | 30 | Solar | 831-1394 | 2023-11-14 | 2023-11-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [12 empty] | STA_831 Putnam
NSTAR | Cambridge | ESMAEX-03147 | 02139 | 40 | Solar | 831-1303 | 2023-11-14 | 2023-11-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [12 empty] | STA_831 Putnam
NSTAR | Newton | ESMAEX-03166 | 02458 | 2.24 | Solar | 277-05 | 2023-11-16 | 2023-12-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [12 empty] | STA_467 Watertown
NSTAR | Dover | ESMAEX-03131 | 02030 | 5 | Battery | 456-H5 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-04 | Online | [12 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-03140 | 02090 | 8.64 | Solar | 148-H3 | 2023-11-10 | 2023-11-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [12 empty] | STA_148 Needham
NSTAR | Cambridge | ESMAEX-03393 | 02139 | 60 | Solar |  | 2024-01-29 | 2024-02-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online
NSTAR | Newton | ESMAEX-03165 | 02458 | 15.3 | Solar | 277-05 | 2023-11-16 | 2023-12-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Online | [12 empty] | STA_467 Watertown
NSTAR | Provincetown | ESMAEX-03138 | 02657 | 19.9 | Solar & Battery | 4-675-675 | 2023-11-10 | 2023-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [11 empty] | 19.9 | STA_976 Wellfleet
NSTAR | Framingham | ESMAEX-03151 | 01702 | 20 | Solar | 240-H6 | 2023-11-14 | 2023-11-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-08 | Online | [12 empty] | STA_240 Framingham
NSTAR | Hopkinton | ESMAEX-03182 | 01748 | 10 | Battery | 126-H2 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [11 empty] | 12.4 | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-03143 | 01720 | 15.2 | Solar | 416-H5 | 2023-11-13 | 2023-11-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [11 empty] | 15.2 | STA_416 Maynard
NSTAR | Needham | ESMAEX-03183 | 02494 | 15.2 | Solar | 148-H4 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-16 | Online | [12 empty] | STA_148 Needham
NSTAR | Brighton | ESMAEX-03144 | 02135 | 15.3 | Solar | 315-H10 | 2023-11-13 | 2024-01-31 | 57 |  | 57 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [12 empty] | STA_315 Electric Avenue
NSTAR | Medway | ESMAEX-03159 | 02053 | 80 | Solar | 65-H3 | 2023-12-15 | 2024-01-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-13 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Online | [12 empty] | STA_065 Medway
NSTAR | Chatham | ESMAEX-03158 | 02633 | 15.2 | Solar | 4-95B-95B | 2023-11-15 | 2023-12-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-15 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [11 empty] | 15.2 | STA_975 Orleans
NSTAR | Waltham | ESMAEX-03162 | 02451 | 100 | Solar | 282-H1 | 2023-11-15 | 2024-02-22 | 71 |  | 71 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [12 empty] | STA_282 Waltham
NSTAR | Holliston | ESMAEX-03163 | 01746 | 20 | Battery | 65-H5 | 2023-11-16 | 2023-12-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Online | [12 empty] | STA_065 Medway
NSTAR | Newton Highlands | ESMAEX-03164 | 02461 | 15.2 | Solar | 292-H3 | 2023-11-16 | 2023-11-30 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Weston | ESMAEX-03175 | 02493 | 22.2 | Solar | 282-H8 | 2023-11-20 | 2024-01-10 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [12 empty] | STA_282 Waltham
NSTAR | Weston | ESMAEX-03320 | 02493 | 15.6 | Solar | 282-H1 | 2023-12-29 | 2024-01-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-08 | Online | [12 empty] | STA_282 Waltham
NSTAR | Ashland | ESMAEX-03181 | 01721 | 10 | Battery | 455-H8 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [11 empty] | 20 | STA_455 West Framingham
NSTAR | Winchester | ESMAEX-03187 | 01890 | 490 | Solar | 211-07 | 2023-12-11 | 2024-01-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 490 | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-03189 | 01748 | 15.744 | Solar | 126-H2 | 2023-11-22 | 2023-12-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-03195 | 02360 | 6 | Solar | 3-14-934 | 2023-11-27 | 2023-12-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online | [8 empty] | Plymouth |  |  | 6 | STA_737 West Pond
NSTAR | Waltham | ESMAEX-03202 | 02452 | 15.2 | Solar | 450-H6 | 2023-11-29 | 2023-12-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-08-12 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | New Bedford | ESMAEX-03339 | 02740 | 250 | Solar | 2-89-89 | 2024-01-08 | 2024-01-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Milton | ESMAEX-03206 | 02186 | 20 | Solar | 311-04 | 2023-11-29 | 2023-12-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [11 empty] | 20 | STA_496 Hyde Park
NSTAR | Billerica | ESMAEX-03207 | 01821 | 10 | Solar & Battery | 533-H7 | 2023-11-30 | 2023-12-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-03281 | 01778 | 12.21 | Solar | 342-H1 | 2023-12-14 | 2024-02-22 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Sherborn | ESMAEX-03255 | 01770 | 18.56 | Solar | 240-H1 | 2023-12-06 | 2024-01-12 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-01 | Online | [12 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03212 | 02420 | 23 | Solar & Battery | 3406 | 2023-12-01 | 2023-12-27 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [11 empty] | 20
NSTAR | Burlington | ESMAEX-03261 | 01803 | 34.5 | Solar & Battery | 346-1395H1 | 2023-12-08 | 2024-01-09 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Online | [12 empty] | STA_391 Burlington
NSTAR | Arlington | ESMAEX-03209 | 02476 | 490 | Solar | 211-H3 | 2023-12-28 | 2024-01-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Westwood | ESMAEX-03307 | 02090 | 15.2 | Solar & Battery | 148-H3 | 2023-12-21 | 2024-03-04 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [11 empty] | 20 | STA_148 Needham
NSTAR | Chilmark | ESMAEX-03230 | 02535 | 11.4 | Solar | 4-97-97 | 2023-12-05 | 2024-02-12 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | West Brewster | ESMAEX-03274 | 02631 | 20.44 | Solar | 4-89A-89A | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Lexington | ESMAEX-03260 | 02420 | 16.64 | Solar | 533-H9 | 2023-12-08 | 2023-12-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-10 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-03335 | 02186 | 15.2 | Solar | 362-1209H2 | 2024-01-04 | 2024-01-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Newton Center | ESMAEX-03302 | 02459 | 20.2 | Solar & Battery | 292-H6 | 2023-12-20 | 2024-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-08 | [7 empty] | 0 |  | 0 |  |  | 2025-08-07 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Cambridge | ESMAEX-03395 | 02142 | 120 | Solar |  | 2024-01-29 | 2024-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Millis | ESMAEX-03263 | 02054 | 19 | Solar & Battery | 130-H2 | 2023-12-11 | 2024-01-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Online | [11 empty] | 19.9 | STA_130 Holliston
NSTAR | East Freetown | ESMAEX-03264 | 02717 | 15.36 | Solar | 2-108-108 | 2023-12-12 | 2024-01-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Westwood | ESMAEX-03269 | 02090 | 23 | Solar & Battery | 456-H1 | 2023-12-12 | 2024-01-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [12 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-03272 | 01748 | 15.2 | Solar | 126-H4 | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Provincetown | ESMAEX-03277 | 02657 | 19.8 | Solar | 4-675-675 | 2023-12-14 | 2024-01-17 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-05-02 | Online | [11 empty] | 20 | STA_976 Wellfleet
NSTAR | Lexington | ESMAEX-03278 | 02420 | 15.2 | Solar | 351-02 | 2023-12-14 | 2024-01-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-03 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [12 empty] | STA_211 Woburn
NSTAR | Acton | ESMAEX-03348 | 01720 | 50 | Solar | 416-H5 | 2024-01-09 | 2024-01-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-08-21 | Online | [12 empty] | STA_416 Maynard
NSTAR | Hopkinton | ESMAEX-03398 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-01-30 | 2024-02-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Online | [11 empty] | 20 | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-03289 | 02421 | 17.6 | Solar & Battery | 450-H5 | 2023-12-19 | 2024-01-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Marshfield | ESMAEX-03291 | 02050 | 999 | Other | 3-24B-915 | 2024-06-12 | 2024-07-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 999 | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-03387 | 02421 | 1836 | Solar & Battery | 391-H11 | 2024-06-06 | 2024-07-12 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_391 Burlington
NSTAR | Natick | ESMAEX-03384 | 01760 | 16.8 | Solar | 240-H5 | 2024-01-25 | 2024-02-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [12 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03313 | 02420 | 15.2 | Solar | 391-H11 | 2023-12-27 | 2024-01-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [12 empty] | STA_391 Burlington
NSTAR | Lexington | ESMAEX-03532 | 02421 | 17.6 | Solar & Battery | 3402 | 2024-03-12 | 2024-03-28 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Online | [12 empty] | STA_320 Lexington
NSTAR | Woods Hole | ESMAEX-03334 | 02543 | 10 | Battery | 4-91-91 | 2024-01-04 | 2024-08-15 | 160 |  | 160 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-05 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | Cape |  |  | 10 | STA_933 Falmouth
NSTAR | Sudbury | ESMAEX-03362 | 01776 | 43.01 | Solar & Battery | 416-H6 | 2024-01-16 | 2024-02-22 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Online | [12 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-03351 | 02067 | 12.6 | Solar & Battery | 470-H3 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-20 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [12 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-03324 | 02052 | 23 | Solar & Battery | 456-H2 | 2024-01-03 | 2024-01-31 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Online | [11 empty] | 7.33 | STA_456 Dover
NSTAR | Jamaica Plain | ESMAEX-03333 | 02130 | 50 | Solar | 496-H4 | 2024-01-04 | 2024-01-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Hopkinton | ESMAEX-03376 | 01748 | 4.8 | Solar & Battery | 126-H2 | 2024-01-22 | 2024-02-22 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [11 empty] | 4.8 | STA_126 Hopkinton
NSTAR | Newton | ESMAEX-03366 | 02458 | 22.8 | Solar & Battery | 467-H3 | 2024-01-17 | 2024-02-22 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Online | [11 empty] | 22.8 | STA_467 Watertown
NSTAR | Stoneham | ESMAEX-03369 | 02180 | 10 | Battery | 375-H7 | 2024-01-18 | 2024-02-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-13 | Online | [11 empty] | 14.04 | STA_375 Dragon Court
NSTAR | East Walpole | ESMAEX-03354 | 02032 | 7.6 | Solar | 146-H4 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Online | [12 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03391 | 02139 | 160 | Solar |  | 2024-01-29 | 2024-02-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Online
NSTAR | Holliston | ESMAEX-03341 | 01746 | 7.6 | Solar | 65-H2 | 2024-01-09 | 2024-01-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [11 empty] | 7.6 | STA_065 Medway
NSTAR | Wayland | ESMAEX-03353 | 01778 | 16 | Solar | 342-H1 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [11 empty] | 16 | STA_342 Sudbury
NSTAR | Framingham | ESMAEX-03357 | 01701 | 30.66 | Solar & Battery | 455-H1 | 2024-01-12 | 2024-02-07 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Cambridge | ESMAEX-03423 | 02139 | 20 | Solar | 814-12 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Online | [11 empty] | 20 | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-03422 | 02139 | 20 | Solar | 815-10 | 2024-02-07 | 2024-02-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Technical Review | [12 empty] | STA_831 Putnam
NSTAR | Somerville | ESMAEX-03421 | 02145 | 25 | Solar | 387-148H2 | 2024-02-07 | 2024-02-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 11 | STA_250 Mystic
NSTAR | Dover | ESMAEX-03546 | 02030 | 23.03 | Solar | 456-H3 | 2024-03-18 | 2024-04-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | East Freetown | ESMAEX-03512 | 02717 | 200 | Solar | 2-108-108 | 2024-03-06 | 2024-03-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Ashland | ESMAEX-03400 | 01721 | 15.29 | Solar | 274-H6 | 2024-01-30 | 2024-02-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [11 empty] | 15.29
NSTAR | Holliston | ESMAEX-03386 | 01746 | 480 | Solar | 65-H5 | 2024-03-04 | 2024-03-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_065 Medway
NSTAR | Holliston | ESMAEX-03401 | 01746 | 50 | Solar | 65-H2 | 2024-01-30 | 2024-02-26 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Online | [12 empty] | STA_065 Medway
NSTAR | Waban | ESMAEX-03429 | 02468 | 17.6 | Solar & Battery | 1701 | 2024-02-08 | 2024-02-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [11 empty] | 7.05 | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-03414 | 01720 | 40 | Solar | 416-H1 | 2024-02-05 | 2024-02-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [12 empty] | STA_416 Maynard
NSTAR | South Wellfleet | ESMAEX-03501 | 02663 | 12.6 | Solar & Battery | 4-94B-653 | 2024-03-01 | 2024-03-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Newton Center | ESMAEX-03405 | 02459 | 10 | Battery | 292-H11 | 2024-02-01 | 2024-03-14 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Hopkinton | ESMAEX-03430 | 01748 | 23 | Battery | 126-H4 | 2024-02-09 | 2024-02-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [11 empty] | 20 | STA_126 Hopkinton
NSTAR | Brighton | ESMAEX-03476 | 02135 | 34.6 | Solar | 329-1N51H2 | 2024-02-23 | 2024-03-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-16 | Online | [12 empty] | STA_329 Brighton
NSTAR | Cambridge | ESMAEX-03457 | 02138 | 225 | Solar | 827-31 | 2024-02-16 | 2024-03-05 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-15 | Online | [12 empty] | STA_828 Alewife
NSTAR | Carlisle | ESMAEX-03506 | 01741 | 10 | Battery | 533-H8 | 2024-03-05 | 2024-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Lexington | ESMAEX-03436 | 02420 | 5 | Battery | 533-H9 | 2024-02-14 | 2024-03-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Online | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-03424 | 02186 | 10 | Battery | 362-1209H2 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-03452 | 02493 | 34.2 | Solar | 282-H10 | 2024-02-15 | 2024-03-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [12 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-03425 | 01720 | 10 | Battery | 512-1399H1 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [11 empty] | 12.4 | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-03426 | 01760 | 15.2 | Solar | 433-H10 | 2024-02-08 | 2024-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Online | [11 empty] | 15.2 | STA_433 Speen Street
NSTAR | Lexington | ESMAEX-03427 | 02421 | 16 | Solar | 3409 | 2024-02-08 | 2024-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-06-12 | Online | [11 empty] | 16
NSTAR | North Cambridge | ESMAEX-03439 | 02140 | 16.8 | Solar | 823-23 | 2024-02-14 | 2024-03-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [12 empty] | STA_828 Alewife
NSTAR | Sudbury | ESMAEX-03428 | 01776 | 9.6 | Solar & Battery | 342-H2 | 2024-02-08 | 2024-03-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-10-06 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-03472 | 01760 | 200 | Fuel Cell | 2302 | 2024-02-22 | 2024-03-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Online | [12 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03433 | 02420 | 300 | Photovoltaic + Battery | 34-1378 | 2024-06-07 | 2024-08-06 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-31 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Duxbury | ESMAEX-03461 | 02332 | 15.36 | Solar & Battery | 3-26-26 | 2024-02-19 | 2024-03-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online
NSTAR | Westwood | ESMAEX-03450 | 02090 | 10 | Solar & Battery | 148-H3 | 2024-02-14 | 2024-03-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [11 empty] | 10 | STA_148 Needham
NSTAR | Weston | ESMAEX-03454 | 02493 | 20 | Solar & Battery | 433-H5 | 2024-02-15 | 2024-03-05 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Online | [11 empty] | 20 | STA_433 Speen Street
NSTAR | Lexington | ESMAEX-03460 | 02421 | 11.4 | Solar & Battery | 3409 | 2024-02-19 | 2024-03-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online
NSTAR | Burlington | ESMAEX-03618 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-10 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Cataumet | ESMAEX-03462 | 02534 | 34.2 | Solar | 4-81A-81A | 2024-02-20 | 2024-03-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | Boston | ESMAEX-03557 | 02119 | 20 | Solar | 483-H3 | 2024-03-20 | 2024-05-15 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [12 empty] | STA_483 Dewar Street
NSTAR | Plymouth | ESMAEX-03475 | 02360 | 23.8 | Battery | 3-73-927 | 2024-02-23 | 2024-03-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [11 empty] | 12.28 | STA_721 Manomet
NSTAR | Needham | ESMAEX-03469 | 02492 | 22.8 | Solar | 148-02 | 2024-02-22 | 2024-03-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-26 | Online | [12 empty] | STA_148 Needham
NSTAR | Winchester | ESMAEX-03466 | 01890 | 17.6 | Solar & Battery | 211-H6 | 2024-02-20 | 2024-03-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [12 empty] | STA_211 Woburn
NSTAR | Mattapan | ESMAEX-03465 | 02126 | 7.6 | Solar | 311-02 | 2024-02-20 | 2024-03-04 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [11 empty] | 7.6 | STA_496 Hyde Park
NSTAR | Walpole | ESMAEX-03497 | 02081 | 3.8 | Solar | 2601 | 2024-02-29 | 2024-03-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Online | [11 empty] | 3.8 | STA_146 Walpole
NSTAR | Westwood | ESMAEX-03477 | 02090 | 9.9 | Solar & Battery | 456-H1 | 2024-02-26 | 2024-04-03 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [12 empty] | STA_456 Dover
NSTAR | Lincoln | ESMAEX-03470 | 01773 | 23.7 | Solar | 320-H6 | 2024-02-22 | 2024-03-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Online | [11 empty] | 9.99 | STA_320 Lexington
NSTAR | Brookline | ESMAEX-03509 | 02445 | 24.9 | Solar & Battery | 350-H8 | 2024-03-05 | 2024-03-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Online | [11 empty] | 19.48 | STA_350 Colburn Street
NSTAR | Arlington | ESMAEX-03508 | 02474 | 10 | Battery | 211-H11 | 2024-03-05 | 2024-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online | [11 empty] | 11.34 | STA_211 Woburn
NSTAR | Dartmouth | ESMAEX-03486 | 02748 | 150 | Solar | 2-53-65 | 2024-02-28 | 2024-04-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [12 empty] | STA_611 Pine Street
NSTAR | Wayland | ESMAEX-03496 | 01778 | 10 | Solar & Battery | 278-H2 | 2024-02-29 | 2024-04-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-08 | Online | [11 empty] | 20 | STA_278 Saxonville
NSTAR | Needham | ESMAEX-03484 | 02492 | 15.2 | Solar | 148-H7 | 2024-02-28 | 2024-03-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [12 empty] | STA_148 Needham
NSTAR | Framingham | ESMAEX-03478 | 01701 | 21.6 | Solar | 455-H1 | 2024-02-26 | 2024-03-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-25 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [11 empty] | 20.88 | STA_455 West Framingham
NSTAR | Carlisle | ESMAEX-03480 | 01741 | 3 | Solar | 533-H8 | 2024-02-27 | 2024-03-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Acusnet | ESMAEX-03479 | 02743 | 15.2 | Solar | 2-241-241 | 2024-02-27 | 2024-03-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Framingham | ESMAEX-03494 | 01701 | 16 | Solar | 455-H1 | 2024-02-29 | 2024-03-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [11 empty] | 16 | STA_455 West Framingham
NSTAR | Dover | ESMAEX-03491 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2024-02-29 | 2024-03-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [11 empty] | 19.8 | STA_456 Dover
NSTAR | Medway | ESMAEX-03487 | 02053 | 109 | Solar | 65-H3 | 2024-02-28 | 2024-04-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Online | [12 empty] | STA_065 Medway
NSTAR | Dorchester | ESMAEX-03535 | 02122 | 250 | Solar | 43-1490H3 | 2024-03-13 | 2024-04-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-14 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_483 Dewar Street
NSTAR | Sudbury | ESMAEX-03500 | 01776 | 800 | Solar | 342-H2 | 2024-03-01 | 2024-03-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 800 | STA_342 Sudbury
NSTAR | Arlington | ESMAEX-03505 | 02476 | 360 | Solar | 320-H7 | 2024-04-19 | 2024-05-20 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Dorchester | ESMAEX-03518 | 02121 | 22.8 | Solar | 483-H5 | 2024-03-08 | 2024-03-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online | [11 empty] | 20 | STA_483 Dewar Street
NSTAR | Newton Center | ESMAEX-03515 | 02459 | 10 | Solar & Battery | 292-H11 | 2024-03-07 | 2024-03-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Duxbury | ESMAEX-03525 | 02332 | 166 | Solar | 3-24B-24B | 2024-06-04 | 2024-07-12 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_738 Duxbury
NSTAR | Sharon | ESMAEX-03527 | 02067 | 487.5 | Solar | 470-H3 | 2024-03-11 | 2024-03-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Newton Center | ESMAEX-03529 | 02459 | 10 | Solar | 292-H5 | 2024-03-11 | 2024-03-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-10-11 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Westwood | ESMAEX-03538 | 02090 | 25 | Battery | 456-H1 | 2024-03-14 | 2024-04-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-28 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online | [12 empty] | STA_456 Dover
NSTAR | Bellingham | ESMAEX-03534 | 02019 | 15.2 | Solar | 65-H4 | 2024-03-13 | 2024-03-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [12 empty] | STA_065 Medway
NSTAR | North Cambridge | ESMAEX-03668 | 02140 | 108 | Solar | 828-1378 | 2024-04-15 | 2024-06-05 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 0 | STA_828 Alewife
NSTAR | Dorchester | ESMAEX-03542 | 02124 | 60 | Solar | 496-H8 | 2024-03-15 | 2024-04-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-03616 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03615 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03614 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Roslindale | ESMAEX-03543 | 02131 | 60 | Solar | 1312 | 2024-03-15 | 2024-04-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Brighton | ESMAEX-03559 | 02135 | 133.2 | Solar | 329-H6 | 2024-03-21 | 2024-05-06 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [12 empty] | STA_329 Brighton
NSTAR | Provincetown | ESMAEX-03685 | 02657 | 50 | Battery | 4-675-675 | 2024-04-18 | 2024-05-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-05 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [11 empty] | 0 | STA_976 Wellfleet
NSTAR | Canton | ESMAEX-03680 | 02021 | 15.2 | Solar & Battery | 269-1320H1 | 2024-04-17 | 2024-05-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [12 empty] | STA_470 Canton
NSTAR | Burlington | ESMAEX-03613 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Bourne | ESMAEX-03619 | 02562 | 27.3 | Solar | 3-89-925 | 2024-04-02 | 2024-05-06 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-06 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Burlington | ESMAEX-03610 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03609 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Westwood | ESMAEX-03549 | 02090 | 3.9 | Solar | 456-H4 | 2024-03-19 | 2024-04-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Online | [12 empty] | STA_456 Dover
NSTAR | Woburn | ESMAEX-03552 | 01801 | 48.38 | Solar | 375-H9 | 2024-03-19 | 2024-05-01 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Brookline | ESMAEX-03564 | 02446 | 29.58 | Solar | 329-H8 | 2024-03-21 | 2024-04-01 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Online | [12 empty] | STA_329 Brighton
NSTAR | Hatchville | ESMAEX-03554 | 02536 | 7.6 | Solar & Battery | 4-98A-98A | 2024-03-20 | 2024-03-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-26 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Burlington | ESMAEX-03606 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-07 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03605 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Orleans | ESMAEX-03556 | 02653 | 204.96 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
NSTAR | Orleans | ESMAEX-03558 | 02653 | 249.9 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 250 | STA_975 Orleans
NSTAR | Wareham | ESMAEX-03560 | 02571 | 3 | Solar & Battery | 3-84-12J1 | 2024-03-21 | 2024-04-01 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-06 | Online
NSTAR | Millis | ESMAEX-03621 | 02054 | 20.2 | Solar | 65-H1 | 2024-04-03 | 2024-05-29 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Online | [11 empty] | 20 | STA_065 Medway
NSTAR | West Roxbury | ESMAEX-04120 | 02132 | 240 | Solar | 468-06 | 2024-09-27 | 2024-10-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | Needham | ESMAEX-03575 | 02492 | 18.048 | Solar | 148-06 | 2024-03-26 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-13 | Online | [12 empty] | STA_148 Needham
NSTAR | Jamaica Plain | ESMAEX-04119 | 02130 | 120 | Solar | 350-H2 | 2024-09-27 | 2024-10-16 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | South Wellfleet | ESMAEX-03774 | 02663 | 22.11 | Solar | 4-94B-656 | 2024-05-16 | 2024-06-17 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-13 | Technical Review | [12 empty] | STA_976 Wellfleet
NSTAR | Newton Lower Falls | ESMAEX-03674 | 02462 | 20 | Solar | 292-H2 | 2024-04-16 | 2024-05-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-18 | [7 empty] | 0 |  | 0 |  |  | 2025-01-03 | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Chatham | ESMAEX-03577 | 02633 | 15.36 | Battery | 4-95B-95B | 2024-03-26 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-22 | Online | [12 empty] | STA_975 Orleans
NSTAR | Chelsea | ESMAEX-03683 | 02150 | 67.3 | Solar | 14-113H2 | 2024-04-18 | 2024-05-23 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Framingham | ESMAEX-03580 | 01701 | 7.6 | Solar | 455-H1 | 2024-03-26 | 2024-04-25 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [11 empty] | 7.6 | STA_455 West Framingham
NSTAR | West Newton | ESMAEX-03649 | 02465 | 60 | Solar | 292-H7 | 2024-04-09 | 2024-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Medway | ESMAEX-03582 | 02053 | 15.2 | Solar | 65-H3 | 2024-03-27 | 2024-04-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [12 empty] | STA_065 Medway
NSTAR | Chatham | ESMAEX-03642 | 02633 | 150 | Solar | 4-95B-95B | 2024-04-09 | 2024-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_975 Orleans
NSTAR | Barnstable | ESMAEX-03860 | 02630 | 23.52 | Solar | 4-84A-84A | 2024-06-25 | 2024-09-05 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [8 empty] | Cape |  |  | 18.62 | STA_920 Oak Street
NSTAR | Waltham | ESMAEX-03594 | 02453 | 2000 | Battery | 386-1366 | 2024-05-22 | 2024-06-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_282 Waltham
NSTAR | Waltham | ESMAEX-03593 | 02453 | 1500 | Battery | 386-1356 | 2024-05-22 | 2024-06-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_282 Waltham
NSTAR | Eastham | ESMAEX-03679 | 02642 | 15.2 | Solar & Battery | 4-94A-94A | 2024-04-17 | 2024-06-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-28 | Online | [12 empty] | STA_975 Orleans
NSTAR | Weston | ESMAEX-03592 | 02493 | 15.2 | Solar | 282-H1 | 2024-03-29 | 2024-04-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [11 empty] | 15.2 | STA_282 Waltham
NSTAR | Plympton | ESMAEX-03629 | 02367 | 4999 | Solar & Battery | 3-51-51 | 2024-04-04 | 2024-04-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_727 Brook Street
NSTAR | Kingston | ESMAEX-03636 | 02364 | 4999 | Solar & Battery | 3-50-50 | 2024-04-05 | 2024-04-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_727 Brook Street
NSTAR | Winchester | ESMAEX-03628 | 01890 | 23 | Solar & Battery | 211-H6 | 2024-04-04 | 2024-05-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Online | [11 empty] | 10 | STA_211 Woburn
NSTAR | Natick | ESMAEX-03622 | 01760 | 3.8 | Solar | 433-H5 | 2024-04-03 | 2024-04-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [11 empty] | 3.8 | STA_433 Speen Street
NSTAR | East Harwich | ESMAEX-03623 | 02645 | 17.6 | Solar & Battery | 4-89B-576 | 2024-04-03 | 2024-04-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [12 empty] | STA_975 Orleans
NSTAR | Framingham | ESMAEX-03627 | 01701 | 9.735 | Solar & Battery | 455-H1 | 2024-04-03 | 2024-04-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Needham | ESMAEX-03639 | 02494 | 24.96 | Solar | 292-H4 | 2024-04-08 | 2024-05-08 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [11 empty] | 19.99 | STA_292 Newton Highlands
NSTAR | Norfolk | ESMAEX-03633 | 02056 | 19 | Solar | 146-H9 | 2024-04-05 | 2024-04-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [12 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-03645 | 01720 | 17.28 | Solar | 416-H8 | 2024-04-09 | 2024-05-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [12 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-03673 | 02420 | 20 | Solar & Battery | 211-H10 | 2024-04-16 | 2024-06-05 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Technical Review | [11 empty] | 20 | STA_211 Woburn
NSTAR | Framingham | ESMAEX-03641 | 01701 | 15.2 | Solar | 342-H9 | 2024-04-08 | 2024-04-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online | [11 empty] | 15.2 | STA_342 Sudbury
NSTAR | Roslindale | ESMAEX-03646 | 02131 | 6.9 | Solar | 496-H5 | 2024-04-09 | 2024-04-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-20 | Technical Review | [12 empty] | STA_496 Hyde Park
NSTAR | Marshfield | ESMAEX-03643 | 02050 | 3.8 | Solar | 3-27-970 | 2024-04-09 | 2024-04-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [12 empty] | STA_738 Duxbury
NSTAR | Brookline | ESMAEX-03651 | 02446 | 34.6 | Solar | 329-H10 | 2024-04-10 | 2024-04-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Online | [12 empty] | STA_329 Brighton
NSTAR | Waltham | ESMAEX-03687 | 02453 | 110 | Solar | 33-H2 | 2024-04-18 | 2024-05-23 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Bedford | ESMAEX-03656 | 01730 | 15.2 | Solar & Battery | 533-H3 | 2024-04-11 | 2024-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Carlisle | ESMAEX-03660 | 01741 | 10 | Battery | 533-H8 | 2024-07-25 | 2024-07-25 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [11 empty] | 10 | STA_533 Hartwell Avenue
NSTAR | Chestnut Hill | ESMAEX-03658 | 02467 | 19.86 | Solar & Battery | 1706 | 2024-04-11 | 2024-05-20 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-22 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | New Bedford | ESMAEX-03661 | 02746 | 3.8 | Solar | 2-85-130 | 2024-04-12 | 2024-05-17 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Online
NSTAR | Sharon | ESMAEX-03666 | 02067 | 17.58 | Solar & Battery | 146-H1 | 2024-04-15 | 2024-05-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [11 empty] | 11.45 | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03885 | 02139 | 40 | Solar & Battery | 817-01 | 2024-07-08 | 2024-07-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_831 Putnam
NSTAR | Dover | ESMAEX-03692 | 02030 | 67.3 | Solar | 456-H2 | 2024-04-22 | 2024-05-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-25 | Online | [12 empty] | STA_456 Dover
NSTAR | Boston | ESMAEX-03677 | 02119 | 27.3 | Solar | 510-77H3 | 2024-04-17 | 2024-06-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Online | [12 empty] | STA_106 Andrew Square
NSTAR | Waltham | ESMAEX-03734 | 02451 | 180 | Solar | 450-H2 | 2024-05-03 | 2024-05-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-28 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Somerville | ESMAEX-03749 | 02144 | 100 | Solar | 59-1471 | 2024-05-10 | 2024-06-20 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_828 Alewife
NSTAR | Bellingham | ESMAEX-03684 | 02019 | 17.6 | Solar | 65-H4 | 2024-04-18 | 2024-05-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [12 empty] | STA_065 Medway
NSTAR | Sharon | ESMAEX-03688 | 02067 | 15.2 | Solar | 146-H7 | 2024-04-19 | 2024-05-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Online | [12 empty] | STA_146 Walpole
NSTAR | Bellingham | ESMAEX-03689 | 02019 | 20 | Solar | 65-H4 | 2024-04-19 | 2024-08-07 | 78 |  | 78 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Technical Review | [12 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-03690 | 01773 | 20 | Battery | 320-H6 | 2024-04-19 | 2024-05-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [11 empty] | 20 | STA_320 Lexington
NSTAR | Watertown | ESMAEX-03714 | 02472 | 120 | Solar | 370-1327 | 2024-07-10 | 2024-08-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Acton | ESMAEX-03717 | 01720 | 0 | Battery | 416-H1 | 2024-04-29 | 2024-05-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Arlington | ESMAEX-03703 | 02476 | 8.68 | Battery | 211-H14 | 2024-04-23 | 2024-05-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [11 empty] | 8.68 | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-03702 | 02138 | 23 | Solar & Battery | 823-30 | 2024-04-23 | 2024-05-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [12 empty] | STA_828 Alewife
NSTAR | Lexington | ESMAEX-03705 | 02421 | 7.68 | Battery | 3409 | 2024-04-23 | 2024-05-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [11 empty] | 7.68
NSTAR | Canton | ESMAEX-03791 | 02021 | 11.5 | Solar & Battery | 269-1320H1 | 2024-05-28 | 2024-07-12 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Online | [12 empty] | STA_470 Canton
NSTAR | Brookline | ESMAEX-03719 | 02446 | 300 | Fuel Cell | 329-H8 | 2024-04-30 | 2024-05-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_329 Brighton
NSTAR | Framingham | ESMAEX-03706 | 01701 | 7.6 | Solar | 433-H8 | 2024-04-23 | 2024-05-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [11 empty] | 7.6 | STA_433 Speen Street
NSTAR | Bedford | ESMAEX-03852 | 01730 | 20 | Solar & Battery | 533-H7 | 2024-06-24 | 2024-07-24 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Chatham | ESMAEX-03710 | 02633 | 36.9 | Solar & Battery | 4-95A-608 | 2024-04-24 | 2024-06-06 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-13 | Online | [8 empty] | Cape |  |  | 19 | STA_968 Harwich
NSTAR | Milton | ESMAEX-03724 | 02186 | 240 | Solar | 496-H2 | 2024-05-01 | 2024-06-20 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Milton | ESMAEX-03736 | 02186 | 240 | Solar | 60-1409H1 | 2024-05-06 | 2024-05-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-03716 | 01803 | 6.4 | Solar & Battery | 375-H6 | 2024-04-29 | 2024-05-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [11 empty] | 6.4 | STA_375 Dragon Court
NSTAR | Milton | ESMAEX-03735 | 02186 | 150 | Solar |  | 2024-05-06 | 2024-06-12 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Acton | ESMAEX-03776 | 01720 | 19 | Solar | 416-H5 | 2024-05-16 | 2024-06-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-03 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online | [12 empty] | STA_416 Maynard
NSTAR | Acton | ESMAEX-03721 | 01720 | 7.6 | Solar | 416-H4 | 2024-05-01 | 2024-05-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Online | [11 empty] | 7.6 | STA_416 Maynard
NSTAR | Charlestown | ESMAEX-03722 | 02129 | 280 | Internal Combustion Engine | 225-184 | 2024-10-16 | 2024-11-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-24 | Online | [11 empty] | 0 | STA_250 Mystic
NSTAR | Framingham | ESMAEX-04059 | 01702 | 100 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-04058 | 01702 | 150 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-04057 | 01702 | 150 | Solar | 455-H4 | 2024-09-13 | 2024-11-26 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Chestnut Hill | ESMAEX-03777 | 02467 | 18.12 | Solar & Battery | 350-H7 | 2024-05-17 | 2024-06-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Carver | ESMAEX-03758 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-13 | 2024-06-13 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_737 West Pond
NSTAR | Carver | ESMAEX-03767 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-15 | 2024-05-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_737 West Pond
NSTAR | Acton | ESMAEX-03785 | 01720 | 7.6 | Solar | 416-H8 | 2024-10-17 | 2024-06-21 | -86 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Online | [11 empty] | 17.6 | STA_416 Maynard
NSTAR | Burlington | ESMAEX-03765 | 01805 | 4998 | Battery | 541-1377H | 2024-07-16 | 2024-08-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [11 empty] | 4998 | STA_391 Burlington
NSTAR | Cambridge | ESMAEX-03813 | 02138 | 24.96 | Solar | 824-27 | 2024-06-05 | 2024-06-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [12 empty] | STA_828 Alewife
NSTAR | Weston | ESMAEX-03741 | 02493 | 17.99 | Solar | 282-H8 | 2024-05-08 | 2024-06-06 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Technical Review | [12 empty] | STA_282 Waltham
NSTAR | Falmouth | ESMAEX-03752 | 02540 | 120 | Solar | 4-98A-98A | 2024-05-13 | 2024-07-24 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Acton | ESMAEX-03781 | 01720 | 22.34 | Solar & Battery | 416-H5 | 2024-05-21 | 2024-06-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [11 empty] | 12.4 | STA_416 Maynard
NSTAR | North Dartmouth | ESMAEX-03845 | 02747 | 17.6 | Solar & Battery | 2-531-531 | 2024-06-17 | 2024-07-05 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Stoneham | ESMAEX-03759 | 02180 | 8.77 | Battery | 211-H12 | 2024-05-14 | 2024-06-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Online | [11 empty] | 8.77 | STA_211 Woburn
NSTAR | Provincetown | ESMAEX-03816 | 02657 | 11.6 | Battery | 4-675-675 | 2024-06-05 | 2024-06-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [11 empty] | 10 | STA_976 Wellfleet
NSTAR | Hopkinton | ESMAEX-03773 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-05-16 | 2024-06-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [11 empty] | 20 | STA_126 Hopkinton
NSTAR | Chelsea | ESMAEX-03762 | 02150 | 490 | Solar | 488-H7 | 2024-07-23 | 2024-08-16 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Jamaica Plain | ESMAEX-03783 | 02130 | 20 | Solar | 284-01 | 2024-05-21 | 2024-06-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Online | [12 empty] | STA_350 Colburn Street
NSTAR | Boston | ESMAEX-03847 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [12 empty] | STA_385D K Street
NSTAR | Stoneham | ESMAEX-03792 | 02180 | 13.92 | Solar | 375-H2 | 2024-05-28 | 2024-12-27 | 153 |  | 153 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 13.92 | STA_375 Dragon Court
NSTAR | Sudbury | ESMAEX-03789 | 01776 | 20 | Solar | 342-H2 | 2024-05-23 | 2024-06-19 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Milton | ESMAEX-03796 | 02186 | 23 | Solar & Battery | 362-1207H1 | 2024-05-28 | 2024-06-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Online | [11 empty] | 19.92
NSTAR | Vineyard Haven | ESMAEX-03788 | 02568 | 16.8 | Solar | 4-75-75 | 2024-05-23 | 2024-06-06 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-28 | [7 empty] | 0 |  | 0 |  |  | 2025-04-04 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Waltham | ESMAEX-03794 | 02452 | 16.72 | Battery | 450-H6 | 2024-05-28 | 2024-06-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [12 empty] | STA_450 Trapelo Road
NSTAR | Millis | ESMAEX-03790 | 02054 | 20 | Solar | 130-H2 | 2024-05-24 | 2024-06-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [11 empty] | 20 | STA_130 Holliston
NSTAR | Framingham | ESMAEX-03799 | 01701 | 46.08 | Solar | 455-H1 | 2024-05-29 | 2024-06-20 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [11 empty] | 20 | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-03795 | 02744 | 480 | Solar | 2-69-69 | 2024-06-19 | 2024-07-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Walpole | ESMAEX-03797 | 02081 | 20 | Solar | 146-H2 | 2024-05-29 | 2024-06-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online | [12 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-03801 | 02492 | 36.52 | Solar & Battery | 148-H2 | 2024-05-29 | 2024-10-16 | 100 |  | 100 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-12 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Online | [11 empty] | 20 | STA_148 Needham
NSTAR | Woburn | ESMAEX-03803 | 01801 | 10 | Solar | 375-H14 | 2024-05-29 | 2024-06-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-29 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Eastham | ESMAEX-03807 | 02642 | 249.6 | Solar | 4-94B-647 | 2024-05-31 | 2024-06-28 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_976 Wellfleet
NSTAR | Boston | ESMAEX-03848 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [12 empty] | STA_385D K Street
NSTAR | Carlisle | ESMAEX-03810 | 01741 | 11.515 | Solar & Battery | 533-H8 | 2024-06-04 | 2024-07-05 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-03-14 | Online | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | East Boston | ESMAEX-03814 | 02128 | 100 | Solar | 108-195H1 | 2024-06-05 | 2024-07-10 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-03826 | 01760 | 120 | Solar | 339-1345H | 2024-12-03 | 2025-01-22 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03863 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03864 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03865 | 01760 | 150 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Sherborn | ESMAEX-03818 | 01770 | 18.88 | Solar | 274-H2 | 2024-06-06 | 2024-06-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Walpole | ESMAEX-03815 | 01776 | 486.6 | Solar | 146-H1 | 2024-08-22 | 2024-09-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Hyannis | ESMAEX-03844 | 02601 | 100 | Solar | 4-84A-84A | 2024-06-14 | 2024-07-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Arlington | ESMAEX-03823 | 02476 | 15.2 | Solar | 211-H14 | 2024-06-11 | 2024-06-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Online | [12 empty] | STA_211 Woburn
NSTAR | Medway | ESMAEX-03873 | 02053 | 5 | Solar & Battery | 65-H5 | 2024-07-01 | 2024-07-31 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [11 empty] | 5 | STA_065 Medway
NSTAR | Chelsea | ESMAEX-03825 | 02150 | 34.6 | Solar | 488-H2 | 2024-06-11 | 2024-07-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Winchester | ESMAEX-03840 | 01890 | 20 | Battery | 211-H7XY | 2024-06-14 | 2024-07-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-15 | Online | [11 empty] | 20 | STA_211 Woburn
NSTAR | Framingham | ESMAEX-03856 | 01702 | 100 | Solar | 2410 | 2024-06-24 | 2024-07-24 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-26 | [7 empty] | 0 |  | 0 |  |  | 2025-07-16 | Online | [12 empty] | STA_240 Framingham
NSTAR | Canton | ESMAEX-03850 | 02021 | 15.2 | Solar | 470-H4 | 2024-06-19 | 2024-07-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Online | [12 empty] | STA_470 Canton
NSTAR | Marshfield | ESMAEX-03851 | 02050 | 150 | Solar | 3-24A-24A | 2024-06-21 | 2024-07-31 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_739 Marshfield
NSTAR | Ashland | ESMAEX-03859 | 01721 | 15.2 | Solar | 455-H3 | 2024-06-25 | 2024-07-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-03900 | 02421 | 9624.5 | Solar & Battery | 244-1362 | 2024-07-16 | 2024-08-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4812.5 | STA_450 Trapelo Road
NSTAR | Medfield | ESMAEX-03858 | 02052 | 22.8 | Solar | 456-H3 | 2024-06-24 | 2024-07-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-21 | Online | [12 empty] | STA_456 Dover
NSTAR | Stoneham | ESMAEX-03868 | 02180 | 15.59 | Battery | 375-H2 | 2024-06-27 | 2024-07-31 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Online | [11 empty] | 15.59 | STA_375 Dragon Court
NSTAR | Sudbury | ESMAEX-03874 | 01776 | 20.46 | Solar | 342-H4 | 2024-07-01 | 2024-07-31 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [12 empty] | STA_342 Sudbury
NSTAR | East Boston | ESMAEX-04153 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04152 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04151 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Sudbury | ESMAEX-03889 | 01776 | 50 | Solar | 342-H5 | 2024-07-10 | 2024-08-09 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Stoneham | ESMAEX-03882 | 02180 | 5.7 | Solar | 375-H8 | 2024-07-02 | 2024-07-31 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Online | [11 empty] | 20 | STA_375 Dragon Court
NSTAR | Canton | ESMAEX-03887 | 02021 | 120 | Solar | 470-H7 | 2024-07-09 | 2024-07-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-28 | Online | [12 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-03886 | 01754 | 7.68 | Solar & Battery | 416-H6 | 2024-07-08 | 2024-08-07 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [12 empty] | STA_416 Maynard
NSTAR | Sherborn | ESMAEX-03940 | 01770 | 15 | Solar | 240-H1 | 2024-07-31 | 2024-08-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-10 | Online | [11 empty] | 9.9 | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03986 | 02421 | 100 | Solar | 320-H5XY | 2024-08-22 | 2024-10-09 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Westwood | ESMAEX-04028 | 02090 | 20 | Battery | 148-H3 | 2024-09-04 | 2024-10-02 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_148 Needham
NSTAR | Acton | ESMAEX-03911 | 01720 | 17.28 | Solar | 416-H5 | 2024-07-18 | 2024-09-18 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Online | [12 empty] | STA_416 Maynard
NSTAR | Walpole | ESMAEX-03903 | 02081 | 300 | Solar | 146-H4 | 2024-11-22 | 2025-01-08 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Brookline | ESMAEX-03908 | 02446 | 20 | Battery | 506-07 | 2024-07-17 | 2024-08-22 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_329 Brighton
NSTAR | Stoneham | ESMAEX-03909 | 02180 | 10.62 | Solar & Battery | 375-H12 | 2024-07-17 | 2024-08-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [11 empty] | 10.62 | STA_375 Dragon Court
NSTAR | Hopkinton | ESMAEX-03926 | 01748 | 16.8 | Solar | 126-H4 | 2024-07-26 | 2024-08-09 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-08 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Hopkinton | ESMAEX-03910 | 01748 | 7.6 | Solar | 126-H2 | 2024-07-18 | 2024-08-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-04 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Assonett | ESMAEX-03917 | 02702 | 15.2 | Solar | 2-605-605 | 2024-07-22 | 2024-08-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Online | [12 empty] | STA_661 Bell Rock
NSTAR | Carlisle | ESMAEX-03927 | 01741 | 19.99 | Solar | 512-1399H1 | 2024-07-26 | 2024-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online | [11 empty] | 19.99 | STA_533 Hartwell Avenue
NSTAR | Hyannis | ESMAEX-04053 | 02601 | 150 | Solar | 4-63-63 | 2024-09-12 | 2024-12-06 | 61 |  | 61 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Woburn | ESMAEX-03923 | 01801 | 9.98 | Solar & Battery | 211-H5 | 2024-07-24 | 2024-08-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Online | [12 empty] | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-03958 | 01748 | 11.5 | Solar & Battery | 455-H8 | 2024-08-09 | 2024-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_455 West Framingham
NSTAR | Natick | ESMAEX-03959 | 01760 | 8.95 | Solar | 240-H5 | 2024-08-09 | 2024-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Online | [11 empty] | 8.95 | STA_240 Framingham
NSTAR | Hyde Park | ESMAEX-03944 | 02136 | 15.2 | Solar | 496-H7 | 2024-08-02 | 2024-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-03935 | 01760 | 20 | Solar & Battery | 433-H12 | 2024-07-30 | 2024-08-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Online | [11 empty] | 20 | STA_433 Speen Street
NSTAR | Newton Center | ESMAEX-03988 | 02459 | 50 | Solar | 292-H11 | 2024-08-22 | 2024-10-10 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 50 | STA_292 Newton Highlands
NSTAR | Newtonville | ESMAEX-03934 | 02460 | 31.2 | Solar & Battery | 1705 | 2024-07-30 | 2024-08-13 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_292 Newton Highlands
NSTAR | Bedford | ESMAEX-03946 | 01730 | 19.9 | Battery | 533-H3 | 2024-08-02 | 2024-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [11 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-03943 | 01701 | 20 | Solar | 455-H1 | 2024-08-02 | 2024-08-14 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [12 empty] | STA_455 West Framingham
NSTAR | Milton | ESMAEX-03969 | 02186 | 51.456 | Solar | 362-1209H2 | 2024-08-14 | 2024-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Somerville | ESMAEX-03945 | 02145 | 27.3 | Solar | 250-1N81H1 | 2024-08-02 | 2024-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Online | [12 empty] | STA_250 Mystic
NSTAR | Newtonville | ESMAEX-03948 | 02460 | 20 | Solar & Battery | 467-H5 | 2024-08-07 | 2024-08-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_467 Watertown
NSTAR | Natick | ESMAEX-03947 | 01760 | 17.202 | Solar | 23-H1 | 2024-08-06 | 2024-08-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Online | [12 empty] | STA_240 Framingham
NSTAR | Newton | ESMAEX-03974 | 02458 | 10 | Battery | 277-05 | 2024-08-15 | 2024-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Online | [12 empty] | STA_467 Watertown
NSTAR | Winchester | ESMAEX-03949 | 01890 | 20 | Solar & Battery | 211-H7XY | 2024-08-08 | 2024-08-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-02 | Online | [11 empty] | 20 | STA_211 Woburn
NSTAR | Sharon | ESMAEX-03955 | 02067 | 12.4 | Battery | 146-H1 | 2024-08-08 | 2024-08-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Online | [11 empty] | 12.4 | STA_146 Walpole
NSTAR | Lexington | ESMAEX-03979 | 02421 | 250 | Fuel Cell | 34-1385 | 2024-08-19 | 2024-09-18 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-03965 | 01760 | 10.1 | Battery | 240-H1 | 2024-08-14 | 2024-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [11 empty] | 10.1 | STA_240 Framingham
NSTAR | Acton | ESMAEX-03991 | 01720 | 5 | Battery | 416-H8 | 2024-08-23 | 2024-10-02 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [12 empty] | STA_416 Maynard
NSTAR | Arlington | ESMAEX-03976 | 02476 | 15.2 | Solar | 320-H7 | 2024-08-16 | 2024-10-09 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 8.16 | STA_320 Lexington
NSTAR | Plymouth | ESMAEX-04000 | 02360 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 3997.8 | STA_737 West Pond
NSTAR | Natick | ESMAEX-03996 | 01760 | 20 | Battery | 240-H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Online | [11 empty] | 20 | STA_240 Framingham
NSTAR | Woburn | ESMAEX-03995 | 01801 | 20 | Solar & Battery | 533-H9 | 2024-08-23 | 2024-09-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Online | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Newton | ESMAEX-03980 | 02135 | 130 | Solar | 467-H3 | 2024-08-20 | 2024-10-25 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Oak Bluffs | ESMAEX-04133 | 02557 | 15.2 | Solar | 4-99-99 | 2024-10-01 | 2024-11-26 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-28 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Construction Stage | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Carver | ESMAEX-03999 | 02330 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 3997.8 | STA_737 West Pond
NSTAR | Roxbury | ESMAEX-03992 | 02119 | 120 | Solar | 465-129H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Acton | ESMAEX-03993 | 01720 | 10 | Battery | 416-H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online | [11 empty] | 0 | STA_416 Maynard
NSTAR | Dorchester | ESMAEX-03997 | 02122 | 300 | Solar | 466-1481H1 | 2024-09-30 | 2024-10-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Boston | ESMAEX-03998 | 02130 | 280 | Solar | 396-01 | 2024-09-27 | 2024-10-16 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_396 Amory Street
NSTAR | Carlisle | ESMAEX-04022 | 01741 | 18.88 | Solar | 512-1399H1 | 2024-08-30 | 2024-10-02 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-08 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Waltham | ESMAEX-04003 | 02451 | 14.2 | Battery | 450-H4 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-18 | Online | [11 empty] | 14.2 | STA_450 Trapelo Road
NSTAR | Sharon | ESMAEX-04004 | 02067 | 10 | Battery | 146-H1 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [11 empty] | 10 | STA_146 Walpole
NSTAR | Roxbury | ESMAEX-04037 | 02120 | 130 | Solar | 5210 | 2024-09-05 | 2024-10-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Canton | ESMAEX-04007 | 02021 | 990 | Solar | 269-1321H2 | 2024-09-24 | 2024-10-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 990 | STA_470 Canton
NSTAR | Carlisle | ESMAEX-04091 | 01741 | 21.888 | Solar | 512-1399H1 | 2024-09-24 | 2024-10-08 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-04009 | 02021 | 320 | Solar | 470-H10 | 2024-09-23 | 2024-11-13 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | West Roxbury | ESMAEX-04011 | 02132 | 17.6 | Solar & Battery | 496-H6 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Chelsea | ESMAEX-04010 | 02150 | 150 | Solar | 488-H2 | 2024-09-24 | 2024-11-04 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Cotuit | ESMAEX-04012 | 02635 | 15.2 | Solar & Battery | 4-88-880 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Cambridge | ESMAEX-04017 | 02139 | 50 | Solar | 814-12 | 2024-08-29 | 2025-01-13 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-27 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_402 Newton Street
NSTAR | Brewster | ESMAEX-04019 | 02631 | 17.4 | Solar | 4-89B-573 | 2024-08-30 | 2024-10-02 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
NSTAR | Eastham | ESMAEX-04020 | 02642 | 11.5 | Battery | 4-94A-94A | 2024-08-30 | 2024-09-23 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Online | [12 empty] | STA_975 Orleans
NSTAR | Dorchester | ESMAEX-04040 | 02124 | 220 | Solar | 466-1481H | 2024-09-06 | 2024-10-03 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Lexington | ESMAEX-04027 | 02421 | 27.3 | Solar | 533-H2 | 2024-09-04 | 2024-10-02 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-10-17 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Sherborn | ESMAEX-04034 | 01770 | 16.104 | Solar | 240-H1 | 2024-09-05 | 2024-10-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [12 empty] | STA_240 Framingham
NSTAR | Norfolk | ESMAEX-04031 | 02056 | 37 | Solar & Battery | 146-H10 | 2024-09-05 | 2024-11-13 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_146 Walpole
NSTAR | Westport | ESMAEX-04049 | 02790 | 25.242 | Solar & Battery | 2-523-523 | 2024-09-11 | 2024-10-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-27 | Online | [8 empty] | Dartmouth-Westport |  |  | 20 | STA_657 Fisher Road
NSTAR | Waltham | ESMAEX-04050 | 02451 | 140 | Solar | 282-H2 | 2024-09-11 | 2024-10-31 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-25 | Online | [12 empty] | STA_282 Waltham
NSTAR | West Barnstable | ESMAEX-04110 | 02668 | 22.09 | Solar | 4-84A-84A | 2024-09-26 | 2024-10-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Online | [12 empty] | STA_920 Oak Street
NSTAR | Newton | ESMAEX-04045 | 02460 | 27.3 | Solar | 467-H3 | 2024-09-09 | 2024-09-23 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Harwich | ESMAEX-04046 | 02645 | 420 | Solar | 4-89B-89B | 2024-11-14 | 2024-12-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
EMA | Carver | ESMAEX-04072 | 02330 | 4980 | Solar & Battery | 3-10-929 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04073 | 02330 | 4980 | Solar & Battery | 3-11-11 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Hold In Queue | 4980 | STA_737 West Pond
NSTAR | Framingham | ESMAEX-04048 | 01701 | 17.3 | Solar | 278-H1 | 2024-09-11 | 2024-09-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-16 | Online | [11 empty] | 3.8 | STA_278 Saxonville
NSTAR | Brookline | ESMAEX-04052 | 02445 | 7.67 | Solar & Battery | 315-H2 | 2024-09-11 | 2024-10-25 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [11 empty] | 20
NSTAR | Sudbury | ESMAEX-04055 | 01776 | 15.2 | Solar & Battery | 342-H7 | 2024-09-13 | 2024-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-22 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Westwood | ESMAEX-04051 | 02090 | 7.5 | Solar | 148-H3 | 2024-09-11 | 2024-10-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Online | [12 empty] | STA_148 Needham
NSTAR | Watertown | ESMAEX-04116 | 02472 | 372 | Solar | 370-1327 | 2024-09-27 | 2024-10-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-04070 | 01760 | 20 | Battery | 240-H6 | 2024-09-18 | 2024-10-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Online | [11 empty] | 20 | STA_240 Framingham
NSTAR | Wayland | ESMAEX-04080 | 01778 | 20 | Battery | 278-H2 | 2024-09-20 | 2024-10-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-03-13 | Online | [11 empty] | 20 | STA_278 Saxonville
NSTAR | Dover | ESMAEX-04060 | 02030 | 16.2 | Solar | 456-H5 | 2024-09-13 | 2024-10-21 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [12 empty] | STA_456 Dover
NSTAR | Kingston | ESMAEX-04062 | 02364 | 498 | Solar | 3-15-15 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_735 Kingston
NSTAR | Falmouth | ESMAEX-04064 | 02540 | 17.644 | Solar & Battery | 4-72-72 | 2024-09-17 | 2024-10-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Wayland | ESMAEX-04066 | 01778 | 11.5 | Battery | 433-H2 | 2024-09-17 | 2024-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Rochester | ESMAEX-04075 | 02770 | 4980 | Solar & Battery | 3-703-703 | 2024-09-19 | 2024-11-01 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven |  | Hold In Queue |  | STA_745 Rochester
NSTAR | Carver | ESMAEX-04076 | 02330 | 4980 | Solar & Battery | 3-81-81 | 2024-09-19 | 2024-10-17 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Hold In Queue | 4980 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04077 | 02330 | 996 | Solar & Battery | 3-81-81 | 2024-09-19 | 2024-10-25 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Plymouth |  | Phase 2 - In Process |  | STA_713 Tremont
NSTAR | Woburn | ESMAEX-04071 | 01801 | 15.744 | Solar | 325-03 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Online | [12 empty] | STA_211 Woburn
NSTAR | Lexington | ESMAEX-04078 | 02421 | 11.5 | Solar & Battery | 320-H2 | 2024-09-19 | 2024-10-02 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [11 empty] | 7.2 | STA_320 Lexington
NSTAR | Dorchester | ESMAEX-04124 | 02125 | 80 | Solar |  | 2024-09-30 | 2024-10-08 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Canton | ESMAEX-04111 | 02021 | 13.8 | Battery | 470-H10 | 2024-09-26 | 2024-10-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-03-12 | Online | [11 empty] | 13.8 | STA_470 Canton
NSTAR | Canton | ESMAEX-04079 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [11 empty] | 20 | STA_470 Canton
NSTAR | Boston | ESMAEX-04118 | 02124 | 150 | Solar | 4302 | 2024-09-27 | 2024-10-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Holliston | ESMAEX-04083 | 01746 | 23 | Solar & Battery | 65-H5 | 2024-09-20 | 2024-12-03 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [11 empty] | 20 | STA_065 Medway
NSTAR | Dover | ESMAEX-04137 | 02030 | 23 | Solar & Battery | 456-H3 | 2024-10-03 | 2024-10-15 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Technical Review | [11 empty] | 20 | STA_456 Dover
NSTAR | Burlington | ESMAEX-04102 | 01803 | 20 | Battery | 346-1395H1 | 2024-09-25 | 2024-10-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [11 empty] | 20 | STA_391 Burlington
NSTAR | Dover | ESMAEX-04089 | 02030 | 20.1 | Solar | 148-H3 | 2024-09-23 | 2024-10-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [12 empty] | STA_148 Needham
NSTAR | Vineyard Haven | ESMAEX-04135 | 02568 | 50 | Solar |  | 2024-10-03 | 2024-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Online | [8 empty] | Cape
NSTAR | North Dartmouth | ESMAEX-04101 | 02747 | 11.88 | Solar | 2-541-541 | 2024-09-24 | 2024-11-08 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  | 19.99 | STA_651 Cross Road
NSTAR | Westwood | ESMAEX-04092 | 02090 | 20 | Solar | 456-H1 | 2024-09-24 | 2024-10-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-12 | [7 empty] | 0 |  | 0 |  |  | 2025-10-15 | Online | [11 empty] | 20 | STA_456 Dover
NSTAR | Needham | ESMAEX-04117 | 02492 | 5 | Battery | 148-02 | 2024-09-27 | 2024-11-12 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-15 | Online | [12 empty] | STA_148 Needham
NSTAR | Watertown | ESMAEX-04125 | 02472 | 920 | Solar & Battery | 467-H4 | 2024-12-19 | 2025-07-16 | 149 |  | 149 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 920 | STA_467 Watertown
NSTAR | Bass River | ESMAEX-04123 | 02664 | 7.6 | Solar & Battery | 4-92A-92A | 2024-09-27 | 2024-10-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Online | [8 empty] | Cape |  |  | 7.6 | STA_961 Hyannis Junction
NSTAR | Kingston | ESMAEX-04140 | 02364 | 200 | Solar | 3-17-17 | 2024-10-04 | 2024-11-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_735 Kingston
NSTAR | Hopkinton | ESMAEX-04131 | 01748 | 7.65 | Battery | 126-H2 | 2024-10-01 | 2024-10-15 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-11 | Online | [11 empty] | 7.65 | STA_126 Hopkinton
NSTAR | Waltham | ESMAEX-04149 | 02451 | 13.3 | Solar | 282-H2 | 2024-10-07 | 2024-11-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online | [12 empty] | STA_282 Waltham
NSTAR | Auburndale | ESMAEX-04178 | 02466 | 24.06 | Solar & Battery | 292-H7 | 2024-10-17 | 2024-11-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [11 empty] | 20 | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-04134 | 02421 | 23.908 | Solar & Battery | 320-H2 | 2024-10-03 | 2024-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [12 empty] | STA_320 Lexington
NSTAR | East Boston | ESMAEX-04159 | 02128 | 30 | Solar | 488-H5 | 2024-10-09 | 2024-11-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Eastham | ESMAEX-04142 | 02642 | 11.5 | Battery | 4-94A-94A | 2024-10-04 | 2024-11-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [12 empty] | STA_975 Orleans
NSTAR | Rochester | ESMAEX-04186 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2024-10-17 | 2024-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Hold In Queue | 4980 | STA_713 Tremont
NSTAR | Sudbury | ESMAEX-04146 | 01776 | 25.73 | Solar & Battery | 342-H7 | 2024-10-07 | 2024-11-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Dorchester | ESMAEX-04355 | 02122 | 180 | Solar |  | 2024-12-10 | 2025-01-27 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online
NSTAR | Marstons Mills | ESMAEX-04284 | 02648 | 100 | Solar | 4-88-88 | 2024-11-18 |  | -32548 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Review | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Holliston | ESMAEX-04150 | 01746 | 14.98 | Solar | 65-H5 | 2024-10-08 | 2024-11-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online | [12 empty] | STA_065 Medway
NSTAR | Edgartown | ESMAEX-04154 | 02539 | 17.6 | Solar |  | 2024-10-08 | 2024-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [8 empty] | Cape
NSTAR | Chestnut Hill | ESMAEX-04158 | 02467 | 17.6 | Solar & Battery | 292-H6 | 2024-10-09 | 2024-11-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [11 empty] | 17.6 | STA_292 Newton Highlands
NSTAR | Allston | ESMAEX-04308 | 02134 | 80 | Solar | 144-138 | 2024-11-26 | 2024-12-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_329 Brighton
NSTAR | Weston | ESMAEX-04204 | 02493 | 19.99 | Solar | 282-H1 | 2024-10-25 | 2024-11-01 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-10-17 | Online | [11 empty] | 19.99 | STA_282 Waltham
NSTAR | Carver | ESMAEX-04185 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-17 | 2024-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_737 West Pond
NSTAR | Bedford | ESMAEX-04160 | 01730 | 49.7 | Solar | 533-H8 | 2024-10-10 | 2024-11-13 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-08-13 | Online | [11 empty] | 49.7 | STA_533 Hartwell Avenue
NSTAR | Roslindale | ESMAEX-04167 | 02131 | 11.5 | Battery | 496-H5 | 2024-10-11 | 2024-11-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Bedford | ESMAEX-04161 | 01730 | 82.9 | Solar |  | 2024-10-10 | 2024-11-13 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-29 | Online
NSTAR | Cambridge | ESMAEX-04195 | 02139 | 19.72 | Solar | 814-12 | 2024-10-18 | 2024-11-26 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_402 Newton Street
NSTAR | Acton | ESMAEX-04207 | 01720 | 15.2 | Solar | 416-H4 | 2024-10-25 | 2024-11-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-02 | Online | [12 empty] | STA_416 Maynard
NSTAR | Milton | ESMAEX-04175 | 02186 | 498 | Solar | 362-1209H2 | 2024-12-20 | 2025-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 498 | STA_496 Hyde Park
NSTAR | Sharon | ESMAEX-04170 | 02067 | 10 | Battery | 146-H7 | 2024-10-14 | 2024-11-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [12 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-04171 | 02186 | 10 | Solar & Battery | 362-1209H1 | 2024-10-14 | 2024-11-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Online | [11 empty] | 10 | STA_496 Hyde Park
NSTAR | Centerville | ESMAEX-04173 | 02632 | 17.26 | Solar | 4-82-82 | 2024-10-15 | 2024-11-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Westport | ESMAEX-04293 | 02790 | 10 | Battery | 2-523-523 | 2025-02-06 | 2024-12-27 | -31 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-05 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Carver | ESMAEX-04183 | 02330 | 996 | Solar & Battery | 3-81-950 | 2024-10-17 | 2024-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Plymouth |  | Phase 2 - In Process |  | STA_713 Tremont
NSTAR | Carver | ESMAEX-04181 | 02330 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04182 | 01851 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_713 Tremont
NSTAR | Waltham | ESMAEX-04179 | 02451 | 15.51 | Solar | 282-H2 | 2024-10-17 | 2024-11-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Meter | [12 empty] | STA_282 Waltham
NSTAR | Norfolk | ESMAEX-04595 | 02056 | 66.6 | Solar | 146-H9 | 2025-03-05 | 2025-10-24 | 167 |  | 167 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-04198 | 01720 | 34.5 | Solar & Battery | 416-H8 | 2024-10-21 | 2024-11-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Weston | ESMAEX-04199 | 02493 | 17.6 | Solar | 282-H8 | 2024-10-21 | 2024-11-26 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-04-14 | Online | [11 empty] | 17.6 | STA_282 Waltham
NSTAR | Wareham | ESMAEX-04213 | 02571 | 999.45 | Solar & Battery | 3-84-84 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 999.45 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04214 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04215 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04216 | 02330 | 4980 | Solar & Battery | 3-14-934 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  | In Queue | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04219 | 02330 | 4980 | Solar & Battery | 3-14-934 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Hold In Queue | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04218 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04220 | 02330 | 4980 | Solar & Battery | 3-10-917 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4980 | STA_737 West Pond
NSTAR | Plympton | ESMAEX-04221 | 02367 | 4980 | Solar & Battery | 3-10-917 | 2024-10-29 | 2024-12-04 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  | Hold In Queue | 4980 | STA_737 West Pond
NSTAR | Wayland | ESMAEX-04281 | 01778 | 20 | Battery | 433-H2 | 2024-11-17 | 2024-12-05 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Permission to Operate | [11 empty] | 20 | STA_433 Speen Street
NSTAR | West Newton | ESMAEX-04223 | 02465 | 110 | Solar | 292-H12 | 2024-10-29 | 2024-11-08 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Acusnet | ESMAEX-04226 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Acusnet | ESMAEX-04227 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Medfield | ESMAEX-04225 | 02052 | 16.13 | Solar | 456-H5 | 2024-10-30 | 2024-11-08 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Online | [12 empty] | STA_456 Dover
NSTAR | Sudbury | ESMAEX-04234 | 01776 | 240 | Solar | 342-H8 | 2024-11-01 | 2024-11-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Sudbury | ESMAEX-04232 | 01776 | 23 | Solar & Battery | 416-H7 | 2024-11-01 | 2024-12-04 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Wayland | ESMAEX-04229 | 01748 | 34.6 | Solar | 342-H1 | 2024-11-01 | 2024-11-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Oak Bluffs | ESMAEX-04236 | 02557 | 15.36 | Solar | 4-99-225 | 2024-11-01 | 2025-02-03 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Carver | ESMAEX-04272 | 02330 | 4750 | Solar & Battery | 3-83-83 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  | Hold In Queue | 4750 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04268 | 02330 | 990 | Solar | 3-10-10 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04270 | 02360 | 500 | Solar | 3-90-90 | 2024-11-12 | 2024-11-25 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Plymouth | ESMAEX-04269 | 02360 | 990 | Solar | 3-11-11 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process |  | STA_737 West Pond
NSTAR | Carver | ESMAEX-04271 | 02330 | 4999 | Solar & Battery | 3-81-81 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  | Hold In Queue | 4999 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04267 | 02330 | 990 | Solar | 3-10-929 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process |  | STA_737 West Pond
NSTAR | Carver | ESMAEX-04241 | 02330 | 4999 | Solar & Battery | 3-11-11 | 2024-11-06 | 2024-11-13 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_737 West Pond
NSTAR | Tisbury | ESMAEX-04245 | 02575 | 97 | Solar |  | 2024-11-07 | 2024-11-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | West Yarmouth | ESMAEX-04247 | 02673 | 10 | Battery | 4-63-532 | 2024-11-07 | 2024-12-19 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online | [8 empty] | Cape |  |  | 10 | STA_961 Hyannis Junction
NSTAR | Hopkinton | ESMAEX-04244 | 01748 | 20.06 | Solar | 126-H2 | 2024-11-07 | 2025-01-08 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Newton Lower Falls | ESMAEX-04246 | 02462 | 1500 | Fuel Cell | 292-H2 | 2025-04-23 | 2025-05-29 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Plymouth | ESMAEX-04253 | 02360 | 999 | Solar & Battery | 3-12-12 | 2024-11-11 | 2024-12-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 999 | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04256 | 02360 | 3500 | Solar & Battery | 3-90-90 | 2024-11-11 | 2024-11-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 3500 | STA_715 Valley
NSTAR | Waltham | ESMAEX-04262 | 02451 | 13.65 | Solar | 282-H2 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  | 2025-08-26 | Online | [12 empty] | STA_282 Waltham
NSTAR | Sharon | ESMAEX-04250 | 02067 | 4950 | Other | 146-H1 | 2025-05-09 | 2025-07-15 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4950 | STA_146 Walpole
NSTAR | Oak Bluffs | ESMAEX-04259 | 02557 | 17.6 | Solar | 4-99-224 | 2024-11-12 | 2024-11-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | East Freetown | ESMAEX-04294 | 02717 | 19 | Solar | 2-102-608 | 2024-11-22 | 2024-12-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Watertown | ESMAEX-04254 | 02472 | 16.2 | Solar | 467-H10 | 2024-11-11 | 2025-01-21 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online | [12 empty] | STA_467 Watertown
NSTAR | Carver | ESMAEX-04255 | 02330 | 4999 | Solar & Battery | 3-81-950 | 2024-11-11 | 2024-11-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | Plymouth Phase 2 Distribution Group Study | Plymouth |  | Phase 2 - In Process | 4999 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04257 | 02330 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-11-19 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04258 | 02360 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-12-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Waltham | ESMAEX-04438 | 02453 | 33.1 | Solar | 282-H4 | 2025-01-16 | 2025-02-21 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-10-16 | Online | [12 empty] | STA_282 Waltham
NSTAR | Plymouth | ESMAEX-04273 | 02360 | 15.2 | Solar | 3-14-30J2 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-01 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Medfield | ESMAEX-04277 | 02052 | 18.705 | Solar | 146-H6 | 2024-11-14 | 2025-01-03 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Online | [12 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-04282 | 02421 | 20 | Solar & Battery | 320-H5XY | 2024-11-18 | 2024-12-05 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [11 empty] | 20 | STA_320 Lexington
NSTAR | Newton | ESMAEX-04486 | 02465 | 17.3 | Solar | 33-H3 | 2025-02-05 | 2025-02-19 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online | [12 empty] | STA_282 Waltham
NSTAR | Jamaica Plain | ESMAEX-04567 | 02130 | 17.3 | Solar | 350-H2 | 2025-02-25 | 2025-03-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Acton | ESMAEX-04433 | 01720 | 300 | Solar | 416-H5 | 2025-03-20 | 2025-05-20 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Needham | ESMAEX-04301 | 02492 | 21.5 | Solar & Battery | 148-06 | 2024-11-26 | 2025-01-15 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-05 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [11 empty] | 20 | STA_148 Needham
NSTAR | Westwood | ESMAEX-04387 | 02090 | 150 | Solar | 469-H4 | 2024-12-17 | 2025-01-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_469 Ellis Avenue
NSTAR | Newton Center | ESMAEX-04315 | 02459 | 30 | Solar | 292-H3 | 2024-11-27 | 2025-01-08 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Online | [12 empty] | STA_292 Newton Highlands
NSTAR | Mashpee | ESMAEX-04319 | 02649 | 50 | Solar |  | 2024-12-03 | 2024-12-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 | [7 empty] | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape
NSTAR | Medfield | ESMAEX-04317 | 02052 | 19.1 | Solar & Battery | 456-H2 | 2024-12-02 | 2025-01-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Online | [12 empty] | STA_456 Dover
NSTAR | Marshfield | ESMAEX-04585 | 02051 | 4980 | Other | 3-25-25 | 2025-02-28 | 2025-04-28 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4980 | STA_738 Duxbury
NSTAR | Westwood | ESMAEX-04345 | 02090 | 20 | Solar & Battery | 469-H2 | 2024-12-06 | 2024-12-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Online | [11 empty] | 20
NSTAR | Winchester | ESMAEX-04397 | 01890 | 31.02 | Solar | 211-H4 | 2024-12-20 | 2025-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-11 | [7 empty] | 0 |  | 0 |  |  | 2025-10-08 | Online | [11 empty] | 20 | STA_211 Woburn
NSTAR | Arlington | ESMAEX-04400 | 02476 | 7.59 | Solar | 211-H14 | 2024-12-20 | 2025-01-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [12 empty] | STA_211 Woburn
NSTAR | Chelsea | ESMAEX-04326 | 02150 | 67.3 | Solar | 488-H5 | 2025-05-01 | 2025-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | New Bedford | ESMAEX-04327 | 02740 | 77.3 | Solar |  | 2025-08-13 | 2025-08-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Freetown | ESMAEX-04331 | 02717 | 4980 | Solar & Battery | 2-102-102 | 2025-01-15 | 2025-01-27 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | New Bedford |  | Hold In Queue |  | STA_636 Industrial Park
NSTAR | Westwood | ESMAEX-04344 | 02090 | 20 | Battery | 148-H3 | 2024-12-06 | 2025-01-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [11 empty] | 20 | STA_148 Needham
NSTAR | Yarmouthport | ESMAEX-04346 | 02675 | 7.6 | Solar | 4-90-90 | 2024-12-06 | 2025-01-08 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Dedham | ESMAEX-04347 | 02026 | 15.2 | Solar | 344-1412H1 | 2024-12-06 | 2025-01-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Vineyard Haven | ESMAEX-04518 | 02568 | 260 | Solar | 4-75-75 | 2025-05-06 | 2025-06-09 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Canton | ESMAEX-04383 | 02021 | 720 | Solar & Battery | 470-H7 | 2025-06-30 | 2025-08-18 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Canton | ESMAEX-04350 | 02021 | 33 | Solar | 269-1320H1 | 2024-12-09 | 2025-01-03 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [11 empty] | 20 | STA_470 Canton
NSTAR | Hyde Park | ESMAEX-04353 | 02136 | 200 | Solar | 344-07 | 2025-01-13 | 2025-01-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Dennis | ESMAEX-04354 | 02638 | 44.88 | Solar | 4-89A-552 | 2024-12-10 | 2025-01-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Weston | ESMAEX-04371 | 02493 | 80 | Solar | 282-H8 | 2024-12-23 | 2025-01-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-08 | [7 empty] | 0 |  | 0 |  |  | 2025-09-05 | Online | [12 empty] | STA_282 Waltham
NSTAR | Dedham | ESMAEX-04363 | 02026 | 17.26 | Solar | 344-1412H1 | 2024-12-11 | 2024-12-19 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [11 empty] | 14 | STA_496 Hyde Park
NSTAR | Wayland | ESMAEX-04369 | 01778 | 22.8 | Solar | 342-H1 | 2024-12-13 |  | -32567 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_342 Sudbury
NSTAR | Burlington | ESMAEX-04441 | 01803 | 15.28 | Solar | 391-H7 | 2025-01-17 | 2025-03-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-18 | [7 empty] | 0 |  | 0 |  |  | 2025-07-07 | Online | [11 empty] | 15.2 | STA_391 Burlington
NSTAR | Framingham | ESMAEX-04386 | 01701 | 480 | Other | 433-H10 | 2025-04-07 | 2025-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Bourne | ESMAEX-04382 | 02532 | 450 | Solar | 4-71-455 | 2025-02-14 | 2025-03-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Falmouth | ESMAEX-04421 | 02540 | 40 | Solar | 4-76-437 | 2025-01-08 | 2025-01-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Teaticket | ESMAEX-04396 | 02536 | 499 | Solar | 4-76-437 | 2025-06-03 | 2025-07-17 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | West Roxbury | ESMAEX-04411 | 02132 | 11.5 | Solar & Battery | 496-H6 | 2024-12-31 | 2025-01-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | 0 | ESMAEX-04409 | 02739 | 4990 | Battery | 2-301-301 | 2024-12-30 | 2025-03-03 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Marion-Fairhaven |  | Hold In Queue | 4990 | STA_646 Crystal Spring
NSTAR | 0 | ESMAEX-04410 | 02739 | 4990 | Battery | 2-306-306 | 2024-12-30 | 2025-04-17 | 78 |  | 78 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven |  | Hold In Queue | 4990 | STA_646 Crystal Spring
NSTAR | Stoneham | ESMAEX-04401 | 02180 | 15.36 | Solar & Battery | 211-H12 | 2024-12-21 | 2025-01-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Roxbury | ESMAEX-04402 | 02119 | 20 | Solar | 510-77H5 | 2024-12-23 | 2025-02-03 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Fairhaven | ESMAEX-04405 | 02719 | 240 | Solar | 2-230-230 | 2024-12-27 | 2025-04-23 | 83 |  | 83 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_612 Acushnet
NSTAR | New Bedford | ESMAEX-04420 | 02746 | 15.2 | Solar | 2-87-135 | 2025-01-07 | 2025-02-25 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Online | [12 empty] | STA_612 Acushnet
NSTAR | Dennis | ESMAEX-04408 | 02638 | 23 | Solar & Battery | 4-89A-89A | 2024-12-31 | 2025-01-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Falmouth | ESMAEX-04407 | 02540 | 11.5 | Battery | 4-72-72 | 2024-12-30 | 2025-03-03 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-14 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_933 Falmouth
NSTAR | West Tisbury | ESMAEX-04471 | 02575 | 90 | Solar & Battery | 4-97-97 | 2025-01-28 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Weston | ESMAEX-04432 | 02493 | 20.352 | Solar | 282-H10 | 2025-01-14 | 2025-03-03 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-10-20 | Online | [11 empty] | 19.999 | STA_282 Waltham
NSTAR | Canton | ESMAEX-04417 | 02021 | 100 | Solar | 470-H4 | 2025-01-03 | 2025-01-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [12 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-04434 | 01773 | 15.5 | Other | 320-H6 | 2025-01-15 | 2025-01-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Online | [11 empty] | 15.5 | STA_320 Lexington
NSTAR | Bedford | ESMAEX-04430 | 01730 | 999 | Solar | 391-H8 | 2025-03-28 | 2025-04-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-04426 | 01748 | 10 | Other | 126-H4 | 2025-01-10 | 2025-02-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Online | [11 empty] | 10 | STA_126 Hopkinton
NSTAR | West Newton | ESMAEX-04422 | 02465 | 15.2 | Solar & Battery | 316-01 | 2025-01-10 | 2025-02-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Online | [12 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-04427 | 01720 | 19.58 | Solar & Battery | 416-H4 | 2025-01-10 | 2025-01-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [12 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-04534 | 01760 | 23 | Other | 23-H1 | 2025-02-18 | 2025-03-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [11 empty] | 0 | STA_240 Framingham
NSTAR | Westwood | ESMAEX-04689 | 02090 | 17.48 | Solar | 148-H3 | 2025-03-26 |  | -32640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-25 | Online | [12 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-04477 | 01803 | 15.18 | Solar | 346-1395H1 | 2025-01-30 | 2025-02-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_391 Burlington
NSTAR | Sharon | ESMAEX-04435 | 02067 | 240 | Solar | 146-H7 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-04437 | 02186 | 17.6 | Solar & Battery | 496-H7 | 2025-01-15 | 2025-03-03 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Online | [11 empty] | 7.6 | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-04481 | 01760 | 20 | Other | 240-H5 | 2025-02-03 | 2025-03-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [11 empty] | 20 | STA_240 Framingham
NSTAR | Lexington | ESMAEX-04440 | 02421 | 490 | Solar | 320-H2 | 2025-01-17 | 2025-02-18 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Edgartown | ESMAEX-04455 | 02539 | 60 | Solar | 4-97-97 | 2025-01-21 | 2025-02-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-29 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Walpole | ESMAEX-04454 | 02081 | 15.3 | Solar & Battery | 146-H4 | 2025-01-21 | 2025-02-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online | [11 empty] | 15.3 | STA_146 Walpole
NSTAR | Carlisle | ESMAEX-04695 | 01741 | 60 | Solar & Battery | 512-1399H1 | 2025-03-26 | 2025-05-23 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 15 | STA_533 Hartwell Avenue
NSTAR | Plymouth | ESMAEX-04457 | 02360 | 15.36 | Solar | 3-72-940 | 2025-01-22 | 2025-03-14 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Framingham | ESMAEX-04462 | 01702 | 23 | Solar & Battery | 455-H5 | 2025-01-23 | 2025-02-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.9 | STA_455 West Framingham
NSTAR | Marion | ESMAEX-04464 | 02738 | 480 | Solar | 3-304-304 | 2025-02-10 | 2025-02-19 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Waltham | ESMAEX-04466 | 02451 | 4999 | Other | 450-H7 | 2025-04-09 | 2025-04-17 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4999 | STA_450 Trapelo Road
NSTAR | Acton | ESMAEX-04469 | 01720 | 23 | Other | 416-H8 | 2025-01-28 | 2025-03-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Sandwich | ESMAEX-04472 | 02563 | 7.68 | Solar | 4-455-455 | 2025-01-28 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | Roxbury Crossing | ESMAEX-04674 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-20 | 2025-05-28 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Bedford | ESMAEX-04555 | 01730 | 22.8 | Solar | 322-1397H1 | 2025-02-21 | 2025-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Roxbury Crossing | ESMAEX-04684 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-25 | 2025-05-28 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Sudbury | ESMAEX-04609 | 01776 | 15.76 | Solar | 342-H2 | 2025-03-10 | 2025-03-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-01 | Online | [11 empty] | 9.29 | STA_342 Sudbury
NSTAR | North Truro | ESMAEX-04490 | 02652 | 11.5 | Solar & Battery | 4-96-96 | 2025-02-06 | 2025-03-21 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [12 empty] | STA_976 Wellfleet
NSTAR | Edgartown | ESMAEX-04537 | 02539 | 4.72 | Solar | 4-75-123 | 2025-02-19 | 2025-03-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Millis | ESMAEX-04479 | 02054 | 25 | Solar | 130-H2 | 2025-02-03 | 2025-02-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [11 empty] | 20 | STA_130 Holliston
NSTAR | North Eastham | ESMAEX-04488 | 02651 | 15.2 | Solar & Battery | 4-94B-956 | 2025-02-05 | 2025-03-04 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Online | [11 empty] | 7.6 | STA_976 Wellfleet
NSTAR | Plymouth | ESMAEX-04482 | 02360 | 490 | Solar | 3-13-943 | 2025-08-15 | 2025-09-23 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Marion | ESMAEX-04485 | 02738 | 15.2 | Solar | 3-85-85 | 2025-02-13 | 2025-03-19 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Newton | ESMAEX-04493 | 02458 | 23 | Solar & Battery | 467-H12 | 2025-02-06 | 2025-03-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Online | [11 empty] | 19.9 | STA_467 Watertown
NSTAR | North Dartmouth | ESMAEX-04499 | 02747 | 15.2 | Solar | 2-533-503 | 2025-02-07 | 2025-03-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-09 | Online | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Acton | ESMAEX-04502 | 01720 | 23 | Solar & Battery | 416-H2 | 2025-02-07 | 2025-03-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_416 Maynard
NSTAR | Norfolk | ESMAEX-04491 | 02056 | 20 | Solar & Battery | 146-H3 | 2025-02-07 | 2025-02-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_146 Walpole
NSTAR | Canton | ESMAEX-04741 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2025-04-05 | 2025-09-19 | 120 |  | 120 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 7.475 | STA_470 Canton
NSTAR | Woburn | ESMAEX-04492 | 01801 | 20.1 | Solar | 375-H6 | 2025-02-06 | 2025-03-07 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-07-28 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Woburn | ESMAEX-04512 | 01801 | 22.66 | Solar & Battery | 211-H8 | 2025-02-27 | 2025-03-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-04496 | 02067 | 15.2 | Solar | 470-H12 | 2025-02-06 | 2025-03-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-14 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [12 empty] | STA_470 Canton
NSTAR | South Walpole | ESMAEX-04522 | 02071 | 100 | Solar | 146-H3 | 2025-02-14 | 2025-03-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Sherborn | ESMAEX-04501 | 01770 | 23 | Solar & Battery | 274-H2 | 2025-02-07 | 2025-03-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-04-26 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Boston | ESMAEX-04500 | 02130 | 84.6 | Solar |  | 2025-02-07 |  | -32607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Walpole | ESMAEX-04525 | 02081 | 18.78 | Solar & Battery | 146-H4 | 2025-02-15 | 2025-03-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-08-11 | Online | [11 empty] | 18.78 | STA_146 Walpole
NSTAR | Rochester | ESMAEX-04503 | 02770 | 4980 | Solar & Battery | 3-702-702 | 2025-03-17 | 2025-04-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven |  | Individual Study |  | STA_745 Rochester
NSTAR | Newton | ESMAEX-04830 | 02456 | 15.58 | Solar | 316-01 | 2025-04-23 | 2025-05-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Carlisle | ESMAEX-04506 | 01741 | 15.2 | Solar | 533-H8 | 2025-02-10 | 2025-02-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Burlington | ESMAEX-04579 | 01803 | 4.5 | Solar | 346-1395H1 | 2025-02-27 | 2025-04-10 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-31 | Online | [11 empty] | 4.5 | STA_391 Burlington
NSTAR | Needham | ESMAEX-04563 | 02494 | 50 | Solar | 292-H9 | 2025-02-25 | 2025-03-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Lincoln | ESMAEX-04519 | 01773 | 17.16 | Solar | 320-H8 | 2025-02-14 | 2025-03-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-16 | Online | [11 empty] | 14.69 | STA_320 Lexington
NSTAR | Chelsea | ESMAEX-04664 | 02150 | 302 | Solar | 488-H7 | 2025-03-19 | 2025-03-25 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_488 Chelsea
NSTAR | Wayland | ESMAEX-04560 | 01778 | 18.4 | Solar & Battery | 278-H2 | 2025-02-24 | 2025-04-09 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-20 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Vineyard Haven | ESMAEX-04529 | 02568 | 15.2 | Solar | 4-91-228 | 2025-02-17 | 2025-02-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-10-16 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Cambridge | ESMAEX-04531 | 02138 | 29.31 | Solar & Battery | 821-22 | 2025-02-18 | 2025-03-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-19 | Online | [11 empty] | 20 | STA_831 Putnam
NSTAR | Bedford | ESMAEX-04669 | 01730 | 32.256 | Solar & Battery | 533-H7 | 2025-03-19 | 2025-03-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-12 | Online | [11 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-04538 | 02021 | 250 | Solar | 470-H7 | 2025-03-31 | 2025-04-28 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Acton | ESMAEX-04539 | 01720 | 7.6 | Solar | 512-1399H1 | 2025-02-19 | 2025-03-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-04541 | 01778 | 15.2 | Solar |  | 2025-02-19 | 2025-03-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-08-18 | Online | [12 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-04571 | 02492 | 16.89 | Solar | 148-07 | 2025-02-26 | 2025-03-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-18 | Online | [12 empty] | STA_148 Needham
NSTAR | East Freetown | ESMAEX-04551 | 02717 | 20 | Solar & Battery | 2-108-108 | 2025-02-20 | 2025-03-06 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online | [8 empty] | Cape |  |  | 20 | STA_636 Industrial Park
NSTAR | Dover | ESMAEX-04544 | 02030 | 19.58 | Solar & Battery | 456-H5 | 2025-02-20 | 2025-03-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Online | [12 empty] | STA_456 Dover
NSTAR | Lincoln | ESMAEX-04546 | 01773 | 18.43 | Solar | 320-H8 | 2025-02-20 | 2025-03-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-04547 | 01701 | 7.6 | Solar | 342-H4 | 2025-02-20 | 2025-03-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_342 Sudbury
NSTAR | New Bedford | ESMAEX-04597 | 02740 | 80 | Solar | 2-53-65 | 2025-03-05 | 2025-04-28 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Westport | ESMAEX-04580 | 02790 | 13.8 | Solar & Battery | 2-522-522 | 2025-02-27 | 2025-06-18 | 79 |  | 79 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 11.9 | STA_657 Fisher Road
NSTAR | Newtonville | ESMAEX-04552 | 02460 | 15.2 | Solar | 467-H5 | 2025-02-24 | 2025-03-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_467 Watertown
NSTAR | Chatham | ESMAEX-04615 | 02633 | 23 | Other | 4-95B-95B | 2025-03-11 | 2025-07-24 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.9 | STA_975 Orleans
NSTAR | Roslindale | ESMAEX-04613 | 02131 | 110 | Solar | 1306 | 2025-03-11 | 2025-03-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Oak Bluffs | ESMAEX-04561 | 02557 | 15.36 | Solar | 4-75-75 | 2025-02-24 | 2025-03-04 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Centerville | ESMAEX-04574 | 02632 | 11.5 | Other | 4-82-82 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-29 | Online | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Sharon | ESMAEX-04575 | 02067 | 10 | Solar | 146-H1 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-14 | Online | [11 empty] | 10 | STA_146 Walpole
NSTAR | Hyannis | ESMAEX-04569 | 02601 | 36.16 | Solar | 4-63-532 | 2025-03-05 | 2025-04-25 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Lexington | ESMAEX-04572 | 02421 | 9 | Solar | 320-H2 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-27 | Online | [12 empty] | STA_320 Lexington
NSTAR | Watertown | ESMAEX-04581 | 02472 | 8.25 | Solar | 467-H9 | 2025-02-28 | 2025-03-06 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-09 | Online | [12 empty] | STA_467 Watertown
NSTAR | Kingston | ESMAEX-04582 | 02364 | 1800 | Solar & Battery | 3-17-17 | 2025-05-01 | 2025-05-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Online | [8 empty] | Plymouth |  |  |  | STA_735 Kingston
NSTAR | Centerville | ESMAEX-04587 | 02632 | 19.1 | Solar & Battery | 4-82-82 | 2025-02-28 | 2025-03-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_920 Oak Street
NSTAR | Falmouth | ESMAEX-04621 | 02540 | 0 | Other | 4-76-436 | 2025-03-12 | 2025-05-07 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 19.99 | STA_933 Falmouth
NSTAR | Dover | ESMAEX-04589 | 02030 | 23 | Solar & Battery | 456-H5 | 2025-03-03 | 2025-03-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [11 empty] | 20 | STA_456 Dover
NSTAR | Osterville | ESMAEX-04658 | 02655 | 57.5 | Solar & Battery | 4-88-88 | 2025-03-18 | 2025-03-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-29 | Online | [8 empty] | Cape |  |  | 19.9 | STA_946 Mashpee
NSTAR | Brighton | ESMAEX-04666 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-28 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Hyde Park | ESMAEX-04903 | 02136 | 250 | Solar | 344-1411H | 2025-05-12 | 2025-07-02 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_496 Hyde Park
NSTAR | New Bedford | ESMAEX-04596 | 02745 | 15.2 | Solar | 2-105-105 | 2025-03-05 | 2025-05-01 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_636 Industrial Park
NSTAR | Norfolk | ESMAEX-04601 | 02056 | 18.81 | Solar | 65-H1 | 2025-03-05 | 2025-04-17 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-23 | Online | [12 empty] | STA_065 Medway
NSTAR | Provincetown | ESMAEX-04763 | 02657 | 17.3 | Solar |  | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold
NSTAR | Provincetown | ESMAEX-04762 | 02657 | 27.3 | Solar |  | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold
NSTAR | Rochester | ESMAEX-04606 | 02770 | 4999 | Solar | 3-703-703 | 2025-03-07 | 2025-04-30 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Marion-Fairhaven |  | Individual Study |  | STA_745 Rochester
NSTAR | Provincetown | ESMAEX-04761 | 02657 | 27.3 | Solar |  | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold
NSTAR | Provincetown | ESMAEX-04759 | 02110 | 17.3 | Solar |  | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold
NSTAR | Canton | ESMAEX-04610 | 02021 | 5.76 | Solar | 470-H1 | 2025-03-10 | 2025-03-17 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [12 empty] | STA_470 Canton
NSTAR | Holliston | ESMAEX-04611 | 01746 | 15.36 | Solar | 65-H5 | 2025-03-11 | 2025-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [12 empty] | STA_065 Medway
NSTAR | Carlisle | ESMAEX-04619 | 01741 | 9.9 | Solar | 512-1399H1 | 2025-03-12 | 2025-03-28 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-14 | Online | [11 empty] | 9.9 | STA_533 Hartwell Avenue
NSTAR | Waltham | ESMAEX-04625 | 02452 | 15.2 | Solar | 282-H7 | 2025-03-13 | 2025-03-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | West Falmouth | ESMAEX-04618 | 02574 | 30.72 | Other | 4-98A-98A | 2025-03-11 | 2025-03-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  | 20 | STA_933 Falmouth
NSTAR | Newton Center | ESMAEX-04690 | 02459 | 16.8 | Solar | 443-02 | 2025-03-26 |  | -32640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-12 | Online | [12 empty] | STA_110 Baker Street
NSTAR | Cambridge | ESMAEX-04705 | 02139 | 90 | Solar | 814-12 | 2025-03-28 | 2025-04-28 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_402 Newton Street
NSTAR | Sharon | ESMAEX-04679 | 02067 | 8.784 | Solar | 146-H7 | 2025-03-24 | 2025-04-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-18 | Online | [11 empty] | 18.38 | STA_146 Walpole
NSTAR | Watertown | ESMAEX-04636 | 02472 | 11.5 | Other | 124-04 | 2025-03-14 | 2025-04-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | West Wareham | ESMAEX-04713 | 02576 | 5 | Other | 3-85-85 | 2025-03-30 | 2025-04-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | Plymouth |  |  | 0 | STA_713 Tremont
NSTAR | Boston | ESMAEX-04728 | 02119 | 50 | Solar | 52-1487H | 2025-04-02 | 2025-05-06 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Brookline | ESMAEX-04714 | 02446 | 105 | Solar | 329-H8 | 2025-03-31 | 2025-09-24 | 127 |  | 127 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_329 Brighton
NSTAR | Plymouth | ESMAEX-04631 | 02360 | 425 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04634 | 02360 | 185 | Solar | 3-13-943 | 2025-04-11 | 2025-04-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04635 | 02360 | 195 | Solar | 3-13-943 | 2025-04-11 | 2025-05-23 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04643 | 02360 | 499.9 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [11 empty] | 499.9 | STA_737 West Pond
NSTAR | Chilmark | ESMAEX-04641 | 02535 | 16.24 | Solar | 4-97-97 | 2025-03-14 | 2025-03-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-15 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-04660 | 02420 | 9.57 | Solar | 391-H11 | 2025-03-18 | 2025-03-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-10 | Online | [12 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-04646 | 01720 | 23.81 | Solar & Battery | 416-H5 | 2025-03-17 | 2025-03-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-17 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | East Boston | ESMAEX-04647 | 02128 | 15.2 | Solar | 108-196H1 | 2025-03-17 | 2025-04-17 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-09 | Online | [12 empty] | STA_488 Chelsea
NSTAR | Bedford | ESMAEX-04652 | 01730 | 22.6 | Solar & Battery | 533-H7 | 2025-03-18 | 2025-05-20 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-19 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Brighton | ESMAEX-04649 | 02135 | 23.76 | Solar & Battery | 315-H7 | 2025-03-18 | 2025-03-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-30 | Online | [11 empty] | 11.54
NSTAR | Wareham | ESMAEX-04650 | 02571 | 990 | Solar | 3-85-928 | 2025-04-11 | 2025-04-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  | Hold In Queue |  | STA_713 Tremont
NSTAR | Woburn | ESMAEX-04653 | 01801 | 770 | Solar | 375-H6 | 2025-05-13 | 2025-06-30 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_375 Dragon Court
NSTAR | Kingston | ESMAEX-04654 | 02364 | 990 | Solar | 3-17-17 | 2025-04-11 | 2025-04-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_735 Kingston
NSTAR | North Dartmouth | ESMAEX-04655 | 02747 | 990 | Solar | 2-533-533 | 2025-04-11 | 2025-04-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Dedham | ESMAEX-04656 | 02026 | 990 | Solar | 20-H1 | 2025-04-11 | 2025-04-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_110 Baker Street
NSTAR | Winchester | ESMAEX-04720 | 01890 | 35.2 | Solar | 211-H11 | 2025-03-31 | 2025-04-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-25 | Online | [12 empty] | STA_211 Woburn
NSTAR | Brighton | ESMAEX-04665 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-25 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Somerville | ESMAEX-04662 | 02143 | 499 | Solar | 387-148H2 | 2025-04-11 | 2025-05-23 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_250 Mystic
NSTAR | Fairhaven | ESMAEX-04668 | 02719 | 7.6 | Solar | 2-240-209 | 2025-03-19 | 2025-05-12 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Somerville | ESMAEX-04671 | 02145 | 15.2 | Solar | 250-H4XY | 2025-03-20 | 2025-03-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_250 Mystic
NSTAR | Arlington | ESMAEX-04715 | 02474 | 16.512 | Solar | 59-1393H1 | 2025-03-31 | 2025-06-09 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-04711 | 01748 | 4998 | Other | 126-H4 | 2025-03-28 | 2025-04-28 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4980 | STA_126 Hopkinton
NSTAR | Boston | ESMAEX-04756 | 02128 | 40 | Solar |  | 2025-04-08 | 2025-04-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Plymouth | ESMAEX-04692 | 02360 | 23 | Solar & Battery |  | 2025-03-26 | 2025-04-25 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online
NSTAR | Brewster | ESMAEX-04724 | 02631 | 14.73 | Solar | 4-89A-89A | 2025-04-01 | 2025-04-25 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 14.73 | STA_968 Harwich
NSTAR | Dorchester | ESMAEX-04718 | 02122 | 40 | Solar | 466-1481H1 | 2025-03-31 | 2025-04-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Burlington | ESMAEX-04694 | 01803 | 23 | Solar & Battery | 391-H6 | 2025-03-26 | 2025-04-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-23 | Online | [11 empty] | 11.1 | STA_391 Burlington
NSTAR | Plymouth | ESMAEX-04702 | 02360 | 7.6 | Solar | 3-90-90 | 2025-03-27 | 2025-04-29 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-24 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Holliston | ESMAEX-04709 | 01746 | 5.76 | Solar | 65-H5 | 2025-03-28 | 2025-04-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_065 Medway
NSTAR | Wayland | ESMAEX-04717 | 01778 | 16.1 | Solar | 342-H1 | 2025-03-31 | 2025-04-04 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-25 | Online | [12 empty] | STA_342 Sudbury
NSTAR | South Dennis | ESMAEX-04729 | 02660 | 30.4 | Solar | 4-92B-92B | 2025-04-02 | 2025-04-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Wareham | ESMAEX-04732 | 02571 | 0 | Other | 3-84-84 | 2025-04-03 | 2025-05-07 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_714 Wareham
NSTAR | Roxbury Crossing | ESMAEX-04723 | 02120 | 100 | Solar | 299-1180H | 2025-04-01 | 2025-05-01 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Dover | ESMAEX-04721 | 02030 | 20.2 | Solar | 456-H5 | 2025-04-04 | 2025-04-14 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-13 | Online | [11 empty] | 20.2 | STA_456 Dover
NSTAR | Boston | ESMAEX-04730 | 02115 | 225 | Internal Combustion Engine | MC-9 | 2025-04-02 | 2025-04-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_350 Colburn Street
NSTAR | Sagamore Beach | ESMAEX-04727 | 02562 | 17.6 | Solar | 3-89-925 | 2025-04-02 | 2025-06-09 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Plymouth | ESMAEX-04731 | 02360 | 6 | Solar | 3-90-90 | 2025-04-03 | 2025-04-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-11 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Dorchester | ESMAEX-04735 | 02124 | 15.2 | Solar | 483-H5 | 2025-04-03 | 2025-04-10 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Stoneham | ESMAEX-04737 | 02180 | 7.6 | Solar | 375-H8 | 2025-04-03 | 2025-05-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-24 | Online | [12 empty] | STA_375 Dragon Court
NSTAR | Holliston | ESMAEX-04739 | 01746 | 5.76 | Solar | 130-H1 | 2025-04-03 | 2025-05-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_130 Holliston
NSTAR | Newton Center | ESMAEX-04754 | 02459 | 19.968 | Solar | 292-H11 | 2025-04-29 | 2025-05-02 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | North Dartmouth | ESMAEX-04740 | 02747 | 23 | Solar & Battery | 2-522-522 | 2025-04-04 | 2025-05-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-11 | Online | [11 empty] | 20 | STA_657 Fisher Road
NSTAR | Edgartown | ESMAEX-04805 | 02539 | 25.74 | Solar | 4-75-75 | 2025-04-17 | 2025-05-08 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-08 | Online | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-04777 | 02420 | 20.736 | Solar | 533-H3 | 2025-04-09 | 2025-04-18 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-05 | Online | [11 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Acton | ESMAEX-04820 | 01720 | 20 | Solar | 416-H8 | 2025-04-21 | 2025-04-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-17 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Plymouth | ESMAEX-04758 | 02360 | 7.6 | Solar | 3-14-934 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-13 | Online | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Allston | ESMAEX-04752 | 02134 | 50 | Solar | 315-H3 | 2025-04-08 | 2025-04-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_315 Electric Avenue
NSTAR | New Bedford | ESMAEX-04821 | 02740 | 156 | Solar |  | 2025-04-21 | 2025-05-20 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Cataumet | ESMAEX-04846 | 02534 | 10.6 | Solar | 4-78-410 | 2025-04-27 | 2025-05-20 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [8 empty] | Cape |  |  | 10.6 | STA_936 Hatchville
NSTAR | Hopkinton | ESMAEX-04785 | 01748 | 5.7 | Solar | 126-H1 | 2025-04-10 | 2025-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [12 empty] | STA_126 Hopkinton
NSTAR | Hyannis | ESMAEX-04772 | 02601 | 15.2 | Solar | 4-80B-80B | 2025-04-09 | 2025-05-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Framingham | ESMAEX-04778 | 01702 | 4999 | Other | 274-H4 | 2025-05-22 | 2025-06-11 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4999 | STA_274 Sherborn
NSTAR | Kingston | ESMAEX-04780 | 02364 | 7.6 | Solar | 3-14-14 | 2025-04-09 | 2025-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-12 | Online | [8 empty] | Plymouth
NSTAR | Natick | ESMAEX-04812 | 01760 | 17.66 | Solar | 240-H1 | 2025-04-18 | 2025-05-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-01 | Online | [12 empty] | STA_240 Framingham
NSTAR | Roxbury | ESMAEX-04783 | 02119 | 330 | Solar | 106-H4 | 2025-06-05 | 2025-06-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_106 Andrew Square
NSTAR | East Orleans | ESMAEX-04822 | 02643 | 22.8 | Solar & Battery |  | 2025-04-22 | 2025-06-10 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-30 | Online
NSTAR | Medway | ESMAEX-04788 | 02053 | 15.2 | Solar | 130-H2 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [12 empty] | STA_130 Holliston
NSTAR | New Bedford | ESMAEX-04789 | 02740 | 30 | Solar | 2-59-38 | 2025-04-14 | 2025-04-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-14 | Online | [11 empty] | 20 | STA_611 Pine Street
NSTAR | Wayland | ESMAEX-04790 | 01778 | 5.76 | Solar | 342-H1 | 2025-04-14 | 2025-05-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-26 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Dedham | ESMAEX-04795 | 02026 | 20.76 | Solar & Battery | 2002 | 2025-04-15 | 2025-04-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | West Yarmouth | ESMAEX-04804 | 02673 | 7.6 | Solar | 4-64-557 | 2025-04-17 | 2025-07-24 | 70 |  | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.92 | STA_961 Hyannis Junction
NSTAR | Mashpee | ESMAEX-04811 | 02649 | 11.5 | Other | 4-455-455 | 2025-04-17 | 2025-04-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  |  | STA_946 Mashpee
NSTAR | North Dartmouth | ESMAEX-04807 | 02747 | 10.2 | Solar | 2-107-107 | 2025-04-17 | 2025-04-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-31 | Online | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Lincoln | ESMAEX-04808 | 01773 | 6.14 | Solar | 320-H6 | 2025-04-17 | 2025-05-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-04 | Online | [11 empty] | 3.7 | STA_320 Lexington
NSTAR | Duxbury | ESMAEX-04817 | 02332 | 498 | Solar | 3-26-26 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_738 Duxbury
NSTAR | Winchester | ESMAEX-04818 | 01890 | 990 | Solar | 211-H2 | 2025-05-29 | 2025-06-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 990 | STA_211 Woburn
NSTAR | Hyannis | ESMAEX-04819 | 02601 | 10 | Solar | 4-63-521 | 2025-04-18 | 2025-04-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-31 | Online | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Chestnut Hill | ESMAEX-04854 | 02467 | 43.056 | Solar & Battery | 496-H5 | 2025-04-30 | 2025-05-08 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [11 empty] | 8.66 | STA_496 Hyde Park
NSTAR | Newton | ESMAEX-04838 | 02458 | 11.5 | Other | 467-H12 | 2025-04-23 | 2025-06-09 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Bedford | ESMAEX-04824 | 01730 | 23 | Solar & Battery | 533-H8 | 2025-04-22 | 2025-05-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-30 | Online | [11 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Walpole | ESMAEX-04840 | 02081 | 16.128 | Solar | 2601 | 2025-04-24 | 2025-05-07 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-20 | Online | [12 empty] | STA_146 Walpole
NSTAR | Harwich | ESMAEX-04826 | 02645 | 499 | Solar & Battery | 4-95A-95A | 2025-04-23 | 2025-05-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  | 499 | STA_968 Harwich
NSTAR | Plymouth | ESMAEX-04832 | 02360 | 11.5 | Other | 3-90-90 | 2025-04-23 | 2025-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Lincoln | ESMAEX-04827 | 01773 | 17.1 | Solar | 320-H6 | 2025-04-22 | 2025-04-28 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-03 | Online | [12 empty] | STA_320 Lexington
NSTAR | Dorchester | ESMAEX-05151 | 02125 | 49.7 | Solar |  | 2025-07-02 | 2025-08-05 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | West Barnstable | ESMAEX-04835 | 02668 | 330 | Solar | 4-84A-84A | 2025-06-27 | 2025-07-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Lexington | ESMAEX-04836 | 02421 | 23 | Other | 533-H1 | 2025-04-23 | 2025-05-26 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-22 | Online | [11 empty] | 13.34 | STA_533 Hartwell Avenue
NSTAR | West Dennis | ESMAEX-04841 | 02670 | 5 | Other |  | 2025-04-24 |  | -32661 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-18 | Online | [11 empty] | 0
NSTAR | Plymouth | ESMAEX-04837 | 02360 | 15.2 | Solar | 3-88-923 | 2025-04-23 | 2025-05-20 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-22 | Online | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Edgartown | ESMAEX-04954 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Cambridge | ESMAEX-04896 | 02138 | 50 | Solar | 828-1369 | 2025-05-07 | 2025-05-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_828 Alewife
NSTAR | Medfield | ESMAEX-04842 | 02052 | 6 | Solar | 146-H2 | 2025-04-24 | 2025-05-20 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-13 | Online | [12 empty] | STA_146 Walpole
NSTAR | Edgartown | ESMAEX-04955 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Winchester | ESMAEX-04920 | 01890 | 5.84 | Solar | 211-H1 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-14 | Online | [12 empty] | STA_211 Woburn
NSTAR | Pocasset | ESMAEX-04845 | 02559 | 23 | Solar & Battery | 4-86-408 | 2025-04-25 | 2025-05-20 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  | 19 | STA_915 Otis
NSTAR | North Dartmouth | ESMAEX-04849 | 02747 | 20 | Solar & Battery | 2-533-503 | 2025-04-28 | 2025-05-05 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-29 | Online | [8 empty] | Dartmouth-Westport |  |  | 10 | STA_651 Cross Road
NSTAR | Hopkinton | ESMAEX-04847 | 01748 | 22.288 | Solar & Battery | 274-H5 | 2025-04-28 | 2025-09-05 | 94 |  | 94 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_274 Sherborn
NSTAR | Chestnut Hill | ESMAEX-04848 | 02467 | 19.2 | Solar | 292-H5 | 2025-04-28 | 2025-05-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-04933 | 01720 | 10 | Other | 416-H1 | 2025-05-15 | 2025-06-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-27 | Online | [11 empty] | 0 | STA_416 Maynard
NSTAR | Newton Center | ESMAEX-04853 | 02459 | 11.5 | Other | 292-H11 | 2025-04-29 | 2025-05-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 9.99 | STA_292 Newton Highlands
NSTAR | Mattapan | ESMAEX-04859 | 02126 | 24.58 | Solar | 496-H8 | 2025-04-30 | 2025-06-09 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-04939 | 02493 | 9.24 | Solar | 282-H10 | 2025-05-15 | 2025-06-26 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 0 | STA_282 Waltham
NSTAR | East Sandwich | ESMAEX-04862 | 02537 | 21.88 | Solar | 4-87A-87A | 2025-05-01 | 2025-05-08 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | Carver | ESMAEX-04864 | 02330 | 7.6 | Solar | 3-10-10 | 2025-05-01 | 2025-05-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_737 West Pond
NSTAR | Canton | ESMAEX-04872 | 02021 | 200 | Solar | 470-H7 | 2025-05-05 | 2025-09-11 | 93 |  | 93 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 200 | STA_470 Canton
NSTAR | South Boston | ESMAEX-04869 | 02127 | 15.36 | Solar | 139-160H1 | 2025-05-02 | 2025-06-06 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-01 | Online
NSTAR | Mattapoisett | ESMAEX-04871 | 02739 | 10 | Solar | 2-302-302 | 2025-05-05 | 2025-05-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Marion-Fairhaven |  |  | 20 | STA_646 Crystal Spring
NSTAR | Boston | ESMAEX-04914 | 02118 | 27.3 | Solar | 318-14 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_106 Andrew Square
NSTAR | Newton Center | ESMAEX-04981 | 02459 | 160 | Solar | 17-H2 | 2025-05-27 | 2025-06-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Plymouth | ESMAEX-04874 | 02360 | 910 | Solar | 3-14-911 | 2025-06-11 | 2025-10-09 | 86 |  | 86 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_737 West Pond
NSTAR | Hyannis | ESMAEX-05058 | 02601 | 84.6 | Solar | 4-84A-84A | 2025-06-13 | 2025-07-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Boston | ESMAEX-04915 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-05-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Lincoln | ESMAEX-05031 | 01773 | 13.71 | Solar | 320-H6 | 2025-06-09 | 2025-07-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-04916 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-04918 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Watertown | ESMAEX-04885 | 02472 | 66.5 | Solar | 124-02 | 2025-05-06 | 2025-05-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Sherborn | ESMAEX-04889 | 01770 | 12.6 | Solar | 130-H2 | 2025-05-06 | 2025-05-20 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-06 | Online | [12 empty] | STA_130 Holliston
NSTAR | Fairhaven | ESMAEX-04890 | 02719 | 15.76 | Solar | 2-222-222 | 2025-05-06 | 2025-05-20 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Sharon | ESMAEX-04952 | 02067 | 18.85 | Solar |  | 2025-05-19 | 2025-05-28 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Sharon | ESMAEX-04899 | 02067 | 2.065 | Solar | 470-H12 | 2025-05-07 | 2025-05-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-04894 | 02421 | 11.904 | Solar & Battery | 320-H2 | 2025-05-07 | 2025-07-17 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Chelsea | ESMAEX-04897 | 02150 | 500 | Other | 488-H6 | 2025-07-11 | 2025-09-09 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 499 | STA_488 Chelsea
NSTAR | Hopkinton | ESMAEX-04944 | 01748 | 11.5 | Solar & Battery | 126-H2 | 2025-05-16 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [11 empty] | 12.2 | STA_126 Hopkinton
NSTAR | East Falmouth | ESMAEX-04901 | 02536 | 5.76 | Solar | 4-77A-77A | 2025-05-08 | 2025-05-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-01 | Online | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Acton | ESMAEX-04924 | 01720 | 51.9 | Solar | 416-H2 | 2025-05-15 | 2025-05-20 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_416 Maynard
NSTAR | Cambridge | ESMAEX-04926 | 02139 | 20 | Solar | 820-45 | 2025-05-15 | 2025-05-28 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-04927 | 02138 | 20 | Solar | 821-24 | 2025-05-15 | 2025-06-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_831 Putnam
NSTAR | East Cambridge | ESMAEX-04931 | 02141 | 17.6 | Solar | 812-16 | 2025-05-15 | 2025-06-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_875 East Cambridge
NSTAR | Acton | ESMAEX-04907 | 01720 | 20 | Other | 416-H2 | 2025-05-13 |  | -32674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [11 empty] | 20 | STA_416 Maynard
NSTAR | Mattapoisett | ESMAEX-04940 | 02739 | 19.1 | Solar & Battery | 2-302-302 | 2025-05-16 | 2025-05-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Wayland | ESMAEX-05117 | 01778 | 35.75 | Solar | 342-H3 | 2025-06-24 | 2025-07-17 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Sudbury | ESMAEX-04911 | 01776 | 15.2 | Solar | 342-H8 | 2025-05-13 | 2025-05-20 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-05321 | 01741 | 38.4 | Solar | 512-1399H1 | 2025-08-14 | 2025-09-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_533 Hartwell Avenue
NSTAR | New Bedford | ESMAEX-04912 | 02740 | 15.2 | Solar | 2-89-89 | 2025-05-13 | 2025-05-29 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Arlington | ESMAEX-04919 | 02476 | 29.592 | Solar & Battery | 320-H7 | 2025-05-14 | 2025-07-22 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 5.72 | STA_320 Lexington
NSTAR | Burlington | ESMAEX-04948 | 01803 | 23 | Other | 346-1395H1 | 2025-05-19 | 2025-06-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-18 | Online | [11 empty] | 19.99 | STA_391 Burlington
NSTAR | New Bedford | ESMAEX-04942 | 02746 | 10 | Other | 2-24-182 | 2025-05-16 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Newton Center | ESMAEX-04921 | 02459 | 15.2 | Solar | 443-02 | 2025-05-14 | 2025-05-20 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | Dover | ESMAEX-04971 | 02030 | 24.576 | Solar | 456-H3 | 2025-05-22 | 2025-06-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.99 | STA_456 Dover
NSTAR | North Truro | ESMAEX-04945 | 02652 | 11.5 | Other | 4-96-96 | 2025-05-17 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_976 Wellfleet
NSTAR | Edgartown | ESMAEX-04956 | 02539 | 31.5 | Solar | 4-75-227 | 2025-05-19 | 2025-06-19 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Boston | ESMAEX-04949 | 02127 | 960 | Solar | 99-H7 | 2025-06-03 | 2025-06-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_099 Seafood Way
NSTAR | Framingham | ESMAEX-04951 | 01701 | 4999 | Other | 455-H2 | 2025-07-31 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4999 | STA_455 West Framingham
NSTAR | Duxbury | ESMAEX-04970 | 02332 | 46 | Solar & Battery | 3-26-26 | 2025-05-22 | 2025-06-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-11 | Online | [11 empty] | 9.9
NSTAR | North Dartmouth | ESMAEX-04961 | 02747 | 16.5 | Solar | 2-70-506 | 2025-05-19 | 2025-06-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-23 | Online
NSTAR | Falmouth | ESMAEX-05104 | 02540 | 200 | Solar | 4-76-436 | 2025-06-23 | 2025-07-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Natick | ESMAEX-05186 | 01760 | 15.2 | Solar | 23-H1 | 2025-07-09 | 2025-07-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Permission to Operate | [11 empty] | 20 | STA_240 Framingham
NSTAR | Chelsea | ESMAEX-04979 | 02150 | 250 | Solar | 488-H7 | 2025-05-23 | 2025-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04978 | 02128 | 50 | Solar | 488-H8 | 2025-05-23 | 2025-06-09 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Boston | ESMAEX-05022 | 02124 | 100 | Solar | 511-1495H | 2025-06-06 | 2025-06-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Norfolk | ESMAEX-04967 | 02056 | 240 | Solar | 146-H9 | 2025-07-24 | 2025-08-05 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_146 Walpole
NSTAR | Waltham | ESMAEX-04968 | 02451 | 750 | Other | 450-H2 | 2025-08-12 | 2025-09-17 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 750 | STA_450 Trapelo Road
NSTAR | Natick | ESMAEX-04973 | 01760 | 750 | Other | 433-H9 | 2025-08-01 | 2025-09-09 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 750 | STA_433 Speen Street
NSTAR | Dorchester | ESMAEX-05039 | 02125 | 150 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_483 Dewar Street
NSTAR | Kingston | ESMAEX-04975 | 02364 | 9.9 | Solar & Battery | 3-18-18 | 2025-05-23 |  | -32682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [11 empty] | 9.9
NSTAR | Dorchester | ESMAEX-05038 | 02125 | 200 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_483 Dewar Street
NSTAR | Kingston | ESMAEX-04976 | 02364 | 28 | Solar & Battery | 3-17-17 | 2025-05-23 | 2025-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  | 9.9
NSTAR | Framingham | ESMAEX-04992 | 01702 | 100 | Solar | 455-H4 | 2025-05-29 | 2025-07-24 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_455 West Framingham
NSTAR | Roxbury | ESMAEX-05035 | 02119 | 110 | Solar | 143-151H1 | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Mattapoisett | ESMAEX-04982 | 02739 | 250 | Solar | 2-304-304 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Carlisle | ESMAEX-04996 | 01741 | 18.048 | Solar | 533-H8 | 2025-05-30 | 2025-07-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-24 | Online | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-04990 | 02021 | 15.2 | Solar | 470-H6 | 2025-05-29 | 2025-07-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_470 Canton
NSTAR | Sudbury | ESMAEX-04991 | 01776 | 15.2 | Solar | 342-H8 | 2025-05-29 | 2025-06-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-22 | Online | [12 empty] | STA_342 Sudbury
NSTAR | Framingham | ESMAEX-05053 | 01701 | 11.5 | Other | 342-H4 | 2025-06-12 | 2025-07-02 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Edgartown | ESMAEX-05002 | 02539 | 34.6 | Solar | 4-75-75 | 2025-06-02 | 2025-06-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | North Falmouth | ESMAEX-05017 | 02556 | 5 | Solar |  | 2025-06-05 | 2025-06-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape
NSTAR | Westport | ESMAEX-05055 | 02790 | 10 | Solar | 2-532-532 | 2025-06-13 | 2025-07-28 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Marshfield | ESMAEX-04999 | 02050 | 22.8 | Solar | 3-25-42J2 | 2025-05-30 | 2025-09-16 | 77 |  | 77 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19 | STA_738 Duxbury
NSTAR | Framingham | ESMAEX-05062 | 01701 | 10 | Solar | 278-H1 | 2025-06-13 |  | -32697 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_278 Saxonville
NSTAR | Millis | ESMAEX-05142 | 02054 | 20 | Solar & Battery | 65-H1 | 2025-06-28 |  | -32707 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-05003 | 01773 | 9.6 | Solar & Battery | 320-H8 | 2025-06-02 | 2025-08-14 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [11 empty] | 20 | STA_320 Lexington
NSTAR | Kingston | ESMAEX-05006 | 02364 | 17.6 | Solar | 3-15-15 | 2025-06-03 | 2025-06-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth
NSTAR | Teaticket | ESMAEX-05008 | 02536 | 400 | Solar | 4-76-437 | 2025-06-03 | 2025-06-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Dedham | ESMAEX-05009 | 02026 | 17.6 | Solar | 2007 | 2025-06-03 | 2025-06-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_110 Baker Street
NSTAR | Acton | ESMAEX-05020 | 01720 | 160 | Solar & Battery | 416-H5 | 2025-06-05 | 2025-07-07 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Walpole | ESMAEX-05014 | 02081 | 15.2 | Solar | 2606 | 2025-06-04 | 2025-06-19 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [12 empty] | STA_146 Walpole
NSTAR | East Falmouth | ESMAEX-05061 | 02536 | 11.5 | Other | 4-98B-449 | 2025-06-13 | 2025-07-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | West Wareham | ESMAEX-05019 | 02576 | 15.2 | Solar | 3-85-928 | 2025-06-05 | 2025-07-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Newton | ESMAEX-05101 | 02459 | 130 | Solar | 292-H3 | 2025-06-23 | 2025-08-18 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | East Harwich | ESMAEX-05025 | 02645 | 22.272 | Solar | 4-95A-95A | 2025-06-09 | 2025-08-14 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Lincoln | ESMAEX-05027 | 01773 | 24.75 | Solar |  | 2025-06-11 |  | -32695 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Boston | ESMAEX-05089 | 02119 | 40 | Solar | 510-77H | 2025-06-18 | 2025-06-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Duxbury | ESMAEX-05040 | 02332 | 20 | Solar | 3-23-23 | 2025-06-10 | 2025-07-17 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Duxbury | ESMAEX-05028 | 02332 | 23.8 | Solar | 3-17-17 | 2025-06-09 | 2025-07-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth
NSTAR | East Walpole | ESMAEX-05029 | 02032 | 5.7 | Solar | 146-H4 | 2025-06-09 | 2025-06-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Ashland | ESMAEX-05032 | 01721 | 5.76 | Solar | 274-H6 | 2025-06-09 | 2025-06-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-29 | Online
NSTAR | Canton | ESMAEX-05033 | 02021 | 720 | Solar | 470-H8 | 2025-08-14 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Duxbury | ESMAEX-05041 | 02332 | 20 | Solar | 3-23-23 | 2025-06-10 | 2025-07-17 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Newton Center | ESMAEX-05070 | 02459 | 40 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Sherborn | ESMAEX-05044 | 01770 | 15.2 | Solar | 274-H2 | 2025-06-10 | 2025-06-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-18 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Newton Center | ESMAEX-05071 | 02459 | 69 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 69 | STA_292 Newton Highlands
NSTAR | Duxbury | ESMAEX-05049 | 02332 | 20 | Solar | 3-23-23 | 2025-06-11 | 2025-07-17 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Newton Center | ESMAEX-05073 | 02459 | 50 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Falmouth | ESMAEX-05271 | 02540 | 184.3 | Solar | 4-76-436 | 2025-08-01 | 2025-08-07 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  |  | STA_933 Falmouth
NSTAR | Winchester | ESMAEX-05054 | 01890 | 24.16 | Solar | 211-H10 | 2025-06-13 | 2025-08-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_211 Woburn
NSTAR | Needham | ESMAEX-05065 | 02492 | 16.4 | Solar | 148-01 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | Carver | ESMAEX-05064 | 02330 | 1999 | Solar & Battery | 3-10-917 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | Plymouth |  | Hold In Queue | 1999 | STA_737 West Pond
NSTAR | Sherborn | ESMAEX-05077 | 01770 | 16.128 | Solar | 274-H2 | 2025-06-17 | 2025-06-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-30 | Online | [12 empty] | STA_274 Sherborn
NSTAR | Wellfleet | ESMAEX-05068 | 02667 | 34.8 | Solar & Battery | 4-94B-656 | 2025-06-16 | 2025-08-13 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-21 | Permission to Operate | [11 empty] | 17.6 | STA_976 Wellfleet
NSTAR | Marshfield | ESMAEX-05092 | 02050 | 21.88 | Solar & Battery | 3-24A-974 | 2025-06-19 | 2025-06-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [12 empty] | STA_739 Marshfield
NSTAR | Walpole | ESMAEX-05078 | 02081 | 15.2 | Solar | 146-H4 | 2025-06-17 | 2025-07-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Wayland | ESMAEX-05080 | 01778 | 6.588 | Solar | 278-H2 | 2025-06-17 | 2025-07-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-03 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Medfield | ESMAEX-05091 | 02052 | 0 | Battery | 456-H3 | 2025-06-18 | 2025-07-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-05079 | 02090 | 19 | Solar | 148-H3 | 2025-06-17 | 2025-07-20 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19 | STA_148 Needham
NSTAR | Centerville | ESMAEX-05103 | 02632 | 67.3 | Solar | 4-82-82 | 2025-06-23 | 2025-07-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Lexington | ESMAEX-05087 | 02420 | 15.2 | Solar | 533-H9 | 2025-06-18 | 2025-07-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-05130 | 01748 | 29.952 | Solar & Battery | 126-H4 | 2025-06-26 | 2025-07-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 8.9 | STA_126 Hopkinton
NSTAR | Holliston | ESMAEX-05088 | 01746 | 15.2 | Solar | 130-H1 | 2025-06-18 | 2025-07-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_130 Holliston
NSTAR | Maynard | ESMAEX-05090 | 01754 | 27.28 | Solar & Battery | 416-H6 | 2025-06-18 | 2025-08-08 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 14.85 | STA_416 Maynard
NSTAR | West Yarmouth | ESMAEX-05097 | 02673 | 11.5 | Solar & Battery | 4-92A-561 | 2025-06-20 | 2025-08-11 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_961 Hyannis Junction
NSTAR | Walpole | ESMAEX-05113 | 02081 | 240 | Solar | 146-H8 | 2025-06-25 | 2025-07-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Mattapoisett | ESMAEX-05098 | 02739 | 3.8 | Solar | 2-301-305 | 2025-06-20 | 2025-07-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Bedford | ESMAEX-05108 | 01730 | 19 | Solar | 533-H3 | 2025-06-23 | 2025-07-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Ashland | ESMAEX-05115 | 01721 | 15.2 | Solar & Battery | 274-H1 | 2025-06-24 | 2025-07-29 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_274 Sherborn
NSTAR | South Carver | ESMAEX-05110 | 02366 | 18.85 | Solar | 3-81-950 | 2025-06-23 | 2025-10-20 | 85 |  | 85 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Cataumet | ESMAEX-05135 | 02534 | 19.18 | Solar & Battery | 4-78-410 | 2025-06-26 | 2025-07-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Framingham | ESMAEX-05112 | 01701 | 15.376 | Solar & Battery | 278-H1 | 2025-06-24 | 2025-09-17 | 61 |  | 61 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_278 Saxonville
NSTAR | Sherborn | ESMAEX-05129 | 01770 | 4.392 | Solar & Battery | 130-H2 | 2025-06-26 | 2025-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_130 Holliston
NSTAR | Wayland | ESMAEX-05137 | 01778 | 15.738 | Solar | 278-H2 | 2025-06-27 | 2025-07-08 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-09 | Online | [12 empty] | STA_278 Saxonville
NSTAR | Mattapoisett | ESMAEX-05128 | 02739 | 15 | Solar | 2-301-305 | 2025-06-26 | 2025-07-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Framingham | ESMAEX-05121 | 01701 | 7.6 | Solar | 433-H4 | 2025-06-25 | 2025-07-03 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_433 Speen Street
NSTAR | Canton | ESMAEX-05138 | 02021 | 35.672 | Solar & Battery | 269-1320H1 | 2025-06-27 | 2025-08-22 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-05122 | 01754 | 199.8 | Solar | 342-H8 | 2025-06-25 | 2025-08-18 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-05123 | 01754 | 199.8 | Solar | 342-H8 | 2025-06-25 | 2025-09-17 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Sharon | ESMAEX-05124 | 02067 | 240 | Solar | 146-H1 | 2025-06-25 | 2025-08-18 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_146 Walpole
NSTAR | Plymouth | ESMAEX-05163 | 02360 | 990 | Solar | 3-14-911 | 2025-08-26 | 2025-10-14 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_737 West Pond
NSTAR | Assonett | ESMAEX-05134 | 02702 | 23 | Solar & Battery | 2-606-606 | 2025-06-26 | 2025-07-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-29 | Online | [11 empty] | 20 | STA_661 Bell Rock
NSTAR | New Bedford | ESMAEX-05255 | 02740 | 27.3 | Solar | 2-55-55 | 2025-07-30 | 2025-08-07 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 25 | STA_611 Pine Street
NSTAR | Waltham | ESMAEX-05144 | 02451 | 7.296 | Solar & Battery | 450-H6 | 2025-06-30 | 2025-09-05 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 12.75 | STA_450 Trapelo Road
NSTAR | Weston | ESMAEX-05201 | 02493 | 22.8 | Solar | 282-H1 | 2025-07-15 | 2025-08-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [12 empty] | STA_282 Waltham
NSTAR | Carlisle | ESMAEX-05146 | 01741 | 17.875 | Solar | 533-H8 | 2025-06-30 | 2025-07-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-06 | Online | [11 empty] | 1.59 | STA_533 Hartwell Avenue
NSTAR | Winchester | ESMAEX-05147 | 01890 | 31.95 | Solar & Battery | 211-H7XY | 2025-06-30 | 2025-07-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-29 | Online | [11 empty] | 20 | STA_211 Woburn
NSTAR | Millis | ESMAEX-05149 | 02054 | 15.744 | Solar & Battery | 130-H2 | 2025-07-01 | 2025-07-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_130 Holliston
NSTAR | Hyannis | ESMAEX-05157 | 02601 | 20.86 | Solar | 4-63-531 | 2025-07-07 | 2025-08-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 15 | STA_961 Hyannis Junction
NSTAR | Framingham | ESMAEX-05152 | 01702 | 7.8 | Battery | 455-H5 | 2025-07-02 | 2025-07-24 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 13.44 | STA_455 West Framingham
NSTAR | Fairhaven | ESMAEX-05159 | 02719 | 150 | Solar | 2-220-220 | 2025-07-07 | 2025-08-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Fairhaven | ESMAEX-05158 | 02719 | 150 | Solar | 2-240-209 | 2025-07-07 | 2025-08-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Wayland | ESMAEX-05156 | 01778 | 34.5 | Other | 342-H1 | 2025-07-04 | 2025-08-15 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Canton | ESMAEX-05164 | 02021 | 21.88 | Solar | 470-H6 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Bedford | ESMAEX-05165 | 01730 | 9.6 | Solar & Battery | 322-1397H1 | 2025-07-08 | 2025-10-27 | 79 |  | 79 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Harwich | ESMAEX-05188 | 02645 | 90 | Solar | 4-89A-556 | 2025-07-09 | 2025-09-04 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Woburn | ESMAEX-05167 | 01801 | 15.2 | Solar | 211-H6 | 2025-07-08 | 2025-07-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_211 Woburn
NSTAR | Dedham | ESMAEX-05175 | 02026 | 7.6 | Solar | 344-1412H1 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-06 | Online | [12 empty] | STA_496 Hyde Park
NSTAR | Woburn | ESMAEX-05177 | 01801 | 15.2 | Solar | 375-H6 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_375 Dragon Court
NSTAR | Acton | ESMAEX-05180 | 01720 | 17.66 | Solar | 126-H2 | 2025-07-08 | 2025-08-18 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 9.63 | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-05181 | 02090 | 15.2 | Solar | 148-H3 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | New Bedford | ESMAEX-05200 | 02745 | 38.95 | Solar | 2-104-104 | 2025-07-16 | 2025-08-18 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Framingham | ESMAEX-05187 | 01701 | 300 | Solar | 455-H6 | 2025-08-01 | 2025-08-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-05185 | 02744 | 480 | Solar |  | 2025-08-20 | 2025-11-05 | 55 |  | 55 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_611 Pine Street
NSTAR | Sherborn | ESMAEX-05218 | 01770 | 21.12 | Solar | 274-H2 | 2025-07-23 | 2025-08-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [11 empty] | 19 | STA_274 Sherborn
NSTAR | New Bedford | ESMAEX-05207 | 02744 | 180 | Solar | 2-62-62 | 2025-08-20 | 2025-09-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_611 Pine Street
NSTAR | Medfield | ESMAEX-05224 | 02052 | 16.512 | Solar | 146-H6 | 2025-07-24 | 2025-08-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Jamaica Plain | ESMAEX-05191 | 02130 | 10 | Solar | 350-H2 | 2025-07-11 | 2025-07-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Burlington | ESMAEX-05520 | 01803 | 100 | Solar | 391-H8 | 2025-09-26 | 2025-10-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_391 Burlington
NSTAR | Bellingham | ESMAEX-05196 | 02019 | 150 | Solar | 65-H4 | 2025-07-14 | 2025-08-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_065 Medway
NSTAR | Boston | ESMAEX-05220 | 02127 | 67.3 | Solar | 465-129H | 2025-07-22 | 2025-07-31 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_106 Andrew Square
NSTAR | Sagamore | ESMAEX-05406 | 02561 | 10.045 | Solar & Battery | 4-81A-81A | 2025-08-31 | 2025-09-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_915 Otis
NSTAR | Somerville | ESMAEX-05211 | 02143 | 17.28 | Solar | 13N29 | 2025-07-16 | 2025-08-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_250 Mystic
NSTAR | Boston | ESMAEX-05199 | 80302 | 249.99 | Solar | 323-78H1 | 2025-07-31 | 2025-09-17 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_106 Andrew Square
NSTAR | South Dartmouth | ESMAEX-05203 | 02748 | 10 | Solar | 2-524-524 | 2025-07-15 | 2025-07-24 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Plymouth | ESMAEX-05204 | 02360 | 240 | Solar | 3-73-927 | 2025-08-15 | 2025-09-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Boston | ESMAEX-05240 | 02115 | 34.6 | Solar |  | 2025-07-28 | 2025-09-04 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 0
NSTAR | New Bedford | ESMAEX-05210 | 02744 | 480 | Solar | 2-7-7 | 2025-08-20 | 2025-09-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_611 Pine Street
NSTAR | Boston | ESMAEX-05239 | 02136 | 70 | Solar | 60-1409H1 | 2025-07-28 | 2025-08-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Edgartown | ESMAEX-05229 | 02539 | 106.92 | Solar | 4-75-223 | 2025-07-25 | 2025-08-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_933 Falmouth
NSTAR | New Bedford | ESMAEX-05253 | 02745 | 200 | Solar | 2-103-103 | 2025-07-30 | 2025-09-25 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold | [8 empty] | Cape |  |  |  | STA_636 Industrial Park
NSTAR | Waltham | ESMAEX-05217 | 02453 | 45.87 | Solar | 467-H5 | 2025-07-18 | 2025-08-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Barnstable | ESMAEX-05237 | 02648 | 11.5 | Other |  | 2025-07-31 | 2025-08-25 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 0
NSTAR | Fairhaven | ESMAEX-05230 | 02719 | 200 | Solar | 2-220-201 | 2025-07-25 | 2025-08-01 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven |  |  |  | STA_654 Arsene
NSTAR | Dorchester | ESMAEX-05382 | 02125 | 200 | Solar | 511-1498H | 2025-08-27 | 2025-09-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_483 Dewar Street
NSTAR | Mattapoisett | ESMAEX-05238 | 02739 | 16 | Battery | 2-301-301 | 2025-07-28 | 2025-08-29 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  | 15.9 | STA_646 Crystal Spring
NSTAR | Dedham | ESMAEX-05225 | 02026 | 15.36 | Solar | 344-1413H1 | 2025-07-24 | 2025-08-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Plympton | ESMAEX-05352 | 02367 | 0 | Other | 3-50-50 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  |  | 5 | STA_727 Brook Street
NSTAR | Rochester | ESMAEX-05226 | 02770 | 10 | Solar | 3-85-85 | 2025-07-24 | 2025-11-06 | 75 |  | 75 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_713 Tremont
NSTAR | Watertown | ESMAEX-05264 | 02472 | 240 | Solar | 467-H4 | 2025-07-31 | 2025-08-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Lexington | ESMAEX-05231 | 02421 | 23 | Solar & Battery | 533-H4 | 2025-07-25 | 2025-08-11 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Bellingham | ESMAEX-05263 | 02019 | 200 | Solar | 65-H4 | 2025-07-31 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_065 Medway
NSTAR | Sudbury | ESMAEX-05232 | 01776 | 23.33 | Solar | 342-H8 | 2025-07-25 | 2025-08-11 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Marshfield | ESMAEX-05234 | 02050 | 30.29 | Solar & Battery | 3-27-970 | 2025-07-27 | 2025-08-07 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_738 Duxbury
NSTAR | Bourne | ESMAEX-05246 | 02559 | 160 | Solar |  | 2025-08-05 | 2025-08-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Sharon | ESMAEX-05241 | 02067 | 15.2 | Solar | 470-H12 | 2025-07-28 | 2025-08-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Falmouth | ESMAEX-05298 | 02540 | 200 | Solar | 4-98A-98A | 2025-08-08 | 2025-09-24 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  | 200 | STA_933 Falmouth
NSTAR | Sudbury | ESMAEX-05342 | 01776 | 11.5 | Other | 342-H2 | 2025-08-20 | 2025-09-17 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.34 | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-05254 | 02360 | 17.28 | Solar | 3-88-923 | 2025-07-30 | 2025-08-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | North Falmouth | ESMAEX-05329 | 02556 | 150 | Solar | 4-78-420 | 2025-08-15 | 2025-09-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_936 Hatchville
NSTAR | Wayland | ESMAEX-05257 | 01778 | 15.76 | Solar | 278-H2 | 2025-07-30 | 2025-08-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_278 Saxonville
NSTAR | North Dartmouth | ESMAEX-05258 | 02747 | 7.6 | Solar | 2-541-541 | 2025-07-30 | 2025-08-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  |  | STA_651 Cross Road
NSTAR | Mashpee | ESMAEX-05267 | 02649 | 90 | Other |  | 2025-07-31 | 2025-08-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Plymouth | ESMAEX-05323 | 02360 | 100 | Solar | 3-13-943 | 2025-08-14 | 2025-09-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_737 West Pond
NSTAR | West Yarmouth | ESMAEX-05266 | 02673 | 25 | Other | 4-64-557 | 2025-07-31 | 2025-09-04 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 25 | STA_961 Hyannis Junction
NSTAR | Westwood | ESMAEX-05261 | 02090 | 4999 | Other | 469-H4 | 2025-10-14 | 2025-11-05 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 4999 | STA_469 Ellis Avenue
NSTAR | North Eastham | ESMAEX-05269 | 02651 | 7.6 | Solar & Battery | 4-94A-94A | 2025-08-01 | 2025-08-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 19.9 | STA_975 Orleans
NSTAR | Sudbury | ESMAEX-05279 | 01776 | 20 | Other | 342-H7 | 2025-08-05 | 2025-08-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_342 Sudbury
NSTAR | Needham | ESMAEX-05284 | 02494 | 15.2 | Solar | 148-H1 | 2025-08-05 | 2025-08-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | West Yarmouth | ESMAEX-05491 | 02673 | 210 | Solar | 4-64-64 | 2025-09-19 | 2025-10-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_961 Hyannis Junction
NSTAR | Hyannis | ESMAEX-05490 | 02601 | 210 | Solar | 4-63-521 | 2025-09-19 | 2025-09-29 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | Orleans | ESMAEX-05273 | 02653 | 102.72 | Solar | 4-89B-89B | 2025-08-05 | 2025-08-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_975 Orleans
NSTAR | Lexington | ESMAEX-05275 | 02421 | 11.5 | Other | 320-H5XY | 2025-08-04 | 2025-08-11 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Wellfleet | ESMAEX-05274 | 02667 | 15.2 | Solar | 4-94B-656 | 2025-08-04 | 2025-08-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_976 Wellfleet
NSTAR | South Yarmouth | ESMAEX-05489 | 02664 | 180 | Solar | 4-92A-92A | 2025-09-19 | 2025-10-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_961 Hyannis Junction
NSTAR | West Roxbury | ESMAEX-05278 | 02132 | 5.376 | Solar & Battery | 496-H6 | 2025-08-05 | 2025-09-24 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-05281 | 02493 | 20.73 | Solar | 342-H1 | 2025-08-05 | 2025-08-14 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-05293 | 01760 | 17.3 | Solar | 23-H1 | 2025-08-07 | 2025-10-02 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_240 Framingham
NSTAR | Burlington | ESMAEX-05288 | 01803 | 6 | Solar | 391-H7 | 2025-08-06 | 2025-08-13 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-05295 | 01720 | 9.1 | Solar & Battery | 416-H5 | 2025-08-08 | 2025-08-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_416 Maynard
NSTAR | Newton Center | ESMAEX-05348 | 02459 | 19.2 | Solar | 292-H8 | 2025-08-22 | 2025-09-01 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Holliston | ESMAEX-05330 | 01746 | 4.392 | Solar & Battery | 274-H3 | 2025-08-18 | 2025-09-26 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_274 Sherborn
NSTAR | Plymouth | ESMAEX-05296 | 02360 | 13.36 | Solar | 3-90-90 | 2025-08-22 | 2025-09-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Chestnut Hill | ESMAEX-05299 | 02467 | 19.5 | Solar & Battery | 443-07 | 2025-08-09 | 2025-10-21 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_110 Baker Street
NSTAR | Waltham | ESMAEX-05380 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05378 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Rochester | ESMAEX-05300 | 02770 | 7.6 | Solar & Battery | 3-703-703 | 2025-08-11 | 2025-08-20 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  | 0 | STA_745 Rochester
NSTAR | Canton | ESMAEX-05307 | 02021 | 250 | Solar | 470-H7 | 2025-08-11 | 2025-11-03 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-05308 | 01773 | 9.15 | Solar | 320-H6 | 2025-08-12 | 2025-09-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Westwood | ESMAEX-05305 | 02090 | 16.5 | Solar | 456-H1 | 2025-08-11 | 2025-08-20 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_456 Dover
NSTAR | East Boston | ESMAEX-05304 | 02128 | 121.1 | Solar | 488-H5 | 2025-08-11 | 2025-09-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_488 Chelsea
NSTAR | Canton | ESMAEX-05303 | 02021 | 5.76 | Solar | 269-1320H1 | 2025-08-11 | 2025-08-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Waltham | ESMAEX-05379 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05366 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-10-03 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05365 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 | 2025-10-17 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | East Orleans | ESMAEX-05309 | 02643 | 20 | Solar | 4-628-628 | 2025-08-12 | 2025-08-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
NSTAR | Waltham | ESMAEX-05353 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Allston | ESMAEX-05312 | 02134 | 40 | Solar | 3604 | 2025-08-12 | 2025-08-20 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20
NSTAR | Boston | ESMAEX-05371 | 02122 | 250 | Solar | 483-H4 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_483 Dewar Street
NSTAR | Holliston | ESMAEX-05313 | 01746 | 17.28 | Solar | 274-H5 | 2025-08-13 | 2025-08-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_274 Sherborn
NSTAR | Cambridge | ESMAEX-05317 | 02138 | 240 | Solar | 828-1104H | 2025-08-14 | 2025-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_828 Alewife
NSTAR | Norfolk | ESMAEX-05314 | 02056 | 7.6 | Solar | 146-H3 | 2025-08-13 | 2025-08-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | North Cambridge | ESMAEX-05567 | 02140 | 173.6 | Solar | 825-20 | 2025-10-09 | 2025-11-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_828 Alewife
NSTAR | Osterville | ESMAEX-05324 | 02655 | 5 | Other | 4-80A-80A | 2025-08-14 | 2025-09-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_920 Oak Street
NSTAR | Natick | ESMAEX-05328 | 01760 | 220 | Solar | 433-H11 | 2025-08-15 | 2025-09-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Yarmouth | ESMAEX-05320 | 02664 | 240 | Solar | 4-64-64 | 2025-08-27 | 2025-10-03 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_961 Hyannis Junction
NSTAR | Pocasset | ESMAEX-05344 | 02559 | 9.91 | Battery | 4-81A-81A | 2025-08-20 |  | -32745 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_915 Otis
NSTAR | East Walpole | ESMAEX-05319 | 02032 | 3.8 | Solar | 135-1319H1 | 2025-08-14 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-05346 | 02421 | 19.2 | Solar & Battery | 3402 | 2025-08-20 | 2025-09-01 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.99 | STA_320 Lexington
NSTAR | Norfolk | ESMAEX-05322 | 02056 | 294.912 | Solar | 146-H3 | 2025-10-01 | 2025-10-10 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_146 Walpole
NSTAR | Chatham | ESMAEX-05325 | 02659 | 42.9 | Solar | 4-95A-95A | 2025-08-15 | 2025-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Holliston | ESMAEX-05374 | 01746 | 11.712 | Solar & Battery | 274-H3 | 2025-08-26 | 2025-09-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 10.7 | STA_274 Sherborn
NSTAR | Sudbury | ESMAEX-05333 | 01776 | 12.81 | Solar & Battery | 416-H6 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 16.32 | STA_416 Maynard
NSTAR | Newton Lower Falls | ESMAEX-05334 | 02462 | 3.3 | Solar & Battery | 292-H2 | 2025-08-18 | 2025-09-05 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Waban | ESMAEX-05335 | 02468 | 15.744 | Solar | 292-H12 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_292 Newton Highlands
NSTAR | Assonett | ESMAEX-05396 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-10-09 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_661 Bell Rock
NSTAR | Dedham | ESMAEX-05327 | 02026 | 11.5 | Solar & Battery | 2007 | 2025-08-15 | 2025-09-15 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_110 Baker Street
NSTAR | Lexington | ESMAEX-05360 | 02421 | 19.14 | Solar | 3401 | 2025-08-25 | 2025-09-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_320 Lexington
NSTAR | Rochester | ESMAEX-05331 | 02770 | 7.6 | Solar | 3-702-702 | 2025-08-15 | 2025-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | Lincoln | ESMAEX-05337 | 01773 | 23.81 | Solar | 320-H8 | 2025-08-18 | 2025-09-01 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_320 Lexington
NSTAR | North Dartmouth | ESMAEX-05336 | 02747 | 15.2 | Solar | 2-522-522 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Lexington | ESMAEX-05351 | 02420 | 16.83 | Solar | 533-H9 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Weston | ESMAEX-05338 | 02493 | 20 | Solar | 282-H8 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-05400 | 01720 | 15.36 | Solar | 416-H8 | 2025-08-29 | 2025-09-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 13.1 | STA_416 Maynard
NSTAR | Cambridge | ESMAEX-05568 | 02139 | 24.4 | Solar | 817-01 | 2025-10-09 | 2025-11-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_831 Putnam
NSTAR | Orleans | ESMAEX-05370 | 02653 | 150 | Solar | 4-83-83 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-05566 | 02139 | 54.4 | Solar | 817-02 | 2025-10-09 |  | -32781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_831 Putnam
NSTAR | Cambridge | ESMAEX-05586 | 02138 | 22.8 | Solar | 822-22 | 2025-10-14 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_828 Alewife
NSTAR | Cambridge | ESMAEX-05587 | 02139 | 50 | Solar | 831-1NA6 | 2025-10-14 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_831 Putnam
NSTAR | East Harwich | ESMAEX-05458 | 02645 | 66.24 | Solar | 4-95A-95A | 2025-09-15 | 2025-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Natick | ESMAEX-05341 | 01760 | 10 | Solar & Battery | 240-H1 | 2025-08-19 | 2025-08-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-15 | Online | [11 empty] | 14 | STA_240 Framingham
NSTAR | Burlington | ESMAEX-05343 | 01803 | 11.5 | Other | 346-1395H1 | 2025-08-20 | 2025-09-16 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-05392 | 01748 | 11.5 | Other | 126-H4 | 2025-08-28 | 2025-09-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.9 | STA_126 Hopkinton
NSTAR | Chelsea | ESMAEX-05345 | 02150 | 200 | Solar | 488-H2 | 2025-08-20 | 2025-09-01 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_488 Chelsea
NSTAR | Holliston | ESMAEX-05347 | 01746 | 23 | Solar & Battery | 65-H5 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 14.24 | STA_065 Medway
NSTAR | Kingston | ESMAEX-05349 | 02364 | 11.5 | Other | 3-18-18 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth
NSTAR | Dennisport | ESMAEX-05350 | 02639 | 6.144 | Solar & Battery | 4-92B-583 | 2025-08-21 | 2025-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_968 Harwich
NSTAR | Lincoln | ESMAEX-05381 | 01773 | 7.6 | Solar | 342-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Sudbury | ESMAEX-05359 | 01776 | 17.28 | Solar & Battery | 342-H6 | 2025-08-22 | 2025-09-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 19.99 | STA_342 Sudbury
NSTAR | Dover | ESMAEX-05373 | 02030 | 5.124 | Solar | 456-H5 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-05354 | 02420 | 7.6 | Solar | 391-H11 | 2025-08-22 | 2025-09-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_391 Burlington
NSTAR | Newton Center | ESMAEX-05358 | 02459 | 11.5 | Other | 292-H11 | 2025-08-22 | 2025-09-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-05363 | 02420 | 23 | Solar & Battery | 351-02 | 2025-08-25 | 2025-09-04 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_211 Woburn
NSTAR | Watertown | ESMAEX-05372 | 02472 | 10 | Other | 467-H4 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Dorchester | ESMAEX-05545 | 02121 | 42.8 | Solar | 143-109H6 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_106 Andrew Square
NSTAR | Dorchester | ESMAEX-05546 | 02121 | 42.8 | Solar | 143-04 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_106 Andrew Square
NSTAR | Maynard | ESMAEX-05369 | 01754 | 3.8 | Solar & Battery | 342-H8 | 2025-08-25 | 2025-09-05 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 8 | STA_342 Sudbury
NSTAR | New Bedford | ESMAEX-05395 | 02746 | 15.2 | Solar | 2-110-110 | 2025-08-29 | 2025-10-09 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_611 Pine Street
NSTAR | Medfield | ESMAEX-05383 | 02052 | 18.048 | Solar | 456-H2 | 2025-08-27 | 2025-09-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Wellfleet | ESMAEX-05403 | 02667 | 67.3 | Solar |  | 2025-08-29 | 2025-10-03 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Wayland | ESMAEX-05397 | 01778 | 15.84 | Solar | 342-H1 | 2025-08-29 | 2025-09-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Canton | ESMAEX-05384 | 02021 | 7.686 | Solar | 470-H10 | 2025-08-28 | 2025-09-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_470 Canton
NSTAR | Assonett | ESMAEX-05394 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-09-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [12 empty] | STA_661 Bell Rock
NSTAR | Natick | ESMAEX-05385 | 01760 | 6 | Solar | 240-H3 | 2025-08-27 | 2025-09-26 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_240 Framingham
NSTAR | Plymouth | ESMAEX-05440 | 02360 | 9.772 | Solar & Battery | 3-82-82 | 2025-09-10 | 2025-11-03 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Sudbury | ESMAEX-05386 | 01776 | 0 | Other | 342-H8 | 2025-08-27 | 2025-10-21 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-05387 | 02360 | 17.6 | Solar | 3-73-73 | 2025-08-28 | 2025-09-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Plymouth |  |  |  | STA_721 Manomet
NSTAR | Winchester | ESMAEX-05389 | 01890 | 38.064 | Solar & Battery | 211-H7XY | 2025-08-28 | 2025-09-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 20 | STA_211 Woburn
NSTAR | Lincoln | ESMAEX-05467 | 01773 | 30 | Other | 320-H6 | 2025-09-17 | 2025-09-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 20 | STA_320 Lexington
NSTAR | West Falmouth | ESMAEX-05412 | 02574 | 19.5 | Solar & Battery | 4-78-420 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Cape |  |  | 19.4 | STA_936 Hatchville
NSTAR | Bedford | ESMAEX-05393 | 01730 | 11.5 | Other | 533-H2 | 2025-08-28 | 2025-09-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | West Somerville | ESMAEX-05488 | 02144 | 50 | Solar | 250-H6 | 2025-09-19 | 2025-10-02 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_250 Mystic
NSTAR | Rochester | ESMAEX-05399 | 02770 | 15.76 | Solar | 3-703-703 | 2025-08-29 | 2025-09-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_745 Rochester
NSTAR | North Chatham | ESMAEX-05404 | 02650 | 8.58 | Solar | 4-95B-95B | 2025-08-30 |  | -32752 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_975 Orleans
NSTAR | Brookline | ESMAEX-05438 | 02446 | 140 | Solar | 350-H8 | 2025-09-09 | 2025-10-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Winchester | ESMAEX-05421 | 01890 | 36.176 | Solar & Battery | 211-H7XY | 2025-09-04 | 2025-09-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 19.99 | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-05408 | 01748 | 7.6 | Solar | 126-H2 | 2025-09-02 | 2025-09-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-05410 | 02420 | 11.5 | Other | 351-02 | 2025-09-02 | 2025-09-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 13.88 | STA_211 Woburn
NSTAR | Chestnut Hill | ESMAEX-05413 | 02467 | 7.4 | Solar | 329-H6 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_329 Brighton
NSTAR | East Wareham | ESMAEX-05414 | 02538 | 3.8 | Solar | 3-82-82 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Plymouth |  |  |  | STA_714 Wareham
NSTAR | Kingston | ESMAEX-05416 | 02364 | 200 | Solar | 3-14-14 | 2025-09-23 | 2025-10-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_737 West Pond
NSTAR | Newton Center | ESMAEX-05418 | 02459 | 21.4 | Solar & Battery | 467-H14 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [11 empty] | 25 | STA_467 Watertown
NSTAR | Medway | ESMAEX-05419 | 02053 | 200 | Solar | 65-H1 | 2025-09-03 | 2025-09-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_065 Medway
NSTAR | Orleans | ESMAEX-05433 | 02653 | 7.26 | Solar | 4-94A-94A | 2025-09-09 | 2025-10-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-05588 | 02139 | 20 | Solar | 814-12 | 2025-10-14 | 2025-10-23 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_402 Newton Street
NSTAR | Medfield | ESMAEX-05424 | 02052 | 20.13 | Solar | 146-H2 | 2025-09-05 | 2025-09-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-05425 | 01801 | 11.5 | Solar & Battery | 533-H9 | 2025-09-05 | 2025-09-17 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-05428 | 01760 | 17.49 | Solar | 240-H5 | 2025-09-16 | 2025-09-30 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_240 Framingham
NSTAR | Mashpee | ESMAEX-05426 | 02649 | 20 | Solar & Battery | 4-452-452 | 2025-09-08 |  | -32758 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  | 19.9 | STA_946 Mashpee
NSTAR | Mashpee | ESMAEX-05429 | 02649 | 15.2 | Solar | 4-81B-81B | 2025-09-08 | 2025-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Cape |  |  |  | STA_916 Sandwich
NSTAR | Framingham | ESMAEX-05431 | 01701 | 19.584 | Solar | 455-H1 | 2025-09-08 | 2025-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_455 West Framingham
NSTAR | Westwood | ESMAEX-05430 | 02090 | 20 | Solar | 469-H2 | 2025-09-08 | 2025-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Arlington | ESMAEX-05530 | 02474 | 4.95 | Solar & Battery | 211-H11 | 2025-09-30 | 2025-10-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 16 | STA_211 Woburn
NSTAR | Canton | ESMAEX-05499 | 02021 | 10 | Solar | 470-H11 | 2025-09-23 | 2025-10-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Dover | ESMAEX-05432 | 02030 | 17.56 | Solar | 456-H5 | 2025-09-09 | 2025-09-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_456 Dover
NSTAR | Norfolk | ESMAEX-05441 | 02056 | 14.976 | Solar | 146-H10 | 2025-09-10 | 2025-10-22 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_146 Walpole
NSTAR | Lincoln | ESMAEX-05434 | 01773 | 15.2 | Solar | 320-H8 | 2025-09-09 | 2025-09-17 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_320 Lexington
NSTAR | West Wareham | ESMAEX-05435 | 02576 | 15.744 | Solar | 3-86-966 | 2025-09-09 | 2025-09-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Plymouth |  |  |  | STA_713 Tremont
NSTAR | Dartmouth | ESMAEX-05436 | 02747 | 367.22 | Solar | 2-541-541 | 2025-09-30 | 2025-10-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_651 Cross Road
NSTAR | Hopkinton | ESMAEX-05452 | 01748 | 9.15 | Solar | 126-H4 | 2025-09-23 | 2025-09-30 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 7.5 | STA_126 Hopkinton
NSTAR | Walpole | ESMAEX-05439 | 02081 | 20 | Solar | 456-H1 | 2025-09-09 | 2025-09-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_456 Dover
NSTAR | Arlington | ESMAEX-05442 | 02474 | 17.92 | Solar | 211-H3 | 2025-09-10 |  | -32760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-05444 | 01748 | 11.5 | Other | 126-H1 | 2025-09-10 | 2025-09-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 3.8 | STA_126 Hopkinton
NSTAR | East Boston | ESMAEX-05446 | 02128 | 103.8 | Solar | 488-H5 | 2025-09-11 | 2025-10-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_488 Chelsea
NSTAR | Marshfield | ESMAEX-05445 | 02050 | 30 | Solar | 3-25-25 | 2025-09-10 | 2025-10-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Hopkinton | ESMAEX-05512 | 01748 | 18.048 | Solar | 274-H5 | 2025-09-25 |  | -32771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_274 Sherborn
NSTAR | Milton | ESMAEX-05466 | 02186 | 3.294 | Solar | 496-H7 | 2025-09-16 | 2025-09-29 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 16.528 | STA_496 Hyde Park
NSTAR | Boston | ESMAEX-05532 | 02130 | 50 | Solar | 350-H7 | 2025-10-01 | 2025-10-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_350 Colburn Street
NSTAR | Dennis | ESMAEX-05448 | 02638 | 15.2 | Solar | 4-89A-89A | 2025-09-12 | 2025-09-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Cape |  |  |  | STA_968 Harwich
NSTAR | Lexington | ESMAEX-05453 | 02420 | 7.24 | Solar | 533-H4 | 2025-09-15 | 2025-09-22 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [11 empty] | 7.24 | STA_533 Hartwell Avenue
NSTAR | West Newton | ESMAEX-05451 | 02465 | 18 | Other | 1713 | 2025-09-14 |  | -32762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_292 Newton Highlands
NSTAR | Provincetown | ESMAEX-05456 | 02657 | 25 | Solar | 4-675-974 | 2025-09-15 | 2025-10-15 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Sharon | ESMAEX-05460 | 02067 | 100 | Solar | 146-H1 | 2025-09-15 | 2025-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_146 Walpole
NSTAR | Burlington | ESMAEX-05459 | 01803 | 15.2 | Solar & Battery | 391-H7 | 2025-09-15 | 2025-09-24 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [11 empty] | 20 | STA_391 Burlington
NSTAR | Sudbury | ESMAEX-05461 | 01776 | 12.87 | Solar | 342-H7 | 2025-09-15 |  | -32763 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_342 Sudbury
NSTAR | Dover | ESMAEX-05462 | 02030 | 45.6 | Solar | 456-H5 | 2025-09-16 |  | -32764 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_456 Dover
NSTAR | Dover | ESMAEX-05465 | 02030 | 23 | Solar & Battery | 456-H5 | 2025-09-16 | 2025-10-16 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_456 Dover
NSTAR | North Dartmouth | ESMAEX-05472 | 02747 | 15.2 | Solar | 2-523-523 | 2025-09-23 | 2025-11-02 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_657 Fisher Road
NSTAR | Wayland | ESMAEX-05478 | 01778 | 18.48 | Solar | 278-H2 | 2025-09-17 | 2025-10-08 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_278 Saxonville
NSTAR | Milton | ESMAEX-05475 | 02186 | 23 | Solar & Battery | 362-02 | 2025-09-17 | 2025-10-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_496 Hyde Park
NSTAR | Mattapoisett | ESMAEX-05497 | 02739 | 11.5 | Solar & Battery | 3-702-702 | 2025-09-23 | 2025-11-05 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_745 Rochester
NSTAR | New Bedford | ESMAEX-05476 | 02740 | 17.3 | Solar | 2-89-89 | 2025-09-17 | 2025-09-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_611 Pine Street
NSTAR | Plymouth | ESMAEX-05479 | 02360 | 17.16 | Solar | 3-89-922 | 2025-09-17 | 2025-09-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Plymouth |  |  |  | STA_715 Valley
NSTAR | Sudbury | ESMAEX-05481 | 01776 | 15.2 | Solar | 416-H6 | 2025-09-17 |  | -32765 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_416 Maynard
NSTAR | North Dartmouth | ESMAEX-05482 | 02747 | 11.4 | Solar | 2-522-522 | 2025-09-17 | 2025-09-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Dartmouth-Westport |  |  | 11 | STA_657 Fisher Road
NSTAR | Carlisle | ESMAEX-05483 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2025-09-18 | 2025-09-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [11 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | South Yarmouth | ESMAEX-05484 | 02664 | 7.6 | Solar | 4-92A-560 | 2025-09-18 | 2025-10-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_961 Hyannis Junction
NSTAR | Holliston | ESMAEX-05486 | 01746 | 18.48 | Solar | 274-H3 | 2025-09-19 | 2025-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_274 Sherborn
NSTAR | West Tisbury | ESMAEX-05505 | 02568 | 45.6 | Solar & Battery |  | 2025-09-24 | 2025-10-02 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_933 Falmouth
NSTAR | Medfield | ESMAEX-05492 | 02052 | 19.2 | Solar | 146-H2 | 2025-09-22 |  | -32768 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | Oak Bluffs | ESMAEX-05514 | 02557 | 33.6 | Solar |  | 2025-09-25 | 2025-10-21 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Arlington | ESMAEX-05494 | 02474 | 13.2 | Solar | 211-H3 | 2025-09-22 | 2025-10-16 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_211 Woburn
NSTAR | Bourne | ESMAEX-05495 | 02532 | 23 | Solar & Battery | 4-86-408 | 2025-09-22 | 2025-10-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_915 Otis
NSTAR | Sharon | ESMAEX-05496 | 02067 | 50 | Solar |  | 2025-09-23 | 2025-10-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Weston | ESMAEX-05509 | 02493 | 21.12 | Solar | 282-H1 | 2025-09-25 | 2025-10-06 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_282 Waltham
NSTAR | Medfield | ESMAEX-05518 | 02052 | 15.2 | Solar | 146-H10 | 2025-09-26 |  | -32772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-05515 | 01720 | 13.82 | Solar | 416-H5 | 2025-09-25 | 2025-10-09 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Canton | ESMAEX-05517 | 02021 | 24.57 | Solar | 470-H11 | 2025-09-25 | 2025-10-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | Plymouth | ESMAEX-05528 | 02360 | 8.064 | Solar & Battery |  | 2025-09-30 |  | -32774 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Boston | ESMAEX-05570 | 02134 | 15.3 | Solar & Battery |  | 2025-10-10 |  | -32782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Weston | ESMAEX-05551 | 02493 | 25.986 | Solar | 282-H1 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_282 Waltham
NSTAR | Oak Bluffs | ESMAEX-05585 | 02557 | 10 | Other | 4-99-99 | 2025-10-14 | 2025-11-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 0 | STA_933 Falmouth
NSTAR | Acton | ESMAEX-05529 | 01720 | 11.4 | Solar | 416-H5 | 2025-09-30 | 2025-10-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Waltham | ESMAEX-05562 | 02451 | 20 | Solar | 282-H5 | 2025-10-08 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05563 | 02451 | 20 | Solar | 282-H1 | 2025-10-08 | 2025-10-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_282 Waltham
NSTAR | Roslindale | ESMAEX-05543 | 02131 | 90 | Solar |  | 2025-10-03 |  | -32777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Framingham | ESMAEX-05571 | 01702 | 18.3 | Solar | 455-H5 | 2025-10-10 | 2025-10-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_455 West Framingham
NSTAR | Acton | ESMAEX-05533 | 01720 | 20 | Solar & Battery | 416-H5 | 2025-10-02 | 2025-10-16 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_416 Maynard
NSTAR | Boston | ESMAEX-05542 | 02118 | 80 | Solar |  | 2025-10-03 |  | -32777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Dorchester | ESMAEX-05541 | 02124 | 150 | Solar | 4302 | 2025-10-03 |  | -32777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_483 Dewar Street
NSTAR | Canton | ESMAEX-05537 | 02021 | 17.16 | Solar | 470-H4 | 2025-10-03 | 2025-10-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_470 Canton
NSTAR | South Boston | ESMAEX-05540 | 02127 | 167.3 | Solar | 106-H3 | 2025-10-03 |  | -32777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_106 Andrew Square
NSTAR | Westport | ESMAEX-05538 | 02790 | 22.8 | Solar | 2-523-523 | 2025-10-03 | 2025-10-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | Dartmouth-Westport |  |  |  | STA_657 Fisher Road
NSTAR | Marstons Mills | ESMAEX-05544 | 02648 | 23 | Solar & Battery | 4-80A-80A | 2025-10-06 | 2025-11-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_920 Oak Street
NSTAR | Cambridge | ESMAEX-05580 | 02138 | 50 | Solar | 819-1NC5 | 2025-10-14 | 2025-10-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_402 Newton Street
NSTAR | Framingham | ESMAEX-05548 | 01701 | 15.2 | Solar & Battery | 455-H1 | 2025-10-06 | 2025-10-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 20 | STA_455 West Framingham
NSTAR | Mashpee | ESMAEX-05549 | 02649 | 23 | Solar & Battery | 4-71-71 | 2025-10-17 | 2025-10-27 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_946 Mashpee
NSTAR | Bedford | ESMAEX-05550 | 01730 | 34.5 | Solar | 533-H7 | 2025-10-06 | 2025-10-10 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Lincoln | ESMAEX-05560 | 01773 | 24.42 | Solar & Battery | 320-H8 | 2025-10-08 | 2025-10-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_320 Lexington
NSTAR | Eastham | ESMAEX-05553 | 02642 | 12.672 | Solar & Battery | 4-94A-94A | 2025-10-07 | 2025-10-21 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_975 Orleans
NSTAR | Lexington | ESMAEX-05578 | 02421 | 10 | Solar | 320-H2 | 2025-10-13 | 2025-10-21 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-05555 | 02119 | 50 | Solar |  | 2025-10-07 | 2025-11-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_106 Andrew Square
NSTAR | Centerville | ESMAEX-05554 | 02632 | 10 | Solar | 4-80A-80A | 2025-10-07 | 2025-11-02 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_920 Oak Street
NSTAR | Allston | ESMAEX-05606 | 02134 | 15.7 | Solar | 315-H3 | 2025-10-21 | 2025-11-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_315 Electric Avenue
NSTAR | Lexington | ESMAEX-05565 | 02420 | 16.128 | Solar | 533-H9 | 2025-10-09 | 2025-10-17 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Marion | ESMAEX-05561 | 02738 | 10 | Solar | 3-304-304 | 2025-10-08 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [8 empty] | Marion-Fairhaven |  |  |  | STA_646 Crystal Spring
NSTAR | Framingham | ESMAEX-05569 | 01701 | 20 | Solar & Battery | 455-H1 | 2025-10-09 | 2025-10-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [11 empty] | 20 | STA_455 West Framingham
NSTAR | Natick | ESMAEX-05581 | 01760 | 21.504 | Solar & Battery | 433-H5 | 2025-10-14 | 2025-10-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_433 Speen Street
NSTAR | Boston | ESMAEX-05591 | 02130 | 27.3 | Solar | 284-1430H | 2025-10-15 | 2025-11-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_350 Colburn Street
NSTAR | Lexington | ESMAEX-05576 | 02421 | 18.24 | Solar | 320-H2 | 2025-10-12 |  | -32782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_320 Lexington
NSTAR | Wayland | ESMAEX-05589 | 01778 | 20.7 | Solar | 342-H1 | 2025-10-14 |  | -32784 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [12 empty] | STA_342 Sudbury
NSTAR | Fairhaven | ESMAEX-05582 | 02719 | 16.128 | Solar | 2-220-201 | 2025-10-14 | 2025-11-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_654 Arsene
NSTAR | Canton | ESMAEX-05579 | 02021 | 15.36 | Solar | 269-1320H1 | 2025-10-13 | 2025-10-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [12 empty] | STA_470 Canton
NSTAR | Needham | ESMAEX-05657 | 02492 | 3.84 | Solar & Battery | 148-01 | 2025-10-29 |  | -32795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | Natick | ESMAEX-05597 | 01760 | 15.84 | Solar | 240-H1 | 2025-10-16 | 2025-10-21 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [11 empty] | 12.4 | STA_240 Framingham
NSTAR | Acton | ESMAEX-05599 | 01720 | 23.04 | Solar & Battery | 416-H5 | 2025-10-16 |  | -32786 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_416 Maynard
NSTAR | Medway | ESMAEX-05598 | 02053 | 10 | Solar | 65-H3 | 2025-10-16 | 2025-11-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_065 Medway
NSTAR | Westwood | ESMAEX-05608 | 02090 | 3.8 | Solar | 456-H1 | 2025-10-21 | 2025-11-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-05602 | 02420 | 15.51 | Solar |  | 2025-10-17 |  | -32787 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | West Somerville | ESMAEX-05604 | 02144 | 15.2 | Solar | 1607 | 2025-10-21 | 2025-11-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_828 Alewife
NSTAR | Lincoln | ESMAEX-05605 | 01773 | 23 | Solar & Battery | 320-H6 | 2025-10-21 |  | -32789 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_320 Lexington
NSTAR | Carlisle | ESMAEX-05610 | 01741 | 0 | Other | 512-1399H1 | 2025-10-22 |  | -32790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_533 Hartwell Avenue
NSTAR | Boston | ESMAEX-05614 | 02118 | 114.8 | Solar | 318-10 | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-05615 | 02215 | 134.6 | Solar | 3603 | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-05616 | 02119 | 34.6 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Ashland | ESMAEX-05665 | 01721 | 7.68 | Solar & Battery | 274-H5 | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_274 Sherborn
NSTAR | Boston | ESMAEX-05617 | 02118 | 77.3 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Boston | ESMAEX-05618 | 02126 | 67.3 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Jamaica Plain | ESMAEX-05619 | 02130 | 51.9 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Roxbury | ESMAEX-05620 | 02119 | 100 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Boston | ESMAEX-05621 | 02128 | 66.6 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Boston | ESMAEX-05622 | 02116 | 150 | Solar |  | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Westport | ESMAEX-05609 | 02790 | 20 | Solar & Battery | 2-532-532 | 2025-10-21 | 2025-11-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Dartmouth-Westport |  |  | 25 | STA_651 Cross Road
NSTAR | Sudbury | ESMAEX-05611 | 01776 | 13.44 | Other | 416-H7 | 2025-10-22 |  | -32790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_416 Maynard
NSTAR | Canton | ESMAEX-05640 | 02021 | 25.44 | Solar & Battery | 470-H10 | 2025-10-27 |  | -32793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_470 Canton
NSTAR | Natick | ESMAEX-05626 | 01760 | 10 | Solar & Battery | 240-H2 | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_240 Framingham
NSTAR | Sudbury | ESMAEX-05627 | 01776 | 24 | Solar | 342-H2 | 2025-10-23 |  | -32791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-05638 | 01760 | 8.25 | Solar | 433-H5 | 2025-10-27 |  | -32793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_433 Speen Street
NSTAR | Sudbury | ESMAEX-05632 | 01776 | 20 | Solar | 342-H4 | 2025-10-24 | 2025-11-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_342 Sudbury
NSTAR | Westport | ESMAEX-05633 | 02791 | 8.7 | Other | 2-523-523 | 2025-10-24 |  | -32792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_657 Fisher Road
NSTAR | East Walpole | ESMAEX-05676 | 02032 | 5.76 | Solar | 135-1319H1 | 2025-10-31 |  | -32797 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_146 Walpole
NSTAR | East Dennis | ESMAEX-05637 | 02641 | 6.912 | Solar & Battery | 4-89A-89A | 2025-10-28 | 2025-11-06 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [12 empty] | STA_968 Harwich
NSTAR | Mattapoisett | ESMAEX-05649 | 02739 | 34.94 | Solar |  | 2025-10-28 |  | -32794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Dorchester | ESMAEX-05674 | 02125 | 180 | Solar | 511-1498H | 2025-10-31 |  | -32797 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_483 Dewar Street
NSTAR | Marshfield | ESMAEX-05644 | 02050 | 25 | Solar | 3-24A-24A | 2025-10-27 |  | -32793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_739 Marshfield
NSTAR | Newton | ESMAEX-05646 | 02458 | 11.5 | Solar & Battery | 467-H14 | 2025-10-28 |  | -32794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-05648 | 01760 | 15.2 | Solar | 240-H5 | 2025-10-28 |  | -32794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Review
NSTAR | Lexington | ESMAEX-05653 | 02421 | 23 | Solar & Battery | 320-H5XY | 2025-10-28 |  | -32794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_320 Lexington
NSTAR | Acusnet | ESMAEX-05654 | 02743 | 10 | Solar | 2-241-241 | 2025-10-29 | 2025-11-06 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | Marion-Fairhaven |  |  |  | STA_624 Wing Lane
NSTAR | Harwichport | ESMAEX-05663 | 02646 | 25 | Solar |  | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents
NSTAR | Westwood | ESMAEX-05658 | 02090 | 10 | Solar | 148-H3 | 2025-10-29 |  | -32795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-05660 | 02747 | 3.8 | Solar | 2-107-107 | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_636 Industrial Park
NSTAR | Monument Beach | ESMAEX-05664 | 02553 | 10 | Solar | 4-86-408 | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_915 Otis
NSTAR | Hopkinton | ESMAEX-05666 | 01748 | 15.2 | Solar | 126-H4 | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study
NSTAR | Brewster | ESMAEX-05667 | 02631 | 15.2 | Solar |  | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Eastham | ESMAEX-05668 | 02642 | 27.6 | Solar & Battery | 4-94A-94A | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliances Documents | [12 empty] | STA_975 Orleans
NSTAR | Acton | ESMAEX-05669 | 01720 | 21.4 | Solar & Battery |  | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study
NSTAR | Wareham | ESMAEX-05673 | 02571 | 100 | Solar | 3-86-966 | 2025-10-31 |  | -32797 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [12 empty] | STA_713 Tremont
WMECO | Springfield | 6S21-2009 | 1105 | 75 | Solar | 8C14 | 2009-03-30 | 2009-04-13 | 11 |  | 11 | [25 empty] | 2009-04-24 |  | 07/2009 | No | Expedited | [8 empty] | 2009-07-23 | Online
WMECO | Savoy | 6B44-2009 | 1256 | 10000 | Wind | 18C1 | 2009-06-26 | [31 empty] | 2010-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A82-2009 | 1002 | 39 | Solar | 17K2 | 2009-06-29 | 2009-07-24 | 20 |  | 20 | [25 empty] | 2009-07-30 |  | 08/2009 | No | Expedited | [8 empty] | 2009-08-10 | Online
WMECO | Leverett | 6A91-2009 | 1054 | 13.8 | Solar | 18G7 | 2009-07-28 | 2009-09-14 | 35 |  | 35 | [25 empty] | 2009-09-17 |  | 08/2009 or 09/2009 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B46-2009 | 1201 | 86 | Solar | 15E3 | 2009-07-29 | 2009-09-29 | 45 |  | 45 | [25 empty] | 2009-09-30 |  | 11/2009 | No | Expedited | [8 empty] | 2010-01-14 | Online
WMECO | Pittsfield | 6B47-2009 | 1201 | 95 | Solar | 19A5 | 2009-07-29 | 2009-09-15 | 35 |  | 35 | [25 empty] | 2009-09-16 |  | 11/2009 | No | Expedited | [8 empty] | 2009-11-10 | Online
WMECO | Lee | 6B55-2009 | 1238 | 125 | Solar | 16B5 | 2009-11-05 | [31 empty] | 2009-11-15 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S34-2009 | 1104 | 50 | Solar | 5J13 | 2009-11-13 | [31 empty] | 2009-11-15 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B59-2009 | 1201 | 126.9 | Solar | 19A2 | 2009-12-01 | [31 empty] | 2009-12-31 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S35-2009 | 1105 | 30 | Solar | 8C26 | 2009-12-01 | 2009-12-30 | 22 |  | 22 | [25 empty] | 2010-01-11 |  | 2009-12-30 | No | Expedited | [8 empty] | 2010-02-12 | Online
WMECO | Lee | 6B60-2009 | 1238 | 125 | Solar | 16B5 | 2009-12-09 | 2009-12-16 | 6 |  | 6 | [25 empty] | 2009-12-24 |  | 2009-12-31 | No | Expedited | [8 empty] | 2009-12-30 | Online
WMECO | Springfield | 6S36-2009 | 1111 | 87 | Solar | 5J14 | 2009-12-24 | 2010-01-29 | 27 |  | 27 | [25 empty] | 2010-02-08 |  | 2010-03-26 | No | Expedited | [8 empty] | 2010-08-11 | Online
WMECO | Hancock | 6B62-2009 | 1237 | 81.2 | Solar | 30B7 | 2009-12-28 | [31 empty] | 2009-12-31 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S37-2009 | 1104 | 95 | Solar | 5J14 | 2009-12-28 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A104-2009 | 1002 | 2000 | Natural Gas / Fuel Oil | 18G2 | 2009-12-30 | 2010-02-17 | 36 |  | 36 | [15 empty] | 2010-07-19 |  | -28841 | [7 empty] | 2011-02-22 |  | 09/2010 | Yes | Standard | [8 empty] | 2011-03-01 | Online
WMECO | Springfield | 6S38-2010 | 1104 | 38.07 | Solar | 5J13 | 2010-01-05 | 2010-01-29 | 19 |  | 19 | [25 empty] | 2010-02-02 |  | 2010-01-15 | No | Expedited | [8 empty] | 2010-02-19 | Online
WMECO | Hancock | 6B63-2010 | 1237 | 81.2 | Solar | 30B7 | 2010-01-12 | 2010-02-08 | 20 |  | 20 | [25 empty] | 2010-02-19 |  | 2009-12-31 | No | Expedited | [8 empty] | 2010-03-09 | Online
WMECO | Pittsfield | 6B64-2010 | 1201 | 126.91 | Solar | 19A2 | 2010-01-12 | 2010-01-28 | 13 |  | 13 | [25 empty] | 2010-02-09 |  | 2009-12-31 | No | Expedited | [8 empty] | 2010-02-25 | Online
WMECO | Springfield | 6S39-2010 | 1104 | 95 | Solar | 5J14 | 2010-02-03 | 2010-03-05 | 23 |  | 23 | [25 empty] | 2010-04-05 |  | 2010-03-15 | No | Expedited | [8 empty] | 2010-10-13 | Online
WMECO | Leverett | 6A107-2010 | 1054 | 13.795 | Solar | 18G7 | 2010-02-05 | 2010-02-11 | 5 |  | 5 | [25 empty] | 2010-02-12 |  | 2010-02-01 | Yes | Expedited | [8 empty] | 2010-02-18 | Online
WMECO | Amherst | 6A110-2010 | 1002 | 14.7 | Solar | 17K3 | 2010-04-01 | 2010-04-12 | 8 |  | 8 | [25 empty] | 2010-05-18 |  | 5/2010 | Yes | Expedited | [8 empty] | 2010-06-23 | Online
WMECO | Shelburne | 6F155-2010 | 1370 | 24.2 | Solar | 22B5 | 2010-04-06 | 2010-04-22 | 13 |  | 13 | [25 empty] | 2010-04-27 |  | 5/2010 | Yes | Expedited | [8 empty] | 2010-05-21 | Online
WMECO | Whately | 6AF157-2010 | 1093 | 20 | Solar | 18G8 | 2010-04-21 | [31 empty] | 7/2010 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Northfield | 6F158-2010 | 1360 | 65.4 | Solar | 21B8 | 2010-04-21 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Whately | 6AF160-2010 | 1093 | 15.6 | Solar | 18G8 | 2010-06-01 | 2010-06-18 | 14 |  | 14 | [25 empty] | 2010-06-28 |  | 7/2010 | Yes | Expedited | [8 empty] | 2010-07-09 | Online
WMECO | Pittsfield | 6B71-2010 | 1201 | 36 | Solar | 30B4 | 2010-06-01 | 2010-08-23 | 60 |  | 60 | [25 empty] | 2010-10-04 |  | 2010-09-13 | No | Expedited | [8 empty] | 2010-12-22 | Online
WMECO | Greenfield | 6F161-2010 | 1301 | 2000 | Solar | 22B3 | 2010-06-03 | 2011-01-05 | 154 |  | 154 | [15 empty] | 2010-07-20 | 2011-01-28 | 138 |  | 138 | [5 empty] | 2011-01-28 |  | 2011-03-04 | Yes | Standard | [8 empty] | 2012-06-20 | Online
WMECO | Pittsfield | 6B72-2010 | 1201 | 1800 | Solar | 30B3 | 2010-06-11 | [31 empty] | 11/2010 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B74-2010 | 1201 | 1800 | Solar | 30B2 | 2010-06-24 | [31 empty] | 11/2010 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B75-2010 | 1201 | 62 | Hydro | 19A7 | 2010-07-01 | 2011-02-14 | 162 |  | 162 | [15 empty] | 2010-09-30 |  | -28894 | [7 empty] | 2011-04-07 |  | 2010-11-15 | No | Standard | [8 empty] | 2011-06-16 | Online
WMECO | Pittsfield | 6B77-2010 | 1201 | 1500 | Solar | 30B3 | 2010-07-30 | 2011-02-02 | 133 |  | 133 | [15 empty] | 2010-08-20 |  | -28865 | [7 empty] | 2011-03-24 |  | 2010-12-10 | Yes | Standard | [7 empty] | 2012-02-01 | 2012-02-01 | Online
WMECO | Greenfield | 6F171-2010 | 1301 | 50 | Solar | 22B7 | 2010-08-03 | 2011-01-11 | 115 |  | 115 | [25 empty] | 2011-01-12 |  | 2010-10-20 | No | Expedited | [8 empty] | 2011-02-10 | Online
WMECO | Springfield | 6S46-2010 | 1118 | 26.4 | Solar | 22H16 | 2010-08-03 | 2010-09-18 | 34 |  | 34 | [25 empty] | 2010-10-20 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-11-03 | Online
WMECO | Hadley | 6A134-2010 | 1035 | 30.3 | Solar | 17K5 | 2010-08-20 | 2010-09-03 | 11 |  | 11 | [25 empty] | 2010-09-21 |  | 2010-09-20 | Yes | Expedited | [8 empty] | 2010-11-10 | Online
WMECO | Amherst | 6A136-2010 | 1002 | 39.6 | Solar | 19B15 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-01 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-10-15 | Online
WMECO | Deerfield | 6F175-2010 | 1343 | 50 | Solar | 22B3 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-26 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-12-17 | Online
WMECO | Lee | 6B78S-2010 | 1238 | 30 | Solar | 17G3 | 2010-09-17 | 2011-03-01 | 117 |  | 117 | [25 empty] | 2011-06-01 |  | 2010-10-01 | Yes | Expedited | [8 empty] | 2011-12-01 | Online
WMECO | Hadley | 6A138-2010 | 1035 | 25.5 | Solar | 18G5 | 2010-09-21 | 2010-10-22 | 24 |  | 24 | [25 empty] | 2010-11-30 |  | 2010-11-01 | Yes | Expedited | [8 empty] | 2011-02-23 | Online
WMECO | Ashfield | 6F192-2010 | 1330 | 41.385 | Solar | 38A1 | 2010-12-03 | 2011-01-28 | 41 |  | 41 | [25 empty] | 2011-01-28 |  | 2010-01-01 | Yes | Expedited | [8 empty] | 2011-04-19 | Online
WMECO | West Springfield | 6S52-2010 | 1089 | 50 | Solar | 16C14 | 2010-12-07 | 2011-01-25 | 36 |  | 36 | [25 empty] | 2011-03-02 |  | 2011-02-01 | No | Expedited | [8 empty] | 2011-03-29 | Online
WMECO | Pittsfield | 6B82-2010 | 1201 | 195 | Digester Gas | 30B3 | 2010-12-09 | 2011-08-18 | 181 |  | 181 | [25 empty] | 2011-09-27 |  | 2011-01-01 | No | Standard | [8 empty] | 2012-02-10 | Online
WMECO | Pittsfield | 6B86-2010 | 1201 | 387.2 | Solar | 30B7 | 2010-12-15 | 2011-06-17 | 133 |  | 133 | [25 empty] | 2011-06-17 |  | 2011-01-01 | No | Expedited | [8 empty] | 2011-07-27 | Online
WMECO | Hadley | 6A149-2011 | 1035 | 450 | Biogas | 19B15 | 2011-01-04 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Greenfield | 6F194-2011 | 1301 | 83 | Solar | 22B7 | 2011-01-04 | 2011-07-08 | 134 |  | 134 | [25 empty] | 2011-12-13 |  | 2011-03-01 | No | Expedited | [8 empty] | 2012-02-06 | Online
WMECO | Deerfield | 6F195-2011 | 1342 | 450 | Biogas | 22B1 | 2011-01-04 | [31 empty] | 2011-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Easthampton | 6A151-2011 | 1027 | 2000 | Solar | 15A3 | 2011-01-27 | 2011-03-16 | 35 |  | 35 | [15 empty] | 2011-03-21 | 2011-06-29 | 73 |  | 73 | 2011-07-06 |  | -29092 |  |  | 2011-10-21 |  | 2011-11-19 | Yes | Standard | [8 empty] | 2012-06-01 | Online
WMECO | Hadley | 6A156-2011 | 1035 | 450 | Biogas | 19B15 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B92-2011 | 1201 | 2000 | Solar | 19A3 | 2011-02-23 | [19 empty] | 2011-05-26 |  | -29063 | [9 empty] | 2011-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Deerfield | 6F201-2011 | 1373 | 450 | Biogas | 22B1 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Sandisfield | 6B93-2011 | 1255 | 14 | Solar | 19J4 | 2011-03-03 | 2011-03-28 | 18 |  | 18 | [25 empty] | 2011-04-27 |  | 2011-06-01 | No | Expedited | [8 empty] | 2011-12-05 | Online
WMECO | Greenfield | 6F203-2011 | 1301 | 100 | Solar | 22B4 | 2011-03-04 | 2011-12-07 | 199 |  | 199 | [25 empty] | 2012-03-26 |  | 2011-07-01 | No | Expedited | [8 empty] | 2012-05-07 | Online
WMECO | Springfield | 6S56-2011 | 1107 | 120.4 | Solar | 21S7 | 2011-03-17 | 2012-01-06 | 211 |  | 211 | [25 empty] | 2012-01-30 |  | 2011-05-01 | No | Standard | [8 empty] | 2012-03-12 | Online
WMECO | Westfield | 6A164-2011 | 1085 | 250 | Solar | 19J2 | 2011-04-07 | [31 empty] | 2011-07-31 | TBD | Standard | [9 empty] | Withdrawn
WMECO | Northfield | 6F215-2011 | 1360 | 2000 | Solar | 21B8 | 2011-04-07 | 2011-08-18 | 96 |  | 96 | [15 empty] | 2011-07-13 | 2011-12-13 | 110 |  | 110 | 2011-11-28 |  | -29195 |  |  | 2012-02-07 |  | 2011-08-01 | Yes | Standard | [8 empty] | 2012-03-30 | Online
WMECO | Agawam | 6S57-2011 | 1001 | 1500 | Solar | 30A6 | 2011-04-19 | 2011-05-26 | 28 |  | 28 | [15 empty] | 2011-06-09 | 2011-10-21 | 97 |  | 97 | 2011-11-14 |  | -29185 |  |  | 2012-04-27 |  | 2011-09-01 | Yes | Standard | [6 empty] | 2013-03-11 | 2013-03-13 | 2013-03-13 | Online
WMECO | Westfield | 6A168-2011 | 1085 | 1000 | Solar | 19J2 | 2011-05-17 | 2011-07-20 | 47 |  | 47 | [27 empty] | 2011-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A170-2011 | 1373 | 1500 | Solar | 18G8 | 2011-05-19 | 2011-07-21 | 46 |  | 46 | [15 empty] | 2011-07-08 | 2011-12-28 | 124 |  | 124 | 2011-12-21 |  | -29212 |  |  | 2012-04-03 |  | 2011-09-01 | Yes | Standard | [6 empty] | 2013-01-29 | 2013-02-01 | 2013-03-11 | Online
WMECO | Greenfield | 6F230-2011 | 1301 | 34.2 | Solar | 22B4 | 2011-06-14 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Dalton | 6B105-2011 | 1226 | 224 | Steam | 19A6 | 2011-06-20 | 2012-01-11 | 147 |  | 147 | [15 empty] | 2011-10-20 |  | -29168 | [7 empty] | 2012-01-11 |  | 2011-11-11 | No | Standard | [8 empty] | 2012-01-24 | Online
WMECO | Dalton | 6B106-2011 | 1226 | 250 | Hydro | 19A6 | 2011-06-20 | 2012-05-29 | 242 |  | 242 | [15 empty] | 2012-07-16 | 2012-12-19 | 108 |  | 108 | [5 empty] | 2013-04-30 |  | 2012-04-01 | Yes | Standard | [6 empty] | 2013-09-27 | 2013-10-03 | 2013-10-03 | Online
WMECO | Greenfield | 6F235-2011 | 1301 | 34.2 | Solar | 22B4 | 2011-06-24 | 2011-07-15 | 16 |  | 16 | [25 empty] | 2011-07-20 |  | 2011-07-21 | No | Expedited | [8 empty] | 2011-08-05 | Online
WMECO | Agawam | 6S60-2011 | 1001 | 1500 | Solar | 16C16 | 2011-07-07 | 2011-08-03 | 20 |  | 20 | [15 empty] | 2011-09-01 | 2011-12-29 | 86 |  | 86 | 2011-12-21 |  | -29212 |  |  | 2012-04-13 |  | 2011-12-01 | Yes | Standard | [6 empty] | 2013-02-06 | 2013-02-22 | 2013-03-11 | Online
WMECO | Chesterfield | 6F243-2011 | 1012 | 12 | Solar | 18K3 | 2011-07-25 | 2011-08-22 | 21 |  | 21 | [25 empty] | 2011-08-23 |  | 2011-08-01 | No | Expedited | [8 empty] | 2011-09-15 | Online
WMECO | Amherst | 6A183-2011 | 1002 | 60 | Solar | 19B16 | 2011-07-28 | 2011-09-22 | 41 |  | 41 | [25 empty] | 2011-10-17 |  | 2011-11-01 | No | Expedited | [8 empty] | 2011-11-18 | Online
WMECO | Conway | 6F248-2011 | 1341 | 22.8 | Solar | 38A1 | 2011-08-12 | 2011-10-26 | 54 |  | 54 | [25 empty] | 2011-11-17 |  | 2011-09-10 | Yes | Expedited | [8 empty] | 2012-02-27 | Online
WMECO | Whately | 6F251-2011 | 1373 | 100 | Solar | 18G8 | 2011-08-18 | 2011-10-13 | 41 |  | 41 | [25 empty] | 2011-10-18 |  | not supplied | No | Expedited | [8 empty] | 2011-12-28 | Online
WMECO | Hadley | 6A196-2011 | 1035 | 95 | Solar | 18G4 | 2011-09-01 | 2011-10-25 | 39 |  | 39 | [25 empty] | 2011-11-30 |  | 2011-11-01 | Yes | Expedited | [8 empty] | 2012-03-30 | Online
WMECO | Pittsfield | 6B111-2011 | 1201 | 300 | Solar | 30B4 | 2011-09-02 | 2011-10-05 | 24 |  | 24 | [25 empty] | 2012-02-07 |  | 2011-10-01 | No | Expedited | [8 empty] | 2012-06-01 | Online
WMECO | Springfield | 6S68-2011 | 1111 | 208 | Solar | 5J14 | 2011-09-12 | 2011-11-17 | 49 |  | 49 | [25 empty] | 2011-11-30 |  | 2011-10-15 | No | Expedited | [8 empty] | 2012-01-24 | Online
WMECO | Deerfield | 6F264-2011 | 1342 | 30 | Solar | 22B7 | 2011-09-16 | 2011-10-19 | 24 |  | 24 | [25 empty] | 2011-11-07 |  | 2011-10-31 | No | Expedited | [8 empty] | 2012-02-03 | Online
WMECO | Hadley | 6A209-2011 | 1035 | 300 | Biogas | 19B15 | 2011-09-21 | 2013-10-18 | 522 |  | 522 | 2013-10-21 |  | -29669 | [22 empty] | 2013-12-19 |  | 2012-04-01 | Yes | Standard | [8 empty] | 2013-12-31 | Online
WMECO | Deerfield | 6F265-2011 | 1372 | 600 | Biogas | 22B1 | 2011-09-21 | [31 empty] | 2012-04-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B116-2011 | 1238 | 295 | Solar | 16B5 | 2011-10-21 | [31 empty] | Q2 2012 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Colrain | 6F274-2011 | 1340 | 15.36 | Solar | 29R2 | 2011-10-24 | 2012-01-12 | 58 |  | 58 | [25 empty] | 2012-02-07 |  | 2011-11-30 | Yes | Expedited | [8 empty] | 2012-05-23 | Online
WMECO | Whately | 6A225-2011 | 1093 | 260 | Solar | 18G8 | 2011-11-07 | [31 empty] | 2012-03-16 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A228-2011 | 1035 | 17.995 | Solar | 18G5 | 2011-11-09 | 2011-12-20 | 30 |  | 30 | [25 empty] | 2011-12-21 |  | 2011-11-28 | No | Expedited | [8 empty] | 2012-01-19 | Online
WMECO | Pittsfield | 6B117-2011 | 1201 | 100 | Solar | 30B3 | 2011-11-09 | 2012-01-18 | 49 |  | 49 | [5 empty] | 2011-12-12 |  | -29205 | [17 empty] | 2012-03-02 |  | 2011-12-15 | Yes | Expedited | [8 empty] | 2012-05-03 | Online
WMECO | Springfield | 6S74-2011 | 1104 | 60 | Solar | 21S7 | 2011-11-15 | 2012-04-10 | 103 |  | 103 | [25 empty] | 2012-04-10 |  | 2012-03-01 | No | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S75-2011 | 1104 | 95 | Solar | 21S7 | 2011-11-15 | 2012-04-09 | 102 |  | 102 | 2011-12-20 |  | -29211 | [22 empty] | 2012-04-19 |  | 2012-03-01 | No | Expedited | [6 empty] | 2014-04-30 | 2014-05-05 | 2014-05-05 | Online
WMECO | Dalton | 6B120-2011 | 1226 | 13 | Solar | 19A2 | 2011-11-23 | [31 empty] | 2011-12-22 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Buckland | 6F286-2011 | 1338 | 57 | Solar | 22B5 | 2011-12-07 | 2012-02-22 | 53 |  | 53 | [25 empty] | 2012-03-12 |  | 2012-01-01 | Yes | Expedited | [8 empty] | 2012-05-01 | Online
WMECO | Greenfield | 6F290-2011 | 1301 | 14.7 | Solar | 21C4 | 2011-12-14 | 2012-01-26 | 30 |  | 30 | [25 empty] | 2012-02-08 |  | 2012-01-01 | No | Expedited | [8 empty] | 2012-03-19 | Online
WMECO | Whately | 6A239-2011 | 1093 | 260 | Solar | 18G8 | 2011-12-16 | 2012-04-13 | 83 |  | 83 | [25 empty] | 2012-04-19 |  | 2012-03-16 | No | Expedited | [8 empty] | 2012-05-01 | Online
WMECO | Easthampton | 6A241-2011 | 1027 | 3.3 | Wind | 15A5 | 2011-12-22 | 2012-01-04 | 9 |  | 9 | [25 empty] | 2012-01-12 |  | not supplied | No | Expedited | [8 empty] | 2012-02-13 | Online
WMECO | Hadley | 6A242-2011 | 1035 | 2000 | Solar | 18G4 | 2011-12-27 | 2012-02-16 | 36 |  | 36 | [15 empty] | 2012-04-02 | 2013-07-09 | 316 | 0 | 316 | 2013-05-03 | 2013-09-12 | 91 | 51 | 40 | 2013-10-04 |  | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A247-2012 | 1093 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A250-2012 | 1039 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6BA253-2012 | 1008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6BA254-2012 | 1008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Turners Falls | 6F295-2012 | 1376 | 370 | Hydro | 21C6 | 2012-01-10 | 2012-03-05 | 38 |  | 38 | [15 empty] | 2012-03-20 |  | -29273 | [7 empty] | 2013-03-27 |  | not supplied | No | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B125-2012 | 1634 | 3500 | Solar | 19J4 | 2012-01-25 | 2013-01-31 | 255 | 0 | 255 | [15 empty] | 2012-06-18 | 2013-06-07 | 243 | 0 | 243 | 2013-07-31 | 2013-09-06 | 27 |  | 27 | 2013-09-06 |  | 2012-09-25 | Yes | Complex | [6 empty] | 2014-09-25 | 2014-10-03 | 2014-10-03 | Online
WMECO | Tolland | 6B126-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29335 | [9 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B127-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29335 | [9 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B128-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [31 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S90-2012 | 1089 | 110 | Solar | 21N5 | 2012-02-01 | 2012-03-02 | 22 |  | 22 | [5 empty] | 2012-02-29 |  | -29259 | [17 empty] | 2012-05-24 |  | not supplied | No | Expedited | [8 empty] | 2012-07-12 | Online
WMECO | Pittsfield | 6B130-2012 | 1201 | 2000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B131-2012 | 1201 | 3000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Ludlow | 6S91-2012 | 1056 | 3000 | Solar | 19S3 | 2012-02-03 | [31 empty] | 2012-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A262-2012 | 1038 | 45.6 | Solar | 18G5 | 2012-02-06 | 2012-04-11 | 47 |  | 47 | [25 empty] | 2012-05-02 |  | not supplied | Yes | Expedited | [6 empty] | 2012-08-24 | 2012-08-28 | 2012-08-28 | Online
WMECO | Shutesbury | 6A263-2012 | 1072 | 11.4 | Solar | 18G7 | 2012-02-07 | 2012-05-01 | 59 |  | 59 | [25 empty] | 2012-05-25 |  | 2/2012 | No | Expedited | [8 empty] | 2012-06-13 | Online
WMECO | Deerfield | 6F303-2012 | 1342 | 22.8 | Solar | 22B4 | 2012-02-07 | 2012-05-07 | 63 |  | 63 | [5 empty] | 2012-04-17 |  | -29292 | [17 empty] | 2012-05-10 |  | 2012-04-01 | Yes | Expedited | [8 empty] | 2012-09-12 | Online
WMECO | Southampton | 6A266-2012 | 1073 | 11.18 | Solar | 15A1 | 2012-02-17 | 2012-04-04 | 33 |  | 33 | [25 empty] | 2012-06-18 |  | 2012-04-25 | No | Expedited | [8 empty] | 2012-08-06 | Online
WMECO | Whately | 6A267-2012 | 1373 | 2000 | Solar | 18G8 | 2012-02-17 | 2012-04-10 | 37 |  | 37 | [15 empty] | 2012-05-17 | 2012-11-07 | 121 | 0 | 121 | 2012-09-12 | 2013-01-22 | 88 | 0 | 88 | 2013-02-26 |  | 2012-09-01 | Yes | Standard | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-06-25 | Online
WMECO | Blandford | 6B133-2012 | 1008 | 2000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B134-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B135-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B136-2012 | 1008 | 4000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B137-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Ludlow | 6S96-2012 | 1056 | 2000 | Solar | 27A5 | 2012-02-23 | 2012-06-29 | 90 |  | 90 | [15 empty] | 2012-08-02 | 2012-10-22 | 56 |  | 56 | 2012-12-26 | 2013-03-08 | 50 | 0 | 50 | 2013-03-14 |  | 2012-09-30 | Yes | Standard | 2013-07-31 |  | 2013-07-30 |  |  |  | 2013-08-02 | 2013-08-07 | 2013-08-26 | Online
WMECO | Ludlow | 6S97-2012 | 1056 | 1000 | Solar | 19S3 | 2012-02-23 | [31 empty] | 2012-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A271-2012 | 1038 | 2000 | Solar | 18G6 | 2012-02-24 | 2012-07-19 | 102 |  | 102 | [15 empty] | 2012-04-30 | 2012-11-01 | 130 | 0 | 130 | 2012-10-10 | 2012-10-17 | 6 | 0 | 6 | 2013-02-13 |  | 2012-11-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B139-2012 | 1201 | 2000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B140-2012 | 1201 | 1000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Agawam | 6S98-2012 | 1001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Agawam | 6S99-2012 | 1001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Easthampton | 6A273-2012 | 1027 | 11 | Solar | 15A5 | 2012-03-01 | [31 empty] | 2012-03-20 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Lee | 6B141-2012 | 1238 | 295 | Solar | 16B5 | 2012-03-01 | 2012-06-11 | 71 |  | 71 | [25 empty] | 2012-06-14 |  | Q2 2012 | No | Expedited | [8 empty] | 2012-08-10 | Online
WMECO | Easthampton | 6A275-2012 | 1027 | 26.4 | Solar | 15A3 | 2012-03-02 | 2012-05-11 | 50 |  | 50 | [25 empty] | 2012-09-12 |  | 2012-04-15 | No | Expedited | [8 empty] | 2012-10-04 | Online
WMECO | Hadley | 6A277-2012 | 1035 | 1000 | Solar | 17K1 | 2012-03-12 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A278-2012 | 1035 | 2500 | Solar | 17K1 | 2012-03-12 | 2012-07-18 | 90 |  | 90 | [15 empty] | 2012-08-29 | 2013-06-07 | 192 | 0 | 192 | 2013-05-31 | 2013-07-23 | 36 | 18 | 18 | 2013-07-30 |  | 2012-10-12 | Yes | Standard | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-07-02 | Online
WMECO | Longmeadow | 6S102-2012 | 1106 | 45.6 | Solar | 22H11 | 2012-03-14 | 2012-05-03 | 36 |  | 36 | [25 empty] | 2012-06-11 |  | 2012-07-01 | No | Expedited | [8 empty] | 2012-08-15 | Online
WMECO | Lenoxdale | 6B142-2012 | 1242 | 780 | Solar | 17G3 | 2012-03-19 | 2013-03-27 | 256 |  | 256 |  |  |  | 0 | [11 empty] | 2012-12-17 | 2013-07-08 | 138 | 29 | 109 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B143-2012 | 1238 | 500 | Solar | 17G7 | 2012-03-19 | 2013-03-27 | 256 |  | 256 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 29 | 94 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-12 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B144-2012 | 1238 | 750 | Solar | 16B5 | 2012-03-19 | 2013-03-27 | 256 |  | 256 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B145-2012 | 1238 | 750 | Solar | 16B5 | 2012-03-21 | 2013-03-27 | 254 |  | 254 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B146-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B147-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B148-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B149-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B150-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A286-2012 | 1002 | 3750 | Solar | 17K2 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A287-2012 | 1373 | 1000 | Solar | 18G8 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Middlefield | 6B156-2012 | 1243 | 12.04 | Solar | 18C2 | 2012-03-29 | 2012-06-18 | 56 |  | 56 | [25 empty] | 2012-07-17 |  | 2012-04-24 | No | Expedited | [7 empty] | 2012-09-13 | 2012-09-13 | Online
WMECO | Whately | 6A289-2012 | 1373 | 1000 | Solar | 18G8 | 2012-04-03 | [31 empty] | 2012-01-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A290-2012 | 1038 | 44.4 | Solar | 18G5 | 2012-04-06 | 2012-06-08 | 44 |  | 44 | [25 empty] | 2012-06-29 |  | 2012-04-30 | No | Expedited | [8 empty] | 2012-07-27 | Online
WMECO | Hadley | 6A291-2012 | 1035 | 1000 | Solar | 17K1 | 2012-04-06 | 2012-06-29 | 59 |  | 59 | [15 empty] | 2012-08-29 |  | -29386 | [9 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B159-2012 | 1008 | 125 | Solar | 19J4 | 2012-04-09 | [31 empty] | 2012-05-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A294-2012 | 1088 | 67.5 | Solar | 18G5 | 2012-04-10 | 2012-10-09 | 126 |  | 126 | [25 empty] | 2012-10-10 |  | 2012-10-31 | No | Expedited | [8 empty] | 2012-11-13 | Online
WMECO | Chesterfield | 6F316-2012 | 1012 | 60 | Solar | 18K3 | 2012-04-11 | 2012-05-18 | 27 |  | 27 | [5 empty] | 2012-07-12 |  | -29352 | [17 empty] | 2012-05-31 |  | 2012-05-01 | No | Expedited | [8 empty] | 2012-09-25 | Online
WMECO | Turners Falls | 6F319-2012 | 1376 | 8.6 | Solar | 21C2 | 2012-04-23 | 2012-07-18 | 61 |  | 61 | [25 empty] | 2012-07-25 |  | 2012-04-30 | No | Expedited | [8 empty] | 2012-09-18 | Online
WMECO | Cummington | 6F322-2012 | 1026 | 12.255 | Solar | 18K3 | 2012-05-14 | [31 empty] | 2012-05-25 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A312-2012 | 1035 | 95 | Solar | 17K6 | 2012-05-17 | 2012-07-05 | 34 |  | 34 | [25 empty] | 2012-09-25 |  | 2012-07-13 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-28 | Online
WMECO | West Springfield | 6S112-2012 | 1089 | 333 | Solar | 21N8 | 2012-05-18 | 2012-08-15 | 62 |  | 62 | [25 empty] | 2012-08-17 |  | 2012-10-29 | No | Expedited | [9 empty] | Withdrawn
WMECO | Turners Falls | 6F325-2012 | 1376 | 500 | Solar | 21C3 | 2012-05-29 | [31 empty] | 2012-11-01 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Easthampton | 6A316-2012 | 1027 | 298 | Solar | 15A3 | 2012-05-30 | 2013-08-27 | 311 |  | 311 | 2013-08-28 | 2013-12-10 | 70 | 58 | 12 | 2013-12-10 |  | -29702 | 52 | [18 empty] | 2012-08-10 |  | Expedited | [9 empty] | Withdrawn
WMECO | Easthampton | 6A317-2012 | 1027 | 120 | Solar | 15A2 | 2012-05-30 | 2013-08-06 | 296 | 297 | -1 | 2013-08-07 | 2013-09-11 | 25 | 5 | 20 | 2014-04-29 | 2014-05-20 | 16 | 0 | 16 | [15 empty] | 2014-07-31 |  | 2012-08-10 | TBD | Expedited | [6 empty] | 2015-06-26 | 2015-06-26 | 2015-07-10 | Online
WMECO | Deerfield | 6F328-2012 | 1342 | 19.99 | Solar | 22B1 | 2012-06-04 | 2012-08-14 | 51 |  | 51 | [25 empty] | 2012-08-29 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-11-01 | 2012-11-07 | 2012-11-08 | Online
WMECO | Springfield | 6S115-2012 | 1104 | 500 | Solar | 5J15 | 2012-06-04 | 2012-10-18 | 96 |  | 96 | [25 empty] | 2013-02-21 |  | Q4 2012 | No | Expedited | [6 empty] | 2013-05-20 | 2013-05-21 | 2013-05-30 | Online
WMECO | Hatfield | 6A320-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A321-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A322-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hinsdale | 6B169-2012 | 1235 | 23.995 | Solar | 18C2 | 2012-06-27 | 2012-08-03 | 27 |  | 27 | [25 empty] | 2012-08-10 |  | 2012-08-01 | Yes | Expedited | [7 empty] | 2012-09-28 | 2012-09-28 | Online
WMECO | Shelburne Falls | 6F338-2012 | 1370 | 82 | Solar | 29R1 | 2012-06-28 | 2012-10-07 | 70 |  | 70 | [25 empty] | 2012-10-22 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-11-28 | 2012-12-05 | 2012-12-06 | Online
WMECO | Easthampton | 6A332-2012 | 1027 | 14 | Solar | 15A5 | 2012-07-13 | 2012-11-02 | 79 |  | 79 | 2012-11-05 | 2012-11-16 | 9 | 0 | 9 | [20 empty] | 2012-11-20 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-12-14 | 2012-12-20 | 2012-12-20 | Online
WMECO | Springfield | 6S123-2012 | 1104 | 142 | Solar | 5J9 | 2012-07-16 | 2012-10-23 | 70 |  | 70 | [25 empty] | 2013-03-13 |  | not supplied | No | Expedited | [6 empty] | 2012-04-10 | 2013-04-11 | 2013-04-23 | Online
WMECO | Springfield | 6S124-2012 | 1104 | 266 | Solar | 5J18 | 2012-07-16 | 2012-08-30 | 34 |  | 34 | [25 empty] | 2013-04-16 |  | 2012-10-30 | No | Expedited | [6 empty] | 2013-05-30 | 2013-05-31 | 2013-05-31 | Online
WMECO | Southwick | 6S126-2012 | 1077 | 1500 | Solar | 29A1 | 2012-07-17 | 2012-10-18 | 66 | 65 | 1 | [10 empty] | 2012-10-19 | 2013-03-05 | 91 | 89 | 2 | 2013-04-16 | 2013-09-20 | 110 | 0 | 110 | 2014-03-31 | 2014-08-20 | 99 | 99 | 0 | 2013-12-16 |  | Q4 2012 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A336-2012 | 1002 | 11.4 | Solar | 19B16 | 2012-07-24 | 2012-09-28 | 48 |  | 48 | [25 empty] | 2012-10-11 |  | 2012-08-01 | No | Expedited | [6 empty] | 2012-11-15 | 2012-11-16 | 2012-11-16 | Online
WMECO | Hatfield | 6A339-2012 | 1038 | 175 | Solar | 18G5 | 2012-07-27 | 2012-08-31 | 26 |  | 26 | [25 empty] | 2012-10-09 |  | not supplied | No | Expedited | [6 empty] | 2012-11-29 | 2012-12-03 | 2012-12-01 | Online
WMECO | Amherst | 6A341-2012 | 1002 | 34.2 | Solar | 17K2 | 2012-07-30 | 2012-11-29 | 84 |  | 84 | 2012-11-30 | 2012-12-04 | 3 | 0 | 3 | [20 empty] | 2012-12-05 |  | 2012-09-12 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-31 | Online
WMECO | Amherst | 6A343-2012 | 1027 | 57 | Solar | 17K8 | 2012-07-31 | 2012-12-10 | 90 |  | 90 | 2012-12-11 | 2013-01-08 | 19 | 0 | 19 | [20 empty] | 2013-01-10 |  | 2012-09-01 | No | Expedited | [6 empty] | 2013-02-26 | 2013-02-28 | 2013-02-28 | Online
WMECO | Amherst | 6A344-2012 | 1002 | 29.985 | Solar | 17K7 | 2012-08-01 | 2012-10-03 | 45 |  | 45 | [25 empty] | 2012-11-20 |  | not supplied | No | Expedited | [6 empty] | 2012-12-18 | 2012-12-19 | 2012-12-19 | Online
WMECO | Greenfield | 6F354-2012 | 1301 | 135 | Solar | 21C1 | 2012-08-17 | 2012-10-29 | 50 |  | 50 | [25 empty] | 2012-11-20 |  | not supplied | No | Expedited | [6 empty] | 2012-12-10 | 2012-12-12 | 2012-12-12 | Online
WMECO | Gill | 6F355-2012 | 1354 | 1250 | Diesel | 21B8 | 2012-08-20 | 2012-09-12 | 17 |  | 17 | [15 empty] | 2012-12-14 | 2013-08-21 | 171 | 17 | 154 | [5 empty] | 2013-12-12 |  | 2012-11-25 | TBD | Standard | [6 empty] | 2017-08-10 | 2017-05-19 | 2017-08-21 | Online
WMECO | Springfield | 6S136-2012 | 1119 | 333 | Solar | 20A33 | 2012-08-20 | 2012-10-05 | 34 |  | 34 | [25 empty] | 2012-12-21 |  | 2012-11-01 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-31 | 2012-12-31 | Online
WMECO | Tolland | 6B180-2012 | 1034 | 136.8 | Solar | 19J4 | 2012-08-22 | [31 empty] | 2013-01-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A347-2012 | 1002 | 14 | Solar | 17K8 | 2012-08-24 | 2012-11-26 | 62 |  | 62 | 2012-11-27 | 2012-11-29 | 3 | 0 | 3 | [20 empty] | 2012-11-30 |  | 2012-12-01 | Yes | Expedited |  | 2012-12-06 | 2012-12-06 | 1 | 0 | 1 | 2012-12-14 | 2012-12-17 | 2012-12-17 | Online
WMECO | Leyden | 6F358-2012 | 1337 | 38 | Solar | 22B7 | 2012-08-28 | 2012-09-07 | 8 |  | 8 | [25 empty] | 2012-11-06 |  | 2012-12-01 | Yes | Expedited | [6 empty] | 2013-05-17 | 2013-05-22 | 2013-05-22 | Online
WMECO | Easthampton | 6A349-2012 | 1027 | 83 | Solar | 15A2 | 2012-08-29 | 2012-09-26 | 20 |  | 20 | [25 empty] | 2013-01-16 |  | 2012-11-12 | No | Expedited | [6 empty] | 2013-03-29 | 2013-04-02 | 2013-04-02 | Online
WMECO | Greenfield | 6F360-2012 | 1301 | 3.4 | Solar | 28WNW_1 | 2012-08-29 | 2012-09-20 | 16 |  | 16 | [25 empty] | 2013-01-15 |  | 2012-09-30 | No | Standard | [6 empty] | 2013-04-22 | 2013-04-23 | 2013-04-23 | Online
WMECO | Hancock | 6B183-2012 | 1237 | 6000 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hancock | 6B184-2012 | 1237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hancock | 6B185-2012 | 1237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Deerfield | 6F368-2012 | 1342 | 34.83 | Solar | 22B1 | 2012-09-06 | 2012-11-09 | 46 |  | 46 | 2012-11-12 | 2012-11-19 | 5 | 0 | 5 | [20 empty] | 2012-11-26 |  | not supplied | No | Expedited | [6 empty] | 2012-12-14 | 2013-01-03 | 2013-01-03 | Online
WMECO | Russell | 6A357-2012 | 1071 | 125 | Solar | 19J2 | 2012-09-17 | 2012-10-04 | 14 | 2 | 12 | 2012-11-05 | 2012-11-06 | 2 | 0 | 2 | [10 empty] | 2013-03-18 | 2013-09-03 | 117 | 0 | 117 | 2013-09-18 | 2013-10-10 | 17 | 0 | 17 | 2013-12-10 |  | 2012-11-08 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Middlefield | 6B190-2012 | 1243 | 10.965 | Solar | 18C2 | 2012-09-24 | 2012-10-17 | 17 | 0 | 17 | [25 empty] | 2013-01-24 |  | 2012-11-24 | No | Expedited | [6 empty] | 2013-06-18 | 2013-06-20 | 2013-06-20 | Online
WMECO | Westhampton | 6A363-2012 | 1027 | 12.9 | Solar | 15A3 | 2012-10-01 | 2012-10-01 | 1 |  | 1 | [25 empty] | 2012-11-27 |  | 2012-09-28 | No | Expedited | [6 empty] | 2012-12-26 | 2012-12-31 | 2012-12-31 | Online
WMECO | Pittsfield | 6B194-2012 | 1201 | 23.22 | Solar | 30B4 | 2012-10-02 | 2012-11-15 | 31 |  | 31 | 2012-11-16 |  | -29440 | [22 empty] | 2013-04-11 |  | not supplied | No | Expedited | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Online
WMECO | Pittsfield | 6B195-2012 | 1201 | 18.06 | Solar | 30B4 | 2012-10-02 | 2012-11-13 | 29 |  | 29 | 2012-11-14 |  | -29438 | [22 empty] | 2013-04-11 |  | not supplied | No | Expedited | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Online
WMECO | Ludlow | 6S144-2012 | 1056 | 600 | Diesel | 27A4 | 2012-10-19 | 2012-11-15 | 19 | 0 | 19 | 2012-11-27 | 2013-06-21 | 142 | 40 | 102 | [20 empty] | 2013-07-03 |  | 2012-11-12 | No | Expedited | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-08-01 | Online
WMECO | Pittsfield | 6B225-2012 | 1201 | 23.22 | Solar | 30BNW_1 | 2012-10-23 | 2012-11-07 | 12 |  | 12 | 2012-11-08 |  | -29435 | [22 empty] | 2013-03-21 |  | not supplied | No | Expedited | [6 empty] | 2013-04-01 | 2013-04-05 | 2013-04-05 | Online
WMECO | Pittsfield | 6B234-2012 | 1201 | 19.78 | Solar | 30B7 | 2012-11-16 | 2013-02-21 | 64 | 28 | 36 | 2013-02-22 | 2013-02-22 | 1 | 0 | 1 | [20 empty] | 2013-04-08 |  | 2013-01-21 | No | Expedited | [6 empty] | 2014-03-03 | 2014-03-05 | 2014-03-05 | Online
WMECO | Hadley | 6A381-2012 | 1035 | 760 | Solar | 17K5 | 2012-11-21 | 2013-07-30 | 170 | 2 | 168 | 2012-11-30 | 2013-09-10 | 194 | 153 | 41 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | 2013-10-08 | 2013-11-25 | 33 | 2 | 31 | [7 empty] | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A382-2012 | 1035 | 760 | Solar | 17K5 | 2012-11-21 | 2012-11-29 | 5 | 2 | 3 | 2012-11-30 | 2013-01-31 | 42 | 0 | 42 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | [12 empty] | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lanesborough | 6B236-2012 | 1237 | 20.2 | Solar | 15E1 | 2012-11-21 | 2012-12-03 | 7 | 0 | 7 | 2012-11-22 | 2012-11-22 | 0 | 0 | [23 empty] | 2013-02-07 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S149-2012 | 1105 | 5000 | Natural Gas / Diesel | 21S3 | 2012-11-26 |  |  | 208 | [28 empty] | 2012-10-15 | TBD | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B238-2012 | 1201 | 45.795 | Solar | 30B4 | 2012-11-27 | 2012-12-03 | 5 |  | 5 | 2012-12-04 | 2013-06-27 | 141 | 46 | 95 | [20 empty] | 2013-08-19 |  | 2012-11-30 | TBD | Expedited | [6 empty] | 2013-09-29 | 2013-09-30 | 2013-09-30 | Online
WMECO | Southampton | 6A384-2012 | 1073 | 600 | Diesel | 15A1 | 2012-12-04 | 2012-12-07 | 4 | 0 | 4 | 2013-06-10 | 2013-06-21 | 9 | 8 | 1 | [20 empty] | 2013-07-03 |  | 2012-12-31 | TBD | Expedited | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-07-30 | Online
WMECO | Pittsfield | 6B240-2012 | 1201 | 11.4 | Solar | 30B3 | 2012-12-05 | 2013-03-13 | 67 | 33 | 34 | 2013-03-14 | 2013-04-08 | 18 | 0 | 18 | [20 empty] | 2013-04-09 |  | 2013-01-21 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Montague | 6F410-2012 | 1351 | 11.4 | Solar | 21C7 | 2012-12-13 | 2013-02-12 | 41 |  | 41 | 2013-02-12 | 2013-02-12 | 1 | 0 | 1 | [20 empty] | 2013-03-19 |  | 2013-02-01 | No | Expedited | [6 empty] | 2013-04-30 | 2013-05-03 | 2013-05-03 | Online
WMECO | Amherst | 6A385-2012 | 1002 | 19.35 | Solar | 17K2 | 2012-12-17 | 2013-02-05 | 34 |  | 34 | 2013-02-05 | 2013-02-12 | 6 | 0 | 6 | [20 empty] | 2013-02-14 |  | not supplied | No | Expedited | [6 empty] | 2013-03-29 | 2013-04-01 | 2013-04-01 | Online
WMECO | Springfield | 6S154-2012 | 1111 | 5000 | Diesel | 5J14 | 2012-12-17 | 2013-04-19 | 85 | 0 | 85 | 2013-05-13 | 2013-10-28 | 116 | 45 | 71 | [5 empty] | 2013-04-22 | 2013-04-22 | 1 | 0 | 1 | 2013-10-28 | 2013-11-13 | 12 | 0 | 12 | [5 empty] | 2014-01-09 |  | not supplied | TBD | Standard | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Online
WMECO | Amherst | 6A387-2012 | 1059 | 3000 | Solar | 18G7 | 2012-12-26 |  |  | 148 | [28 empty] | 2013-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Richmond | 6B254-2013 | 1254 | 11.2 | Solar | 30B7 | 2013-01-08 | 2013-02-20 | 30 | 2 | 28 | 2013-02-21 | 2013-03-11 | 13 | 0 | 13 | [20 empty] | 2013-03-14 |  | 2013-03-13 | No | Expedited | [9 empty] | Withdrawn
WMECO | West Springfield | 6S155-2013 | 1089 | 16.985 | Solar | 21N9 | 2013-01-10 | 2013-03-06 | 38 | 1 | 37 | 2013-03-07 | 2013-03-07 | 1 | 0 | 1 | [20 empty] | 2013-04-01 |  | 2013-01-01 | No | Expedited | [6 empty] | 2013-05-08 | 2013-05-09 | 2013-05-09 | Online
WMECO | Pittsfield | 6B257-2013 | 1201 | 21.93 | Solar | 30B4 | 2013-01-16 | 2013-01-23 | 5 | 0 | 5 | 2013-01-24 | 2013-01-24 | 1 | 0 | 1 | [20 empty] | 2013-07-08 |  | not supplied | TBD | Expedited | [6 empty] | 2013-10-09 | 2013-10-10 | 2013-10-10 | Online
WMECO | Bernardston | 6F432-2013 | 1337 | 31.39 | Solar | 21B8 | 2013-02-01 | 2013-03-18 | 31 | 4 | 27 | 2013-03-19 | 2013-04-03 | 12 | 5 | 7 | [20 empty] | 2013-04-08 |  | 2013-05-01 | Yes | Expedited | [6 empty] | 2013-05-31 | 2013-06-05 | 2013-06-05 | Online
WMECO | Hadley | 6A405-2013 | 1035 | 833 | Solar | 18G4 | 2013-02-11 | 2013-06-19 | 89 | 26 | 63 | 2013-07-09 | 2013-07-12 | 4 | 0 | 4 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | [5 empty] | 2013-12-23 |  | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A408-2013 | 1035 | 2730 | Solar | 17K1 | 2013-02-14 | 2013-03-29 | 31 | 1 | 30 | 2013-04-01 |  | -29530 | 93 | [23 empty] | 2013-10-13 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Sunderland | 6A411-2013 | 1375 | 300 | Solar | 18G3 | 2013-02-27 | 2013-04-03 | 26 | 18 | 8 | 2013-04-04 | 2013-09-11 | 110 | 84 | 26 | 2013-09-20 | 2013-10-11 | 16 | 0 | 16 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Sunderland | 6A412-2013 | 1375 | 349.5 | Solar | 18G3 | 2013-02-27 | 2013-04-01 | 24 | 16 | 8 | 2013-04-02 | 2013-09-11 | 112 | 85 | 27 | 2013-10-15 | 2013-11-12 | 20 | 0 | 20 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B265-2013 | 1201 | 9.89 | Solar | 30BNW_1 | 2013-03-14 | 2013-03-28 | 11 | 0 | 11 | 2013-03-29 | 2013-07-02 | 65 | 8 | 57 | [20 empty] | 2013-08-01 |  | 2013-05-09 | TBD | Standard | [8 empty] | 2013-10-25 | Online
WMECO | Hadley | 6A415-2013 | 1035 | 833 | Solar | 18G4 | 2013-03-18 | 2013-06-18 | 64 | 21 | 43 | 2013-07-11 | 2013-07-12 | 2 | 0 | 2 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | 2014-03-04 | 2014-04-14 | 29 | 3 | 26 | 2014-05-07 |  | 2013-10-15 | Yes | Standard | 2014-09-15 | 2014-09-15 |  | -29891 |  |  | 2014-10-21 | 2014-10-30 | 2014-10-30 | Online
WMECO | West Springfield | 6S165-2013 | 1089 | 79.8 | Solar | 21N5 | 2013-03-18 | 2013-04-25 | 28 | 22 | 6 | 2013-04-26 |  | -29548 | 38 | [21 empty] | 2013-08-06 |  | 2013-04-25 | TBD | Expedited | [6 empty] | 2013-11-13 | 2013-12-10 | 2013-12-10 | Online
WMECO | Hadley | 6A418-2013 | 1035 | 57.405 | Solar | 17K5 | 2013-04-09 | 2013-06-12 | 45 | 37 | 8 | 2013-06-13 | 2013-08-06 | 37 | 28 | 9 | [20 empty] | 2013-08-09 |  | 2013-07-22 | TBD | Expedited | [6 empty] | 2013-11-13 | 2013-12-12 | 2013-12-31 | Online
WMECO | Greenfield | 6F447-2013 | 1301 | 300 | Solar | 21C1 | 2013-04-09 | 2013-05-07 | 20 |  | 20 | 2013-05-08 | 2013-05-23 | 12 |  | 12 | 2013-06-03 | 2013-06-26 | 17 | 0 | 17 | [15 empty] | 2013-07-15 |  | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Amherst | 6A419-2013 | 1002 | 100 | Solar | 18G4 | 2013-04-16 | 2013-04-30 | 11 |  | 11 | 2013-05-01 | 2013-06-06 | 26 | 2 | 24 | [20 empty] | 2013-06-06 |  | 2013-05-01 | TBD | Expedited | [6 empty] | 2013-10-15 | 2013-10-22 | 2013-10-22 | Online
WMECO | Otis | 6B269-2013 | 1253 | 1800 | Wind | 19J6 | 2013-04-19 | 2013-05-02 | 10 | 0 | 10 | [10 empty] | 2013-05-03 | 2014-02-18 | 196 | 166 | 30 | 2014-04-10 | 2014-07-01 | 56 | 3 | 53 | [7 empty] | 2013-11-13 | Yes | Complex | [9 empty] | Withdrawn
WMECO | Peru | 6B277-2013 | 1235 | 16500 | Wind | 18C2 | 2013-05-06 | 2013-05-23 | 14 | 2 | 12 | [10 empty] | 2013-05-24 | 2013-09-06 | 72 | 47 | 25 |  |  |  | 29 | [8 empty] | not supplied | Yes | Complex | [9 empty] | Withdrawn
WMECO | Lanesborough | 6B280-2013 | 1237 | 20.21 | Solar | 15E1 | 2013-05-13 | 2013-11-12 | 126 | 120 | 6 | 2013-10-29 | 2013-10-29 | 1 | 0 | 1 | [20 empty] | 2013-11-12 |  | 2013-07-10 | TBD | Expedited | [6 empty] | 2014-03-28 | 2014-04-01 | 2014-04-01 | Online
WMECO | Amherst | 6A449-2013 | 1002 | 19.99 | Solar | 17K7 | 2013-06-26 | 2013-07-03 | 6 | 0 | 6 | 2013-07-05 | 2013-09-05 | 44 | 21 | 23 | [20 empty] | 2013-10-07 |  | 2013-09-01 | TBD | Expedited | [6 empty] | 2013-10-28 | 2013-10-29 | 2013-11-18 | Online
WMECO | Southwick | 6S195-2013 | 1077 | 40 | Hydro | 29A5 | 2013-07-09 | 2013-07-30 | 16 | 8 | 8 | 2013-07-31 |  | -29613 | 17 | [23 empty] | 2013-11-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Conway | 6F473-2013 | 1341 | 19.99 | Solar | 38A1 | 2013-07-15 | 2013-07-24 | 8 | 0 | 8 | 2013-07-25 | 2013-09-19 | 40 | 9 | 31 | 2013-09-26 | 2013-11-04 | 27 | 0 | 27 | [15 empty] | 2013-11-15 |  | 2013-08-01 |  | Expedited | [6 empty] | 2013-12-10 | 2013-12-13 | 2013-12-20 | Online
WMECO | Southwick | 6S200-2013 | 1077 | 3340 | Solar | 29A1 | 2013-07-18 | 2013-08-07 | 15 | 9 | 6 | [10 empty] | 2013-08-08 | 2013-10-15 | 47 | 27 | 20 | 2013-12-13 | 2014-05-01 | 94 | 0 | 94 | 2014-05-05 | 2014-11-05 | 128 | 12 | 116 | 2014-05-01 |  | 2014-08-01 |  | Standard |  | 2015-03-09 | 2015-03-20 | 9 |  | 9 | 2015-03-09 | 2015-03-30 | 2015-03-30 | Online
WMECO | Richmond | 6B301-2013 | 1254 | 18 | Solar | 30B7 | 2013-08-28 | 2013-10-07 | 28 | 20 | 8 | 2013-10-08 | 2013-11-20 | 30 | 19 | 11 | [20 empty] | 2013-11-20 |  | 2013-09-01 |  | Expedited | [6 empty] | 2013-12-13 | 2013-12-18 | 2013-12-31 | Online
WMECO | Springfield | 6S208-2013 | 1129 | 333 | Solar | 20A35 | 2013-08-29 | 2013-09-20 | 16 | 12 | 4 | 2013-10-31 | 2013-10-31 | 1 | 0 | 1 | 2013-12-02 | 2014-01-06 | 24 | 0 | 24 | [15 empty] | 2014-02-06 |  | 2014-06-30 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B316-2013 | 1201 | 600 | Diesel | 30B4 | 2013-10-01 | 2013-11-05 | 25 | 13 | 12 | 2013-11-05 | 2014-01-13 | 45 | 45 | 0 | 2014-01-17 | 2014-04-11 | 58 | 44 | 14 | [15 empty] | 2014-05-20 |  | 2013-10-24 |  | Expedited | [8 empty] | 2018-04-25 | Online
WMECO | Southwick | 6S217-2013 | 1077 | 40 | Hydro | 29A2 | 2013-10-21 | 2013-11-05 | 12 | 1 | 11 | 2013-11-06 | 2013-12-04 | 18 | 2 | 16 | 2013-12-09 | 2014-01-30 | 36 | 20 | 16 | [15 empty] | 2014-02-06 |  | 2014-03-28 |  | Expedited | [6 empty] | 2015-11-16 | 2015-11-30 | 2015-11-30 | Online
WMECO | Greenfield | 6F508-2013 | 1301 | 29.985 | Solar | 22B2 | 2013-10-25 | 2013-11-05 | 8 | 0 | 8 | 2013-11-05 | 2013-11-05 | 1 | 0 | 1 | [20 empty] | 2014-01-03 |  | ASAP |  | Expedited | [6 empty] | 2014-04-14 | 2014-04-15 | 2014-04-15 | Online
WMECO | Hadley | 6A496-2013 | 1305 | 1950 | Solar | 17K1 | 2013-10-28 | 2014-01-17 | 55 | 10 | 45 | [10 empty] | 2014-01-21 | 2014-03-10 | 34 | 21 | 13 | 2014-04-09 | 2014-06-30 | 56 | 0 | 56 | 2014-12-09 | 2015-05-27 | 115 | 97 | 18 | 2015-07-21 |  |  |  | Standard | [7 empty] | 2016-10-20 | 2016-10-25 | Online
WMECO | Greenfield | 6F513-2013 | 1301 | 16 | Solar | 22B7 | 2013-10-29 | 2013-11-05 | 6 | 3 | 3 | 2013-11-07 | 2013-11-12 | 3 | 0 | 3 | [20 empty] | 2013-11-18 |  | 2013-11-10 |  | Expedited | [6 empty] | 2013-12-18 | 2013-12-23 | 2014-01-17 | Online
WMECO | Dalton | 6B345-2013 | 1226 | 1650 | Solar | 19A3 | 2013-12-03 | 2014-02-28 | 60 | 57 | 3 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | 2014-05-12 |  | -29805 | 11 | [10 empty] | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B359-2014 | 1201 | 16.5 | Solar | 30B7 | 2014-01-06 | 2014-02-12 | 27 | 15 | 12 | 2014-02-12 | 2014-02-12 | 1 | 0 | 1 | [20 empty] | 2014-02-18 |  | 2014-02-04 |  | Expedited | [6 empty] | 2014-04-17 | 2014-04-18 | 2014-04-18 | Online
WMECO | Dalton | 6B364-2014 | 1226 | 1250 | Solar | 19A3 | 2014-01-14 | 2014-02-28 | 32 | 16 | 16 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | [14 empty] | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S240-2014 | 1089 | 1950 | Solar | 16C12 | 2014-01-17 | 2014-03-12 | 37 | 22 | 15 | [10 empty] | 2014-03-13 | 2014-06-12 | 63 | 56 | 7 | 2014-07-18 | 2014-12-05 | 97 | 90 | 7 | 2015-04-21 | 2015-11-20 | 148 | 70 | 78 | 2015-11-30 |  | 2014-10-01 |  | Complex | [6 empty] | 2017-03-14 | 2017-03-22 | 2017-03-30 | Online
WMECO | Springfield | 6S244-2014 | 1111 | 4000 | Diesel | 5J14 | 2014-02-04 | 2014-02-24 | 14 | 13 | 1 | 2014-02-25 | 2014-03-19 | 16 | 0 | 16 | 2014-04-22 | 2014-05-12 | 15 | 10 | 5 | [15 empty] | 2014-07-02 |  | 2014-06-01 |  | Expedited | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Online
WMECO | Lee | 6B369-2014 | 1238 | 15.265 | Solar | 16B5 | 2014-02-05 | 2014-02-19 | 10 | 6 | 4 | 2014-02-20 |  | -29750 | 25 | [23 empty] | 2014-03-28 |  | Expedited | [9 empty] | Withdrawn
WMECO | Lee | 6B370-2014 | 1238 | 17.325 | Solar | 16B5 | 2014-02-05 | 2014-02-25 | 14 | 10 | 4 | 2014-02-26 | 2014-06-23 | 80 | 71 | 9 | [20 empty] | 2014-08-05 |  | 2014-01-24 |  | Expedited | [6 empty] | 2016-02-10 | 2016-02-16 | 2016-02-16 | Online
WMECO | Conway | 6F542-2014 | 1341 | 16.125 | Solar | 38A1 | 2014-02-24 | 2014-04-10 | 33 | 25 | 8 | 2014-04-11 | 2014-04-15 | 3 | 1 | 2 | [20 empty] | 2014-04-15 |  | 2014-03-21 |  | Expedited | [6 empty] | 2014-04-22 | 2014-04-24 | 2014-04-24 | Online
WMECO | Amherst | 6A540-2014 | 1002 | 24 | Solar | 17K6 | 2014-02-28 | 2014-03-12 | 9 | 8 | 1 | 2014-03-13 | 2014-05-01 | 34 | 14 | 20 | [20 empty] | 2014-05-07 |  | 2014-04-01 |  | Expedited | [6 empty] | 2014-05-30 | 2014-06-04 | 2014-06-04 | Online
WMECO | Lee | 6B383-2014 | 1238 | 19.8 | Solar | 16B5 | 2014-03-03 | 2014-03-19 | 12 | 7 | 5 | 2014-03-20 | 2014-05-20 | 43 | 6 | 37 | [20 empty] | 2014-06-10 |  | 2014-04-15 |  | Expedited | [6 empty] | 2014-09-12 | 2014-09-15 | 2014-09-30 | Online
WMECO | West Hatfield | 6A543-2014 | 1088 | 500 | Solar | 18G5 | 2014-03-06 | [31 empty] | 2014-06-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Longmeadow | 6S254-2014 | 1106 | 12 | Solar | 22H12 | 2014-03-11 | [31 empty] | 2014-05-30 |  | Expedited | [9 empty] | Withdrawn
WMECO | Whately | 6A564-2014 | 1093 | 22.8 | Solar | 18G6 | 2014-04-14 | 2014-04-23 | 7 | 0 | 7 | 2014-05-05 | 2014-05-21 | 13 | 7 | 6 | [20 empty] | 2014-05-21 |  | 2014-05-01 |  | Expedited | [6 empty] | 2014-08-05 | 2014-08-06 | 2014-08-06 | Online
WMECO | Springfield | 6S312-2014 | 1119 | 336 | Solar | 20A33 | 2014-06-11 | 2014-07-03 | 16 | 6 | 10 | 2014-07-07 | 2015-01-20 | 135 | 134 | 1 | 2015-01-21 | 2015-02-11 | 16 | 0 | 16 | [15 empty] | 2015-03-27 |  | 2014-11-17 |  | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B409-2014 | 1201 | 266 | Solar | 15E2 | 2014-06-23 | 2014-07-22 | 21 | 18 | 3 | 2014-07-23 | 2015-05-06 | 196 | 192 | 4 | 2015-05-21 | 2015-06-17 | 18 | 0 | 18 | [15 empty] | 2015-08-14 |  | 2014-08-25 |  | Expedited | [6 empty] | 2015-12-17 | 2016-04-21 | 2016-04-21 | Online
WMECO | Springfield | 6S334-2014 | 1129 | 278.4 | Solar | 20A35 | 2014-06-23 | [31 empty] | 2014-10-31 |  | Expedited | [9 empty] | Withdrawn
WMECO | Windsor | 6B413-2014 | 1270 | 24 | Solar | 18C1 | 2014-07-10 | 2014-07-22 | 9 | 2 | 7 | 2014-08-21 | 2014-09-03 | 9 | 8 | 1 | [20 empty] | 2014-09-05 |  | 2014-11-01 |  | Expedited | [6 empty] | 2014-12-09 | 2014-12-16 | 2014-12-16 | Online
WMECO | Russell | 6A681-2014 | 1071 | 49 | Solar | 19J2 | 2014-07-16 | 2014-09-05 | 37 | 30 | 7 | 2014-09-12 | 2014-12-03 | 56 | 50 | 6 | [20 empty] | 2014-12-16 |  | 2014-09-26 |  | Expedited | [6 empty] | 2015-10-02 | 2015-10-06 | 2015-10-06 | Online
WMECO | Hadley | 6A682-2014 | 1035 | 24.98 | Solar | 18G4 | 2014-07-16 | 2014-08-26 | 30 | 26 | 4 | 2014-08-27 | 2014-09-04 | 6 | 2 | 4 | [20 empty] | 2014-09-04 |  | not supplied |  | Expedited | [6 empty] | 2014-12-22 | 2014-12-22 | 2014-12-22 | Online
WMECO | Greenfield | 6F594-2014 | 1301 | 600 | Diesel | 22B7 | 2014-07-24 | 2014-08-26 | 24 | 23 | 1 | 2014-08-26 | 2014-12-03 | 68 | 54 | 14 | 2014-12-03 | 2014-12-29 | 18 | 0 | 18 | [15 empty] | 2015-01-07 |  | not supplied |  | Expedited | [8 empty] | 2018-04-25 | Online
WMECO | Springfield | 6S386-2014 | 1103 | 42 | Solar | 8CNW_1 | 2014-08-04 | 2014-08-25 | 16 | 15 | 1 | 2014-08-26 | 2014-09-29 | 24 | 22 | 2 |  |  |  | 17 | [18 empty] | 2014-08-01 |  | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S468-2014 | 1089 | 200 | Solar | 16C12 | 2014-08-25 |  |  | 165 | [28 empty] | 2014-08-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B427-2014 | 1201 | 30.25 | Solar | 30B4 | 2014-08-26 | 2014-09-18 | 17 | 14 | 3 | 2014-09-19 | 2014-09-22 | 2 | 1 | 1 | [20 empty] | 2014-09-22 |  | 2014-12-01 |  | Expedited | [6 empty] | 2015-01-29 | 2015-02-04 | 2015-02-04 | Online
WMECO | Chesterfield | 6F652-2014 | 1012 | 22 | Solar | 18K3 | 2014-09-15 | 2014-10-15 | 22 | 20 | 2 | 2014-10-16 | 2014-11-05 | 15 | 8 | 7 | [20 empty] | 2014-11-12 |  | Q4 2014 |  | Expedited | [6 empty] | 2015-01-21 | 2015-01-26 | 2015-01-26 | Online
WMECO | Pittsfield | 6B436-2014 | 1201 | 499 | Solar | 30B2 | 2014-09-25 | 2014-10-09 | 11 | 5 | 6 | 2014-10-09 | 2014-10-15 | 4 | 3 | 1 | 2014-10-16 | 2014-11-07 | 17 | 0 | 17 | [15 empty] | 2014-12-02 |  | 2014-12-14 |  | Expedited | 2014-12-27 | 2014-12-30 | 2014-12-30 | 1 |  | 1 | 2014-12-26 | 2014-12-31 | 2015-01-12 | Online
WMECO | Springfield | 6S530-2014 | 1109 | 44.55 | Solar | 5JNW_1 | 2014-09-29 |  |  | 14 | [28 empty] | 2014-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S531-2014 | 1109 | 44.55 | Solar | 5J9 | 2014-09-29 | 2014-10-28 | 21 | 20 | 1 | 2014-10-29 | 2014-11-18 | 14 | 3 | 11 | [20 empty] | 2014-11-24 |  | 2014-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2015-02-18 | Online
WMECO | Indian Orchard | 6S532-2014 | 1151 | 180 | Solar | 27A13 | 2014-09-29 | 2014-10-14 | 11 | 10 | 1 | 2014-10-15 | 2014-11-26 | 30 | 9 | 21 | [20 empty] | 2014-12-05 |  | 2014-11-30 |  | Expedited |  |  |  | 0 |  |  | 2015-08-28 | 2015-09-02 | 2015-09-02 | Online
WMECO | Easthampton | 6A880-2014 | 1027 | 98 | Solar | 15A2 | 2014-10-06 | 2014-11-26 | 36 | 34 | 2 | 2014-11-28 | 2015-02-19 | 56 | 35 | 21 | [20 empty] | 2015-04-15 |  | 2014-12-01 |  | Expedited |  |  |  | 0 |  |  | 2016-03-03 | 2016-03-10 | 2016-03-10 | Online
WMECO | Pittsfield | 6B446-2014 | 1201 | 234 | Solar | 19A5 | 2014-10-15 | 2014-10-28 | 10 | 3 | 7 | 2014-10-29 | 2014-12-10 | 29 | 13 | 16 | 2014-12-11 | 2016-02-19 | 295 | 262 | 33 | [15 empty] | 2016-02-22 |  | 2014-12-31 |  | Expedited |  |  |  | 0 |  |  | 2016-03-17 | 2016-03-23 | 2016-03-23 | Online
WMECO | Pittsfield | 6B447-2014 | 1201 | 168 | Solar | 30B2 | 2014-10-24 | 2014-10-29 | 4 | 0 | 4 | 2014-10-30 | 2014-11-18 | 13 | 12 | 1 | [20 empty] | 2014-12-09 |  | 2014-12-12 |  | Expedited |  |  |  | 0 |  |  | 2015-01-21 | 2015-01-22 | 2015-01-22 | Online
WMECO | Amherst | 6A919-2014 | 1002 | 57.75 | Solar | 17K8 | 2014-11-05 | 2014-11-25 | 14 | 6 | 8 | 2014-11-26 | 2015-03-02 | 64 | 33 | 31 | [20 empty] | 2015-03-04 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-06-12 | 2015-06-15 | 2015-06-15 | Online
WMECO | Hatfield | 6A935-2014 | 1038 | 3300 | Solar | 18G5 | 2014-11-13 | 2015-03-04 | 75 | 69 | 6 | [10 empty] | 2015-03-05 | 2015-06-06 | 64 | 61 | 3 | 2015-05-29 | 2015-11-05 | 111 | 12 | 99 | 2016-04-12 |  | -30281 |  |  |  |  | 2015-10-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S672-2014 | 1056 | 998 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S673-2014 | 1056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S674-2014 | 1056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S689-2014 | 1104 | 150 | Solar | 21S7 | 2014-11-25 | 2015-07-30 | 168 | 163 | 5 | 2015-07-31 | 2016-05-05 | 190 | 31 | 159 | [10 empty] | 2016-05-06 | 2016-09-26 | 98 | 46 | 52 | [5 empty] | 2016-09-26 |  | 12/2014 |  | Standard |  |  |  | 0 |  |  | 2017-08-24 | 2017-08-25 | 2017-08-25 | Online
WMECO | Otis | 6B458-2014 | 1029 | 1500 | Wind | 19J6 | 2014-12-01 | 2014-12-17 | 13 | 12 | 1 | [10 empty] | 2014-12-18 | 2015-03-26 | 66 | 63 | 3 | 2015-03-27 | 2015-07-23 | 81 | 17 | 64 | 2016-02-23 |  | -30247 | 144 |  | 2015-07-27 |  | 2015-06-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-03-09 | Online
WMECO | Otis | 6B459-2014 | 1253 | 960 | Solar | 19J4 | 2014-12-02 | 2015-01-19 | 32 | 27 | 5 | 2015-01-20 | 2015-06-15 | 101 | 44 | 57 | [10 empty] | 2015-08-03 | 2016-01-04 | 105 | 41 | 64 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A962-2014 | 1375 | 22.8 | Solar | 18G3 | 2014-12-03 | 2014-12-30 | 19 | 9 | 10 | 2014-12-31 | 2015-02-27 | 40 | 36 | 4 | [20 empty] | 2015-03-06 |  | 2015-02-01 |  | Expedited |  |  |  | 0 |  |  | 2015-04-15 | 2015-04-16 | 2015-04-16 | Online
WMECO | Pittsfield | 6B462-2014 | 1201 | 3300 | Solar | 15E2 | 2014-12-08 | 2014-12-15 | 6 | 2 | 4 | [10 empty] | 2014-12-16 | 2015-02-17 | 42 | 26 | 16 | 2015-03-16 | 2015-08-24 | 111 | 33 | 78 | 2015-08-11 | 2015-10-22 | 51 | 30 | 21 | 2015-10-23 |  | 2015-08-27 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-04-13 | Online
WMECO | Otis | 6B463-2014 | 1253 | 960 | Solar | 19J4 | 2014-12-08 | 2015-01-19 | 28 | 24 | 4 | 2015-01-20 | 2015-06-15 | 101 | 44 | 57 | [10 empty] | 2015-08-03 | 2016-01-04 | 105 | 41 | 64 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S708-2014 | 1106 | 16.35 | Solar | 22H12 | 2014-12-09 | 2014-12-15 | 5 | 0 | 5 | 2014-12-16 | 2015-01-23 | 26 | 11 | 15 | [20 empty] | 2015-02-03 |  | 2015-02-09 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F724-2014 | 1301 | 48 | Solar | 21C1 | 2014-12-12 | 2014-12-30 | 12 | 10 | 2 | 2014-12-31 | 2015-03-09 | 46 | 38 | 8 | [20 empty] | 2015-03-25 |  | 2015-02-15 |  | Expedited |  |  |  | 0 |  |  | 2015-06-04 | 2015-06-08 | 2015-06-08 | Online
WMECO | Deerfield | 6F725-2014 | 1342 | 4500 | Solar | 22B4 | 2014-12-12 | 2015-01-29 | 32 | 23 | 9 | [10 empty] | 2015-01-30 | 2015-03-17 | 31 | 16 | 15 | 2015-03-18 | 2015-11-30 | 176 | 38 | 138 | 2016-03-18 |  | -30264 |  |  | 2015-12-07 |  | Q3/4 2015 |  | Complex |  |  |  | 0 |  |  | 2017-10-11 | 2017-10-18 | 2017-12-08 | Online
WMECO | Greenfield | 6F736-2014 | 1301 | 24 | Solar | 21C4 | 2014-12-26 | 2015-01-22 | 18 | 13 | 5 | 2015-01-23 | 2015-03-12 | 34 | 23 | 11 | [22 empty] | Feb 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S764-2015 | 1108 | 37.8 | Solar | 22H16 | 2015-01-06 | 2015-01-30 | 18 | 17 | 1 | 2015-02-02 | 2015-03-06 | 24 | 15 | 9 | 2015-03-09 | 2015-04-03 | 19 | 1 | 18 | [15 empty] | 2015-04-20 |  | 2015-01-22 |  | Expedited |  |  |  | 0 |  |  | 2015-08-10 | 2015-08-12 | 2015-08-13 | Online
WMECO | Pittsfield | 6B474-2015 | 1201 | 36 | Solar | 15E3 | 2015-01-07 | 2015-02-11 | 25 | 9 | 16 | 2015-02-12 | 2015-04-08 | 38 | 37 | 1 | 2015-04-28 | 2015-05-18 | 15 | 14 | 1 | [15 empty] | 2015-07-08 |  | 2015-08-01 |  | Expedited |  |  |  | 0 |  |  | 2015-11-10 | 2015-11-13 | 2015-11-13 | Online
WMECO | Deerfield | 6F749-2015 | 1342 | 40 | Solar | 22B1 | 2015-01-07 | 2015-02-04 | 20 | 15 | 5 | 2015-02-05 | 2015-09-18 | 155 | 111 | 44 | [20 empty] | 2015-09-18 |  | 2015-02-01 |  | Expedited |  |  |  | 0 |  |  | 2015-11-05 | 2015-11-12 | 2016-02-03 | Online
WMECO | Hadley | 6A1005-2015 | 1035 | 253 | Solar | 17K6 | 2015-01-09 | 2015-01-23 | 10 | 5 | 5 | 2015-01-26 | 2015-03-02 | 25 | 15 | 10 | 2015-03-05 | 2015-03-27 | 16 | 0 | 16 | [15 empty] | 2015-04-03 |  | 2015-05-05 |  | Expedited |  |  |  | 0 |  |  | 2015-06-24 | 2015-07-01 | 2015-07-23 | Online
WMECO | Lanesborough | 6B479-2015 | 1237 | 368 | Solar | 15E2 | 2015-01-21 | 2015-02-04 | 11 | 6 | 5 | 2015-02-05 | 2015-03-03 | 18 | 12 | 6 | 2015-03-04 | 2017-01-08 | 459 | 435 | 24 | [15 empty] | 2017-01-10 |  | 2015-05-05 |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-12-22 | Online
WMECO | Becket | 6B481-2015 | 1223 | 24 | Solar | 16B1 | 2015-01-23 | 2015-01-26 | 2 | 1 | 1 | 2015-01-27 | 2015-03-06 | 28 | 16 | 12 | [20 empty] | 2015-03-10 |  | Spring 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-10-05 | 2015-10-07 | 2015-10-09 | Online
WMECO | Whately | 6A1047-2015 | 1093 | 20 | Solar | 18G8 | 2015-02-02 | 2015-02-19 | 13 | 5 | 8 | 2015-02-19 | 2015-02-20 | 2 | 0 | 2 | [20 empty] | 2015-02-20 |  | Q1 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-07-03 | 2015-07-07 | 2015-07-07 | Online
WMECO | Hatfield | 6A1053-2015 | 1038 | 1890 | Solar | 18G6 | 2015-02-09 | 2015-05-15 | 67 | 65 | 2 | 2015-05-18 | 2015-10-29 | 114 | 76 | 38 | [10 empty] | 2015-10-30 | 2016-02-12 | 71 | 2 | 69 | 2016-03-07 |  | -30256 |  |  | 2016-02-12 |  | Sept 2015 |  | Complex |  |  |  | 0 |  |  | 2017-07-03 | 2017-07-10 | 2017-09-07 | Online
WMECO | Whately | 6A1062-2015 | 1093 | 19.3 | Solar | 18G6 | 2015-02-19 | 2015-04-22 | 43 | 41 | 2 | 2015-04-23 | 2015-07-10 | 54 | 47 | 7 | [20 empty] | 2015-07-10 |  | 2015-04-06 |  | Expedited |  |  |  | 0 |  |  | 2016-01-29 | 2016-02-02 | 2016-02-02 | Online
WMECO | Becket | 6B483-2015 | 1223 | 17.5 | Solar | 19J6 | 2015-02-23 | 2015-04-16 | 38 | 18 | 20 | 2015-04-17 | 2015-04-30 | 9 | 8 | 1 | [20 empty] | 2015-05-18 |  | 2015-05-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2015-11-04 | Online
WMECO | South Deerfield | 6F801-2015 | 1342 | 500 | Biogas | 22B1 | 2015-02-24 | 2015-04-15 | 36 | 34 | 2 | 2015-04-16 | 2015-05-22 | 26 | 16 | 10 | [22 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F802-2015 | 1373 | 18 | Solar | 18G3 | 2015-02-24 | 2015-03-05 | 8 | 0 | 8 | 2015-03-06 | 2015-03-13 | 6 | 4 | 2 | [20 empty] | 2015-03-24 |  | March 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-05-19 | 2015-05-21 | 2015-05-21 | Online
WMECO | Greenfield | 6F815-2015 | 1301 | 56 | Solar | 21C1 | 2015-03-05 | 2015-03-31 | 18 | 15 | 3 | 2015-04-01 | 2015-04-13 | 9 | 2 | 7 | [20 empty] | 2015-04-15 |  | 2015-05-01 |  | Expedited |  |  |  | 0 |  |  | 2017-04-19 | 2017-04-20 | 2017-04-20 | Online
WMECO | Lee | 6B490-2015 | 1238 | 1904 | Solar | 17G7 | 2015-03-12 | 2015-03-20 | 6 | 2 | 4 | [10 empty] | 2015-03-23 | 2015-04-30 | 28 | 23 | 5 | 2015-05-15 | 2015-08-12 | 61 | 3 | 58 | 2015-08-20 |  | -30122 |  |  | 2015-08-27 |  | 2015-09-30 |  | Standard |  |  |  | 0 |  |  | 2017-03-28 | 2015-04-11 | 2017-04-11 | Online
WMECO | Pittsfield | 6B497-2015 | 1201 | 2340 | Solar | 19A3 | 2015-03-24 | 2015-03-31 | 6 | 2 | 4 | [10 empty] | 2015-04-01 | 2015-06-04 | 45 | 30 | 15 | 2015-06-05 | 2015-11-06 | 107 | 0 | 107 | 2015-11-24 | 2016-09-21 | 206 | 0 | 206 | 2015-11-09 |  | Fall 2015 |  | Complex |  |  |  | 0 |  |  | 2017-01-18 | 2017-01-20 | 2017-01-31 | Online
WMECO | Greenfield | 6F836-2015 | 1301 | 19.3 | Solar | 21C4 | 2015-03-27 | 2015-04-20 | 16 | 8 | 8 | 2015-04-21 | 2015-04-21 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2015-04-22 |  | 2015-04-01 |  | Expedited |  |  |  | 0 |  |  | 2015-05-15 | 2015-05-19 | 2015-05-19 | Online
WMECO | Granville | 6S941-2015 | 1034 | 24.99 | Solar | 29A5 | 2015-04-06 | 2015-04-16 | 9 | 6 | 3 | 2015-04-16 | 2015-04-16 | 1 | 0 | 1 | 2015-04-21 | 2015-05-06 | 12 | 0 | 12 |  |  | 0 | [12 empty] | 2015-05-07 |  | 2015-06-01 |  | Expedited |  |  |  | 0 |  |  | 2015-07-30 | 2015-07-31 | 2015-07-31 | Online
WMECO | Sunderland | 6A1124-2015 | 1375 | 44 | Solar | 18G3 | 2015-04-17 | 2015-05-12 | 17 | 11 | 6 | 2015-05-13 | 2015-06-18 | 25 | 0 | 25 | 2015-06-22 | 2015-06-30 | 7 | 0 | 7 |  |  | 0 | [12 empty] | 2015-06-30 |  | July 2015 |  | Expedited |  |  | 2015-09-25 | 30147 |  | 30147 | 2015-09-24 | 2015-09-30 | 2015-09-30 | Online
WMECO | Northfield | 6F857-2015 | 1360 | 56 | Solar | 21B8 | 2015-04-17 | 2015-05-12 | 17 | 6 | 11 | 2015-05-13 | 2015-05-27 | 10 | 0 | 10 | 2015-06-17 | 2015-07-20 | 22 | 17 | 5 |  |  | 0 | [12 empty] | 2015-07-31 |  | 7/2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-02 | 2016-02-03 | 2016-02-03 | Online
WMECO | Southwick | 6S959-2015 | 1077 | 1316 | Solar | 29A5 | 2015-04-17 | 2015-04-22 | 3 | 0 | 3 | 2015-04-23 | 2015-09-21 | 104 | 93 | 11 | [7 empty] | 0 |  |  | 2015-09-22 | 2015-12-11 | 56 | 0 | 56 | 2016-01-11 |  | -30218 |  |  | 2016-01-26 |  | 2015-12-01 |  | Complex |  |  |  | 0 |  |  |  | 2016-12-06 | 2016-12-14 | Online
WMECO | Shelburne Falls | 6F872-2015 | 1370 | 39.6 | Solar | 22B5 | 2015-04-23 | [16 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A1145-2015 | 1038 | 18.5 | Solar | 18G6 | 2015-04-27 | 2015-06-02 | 26 | 20 | 6 | 2015-06-03 | 2015-07-02 | 21 | 4 | 17 | [7 empty] | 0 | [12 empty] | 2015-07-10 |  | June 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-08-11 | 2015-08-17 | 2015-08-17 | Online
WMECO | South Deerfield | 6F881-2015 | 1373 | 16.7 | Solar | 22B1 | 2015-04-27 | 2015-05-18 | 16 | 13 | 3 | 2015-05-19 | 2015-05-27 | 6 | 3 | 3 | [7 empty] | 0 | [12 empty] | 2015-05-29 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-02-02 | 2016-02-03 | 2016-02-03 | Online
WMECO | Amherst | 6A1148-2015 | 1002 | 54 | Solar | 19B16 | 2015-04-29 | 2015-07-16 | 54 | 40 | 14 | 2015-07-17 | 2015-11-18 | 86 | 18 | 68 | [7 empty] | 0 | [12 empty] | 2015-11-18 |  | July 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-09-01 | 2016-09-07 | 2016-09-07 | Online
WMECO | Ashfield | 6F890-2015 | 1330 | 1995 | Biogas | 38A1 | 2015-05-01 | 2015-11-02 | 127 | 63 | 64 | 2015-11-03 | 2016-02-17 | 71 | 30 | 41 | [7 empty] | 0 |  |  | 2016-02-18 | 2016-08-15 | 123 | 54 | 69 | 2016-08-16 | 2017-10-05 | 286 | 34 | 252 | 2017-10-10 |  | 2016-01-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Richmond | 6B516-2015 | 1254 | 18 | Solar | 30B2 | 2015-05-04 | 2015-08-10 | 68 | 55 | 13 | 2015-08-11 | 2015-10-14 | 45 | 5 | 40 | 2015-10-15 | 2016-01-29 | 72 | 44 | 28 |  |  | 0 | [12 empty] | 2016-02-02 |  | 2015-06-01 |  | Expedited |  |  |  | 0 |  |  | 2016-09-21 | 2016-09-26 | 2016-10-18 | Online
WMECO | Pittsfield | 6B521-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-01 | 16 | 8 | 8 | 2015-06-02 | 2015-12-30 | 145 | 44 | 101 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B522-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 27 | 111 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B523-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 32 | 106 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B525-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 27 | 111 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | West Springfield | 6S1051-2015 | 1089 | 180 | Solar | 16C12 | 2015-05-08 | 2015-06-25 | 33 | 20 | 13 | 2015-06-26 |  | -30084 | [9 empty] | 0 | [14 empty] | 2015-11-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1169-2015 | 1035 | 140 | Solar | 18G5 | 2015-05-12 | 2015-06-11 | 22 | 10 | 12 | 2015-06-12 | 2015-11-16 | 107 | 105 | 2 | [7 empty] | 0 |  |  | 2015-11-16 | 2016-02-11 | 60 | 5 | 55 | [5 empty] | 2016-02-12 |  | 2015-08-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2016-09-27 | Online
WMECO | Pittsfield | 6B529-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-12 | 2015-07-06 | 37 | 10 | 27 | 2015-07-07 | 2015-12-30 | 122 | 32 | 90 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-10-24 | Online
WMECO | Ludlow | 6S1070-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 52 | 51 | 1 | 2015-07-31 | 2016-02-18 | 137 | 43 | 94 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-01-03 | Online
WMECO | Ludlow | 6S1071-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 52 | 51 | 1 | 2015-07-31 | 2016-02-18 | 137 | 43 | 94 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-12-21 | Online
WMECO | Shelburne Falls | 6F914-2015 | 1370 | 25 | Solar | 29R2 | 2015-05-19 | 2015-07-10 | 36 | 16 | 20 | 2015-07-13 | 2015-07-14 | 2 | 0 | 2 | [7 empty] | 0 | [12 empty] | 2015-07-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-08-24 | 2015-08-25 | 2015-08-25 | Online
WMECO | Pittsfield | 6B537-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 30 | 57 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Pittsfield | 6B538-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 29 | 58 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Pittsfield | 6B539-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 29 | 58 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Greenfield | 6F915-2015 | 1301 | 480 | Solar | 21C1 | 2015-05-21 | 2015-07-09 | 33 | 7 | 26 | 2015-07-10 | 2016-01-07 | 124 | 43 | 81 | [7 empty] | 0 |  |  | 2016-01-08 | 2016-05-13 | 87 | 29 | 58 | [7 empty] | 2015-07-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6F917-2015 | 1026 | 499 | Solar | 18K3 | 2015-05-21 | 2015-07-30 | 48 | 47 | 1 | 2015-07-31 | 2015-12-30 | 104 | 33 | 71 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | Oct 2015 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-08-09 | Online
WMECO | Ludlow | 6S1096-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-21 | 2015-06-24 | 23 | 17 | 6 | 2015-06-25 | 2016-02-18 | 162 | 43 | 119 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-01-03 | Online
WMECO | Amherst | 6A1199-2015 | 1002 | 2002 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 39 | 14 | 25 | 2015-07-21 | 2015-11-04 | 75 | 53 | 22 | [7 empty] | 0 |  |  | 2015-11-05 | 2016-03-03 | 80 | 13 | 67 | 2016-05-17 |  | -30305 |  |  | 2016-03-04 |  | 2015-12-31 |  | Complex |  |  |  | 0 |  |  | 2017-05-08 | 2017-05-11 | 2017-05-12 | Online
WMECO | Amherst | 6A1200-2015 | 1002 | 1728 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 39 | 14 | 25 | 2015-07-21 | 2015-11-04 | 75 | 53 | 22 | [7 empty] | 0 |  |  | 2015-11-05 | 2016-03-03 | 80 | 13 | 67 | 2016-05-17 |  | -30305 |  |  | 2016-03-04 |  | 2015-12-31 |  | Complex |  |  |  | 0 |  |  | 2017-11-22 | 2017-11-28 | 2017-12-27 | Online
WMECO | Cummington | 6F920-2015 | 1026 | 840 | Solar | 18K3 | 2015-05-22 | 2015-07-30 | 47 | 46 | 1 | 2015-07-31 | 2015-12-30 | 104 | 33 | 71 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-06-15 | 114 | 0 | 114 | [7 empty] | Oct 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F921-2015 | 1342 | 19.3 | Solar | 22B7 | 2015-05-26 | 2015-07-06 | 28 | 4 | 24 | 2015-07-07 | 2015-07-22 | 12 | 1 | 11 | [7 empty] | 0 | [12 empty] | 2015-08-14 |  | Aug 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-04 | 2016-02-08 | 2016-02-08 | Online
WMECO | Amherst | 6A1211-2015 | 1002 | 192 | Solar | 18G2 | 2015-05-29 | 2015-07-06 | 25 | 9 | 16 | 2015-07-07 | 2015-10-08 | 67 | 37 | 30 | [7 empty] | 0 | [12 empty] | 2015-10-23 |  | 2015-09-01 |  | Expedited |  |  |  | 0 |  |  | 2016-02-11 | 2016-02-18 | 2016-02-18 | Online
WMECO | Plainfield | 6F926-2015 | 1070 | 331 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 43 | 6 | 37 | 2015-07-31 | 2015-11-05 | 68 |  | 68 | [7 empty] | 0 | [14 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F927-2015 | 1070 | 499 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 43 | 6 | 37 | 2015-07-31 | 2015-11-05 | 68 |  | 68 | [7 empty] | 0 | [14 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1217-2015 | 1002 | 15 | Solar | 17K8 | 2015-06-01 | 2015-07-06 | 24 | 1 | 23 | 2015-07-07 | 2015-07-23 | 13 | 1 | 12 | [7 empty] | 0 | [12 empty] | 2015-08-14 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-09-01 | 2015-09-11 | 2015-09-11 | Online
WMECO | Turners Falls | 6F939-2015 | 1376 | 1774 | Solar | 21C3 | 2015-06-05 | 2015-10-05 | 84 | 1 | 83 | 2015-10-06 |  | -30154 | [9 empty] | 0 | [14 empty] | 2015-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B553-2015 | 1201 | 1480 | Solar | 30B7 | 2015-06-08 | 2015-07-22 | 31 | 17 | 14 | 2015-07-23 | 2015-10-20 | 62 | 29 | 33 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-07-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-12-21 | Online
WMECO | Pittsfield | 6B554-2015 | 1201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 64 | 44 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 2015-07-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B555-2015 | 1201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 64 | 44 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 1901-12-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne Falls | 6F953-2015 | 1370 | 40 | Solar | 22B5 | 2015-06-10 | 2015-07-17 | 26 | 9 | 17 | 2015-07-20 | 2015-08-10 | 16 | 15 | 1 | 2015-08-20 | 2015-10-05 | 32 | 22 | 10 |  |  | 0 | [12 empty] | 2015-10-07 |  | 2015-08-01 |  | Expedited |  |  |  | 0 |  |  | 2015-12-23 | 2015-12-30 | 2015-12-30 | Online
WMECO | Easthampton | 6A1251-2015 | 1027 | 244 | Solar | 15A3 | 2015-06-15 | 2015-09-28 | 73 | 12 | 61 | 2015-09-29 |  | -30149 | 117 | [8 empty] | 0 | [14 empty] | 2015-07-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1252-2015 | 1093 | 496 | Solar | 18G8 | 2015-06-15 | 2015-07-17 | 23 | 18 | 5 | 2015-07-20 | 2015-11-02 | 74 | 21 | 53 | [7 empty] | 0 |  |  | 2015-11-03 | 2016-01-27 | 57 | 3 | 54 | 2016-03-09 |  | -30258 | 0 |  | 2016-02-04 |  | not supplied |  | Standard |  |  |  | 0 |  |  | 2017-02-28 | 2017-03-01 | 2017-03-02 | Online
WMECO | Springfield | 6S1174-2015 | 1104 | 150 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 59 | 40 | 19 | 2015-09-09 | 2016-06-01 | 181 | 95 | 86 | [7 empty] | 0 |  |  | 2016-06-02 | 2016-08-23 | 57 | 0 | 57 | 2016-09-14 |  | -30387 |  |  | 2016-09-14 |  | 2015-07-31 |  | Standard |  |  |  | 0 |  |  | 2017-10-05 | 2017-10-11 | 2017-10-26 | Online
WMECO | Springfield | 6S1175-2015 | 1104 | 284 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 59 | 40 | 19 | 2015-09-09 | 2016-06-01 | 181 | 95 | 86 | [7 empty] | 0 |  |  | 2016-06-02 | 2016-08-23 | 57 | 0 | 57 | 2016-09-14 |  | -30387 |  |  | 2016-09-14 |  | 1901-12-31 |  | Standard |  |  |  | 0 |  |  | 2018-01-17 | 2018-01-24 | 2018-01-30 | Online
WMECO | Pittsfield | 6B569-2015 | 1201 | 408 | Solar | 19A8 | 2015-06-18 | 2015-09-29 | 72 | 25 | 47 | 2015-09-30 |  | -30150 | [9 empty] | 0 | [14 empty] | 2015-07-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B571-2015 | 1223 | 10 | Solar | 19J6 | 2015-06-18 | 2015-07-22 | 24 | 23 | 1 | 2015-07-23 | 2015-08-20 | 21 | 2 | 19 | [7 empty] | 0 | [12 empty] | 2015-08-20 |  | 08-2015 |  | Expedited |  |  |  | 0 |  |  | 2016-01-25 | 2016-01-25 | 2016-01-25 | Online
WMECO | Shelburne | 6F969-2015 | 1370 | 16.7 | Solar | 22B6 | 2015-06-18 | 2015-07-30 | 30 | 13 | 17 | 2015-07-31 |  | -30108 | [9 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F970-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-10-06 | 77 | 1 | 76 | 2015-10-07 | 2015-12-30 | 57 | 33 | 24 | [7 empty] | 0 |  |  | 2015-12-31 |  | -30212 | [9 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F971-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 72 | 1 | 71 | 2015-09-30 | 2015-12-30 | 62 | 33 | 29 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | 2015-10-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F972-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 72 | 1 | 71 | 2015-09-30 | 2015-12-30 | 62 | 33 | 29 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | 2015-10-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1270-2015 | 1027 | 27 | Solar | 15A3 | 2015-06-19 | 2015-08-10 | 36 | 23 | 13 | 2015-08-11 | 2015-11-10 | 64 | 0 | 64 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-17 | 2015-12-18 | Online
WMECO | Blandford | 6B572-2015 | 1008 | 499 | Solar | 19J2 | 2015-06-19 | 2015-09-28 | 70 | 4 | 66 | 2015-09-29 |  | -30149 | [9 empty] | 0 | [14 empty] | Winter 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B579-2015 | 1201 | 170 | Solar | 30B2 | 2015-06-23 | 2015-09-08 | 54 | 34 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 2015-07-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F980-2015 | 1301 | 450 | Diesel | 21C4 | 2015-06-23 | 2015-09-29 | 69 | 17 | 52 | 2015-09-30 | 2016-02-23 | 98 | 18 | 80 | 2016-02-23 | 2016-10-05 | 156 | 5 | 151 |  |  | 0 | [12 empty] | 2016-10-06 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-12-07 | 2016-12-18 | 2016-12-19 | Online
WMECO | Plainfield | 6F986-2015 | 1070 | 392 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 65 | 0 | 65 | 2015-09-30 | 2015-11-05 | 26 |  | 26 | [7 empty] | 0 | [14 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F987-2015 | 1070 | 499 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 65 | 0 | 65 | 2015-09-30 | 2015-11-05 | 26 |  | 26 | [7 empty] | 0 | [14 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1298-2015 | 1375 | 242 | Solar | 18G3 | 2015-07-02 | 2015-12-21 | 118 | 30 | 88 | 2015-12-22 | 2016-01-28 | 25 | 9 | 16 | [7 empty] | 0 |  |  | 2016-01-28 | 2016-04-28 | 63 | 0 | 63 | [5 empty] | 2016-05-03 |  | winter 2015 |  | Standard |  |  |  | 0 |  |  | 2016-12-27 | 2016-12-28 | 2016-12-30 | Online
WMECO | Sunderland | 6A1309-2015 | 1375 | 160 | Solar | 18G3 | 2015-07-10 | 2015-12-21 | 113 | 25 | 88 | 2015-12-22 | 2016-01-28 | 25 | 9 | 16 | [7 empty] | 0 |  |  | 2016-01-28 | 2016-04-28 | 63 | 0 | 63 | [7 empty] | winter 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6F1012-2015 | 1341 | 19.8 | Solar | 38A1 | 2015-07-14 | 2015-08-07 | 19 | 6 | 13 | 2015-08-10 | 2015-11-03 | 60 | 11 | 49 | 2015-11-12 | 2015-11-30 | 12 | 0 | 12 |  |  | 0 | [12 empty] | 2015-12-07 |  | 2015-09-01 |  | Expedited |  |  |  | 0 |  |  | 2016-03-04 | 2016-03-08 | 2016-03-08 | Online
WMECO | Easthampton | 6A1329-2015 | 1027 | 20.5 | Solar | 15A5 | 2015-07-15 | 2015-08-10 | 19 | 18 | 1 | 2015-08-11 | 2015-10-15 | 46 | 0 | 46 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | 2015-10-05 |  | Expedited |  |  |  | 0 |  |  | 2015-12-18 | 2015-12-22 | 2015-12-22 | Online
WMECO | Bernardston | 6F1028-2015 | 1337 | 36 | Solar | 21C1 | 2015-07-27 | 2015-09-23 | 42 | 5 | 37 | 2015-09-24 | 2015-10-13 | 13 | 3 | 10 | [7 empty] | 0 | [12 empty] | 2015-10-13 |  | Sept 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-17 | 2015-12-18 | Online
WMECO | Easthampton | 6A1343-2015 | 1027 | 1980 | Solar | 15A2 | 2015-07-30 | 2015-12-09 | 91 | 26 | 65 | 2015-12-10 |  | -30198 | [9 empty] | 0 | [14 empty] | 2016-05-28 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B624-2015 | 1201 | 995 | Solar | 30B7 | 2015-07-31 | 2015-08-06 | 5 | 3 | 2 | 2015-08-07 |  | -30113 | [9 empty] | 0 | [14 empty] | 10/1/2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B625-2015 | 1201 | 870 | Solar | 30B3 | 2015-08-03 | 2015-10-06 | 46 | 13 | 33 | 2015-10-07 | 2016-05-02 | 140 | 92 | 48 | [7 empty] | 0 |  |  | 2016-05-03 | 2016-07-19 | 53 | 32 | 21 | [7 empty] | 12/1/2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S1388-2015 | 1089 | 30 | Solar | 21N6 | 2015-08-03 | 2015-09-23 | 37 | 19 | 18 | 2015-09-24 | 2015-11-10 | 33 | 9 | 24 | [7 empty] | 0 | [12 empty] | 2015-11-16 |  | Q3 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-11 | 2016-02-17 | 2016-02-17 | Online
WMECO | Whately | 6A1350-2015 | 1093 | 1115 | Solar | 18G8 | 2015-08-04 | 2015-11-20 | 76 | 11 | 65 | 2015-11-23 | 2016-04-28 | 107 | 51 | 56 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 | 1 | 85 | 2016-10-31 |  | -30419 |  |  | 2016-10-03 |  | 2/28/16 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-10-01 | Online
WMECO | Hinsdale | 6B635-2015 | 1235 | 1484 | Solar | 18C2 | 2015-08-11 | [16 empty] | 0 | [14 empty] | 2015-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1366-2015 | 1035 | 32 | Solar | 17K5 | 2015-08-12 | 2015-10-22 | 50 | 39 | 11 | 2015-10-23 | 2015-11-03 | 8 | 0 | 8 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-01-27 | 2016-01-29 | 2016-01-29 | Online
WMECO | Pittsfield | 6B640-2015 | 1201 | 54 | Solar | 30B2 | 2015-08-12 | 2015-09-23 | 30 | 5 | 25 | 2015-09-24 | 2015-12-29 | 65 | 47 | 18 | [7 empty] | 0 | [12 empty] | 2015-12-30 |  | 2015-07-01 |  | Expedited |  |  |  | 0 |  |  | 2016-05-13 | 2016-05-13 | 2016-05-13 | Online
WMECO | Springfield | 6S1435-2015 | 1104 | 140 | Solar | 5J16 | 2015-08-13 | 2015-09-24 | 30 | 5 | 25 | 2015-09-25 | 2016-02-05 | 90 | 19 | 71 | [7 empty] | 0 |  |  | 2016-02-08 | 2016-05-05 | 61 | 0 | 61 | 2016-10-06 |  | -30403 |  |  | 2016-05-05 |  | 2015-10-23 |  | Standard |  |  |  | 0 |  |  | 2017-09-20 | 2017-09-26 | 2017-10-06 | Online
WMECO | Sandisfield | 6B641-2015 | 1255 | 21.91 | Solar | 19J4 | 2015-08-14 | 2015-09-24 | 29 | 27 | 2 | 2015-09-25 |  | -30147 | [9 empty] | 0 | [14 empty] | 2015-10-13 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B655-2015 | 1201 | 1.8 | Solar | 30B7 | 2015-08-14 | 2015-09-23 | 28 | 21 | 7 | 2015-09-23 | 2016-04-08 | 135 | 105 | 30 | [7 empty] | 0 | [12 empty] | 2016-04-11 |  | 09302015 |  | Expedited |  |  |  | 0 |  |  | 2017-05-16 | 2017-05-30 | 2017-05-30 | Online
WMECO | Hatfield | 6A1390-2015 | 1066 | 584 | Solar | 18G6 | 2015-08-20 | 2015-11-17 | 61 | 4 | 57 | 2015-11-18 | 2016-02-16 | 60 | 28 | 32 | [7 empty] | 0 |  |  | 2016-02-17 |  | -30243 | [9 empty] | 2015-05-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sandisfield | 6B651-2015 | 1255 | 16.4 | Solar | 19J4 | 2015-08-21 | 2015-10-27 | 46 | 41 | 5 | 2015-10-28 | 2015-11-04 | 6 | 0 | 6 | 2015-12-02 | 2015-12-03 | 2 | 0 | 2 |  |  | 0 | [12 empty] | 2015-12-04 |  | Sept 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-12-22 | 2015-12-24 | 2015-12-24 | Online
WMECO | Plainfield | 6F1072-2015 | 1070 | 1050 | Solar | 18K3 | 2015-08-24 | [16 empty] | 0 | [14 empty] | 2016-06-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S1476-2015 | 1077 | 18.4 | Solar | 29A5 | 2015-08-24 | 2015-10-02 | 29 | 12 | 17 | 2015-10-05 | 2016-03-24 | 116 | 95 | 21 | 2016-03-25 |  | -30269 |  |  |  |  | 0 | [14 empty] | 2015-10-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1481-2015 | 1030 | 17.25 | Solar | 16C17 | 2015-08-25 | 2015-10-22 | 41 | 30 | 11 | 2015-10-23 | 2015-10-28 | 4 | 0 | 4 | [7 empty] | 0 | [12 empty] | 2015-10-30 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-11 | 2015-12-14 | 2015-12-14 | Online
WMECO | West Hatfield | 6A1403-2015 | 1088 | 22.5 | Solar | 18G5 | 2015-08-28 | 2015-10-22 | 38 | 27 | 11 | 2015-10-22 | 2015-10-28 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2015-10-30 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-16 | 2015-12-16 | Online
WMECO | Dalton | 6B667-2015 | 1226 | 25 | Solar | 18C1 | 2015-09-02 | 2015-11-05 | 45 | 33 | 12 | 2015-11-06 | 2016-01-06 | 40 | 22 | 18 | 2016-01-07 | 2016-01-13 | 5 | 2 | 3 |  |  | 0 | [12 empty] | 2016-01-13 |  | 2015-09-25 |  | Expedited |  |  |  | 0 |  |  | 2016-06-27 | 2016-06-29 | 2016-06-29 | Online
WMECO | Easthampton | 6A1411-2015 | 1027 | 2100 | Solar | 15A5 | 2015-09-03 | [16 empty] | 0 | [14 empty] | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1520-2015 | 1030 | 5440 | Solar | 30A6 | 2015-09-03 | [16 empty] | 0 | [14 empty] | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B670-2015 | 1201 | 1380 | Solar | 30B7 | 2015-09-04 | 2015-09-17 | 9 | 2 | 7 | 2015-09-17 | 2015-10-20 | 23 | 22 | 1 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | July 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-04-17 | Online
WMECO | Springfield | 6S1550-2015 | 1109 | 1980 | Solar | 5J18 | 2015-09-04 | [16 empty] | 0 | [14 empty] | 2015-05-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1417-2015 | 1073 | 2000 | Solar | 15A1 | 2015-09-08 | 2015-11-09 | 44 | 35 | 9 | 2015-11-10 | 2016-02-05 | 59 | 14 | 45 | [7 empty] | 0 |  |  | 2016-02-05 | 2016-07-19 | 112 | 54 | 58 | 2016-07-20 | 2017-04-21 | 189 | 145 | 44 | 2017-04-28 |  | 2016-08-15 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-20 | Online
WMECO | Savoy | 6B673-2015 | 1256 | 2000 | Solar | 18C1 | 2015-09-08 | 2015-11-09 | 44 | 17 | 27 | 2015-11-10 | 2016-02-11 | 63 | 20 | 43 | [7 empty] | 0 |  |  | 2016-02-12 | 2016-07-15 | 105 | 50 | 55 | 2016-07-18 | 2017-04-20 | 190 | 145 | 45 | 2017-05-10 |  | 8/15/2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-12-19 | Online
WMECO | Hinsdale | 6B674-2015 | 1235 | 1000 | Solar | 18C2 | 2015-09-08 | 2015-11-16 | 48 | 27 | 21 | 2015-11-17 |  | -30182 | [9 empty] | 0 | [14 empty] | 8/15/2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1098-2015 | 1301 | 2000 | Solar | 21C1 | 2015-09-08 | 2015-11-13 | 47 | 36 | 11 | 2015-11-16 | 2016-01-07 | 36 | 22 | 14 | [7 empty] | 0 |  |  | 2016-01-08 | 2016-05-13 | 87 | 29 | 58 | 2016-10-31 |  | -30419 |  |  | 2017-05-22 |  | 2016-08-15 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-01-25 | Online
WMECO | Otis | 6B685-2015 | 1253 | 76.65 | Solar | 19J4 | 2015-09-14 | 2015-10-22 | 28 | 20 | 8 | 2015-10-23 | 2015-11-09 | 12 | 0 | 12 | [7 empty] | 0 | [14 empty] | 2015-10-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B689-2015 | 1235 | 2000 | Solar | 18C2 | 2015-09-15 | 2015-11-16 | 43 | 27 | 16 | 2015-11-17 | 2016-08-30 | 196 | 152 | 44 | [7 empty] | 0 |  |  | 2016-08-31 | 2017-03-08 | 128 | 40 | 88 | 2017-03-09 |  | -30506 |  |  | 2017-04-12 |  | 2016-08-15 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-19 | Online
WMECO | Springfield | 6S1577-2015 | 1119 | 16.7 | Solar | 20A12 | 2015-09-18 | 2015-11-20 | 44 | 18 | 26 | 2015-11-23 | 2015-12-21 | 20 | 17 | 3 | 2015-12-22 | 2016-01-14 | 16 | 0 | 16 |  |  | 0 | [12 empty] | 2016-01-25 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-04-21 | 2016-04-27 | 2016-04-27 | Online
WMECO | Springfield | 6S1588-2015 | 1107 | 5300 | Natural Gas | 21S8 | 2015-09-22 | 2015-12-01 | 48 | 10 | 38 | 2015-12-02 | 2016-02-22 | 55 | 18 | 37 | 2016-02-23 | 2016-04-27 | 45 | 11 | 34 |  |  | 0 | [12 empty] | 2016-04-29 |  | June 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-06 | Online
WMECO | Southampton | 6A1443-2015 | 1073 | 49.55 | Solar | 15A1 | 2015-09-23 | 2015-11-03 | 29 | 20 | 9 | 2015-11-04 | 2015-12-24 | 35 | 22 | 13 | 2015-12-28 | 2016-02-29 | 43 | 3 | 40 |  |  | 0 | [12 empty] | 2016-03-01 |  | 2015-10-12 |  | Expedited |  |  |  | 0 |  |  | 2016-09-09 | 2016-09-14 | 2016-09-14 | Online
WMECO | Lenox | 6B702-2015 | 1201 | 448 | Solar | 17G3 | 2015-09-23 | 2015-11-02 | 28 | 3 | 25 | 2015-11-03 | 2015-12-23 | 35 | 25 | 10 | [7 empty] | 0 |  |  | 2015-12-24 | 2016-02-11 | 33 | 4 | 29 | 2016-02-18 |  | -30244 |  |  | 2016-02-11 |  | 2016-03-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2017-04-12 | Online
WMECO | Southwick | 6S1590-2015 | 1077 | 500 | Solar | 29A5 | 2015-09-23 | 2015-12-01 | 47 | 7 | 40 | 2015-12-02 | 2016-03-18 | 73 | 42 | 31 | [7 empty] | 0 |  |  | 2016-03-21 | 2016-08-22 | 107 | 0 | 107 | [5 empty] | 2016-08-22 |  | 12/1/2015 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6F1134-2015 | 1354 | 1992 | Solar | 21B8 | 2015-09-24 | 2015-11-04 | 29 | 3 | 26 | 2015-11-05 | 2016-02-18 | 70 | 9 | 61 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-04-27 | 47 | 9 | 38 | 2016-05-06 |  | -30298 |  |  | 2016-04-27 |  | 2016-03-01 |  | Complex |  |  |  | 0 |  |  | 2017-12-29 | 2017-12-05 | 2018-01-18 | Online
WMECO | Greenfield | 6F1135-2015 | 1301 | 43.8 | Solar | 22B7 | 2015-09-25 | 2015-10-08 | 10 | 5 | 5 | 2015-10-09 | 2016-02-04 | 79 | 50 | 29 | 2016-02-04 | 2016-02-17 | 9 | 1 | 8 |  |  | 0 | [12 empty] | 2016-02-17 |  | Jan 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S1604-2015 | 1077 | 2000 | Solar | 29A5 | 2015-09-25 | 2015-12-04 | 48 | 26 | 22 | 2015-12-07 |  | -30195 | [9 empty] | 0 | [14 empty] | 8/15/2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S1610-2015 | 1089 | 112 | Solar | 21N5 | 2015-09-28 | 2015-12-17 | 56 | 49 | 7 | 2015-12-18 |  | -30204 | [9 empty] | 0 | [14 empty] | Nov 31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1149-2016 | 1070 | 499 | Solar | 18K3 | 2015-10-02 | 2015-10-22 | 14 | 5 | 9 | 2015-10-23 | 2015-11-05 | 10 |  | 10 | [7 empty] | 0 | [14 empty] | 2016-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1150-2015 | 1070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 56 | 33 | 23 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  |  |  | 2016-04-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1151-2015 | 1070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 56 | 33 | 23 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-12-22 |  | 2016-04-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-15 | Online
WMECO | Amherst | 6A1467-2015 | 1002 | 15.3 | Solar | 17K2 | 2015-10-06 | 2015-11-23 | 33 | 5 | 28 | 2015-11-24 | 2016-03-02 | 67 | 52 | 15 | 2016-03-03 |  | -30254 | 9 |  |  |  | 0 | [14 empty] | 2015-12-05 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A1468-2015 | 1038 | 900 | Solar | 18G5 | 2015-10-06 | 2016-01-13 | 67 | 24 | 43 | 2016-01-14 |  | -30221 | [9 empty] | 0 | [14 empty] | 2015-11-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1673-2015 | 1102 | 1000 | Diesel | 21S3 | 2015-10-09 | 2016-02-23 | 91 | 51 | 40 | 2016-02-24 | 2016-04-04 | 28 | 17 | 11 | 2016-04-05 | 2016-04-12 | 6 | 0 | 6 |  |  | 0 | [12 empty] | 2016-04-13 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1481-2015 | 1093 | 2000 | Solar | 18G8 | 2015-10-15 | 2015-12-11 | 40 | 5 | 35 | 2015-12-14 |  | -30200 | [9 empty] | 0 | [14 empty] | Summer 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1680-2015 | 1128 | 600 | Diesel | 20A34 | 2015-10-15 | 2016-01-20 | 65 | 11 | 54 | 2016-01-21 | 2016-04-14 | 59 | 49 | 10 | 2016-04-15 | 2016-09-08 | 100 | 10 | 90 |  |  | 0 | [12 empty] | 2016-09-09 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-25 | Online
WMECO | Agawam | 6S1687-2015 | 1001 | 999 | Solar | 30A3 | 2015-10-19 | 2015-12-07 | 34 | 2 | 32 | 2015-12-08 |  | -30196 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S1697-2015 | 1001 | 500 | Solar | 16C16 | 2015-10-21 | 2015-12-22 | 43 | 41 | 2 | 2015-12-23 | 2016-04-22 | 82 | 40 | 42 | [7 empty] | 0 |  |  | 2016-04-25 | 2016-08-15 | 78 | 0 | 78 | [7 empty] | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S1698-2015 | 1056 | 311 | Solar | 19S2 | 2015-10-21 | 2015-12-02 | 29 | 5 | 24 | 2015-12-03 | 2016-02-18 | 52 | 43 | 9 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | [5 empty] | 2016-05-11 |  | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S1699-2015 | 1001 | 500 | Solar | 16C16 | 2015-10-21 | 2016-01-20 | 61 | 1 | 60 | 2016-01-21 | 2016-04-22 | 64 | 40 | 24 | [7 empty] | 0 |  |  | 2016-04-25 | 2016-08-15 | 78 | 0 | 78 | [7 empty] | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S1797-2015 | 1056 | 16.7 | Solar | 19S1 | 2015-10-27 | [16 empty] | 0 | [14 empty] | 2015-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Buckland | 6F1201-2015 | 1338 | 16.7 | Solar | 38A1 | 2015-10-28 | 2015-11-30 | 22 | 18 | 4 | 2015-12-01 | 2015-12-15 | 11 | 5 | 6 | [7 empty] | 0 | [12 empty] | 2015-12-15 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-03-07 | 2016-03-09 | 2016-03-09 | Online
WMECO | Montague | 6F1203-2015 | 1351 | 408 | Solar | 21C3 | 2015-10-28 | 2016-01-27 | 61 | 3 | 58 | 2016-01-28 | 2016-06-10 | 93 | 35 | 58 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 |  | 51 | [7 empty] | June 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1730-2015 | 1108 | 299.16 | Solar | 22H17 | 2015-10-29 | 2016-03-08 | 88 | 28 | 60 | 2016-03-09 |  | -30258 | [9 empty] | 0 | [14 empty] | 2015-03-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1208-2015 | 1351 | 1992 | Solar | 21C3 | 2015-10-30 | 2016-01-27 | 59 | 1 | 58 | 2016-01-28 | 2016-06-10 | 93 | 35 | 58 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 | 0 | 51 | [7 empty] | June 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1209-2015 | 1351 | 4176 | Solar | 21C2 | 2015-10-30 | 2016-02-16 | 72 | 11 | 61 | 2016-02-17 | 2016-06-10 | 80 | 35 | 45 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 | 0 | 51 | 2016-11-08 |  | -30425 |  |  | 2016-09-23 |  | June 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-09-24 | Online
WMECO | Ashfield | 6F1210-2015 | 1330 | 45.6 | Solar | 38A1 | 2015-11-02 | 2015-11-19 | 13 | 7 | 6 | 2015-11-20 | 2016-01-19 | 39 | 17 | 22 | 2016-01-20 | 2016-01-29 | 8 | 0 | 8 |  |  | 0 | [12 empty] | 2016-02-03 |  | Nov 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-05-26 | 2016-05-27 | 2016-05-27 | Online
WMECO | Longmeadow | 6S1804-2015 | 1106 | 18 | Solar | 22H17 | 2015-11-03 | 2015-12-15 | 29 | 12 | 17 | 2015-12-15 | 2015-12-17 | 3 | 2 | 1 | [7 empty] | 0 | [12 empty] | 2015-12-17 |  | 2015-12-26 |  | Expedited |  |  |  | 0 |  |  | 2016-06-20 | 2016-06-27 | 2016-06-27 | Online
WMECO | Southwick | 6S1756-2015 | 1077 | 478 | Solar | 29A5 | 2015-11-06 | 2016-01-20 | 49 | 21 | 28 | 2016-01-20 | 2016-03-18 | 41 | 40 | 1 | [7 empty] | 0 |  |  | 2016-03-21 | 2016-08-22 | 107 | 0 | 107 | [5 empty] | 2016-08-22 |  | 2016-02-03 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Hatfield | 6A1528-2015 | 1088 | 292 | Solar | 18G5 | 2015-11-09 | 2015-12-22 | 30 | 12 | 18 | 2015-12-23 |  | -30207 | [9 empty] | 0 | [14 empty] | 2015-03-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1233-2015 | 1070 | 22.8 | Solar | 18K3 | 2015-11-10 | 2015-11-23 | 9 | 4 | 5 | 2015-11-24 | 2015-12-15 | 15 | 4 | 11 | [7 empty] | 0 | [12 empty] | 2015-12-15 |  | Nov 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-04-01 | 2016-04-05 | 2016-04-05 | Online
WMECO | Otis | 6B789-2015 | 1253 | 2000 | Solar | 19J4 | 2015-11-13 | 2016-02-02 | 54 | 7 | 47 | 2016-02-03 |  | -30234 | [9 empty] | 0 | [14 empty] | 2016-07-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1795-2015 | 1030 | 15.3 | Solar | 16C17 | 2015-11-13 | 2015-12-04 | 15 | 8 | 7 | 2015-12-07 | 2015-12-10 | 4 | 0 | 4 | [7 empty] | 0 | [12 empty] | 2016-01-08 |  | 2016-01-13 |  | Expedited |  |  |  | 0 |  |  | 2016-03-23 | 2016-04-11 | 2016-04-11 | Online
WMECO | South Deerfield | 6F1241-2015 | 1373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 20 | 1 | 19 | 2015-12-15 |  | -30201 | [9 empty] | 0 | [14 empty] | Spring 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6F1242-2015 | 1373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 20 | 1 | 19 | 2015-12-15 |  | -30201 | [9 empty] | 0 | [14 empty] | Spring 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1796-2015 | 1104 | 1985 | Solar | 5J18 | 2015-11-16 | 2015-12-21 | 25 | 1 | 24 | 2015-12-22 | 2016-02-23 | 42 | 17 | 25 | [7 empty] | 0 |  |  | 2016-02-24 | 2016-05-02 | 47 | 0 | 47 | 2016-05-12 |  | -30302 | 7 |  | 2016-05-02 |  | 2016-05-31 |  | Standard |  |  |  | 0 |  |  | 2017-06-19 | 2017-06-26 | 2017-06-26 | Online
WMECO | Hadley | 6A1553-2015 | 1035 | 570 | Biogas | 19B15 | 2015-11-20 | 2016-02-24 | 64 | 63 | 1 | 2016-02-25 | 2016-04-20 | 38 | 36 | 2 | [7 empty] | 0 |  |  | 2016-04-21 | 2016-07-11 | 55 | 45 | 10 | 2016-08-22 |  | -30371 |  |  | 2016-08-17 |  | 4/30/2016 |  | Standard |  |  |  | 0 |  |  | 2017-06-30 | 2017-07-13 | 2017-07-13 | Online
WMECO | Whately | 6A1560-2015 | 1093 | 504 | Solar | 18G8 | 2015-11-24 | 2015-12-16 | 16 | 3 | 13 | 2015-12-17 | 2016-04-28 | 90 | 51 | 39 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 |  | 86 | [7 empty] | March 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B807-2015 | 1201 | 72 | Solar | 19A7 | 2015-12-01 | 2016-01-06 | 25 | 5 | 20 | 2016-01-07 | 2016-02-10 | 24 | 11 | 13 | [7 empty] | 0 | [12 empty] | 2016-02-10 |  | 1st qtr 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-05-20 | 2016-05-24 | 2016-05-24 | Online
WMECO | Whately | 6A1570-2015 | 1093 | 2000 | Solar | 18G8 | 2015-12-02 | 2015-12-11 | 8 | 0 | 8 | 2015-12-14 | 2016-04-28 | 93 | 51 | 42 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 | 7 | 79 | 2016-10-31 |  | -30419 |  |  | 2016-10-03 |  | Sept 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-20 | Online
WMECO | Lee | 6B809-2015 | 1238 | 2000 | Solar | 16B5 | 2015-12-03 | 2016-02-11 | 48 | 9 | 39 | 2016-02-12 | 2016-04-04 | 35 | 12 | 23 | [7 empty] | 0 |  |  | 2016-04-05 | 2016-08-05 | 85 | 73 | 12 | [7 empty] | 2016-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6F1262-2015 | 1373 | 452 | Solar | 15E1 | 2015-12-04 | 2016-02-02 | 40 | 2 | 38 | 2016-02-03 |  | -30234 | [9 empty] | 0 | [14 empty] | 2016-03-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1578-2015 | 1027 | 496 | Solar | 15A2 | 2015-12-09 | 2016-01-28 | 34 | 25 | 9 | 2016-01-29 | 2016-06-03 | 87 | 49 | 38 | [7 empty] | 0 |  |  | 2016-06-06 | 2016-09-23 | 77 | 0 | 77 | [5 empty] | 2016-09-23 |  | June 2016 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Indian Orchard | 6S1915-2015 | 1151 | 1931.4 | Solar | 27A12 | 2015-12-15 | 2016-02-10 | 39 | 18 | 21 | 2016-02-11 | 2016-03-17 | 24 | 12 | 12 | [7 empty] | 0 |  |  | 2016-03-18 | 2016-08-08 | 98 | 17 | 81 | [5 empty] | 2016-08-12 |  | 2015-08-01 |  | Standard |  |  |  | 0 |  |  | 2017-02-10 | 2017-02-16 | 2017-02-16 | Online
WMECO | Hadley | 6A1588-2015 | 1035 | 1995.4 | Solar | 17K6 | 2015-12-16 | 2016-04-15 | 83 | 42 | 41 | 2016-04-19 | 2016-08-12 | 81 | 51 | 30 | [7 empty] | 0 |  |  | 2016-08-15 | 2016-12-01 | 75 | 0 | 75 | 2017-01-05 |  | -30463 |  |  | 2017-04-14 |  | Sept 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-01-16 | Online
WMECO | Hadley | 6A1589-2015 | 1035 | 1995.4 | Solar | 17K1 | 2015-12-16 | 2016-04-15 | 83 | 42 | 41 | 2016-04-19 | 2016-08-12 | 81 | 51 | 30 | [7 empty] | 0 |  |  | 2016-08-15 | 2017-01-27 | 113 | 24 | 89 | 2017-02-21 |  | -30494 |  |  | 2017-04-14 |  | Sept 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-01-16 | Online
WMECO | Amherst | 6A1599-2015 | 1002 | 19.3 | Solar | 17K8 | 2015-12-16 | 2016-01-21 | 24 | 13 | 11 | 2016-01-21 | 2016-02-08 | 13 | 9 | 4 | [7 empty] | 0 | [12 empty] | 2016-02-08 |  | 02/16/2016 |  | Expedited |  |  |  | 0 |  |  | 2016-11-30 | 2016-12-01 | 2016-12-01 | Online
WMECO | Hinsdale | 6B826-2015 | 1235 | 1988 | Solar | 18C2 | 2015-12-16 | 2016-02-23 | 46 | 16 | 30 | 2016-02-24 | 2016-06-10 | 75 | 37 | 38 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-10 | 41 | 0 | 41 | 2016-09-09 |  | -30384 |  |  | 2016-08-19 |  | 2015-09-01 |  | Standard |  |  |  | 0 |  |  | 2017-11-17 | 2017-11-20 | 2017-11-21 | Online
WMECO | Amherst | 6A1600-2015 | 1006 | 16.7 | Solar | 18G7 | 2015-12-18 | 2016-01-07 | 13 | 8 | 5 | 2016-01-08 | 2016-02-10 | 23 | 21 | 2 | 2016-02-11 | 2016-02-28 | 11 | 0 | 11 |  |  | 0 | [12 empty] | 2016-02-29 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1953-2015 | 1030 | 16.4 | Solar | 16C17 | 2015-12-23 | 2016-01-06 | 9 | 1 | 8 | 2016-01-06 | 2016-01-06 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-02-01 |  | 2016-02-16 |  | Expedited |  |  |  | 0 |  |  | 2016-08-15 | 2016-08-23 | 2016-08-23 | Online
WMECO | Middlefield | 6F1294-2015 | 1243 | 32.85 | Solar | 18C2 | 2015-12-24 | 2016-01-19 | 16 | 7 | 9 | 2016-01-19 | 2016-07-15 | 123 | 98 | 25 | [7 empty] | 0 | [12 empty] | 2016-07-15 |  | 2015-12-31 |  | Expedited |  |  |  | 0 |  |  | 2016-09-07 | 2016-09-13 | 2016-09-13 | Online
WMECO | Amherst | 6A1612-2015 | 1003 | 154 | Solar | 18G2 | 2015-12-28 | 2016-01-12 | 11 | 6 | 5 | 2016-01-13 | 2016-03-02 | 34 | 33 | 1 | 2016-03-03 | 2016-04-21 | 34 | 2 | 32 |  |  | 0 | [12 empty] | 2016-04-22 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1979-2015 | 1129 | 343 | Solar | 20A23 | 2015-12-28 | 2016-01-28 | 22 | 20 | 2 | 2016-01-29 |  | -30231 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1978-2015 | 1030 | 20.925 | Solar | 16C17 | 2015-12-29 | 2016-01-20 | 15 | 9 | 6 | 2016-01-21 | 2016-02-17 | 19 | 17 | 2 | 2016-02-18 |  | -30244 |  |  |  |  | 0 | [16 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B851-2016 | 1201 | 1000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Hancock | 6B852-2016 | 1237 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Hancock | 6B853-2016 | 1201 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Southwick | 6S1998-2016 | 1077 | 16.7 | Solar | 29A5 | 2016-01-05 | 2016-01-08 | 4 | 2 | 2 | 2016-01-08 |  | -30217 | [9 empty] | 0 | [14 empty] | 2016-03-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1621-2016 | 1002 | 17 | Solar | 19B16 | 2016-01-07 | 2016-01-22 | 11 | 6 | 5 | 2016-01-23 | 2016-02-09 | 12 | 0 | 12 | [7 empty] | 0 | [12 empty] | 2016-02-10 |  | 2016-05-01 |  | Expedited |  |  |  | 0 |  |  | 2016-06-23 | 2016-06-27 | 2016-06-27 | Online
WMECO | Amherst | 6A1622-2016 | 1002 | 27 | Solar | 17K5 | 2016-01-07 | 2016-03-02 | 38 | 19 | 19 | 2016-03-02 | 2016-06-13 | 71 | 63 | 8 | [7 empty] | 0 | [12 empty] | 2016-06-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-09-08 | 2016-09-21 | 2016-09-21 | Online
WMECO | West Springfield | 6S2018-2016 | 1089 | 24 | Solar | 21N9 | 2016-01-08 | 2016-01-14 | 5 | 1 | 4 | 2016-01-14 | 2016-04-04 | 55 | 54 | 1 | 2016-04-05 | 2016-07-19 | 72 | 0 | 72 |  |  | 0 | [12 empty] | 2016-08-04 |  | 2016-03-07 |  | Expedited |  |  |  | 0 |  |  | 2017-01-04 | 2017-01-06 | 2017-01-06 | Online
WMECO | Whately | 6A1625-2016 | 1093 | 16.7 | Solar | 18G8 | 2016-01-12 | 2016-01-20 | 6 | 1 | 5 | 2016-01-20 | 2016-02-09 | 15 | 9 | 6 | [7 empty] | 0 | [12 empty] | 2016-02-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B864-2016 | 1226 | 495.28 | Solar | 19A3 | 2016-01-12 | 2016-07-01 | 118 | 92 | 26 | 2016-07-05 |  | -30337 | [9 empty] | 0 | [14 empty] | 2016-09-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2043-2016 | 1109 | 16.7 | Solar | 20A32 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-29 | 14 | 10 | 4 | [7 empty] | 0 | [12 empty] | 2016-03-18 |  | 2016-02-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2044-2016 | 1118 | 14.35 | Solar | 20A32 | 2016-01-19 | [16 empty] | 0 | [14 empty] | 2016-02-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S2053-2016 | 1106 | 16.7 | Solar | 22H12 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-17 | 6 | 5 | 1 | [7 empty] | 0 | [12 empty] | 2016-02-19 |  | 2016-02-04 |  | Expedited |  |  |  | 0 |  |  | 2016-04-21 | 2016-04-25 | 2016-04-25 | Online
WMECO | Amherst | 6A1637-2016 | 1002 | 99 | Solar | 19B15 | 2016-01-20 | 2016-01-27 | 6 | 4 | 2 | 2016-01-28 | 2016-02-23 | 18 | 0 | 18 | [7 empty] | 0 | [12 empty] | 2016-02-23 |  | Feb 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-06-15 | 2016-06-16 | 2016-06-16 | Online
WMECO | Agawam | 6S2068-2016 | 1001 | 45 | Solar | 16C16 | 2016-01-22 | 2016-02-11 | 15 | 9 | 6 | 2016-02-11 | 2016-02-18 | 5 | 3 | 2 | [7 empty] | 0 | [12 empty] | 2016-02-22 |  | 2016-03-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2016-09-20 | Online
WMECO | Whately | 6A1647-2016 | 1093 | 1992 | Solar | 18G8 | 2016-01-27 | 2016-02-04 | 7 | 1 | 6 | 2016-02-05 |  | -30236 | [9 empty] | 0 | [14 empty] | Summer 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1652-2016 | 1093 | 1548 | Solar | 18G8 | 2016-01-29 | [16 empty] | 0 | [14 empty] | Summer 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2094-2016 | 1104 | 140 | Solar | 5J11 | 2016-02-02 | 2017-02-13 | 257 | 223 | 34 | 2017-02-14 |  | -30490 | [9 empty] | 0 | [14 empty] | 3/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2095-2016 | 1001 | 250 | Solar | 30A6 | 2016-02-02 | 2016-09-08 | 151 | 149 | 2 | 2016-09-09 | 2017-01-27 | 95 | 88 | 7 | 2017-01-30 | 2017-03-01 | 22 | 0 | 22 |  |  | 0 | [14 empty] | 3/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B887-2016 | 1201 | 625.8 | Solar | 30B7 | 2016-02-03 | 2016-03-08 | 24 | 9 | 15 | 2016-03-09 | 2016-05-16 | 47 | 13 | 34 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-16 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  | 2017-11-28 | 2017-12-01 | 2017-12-18 | Online
WMECO | Westhampton | 6A1661-2016 | 1027 | 566.1 | Solar | 15A3 | 2016-02-04 | 2016-04-05 | 42 | 21 | 21 | 2016-04-06 | 2016-07-22 | 74 | 71 | 3 | [7 empty] | 0 |  |  | 2016-07-25 | 2016-10-07 | 54 |  | 54 | [7 empty] | 2016-04-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1662-2016 | 1093 | 8.35 | Solar | 18G6 | 2016-02-04 | 2016-04-11 | 46 | 44 | 2 | 2016-04-11 | 2016-05-04 | 17 | 16 | 1 | 2016-05-05 |  | -30297 |  |  |  |  | 0 | [14 empty] | 2016-04-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B896-2016 | 1201 | 390 | Solar | 19A7 | 2016-02-10 | 2016-05-03 | 57 | 23 | 34 | 2016-05-04 |  | -30296 | [9 empty] | 0 | [14 empty] | not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1697-2015 | 1002 | 22.7 | Solar | 18G7 | 2016-02-22 | 2016-03-10 | 14 | 10 | 4 | 2016-03-10 |  | -30259 | [9 empty] | 0 | [14 empty] | 2016-03-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1704-2016 | 1375 | 288 | Solar | 18G3 | 2016-02-23 | 2016-05-04 | 50 | 44 | 6 | 2016-05-05 |  | -30297 | [9 empty] | 0 | [14 empty] | 2016-05-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1708-2016 | 1375 | 22.5 | Solar | 18G8 | 2016-02-23 | 2016-04-13 | 36 | 6 | 30 | 2016-04-13 | 2016-04-14 | 2 | 1 | 1 | [7 empty] | 0 | [12 empty] | 2016-04-15 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-06-08 | 2016-06-09 | 2016-06-09 | Online
WMECO | South Deerfield | 6F1389-2016 | 1373 | 1000 | Biogas | 22B1 | 2016-02-25 | 2016-04-13 | 34 | 12 | 22 | 2016-04-14 | 2016-07-01 | 54 | 20 | 34 | [7 empty] | 0 |  |  | 2016-07-05 | 2016-10-06 | 67 | 0 | 67 | 2016-10-19 |  | -30411 |  |  | 2016-10-12 |  | 6/20/16 |  | Complex |  |  |  | 0 |  |  | 2017-12-06 | 2017-12-11 | 2017-12-11 | Online
WMECO | Otis | 6B923-2016 | 1253 | 40.75 | Solar | 19J4 | 2016-03-01 | [16 empty] | 0 | [14 empty] | 2016-05-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1736-2016 | 1035 | 16.4 | Solar | 18G4 | 2016-03-03 | 2016-03-10 | 6 | 2 | 4 | 2016-03-10 |  | -30259 | [9 empty] | 0 | [14 empty] | 2016-05-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Buckland | 6F1417-2016 | 1338 | 25.425 | Solar | 38A1 | 2016-03-04 | 2016-06-27 | 78 | 74 | 4 | 2016-06-27 |  | -30332 | [9 empty] | 0 | [14 empty] | 2016-04-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2185-2016 | 1001 | 22.95 | Solar | 16C17 | 2016-03-04 | 2016-03-21 | 11 | 3 | 8 | 2016-03-21 | 2016-03-28 | 6 | 5 | 1 | 2016-03-29 |  | -30271 |  |  |  |  | 0 | [14 empty] | 2016-04-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1743-2016 | 1002 | 19.75 | Solar | 18G4 | 2016-03-07 | 2016-03-14 | 6 | 5 | 1 | 2016-03-15 |  | -30262 | 15 | [8 empty] | 0 | [14 empty] | Q2 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2199-2016 | 1001 | 22.95 | Solar | 16C17 | 2016-03-08 | [16 empty] | 0 | [14 empty] | 2016-04-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1754-2016 | 1027 | 180 | Solar | 15A2 | 2016-03-09 | 2016-04-15 | 27 | 0 | 27 | 2016-04-19 | 2016-06-03 | 33 | 25 | 8 | [7 empty] | 0 |  |  | 2016-06-06 | 2016-09-23 | 77 | 0 | 77 | [5 empty] | 2016-09-23 |  | 5/2016 |  | Standard |  |  |  | 0 |  |  | 2017-03-28 | 2017-04-04 | 2017-04-04 | Online
WMECO | Amherst | 6A1755-2016 | 1002 | 60 | Solar | 17K4 | 2016-03-09 | 2016-04-06 | 20 | 11 | 9 | 2016-04-06 | 2016-04-12 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2016-04-13 |  | May 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-10-04 | 2016-10-06 | 2016-10-06 | Online
WMECO | Hadley | 6A1766-2016 | 1035 | 84 | Solar | 18G5 | 2016-03-11 | 2016-03-21 | 6 | 0 | 6 | 2016-03-21 | 2016-06-20 | 63 | 62 | 1 | 2016-06-21 | 2016-07-18 | 19 | 0 | 19 |  |  | 0 | [12 empty] | 2016-07-19 |  | 3/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-03-21 | 2017-03-22 | 2017-03-22 | Online
WMECO | Southampton | 6A1767-2016 | 1073 | 23.45 | Solar | 15A1 | 2016-03-11 | 2016-04-11 | 21 | 17 | 4 | 2016-04-11 |  | -30280 | [9 empty] | 0 | [14 empty] | 5/10/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F1439-2016 | 1342 | 75 | Solar | 22B3 | 2016-03-11 | 2016-08-10 | 104 | 90 | 14 | 2016-08-10 | 2016-11-30 | 77 | 68 | 9 | [7 empty] | 0 | [12 empty] | 2016-12-05 |  | 5/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-12-12 | 2017-12-13 | 2018-04-23 | Online
WMECO | Turners Falls | 6F1440-2016 | 1376 | 19.3 | Solar | 21C6 | 2016-03-14 | 2016-03-25 | 9 | 8 | 1 | 2016-03-25 | 2016-03-31 | 5 | 4 | 1 | [7 empty] | 0 | [12 empty] | 2016-03-31 |  | 2015-11-09 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hancock | 6B939-2016 | 1237 | 42.25 | Solar | 30B7 | 2016-03-17 | [16 empty] | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F1449-2016 | 1342 | 64 | Solar | 22B3 | 2016-03-17 | 2016-06-27 | 69 | 56 | 13 | 2016-06-28 | 2016-08-11 | 32 | 26 | 6 | [7 empty] | 0 | [12 empty] | 2016-08-11 |  | 6/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-09-22 | 2017-10-04 | 2018-04-25 | Online
WMECO | Springfield | 6S2233-2016 | 1105 | 16.95 | Solar | 21S11 | 2016-03-17 | 2016-07-26 | 89 | 80 | 9 | 2016-07-26 | 2016-09-16 | 38 | 37 | 1 | 2016-09-19 |  | -30390 |  |  |  |  | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cheshire | 6B947-2016 | 1225 | 16.7 | Solar | 19A5 | 2016-03-18 | 2016-03-30 | 9 | 7 | 2 | 2016-03-30 |  | -30272 | [9 empty] | 0 | [14 empty] | 2016-04-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2236-2016 | 1077 | 21.9 | Solar | 29A5 | 2016-03-22 | 2016-04-07 | 13 | 12 | 1 | 2016-04-07 | 2016-04-28 | 15 | 14 | 1 | 2016-04-29 | 2016-05-20 | 16 | 0 | 16 |  |  | 0 | [12 empty] | 2016-05-26 |  | 2016-06-17 |  | Expedited |  |  |  | 0 |  |  | 2017-03-06 | 2017-03-09 | 2017-03-09 | Online
WMECO | Springfield | 6S2248-2016 | 1109 | 72 | Solar | 5J15 | 2016-03-24 | 2016-04-05 | 9 | 7 | 2 | 2016-04-05 | 2016-05-30 | 38 | 30 | 8 | [7 empty] | 0 | [12 empty] | 2016-06-01 |  | July 2015 |  | Expedited |  |  |  | 0 |  |  | 2017-03-31 | 2017-04-05 | 2017-04-05 | Online
WMECO | West Springfield | 6S2264-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-03-29 | 2016-04-07 | 8 | 7 | 1 | 2016-04-07 |  | -30278 | [9 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B960-2016 | 1201 | 21.9 | Solar | 15E2 | 2016-04-05 | 2016-05-03 | 20 | 18 | 2 | 2016-05-03 | 2016-07-12 | 48 | 39 | 9 | 2016-07-13 |  | -30343 |  |  |  |  | 0 | [14 empty] | 2016-04-23 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B973-2016 | 1237 | 16.4 | Solar | 15E1 | 2016-04-11 | 2016-04-19 | 6 | 5 | 1 | 2016-04-19 | 2016-05-09 | 15 | 14 | 1 | 2016-05-10 | 2016-05-10 | 1 | 0 | 1 |  |  | 0 | [12 empty] | 2016-05-16 |  | 2016-05-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2294-2016 | 1001 | 45.9 | Solar | 16C17 | 2016-04-11 | 2016-05-03 | 16 | 13 | 3 | 2016-05-03 | 2016-05-11 | 7 | 6 | 1 | 2016-05-12 | 2016-05-18 | 5 | 0 | 5 |  |  | 0 | [12 empty] | 2016-05-27 |  | 2016-05-28 |  | Expedited |  |  |  | 0 |  |  |  |  | 2016-07-27 | Online
WMECO | Agawam | 6S2295-2016 | 1001 | 46.8 | Solar | 16C18 | 2016-04-11 | 2016-05-03 | 16 | 14 | 2 | 2016-05-03 | 2016-05-03 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-05-05 |  | 2016-05-28 |  | Expedited |  |  |  | 0 |  |  | 2016-08-09 | 2016-08-11 | 2016-08-11 | Online
WMECO | Montague | 6F1484-2016 | 1351 | 18 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 9 | 8 | 1 | 2016-04-25 |  | -30289 | [9 empty] | 0 | [14 empty] | July 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1485-2016 | 1351 | 56.35 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 9 | 8 | 1 | 2016-04-25 | 2016-05-20 | 20 | 18 | 2 | [7 empty] | 0 | [12 empty] | 2016-05-26 |  | July 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-01-18 | 2017-01-26 | 2017-01-26 | Online
WMECO | Southwick | 6S2301-2016 | 1077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 34 | 23 | 11 | 2016-06-02 | 2017-05-03 | 229 | 217 | 12 | [7 empty] | 0 |  |  | 2017-05-04 | 2017-09-19 | 96 | 15 | 81 | 2017-10-28 |  | -30667 |  |  | 2017-10-05 |  | Spring 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-12-20 | Online
WMECO | Southwick | 6S2303-2016 | 1077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 34 | 23 | 11 | 2016-06-02 | 2017-05-03 | 229 | 217 | 12 | [7 empty] | 0 |  |  | 2017-05-04 | 2017-09-19 | 96 | 15 | 81 | 2017-10-28 |  | -30667 |  |  | 2017-10-05 |  | Spring 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-20 | Online
WMECO | West Springfield | 6S2305-2016 | 1089 | 12 | Solar | 21N6 | 2016-04-14 | 2016-04-20 | 4 | 3 | 1 | 2016-04-20 |  | -30286 | [9 empty] | 0 | [14 empty] | 2016-08-07 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2314-2016 | 1056 | 16.7 | Solar | 19S3 | 2016-04-18 | 2016-05-09 | 15 | 14 | 1 | 2016-05-09 |  | -30299 | [9 empty] | 0 | [14 empty] | 2016-06-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2347-2016 | 1056 | 12 | Solar | 19S1 | 2016-04-28 | [16 empty] | 0 | [14 empty] | 2016-05-25 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B996-2016 | 1201 | 1476 | Solar | 30B7 | 2016-05-02 | 2016-05-24 | 17 | 6 | 11 | 2016-05-25 |  | -30311 | [9 empty] | 0 | [14 empty] | 2016-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2367-2016 | 1077 | 16.7 | Solar | 29A5 | 2016-05-04 | 2016-05-16 | 9 | 8 | 1 | 2016-05-16 | 2016-06-15 | 22 | 21 | 1 | 2016-06-16 | 2016-06-22 | 4 | 0 | 4 |  |  | 0 | [12 empty] | 2016-06-23 |  | 2016-03-04 |  | Expedited |  |  |  | 0 |  |  | 2016-11-08 | 2016-11-14 | 2016-11-14 | Online
WMECO | Springfield | 6S2368-2016 | 1119 | 152 | Solar | 27A7 | 2016-05-04 | 2016-05-16 | 9 | 1 | 8 | 2016-05-17 | 2016-07-07 | 35 | 18 | 17 | 2016-07-08 | 2016-08-02 | 18 | 0 | 18 |  |  | 0 | [12 empty] | 2016-08-09 |  | Aug 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-02-07 | 2017-02-10 | 2017-02-10 | Online
WMECO | Hancock | 6B1002-2016 | 1237 | 42.25 | Solar | 30B7 | 2016-05-05 | 2016-09-15 | 92 | 77 | 15 | 2016-09-15 |  | #VALUE! | 42 | #VALUE! | [7 empty] | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1014-2016 | 1226 | 16.15 | Solar | 18C1 | 2016-05-10 | 2016-05-19 | 8 | 3 | 5 | 2016-05-19 | 2016-06-09 | 15 | 14 | 1 | 2016-06-10 | 2016-07-13 | 22 | 0 | 22 |  |  | 0 | [12 empty] | 2016-07-14 |  | 2016-07-03 |  | Expedited |  |  |  | 0 |  |  | 2016-12-07 | 2016-12-13 | 2016-12-13 | Online
WMECO | Montague | 6F1500-2016 | 1351 | 36 | Solar | 21C7 | 2016-05-10 | 2016-06-15 | 26 | 22 | 4 | 2016-06-15 | 2016-07-11 | 17 | 16 | 1 | 2016-07-12 | 2016-09-26 | 54 | 17 | 37 |  |  | 0 | [12 empty] | 2016-09-29 |  | 2016-08-01 |  | Expedited |  |  |  | 0 |  |  | 2017-06-09 | 2017-06-21 | 2017-11-10 | Online
WMECO | Plainfield | 6F1513-2016 | 1070 | 17.5 | Solar | 18K3 | 2016-05-25 | [16 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1034-2016 | 1238 | 36 | Solar | 16B5 | 2016-05-26 | 2016-08-05 | 49 | 48 | 1 | 2016-08-05 | 2016-08-29 | 17 | 7 | 10 | [7 empty] | 0 | [12 empty] | 2016-08-30 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2017-01-17 | 2017-01-19 | 2017-01-20 | Online
WMECO | Turners Falls | 6F1515-2016 | 1376 | 1160 | Solar | 21C8 | 2016-05-27 | 2016-06-28 | 21 | 15 | 6 | 2016-06-29 | 2016-07-22 | 17 | 6 | 11 | [7 empty] | 0 |  |  | 2016-07-25 | 2016-10-06 | 53 | 0 | 53 | [7 empty] | 2016-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2463-2016 | 1077 | 15.75 | Solar | 29A5 | 2016-05-31 | 2016-06-23 | 17 | 14 | 3 | 2016-06-23 | 2016-07-07 | 10 | 9 | 1 | [7 empty] | 0 | [12 empty] | 2016-07-14 |  | 2016-06-15 |  | Expedited |  |  |  | 0 |  |  | 2016-11-28 | 2016-11-29 | 2016-11-29 | Online
WMECO | Pittsfield | 6B1040-2016 | 1201 | 60 | Solar | 30B7 | 2016-06-01 | 2016-07-20 | 34 | 32 | 2 | 2016-07-20 | 2016-11-02 | 74 | 48 | 26 | [7 empty] | 0 | [12 empty] | 2016-11-02 |  | Sept 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-04-04 | 2017-04-06 | 2017-04-06 | Online
WMECO | Pittsfield | 6B1047-2016 | 1201 | 166.5 | Solar | 30B3 | 2016-06-08 | 2016-06-30 | 16 | 14 | 2 | 2016-06-30 | 2016-07-19 | 13 | 12 | 1 | 2016-07-19 | 2018-07-13 | 496 | 236 | 260 |  |  | 0 | [12 empty] | 2018-07-17 |  | Oct 2016 |  | Standard |  |  |  | 0 |  |  | 2018-08-30 | 2018-08-31 | 2018-09-04 | Online
WMECO | Amherst | 6A1948-2016 | 1002 | 86.995 | Solar | 18G4 | 2016-06-10 | 2016-06-21 | 7 | 5 | 2 | 2016-06-21 |  | -30328 | [9 empty] | 0 | [14 empty] | Sept 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1052-2016 | 1238 | 3328 | Natural Gas | 16B3 | 2016-06-10 | 2016-07-12 | 21 | 6 | 15 | 2016-07-13 | 2016-09-21 | 50 | 37 | 13 | [7 empty] | 0 |  |  | 2016-09-22 | 2017-03-13 | 116 | 78 | 38 | [7 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1053-2016 | 1201 | 460 | Solar | 19A5 | 2016-06-10 | 2017-01-11 | 146 | 137 | 9 | 2017-01-12 | 2017-03-10 | 40 | 38 | 2 | [7 empty] | 0 |  |  | 2017-03-13 | 2017-05-18 | 48 | 0 | 48 | [7 empty] | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1949-2016 | 1073 | 18 | Solar | 15A1 | 2016-06-13 | 2016-07-12 | 20 | 15 | 5 | 2016-07-13 | 2016-09-06 | 39 | 37 | 2 | [7 empty] | 0 | [12 empty] | 2016-09-13 |  | 8/12 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A1953-2016 | 1002 | 19.3 | Solar | 17K2 | 2016-06-15 | 2016-07-28 | 30 | 26 | 4 | 2016-07-28 | 2016-08-23 | 19 | 18 | 1 | [7 empty] | 0 | [12 empty] | 2016-08-29 |  | 2016-08-14 |  | Expedited |  |  |  | 0 |  |  | 2017-03-02 | 2017-03-07 | 2017-03-07 | Online
WMECO | West Springfield | 6S2516-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-06-22 | 2016-07-18 | 18 | 12 | 6 | 2016-07-18 | 2016-09-02 | 35 | 34 | 1 | 2016-09-06 |  | -30381 |  |  |  |  | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1971-2016 | 1073 | 21.9 | Solar | 15A1 | 2016-06-23 | 2016-06-29 | 5 | 2 | 3 | 2016-06-29 | 2016-07-19 | 14 | 13 | 1 | 2016-07-20 |  | -30348 | 2 |  |  |  | 0 | [14 empty] | 2016-07-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S2539-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-06-29 | [16 empty] | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2573-2016 | 1056 | 396 | Solar | 27A5 | 2016-07-11 | 2016-08-09 | 22 | 19 | 3 | 2016-08-12 |  | -30365 | [9 empty] | 0 | [14 empty] | 2016-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A2007-2016 | 1073 | 23.4 | Solar | 15A1 | 2016-07-26 | [16 empty] | 0 | [14 empty] | 2016-05-26 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1113-2016 | 1253 | 67.6 | Solar | 19J4 | 2016-07-26 | 2016-09-23 | 43 | 38 | 5 | 2016-09-26 | 2016-10-07 | 10 | 8 | 2 | 2016-10-11 |  | -30405 |  |  |  |  | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1127-2016 | 1201 | 1476 | Solar | 30B7 | 2016-08-04 | 2016-08-31 | 20 | 15 | 5 | 2016-09-01 |  | -30379 | [9 empty] | 0 | [14 empty] | 2016-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6F1588-2016 | 1337 | 42 | Solar | 21C1 | 2016-08-08 | 2016-08-15 | 6 | 5 | 1 | 2016-08-15 |  | -30366 | [9 empty] | 0 | [14 empty] | Nov 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1590-2016 | 1301 | 50 | Solar | 21C1 | 2016-08-08 | [16 empty] | 0 | [14 empty] | August |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A2032-2016 | 1035 | 25 | Solar | 18G6 | 2016-08-12 | 2016-09-13 | 22 | 12 | 10 | 2016-08-31 |  | -30378 | [9 empty] | 0 | [14 empty] | 2016-10-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1134-2016 | 1201 | 16.75 | Solar | 19A1 | 2016-08-12 | 2016-09-27 | 32 | 13 | 19 | 2016-09-28 | 2016-09-28 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-09-29 |  | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2045-2016 | 1002 | 86.995 | Solar | 18G4 | 2016-08-17 | 2016-09-27 | 29 | 18 | 11 | 2016-09-28 | 2016-11-03 | 26 | 11 | 15 | [7 empty] | 0 | [12 empty] | 2016-11-03 |  | Sept 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-03-15 | 2017-03-21 | 2017-03-21 | Online
WMECO | Pittsfield | 6B1139-2016 | 1201 | 240 | Solar | 19A7 | 2016-08-17 | 2016-09-01 | 12 | 10 | 2 | 2016-09-02 |  | -30380 | 44 | [8 empty] | 0 | [14 empty] | 2016-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2702-2016 | 1104 | 420 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 19 | 14 | 5 | 2016-09-15 |  | -30388 | [9 empty] | 0 | [14 empty] | 2016-12-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2703-2016 | 1104 | 300 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 19 | 14 | 5 | 2016-09-15 |  | -30388 | [9 empty] | 0 | [14 empty] | 2016-12-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2720-2016 | 1104 | 796 | Solar | 5J13 | 2016-08-23 | 2016-09-13 | 15 | 9 | 6 | 2016-09-14 | 2016-11-29 | 52 | 32 | 20 | [7 empty] | 0 |  |  | 2016-11-30 | 2017-01-27 | 40 | 0 | 40 | 2017-03-30 |  | -30521 |  |  | 2017-03-21 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A2060-2016 | 1027 | 16.7 | Solar | 15A3 | 2016-08-24 | [16 empty] | 0 | [14 empty] | 2016-10-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2770-2016 | 1056 | 16.7 | Solar | 19S3 | 2016-09-13 | 2016-10-24 | 29 | 19 | 10 | 2016-10-24 |  | -30414 | [9 empty] | 0 | [14 empty] | 2016-06-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A2086-2016 | 1035 | 399.6 | Solar | 18G5 | 2016-09-14 | 2016-09-27 | 10 | 5 | 5 | 2016-09-28 | 2016-11-10 | 31 | 19 | 12 | [7 empty] | 0 |  |  | 2016-11-14 | 2017-04-19 | 107 | 56 | 51 | 2017-04-20 | 2017-08-10 | 79 | 21 | 58 | 2017-08-23 |  | Nov 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-06-20 | Online
WMECO | Worthington | 6F1646-2016 | 1098 | 13.5 | Solar | 18K3 | 2016-09-15 | [16 empty] | 0 | [14 empty] | 2016-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Middlefield | 6F1675-2016 | 1243 | 41.5 | Solar | 18C2 | 2016-10-03 | 2016-10-17 | 10 | 8 | 2 | 2016-10-17 | 2016-11-07 | 16 | 0 | 16 | [7 empty] | 0 | [12 empty] | 2016-11-07 |  | 2016-12-01 |  | Expedited |  |  |  | 0 |  |  | 2017-06-01 | 2017-06-05 | 2017-06-06 | Online
WMECO | Northfield | 6F1684-2016 | 1360 | 21.9 | Solar | 21B8 | 2016-10-06 | 2016-11-23 | 33 | 32 | 1 | 2016-11-25 |  | -30436 | [9 empty] | 0 | [14 empty] | 2017-01-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6F1694-2016 | 1098 | 13.5 | Solar | 18K3 | 2016-10-11 | [16 empty] | 0 | [14 empty] | 2016-12-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2863-2016 | 1109 | 16.7 | Solar | 20A32 | 2016-10-11 | 2016-12-05 | 38 | 33 | 5 | 2016-12-05 | 2016-12-12 | 6 | 1 | 5 | [7 empty] | 0 | [12 empty] | 2016-12-12 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-02-21 | Online
WMECO | Greenfield | 6F1707-2016 | 1301 | 1200 | Solar | 21C1 | 2016-10-18 | 2016-10-31 | 10 | 7 | 3 | 2016-11-01 | 2016-11-17 | 12 | 10 | 2 | [7 empty] | 0 |  |  | 2016-11-18 | 2017-01-27 | 47 | 0 | 47 | 2017-02-21 |  | -30494 |  |  | 2017-03-10 |  | 2017-09-21 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-12-23 | Online
WMECO | Pittsfield | 6B1240-2016 | 1201 | 1320 | Solar | 15E3 | 2016-10-25 | 2016-11-23 | 21 | 9 | 12 | 2016-11-25 |  | -30436 | [9 empty] | 0 | [14 empty] | May 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2924-2016 | 1104 | 37.8 | Solar | 5J15 | 2016-10-26 | 2016-11-01 | 5 | 3 | 2 | 2016-11-01 | 2016-12-07 | 25 | 18 | 7 | [7 empty] | 0 | [12 empty] | 2016-12-07 |  | 2016-12-05 |  | Expedited |  |  |  | 0 |  |  | 2017-05-24 | 2017-05-26 | 2017-05-26 | Online
WMECO | Amherst | 6A2150-2016 | 1002 | 19.8 | Solar | 18G4 | 2016-10-27 | [16 empty] | 0 | [14 empty] | 11/30/2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2929-2016 | 1104 | 252 | Solar | 21S6 | 2016-10-27 | 2016-11-08 | 9 | 6 | 3 | 2016-11-09 | 2016-12-05 | 17 | 15 | 2 | 2016-12-06 | 2016-12-29 | 17 | 6 | 11 |  |  | 0 | [12 empty] | 2017-03-15 |  | May 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-11-15 | 2017-12-07 | 2017-12-07 | Online
WMECO | Dalton | 6B1258-2016 | 1226 | 27.5 | Solar | 18C1 | 2016-11-03 | 2016-12-13 | 27 | 25 | 2 | 2016-12-13 | 2017-01-20 | 26 | 3 | 23 | [7 empty] | 0 | [12 empty] | 2017-01-24 |  | Q4 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-09-22 | 2016-09-27 | 2017-09-27 | Online
WMECO | Springfield | 6S2985-2016 | 1118 | 149.9 | Solar | 20A22 | 2016-11-14 | 2016-12-01 | 13 | 10 | 3 | 2016-12-01 | 2016-12-07 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2016-12-07 |  | 1/4/2017 |  | Expedited |  |  |  | 0 |  |  | 2018-01-08 | 2018-01-11 | 2018-01-11 | Online
WMECO | Becket | 6B1277-2016 | 1223 | 4950 | Solar | 19J6 | 2016-11-15 | 2016-12-19 | 24 | 21 | 3 | 2016-12-19 |  | -30452 | [9 empty] | 0 | [14 empty] | 2017-10-18 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B1278-2016 | 1223 | 4950 | Solar | 16B1 | 2016-11-15 | 2016-12-01 | 12 | 9 | 3 | 2016-12-02 | 2017-01-25 | 36 | 29 | 7 | [7 empty] | 0 |  |  | 2017-01-26 | 2017-03-30 | 45 | 0 | 45 | 2017-04-20 |  | -30535 |  |  | 2017-04-19 |  | 2017-10-18 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-11-15 | Online
WMECO | Lee | 6B1279-2016 | 1238 | 1860 | Solar | 16B1 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-24 | 2017-03-22 | 41 | 3 | 38 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-24 | 85 | 17 | 68 | 2017-07-25 | 2017-11-03 | 72 | 0 | 72 | 2017-11-03 |  | Sept 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-08-24 | Online
WMECO | Lanesborough | 6B1280-2016 | 1237 | 4491 | Solar | 15E1 | 2016-11-15 | 2017-02-13 | 61 | 58 | 3 | 2017-02-14 | 2017-03-22 | 26 | 21 | 5 | [7 empty] | 0 |  |  | 2017-03-23 |  | -30516 | [9 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1281-2016 | 1201 | 1500 | Solar | 15E2 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-04 |  | -30462 | [9 empty] | 0 | [14 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1738-2016 | 1351 | 4080 | Solar | 21C8 | 2016-11-15 | 2017-02-17 | 65 | 64 | 1 | 2017-02-21 | 2017-03-22 | 22 | 16 | 6 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-28 | 89 | 16 | 73 | 2017-07-31 | 2017-10-02 | 45 | 0 | 45 | 2017-10-19 |  | Sept 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-10-12 | Online
WMECO | Ludlow | 6S2989-2016 | 1056 | 1860 | Solar | 19S1 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-24 | 2017-03-02 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-06-12 | 70 | 20 | 50 | 2017-06-13 | 2017-10-03 | 79 | 0 | 79 | 2017-10-17 |  | Sept 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-08-29 | Online
WMECO | Agawam | 6S2990-2016 | 1030 | 4140 | Solar | 30A6 | 2016-11-15 | 2017-01-23 | 46 | 42 | 4 | 2017-01-24 | 2017-03-02 | 27 | 13 | 14 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-05-12 | 50 | 0 | 50 | [7 empty] | Sept 2017 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2996-2016 | 1001 | 95.4 | Solar | 16C16 | 2016-11-15 | 2016-12-05 | 14 | 11 | 3 | 2016-12-05 | 2016-12-15 | 9 | 6 | 3 | [7 empty] | 0 | [12 empty] | 2016-12-15 |  | 12/23/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-07-10 | 2017-07-12 | 2017-07-18 | Online
WMECO | Pittsfield | 6B1282-2016 | 1201 | 1590 | Solar | 30B7 | 2016-11-16 | 2016-12-01 | 11 | 6 | 5 | 2016-12-02 | 2016-12-19 | 12 | 4 | 8 | 2016-12-20 | 2017-02-08 | 34 | 15 | 19 |  |  | 0 |  |  | 2017-02-09 | 2017-04-11 | 43 | 0 | 43 | 2017-04-21 |  | -30536 |  |  | 2017-04-26 |  | 12/2016 |  | Standard |  |  |  | 0 |  |  |  | 2018-08-10 | 2018-09-10 | Online
WMECO | Hadley | 6A2172-2016 | 1035 | 1630 | Solar | 19B15 | 2016-11-21 | 2017-01-23 | 42 | 35 | 7 | 2017-01-24 | 2017-03-02 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-05-19 | 55 | 0 | 55 | [7 empty] | 2017-09-28 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1290-2016 | 1238 | 999 | Solar | 16B1 | 2016-11-21 | 2016-12-01 | 8 | 7 | 1 | 2016-12-02 |  | -30441 | [9 empty] | 0 | [14 empty] | 5/1/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3021-2016 | 1030 | 849.7 | Solar | 30A6 | 2016-11-21 | 2017-02-28 | 67 | 65 | 2 | 2017-03-01 | 2017-03-22 | 16 | 10 | 6 | [7 empty] | 0 |  |  | 2017-03-23 |  | -30516 | 24 | [8 empty] | 9/28/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A2182-2016 | 1351 | 450 | Solar | 21C8 | 2016-11-22 | 2017-01-03 | 28 | 27 | 1 | 2017-01-04 | 2017-04-05 | 64 | 60 | 4 | [7 empty] | 0 |  |  | 2017-04-06 | 2018-02-23 | 221 | 179 | 42 | [5 empty] | 2018-02-28 |  | Dec 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3052-2016 | 1118 | 266.4 | Solar | 20A32 | 2016-12-02 | 2017-04-03 | 83 | 81 | 2 | 2017-04-04 |  | -30524 | [9 empty] | 0 | [14 empty] | 2017-06-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3100-2016 | 1001 | 129.6 | Solar | 30A2 | 2016-12-21 | [16 empty] | 0 | [14 empty] | 2017-01-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3147-2017 | 1103 | 1023.24 | Solar | 08C32 | 2017-01-03 | 2017-02-14 | 30 | 23 | 7 | 2017-02-15 |  | -30491 | [9 empty] | 0 | [14 empty] | 2017-10-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S3151-2017 | 1034 | 475 | Biogas | 29A5 | 2017-01-03 | 2017-02-16 | 32 | 28 | 4 | 2017-02-17 | 2017-04-27 | 48 | 46 | 2 | [7 empty] | 0 |  |  | 2017-04-28 | 2017-07-20 | 58 | 11 | 47 | 2017-07-21 | 2017-10-03 | 52 | 0 | 52 | 2017-10-19 |  | 2017-10-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-05-16 | Online
WMECO | Hatfield | 6A2232-2017 | 1088 | 334.42 | Solar | 18G5 | 2017-01-09 | 2017-03-20 | 49 | 46 | 3 | 2017-03-21 |  | -30514 | [9 empty] | 0 | [14 empty] | 9/1/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1329-2017 | 1201 | 725 | Natural Gas | 30B1 | 2017-01-10 | 2017-02-13 | 24 | 22 | 2 | 2017-02-14 | 2017-04-21 | 47 | 36 | 11 | 2017-04-24 | 2017-07-13 | 57 | 40 | 17 |  |  | 0 | [12 empty] | 2017-07-24 |  | 11/1/2017 |  | Expedited |  |  |  | 0 |  |  | 2018-05-14 | 2018-05-23 | 2018-06-07 | Online
WMECO | Erving | 6F1795-2017 | 1344 | 210 | Solar | 21B9 | 2017-01-11 | 2017-03-15 | 44 | 40 | 4 | 2017-03-16 |  | -30511 | [9 empty] | 0 | [14 empty] | 2017-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chicopee | 6S3180-2017 | 1013 | 2535 | Solar | 21N7 | 2017-01-18 | 2017-02-14 | 20 | 8 | 12 | 2017-02-15 | 2017-03-09 | 16 | 12 | 4 | [7 empty] | 0 |  |  | 2017-03-10 | 2017-06-15 | 68 | 3 | 65 | [5 empty] | 2017-06-30 |  | 2017-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3184-2017 | 1103 | 6250 | Diesel | 8C31 | 2017-01-19 | 2017-02-17 | 22 | 12 | 10 | 2017-02-21 | 2017-05-08 | 54 | 18 | 36 | [7 empty] | 0 |  |  | 2017-05-09 | 2017-08-04 | 62 | 55 | 7 | [5 empty] | 2017-08-24 |  | Not supplied |  | Standard |  |  |  | 0 |  |  | 2017-09-15 | 2017-09-18 | 2017-09-25 | Online
WMECO | Greenfield | 6F1810-2017 | 1301 | 250 | Solar | 22B7 | 2017-01-24 | 2017-03-01 | 26 | 12 | 14 | 2017-03-01 |  | -30500 | [9 empty] | 0 | [14 empty] | 2017-05-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1809-2017 | 1301 | 294 | Solar | 22B7 | 2017-01-25 | 2017-03-01 | 25 | 12 | 13 | 2017-03-01 |  | -30500 | [9 empty] | 0 | [14 empty] | 2017-05-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Savoy | 6B1350-2017 | 1256 | 7500 | Wind | 18C1 | 2017-02-01 | 2017-02-23 | 16 | 12 | 4 | 2017-02-24 | 2017-03-28 | 23 | 15 | 8 | [7 empty] | 0 |  |  | 2017-03-29 | 2018-02-22 | 226 | 106 | 120 | 2018-02-23 |  | -30746 |  |  |  |  | Sept 2018 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3221-2017 | 1001 | 1252 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 | 2017-06-12 | 76 | 52 | 24 | [7 empty] | 0 |  |  | 2017-06-13 |  | -30572 |  |  | 2017-08-17 |  | -30618 |  |  |  |  | May 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3222-2017 | 1001 | 167 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 |  | -30496 | [9 empty] | 0 | [14 empty] | May 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3223-2017 | 1001 | 72 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 |  | -30496 | [9 empty] | 0 | [14 empty] | May 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3230-2017 | 1103 | 16.2 | Solar | 8CNW_1 | 2017-02-08 | 2017-03-16 | 26 | 19 | 7 | 2017-03-17 | 2017-04-13 | 20 |  | 20 | [7 empty] | 0 | [14 empty] | 2017-04-10 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2263-2017 | 1002 | 3120 | Solar | 18G4 | 2017-02-09 | 2017-02-15 | 5 | 4 | 1 | 2017-02-16 | 2017-05-04 | 54 | 44 | 10 | [7 empty] | 0 |  |  | 2017-05-05 | 2017-08-04 | 64 | 15 | 49 | 2017-08-07 |  | -30610 |  |  | 2017-08-23 |  | 2017-12-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-20 | Online
WMECO | Worthington | 6A2274-2017 | 1098 | 5000 | Solar | 18K3 | 2017-02-13 | 2017-03-01 | 12 | 10 | 2 | 2017-03-02 |  | -30501 | [9 empty] | 0 | [14 empty] | 2018-01-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1362-2017 | 1008 | 1000 | Solar | 19J2 | 2017-02-13 | 2017-02-27 | 10 | 7 | 3 | 2017-02-28 | 2017-04-14 | 34 | 20 | 14 | [7 empty] | 0 |  |  | 2017-04-17 | 2017-08-08 | 79 | 38 | 41 | 2017-08-09 | 2017-11-17 | 70 | 4 | 66 | 2017-11-17 |  | Dec 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-11-15 | Online
WMECO | Hinsdale | 6B1363-2017 | 1235 | 5000 | Solar | 18C2 | 2017-02-13 | 2017-03-16 | 23 | 21 | 2 | 2017-03-17 |  | -30512 | [9 empty] | 0 | [14 empty] | Dec 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1365-2017 | 1201 | 499.5 | Solar | 30B5 | 2017-02-15 | 2017-03-29 | 30 | 20 | 10 | 2017-03-30 |  | -30521 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1366-2017 | 1226 | 499.5 | Solar | 19A3 | 2017-02-15 | 2017-03-29 | 30 | 20 | 10 | 2017-03-30 | 2017-05-05 | 26 | 22 | 4 | [7 empty] | 0 |  |  | 2017-05-08 | 2017-08-14 | 69 | 26 | 43 | 2017-08-24 |  | -30623 |  |  | 2017-08-14 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-28 | Online
WMECO | Cummington | 6A2290-2017 | 1026 | 10.95 | Solar | 18K3 | 2017-02-23 | 2017-03-06 | 8 | 4 | 4 | 2017-03-06 | 2017-04-28 | 39 | 24 | 15 | [7 empty] | 0 | [12 empty] | 2017-04-28 |  | 2017-05-15 |  | Expedited |  |  |  | 0 |  |  | 2017-06-26 | 2017-06-30 | 2017-06-30 | Online
WMECO | Pittsfield | 6B1375-2017 | 1201 | 1160 | Solar | 15E2 | 2017-02-27 | 2017-03-08 | 8 | 6 | 2 | 2017-03-08 | 2017-03-22 | 11 | 8 | 3 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-28 | 89 | 16 | 73 | 2017-07-31 | 2017-09-29 | 44 | 9 | 35 | 2017-10-06 |  | 2017-09-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-08-17 | Online
WMECO | Lanesborough | 6B1377-2017 | 1237 | 1998 | Solar | 15E1 | 2017-02-28 | 2017-04-11 | 31 | 28 | 3 | 2017-04-12 |  | -30530 | 9 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1378-2017 | 1201 | 27.44 | Solar | 19A7 | 2017-02-28 | 2017-03-29 | 22 | 21 | 1 | 2017-03-29 | 2017-04-20 | 16 | 15 | 1 | 2017-04-21 | 2017-07-14 | 59 | 0 | 59 |  |  | 0 | [12 empty] | 2017-07-14 |  | Aug 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-03-21 | 2018-03-21 | 2018-03-23 | Online
WMECO | Greenfield | 6A2305-2017 | 1337 | 995 | Biogas | 22B7 | 2017-03-06 | 2017-03-20 | 11 | 9 | 2 | 2017-03-21 |  | -30514 | 30 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A2316-2017 | 1098 | 21.9 | Solar | 18K3 | 2017-03-09 | 2017-03-30 | 16 | 14 | 2 | 2017-03-30 |  | -30521 | [9 empty] | 0 | [14 empty] | 2017-06-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1399-2017 | 1237 | 1998 | Solar | 15E1 | 2017-03-20 | [16 empty] | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A2364-2017 | 1354 | 4998.4 | Solar | 21C5 | 2017-03-29 | 2017-04-17 | 13 | 7 | 6 | 2017-04-18 | 2017-07-24 | 68 | 29 | 39 | [7 empty] | 0 |  |  | 2017-07-25 | 2017-12-18 | 101 | 18 | 83 | [7 empty] | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S3353-2017 | 1106 | 86.4 | Solar | 22H15 | 2017-04-07 | [16 empty] | 0 | [14 empty] | 5/7 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2398-2017 | 1059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 |  | -30576 | [9 empty] | 0 | [14 empty] | 2017-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2399-2017 | 1059 | 4980 | Battery | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 | 2017-08-08 | 36 | 28 | 8 | [7 empty] | 0 |  |  | 2017-08-09 | 2017-10-17 | 48 | 0 | 48 | 2017-12-15 |  | -30700 |  |  | 2017-10-30 |  | 2017-12-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Amherst | 6A2400-2017 | 1059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 |  | -30576 | [9 empty] | 0 | [14 empty] | 2017-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3370-2017 | 1089 | 300 | Natural Gas | 21N5 | 2017-04-13 | 2017-07-20 | 68 | 67 | 1 | 2017-07-21 | 2017-10-10 | 56 | 49 | 7 | [7 empty] | 0 |  |  | 2017-10-11 | 2017-11-10 | 22 | 0 | 22 | [7 empty] | 2/2018 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3392-2017 | 1118 | 165 | Solar | 20A32 | 2017-04-21 | 2017-05-01 | 7 | 5 | 2 | 2017-05-01 | 2017-05-08 | 6 | 3 | 3 | 2017-05-09 | 2017-08-31 | 81 | 43 | 38 |  |  | 0 |  |  | 2017-09-01 | 2017-11-28 | 59 | 7 | 52 | [5 empty] | 2017-11-28 |  | 2017-06-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1444-2017 | 1201 | 240 | Solar | 15E2 | 2017-04-25 | 2017-05-15 | 15 | 13 | 2 | 2017-05-16 | 2017-06-23 | 28 | 3 | 25 |  | 2017-07-06 | [5 empty] | 0 |  |  | 2017-06-23 | 2017-10-04 | 72 | 64 | 8 | 2017-10-05 | 2017-12-21 | 53 | 0 | 53 | 2017-12-21 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A2448-2017 | 1038 | 15.36 | Solar | 18G6 | 2017-05-01 | 2017-05-12 | 10 | 7 | 3 | 2017-05-12 |  | -30551 | [9 empty] | 0 | [14 empty] | 2017-05-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1446-2017 | 1237 | 2597.4 | Solar | 15E2 | 2017-05-04 | 2017-05-18 | 11 | 2 | 9 | 2017-05-19 |  | -30556 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1447-2017 | 1201 | 1998 | Solar | 19A4 | 2017-05-05 | 2017-05-18 | 10 | 3 | 7 | 2017-05-19 | 2017-06-02 | 10 | 6 | 4 | [7 empty] | 0 |  |  | 2017-06-05 | 2017-08-23 | 57 | 4 | 53 | 2017-08-24 |  | -30623 |  |  | 2017-08-30 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-21 | Online
WMECO | Blandford | 6B1451-2017 | 1008 | 4700 | Solar | 19J4 | 2017-05-08 | 2017-08-18 | 73 | 60 | 13 | 2017-08-21 | 2017-09-14 | 18 | 11 | 7 | [7 empty] | 0 |  |  | 2017-09-15 | 2017-12-04 | 54 | 10 | 44 | 2017-12-19 |  | -30702 |  |  | 2017-12-04 |  | 2018-09-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-06-30 | Online
WMECO | Springfield | 6S3435-2017 | 1104 | 1440 | Solar | 5J11 | 2017-05-08 | 2017-06-01 | 18 | 9 | 9 | 2017-06-02 | 2017-07-19 | 33 | 30 | 3 | [7 empty] | 0 |  |  | 2017-07-20 | 2017-11-02 | 74 | 17 | 57 | 2017-11-10 |  | -30676 |  |  | 2017-12-11 |  | Nov 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-10-17 | Online
WMECO | Pittsfield | 6B1454-2017 | 1201 | 1556 | Solar | 30B5 | 2017-05-11 | 2017-06-19 | 27 | 21 | 6 | 2017-06-20 |  | -30577 | [9 empty] | 0 | [14 empty] | 2018-01-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2489-2017 | 1026 | 480 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 17 | 13 | 4 | 2017-06-07 | 2017-07-17 | 28 | 22 | 6 | [7 empty] | 0 |  |  | 2017-07-18 | 2017-09-28 | 52 | 0 | 52 | [7 empty] | 2018-02-15 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2491-2017 | 1026 | 240 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 17 | 13 | 4 | 2017-06-07 |  | -30568 | 111 | [8 empty] | 0 | [14 empty] | 2018-02-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A2495-2017 | 1370 | 60 | Solar | 29R2 | 2017-05-17 | 2017-05-25 | 7 | 2 | 5 | 2017-05-25 | 2017-06-05 | 7 | 5 | 2 | [7 empty] | 0 | [12 empty] | 2017-06-09 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2018-01-31 | 2018-02-02 | 2018-02-02 | Online
WMECO | Easthampton | 6A2529-2017 | 1027 | 1095.8 | Solar | 15A5 | 2017-05-25 | 2017-08-17 | 59 | 51 | 8 | 2017-08-18 | 2017-10-27 | 49 | 37 | 12 | [7 empty] | 0 |  |  | 2017-10-30 | 2018-03-15 | 93 | 21 | 72 | 2018-03-16 | 2018-06-26 | 70 | 11 | 59 | 2018-06-29 |  | 2018-04-15 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A2524-2017 | 1342 | 72 | Solar | 22B1 | 2017-05-30 | 2017-06-08 | 8 | 5 | 3 | 2017-06-09 | 2017-06-22 | 10 | 2 | 8 | [7 empty] | 0 | [12 empty] | 2017-06-22 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2017-12-26 | 2017-12-17 | 2018-01-12 | Online
WMECO | Dalton | 6B1482-2017 | 1226 | 4980 | Solar | 29M1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30575 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1483-2017 | 1237 | 4980 | Solar | 15E2 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30575 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S3507-2017 | 1077 | 4980 | Solar | 29A1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 | 2017-09-01 | 55 | 48 | 7 | [7 empty] | 0 |  |  | 2017-09-05 | 2017-10-20 | 33 | 0 | 33 | 2017-10-31 |  | -30669 |  |  | 2017-10-30 |  | 1905-07-09 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-02-01 | Online
WMECO | Greenfield | 6A2544-2017 | 1301 | 380 | Solar | 22B2 | 2017-06-06 | 2017-06-20 | 11 | 4 | 7 | 2017-06-21 | 2017-09-25 | 67 | 30 | 37 | 2017-09-26 | 2017-12-28 | 64 | 41 | 23 |  |  | 0 |  |  | 2017-12-29 | 2018-02-02 | 24 | 8 | 16 | [5 empty] | 2018-02-07 |  | 10-17 |  | Standard |  |  |  | 0 |  |  |  | 2018-04-27 | 2018-04-30 | Online
WMECO | Hatfield | 6A2545-2017 | 1038 | 380 | Biogas | 18G6 | 2017-06-06 | 2017-06-30 | 19 | 10 | 9 | 2017-07-03 | 2017-07-27 | 18 | 8 | 10 | [7 empty] | 0 |  |  | 2017-07-28 | 2017-11-03 | 69 | 1 | 68 | 2018-01-19 |  | -30722 |  |  | 2017-11-10 |  | 6/2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-05-21 | Online
WMECO | Springfield | 6S3522-2017 | 1151 | 3500 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 74 | 35 | 39 | 2017-09-25 | 2017-12-06 | 50 | 45 | 5 | [7 empty] | 0 |  |  | 2017-12-07 | 2018-03-19 | 68 | 10 | 58 | 2018-04-03 |  | -30772 |  |  | 2018-04-10 |  | 2018-06-07 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-27 | Online
WMECO | Springfield | 6S3523-2017 | 1151 | 2000 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 74 | 33 | 41 | 2017-09-25 | 2018-02-13 | 96 | 92 | 4 | [7 empty] | 0 |  |  | 2018-02-14 | 2018-09-04 | 139 |  | 139 | [5 empty] | 2018-08-15 |  | 2018-06-07 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S3529-2017 | 1106 | 16 | Solar | 22H12 | 2017-06-12 | 2017-06-22 | 9 | 3 | 6 | 2017-06-22 | 2017-06-26 | 3 | 0 | 3 | [7 empty] | 0 | [12 empty] | 2017-06-30 |  | 2017-07-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-11-08 | Online
WMECO | Pittsfield | 6B1488-2017 | 1201 | 33.3 | Solar | 30B5 | 2017-06-14 | 2017-07-13 | 21 | 13 | 8 | 2017-07-13 | 2017-08-25 | 32 | 15 | 17 | [7 empty] | 0 | [12 empty] | 2017-09-17 |  | 2017-08-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-08-04 | Online
WMECO | Sunderland | 6A2588-2017 | 1375 | 1084 | Solar | 18G3 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-24 | 41 | 30 | 11 | [7 empty] | 0 |  |  | 2017-08-24 | 2017-10-19 | 39 | 0 | 39 | 2017-11-10 |  | -30676 |  |  | 2017-10-30 |  | DEC 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-09-21 | Online
WMECO | Pittsfield | 6B1490-2017 | 1201 | 499.5 | Solar | 30B1 | 2017-06-15 | 2017-07-05 | 14 | 3 | 11 | 2017-07-06 |  | -30588 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1491-2017 | 1201 | 765.9 | Solar | 30B1 | 2017-06-15 | 2017-07-03 | 13 | 3 | 10 | 2017-07-05 | 2017-12-18 | 115 | 93 | 22 | [7 empty] | 0 |  |  | 2017-12-19 | 2018-03-21 | 62 |  | 62 | [7 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3543-2017 | 1001 | 4989.8 | Solar | 30A3 | 2017-06-15 | 2017-06-28 | 10 | 6 | 4 | 2017-06-29 |  | -30584 | [9 empty] | 0 | [14 empty] | Fall 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3544-2017 | 1001 | 4990 | Solar | 30A3 | 2017-06-15 | 2017-06-30 | 12 | 6 | 6 | 2017-07-03 | 2017-08-01 | 21 | 14 | 7 | [7 empty] | 0 |  |  | 2017-08-02 | 2017-12-14 | 93 | 36 | 57 | 2017-12-15 | 2018-03-15 | 61 | 12 | 49 | 2018-03-16 |  | Fall 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-11 | Online
WMECO | Springfield | 6S3549-2017 | 1104 | 4000 | Solar | 5J18 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-23 | 40 | 32 | 8 | [7 empty] | 0 |  |  | 2017-08-24 | 2017-11-28 | 65 | 0 | 65 | 2017-12-06 |  | -30693 |  |  | 2017-12-05 |  | DEC 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-01 | Online
WMECO | Amherst | 6A2594-2017 | 1002 | 3875 | Solar | 17K8 | 2017-06-19 | 2017-06-29 | 9 | 7 | 2 | 2017-06-30 | 2017-08-29 | 42 | 31 | 11 | [7 empty] | 0 |  |  | 2017-08-30 | 2017-11-01 | 44 |  | 44 | [5 empty] | 2017-12-05 |  | 7/18 |  | Complex |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Hinsdale | 6B1495-2017 | 1235 | 999 | Solar | 18C2 | 2017-06-19 | 2017-07-05 | 12 | 5 | 7 | 2017-07-06 | 2017-08-18 | 32 | 23 | 9 | [7 empty] | 0 |  |  | 2017-08-21 | 2017-10-24 | 45 | 0 | 45 | 2017-11-29 |  | -30688 |  |  | 2017-11-02 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-10-30 | Online
WMECO | Feeding Hills | 6S3555-2017 | 1030 | 18.88 | Solar | 16C17 | 2017-06-19 | 2017-07-07 | 14 | 6 | 8 | 2017-07-07 |  | -30589 | [9 empty] | 0 | [14 empty] | 2017-07-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1497-2017 | 1237 | 499.5 | Solar | 15E1 | 2017-06-21 | 2017-07-07 | 12 | 6 | 6 | 2017-07-10 | 2017-10-04 | 62 | 55 | 7 | [7 empty] | 0 |  |  | 2017-10-05 | 2017-12-14 | 48 | 0 | 48 | 2018-01-26 |  | -30727 |  |  | 2017-12-18 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-07-25 | Online
WMECO | Southwick | 6S3566-2017 | 1077 | 2000 | Solar | 29A1 | 2017-06-21 | 2017-08-07 | 33 | 16 | 17 | 2017-08-08 |  | -30611 | 37 | [8 empty] | 0 | [5 empty] | 11 | [8 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2609-2017 | 1027 | 32.85 | Solar | 15A5 | 2017-06-22 | 2017-06-28 | 5 | 0 | 5 | 2017-06-28 | 2017-08-10 | 31 | 31 | 0 | 2017-08-11 | 2017-08-25 | 11 | 0 | 11 |  |  | 0 | [12 empty] | 2017-08-28 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-08-30 | 2018-08-31 | 2018-08-31 | Online
WMECO | Agawam | 6S3582-2017 | 1001 | 2330 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 106 | 99 | 7 | 2017-12-01 |  | -30690 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3583-2017 | 1001 | 5555 | Solar | 30A4 | 2017-06-29 | 2017-12-14 | 116 | 112 | 4 | 2017-12-14 | 2017-12-14 | 1 |  | 1 | [7 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3584-2017 | 1001 | 5500 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 106 | 99 | 7 | 2017-12-01 |  | -30690 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3585-2017 | 1001 | 2330 | Solar | 30A4 | 2017-06-29 | [16 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1522-2017 | 1008 | 4920 | Solar | 19J2 | 2017-07-17 | 2017-07-20 | 4 | 1 | 3 | 2017-07-21 | 2017-11-10 | 78 | 31 | 47 | [7 empty] | 0 |  |  | 2017-11-13 | 2018-03-13 | 82 | 7 | 75 | 2018-06-29 |  | -30833 |  |  | 2018-05-07 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2019-12-27 | Online
WMECO | Hatfield | 6A2693-2017 | 1038 | 3600 | Solar | 18G5 | 2017-07-24 | 2017-07-27 | 4 | 0 | 4 | 2017-07-27 | 2017-09-27 | 44 | 20 | 24 | [7 empty] | 0 |  |  | 2017-09-28 | 2017-11-16 | 34 | 0 | 34 | 2017-11-28 |  | -30687 |  |  | 2017-11-27 |  | Nov 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-11-02 | Online
WMECO | Amherst | 6A2698-2017 | 1002 | 98.5 | Solar | 18G4 | 2017-07-26 | 2017-09-22 | 42 | 33 | 9 | 2017-09-25 | 2017-10-20 | 19 | 8 | 11 | [7 empty] | 0 | [12 empty] | 2017-10-27 |  | 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-03-30 | Online
WMECO | Pittsfield | 6B1539-2017 | 1201 | 4980 | Solar | 15E2 | 2017-07-28 | 2017-09-11 | 31 | 22 | 9 | 2017-09-12 |  | -30635 | 44 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A2710-2017 | 1342 | 2200 | Solar | 22B4 | 2017-07-31 | 2017-08-09 | 8 | 1 | 7 | 2017-08-10 | 2017-08-28 | 13 | 6 | 7 | [7 empty] | 0 |  |  | 2017-08-29 | 2018-02-26 | 122 | 11 | 111 | [5 empty] | 2018-06-20 |  | 2018-03-02 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2718-2017 | 1027 | 2200 | Solar | 15A2 | 2017-08-02 | 2017-08-28 | 19 | 15 | 4 | 2017-08-28 | 2017-09-22 | 19 | 18 | 1 | [7 empty] | 0 |  |  | 2017-09-25 | 2017-12-07 | 51 | 17 | 34 | 2017-12-08 | 2018-03-23 | 71 | 21 | 50 | 2018-04-02 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2774-2017 | 1002 | 233.1 | Solar | 17K8 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 |  | -30625 | [9 empty] | 0 | [14 empty] | 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2776-2017 | 1002 | 233.1 | Solar | 17K2 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 | 2017-09-28 | 23 | 20 | 3 | [7 empty] | 0 |  |  | 2017-09-29 | 2017-10-31 | 22 | 0 | 22 | [7 empty] | 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1571-2017 | 1238 | 4993 | Solar | 16B1 | 2017-08-24 | 2017-09-26 | 23 | 15 | 8 | 2017-09-27 | 2018-06-20 | 181 | 62 | 119 | [7 empty] | 0 |  |  | 2018-06-21 | 2018-11-05 | 95 |  | 95 | [5 empty] | 2018-11-09 |  |  |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3712-2017 | 1089 | 20 | Solar | 21N4 | 2017-08-24 | 2017-09-19 | 18 | 4 | 14 | 2017-09-20 | 2017-10-16 | 18 | 0 | 18 | [7 empty] | 0 | [12 empty] | 2017-10-16 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2017-12-18 | 2017-12-21 | 2017-12-28 | Online
WMECO | Greenfield | 6A2815-2017 | 1301 | 7190 | Solar | 21C1 | 2017-08-29 | 2017-09-21 | 17 | 4 | 13 | 2017-09-22 |  | -30643 | [9 empty] | 0 | [14 empty] | 2018-08-18 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A2826-2017 | 1344 | 990 | Solar | 21B8 | 2017-09-01 | 2017-10-12 | 28 | 20 | 8 | 2017-10-13 | 2018-02-09 | 81 | 47 | 34 | [7 empty] | 0 |  |  | 2018-02-09 | 2018-07-19 | 110 | 32 | 78 | 2018-07-20 |  | -30847 |  |  | 2018-08-15 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2020-09-11 | Online
WMECO | Springfield | 6S3764-2017 | 1105 | 72 | Solar | 5J16 | 2017-09-08 | 2017-09-21 | 10 | 7 | 3 | 2017-09-22 | 2017-12-07 | 52 | 33 | 19 | [7 empty] | 0 | [12 empty] | 2017-12-08 |  | 11/17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2837-2017 | 1026 | 999 | Solar | 18K3 | 2017-09-11 | 2017-10-12 | 23 | 16 | 7 | 2017-10-13 |  | -30657 | [9 empty] | 0 | [14 empty] | Fall 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Leverett | 6A2858-2017 | 1054 | 366.3 | Solar | 18G7 | 2017-09-14 | 2017-09-27 | 10 | 9 | 1 | 2017-09-28 | 2017-11-02 | 25 | 7 | 18 | [7 empty] | 0 |  |  | 2017-11-03 | 2018-01-23 | 53 | 0 | 53 | [5 empty] | 2018-02-01 |  | 2018-01-20 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-02-14 | Online
WMECO | Springfield | 6S3788-2017 | 1105 | 57.6 | Solar | 8C26 | 2017-09-19 | 2017-09-28 | 8 | 7 | 1 | 2017-09-29 | 2018-01-22 | 76 | 53 | 23 | [7 empty] | 0 | [12 empty] | 2018-01-22 |  | 2018-10-26 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-04-26 | Online
WMECO | Springfield | 6S3797-2017 | 1103 | 450 | Natural Gas | 8C31 | 2017-09-20 | 2017-11-06 | 33 | 24 | 9 | 2017-11-07 | 2017-12-05 | 19 | 6 | 13 | 2017-12-06 | 2018-02-26 | 55 | 40 | 15 |  |  | 0 | [12 empty] | 2018-03-06 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2885-2017 | 1002 | 2000 | Diesel | 17K5 | 2017-09-21 | 2017-10-18 | 19 | 13 | 6 | 2017-10-19 | 2018-02-28 | 89 | 26 | 63 | [7 empty] | 0 | [12 empty] | 2018-04-10 |  | Sept 2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-11-20 | Online
WMECO | South Deerfield | 6A2888-2017 | 1373 | 57.5 | Solar | 22B1 | 2017-09-22 | 2017-10-05 | 10 | 5 | 5 | 2017-10-06 | 2017-11-07 | 22 | 21 | 1 | 2017-11-08 | 2017-11-14 | 4 | 0 | 4 |  |  | 0 | [12 empty] | 2017-11-28 |  | Nov 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-20 | Online
WMECO | South Deerfield | 6A2889-2017 | 1373 | 57 | Solar | 22B1 | 2017-09-22 | [16 empty] | 0 | [14 empty] | Nov 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1612-2017 | 1201 | 22.8 | Solar | 30B3 | 2017-09-22 | 2017-10-10 | 12 | 9 | 3 | 2017-10-11 |  | -30655 | [9 empty] | 0 | [14 empty] | 12/17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1616-2017 | 1253 | 24 | Solar | 19J4 | 2017-09-26 | 2017-10-04 | 7 | 5 | 2 | 2017-10-05 | 2018-09-24 | 241 |  | 241 | 2018-09-25 | 2018-10-23 | 20 |  | 20 |  |  | 0 | [12 empty] | 2018-10-23 |  | 2017-11-22 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Southwick | 6S3810-2017 | 1077 | 4980 | Solar | 29A5 | 2017-09-27 | 2017-09-29 | 3 | 0 | 3 | 2017-10-02 |  | -30649 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2904-2017 | 1027 | 2460 | Solar | 15A2 | 2017-09-28 | 2017-09-29 | 2 | 0 | 2 | 2017-10-02 | 2017-11-21 | 35 | 10 | 25 | [7 empty] | 0 |  |  | 2017-11-22 | 2018-02-09 | 54 | 0 | 54 | 2018-02-12 |  | -30738 |  |  | 2018-02-20 |  | Q4 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-09-22 | Online
WMECO | Shelburne Falls | 6A2914-2017 | 1370 | 60 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 13 | 11 | 2 | 2017-10-18 | 2017-10-27 | 8 | 4 | 4 | 2017-10-27 | 2017-12-06 | 27 | 3 | 24 |  |  | 0 | [12 empty] | 2017-12-14 |  | Nov 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-05-15 | 2018-05-17 | 2018-05-17 | Online
WMECO | Shelburne Falls | 6A2915-2017 | 1370 | 50 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 13 | 11 | 2 | 2017-10-18 |  | -30660 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1618-2017 | 1226 | 9.28 | Solar | 19A2 | 2017-09-28 | [16 empty] | 0 | [14 empty] | 2017-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1620-2017 | 1235 | 3000 | Solar | 18C2 | 2017-09-28 | 2017-10-04 | 5 | 2 | 3 | 2017-10-05 | 2017-10-24 | 13 | 4 | 9 | [7 empty] | 0 |  |  | 2017-10-25 | 2018-02-27 | 84 | 0 | 84 | 2018-02-28 |  | -30749 |  |  | 2018-02-27 |  | 12.18 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-10-15 | Online
WMECO | Otis | 6B1625-2017 | 1253 | 24 | Solar | 19J4 | 2017-09-29 | 2017-10-04 | 4 | 2 | 2 | 2017-10-05 | 2018-09-24 | 241 |  | 241 | 2018-09-25 | 2018-10-23 | 20 |  | 20 |  |  | 0 | [12 empty] | 2018-10-23 |  | Nov 22 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-10 | Online
WMECO | Hinsdale | 6B1626-2017 | 1235 | 2200 | Solar | 18C2 | 2017-09-29 | 2017-10-05 | 5 | 3 | 2 | 2017-10-06 |  | -30653 | [9 empty] | 0 | [14 empty] | 2018-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3822-2017 | 1089 | 46.8 | Solar | 16C15 | 2017-10-02 | 2017-11-10 | 28 | 26 | 2 | 2017-11-13 | 2018-01-26 | 51 | 40 | 11 | [7 empty] | 0 | [12 empty] | 2018-01-26 |  | 2017-11-01 |  | Expedited |  |  |  | 0 |  |  | 2018-04-02 | 2018-04-10 | 2018-04-13 | Online
WMECO | Russell | 6A2932-2017 | 1071 | 2988 | Solar | 19J2 | 2017-10-04 | 2017-10-17 | 9 | 8 | 1 | 2017-10-18 | 2017-11-27 | 27 | 3 | 24 | [7 empty] | 0 |  |  | 2017-11-28 | 2018-05-24 | 122 | 60 | 62 | 2018-06-06 |  | -30816 |  |  | 2018-06-01 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-10-26 | Online
WMECO | Tolland | 6B1628-2017 | 1034 | 4980 | Solar | 19J4 | 2017-10-04 | 2017-10-17 | 9 | 7 | 2 | 2017-10-18 | 2017-12-11 | 37 | 16 | 21 | [7 empty] | 0 |  |  | 2017-12-12 | 2018-02-20 | 47 | 0 | 47 | 2018-03-01 |  | -30750 |  |  | 2018-02-27 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-12-28 | Online
WMECO | Pittsfield | 6B1632-2017 | 1201 | 4987 | Solar | 15E2 | 2017-10-06 | 2017-10-17 | 7 | 4 | 3 | 2017-10-18 |  | -30660 | [9 empty] | 0 | [14 empty] | Summer 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A2951-2017 | 1349 | 800 | Solar | 21C2 | 2017-10-11 | 2017-12-15 | 46 | 45 | 1 | 2017-12-18 | 2018-02-21 | 44 | 28 | 16 | [7 empty] | 0 |  |  | 2018-02-22 | 2018-05-08 | 52 | 22 | 30 | 2018-05-09 |  | -30797 |  |  | 2018-07-19 |  | 6/31/2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-31 | Online
WMECO | Windsor | 6B1641-2017 | 1270 | 999 | Solar | 18C1 | 2017-10-12 | 2017-11-16 | 25 | 19 | 6 | 2017-11-17 | 2017-12-27 | 27 | 24 | 3 | [7 empty] | 0 |  |  | 2017-12-28 | 2018-04-27 | 82 | 42 | 40 | [5 empty] | 2018-10-26 |  | Fall 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-29 | Online
WMECO | Springfield | 6S3848-2017 | 1119 | 600 | Diesel | 20A14 | 2017-10-12 | 2017-11-06 | 18 | 13 | 5 | 2017-11-07 | 2018-01-23 | 51 | 35 | 16 | 2018-01-24 | 2018-04-02 | 47 | 41 | 6 |  |  | 0 | [12 empty] | 2018-04-18 |  | 2017-12-15 |  | Expedited |  |  |  | 0 |  |  | 2018-04-25 | 2018-06-07 | 2018-06-07 | Online
WMECO | Springfield | 6S3870-2017 | 1103 | 1140 | Solar | 8C31 | 2017-10-18 | 2017-11-06 | 14 | 12 | 2 | 2017-11-07 | 2018-04-20 | 111 | 71 | 40 | [7 empty] | 0 | [12 empty] | 2018-04-26 |  | 2018-11-30 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-07-22 | Online
WMECO | Turners Falls | 6A2995-2017 | 1349 | 996 | Solar | 21C2 | 2017-10-30 | 2017-11-16 | 13 | 8 | 5 | 2017-11-17 | 2018-01-08 | 34 | 26 | 8 | [7 empty] | 0 |  |  | 2018-01-05 | 2018-06-11 | 107 | 94 | 13 | [5 empty] | 2018-09-20 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-24 | Online
WMECO | Westhampton | 6A3031-2017 | 1027 | 4980 | Solar | 15A3 | 2017-11-13 | 2017-12-15 | 24 | 22 | 2 | 2017-12-18 | 2018-01-08 | 14 | 2 | 12 | [7 empty] | 0 |  |  | 2018-01-09 | 2018-04-02 | 57 | 11 | 46 | 2018-04-05 |  | -30774 |  |  | 2018-04-13 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-01-26 | Online
WMECO | Agawam | 6S3940-2017 | 1001 | 366.3 | Solar | 16C16 | 2017-11-20 | 2017-12-15 | 19 | 17 | 2 | 2017-12-18 | 2018-02-28 | 49 | 44 | 5 | 2018-03-01 | 2018-03-14 | 10 | 8 | 2 |  |  | 0 | [12 empty] | 2018-03-29 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2018-10-03 | 2018-10-03 | 2018-10-05 | Online
WMECO | Lanesborough | 6B1701-2017 | 1237 | 4536 | Solar | 15E2 | 2017-11-21 | 2017-12-22 | 23 | 16 | 7 | 2017-12-22 | 2018-03-12 | 53 | 36 | 17 | [7 empty] | 0 |  |  | 2018-03-13 | 2018-06-15 | 66 | 4 | 62 | 2018-07-26 |  | -30851 |  |  | 2018-06-28 |  | asap |  | Complex |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Lanesborough | 6B1702-2017 | 1237 | 3600 | Solar | 15E1 | 2017-11-21 | 2017-12-22 | 23 | 16 | 7 | 2017-12-22 | 2018-03-12 | 53 | 51 | 2 | [7 empty] | 0 |  |  | 2018-03-13 | 2018-06-15 | 66 | 4 | 62 | 2018-07-18 |  | -30845 |  |  | 2018-06-28 |  | asap |  | Standard |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Hadley | 6A3069-2017 | 1035 | 2990 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3073-2017 | 1035 | 2000 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1708-2017 | 1027 | 2573 | Solar | 18C1 | 2017-11-27 | 2017-12-15 | 15 | 13 | 2 | 2017-12-15 |  | -30700 | [9 empty] | 0 | [14 empty] | 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A3081-2017 | 1376 | 3770 | Solar | 21C2 | 2017-11-29 | 2018-02-28 | 62 | 37 | 25 | 2018-03-01 | 2018-06-11 | 70 | 63 | 7 | [7 empty] | 0 |  |  | 2018-06-12 | 2018-10-31 | 99 |  | 99 | [5 empty] | 2018-10-29 |  | August 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-11-23 | Online
WMECO | Worthington | 6A3090-2017 | 1098 | 8300 | Solar | 18K3 | 2017-12-01 | 2017-12-18 | 12 | 9 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3094-2017 | 1301 | 1000 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 89 | 70 | 19 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-09-17 | 94 |  | 94 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | Complex |  |  |  | 0 | [5 empty] | In Queue
WMECO | Chesterfield | 6A3095-2017 | 1012 | 500 | Solar | 18K3 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3096-2017 | 1301 | 500 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3097-2017 | 1360 | 1000 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 89 | 65 | 24 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-10-19 | 117 |  | 117 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3098-2017 | 1360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3099-2017 | 1360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1724-2017 | 1201 | 1380 | Solar | 30B5 | 2017-12-05 | 2018-01-16 | 28 | 23 | 5 | 2018-01-17 | 2018-02-28 | 30 | 24 | 6 | [7 empty] | 0 |  |  | 2018-03-01 | 2018-07-16 | 94 | 40 | 54 | 2018-07-17 |  | -30844 |  |  | 2018-07-16 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-30 | Online
WMECO | Ludlow | 6S3969-2017 | 1056 | 3969 | Solar | 27A5 | 2017-12-05 | 2018-02-08 | 45 | 30 | 15 | 2018-02-09 | 2018-04-27 | 53 | 29 | 24 | [7 empty] | 0 |  |  | 2018-04-30 | 2018-10-15 | 117 |  | 117 | [5 empty] | 2018-10-27 |  | 2018 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-01-29 | Online
WMECO | Lanesborough | 6B1728-2017 | 1237 | 3000 | Solar | 15E1 | 2017-12-07 | [16 empty] | 0 | [14 empty] | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3130-2017 | 1301 | 4500 | Solar | 21C1 | 2017-12-14 | 2017-12-27 | 9 | 2 | 7 | 2017-12-28 | 2018-02-14 | 33 | 7 | 26 | [7 empty] | 0 |  |  | 2018-02-15 | 2018-07-25 | 110 | 42 | 68 | 2018-07-26 |  | -30851 |  |  | 2020-03-23 |  | 2018-12-21 |  | Standard |  |  |  | 0 |  |  |  |  | 2024-07-23 | Online
WMECO | Lanesborough | 6B1736-2017 | 1237 | 4536 | Solar | 15E1 | 2017-12-14 | 2017-12-22 | 7 | 0 | 7 | 2017-12-22 | 2018-05-31 | 108 | 106 | 2 | [7 empty] | 0 |  |  | 2018-06-01 | 2018-08-27 | 61 |  | 61 | [5 empty] | 2018-09-25 |  | ASAP |  | Standard |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Lanesborough | 6B1737-2017 | 1237 | 3000 | Solar | 15E1 | 2017-12-14 | 2017-12-15 | 2 | 0 | 2 | 2017-12-18 | 2018-01-16 | 19 | 11 | 8 | [7 empty] | 0 |  |  | 2018-09-20 | 2018-10-16 | 18 |  | 18 | [5 empty] | 2019-05-21 |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A3136-2017 | 1027 | 4998 | Solar | 15A3 | 2017-12-15 | 2018-01-02 | 11 | 5 | 6 | 2018-01-03 | 2018-06-05 | 105 | 97 | 8 | [7 empty] | 0 |  |  | 2018-06-06 | 2018-10-22 | 96 |  | 96 | [5 empty] | 2018-10-18 |  | 2019-01-14 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-11-30 | Online
WMECO | Pittsfield | 6B1741-2017 | 1201 | 5000 | Solar | 30B2 | 2017-12-18 | 2017-12-27 | 7 | 1 | 6 | 2017-12-28 | 2018-02-28 | 42 | 12 | 30 | [7 empty] | 0 |  |  | 2018-03-01 | 2018-09-24 | 143 |  | 143 | [5 empty] | 2018-10-05 |  | 2019-01-14 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S4000-2017 | 1089 | 180 | Solar | 16C12 | 2017-12-18 | 2018-02-02 | 32 | 6 | 26 | 2018-02-05 | 2018-03-12 | 25 | 7 | 18 | [7 empty] | 0 | [12 empty] | 2018-03-15 |  | 2018-03-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6A3138-2017 | 1341 | 2178 | Solar | 22B1 | 2017-12-19 | 2018-01-10 | 15 | 13 | 2 | 2018-01-11 |  | -30717 | [9 empty] | 0 | [14 empty] | Dec 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4010-2017 | 1118 | 99.9 | Solar | 20A32 | 2017-12-20 | 2018-01-10 | 14 | 9 | 5 | 2018-01-11 | 2018-02-09 | 21 | 2 | 19 | [7 empty] | 0 | [12 empty] | 2018-02-09 |  | 2018-05-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-10-03 | Online
WMECO | Southwick | 6S4042-2018 | 1077 | 9950 | Solar | 29A1 | 2018-01-03 | 2018-02-08 | 26 | 21 | 5 | 2018-02-09 |  | -30737 | [9 empty] | 0 | [14 empty] | 2018-12-10 |  | Standard |  |  |  | 0 | [5 empty] | In Queue
WMECO | Hatfield | 6A3180-2018 | 1038 | 500 | Solar | 18G5 | 2018-01-08 | 2018-01-31 | 17 | 1 | 16 | 2018-02-01 |  | -30731 | 11 | [8 empty] | 0 | [14 empty] | 2018-04-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B1756-2018 | 1223 | 33.3 | Solar | 19J6 | 2018-01-12 | 2018-01-22 | 6 | 4 | 2 | 2018-01-23 | 2018-02-28 | 26 | 0 | 26 | [7 empty] | 0 | [12 empty] | 2018-02-02 |  | 2018-05-01 |  | Expedited |  |  |  | 0 |  |  | 2018-07-11 | 2018-07-17 | 2018-07-18 | Online
WMECO | Deerfield | 6A3216-2018 | 1373 | 500 | Solar | 22B3 | 2018-01-16 | 2018-01-31 | 12 | 5 | 7 | 2018-02-01 | 2018-03-13 | 28 | 22 | 6 | [7 empty] | 0 |  |  | 2018-03-14 | 2018-04-30 | 32 | 2 | 30 | [7 empty] | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1761-2018 | 1008 | 4450 | Solar | 19J6 | 2018-01-17 | 2018-01-29 | 9 | 1 | 8 | 2018-01-30 |  | -30729 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A3219-2018 | 1344 | 4980 | Solar | 21C8 | 2018-01-18 | 2018-01-31 | 10 | 1 | 9 | 2018-02-01 | 2018-05-03 | 63 | 43 | 20 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-08-03 | 64 | 8 | 56 | [5 empty] | 2018-08-10 |  | Summer 2018 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-11-25 | Online
WMECO | Deerfield | 6A3221-2018 | 1373 | 1000 | Solar | 22B3 | 2018-01-18 | 2018-01-30 | 9 | 3 | 6 | 2018-01-31 | 2018-02-06 | 5 |  | 5 | [7 empty] | 0 | [14 empty] | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Peru | 6B1762-2018 | 1235 | 3320 | Solar | 18C2 | 2018-01-18 | 2018-01-30 | 9 | 2 | 7 | 2018-01-31 | 2018-03-09 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2018-03-12 | 2018-05-11 | 43 | 0 | 43 | 2018-05-16 |  | -30802 |  |  | 2018-05-18 |  | Q4 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-11-18 | Online
WMECO | Northfield | 6A3238-2018 | 1360 | 5000 | Solar | 21B8 | 2018-01-30 | 2018-02-21 | 16 | 7 | 9 | 2018-02-22 | 2018-10-26 | 171 | 165 | 6 | [7 empty] | 0 |  |  | 2018-10-29 |  | -30916 |  |  |  |  | 0 |  |  | 2018-11-30 |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1777-2018 | 1270 | 20 | Solar | 18C1 | 2018-01-31 | 2018-02-08 | 7 | 5 | 2 | 2018-02-09 | 2018-04-17 | 45 | 24 | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-17 |  | 2018-03-15 |  | Expedited |  |  |  | 0 |  |  | 2018-06-12 | 2018-06-15 | 2018-06-18 | Online
WMECO | Leverett | 6A3271-2018 | 1054 | 3120 | Solar | 18G7 | 2018-02-09 | 2018-02-21 | 8 | 6 | 2 | 2018-02-22 | 2018-04-04 | 29 | 28 | 1 | [7 empty] | 0 |  |  | 2018-04-05 | 2018-05-24 | 35 | 0 | 35 |  |  | 0 |  |  | 2018-06-28 |  | 2018-12-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1787-2018 | 1201 | 2574 | Solar | 30B2 | 2018-02-09 | 2018-03-05 | 16 | 4 | 12 | 2018-03-06 | 2018-03-14 | 7 |  | 7 | [7 empty] | 0 |  |  | 2019-04-05 | 2019-11-22 | 160 |  | 160 |  |  | 0 |  |  | 2020-03-23 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3277-2018 | 1360 | 3575 | Solar | 21B8 | 2018-02-12 | 2018-03-09 | 19 | 12 | 7 | 2018-03-12 | 2018-03-19 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-03-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3279-2018 | 1093 | 5225 | Solar | 18G8 | 2018-02-12 | 2018-02-22 | 8 | 0 | 8 | 2018-02-23 | 2018-05-10 | 53 | 46 | 7 | [7 empty] | 0 |  |  | 2018-05-11 | 2018-10-11 | 106 |  | 106 |  |  | 0 |  |  |  |  | 2018-08-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3280-2018 | 1337 | 1410 | Solar | 21C1 | 2018-02-12 | 2018-02-22 | 8 | 0 | 8 | 2018-02-23 | 2018-05-11 | 54 | 48 | 6 | [7 empty] | 0 |  |  | 2018-05-14 | 2018-11-14 | 128 |  | 128 |  |  | 0 |  |  | 2018-11-28 |  | 2018-08-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2022-10-31 | Online
WMECO | Westhampton | 6A3288-2018 | 1027 | 22.8 | Solar | 15A3 | 2018-02-14 | 2018-02-22 | 6 | 4 | 2 | 2018-02-23 | 2018-03-05 | 7 | 3 | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-03-07 |  | 2018-03-15 |  | Expedited |  |  |  | 0 |  |  | 2018-05-30 | 2018-06-13 | 2018-06-13 | Online
WMECO | Whately | 6A3295-2018 | 1093 | 1000 | Solar | 18G8 | 2018-02-16 | 2018-02-22 | 4 | 3 | 1 | 2018-02-23 | 2018-07-31 | 109 | 105 | 4 | [7 empty] | 0 |  |  | 2018-08-01 | 2018-11-18 | 75 |  | 75 |  |  | 0 |  |  |  |  | 2018-12-31 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1793-2018 | 1008 | 4998 | Solar | 19J4 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-03-08 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S4145-2018 | 1089 | 19.3 | Solar | 16C14 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-03-06 | 8 | 4 | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-03-07 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4152-2018 | 1056 | 4998 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-06-20 | 81 | 67 | 14 | [7 empty] | 0 |  |  | 2018-06-21 | 2018-10-02 | 72 |  | 72 |  |  | 0 |  |  | 2018-11-12 |  | 2019-10-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-12-16 | Online
WMECO | Ludlow | 6S4153-2018 | 1056 | 5000 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 |  | -30746 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3297-2018 | 1373 | 1925 | Solar | 18G8 | 2018-02-20 | 2018-03-09 | 14 | 9 | 5 | 2018-03-12 | 2018-03-15 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cheshire | 6B1794-2018 | 1225 | 1650 | Solar | 19A5 | 2018-02-20 | 2018-03-05 | 10 | 7 | 3 | 2018-03-06 |  | -30753 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1795-2018 | 1235 | 2200 | Solar | 18C2 | 2018-02-22 | 2018-03-14 | 15 | 11 | 4 | 2018-03-15 |  | -30760 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3302-2018 | 1337 | 4160 | Solar | 21C1 | 2018-02-23 | 2018-03-14 | 14 | 10 | 4 | 2018-03-15 | 2018-03-16 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1798-2018 | 1201 | 3250 | Solar | 30B5 | 2018-02-26 | 2018-03-28 | 22 | 19 | 3 | 2018-03-29 | 2018-05-14 | 32 | 17 | 15 | [7 empty] | 0 |  |  | 2018-05-15 | 2018-10-23 | 112 | 37 | 75 |  |  | 0 |  |  | 2018-11-23 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4177-2018 | 1077 | 248 | Solar | 29A1 | 2018-02-28 | 2018-03-29 | 21 | 19 | 2 | 2018-04-02 | 2018-04-23 | 15 | 4 | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-23 |  | 5/2018 |  | Expedited |  |  |  | 0 |  |  | 2018-10-02 | 2018-10-02 | 2018-10-02 | Online
WMECO | Amherst | 6A3310-2018 | 1002 | 32.95 | Solar | 17K3 | 2018-03-01 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | March 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3312-2018 | 1002 | 99.9 | Solar | 17K5 | 2018-03-02 | 2018-03-14 | 9 | 8 | 1 | 2018-03-15 | 2018-08-06 | 99 | 48 | 51 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-08-06 |  | 2018-06-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-01-10 | Online
WMECO | Shelburne Falls | 6A3316-2018 | 1370 | 900 | Solar | 22B5 | 2018-03-05 | 2018-06-20 | 75 | 72 | 3 | 2018-06-21 | 2018-06-21 | 1 |  | 1 | [7 empty] | 0 |  |  | 2018-10-09 | 2019-03-13 | 105 |  | 105 |  |  | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A3317-2018 | 1050 | 900 | Solar | 19J5 | 2018-03-05 | 2018-06-20 | 75 | 72 | 3 | 2018-06-21 | 2018-06-26 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A3322-2018 | 1027 | 2500 | Solar | 15A3 | 2018-03-06 | 2018-04-18 | 30 | 23 | 7 | 2018-04-19 | 2018-10-19 | 128 | 126 | 2 | [7 empty] | 0 |  |  | 2018-10-19 | 2018-12-18 | 41 |  | 41 |  |  | 0 |  |  | 2019-01-27 |  | 2019-04-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4201-2018 | 1118 | 15.68 | Solar | 20A32 | 2018-03-13 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-04-05 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3340-2018 | 1070 | 495 | Solar | 19J5 | 2018-03-14 | 2018-06-13 | 63 | 55 | 8 | 2018-06-14 | 2018-06-22 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6A3341-2018 | 1373 | 2000 | Solar | 18G8 | 2018-03-15 | 2018-03-28 | 9 | 4 | 5 | 2018-03-29 |  | -30769 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6A3350-2018 | 1341 | 4400 | Solar | 38A1 | 2018-03-16 | 2018-04-18 | 22 | 17 | 5 | 2018-04-19 | 2018-05-11 | 17 | 11 | 6 | [7 empty] | 0 |  |  | 2018-05-14 | 2018-09-25 | 94 |  | 94 |  |  | 0 |  |  | 2019-02-22 |  | 2018-12-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-07-28 | Online
WMECO | Pittsfield | 6B1811-2018 | 1201 | 4890 | Solar | 30B5 | 2018-03-16 | 2018-04-06 | 15 | 9 | 6 | 2018-04-09 | 2018-08-03 | 82 | 17 | 65 | [7 empty] | 0 |  |  | 2018-08-06 | 2018-11-16 | 72 |  | 72 |  |  | 0 |  |  |  |  | 2018-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1817-2018 | 1201 | 187 | Solar | 30B5 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-27 | 17 | 15 | 2 | 2018-04-30 | 2018-07-20 | 58 | 22 | 36 |  |  | 0 | [9 empty] | 0 |  |  | 2018-09-17 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Pittsfield | 6B1818-2018 | 1201 | 191 | Solar | 30B4 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-13 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1819-2018 | 1201 | 249 | Solar | 30B7 | 2018-03-21 | 2018-04-04 | 11 | 5 | 6 | 2018-04-05 | 2018-05-24 | 35 | 22 | 13 | 2018-05-25 | 2018-09-17 | 79 |  | 79 |  |  | 0 | [9 empty] | 0 |  |  | 2018-10-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-14 | Online
WMECO | Dalton | 6B1825-2018 | 1226 | 4400 | Solar | 18C1 | 2018-03-21 | 2018-04-19 | 21 | 18 | 3 | 2018-04-20 | 2018-08-03 | 74 | 48 | 26 | [7 empty] | 0 |  |  | 2018-08-06 | 2018-11-29 | 80 |  | 80 |  |  | 0 |  |  | 2018-11-30 |  | 2018-12-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-05-25 | Online
WMECO | Springfield | 6S4229-2018 | 1119 | 14.4 | Solar | 20A35 | 2018-03-21 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-04-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1824-2018 | 1201 | 480 | Solar | 30B5 | 2018-03-22 | 2018-04-03 | 9 | 2 | 7 | 2018-04-04 | 2021-04-23 | 758 |  | 758 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Richmond | 6B1826-2018 | 1254 | 97.75 | Solar | 30B7 | 2018-03-22 | 2018-03-29 | 6 | 1 | 5 | 2018-04-02 | 2018-04-20 | 14 | 6 | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-20 |  | 6/2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-08-28 | Online
WMECO | Pittsfield | 6B1831-2018 | 1201 | 350 | Solar | 19A5 | 2018-03-26 | 2018-07-03 | 70 | 60 | 10 | 2018-07-05 | 2019-07-01 | 246 |  | 246 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4247-2018 | 1034 | 4455 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-06-11 | 41 | 32 | 9 | [7 empty] | 0 |  |  | 2018-06-12 | 2018-10-29 | 97 |  | 97 |  |  | 0 |  |  | 2018-11-06 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2022-05-31 | Online
WMECO | Granville | 6S4248-2018 | 1034 | 996 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-10-29 | 138 |  | 138 | [7 empty] | 0 |  |  | 2018-10-29 | 2019-02-14 | 73 |  | 73 |  |  | 0 |  |  | 2019-04-19 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A3370-2018 | 1543 | 4890 | Solar | 17K2 | 2018-03-28 | 2019-02-05 | 214 |  | 214 | 2019-02-05 | 2019-03-22 | 32 |  | 32 | [7 empty] | 0 |  |  | 2019-10-16 | 2020-01-07 | 55 |  | 55 |  |  | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A3396-2018 | 1070 | 4998 | Solar | 18K3 | 2018-04-06 | 2018-07-05 | 62 | 60 | 2 | 2018-07-06 | 2018-07-30 | 17 |  | 17 | [7 empty] | 0 |  |  | 2019-01-18 | 2019-04-25 | 66 |  | 66 |  |  | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1847-2018 | 1235 | 4998 | Solar | 18C2 | 2018-04-09 | 2018-05-07 | 20 | 15 | 5 | 2018-05-08 |  | -30796 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4298-2018 | 1104 | 500 | Solar | 21S6 | 2018-04-09 | 2018-05-02 | 17 | 14 | 3 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | 2018-05-17 | 2018-06-07 | 15 |  | 15 |  |  | 0 |  |  | 2018-05-16 |  | -30802 |  |  |  |  | 0 |  |  | 2018-11-26 |  | 2018-06-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4299-2018 | 1001 | 576.6 | Solar | 16C16 | 2018-04-09 | 2018-05-02 | 17 | 14 | 3 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | [7 empty] | 0 |  |  | 2018-05-16 | 2018-09-29 | 95 |  | 95 |  |  | 0 |  |  |  |  | 2018-06-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1854-2018 | 1253 | 1375 | Solar | 19J4 | 2018-04-16 | 2018-05-07 | 15 | 5 | 10 | 2018-05-08 | 2018-05-10 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | April 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3441-2018 | 1360 | 4988 | Solar | 21B8 | 2018-04-23 | 2018-05-14 | 16 | 6 | 10 | 2019-02-06 |  | -30982 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1868-2018 | 1237 | 15.12 | Solar | 15E2 | 2018-04-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-21 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4359-2018 | 1129 | 12.32 | Solar | 20A34 | 2018-04-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4367-2018 | 1104 | 800 | Solar | 5J15 | 2018-05-01 | 2018-06-05 | 25 | 17 | 8 | 2018-06-06 | 2018-07-18 | 30 |  | 30 | [7 empty] | 0 |  |  | 2018-09-26 | 2018-11-19 | 37 |  | 37 |  |  | 0 |  |  | 2018-11-21 |  | 2018-08-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2022-08-16 | Online
WMECO | Gill | 6A3473-2018 | 1354 | 132 | Solar | 21B8 | 2018-05-07 | 2018-06-11 | 25 | 20 | 5 | 2018-06-12 | 2018-06-19 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A3474-2018 | 1354 | 2310 | Solar | 21B8 | 2018-05-08 | 2018-05-29 | 15 | 9 | 6 | 2018-05-30 | 2018-05-31 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A3478-2018 | 1070 | 990 | Solar | 18K3 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A3480-2018 | 1050 | 900 | Solar | 29R2 | 2018-05-09 | 2018-06-21 | 31 | 23 | 8 | 2018-06-22 | 2018-08-01 | 28 |  | 28 | [7 empty] | 0 |  |  | 2018-12-04 | 2019-05-17 | 112 |  | 112 |  |  | 0 |  |  | 2019-06-26 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1875-2018 | 1237 | 990 | Solar | 15E2 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-05 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4395-2018 | 1034 | 990 | Solar | 29A5 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1876-2018 | 1270 | 990 | Solar | 18C1 | 2018-05-10 | 2018-06-20 | 29 | 21 | 8 | 2018-06-21 | 2018-07-23 | 22 |  | 22 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A3483-2018 | 1038 | 249.8 | Solar | 18G5 | 2018-05-14 | 2018-06-06 | 17 | 5 | 12 | 2018-06-07 | 2018-08-15 | 49 |  | 49 | [7 empty] | 0 |  |  | 2018-12-02 | 2018-12-03 | 1 |  | 1 |  |  | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3484-2018 | 1035 | 499.9 | Solar | 17K5 | 2018-05-14 | 2018-06-06 | 17 | 6 | 11 | 2018-06-07 | 2018-08-06 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4407-2018 | 1107 | 240 | Solar | 21S6 | 2018-05-14 | 2018-05-31 | 13 | 5 | 8 | 2018-06-01 | 2018-06-14 | 10 | 8 | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-06-28 |  | 2018-08-17 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-12-12 | Online
WMECO | Springfield | 6S4409-2018 | 1104 | 199.8 | Solar | 5J13 | 2018-05-14 | 2018-06-13 | 22 | 14 | 8 | 2018-06-14 | 2018-10-23 | 91 |  | 91 | 2018-10-24 |  | -30913 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-27 |  | 2018-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-04 | Online
WMECO | Conway | 6A3492-2018 | 1341 | 900 | Solar | 38A1 | 2018-05-15 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2018-07-06 | 11 |  | 11 | [7 empty] | 0 |  |  | 2018-12-04 | 2019-05-17 | 112 |  | 112 |  |  | 0 |  |  | 2019-06-13 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A3493-2018 | 1098 | 990 | Solar | 18K3 | 2018-05-15 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2018-07-06 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1881-2018 | 1201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 91 | 0 | 91 | 2018-09-21 | 2018-11-19 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1882-2018 | 1201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 91 | 0 | 91 | 2018-09-21 | 2018-11-19 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A3497-2018 | 1370 | 990 | Solar | 22B5 | 2018-05-16 | 2018-06-20 | 25 | 21 | 4 | 2018-06-21 | 2019-03-29 | 191 |  | 191 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A3498-2018 | 1098 | 990 | Solar | 18K3 | 2018-05-16 | 2018-06-20 | 25 | 21 | 4 | 2018-06-21 | 2018-07-27 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1887-2018 | 1238 | 480 | Solar | 16B1 | 2018-05-17 | 2018-09-19 | 87 | 0 | 87 | 2018-09-19 | 2018-11-05 | 33 |  | 33 | [7 empty] | 0 |  |  | 2018-11-14 |  | -30927 |  |  |  |  | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4424-2018 | 1119 | 19.2 | Solar | 20A33 | 2018-05-17 | 2018-11-08 | 122 |  | 122 | 2018-11-08 |  | -30924 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-07-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3509-2018 | 1330 | 4980 | Solar | 38A1 | 2018-05-21 | 2018-06-21 | 23 | 19 | 4 | 2018-06-22 | 2018-07-31 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A3510-2018 | 1050 | 4980 | Solar | 19J5 | 2018-05-21 | 2018-06-21 | 23 | 19 | 4 | 2018-06-22 | 2018-07-31 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3512-2018 | 1342 | 2000 | Solar | 22B3 | 2018-05-22 | 2018-06-05 | 10 | 9 | 1 | 2018-06-06 | 2018-07-16 | 28 | 17 | 11 | [7 empty] | 0 |  |  | 2018-07-17 | 2018-11-02 | 77 |  | 77 |  |  | 0 |  |  | 2018-11-29 |  | 2019-01-31 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-09-20 | Online
WMECO | Granville | 6S4443-2018 | 1034 | 4980 | Solar | 29A5 | 2018-05-23 | 2018-06-21 | 21 | 17 | 4 | 2018-06-22 | 2018-07-30 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3523-2018 | 1342 | 72 | Solar | 22B1 | 2018-05-24 | 2018-06-20 | 19 | 13 | 6 | 2018-06-21 | 2018-07-16 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-08-30 |  | 2018-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-10-02 | Online
WMECO | Springfield | 6S4457-2018 | 1104 | 975 | Solar | 5J9 | 2018-05-25 | 2018-06-11 | 11 | 8 | 3 | 2018-06-12 | 2018-09-20 | 71 |  | 71 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-02-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4459-2018 | 1129 | 333.3 | Solar | 20A23 | 2018-05-25 | 2018-06-20 | 18 | 5 | 13 | 2018-06-21 | 2018-06-22 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-07 |  | 2018-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A3534-2018 | 1073 | 5000 | Solar | 15A1 | 2018-05-30 | 2018-08-02 | 46 | 39 | 7 | 2018-08-03 | 2018-09-11 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1906-2018 | 1201 | 2656 | Solar | 30B2 | 2018-05-30 | 2018-07-31 | 44 | 34 | 10 | 2018-08-01 | 2020-03-18 | 403 |  | 403 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1907-2018 | 1008 | 4980 | Solar | 19J2 | 2018-05-30 | 2018-09-12 | 74 | 49 | 25 | 2018-09-13 |  | -30885 | [9 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4467-2018 | 1104 | 210 | Solar | 21S7 | 2018-05-31 | 2018-06-27 | 20 | 3 | 17 | 2018-06-28 | 2018-08-08 | 29 |  | 29 | 2018-11-13 | 2018-11-20 | 6 |  | 6 |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-21 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4468-2018 | 1034 | 594 | Solar | 29A5 | 2018-05-31 | 2018-06-25 | 18 | 14 | 4 | 2018-06-26 | 2018-07-31 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4469-2018 | 1034 | 1992 | Solar | 29A5 | 2018-05-31 | 2018-07-31 | 43 | 33 | 10 | 2018-08-01 | 2018-08-20 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A3550-2018 | 1344 | 2000 | Solar | 21C5 | 2018-06-05 | 2018-06-28 | 18 | 14 | 4 | 2018-06-29 | 2018-08-01 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A3553-2018 | 1027 | 27 | Solar | 15A3 | 2018-06-07 | 2018-06-20 | 10 | 2 | 8 | 2018-06-21 |  | -30827 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4501-2018 | 1104 | 999 | Solar | 5J13 | 2018-06-07 | 2018-07-12 | 25 | 17 | 8 | 2018-07-13 | 2018-08-24 | 31 |  | 31 | [7 empty] | 0 |  |  | 2018-12-31 | 2019-05-16 | 94 |  | 94 |  |  | 0 |  |  | 2019-12-20 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2024-07-23 | Online
WMECO | Amherst | 6A3567-2018 | 1002 | 433.3 | Solar | 17K8 | 2018-06-12 | 2018-06-20 | 7 | 0 | 7 | 2018-06-21 | 2018-09-18 | 62 |  | 62 | 2018-09-19 | 2018-11-02 | 32 |  | 32 |  |  | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  | 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4517-2018 | 1105 | 2500 | Diesel | 8CNW_1 | 2018-06-14 | 2019-02-05 | 160 | 158 | 2 | 2019-02-05 | 2020-01-14 | 234 |  | 234 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2023-06-14 |  | 2012 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Hadley | 6A3587-2018 | 1035 | 133.2 | Solar | 17K5 | 2018-06-20 | 2018-08-01 | 30 | 24 | 6 | 2018-08-02 | 2018-09-05 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-12-07 |  | September 2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-04-25 | Online
WMECO | Lee | 6B1926-2018 | 1238 | 2000 | Solar | 17G3 | 2018-06-20 | 2018-07-16 | 18 | 6 | 12 | 2018-07-17 | 2018-08-27 | 30 |  | 30 | [7 empty] | 0 |  |  | 2018-11-23 | 2019-12-10 | 260 |  | 260 |  |  | 0 |  |  | 2020-03-24 |  | 2019-01-20 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3593-2018 | 1002 | 2000 | Battery | 18G7 | 2018-06-22 | 2019-01-17 | 142 |  | 142 | 2019-01-17 | 2019-05-31 | 92 |  | 92 | [7 empty] | 0 |  |  | 2019-06-10 | 2019-07-31 | 37 |  | 37 |  |  | 0 |  |  | 2019-09-04 |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Blandford | 6B1932-2018 | 1008 | 4450 | Solar | 19J2 | 2018-06-26 | 2018-08-01 | 26 | 13 | 13 | 2018-08-02 | 2018-10-10 | 48 |  | 48 | [7 empty] | 0 |  |  | 2019-02-07 | 2019-07-19 | 112 |  | 112 |  |  | 0 |  |  | 2019-08-05 |  | 2019-09-30 |  | Complex |  |  |  | 0 | [5 empty] | customer hold
WMECO | Longmeadow | 6S4578-2018 | 1106 | 600 | Diesel | 22H12 | 2018-06-28 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-10-26 | Online
WMECO | Pittsfield | 6B1937-2018 | 1201 | 1850 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 23 | 19 | 4 | 2018-08-02 |  | -30856 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1938-2018 | 1201 | 4998 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 23 | 18 | 5 | 2018-08-02 | 2018-08-29 | 20 |  | 20 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A3610-2018 | 1340 | 3300 | Solar | 29R2 | 2018-07-03 | 2018-07-17 | 10 | 4 | 6 | 2018-07-18 | 2018-08-15 | 21 |  | 21 | [7 empty] | 0 |  |  | 2019-08-13 |  | -31111 |  |  |  |  | 0 |  |  |  |  | 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4596-2018 | 1034 | 40 | Solar | 29A5 | 2018-07-03 | 2018-07-24 | 15 | 6 | 9 | 2018-07-25 | 2018-10-22 | 62 |  | 62 | 2018-10-22 |  | -30911 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-29 |  | 2018-08-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-11-24 | Online
WMECO | Greenfield | 6A3611-2018 | 1301 | 4998 | Solar | 22B7 | 2018-07-05 | 2018-07-24 | 14 | 7 | 7 | 2018-07-25 |  | -30850 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q2 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A3612-2018 | 1373 | 4998 | Solar | 18G6 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-28 | 25 |  | 25 | [7 empty] | 0 |  |  | 2018-11-20 | 2019-04-16 | 98 |  | 98 |  |  | 0 |  |  | 2019-05-15 |  | Q2 2019 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3615-2018 | 1337 | 180 | Solar | 21C1 | 2018-07-05 | 2018-08-01 | 20 | 17 | 3 | 2018-08-02 | 2018-09-05 | 24 |  | 24 |  | 2019-10-09 | [5 empty] | 0 | [9 empty] | 0 |  |  | 2019-10-09 |  | 2018-12-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-22 | Online
WMECO | Tolland | 6B1941-2018 | 1034 | 4998 | Solar | 19J4 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-15 | 16 |  | 16 | [7 empty] | 0 |  |  | 2019-05-07 |  | -31043 |  |  |  |  | 0 |  |  |  |  | Q2 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4610-2018 | 1056 | 14.08 | Solar | 19S1 | 2018-07-06 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3626-2018 | 1035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 58 |  | 58 | 2018-09-28 | 2019-04-18 | 135 |  | 135 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3627-2018 | 1035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 58 |  | 58 | 2018-10-02 | 2018-10-31 | 21 |  | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3631-2018 | 1071 | 13.688 | Solar | 19J2 | 2018-07-11 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S4648-2018 | 1030 | 15.36 | Solar | 16C17 | 2018-07-13 | 2018-10-18 | 68 | 31 | 37 | 2018-10-18 | 2019-01-17 | 61 |  | 61 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-28 |  | 2018-09-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-19 | Online
WMECO | Gill | 6A3641-2018 | 1354 | 4950 | Solar | 21C5 | 2018-07-17 | 2018-08-02 | 13 | 0 | 13 | 2018-08-03 | 2018-09-10 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-02-25 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4645-2018 | 1108 | 37.6 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-08-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-05-03 | Online
WMECO | Springfield | 6S4646-2018 | 1108 | 37.9 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-20 |  | 2018-08-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-05-03 | Online
WMECO | Russell | 6A3655-2018 | 1071 | 13.928 | Solar | 19J2 | 2018-07-24 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-09-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1959-2018 | 1237 | 4890 | Solar | 15E1 | 2018-07-24 | 2018-08-31 | 29 | 11 | 18 | 2018-09-04 | 2019-04-01 | 141 |  | 141 | [7 empty] | 0 |  |  | 2019-05-30 | 2022-06-13 | 760 |  | 760 |  |  | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4675-2018 | 1001 | 4890 | Solar | 30A3 | 2018-07-24 | 2018-08-13 | 15 | 13 | 2 | 2018-08-14 | 2019-03-29 | 154 |  | 154 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4685-2018 | 1077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 128 |  | 128 | 2019-01-29 | 2019-05-07 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4686-2018 | 1077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 128 |  | 128 | 2019-01-29 | 2019-05-07 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4747-2018 | 1106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-26 | 33 | 0 | 33 | 2018-09-27 |  | -30895 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-08 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4748-2018 | 1104 | 209.8 | Solar | 5J14 | 2018-08-10 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4750-2018 | 1106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-21 | 30 | 0 | 30 | 2018-10-12 | 2018-11-21 | 28 |  | 28 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-25 |  | 2018-11-08 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4751-2018 | 1104 | 209.8 | Solar | 5J14 | 2018-08-10 | 2018-10-12 | 44 | 0 | 44 | 2018-10-12 | 2018-11-20 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4753-2018 | 1001 | 286.4 | Solar | 30A3 | 2018-08-10 | 2018-10-01 | 36 | 0 | 36 | 2018-10-01 | 2018-11-20 | 35 |  | 35 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-25 |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4754-2018 | 1106 | 66.6 | Solar | 22H12 | 2018-08-10 | 2018-10-03 | 38 | 0 | 38 | 2018-10-03 | 2018-11-26 | 36 |  | 36 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-11-06 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-01 | Online
WMECO | Northfield | 6A3710-2018 | 1360 | 4950 | Solar | 21B8 | 2018-08-14 | 2018-09-12 | 21 | 1 | 20 | 2018-09-13 | 2019-08-16 | 230 |  | 230 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-02-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4780-2018 | 1106 | 163.3 | Solar | 22H16 | 2018-08-16 | 2018-10-12 | 40 | 0 | 40 | 2018-10-12 | 2018-11-26 | 30 |  | 30 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-11-12 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3737-2018 | 1071 | 4998 | Solar | 19J2 | 2018-08-21 | 2018-10-29 | 48 |  | 48 | 2018-10-30 | 2019-04-01 | 102 |  | 102 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A3738-2018 | 1344 | 4494.4 | Solar | 21B9 | 2018-08-21 | 2019-01-03 | 91 |  | 91 | 2019-01-03 | 2019-03-28 | 58 |  | 58 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1993-2018 | 1253 | 4998 | Solar | 19J4 | 2018-08-21 | 2018-12-11 | 77 | 71 | 6 | 2018-12-11 | 2019-04-01 | 74 |  | 74 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1994-2018 | 1238 | 120 | Solar | 17G3 | 2018-08-23 | 2018-10-09 | 32 | 0 | 32 | 2018-10-10 | 2019-01-15 | 65 |  | 65 | 2019-03-26 | 2019-04-30 | 25 |  | 25 |  |  | 0 | [9 empty] | 0 |  |  | 2019-05-13 |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1997-2018 | 1201 | 253.1 | Solar | 30B2 | 2018-08-27 | 2018-09-20 | 18 | 0 | 18 | 2018-09-20 | 2018-12-12 | 57 |  | 57 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-25 |  | 2018-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S4816-2018 | 1030 | 250 | Solar | 16C17 | 2018-08-28 | 2018-10-24 | 40 | 0 | 40 | 2018-10-25 | 2018-12-12 | 33 |  | 33 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 11/31/18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2002-2018 | 1201 | 1450 | Solar | 19A5 | 2018-08-29 | 2018-11-28 | 62 | 0 | 62 | 2018-11-28 | 2019-03-05 | 65 |  | 65 | [7 empty] | 0 |  |  | 2019-05-21 | 2019-08-19 | 63 |  | 63 |  |  | 0 |  |  | 2019-08-19 |  | 2018-09-01 |  | Standard |  |  |  | 0 | [5 empty] | customer hold
WMECO | Chesterfield | 6A3750-2018 | 1026 | 3500 | Solar | 18K3 | 2018-08-30 | 2018-09-25 | 18 | 0 | 18 | 2018-09-26 |  | -30894 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 3/15/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4833-2018 | 1056 | 2772 | Solar | 19S1 | 2018-08-31 | 2018-11-28 | 60 | 0 | 60 | 2018-11-28 |  | -30936 | [9 empty] | 0 |  |  | 2019-07-25 | 2020-03-09 | 154 |  | 154 |  |  | 0 |  |  | 2020-03-25 |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Sandisfield | 6B2011-2018 | 1255 | 400 | Solar | 19J4 | 2018-09-06 | 2018-09-21 | 12 | 0 | 12 | 2018-09-24 | 2018-11-25 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4841-2018 | 1104 | 450 | Solar | 5J9 | 2018-09-06 | 2018-11-29 | 58 | 0 | 58 | 2018-11-29 | 2018-12-12 | 10 |  | 10 | [7 empty] | 0 |  |  | 2018-12-18 | 2018-12-19 | 2 |  | 2 |  |  | 0 |  |  |  |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4842-2018 | 1001 | 580 | Solar | 16C16 | 2018-09-10 | 2018-10-09 | 21 | 0 | 21 | 2018-10-10 | 2020-08-06 | 453 |  | 453 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-29 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3767-2018 | 1330 | 4450 | Solar | 38A1 | 2018-09-11 | 2018-11-30 | 56 | 0 | 56 | 2018-12-03 | 2019-02-22 | 55 |  | 55 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 10/1/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4890-2018 | 1106 | 16.24 | Solar | 22H12 | 2018-09-19 | 2018-10-24 | 25 | 0 | 25 | 2018-10-25 | 2018-11-21 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-23 |  | 2018-09-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-11-26 | Online
WMECO | Agawam | 6S4959-2018 | 1001 | 366.3 | Solar | 30A3 | 2018-10-05 | 2018-10-30 | 17 |  | 17 | 2018-10-31 | 2019-01-17 | 52 |  | 52 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-30 |  | 2018-11-26 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3820-2018 | 1071 | 5000 | Solar | 19J2 | 2018-10-08 | 2018-12-19 | 50 |  | 50 | 2018-12-19 | 2019-05-07 | 93 |  | 93 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2036-2018 | 1201 | 1000 | Solar | 30B3 | 2018-10-12 | 2019-01-14 | 62 |  | 62 | 2019-01-14 | 2019-02-04 | 15 |  | 15 | [7 empty] | 0 |  |  | 2019-12-09 | 2020-03-13 | 65 |  | 65 |  |  | 0 |  |  | 2020-04-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3840-2018 | 1002 | 250 | Solar | 19B16 | 2018-10-15 | 2018-11-06 | 17 |  | 17 | 2018-11-06 | 2019-01-10 | 43 |  | 43 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3841-2018 | 1002 | 1000 | Solar | 19B16 | 2018-10-15 | 2018-11-20 | 26 |  | 26 | 2018-11-20 | 2019-01-28 | 45 |  | 45 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4998-2018 | 1077 | 18872 | Solar | 29A5 | 2018-10-18 | [16 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S5004-2018 | 1077 | 150 | Solar | 29A5 | 2018-10-22 | 2018-10-24 | 3 | 0 | 3 | 2018-10-25 | 2019-01-11 | 52 |  | 52 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5005-2018 | 1108 | 99.9 | Solar | 21S12 | 2018-10-22 | 2018-10-25 | 4 | 0 | 4 | 2018-10-26 |  | -30915 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2044-2018 | 1008 | 18872 | Solar | 19J2 | 2018-10-23 | 2019-01-14 | 55 |  | 55 | 2019-01-14 | 2019-02-13 | 22 |  | 22 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S5010-2018 | 1077 | 4400 | Solar | 29A5 | 2018-10-23 | 2019-02-07 | 72 |  | 72 | 2019-02-07 | 2019-03-28 | 34 |  | 34 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3861-2018 | 1373 | 4885 | Solar | 18G6 | 2018-10-26 | 2019-01-14 | 52 |  | 52 | 2019-01-14 | 2019-04-17 | 64 |  | 64 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3868-2018 | 1373 | 999 | Solar | 18G8 | 2018-10-30 | 2019-01-17 | 53 | 50 | 3 | 2019-01-17 | 2019-03-29 | 49 |  | 49 | [7 empty] | 0 |  |  |  | 2023-11-09 | [5 empty] | 0 |  |  | 2023-11-10 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Ludlow | 6S5036-2018 | 1056 | 5550 | Solar | 19S1 | 2018-10-30 | 2019-01-17 | 53 |  | 53 | 2019-01-17 | 2019-03-22 | 44 |  | 44 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3871-2018 | 1002 | 36.496 | Solar | 17K4 | 2018-11-01 | 2018-11-05 | 3 |  | 3 | 2018-11-05 | 2019-01-29 | 56 |  | 56 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A3880-2018 | 1073 | 3180 | solar | 15A1 | 2018-11-02 | 2019-01-30 | 58 |  | 58 | 2019-01-30 | 2019-03-29 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne Falls | 6A3884-2018 | 1370 | 250 | Solar | 29R2 | 2018-11-05 | 2018-12-06 | 22 |  | 22 | 2018-12-06 | 2018-12-19 | 10 |  | 10 | 2019-10-25 | 2019-11-22 | 20 |  | 20 |  |  | 0 | [9 empty] | 0 |  |  | 2019-11-26 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-07-21 | Online
WMECO | Ludlow | 6S5054-2018 | 1056 | 4400 | Solar | 19S3 | 2018-11-05 | 2018-12-06 | 22 |  | 22 | 2018-12-06 | 2019-01-03 | 18 |  | 18 | [7 empty] | 0 |  |  | 2019-03-05 | 2019-07-25 | 99 |  | 99 |  |  | 0 |  |  | 2020-03-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6A3888-2018 | 1235 | 39600 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 | 2019-03-22 | 46 |  | 46 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6A3889-2018 | 1235 | 14400 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 |  | -30967 | [9 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2053-2018 | 1201 | 4347.65 | Solar | 15E2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 | 2019-02-13 | 21 |  | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3896-2018 | 1360 | 2104 | Solar | 21B8 | 2018-11-13 | 2019-03-19 | 84 |  | 84 | 2019-03-19 | 2019-03-28 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3901-2018 | 1035 | 518.4 | Solar | 17K5 | 2018-11-15 | 2018-12-06 | 15 |  | 15 | 2018-12-06 | 2018-12-26 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3916-2018 | 1002 | 3000 | Battery | 18G4 | 2018-11-19 | 2019-02-04 | 51 |  | 51 | 2019-02-04 | 2019-05-08 | 65 |  | 65 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2020-03-26 |  | 4/5/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-01-09 | Online
WMECO | Springfield | 6S5117-2018 | 1103 | 32.83 | Solar | 8CNW_1 | 2018-11-20 | 2019-01-18 | 40 |  | 40 | 2019-01-18 | 2019-04-10 | 56 |  | 56 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5103-2018 | 1104 | 532.8 | Solar | 5J9 | 2018-11-21 | 2018-11-26 | 3 |  | 3 | 2018-11-26 | 2019-01-17 | 36 |  | 36 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Nov 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2062-2018 | 1201 | 463.01 | Solar | 19A5 | 2018-11-26 | 2019-01-24 | 40 |  | 40 | 2019-01-24 |  | -30973 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3912-2018 | 1373 | 15.78 | Solar | 22B1 | 2018-11-28 | 2018-12-03 | 4 |  | 4 | 2018-12-03 | 2018-12-24 | 15 |  | 15 | [7 empty] | 0 |  |  | 2018-12-03 |  | -30939 |  |  |  |  | 0 |  |  | 2019-03-08 |  | 12/2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-17 | Online
WMECO | Agawam | 6S5118-2018 | 1001 | 4950 | Solar | 16C16 | 2018-11-30 | 2019-01-15 | 30 |  | 30 | 2019-01-28 | 2019-03-28 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3920-2018 | 1002 | 2500 | Solar | 17K2 | 2018-12-04 | 2019-01-24 | 34 |  | 34 | 2019-01-24 | 2019-03-22 | 40 |  | 40 | [7 empty] | 0 |  |  | 2019-04-24 | 2019-11-27 | 151 |  | 151 |  |  | 0 |  |  | 2020-03-27 |  | 10/1/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-08-23 | Online
WMECO | Lanesborough | 6B2072-2018 | 1237 | 4540 | Solar | 15E1 | 2018-12-11 | 2019-01-15 | 23 |  | 23 | 2019-01-15 | 2019-03-22 | 46 |  | 46 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Fall 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5140-2018 | 1109 | 24 | Solar | 5J17 | 2018-12-11 | 2019-01-17 | 25 |  | 25 | 2019-01-17 | 2019-04-02 | 51 |  | 51 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-03-18 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-16 | Online
WMECO | Greenfield | 6A3934-2018 | 1301 | 41.47 | Solar | 22B2 | 2018-12-14 | 2019-01-31 | 31 |  | 31 | 2019-01-31 | 2019-03-22 | 35 |  | 35 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3935-2018 | 1301 | 96 | Solar | 21C4 | 2018-12-14 | 2019-01-23 | 25 |  | 25 | 2019-01-23 | 2019-03-22 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3936-2018 | 1301 | 101.38 | Solar | 22B3 | 2018-12-14 | 2019-02-07 | 36 |  | 36 | 2019-02-07 | 2019-03-22 | 30 |  | 30 | 2019-06-19 |  | -31073 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3937-2018 | 1301 | 36 | Solar | 22B2 | 2018-12-14 | 2019-01-23 | 25 |  | 25 | 2019-01-23 | 2019-03-22 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-06-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3938-2018 | 1301 | 88.13 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 26 |  | 26 | 2019-01-24 | 2019-03-22 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-06-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3939-2018 | 1301 | 194 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 26 |  | 26 | 2019-01-24 | 2019-04-02 | 47 |  | 47 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3949-2018 | 1002 | 3182.224 | Solar | 18G7 | 2018-12-19 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S5163-2018 | 1089 | 228 | Solar | 16C15 | 2018-12-20 | 2019-01-03 | 8 |  | 8 | 2019-01-03 | 2019-01-17 | 11 |  | 11 | [7 empty] | 0 |  |  | 2019-01-03 |  | -30959 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3958-2018 | 1330 | 4998 | Solar | 38A1 | 2018-12-24 | 2019-02-04 | 27 |  | 27 | 2019-02-04 | 2019-03-28 | 37 |  | 37 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A4077-2019 | 1035 | 1000 | Battery | 17K6 | 2019-01-03 | 2019-05-06 | 84 |  | 84 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2019-12-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-05-09 | Online
WMECO | Hadley | 6A4078-2019 | 1035 | 1000 | Battery | 17K1 | 2019-01-03 | 2019-05-06 | 84 |  | 84 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2019-12-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-03-26 | Online
WMECO | Plainfield | 6A3984-2019 | 1070 | 1000 | Battery | 18K3 | 2019-01-22 | 2019-02-07 | 13 |  | 13 | 2019-02-07 | 2019-03-22 | 30 |  | 30 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-16 | 61 |  | 61 |  |  | 0 |  |  | 2020-03-27 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-01-24 | Online
WMECO | Hatfied | 6A4031-2019 | 1038 | 232 | Solar | 18G5 | 2019-02-14 | 2019-03-19 | 22 |  | 22 | 2019-03-19 | 2019-04-02 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-24 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-07-21 | Online
WMECO | Leyden | 6A4033-2019 | 1301 | 4980 | Solar | 22B7 | 2019-02-14 | 2019-02-22 | 6 |  | 6 | 2019-02-22 | 2019-04-18 | 38 |  | 38 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4034-2019 | 1340 | 1980 | Solar | 29R2 | 2019-02-14 | 2019-02-22 | 6 |  | 6 | 2019-02-22 | 2019-03-19 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4045-2019 | 1360 | 3000 | Solar | 21B8 | 2019-02-20 | 2019-04-01 | 28 | 27 | 1 | 2019-04-01 | 2019-04-18 | 13 |  | 13 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Northfield | 6A4048-2019 | 1360 | 2000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 52 | 47 | 5 | 2019-05-06 | 2019-06-07 | 24 |  | 24 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Northfield | 6A4049-2019 | 1360 | 1000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 52 | 42 | 10 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Ashfield | 6A4068-2019 | 1330 | 4950 | Solar |  | 2019-03-06 | 2019-05-08 | 44 |  | 44 | [12 empty] | 0 | [9 empty] | 0 |  |  |  |  | 4/4/2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5364-2019 | 1056 | 212 | Solar | 27A5 | 2019-03-13 | 2019-05-14 | 43 |  | 43 | 2019-05-14 | 2019-06-28 | 33 |  | 33 | 2020-04-15 | 2020-09-16 | 107 |  | 107 |  |  | 0 | [9 empty] | 0 |  |  | 2020-09-16 |  | 2019-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-07-10 | Online
WMECO | Whately | 6A4126-2019 | 1093 | 1000 | Battery | 18G8 | 2019-03-18 | 2019-04-22 | 24 |  | 24 | 2019-04-22 | 2019-05-08 | 13 |  | 13 | [7 empty] | 0 |  |  |  | 2020-01-16 | [5 empty] | 0 |  |  | 2020-03-23 |  | 3/1/2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5370-2019 | 1056 | 136 | Solar | 19S3 | 2019-03-19 | 2019-04-30 | 30 |  | 30 | 2019-04-30 | 2019-05-13 | 10 |  | 10 | 2019-06-04 | 2019-07-30 | 40 |  | 40 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-22 |  | Q3 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5376-2019 | 1001 | 15.08 | Solar | 30A5 | 2019-03-19 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-03-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A4093-2019 | 1342 | 72 | Solar | 22B1 | 2019-03-25 | 2019-05-07 | 31 |  | 31 | 2019-05-07 | 2019-09-05 | 85 |  | 85 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-09-26 |  | 5/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-21 | Online
WMECO | Springfield | 6S5394-2019 | 1104 | 80 | Solar | 5J16 | 2019-03-27 | 2019-04-03 | 6 |  | 6 | 2019-04-03 | 2019-04-11 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | ASAP |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4098-2019 | 1360 | 1000 | Solar | 21B8 | 2019-03-29 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5405-2019 | 1001 | 4990 | Solar | 30A3 | 2019-04-03 | 2019-05-06 | 23 |  | 23 | 2019-05-06 | 2019-05-23 | 14 |  | 14 | [7 empty] | 0 |  |  |  | 2019-06-24 | [5 empty] | 0 |  |  |  |  | Summer 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A4131-2019 | 1342 | 25.3 | Solar | 22B7 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-06-03 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-08-15 |  | 6/12/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-12-11 | Online
WMECO | Lanesborough | 6B2129-2019 | 1237 | 3960 | Solar | 15E1 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2130-2019 | 1237 | 4990 | Solar | 15E2 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2131-2019 | 1237 | 4990 | Solar | 15E1 | 2019-04-17 | 2019-05-06 | 14 |  | 14 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5434-2019 | 1229 | 200 | Solar | 27A13 | 2019-04-17 | 2019-05-08 | 16 |  | 16 | 2019-05-08 | 2019-05-23 | 12 |  | 12 | 2019-09-25 | 2020-06-23 | 184 |  | 184 |  |  | 0 | [9 empty] | 0 |  |  | 2020-06-23 |  | 2020-03-24 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-09-21 | Online
WMECO | Colrain | 6A4169-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 7/30/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4199-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4200-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4201-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A4175-2019 | 1002 | 3778 | Solar | 18G7 | 2019-05-13 | [16 empty] | 0 | [9 empty] | 0 |  |  | 2019-09-11 |  | Oct 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Tolland | 6B2161-2019 | 1034 | 5000 | Solar | 19J4 | 2019-06-11 | 2019-06-20 | 8 | 6 | 2 | 2019-06-20 | 2019-06-21 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Plainfield / Blandford Group Study
WMECO | Whately | 6A4237-2019 | 1093 | 1000 | Solar | 18G8 | 2019-06-13 | 2019-06-20 | 6 |  | 6 | 2019-06-20 | 2019-06-26 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5606-2019 | 1001 | 4975 | Solar | 30A1 | 2019-06-14 | 2019-06-20 | 5 |  | 5 | 2019-06-20 | 2019-06-24 | 3 |  | 3 | [7 empty] | 0 |  |  | 2019-12-02 | 2020-02-19 | 53 |  | 53 |  |  | 0 |  |  | 2020-04-03 |  | 2018-12-14 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-16 | Online
WMECO | Westhampton | 6A4242-2019 | 1027 | 34 | Solar | 15A3 | 2019-06-17 | 2019-09-11 | 61 |  | 61 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | 2019-10-17 | 2020-02-05 | 74 |  | 74 |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-12 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-08-17 | Online
WMECO | Greenfield | 6A4259-2019 | 1301 | 20 | Solar | 21C4 | 2019-06-21 | 2019-08-27 | 47 |  | 47 | 2019-08-27 | 2019-10-11 | 33 |  | 33 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-03 |  | 2019-08-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-16 | Online
WMECO | Turners Falls | 6A4261-2019 | 1376 | 460 | Solar | 21C2 | 2019-06-25 | 2019-06-26 | 2 |  | 2 | 2019-06-26 | 2019-07-01 | 4 |  | 4 | 2019-09-10 | 2019-10-22 | 30 |  | 30 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-24 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A4268-2019 | 1050 | 21.54 | Solar | 19J5 | 2019-06-25 | 2019-09-09 | 53 |  | 53 | 2019-09-09 | 2019-08-14 | -18 |  |  | 2019-09-12 | 2019-10-25 | 31 |  | 31 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-30 |  | Fall 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-08-20 | Online
WMECO | Springfield | 6S5635-2019 | 1102 | 1875 | Diesel | 5J13 | 2019-07-02 | 2019-09-09 | 48 |  | 48 | 2019-09-09 | 2019-12-11 | 65 |  | 65 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-08-11 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-15 | Online
WMECO | Ashfield | 6A4287-2019 | 1330 | 25 | Solar | 22B5 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 |  | -31087 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A4288-2019 | 1370 | 25 | Solar | 38A1 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 | 2019-08-06 | 20 |  | 20 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S5659-2019 | 1089 | 233.3 | Solar | 21N5 | 2019-07-12 | 2019-07-18 | 5 |  | 5 | 2019-07-18 | 2019-07-29 | 8 |  | 8 | 2020-02-19 |  | -31238 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2020-07-01 |  | 2019-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A4306-2019 | 1002 | 4400 | Solar | 17K2 | 2019-07-15 | 2019-09-26 | 53 | 52 | 1 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-06-29 | 391 |  | 391 |  |  | 0 |  |  |  |  | 1/1/21 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Amherst | 6A4309-2019 | 1002 | 4400 | Solar | 17K7 | 2019-07-15 | 2019-09-26 | 53 | 51 | 2 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-05-13 | 358 |  | 358 |  |  | 0 |  |  | 2023-01-20 |  | 2021-01-21 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Easthampton | 6A4329-2019 | 1027 | 1000 | Solar | 15A3 | 2019-07-19 | 2019-07-31 | 9 | 9 | 0 | 2019-07-31 | 2019-08-21 | 16 |  | 16 | [7 empty] | 0 |  |  | 2021-03-01 |  | -31493 |  |  |  |  | 0 |  |  |  |  | 2020-07-10 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6A4414-2019 | 1773 | 25 | Solar | 22B3 | 2019-08-28 | 2019-09-03 | 4 |  | 4 | 2019-09-03 | 2019-09-03 | 1 |  | 1 | 2019-09-24 |  | -31140 |  |  |  |  | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A4433-2019 | 1354 | 17.6 | Solar | 21C5 | 2019-09-03 | 2019-09-06 | 4 |  | 4 | 2019-09-06 | 2019-10-10 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-03 |  | 2019-10-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-03-31 | Online
WMECO | Lanesborough | 6B2239-2019 | 1237 | 34.2 | Solar | 15E1 | 2019-09-03 | 2019-10-02 | 22 |  | 22 | 2019-10-02 | 2019-10-10 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-30 |  | Nov 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A4430-2019 | 1301 | 25 | Solar | 22B4 | 2019-09-05 | 2019-09-13 | 7 |  | 7 | 2019-09-13 | 2019-09-17 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-11-13 |  | Nov 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-02-07 | Online
WMECO | Windsor | 6B2245-2019 | 1270 | 6 | Solar | 18C1 | 2019-09-05 | 2019-10-30 | 39 |  | 39 | 2019-10-31 | 2019-10-31 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5825-2019 | 1128 | 72 | Battery | 20A21 | 2019-09-12 | 2019-10-07 | 18 |  | 18 | 2019-10-07 | 2019-10-15 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-30 |  | 2019-12-30 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-08-27 | Online
WMECO | Northfield | 6A4475-2019 | 1360 | 25 | Solar | 21B8 | 2019-09-20 | 2019-10-01 | 8 |  | 8 | 2019-10-01 | 2019-10-08 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2269-2019 | 1008 | 4998 | Solar | 19J2 | 2019-10-01 | 2019-10-07 | 5 | 3 | 2 | 2019-10-07 | 2019-10-16 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Indian Orchard | 6S5881-2019 | 1151 | 6780 | Solar | 27A11 | 2019-10-01 | 2019-10-01 | 1 |  | 1 | 2019-10-01 | 2020-01-09 | 67 |  | 67 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-04-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5908-2019 | 1056 | 3.8 | Solar | 27A4 | 2019-10-09 | 2019-10-28 | 13 |  | 13 | 2019-10-29 | 2019-11-01 | 4 |  | 4 | 2020-05-19 | 2020-05-20 | 2 |  | 2 |  |  | 0 | [9 empty] | 0 |  |  | 2020-05-21 |  | 2019-11-08 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-15 | Online
WMECO | Amherst | 6A4520-2019 | 1002 | 20 | Solar | 17K8 | 2019-10-10 | 2019-10-15 | 3 |  | 3 | 2019-10-15 | 2019-10-21 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-11-06 |  | Dec 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-02-13 | Online
WMECO | Greenfield | 6A4584-2019 | 1301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 4 |  | 4 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  | 5/2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-30 | Online
WMECO | Greenfield | 6A4585-2019 | 1301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 4 |  | 4 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  | 5/2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-30 | Online
WMECO | Deerfield | 6A4600-2019 | 1373 | 2250 | Solar | 22B1 | 2019-11-14 | 2019-11-20 | 5 | 3 | 2 | 2019-11-20 | 2019-12-02 | 8 |  | 8 | [7 empty] | 0 |  |  | 2021-02-26 | 2023-11-07 | 693 |  | 693 |  |  | 0 |  |  | 2023-11-10 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Pelham | 6A4622-2019 | 1002 | 17.6 | Solar | 17K2 | 2019-11-21 | 2020-01-30 | 46 |  | 46 | 2020-01-30 | 2020-02-04 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-30 |  | 2019-12-17 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-14 | Online
WMECO | Tyringham | 6B2332-2019 | 1264 | 26.25 | Solar | 16B1 | 2019-11-27 | 2019-12-17 | 14 |  | 14 | 2019-12-17 | 2020-01-22 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A4674-2019 | 1301 | 23.4 | Solar | 22B7 | 2019-12-31 | 2020-01-10 | 8 |  | 8 | 2020-01-13 | 2020-01-31 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-24 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A4686-2020 | 1071 | 2750 | Solar | 19J2 | 2020-01-13 | 2020-01-15 | 3 | 2 | 1 | 2020-01-16 | 2020-02-10 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-09-30 |  | Expedited |  |  |  | 0 | [5 empty] | Plainfield / Blandford Group Study
WMECO | Greenfield | 6A4689-2020 | 1301 | 23.4 | Solar | 28WNW_1 | 2020-01-13 | 2020-01-28 | 11 |  | 11 | 2020-01-28 | 2020-01-30 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-06-01 |  | 2020-03-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-08 | Online
WMECO | Windsor | 6B2367-2020 | 1270 | 6 | Solar | 18C1 | 2020-01-16 | 2020-02-28 | 30 |  | 30 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-13 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-01-08 | Online
WMECO | Chesterfield | 6A4702-2020 | 1012 | 17 | Solar | 18K3 | 2020-01-22 | 2020-01-24 | 3 |  | 3 | 2020-01-28 | 2020-01-28 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | March 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A4735-2020 | 1370 | 240 | Solar | 29R2 | 2020-02-19 | 2020-02-26 | 6 |  | 6 | 2020-02-27 | 2020-03-09 | 8 |  | 8 | 2020-04-07 | 2020-07-09 | 65 |  | 65 |  |  | 0 | [9 empty] | 0 |  |  | 2020-07-09 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-10-07 | Online
WMECO | Conway | 6A4737-2020 | 1341 | 17.6 | Solar | 38A1 | 2020-02-19 | 2020-02-28 | 8 |  | 8 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-04-07 |  | 2020-04-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-22 | Online
WMECO | Easthampton | 6A4739-2020 | 1027 | 133 | Solar | 15A3 | 2020-02-21 | 2020-02-28 | 6 |  | 6 | 2020-02-28 | 2020-03-13 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-08-27 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-09-05 | Online
WMECO | Greenfield | 6A4743-2020 | 1301 | 498 | Solar | 22B7 | 2020-02-25 | 2020-03-09 | 10 | 10 | 0 | 2020-03-09 | 2020-03-17 | 6 |  | 6 | 2020-09-15 | 2020-10-30 | 33 |  | 33 |  |  | 0 |  |  | 2021-01-09 | 2022-11-14 | 468 | 109 | 359 |  |  | 0 |  |  | 2023-01-12 |  | 1905-07-12 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Easthampton | 6A4745-2020 | 1027 | 500 | Solar | 15A3 | 2020-02-26 | 2020-02-28 | 3 |  | 3 | 2020-02-28 | 2020-03-17 | 12 |  | 12 | 2020-06-08 | 2020-08-17 | 50 |  | 50 |  |  | 0 | [9 empty] | 0 |  |  | 2020-08-18 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-15 | Online
WMECO | Haldle | 6A4756-2020 | 1035 | 18 | Solar | 18G5 | 2020-02-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4755-2020 | 1360 | 2000 | Solar | 21B8 | 2020-03-02 | 2020-06-24 | 80 | 80 | 0 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 | 2022-12-14 | 532 |  | 532 |  |  | 0 |  |  | 2023-02-27 |  | 2021-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Shelburne Falls | 6A4759-2020 | 1370 | 60 | Solar | 29R2 | 2020-03-03 | 2020-03-09 | 5 |  | 5 | 2020-03-09 | 2020-03-12 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-27 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-01-20 | Online
WMECO | Erving | 6A4764-2020 | 1344 | 43.2 | Solar | 21B8 | 2020-03-09 | 2020-03-11 | 3 |  | 3 | 2020-03-12 | 2020-03-31 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-04 |  | 2020-02-27 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-12-01 | Online
WMECO | Amherst | 6A4781-2020 | 1002 | 17 | Solar | 17K2 | 2020-03-17 | 2020-04-02 | 12 |  | 12 | 2020-04-02 | 2020-04-06 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-28 |  | 2020-04-25 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-15 | Online
WMECO | Springfield | 6S6248-2020 | 1105 | 292 | Solar | 21S4 | 2020-03-18 | 2020-04-21 | 24 |  | 24 | 2020-04-21 | 2020-04-27 | 5 |  | 5 | 2021-01-19 | 2021-02-04 | 12 |  | 12 |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-05-07 | Online
WMECO | Bernardston | 6A4815-2020 | 1337 | 996 | Solar | 21B8 | 2020-04-06 | 2020-11-03 | 147 | 0 | 147 | 2020-11-04 | 2020-11-09 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | July 2021 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Hatfield | 6A4825-2020 | 1038 | 2750 | Solar | 18G6 | 2020-04-13 | 2020-04-15 | 3 | 2 | 1 | 2020-04-16 | 2020-04-22 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-09-30 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Huntington | 6A4832-2020 | 1050 | 20 | Solar | 19J5 | 2020-04-17 | 2020-04-27 | 6 |  | 6 | 2020-04-28 | 2020-05-01 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-12 |  | Not Supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-11 | Online
WMECO | South Deerfield | 6A4834-2020 | 1373 | 10 | Battery | 22B1 | 2020-04-20 | 2020-04-27 | 5 |  | 5 | 2020-04-28 | 2020-05-05 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-15 |  | asap |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-03-10 | Online
WMECO | Northfield | 6A4835-2020 | 1360 | 2250 | Solar | 21B8 | 2020-04-20 | 2020-06-24 | 46 | 45 | 1 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-13 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Northfield | 6A4838-2020 | 1360 | 2000 | Solar | 21B8 | 2020-04-22 | 2020-06-24 | 45 | 43 | 2 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4839-2020 | 1360 | 2000 | Solar | 21B8 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Plainfield | 6A4840-2020 | 1070 | 3300 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 46 |  | 46 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A4841-2020 | 1070 | 3000 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 46 |  | 46 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4842-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-08-06 | 29 |  | 29 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Bernardston | 6A4843-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4844-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4845-2020 | 1337 | 1570 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B2431-2020 | 1223 | 3640 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-23 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-23 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Becket | 6B2432-2020 | 1223 | 7860 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-23 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-23 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Dalton | 6B2451-2020 | 1226 | 16 | Solar | 19A1 | 2020-05-05 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-06-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Tolland | 6B2464-2020 | 1034 | 30.36 | Solar | 19J4 | 2020-05-21 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A4896-2020 | 1002 | 10 | Battery | 17K4 | 2020-06-05 | 2020-07-14 | 27 |  | 27 | 2020-07-15 | 2020-08-19 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-09-28 |  | July 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-22 | Online
WMECO | Tolland | 6B2480-2020 | 1034 | 30.36 | Solar | 19J4 | 2020-06-09 | 2020-08-18 | 50 | 49 | 1 | 2020-08-19 | 2020-09-03 | 12 |  | 12 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-10-21 |  | 2020-08-09 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-16 | Online
WMECO | Springfield | 6S6361-2020 | 1104 | 1669 | Solar | 5J13 | 2020-06-11 | 2020-06-25 | 11 | 11 | 0 | 2020-06-26 | 2020-07-30 | 24 |  | 24 | [7 empty] | 0 |  |  | 2020-12-04 | 2022-09-09 | 445 |  | 445 |  |  | 0 |  |  | 2022-09-19 |  | 2020-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Lee | 6B2503-2020 | 1238 | 4000 | Solar | 16B1 | 2020-06-15 | 2020-07-09 | 18 |  | 18 | 2020-07-10 | 2020-10-15 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4913-2020 | 1337 | 4500 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Greenfield | 6A4914-2020 | 1301 | 1300 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-12-30 | 523 | 18 | 505 |  |  | 0 |  |  | 2023-01-12 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6392-2020 | 1034 | 6750 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6393-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6394-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-09-25 | 54 |  | 54 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6395-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 13 | -1 | 2020-07-13 | 2020-10-05 | 60 |  | 60 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2020-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Dalton | 6B2502-2020 | 1226 | 499 | Solar | 19A3 | 2020-07-06 | 2020-08-05 | 23 | 22 | 1 | 2020-08-05 | 2020-08-14 | 8 | 34 | -26 |  |  |  | 0 |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-12 |  | Dec 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-29 | Online
WMECO | Feeding Hills | 6S6432-2020 | 1030 | 10 | Battery | 30A1 | 2020-07-13 | 2020-08-31 | 36 |  | 36 |  | 2020-09-23 | [10 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-02 |  | summer 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-03-15 | Online
WMECO | Agawam | 6S6455-2020 | 1001 | 50 | Solar | 30A3 | 2020-07-22 | 2020-10-23 | 66 |  | 66 | 2020-10-26 | 2020-11-19 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-12-16 |  | 2020-09-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-05-20 | Online
WMECO | Tyringham | 6B2524-2020 | 1264 | 9.6 | Battery | 16B1 | 2020-07-24 | 2020-08-31 | 27 |  | 27 | 2020-08-31 | 2020-09-09 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-15 |  | Summer 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-08-03 | Online
WMECO | Hatfield | 6A4961-2020 | 1038 | 20 | Solar | 18G6 | 2020-07-28 | 2020-09-09 | 31 |  | 31 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-05 |  | Autumn |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-02-10 | Online
WMECO | Deerfield | 6A4968-2020 | 1342 | 900 | Solar | 22B1 | 2020-08-04 | 2020-09-09 | 26 | 24 | 2 | 2020-09-09 | 2020-09-28 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | April 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6539-2020 | 1034 | 436 | Biogas | 29A5 | 2020-08-17 | 2020-09-16 | 22 | 20 | 2 | 2020-09-16 | 2020-10-21 | 25 |  | 25 | 2020-11-23 | 2021-01-25 | 40 |  | 40 |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-01-15 |  | Expedited |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Springfield | 6S6574-2020 | 1103 | 30 | Diesel | 8C24 | 2020-08-28 | 2020-09-22 | 17 | 15 | 2 | 2020-09-23 | 2020-10-27 | 24 | 21 | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-03-11 |  | Dec 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-06-23 | Online
WMECO | Springfield | 6S6575-2020 | 1103 | 75 | Diesel | 8C24 | 2020-08-28 | 2020-09-09 | 8 | 6 | 2 | 2020-09-10 | 2020-10-28 | 34 |  | 34 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Dec 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6576-2020 | 1103 | 35 | Diesel | 8C23 | 2020-08-28 | 2020-09-23 | 18 | 16 | 2 | 2020-09-24 | 2020-10-27 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Dec 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A5004-2020 | 1370 | 499 | Solar | 22B5 | 2020-09-03 | 2020-10-20 | 32 | 30 | 2 | 2020-10-21 | 2020-11-03 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2023-09-07 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Hadley | 6A5016-2020 | 1035 | 5000 | Solar | 18G4 | 2020-09-09 | 2020-09-09 | 1 | 0 | 1 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [7 empty] | 0 |  |  | 2021-04-21 | 2022-10-19 | 383 | 49 | 334 |  |  | 0 |  |  | 2023-01-12 |  | 2020-12-15 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Amherst | 6A5034-2020 | 1002 | 14.64 | Solar | 17K2 | 2020-09-17 | 2020-11-19 | 45 |  | 45 | 2020-11-20 | 2020-11-25 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-11-25 |  | 2020-11-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6623-2020 | 1034 | 15.36 | Solar | 29A5 | 2020-09-17 | 2021-09-03 | 239 | 237 | 2 | 2021-09-03 | 2021-09-27 | 16 | 0 | 16 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-10-01 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-04-18 | Online
WMECO | Pittsfield | 6B2615-2020 | 1201 | 2490 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 17 | 11 | 6 | 2020-10-21 | 2020-11-09 | 14 |  | 14 | [7 empty] | 0 |  |  | 2021-02-22 | 2022-01-20 | 229 | 17 | 212 |  |  | 0 |  |  | 2023-01-13 |  | 2021-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Pittsfield | 6B2616-2020 | 1201 | 996 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 17 | 11 | 6 | 2020-10-21 | 2020-10-23 | 3 |  | 3 | [7 empty] | 0 |  |  | 2021-02-22 | 2022-01-20 | 229 | 17 | 212 |  |  | 0 |  |  | 2022-09-09 |  | 2021-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Amherst | 6A5066-2020 | 1002 | 20 | Solar | 17K2 | 2020-10-06 | 2020-11-02 | 19 | 15 | 4 | 2020-11-03 | 2020-11-03 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-06-03 |  | 2020-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-26 | Online
WMECO | Ludlow | 6S6730-2020 | 1056 | 990 | Solar | 19S1 | 2020-10-19 | 2020-11-02 | 11 | 7 | 4 | 2020-11-03 | 2021-01-05 | 42 |  | 42 | [7 empty] | 0 |  |  | 2021-05-11 | 2022-10-07 | 361 | 22 | 339 |  |  | 0 |  |  | 2022-11-09 |  | 2022-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S6731-2020 | 1106 | 20 | Solar | 22H12 | 2020-10-20 | 2020-11-03 | 11 | 8 | 3 | 2020-11-04 | 2020-11-24 | 15 |  | 15 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-06-15 |  | 2020-12-20 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-04-12 | Online
WMECO | Greenfield | 6A5099-2020 | 1301 | 4990 | Battery | 21C1 | 2020-10-27 | 2020-11-05 | 8 |  | 8 | 2020-11-06 | 2020-11-09 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6762-2020 | 1109 | 130.9 | Solar | 5J17 | 2020-10-27 | 2020-11-09 | 10 | 4 | 6 | 2020-11-10 | 2020-12-21 | 29 | 0 | 29 | 2021-01-15 | 2021-02-17 | 21 | 15 | 6 |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-02 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S6770-2020 | 1089 | 20 | Solar | 21N4 | 2020-10-30 | 2020-12-08 | 27 | 23 | 4 | 2020-12-09 | 2021-04-05 | 77 | 0 | 77 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-04-05 |  | 2020-11-03 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-02-25 | Online
WMECO | Greenfield | 6A5102-2020 | 1301 | 4990 | Solar | 22B3 | 2020-11-05 | 2020-11-12 | 6 | 0 | 6 | 2020-11-12 | 2020-11-19 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | -31544 |  |  |  |  | 0 |  |  |  |  | 2022-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6773-2020 | 1104 | 25 | Solar | 5J16 | 2020-11-05 | 2020-11-23 | 13 |  | 13 | 2020-11-24 | 2021-01-22 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-25 |  | 2021-01-31 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-01-24 | Online
WMECO | Plainfield | 6A5104-2020 | 1070 | 10 | Battery | 18K3 | 2020-11-09 | 2020-11-23 | 11 |  | 11 | 2020-11-24 | 2020-12-29 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-20 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-16 | Online
WMECO | Pittsfield | 6B2658-2020 | 1201 | 2495 | Battery |  | 2020-11-12 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B2659-2020 | 1270 | 2495 | Battery |  | 2020-11-12 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6772-2020 | 1001 | 15.2 | Solar | 16C17 | 2020-11-12 | 2020-11-16 | 3 |  | 3 | 2020-11-16 | 2020-12-03 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | 2021-01-11 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-03 | Online
WMECO | Southwick | 6S6774-2020 | 1077 | 10 | Solar | 29A5 | 2020-11-13 | 2021-02-16 | 61 |  | 61 | 2021-02-16 | 2021-03-05 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-05 |  | 2021-01-13 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-11-08 | Online
WMECO | Lee | 6B2660-2020 | 1240 | 3625 | Solar | 16B5 | 2020-11-16 | 2020-11-23 | 6 | 2 | 4 | 2020-11-23 | 2020-11-30 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | Q 4 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A5103-2020 | 1002 | 2840 | Solar |  | 2020-11-18 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A5105-2020 | 1029 | 125 | Solar | 15A2 | 2020-11-24 | 2020-12-09 | 11 |  | 11 | 2020-12-10 | 2021-02-08 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-08 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-06-28 | Online
WMECO | Amherst | 6A5106-2020 | 1002 | 20 | Solar | 19B16 | 2020-12-03 | 2021-01-19 | 30 | 28 | 2 | 2021-01-19 | 2021-04-05 | 52 | 0 | 52 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-04-05 |  | 2021-01-24 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-02 | Online
WMECO | Deerfield | 6A5118-2020 | 1342 | 17.6 | Solar | 22B1 | 2020-12-10 | 2021-01-19 | 25 |  | 25 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-24 |  | 2021-02-07 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-01-11 | Online
WMECO | Amherst | 6A5119-2020 | 1002 | 20 | Solar | 17K5 | 2020-12-10 | 2021-01-19 | 25 |  | 25 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-24 |  | 2021-02-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-01-03 | Online
WMECO | South Deerfield | 6A5107-2020 | 1373 | 4980 | Solar |  | 2020-12-14 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A5111-2020 | 1027 | 22.8 | Solar | 15A3 | 2020-12-16 | 2021-02-01 | 29 | 26 | 3 | 2021-02-01 | 2021-03-10 | 27 | 0 | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-10-19 | Online
WMECO | Ludlow | 6S6775-2020 | 1056 | 133.2 | Solar | 27A6 | 2020-12-16 | 2020-12-24 | 6 |  | 6 | 2020-12-24 | 2021-02-05 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-05 |  | 2021-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A5108-2020 | 1376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A5109-2020 | 1376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A5110-2020 | 1360 | 4500 | Battery | 21B8 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A5112-2020 | 1098 | 1990 | Solar | 18K3 | 2020-12-22 | 2020-12-24 | 2 |  | 2 | 2020-12-24 | 2021-01-11 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-04-20 |  | -31527 |  |  |  |  | 0 |  |  |  |  | 2022-01-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S6776-2020 | 1030 | 7.6 | Solar | 16C17 | 2020-12-22 | 2021-01-21 | 18 |  | 18 | 2021-01-21 | 2021-02-16 | 18 | 0 | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-16 |  | 2020-12-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-07-19 | Online
WMECO | Shelburne | 6A5113-2020 | 1370 | 10 | Solar | 22B5 | 2020-12-23 | 2021-01-05 | 7 |  | 7 | 2021-01-05 | 2021-02-16 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-16 |  | May |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-20 | Online
WMECO | Feeding Hills | 6S6777-2020 | 1030 | 17.6 | Solar | 16C17 | 2020-12-23 | 2021-03-04 | 46 |  | 46 | 2021-03-04 | 2021-03-12 | 7 | 0 | 7 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-19 |  | 2021-02-22 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-07-19 | Online
WMECO | Cummington | 6A5114-2020 | 1026 | 4990 | Battery | 18K3 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-01-27 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-22 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A5115-2020 | 1002 | 4990 | Battery | 18G3 | 2020-12-28 | 2021-01-11 | 10 |  | 10 | 2021-01-11 | 2021-01-29 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-22 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B2662-2020 | 1235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-02-10 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B2663-2020 | 1235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-02-10 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B2664-2020 | 1253 | 4990 | Battery | 19J4 | 2020-12-28 | 2021-01-11 | 10 |  | 10 | 2021-01-11 | 2021-02-02 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A5116-2020 | 1337 | 4990 | Battery | 21C1 | 2020-12-29 | 2021-01-19 | 14 |  | 14 | 2021-01-19 | 2021-01-27 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6778-2020 | 1119 | 4.8 | Solar | 20A33 | 2020-12-29 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-01-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S6779-2020 | 1056 | 5000 | Battery |  | 2020-12-29 | 2021-01-19 | 14 |  | 14 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A5120-2021 | 1027 | 120 | Solar | 15A2 | 2021-01-08 | 2021-01-19 | 7 |  | 7 | 2021-01-19 | 2021-02-22 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | 2021-06-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-09-29 | Online
WMECO | Easthampton | 6A5121-2021 | 1027 | 16.86 | Battery | 15A5 | 2021-01-08 | 2021-02-01 | 15 |  | 15 | 2021-02-01 | 2021-03-12 | 29 |  | 29 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-10 |  | March 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6A5117-2021 | 1270 | 10 | Battery | 18K3 | 2021-01-11 | 2021-02-01 | 14 |  | 14 | 2021-02-01 | 2021-03-10 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2665-2021 | 1224 | 4990 | Solar | 19A5 | 2021-01-14 | 2021-02-22 | 25 |  | 25 | 2021-02-22 | 2021-03-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-20 |  | -31549 |  |  |  |  | 0 |  |  |  |  | ASAP |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westfield | 6S6780-2021 | 1085 | 2000 | Hydro | 18F1 | 2021-01-19 | 2021-02-01 | 9 | 4 | 5 | 2021-02-01 | 2021-04-26 | 58 | 0 | 58 |  |  | 0 | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2023-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B2666-2021 | 1223 | 10 | Solar | 19J6 | 2021-01-21 | 2021-02-22 | 22 |  | 22 | 2021-02-22 | 2021-03-24 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-25 |  | Spring 2021 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-10-05 | Online
WMECO | Ludlow | 6S6781-2021 | 1056 | 990 | Solar | 19S1 | 2021-01-26 | 2021-02-02 | 6 |  | 6 | 2021-02-02 | 2021-02-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Easthampton | 6A5123-2021 | 1027 | 450 | Solar | 15A2 | 2021-01-29 | 2021-02-22 | 16 | 4 | 12 | 2021-02-22 | 2021-03-15 | 16 | 0 | 16 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-01 | 2022-06-14 | 139 | 8 | 131 |  |  | 0 |  |  | 2022-08-08 |  | 2021-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-19 | Online
WMECO | Amherst | 6A5122-2021 | 1002 | 25 | Solar | 18G7 | 2021-02-01 | 2021-02-22 | 15 |  | 15 | 2021-02-22 | 2021-03-24 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-26 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-26 | Online
WMECO | Dalton | 6B2667-2021 | 1226 | 25 | Solar | 19A2 | 2021-02-03 | 2021-02-22 | 13 |  | 13 | 2021-02-22 | 2021-04-05 | 30 | 0 | 30 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-12 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S6782-2021 | 1077 | 4600 | Solar | 29A1 | 2021-02-10 | 2021-02-22 | 8 |  | 8 | 2021-02-22 | 2021-03-22 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-21 | 2022-11-29 | 307 |  | 307 |  |  | 0 |  |  | 2022-12-08 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Dalton | 6B2669-2021 | 1226 | 2660 | Solar | 18C1 | 2021-02-15 | 2021-02-22 | 5 | 3 | 2 | 2021-02-22 | 2021-03-04 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-19 | 2022-08-23 | 322 | 38 | 284 |  |  | 0 |  |  | 2023-01-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Pittsfield | 6B2668-2021 | 1201 | 86.4 | Solar | 30B7 | 2021-02-16 | 2021-03-25 | 27 | 27 | 0 | 2021-03-25 | 2021-04-26 | 22 | 0 | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | 2021-06-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-06-30 | Online
WMECO | Hadley | 6A5124-2021 | 1035 | 20 | Battery | 17K5 | 2021-02-18 | 2021-03-03 | 10 | 9 | 1 | 2021-03-03 | 2021-04-05 | 23 | 0 | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-04-05 |  | March 2021 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-04-15 | Online
WMECO | Springfield | 6S6783-2021 | 1119 | 4.8 | Solar | 20A33 | 2021-02-18 | 2021-02-22 | 3 | 2 | 1 | 2021-02-22 | 2021-03-08 | 11 | 0 | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-03-11 |  | 2021-01-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2670-2021 | 1008 | 1000 | Solar | 19J2 | 2021-02-26 | 2021-03-25 | 19 | 19 | 0 | 2021-03-25 | 2021-04-23 | 21 | 6 | 15 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | Jan 2022 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A5125-2021 | 1038 | 250 | Biogas | 18G6 | 2021-03-01 | 2021-05-19 | 56 | 56 | 0 | 2021-05-19 | 2021-06-14 | 18 | 0 | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2021-08-30 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Easthampton | 6A5126-2021 | 1027 | 17.6 | Solar | 15A5 | 2021-03-09 | 2021-03-29 | 14 | 6 | 8 | 2021-03-29 | 2021-05-03 | 25 | 2 | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-26 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6784-2021 | 1001 | 360 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 12 | 4 | 8 | 2021-03-25 | 2021-04-22 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-22 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6785-2021 | 1001 | 499.9 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 12 | 4 | 8 | 2021-03-25 | 2021-04-29 | 25 | 0 | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-22 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2671-2021 | 1201 | 166.6 | Solar | 30B4 | 2021-03-12 | 2021-03-29 | 11 | 9 | 2 | 2021-03-29 | 2021-04-26 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | 2021-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Lanesborough | 6B2672-2021 | 1237 | 16 | Solar | 15E1 | 2021-03-16 | 2021-03-29 | 9 | 6 | 3 | 2021-03-29 | 2021-04-26 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-13 | Online
WMECO | Springfield | 6S6786-2021 | 1128 | 500 | Solar |  | 2021-03-18 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | Oct 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6787-2021 | 1129 | 500 | Solar |  | 2021-03-18 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A5127-2021 | 1360 | 1500 | Solar | 21B8 | 2021-03-26 | 2021-04-09 | 11 | 0 | 11 | 2021-04-09 | 2021-04-19 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2022-04-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | ESMAEX-00037 | 1035 | 25 | Solar & Battery | 18G4 | 2021-04-08 | 2021-05-03 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-06 | [7 empty] | 0 |  |  |  |  | 2022-02-11 | Online | [11 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-00043 | 1077 | 8.7 | Solar & Battery | 29A1 | 2021-04-14 | 2021-05-18 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-07 | [7 empty] | 0 |  |  |  |  | 2021-12-16 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Indian Orchard | ESMAEX-00045 | 1151 | 2040 | Solar |  | 2021-05-28 | 2021-06-21 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-06 | [7 empty] | 0 |  |  |  |  | 2025-09-26 | Online | [8 empty] | 2023 ASO Batch 1
WMECO | West Springfield | ESMAEX-00061 | 1089 | 21.4 | Solar & Battery | 21N9 | 2021-04-19 | 2021-05-18 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-24 | [7 empty] | 0 |  |  |  |  | 2022-01-18 | Online | [10 empty] | 11.4 | 21N PIPER
WMECO | Ludlow | ESMAEX-00069 | 1056 | 19.8 | Solar | 27A6 | 2021-04-22 | 2021-05-18 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-21 | [7 empty] | 0 |  |  |  |  | 2021-11-02 | Online | [10 empty] | 9.8 | 27A ORCHARD
WMECO | Amherst | ESMAEX-00170 | 1002 | 66.6 | Solar | 17K4 | 2022-02-11 | 2021-06-21 | -164 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-02-11 | [7 empty] | 0 |  |  |  |  | 2023-01-11 | Online | [11 empty] | 17K AMHERST
WMECO | Huntington | ESMAEX-00294 | 1050 | 20 | Solar | 19J5 | 2021-08-11 | 2021-08-23 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-21 | [7 empty] | 0 |  |  |  |  | 2022-06-28 | Online | [10 empty] | 0
WMECO | Chicopee | ESMAEX-00185 | 1013 | 4999 | Battery | 21N7 | 2021-06-15 | 2024-10-23 | 870 |  | 870 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-27 | [7 empty] | 0 | [5 empty] | Technical Review | [8 empty] | 2023 ASO Batch 1 |  | 4999 | 21N PIPER
WMECO | Greenfield | ESMAEX-00134 | 1301 | 15 | Solar | 22B7 | 2021-05-18 | 2021-06-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-14 | [7 empty] | 0 |  |  |  |  | 2021-10-26 | Online | [10 empty] | 0 | 22B CUMBERLAND
WMECO | New Ashford | ESMAEX-00146 | 1237 | 10 | Solar & Battery | 15E1 | 2021-05-24 | 2021-06-21 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-24 | [7 empty] | 0 |  |  |  |  | 2022-10-03 | Online
WMECO | Huntington | ESMAEX-00150 | 1050 | 18 | Solar & Battery | 19J5 | 2021-05-26 | 2021-06-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-03 | [7 empty] | 0 |  |  |  |  | 2021-11-15 | Online | [10 empty] | 7.68
WMECO | Colrain | ESMAEX-00162 | 1340 | 22.8 | Solar | 29R2 | 2021-06-02 | 2021-06-21 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-02 | [7 empty] | 0 |  |  |  |  | 2021-12-02 | Online | [11 empty] | 29R SHELBURNE
WMECO | Springfield | ESMAEX-00165 | 1109 | 7.5 | Solar | 5J17 | 2021-06-03 | 2021-06-21 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-12 | [7 empty] | 0 |  |  |  |  | 2021-12-10 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Hadley | ESMAEX-00177 | 1035 | 375 | Solar | 18G5 | 2021-06-09 | 2021-06-21 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-19 | [7 empty] | 0 |  |  |  |  | 2024-06-14 | Online | [11 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-00366 | 1001 | 17.6 | Solar & Battery | 16C16 | 2021-08-27 | 2021-09-30 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-10-26 | [7 empty] | 0 |  |  |  |  | 2022-05-13 | Online | [11 empty] | 16C AGAWAM
WMECO | Agawam | ESMAEX-00187 | 1001 | 22 | Solar | 16C16 | 2021-06-15 | 2021-07-16 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-20 | [7 empty] | 0 |  |  |  |  | 2021-10-13 | Online | [10 empty] | 12 | 16C AGAWAM
WMECO | Hadley | ESMAEX-00212 | 1035 | 10.44 | Solar | 19B15 | 2021-06-25 | 2021-07-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-03 | [7 empty] | 0 |  |  |  |  | 2021-10-26 | Online | [11 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-00205 | 1201 | 60 | Internal Combustion Engine | 30B2 | 2021-06-23 | 2021-07-16 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-21 | [7 empty] | 0 |  |  |  |  | 2025-07-28 | Online | [11 empty] | 30B OSWALD
WMECO | Southampton | ESMAEX-00220 | 1073 | 996 | Solar & Battery | 15A1 | 2021-10-20 | 2021-10-26 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-02 | [7 empty] | 0 | [5 empty] | ISA Agreement | [10 empty] | 2000 | 15A GUNN
WMECO | Greenfield | ESMAEX-00256 | 1301 | 100.8 | Solar | 21C1 | 2021-07-21 | 2021-08-06 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-25 | [7 empty] | 0 |  |  |  |  | 2023-09-14 | Online | [11 empty] | 21C MONTAGUE
WMECO | Tyringham | ESMAEX-00233 | 1264 | 22.8 | Solar | 16B1 | 2021-07-12 | 2021-08-23 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-17 | [7 empty] | 0 |  |  |  |  | 2022-04-11 | Online | [11 empty] | 16B PLEASANT
WMECO | Westhampton | ESMAEX-00728 | 1027 | 30 | Battery | 15A3 | 2022-01-13 | 2022-01-26 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-28 | [7 empty] | 0 |  |  |  |  | 2022-07-27 | Online | [11 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-00242 | 1030 | 8 | Solar | 30A1 | 2021-07-16 | 2021-08-06 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-09 | [7 empty] | 0 |  |  |  |  | 2021-10-07 | Online | [11 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00290 | 1103 | 150 | Internal Combustion Engine | 8C24 | 2022-01-20 | 2022-02-10 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-18 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [10 empty] | 0 | 8C WEST SPRINGFIELD
WMECO | Easthampton | ESMAEX-00295 | 1027 | 9.8 | Solar | 15A1 | 2021-08-10 | 2021-10-12 | 44 |  | 44 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-10-26 | [7 empty] | 0 |  |  |  |  | 2022-01-31 | Online | [11 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-00296 | 1129 | 17.6 | Solar | 20A23 | 2021-08-10 | 2021-10-21 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-01 | [7 empty] | 0 |  |  |  |  | 2022-05-10 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Springfield | ESMAEX-00332 | 1105 | 60 | Internal Combustion Engine | 21S5 | 2021-08-19 | 2021-10-22 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-01 | [7 empty] | 0 |  |  |  |  | 2022-05-06 | Online | [11 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-00369 | 1035 | 45.6 | Solar | 18G4 | 2021-08-30 | 2021-08-30 | 1 |  | 1 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-05 | [7 empty] | 0 |  |  |  |  | 2023-10-24 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00383 | 1109 | 17.5 | Battery | 5J17 | 2021-09-03 | 2021-10-26 | 36 |  | 36 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-02 | [7 empty] | 0 |  |  |  |  | 2021-12-01 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-00370 | 1109 | 15.8 | Solar | 20A31 | 2021-08-30 | 2021-09-20 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-28 | [7 empty] | 0 |  |  |  |  | 2022-01-27 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00401 | 1077 | 18 | Solar | 29A1 | 2021-09-10 | 2021-09-28 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-28 | [7 empty] | 0 |  |  |  |  | 2023-02-07 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-00475 | 1056 | 2000 | Solar & Battery | 27A5 | 2021-10-06 | 2021-10-12 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-17 | [7 empty] | 0 | [5 empty] | ISA Agreement | [8 empty] | 2023 ASO Batch 1 |  |  | 27A ORCHARD
WMECO | West Springfield | ESMAEX-00456 | 1089 | 16.225 | Solar | 21N9 | 2021-09-29 | 2021-10-26 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-02 | [7 empty] | 0 |  |  |  |  | 2023-10-11 | Online | [11 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-00459 | 1027 | 9.735 | Solar & Battery | 15A3 | 2021-09-30 | 2021-10-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2022-05-24 | Online | [11 empty] | GUNN
WMECO | Longmeadow | ESMAEX-00471 | 1106 | 15.2 | Solar | 22H11 | 2021-10-04 | 2021-11-08 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-29 | [7 empty] | 0 |  |  |  |  | 2022-09-12 | Online | [11 empty] | 22H FRANCONIA
WMECO | Springfield | ESMAEX-00491 | 1107 | 3000 | Internal Combustion Engine | 21S8 | 2021-10-12 | 2021-11-09 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-11 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [11 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-00483 | 1375 | 60 | Solar | 18G3 | 2021-10-08 | 2021-10-26 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00501 | 1104 | 108 | Solar | 5J9 | 2021-10-14 | 2021-10-26 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-06 | [7 empty] | 0 |  |  |  |  | 2023-08-31 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Bernardston | ESMAEX-00657 | 1337 | 2200 | Solar & Battery | 21B8 | 2021-12-13 | 2021-12-14 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval |  | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-00503 | 1201 | 4990 | Battery | 19A1 | 2022-02-23 | 2022-03-17 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-02 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 19A DOREEN
WMECO | Colrain | ESMAEX-00550 | 1340 | 10 | Battery | 29R2 | 2021-10-27 | 2021-11-08 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-01 | [7 empty] | 0 |  |  |  |  | 2023-03-07 | Online | [11 empty] | 29R SHELBURNE
WMECO | Hinsdale | ESMAEX-00541 | 1235 | 20 | Solar | 18C2 | 2021-10-25 | 2021-11-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2022-09-14 | Online | [11 empty] | BERKSHIRE
WMECO | Agawam | ESMAEX-00578 | 1001 | 4990 | Battery | 30A6 | 2022-01-12 | 2022-01-20 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-05 | [7 empty] | 0 | [5 empty] | Compliances Documents | [8 empty] | 2023 ASO Batch 1 |  |  | 30A SILVER
WMECO | Chicopee | ESMAEX-00750 | 1013 | 4100 | Fuel Cell | 21N7 | 2022-01-21 | 2022-02-10 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-07 | [7 empty] | 0 | [5 empty] | Compliances Documents | [8 empty] | 2023 ASO Batch 1 |  |  | 21N PIPER
WMECO | Hinsdale | ESMAEX-00608 | 1235 | 19.52 | Solar | 18C2 | 2021-11-19 | 2021-12-12 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-10 | [7 empty] | 0 |  |  |  |  | 2022-03-29 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Dalton | ESMAEX-00846 | 1226 | 42.6 | Solar |  | 2022-02-22 | 2022-03-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-10 | [7 empty] | 0 |  |  |  |  | 2022-08-02 | Online
WMECO | Springfield | ESMAEX-00618 | 1128 | 9.92 | Solar & Battery | 20A34 | 2021-11-23 | 2021-12-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-11 | [7 empty] | 0 |  |  |  |  | 2022-03-22 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Montague | ESMAEX-00653 | 1351 | 5 | Battery | 21C2 | 2021-12-10 | 2021-12-16 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-18 | [7 empty] | 0 |  |  |  |  | 2022-11-23 | Online | [7 empty] | Gill-Montague |  |  | 14 | 21C MONTAGUE
WMECO | Southwick | ESMAEX-00695 | 1077 | 3984 | Solar | 29A3 | 2022-01-31 | 2022-02-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Southwick | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Buckland | ESMAEX-00739 | 1338 | 24 | Solar | 38A1 | 2022-01-19 | 2022-01-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-31 | [7 empty] | 0 |  |  |  |  | 2023-03-02 | Online | [11 empty] | 38A ASHFIELD
WMECO | Erving | ESMAEX-00810 | 1344 | 2600 | Battery | 21C8 | 2022-02-04 | 2022-02-28 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [8 empty] | 2023 ASO Batch 1 |  |  | 21C MONTAGUE
WMECO | Lee | ESMAEX-00749 | 1238 | 9.49 | Solar & Battery | 16B5 | 2022-01-21 | 2022-01-24 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-02 | [7 empty] | 0 |  |  |  |  | 2023-04-03 | Online | [11 empty] | 16B PLEASANT
WMECO | Northfield | ESMAEX-00836 | 1360 | 40 | Battery |  | 2022-02-16 | 2022-03-10 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-15 | [7 empty] | 0 |  |  |  |  | 2022-07-01 | Online
WMECO | Whately | ESMAEX-00756 | 1093 | 6.4 | Battery | 18G6 | 2022-01-25 | 2022-01-28 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-28 | [7 empty] | 0 |  |  |  |  | 2022-06-15 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00823 | 1105 | 46.4 | Solar | 21S4 | 2022-02-09 | 2022-02-18 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-01 | [7 empty] | 0 |  |  |  |  | 2023-01-10 | Online | [11 empty] | CLINTON
WMECO | Longmeadow | ESMAEX-00766 | 1106 | 7.09 | Solar & Battery | 22H11 | 2022-01-29 | 2022-02-22 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-09 | [7 empty] | 0 |  |  |  |  | 2022-04-21 | Online | [11 empty] | 22H FRANCONIA
WMECO | Lee | ESMAEX-00806 | 1238 | 7.6 | Solar & Battery | 16B5 | 2022-02-03 | 2022-04-06 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-12 | [7 empty] | 0 |  |  |  |  | 2022-09-08 | Online | [11 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00914 | 1201 | 440 | Solar | 19A3 | 2022-04-07 | 2022-04-19 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-06 | [7 empty] | 0 |  |  |  |  | 2024-09-12 | Online | [11 empty] | 19A DOREEN
WMECO | Lee | ESMAEX-00855 | 1238 | 19.8 | Solar & Battery | 16B1 | 2022-02-24 | 2022-03-02 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-05 | [7 empty] | 0 |  |  |  |  | 2023-01-09 | Online | [11 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00854 | 1201 | 15.2 | Solar & Battery | 30B7 | 2022-02-24 | 2022-04-06 | 30 |  | 30 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-12 | [7 empty] | 0 |  |  |  |  | 2023-09-14 | Online | [11 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-00868 | 1089 | 5 | Battery | 21N4 | 2022-03-01 | 2022-03-29 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-02 | [7 empty] | 0 |  |  |  |  | 2022-09-01 | Online | [10 empty] | 14 | 21N PIPER
WMECO | Feeding Hills | ESMAEX-00898 | 1030 | 15.2 | Solar | 30A6 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-22 | [7 empty] | 0 |  |  |  |  | 2022-12-21 | Online | [11 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00942 | 1108 | 13.6 | Solar | 22H16 | 2022-03-17 | 2022-03-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-02 | [7 empty] | 0 |  |  |  |  | 2022-10-17 | Online | [11 empty] | 22H FRANCONIA
WMECO | Ludlow | ESMAEX-00910 | 1056 | 9.8 | Solar | 27A5 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-28 | [7 empty] | 0 |  |  |  |  | 2022-09-19 | Online | [11 empty] | 27A ORCHARD
WMECO | Agawam | ESMAEX-00944 | 1001 | 149.1 | Solar | 30A3 | 2022-03-18 | 2022-03-28 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-15 | [7 empty] | 0 |  |  |  |  | 2023-09-12 | Online | [11 empty] | SILVER
WMECO | Southwick | ESMAEX-00933 | 1077 | 15.2 | Solar | 29A5 | 2022-03-16 | 2022-04-12 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2023-01-05 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Pittsfield | ESMAEX-00941 | 1201 | 10 | Solar | 30B7 | 2022-03-17 | 2022-04-07 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-21 | [7 empty] | 0 |  |  |  |  | 2022-08-05 | Online | [11 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-00957 | 1095 | 240 | Solar | 20A35 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-11 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00958 | 1077 | 240 | Solar | 29A5 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-20 | [7 empty] | 0 |  |  |  |  | 2024-12-30 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Montague | ESMAEX-00988 | 1376 | 11000 | Battery | 21C6 | 2023-01-20 | 2023-01-23 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval | 4990 | 21C MONTAGUE
WMECO | Granville | ESMAEX-01120 | 1034 | 15.2 | Solar & Battery | 29A5 | 2022-04-27 | 2022-05-09 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-10 | [7 empty] | 0 |  |  |  |  | 2022-11-14 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Dalton | ESMAEX-01075 | 1226 | 20 | Solar | 18C1 | 2022-04-12 | 2022-04-26 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2022-08-08 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Northfield | ESMAEX-01087 | 1360 | 10 | Battery | 21B8 | 2022-04-16 | 2022-05-16 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-16 | [7 empty] | 0 |  |  |  |  | 2022-11-23 | Online | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Huntington | ESMAEX-01102 | 1050 | 4999 | Solar | 19J5 | 2022-05-12 | 2022-05-26 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-01110 | 1237 | 3.54 | Solar & Battery | 15E1 | 2022-04-25 | 2022-05-04 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2022-09-14 | Online
WMECO | Westhampton | ESMAEX-01141 | 1027 | 3.8 | Solar & Battery | 15A3 | 2022-05-03 | 2022-05-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-25 | [7 empty] | 0 |  |  |  |  | 2024-09-24 | Online | [11 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-01146 | 1089 | 3.8 | Solar & Battery | 21N4 | 2022-05-04 | 2022-05-18 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-24 | [7 empty] | 0 |  |  |  |  | 2023-03-09 | Online | [11 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01148 | 1104 | 400 | Solar & Battery | 5J9 | 2022-06-14 | 2022-06-30 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-14 | [7 empty] | 0 | [5 empty] | Construction Stage | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Greenfield | ESMAEX-01159 | 1301 | 996 | Solar & Battery | 22B7 | 2022-10-10 | 2022-10-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-28 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 22B CUMBERLAND
WMECO | Agawam | ESMAEX-01547 | 1001 | 117.3 | Solar | 30A2 | 2022-09-06 | 2022-09-13 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-13 | [7 empty] | 0 |  |  |  |  | 2023-10-06 | Online | [11 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-01165 | 1106 | 10 | Solar & Battery | 22H17 | 2022-05-10 | 2022-05-18 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-20 | [7 empty] | 0 |  |  |  |  | 2022-08-22 | Online | [11 empty] | 22H FRANCONIA
WMECO | Plainfield | ESMAEX-01166 | 1070 | 4980 | Solar & Battery | 18K3 | 2023-03-24 | 2023-05-05 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Complex |  |  |  | 0 | [5 empty] | Compliances Documents | [10 empty] | 4980 | 18K PLAINFIELD
WMECO | Westhampton | ESMAEX-01182 | 1027 | 15.2 | Solar & Battery | 15A3 | 2022-05-16 | 2022-06-09 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-26 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [11 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-01230 | 1109 | 791.5 | Solar & Battery | 21S4 | 2022-07-28 | 2022-08-04 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-20 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 21S CLINTON
WMECO | Bernardston | ESMAEX-01240 | 1337 | 15.2 | Solar | 21C5 | 2022-06-01 | 2022-06-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-07 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-01249 | 1089 | 10 | Battery | 21N4 | 2022-06-02 | 2022-06-09 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-11 | [7 empty] | 0 |  |  |  |  | 2023-07-05 | Online | [11 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01251 | 1103 | 990 | Solar & Battery | 5J13 | 2023-08-02 | 2023-08-11 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Supplemental Designer Review | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-01257 | 1129 | 6 | Solar | 20A14 | 2022-06-06 | 2022-06-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-17 | [7 empty] | 0 |  |  |  |  | 2022-09-19 | Online | [10 empty] | 6 | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-01410 | 1002 | 50 | Solar | 17K5 | 2022-07-25 | 2022-08-04 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-14 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online | [11 empty] | 17K AMHERST
WMECO | Easthampton | ESMAEX-01308 | 1027 | 10 | Solar | 15A1 | 2022-06-17 | 2022-06-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-26 | [7 empty] | 0 |  |  |  |  | 2022-10-12 | Online | [10 empty] | 10 | 15A GUNN
WMECO | Feeding Hills | ESMAEX-01317 | 1030 | 15.2 | Solar | 30A6 | 2022-06-22 | 2022-06-30 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-09 | [7 empty] | 0 |  |  |  |  | 2023-04-13 | Online | [10 empty] | 16 | 30A SILVER
WMECO | Easthampton | ESMAEX-01326 | 1027 | 17.6 | Battery |  | 2022-06-27 | 2022-07-01 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-26 | [7 empty] | 0 |  |  |  |  | 2023-10-02 | Online
WMECO | Whately | ESMAEX-01352 | 1093 | 10 | Battery | 18G8 | 2022-07-07 | 2022-07-29 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2023-02-02 | Online | [11 empty] | 18G PODICK
WMECO | Greenfield | ESMAEX-01376 | 1301 | 15.2 | Solar | 22B7 | 2022-07-13 | 2022-08-04 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Lanesborough | ESMAEX-01480 | 1224 | 17.6 | Solar & Battery | 19A5 | 2022-08-17 | 2022-09-07 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-28 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [11 empty] | 19A DOREEN
WMECO | Southampton | ESMAEX-01350 | 1073 | 17.68 | Solar & Battery | 15A1 | 2022-07-06 | 2022-08-04 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2023-01-05 | Online | [10 empty] | 7.68 | 15A GUNN
WMECO | Springfield | ESMAEX-01356 | 1107 | 2000 | Battery | 21S10 | 2022-10-18 | 2022-12-05 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-26 | [7 empty] | 0 |  |  |  |  | 2025-01-08 | Online | [8 empty] | 2023 ASO Batch 1 |  | 0 | 21S CLINTON
WMECO | Springfield | ESMAEX-01384 | 1109 | 2549.99 | Solar & Battery | 20A33 | 2023-01-13 | 2023-02-02 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review | [8 empty] | 2023 ASO Batch 1 |  |  | 20A BRECKWOOD
WMECO | Longmeadow | ESMAEX-01501 | 1106 | 15.2 | Solar & Battery | 22H11 | 2022-08-23 | 2022-09-23 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-03 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online | [11 empty] | 22H FRANCONIA
WMECO | Cheshire | ESMAEX-01421 | 1225 | 3800 | Solar & Battery | 19A5 | 2022-08-15 | 2022-09-07 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-13 | [7 empty] | 0 | [5 empty] | Compliances Documents | [8 empty] | 2023 ASO Batch 1 |  | 3800 | 19A DOREEN
WMECO | Southwick | ESMAEX-01444 | 1077 | 15.2 | Solar & Battery |  | 2022-08-08 | 2022-08-24 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-24 | [7 empty] | 0 |  |  |  |  | 2023-01-31 | Online
WMECO | Granville | ESMAEX-01439 | 1034 | 3000 | Solar & Battery | 29A5 | 2022-09-07 | 2022-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Southwick | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval | 3000 | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01445 | 1002 | 69.2 | Solar | 17K4 | 2022-08-08 | 2022-08-16 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-09 | [7 empty] | 0 |  |  |  |  | 2024-02-14 | Online | [11 empty] | 17K AMHERST
WMECO | Ludlow | ESMAEX-01447 | 1056 | 20 | Solar |  | 2022-08-08 | 2022-12-16 | 95 |  | 95 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-30 | [7 empty] | 0 |  |  |  |  | 2024-05-01 | Online
WMECO | Springfield | ESMAEX-01448 | 1109 | 1683 | Solar & Battery | 20A14 | 2023-01-17 | 2023-02-02 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review | [8 empty] | 2023 ASO Batch 1 |  |  | 20A BRECKWOOD
WMECO | Savoy | ESMAEX-02010 | 1256 | 15.2 | Solar & Battery | 18K4 | 2023-01-12 | 2023-01-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-03 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Blandford | ESMAEX-01479 | 1008 | 4998 | Solar & Battery | 19J5 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 4998 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-01489 | 1201 | 240 | Solar |  | 2023-01-12 | 2022-09-07 | -92 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-05 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online
WMECO | Springfield | ESMAEX-01502 | 1108 | 3 | Solar & Battery | 22H15 | 2022-08-23 | 2022-09-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-06 | [7 empty] | 0 |  |  |  |  | 2023-04-12 | Online | [10 empty] | 14 | 22H FRANCONIA
WMECO | Otis | ESMAEX-01512 | 1253 | 20 | Solar | 19J4 | 2022-08-25 | 2022-09-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-12 | [7 empty] | 0 | [5 empty] | Construction Stage | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Shelburne Falls | ESMAEX-01514 | 1370 | 20 | Solar | 22B5 | 2022-08-25 | 2022-09-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-25 | [7 empty] | 0 |  |  |  |  | 2024-11-22 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Hadley | ESMAEX-01515 | 1035 | 15.6 | Solar & Battery | 18G5 | 2022-08-26 | 2022-09-07 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-04 | [7 empty] | 0 |  |  |  |  | 2023-02-08 | Online | [11 empty] | 18G PODICK
WMECO | Amherst | ESMAEX-01522 | 1002 | 4990 | Battery | 18G6 | 2022-08-29 | 2022-09-14 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [10 empty] | 4990 | 18G PODICK
WMECO | Agawam | ESMAEX-01527 | 1001 | 960 | Solar | 30A3 | 2022-09-19 | 2022-09-23 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-08 | [7 empty] | 0 |  |  |  |  | 2025-02-14 | Online | [11 empty] | 30A SILVER
WMECO | Hatfield | ESMAEX-01533 | 1038 | 20 | Solar | 18G6 | 2022-09-01 | 2022-09-13 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-04 | [7 empty] | 0 |  |  |  |  | 2022-12-21 | Online | [11 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-01539 | 1375 | 10 | Solar & Battery | 18G8 | 2022-09-02 | 2022-09-21 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-05 | [7 empty] | 0 |  |  |  |  | 2023-03-06 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01563 | 1109 | 60 | Solar | 20A33 | 2022-09-11 | 2022-09-23 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-22 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-01581 | 1077 | 4999 | Battery | 29A3 | 2023-03-20 | 2023-04-19 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01582 | 1077 | 6700 | Solar & Battery | 29A3 | 2023-03-20 | 2023-03-22 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01586 | 1002 | 3830 | Solar & Battery | 17K8 | 2022-09-14 | 2022-09-15 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-11 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 3830 | 17K AMHERST
WMECO | Lanesborough | ESMAEX-01590 | 1237 | 16.4 | Solar | 15E1 | 2022-09-14 | 2022-09-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-27 | [7 empty] | 0 |  |  |  |  | 2023-07-06 | Online | [11 empty] | PARTRIDGE
WMECO | Buckland | ESMAEX-01594 | 1338 | 250 | Solar | 29R1 | 2022-10-07 | 2022-10-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-02 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online | [11 empty] | 29R SHELBURNE
WMECO | Worthington | ESMAEX-01622 | 1098 | 3000 | Solar & Battery | 18K3 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 3000 | 18K PLAINFIELD
WMECO | Blandford | ESMAEX-01635 | 1008 | 2000 | Solar | 19J2 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 2000 | 19J BLANDFORD
WMECO | Cummington | ESMAEX-01631 | 1026 | 5 | Solar | 18C1 | 2022-09-26 | 2022-10-05 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-02 | [7 empty] | 0 |  |  |  |  | 2023-02-24 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Hatfield | ESMAEX-01733 | 1038 | 7.6 | Solar & Battery | 18G5 | 2022-10-27 | 2023-01-11 | 55 |  | 55 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-18 | [7 empty] | 0 |  |  |  |  | 2023-06-15 | Online | [11 empty] | 18G PODICK
WMECO | Longmeadow | ESMAEX-01682 | 1106 | 10.752 | Solar & Battery | 22H11 | 2022-10-13 | 2022-11-21 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-15 | [7 empty] | 0 |  |  |  |  | 2023-04-27 | Online | [11 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-01647 | 1254 | 22.8 | Solar & Battery | 30B7 | 2022-09-30 | 2022-12-01 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-07 | [7 empty] | 0 |  |  |  |  | 2024-10-11 | Online | [11 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-01645 | 1109 | 12.6 | Solar & Battery | 5J17 | 2022-09-29 | 2022-10-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-21 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Amherst | ESMAEX-01862 | 1002 | 60 | Solar | 17K6 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-07 | [7 empty] | 0 |  |  |  |  | 2024-08-05 | Online | [11 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-01852 | 1223 | 2490 | Solar | 19J6 | 2022-11-28 | 2022-12-05 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study | [7 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-01748 | 1330 | 10 | Solar | 38A1 | 2022-11-01 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-03 | [7 empty] | 0 |  |  |  |  | 2023-04-25 | Online | [10 empty] | 0 | 38A ASHFIELD
WMECO | Whately | ESMAEX-01677 | 1093 | 400 | Solar | 18G8 | 2023-02-16 | 2023-02-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-01715 | 1077 | 10 | Solar & Battery | 29A5 | 2022-10-25 | 2022-10-28 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-31 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online | [7 empty] | Southwick |  |  | 7 | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-01813 | 1056 | 17.6 | Solar & Battery | 19S1 | 2022-11-15 | 2023-01-23 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-31 | [7 empty] | 0 |  |  |  |  | 2023-05-30 | Online | [10 empty] | 17.6 | 19S LUDLOW
WMECO | West Springfield | ESMAEX-01719 | 1089 | 225 | Solar | 21N5 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-30 | [7 empty] | 0 |  |  |  |  | 2024-10-24 | Online | [11 empty] | 21N PIPER
WMECO | Granville | ESMAEX-01695 | 1034 | 17.1 | Solar | 29A5 | 2022-10-19 | 2022-10-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-23 | [7 empty] | 0 |  |  |  |  | 2023-04-20 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-01708 | 1237 | 3800 | Solar & Battery | 30B5 | 2023-01-10 | 2024-07-29 | 405 |  | 405 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [10 empty] | 2800 | 30B OSWALD
WMECO | Conway | ESMAEX-01702 | 1341 | 12.6 | Solar | 38A1 | 2022-10-21 | 2022-11-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-12 | [7 empty] | 0 |  |  |  |  | 2023-02-09 | Online | [11 empty] | 38A ASHFIELD
WMECO | Blandford | ESMAEX-01704 | 1008 | 4998 | Solar & Battery | 19J2 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 4998 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-01713 | 1027 | 15.2 | Solar & Battery | 15A2 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-12 | [7 empty] | 0 |  |  |  |  | 2023-04-13 | Online | [11 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-01764 | 1002 | 10 | Battery | 17K8 | 2022-11-03 | 2022-12-07 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-18 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online | [11 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-01830 | 1077 | 15.93 | Solar | 29A1 | 2022-11-17 | 2022-12-05 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-05 | [7 empty] | 0 |  |  |  |  | 2023-08-29 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01769 | 1077 | 10 | Solar & Battery | 29A5 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-16 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online | [7 empty] | Southwick |  |  | 7 | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-01754 | 1035 | 10 | Solar | 18G4 | 2022-11-02 | 2022-11-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-14 | [7 empty] | 0 |  |  |  |  | 2023-06-06 | Online | [11 empty] | 18G PODICK
WMECO | Washington | ESMAEX-01766 | 1223 | 5 | Solar & Battery | 19J6 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-18 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [10 empty] | 0
WMECO | Bernardston | ESMAEX-01755 | 1337 | 4700 | Solar & Battery | 21C1 | 2023-09-21 | 2023-09-29 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4700 | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-01802 | 1030 | 10 | Solar | 30A1 | 2022-11-11 | 2022-11-16 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-21 | [7 empty] | 0 |  |  |  |  | 2023-04-07 | Online | [10 empty] | 7 | 30A SILVER
WMECO | Ludlow | ESMAEX-01826 | 1056 | 14.7 | Solar | 27A5 | 2022-11-17 | 2022-12-21 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-23 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online | [11 empty] | 27A ORCHARD
WMECO | Conway | ESMAEX-01828 | 1341 | 4200 | Solar & Battery | 22B1 | 2023-01-25 | 2023-02-01 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [10 empty] | 4200 | 22B CUMBERLAND
WMECO | Whately | ESMAEX-01872 | 1093 | 20 | Solar | 18G6 | 2022-11-30 | 2022-12-05 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-25 | [7 empty] | 0 |  |  |  |  | 2023-05-12 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01869 | 1118 | 15.2 | Solar & Battery | 20A32 | 2022-11-29 | 2022-12-14 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-03 | [7 empty] | 0 |  |  |  |  | 2025-07-02 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Whately | ESMAEX-02067 | 1093 | 5 | Battery | 18G8 | 2023-01-25 | 2023-02-21 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-09 | [7 empty] | 0 |  |  |  |  | 2024-06-17 | Online | [11 empty] | 18G PODICK
WMECO | Otis | ESMAEX-02145 | 1253 | 15.2 | Solar & Battery | 19J4 | 2023-02-09 | 2023-02-24 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-10-23 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-02059 | 1330 | 20 | Solar | 38A1 | 2023-01-23 | 2023-02-01 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-20 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online | [11 empty] | 38A ASHFIELD
WMECO | Whately | ESMAEX-01991 | 1093 | 15.2 | Solar | 18G6 | 2023-01-10 | 2023-01-23 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-15 | [7 empty] | 0 |  |  |  |  | 2024-02-08 | Online | [11 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-01968 | 1056 | 240 | Solar |  | 2023-01-05 | 2023-02-01 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-03 | [7 empty] | 0 | [5 empty] | Compliances Documents
WMECO | Longmeadow | ESMAEX-02008 | 1106 | 20 | Solar | 22H13 | 2023-01-12 | 2023-02-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-15 | [7 empty] | 0 |  |  |  |  | 2023-05-23 | Online | [11 empty] | 22H FRANCONIA
WMECO | Feeding Hills | ESMAEX-02090 | 1030 | 10.62 | Solar & Battery | 30A1 | 2023-01-30 | 2023-03-31 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-03 | [7 empty] | 0 |  |  |  |  | 2023-08-04 | Online | [11 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-02073 | 1002 | 15.2 | Solar | 18G7 | 2023-01-25 | 2023-02-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-09 | [7 empty] | 0 |  |  |  |  | 2023-09-05 | Online | [11 empty] | 18G PODICK
WMECO | Feeding Hills | ESMAEX-02040 | 1030 | 15.2 | Solar | 16C17 | 2023-01-19 | 2023-02-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-28 | [7 empty] | 0 |  |  |  |  | 2023-08-04 | Online | [10 empty] | 17.4 | 16C AGAWAM
WMECO | Deerfield | ESMAEX-02052 | 1342 | 480 | Solar | 22B3 | 2023-02-17 | 2023-03-03 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22B CUMBERLAND
WMECO | Longmeadow | ESMAEX-02128 | 1106 | 10 | Battery | 22H13 | 2023-02-06 | 2023-02-24 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-01 | [7 empty] | 0 |  |  |  |  | 2024-01-25 | Online | [11 empty] | 22H FRANCONIA
WMECO | Agawam | ESMAEX-02138 | 1030 | 15.2 | Solar & Battery | 16C17 | 2023-02-07 | 2023-02-17 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-17 | [7 empty] | 0 |  |  |  |  | 2023-09-07 | Online | [11 empty] | 16C AGAWAM
WMECO | Feeding Hills | ESMAEX-02074 | 1030 | 15.2 | Solar | 30A1 | 2023-01-26 | 2023-02-08 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-08 | [7 empty] | 0 |  |  |  |  | 2023-05-11 | Online | [11 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-02093 | 1106 | 20.56 | Solar & Battery | 22H13 | 2023-01-31 | 2023-02-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-15 | [7 empty] | 0 |  |  |  |  | 2023-07-07 | Online | [11 empty] | 22H FRANCONIA
WMECO | Pelham | ESMAEX-02103 | 1002 | 13.26 | Solar & Battery | 17K2 | 2023-02-02 | 2023-03-31 | 42 |  | 42 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-13 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [11 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-02155 | 1035 | 2000 | Solar | 17K5 | 2023-02-13 | 2023-02-15 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-11 | [7 empty] | 0 | [5 empty] | ISA Agreement | [10 empty] | 2000 | 17K AMHERST
WMECO | Colrain | ESMAEX-02141 | 1340 | 18.24 | Solar & Battery | 29R2 | 2023-02-08 | 2023-02-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-27 | [7 empty] | 0 |  |  |  |  | 2023-12-08 | Online | [11 empty] | 29R SHELBURNE
WMECO | Agawam | ESMAEX-02252 | 1001 | 15.2 | Solar | 30A5 | 2023-03-09 | 2023-03-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-23 | [7 empty] | 0 |  |  |  |  | 2023-08-14 | Online | [11 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-02230 | 1108 | 15.2 | Solar | 22H15 | 2023-03-03 | 2023-03-08 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-24 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online | [11 empty] | 22H FRANCONIA
WMECO | Longmeadow | ESMAEX-02189 | 1106 | 15.2 | Solar & Battery | 22H13 | 2023-02-22 | 2023-03-03 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online | [11 empty] | 22H FRANCONIA
WMECO | Southampton | ESMAEX-02171 | 1073 | 4980 | Solar & Battery | 15A1 | 2023-03-27 | 2023-06-02 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Transmission Study | [10 empty] | 4980 | 15A GUNN
WMECO | Lanesborough | ESMAEX-02210 | 1237 | 7.6 | Solar & Battery | 15E1 | 2023-02-28 | 2023-03-03 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [10 empty] | 14
WMECO | West Hatfield | ESMAEX-02405 | 1088 | 125 | Solar | 18G5 | 2023-04-21 | 2023-04-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2024-08-23 | Online | [11 empty] | 18G PODICK
WMECO | Blandford | ESMAEX-02238 | 1008 | 17.4 | Solar | 29A5 | 2023-03-06 | 2023-03-17 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-17 | [7 empty] | 0 |  |  |  |  | 2023-05-23 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Lee | ESMAEX-02279 | 1238 | 20.736 | Solar | 16B5 | 2023-03-17 | 2023-03-31 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-09-08 | Online | [11 empty] | 16B PLEASANT
WMECO | Longmeadow | ESMAEX-02289 | 1106 | 15.2 | Solar & Battery | 22H12 | 2023-03-21 | 2023-03-31 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-03 | [7 empty] | 0 |  |  |  |  | 2023-09-08 | Online | [11 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-02258 | 1201 | 12.98 | Solar | 19A7 | 2023-03-10 | 2023-03-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-07-20 | Online | [11 empty] | 19A DOREEN
WMECO | Amherst | ESMAEX-02259 | 1002 | 84.672 | Solar |  | 2023-03-10 | 2024-03-27 | 274 |  | 274 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-07 | [7 empty] | 0 |  |  |  |  | 2025-05-09 | Online
WMECO | Springfield | ESMAEX-02264 | 1108 | 8.26 | Solar & Battery | 21S12 | 2023-03-14 | 2023-03-20 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-21 | [7 empty] | 0 |  |  |  |  | 2023-05-03 | Online | [11 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-02288 | 1035 | 17.6 | Solar | 18G4 | 2023-03-20 | 2023-03-31 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-12 | [7 empty] | 0 |  |  |  |  | 2023-08-10 | Online | [11 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02312 | 1254 | 15.2 | Solar & Battery | 30B2 | 2023-03-27 | 2023-04-26 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-09-26 | Online | [11 empty] | 30B OSWALD
WMECO | Bernardston | ESMAEX-02295 | 1337 | 15.2 | Solar |  | 2023-03-22 | 2023-05-17 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online
WMECO | Cummington | ESMAEX-02311 | 1026 | 10 | Solar & Battery | 18C1 | 2023-03-27 | 2023-05-01 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-06 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-02314 | 1077 | 2000 | Solar | 29A5 | 2023-07-27 | 2023-08-02 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study | [7 empty] | Southwick |  | Phase 1 - Pending CIP Approval | 2000 | 29A SOUTHWICK
WMECO | Becket | ESMAEX-02317 | 1223 | 9.3 | Solar | 19J6 | 2023-03-28 | 2023-04-07 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-08-03 | Online
WMECO | Springfield | ESMAEX-02322 | 1109 | 999 | Solar & Battery | 20A21 | 2023-05-09 | 2023-06-09 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-18 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-02326 | 1002 | 10 | Solar | 19B16 | 2023-03-30 | 2023-04-12 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-16 | [7 empty] | 0 |  |  |  |  | 2023-09-21 | Online | [11 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-02362 | 1201 | 60 | Solar | 19A7 | 2023-04-10 | 2023-04-26 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2024-01-18 | Online | [11 empty] | DOREEN
WMECO | Hadley | ESMAEX-02350 | 1035 | 15.2 | Solar | 19B15 | 2023-04-06 | 2023-04-26 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-26 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online | [10 empty] | 15.2 | 19B MIDWAY
WMECO | Southampton | ESMAEX-02348 | 1073 | 6 | Solar | 15A1 | 2023-04-05 | 2023-04-26 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-26 | [7 empty] | 0 |  |  |  |  | 2023-06-26 | Online | [10 empty] | 6 | 15A GUNN
WMECO | Southampton | ESMAEX-02396 | 1073 | 6 | Solar | 15A3 | 2023-04-20 | 2023-05-05 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2023-08-31 | Online | [10 empty] | 6 | 15A GUNN
WMECO | Peru | ESMAEX-02361 | 1235 | 10 | Battery |  | 2023-04-10 | 2023-05-17 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-26 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online
WMECO | Longmeadow | ESMAEX-02370 | 1106 | 15.2 | Solar & Battery | 22H17 | 2023-04-11 | 2023-04-26 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-28 | [7 empty] | 0 |  |  |  |  | 2023-09-21 | Online | [11 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-02475 | 1254 | 50 | Solar | 30B7 | 2023-05-15 | 2023-05-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2025-01-31 | Online | [11 empty] | 30B OSWALD
WMECO | Greenfield | ESMAEX-02459 | 1301 | 25 | Solar | 22B7 | 2023-05-08 | 2023-05-12 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-23 | [7 empty] | 0 |  |  |  |  | 2023-12-27 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02394 | 1105 | 100 | Solar | 5J16 | 2023-04-19 | 2023-06-08 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-08 | [7 empty] | 0 |  |  |  |  | 2025-09-29 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-02390 | 1253 | 20 | Solar | 19J4 | 2023-04-19 | 2023-05-15 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-26 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Shelburne Falls | ESMAEX-02408 | 1370 | 250 | Solar |  | 2023-04-21 |  | -32042 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Application Review
WMECO | Southwick | ESMAEX-02540 | 1077 | 16.52 | Solar | 29A5 | 2023-05-30 | 2023-07-07 | 29 |  | 29 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-02541 | 1073 | 15.2 | Solar & Battery | 15A1 | 2023-05-31 | 2023-06-16 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-09-03 | Online | [11 empty] | 15A GUNN
WMECO | Worthington | ESMAEX-02438 | 1098 | 2000 | Solar & Battery | 18K3 | 2023-05-26 | 2023-06-02 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 2000 | 18K PLAINFIELD
WMECO | Longmeadow | ESMAEX-02482 | 1106 | 21 | Solar | 22H11 | 2023-05-16 | 2023-05-31 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online | [11 empty] | FRANCONIA
WMECO | Amherst | ESMAEX-02471 | 1002 | 7.8 | Solar & Battery | 17K2 | 2023-05-11 | 2023-05-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [11 empty] | 17K AMHERST
WMECO | Southampton | ESMAEX-02462 | 1073 | 10 | Solar | 15A3 | 2023-05-08 | 2023-05-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-09-05 | Online | [10 empty] | 10 | 15A GUNN
WMECO | Longmeadow | ESMAEX-02470 | 1106 | 15.2 | Solar & Battery | 22H13 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-25 | [7 empty] | 0 |  |  |  |  | 2023-09-12 | Online | [11 empty] | 22H FRANCONIA
WMECO | Sunderland | ESMAEX-02492 | 1375 | 25 | Solar |  | 2023-05-18 | 2023-05-24 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-08-02 | Online
WMECO | Montague | ESMAEX-02511 | 1376 | 4000 | Battery | 21C5 | 2023-05-23 | 2023-06-06 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4000 | 21C MONTAGUE
WMECO | Amherst | ESMAEX-02473 | 1002 | 15.2 | Solar & Battery | 19B16 | 2023-05-11 | 2023-07-06 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2023-10-17 | Online | [11 empty] | 19B MIDWAY
WMECO | Feeding Hills | ESMAEX-02493 | 1030 | 15.2 | Solar | 30A6 | 2023-05-18 | 2023-06-02 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-05 | [7 empty] | 0 |  |  |  |  | 2023-08-10 | Online | [11 empty] | 30A SILVER
WMECO | Worthington | ESMAEX-02520 | 1098 | 23.6 | Solar & Battery | 18C2 | 2023-05-25 | 2023-06-09 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-22 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Becket | ESMAEX-02484 | 1223 | 15.2 | Solar & Battery | 19J6 | 2023-05-16 | 2023-05-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online
WMECO | Deerfield | ESMAEX-02485 | 1342 | 15.2 | Solar & Battery | 22B1 | 2023-05-16 | 2023-06-06 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-06 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Ludlow | ESMAEX-02496 | 1056 | 14 | Battery | 27A6 | 2023-05-19 | 2023-10-13 | 106 |  | 106 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Becket | ESMAEX-02501 | 1223 | 4999 | Solar & Battery | 16B1 | 2023-05-22 | 2023-05-31 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-04 | [7 empty] | 0 | [5 empty] | ISA Agreement | [10 empty] | 4999 | 16B PLEASANT
WMECO | Southwick | ESMAEX-02529 | 1077 | 15.2 | Solar |  | 2023-05-26 | 2023-06-19 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-19 | [7 empty] | 0 |  |  |  |  | 2024-04-30 | Online
WMECO | Springfield | ESMAEX-02508 | 1109 | 14 | Battery | 5J14 | 2023-05-22 | 2023-07-31 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-10 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Blandford | ESMAEX-02512 | 1008 | 2656 | Solar & Battery | 19J2 | 2023-07-05 | 2023-07-13 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study | [7 empty] | Blandford |  | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Sunderland | ESMAEX-02515 | 1375 | 15.2 | Solar & Battery | 18G3 | 2023-05-24 | 2023-06-09 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-10-23 | Online | [11 empty] | 18G PODICK
WMECO | Montague | ESMAEX-02552 | 1376 | 4999 | Battery | 21C2 | 2023-07-20 | 2023-08-03 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague |  | Phase X - Pending CIP Approval |  | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-02604 | 1030 | 15.2 | Solar | 16C17 | 2023-06-22 | 2023-07-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online | [11 empty] | 16C AGAWAM
WMECO | West Hatfield | ESMAEX-02557 | 1088 | 15.2 | Solar | 18G5 | 2023-06-06 | 2023-06-27 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-01-05 | Online | [11 empty] | 18G PODICK
WMECO | Russell | ESMAEX-02599 | 1071 | 5 | Battery | 19J2 | 2023-06-21 | 2023-07-07 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Agawam | ESMAEX-02606 | 1001 | 996 | Solar | 30A3 | 2023-08-15 | 2023-08-17 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-02613 | 1235 | 19 | Solar | 18C2 | 2023-06-23 | 2023-07-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-02 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | South Deerfield | ESMAEX-02623 | 1373 | 20 | Solar | 22B3 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-14 | [7 empty] | 0 |  |  |  |  | 2023-12-18 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02625 | 1104 | 6 | Solar | 5J15 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-09-26 | Online | [10 empty] | 6 | 5J EAST SPRINGFIELD
WMECO | Tolland | ESMAEX-02715 | 1034 | 6 | Solar & Battery | 19J4 | 2023-07-26 | 2023-08-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-24 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Amherst | ESMAEX-02641 | 1002 | 18.048 | Solar | 17K8 | 2023-07-06 | 2023-08-30 | 40 |  | 40 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-03 | [7 empty] | 0 |  |  |  |  | 2023-11-13 | Online | [11 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-02695 | 1238 | 110 | Solar |  | 2023-07-20 | 2023-08-01 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-02 | [7 empty] | 0 |  |  |  |  | 2024-06-20 | Online
WMECO | Southwick | ESMAEX-02662 | 1077 | 4998 | Solar & Battery | 29A1 | 2023-08-08 | 2023-08-09 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-02696 | 1243 | 17.28 | Solar | 18C2 | 2023-07-21 | 2023-08-08 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-08 | [7 empty] | 0 |  |  |  |  | 2024-03-22 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Pittsfield | ESMAEX-02692 | 1201 | 22.8 | Solar & Battery | 30B4 | 2023-07-19 | 2023-08-03 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-06 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online | [11 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-02764 | 1104 | 15.2 | Solar | 5J10 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-28 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online | [10 empty] | 0 | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-02682 | 1027 | 15.2 | Solar & Battery | 15A5 | 2023-07-18 | 2023-12-15 | 109 |  | 109 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [11 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-02685 | 1054 | 15.2 | Solar & Battery | 21C7 | 2023-07-18 | 2023-09-06 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-25 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-02702 | 1089 | 11.21 | Solar & Battery | 21N4 | 2023-07-21 | 2023-08-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-07 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [11 empty] | 21N PIPER
WMECO | Middlefield | ESMAEX-02742 | 1243 | 10 | Battery | 18C2 | 2023-08-01 | 2023-09-05 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-02 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-02710 | 1073 | 15.2 | Solar & Battery |  | 2023-07-25 | 2023-08-03 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-12 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Amherst | ESMAEX-02721 | 1002 | 20 | Solar | 17K2 | 2023-07-28 | 2023-08-11 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-22 | [7 empty] | 0 |  |  |  |  | 2023-11-13 | Online | [11 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-02741 | 1201 | 120 | Solar | 30B4 | 2023-10-19 | 2023-11-06 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-11-14 | Online | [11 empty] | 30B OSWALD
WMECO | Leverett | ESMAEX-02743 | 1054 | 15.2 | Solar & Battery | 18G7 | 2023-08-01 | 2023-08-15 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-18 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online | [11 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02753 | 1254 | 24.4 | Solar | 30B7 | 2023-08-04 | 2023-08-11 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-15 | [7 empty] | 0 |  |  |  |  | 2025-09-09 | Online | [11 empty] | 30B OSWALD
WMECO | Agawam | ESMAEX-02765 | 1001 | 200 | Solar | 16C16 | 2023-08-29 | 2023-08-11 | -13 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-02 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 16C AGAWAM
WMECO | Easthampton | ESMAEX-02766 | 1027 | 10 | Solar | 15A3 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2023-12-18 | Online | [11 empty] | 15A GUNN
WMECO | Becket | ESMAEX-02759 | 1223 | 13.12 | Solar & Battery | 19J6 | 2023-08-04 | 2023-08-30 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-02 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Southampton | ESMAEX-02782 | 1073 | 15.2 | Solar & Battery | 15A1 | 2023-08-09 | 2023-08-17 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-18 | [7 empty] | 0 |  |  |  |  | 2024-01-03 | Online | [11 empty] | 15A GUNN
WMECO | Hinsdale | ESMAEX-02797 | 1235 | 4950 | Solar & Battery | 18C2 | 2023-12-07 | 2023-12-12 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Berkshire | Berkshire |  | Phase 1 - Executed ISA |  | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-02897 | 1070 | 5 | Solar & Battery | 18K4 | 2023-09-07 | 2023-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-18 | [7 empty] | 0 |  |  |  |  | 2024-05-07 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-02846 | 1075 | 4980 | Solar & Battery | 18K3 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 4980 | 18K PLAINFIELD
WMECO | Lanesborough | ESMAEX-02849 | 1237 | 4980 | Solar & Battery | 15E1 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 15E PARTRIDGE
WMECO | Agawam | ESMAEX-02855 | 1001 | 16 | Solar | 30A3 | 2023-08-23 | 2023-08-30 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-31 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online | [10 empty] | 16 | SILVER
WMECO | Indian Orchard | ESMAEX-02866 | 1151 | 6 | Solar | 27A13 | 2023-08-25 | 2023-08-30 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-03 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online | [10 empty] | 0 | 27A ORCHARD
WMECO | Northfield | ESMAEX-03085 | 1360 | 10 | Solar | 21B8 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-04 | [7 empty] | 0 |  |  |  |  | 2024-05-14 | Online | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Russell | ESMAEX-02942 | 1071 | 25 | Solar | 19J2 | 2023-09-21 | 2023-10-04 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-05-29 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-02907 | 1027 | 21.25 | Solar & Battery | 15A2 | 2023-09-11 | 2023-09-19 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-01 | [7 empty] | 0 |  |  |  |  | 2024-03-11 | Online | [11 empty] | 15A GUNN
WMECO | Dalton | ESMAEX-02940 | 1226 | 22.8 | Solar | 19A2 | 2023-09-21 | 2023-10-12 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-09-20 | Online | [11 empty] | 19A DOREEN
WMECO | Springfield | ESMAEX-02924 | 1108 | 10 | Battery | 22H15 | 2023-09-15 | 2023-10-12 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-06-21 | Online | [11 empty] | 22H FRANCONIA
WMECO | Tyringham | ESMAEX-02990 | 1264 | 15.2 | Solar & Battery |  | 2023-09-29 | 2023-10-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Dalton | ESMAEX-03002 | 1226 | 15.2 | Solar | 18C1 | 2023-10-02 | 2023-10-12 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-06-19 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Richmond | ESMAEX-03008 | 1254 | 15.2 | Solar | 30B2 | 2023-10-03 | 2023-10-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-13 | [7 empty] | 0 |  |  |  |  | 2024-04-16 | Online | [11 empty] | 30B OSWALD
WMECO | Hatfield | ESMAEX-03011 | 1038 | 1992 | Solar & Battery | 18G6 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [11 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03039 | 1056 | 20 | Solar | 19S3 | 2023-10-12 | 2023-11-06 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-06 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [11 empty] | 19S LUDLOW
WMECO | Pittsfield | ESMAEX-03068 | 1201 | 30 | Solar | 30B2 | 2023-10-19 | 2024-09-16 | 238 |  | 238 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-08 | [7 empty] | 0 | [5 empty] | Meter | [11 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-03047 | 1107 | 6 | Solar | 21S6 | 2023-10-13 | 2023-10-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-06 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online | [10 empty] | 6 | 21S CLINTON
WMECO | Ludlow | ESMAEX-03087 | 1056 | 17.28 | Solar | 19S1 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-02-08 | Online | [11 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-03121 | 1035 | 16 | Solar & Battery | 19B15 | 2023-11-06 | 2023-12-07 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-03-05 | Online | [11 empty] | 19B MIDWAY
WMECO | Dalton | ESMAEX-03120 | 1226 | 15.2 | Solar & Battery |  | 2023-11-06 | 2023-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-22 | [7 empty] | 0 |  |  |  |  | 2024-06-21 | Online
WMECO | Agawam | ESMAEX-03118 | 1001 | 14.79 | Solar | 30A1 | 2023-11-03 | 2023-11-16 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-08 | [7 empty] | 0 |  |  |  |  | 2024-05-20 | Online | [11 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-03125 | 1002 | 15 | Battery |  | 2023-11-07 | 2024-02-27 | 81 |  | 81 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-10-22 | Online
WMECO | Springfield | ESMAEX-03156 | 1118 | 7.6 | Solar & Battery | 20A32 | 2023-11-15 | 2023-11-20 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-12 | [7 empty] | 0 |  |  |  |  | 2024-11-22 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Deerfield | ESMAEX-03331 | 1342 | 10 | Battery | 22B7 | 2024-01-04 | 2024-03-13 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-25 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 22B CUMBERLAND
WMECO | Hatfield | ESMAEX-03241 | 1088 | 20 | Solar & Battery | 18G5 | 2023-12-06 | 2023-12-28 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-01 | [7 empty] | 0 |  |  |  |  | 2024-09-11 | Online | [11 empty] | 18G PODICK
WMECO | Westhampton | ESMAEX-03179 | 1027 | 15.2 | Solar | 15A3 | 2023-11-20 | 2023-11-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-13 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online | [11 empty] | 15A GUNN
WMECO | Tolland | ESMAEX-03176 | 1034 | 2988 | Solar & Battery | 19J4 | 2023-11-20 | 2023-12-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Blandford |  | Hold In Queue | 2988 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-03184 | 1027 | 100 | Solar | 15A2 | 2023-11-21 | 2023-11-22 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-08 | [7 empty] | 0 |  |  |  |  | 2024-01-24 | Online | [11 empty] | 15A GUNN
WMECO | Plainfield | ESMAEX-03192 | 1070 | 3820 | Solar & Battery | 18K3 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [10 empty] | 3820 | 18K PLAINFIELD
WMECO | Hadley | ESMAEX-03228 | 1035 | 499 | Solar | 18G6 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-24 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 499 | 18G PODICK
WMECO | Hadley | ESMAEX-03229 | 1035 | 499 | Solar | 18G5 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-02 | [7 empty] | 0 | [5 empty] | Technical Review | [10 empty] | 499 | 18G PODICK
WMECO | Whately | ESMAEX-03396 | 1093 | 84.6 | Solar & Battery | 18G8 | 2024-01-30 | 2024-02-22 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-16 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-03234 | 1027 | 15.2 | Solar | 15A3 | 2023-12-06 | 2023-12-22 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online | [11 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03323 | 1027 | 15.36 | Solar & Battery | 15A3 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [11 empty] | 15A GUNN
WMECO | Ashfield | ESMAEX-03516 | 1330 | 10 | Solar & Battery | 38A1 | 2024-03-08 | 2024-03-19 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-26 | [7 empty] | 0 |  |  |  |  | 2024-08-06 | Online | [10 empty] | 10 | 38A ASHFIELD
WMECO | Richmond | ESMAEX-03326 | 1254 | 15.36 | Solar & Battery | 30B2 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-13 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online | [11 empty] | 30B OSWALD
WMECO | Hadley | ESMAEX-03306 | 1035 | 10 | Solar | 18G4 | 2023-12-21 | 2024-01-04 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-23 | Online | [11 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03290 | 1056 | 7.6 | Battery | 27A4 | 2023-12-19 | 2024-01-17 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-15 | [7 empty] | 0 |  |  |  |  | 2024-11-19 | Online | [11 empty] | 27A ORCHARD
WMECO | Easthampton | ESMAEX-03304 | 1027 | 18 | Solar | 15A5 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-05 | [7 empty] | 0 |  |  |  |  | 2024-09-19 | Online | [11 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03309 | 1027 | 22.8 | Solar | 15A2 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [11 empty] | 15A GUNN
WMECO | Longmeadow | ESMAEX-03380 | 1106 | 15.2 | Solar & Battery |  | 2024-01-24 | 2024-02-01 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-26 | [7 empty] | 0 |  |  |  |  | 2024-10-28 | Online
WMECO | Buckland | ESMAEX-03311 | 1338 | 37.5 | Solar | 22B5 | 2023-12-22 | 2024-01-09 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-13 | [7 empty] | 0 |  |  |  |  | 2025-01-21 | Online | [11 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03327 | 1089 | 15.2 | Solar | 16C11 | 2024-01-03 | 2024-01-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-24 | [7 empty] | 0 |  |  |  |  | 2024-03-05 | Online | [10 empty] | 15.2 | 16C AGAWAM
WMECO | Westhampton | ESMAEX-03330 | 1027 | 15.2 | Solar & Battery | 15A3 | 2024-01-04 | 2024-01-17 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-08-29 | Online | [11 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-03343 | 1002 | 16.5 | Solar | 18G4 | 2024-01-09 | 2024-01-17 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [10 empty] | 15.95 | 18G PODICK
WMECO | Conway | ESMAEX-03473 | 1341 | 20 | Battery | 38A1 | 2024-02-22 | 2024-02-28 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-08-30 | Online | [10 empty] | 10 | 38A ASHFIELD
WMECO | Greenfield | ESMAEX-03367 | 1301 | 999 | Solar & Battery | 22B2 | 2025-04-25 | 2025-05-08 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 999 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-03638 | 1027 | 17.6 | Solar | 15A3 | 2024-04-08 | 2024-04-18 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-28 | [7 empty] | 0 |  |  |  |  | 2025-01-16 | Online | [11 empty] | 15A GUNN
WMECO | Greenfield | ESMAEX-03857 | 1301 | 30 | Solar | 22B4 | 2024-06-24 | 2024-07-25 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 |  |  |  |  | 2025-03-20 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Hancock | ESMAEX-04296 | 1237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 2000 | 30B OSWALD
WMECO | Tolland | ESMAEX-03388 | 1034 | 9.9 | Solar & Battery | 19J4 | 2024-01-26 | 2024-02-09 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-13 | [7 empty] | 0 |  |  |  |  | 2024-05-20 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Hancock | ESMAEX-04297 | 1237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 2000 | 30B OSWALD
WMECO | Pittsfield | ESMAEX-04298 | 1201 | 1000 | Solar | 30B7 | 2024-11-22 | 2025-01-22 | 44 |  | 44 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 1000 | 30B OSWALD
WMECO | South Deerfield | ESMAEX-03438 | 1373 | 10 | Battery | 18G3 | 2024-02-14 | 2024-03-18 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [11 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-03394 | 1035 | 15.2 | Solar | 17K5 | 2024-01-29 | 2024-02-01 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-12 | [7 empty] | 0 |  |  |  |  | 2024-09-13 | Online | [11 empty] | 17K AMHERST
WMECO | Lanesborough | ESMAEX-03409 | 1237 | 1992 | Solar & Battery | 30B5 | 2024-02-29 | 2024-03-06 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [11 empty] | 30B OSWALD
WMECO | Greenfield | ESMAEX-03468 | 1301 | 100 | Solar | 21C4 | 2024-02-21 | 2024-05-02 | 52 |  | 52 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-22 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Springfield | ESMAEX-03437 | 1118 | 5 | Solar & Battery | 20A21 | 2024-02-14 | 2024-02-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-26 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Plainfield | ESMAEX-03434 | 1070 | 24 | Solar | 18C1 | 2024-02-13 | 2024-04-23 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-04 | [7 empty] | 0 |  |  |  |  | 2024-10-06 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Turners Falls | ESMAEX-03587 | 1376 | 40 | Solar | 21C6 | 2024-03-28 | 2024-05-09 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-11 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Agawam | ESMAEX-03455 | 1001 | 1500 | Solar | 30A3 | 2024-05-06 | 2024-06-06 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [11 empty] | 30A SILVER
WMECO | West Springfield | ESMAEX-03502 | 1089 | 250 | Solar | 21N8 | 2024-03-01 | 2024-04-03 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-24 | [7 empty] | 0 |  |  |  |  | 2025-09-05 | Online | [11 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-03541 | 1103 | 700 | Fuel Cell | 8C13 | 2024-03-19 | 2024-04-03 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 8C WEST SPRINGFIELD
WMECO | Erving | ESMAEX-03495 | 1360 | 4980 | Solar & Battery | 21B8 | 2024-02-29 | 2024-03-18 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4980 | 21B FRENCH KING
WMECO | Worthington | ESMAEX-03482 | 1098 | 15.2 | Solar | 18C2 | 2024-02-27 | 2024-03-06 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-09-24 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Lenox Dale | ESMAEX-03488 | 1242 | 13.6 | Solar & Battery | 17G3 | 2024-02-28 | 2024-03-06 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-06 | [7 empty] | 0 |  |  |  |  | 2025-01-31 | Online | [11 empty] | 17G WOODLAND RD
WMECO | Worthington | ESMAEX-03492 | 1098 | 20 | Solar | 18C2 | 2024-02-29 | 2024-03-06 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-10-04 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03550 | 1104 | 32.83 | Solar | 5J13 | 2024-03-19 | 2024-05-13 | 40 |  | 40 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-22 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-03531 | 1253 | 70 | Solar | 19J4 | 2024-03-12 | 2024-04-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-24 | [7 empty] | 0 | [5 empty] | Construction Stage | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Lee | ESMAEX-03528 | 1238 | 10 | Solar & Battery | 16B5 | 2024-03-11 | 2024-03-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-25 | [7 empty] | 0 |  |  |  |  | 2024-08-09 | Online | [11 empty] | 16B PLEASANT
WMECO | Turners Falls | ESMAEX-03511 | 1376 | 990 | Battery | 21C8 | 2024-07-24 | 2024-09-16 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-25 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Hadley | ESMAEX-03526 | 1035 | 498 | Solar | 18G4 | 2024-06-11 | 2024-06-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Worthington | ESMAEX-03537 | 1098 | 16.8 | Solar | 18C2 | 2024-03-14 | 2024-03-21 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-08-29 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03563 | 1027 | 15.2 | Solar & Battery | 15A5 | 2024-03-21 | 2024-03-27 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-01 | [7 empty] | 0 |  |  |  |  | 2024-08-08 | Online | [11 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04793 | 1077 | 10 | Solar & Battery | 29A1 | 2025-04-15 | 2025-04-29 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-03579 | 1243 | 10 | Solar & Battery | 18C2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-31 | [7 empty] | 0 |  |  |  |  | 2025-01-24 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Peru | ESMAEX-03573 | 1235 | 4999.8 | Solar & Battery | 18C2 | 2024-03-25 | 2024-05-15 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Berkshire | Berkshire |  | Phase 1 - Executed ISA | 4999.8 | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03576 | 1027 | 15.2 | Solar | 15A2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-15 | [7 empty] | 0 |  |  |  |  | 2024-09-12 | Online | [11 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-03620 | 1089 | 50 | Solar |  | 2024-04-03 | 2024-05-15 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-28 | [7 empty] | 0 |  |  |  |  | 2025-01-22 | Online
WMECO | Deerfield | ESMAEX-03581 | 1342 | 46 | Solar & Battery | 22B4 | 2024-03-27 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-21 | [7 empty] | 0 |  |  |  |  | 2024-10-28 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-03600 | 1118 | 15.2 | Solar | 20A32 | 2024-04-01 | 2024-04-12 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-28 | [7 empty] | 0 |  |  |  |  | 2025-02-26 | Online | [11 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-03626 | 1002 | 20 | Solar | 18G3 | 2024-04-03 | 2024-06-05 | 46 |  | 46 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-11-07 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03681 | 1108 | 10 | Battery | 22H16 | 2024-04-18 | 2024-04-24 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-26 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online | [11 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-03648 | 1002 | 15.2 | Solar | 18G7 | 2024-04-09 | 2024-05-21 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [11 empty] | 18G PODICK
WMECO | Lanesborough | ESMAEX-03699 | 1237 | 9.9 | Solar & Battery | 15E1 | 2024-04-22 | 2024-05-13 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-10 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [10 empty] | 9.75
WMECO | Ludlow | ESMAEX-03662 | 1056 | 3.8 | Solar | 27A4 | 2024-04-12 | 2024-05-28 | 33 |  | 33 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-30 | [7 empty] | 0 |  |  |  |  | 2024-09-16 | Online | [11 empty] | 27A ORCHARD
WMECO | Pittsfield | ESMAEX-03669 | 1201 | 7.6 | Solar | 19A1 | 2024-04-15 | 2024-06-06 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [11 empty] | 19A DOREEN
WMECO | Savoy | ESMAEX-03695 | 1256 | 10 | Battery | 18K4 | 2024-04-22 | 2024-05-14 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-22 | [7 empty] | 0 |  |  |  |  | 2024-08-28 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Amherst | ESMAEX-03769 | 1002 | 100 | Solar | 17K7 | 2024-05-15 | 2024-05-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | Meter | [11 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-03737 | 1238 | 100 | Solar | 16B5 | 2024-05-07 | 2024-05-28 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 16B PLEASANT
WMECO | Shutesbury | ESMAEX-03732 | 1072 | 11.5 | Solar & Battery | 18G7 | 2024-05-03 | 2024-05-14 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-18 | [7 empty] | 0 |  |  |  |  | 2024-10-07 | Online | [11 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03727 | 1056 | 15.2 | Solar |  | 2024-05-02 | 2024-05-31 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-17 | [7 empty] | 0 |  |  |  |  | 2024-12-17 | Online
WMECO | Sunderland | ESMAEX-03718 | 1375 | 10 | Solar | 18G6 | 2024-04-30 | 2024-06-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-30 | [7 empty] | 0 |  |  |  |  | 2025-01-14 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03739 | 1108 | 240 | Solar | 22H17 | 2024-05-08 | 2024-05-16 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-26 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 22H FRANCONIA
WMECO | Hatfield | ESMAEX-03738 | 1038 | 15 | Solar | 18G6 | 2024-05-08 | 2024-05-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-12-02 | Online | [11 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-03748 | 1001 | 9 | Solar | 30A5 | 2024-05-10 | 2024-07-09 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-12 | [7 empty] | 0 |  |  |  |  | 2024-09-03 | Online | [11 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-03822 | 1235 | 4999.8 | Solar & Battery | 18C2 | 2024-06-10 | 2024-06-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | Berkshire | Berkshire |  | Phase 1 - Executed ISA | 4999.8 | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03751 | 1108 | 15.2 | Solar | 21S11 | 2024-05-10 | 2024-05-30 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-15 | [7 empty] | 0 |  |  |  |  | 2024-10-30 | Online | [11 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-03764 | 1375 | 20 | Solar | 18G6 | 2024-05-14 | 2024-06-06 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03772 | 1107 | 20 | Solar | 21S10 | 2024-05-15 | 2024-06-21 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-10 | [7 empty] | 0 |  |  |  |  | 2025-06-12 | Online | [11 empty] | 21S CLINTON
WMECO | Turners Falls | ESMAEX-03804 | 1376 | 600 | Internal Combustion Engine | 21C2 | 2024-05-30 | 2024-06-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Gill-Montague |  |  | 0 | 21C MONTAGUE
WMECO | Montgomery | ESMAEX-03811 | 1085 | 15.2 | Solar | 19J5 | 2024-06-04 | 2024-07-01 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2024-12-20 | Online | [7 empty] | Blandford
WMECO | Bernardston | ESMAEX-03896 | 1337 | 200 | Solar | 21B8 | 2024-07-12 | 2024-07-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Bernardston | ESMAEX-03897 | 1337 | 240 | Solar | 21B8 | 2024-07-12 | 2024-07-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Greenfield | ESMAEX-03922 | 1301 | 240 | Solar | 22B2 | 2024-07-24 | 2024-08-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-15 | [7 empty] | 0 | [5 empty] | Construction Stage | [11 empty] | 22B CUMBERLAND
WMECO | Greenfield | ESMAEX-03928 | 1301 | 240 | Solar | 22B7 | 2024-07-26 | 2024-08-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 22B CUMBERLAND
WMECO | Hatfield | ESMAEX-03820 | 1038 | 750 | Solar | 18G5 | 2024-10-24 | 2024-11-01 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-03843 | 1375 | 20 | Solar | 18G3 | 2024-06-14 | 2024-08-05 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [11 empty] | 18G PODICK
WMECO | Leyden | ESMAEX-03827 | 1337 | 10 | Solar | 22B7 | 2024-06-12 | 2024-07-08 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-07 | [7 empty] | 0 |  |  |  |  | 2025-01-02 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Colrain | ESMAEX-03862 | 1340 | 20 | Solar & Battery | 29R2 | 2024-06-25 | 2024-07-23 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-28 | [7 empty] | 0 |  |  |  |  | 2025-01-02 | Online | [11 empty] | 29R SHELBURNE
WMECO | South Deerfield | ESMAEX-03855 | 1373 | 15.2 | Solar | 22B1 | 2024-06-24 | 2024-07-05 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-08 | [7 empty] | 0 |  |  |  |  | 2024-11-26 | Online | [11 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03872 | 1089 | 20 | Solar | 21N9 | 2024-06-29 | 2024-07-23 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-29 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [11 empty] | 21N PIPER
WMECO | Ludlow | ESMAEX-03876 | 1056 | 23 | Solar & Battery | 19S3 | 2024-07-01 | 2024-07-09 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-02-14 | Online | [11 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-03880 | 1002 | 23 | Solar | 19B16 | 2024-07-02 | 2024-08-07 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2024-12-24 | Online | [11 empty] | 19B MIDWAY
WMECO | East Otis | ESMAEX-03888 | 1029 | 20 | Solar | 19J4 | 2024-07-10 | 2024-08-06 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-06 | [7 empty] | 0 |  |  |  |  | 2025-01-10 | Online | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-03925 | 1201 | 3500 | Solar & Battery | 15E2 | 2024-07-25 | 2024-08-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [11 empty] | 15E PARTRIDGE
WMECO | Lee | ESMAEX-03914 | 1238 | 4999 | Other | 16B5 | 2025-02-04 | 2025-02-11 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Standard |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 4999 | 16B PLEASANT
WMECO | Huntington | ESMAEX-03924 | 1050 | 23 | Solar & Battery | 19J5 | 2024-07-25 | 2024-08-20 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online
WMECO | Feeding Hills | ESMAEX-03937 | 1030 | 15.2 | Solar | 30A6 | 2024-07-30 | 2024-09-13 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-16 | [7 empty] | 0 |  |  |  |  | 2025-01-06 | Online | [11 empty] | 30A SILVER
WMECO | Tyringham | ESMAEX-03966 | 1264 | 23 | Solar | 16B1 | 2024-08-14 | 2024-08-28 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2025-01-14 | Online | [11 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-03954 | 1201 | 180 | Solar | 30B2 | 2024-09-06 | 2024-11-08 | 46 |  | 46 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-17 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-03961 | 1106 | 15.36 | Solar | 22H13 | 2024-08-12 | 2024-08-14 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-16 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [11 empty] | 22H FRANCONIA
WMECO | Lee | ESMAEX-03957 | 1238 | 15.2 | Solar | 16B5 | 2024-08-09 | 2024-09-11 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-06 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [11 empty] | 16B PLEASANT
WMECO | Montague | ESMAEX-03967 | 1351 | 20 | Battery | 21C7 | 2024-08-14 | 2024-09-11 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-16 | [7 empty] | 0 |  |  |  |  | 2024-12-30 | Online | [7 empty] | Gill-Montague |  |  | 10 | 21C MONTAGUE
WMECO | West Hatfield | ESMAEX-03989 | 1088 | 9.57 | Solar | 18G5 | 2024-08-22 | 2024-08-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [11 empty] | 18G PODICK
WMECO | Whately | ESMAEX-03978 | 1093 | 23 | Solar & Battery | 18G8 | 2024-08-18 | 2024-08-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-25 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 18G PODICK
WMECO | Otis | ESMAEX-03984 | 1253 | 5000 | Solar & Battery | 19J4 | 2024-09-09 | 2024-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Blandford |  | Hold In Queue |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-04002 | 1237 | 16.9 | Battery | 15E1 | 2024-08-27 | 2024-09-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-17 | [7 empty] | 0 | [5 empty] | Compliances Documents | [10 empty] | 6.9
WMECO | Southampton | ESMAEX-04025 | 1073 | 23 | Solar & Battery | 15A3 | 2024-09-04 | 2024-09-26 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-02-24 | Online | [11 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-04054 | 1002 | 30 | Solar | 18G7 | 2024-09-12 | 2024-09-20 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-01-24 | Online | [11 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-04039 | 1035 | 999 | Solar | 17K5 | 2024-11-19 | 2025-01-28 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [10 empty] | 999 | 17K AMHERST
WMECO | Hadley | ESMAEX-04202 | 1035 | 625 | Solar | 17K5 | 2024-10-24 | 2024-11-18 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 17K AMHERST
WMECO | Deerfield | ESMAEX-04030 | 1342 | 2500 | Solar | 22B4 | 2024-12-13 |  | -32472 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22B CUMBERLAND
WMECO | Lee | ESMAEX-04068 | 1238 | 15.2 | Solar |  | 2024-09-18 | 2024-10-22 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-24 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online
WMECO | Hadley | ESMAEX-04056 | 1035 | 240 | Solar | 17K1 | 2024-09-13 | 2024-09-19 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-03 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-04115 | 1077 | 7.6 | Solar | 29A1 | 2024-09-26 | 2024-10-17 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-28 | [7 empty] | 0 |  |  |  |  | 2025-07-17 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-04155 | 1073 | 15.2 | Solar | 15A1 | 2024-10-08 | 2024-10-28 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-03 | [7 empty] | 0 |  |  |  |  | 2025-03-12 | Online | [11 empty] | 15A GUNN
WMECO | North Hatfield | ESMAEX-04157 | 1066 | 17.16 | Solar | 18G6 | 2024-10-09 | 2024-10-18 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-09 | [7 empty] | 0 |  |  |  |  | 2025-04-08 | Online | [11 empty] | 18G PODICK
WMECO | Dalton | ESMAEX-04162 | 1226 | 3000 | Solar & Battery | 18C1 | 2024-11-01 | 2024-11-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review | [7 empty] | Berkshire |  | Hold In Queue |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-04166 | 1073 | 3000 | Solar & Battery | 15A1 | 2024-11-06 | 2024-11-18 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study | [11 empty] | 15A GUNN
WMECO | Ludlow | ESMAEX-04200 | 1056 | 7.6 | Solar | 19S3 | 2024-10-22 | 2024-11-08 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-18 | [7 empty] | 0 |  |  |  |  | 2025-03-25 | Online | [11 empty] | 19S LUDLOW
WMECO | Richmond | ESMAEX-04237 | 1254 | 10 | Solar & Battery | 30B7 | 2024-11-04 | 2024-11-12 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 | [7 empty] | 0 | [5 empty] | Technical Review | [11 empty] | 30B OSWALD
WMECO | Easthampton | ESMAEX-04203 | 1027 | 11.5 | Battery | 15A2 | 2024-10-24 |  | -32436 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-06-13 | Online | [11 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04231 | 1077 | 15 | Battery | 29A5 | 2024-11-01 | 2024-11-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-03 | [7 empty] | 0 |  |  |  |  | 2025-07-18 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-04607 | 1035 | 480 | Solar | 17K1 | 2025-03-07 | 2025-06-10 | 68 |  | 68 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 17K AMHERST
WMECO | Dalton | ESMAEX-04224 | 1226 | 24 | Solar | 19A2 | 2024-10-29 | 2024-11-06 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-06 | [7 empty] | 0 |  |  |  |  | 2025-02-27 | Online | [11 empty] | 19A DOREEN
WMECO | Hinsdale | ESMAEX-04230 | 1235 | 13.8 | Solar | 18C2 | 2024-11-01 | 2025-01-08 | 49 |  | 49 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-06 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-04274 | 1077 | 11.5 | Battery | 29A5 | 2024-11-13 |  | -32450 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-27 | [7 empty] | 0 |  |  |  |  | 2025-06-13 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-04280 | 1002 | 300 | Solar | 17K5 | 2025-02-14 | 2025-02-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-04356 | 1035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-05 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04357 | 1035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 19B MIDWAY
WMECO | West Springfield | ESMAEX-04335 | 1089 | 11.5 | Battery | 16C11 | 2024-12-05 | 2025-01-24 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-06 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 16C AGAWAM
WMECO | Blandford | ESMAEX-04291 | 1008 | 1999 | Solar & Battery | 19J2 | 2024-11-21 | 2024-12-05 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Blandford |  | Hold In Queue | 1999 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-04288 | 1201 | 46 | Solar & Battery |  | 2024-11-20 | 2024-11-26 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 | [7 empty] | 0 |  |  |  |  | 2025-07-16 | Online
WMECO | West Springfield | ESMAEX-04318 | 1089 | 22.77 | Solar |  | 2024-12-03 | 2024-12-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-14 | [7 empty] | 0 |  |  |  |  | 2025-09-17 | Online
WMECO | Feeding Hills | ESMAEX-04359 | 1030 | 15.2 | Solar | 30A1 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-18 | [7 empty] | 0 |  |  |  |  | 2025-10-20 | Online | [11 empty] | 30A SILVER
WMECO | Deerfield | ESMAEX-04370 | 1342 | 4999 | Solar & Battery | 22B7 | 2024-12-13 |  | -32472 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22B CUMBERLAND
WMECO | Erving | ESMAEX-04365 | 1344 | 200 | Solar | 21C8 | 2024-12-17 | 2025-01-28 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Amherst | ESMAEX-04361 | 1002 | 15.2 | Solar | 19B16 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-07 | [7 empty] | 0 |  |  |  |  | 2025-04-29 | Online | [11 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04385 | 1035 | 67.3 | Solar | 18G4 | 2024-12-16 | 2025-01-21 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-09-29 | Online | [11 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04467 | 1089 | 240 | Solar | 21N5 | 2025-06-17 | 2025-06-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-04403 | 1027 | 15.2 | Solar | 15A3 | 2024-12-23 | 2025-01-22 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-06-17 | Online | [11 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-04412 | 1109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04476 | 1201 | 120 | Solar | 30B2 | 2025-01-29 | 2025-02-11 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04431 | 1093 | 11.4 | Solar | 18G8 | 2025-01-14 | 2025-01-30 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-06-16 | Online | [11 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-04459 | 1027 | 15.2 | Solar | 15A5 | 2025-01-22 | 2025-02-07 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-17 | [7 empty] | 0 |  |  |  |  | 2025-06-18 | Online | [11 empty] | 15A GUNN
WMECO | Pittsfield | ESMAEX-04680 | 1201 | 1999 | Other | 30B3 | 2025-03-24 | 2025-04-16 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 30B OSWALD
WMECO | Hadley | ESMAEX-04586 | 1035 | 15.2 | Battery | 18G4 | 2025-03-04 | 2025-03-10 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-13 | Online | [10 empty] | 13.8 | 18G PODICK
WMECO | Pittsfield | ESMAEX-04470 | 1201 | 120 | Solar | 30B2 | 2025-01-28 | 2025-02-11 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 30B OSWALD
WMECO | Chesterfield | ESMAEX-04473 | 1012 | 30 | Solar & Battery |  | 2025-01-29 | 2025-02-26 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-05 | [7 empty] | 0 | [5 empty] | Construction Stage
WMECO | Hadley | ESMAEX-04478 | 1035 | 225 | Solar | 18G4 | 2025-01-31 | 2025-02-11 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Review | [11 empty] | 18G PODICK
WMECO | Westhampton | ESMAEX-04474 | 1027 | 15.2 | Solar | 15A3 | 2025-01-29 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 | [7 empty] | 0 |  |  |  |  | 2025-06-17 | Online | [11 empty] | 15A GUNN
WMECO | Conway | ESMAEX-04480 | 1341 | 18.48 | Solar | 38A1 | 2025-02-13 | 2025-02-26 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-26 | [7 empty] | 0 | [5 empty] | Compliances Documents | [11 empty] | 38A ASHFIELD
WMECO | Lee | ESMAEX-04484 | 1238 | 51.9 | Solar | 16B5 | 2025-02-04 | 2025-02-19 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-21 | [7 empty] | 0 |  |  |  |  | 2025-10-03 | Online | [11 empty] | 16B PLEASANT
WMECO | Hatfield | ESMAEX-04498 | 1038 | 9 | Solar | 18G5 | 2025-02-07 | 2025-03-21 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 |  |  |  |  | 2025-10-09 | Online | [10 empty] | 9 | 18G PODICK
WMECO | Leyden | ESMAEX-04516 | 1301 | 23 | Solar & Battery | 22B7 | 2025-02-24 | 2025-03-10 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-29 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-10 | Online | [10 empty] | 15 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-04497 | 1027 | 10.56 | Solar | 15A3 | 2025-02-07 | 2025-02-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-31 | [7 empty] | 0 |  |  |  |  | 2025-07-17 | Online | [11 empty] | 15A GUNN
WMECO | Hadley | ESMAEX-04495 | 1035 | 450 | Solar | 18G5 | 2025-03-10 | 2025-04-16 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Hinsdale | ESMAEX-04505 | 1235 | 4999 | Solar & Battery | 18C2 | 2025-02-10 | 2025-04-07 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Berkshire |  | Hold In Queue | 4999 | 18C BERKSHIRE
WMECO | Ludlow | ESMAEX-04504 | 1056 | 5.76 | Solar | 19S3 | 2025-02-10 | 2025-03-03 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-15 | [7 empty] | 0 | [5 empty] | Construction Stage | [11 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-04513 | 1002 | 15.744 | Solar | 17K8 | 2025-02-12 | 2025-02-25 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 | [7 empty] | 0 |  |  |  |  | 2025-10-08 | Online | [11 empty] | 17K AMHERST
WMECO | Conway | ESMAEX-04521 | 1341 | 11.5 | Solar & Battery | 38A1 | 2025-02-14 | 2025-03-24 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-30 | [7 empty] | 0 | [5 empty] | ISA Agreement | [11 empty] | 38A ASHFIELD
WMECO | Greenfield | ESMAEX-04532 | 1301 | 999.45 | Solar & Battery | 22B3 | 2025-03-27 | 2025-04-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 999.45 | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-04542 | 1073 | 20 | Solar | 15A1 | 2025-02-19 | 2025-03-10 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-08-26 | Online | [11 empty] | 15A GUNN
WMECO | Southampton | ESMAEX-04557 | 1073 | 10 | Solar | 15A1 | 2025-02-21 | 2025-03-10 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-09-18 | Online | [11 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-04568 | 1054 | 11.4 | Solar | 18G7 | 2025-02-25 | 2025-03-03 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-29 | Online | [11 empty] | 18G PODICK
WMECO | Pittsfield | ESMAEX-04562 | 1201 | 21.4 | Solar | 15E2 | 2025-03-03 | 2025-03-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-17 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-17 | Online
WMECO | Amherst | ESMAEX-04600 | 1002 | 7.6 | Solar | 18G7 | 2025-03-06 | 2025-03-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-17 | Online | [11 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04628 | 1089 | 50 | Solar | 21N5 | 2025-03-14 | 2025-04-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 21N PIPER
WMECO | Pittsfield | ESMAEX-04566 | 1201 | 4350 | Other | 15E2 | 2025-07-22 | 2025-08-13 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 4350 | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-04570 | 1056 | 8.36 | Solar & Battery | 19S2 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-12 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-26 | Online | [11 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-04573 | 1035 | 11.5 | Solar & Battery | 18G4 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-04578 | 1109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04602 | 1201 | 9.6 | Solar | 30B5 | 2025-03-05 | 2025-03-21 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-17 | Online | [11 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-04617 | 1106 | 5.76 | Solar | 22H11 | 2025-03-11 | 2025-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-27 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-12 | Online | [11 empty] | 22H FRANCONIA
WMECO | Hadley | ESMAEX-04633 | 1035 | 15.2 | Solar | 19B15 | 2025-03-14 | 2025-03-25 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-23 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-05 | Online | [11 empty] | 19B MIDWAY
WMECO | Springfield | ESMAEX-04651 | 1129 | 990 | Solar | 27A7 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-04657 | 1035 | 990 | Solar | 17K5 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 17K AMHERST
WMECO | Longmeadow | ESMAEX-04661 | 1106 | 240 | Solar | 22H12 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22H FRANCONIA
WMECO | Savoy | ESMAEX-04663 | 1256 | 5.76 | Solar | 18K4 | 2025-03-19 | 2025-04-09 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-15 | Online | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-04670 | 1027 | 17.6 | Solar & Battery |  | 2025-03-19 | 2025-04-29 | 30 |  | 30 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-20 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | New Ashford | ESMAEX-04682 | 1237 | 9.3 | Solar | 15E1 | 2025-03-24 | 2025-03-31 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Partridge |  |  |  | 15E PARTRIDGE
WMECO | Blandford | ESMAEX-04687 | 1008 | 498 | Solar | 19J2 | 2025-04-01 | 2025-04-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Designer Review | [11 empty] | 19J BLANDFORD
WMECO | Hadley | ESMAEX-04703 | 1035 | 22.8 | Solar | 18G5 | 2025-03-28 | 2025-04-15 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-15 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-29 | Online | [11 empty] | 18G PODICK
WMECO | Shelburne Falls | ESMAEX-04706 | 1370 | 498 | Solar | 29R2 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-03 |  |  |  | Complex |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 29R SHELBURNE
WMECO | Deerfield | ESMAEX-04917 | 1342 | 95 | Solar | 22B1 | 2025-05-14 | 2025-07-01 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-04725 | 1027 | 498 | Solar | 15A3 | 2025-07-01 | 2025-08-22 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Designer Review | [11 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-04764 | 1054 | 13.8 | Solar | 18G7 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [11 empty] | 18G PODICK
WMECO | Southampton | ESMAEX-04748 | 1073 | 1500 | Solar | 15A1 | 2025-04-07 | 2025-04-24 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 15A GUNN
WMECO | South Deerfield | ESMAEX-04749 | 1373 | 15.2 | Solar | 22B1 | 2025-04-07 | 2025-04-15 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-03 | Online | [11 empty] | 22B CUMBERLAND
WMECO | Buckland | ESMAEX-04755 | 1370 | 498 | Solar | 38A1 | 2025-04-23 | 2025-05-08 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 38A ASHFIELD
WMECO | Springfield | ESMAEX-05060 | 1105 | 161 | Solar | 21S12 | 2025-06-13 | 2025-07-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-04767 | 1375 | 7.6 | Solar | 18G6 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-19 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-30 | Online | [11 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-04769 | 1077 | 20 | Solar | 29A5 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Northfield | ESMAEX-04863 | 1360 | 11.5 | Solar & Battery | 21B8 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-11 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-02 | Online | [7 empty] | Gill-Montague |  |  | 10 | 21B FRENCH KING
WMECO | Hinsdale | ESMAEX-04784 | 1235 | 4999 | Solar & Battery | 18C2 | 2025-04-10 | 2025-04-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Berkshire |  | Hold In Queue | 4999 | 18C BERKSHIRE
WMECO | Lee | ESMAEX-04791 | 1238 | 23 | Solar & Battery | 16B5 | 2025-04-14 | 2025-04-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-02 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-28 | Online | [10 empty] | 8 | 16B PLEASANT
WMECO | Easthampton | ESMAEX-04803 | 1027 | 11.5 | Other | 15A2 | 2025-04-17 | 2025-04-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-05 | Online | [11 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-04833 | 1030 | 4.22 | Solar & Battery | 16C17 | 2025-05-01 | 2025-05-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 16C AGAWAM
WMECO | Springfield | ESMAEX-04814 | 1105 | 99.9 | Solar |  | 2025-04-18 | 2025-06-30 | 52 |  | 52 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [10 empty] | 100
WMECO | Lanesborough | ESMAEX-04806 | 1237 | 5.76 | Solar | 30B5 | 2025-04-17 | 2025-05-01 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-08 | Online | [11 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04816 | 1093 | 498 | Solar | 18G8 | 2025-05-12 | 2025-06-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Granville | ESMAEX-04868 | 1034 | 7.6 | Solar | 29A5 | 2025-05-02 | 2025-05-20 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-23 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-20 | Online | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Agawam | ESMAEX-04834 | 1001 | 15.18 | Solar | 30A1 | 2025-04-25 | 2025-05-14 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-22 | Online | [11 empty] | 30A SILVER
WMECO | Otis | ESMAEX-04873 | 1253 | 16.2 | Solar | 19J4 | 2025-05-05 | 2025-06-11 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-24 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Hadley | ESMAEX-05100 | 1035 | 20 | Solar | 18G4 | 2025-06-24 | 2025-07-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 18G PODICK
WMECO | Cummington | ESMAEX-04865 | 1026 | 24.42 | Solar | 18C1 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-04 | Online | [7 empty] | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Leverett | ESMAEX-04895 | 1054 | 15.2 | Solar | 18G7 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-29 | Online | [11 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-04957 | 1373 | 250 | Solar | 22B3 | 2025-05-20 | 2025-06-01 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-04900 | 1002 | 10 | Solar | 19B16 | 2025-05-12 | 2025-05-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04867 | 1035 | 499 | Solar | 19B15 | 2025-05-16 | 2025-08-22 | 71 |  | 71 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 19B MIDWAY
WMECO | Ashfield | ESMAEX-04941 | 1330 | 10 | Solar | 38A1 | 2025-05-16 | 2025-06-02 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 38A ASHFIELD
WMECO | West Springfield | ESMAEX-05066 | 1089 | 80 | Solar |  | 2025-06-16 |  | -32603 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review
WMECO | Hadley | ESMAEX-05059 | 1035 | 100 | Solar | 17K5 | 2025-06-13 | 2025-06-30 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 17K AMHERST
WMECO | Longmeadow | ESMAEX-04880 | 1106 | 15.2 | Solar | 22H12 | 2025-05-06 | 2025-05-30 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-03 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-10 | Online | [11 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-04891 | 1002 | 10 | Solar | 19B16 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-27 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [11 empty] | 19B MIDWAY
WMECO | Otis | ESMAEX-04888 | 1253 | 20 | Solar | 19J4 | 2025-05-06 | 2025-06-23 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Greenfield | ESMAEX-04959 | 1301 | 22.8 | Solar | 22B4 | 2025-05-20 | 2025-06-10 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 22B CUMBERLAND
WMECO | Conway | ESMAEX-04906 | 1341 | 15 | Solar | 38A1 | 2025-05-13 | 2025-05-21 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-07 | Online | [11 empty] | 38A ASHFIELD
WMECO | Bernardston | ESMAEX-04910 | 1337 | 15.2 | Solar | 21C1 | 2025-05-13 | 2025-06-10 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Pittsfield | ESMAEX-04946 | 1201 | 15.18 | Solar | 19A1 | 2025-05-18 | 2025-06-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-25 | Online | [11 empty] | 19A DOREEN
WMECO | Hinsdale | ESMAEX-04934 | 1235 | 15.2 | Solar | 18C2 | 2025-05-15 | 2025-06-01 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Hadley | ESMAEX-04936 | 1035 | 499 | Other | 17K5 | 2025-08-01 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 499 | 17K AMHERST
WMECO | Ashfield | ESMAEX-04962 | 1330 | 50 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 38A ASHFIELD
WMECO | Ashfield | ESMAEX-04963 | 1330 | 120 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 38A ASHFIELD
WMECO | Pittsfield | ESMAEX-04950 | 1201 | 15.2 | Solar | 30B7 | 2025-05-19 | 2025-06-06 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 30B OSWALD
WMECO | Huntington | ESMAEX-05030 | 1050 | 10 | Solar | 19J5 | 2025-06-09 | 2025-06-26 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-28 | Online
WMECO | West Springfield | ESMAEX-04964 | 1089 | 15.2 | Solar | 16C11 | 2025-05-21 | 2025-06-04 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-11 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-24 | Online | [11 empty] | 16C AGAWAM
WMECO | Lee | ESMAEX-04965 | 1238 | 7.6 | Solar | 16B5 | 2025-05-21 | 2025-06-10 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [11 empty] | 16B PLEASANT
WMECO | Southampton | ESMAEX-04983 | 1073 | 19 | Solar | 15A1 | 2025-05-27 | 2025-06-05 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [11 empty] | 15A GUNN
WMECO | Granville | ESMAEX-05010 | 1034 | 498 | Solar | 29A5 | 2025-06-26 | 2025-07-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Feeding Hills | ESMAEX-05012 | 1030 | 5.76 | Solar | 30A6 | 2025-06-04 | 2025-07-10 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-31 | Online | [11 empty] | 30A SILVER
WMECO | Hadley | ESMAEX-05024 | 1035 | 225 | Solar | 18G4 | 2025-06-06 | 2025-06-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-11 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Pittsfield | ESMAEX-05016 | 1201 | 5.76 | Solar | 30B5 | 2025-06-05 | 2025-06-23 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-11 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 30B OSWALD
WMECO | Southwick | ESMAEX-05043 | 1077 | 15.76 | Solar | 29A1 | 2025-06-10 | 2025-06-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-27 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Springfield | ESMAEX-05072 | 1104 | 250 | Solar | 5J9 | 2025-06-19 | 2025-06-30 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [11 empty] | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-05056 | 1027 | 7.6 | Solar | 15A5 | 2025-06-13 | 2025-06-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 15A GUNN
WMECO | Montgomery | ESMAEX-05069 | 1085 | 20 | Solar | 19J5 | 2025-06-16 | 2025-07-01 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | West Springfield | ESMAEX-05093 | 1089 | 160 | Solar |  | 2025-06-20 | 2025-07-25 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 21N PIPER
WMECO | Hatfield | ESMAEX-05096 | 1038 | 10 | Solar | 18G5 | 2025-06-20 | 2025-07-03 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-05106 | 1035 | 999 | Solar | 18G4 | 2025-09-26 |  | -32677 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [10 empty] | 999 | 18G PODICK
WMECO | Ludlow | ESMAEX-05166 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05168 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05169 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05170 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05171 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05172 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05173 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05202 | 1056 | 100 | Solar | 27A6 | 2025-07-15 | 2025-07-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-05109 | 1035 | 1750 | Solar | 18G4 | 2025-08-05 | 2025-08-22 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-05102 | 1035 | 499 | Solar | 19B15 | 2025-07-21 | 2025-08-13 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-05107 | 1201 | 11.5 | Solar & Battery | 30B7 | 2025-06-23 | 2025-07-10 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-31 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 30B OSWALD
WMECO | Westhampton | ESMAEX-05132 | 1027 | 50 | Solar |  | 2025-06-26 | 2025-07-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Erving | ESMAEX-05120 | 1344 | 5.76 | Solar | 21C8 | 2025-06-25 | 2025-07-10 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Lanesborough | ESMAEX-05162 | 1237 | 6.9 | Solar | 15E1 | 2025-07-07 | 2025-07-21 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-22 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Conway | ESMAEX-05133 | 1341 | 28.33 | Solar | 38A1 | 2025-06-26 | 2025-08-22 | 42 |  | 42 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 38A ASHFIELD
WMECO | Longmeadow | ESMAEX-05136 | 1106 | 22.8 | Solar | 22H13 | 2025-06-27 | 2025-07-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 22H FRANCONIA
WMECO | West Springfield | ESMAEX-05140 | 1089 | 7.6 | Solar | 16C11 | 2025-06-27 | 2025-07-18 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 16C AGAWAM
WMECO | Westhampton | ESMAEX-05160 | 1027 | 498 | Solar | 15A3 | 2025-07-21 | 2025-08-13 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 15A GUNN
WMECO | Colrain | ESMAEX-05161 | 1340 | 15.2 | Solar | 29R2 | 2025-07-07 | 2025-07-18 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-10 | Online | [11 empty] | 29R SHELBURNE
WMECO | Hadley | ESMAEX-05179 | 1035 | 7.6 | Solar | 17K5 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-05197 | 1077 | 3340 | Solar | 29A1 | 2025-09-24 | 2025-10-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 29A SOUTHWICK
WMECO | Turners Falls | ESMAEX-05407 | 1376 | 483 | Solar | 21C2 | 2025-09-02 | 2025-09-29 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 21C MONTAGUE
WMECO | Russell | ESMAEX-05189 | 1071 | 15.2 | Solar | 19J2 | 2025-07-10 | 2025-07-14 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-05194 | 1201 | 10.89 | Solar | 30B7 | 2025-07-11 | 2025-07-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-12 | Online | [11 empty] | 30B OSWALD
WMECO | Huntington | ESMAEX-05195 | 1050 | 20.736 | Solar | 19J5 | 2025-07-11 | 2025-07-22 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Amherst | ESMAEX-05190 | 1002 | 5.76 | Solar | 17K1 | 2025-07-10 | 2025-07-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-05198 | 1201 | 400 | Solar | 19A8 | 2025-08-08 | 2025-08-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 19A DOREEN
WMECO | Agawam | ESMAEX-05206 | 1001 | 7.6 | Solar | 30A3 | 2025-07-15 | 2025-07-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-10 | Online | [11 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05282 | 1002 | 37.3 | Solar | 17K2 | 2025-08-05 | 2025-09-08 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-05235 | 1035 | 5.76 | Solar | 18G4 | 2025-07-28 | 2025-07-29 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-05214 | 1373 | 19 | Solar | 22B3 | 2025-07-18 | 2025-07-18 | 1 |  | 1 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-05 | Online | [10 empty] | 19 | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-05221 | 1002 | 19.032 | Solar | 18G7 | 2025-07-22 | 2025-07-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [11 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-05215 | 1056 | 11 | Solar | 19S3 | 2025-07-18 |  | -32627 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 19S LUDLOW
WMECO | Granville | ESMAEX-05260 | 1034 | 11.5 | Other | 29A5 | 2025-07-31 | 2025-08-25 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [10 empty] | 0 | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-05251 | 1035 | 7.6 | Solar | 19B15 | 2025-07-29 | 2025-08-04 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 19B MIDWAY
WMECO | Northfield | ESMAEX-05292 | 1360 | 11.4 | Solar | 21B8 | 2025-08-07 | 2025-08-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | Gill-Montague |  |  | 9 | 21B FRENCH KING
WMECO | Ludlow | ESMAEX-05272 | 1056 | 4988 | Solar & Battery | 19S3 | 2025-08-04 | 2025-08-22 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 4988 | 19S LUDLOW
WMECO | Amherst | ESMAEX-05291 | 1002 | 15.2 | Solar | 17K8 | 2025-08-07 | 2025-08-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 17K AMHERST
WMECO | Worthington | ESMAEX-05332 | 1098 | 7.6 | Solar & Battery | 18C2 | 2025-08-18 | 2025-08-26 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 18C BERKSHIRE
WMECO | Deerfield | ESMAEX-05268 | 1342 | 498 | Solar | 18G3 | 2025-08-13 | 2025-09-03 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 18G PODICK
WMECO | Whately | ESMAEX-05270 | 1093 | 166 | Solar | 18G8 | 2025-08-15 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 18G PODICK
WMECO | Plainfield | ESMAEX-05280 | 1070 | 4950 | Solar | 18K3 | 2025-10-02 | 2025-10-21 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 18K PLAINFIELD
WMECO | Greenfield | ESMAEX-05511 | 1301 | 67.3 | Solar | 22B8 | 2025-09-29 | 2025-10-08 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-05297 | 1073 | 11.4 | Solar | 15A1 | 2025-08-08 | 2025-09-04 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 15A GUNN
WMECO | Whately | ESMAEX-05315 | 1093 | 250 | Solar | 18G6 | 2025-10-08 | 2025-10-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 18G PODICK
WMECO | Otis | ESMAEX-05411 | 1253 | 25 | Solar | 19J4 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | Blandford |  |  | 20 | 19J BLANDFORD
WMECO | Springfield | ESMAEX-05318 | 1101 | 11.5 | Other | 22H15 | 2025-08-14 | 2025-08-26 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 22H FRANCONIA
WMECO | West Springfield | ESMAEX-05357 | 1089 | 5.376 | Battery | 16C11 | 2025-08-22 | 2025-09-18 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [11 empty] | 16C AGAWAM
WMECO | Greenfield | ESMAEX-05340 | 1301 | 240 | Solar | 22B7 | 2025-08-27 | 2025-09-12 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-05510 | 1105 | 50 | Solar |  | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Bernardston | ESMAEX-05356 | 1337 | 10 | Solar | 21B8 | 2025-08-22 | 2025-09-03 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-05361 | 1201 | 15.2 | Solar | 19A7 | 2025-08-25 | 2025-08-26 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 19A DOREEN
WMECO | Chicopee | ESMAEX-05362 | 1013 | 980 | Solar | 21N7 | 2025-10-31 |  | -32702 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 21N PIPER
WMECO | Agawam | ESMAEX-05364 | 1001 | 480 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 30A SILVER
WMECO | Bernardston | ESMAEX-05375 | 1337 | 499 | Solar | 21C1 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 21C MONTAGUE
WMECO | Southwick | ESMAEX-05377 | 1077 | 23 | Battery | 29A5 | 2025-08-26 | 2025-09-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | Southwick |  |  | 13.4 | 29A SOUTHWICK
WMECO | Savoy | ESMAEX-05391 | 1256 | 4980 | Solar & Battery | 18C1 | 2025-09-25 | 2025-10-15 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 18C BERKSHIRE
WMECO | Sunderland | ESMAEX-05409 | 1375 | 11.5 | Other | 18G6 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [10 empty] | 20 | 18G PODICK
WMECO | Montague | ESMAEX-05600 | 1351 | 21.4 | Solar |  | 2025-10-17 | 2025-10-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Longmeadow | ESMAEX-05437 | 1106 | 15.2 | Solar | 22H11 | 2025-09-10 | 2025-09-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 22H FRANCONIA
WMECO | Greenfield | ESMAEX-05464 | 1301 | 150 | Solar | 22B6 | 2025-09-16 |  | -32669 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 22B CUMBERLAND
WMECO | Middlefield | ESMAEX-05454 | 1243 | 22.8 | Solar | 18C2 | 2025-09-15 | 2025-09-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [11 empty] | 18C BERKSHIRE
WMECO | Northfield | ESMAEX-05455 | 1360 | 15.76 | Solar | 21B8 | 2025-09-15 | 2025-09-29 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Easthampton | ESMAEX-05559 | 1027 | 50 | Solar |  | 2025-10-09 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Longmeadow | ESMAEX-05468 | 1106 | 15.2 | Solar | 22H18 | 2025-09-17 | 2025-09-29 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-05474 | 1201 | 400 | Solar | 15E2 | 2025-10-15 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-05477 | 1056 | 20 | Solar & Battery | 19S1 | 2025-09-17 | 2025-09-25 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-31 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [10 empty] | 20 | 19S LUDLOW
WMECO | Longmeadow | ESMAEX-05480 | 1106 | 21.25 | Solar | 22H13 | 2025-09-17 | 2025-09-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [11 empty] | 22H FRANCONIA
WMECO | Southwick | ESMAEX-05487 | 1077 | 450 | Solar | 29A1 | 2025-10-24 |  | -32697 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-05493 | 1237 | 23 | Other | 30B5 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-05513 | 1089 | 30 | Solar |  | 2025-09-25 | 2025-10-16 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Southwick | ESMAEX-05501 | 1077 | 160 | Solar |  | 2025-09-23 | 2025-10-08 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold
WMECO | Easthampton | ESMAEX-05523 | 1027 | 11.5 | Solar & Battery | 15A1 | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 15A GUNN
WMECO | Lanesborough | ESMAEX-05508 | 1237 | 6 | Solar | 15E1 | 2025-09-24 | 2025-10-14 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement
WMECO | Easthampton | ESMAEX-05524 | 1027 | 11.5 | Solar & Battery | 15A5 | 2025-09-29 | 2025-10-02 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 15A GUNN
WMECO | Hatfield | ESMAEX-05525 | 1038 | 19.8 | Solar |  | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Bernardston | ESMAEX-05531 | 1337 | 15.2 | Solar | 21C1 | 2025-10-01 |  | -32680 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [11 empty] | 21C MONTAGUE
WMECO | Amherst | ESMAEX-05535 | 1002 | 240 | Solar | 17K3 | 2025-10-02 | 2025-10-15 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-05536 | 1238 | 249 | Solar | 16B5 | 2025-10-03 | 2025-10-14 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 16B PLEASANT
WMECO | Agawam | ESMAEX-05539 | 1001 | 70 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [11 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05613 | 1002 | 18.666 | Solar | 17K2 | 2025-10-23 |  | -32696 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-05552 | 1223 | 4999 | Solar | 16B1 | 2025-10-06 | 2025-10-24 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 4999 | 16B PLEASANT
WMECO | Otis | ESMAEX-05624 | 1253 | 11.52 | Solar | 19J4 | 2025-10-23 | 2025-11-05 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Otis | ESMAEX-05593 | 1253 | 13.2 | Solar | 19J4 | 2025-10-16 | 2025-10-28 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-05631 | 1201 | 23 | Solar | 30B7 | 2025-10-24 | 2025-11-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [10 empty] | 20 | 30B OSWALD
WMECO | South Deerfield | ESMAEX-05590 | 1373 | 17.16 | Solar | 18G3 | 2025-10-15 | 2025-10-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Review | [11 empty] | 18G PODICK
WMECO | Greenfield | ESMAEX-05596 | 1301 | 50 | Solar |  | 2025-10-16 | 2025-10-28 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold
WMECO | Deerfield | ESMAEX-05662 | 1342 | 80 | Solar | 22B3 | 2025-10-31 |  | -32702 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [11 empty] | 22B CUMBERLAND
WMECO | Southwick | ESMAEX-05612 | 1077 | 22.8 | Solar | 29A5 | 2025-10-23 |  | -32696 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [11 empty] | 29A SOUTHWICK
WMECO | Pittsfield | ESMAEX-05603 | 1201 | 15.2 | Solar | 19A1 | 2025-10-20 | 2025-10-31 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 19A DOREEN
WMECO | Gill | ESMAEX-05628 | 1354 | 17.6 | Solar | 21B8 | 2025-10-24 |  | -32697 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [11 empty] | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-05629 | 1201 | 5.76 | Solar | 30B1 | 2025-10-24 | 2025-10-28 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [11 empty] | 30B OSWALD
Fitchburg | Lunenburg | 11855 | 1462 | 0 | Storage - Battery | F30W30 | 2025-10-13 | 2025-10-29 | 12 | 8 | 4 | 2025-10-29 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11847 | 1420 | 7.6 | Solar + Energy Storage | F11W12 | 2025-10-08 | 2025-10-24 | 12 | 4 | 8 | 2025-10-24 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11843 | 1420 | 3.8 | Solar + Energy Storage | F25W28 | 2025-10-07 | 2025-10-23 | 12 | 5 | 7 | 2025-10-23 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11834 | 1420 | 7.6 | Solar + Energy Storage | F11W12 | 2025-10-01 | 2025-10-09 | 7 | 4 | 3 | 2025-10-09 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Ashby | 11833 | 1431 | 10 | Solar + Energy Storage | F39W19 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11832 | 1420 | 5.7 | Solar + Energy Storage | F40W42 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11831 | 1420 | 0 | Storage - Battery | F01W04 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11829 | 1420 | 100 | Solar | F11W11 | 2025-09-30 | 2025-10-27 | 19 | 16 | 3 | 2025-10-27 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11828 | 1420 | 100 | Solar | F40W39 | 2025-09-30 | 2025-10-24 | 18 | 15 | 3 | 2025-10-24 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11822 | 1420 | 3.8 | Solar + Energy Storage | F40W38 | 2025-09-29 | 2025-10-13 | 10 | 5 | 5 | 2025-10-13 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11815 | 1420 | 12.2 | Solar + Energy Storage | F40W40 | 2025-09-24 | 2025-10-16 | 16 | 9 | 7 | 2025-10-16 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11813 | 1420 | 10 | Solar + Energy Storage | F35W36 | 2025-09-23 | 2025-10-16 | 17 | 13 | 4 | 2025-10-16 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11811 | 1420 | 7.6 | Solar + Energy Storage | F25W27 | 2025-09-23 | 2025-10-14 | 15 | 6 | 9 | 2025-10-14 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Fitchburg | 11803 | 1420 | 15.2 | Solar | F31W34 | 2025-09-22 | 2025-10-01 | 8 | 7 | 1 | 2025-10-01 | 2025-10-02 | 2 | 0 | 2 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11790 | 1420 | 15.7 | Solar + Energy Storage | F40W40 | 2025-09-17 | 2025-09-24 | 7 | 6 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11787 | 1462 | 11.5 | Solar + Energy Storage | F30W30 | 2025-09-23 | 2025-10-01 | 11 | 10 | 1 | 2025-10-01 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11783 | 1462 | 20 | Solar | F30W30 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11780 | 1420 | 11.5 | Solar + Energy Storage | F25W27 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11773 | 1420 | 17.6 | Solar + Energy Storage | F40W42 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11772 | 1420 | 15.7 | Solar + Energy Storage | F25W27 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-30 | 5 | 0 | 5 | [20 empty] | 2025-10-16 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11759 | 1420 | 15.7 | Solar + Energy Storage | F40W40 | 2025-09-10 | 2025-09-30 | 15 | 10 | 5 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11752 | 1420 | 11.5 | Solar + Energy Storage | F22W1 | 2025-09-08 | 2025-10-01 | 18 | 12 | 3 | 2025-10-01 | 2025-10-02 | 1 | 0 | 1 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11742 | 1420 | 11.5 | Solar + Energy Storage | F22W1 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-29 | 4 | 0 | 4 | [20 empty] | 2025-09-29 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11739 | 1462 | 0 | Storage - Battery | F30W31 | 2025-09-02 | 2025-10-01 | 22 | 16 | 6 | 2025-10-01 | [28 empty] | Expedited | [9 empty] | Expedited Screening On Hold | Res | Y
Fitchburg | Townsend | 11738 | 1474 | 15.7 | Solar + Energy Storage | F39W18 | 2025-09-02 | 2025-09-30 | 21 | 15 | 6 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11737 | 1420 | 23.8 | Solar + Energy Storage | F01W02 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-10-01 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11728 | 1420 | 17.6 | Solar + Energy Storage | F11W12 | 2025-08-28 | 2025-09-03 | 4 | 3 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-08 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11726 | 1420 | 250.8 | Solar | F50W55 | 2025-08-27 | 2025-09-30 | 24 | 14 | 10 | 2025-09-30 | [28 empty] | Expedited | [9 empty] | Expedited Screening | Res | Y
Fitchburg | Fitchburg | 11727 | 1420 | 180.4 | Solar | F50W55 | 2025-08-27 | 2025-10-02 | 26 | 11 | 15 | 2025-10-03
Fitchburg | Fitchburg | 11722 | 1420 | 7.6 | Solar + Energy Storage | F40W42 | 2025-08-26 | 2025-09-23 | 20 | 16 | 4 | 2025-09-23 | 2025-10-06 | 10 | 7 | 3 | [20 empty] | 2025-10-14 |  |  | YES | Expedited | [9 empty] | Waiting for Signed ISA | Res | Y
Fitchburg | Fitchburg | 11713 | 1420 | 11.5 | Solar + Energy Storage | F22W1 | 2025-08-21 | 2025-09-03 | 9 | 8 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-23 |  |  | Yes | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11709 | 1420 | 15.7 | Solar+Energy Storage | 25W27 | 2025-08-20 | 2025-08-28 | 8 | 5 | 3 | 2025-08-28 | 2025-08-29 | 1 | 0 | 1 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11700 | 1462 | 17.6 | Solar | 30W31 | 2025-08-18 | 2025-08-28 | 9 | 7 | 2 | 2025-08-28 | 2025-09-04 | 5 | 0 | 5 | [20 empty] | 2025-09-12 |  |  | YES | Expedited | [9 empty] | Waiting for Signed ISA | Res | Y
Fitchburg | Fitchburg | 11691 | 1420 | 13.8 | Solar + Energy Storage | F40W40 | 2025-08-27 | 2025-09-23 | 19 | 10 | 9 | 2025-09-23 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11677 | 1474 | 15.7 | Solar+Energy Storage | 39W18 | 2025-08-11 | 2025-08-25 | 11 | 7 | 4 | 2025-08-25 | 2025-08-29 | 5 | 2 | 3 | [20 empty] | 2025-09-07 |  |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11676 | 1420 | 13.7 | Solar+Energy Storage | 25W28 | 2025-08-11 | 2025-08-21 | 9 | 2 | 7 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11675 | 1420 | 15.7 | Solar+Energy Storage | 11W12 | 2025-08-11 | 2025-08-21 | 10 | 7 | 3 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-08 |  |  | Yes | Expedited | [9 empty] | Waiting for Signed ISA | Res | Y
Fitchburg | Lunenburg | 11674 | 1462 | 17.6 | Solar+Energy Storage | 31W37 | 2025-08-11 | 2025-08-20 | 8 | 7 | 1 | 2025-08-20 | 2025-08-27 | 6 | 0 | 6 | [20 empty] | 2025-08-27 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11663 | 1420 | 11.5 | Solar+Energy Storage | 40W42 | 2025-08-06 | 2025-08-14 | 16 | 10 | 6 | 2025-08-14 | 2025-08-15 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11658 | 1420 | 13.7 | Solar | F25W28 | 2025-08-11 | 2025-09-11 | 24 | 20 | 4 | 2025-09-11 | 2025-09-12 | 1 | 0 | 1 | [20 empty] | 2025-09-22 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11605 | 1420 | 7.6 | Solar+Energy Storage | 31W34 | 2025-07-16 | 2025-07-29 | 10 | 6 | 4 | 2025-08-11 | 2025-08-11 | 0 | 0 | 0 | [20 empty] | 2025-08-14 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11600 | 1420 | 33.1 | Solar | 20W22 | 2025-07-15 | 2025-07-25 | 9 | 7 | 2 | 2025-07-25 | 2025-07-28 | 3 | 0 | 3 | [20 empty] | 2025-07-29 |  |  | NO | Expedited | [8 empty] | 2025-08-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 11578 | 1420 | 16.2 | Solar | 25W27 | 2025-07-09 | 2025-07-22 | 10 | 7 | 3 | 2025-07-22 | 2025-07-25 | 4 | 0 | 4 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11571 | 1420 | 11.5 | Solar+Energy Storage | 11W11 | 2025-07-08 | 814/2025 | 13 | 9 | 4 | 2025-08-14 | 2025-08-14 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11554 | 1462 | 17.4 | Solar | 30W30 | 2025-06-27 | 2025-07-23 | 18 | 16 | 2 | 2025-07-23 | 2025-07-24 | 1 | 0 | 1 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Ashby | 11539 | 1431 | 990 | Solar | 39W19 | 2025-06-24 | 2025-07-29 | 25 | 22 | 3 | [10 empty] | 2025-07-29 | 2025-08-01 | 3 | 0 | 3 | [14 empty] | Standard | [9 empty] | Cancelled | Comm | N
Fitchburg | Fitchburg | 11527 | 1420 | 996 | Solar+Energy Storage | 40W40 | 2025-06-23 | 2025-06-30 | 5 | 4 | 1 | [10 empty] | 2025-06-30 | 2025-07-09 | 7 | 0 | 7 | [14 empty] | Standard | [9 empty] | On Hold | Comm | N
Fitchburg | West Townsend | 11518 | 1474 | 24.576 | Solar | 39W18 | 2025-07-01 | 2025-07-07 | 3 | 0 | 3 | 2025-07-07 | 2025-07-08 | 1 | 0 | 1 | [20 empty] | 2025-07-16 | 2025-08-18 |  | YES | Expedited | [9 empty] | Perform Mods | Res | Y
Fitchburg | Ashby | 11517 | 1431 | 20 | Solar | 39W19 | 2025-06-23 | 2025-07-08 | 10 | 6 | 4 | 2025-07-08 | 2025-07-09 | 1 | 0 | 1 | [20 empty] | 2025-07-09 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11513 | 1420 | 11.5 | Solar + Energy Storage | 50W56 | 2025-06-13 | 2025-06-24 | 10 | 3 | 7 | 2025-06-24 | 2025-06-26 | 3 | 0 | 3 | [20 empty] | 2025-07-03 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 11496 | 1431 | 23 | Solar + Energy Storage | 40W40 | 2025-06-09 | 2025-06-25 | 15 | 9 | 6 | 2025-06-25 | 2025-07-21 | 18 | 17 | 1 | [20 empty] | 2025-07-21 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11481 | 1420 | 11.5 | Solar + Energy Storage | 40W40 | 2025-06-02 | 2025-06-16 | 10 | 9 | 1 | 2025-06-16 | 2025-07-07 | 14 | 4 | 10 | [20 empty] | 2025-07-07 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11474 | 1469 | 498 | Solar | 39W18 | 2025-05-29 | 2025-06-05 | 5 | 2 | 3 | [10 empty] | 2025-06-06 | 2025-06-17 | 7 | 0 | 7 | 2025-09-26 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N
Fitchburg | Lunenburg | 11447 | 1462 | 11.4 | Solar | 31W37 | 2025-05-20 | 2025-06-05 | 22 | 12 | 10 | 2025-06-05 | 2025-06-11 | 5 | 0 | 5 | [20 empty] | 2025-06-14 |  |  | NO | Expedited | [8 empty] | 2025-07-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 11439 | 1462 | 15.2 | Solar | 30W30 | 2025-05-16 | 2025-05-30 | 10 | 8 | 2 | 2025-05-30 | 2025-06-03 | 3 | 0 | 3 | [20 empty] | 2025-06-10 | 2025-08-05 |  | YES | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 11437 | 1420 | 20.1 | Solar | 50W56 | 2025-06-03 | 2025-06-05 | 2 | 1 | 1 | 2025-06-05 | 2025-06-11 | 4 | 0 | 4 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11351 | 1420 | 49.7 | Solar | 22W1 | 2025-04-18 | 2025-05-12 | 20 | 17 | 3 | 2025-05-12 | 2025-05-13 | 1 | 0 | 1 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11344 | 1469 | 11.5 | Solar + Energy Storage | 15W17 | 2025-04-17 | 2025-04-28 | 8 | 7 | 1 | 2025-04-28 | 2025-04-30 | 3 | 0 | 3 | [20 empty] | 2025-05-13 |  |  | NO | Expedited | [8 empty] | 2025-08-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 11336 | 1462 | 11.5 | Solar + Energy Storage | 31W37 | 2025-04-15 | 2025-04-28 | 10 | 5 | 5 | 2025-05-01 | 2025-05-02 | 3 | 0 | 3 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Townsend | 11328 | 1469 | 10 | Solar + Energy Storage | 39W18 | 2025-04-30 | 2025-05-01 | 1 | 0 | 1 | 2025-05-01 | 2025-05-05 | 4 | 0 | 4 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11249 | 1420 | 15.2 | Solar | 20W22 | 2025-04-15 | 2025-04-25 | 9 | 4 | 5 | 2025-04-25 | 2025-04-28 | 2 | 0 | 2 | [20 empty] | 2025-04-01 |  |  | NO | Expedited | [8 empty] | 2025-07-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 11240 | 1462 | 38 | Solar | 30W30 | 2025-03-17 | 2025-04-08 | 17 | 5 | 12 | 2025-04-21 | 2025-04-21 | 1 | 0 | 1 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11230 | 1462 | 9 | Solar + Energy Storage | 31W37 | 2025-04-15 | 2025-05-05 | 15 | 8 | 7 | 2025-05-05 | 2025-05-09 | 5 | 0 | 5 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11228 | 1462 | 1000 | Solar + Energy Storage | 30W30 | 2025-03-12 | 2025-03-26 | 11 | 10 | 1 | [10 empty] | 2025-03-27 | 2025-03-31 | 3 | 0 | 3 | 2025-07-18 | 2025-10-17 | 64 | 0 | 64 | [9 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N
Fitchburg | Fitchburg | 11216 | 1420 | 15.2 | Solar | 50W55 | 2025-03-10 | 2025-04-17 | 29 | 26 | 3 | 2025-04-17 | 2025-04-28 | 8 | 0 | 8 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11190 | 1469 | 15.84 | Solar | 15W16 | 2025-03-01 | 2025-03-27 | 19 | 0 | 19 | 2025-03-27 | 2025-03-29 | 1 | 0 | 1 | [20 empty] | 2025-04-16 |  |  | No | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11176 | 1420 | 4999 | Storage - Battery | 40W39 | 2025-02-28 | 2025-03-13 | 10 | 9 | 1 | [10 empty] | 2025-03-15 | 2025-03-25 | 7 | 0 | 7 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Fitchburg | 11167 | 1420 | 15.2 | Solar | 01W04 | 2025-03-06 | 2025-03-26 | 14 |  | 14 | 2025-03-27 | 2025-03-31 | 3 |  | 3 | [20 empty] | 2025-04-02 |  |  | NO | Expedited | [8 empty] | 2025-05-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 11163 | 1420 | 9.5 | Solar | 11W11 | 2025-02-20 | 2025-03-10 | 13 | 12 | 1 | 2025-03-11 | 2025-03-11 | 1 | 0 | 1 | [20 empty] | 2025-03-14 |  |  | NO | Expedited | [8 empty] | 2025-07-31 | In Operation | Res | Y
Fitchburg | Ashby | 11154 | 1431 | 20 | Solar | 39W19 | 2025-02-17 | 2025-03-04 | 12 | 11 | 1 | 2025-03-10 | 2025-03-11 | 2 | 0 | 2 | [20 empty] | 2025-03-31 | 2025-05-19 |  | YES | Expedited | [8 empty] | 2025-08-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 11150 | 1462 | 20 | Solar | 30W30 | 2025-02-14 | 2025-03-03 | 12 | 11 | 1 | 2025-03-04 | 2025-03-04 | 1 | 0 | 1 | [20 empty] | 2025-04-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11144 | 1420 | 4000 | Storage - Battery | 40W39 | 2025-04-22 | 2025-05-14 | 17 | 10 | 7 | [10 empty] | 2025-05-15 | 2025-05-16 | 2 | 0 | 2 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Townsend | 11113 | 1469 | 15.2 | Solar | 15W17 | 2025-02-03 | 2025-02-19 | 13 | 12 | 1 | 2025-02-19 | 2025-02-20 | 2 | 0 | 2 | [20 empty] | 2025-02-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11059 | 1420 | 34.6 | Solar | 20W22 | 2025-01-08 | 2025-01-23 | 12 | 9 | 3 | 2025-01-24 | 2025-01-24 | 1 | 0 | 1 | [20 empty] | 2025-01-29 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11032 | 1462 | 0 | Storage - Battery | 31W38 | 2024-12-26 | 2025-02-10 | 33 | 32 | 1 | 2025-02-18 | 2025-03-13 | 18 | 6 | 12 | [20 empty] | 2025-03-28 | 2025-05-06 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 10973 | 1420 | 4998 | Storage - Battery | 40W39 | 2025-04-04 | 2025-04-21 | 11 | 6 | 5 | [10 empty] | 2025-04-30 | 2025-05-02 | 2 | 0 | 2 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Fitchburg | 10966 | 1420 | 16.13 | Solar | 22W1 | 2024-12-04 | 2024-12-24 | 15 | 14 | 1 | 2025-01-06 | 2025-01-07 | 2 |  | 2 | [20 empty] | 2025-01-17 |  |  | NO | Expedited | [8 empty] | 2025-03-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 10960 | 1420 | 5.76 | Solar + Energy Storage | 01W02 | 2024-12-02 | 2024-12-06 | 5 | 0 | 5 | 2024-12-19 | 2024-12-19 | 1 | 0 | 1 | [20 empty] | 2025-01-02 |  |  | NO | Expedited | [8 empty] | 2025-06-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 10943 | 1420 | 7.72 | Solar | 35W36 | 2024-11-26 | 2024-12-23 | 19 | 14 | 5 | 2024-12-24 | 2025-01-07 | 10 |  | 10 | [20 empty] | 2025-01-28 |  |  | NO | Expedited | [8 empty] | 2025-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 10833 | 1462 | 15.2 | Solar + Energy Storage | 31W37 | 2024-10-28 | 2024-11-21 | 18 | 17 | 1 | 2024-11-22 | 2024-11-26 | 3 |  | 3 | [20 empty] | 2024-12-13 |  |  | NO | Expedited | [8 empty] | 2025-03-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 10724 | 1462 | 10 | Solar | 30W31 | 2024-09-30 | 2024-10-17 | 13 | 4 | 9 | 2024-10-18 | 2024-10-18 | 1 |  | 1 | [20 empty] | 2024-10-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 10673 | 1431 | 0 | Storage - Battery | 39W19 | 2024-09-17 | 2024-10-23 | 26 | 17 | 9 | 2024-10-24 | 2024-10-25 | 2 | 0 | 2 | [20 empty] | 2024-10-30 |  |  | NO | Expedited | [8 empty] | 2025-06-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 10586 | 1420 | 40 | Solar | 40W39 | 2024-08-28 | 2024-11-05 | 48 | 44 | 4 | 2024-11-06 | 2024-11-07 | 2 | 0 | 2 | [20 empty] | 2024-11-17 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | N
Fitchburg | Fitchburg | 10579 | 1420 | 120 | Solar | 40W39 | 2024-08-27 | 2024-11-06 | 50 | 49 | 1 | 2024-11-13 | 2024-11-14 | 2 |  | 2 | [20 empty] | 2024-12-04 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 10556 | 1462 | 10 | Solar + Energy Storage | 30W31 | 2024-08-22 | 2024-09-17 | 18 | 9 | 9 | 2024-09-18 | 2024-09-18 | 1 |  | 1 | [20 empty] | 2024-09-27 |  |  | NO | Expedited | [8 empty] | 2025-02-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 10460 | 1462 | 33.75 | Solar + Energy Storage | 30W30 | 2024-07-19 | 2024-09-27 | 50 | 47 | 3 | 2024-09-27 | 2024-09-30 | 2 |  | 2 | [20 empty] | 2024-10-17 |  |  | NO | Expedited | [8 empty] | 2025-03-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 10421 | 1420 | 15.51 | Solar | 01W04 | 2024-07-09 | 2024-08-01 | 18 | 16 | 2 | 2024-08-01 | 2024-08-01 | 1 |  | 1 | [20 empty] | 2024-08-12 |  |  | NO | Expedited | [8 empty] | 2024-12-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 10273 | 1420 | 9.8 | Solar + Energy Storage | 25W27 | 2024-05-28 | 2024-07-01 | 25 | 20 | 5 | 2024-07-02 | 2024-07-08 | 4 |  | 4 | [20 empty] | 2024-07-31 |  |  | NO | Expedited | [8 empty] | 2024-12-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 10188 | 1420 | 250 | Solar | 22W1 | 2024-05-07 | 2024-05-13 | 5 | 0 | 5 | 2024-05-14 | 2024-07-30 | 54 | 0 | 54 | [20 empty] | 2024-09-02 | 2025-02-26 |  | YES | Expedited | [9 empty] | Perform Mods | Res | N
Fitchburg | Townsend | 10182 | 1474 | 8.832 | Solar + Energy Storage | 39W18 | 2024-05-06 | 2024-05-20 | 11 | 10 | 1 | 2024-05-21 | 2024-05-21 | 1 |  | 1 | [20 empty] | 2024-05-28 |  |  | NO | Expedited | [8 empty] | 2025-02-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 10133 | 1462 | 6 | Solar + Energy Storage | 30W30 | 2024-04-19 | 2024-06-06 | 34 | 32 | 2 | [5 empty] | 2024-07-11 | 2024-07-12 | 2 | 0 | 2 | [15 empty] | 2024-07-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 10102 | 1420 | 66 | Solar | 31W34 | 2024-04-11 | 2024-04-30 | 13 | 5 | 8 | 2024-05-06 | 2024-06-03 | 20 | 17 | 3 | [20 empty] | 2024-06-24 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | N
Fitchburg | Fitchburg | 10090 | 1420 | 120 | Solar | 50W55 | 2024-04-08 | 2024-05-06 | 20 | 10 | 10 | 2024-05-07 | 2024-05-08 | 2 |  | 2 | [20 empty] | 2024-05-28 |  |  | NO | Expedited | [8 empty] | 2025-05-07 | In Operation | Res | N
Fitchburg | Ashby | 10089 | 1431 | 14.83 | Solar + Energy Storage | 39W19 | 2024-04-08 | 2024-04-18 | 8 | 6 | 2 | 2024-04-19 | 2024-04-19 | 1 |  | 1 | [20 empty] | 2024-05-03 |  |  | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 10055 | 1420 | 80 | Solar | 50W56 | 2024-03-28 | 2024-04-11 | 11 | 7 | 4 | 2024-04-12 | 2024-04-17 | 3 | 0 | 3 | [20 empty] | 2024-04-22 |  |  | NO | Expedited | [8 empty] | 2025-07-23 | In Operation | Comm | Y
Fitchburg | Townsend | 9985 | 1474 | 10 | Solar w/ Back-up Battery | 39W18 | 2024-03-11 | 2024-03-25 | 11 | 10 | 1 | 2024-03-26 | 2024-03-26 | 1 |  | 1 | [20 empty] | 2024-04-02 |  |  | NO | Expedited | [8 empty] | 2024-07-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 9883 | 1420 | 16.13 | Solar | 22W1 | 2024-02-13 | 2024-04-18 | 46 | 39 | 7 | 2024-04-19 | 2024-04-19 | 1 |  | 1 | [20 empty] | 2024-04-25 |  |  | NO | Expedited | [9 empty] | Cancelled
Fitchburg | Lunenburg | 9793 | 1462 | 16.89 | Solar | 30W30 | 2024-01-19 | 2024-02-06 | 13 | 6 | 7 | 2024-02-07 | 2024-02-08 | 2 |  | 2 | [20 empty] | 2024-03-06 | 2024-03-18 |  | YES | Expedited | [8 empty] | 2025-03-18 | In Operation | Res | Y
Fitchburg | Townsend | 9697 | 1469 | 0 | battery | 15W16 | 2023-12-19 | 2024-02-19 | 41 | 37 | 4 | 2024-02-20 | 2024-04-08 | 35 | 30 | 5 | [20 empty] | 2024-04-11 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 9661 | 1469 | 14.8 | Solar + Energy Storage | 39W18 | 2023-12-07 | 2024-01-28 | 34 | 25 | 9 | 2024-01-29 | 2024-01-29 | 1 |  | 1 | [20 empty] | 2024-02-13 |  |  | NO | Expedited | [8 empty] | 2024-05-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 9582 | 1462 | 6.48 | Solar + Energy Storage | 30W31 | 2023-11-20 | 2024-05-15 | 122 | 120 | 2 | 2024-05-16 | 2024-06-06 | 15 |  | 15 | [20 empty] | 2024-06-24 |  |  | NO | Expedited | [8 empty] | 2024-07-19 | In Operation | Res | Y
Fitchburg | Townsend | 9572 | 1474 | 6 | Solar w/ Back-up Battery | 39W18 | 2023-11-17 | 2023-12-19 | 22 | 16 | 6 | 2023-12-20 | 2023-12-22 | 3 |  | 3 | [20 empty] | 2024-01-04 |  |  | NO | Expedited | [8 empty] | 2024-08-05 | In Operation | Res | Y
Fitchburg | Townsend | 9547 | 1469 | 14.8 | Solar + Energy Storage | 15W16 | 2023-11-13 | 2023-12-14 | 23 | 8 | 15 | 2023-12-15 | 2023-12-18 | 2 |  | 2 | [20 empty] | 2023-12-21 |  |  | NO | Expedited | [8 empty] | 2024-04-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 9480 | 1462 | 15.744 | Solar | 31W38 | 2023-11-02 | 2023-11-14 | 9 | 7 | 2 | 2023-11-15 | 2023-11-15 | 1 |  | 1 | [20 empty] | 2023-11-16 |  |  | NO | Expedited | [8 empty] | 2024-01-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 9438 | 1420 | 18 | Solar | 20W22 | 2023-10-26 | 2023-12-14 | 35 | 28 | 7 | 2023-12-15 | 2023-12-15 | 1 |  | 1 | [20 empty] | 2024-01-10 | 2024-01-30 |  | YES | Expedited | [8 empty] | 2024-04-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 9124 | 1462 | 7.6 | Solar + Energy Storage | 30W30 | 2023-09-25 | 2023-10-31 | 26 | 3 | 23 | 2023-11-01 | 2023-11-03 | 3 | 1 | 2 | [20 empty] | 2023-11-13 |  |  | NO | Expedited | [8 empty] | 2024-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 9097 | 1420 | 43.2 | Solar | 11W11 | 2023-09-08 | 2023-09-26 | 13 | 12 | 1 | 2023-09-27 | 2024-04-12 | 137 | 136 | 1 | [20 empty] | 2024-04-15 |  |  | NO | Expedited | [8 empty] | 2025-08-13 | In Operation | Comm | N
Fitchburg | Lunenburg | 9057 | 1462 | 6.27 | Solar + Energy Storage | 31W37 | 2023-08-30 | 2023-09-19 | 14 | 13 | 1 | 2023-09-20 | 2023-09-27 | 6 |  | 6 | [20 empty] | 2023-10-09 |  |  | NO | Expedited | [8 empty] | 2023-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 7795 | 1420 | 16 | Solar | 20W22 | 2023-07-19 | 2023-08-21 | 24 | 24 | 1 | 2023-08-21 | 2023-08-21 | 1 |  | 1 | [20 empty] | 2023-09-01 |  |  | NO | Expedited | [8 empty] | 2024-05-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 7752 | 1462 | 7.45 | Solar w/ Back-up Battery | 30W30 | 2023-08-18 | 2023-09-20 | 23 | 21 | 2 | 2023-09-21 | 2023-09-27 | 5 |  | 5 | [20 empty] | 2023-10-09 |  |  | NO | Expedited | [8 empty] | 2024-03-29 | In Operation | Res | Y
Fitchburg | Townsend | 7702 | 1469 | 3.8 | Solar + Energy Storage | 39W18 | 2023-09-06 | 2023-09-11 | 4 | 3 | 1 | 2023-09-15 | 2023-09-18 | 2 |  | 2 | [20 empty] | 2023-10-03 |  |  |  | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 7521 | 1469 | 180 | Solar | 15W17 | 2023-05-26 | 2023-06-07 | 8 | 7 | 1 | 2023-06-08 | 2023-06-09 | 2 |  | 2 | [20 empty] | 2023-06-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 7519 | 1469 | 100 | Solar | 15W17 | 2023-05-26 | 2023-05-31 | 3 | 3 | 1 | 2023-06-01 | 2023-06-02 | 2 | 0 | 2 | [20 empty] | 2023-06-07 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Comm | N
Fitchburg | Fitchburg | 7410 | 1420 | 5 | Solar | 11H10 | 2023-05-08 | 2023-05-26 | 15 | 11 | 4 | 2023-05-30 | 2023-05-30 | 1 |  | 1 | [20 empty] | 2023-06-07 | 2023-07-25 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 7401 | 1420 | 7.5 | Solar w/ Back-up Battery | 25W27 | 2023-07-05 | 2023-07-07 | 3 | 2 | 1 | 2023-07-07 | 2023-07-10 | 2 |  | 2 | [20 empty] | 2023-07-17 |  |  | NO | Expedited | [8 empty] | 2024-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 7320 | 1462 | 12.3 | Solar + Energy Storage | 30W31 | 2023-08-10 | 2023-08-17 | 6 | 5 | 1 | 2023-08-18 | 2023-08-21 | 2 |  | 2 | [20 empty] | 2023-09-01 |  |  | NO | Expedited | [8 empty] | 2023-10-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 7278 | 1462 | 15.9 | Solar | 30W30 | 2023-04-14 | 2023-05-12 | 20 | 19 | 1 | 2023-05-13 | 2023-05-19 | 5 |  | 5 | [20 empty] | 2023-05-24 |  |  | NO | Expedited | [8 empty] | 2023-07-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 7194 | 1420 | 4999 | Solar | 25W27 | 2023-03-22 | 2023-03-30 | 7 | 5 | 2 | [10 empty] | 2023-04-01 | 2023-04-18 | 11 |  |  | 2023-06-30 | 2023-11-08 | 91 |  | 91 | [5 empty] | 2024-08-01 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 7182 | 1420 | 15.6 | Solar | 11W11 | 2023-03-21 | 2023-04-13 | 18 | 15 | 3 | 2023-04-14 | 2023-04-24 | 6 |  | 6 | [20 empty] | 2023-05-03 | 2023-09-06 |  | YES | Expedited | [8 empty] | 2023-09-19 | In Operation | Res | Y
Fitchburg | Ashby | 7029 | 1431 | 7.965 | Solar + Energy Storage | 39W19 | 2023-02-08 | 2023-03-08 | 20 | 19 | 1 | 2023-03-09 | 2023-03-09 | 1 |  | 1 | [20 empty] | 2023-03-14 |  |  | NO | Expedited | [8 empty] | 2023-10-31 | In Operation | Res | Y
Fitchburg | Townsend | 6969 | 1469 | 3.8 | Solar + Energy Storage | 15W16 | 2023-01-24 | 2023-03-08 | 29 | 29 | 1 | 2023-03-08 | 2023-03-15 | 4 |  | 4 | [20 empty] | 2023-03-20 |  |  | NO | Expedited | [8 empty] | 2023-03-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 6751 | 1420 | 4999.2 | Storage - Battery | 50W55 | 2022-11-17 | 2022-11-29 | 8 | 7 | 1 | [10 empty] | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 2023-02-18 | 2024-08-19 | 374 | 196 | 178 | [5 empty] | 2024-10-25 |  |  | YES | Standard | [9 empty] | Waiting for Mods Fee | Comm | N
Fitchburg | Lunenburg | 6664 | 1462 | 12 | Solar + Energy Storage | 30W30 | 2022-11-02 | 2022-11-08 | 5 | 3 | 2 | 2022-11-09 | 2022-11-17 | 6 | 5 | 1 | [20 empty] | 2022-11-21 |  |  | NO | Expedited | [8 empty] | 2023-06-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 6561 | 1462 | 19 | Solar | 30W30 | 2022-10-07 | 2022-11-07 | 21 | 20 | 1 | 2022-11-08 | 2022-11-08 | 1 |  | 1 | [20 empty] | 2022-11-08 |  |  | NO | Expedited | [8 empty] | 2022-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 6550 | 1462 | 4999 | Storage - Battery | 30W30 | 2022-10-06 | 2022-10-20 | 10 | 9 | 1 | [10 empty] | 2022-10-22 | 2022-11-10 | 14 | 0 | 14 | 2023-02-18 | 2024-07-03 | 342 | 75 | 267 | [5 empty] | 2024-10-25 | 2025-10-03 |  | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 6544 | 1420 | 80 | Solar | 50W56 | 2022-10-05 | 2022-10-19 | 10 | 5 | 5 | 2022-10-20 | 2022-10-24 | 3 |  | 3 | [20 empty] | 2022-11-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 6370 | 1431 | 7.6 | Solar + Energy Storage | 39W19 | 2022-08-25 | 2022-09-19 | 17 | 3 | 14 | 2022-09-19 | 2023-01-30 | 85 | 81 | 4 | [20 empty] | 2023-02-02 |  |  | NO | Expedited | [8 empty] | 2023-10-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 6367 | 1462 | 16.128 | Solar | 30W31 | 2022-08-24 | 2022-09-02 | 8 | 3 | 5 | 2022-09-05 | 2022-09-15 | 8 |  | 8 | [20 empty] | 2022-09-21 |  |  | NO | Expedited | [8 empty] | 2023-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 6265 | 1420 | 490 | Solar | 35W36 | 2022-08-02 | 2022-08-16 | 11 | 10 | 1 | 2022-08-17 | 2022-09-13 | 19 | 0 | 19 | 2022-10-13 | 2022-12-09 | 40 | 8 | 32 | [15 empty] | 2022-12-27 | 2024-02-05 |  | YES | Expedited | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 6247 | 1420 | 7.5 | Solar | 01W02 | 2022-07-28 | 2022-08-19 | 17 | 16 | 1 | 2022-08-19 | 2022-08-22 | 2 |  | 2 | [20 empty] | 2022-08-25 |  |  | NO | Expedited | [8 empty] | 2023-01-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 6224 | 1462 | 4 | Solar | 30W30 | 2022-07-22 | 2022-07-29 | 6 | 5 | 1 | 2022-08-01 | 2022-08-02 | 2 |  | 2 | [20 empty] | 2022-08-03 |  |  | NO | Expedited | [8 empty] | 2022-09-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 6187 | 1420 | 10.03 | Solar + Energy Storage | 35W36 | 2022-07-15 | 2022-09-21 | 48 | 47 | 1 | 2022-09-22 | 2022-09-28 | 5 |  | 5 | [20 empty] | 2022-09-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 6129 | 1420 | 84.6 | Solar | 22W1 | 2022-06-30 | 2022-07-26 | 18 | 16 | 2 | 2022-07-27 | 2022-08-03 | 6 |  | 6 | [20 empty] | 2022-08-11 |  |  | NO | Expedited | [8 empty] | 2023-12-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 6065 | 1462 | 7.6 | Solar + Energy Storage | 31W38 | 2022-06-15 | 2022-09-13 | 63 | 59 | 4 | 2022-09-14 | 2022-12-23 | 69 |  | 69 | [20 empty] | 2022-12-27 |  |  | NO | Expedited | [8 empty] | 2024-01-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 6010 | 1462 | 10 | Solar | 30W31 | 2022-06-02 | 2022-06-07 | 4 | 3 | 1 | 2022-06-08 | 2022-06-08 | 1 |  | 1 | [20 empty] | 2022-06-13 |  |  | NO | Expedited | [8 empty] | 2022-08-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5982 | 1420 | 4.5 | Solar + Energy Storage | 20W22 | 2022-05-26 | 2022-06-15 | 14 | 12 | 2 | 2022-06-15 | 2022-06-29 | 11 | 10 | 1 | [20 empty] | 2022-08-22 |  |  | NO | Expedited | [8 empty] | 2022-09-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 5916 | 1420 | 3.8 | Solar | 11H10 | 2022-05-12 | 2022-05-18 | 5 | 4 | 1 | 2022-05-19 | 2022-05-19 | 1 |  | 1 | [20 empty] | 2022-05-20 |  |  | NO | Expedited | [8 empty] | 2022-07-25 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5914 | 1420 | 2.95 | Solar | 11W12 | 2022-05-12 | 2022-05-18 | 5 | 3 | 2 | 2022-05-19 | 2022-05-19 | 1 |  | 1 | [20 empty] | 2022-05-20 |  |  | NO | Expedited | [8 empty] | 2023-02-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5855 | 1420 | 6 | Solar | 11W12 | 2022-04-29 | 2022-05-05 | 5 | 3 | 2 | 2022-05-05 | 2022-05-05 | 1 |  | 1 | [20 empty] | 2022-05-09 |  |  | NO | Expedited | [8 empty] | 2022-07-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5850 | 1420 | 5.31 | Solar | 11H11 | 2022-04-28 | 2022-05-05 | 6 | 4 | 2 | 2022-05-05 | 2022-05-05 | 1 |  | 1 | [20 empty] | 2022-05-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5817 | 1420 | 10 | Solar | 11W11 | 2022-04-20 | 2022-04-25 | 4 | 2 | 2 | 2022-04-26 | 2022-04-27 | 2 |  | 2 | [20 empty] | 2022-04-29 |  |  | NO | Expedited | [8 empty] | 2022-07-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 5786 | 1420 | 6 | Solar | 11W11 | 2022-04-13 | 2022-04-25 | 8 | 5 | 3 | 2022-04-26 | 2022-04-27 | 2 |  | 2 | [20 empty] | 2022-04-29 |  |  | NO | Expedited | [8 empty] | 2022-07-06 | In Operation | Res | Y
Fitchburg | Ashby | 5781 | 1431 | 10 | Solar | 39W19 | 2022-04-12 | 2022-05-16 | 24 | 20 | 4 | 2022-05-17 | 2022-05-23 | 5 |  | 5 | [20 empty] | 2022-05-25 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5766 | 1420 | 6 | Solar | 40W42 | 2022-04-12 | 2022-04-15 | 4 | 1 | 3 | 2022-04-15 | 2022-04-15 | 1 |  | 1 | [20 empty] | 2022-04-21 |  |  | NO | Expedited | [8 empty] | 2022-06-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5758 | 1420 | 14.16 | Solar | 40W42 | 2022-04-11 | 2022-06-06 | 39 | 34 | 5 | 2022-06-07 | 2022-06-08 | 2 |  | 2 | [20 empty] | 2022-06-14 |  |  | NO | Expedited | [8 empty] | 2023-05-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 5726 | 1420 | 3800 | Solar | 11H10 | 2022-04-04 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5681 | 1469 | 10 | Solar | 15W17 | 2022-03-17 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5680 | 1420 | 8 | Solar | 40W42 | 2022-03-17 | 2022-03-21 | 3 | 3 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-04-25 |  |  | NO | Expedited | [8 empty] | 2022-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5679 | 1420 | 3.8 | Solar | 11W11 | 2022-03-17 | 2022-03-21 | 3 | 3 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-03-28 |  |  | NO | Expedited | [8 empty] | 2022-06-22 | In Operation | Res | Y
Fitchburg | Ashby | 5674 | 1431 | 10 | Solar | 39W19 | 2022-03-16 | 2022-03-21 | 4 | 4 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-04-25 |  |  | NO | Expedited | [8 empty] | 2022-05-26 | In Operation | Res | Y
Fitchburg | Townsend | 5647 | 1469 | 7.6 | Solar + Energy Storage | 15W16 | 2022-03-01 | 2022-04-13 | 32 | 25 | 7 | 2022-04-13 | 2022-04-14 | 2 |  | 2 | [20 empty] | 2022-04-21 | 2022-05-11 |  | YES | Expedited | [8 empty] | 2022-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 5639 | 1420 | 307.52 | Solar | 0 | 2022-02-28 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5616 | 1420 | 6 | Solar | 40W42 | 2022-02-22 | 2022-03-01 | 6 | 6 | 1 | 2022-03-02 | 2022-03-02 | 1 |  | 1 | [20 empty] | 2022-03-07 |  |  | NO | Expedited | [8 empty] | 2022-09-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 5604 | 1462 | 7.6 | Solar + Energy Storage | 30W30 | 2022-02-17 | 2022-03-11 | 16 | 16 | 1 | 2022-03-11 | 2022-03-24 | 10 | 9 | 1 | [20 empty] | 2022-03-28 | 2022-04-12 |  | YES | Expedited | [8 empty] | 2022-04-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5583 | 1420 | 6 | Solar | 40W42 | 2022-02-10 | 2022-02-16 | 5 | 4 | 1 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-22 |  |  | NO | Expedited | [8 empty] | 2022-05-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5582 | 1420 | 3.8 | Solar | 11W11 | 2022-02-10 | 2022-02-16 | 5 | 4 | 1 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 5574 | 1420 | 3.8 | Solar | 11W11 | 2022-02-09 | 2022-02-11 | 3 | 2 | 1 | 2022-02-14 | 2022-02-14 | 1 |  | 1 | [20 empty] | 2022-02-17 |  |  | NO | Expedited | [8 empty] | 2022-06-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 5573 | 1420 | 3.8 | Solar | 40W42 | 2022-02-09 | 2022-02-14 | 4 | 2 | 2 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5572 | 1420 | 3.8 | Solar | 11W11 | 2022-02-09 | 2022-02-24 | 11 | 8 | 3 | 2022-02-24 | 2022-02-24 | 1 |  | 1 | [20 empty] | 2022-03-17 |  |  | NO | Expedited | [8 empty] | 2022-06-24 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5547 | 1420 | 150 | Solar | 50W51 | 2022-02-01 | 2022-02-09 | 7 | 2 | 5 | 2022-02-10 | 2022-05-19 | 69 | 63 | 6 | [20 empty] | 2022-05-25 | 2023-09-25 | 2026-01-05 | YES | Expedited | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 5525 | 1420 | 6 | Solar | 11W11 | 2022-01-24 | 2022-02-03 | 9 | 7 | 2 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2022-06-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5523 | 1420 | 5 | Solar | 11H11 | 2022-01-24 | 2022-02-03 | 9 | 7 | 2 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5521 | 1469 | 8.56 | Solar + Energy Storage | 39W18 | 2022-01-24 | 2022-03-01 | 26 | 24 | 2 | 2022-03-01 | 2022-03-02 | 2 |  | 2 | [20 empty] | 2022-03-07 |  |  | NO | Expedited | [8 empty] | 2022-05-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5516 | 1420 | 302.87 | Solar | 0 | 2022-01-21 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5492 | 1420 | 3.8 | Solar | 11W12 | 2022-01-06 | 2022-01-19 | 9 | 8 | 1 | 2022-01-20 | 2022-01-24 | 3 |  | 3 | [20 empty] | 2022-01-27 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 5486 | 1462 | 11.4 | Solar + Energy Storage | 30W30 | 2022-01-05 | 2022-02-11 | 27 | 25 | 2 | 2022-02-14 | 2022-02-21 | 5 |  | 5 | [20 empty] | 2022-03-02 | 2022-03-09 |  | YES | Expedited | [8 empty] | 2022-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5457 | 1420 | 6.5 | Solar | 35W36 | 2021-12-22 | 2022-02-03 | 31 | 27 | 4 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2023-04-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5453 | 1420 | 6 | Solar | 11H10 | 2021-12-21 | 2022-01-10 | 15 | 10 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5452 | 1420 | 6 | Solar | 11W11 | 2021-12-21 | 2022-01-10 | 15 | 10 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-07-11 | In Operation | Res | Y
Fitchburg | Ashby | 5449 | 1431 | 9.8 | Solar | 39W19 | 2021-12-20 | 2022-01-10 | 16 | 11 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-06-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5442 | 1420 | 100 | Solar | 50W56 | 2021-12-17 | 2022-01-04 | 13 | 10 | 3 | 2022-01-04 | 2022-05-19 | 95 | 94 | 1 | [20 empty] | 2022-05-25 | 2023-02-27 | 2026-01-05 | YES | Expedited | [9 empty] | Pending COC & Photos | Comm | N
Fitchburg | Fitchburg | 5441 | 1420 | 250 | Solar | 0 | 2021-12-17 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5438 | 1420 | 100 | Solar | 50W51 | 2021-12-15 | 2022-01-24 | 28 | 23 | 5 | 2022-01-25 | 2022-05-19 | 81 | 62 | 19 | [20 empty] | 2022-05-25 | 2023-09-25 | 2026-12-01 | YES | Expedited | [9 empty] | Pending COC & Photos | Comm | N
Fitchburg | Fitchburg | 5420 | 1420 | 6 | Solar | 25W27 | 2021-12-09 | 2021-12-14 | 4 | 3 | 1 | 2021-12-15 | 2021-12-15 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5416 | 1420 | 7.6 | Solar | 11W11 | 2021-12-08 | 2022-02-11 | 47 | 46 | 1 | 2022-02-14 | 2022-02-14 | 1 |  | 1 | [20 empty] | 2022-03-02 |  |  | NO | Expedited | [8 empty] | 2022-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5415 | 1420 | 6 | Solar | 40W42 | 2021-12-08 | 2022-02-16 | 50 | 47 | 3 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-05-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 5413 | 1420 | 6 | Solar | 11W11 | 2021-12-08 | 2021-12-13 | 4 | 3 | 1 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 | 2022-01-05 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5412 | 1431 | 10 | Solar | 0 | 2021-12-08 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5409 | 1420 | 6 | Solar | 11W11 | 2021-12-07 | 2021-12-13 | 5 | 3 | 2 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [8 empty] | 2022-03-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 5408 | 1420 | 6 | Solar | 40W42 | 2021-12-07 | 2021-12-14 | 6 | 5 | 1 | 2021-12-15 | 2021-12-15 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 5405 | 1462 | 11.4 | Solar | 31W38 | 2021-12-07 | 2021-12-17 | 9 | 8 | 1 | 2021-12-20 | 2021-12-21 | 2 |  | 2 | [20 empty] | 2021-12-30 | 2022-01-25 |  | YES | Expedited | [8 empty] | 2022-02-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 5395 | 1420 | 230 | Solar | 22W1 | 2021-12-03 | 2021-12-22 | 14 | 13 | 1 | 2021-12-23 | 2022-01-11 | 14 |  | 14 | 2022-01-26 | 2022-01-28 | 3 |  | 3 | [15 empty] | 2022-02-03 | 2022-03-01 |  | YES | Expedited | [8 empty] | 2023-07-17 | In Operation | Res | Y
Fitchburg | Townsend | 5388 | 1469 | 9.44 | Solar | 15W16 | 2021-12-02 | 2021-12-08 | 5 | 4 | 1 | 2021-12-09 | 2021-12-14 | 4 |  | 4 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5378 | 1469 | 2.88 | Solar | 15W16 | 2021-11-29 | 2021-12-07 | 7 | 1 | 6 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5358 | 1420 | 9.92 | Solar + Energy Storage | 0 | 2021-11-19 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5350 | 1420 | 8 | Solar | 25W27 | 2021-11-17 | 2021-12-07 | 14 | 5 | 9 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5343 | 1420 | 3.8 | Solar | 25W27 | 2021-11-16 | 2021-12-07 | 15 | 5 | 10 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5320 | 1420 | 9.8 | Solar | 11W11 | 2021-11-23 | 2021-11-29 | 4 | 3 | 1 | 2021-11-29 | 2021-11-29 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [8 empty] | 2022-06-09 | In Operation | Res | Y
Fitchburg | Ashby | 5318 | 1431 | 8.1 | Storage - Battery | 39W19 | 2021-11-11 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5308 | 1420 | 5.02 | Solar | 25W27 | 2021-11-09 | 2021-12-20 | 28 | 27 | 1 | 2021-12-21 | 2021-12-21 | 1 |  | 1 | [20 empty] | 2021-12-23 |  |  | NO | Expedited | [8 empty] | 2023-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5293 | 1420 | 6 | Solar | 11W11 | 2021-11-04 | 2021-11-09 | 4 | 3 | 1 | 2021-11-10 | 2021-12-15 | 24 | 23 | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-03-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 5290 | 1420 | 6 | Solar | 25W28 | 2021-11-04 | 2021-12-09 | 24 | 5 | 19 | 2021-12-10 | 2021-12-10 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5289 | 1469 | 6 | Solar | 39W18 | 2021-11-04 | 2021-12-07 | 22 | 3 | 19 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 | 2022-03-01 |  | YES | Expedited | [8 empty] | 2022-03-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5288 | 1420 | 7.6 | Solar | 11W11 | 2021-11-03 | 2021-12-27 | 37 | 32 | 5 | 2021-12-28 | [24 empty] | 2022-01-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5287 | 1469 | 5 | Solar | 15W16 | 2021-11-09 | 2021-11-19 | 8 | 7 | 1 | 2021-11-19 | 2021-11-22 | 2 |  | 2 | [20 empty] | 2021-11-30 |  |  | NO | Expedited | [8 empty] | 2022-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5286 | 1420 | 9.8 | Solar | 11W11 | 2021-11-03 | 2021-12-12 | 26 | 6 | 20 | 2021-12-13 | 2022-01-06 | 19 |  | 19 | [20 empty] | 2022-01-20 | 2022-04-12 |  | YES | Expedited | [8 empty] | 2022-09-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5283 | 1420 | 7.08 | Solar | 11W11 | 2021-11-03 | 2021-12-08 | 24 | 4 | 20 | 2021-12-09 | 2021-12-09 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-04-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5278 | 1420 | 6 | Solar | 25W27 | 2021-11-01 | 2021-11-24 | 17 | 16 | 1 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-02-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 5276 | 1420 | 9.8 | Solar | 11W11 | 2021-11-01 | 2021-11-22 | 15 | 12 | 3 | 2021-11-22 | 2021-11-22 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 5271 | 1462 | 10 | Solar | 30W31 | 2021-10-28 | 2021-11-15 | 12 | 7 | 5 | 2021-11-18 | 2022-01-11 | 38 |  | 38 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-02-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 5270 | 1420 | 3.8 | Solar | 25W28 | 2021-10-27 | 2021-11-08 | 9 | 5 | 4 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5269 | 1420 | 6 | Solar | 01W04 | 2021-10-27 | 2021-11-04 | 7 | 6 | 1 | 2021-11-05 | 2021-11-05 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5268 | 1420 | 3.8 | Solar | 40W42 | 2021-01-03 | 2021-11-18 | 222 | 221 | 1 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 5267 | 1474 | 3.8 | Solar | 39W18 | 2021-11-18 | 2021-12-01 | 9 | 8 | 1 | 2021-12-01 | 2021-12-01 | 1 |  | 1 | [20 empty] | 2021-12-09 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5257 | 1420 | 8.5 | Solar | 40W42 | 2021-10-26 | 2021-11-24 | 21 | 5 | 16 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-03-07 | In Operation | Res | Y
Fitchburg | Ashby | 5249 | 1431 | 7.6 | Solar | 39W19 | 2021-10-21 | 2021-11-23 | 23 | 7 | 16 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5244 | 1420 | 9.8 | Solar | 25W28 | 2021-10-20 | 2021-12-13 | 37 | 34 | 3 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [8 empty] | 2022-05-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5240 | 1420 | 5.9 | Solar | 31W37 | 2021-10-18 | 2022-01-03 | 54 | 50 | 4 | 2022-01-04 | 2022-01-04 | 1 |  | 1 | [20 empty] | 2022-01-10 |  |  | NO | Expedited | [8 empty] | 2022-02-15 | In Operation | Res | Y
Fitchburg | Townsend | 5232 | 1469 | 10.03 | Solar | 15W16 | 2021-10-26 | 2021-11-17 | 16 | 1 | 15 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [8 empty] | 2012-12-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5221 | 1420 | 7.6 | Solar | 35W36 | 2021-10-13 | 2021-10-26 | 10 | 6 | 4 | 2021-10-27 | 2021-10-27 | 1 |  | 1 | [20 empty] | 2021-10-28 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5216 | 1420 | 123 | Solar | 0 | 2021-10-12 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5215 | 1420 | 8.8 | Solar | 20W22 | 2021-10-18 | 2021-10-27 | 8 | 6 | 2 | 2021-10-28 | 2021-11-15 | 12 |  | 12 | [20 empty] | 2021-11-18 |  |  | NO | Expedited | [8 empty] | 2022-08-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 5213 | 1462 | 10.03 | Solar | 30W31 | 2021-10-11 | 2021-10-14 | 3 | 2 | 1 | 2021-10-19 | 2021-10-20 | 2 |  | 2 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5212 | 1420 | 7.6 | Solar | 25W27 | 2021-10-28 | 2021-11-17 | 14 | 13 | 1 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [8 empty] | 2021-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5209 | 1420 | 4 | Solar | 25W27 | 2021-10-08 | 2021-11-14 | 24 | 7 | 17 | 2021-11-15 | 2021-11-15 | 1 |  | 1 | [20 empty] | 2021-11-16 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5203 | 1420 | 7998 | Storage - Battery | 40W42 | 2021-10-05 | 2021-10-18 | 9 | 8 | 1 | [10 empty] | 2021-10-20 | [17 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Ashby | 5201 | 1431 | 7.6 | Solar | 39W19 | 2021-10-05 | 2021-10-19 | 10 | 9 | 1 | 2021-10-20 | 2021-10-20 | 1 |  | 1 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5199 | 1469 | 8 | Solar | 39W18 | 2021-10-04 | 2021-11-16 | 30 | 6 | 24 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5193 | 1420 | 8 | Solar | 50W51 | 2021-10-01 | 2021-10-28 | 19 | 5 | 14 | 2021-10-29 | 2021-11-02 | 3 |  | 3 | [20 empty] | 2021-11-04 |  |  | NO | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5192 | 1420 | 6 | Solar | 01W02 | 2021-10-01 | 2021-11-16 | 31 | 7 | 24 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-18 |  |  | NO | Expedited | [8 empty] | 2021-12-09 | In Operation | Res | Y
Fitchburg | Townsend | 5180 | 1469 | 7.6 | Solar | 39W18 | 2021-09-28 | 2021-10-18 | 14 | 13 | 1 | 2021-10-19 | 2021-11-15 | 19 |  | 19 | [20 empty] | 2021-11-17 | 2021-11-23 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5169 | 1462 | 7.6 | Solar | 30W31 | 2021-09-22 | 2021-09-27 | 4 |  | 4 | 2021-09-28 | 2021-09-29 | 2 |  | 2 | [20 empty] | 2021-09-30 | 2021-10-18 |  | YES | Expedited | [8 empty] | 2021-01-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 5168 | 1420 | 7.6 | Solar | 50W56 | 2021-09-22 | 2021-10-08 | 13 | 12 | 1 | 2021-10-11 | 2021-10-13 | 2 |  | 2 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5167 | 1420 | 6 | Solar | 01W04 | 2021-09-22 | 2021-10-07 | 12 | 11 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2022-01-12 | In Operation | Res | Y
Fitchburg | Ashby | 5164 | 1431 | 6 | Solar | 39W19 | 2021-09-21 | 2021-10-07 | 13 | 12 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2021-11-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5155 | 1420 | 6 | Solar | 40W42 | 2021-09-17 | 2021-10-07 | 15 | 14 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 5145 | 1462 | 9.8 | Solar | 31W38 | 2021-09-15 | 2021-10-18 | 23 | 19 | 4 | 2021-10-19 | 2021-10-20 | 2 |  | 2 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5144 | 1420 | 6 | Solar | 50W51 | 2021-09-15 | 2021-11-23 | 48 | 5 | 43 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-07 | 2021-12-14 |  | YES | Expedited | [8 empty] | 2022-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 5135 | 1431 | 3.8 | Solar | 39W19 | 2021-09-22 | 2021-09-22 | 1 |  | 1 | 2021-09-23 | 2021-09-23 | 1 |  | 1 | [20 empty] | 2021-09-24 | 2021-10-01 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5133 | 1420 | 9.15 | Solar | 20W22 | 2021-09-13 | 2021-09-14 | 2 |  | 2 | 2021-09-15 | 2021-09-22 | 6 |  | 6 | [20 empty] | 2021-09-24 |  |  | NO | Expedited | [8 empty] | 2021-12-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 5126 | 1420 | 5 | Solar | 11W11 | 2021-09-21 | 2021-10-25 | 24 |  | 24 | 2021-10-26 | 2021-10-26 | 1 |  | 1 | [20 empty] | 2021-10-28 | 2021-11-23 |  | YES | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 5118 | 1462 | 9 | Solar + Energy Storage | 30W31 | 2021-10-20 | 2021-11-04 | 12 | 4 | 8 | 2021-11-05 | 2022-02-08 | [23 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2023-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 5114 | 1420 | 9.735 | Solar | 01W02 | 2021-09-03 | 2021-09-08 | 3 |  | 3 | 2021-09-09 | 2021-09-09 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2021-10-27 |  | YES | Expedited | [8 empty] | 2022-03-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5112 | 1420 | 7.6 | Solar | 11W11 | 2021-09-01 | 2021-10-19 | 33 | 29 | 4 | 2021-10-20 | 2021-10-20 | 1 |  | 1 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5111 | 1420 | 6 | Solar | 25W28 | 2021-09-01 | 2021-09-15 | 10 | 5 | 5 | 2021-09-16 | 2021-09-20 | 3 |  | 3 | [20 empty] | 2021-09-24 |  |  | NO | Expedited | [8 empty] | 2021-12-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5105 | 1420 | 3.8 | Solar | 20W22 | 2021-08-31 | 2021-09-27 | 19 | 7 | 12 | 2021-09-28 | 2021-09-29 | 2 |  | 2 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5104 | 1420 | 4 | Solar | 01W04 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 |  |  | NO | Expedited | [8 empty] | 2022-04-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5103 | 1420 | 6 | Solar | 01W04 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2021-12-09 |  | YES | Expedited | [8 empty] | 2021-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 5102 | 1420 | 3.8 | Solar | 35W36 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-10-13 | 18 |  | 18 | [20 empty] | 2021-10-18 | 2022-03-22 |  | YES | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5101 | 1420 | 6 | Solar | 01W04 | 2021-08-30 | 2021-09-16 | 13 | 8 | 5 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2022-02-01 |  | YES | Expedited | [8 empty] | 2021-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5097 | 1420 | 3.8 | Solar | 01W04 | 2021-08-30 | 2021-09-23 | 18 |  | 18 | 2021-09-24 | 2021-09-28 | 3 |  | 3 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [8 empty] | 2022-02-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 5096 | 1462 | 7.25 | Solar | 31W37 | 2021-10-22 | 2021-10-27 | 4 |  | 4 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 | 2021-12-06 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 5095 | 1462 | 10.29 | Solar | 31W37 | 2021-08-29 | 2021-09-30 | 23 | 3 | 20 | 2021-10-01 | 2021-10-01 | 1 |  | 1 | [20 empty] | 2021-10-01 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5088 | 1420 | 7.6 | Solar | 35W36 | 2021-08-25 | 2021-08-30 | 4 |  | 4 | 2021-08-31 | 2021-09-09 | 7 |  | 7 | [20 empty] | 2021-09-09 |  |  | NO | Expedited | [8 empty] | 2021-12-09 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5082 | 1420 | 6 | Solar | 01W04 | 2021-08-30 | 2021-11-08 | 49 | 10 | 39 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-10-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 5077 | 1420 | 7.6 | Solar | 11W12 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5076 | 1420 | 7.6 | Solar | 11W11 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5075 | 1420 | 3.8 | Solar | 01W04 | 2021-08-19 | 2021-08-27 | 7 | 4 | 3 | 2021-08-27 | 2021-08-30 | 2 |  | 2 | [20 empty] | 2021-09-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5073 | 1431 | 7.6 | Solar | 39W19 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5072 | 1420 | 10.03 | Solar | 31W37 | 2021-08-19 | 2021-09-01 | 10 | 6 | 4 | 2021-09-02 | 2021-09-02 | 1 |  | 1 | [20 empty] | 2021-09-02 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5065 | 1420 | 8.3 | Solar | 11W11 | 2021-08-18 | 2021-11-30 | 71 | 66 | 5 | 2021-12-01 | 2021-12-01 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5064 | 1420 | 9.8 | Solar | 50W51 | 2021-08-18 | 2021-10-06 | 35 |  | 35 | 2021-10-07 | 2021-10-19 | 8 |  | 8 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5056 | 1469 | 10 | Solar | 15W16 | 2021-08-16 | 2021-09-01 | 13 | 9 | 4 | 2021-09-02 | 2021-09-02 | 1 |  | 1 | [20 empty] | 2021-09-02 | 2021-10-12 |  | YES | Expedited | [8 empty] | 2021-11-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 5049 | 1420 | 3.8 | Solar | 01W04 | 2021-08-09 | 2021-08-19 | 9 | 5 | 4 | 2021-08-20 | 2021-08-23 | 2 |  | 2 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5046 | 1431 | 6 | Solar | 39W19 | 2021-08-09 | 2021-08-17 | 7 | 5 | 2 | 2021-08-18 | 2021-08-18 | 1 |  | 1 | [20 empty] | 2021-08-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5045 | 1420 | 6 | Solar | 25W27 | 2021-08-09 | 2021-08-17 | 7 | 5 | 2 | 2021-08-18 | 2021-08-18 | 1 |  | 1 | [20 empty] | 2021-08-25 | 2022-04-08 |  | YES | Expedited | [8 empty] | 2022-04-12 | Cancelled | Res | Y
Fitchburg | Lunenburg | 5040 | 1462 | 7.6 | Solar | 30W30 | 2021-08-31 | 2021-09-14 | 10 |  | 10 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-21 | 2021-09-27 |  | YES | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 5038 | 1462 | 10.03 | Solar | 30W30 | 2021-08-06 | 2021-08-13 | 6 | 1 | 5 | 2021-08-14 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 | 2022-04-13 |  | YES | Expedited | [8 empty] | 2022-08-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5037 | 1420 | 6 | Solar | 25W28 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-06-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 5036 | 1420 | 6 | Solar | 01W02 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5035 | 1420 | 9.8 | Solar | 01W02 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 | 2022-03-25 |  | YES | Expedited | [8 empty] | 2021-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5034 | 1420 | 3.8 | Solar | 01W04 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5033 | 1420 | 6 | Solar | 01W04 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-02-07 | In Operation | Res | Y
Fitchburg | Ashby | 5030 | 1431 | 5 | Solar | 39W19 | 2021-08-05 | 2021-08-11 | 5 | 2 | 3 | 2021-08-12 | 2021-08-23 | 8 |  | 8 | [20 empty] | 2021-08-25 |  |  | NO | Expedited | [8 empty] | 2021-11-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5029 | 1420 | 4.5 | Solar | 01W01 | 2021-08-05 | 2021-08-12 | 6 | 2 | 4 | 2021-08-13 | 2021-08-16 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5028 | 1420 | 2.75 | Solar | 01W04 | 2021-08-05 | 2021-08-14 | 7 | 4 | 3 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-08-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5018 | 1420 | 5.75 | Solar | 35W36 | 2021-08-02 | 2021-11-04 | 67 |  | 67 | 2021-11-05 | 2021-11-05 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5017 | 1420 | 5.5 | Solar | 31W37 | 2021-10-27 | 2021-11-08 | 9 |  | 9 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 5011 | 1420 | 10.4 | Solar | 11W11 | 2021-07-29 | 2021-08-11 | 10 | 8 | 2 | 2021-08-12 | 2021-08-17 | 4 | 1 | 3 | [20 empty] | 2021-08-23 |  |  | NO | Expedited | [8 empty] | 2021-11-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5007 | 1420 | 3.8 | Solar | 01W04 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5006 | 1420 | 6 | Solar | 11W11 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-09 | 5 |  | 5 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5005 | 1420 | 9.8 | Solar | 11W12 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5004 | 1420 | 3.8 | Solar | 11W12 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2022-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5003 | 1420 | 3.8 | Solar | 01W02 | 2021-07-28 | 2021-08-02 | 4 | 2 | 2 | 2021-08-26 | 2021-09-01 | 5 |  | 5 | [20 empty] | 2021-09-02 |  |  | NO | Expedited | [8 empty] | 2021-12-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4998 | 1420 | 10 | Solar | 50W51 | 2021-07-27 | 2021-08-04 | 7 | 3 | 4 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4996 | 1420 | 7.6 | Solar | 25W27 | 2021-07-27 | 2021-08-02 | 5 | 3 | 2 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4994 | 1420 | 3.8 | Solar | 40W42 | 2021-07-27 | 2021-10-28 | 66 |  | 66 | 2021-10-29 | 2021-11-02 | 3 |  | 3 | [20 empty] | 2021-11-04 |  |  | NO | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4993 | 1420 | 7.68 | Solar + Energy Storage | 01W04 | 2021-07-27 | 2021-12-27 | 106 | 104 | 2 | 2021-12-28 | 2021-12-28 | 1 |  | 1 | [20 empty] | 2022-01-07 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Townsend | 4992 | 1469 | 3.8 | Solar | 39W18 | 2021-07-27 | 2021-08-04 | 7 | 5 | 2 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 | 2021-08-27 |  | YES | Expedited | [8 empty] | 2021-11-22 | In Operation | Res | Y
Fitchburg | Ashby | 4991 | 1431 | 3.8 | Solar | 39W19 | 2021-07-27 | 2021-07-29 | 3 | 2 | 1 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-02 | 2021-08-06 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4982 | 1420 | 3.8 | Solar | 25W27 | 2021-07-22 | 2021-07-29 | 6 | 5 | 1 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4981 | 1420 | 7.6 | Solar | 01W04 | 2021-07-22 | 2021-07-29 | 6 | 4 | 2 | 2021-07-29 | 2021-07-29 | 1 |  | 1 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2022-09-12 | In Operation | Res | Y
Fitchburg | Townsend | 4969 | 1469 | 10 | Solar | 30W31 | 2021-07-16 | 2021-07-27 | 8 | 7 | 1 | 2021-07-28 | 2021-07-28 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Ashby | 4965 | 1431 | 7.6 | Solar | 39W19 | 2021-07-16 | 2021-07-21 | 4 | 3 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 |  |  | NO | Expedited | [8 empty] | 2022-03-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 4960 | 1420 | 5 | Solar | 25W28 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-02 |  | YES | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4959 | 1420 | 7.6 | Solar | 01W04 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-02 |  | YES | Expedited | [8 empty] | 2021-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4958 | 1420 | 10 | Solar | 25W28 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-26 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4957 | 1420 | 7.25 | Solar | 01W02 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 |  |  | NO | Expedited | [8 empty] | 2021-10-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4953 | 1462 | 7.6 | Solar | 30W30 | 2021-07-13 | 2021-07-29 | 13 | 11 | 2 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4939 | 1420 | 9.8 | Solar | 11H10 | 2021-07-08 | 2021-08-09 | 23 |  | 23 | 2021-08-10 | 2021-08-23 | 10 |  | 10 | [20 empty] | 2021-08-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4938 | 1474 | 10 | Solar | 39W18 | 2021-07-08 | 2021-07-13 | 4 | 3 | 1 | 2021-07-13 | 2021-07-14 | 2 |  | 2 | [20 empty] | 2021-07-20 | 2021-07-22 |  | YES | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4937 | 1462 | 8.85 | Solar | 30W30 | 2021-07-08 | 2021-07-13 | 4 | 3 | 1 | 2021-07-13 | 2021-07-14 | 2 |  | 2 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [8 empty] | 2021-08-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4929 | 1420 | 10 | Solar | 11W11 | 2021-07-01 | 2021-07-28 | 20 | 18 | 2 | 2021-07-28 | 2021-07-28 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [8 empty] | 2021-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4918 | 1420 | 8.8 | Solar | 40W42 | 2021-06-29 | 2021-07-08 | 8 | 6 | 2 | 2021-07-09 | 2021-07-09 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4909 | 1420 | 7.6 | Solar | 25W28 | 2021-06-25 | 2021-07-02 | 6 | 3 | 3 | 2021-07-02 | 2021-07-02 | 1 |  | 1 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2021-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4905 | 1420 | 9.8 | Solar | 20W22 | 2021-06-23 | 2021-07-08 | 12 | 10 | 2 | 2021-07-09 | 2021-07-09 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-11-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4903 | 1420 | 7.6 | Solar | 50W51 | 2021-06-23 | 2021-07-01 | 7 | 4 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4902 | 1420 | 5.5 | Solar | 25W27 | 2021-06-23 | 2021-07-02 | 8 | 4 | 4 | 2021-07-02 | 2021-07-02 | 1 |  | 1 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4901 | 1420 | 7.5 | Solar | 25W27 | 2021-06-23 | 2021-07-20 | 20 | 17 | 3 | 2021-07-21 | 2021-07-21 | 1 |  | 1 | [20 empty] | 2021-07-26 |  |  | NO | Expedited | [8 empty] | 2022-03-03 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4899 | 1420 | 6 | Solar | 25W27 | 2021-06-23 | 2021-07-01 | 7 | 4 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-10-29 | In Operation | Res | Y
Fitchburg | West Townsend | 4898 | 1474 | 7.6 | Solar | 39W18 | 2021-06-22 | 2021-06-30 | 7 | 3 | 4 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-10-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4897 | 1420 | 3.8 | Solar | 31W37 | 2021-06-22 | 2021-07-01 | 8 | 5 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4896 | 1462 | 5.75 | Solar | 30W31 | 2021-06-22 | 2021-08-04 | 32 |  | 32 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2022-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4891 | 1420 | 10 | Solar | 11W12 | 2021-06-18 | 2021-06-30 | 9 | 7 | 2 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-09-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 4889 | 1462 | 9.8 | Solar | 30W30 | 2021-06-18 | 2021-07-01 | 10 | 8 | 2 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2021-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4888 | 1420 | 6 | Solar | 11W11 | 2021-06-18 | 2021-07-01 | 10 | 7 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4887 | 1474 | 10 | Solar | 39W18 | 2021-06-18 | 2021-06-24 | 5 | 4 | 1 | 2021-06-24 | 2021-06-25 | 2 |  | 2 | [20 empty] | 2021-07-06 | 2021-08-03 |  | YES | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4885 | 1420 | 6 | Solar | 11H10 | 2021-06-17 | 2021-06-29 | 9 | 6 | 3 | 2021-06-30 | 2021-06-30 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4884 | 1469 | 10 | Solar | 39W18 | 2021-06-17 | 2021-06-22 | 4 | 3 | 1 | 2021-06-21 | 2021-06-23 | 3 |  | 3 | [20 empty] | 2021-07-06 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-12-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 4879 | 1462 | 9.8 | Solar | 30W30 | 2021-06-11 | 2021-06-18 | 6 | 4 | 2 | 2021-06-18 | 2021-06-21 | 2 |  | 2 | [20 empty] | 2021-06-24 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4875 | 1462 | 5 | Solar | 30W30 | 2021-06-11 | 2021-06-21 | 7 | 6 | 1 | 2021-06-21 | 2021-06-22 | 2 |  | 2 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4872 | 1420 | 7.6 | Solar | 25W28 | 2021-06-09 | 2021-06-17 | 7 | 6 | 1 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Townsend | 4871 | 1469 | 8.85 | Solar | 15W17 | 2021-06-09 | 2021-06-16 | 6 | 3 | 3 | 2021-06-16 | 2021-06-16 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4870 | 1420 | 3.8 | Solar | 40W42 | 2021-06-09 | 2021-06-17 | 7 | 4 | 3 | 2021-06-18 | 2021-06-22 | 3 |  | 3 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4867 | 1420 | 10 | Solar | 25W28 | 2021-06-08 | 2021-08-11 | 47 |  | 47 | 2021-08-12 | 2021-08-16 | 3 |  | 3 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4866 | 1420 | 10 | Solar | 01W04 | 2021-06-08 | 2021-06-29 | 16 | 13 | 3 | 2021-06-30 | 2021-06-30 | 1 |  | 1 | [20 empty] | 2021-07-15 | 2021-10-12 |  | YES | Expedited | [8 empty] | 2022-04-07 | In Operation | Res | Y
Fitchburg | Townsend | 4865 | 1469 | 10 | Solar | 15W16 | 2021-06-08 | 2021-06-22 | 11 | 10 | 1 | 2021-06-22 | 2021-06-23 | 2 |  | 2 | [20 empty] | 2021-07-15 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-09-16 | In Operation | Res | Y
Fitchburg | Townsend | 4864 | 1474 | 6 | Solar | 39W18 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-18 | 2021-06-18 | 1 |  | 1 | [20 empty] | 2021-06-24 |  |  | NO | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Ashby | 4863 | 1431 | 10 | Solar | 39W19 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [8 empty] | 2021-07-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4862 | 1420 | 6 | Solar | 50W51 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4860 | 1420 | 3.8 | Solar | 25W27 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4851 | 1420 | 10 | Solar | 20W22 | 2021-06-03 | 2021-07-30 | 42 | 40 | 2 | 2021-07-30 | 2021-08-02 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4843 | 1420 | 1.77 | Solar | 01W04 | 2021-06-01 | 2021-06-07 | 5 | 4 | 1 | 2021-06-08 | 2021-06-08 | 1 |  | 1 | [20 empty] | 2021-06-14 | 2021-06-17 |  | YES | Expedited | [8 empty] | 2022-01-21 | In Operation | Res | Y
Fitchburg | Townsend | 4842 | 1469 | 10 | Solar | 15W16 | 2021-06-01 | 2021-06-10 | 8 | 2 | 6 | 2021-06-11 | 2021-06-11 | 1 |  | 1 | [20 empty] | 2021-06-21 | 2021-10-19 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 4840 | 1462 | 10 | Solar | 30W30 | 2021-06-01 | 2021-06-16 | 12 | 8 | 4 | 2021-06-16 | 2021-06-17 | 2 |  | 2 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Townsend | 4839 | 1469 | 2.65 | Solar | 39W18 | 2021-06-01 | 2021-06-07 | 5 | 4 | 1 | 2021-06-08 | 2021-06-08 | 1 |  | 1 | [20 empty] | 2021-06-14 |  |  | NO | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Townsend | 4832 | 1474 | 7.6 | Solar | 39W18 | 2021-05-27 | 2021-06-30 | 24 | 22 | 2 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2022-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 4819 | 1420 | 5.25 | Solar | 31W37 | 2021-05-21 | 2021-06-17 | 19 | 7 | 12 | 2021-06-18 | 2021-06-18 | 1 |  | 1 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Westminster | 4811 | 0 | 18000 | Wood | K-Line | [33 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4808 | 1420 | 10 | Solar | 0 | 2021-05-18 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 4806 | 1462 | 9.75 | Solar | 30W30 | 2021-05-18 | 2021-06-22 | 25 | 24 | 1 | 2021-06-22 | 2021-06-23 | 2 |  | 2 | [20 empty] | 2021-06-29 |  |  | NO | Expedited | [8 empty] | 2021-10-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4804 | 1420 | 7.6 | Solar | 20W22 | 2021-05-17 | 2021-05-26 | 8 | 5 | 3 | 2021-05-27 | 2021-06-01 | 3 |  | 3 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4803 | 1420 | 3.8 | Solar | 40W40 | 2021-05-17 | 2021-05-27 | 9 | 6 | 3 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-10 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4801 | 1420 | 9.15 | Solar | 40W40 | 2021-05-14 | 2021-05-19 | 4 | 2 | 2 | 2021-05-20 | 2021-05-20 | 1 |  | 1 | [20 empty] | 2021-06-02 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4800 | 1420 | 8.42 | Solar | 40W40 | 2021-05-14 | 2021-05-27 | 10 | 6 | 4 | 2021-05-28 | 2021-06-03 | 4 |  | 4 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4799 | 1420 | 6 | Solar | 01W04 | 2021-05-14 | 2021-05-28 | 11 | 7 | 4 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2022-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4798 | 1420 | 9.8 | Solar | 25W27 | 2021-05-14 | 2021-05-28 | 11 | 9 | 2 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4797 | 1462 | 6 | Solar | 31W38 | 2021-05-14 | 2021-05-27 | 10 | 9 | 1 | 2021-05-28 | 2021-06-03 | 4 |  | 4 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4794 | 1462 | 9.8 | Solar | 30W30 | 2021-05-13 | 2021-06-18 | 26 | 25 | 1 | 2021-06-18 | 2021-06-21 | 2 |  | 2 | [20 empty] | 2021-06-24 | 2021-10-19 |  | YES | Expedited | [8 empty] | 2021-12-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4793 | 1420 | 9.8 | Solar | 01W04 | 2021-05-13 | 2021-05-21 | 7 | 4 | 3 | 2021-05-21 | 2021-05-24 | 2 |  | 2 | [20 empty] | 2021-06-02 |  |  | NO | Expedited | [8 empty] | 2022-04-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4788 | 1420 | 6 | Solar | 11W11 | 2021-05-11 | 2021-07-01 | 37 | 35 | 2 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4787 | 1420 | 6 | Solar | 25W28 | 2021-05-11 | 2021-05-13 | 3 | 1 | 2 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 | 2021-06-01 |  | YES | Expedited | [8 empty] | 2021-12-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4780 | 1420 | 9.8 | Solar | 50W51 | 2021-05-07 | 2021-05-13 | 5 | 4 | 1 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4779 | 1462 | 7.6 | Solar | 31W38 | 2021-05-07 | 2021-05-21 | 11 | 7 | 4 | 2021-05-21 | 2021-05-25 | 3 |  | 3 | [20 empty] | 2021-06-02 | 2021-06-10 |  | YES | Expedited | [8 empty] | 2021-08-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 4778 | 1420 | 9.8 | Solar | 25W27 | 2021-05-06 | 2021-05-13 | 6 | 5 | 1 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4777 | 1420 | 5 | Solar | 01W04 | 2021-05-06 | 2021-05-13 | 6 | 4 | 2 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 | 2021-09-21 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4776 | 1420 | 3.8 | Solar | 01W04 | 2021-05-06 | 2021-05-17 | 8 | 7 | 1 | 2021-05-18 | 2021-05-18 | 1 |  | 1 | [20 empty] | 2021-05-27 |  |  | NO | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4771 | 1420 | 6 | Solar | 50W51 | 2021-05-05 | 2021-05-12 | 6 | 5 | 1 | 2021-05-13 | 2021-05-17 | 3 |  | 3 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4764 | 1462 | 9.8 | Solar | 31W38 | 2021-05-03 | 2021-05-04 | 2 |  | 2 | 2021-05-05 | 2021-05-18 | 10 |  | 10 | [20 empty] | 2021-05-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4761 | 1420 | 12.095 | Solar | 31W37 | 2021-05-03 | 2021-05-24 | 16 | 13 | 3 | 2021-05-25 | 2021-05-26 | 2 |  | 2 | [20 empty] | 2021-06-02 |  |  | NO | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 4759 | 1462 | 10 | Solar | 30W30 | 2021-04-30 | 2021-05-03 | 2 |  | 2 | 2021-05-04 | 2021-05-04 | 1 |  | 1 | [20 empty] | 2021-05-12 | 2021-05-17 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4758 | 1420 | 5 | Solar | 01W04 | 2021-04-30 | 2021-06-10 | 29 | 27 | 2 | 2021-06-11 | 2021-06-14 | 2 |  | 2 | [20 empty] | 2021-06-21 | 2021-02-04 |  | YES | Expedited | [8 empty] | 2022-06-01 | In Operation | Res | Y
Fitchburg | Ashby | 4751 | 1431 | 10 | Solar | 39W19 | 2021-04-28 | 2021-04-30 | 3 | 2 | 1 | 2021-04-30 | 2021-05-03 | 2 |  | 2 | [20 empty] | 2021-05-11 |  |  | NO | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Ashby | 4747 | 1431 | 9.8 | Solar | 39W19 | 2021-04-26 | 2021-05-04 | 7 | 6 | 1 | 2021-05-05 | 2021-05-05 | 1 |  | 1 | [20 empty] | 2021-05-13 | 2021-05-17 |  | YES | Expedited | [8 empty] | 2021-06-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4744 | 1462 | 10 | Solar | 30W30 | 2021-04-23 | 2021-04-27 | 3 | 2 | 1 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2022-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4743 | 1420 | 9.8 | Solar | 01W04 | 2021-04-23 | 2021-04-28 | 4 | 3 | 1 | 2021-04-29 | 2021-04-29 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4740 | 1420 | 7.6 | Solar | 20W22 | 2021-04-22 | 2021-04-28 | 5 | 3 | 2 | 2021-04-29 | 2021-04-29 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2022-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 4735 | 1420 | 7.6 | Solar | 01W04 | 2021-04-21 | 2021-04-27 | 5 | 2 | 3 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2021-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4734 | 1420 | 3.8 | Solar | 01W04 | 2021-04-21 | 2021-04-27 | 5 | 3 | 2 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2022-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4733 | 1462 | 7.6 | Solar | 30W30 | 2021-04-21 | 2021-04-27 | 5 | 3 | 2 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4731 | 1420 | 5.31 | Solar | 25W27 | 2021-04-20 | 2021-04-27 | 6 | 3 | 3 | 2021-04-28 | [24 empty] | 2021-05-14 | 2021-07-16 |  | YES | Expedited | [8 empty] | 2021-09-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 4730 | 1420 | 3.8 | Solar | 0 | 2021-04-20 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4729 | 1431 | 3.8 | Solar | 39W19 | 2021-04-20 | 2021-04-26 | 5 | 2 | 3 | 2021-04-27 | 2021-04-27 | 1 |  | 1 | [20 empty] | 2021-05-04 | 2021-05-18 |  | YES | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4727 | 1420 | 3.8 | Solar | 25W27 | 2021-04-19 | 2021-04-23 | 4 | 3 | 1 | 2021-04-26 | 2021-04-26 | 1 |  | 1 | [20 empty] | 2021-04-28 |  |  | NO | Expedited | [8 empty] | 2021-10-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4726 | 1462 | 9.8 | Solar | 30W30 | 2021-04-19 | 2021-04-23 | 4 | 3 | 1 | 2021-04-26 | 2021-04-26 | 1 |  | 1 | [20 empty] | 2021-04-28 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4722 | 1462 | 9 | Solar | 30W31 | 2021-04-16 | 2021-06-23 | 47 | 46 | 1 | 2021-06-23 | 2021-06-24 | 2 |  | 2 | [20 empty] | 2021-06-29 | 2021-07-02 |  | YES | Expedited | [8 empty] | 2021-08-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 4721 | 1420 | 7.6 | Solar | 20W22 | 2021-04-16 | 2021-04-19 | 1 | 1 | 0 | 2021-04-20 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-21 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4720 | 1420 | 8.26 | Solar | 35W36 | 2021-04-15 | 2021-05-26 | 29 | 27 | 2 | 2021-05-27 | 2021-06-03 | 5 |  | 5 | [20 empty] | 2021-06-07 | 2021-07-07 |  | YES | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4719 | 1420 | 5 | Solar | 25W28 | 2021-04-15 | 2021-04-19 | 2 | 1 | 1 | 2021-04-20 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-26 | 2021-05-12 |  | YES | Expedited | [8 empty] | 2021-07-01 | In Operation | Res | Y
Fitchburg | Townsend | 4714 | 1474 | 9.8 | Solar | 39W18 | 2021-04-14 | 2021-06-03 | 35 | 33 | 2 | 2021-06-04 | 2021-06-07 | 2 |  | 2 | [20 empty] | 2021-06-10 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4713 | 1431 | 10 | Solar + Energy Storage | 39W19 | 2021-04-13 | 2021-05-24 | 29 | 26 | 3 | 2021-05-25 | 2021-05-27 | 3 |  | 3 | [20 empty] | 2021-06-02 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4706 | 1420 | 3.8 | Solar | 31W37 | 2021-04-07 | 2021-04-21 | 10 | 8 | 2 | 2021-04-22 | 2021-04-22 | 1 |  | 1 | [20 empty] | 2021-04-29 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-06-01 | Cancelled | Res | Y
Fitchburg | Lunenburg | 4705 | 1462 | 6 | Solar | 31W37 | 2021-04-07 | 2021-04-21 | 10 | 9 | 1 | 2021-04-22 | 2021-04-22 | 1 |  | 1 | [20 empty] | 2021-04-27 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4693 | 1420 | 7.6 | Solar | 11W11 | 2021-04-01 | 2021-04-12 | 8 | 5 | 3 | 2021-04-13 | 2021-04-21 | 6 |  | 6 | [20 empty] | 2021-04-26 |  |  | NO | Expedited | [8 empty] | 2021-10-26 | In Operation | Res | Y
Fitchburg | Ashby | 4692 | 1431 | 3.8 | Solar | 39W19 | 2021-04-01 | 2021-04-20 | 13 | 5 | 8 | 2021-04-21 | 2021-04-21 | 1 |  | 1 | [20 empty] | 2021-04-27 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Townsend | 4691 | 1469 | 10.03 | Solar | 39W18 | 2021-03-31 | 2021-04-08 | 7 | 4 | 3 | 2021-04-09 | 2021-04-09 | 1 |  | 1 | [20 empty] | 2021-04-19 |  |  | NO | Expedited | [8 empty] | 2021-07-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4689 | 1420 | 9.735 | Solar | 40W40 | 2021-03-31 | 2021-04-29 | 21 | 21 | 0 | 2021-04-30 | 2021-05-13 | [23 empty] | 2021-05-19 | 2021-06-08 |  | YES | Expedited | [8 empty] | 2021-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4687 | 1420 | 6 | Solar | 25W28 | 2021-03-30 | 2021-04-12 | 10 | 8 | 2 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-04-26 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4686 | 1420 | 7.6 | Solar | 35W36 | 2021-03-30 | 2021-04-12 | 10 | 8 | 2 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-08-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4685 | 1420 | 8 | Solar | 11H11 | 2021-03-29 | 2021-04-06 | 7 | 6 | 1 | 2021-04-07 | 2021-04-21 | 10 |  | 10 | [20 empty] | 2021-04-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4677 | 1462 | 3.8 | Solar | 31W37 | 2021-03-26 | 2021-04-08 | 10 | 9 | 1 | 2021-04-09 | 2021-04-09 | 1 |  | 1 | [20 empty] | 2021-04-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4675 | 1420 | 2000 | Solar + Energy Storage | 40W39 | 2021-03-26 | 2021-04-07 | 9 | 4 | 5 | [10 empty] | 2021-04-09 | 2021-04-20 | 7 |  | 8 | 2021-07-02 | [12 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4667 | 1420 | 3.8 | Solar | 01W02 | 2021-03-22 | 2021-03-29 | 6 | 3 | 3 | 2021-03-30 | 2021-03-31 | 2 |  | 2 | [20 empty] | 2021-04-06 |  |  | NO | Expedited | [8 empty] | 2021-08-17 | In Operation | Res | Y
Fitchburg | Ashby | 4661 | 1431 | 8.5 | Solar | 39W19 | 2021-03-19 | 2021-04-01 | 10 | 9 | 1 | 2021-04-01 | 2021-04-02 | 2 |  | 2 | [20 empty] | 2021-04-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4660 | 1431 | 5.5 | Solar | 39W19 | 2021-03-19 | 2021-04-16 | 21 | 9 | 12 | 2021-04-19 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-26 | 2021-06-01 |  | YES | Expedited | [8 empty] | 2021-06-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4659 | 1420 | 8.26 | Solar | 25W27 | 2021-03-19 | 2021-04-01 | 10 | 9 | 1 | 2021-04-01 | 2021-04-02 | 2 |  | 2 | [20 empty] | 2021-04-08 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4657 | 1420 | 8 | Solar | 01W04 | 2021-03-18 | 2021-04-02 | 12 | 10 | 2 | 2021-04-05 | 2021-04-07 | 3 |  | 3 | [20 empty] | 2021-04-14 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4656 | 1462 | 4.5 | Solar | 31W38 | 2021-03-18 | 2021-03-26 | 7 | 5 | 2 | 2021-03-26 | 2021-03-29 | 2 |  | 2 | [20 empty] | 2021-04-02 |  |  | NO | Expedited | [8 empty] | 2021-06-03 | In Operation | Res | Y
Fitchburg | Townsend | 4651 | 1469 | 19 | Solar | 15W16 | 2021-03-16 | 2021-04-12 | 20 | 15 | 5 | 2021-04-13 | 2021-04-15 | 3 |  | 3 | [20 empty] | 2021-04-19 | 2022-03-22 |  | YES | Expedited | [8 empty] | 2022-05-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4646 | 1462 | 7.5 | Solar | 30W30 | 2021-03-13 | 2021-03-24 | 8 | 6 | 2 | 2021-03-24 | 2021-03-25 | 2 |  | 2 | [20 empty] | 2021-03-30 | 2021-04-12 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4645 | 1420 | 7.965 | Solar + Energy Storage | 20W22 | 2021-03-12 | 2021-04-02 | 16 | 7 | 9 | 2021-04-05 | 2021-04-07 | 3 |  | 3 | [20 empty] | 2021-04-14 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 4644 | 1462 | 19.6 | Solar | 0 | 2021-03-12 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4640 | 1462 | 7.6 | Solar | 30W31 | 2021-03-10 | 2021-04-12 | 24 | 23 | 1 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-06-14 |  | YES | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 4637 | 1420 | 6 | Solar | 31W37 | 2021-03-06 | 2021-03-16 | 7 | 3 | 4 | 2021-03-17 | 2021-03-22 | 4 |  | 4 | [20 empty] | 2021-05-06 | 2021-05-14 |  | YES | Expedited | [8 empty] | 2021-09-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4626 | 1420 | 16 | Solar | 22W1 | 2021-02-26 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4623 | 1420 | 6 | Solar | 50W51 | 2021-02-25 | 2021-03-01 | 3 | 2 | 1 | 2021-03-02 | 2021-03-03 | 2 |  | 2 | [20 empty] | 2021-03-12 | 2021-04-16 |  | YES | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4622 | 1420 | 10 | Solar | 01W01 | 2021-02-25 | 2021-03-01 | 3 | 2 | 1 | 2021-03-02 | 2021-03-04 | 3 |  | 3 | [20 empty] | 2021-03-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4619 | 1462 | 6.49 | Solar | 30W30 | 2021-02-22 | 2021-03-09 | 12 | 11 | 1 | 2021-03-10 | 2021-03-10 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-03-31 |  | YES | Expedited | [8 empty] | 2021-04-16 | In Operation | Res | Y
Fitchburg | Ashby | 4614 | 1431 | 7.6 | Solar | 39W19 | 2021-02-18 | 2021-03-09 | 14 | 13 | 1 | 2021-03-10 | 2021-03-10 | 1 |  | 1 | [20 empty] | 2021-03-17 |  |  | NO | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4612 | 1420 | 4.75 | Solar | 50W51 | 2021-02-18 | 2021-02-24 | 5 | 4 | 1 | 2021-02-24 | 2021-02-25 | 2 |  | 2 | [20 empty] | 2021-03-09 | 2021-03-12 |  | YES | Expedited | [8 empty] | 2021-05-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4608 | 1420 | 8.96 | Solar | 20W22 | 2021-02-16 | 2021-02-22 | 5 | 4 | 1 | 2021-02-22 | 2021-02-22 | 1 |  | 1 | [20 empty] | 2021-02-26 | 2021-07-12 |  | YES | Expedited | [8 empty] | 2021-08-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 4606 | 1420 | 7.6 | Solar | 35W36 | 2021-02-12 | 2021-03-30 | 32 | 32 | 0 | 2021-03-30 | 2021-03-31 | 2 |  | 2 | [20 empty] | 2021-04-06 | 2021-05-17 |  | YES | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Ashby | 4604 | 1431 | 7.965 | Solar | 39W19 | 2021-02-12 | 2021-02-19 | 5 | 5 | 0 | 2021-02-19 | 2021-02-22 | 2 |  | 2 | [20 empty] | 2021-02-26 | 2021-03-01 |  | YES | Expedited | [8 empty] | 2021-05-19 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4603 | 1462 | 3.8 | Solar | 30W31 | 2021-02-11 | 2021-02-18 | 5 | 4 | 1 | 2021-02-19 | 2021-02-22 | 2 |  | 2 | [20 empty] | 2021-02-26 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4601 | 1420 | 3.8 | Solar | 35W36 | 2021-02-11 | 2021-03-02 | 13 | 13 | 0 | 2021-03-03 | 2021-03-04 | 2 |  | 2 | [20 empty] | 2021-04-26 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-09-03 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4600 | 1420 | 5 | Solar | 20W22 | 2021-02-10 | 2021-03-02 | 14 | 14 | 0 | 2021-03-03 | 2021-03-05 | 3 |  | 3 | [20 empty] | 2021-03-12 | 2021-03-30 |  | YES | Expedited | [8 empty] | 2021-07-06 | In Operation | Res | Y
Fitchburg | Townsend | 4589 | 1474 | 10 | Solar | 39W18 | 2021-02-05 | 2021-02-17 | 8 | 8 | 0 | 2021-02-17 | 2021-02-17 | 1 |  | 1 | [20 empty] | 2021-02-18 | 2021-02-26 |  | YES | Expedited | [8 empty] | 2021-05-03 | In Operation | Res | Y
Fitchburg | Ashby | 4588 | 1431 | 7.6 | Solar | 39W19 | 2021-02-05 | 2021-02-17 | 8 | 8 | 0 | 2021-02-18 | 2021-02-23 | 4 |  | 4 | [20 empty] | 2021-02-26 | 2021-03-23 |  | YES | Expedited | [8 empty] | 2021-06-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4586 | 1420 | 6 | Solar | 31W37 | 2021-02-02 | 2021-03-18 | 32 | 30 | 2 | 2021-03-19 | 2021-03-22 | 2 |  | 2 | [20 empty] | 2021-03-26 | 2021-04-01 |  | YES | Expedited | [8 empty] | 2021-09-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4574 | 1462 | 7.68 | Solar | 30W30 | 2021-01-27 | 2021-02-25 | 21 | 21 | 0 | 2021-03-08 | 2021-03-08 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-06-15 | In Operation | Res | Y
Fitchburg | Townsend | 4572 | 1469 | 10 | Solar | 15W16 | 2021-01-26 | 2021-02-17 | 16 | 15 | 1 | 2021-02-17 | 2021-02-17 | 1 |  | 1 | [20 empty] | 2021-02-24 | 2021-03-10 |  | YES | Expedited | [8 empty] | 2021-04-19 | In Operation | Res | Y
Fitchburg | Townsend | 4571 | 1474 | 9.75 | Solar | 39W18 | 2021-01-26 | 2021-02-16 | 15 | 14 | 1 | 2021-02-17 | 2021-03-22 | 24 | 23 | 1 | [20 empty] | 2021-03-26 | 2021-04-05 |  | YES | Expedited | [8 empty] | 2021-05-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 4570 | 1420 | 9.75 | Solar | 01W04 | 2021-01-26 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4568 | 1420 | 2738 | Solar + Energy Storage | 25W27 | 2021-01-21 | 2021-02-02 | 9 | 8 | 1 | [10 empty] | 2021-02-04 | 2021-03-16 | 28 |  | 27 | 2021-04-29 | 2021-09-02 | 90 | 21 | 69 | [5 empty] | 2021-11-17 |  |  | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4564 | 1420 | 6 | Solar | 01W04 | 2021-01-21 | 2021-02-16 | 18 | 17 | 1 | 2021-02-16 | 2021-02-17 | 2 |  | 2 | [20 empty] | 2021-02-18 | 2021-04-12 |  | YES | Expedited | [8 empty] | 2021-04-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4554 | 1420 | 10 | Solar | 01W04 | 2021-01-06 | 2021-01-20 | 10 | 9 | 1 | 2021-01-20 | 2021-01-20 | 1 |  | 1 | [20 empty] | 2021-01-25 | 2021-02-10 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4552 | 1462 | 6.5 | Solar | 30W31 | 2021-01-06 | 2021-02-04 | 21 | 21 | 0 | 2021-02-04 | 2021-02-04 | 1 |  | 1 | [20 empty] | 2021-02-12 | 2021-02-23 |  | YES | Expedited | [8 empty] | 2021-04-22 | In Operation | Res | Y
Fitchburg | Townsend | 4551 | 1469 | 7.6 | Solar | 39W18 | 2021-01-05 | 2021-01-29 | 18 | 16 | 2 | 2021-02-01 | 2021-02-02 | 2 |  | 2 | [20 empty] | 2021-02-08 | 2021-02-15 |  | YES | Expedited | [8 empty] | 2021-08-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 4548 | 1462 | 9.735 | Solar | 30W30 | 2020-12-31 | 2021-01-20 | 13 | 12 | 1 | 2021-01-20 | 2021-01-21 | 2 |  | 2 | [20 empty] | 2021-02-01 | 2021-02-19 |  | YES | Expedited | [8 empty] | 2021-04-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 4544 | 1462 | 7.6 | Solar | 30W31 | 2020-12-30 | 2021-01-18 | 12 | 7 | 5 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-22 | 2021-04-15 |  | YES | Expedited | [8 empty] | 2021-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 4543 | 1462 | 8.96 | Solar | 31W37 | 2020-12-30 | 2021-01-19 | 13 | 10 | 3 | 2021-01-19 | 2021-01-19 | 1 |  | 1 | [20 empty] | 2021-01-22 | 2021-04-09 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 4542 | 1462 | 7.6 | Solar | 30W31 | 2020-12-30 | 2021-01-18 | 12 | 12 | 0 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-21 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-08-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4540 | 1420 | 7.6 | Solar | 35W36 | 2020-12-29 | 2021-01-07 | 7 | 6 | 1 | 2021-01-07 | 2021-01-08 | 2 |  | 2 | [20 empty] | 2021-01-21 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4535 | 1420 | 3 | Solar | 01W04 | 2020-12-24 | 2021-01-21 | 18 | 18 | 0 | 2021-01-22 | 2021-01-22 | 1 |  | 1 | [20 empty] | 2021-02-01 | 2021-02-04 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4533 | 1462 | 9.8 | Solar | 30W30 | 2020-12-23 | 2021-01-18 | 16 | 6 | 10 | 2021-01-18 | 2021-01-19 | 1 |  | 1 | [20 empty] | 2021-01-22 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-10-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 4531 | 1420 | 9.75 | Solar | 31W37 | 2020-12-22 | 2021-02-04 | 30 | 30 | 0 | 2021-02-04 | 2021-02-04 | 1 |  | 1 | [20 empty] | 2021-02-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4526 | 1431 | 10 | Solar | 39W19 | 2020-12-18 | 2021-01-18 | 19 | 16 | 3 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-21 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-03-25 | In Operation | Res | Y
Fitchburg | Ashby | 4519 | 1431 | 6 | Solar | 39W19 | 2020-12-17 | 2020-12-21 | 3 |  | 3 | 2020-12-22 | 2020-12-29 | 5 |  | 5 | [20 empty] | 2021-01-18 | 2021-02-11 |  | YES | Expedited | [8 empty] | 2021-03-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 4518 | 1462 | 7.6 | Solar | 30W31 | 2020-12-15 | 2021-02-26 | 50 | 41 | 9 | 2021-02-26 | 2021-02-26 | 1 |  | 1 | [20 empty] | 2021-03-09 | 2021-12-09 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4510 | 1420 | 3.8 | Solar | 01W04 | 2020-12-11 | 2020-12-21 | 7 | 5 | 2 | 2020-12-22 | 2020-12-29 | 5 |  | 5 | [20 empty] | 2021-01-05 | 2021-01-08 |  | YES | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4501 | 1420 | 10 | Solar | 30W31 | 2020-12-08 | 2020-12-09 | 2 | 1 | 1 | 2020-12-10 | 2020-12-10 | 1 |  | 1 | [20 empty] | 2021-01-21 | 2021-02-04 |  | YES | Expedited | [8 empty] | 2021-03-26 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4499 | 1420 | 500 | Solar | 50W56 | 2020-12-07 | 2021-02-15 | 47 | 47 | 1 | [10 empty] | 2021-02-18 | 2021-03-11 | 16 |  | 16 | 2021-08-13 | 2023-05-25 | 439 | 368 | 71 | [5 empty] | 2023-08-01 | 2024-04-25 | 2026-06-20 | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Lunenburg | 4496 | 1462 | 7.6 | Solar | 0 | 2020-12-07 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4493 | 1469 | 6.75 | Solar | 15W16 | 2020-12-03 | 2020-12-14 | 8 | 6 | 2 | 2020-12-14 | 2020-12-15 | 2 |  | 2 | [20 empty] | 2020-12-22 | 2021-03-08 |  | YES | Expedited | [8 empty] | 2021-03-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4491 | 1420 | 7.6 | Solar | 01W04 | 2020-12-02 | 2021-01-06 | 24 | 23 | 1 | 2021-01-06 | 2021-01-07 | 2 |  | 2 | [20 empty] | 2021-02-01 | 2021-02-12 |  | YES | Expedited | [8 empty] | 2022-02-09 | In Operation | Res | Y
Fitchburg | Ashby | 4480 | 1431 | 7.6 | Solar | 39W19 | 2020-11-25 | 2020-12-01 | 4 | 3 | 1 | 2020-12-02 | 2020-12-07 | 0 |  | 0 | [20 empty] | 2020-12-14 | 2020-12-18 | 2020-12-12 | YES | Expedited | [8 empty] | 2021-05-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 4478 | 1462 | 8.5 | Solar | 30W31 | 2020-11-24 | 2021-01-27 | 43 | 40 | 3 | 2021-01-27 | 2021-01-27 | 0 |  | 0 | [20 empty] | 2021-02-08 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-03-17 | In Operation | Res | Y
Fitchburg | Townsend | 4476 | 1469 | 3.8 | Solar | 15W16 | 2020-11-24 | 2021-01-29 | 45 | 41 | 4 | 2021-01-29 | 2021-02-01 | 0 |  | 0 | [20 empty] | 2021-02-08 | 2021-04-06 |  | YES | Expedited | [8 empty] | 2021-08-13 | In Operation | Res | Y
Fitchburg | Townsend | 4474 | 1469 | 9.8 | Solar | 15W16 | 2020-11-23 | 2021-01-25 | 42 | 42 | 0 | 2021-01-26 | 2021-01-26 | 0 |  | 0 | [20 empty] | 2021-02-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4466 | 1462 | 8.84 | Solar | 31W38 | 2020-11-19 | 2020-12-28 | 26 | 25 | 1 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-06 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4464 | 1420 | 2738 | Solar + Energy Storage | 20W22 | 2020-11-18 | 2020-11-30 | 8 | 3 | 5 | [10 empty] | 2020-12-02 | 2020-12-09 | 6 |  | 5 | 2021-02-02 | 2021-06-22 | 98 | 16 | 82 | [5 empty] | 2021-08-25 | 2022-11-28 | 2020-12-03 | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Townsend | 4446 | 1469 | 7.5 | Solar | 15W16 | 2020-11-10 | 2020-11-20 | 8 | 6 | 2 | 2020-11-21 | 2020-11-23 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-23 | 2020-11-02 | YES | Expedited | [8 empty] | 2021-01-09 | In Operation | Res | Y
Fitchburg | Townsend | 4442 | 1469 | 5 | Solar | 15W16 | 2020-11-07 | 2021-01-11 | 42 | 41 | 1 | 2021-01-12 | 2021-01-19 | 5 |  | 5 | [20 empty] | 2021-01-22 | 2021-03-25 |  | YES | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4435 | 1462 | 10 | Solar | 30W31 | 2020-10-30 | 2020-11-24 | 17 | 16 | 1 | 2020-11-25 | 2020-11-25 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-09 |  | YES | Expedited | [8 empty] | 2021-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 4432 | 1462 | 4 | Solar | 31W37 | 2020-10-27 | 2021-01-18 | 55 | 51 | 4 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-22 | 2021-02-16 | 2020-08-31 | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Townsend | 4425 | 1469 | 10 | Solar | 39W18 | 2020-10-26 | 2020-11-05 | 9 | 8 | 1 | 2020-11-06 | 2020-12-07 | 20 |  | 20 | [20 empty] | 2020-12-14 | 2020-12-18 | 2020-11-19 | YES | Expedited | [8 empty] | 2021-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 4424 | 1462 | 10 | Solar | 31W37 | 2020-10-24 | [31 empty] | 2020-11-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4423 | 1462 | 10 | Solar | 30W30 | 2020-10-24 | 2021-01-12 | 53 | 41 | 12 | 2021-01-13 | 2021-01-19 | 4 |  | 4 | [20 empty] | 2021-01-22 | 2021-02-03 | 2020-11-24 | YES | Expedited | [8 empty] | 2021-06-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4422 | 1462 | 8 | Solar | 30W30 | 2020-10-23 | [31 empty] | 2020-10-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4421 | 1469 | 10 | Solar | 39W18 | 2020-10-23 | 2020-12-28 | 44 | 40 | 4 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-18 |  | 2020-11-23 | NO | Expedited | [8 empty] | 2021-11-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 4420 | 1462 | 7.6 | Solar | 31W37 | 2020-10-23 | [31 empty] | 2020-11-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4419 | 1462 | 7.6 | Solar | 30W31 | 2020-10-23 | [31 empty] | 2020-11-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4418 | 1420 | 5 | Solar | 20W22 | 2020-10-23 | 2020-11-24 | 22 | 21 | 1 | 2020-11-25 | 2020-11-25 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-09 |  | YES | Expedited | [8 empty] | 2020-12-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 4414 | 1462 | 10 | Solar | 31W37 | 2020-10-21 | 2020-12-28 | 46 | 44 | 2 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-06 | 2021-02-03 | 2020-10-12 | YES | Expedited | [8 empty] | 2021-07-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 4410 | 1462 | 10 | Solar | 30W31 | 2020-10-20 | 2020-10-28 | 7 | 5 | 2 | 2020-10-28 | 2020-10-29 | 2 |  | 2 | [20 empty] | 2020-11-10 | 2020-11-17 | 2020-10-26 | YES | Expedited | [8 empty] | 2021-04-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 4409 | 1462 | 9.75 | Solar | 31W38 | 2020-10-19 | 2020-10-27 | 7 | 6 | 1 | 2020-10-28 | 2020-10-28 | 1 |  | 1 | [20 empty] | 2020-11-10 | 2021-02-03 | 2020-09-19 | YES | Expedited | [8 empty] | 2021-02-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4408 | 1420 | 3.8 | Solar | 01W04 | 2020-10-19 | 2020-10-23 | 5 | 4 | 1 | 2020-10-23 | 2020-10-26 | 2 |  | 2 | [20 empty] | 2020-10-29 | 2020-11-03 | 2020-11-09 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4404 | 1420 | 7.6 | Multiple | 40W40 | 2020-10-16 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 4388 | 1469 | 10 | Solar | 15W17 | 2020-10-08 | 2020-10-28 | 14 | 13 | 1 | 2020-10-28 | 2020-10-29 | 2 |  | 2 | [20 empty] | 2020-11-10 | 2020-11-17 |  | YES | Expedited | [8 empty] | 2021-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4387 | 1420 | 5 | Solar | 22W1 | 2020-10-07 | 2020-11-16 | 27 | 23 | 4 | 2020-11-17 | 2020-11-25 | 7 | 6 | 1 | [20 empty] | 2020-12-03 | 2021-01-26 |  | YES | Expedited | [8 empty] | 2021-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 4378 | 1420 | 3.8 | Solar | 31W37 | 2020-09-30 | 2020-10-06 | 5 | 3 | 2 | 2020-10-07 | 2020-10-07 | 1 |  | 1 | [20 empty] | 2020-10-15 |  | 2020-09-20 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4376 | 1420 | 9.75 | Solar | 01W04 | 2020-09-30 | 2020-10-13 | 9 | 7 | 2 | 2020-10-13 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2021-02-23 | 2020-10-16 | YES | Expedited | [8 empty] | 2021-03-09 | In Operation | Res | Y
Fitchburg | Townsend | 4375 | 1474 | 7.5 | Solar | 39W18 | 2020-09-30 | 2020-10-27 | 19 | 18 | 1 | 2020-10-28 | 2020-10-28 | 1 |  | 1 | [20 empty] | 2020-11-10 | 2020-12-14 | 2020-10-05 | YES | Expedited | [8 empty] | 2020-12-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 4374 | 1462 | 10 | Solar | 31W38 | 2020-09-28 | 2020-10-14 | 12 | 7 | 5 | 2020-10-15 | 2020-10-15 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-12-18 |  | YES | Expedited | [8 empty] | 2021-01-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 4371 | 1462 | 7.6 | Solar | 30W31 | 2020-09-25 | 2020-10-05 | 7 | 5 | 2 | 2020-10-05 | 2020-10-06 | 2 |  | 2 | [20 empty] | 2020-10-15 | 2020-10-22 | 2020-10-11 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4361 | 1474 | 5.5 | Solar | 39W18 | 2020-09-22 | 2020-10-01 | 8 | 7 | 1 | 2020-10-01 | 2020-10-02 | 2 |  | 2 | [20 empty] | 2020-10-23 | 2020-11-06 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4352 | 1462 | 8 | Solar | 30W31 | 2020-09-15 | 2020-11-16 | 43 | 40 | 3 | 2020-11-17 | 2020-11-17 | 1 |  | 1 | [20 empty] | 2020-11-30 | 2021-01-06 | 2020-09-26 | YES | Expedited | [8 empty] | 2021-01-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 4351 | 1462 | 7.6 | Solar | 30W31 | 2020-09-15 | 2020-09-23 | 7 | 4 | 3 | 2020-09-23 | 2020-09-23 | 1 |  | 1 | [20 empty] | 2020-10-20 |  | 2020-11-07 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4350 | 1462 | 15.2 | Solar + Energy Storage | 30W31 | 2020-09-14 | 2020-09-30 | 13 | 12 | 1 | 2020-10-01 | 2021-02-10 | [23 empty] | 2021-02-16 | 2021-02-25 |  | YES | Expedited | [8 empty] | 2021-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 4347 | 1420 | 16 | Solar | 40W40 | 2020-09-14 | 2020-09-23 | 8 | 7 | 1 | 2020-09-23 | 2020-09-24 | 2 |  | 2 | [20 empty] | 2020-10-05 |  | 2020-09-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4346 | 1469 | 9.75 | Solar | 39W18 | 2020-09-11 | 2020-09-15 | 3 | 2 | 1 | 2020-09-16 | 2020-09-18 | 3 |  | 3 | [20 empty] | 2020-10-05 | 2021-02-19 | 2020-09-16 | YES | Expedited | [8 empty] | 2021-04-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 4339 | 1464 | 2 | Solar | 30W30 | 2020-09-08 | 2020-10-12 | 24 | 22 | 2 | 2020-10-12 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-10-28 | 2020-09-17 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4338 | 1420 | 2.95 | Solar | 31W37 | 2020-09-08 | 2020-09-17 | 8 | 7 | 1 | 2020-09-18 | 2020-09-18 | 1 |  | 1 | [20 empty] | 2020-09-25 | 2021-02-03 | 2020-09-18 | YES | Expedited | [8 empty] | 2021-02-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 4329 | 1462 | 10.15 | Solar | 30W31 | 2020-09-02 | 2020-09-10 | 6 | 5 | 1 | 2020-09-11 | 2020-09-15 | 3 |  | 3 | [20 empty] | 2020-09-17 |  | 2020-09-19 | NO | Expedited | [8 empty] | 2020-11-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4327 | 1420 | 7.68 | Solar w/ Back-up Battery | 01W04 | 2020-09-02 | 2020-10-30 | 41 | 39 | 2 | 2020-11-02 | 2020-11-03 | 2 |  | 2 | [20 empty] | 2020-11-17 | 2020-12-10 | 2020-09-20 | YES | Expedited | [8 empty] | 2021-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4325 | 1420 | 7.6 | Solar | 01W04 | 2020-08-31 | 2020-09-11 | 9 | 8 | 1 | 2020-09-14 | 2020-09-16 | 3 |  | 3 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-09-21 | YES | Expedited | [8 empty] | 2021-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 4324 | 1462 | 10 | Solar | 30W30 | 2020-08-31 | 2020-09-14 | 10 | 9 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-18 | 2020-09-25 | 2020-10-27 | YES | Expedited | [8 empty] | 2020-12-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 4323 | 1462 | 7.6 | Solar | 30W31 | 2020-08-31 | 2020-09-14 | 10 | 9 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-25 | 2020-10-12 | 2020-09-24 | YES | Expedited | [8 empty] | 2021-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4320 | 1420 | 7.6 | Solar | 31W37 | 2020-08-28 | 2020-09-14 | 11 | 10 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-25 | 2020-10-09 | 2020-09-01 | YES | Expedited | [8 empty] | 2021-06-22 | In Operation | Res | Y
Fitchburg | Townsend | 4316 | 1469 | 6.75 | Solar | 15W16 | 2020-08-27 | 2020-09-10 | 10 | 8 | 2 | 2020-09-11 | 2020-09-16 | 4 |  | 4 | [20 empty] | 2020-09-17 | 2020-09-21 | 2020-09-10 | YES | Expedited | [8 empty] | 2020-10-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4312 | 1420 | 7.95 | Solar | 35W36 | 2020-08-26 | 2020-08-27 | 2 |  | 2 | 2020-08-28 | 2020-09-01 | 3 |  | 3 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-08-26 | YES | Expedited | [8 empty] | 2021-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4309 | 1420 | 7.5 | Solar | 01W04 | 2020-08-25 | 2020-08-31 | 5 | 4 | 1 | 2020-09-01 | 2020-09-02 | 2 |  | 2 | [20 empty] | 2020-09-02 |  | 2020-06-21 | NO | Expedited | [8 empty] | 2021-10-15 | In Operation | Res | Y
Fitchburg | Ashby | 4308 | 1431 | 9.5 | Solar | 39W19 | 2020-08-25 | 2020-08-31 | 5 | 4 | 1 | 2020-08-31 | 2020-09-01 | 2 |  | 2 | [20 empty] | 2020-09-02 | 2020-10-26 | 2020-06-29 | YES | Expedited | [8 empty] | 2020-10-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4307 | 1420 | 4999 | Solar + Energy Storage | 40W38 | 2020-08-25 | 2020-09-23 | 21 | 19 | 2 | [10 empty] | 2020-10-06 | 2020-10-22 | 12 |  | 12 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 4301 | 1420 | 6.75 | Solar | 31W37 | 2020-08-21 | 2020-08-28 | 6 | 5 | 1 | 2020-08-31 | 2020-09-01 | 2 |  | 2 | [20 empty] | 2020-09-02 | 2020-12-23 | 2020-09-25 | YES | Expedited | [8 empty] | 2021-02-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 4291 | 1420 | 3.8 | Solar | 01W04 | 2020-08-14 | 2020-09-04 | 16 | 14 | 2 | 2020-09-07 | 2020-09-15 | 6 |  | 6 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-10-05 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4284 | 1462 | 3.8 | Solar | 30W31 | 2020-08-12 | 2020-08-20 | 7 | 3 | 4 | 2020-08-21 | 2020-08-25 | 3 |  | 3 | [20 empty] | 2020-08-31 | 2020-09-09 | 2020-09-30 | YES | Expedited | [8 empty] | 2020-12-29 | In Operation | Res | Y
Fitchburg | Ashby | 4279 | 1431 | 3.8 | Solar | 39W19 | 2020-08-11 | [31 empty] | 2020-10-13 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 4273 | 1462 | 7.6 | Solar | 30W30 | 2020-08-06 | 2020-08-13 | 6 | 5 | 1 | 2020-08-13 | 2020-08-14 | 2 |  | 2 | [20 empty] | 2020-08-31 | 2020-09-09 | 2020-09-01 | YES | Expedited | [8 empty] | 2020-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 4267 | 1462 | 7.6 | Solar | 30W31 | 2020-08-05 | 2020-08-06 | 2 |  | 2 | 2020-08-07 | 2020-08-11 | 3 |  | 3 | [20 empty] | 2020-08-12 | 2020-08-17 | 2020-10-06 | YES | Expedited | [8 empty] | 2020-12-08 | In Operation | Res | Y
Fitchburg | Ashby | 4257 | 1431 | 6 | Solar | 39W19 | 2020-08-10 | 2020-08-11 | 2 |  | 2 | 2020-08-11 | 2020-08-11 | 1 |  | 1 | [20 empty] | 2020-08-24 | 2020-09-09 | 2020-08-10 | YES | Expedited | [8 empty] | 2020-10-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4254 | 1420 | 12.15 | Solar | 35W36 | 2020-07-30 | 2020-09-30 | 44 | 40 | 4 | 2020-10-01 | 2020-10-07 | 5 |  | 5 | [20 empty] | 2020-10-29 | 2021-03-02 | 2020-09-30 | YES | Expedited | [8 empty] | 2021-03-11 | In Operation | Res | Y
Fitchburg | Townsend | 4241 | 1469 | 10 | Solar | 15W16 | 2020-07-21 | 2020-10-13 | 59 | 55 | 4 | 2020-10-13 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-10-21 | 2020-09-01 | YES | Expedited | [8 empty] | 2020-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4237 | 1420 | 2999 | Solar + Energy Storage | 25W28 | 2020-07-20 | 2020-08-10 | 16 | 8 | 8 | [10 empty] | 2020-08-14 | 2020-08-28 | 11 |  | 11 | 2020-09-18 | [12 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 4228 | 1462 | 24.4 | Solar + Energy Storage | 30W31 | 2020-07-10 | 2020-07-20 | 7 | 5 | 2 | 2020-08-13 | 2020-09-24 | [23 empty] | 2020-10-16 | 2021-02-09 | 2020-09-10 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4213 | 1420 | 245 | Solar + Energy Storage | 20H22 | 2020-06-29 | 2020-07-10 | 10 | 2 | 8 | [5 empty] | 2020-10-14 | 2020-11-16 | 23 |  | 23 | [17 empty] | 2020-09-15 | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 4204 | 1469 | 8 | Solar | 39W18 | 2020-06-15 | 2020-06-18 | 4 | 1 | 3 | 2020-06-19 | 2020-06-23 | 3 |  | 3 | [20 empty] | 2020-07-09 | 2020-07-20 | 2020-07-02 | YES | Expedited | [8 empty] | 2020-08-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 4192 | 1420 | 86.4 | Solar | 22W1 | 2020-06-24 | 2020-07-01 | 6 | 3 | 3 | 2020-07-02 | 2020-08-13 | 31 |  | 31 | [20 empty] | 2020-08-31 | 2020-09-11 | 2020-09-07 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4178 | 1469 | 5.9 | Solar | 15W16 | 2020-05-26 | 2020-06-23 | 21 | 19 | 2 | 2018-06-24 | 2018-06-25 | 1 |  | 1 | [20 empty] | 2020-06-30 | 2020-07-06 | 2020-07-19 | YES | Expedited | [8 empty] | 2020-09-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 4176 | 1462 | 7 | Solar | 31W38 | 2020-05-28 | 2020-06-10 | 10 | 6 | 4 | 2020-06-11 | 2020-06-15 | 3 |  | 3 | [20 empty] | 2020-06-18 | 2020-06-22 | 2020-06-23 | YES | Expedited | [8 empty] | 2020-11-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4163 | 1462 | 10 | Solar | 31W37 | 2020-05-18 | 2020-05-21 | 4 | 2 | 2 | 2020-05-22 | 2020-05-26 | 2 |  | 2 | [20 empty] | 2020-05-28 | 2020-06-15 |  | YES | Expedited | [8 empty] | 2020-10-07 | In Operation | Res | Y
Fitchburg | Townsend | 4160 | 1474 | 10 | Solar | 39W19 | 2020-05-11 | 2020-05-15 | 5 | 2 | 3 | 2020-05-18 | 2020-05-18 | 1 |  | 1 | [20 empty] | 2020-05-27 | 2020-07-07 | 2020-07-10 | YES | Expedited | [8 empty] | 2020-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4147 | 1420 | 3.8 | Solar | 35W36 | 2020-04-30 | 2020-07-02 | 45 | 34 | 11 | 2020-07-06 | 2020-07-09 | 4 |  | 4 | [20 empty] | 2020-07-16 | 2020-07-29 | 2020-06-30 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4128 | 1420 | 3.8 | Solar | 01W04 | 2020-04-13 | 2020-04-20 | 5 | 4 | 1 | 2020-04-21 | 2020-04-21 | 1 |  | 1 | [20 empty] | 2020-05-07 | 2020-09-03 | 2020-06-13 | YES | Expedited | [8 empty] | 2020-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4127 | 1420 | 7.6 | Solar | 01W04 | 2020-04-13 | 2020-04-21 | 6 | 4 | 2 | 2020-04-22 | 2020-04-23 | 2 |  | 2 | [20 empty] | 2020-05-15 | 2020-06-25 | 2020-06-13 | YES | Expedited | [8 empty] | 2020-07-13 | In Operation | Res | Y
Fitchburg | Ashby | 4122 | 1431 | 9.765 | Solar | 39W19 | 2020-04-09 | 2020-05-28 | 34 | 21 | 13 | 2020-06-03 | 2020-06-17 | 11 | 6 | 5 | [20 empty] | 2020-06-18 | 2020-07-20 |  | YES | Expedited | [8 empty] | 2020-08-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 4121 | 1462 | 5 | Solar | 30W30 | 2020-04-08 | 2020-05-15 | 27 | 22 | 5 | 2020-05-18 | 2020-05-18 | 1 |  | 1 | [20 empty] | 2020-07-17 | 2020-07-22 |  | YES | Expedited | [8 empty] | 2020-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4118 | 1462 | 3.8 | Solar | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 | 2020-08-05 | 2020-06-03 | YES | Expedited | [8 empty] | 2020-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4117 | 1462 | 7.6 | Solar | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 |  | 2020-06-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4116 | 1462 | 3.8 | Solar | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 |  | 2020-06-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4115 | 1462 | 10 | Solar | 30W30 | 2020-04-03 | 2020-04-13 | 7 | 4 | 3 | 2020-04-13 | 2020-04-13 | 1 |  | 1 | [20 empty] | 2020-04-23 | 2020-09-25 | 2020-06-03 | YES | Expedited | [8 empty] | 2020-09-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4113 | 1462 | 6.785 | Solar | 30W31 | 2020-04-03 | 2020-04-14 | 8 | 5 | 3 | 2020-04-15 | 2020-04-16 | 2 |  | 2 | [20 empty] | 2020-05-27 | 2020-07-20 |  | YES | Expedited | [8 empty] | 2020-08-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 4099 | 1420 | 4394 | Solar + Energy Storage | 25W28 | 2020-03-13 | 2020-04-08 | 19 | 17 | 2 | [10 empty] | 2020-05-19 | 2020-05-19 | 0 |  | 0 | 2020-05-19 | 2020-09-10 | 81 | 1 | 80 | [5 empty] | 2020-11-06 | 2021-10-19 | 2019-10-01 | YES | Standard | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-09-12 | In Operation | Comm | N
Fitchburg | Fitchburg | 4092 | 1420 | 5.5 | Solar | 31W37 | 2020-03-13 | 2020-03-17 | 3 | 2 | 1 | 2020-03-18 | 2020-03-19 | 2 |  | 2 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-05-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4091 | 1420 | 4.25 | Solar | 01W04 | 2020-03-13 | 2020-03-17 | 3 | 2 | 1 | 2020-03-18 | 2020-03-19 | 2 |  | 2 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-07-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4089 | 1462 | 7.6 | Solar | 31W38 | 2020-03-11 | 2020-03-18 | 6 | 3 | 3 | 2020-03-19 | 2020-03-19 | 1 |  | 1 | [20 empty] | 2020-04-06 | 2020-08-12 | 2020-06-11 | YES | Expedited | [8 empty] | 2020-08-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4069 | 1420 | 8.75 | Solar | 31W37 | 2020-03-07 | 2020-03-13 | 5 | 3 | 2 | 2020-03-16 | 2020-03-19 | 4 |  | 4 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-05-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 4051 | 1462 | 6 | Solar | 30W30 | 2020-02-24 | 2020-03-04 | 8 | 5 | 3 | 2020-03-06 | 2020-03-10 | 3 |  | 3 | [20 empty] | 2020-04-07 | 2020-04-20 | 2020-04-20 | YES | Expedited | [8 empty] | 2020-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 4044 | 1462 | 9.9 | Solar | 31W38 | 2020-02-13 | 2020-04-30 | 54 | 53 | 1 | 2020-05-01 | 2020-06-01 | 21 |  | 21 | [20 empty] | 2020-06-18 | 2020-11-24 | 2020-04-13 | YES | Expedited | [8 empty] | 2021-04-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4043 | 1420 | 4.25 | Solar | 31W37 | 2020-02-18 | 2020-02-19 | 2 |  | 2 | 2020-02-20 | 2020-03-11 | 15 |  | 15 | [20 empty] | 2020-04-01 | 2020-04-13 | 2020-02-29 | YES | Expedited | [8 empty] | 2020-06-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4038 | 1462 | 9.8 | Solar | 30W30 | 2020-02-12 | 2020-02-13 | 2 |  | 2 | 2020-02-14 | 2020-02-17 | 1 |  | 1 | [20 empty] | 2020-02-25 | 2020-03-12 | 2020-03-09 | YES | Expedited | [8 empty] | 2020-06-24 | In Operation | Res | Y
Fitchburg | Townsend | 4027 | 1469 | 5 | Solar | 15W17 | 2020-01-30 | 2020-02-04 | 4 |  | 4 | 2020-02-05 | 2020-02-10 | 4 |  | 4 | [20 empty] | 2020-02-13 | 2020-02-14 | 2020-02-29 | YES | Expedited | [8 empty] | 2020-03-31 | In Operation | Res | Y
Fitchburg | Ashby | 4022 | 1431 | 10 | Solar | 39W19 | 2020-01-23 | 2020-02-10 | 13 | 11 | 2 | 2020-02-11 | 2020-02-18 | 5 |  | 5 | [20 empty] | 2020-02-25 | 2020-03-10 | 2020-04-01 | YES | Expedited | [8 empty] | 2020-12-04 | In Operation | Res | Y
Fitchburg | Townsend | 4021 | 1469 | 10 | Solar | 39W18 | 2020-01-21 | 2020-01-23 | 3 |  | 3 | 2020-01-27 | 2020-01-28 | 2 |  | 2 | [20 empty] | 2020-02-03 | 2020-02-05 |  | YES | Expedited | [8 empty] | 2020-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4017 | 1462 | 7.67 | Solar | 31W38 | 2020-01-20 | 2020-02-07 | 14 | 11 | 3 | 2020-02-10 | 2020-02-17 | 5 |  | 5 | [20 empty] | 2020-02-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4013 | 1420 | 7.6 | Solar | 35W36 | 2020-01-23 | 2020-01-24 | 2 |  | 2 | 2020-01-27 | 2020-01-31 | 5 |  | 5 | [20 empty] | 2020-02-03 | 2020-02-07 |  | YES | Expedited | [8 empty] | 2020-06-05 | In Operation | Res | Y
Fitchburg | Ashby | 4005 | 1431 | 10 | Solar | 39W19 | 2019-12-24 | 2019-12-27 | 3 |  | 3 | 2019-12-30 | 2020-01-07 | 6 |  | 6 | [20 empty] | 2020-01-14 | 2020-01-16 | 2020-01-20 | YES | Expedited | [8 empty] | 2020-02-19 | In Operation | Res | Y
Fitchburg | Townsend | 3998 | 1474 | 5.76 | Solar | 39W18 | 2019-12-11 | 2019-12-18 | 6 | 3 | 3 | 2019-12-19 | 2019-12-24 | 4 |  | 4 | [20 empty] | 2020-01-07 | 2020-01-13 | 2020-02-11 | YES | Expedited | [8 empty] | 2020-06-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3993 | 1462 | 7.08 | Solar | 39W18 | 2019-12-26 | 2019-12-27 | 2 |  | 2 | 2019-12-30 | 2019-12-31 | 2 |  | 2 | [20 empty] | 2020-01-07 | 2020-02-04 |  | YES | Expedited | [8 empty] | 2020-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 3989 | 1469 | 10 | Solar | 39W18 | 2019-12-09 | 2019-12-09 | 1 |  | 1 | 2019-12-10 | 2019-12-12 | 3 |  | 3 | [20 empty] | 2019-12-17 | 2020-02-04 | 2020-01-03 | YES | Expedited | [8 empty] | 2020-03-04 | In Operation | Res | Y
Fitchburg | Ashby | 3988 | 1431 | 3.8 | Solar | 39W19 | 2019-12-09 | 2019-12-09 | 1 |  | 1 | 2019-12-10 | 2019-12-12 | 3 |  | 3 | [20 empty] | 2019-12-17 | 2019-12-27 |  | YES | Expedited | [8 empty] | 2020-04-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3987 | 1462 | 10 | Solar | 31W37 | [33 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3974 | 1462 | 3.8 | Solar | 30W31 | 2019-12-23 | 2020-01-21 | 19 | 19 | 0 | 2020-01-22 | 2020-01-23 | 2 |  | 2 | [20 empty] | 2020-01-28 | 2020-01-31 |  | YES | Expedited | [8 empty] | 2020-11-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3971 | 1420 | 10 | Solar | 35W36 | 2019-11-25 | 2019-11-26 | 2 |  | 2 | 2019-11-27 | 2019-12-04 | 6 |  | 6 | [20 empty] | 2020-01-14 | 2020-01-22 |  | YES | Expedited | [8 empty] | 2020-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 3956 | 1462 | 7.6 | Solar | 31W37 | 2019-11-13 | 2019-11-13 | 1 |  | 1 | 2019-11-14 | 2019-11-25 | 7 |  | 7 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3945 | 1462 | 7.6 | Solar | 30W31 | 2019-12-10 | 2019-12-11 | 2 |  | 2 | 2019-12-11 | 2019-12-11 | 1 |  | 1 | 2020-01-24 | 2020-02-10 | 12 |  | 12 | [15 empty] | 2020-02-13 | 2020-02-20 |  | YES | Expedited | [8 empty] | 2020-10-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3944 | 1462 | 7.6 | Solar | 30W30 | 2019-11-06 | 2019-11-07 | 2 |  | 2 | 2019-11-08 | 2019-11-13 | 3 |  | 3 | [20 empty] | 2019-11-19 | 2019-11-27 |  | YES | Expedited | [8 empty] | 2021-01-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3943 | 1462 | 5 | Solar | 31W38 | 2019-11-05 | 2019-11-07 | 3 |  | 3 | 2019-11-08 | 2019-11-13 | 3 |  | 3 | [20 empty] | 2019-11-19 | 2019-11-26 |  | YES | Expedited | [8 empty] | 2020-05-12 | In Operation | Res | Y
Fitchburg | Townsend | 3941 | 1469 | 6 | Solar | 15W17 | 2019-11-19 | 2019-11-26 | 5 |  | 5 | 2019-11-27 | 2019-12-04 | 6 |  | 6 | [20 empty] | 2020-01-28 | 2020-02-06 |  | YES | Expedited | [8 empty] | 2020-03-03 | In Operation | Res | Y
Fitchburg | Townsend | 3931 | 1474 | 7.6 | Solar | 39W18 | 2019-10-22 | 2019-10-22 | 1 |  | 1 | 2019-10-23 | 2019-10-29 | 5 |  | 5 | [20 empty] | 2019-11-01 | 2019-11-21 | 2019-12-19 | YES | Expedited | [8 empty] | 2020-07-08 | In Operation | Res | Y
Fitchburg | Townsend | 3927 | 1474 | 3.8 | Solar | 39W19 | 2019-11-05 | 2019-12-11 | 25 | 20 | 5 | 2019-12-12 | 2019-12-12 | 1 |  | 1 | [20 empty] | 2019-12-17 | 2020-01-10 |  | YES | Expedited | [8 empty] | 2020-02-20 | Cancelled | Res | Y
Fitchburg | Townsend | 3923 | 1469 | 6 | Solar | 39W18 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-12-10 | 2019-11-15 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3922 | 1474 | 10 | Solar | 39W18 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-05 | 2019-11-15 | YES | Expedited | [8 empty] | 2019-01-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3920 | 1420 | 7.6 | Solar | 31W37 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-13 | 2019-11-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3915 | 1431 | 10 | Solar | 39W19 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-12 |  | YES | Expedited | [8 empty] | 2019-12-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3914 | 1462 | 7.6 | Solar | 31W38 | 2019-10-29 | 2019-11-12 | 10 | 6 | 4 | 2019-11-13 | 2019-11-25 | 8 |  | 8 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [8 empty] | 2020-06-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3913 | 1420 | 3.8 | Solar | 31W37 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-13 |  | YES | Expedited | [8 empty] | 2020-08-18 | Cancelled | Res | Y
Fitchburg | Ashby | 3909 | 1431 | 7.6 | Solar | 39W19 | 2019-10-10 | 2019-10-14 | 3 |  | 3 | 2019-10-15 | 2019-10-21 | 5 |  | 5 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [8 empty] | 2020-05-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 3896 | 1462 | 10 | Solar | 30W31 | 2019-09-24 | 2019-09-30 | 5 |  | 5 | 2019-09-30 | 2019-09-30 | 1 |  | 1 | [20 empty] | 2019-10-08 | 2019-10-16 | 2019-11-08 | YES | Expedited | [8 empty] | 2019-12-09 | In Operation | Res | Y
Fitchburg | Ashby | 3891 | 1431 | 4.75 | Solar | 39W19 | 2019-10-03 | 2019-10-04 | 2 |  | 2 | 2019-10-14 | 2019-10-15 | 2 |  | 2 | [20 empty] | 2019-10-18 | 2019-11-12 |  | YES | Expedited | [8 empty] | 2019-12-20 | In Operation |  | Y
Fitchburg | Lunenburg | 3889 | 1462 | 10.03 | Solar | 30W30 | 2019-09-20 | 2019-09-20 | 1 |  | 1 | 2019-09-23 | 2019-09-24 | 2 |  | 2 | [20 empty] | 2019-09-30 | 2019-10-04 | 2019-10-31 | YES | Expedited | [8 empty] | 2019-12-20 | In Operation | Res | Y
Fitchburg | Townsend | 3881 | 1474 | 7.6 | Solar | 39W18 | 2019-10-04 | 2019-10-11 | 5 |  | 5 | 2019-10-14 | 2019-10-14 | 1 |  | 1 | [20 empty] | 2019-10-18 | 2019-11-21 |  | YES | Expedited | [8 empty] | 2020-03-24 | In Operation |  | Y
Fitchburg | Fitchburg | 3871 | 1420 | 17.6 | Solar | 50W55 | 2019-09-04 | 2021-02-24 |  |  |  | 2021-02-24 | 2021-02-25 | 2 |  | 2 | [20 empty] | 2021-03-09 | 2021-03-18 | 2019-04-28 | YES | Expedited | [8 empty] | 2022-01-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 3870 | 1462 | 7.6 | Solar | 31W38 | 2019-09-11 | 2019-09-13 | 3 |  | 3 | 2019-09-13 | 2019-09-16 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-09-25 | 2019-10-29 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3869 | 1420 | 7.6 | Solar | 01W04 | 2019-09-23 | 2019-09-24 | 2 |  | 2 | [27 empty] | 2019-09-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3868 | 1462 | 11.4 | Solar | 30W31 | 2019-09-03 | 2019-09-05 | 2 |  | 2 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-13 | 2019-09-24 |  | YES | Expedited | [8 empty] | 2019-11-19 | In Operation | Res | Y
Fitchburg | Townsend | 3865 | 1469 | 7.6 | Solar | 39W18 | 2019-09-04 | 2019-09-05 | 2 |  | 2 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-12 | 2019-09-16 | YES | Expedited | [8 empty] | 2019-10-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 3863 | 1462 | 10 | Solar | 31W37 | 2019-09-06 | 2019-09-10 | 3 |  | 3 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-10-15 | 2019-10-29 | YES | Expedited | [8 empty] | 2020-04-24 | In Operation | Res | Y
Fitchburg | Ashby | 3858 | 1431 | 3.52 | Solar | 39W19 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-16 | 2019-06-30 | YES | Expedited | [8 empty] | 2020-04-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 3855 | 1462 | 9.75 | Solar | 30W30 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | 2019-08-28 | 2019-08-28 | 1 |  | 1 | [20 empty] | 2019-09-04 | 2019-09-12 |  | YES | Expedited | [8 empty] | 2019-10-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3847 | 1420 | 10 | Solar | 01W04 | 2019-08-16 | 2019-08-21 | 4 |  | 4 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | [20 empty] | 2019-08-29 | 2019-08-30 |  | YES | Expedited | [8 empty] | 2020-01-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 3833 | 1462 | 4.5 | Solar | 30W30 | 2019-08-13 | 2019-08-14 | 2 |  | 2 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-20 |  | YES | Expedited | [8 empty] | 2019-10-22 | In Operation | Res | Y
Fitchburg | Ashby | 3829 | 1431 | 3.5 | Solar | 39W19 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | 2019-08-28 | 2019-08-28 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-11-25 | 2019-08-25 | YES | Expedited | [8 empty] | 2020-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 3823 | 1462 | 1000 | Solar + Energy Storage | 31W37 | 2019-07-31 | 2019-08-06 | 5 |  | 5 | [10 empty] | 2019-08-08 | 2019-08-30 | 17 |  | 17 | [14 empty] | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 3820 | 1462 | 7.6 | Solar | 30W30 | 2019-09-09 | 2019-09-10 | 2 |  | 2 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-10-03 |  | YES | Expedited | [8 empty] | 2019-12-24 | In Operation |  | Y
Fitchburg | Lunenburg | 3807 | 1462 | 7.6 | Solar | 31W38 | 2019-07-31 | 2019-08-01 | 2 |  | 2 | 2019-08-06 | 2019-08-06 | 1 |  | 1 | [20 empty] | 2019-08-15 | 2019-08-29 | 2019-07-10 | YES | Expedited | [8 empty] | 2019-12-09 | In Operation | Res | Y
Fitchburg | Townsend | 3804 | 1469 | 1000 | Solar + Energy Storage | 39W18 | 2019-07-19 | 2019-07-23 | 3 |  | 3 | [10 empty] | 2019-07-25 | 2019-08-30 | 27 |  | 27 | 2019-09-17 | 2020-03-13 | 122 | 19 | 103 | [5 empty] | 2020-10-30 |  | 2019-07-14 |  | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 3796 | 1474 | 10 | Solar | 39W18 | 2019-08-08 | 2019-08-12 | 3 |  | 3 | 2019-08-13 | 2019-08-14 | 2 |  | 2 | [20 empty] | 2019-08-15 | 2019-09-24 |  | YES | Expedited | [8 empty] | 2019-11-21 | In Operation |  | Y
Fitchburg | Lunenburg | 3795 | 1462 | 7.6 | Solar | 31W37 | 2019-07-22 | 2019-07-22 | 1 |  | 1 | 2019-07-23 | 2019-07-23 | 1 |  | 1 | [20 empty] | 2019-08-02 | 2019-08-15 | 2019-07-16 | YES | Expedited | [8 empty] | 2019-08-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 3794 | 1420 | 6 | Solar | 31W37 | 2019-07-18 | 2019-07-18 | 1 |  | 1 | 2019-07-19 | 2019-07-19 | 1 |  | 1 | [20 empty] | 2019-07-24 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3786 | 1420 | 6 | Solar | 25W27 | 2019-07-16 | 2021-03-08 |  |  |  | 2021-03-08 | 2021-03-08 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-03-25 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation |  | Y
Fitchburg | Townsend | 3785 | 1474 | 10 | Solar | 39W18 | 2019-07-17 | 2019-07-18 | 2 |  | 2 | 2019-07-19 | 2019-07-19 | 1 |  | 1 | [20 empty] | 2019-07-24 | 2019-07-29 |  | YES | Expedited | [8 empty] | 2019-08-16 | In Operation | Res | Y
Fitchburg | Townsend | 3770 | 1474 | 10 | Solar | 39W18 | 2019-07-02 | 2019-07-08 | 4 |  | 4 | 2019-07-09 | 2019-07-11 | 3 |  | 3 | [20 empty] | 2019-07-18 | 2019-08-28 |  | YES | Expedited | [8 empty] | 2019-11-25 | In Operation | Res | Y
Fitchburg | Townsend | 3768 | 1469 | 9.6 | Solar | 15W17 | 2019-07-01 | 2019-07-08 | 5 |  | 5 | 2019-07-09 | 2019-07-11 | 3 |  | 3 | [20 empty] | 2019-07-18 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3765 | 1420 | 3.8 | Solar | 25W27 | 2019-06-26 | [33 empty] | Expedited | [9 empty] | Cancelled |  | Y
Fitchburg | Lunenburg | 3751 | 1462 | 7.6 | Solar | 31W38 | 2019-06-21 | 2019-06-24 | 2 |  | 2 | 2019-06-25 | 2019-06-27 | 3 |  | 3 | [20 empty] | 2019-07-08 | 2019-07-10 | 2019-07-22 | YES | Expedited | [8 empty] | 2020-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 3750 | 1420 | 7.6 | Solar | 01W04 | 2019-06-24 | 2019-06-25 | 2 |  | 2 | 2019-06-26 | 2019-06-27 | 2 |  | 2 | [20 empty] | 2019-07-08 | 2019-11-20 | 2019-08-18 | YES | Expedited | [8 empty] | 2019-12-12 | In Operation | Res | Y
Fitchburg | Ashby | 3739 | 1431 | 3.8 | Solar | 39W19 | 2019-07-02 | 2019-07-09 | 5 |  | 5 | 2019-07-10 | 2019-07-10 | 1 |  | 1 | [20 empty] | 2019-07-18 | 2019-07-26 |  | YES | Expedited | [8 empty] | 2019-08-07 | In Operation |  | Y
Fitchburg | Townsend | 3738 | 1474 | 7.6 | Solar | 39W18 | 2019-06-12 | 2019-06-13 | 2 |  | 2 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-07-22 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 3722 | 1420 | 7.6 | Solar | 40W42 | 2019-06-10 | 2019-06-11 | 2 |  | 2 | 2020-04-04 | 2020-04-13 | 6 |  | 6 | [20 empty] | 2020-04-13 | 2020-04-20 | 2019-07-31 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3720 | 1431 | 7.6 | Solar | 39W19 | 2019-06-04 | 2019-06-04 | 1 |  | 1 | 2019-06-04 | 2019-06-04 | 1 |  | 1 | [20 empty] | 2019-06-14 | 2019-06-11 | 2019-03-21 | YES | Expedited | [8 empty] | 2019-06-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3718 | 1462 | 7.6 | Solar | 30W30 | 2019-06-17 | 2019-06-18 | 1 |  | 1 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-07-01 | 2019-07-10 | YES | Expedited | [8 empty] | 2019-08-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3714 | 1462 | 10.62 | Solar | 30W31 | 2019-05-31 | 2019-06-03 | 2 |  | 2 | 2019-06-04 | 2019-06-05 | 2 |  | 2 | [20 empty] | 2019-06-10 | 2019-06-17 | 2019-08-02 | YES | Expedited | [8 empty] | 2019-08-13 | In Operation |  | Y
Fitchburg | Fitchburg | 3712 | 1420 | 9.86 | Solar | 01W04 | 2019-06-03 | 2019-06-04 | 2 |  | 2 | 2019-06-05 | 2019-06-05 | 1 |  | 1 | [20 empty] | 2019-06-10 | 2019-06-17 |  | YES | Expedited | [8 empty] | 2019-07-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3700 | 1462 | 20 | Solar | 31W38 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | 2019-05-22 | 2019-06-21 | 21 | 12 | 9 | [20 empty] | 2019-06-25 | 2019-07-02 |  | YES | Expedited | [8 empty] | 2019-10-11 | In Operation |  | Y
Fitchburg | Ashby | 3698 | 1431 | 7.6 | Solar | 39W19 | 2019-06-18 | 2019-06-18 | 1 |  | 1 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-08-27 |  | YES | Expedited | [8 empty] | 2019-10-25 | In Operation | Res | Y
Fitchburg | Townsend | 3696 | 1469 | 8.26 | Solar | 39W18 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | 2019-05-30 | 2019-06-05 | 5 |  | 5 | [20 empty] | 2019-06-10 | 2019-06-18 |  | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Ashby | 3687 | 1431 | 6 | Solar | 39W19 | 2019-05-07 | 2019-05-09 | 3 |  | 3 | 2019-05-10 | 2019-05-21 | 8 |  | 8 | [20 empty] | 2019-05-22 | 2019-06-03 |  | YES | Expedited | [8 empty] | 2019-08-06 | In Operation |  | Y
Fitchburg | Ashby | 3685 | 1431 | 7.6 | Solar | 39W19 | 2019-05-07 | 2019-05-10 | 4 |  | 4 | 2019-05-13 | 2019-05-29 | 12 |  | 12 | [20 empty] | 2019-06-04 | 2019-06-19 | 2019-05-27 | YES | Expedited | [8 empty] | 2019-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3684 | 1462 | 9.95 | Solar | 30W31 | 2019-05-14 | 2019-05-14 | 1 |  | 1 | 2019-05-15 | 2019-05-21 | 5 |  | 5 | [20 empty] | 2019-05-22 | 2019-06-06 |  | YES | Expedited | [8 empty] | 2019-11-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3682 | 1420 | 8.64 | Solar | 25W27 | 2019-05-14 | 2019-05-17 | 4 |  | 4 | 2019-07-11 | 2019-07-11 | 1 |  | 1 | [20 empty] | 2019-07-18 | 2019-11-12 | 2019-06-04 | YES | Expedited | [8 empty] | 2020-02-10 | In Operation | Res | Y
Fitchburg | Ashby | 3681 | 1431 | 7.6 | Solar | 39W19 | 2019-05-14 | 2019-05-17 | 4 |  | 4 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | [22 empty] | 2019-03-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3667 | 1420 | 10 | Solar | 25W28 | 2019-05-10 | 2019-05-16 | 5 |  | 5 | 2021-03-02 | 2021-03-05 | 4 |  | 4 | [20 empty] | 2021-03-15 |  | 2019-05-10 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3665 | 1420 | 7.6 | Solar | 25W28 | 2019-04-26 | 2019-04-29 | 2 |  | 2 | 2019-04-30 | 2019-05-21 | 16 |  | 16 | [20 empty] | 2019-05-22 | 2019-05-30 | 2019-05-26 | YES | Expedited | [8 empty] | 2019-08-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3664 | 1462 | 6 | Solar | 31W38 | 2019-04-29 | 2019-04-30 | 2 |  | 2 | 2019-05-01 | 2019-05-08 | 6 |  | 6 | [20 empty] | 2019-05-15 | 2019-05-20 | 2019-05-26 | YES | Expedited | [8 empty] | 2019-07-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3663 | 1462 | 5 | Solar | 31W37 | 2019-04-29 | 2019-05-08 | 8 | 5 | 3 | 2019-05-09 | 2019-05-15 | 5 |  | 5 | [20 empty] | 2019-05-22 | 2019-05-30 |  | YES | Expedited | [8 empty] | 2019-06-17 | In Operation |  | Y
Fitchburg | Lunenburg | 3649 | 1462 | 9.1 | Solar | 30W31 | 2019-04-26 | 2019-04-29 | 2 |  | 2 | 2019-04-30 | 2019-05-21 | 16 | 5 | 11 | [20 empty] | 2019-05-22 | 2019-06-24 | 2019-05-30 | YES | Expedited | [8 empty] | 2019-07-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3646 | 1462 | 9.145 | Solar | 30W31 | 2019-04-20 | 2019-04-22 | 1 |  | 1 | 2019-04-23 | 2019-04-24 | 2 |  | 2 | [20 empty] | 2019-05-22 | 2019-05-30 | 2019-05-30 | YES | Expedited | [8 empty] | 2019-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3645 | 1420 | 7.6 | Solar | 31W37 | 2019-04-25 | 2019-04-29 | 3 |  | 3 | 2019-04-30 | 2019-05-08 | 7 |  | 7 | [20 empty] | 2019-05-15 | 2019-06-24 | 2019-05-17 | YES | Expedited | [8 empty] | 2019-10-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3643 | 1420 | 3 | Solar | 25W27 | 2019-04-18 | 2019-04-19 | 2 |  | 2 | [27 empty] | 2019-05-17 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3624 | 1469 | 5 | Solar | 39W18 | 2019-04-30 | 2019-04-30 | 1 |  | 1 | 2019-05-01 | 2019-05-06 | 4 |  | 4 | [20 empty] | 2019-06-26 | 2019-07-09 | 2019-05-03 | YES | Expedited | [8 empty] | 2019-09-03 | In Operation | Res | Y
Fitchburg | Townsend | 3616 | 1474 | 7.38 | Solar | 39W18 | 2019-04-12 | 2019-04-12 | 1 |  | 1 | 2019-04-15 | 2019-04-16 | 1 |  | 1 | [20 empty] | 2019-04-18 | 2019-04-23 |  | YES | Expedited | [8 empty] | 2020-12-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 3583 | 1462 | 6 | Solar | 30W30 | 2019-03-14 | 2019-03-15 | 2 |  | 2 | 2019-03-16 | 2019-03-28 | 9 |  | 9 | [20 empty] | 2019-04-02 | 2019-05-06 | 2019-04-13 | YES | Expedited | [8 empty] | 2019-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 3580 | 1420 | 5 | Solar | 01W04 | 2019-03-13 | 2019-03-15 | 3 |  | 3 | 2019-03-16 | 2019-03-25 | 6 |  | 6 | [20 empty] | 2019-03-27 | 2019-04-02 | 2019-03-20 | YES | Expedited | [8 empty] | 2019-05-23 | In Operation | Res | Y
Fitchburg | Ashby | 3574 | 1431 | 7.6 | Solar | 39W19 | 2019-03-05 | 2019-03-05 | 1 |  | 1 | 2019-03-06 | 2019-03-13 | 6 |  | 6 | [20 empty] | 2019-03-15 | 2019-03-20 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-04-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3573 | 1420 | 0 | Solar + Energy Storage | 35W36 | 2019-03-01 | 2019-03-01 | 1 |  | 1 | [10 empty] | 2019-03-05 | 2019-03-05 | 1 |  | 1 | 2019-05-22 | 2019-11-12 | 119 | 49 | 70 | [5 empty] | 2020-01-02 | 2020-12-21 | 2019-07-01 | YES | Standard | [8 empty] | 2024-04-26 | Cancelled | Comm
Fitchburg | Ashby | 3570 | 1431 | 7.6 | Solar | 39W19 | 2019-02-28 | 2019-03-01 | 2 |  | 2 | 2019-03-07 | 2019-03-13 | 5 |  | 5 | [20 empty] | 2019-03-15 | 2019-06-28 | 2019-03-19 | YES | Expedited | [8 empty] | 2019-07-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 3565 | 1420 | 6 | Solar | 25W27 | 2019-02-27 | 2019-02-28 | 2 |  | 2 | 2019-03-01 | 2019-03-04 | 2 |  | 2 | [20 empty] | 2019-03-14 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3562 | 1462 | 10 | Solar | 30W31 | 2019-02-28 | 2019-02-28 | 1 |  | 1 | 2019-03-07 | 2019-03-13 | 5 |  | 5 | [20 empty] | 2019-03-15 | 2019-07-02 | 2019-03-19 | YES | Expedited | [8 empty] | 2019-08-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3561 | 1420 | 11.4 | Solar | 35W36 | 2019-02-22 | 2019-02-25 | 1 |  | 1 | 2019-02-26 | 2019-03-04 | 4 |  | 4 | [20 empty] | 2019-03-12 | 2019-03-20 | 2019-05-01 | YES | Expedited | [8 empty] | 2019-05-16 | In Operation | Res | Y
Fitchburg | Ashby | 3560 | 1431 | 7.6 | Solar | 39W19 | 2019-02-28 | 2019-03-01 | 2 |  | 2 | 2019-03-01 | 2019-03-04 | 2 |  | 2 | [20 empty] | 2019-03-13 | 2019-04-01 | 2019-03-21 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3551 | 1462 | 6 | Solar | 30W31 | 2019-02-21 | 2019-02-21 | 1 |  | 1 | 2019-02-22 | 2019-02-28 | 3 |  | 3 | [20 empty] | 2019-03-12 | 2019-03-27 | 2019-03-02 | YES | Expedited | [8 empty] | 2019-05-13 | In Operation | Res | Y
Fitchburg | Townsend | 3542 | 1474 | 10 | Solar | 39W18 | 2019-02-05 | 2019-02-05 | 1 |  | 1 | 2019-02-06 | 2019-02-14 | 7 |  | 7 | [20 empty] | 2019-02-21 | 2019-02-26 | 2019-02-18 | YES | Expedited | [8 empty] | 2019-04-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3535 | 1420 | 9.8 | Solar | 35W36 | 2019-02-01 | 2019-02-01 | 1 |  | 1 | 2019-02-04 | 2019-02-04 | 1 |  | 1 | [20 empty] | 2019-02-15 | 2019-03-01 | 2019-03-28 | YES | Expedited | [8 empty] | 2020-02-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3531 | 1420 | 8.5 | Solar | 50W51 | 2019-02-06 | 2019-02-06 | 1 |  | 1 | 2019-02-07 | 2019-05-08 | 61 | 60 | 1 | [20 empty] | 2020-12-09 |  | 2019-03-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3518 | 1420 | 6.4 | Solar | 31W37 | 2019-01-18 | 2019-02-01 | 11 | 6 | 5 | 2019-02-04 | 2019-02-04 | 1 |  | 1 | [20 empty] | 2019-02-15 | 2019-03-25 |  | YES | Expedited | [8 empty] | 2018-03-27 | In Operation |  | Y
Fitchburg | Lunenburg | 3517 | 1462 | 6 | Solar | 30W31 | 2019-01-17 | 2019-01-17 | 1 |  | 1 | 2019-01-17 | 2019-01-21 | 3 |  | 3 | [20 empty] | 2019-01-24 | 2019-02-11 |  | YES | Expedited | [8 empty] | 2019-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 3514 | 1420 | 7.6 | Solar | 20H22 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-21 | 3 |  | 3 | [20 empty] | 2019-04-10 |  | 2019-02-16 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3507 | 1469 | 7.6 | Solar | 39W18 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-17 | 1 |  | 1 | [20 empty] | 2019-01-22 |  | 2019-03-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3506 | 1469 | 10 | Solar | 39W18 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-17 | 1 |  | 1 | [20 empty] | 2019-01-22 | 2019-08-29 | 2019-03-09 | YES | Expedited | [8 empty] | 2019-08-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3505 | 1420 | 7.6 | Solar | 25W27 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-16 | 0 |  | 0 | [20 empty] | 2019-01-22 |  | 2019-03-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3501 | 1420 | 7.6 | Solar | 25W28 | 2019-01-14 | 2019-01-14 | 1 |  | 1 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | [20 empty] | 2019-01-22 | 2019-02-12 | 2019-02-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3498 | 1469 | 5 | Solar | 39W18 | 2019-01-04 | 2019-01-04 | 1 |  | 1 | 2019-01-07 | 2019-01-07 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2019-02-13 |  | YES | Expedited | [8 empty] | 2019-03-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 3493 | 1462 | 3.8 | Solar | 30W30 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-09 | 2019-08-02 | 2019-02-28 | YES | Expedited | [8 empty] | 2019-08-09 | In Operation | Res | Y
Fitchburg | Townsend | 3492 | 1469 | 7.6 | Solar | 39W18 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-10 | 2019-01-24 | 2018-01-27 | YES | Expedited | [8 empty] | 2019-03-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 3490 | 1462 | 3.8 | Solar | 31W38 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-09 | 2019-04-25 | 2019-02-21 | YES | Expedited | [8 empty] | 2019-08-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 3489 | 1462 | 10 | Solar | 30W30 | 2018-12-26 | 2018-12-27 | 2 |  | 2 | 2018-12-28 | 2019-01-03 | 4 |  | 4 | [20 empty] | 2019-01-09 |  | 2019-02-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3486 | 1420 | 3.8 | Solar | 35W36 | 2019-01-02 | 2019-01-03 | 2 |  | 2 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2019-02-06 | 2018-01-14 | YES | Expedited | [8 empty] | 2019-10-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 3485 | 1420 | 7.6 | Solar | 50W51 | 2018-12-20 | 2018-12-20 | 1 |  | 1 | 2018-12-21 | 2019-01-09 | 12 |  | 12 | 2018-03-29 | 2019-05-08 | 277 |  | 277 | [15 empty] | 2020-12-09 |  | 2019-02-19 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3481 | 1469 | 5 | Solar | 39W18 | 2018-12-26 | 2018-12-27 | 2 |  | 2 | 2018-12-28 | 2019-01-02 | 3 |  | 3 | [20 empty] | 2019-01-09 | 2019-02-28 | 2019-01-18 | YES | Expedited | [8 empty] | 2019-03-22 | In Operation | Res | Y
Fitchburg | Ashby | 3478 | 1431 | 10 | Solar | 39W19 | 2018-12-19 | 2018-12-19 | 1 |  | 1 | 2018-12-21 | 2019-01-09 | 12 |  | 12 | [20 empty] | 2019-01-11 | 2019-02-13 |  | YES | Expedited | [8 empty] | 2019-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 3470 | 1462 | 5.5 | Solar | 30W31 | 2018-12-17 | 2018-12-17 | 1 |  | 1 | 2018-12-18 | 2018-12-21 | 4 |  | 4 | [20 empty] | 2018-12-28 | 2019-03-05 | 2019-01-14 | YES | Expedited | [8 empty] | 2019-03-15 | In Operation | Res | Y
Fitchburg | Townsend | 3469 | 1469 | 7.67 | Solar | 39W18 | 2018-12-17 | 2018-12-18 | 2 |  | 2 | 2018-12-19 | 2018-12-21 | 3 |  | 3 | [20 empty] | 2018-12-28 | 2019-01-14 | 2019-02-05 | YES | Expedited | [8 empty] | 2019-06-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3464 | 1420 | 8.36 | Solar | 20W22 | 2018-12-10 | 2018-12-17 | 6 | 1 | 5 | 2018-12-18 | 2019-01-09 | 15 |  | 15 | 2019-03-11 | 2019-04-09 | 22 |  | 22 | [15 empty] | 2020-09-29 | 2020-11-03 | 2019-01-07 | YES | Expedited | [8 empty] | 2020-11-09 | In Operation | Res | Y
Fitchburg | Townsend | 3462 | 1469 | 10.75 | Solar | 15W17 | 2018-12-10 | 2019-01-09 | 21 | 18 | 3 | 2019-01-09 | 2019-01-09 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2020-04-27 | 2018-01-20 | YES | Expedited | [8 empty] | 2021-01-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 3457 | 1420 | 7 | Solar | 50W51 | 2018-12-20 | 2018-12-21 | 2 |  | 2 | 2018-12-21 | 2019-01-09 | 12 | 1 | 11 | 2019-04-10 | 2019-05-08 | 20 |  | 20 | [15 empty] | 2020-12-15 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3444 | 1420 | 10 | Solar | 50W51 | 2018-11-14 | 2018-12-06 | 16 | 12 | 4 | 2018-12-07 | 2019-01-09 | 22 | 20 | 2 | 2019-03-29 | 2019-05-08 | 28 |  | 28 | [15 empty] | 2019-05-08 |  | 2018-01-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3440 | 1420 | 7.6 | Solar | 50W51 | 2018-11-12 | 2018-12-06 | 18 | 14 | 4 | 2018-12-07 | 2019-01-09 | 22 | 16 | 6 | 2019-03-29 | 2019-05-08 | 28 |  | 28 | [15 empty] | 2019-05-08 |  | 2018-01-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3438 | 1420 | 9.86 | Solar | 20W22 | 2018-11-07 | 2018-11-14 | 6 | 2 | 4 | 2018-11-20 | 2019-01-04 | 31 | 24 | 7 | 2019-03-11 | 2019-04-09 | 22 |  | 22 | [15 empty] | 2020-09-29 | 2020-10-02 |  | YES | Expedited | [8 empty] | 2020-11-20 | In Operation | Res | Y
Fitchburg | Townsend | 3437 | 1474 | 10 | Solar | 39W18 | 2018-11-08 | 2018-11-13 | 4 | 1 | 3 | 2018-11-14 | 2018-12-10 | 18 | 15 | 3 | [20 empty] | 2018-12-26 | 2019-06-26 | 2018-12-10 | YES | Expedited | [8 empty] | 2019-07-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 3436 | 1420 | 7.6 | Solar | 01W04 | 2018-11-08 | 2018-11-13 | 4 | 1 | 3 | 2018-11-14 | 2018-12-06 | 16 | 11 | 5 | [20 empty] | 2018-12-10 | 2019-01-18 | 2018-12-10 | YES | Expedited | [8 empty] | 2019-01-22 | In Operation | Res | Y
Fitchburg | Townsend | 3432 | 1469 | 5 | Solar | 39W18 | 2018-11-01 | 2018-11-14 | 10 | 5 | 5 | 2018-11-15 | 2018-12-10 | 17 | 14 | 3 | [20 empty] | 2018-12-10 |  | 2018-12-01 | NO | Expedited | [8 empty] | 2019-02-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3426 | 1420 | 6 | Solar | 20W22 | 2018-10-31 | 2018-11-02 | 3 |  | 3 | 2018-11-05 | 2018-11-19 | 11 | 9 | 2 | [20 empty] | 2018-11-29 | 2018-11-03 | 2018-12-31 | YES | Expedited | [8 empty] | 2019-01-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3424 | 1462 | 10 | Solar | 31W37 | 2018-10-29 | 2018-11-01 | 4 |  | 4 | 2018-11-02 | 2018-12-10 | 26 | 11 | 15 | [20 empty] | 2018-12-19 | 2019-01-22 | 2018-11-08 | YES | Expedited | [8 empty] | 2019-01-25 | In Operation | Res | Y
Fitchburg | Townsend | 3423 | 1469 | 7.6 | Solar | 39W18 | 2018-10-25 | 2018-10-26 | 2 |  | 2 | 2018-10-30 | 2018-12-06 | 27 | 12 | 15 | [20 empty] | 2018-12-10 | 2019-01-14 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 3410 | 1420 | 10 | Solar | 50W51 | 2018-10-15 | 2018-10-22 | 6 | 3 | 3 | 2018-10-22 | 2018-11-26 | 25 | 17 | 8 | [20 empty] | 2018-11-27 |  | 2018-11-20 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3409 | 1420 | 3.8 | Solar | 35W36 | 2018-10-12 | 2018-10-12 | 1 |  | 1 | 2018-10-15 | 2018-10-15 | 1 |  | 1 | [20 empty] | 2018-11-27 | 2018-12-05 | 2018-11-18 | YES | Expedited | [8 empty] | 2019-01-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3400 | 1420 | 7.6 | Solar | 01W04 | 2018-10-04 | 2018-10-08 | 2 |  | 2 | 2018-10-09 | 2018-10-09 | 1 |  | 1 | [20 empty] | 2018-10-12 |  | 2018-10-31 | NO | Expedited | [8 empty] | 2019-01-11 | In Operation | Res | Y
Fitchburg | Townsend | 3399 | 1469 | 7.6 | Solar | 39W18 | 2018-10-03 | 2018-10-15 | 8 | 6 | 2 | 2018-10-15 | 2018-10-16 | 2 |  | 2 | [20 empty] | 2018-10-30 |  | 2018-10-30 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Ashby | 3387 | 1431 | 6 | Solar | 39W19 | 2018-10-01 | 2018-10-01 | 1 |  | 1 | 2018-10-02 | 2018-10-04 | 3 |  | 3 | [20 empty] | 2018-10-11 |  | 2018-10-24 | NO | Expedited | [8 empty] | 2018-11-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 3384 | 1462 | 7.6 | Solar | 30W31 | 2018-09-27 | 2018-10-01 | 3 |  | 3 | 2018-10-02 | 2018-10-03 | 2 |  | 2 | [20 empty] | 2018-10-19 | 2019-10-15 | 2018-11-24 | YES | Expedited | [8 empty] | 2019-10-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3378 | 1462 | 7.6 | Solar | 31W34 | 2018-09-27 | 2018-10-01 | 3 |  | 3 | 2018-10-02 | 2018-10-04 | 3 |  | 3 | [20 empty] | 2018-10-11 | 2021-02-26 | 2018-11-19 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3375 | 1462 | 10.95 | Solar | 31W37 | 2018-09-24 | 2018-09-25 | 2 |  | 2 | 2018-09-25 | 2018-09-26 | 2 |  | 2 | 2019-01-07 | 2019-02-01 | 19 |  | 19 | [15 empty] | 2019-02-15 | 2019-04-01 |  | YES | Expedited | [8 empty] | 2019-05-09 | In Operation | Res | Y
Fitchburg | Ashby | 3369 | 1431 | 7.6 | Solar | 39W19 | 2018-09-10 | 2018-09-25 | 12 | 6 | 6 | 2018-09-25 | 2018-09-25 | 1 |  | 1 | [20 empty] | 2018-09-28 | 2018-12-05 |  | YES | Expedited | [8 empty] | 2018-12-18 | In Operation | Res | Y
Fitchburg | Ashby | 3367 | 1431 | 8.12 | Solar | 39W19 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | 2018-09-10 | 2018-09-17 | 6 |  | 6 | [20 empty] | 2018-09-24 |  |  | NO | Expedited | [8 empty] | 2018-11-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3363 | 1462 | 7.6 | Solar | 31W38 | 2018-08-30 | 2018-09-10 | 7 | 3 | 4 | 2018-09-10 | 2018-09-17 | 6 |  | 6 | [20 empty] | 2018-09-24 | 2019-09-23 | 2018-10-30 | YES | Expedited | [8 empty] | 2019-10-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3361 | 1469 | 6 | Solar | 30W31 | 2018-10-01 | 2018-10-01 | 1 |  | 1 | 2018-10-03 | 2018-10-03 | 1 |  | 1 | [20 empty] | 2018-10-19 | 2019-01-24 | 2018-09-30 | YES | Expedited | [8 empty] | 2019-02-01 | In Operation | Res | Y
Fitchburg | Ashby | 3358 | 1431 | 7.68 | Solar | 39W19 | 2018-08-29 | 2018-09-06 | 6 | 2 | 4 | 2018-09-05 | 2018-09-10 | 4 |  | 4 | [20 empty] | 2021-09-07 | 2021-09-29 | 2018-09-07 | YES | Expedited | [8 empty] | 2021-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3353 | 1462 | 7.6 | Solar | 31W37 | 2018-08-24 | 2018-08-31 | 6 | 4 | 2 | 2018-09-03 | 2018-09-05 | 2 |  | 2 | [20 empty] | 2018-09-12 |  | 2018-09-21 | NO | Expedited | [8 empty] | 2018-10-24 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3350 | 1462 | 10 | Solar | 31W38 | 2018-08-21 | 2018-08-28 | 6 | 3 | 3 | 2018-08-28 | 2018-08-28 | 1 |  | 1 | [20 empty] | 2018-08-31 | 2019-05-13 | 2018-09-18 | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3346 | 1462 | 10.6 | Solar | 31W38 | 2018-08-17 | 2018-09-07 | 15 | 12 | 3 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | [20 empty] | 2018-09-12 | 2019-02-05 | 2018-09-18 | YES | Expedited | [8 empty] | 2018-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3345 | 1420 | 3.8 | Solar | 31W37 | 2018-08-14 | 2018-08-16 | 3 |  | 3 | 2018-08-29 | 2018-08-29 | 1 |  | 1 | [20 empty] | 2018-08-31 | 2019-03-01 | 2018-10-13 | YES | Expedited | [8 empty] | 2019-04-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3344 | 1420 | 7.6 | Solar | 25W27 | 2018-08-13 | 2018-08-15 | 3 |  | 3 | 2018-08-16 | 2018-08-29 | 10 | 8 | 2 | [20 empty] | 2018-08-31 |  | 2018-10-11 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3341 | 1462 | 10 | Solar | 31W38 | 2018-08-08 | 2018-09-10 | 23 | 18 | 5 | 2018-09-11 | 2018-09-17 | 5 |  | 5 | [20 empty] | 2018-09-24 | 2019-07-01 | 2018-10-08 | YES | Expedited | [8 empty] | 2019-08-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 3340 | 1420 | 6 | Solar | 01W04 | 2018-08-07 | 2018-08-15 | 7 |  | 7 | 2018-08-20 | 2018-08-21 | 2 | 1 | 1 | [20 empty] | 2018-09-13 |  | 2018-09-15 | NO | Expedited | [8 empty] | 2018-10-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3336 | 1462 | 6.6 | Solar | 30W31 | 2018-09-24 | 2018-09-25 | 2 |  | 2 | 2018-09-25 | 2018-09-25 | 1 |  | 1 | [20 empty] | 2018-10-01 | 2019-02-27 | 2018-09-08 | YES | Expedited | [8 empty] | 2019-03-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 3335 | 1420 | 5 | Solar | 01W04 | 2018-08-06 | 2018-08-10 | 5 |  | 5 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | [20 empty] | 2018-09-12 | 2019-02-06 | 2018-09-08 | YES | Expedited | [8 empty] | 2018-12-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3333 | 1462 | 7.6 | Solar | 30W30 | 2018-08-01 | 2018-08-14 | 10 | 4 | 6 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-09-06 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3329 | 1462 | 7.6 | Solar | 30W31 | 2018-07-31 | 2018-08-14 | 11 | 8 | 3 | 2018-09-21 | 2018-09-21 | 1 |  | 1 | [20 empty] | 2018-09-24 | 2019-09-23 |  | YES | Expedited | [8 empty] | 2020-04-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3325 | 1420 | 10 | Solar | 01W04 | 2018-07-26 | 2018-07-30 | 3 |  | 3 | 2018-10-09 | 2018-10-09 | 1 |  | 1 | [20 empty] | 2018-10-11 | 2019-04-26 | 2018-10-28 | YES | Expedited | [8 empty] | 2019-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3320 | 1420 | 10 | Solar | 01W04 | 2018-07-25 | 2018-07-30 | 4 |  | 4 | 2018-08-06 | 2018-08-06 | 1 |  | 1 | [20 empty] | 2018-08-07 |  | 2018-09-01 | NO | Expedited | [8 empty] | 2018-09-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3318 | 1420 | 8.36 | Solar | 25W27 | 2018-07-25 | 2018-07-30 | 4 |  | 4 | 2018-08-21 | 2018-08-21 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-08-26 | NO | Expedited | [8 empty] | 2018-10-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3316 | 1462 | 999 | Solar + Energy Storage | 31W38 | 2018-08-27 | 2018-09-06 | 8 |  | 8 | [5 empty] | 2018-09-27 | 2018-11-28 | 43 |  | 43 | [5 empty] | 2018-12-20 | 2019-04-23 | 82 |  | 82 | [5 empty] | 2019-05-23 | 2020-05-18 |  | YES | Standard | [8 empty] | 2021-12-28 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3315 | 1462 | 7.6 | Solar | 30W30 | 2018-07-21 | 2018-08-06 | 11 | 3 | 8 | 2018-08-07 | 2018-08-10 | 4 |  | 4 | [20 empty] | 2018-08-14 | 2019-03-25 | 2018-09-20 | YES | Expedited | [8 empty] | 2019-07-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 3314 | 1420 | 6.4 | Solar | 50W51 | 2018-07-21 | 2018-07-30 | 6 | 1 | 5 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-08-10 | NO | Expedited | [8 empty] | 2018-11-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3309 | 1462 | 8.7 | Solar | 30W30 | 2018-07-18 | 2018-08-14 | 20 | 10 | 10 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  |  | NO | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3304 | 1420 | 3.8 | Solar | 25W27 | 2018-07-13 | 2018-07-18 | 4 |  | 4 | 2018-08-10 | 2018-08-10 | 1 |  | 1 | [20 empty] | 2018-08-14 | 2019-11-22 | 2018-09-13 | YES | Expedited | [8 empty] | 2020-04-30 | Cancelled | Res | Y
Fitchburg | Fitchburg | 3301 | 1420 | 7.68 | Solar | 35W36 | 2018-07-12 | 2018-07-16 | 3 |  | 3 | 2018-07-18 | 2018-07-19 | 2 |  | 2 | [20 empty] | 2018-07-26 |  | 2018-08-20 | NO | Expedited | [8 empty] | 2018-09-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3299 | 1420 | 3 | Solar | 20W22 | 2018-07-16 | 2018-07-20 | 5 | 1 | 4 | 2018-08-02 | 2018-08-06 | 3 |  | 3 | [20 empty] | 2018-08-07 |  | 2018-08-10 | NO | Expedited | [8 empty] | 2018-08-31 | In Operation | Res | Y
Fitchburg | Ashby | 3298 | 1431 | 5.22 | Solar | 39W19 | 2018-07-10 | 2018-07-24 | 11 | 9 | 2 | 2018-07-24 | 2018-07-25 | 2 |  | 2 | [20 empty] | 2018-08-03 |  | 2018-06-02 | NO | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 3294 | 1462 | 7.6 | Solar | 30W31 | 2018-07-06 | 2018-08-16 | 30 | 27 | 3 | 2018-08-16 | 2018-08-21 | 4 |  | 4 | [20 empty] | 2018-08-23 | 2019-01-29 | 2018-08-08 | YES | Expedited | [8 empty] | 2019-04-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 3293 | 1462 | 12 | Solar | 30W30 | 2018-07-06 | 2018-08-17 | 31 | 28 | 3 | 2018-08-17 | 2018-08-21 | 3 |  | 3 | [20 empty] | 2018-08-23 |  |  |  | Expedited | [8 empty] | 2018-09-24 | In Operation |  | Y
Fitchburg | Lunenburg | 3290 | 1462 | 3.8 | Solar | 31W38 | 2018-06-28 | 2018-07-10 | 8 | 2 | 6 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  | 2018-08-28 | NO | Expedited | [8 empty] | 2018-11-08 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3289 | 1462 | 10.95 | Solar | 31W38 | 2018-06-26 | 2018-07-03 | 6 | 4 | 2 | 2018-07-03 | 2018-07-05 | 2 |  | 2 | [20 empty] | 2018-07-10 |  | 2018-07-24 | YES | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 3285 | 1462 | 7.6 | Solar | 30W31 | 2018-06-26 | 2018-07-10 | 10 | 5 | 5 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  | 2018-08-25 | NO | Expedited | [8 empty] | 2018-11-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 3283 | 1420 | 3.8 | Solar | 01W04 | 2018-06-25 | 2018-06-29 | 5 |  | 5 | 2018-07-11 | 2018-08-08 | 21 |  | 21 | [20 empty] | 2018-08-14 |  |  | NO | Expedited | [8 empty] | 2018-10-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 3282 | 1420 | 5 | Solar | 20W22 | 2018-06-25 | 2018-07-02 | 6 | 1 | 5 | 2018-08-23 | 2018-08-28 | 4 |  | 4 | [20 empty] | 2018-08-30 |  |  | NO | Expedited | [8 empty] | 2018-09-05 | In Operation | Res | Y
Fitchburg | Townsend | 3279 | 1474 | 30 | Solar | 39W18 | 2018-06-21 | 2018-07-05 | 10 | 1 | 9 | 2018-07-06 | 2018-07-06 | 1 |  | 1 | [20 empty] | 2018-07-31 | 2018-08-06 | 2018-06-28 | YES | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3278 | 1462 | 7.6 | Solar | 31W37 | 2018-06-20 | 2018-07-13 | 17 | 12 | 5 | 2018-07-13 | 2018-07-17 | 3 |  | 3 | [20 empty] | 2018-07-24 |  |  | YES | Expedited | [8 empty] | 2018-11-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3276 | 1462 | 7.6 | Solar | 30W30 | 2018-06-20 | 2018-07-26 | 26 | 21 | 5 | 2018-07-27 | 2018-07-30 | 2 |  | 2 | [20 empty] | 2018-08-03 |  | 2018-08-19 | NO | Expedited | [8 empty] | 2018-08-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 3275 | 1462 | 3.3 | Solar | 30W30 | 2018-06-19 | 2018-07-02 | 10 | 8 | 2 | 2018-07-02 | 2018-07-05 | 3 |  | 3 | [20 empty] | 2018-07-10 |  | 2018-08-27 | YES | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3273 | 1420 | 9.4 | Solar | 31W37 | 2018-06-18 | 2018-06-22 | 5 |  | 5 | 2018-07-02 | 2018-07-03 | 2 |  | 2 | [20 empty] | 2018-07-06 | 2019-02-12 |  | YES | Expedited | [8 empty] | 2018-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3271 | 1420 | 3.8 | Solar | 25W27 | 2018-06-15 | 2018-07-06 | 15 | 12 | 3 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  |  | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3270 | 1462 | 9.84 | Solar | 31W37 | 2018-06-18 | 2018-07-20 | 24 | 21 | 3 | 2018-07-24 | 2018-07-25 | 2 |  | 2 | [20 empty] | 2018-08-03 |  |  | NO | Expedited | [8 empty] | 2018-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 3269 | 1420 | 10 | Solar | 50W51 | 2018-06-15 | 2018-06-19 | 3 |  | 3 | 2018-06-20 | 2018-06-22 | 3 |  | 3 | [20 empty] | 2018-06-26 |  | 2018-07-30 | NO | Expedited | [8 empty] | 2018-10-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3266 | 1420 | 4885 | Solar + Energy Storage | 25W28 | 2018-09-11 | 2018-10-02 | 16 | 15 | 1 | [10 empty] | 2018-10-13 | 2018-10-24 | 8 |  | 8 | 2018-11-30 | 2019-05-16 | 113 |  | 113 | [5 empty] | 2019-05-23 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 3264 | 1420 | 5 | Solar | 01W04 | 2018-06-12 | 2018-06-26 | 11 | 5 | 6 | 2018-07-09 | 2018-07-11 | 3 |  | 3 | [20 empty] | 2018-07-13 |  |  | NO | Expedited | [8 empty] | 2018-09-04 | In Operation |  | Y
Fitchburg | Lunenburg | 3262 | 1462 | 7.6 | Solar | 30W30 | 2018-06-08 | 2018-06-19 | 8 | 6 | 2 | 2018-06-19 | 2018-06-22 | 4 |  | 4 | [20 empty] | 2018-06-26 | 2020-05-22 | 2018-08-08 | YES | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3261 | 1462 | 7.6 | Solar | 30W31 | 2018-06-07 | 2018-07-17 | 28 | 24 | 4 | 2018-07-18 | 2018-07-19 | 2 |  | 2 | [20 empty] | 2018-07-26 |  | 2018-08-06 | NO | Expedited | [8 empty] | 2018-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3259 | 1462 | 5 | Solar | 30W31 | 2018-06-07 | 2018-06-27 | 15 | 12 | 3 | 2018-06-27 | 2018-07-05 | 6 |  | 6 | [20 empty] | 2018-07-10 |  | 2018-07-08 | NO | Expedited | [8 empty] | 2018-09-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 3258 | 1462 | 10.95 | Solar | 31W38 | 2018-06-06 | 2018-06-28 | 17 | 13 | 4 | 2018-06-28 | 2018-07-03 | 4 |  | 4 | [20 empty] | 2018-07-09 |  | 2018-08-04 | NO | Expedited | [8 empty] | 2018-09-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3256 | 1462 | 13.6 | Solar | 31W37 | 2018-06-05 | 2018-06-13 | 7 | 6 | 1 | 2018-06-13 | 2018-06-13 | 1 |  | 1 | [20 empty] | 2018-06-21 |  | 2018-08-05 | NO | Expedited | [8 empty] | 2018-08-22 | In Operation | Res | Y
Fitchburg | Ashby | 3251 | 1431 | 3.8 | Solar | 39W19 | 2018-06-01 | 2018-06-11 | 7 | 6 | 1 | 2018-06-11 | 2018-06-11 | 1 |  | 1 | [20 empty] | 2018-06-13 |  | 2018-08-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3249 | 1462 | 10.95 | Solar | 30W31 | 2018-06-01 | 2018-06-29 | 21 | 12 | 9 | 2018-06-29 | 2018-07-05 | 4 |  | 4 | [20 empty] | 2018-07-10 |  | 2018-07-02 | NO | Expedited | [8 empty] | 2018-09-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3247 | 1462 | 6 | Solar | 30W30 | 2018-05-31 | 2018-06-14 | 11 | 9 | 2 | 2018-06-14 | 2018-06-15 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-30 | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3246 | 1420 | 3.8 | Solar | 01W04 | 2018-05-30 | 2018-06-05 | 5 |  | 5 | 2018-06-06 | 2018-06-11 | 4 |  | 4 | [20 empty] | 2018-06-13 |  |  | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Townsend | 3238 | 1469 | 10.95 | Solar | 39W18 | 2018-05-23 | 2018-05-29 | 4 |  | 4 | 2018-06-01 | 2018-06-04 | 2 |  | 2 | [20 empty] | 2018-06-08 |  | 2018-06-20 | NO | Expedited | [8 empty] | 2018-08-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3234 | 1420 | 9.8 | Solar | 31W37 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-05-25 | 2018-05-29 | 2 |  | 2 | [20 empty] | 2018-05-31 |  | 2018-07-17 | NO | Expedited | [8 empty] | 2018-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3233 | 1420 | 10.95 | Solar | 35W36 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-19 | NO | Expedited | [8 empty] | 2018-08-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 3232 | 1420 | 9.3 | Solar | 50W51 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-19 | NO | Expedited | [8 empty] | 2018-08-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3230 | 1420 | 10.95 | Solar | 35W36 | 2018-04-23 | 2018-05-21 | 21 |  | 21 | 2018-06-01 | 2018-06-04 | 2 |  | 2 | [20 empty] | 2018-06-08 | 2019-07-24 |  | YES | Expedited | [8 empty] | 2019-09-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 3229 | 1462 | 12.6 | Solar | 31W34 | 2018-05-15 | 2018-06-08 | 18 | 10 | 8 | 2018-06-08 | 2018-06-11 | 2 |  | 2 | [20 empty] | 2018-06-13 |  | 2018-07-15 | NO | Expedited | [8 empty] | 2018-09-12 | In Operation | Res | Y
Fitchburg | Townsend | 3223 | 1469 | 9 | Solar | 39W18 | 2018-05-09 | 2018-05-21 | 9 | 5 | 4 | 2018-07-25 | 2018-07-25 | 1 |  | 1 | [20 empty] | 2018-08-03 |  |  | NO | Expedited | [8 empty] | 2018-09-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3222 | 1420 | 5 | Solar | 20W22 | 2018-05-09 | 2018-05-14 | 4 | 1 | 3 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  |  | NO | Expedited | [8 empty] | 2018-07-25 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3219 | 1462 | 7.6 | Solar | 30W30 | 2018-05-09 | 2018-05-14 | 4 | 2 | 2 | 2018-05-16 | 2018-05-21 | 4 |  | 4 | [20 empty] | 2018-05-22 |  | 2018-06-30 | NO | Expedited | [8 empty] | 2018-07-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3218 | 1462 | 3.8 | Solar | 31W38 | 2018-05-09 | 2018-06-13 | 25 | 22 | 3 | 2018-06-13 | 2018-06-13 | 1 |  | 1 | [20 empty] | 2018-06-21 |  | 2018-07-08 | NO | Expedited | [8 empty] | 2018-08-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 3213 | 1462 | 7.6 | Solar | 31W37 | 2018-05-04 | 2018-06-08 | 25 | 20 | 5 | 2018-06-08 | 2018-06-11 | 2 |  | 2 | [20 empty] | 2018-06-13 |  | 2018-07-04 | NO | Expedited | [8 empty] | 2018-10-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3212 | 1420 | 200 | Solar | 11H11 | 2018-06-07 | 2018-07-05 | 20 | 11 | 9 | 2018-07-05 | 2018-07-05 | 1 |  | 1 | 2018-08-11 | 2018-09-18 | 26 |  | 26 | [15 empty] | 2018-09-24 |  |  |  | Expedited | [9 empty] | Cancelled
Fitchburg | Lunenburg | 3211 | 1462 | 7.6 | Solar | 30W31 | 2018-05-21 | 2018-05-21 | 1 |  | 1 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  | 2018-06-18 | NO | Expedited | [8 empty] | 2018-07-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3208 | 1462 | 10.95 | Solar | 30W31 | 2018-05-01 | 2018-05-29 | 20 | 19 | 1 | 2018-05-29 | 2018-05-30 | 2 |  | 2 | [20 empty] | 2018-05-31 |  | 2018-05-29 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3205 | 1420 | 3.8 | Solar | 20W22 | 2018-04-26 | 2018-05-01 | 4 |  | 4 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  | 2018-05-23 | NO | Expedited | [8 empty] | 2018-08-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3204 | 1420 | 7.6 | Solar | 31W37 | 2018-04-26 | 2018-05-01 | 4 |  | 4 | 2018-05-15 | 2018-05-21 | 5 |  | 5 | [20 empty] | 2018-05-22 |  | 2018-06-24 | NO | Expedited | [8 empty] | 2018-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3198 | 1420 | 10.95 | Solar | 25W27 | 2018-04-25 | 2018-05-22 | 20 | 15 | 5 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-26 | 2018-07-23 | 2018-05-24 | YES | Expedited | [8 empty] | 2018-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3197 | 1462 | 3.8 | Solar | 30W31 | 2018-04-25 | 2018-05-04 | 8 | 3 | 5 | 2018-05-04 | 2018-05-07 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-24 | NO | Expedited | [8 empty] | 2018-06-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3195 | 1462 | 7.6 | Solar | 30W30 | 2018-04-14 | 2018-04-30 | 10 | 2 | 8 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-23 |  |  | YES | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3193 | 1462 | 10.95 | Solar | 30W30 | 2018-04-19 | 2018-04-27 | 7 | 5 | 2 | 2018-04-27 | 2018-04-30 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-06-11 | NO | Expedited | [8 empty] | 2018-07-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 3190 | 1462 | 5 | Solar | 31W38 | 2018-04-17 | 2018-04-30 | 10 | 8 | 2 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-14 |  | 2018-05-18 | NO | Expedited | [8 empty] | 2018-11-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3189 | 1420 | 10.95 | Solar | 35W36 | 2018-04-16 | 2018-04-25 | 7 | 5 | 2 | 2018-05-15 | 2018-05-21 | 5 |  | 5 | [20 empty] | 2018-05-22 |  | 2018-06-28 | NO | Expedited | [8 empty] | 2018-08-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 3188 | 1462 | 8.36 | Solar | 30W31 | 2018-04-11 | 2018-04-27 | 12 | 8 | 4 | 2018-04-27 | 2018-04-30 | 2 |  | 2 | [20 empty] | 2018-05-04 |  | 2018-05-13 | NO | Expedited | [8 empty] | 2018-07-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3187 | 1420 | 7.6 | Solar | 25W27 | 2018-04-11 | 2018-04-16 | 3 |  | 3 | 2018-04-23 | 2018-04-23 | 1 |  | 1 | [20 empty] | 2018-05-03 |  | 2018-06-01 | NO | Expedited | [8 empty] | 2018-09-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3183 | 1462 | 5 | Solar | 31W38 | 2018-04-10 | 2018-04-30 | 14 | 12 | 2 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-09 | NO | Expedited | [8 empty] | 2018-09-11 | Cancelled | Res | Y
Fitchburg | Fitchburg | 3182 | 1420 | 8.36 | Solar | 35W36 | 2018-04-09 | 2018-04-20 | 9 | 6 | 3 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-11 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3180 | 1462 | 12 | Solar | 31W38 | 2017-11-14 | 2018-04-17 | 102 | 93 | 9 | 2018-04-20 | 2018-04-20 | 1 |  | 1 | [20 empty] | 2018-04-23 |  | 2018-01-14 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3179 | 1420 | 70.8 | Solar | 31W37 | 2018-06-01 | 2018-06-28 | 20 |  | 20 | 2018-06-29 | 2018-08-31 | 45 | 1 | 44 | [20 empty] | 2018-10-03 | 2019-05-14 |  | YES | Expedited | [8 empty] | 2022-05-04 | In Operation |  | Y
Fitchburg | Townsend | 3175 | 1453 | 750 | Solar | 39W18 | 2018-04-06 | 2018-04-07 | 1 |  | 1 | 2018-04-07 | 2018-04-16 | 5 |  | 5 | 2018-05-04 | 2018-07-11 | 47 |  | 47 | [15 empty] | 2018-07-11 | 2019-06-03 |  | YES | Expedited | [6 empty] | 2021-03-26 | 2021-03-26 | 2021-04-14 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3174 | 1462 | 7.6 | Solar | 30W30 | 2018-03-30 | 2018-05-10 | 29 | 28 | 1 | 2018-05-10 | 2018-06-12 | 23 | 19 | 4 | [20 empty] | 2018-06-21 |  | 2018-05-30 | NO | Expedited | [8 empty] | 2018-07-10 | Cancelled | Res | Y
Fitchburg | West Townsend | 3173 | 1474 | 5 | Solar | 39W18 | 2018-03-29 | 2018-04-04 | 5 |  | 5 | 2018-04-09 | 2018-04-17 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-07-15 | YES | Expedited | [8 empty] | 2018-08-13 | In Operation | Res | Y
Fitchburg | Ashby | 3171 | 1431 | 10.95 | Solar | 39W19 | 2018-03-29 | 2018-04-27 | 21 | 20 | 1 | 2018-04-27 | 2018-04-27 | 1 |  | 1 | [20 empty] | 2018-05-04 |  | 2018-05-28 | NO | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3170 | 1462 | 7.6 | Solar | 30W30 | 2018-03-29 | 2018-04-06 | 7 | 5 | 2 | 2018-04-06 | 2018-04-06 | 1 |  | 1 | [20 empty] | 2018-04-23 |  | 2018-05-28 | NO | Expedited | [8 empty] | 2018-07-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 3163 | 1462 | 3.8 | Solar | 30W31 | 2018-03-21 | 2018-04-04 | 11 | 10 | 1 | 2018-04-04 | 2018-04-16 | 8 |  | 8 | [20 empty] | 2018-04-23 |  | 2018-05-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3162 | 1420 | 7.6 | Solar | 50W51 | 2018-03-15 | 2018-03-19 | 3 |  | 3 | 2018-03-26 | 2018-04-24 | 21 |  | 21 | [20 empty] | 2018-05-02 |  | 2018-06-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3158 | 1462 | 10 | Solar | 31W37 | 2018-03-13 | 2018-03-29 | 13 | 11 | 2 | 2018-03-29 | 2018-04-16 | 12 |  | 12 | [20 empty] | 2018-04-23 |  | 2018-04-15 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3157 | 1420 | 3.8 | Solar | 50W51 | 2018-03-08 | 2018-03-14 | 3 |  | 3 | [25 empty] | 2018-03-26 |  | 2018-05-02 | NO | Expedited | [8 empty] | 2018-04-13 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3156 | 1462 | 12 | Solar | 30W31 | 2018-03-08 | 2018-03-15 | 4 |  | 4 | 2018-03-15 | 2018-03-22 | 6 |  | 6 | [20 empty] | 2018-03-29 |  | 2018-04-08 | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3155 | 1462 | 7.6 | Solar | 31W37 | 2018-03-08 | 2018-04-06 | 20 | 19 | 1 | 2018-04-06 | 2018-04-16 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-05-08 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3154 | 1462 | 17.01 | Solar | 30W31 | 2018-03-07 | 2018-04-17 | 26 | 20 | 6 | 2018-04-17 | 2018-04-18 | 2 |  | 2 | [20 empty] | 2018-05-04 |  | 2018-04-09 | NO | Expedited | [8 empty] | 2018-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 3149 | 1462 | 7.6 | Solar | 30W30 | 2018-02-07 | 2018-03-13 | 21 | 10 | 11 | 2018-03-16 | 2018-03-16 | 1 |  | 1 | [20 empty] | 2018-03-19 |  | 2018-02-01 | NO | Expedited | [8 empty] | 2018-05-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3148 | 1469 | 3200 | Solar | 30W31 | 2018-03-01 | 2018-04-01 | 19 | 18 | 1 | [5 empty] | 2018-06-22 | 2018-07-23 | 21 |  | 21 | [15 empty] | 2018-08-06 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 3146 | 1462 | 5 | Solar | 30W31 | 2018-02-28 | 2018-03-05 | 4 |  | 4 | 2018-03-12 | 2018-03-15 | 4 |  | 4 | [20 empty] | 2018-03-19 |  | 2018-03-09 | NO | Expedited | [8 empty] | 2018-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3138 | 1420 | 7.6 | Solar | 25W27 | 2018-02-20 | 2018-02-23 | 3 |  | 3 | 2018-03-01 | 2018-03-15 | 8 |  | 8 | [20 empty] | 2018-03-16 |  | 2018-04-20 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3130 | 1420 | 6 | Solar | 01W04 | 2018-02-09 | 2018-03-09 | 17 | 16 | 1 | 2018-04-06 | 2018-04-16 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-03-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3129 | 1462 | 12 | Solar | 30W30 | 2018-01-06 | 2018-02-16 | 29 | 25 | 4 | 2018-02-16 | 2018-02-19 | 2 |  | 2 | [20 empty] | 2018-02-23 |  | 2018-03-04 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3123 | 1462 | 7.6 | Solar | 31W38 | 2018-01-29 | 2018-03-14 | 29 | 28 | 1 | 2018-03-14 | 2018-04-10 | 20 |  | 20 | [20 empty] | 2018-04-23 |  | 2018-03-29 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3121 | 1431 | 10.95 | Solar | 39W19 | 2018-01-29 | 2018-02-06 | 7 | 5 | 2 | 2018-02-06 | 2018-02-20 | 10 |  | 10 | [20 empty] | 2018-02-23 |  |  | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Ashby | 3113 | 1431 | 7.6 | Solar | 39W19 | 2018-01-24 | 2018-02-12 | 14 | 11 | 3 | 2018-02-12 | 2018-02-20 | 6 |  | 6 | [20 empty] | 2018-02-23 |  | 2018-02-12 | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3112 | 1420 | 3.8 | Solar | 35W36 | 2018-01-19 | 2018-01-26 | 6 |  | 6 | 2018-02-09 | 2018-02-19 | 7 |  | 7 | [20 empty] | 2018-02-23 |  | 2018-02-22 | NO | Expedited | [8 empty] | 2018-06-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3111 | 1462 | 6 | Solar | 30W30 | 2018-01-24 | 2018-02-21 | 20 | 10 | 10 | 2018-02-21 | 2018-02-23 | 3 |  | 3 | [20 empty] | 2018-02-23 |  | 2018-02-23 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3110 | 1462 | 10.95 | Solar | 30W30 | 2018-01-17 | 2018-01-24 | 6 |  | 6 | 2018-01-24 | 2018-01-29 | 4 |  | 4 | [20 empty] | 2018-01-29 |  | 2018-02-24 | NO | Expedited | [8 empty] | 2018-05-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3105 | 1462 | 15.3 | Solar | 30W31 | 2018-01-15 | 2018-01-22 | 5 |  | 5 | 2018-01-22 | 2018-02-20 | 21 | 2 | 19 | [20 empty] | 2018-02-20 |  | 2018-03-15 | YES | Expedited | [8 empty] | 2018-03-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 3102 | 1462 | 11.4 | Solar | 30W31 | 2018-01-12 | 2018-01-22 | 6 | 3 | 3 | 2018-01-22 | 2018-02-19 | 21 | 2 | 19 | [20 empty] | 2018-02-19 |  | 2018-03-12 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3100 | 1420 | 3.8 | Solar | 50W51 | 2018-01-12 | 2018-01-22 | 6 |  | 6 | 2018-02-01 | 2018-02-13 | 9 |  | 9 | [22 empty] | 2018-03-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3090 | 1462 | 7.6 | Solar | 31W38 | 2018-01-08 | 2018-02-09 | 24 | 20 | 4 | 2018-02-09 | 2018-02-19 | 7 |  | 7 | [20 empty] | 2018-02-23 |  | 2018-02-05 | NO | Expedited | [8 empty] | 2018-04-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3079 | 1420 | 3.8 | Solar | 50W51 | 2018-01-02 | 2018-01-09 | 6 |  | 6 | 2018-01-11 | 2018-01-16 | 3 |  | 3 | [20 empty] | 2018-01-22 |  |  | NO | Expedited | [8 empty] | 2018-03-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3078 | 1462 | 7.6 | Solar | 31W38 | 2018-01-02 | 2018-01-15 | 10 | 3 | 7 | 2018-01-19 | 2018-01-26 | 6 |  | 6 | [20 empty] | 2018-02-01 |  | 02/29/2018 | NO | Expedited | [8 empty] | 2018-05-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 3076 | 1420 | 6.6 | Solar | 20W22 | 2017-12-28 | 2018-01-09 | 8 |  | 8 | 2018-01-29 | 2018-02-02 | 5 |  | 5 | [20 empty] | 2018-02-02 |  | 2018-02-19 | NO | Expedited | [8 empty] | 2018-03-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3075 | 1420 | 21.6 | Solar | 31W37 | 2017-12-28 | 2018-01-18 | 14 |  | 14 | 2018-01-18 | 2018-02-08 | 16 |  | 16 | [20 empty] | 2018-02-08 |  | 02/29/2018 | NO | Expedited | [8 empty] | 2018-06-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3074 | 1462 | 8.35 | Solar | 30W31 | 2017-12-28 | 2018-01-09 | 8 |  | 8 | 2018-01-24 | 2018-01-26 | 3 |  | 3 | [20 empty] | 2018-02-01 |  | 2018-02-05 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3072 | 1462 | 3000 | Solar | 0 | 2018-02-09 | 2018-04-05 | 36 |  | 36 | [28 empty] | NO | Standard | [9 empty] | Cancelled | Com | Y
Fitchburg | Fitchburg | 3071 | 1420 | 8.36 | Solar | 31W37 | 2017-12-27 | 2018-01-05 | 7 |  | 7 | 2018-02-01 | 2018-02-13 | 9 |  | 9 | [20 empty] | 2018-02-19 |  | 2018-01-29 | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3069 | 1462 | 10.95 | Solar | 31W37 | 2017-12-21 | 2018-01-08 | 11 | 1 | 10 | 2018-01-12 | 2018-01-16 | 2 |  | 2 | [20 empty] | 2018-01-22 |  | 2018-01-20 | YES | Expedited | [8 empty] | 2018-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3066 | 1420 | 5.52 | Solar | 20W22 | 2017-12-20 | 2018-01-05 | 11 | 1 | 10 | 2018-01-11 | 2018-01-16 | 3 |  | 3 | [20 empty] | 2018-01-18 |  |  | NO | Expedited | [8 empty] | 2018-04-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3065 | 1420 | 7.6 | Solar | 11W11 | 2017-12-15 | 2018-01-03 | 12 |  | 12 | 2018-01-08 | 2018-01-15 | 6 |  | 6 | [20 empty] | 2018-01-25 |  | 2018-02-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3062 | 1462 | 240 | Solar | 31W38 | 2017-12-14 | 2018-01-10 | 18 | 5 | 13 | 2018-01-10 | 2018-01-24 | 10 |  | 10 | 2018-01-30 | 2018-02-26 | 19 |  | 19 | [15 empty] | 2018-02-28 | 2019-04-16 | 2017-05-01 | YES | Expedited | [8 empty] | 2019-08-12 | In Operation | Res | Y
Fitchburg | Townsend | 3060 | 1474 | 5 | Solar | 39W18 | 2017-12-14 | 2017-12-22 | 7 | 1 | 6 | 2018-01-02 | 2018-01-05 | 4 |  | 4 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-03-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 3059 | 1420 | 4400 | Solar | 25W28 | 2017-12-01 | 2017-12-18 | 12 |  | 12 | [10 empty] | 2017-12-19 | 2018-01-17 | 19 |  | 19 | 2018-02-09 | 2018-07-06 | 99 | 40 | 59 | [5 empty] | 2018-07-24 |  | 2018-09-14 | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 3057 | 1469 | 6.96 | Solar | 15W16 | 2017-12-11 | 2018-01-05 | 18 | 9 | 9 | 2018-01-16 | 2018-01-30 | 10 |  | 10 | [20 empty] | 2018-02-01 |  |  | YES | Expedited | [8 empty] | 2018-04-02 | In Operation | Res | Y
Fitchburg | Townsend | 3056 | 1469 | 10.95 | Solar | 15W17 | 2017-12-11 | 2017-12-19 | 7 |  | 7 | 2018-02-06 | 2018-02-09 | 4 |  | 4 | [20 empty] | 2018-02-12 |  | 2018-01-01 | NO | Expedited | [8 empty] | 2018-03-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3054 | 1462 | 7.6 | Solar | 30W30 | 2017-12-12 | 2017-12-19 | 6 |  | 6 | 2018-01-08 | 2018-01-15 | 6 |  | 6 | [20 empty] | 2018-01-23 |  | 2018-01-30 | NO | Expedited | [8 empty] | 2018-04-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 3053 | 1420 | 6 | Solar | 01W02 | 2017-12-11 | 2017-12-14 | 4 |  | 4 | 2018-01-04 | 2018-01-05 | 2 |  | 2 | [20 empty] | 2018-01-08 |  | 2018-01-11 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3052 | 1420 | 5 | Solar | 20W22 | 2017-12-07 | 2017-12-13 | 5 |  | 5 | 2018-01-26 | 2018-01-26 | 1 |  | 1 | [20 empty] | 2018-01-29 |  |  | NO | Expedited | [8 empty] | 2018-05-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 3049 | 1420 | 8.12 | Solar | 50W51 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-08 |  | 2017-01-30 | NO | Expedited | [8 empty] | 2018-05-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3048 | 1420 | 3.8 | Solar | 20W22 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2018-01-03 | 2018-01-03 | 1 |  | 1 | [20 empty] | 2018-01-05 |  |  | NO | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3047 | 1462 | 6 | Solar | 30W30 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2018-01-03 | 2018-01-05 | 3 |  | 3 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3046 | 1420 | 8.35 | Solar | 50W51 | 2017-12-05 | 2017-12-07 | 3 |  | 3 | 2017-12-20 | 2018-01-03 | 9 |  | 9 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3045 | 1420 | 300 | Gas | 50W55 | 2017-12-18 | 2018-01-03 | 11 | 3 | 8 | [10 empty] | 2018-01-04 | 2018-01-31 | 19 |  | 19 | 2018-04-16 | 2018-07-26 | 71 | 9 | 62 | [5 empty] | 2019-01-16 |  | 2017-03-15 | NO | Standard | [8 empty] | 2019-05-16 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3042 | 1462 | 7.6 | Solar | 30W31 | 2017-12-01 | 2017-12-05 | 3 |  | 3 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-05 |  | 2018-01-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3041 | 1462 | 10.95 | Solar | 31W38 | 2017-12-01 | 2017-12-05 | 3 |  | 3 | 2018-01-02 | 2018-01-03 | 2 |  | 2 | [20 empty] | 2018-01-05 |  | 2018-01-02 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3038 | 1462 | 3.8 | Solar | 30W31 | 2017-11-30 | 2017-12-06 | 5 | 1 | 4 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-08 |  | 2018-01-29 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3037 | 1420 | 5 | Solar | 01W04 | 2017-11-28 | 2017-11-30 | 3 |  | 3 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-05 |  | 2018-02-14 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3035 | 1420 | 6 | Solar | 01W04 | 2017-11-22 | 2017-11-28 | 4 |  | 4 | 2018-01-02 | 2018-01-05 | 4 |  | 4 | [20 empty] | 2018-01-08 |  | 2017-12-24 | NO | Expedited | [8 empty] | 2018-03-05 | In Operation | Res | Y
Fitchburg | Ashby | 3034 | 1431 | 6 | Solar | 39W19 | 2017-11-20 | 2017-11-27 | 5 |  | 5 | 2018-01-11 | 2018-01-15 | 3 |  | 3 | [20 empty] | 2018-01-29 |  | 2017-12-18 | YES | Expedited | [8 empty] | 2018-05-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3028 | 1462 | 7.6 | Solar | 30W30 | 2017-11-15 | 2017-11-22 | 6 |  | 6 | 2018-01-12 | 2018-01-15 | 2 |  | 2 | [20 empty] | 2018-01-23 |  | 2018-01-14 | NO | Expedited | [8 empty] | 2018-04-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3026 | 1420 | 3.8 | Solar | 25W27 | 2017-11-14 | 2017-11-22 | 7 |  | 7 | 2017-12-05 | 2017-12-19 | 11 |  | 11 | [20 empty] | 2017-12-22 |  |  | NO | Expedited | [8 empty] | 2018-05-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3025 | 1420 | 5 | Solar | 40W40 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2018-01-22 | 2018-01-25 | 4 |  | 4 | [20 empty] | 2018-01-25 |  | 2018-01-23 | NO | Expedited | [8 empty] | 2018-04-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 3024 | 1420 | 10.95 | Solar | 25W27 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-11 |  | 2018-01-13 | YES | Expedited | [8 empty] | 2018-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3023 | 1420 | 10 | Solar | 31W37 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2018-01-02 | 2018-01-03 | 2 |  | 2 | [20 empty] | 2018-01-05 |  | 2017-12-16 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Townsend | 3022 | 1469 | 10.95 | Solar | 15W16 | 2017-11-10 | 2017-11-21 | 8 |  | 8 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-11 |  | 2017-12-27 | NO | Expedited | [8 empty] | 2018-01-22 | In Operation | Res | Y
Fitchburg | Ashby | 3019 | 1431 | 10.95 | Solar | 39W19 | 2017-11-09 | 2017-11-16 | 6 | 5 | 1 | 2017-11-29 | 2017-12-04 | 4 |  | 4 | [20 empty] | 2017-12-05 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-04-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 3018 | 1420 | 6 | Solar | 11W11 | 2017-11-08 | 2017-11-13 | 4 |  | 4 | 2018-03-02 | 2018-03-12 | 4 |  | 4 | [20 empty] | 2017-11-28 |  | 2017-12-11 | YES | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 3016 | 1420 | 5.12 | Solar | 31W37 | 2017-11-07 | 2017-11-08 | 2 |  | 2 | 2017-12-19 | 2018-01-03 | 10 |  | 10 | [20 empty] | 2018-01-08 |  | 2017-12-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3014 | 1431 | 9.2 | Solar | 39W19 | 2017-11-06 | 2017-11-09 | 4 |  | 4 | 2017-12-01 | 2017-12-19 | 13 |  | 13 | [20 empty] | 2017-12-22 |  |  | YES | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3013 | 1420 | 7.6 | Solar | 01W04 | 2017-11-06 | 2017-11-08 | 3 |  | 3 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-07 |  | 2017-12-04 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3012 | 1462 | 7.6 | Solar | 39W18 | 2017-11-06 | 2017-11-08 | 3 |  | 3 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3010 | 1420 | 7.6 | Solar | 31W37 | 2017-11-02 | 2017-11-07 | 4 |  | 4 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2018-01-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3009 | 1420 | 5 | Solar | 01W04 | 2017-11-02 | 2017-11-07 | 4 |  | 4 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-07 |  | 2017-12-04 | NO | Expedited | [8 empty] | 2018-03-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3008 | 1420 | 3.8 | Solar | 40W40 | 2017-11-02 | 2017-11-08 | 5 |  | 5 | 2017-12-12 | 2017-12-19 | 6 |  | 6 | [20 empty] | 2017-12-22 |  | 2017-12-17 | NO | Expedited | [8 empty] | 2018-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3007 | 1420 | 10.9 | Solar | 01W04 | 2017-11-03 | 2017-11-08 | 4 | 1 | 3 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 | 2021-03-26 |  | YES | Expedited | [8 empty] | 2021-05-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3006 | 1420 | 7.6 | Solar | 25W27 | 2017-11-01 | 2017-11-06 | 4 | 1 | 3 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2018-01-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3005 | 1462 | 7.6 | Solar | 30W30 | 2017-11-01 | 2017-11-06 | 4 |  | 4 | 2017-11-27 | 2017-12-08 | 10 |  | 10 | [20 empty] | 2017-12-08 |  | 2017-12-03 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3003 | 1462 | 9.52 | Solar | 30W30 | 2017-11-01 | 2017-11-07 | 5 |  | 5 | 2018-01-02 | 2018-01-08 | 5 |  | 5 | [20 empty] | 2018-01-08 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3002 | 1462 | 9.8 | Solar | 30W31 | 2017-10-31 | 2017-11-03 | 3 |  | 3 | 2017-11-14 | 2017-11-28 | 10 |  | 10 | [20 empty] | 2017-11-28 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-03-05 | In Operation | Res | Y
Fitchburg | Ashby | 3001 | 1431 | 9 | Solar | 39W19 | 2017-10-30 | 2017-11-03 | 4 |  | 4 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 3000 | 1462 | 10 | Solar | 31W37 | 2017-10-30 | 2017-11-03 | 4 |  | 4 | 2017-12-20 | 2018-01-03 | 9 |  | 9 | [20 empty] | 2018-01-05 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2999 | 1420 | 7.6 | Solar | 20W22 | 2017-10-27 | 2017-12-11 | 30 | 25 | 5 | 2018-01-04 | 2018-01-08 | 3 |  | 3 | [20 empty] | 2018-01-08 |  | 2017-11-29 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2997 | 1420 | 10.95 | Solar | 20W22 | 2017-10-26 | 2017-11-08 | 9 | 1 | 8 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  |  | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2996 | 1462 | 5 | Solar | 30W31 | 2017-10-26 | 2017-11-03 | 6 |  | 6 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2995 | 1431 | 9.6 | Solar | 39W19 | 2017-10-24 | 2017-11-03 | 8 |  | 8 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Townsend | 2992 | 1469 | 10.95 | Solar | 15W16 | 2017-10-25 | 2017-11-01 | 5 | 1 | 4 | 2017-11-20 | 2017-11-28 | 6 |  | 6 | [20 empty] | 2017-12-01 |  | 2017-11-27 | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2990 | 1420 | 10.95 | Solar | 50W56 | 2017-10-30 | 2017-11-06 | 5 | 4 | 1 | 2017-12-07 | 2017-12-19 | 9 |  | 9 | [20 empty] | 2017-12-22 |  | 2017-11-09 | NO | Expedited | [8 empty] | 2018-02-16 | In Operation | Res | Y
Fitchburg | Townsend | 2989 | 1474 | 5.2 | Solar | 39W18 | 2017-10-23 | 2017-10-30 | 6 |  | 6 | 2017-11-16 | 2017-12-01 | 11 |  | 11 | [20 empty] | 2017-12-08 |  | 2018-01-17 | NO | Expedited | [8 empty] | 2018-02-05 | In Operation | Res | Y
Fitchburg | Townsend | 2986 | 1469 | 6.7 | Solar | 39W18 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-13 | 2017-11-27 | 10 |  | 10 | [20 empty] | 2017-11-27 |  | 2017-11-10 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2985 | 1462 | 6.6 | Solar | 30W30 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-16 | 2017-11-28 | 8 |  | 8 | [20 empty] | 2017-12-01 |  | 2018-01-07 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2984 | 1462 | 3.8 | Solar | 31W38 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2017-12-19 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Ashby | 2983 | 1431 | 120.8 | Solar | 39W19 | 2017-10-23 | 2017-11-07 | 11 |  | 11 | 2017-11-07 | 2017-11-27 | 14 |  | 14 | [20 empty] | 2017-11-27 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2981 | 1420 | 59.4 | Solar | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2980 | 1420 | 5.4 | Solar | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2979 | 1420 | 59.4 | Solar | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2978 | 1420 | 400 | Solar | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2977 | 1420 | 59.4 | Solar | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2976 | 1469 | 59.4 | Solar | 15W17 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2974 | 1431 | 8.64 | Solar | 39W19 | 2017-10-19 | 2017-10-25 | 5 | 2 | 3 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2017-11-16 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Townsend | 2973 | 1469 | 6 | Solar | 15W16 | 2017-10-19 | 2017-10-23 | 3 |  | 3 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2018-01-07 | NO | Expedited | [8 empty] | 2018-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 2972 | 1431 | 7.6 | Solar | 35W36 | 2017-10-19 | 2017-10-23 | 3 |  | 3 | 2017-11-16 | 2017-12-01 | 11 |  | 11 | [20 empty] | 2017-12-08 |  | 2017-12-18 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2971 | 1420 | 6 | Solar | 25W27 | 2017-10-17 | 2017-10-26 | 8 | 2 | 6 | 2017-11-13 | 2017-12-01 | 14 |  | 14 | [20 empty] | 2017-12-08 |  | 2017-11-16 | NO | Expedited | [8 empty] | 2018-04-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 2969 | 1462 | 5 | Solar | 30W31 | 2017-10-17 | 2017-10-26 | 8 | 3 | 5 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2968 | 1462 | 7.6 | Solar | 30W31 | 2017-10-16 | 2017-10-25 | 8 | 1 | 7 | 2017-11-15 | 2017-11-28 | 9 |  | 9 | [20 empty] | 2017-12-01 |  | 2017-12-21 | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2966 | 1462 | 7.6 | Solar | 30W31 | 2017-10-13 | 2017-10-20 | 6 |  | 6 | 2017-11-08 | 2017-11-20 | 9 |  | 9 | [20 empty] | 2017-11-30 |  | 2017-12-12 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2965 | 1420 | 10.95 | Solar | 25W27 | 2017-10-12 | 2017-10-20 | 7 | 1 | 6 | 2017-11-17 | 2017-12-01 | 10 |  | 10 | [20 empty] | 2017-12-07 |  | 2017-11-01 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Townsend | 2964 | 1469 | 9.8 | Solar | 15W16 | 2017-10-11 | 2017-10-24 | 10 | 1 | 9 | 2017-11-07 | 2017-11-20 | 10 |  | 10 | [20 empty] | 2017-11-27 |  | 2017-11-11 | NO | Expedited | [8 empty] | 2018-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2963 | 1462 | 10.95 | Solar | 30W30 | 2017-10-09 | 2017-10-12 | 3 |  | 3 | 2017-11-02 | 2017-11-20 | 13 |  | 13 | [20 empty] | 2017-11-30 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2017-12-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2962 | 1420 | 7.6 | Solar | 25W27 | 2017-10-09 | 2017-10-19 | 8 | 4 | 4 | 2017-11-08 | 2017-11-21 | 10 |  | 10 | [20 empty] | 2017-11-22 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2961 | 1462 | 12 | Solar | 30W30 | 2017-10-09 | 2017-10-16 | 5 | 2 | 3 | 2018-01-05 | 2018-01-05 | 1 |  | 1 | [20 empty] | 2018-01-05 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-03-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2960 | 1462 | 8.35 | Solar | 30W30 | 2017-10-06 | 2017-10-17 | 7 | 2 | 5 | 2017-11-16 | 2017-11-28 | 8 |  | 8 | [20 empty] | 2017-12-08 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-07-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2959 | 1420 | 6 | Solar | 20W22 | 2017-10-05 | 2017-10-19 | 10 | 5 | 5 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2018-03-10 | NO | Expedited | [8 empty] | 2018-01-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2958 | 1420 | 6 | Solar | 50W51 | 2017-10-05 | 2017-10-20 | 11 | 5 | 6 | 2017-11-06 | 2017-11-21 | 12 |  | 12 | [20 empty] | 2017-11-22 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2017-12-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2957 | 1420 | 6 | Solar | 40W42 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-25 | 2017-11-20 | 18 |  | 18 | [20 empty] | 2017-11-22 |  |  | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2956 | 1462 | 3.8 | Solar | 31W38 | 2017-10-03 | 2017-10-19 | 12 | 11 | 1 | 2017-10-27 | 2017-11-13 | 11 |  | 11 | [20 empty] | 2017-11-14 |  | 2017-12-02 | NO | Expedited | [8 empty] | 2018-05-08 | In Operation | Res | Y
Fitchburg | Ashby | 2955 | 1431 | 5 | Solar | 39W19 | 2017-10-03 | 2017-10-16 | 9 | 5 | 4 | 2017-10-30 | 2017-11-20 | 15 |  | 15 | [20 empty] | 2017-11-27 |  | 2017-11-06 | YES | Expedited | [8 empty] | 2018-01-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2954 | 1462 | 7.6 | Solar | 30W30 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-15 |  | 2017-12-02 | NO | Expedited | [8 empty] | 2018-03-12 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2953 | 1462 | 12 | Solar | 30W31 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-27 | 2017-11-17 | 15 |  | 15 | [20 empty] | 2017-11-17 |  | 2017-12-02 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 2951 | 1420 | 6 | Solar | 20W22 | 2017-09-27 | 2017-10-10 | 9 |  | 9 | 2017-10-26 | 2017-11-20 | 17 |  | 17 | [20 empty] | 2017-11-22 |  | 2017-11-28 | NO | Expedited | [8 empty] | 2017-12-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 2949 | 1462 | 6.72 | Solar | 31W37 | 2017-09-27 | 2017-10-03 | 5 |  | 5 | 2017-10-27 | 2017-11-14 | 12 |  | 12 | [20 empty] | 2017-11-14 |  |  | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | West Townsend | 2948 | 1474 | 10 | Solar | 39W18 | 2017-09-27 | 2017-10-03 | 5 |  | 5 | 2017-10-26 | 2017-11-27 | 21 |  | 21 | [20 empty] | 2017-11-27 |  | 2017-09-22 | NO | Expedited | [8 empty] | 2018-02-15 | In Operation | Res | Y
Fitchburg | Townsend | 2947 | 1469 | 7.6 | Solar | 39W18 | 2017-09-28 | 2017-10-03 | 4 |  | 4 | 2017-10-20 | 2017-11-06 | 11 |  | 11 | [20 empty] | 2017-11-06 |  | 2017-10-19 | NO | Expedited | [8 empty] | 2017-12-28 | In Operation | Res | Y
Fitchburg | Townsend | 2946 | 1469 | 6 | Solar | 15W16 | 2017-09-28 | 2017-10-03 | 4 |  | 4 | 2017-11-03 | 2017-11-20 | 12 |  | 12 | [20 empty] | 2017-11-27 |  | 2017-10-30 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2945 | 1462 | 7.6 | Solar | 30W30 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-16 |  | 2017-11-25 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 2944 | 1469 | 3.8 | Solar | 39W18 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-10-23 | 2017-11-15 | 17 |  | 17 | [20 empty] | 2017-11-15 |  | 2017-11-25 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2943 | 1431 | 7.6 | Solar | 39W19 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-11-15 | 2017-11-15 | 1 |  | 1 | [20 empty] | 2017-11-16 |  | 2017-11-25 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 2939 | 1420 | 7.6 | Solar | 20W22 | 2017-09-25 | 2017-10-03 | 7 |  | 7 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-14 |  | 2017-10-23 | YES | Expedited | [8 empty] | 2018-08-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2938 | 1420 | 6.6 | Solar | 40W39 | 2017-09-25 | 2017-10-03 | 7 |  | 7 | 2017-11-02 | 2017-11-21 | 14 |  | 14 | [20 empty] | 2017-11-22 |  | 2017-10-25 | NO | Expedited | [8 empty] | 2018-04-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 2936 | 1420 | 4.4 | Solar | 01W04 | 2017-09-25 | 2017-10-02 | 6 |  | 6 | 2017-11-02 | 2017-11-21 | 14 |  | 14 | [20 empty] | 2017-11-22 |  | 2017-10-25 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2935 | 1420 | 3.8 | Solar | 31W37 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-27 | 2017-11-13 | 11 |  | 11 | [20 empty] | 2017-11-14 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Ashby | 2934 | 1431 | 8.35 | Solar | 39W19 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-27 | 2017-12-28 | 42 |  | 42 | [20 empty] | 2018-01-02 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2018-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2932 | 1420 | 3.8 | Solar | 01W04 | 2017-09-20 | 2017-09-29 | 8 |  | 8 | 2017-10-20 | 2017-11-01 | 8 |  | 8 | [20 empty] | 2017-11-06 |  |  | NO | Expedited | [8 empty] | 2018-07-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 2931 | 1462 | 3.8 | Solar | 30W31 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [20 empty] | 2017-11-17 |  | 2017-11-19 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2930 | 1462 | 12 | Solar | 30W30 | 2017-09-18 | 2017-09-25 | 6 |  | 6 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-17 |  | 2017-11-15 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2929 | 1462 | 12 | Solar | 31W38 | 2017-09-18 | 2017-09-25 | 6 |  | 6 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-11-16 |  | 2017-09-15 | YES | Expedited | [8 empty] | 2018-03-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 2928 | 1462 | 9 | Solar | 31W37 | 2017-09-15 | 2017-09-25 | 7 |  | 7 | 2017-10-26 | 2017-11-21 | 18 |  | 18 | [20 empty] | 2017-11-22 |  | 2017-08-22 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2925 | 1462 | 3.8 | Solar | 31W38 | 2017-09-14 | 2017-09-25 | 8 |  | 8 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-11-14 |  | 2017-11-11 | NO | Expedited | [8 empty] | 2018-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2924 | 1420 | 10.4 | Solar | 11W11 | 2017-09-11 | 2017-09-29 | 15 |  | 15 | 2017-10-31 | 2017-12-28 | 40 |  | 40 | [20 empty] | 2018-01-02 |  | 2017-11-13 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2921 | 1462 | 15 | Solar | 30W31 | 2017-09-11 | 2017-10-10 | 21 | 7 | 14 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [20 empty] | 2017-11-17 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2018-01-15 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2920 | 1462 | 10.95 | Solar | 30W30 | 2017-09-07 | 2017-10-11 | 24 | 7 | 17 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2017-12-22 | NO | Expedited | [8 empty] | 2018-01-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2917 | 1462 | 10.95 | Solar | 30W31 | 2017-09-01 | 2017-10-05 | 24 | 5 | 19 | 2017-10-20 | 2017-11-01 | 8 |  | 8 | [20 empty] | 2017-11-06 |  | 2017-10-28 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2914 | 1420 | 7.6 | Solar | 01W02 | 2017-09-01 | 2017-09-25 | 16 |  | 16 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-12-07 |  | 2017-11-01 | YES | Expedited | [8 empty] | 2018-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2904 | 1420 | 5 | Solar | 01W04 | 2017-08-30 | 2017-09-22 | 17 |  | 17 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2901 | 1420 | 8.35 | Solar | 11W11 | 2017-08-29 | 2017-09-27 | 21 |  | 21 | 2017-10-23 | 2017-11-20 | 20 |  | 20 | [20 empty] | 2017-11-30 |  | 2017-10-29 | YES | Expedited | [8 empty] | 2018-03-27 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2892 | 1462 | 8.35 | Solar | 30W30 | 2017-08-28 | 2017-09-15 | 14 | 1 | 13 | 2017-10-13 | 2017-11-07 | 17 |  | 17 | [20 empty] | 2017-11-07 |  | 2017-10-02 | NO | Expedited | [8 empty] | 2018-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2888 | 1420 | 7.6 | Solar | 50W51 | 2017-08-28 | 2017-09-20 | 17 |  | 17 | 2017-10-16 | 2017-11-01 | 12 |  | 12 | [20 empty] | 2017-11-15 |  | 2017-10-13 | NO | Expedited | [8 empty] | 2017-11-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 2884 | 1462 | 7.6 | Solar | 30W30 | 2017-08-24 | 2017-09-15 | 16 | 3 | 13 | 2017-10-17 | 2017-11-13 | 19 |  | 19 | [20 empty] | 2017-11-13 |  | 2017-09-20 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2882 | 1420 | 10.95 | Solar | 01W02 | 2017-08-23 | 2017-09-15 | 17 | 2 | 15 | 2017-10-16 | 2017-11-13 | 20 |  | 20 | [20 empty] | 2017-11-13 |  |  | NO | Expedited | [8 empty] | 2018-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2879 | 1420 | 3.8 | Solar | 35W36 | 2017-08-22 | 2017-09-15 | 18 | 15 | 3 | 2017-09-30 | 2017-10-25 | 17 |  | 17 | [20 empty] | 2017-10-25 |  | 2017-10-21 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2878 | 1462 | 6 | Solar | 30W30 | 2017-08-21 | 2017-09-19 | 21 | 19 | 2 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  | 2017-09-25 | NO | Expedited | [8 empty] | 2017-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2876 | 1420 | 3.8 | Solar | 01W02 | 2017-08-21 | 2017-09-15 | 19 |  | 19 | 2017-09-30 | 2017-11-03 | 23 |  | 23 | [20 empty] | 2017-11-03 |  | 2017-10-21 | YES | Expedited | [8 empty] | 2018-07-06 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2875 | 1420 | 5 | Solar | 11W11 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | 2017-10-10 | 2017-10-25 | 12 |  | 12 | [20 empty] | 2017-10-25 |  |  | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Townsend | 2874 | 1469 | 7.6 | Solar | 15W16 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | 2017-10-13 | 2017-11-06 | 16 |  | 16 | [20 empty] | 2017-11-09 |  | 2017-10-19 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2872 | 1420 | 5.22 | Solar | 01W04 | 2017-08-17 | 2017-09-08 | 16 |  | 16 | [27 empty] | 2017-09-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2871 | 1431 | 1.8 | Solar | 39W19 | 2017-08-16 | 2017-09-19 | 24 | 7 | 17 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  |  | NO | Expedited | [8 empty] | 2017-11-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2869 | 1420 | 8.35 | Solar | 25W27 | 2017-08-17 | 2017-09-07 | 15 |  | 15 | 2017-09-29 | 2017-10-25 | 18 |  | 18 | [20 empty] | 2017-10-25 |  | 2017-10-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2868 | 1474 | 9.28 | Solar | 39W18 | 2017-08-16 | 2017-09-05 | 14 | 3 | 11 | 2017-09-29 | 2017-10-26 | 19 |  | 19 | [20 empty] | 2017-10-26 |  | 2017-10-20 | NO | Expedited | [8 empty] | 2018-01-29 | In Operation | Res | Y
Fitchburg | Townsend | 2867 | 1469 | 10.95 | Solar | 15W16 | 2017-08-16 | 2017-09-05 | 14 |  | 14 | 2017-09-29 | 2017-10-26 | 19 |  | 19 | [20 empty] | 2017-10-26 |  | 2017-09-16 | NO | Expedited | [8 empty] | 2017-12-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2865 | 1462 | 10.95 | Solar | 30W30 | 2017-08-15 | 2017-08-23 | 7 |  | 7 | 2017-09-15 | 2017-10-26 | 29 |  | 29 | [20 empty] | 2017-10-26 |  | 2017-08-17 | NO | Expedited | [8 empty] | 2017-12-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2864 | 1462 | 10.95 | Solar | 30W30 | 2017-08-14 | 2017-09-22 | 29 | 1 | 28 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  | 2017-08-28 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2855 | 1420 | 10.95 | Solar | 50W51 | 2017-08-10 | 2017-08-17 | 6 |  | 6 | 2017-09-14 | 2017-09-29 | 12 |  | 12 | [20 empty] | 2017-10-05 |  | 2017-10-10 | NO | Expedited | [8 empty] | 2017-11-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2853 | 1462 | 3.8 | Solar | 31W38 | 2017-08-14 | 2017-08-17 | 4 |  | 4 | 2017-09-14 | 2017-09-29 | 12 |  | 12 | [20 empty] | 2017-10-11 |  | 2017-10-11 | NO | Expedited | [8 empty] | 2018-02-15 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2852 | 1420 | 5 | Solar | 20W22 | 2017-08-11 | 2017-09-25 | 31 | 25 | 6 | 2017-10-27 | 2017-11-22 | 18 | 3 | 15 | [20 empty] | 2017-11-22 |  | 2017-08-20 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2849 | 1462 | 5.45 | Solar | 30W31 | 2017-08-08 | 2017-08-11 | 4 |  | 4 | 2017-09-25 | 2017-10-24 | 21 |  | 21 | [20 empty] | 2017-11-01 |  | 2017-09-08 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2847 | 1469 | 9 | Solar | 15W16 | 2017-08-08 | 2017-08-11 | 4 |  | 4 | 2017-09-11 | 2017-09-29 | 15 |  | 15 | [20 empty] | 2017-10-12 |  | 2017-10-10 | NO | Expedited | [8 empty] | 2017-11-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2846 | 1462 | 7.6 | Solar | 31W37 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-07 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2845 | 1420 | 7.6 | Solar | 11W11 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-04 | NO | Expedited | [8 empty] | 2018-04-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2844 | 1462 | 12 | Solar | 30W30 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-04 | NO | Expedited | [8 empty] | 2017-11-09 | In Operation | Res | Y
Fitchburg | Townsend | 2843 | 1469 | 8.35 | Solar | 15W16 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-08-30 | 2017-09-15 | 12 |  | 12 | [20 empty] | 2017-10-12 |  | 2017-10-03 | YES | Expedited | [8 empty] | 2018-04-04 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2842 | 1462 | 8.35 | Solar | 30W30 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-15 | 10 |  | 10 | [20 empty] | 2017-10-12 |  | 2017-10-03 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2841 | 1462 | 12 | Solar | 31W38 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-15 | 10 |  | 10 | [20 empty] | 2017-10-04 |  | 2017-10-03 | YES | Expedited | [8 empty] | 2018-03-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2837 | 1420 | 1860 | Solar | 31W37 | 2018-01-11 | 2018-03-19 | 43 | 43 | 0 | [10 empty] | 2018-04-17 | 2018-05-13 | 19 |  | 19 | 2018-08-03 | 2019-03-28 | 161 | 29 | 132 | [7 empty] | 2018-10-01 | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 2828 | 1462 | 8.35 | Solar | 30W30 | 2017-08-01 | 2017-08-14 | 10 |  | 10 | 2017-09-13 | 2017-09-28 | 12 |  | 12 | [20 empty] | 2017-10-12 |  | 2017-09-27 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2815 | 1462 | 8.35 | Solar | 30W30 | 2017-06-30 | 2017-08-02 | 23 |  | 23 | 2017-08-09 | 2017-08-31 | 17 |  | 17 | [20 empty] | 2017-08-31 |  | 2017-08-29 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2808 | 1462 | 10.95 | Solar | 31W37 | 2017-07-31 | 2017-08-03 | 4 | 1 | 3 | 2017-08-17 | 2017-09-15 | 21 |  | 21 | [20 empty] | 2017-09-19 |  | 09/31/2017 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2807 | 1462 | 8.35 | Solar | 30W31 | 2017-07-27 | 2017-08-03 | 6 | 2 | 4 | 2017-09-06 | 2017-09-28 | 17 |  | 17 | [20 empty] | 2017-10-10 |  | 2017-08-27 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2803 | 1462 | 7.68 | Solar | 30W30 | 2017-07-25 | 2017-08-01 | 6 |  | 6 | 2017-08-17 | 2017-09-15 | 21 |  | 21 | [20 empty] | 2017-09-19 |  | 2017-07-25 | NO | Expedited | [8 empty] | 2017-12-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2802 | 1420 | 3 | Solar | 01W02 | 2017-07-24 | 2017-07-26 | 3 | 1 | 2 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2797 | 1420 | 7.6 | Solar | 25W27 | 2017-07-21 | 2017-07-25 | 3 |  | 3 | 2017-08-03 | 2017-08-23 | 15 |  | 15 | [20 empty] | 2017-08-31 |  |  | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2794 | 1420 | 10 | Solar | 35W36 | 2017-07-20 | 2017-07-28 | 7 | 3 | 4 | 2017-08-17 | 2017-09-18 | 22 |  | 22 | [20 empty] | 2017-09-19 |  | 2017-10-07 | NO | Expedited | [8 empty] | 2017-11-07 | In Operation | Res | Y
Fitchburg | Townsend | 2793 | 1469 | 8.35 | Solar | 39W18 | 2017-07-20 | 2017-07-27 | 6 | 2 | 4 | 2017-08-10 | 2017-09-07 | 20 |  | 20 | [20 empty] | 2017-09-07 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-10-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2792 | 1420 | 5 | Solar | 25W27 | 2017-07-19 | 2017-07-21 | 3 |  | 3 | 2017-08-01 | 2017-08-23 | 17 |  | 17 | [20 empty] | 2017-08-28 |  |  | NO | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2791 | 1420 | 3.8 | Solar | 40W42 | 2017-07-19 | 2017-07-21 | 3 |  | 3 | 2017-08-04 | 2017-08-23 | 14 |  | 14 | [20 empty] | 2017-08-28 |  |  | NO | Expedited | [8 empty] | 2017-11-08 | In Operation | Res | Y
Fitchburg | West Townsend | 2790 | 1474 | 8.35 | Solar | 39W18 | 2017-07-19 | 2017-07-27 | 7 | 5 | 2 | 2017-08-24 | 2017-09-24 | 21 |  | 21 | [20 empty] | 2017-09-21 |  | 2017-08-02 | YES | Expedited | [8 empty] | 2017-11-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2788 | 1462 | 8.35 | Solar | 31W38 | 2017-07-17 | 2017-07-19 | 3 |  | 3 | 2017-08-02 | 2017-09-15 | 32 |  | 32 | [20 empty] | 2017-09-15 |  | 2017-09-14 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2785 | 1469 | 8.35 | Solar | 39W18 | 2017-07-14 | 2017-08-03 | 15 | 9 | 6 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | [20 empty] | 2017-09-19 |  | 2017-08-13 | NO | Expedited | [8 empty] | 2017-10-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2784 | 1420 | 3 | Solar | 25W27 | 2017-07-14 | 2017-07-19 | 4 |  | 4 | 2017-08-09 | 2017-09-15 | 27 |  | 27 | [20 empty] | 2017-10-04 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2783 | 1420 | 10.1 | Solar | 25W27 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-08-24 | 2017-09-15 | 16 |  | 16 | [20 empty] | 2017-09-21 |  | 2017-09-13 | NO | Expedited | [8 empty] | 2018-04-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2781 | 1462 | 3.8 | Solar | 31W38 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-07-27 | 2017-08-23 | 20 |  | 20 | [20 empty] | 2017-08-28 |  | 2017-09-13 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Townsend | 2780 | 1474 | 8.35 | Solar | 39W18 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-07-27 | 2017-08-23 | 20 |  | 20 | [20 empty] | 2017-08-28 |  | 2017-09-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2779 | 1420 | 3.8 | Solar | 25W27 | 2017-07-13 | 2017-07-14 | 2 |  | 2 | 2017-08-03 | 2017-08-23 | 15 |  | 15 | [20 empty] | 2017-08-31 |  |  | NO | Expedited | [8 empty] | 2018-01-04 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2774 | 1420 | 7.6 | Solar | 50W51 | 2017-10-17 | 2017-10-18 | 2 |  | 2 | 2017-08-21 | 2017-09-18 | 20 |  | 20 | [20 empty] | 2017-10-19 |  | 2017-08-07 | NO | Expedited | [8 empty] | 2017-10-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2773 | 1462 | 7.6 | Solar | 30W31 | 2017-07-10 | 2017-07-11 | 2 |  | 2 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-07 |  | 2017-09-10 | NO | Expedited | [8 empty] | 2018-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2772 | 1420 | 8.35 | Solar | 25W27 | 2017-06-30 | 2017-07-05 | 3 |  | 3 | 2017-08-10 | 2017-09-06 | 19 |  | 19 | [20 empty] | 2017-09-06 |  |  | NO | Expedited | [8 empty] | 2018-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2771 | 1420 | 10.05 | Solar | 31W37 | 2017-06-30 | 2017-07-07 | 5 |  | 5 | 2017-07-25 | 2017-08-23 | 22 |  | 22 | [20 empty] | 2017-08-29 |  | 2017-08-30 | NO | Expedited | [8 empty] | 2017-10-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2770 | 1462 | 10 | Solar | 30W31 | 2017-06-27 | 2017-06-30 | 4 |  | 4 | 2017-07-14 | 2017-08-22 | 28 |  | 28 | [20 empty] | 2017-08-23 |  |  | NO | Expedited | [8 empty] | 2017-10-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2769 | 1462 | 10.95 | Solar | 30W30 | 2017-06-27 | 2017-07-05 | 6 |  | 6 | 2017-07-17 | 2017-08-23 | 28 |  | 28 | [20 empty] | 2017-08-24 |  | 2017-07-24 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Townsend | 2768 | 1469 | 10.95 | Solar | 15w16 | 2017-06-27 | 2017-06-30 | 4 |  | 4 | 2017-08-04 | 2017-08-24 | 15 |  | 15 | [20 empty] | 2017-08-31 |  | 2017-07-07 | NO | Expedited | [8 empty] | 2017-11-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2762 | 1420 | 6 | Solar | 01W04 | 2017-06-26 | 2017-06-28 | 3 |  | 3 | 2017-08-04 | 2017-08-24 | 15 |  | 15 | [20 empty] | 2017-08-31 |  | 2017-07-28 | NO | Expedited | [8 empty] | 2017-11-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2755 | 1420 | 3 | Solar | 01W04 | 2017-06-23 | 2017-07-10 | 11 | 8 | 3 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2753 | 1420 | 4.15 | Solar | 20W22 | 2017-06-21 | 2017-06-27 | 5 |  | 5 | 2017-07-13 | 2017-08-22 | 29 |  | 29 | [20 empty] | 2017-08-22 |  | 2017-08-21 | NO | Expedited | [8 empty] | 2017-10-17 | In Operation | Res | Y
Fitchburg | Townsend | 2752 | 1469 | 6.6 | Solar | 15W16 | 2017-06-21 | 2017-06-26 | 4 |  | 4 | 2017-08-18 | [24 empty] | 2017-08-18 |  | 2017-08-21 | NO | Expedited | [8 empty] | 2017-09-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2751 | 1420 | 4.6 | Solar | 25W27 | 2017-06-19 | 2017-06-26 | 6 |  | 6 | 2017-07-13 | 2017-08-22 | 29 |  | 29 | [20 empty] | 2017-08-23 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2747 | 1462 | 9.9 | Solar | 31W38 | 2017-06-15 | 2017-06-20 | 4 |  | 4 | 2017-07-18 | 2017-09-13 | 41 |  | 41 | [20 empty] | 2017-08-31 |  | 2017-08-13 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 2746 | 1462 | 10.95 | Solar | 30W30 | 2017-06-13 | 2017-06-20 | 6 |  | 6 | 2017-07-06 | 2017-09-07 | 45 |  | 45 | [20 empty] | 2017-09-07 |  | 2017-08-14 | NO | Expedited | [8 empty] | 2018-01-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2744 | 1420 | 159.9 | Solar | 01W04 | 2017-06-23 | 2017-06-27 | 3 |  | 3 | 2017-07-06 | 2017-08-02 | 20 |  | 20 | [20 empty] | 2017-08-02 |  | 2017-10-01 | YES | Expedited | [8 empty] | 2018-03-06 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2743 | 1462 | 4.15 | Solar | 30W31 | 2017-06-08 | 2017-07-10 | 22 | 17 | 5 | 2017-08-22 | 2017-09-15 | 18 |  | 18 | [20 empty] | 2017-09-19 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-11-16 | In Operation | Rres | Y
Fitchburg | Fitchburg | 2742 | 1420 | 8.35 | Solar | 31W37 | 2017-06-08 | 2017-06-13 | 4 |  | 4 | 2017-06-27 | 2017-08-17 | 37 |  | 37 | [20 empty] | 2017-08-18 |  | 2017-08-07 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2739 | 1420 | 8.35 | Solar | 01W02 | 2017-06-06 | 2017-06-12 | 5 |  | 5 | 2017-06-27 | 2017-08-17 | 37 |  | 37 | [20 empty] | 2017-08-18 |  | 2017-08-06 | NO | Expedited | [8 empty] | 2017-09-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2729 | 1462 | 7.68 | Solar | 30W30 | 2017-06-01 | 2017-06-05 | 3 |  | 3 | 2017-07-13 | 2017-08-17 | 26 |  | 26 | [20 empty] | 2017-08-18 |  | 2017-09-11 | NO | Expedited | [8 empty] | 2017-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 2723 | 1469 | 997.7 | Solar | 39W18 | 2017-05-24 | 2017-06-23 | 22 | 10 | 12 | [10 empty] | 2017-06-24 | 2017-08-05 | 29 |  | 29 | 2017-08-19 | 2017-12-22 | 86 |  | 86 | 2018-05-04 | 2018-06-26 | 37 |  | 37 | 2018-07-11 | 2019-06-13 | 2018-01-30 | YES | Standard | [6 empty] | 2020-07-10 | 2020-07-10 | 2020-10-07 | In Operation | Comm | Y
Fitchburg | Townsend | 2720 | 1469 | 8.35 | Solar | 15W16 | 2017-05-23 | 2017-06-01 | 7 | 5 | 2 | 2017-06-23 | 2017-08-02 | 28 | 5 | 23 | [20 empty] | 2017-08-02 |  |  | NO | Expedited | [8 empty] | 2017-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2714 | 1462 | 10.95 | Solar | 30W30 | 2017-05-17 | 2017-05-22 | 4 |  | 4 | 2017-07-17 | 2017-08-31 | 34 |  | 34 | [20 empty] | 2017-08-31 |  | 2017-04-14 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Ashby | 2712 | 1431 | 10.95 | Solar | 39W19 | 2017-05-17 | 2017-05-22 | 4 |  | 4 | 2017-06-08 | 2017-06-21 | 10 |  | 10 | [20 empty] | 2017-06-27 |  | 2017-07-01 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Townsend | 2709 | 1469 | 8.35 | Solar | 15W16 | 2017-05-15 | 2017-05-19 | 5 | 1 | 4 | 2017-07-17 | 2017-08-18 | 25 |  | 25 | [20 empty] | 2017-08-18 |  | 2017-06-09 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 2708 | 1462 | 5.45 | Solar | 30W30 | 2017-05-15 | 2017-05-17 | 3 |  | 3 | 2017-05-30 | 2017-06-26 | 20 |  | 20 | [20 empty] | 2017-06-26 |  |  | NO | Expedited | [8 empty] | 2017-08-14 | In Operation | Res | Y
Fitchburg | Townsend | 2704 | 1469 | 8.35 | Solar | 39W18 | 2017-05-12 | 2017-05-16 | 3 |  | 3 | 2017-05-30 | 2017-06-20 | 16 |  | 16 | [20 empty] | 2017-06-27 |  | 2017-07-10 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2695 | 1420 | 168 | Solar | 40W40 | 2017-05-03 | 2017-06-12 | 28 | 13 | 15 | 2017-06-12 | 2017-07-31 | 35 |  | 35 | [20 empty] | 2017-07-31 |  | 2017-08-02 | NO | Expedited | [8 empty] | 2017-12-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2692 | 1462 | 10 | Solar | 30W30 | 2017-05-02 | 2017-05-04 | 3 |  | 3 | 2017-06-02 | 2017-06-27 | 18 |  | 18 | [20 empty] | 2017-06-27 |  | 2017-05-24 | NO | Expedited | [8 empty] | 2017-12-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2691 | 1462 | 4.95 | Solar | 31W38 | 2017-05-02 | 2017-05-03 | 2 |  | 2 | 2017-05-23 | 2017-06-12 | 14 |  | 14 | [20 empty] | 2017-06-12 |  | 2017-07-01 | NO | Expedited | [8 empty] | 2017-07-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2690 | 1462 | 10.95 | Solar | 30W30 | 2017-05-02 | 2017-05-03 | 2 |  | 2 | 2017-06-19 | 2017-06-21 | 3 |  | 3 | [20 empty] | 2017-06-27 |  | 2017-07-01 | YES | Expedited | [8 empty] | 2017-09-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2688 | 1462 | 9.92 | Solar | 30W31 | 2017-05-01 | 2017-05-03 | 3 |  | 3 | 2017-05-15 | 2017-06-20 | 26 |  | 26 | [20 empty] | 2017-06-26 |  | 2017-06-30 | NO | Expedited | [8 empty] | 2017-09-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2684 | 1462 | 10.13 | Solar | 30W30 | 2017-04-28 | 2017-05-01 | 2 |  | 2 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2682 | 1431 | 5.76 | Solar | 39W19 | 2017-04-26 | 2017-04-27 | 2 |  | 2 | 2017-05-11 | 2017-06-20 | 28 |  | 28 | [20 empty] | 2017-06-26 |  | 2017-06-01 | NO | Expedited | [8 empty] | 2017-08-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2681 | 1462 | 10 | Solar | 30W30 | 2017-04-26 | 2017-04-27 | 2 |  | 2 | 2017-05-12 | [26 empty] | 2017-06-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2673 | 1420 | 10 | Solar | 31W37 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-09 | 2017-06-20 | 30 | 7 | 23 | [22 empty] | 2017-05-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2672 | 1462 | 9.92 | Solar | 30W31 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-08 | 2017-06-20 | 31 |  | 31 | [20 empty] | 2017-06-23 |  | 06/31/2017 | NO | Expedited | [8 empty] | 2017-08-01 | In Operation | Res | Y
Fitchburg | Townsend | 2671 | 1469 | 6 | Solar | 30W31 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-12 | 2017-06-20 | 27 |  | 27 | [20 empty] | 2017-06-26 |  | 2017-06-18 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2670 | 1420 | 8.75 | Solar | 01W02 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-11 | 2017-06-20 | 28 |  | 28 | [20 empty] | 2017-06-23 |  | 2017-06-03 | NO | Expedited | [8 empty] | 2017-08-08 | In Operation | Res | Y
Fitchburg | Townsend | 2667 | 1469 | 8.35 | Solar | 15W16 | 2017-04-18 | 2017-04-24 | 5 | 2 | 3 | 2017-05-05 | 2017-06-19 | 31 |  | 31 | [20 empty] | 2017-06-20 |  | 2017-05-12 | NO | Expedited | [8 empty] | 2017-07-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2666 | 1462 | 3.8 | Solar | 30W30 | 2017-04-18 | 2017-04-20 | 3 |  | 3 | 2017-05-02 | 2017-06-20 | 35 |  | 35 | [20 empty] | 2017-06-23 |  | 2017-06-18 | NO | Expedited | [8 empty] | 2017-07-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2665 | 1420 | 6 | Solar | 01W02 | 2017-04-18 | 2017-04-19 | 2 |  | 2 | 2017-05-26 | 2017-06-20 | 17 |  | 17 | [20 empty] | 2017-06-26 |  | 2017-05-17 | NO | Expedited | [8 empty] | 2017-08-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2664 | 1420 | 7.45 | Solar | 50W51 | 2017-04-17 | 2017-04-19 | 2 |  | 2 | 2017-05-01 | 2017-06-15 | 33 |  | 33 | [20 empty] | 2017-06-16 |  | 2017-12-27 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Townsend | 2663 | 1469 | 12.15 | Solar | 15W16 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | 2017-05-02 | 2017-06-15 | 32 |  | 32 | [20 empty] | 2017-06-16 |  | 2017-06-14 | NO | Expedited | [8 empty] | 2017-09-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2662 | 1420 | 12 | Solar | 20W22 | 2017-04-14 | 2017-04-19 | 3 | 1 | 2 | 2017-05-02 | 2017-06-15 | 32 |  | 32 | [20 empty] | 2017-06-16 |  | 2017-06-13 | NO | Expedited | [8 empty] | 2017-09-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2661 | 1420 | 4 | Solar | 31W37 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | 2017-05-01 | 2017-06-05 | 25 |  | 25 | [20 empty] | 2017-06-12 |  | 2017-06-14 | NO | Expedited | [8 empty] | 2017-08-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2660 | 1462 | 9.6 | Solar | 31w37 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | [27 empty] | 2016-06-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2659 | 1420 | 8.35 | Solar | 25W27 | 2017-04-14 | 2017-04-18 | 2 |  | 2 | 2017-04-27 | 2017-06-05 | 27 |  | 27 | [20 empty] | 2017-06-05 |  | 2017-05-26 | NO | Expedited | [8 empty] | 2017-07-05 | In Operation | Res | Y
Fitchburg | Townsend | 2656 | 1474 | 14.75 | Solar | 39W18 | 2017-04-12 | 2017-04-13 | 2 |  | 2 | 2017-04-20 | 2017-06-16 | 41 |  | 41 | [20 empty] | 2017-06-16 |  | 2017-06-11 | YES | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2654 | 1420 | 8.75 | Solar | 25W27 | 2017-04-10 | 2017-04-13 | 4 |  | 4 | 2017-04-26 | 2017-06-20 | 39 |  | 39 | [20 empty] | 2017-06-20 |  | 2017-06-10 | NO | Expedited | [8 empty] | 2017-09-06 | In Operation | Res | Y
Fitchburg | Townsend | 2653 | 1474 | 8.35 | Solar | 39W18 | 2017-04-06 | 2017-04-10 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-22 | In Operation | Res | Y
Fitchburg | Townsend | 2651 | 1469 | 12.5 | Solar | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-25 | 26 |  | 26 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Townsend | 2650 | 1469 | 8.35 | Solar | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Townsend | 2649 | 1469 | 8.35 | Solar | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-25 | 26 |  | 26 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2647 | 1420 | 6.4 | Solar | 01W04 | 2017-04-03 | 2017-04-05 | 3 |  | 3 | [27 empty] | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2644 | 1469 | 12.15 | Solar | 39W18 | 2017-04-03 | 2017-04-05 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-02 | NO | Expedited | [8 empty] | 2018-03-21 | In Operation | Res | Y
Fitchburg | Townsend | 2643 | 1469 | 15 | Solar | 15W16 | 2017-04-26 | 2017-06-05 | 28 |  | 28 | 2017-06-30 | 2017-08-18 | 35 |  | 35 | [20 empty] | 2017-08-18 |  | 2017-08-01 | NO | Expedited | [8 empty] | 2017-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 2642 | 1469 | 7.95 | Solar | 15W16 | 2017-03-27 | 2017-05-17 | 37 | 32 | 5 | 2017-05-26 | 2017-06-19 | 16 |  | 16 | [20 empty] | 2017-06-21 |  | 2017-06-28 | NO | Expedited | [8 empty] | 2018-03-16 | In Operation | Res | Y
Fitchburg | Townsend | 2640 | 1469 | 7.6 | Solar | 39W18 | 2017-03-31 | 2017-04-04 | 3 |  | 3 | 2017-04-26 | 2017-06-20 | 39 |  | 39 | [20 empty] | 2017-06-20 |  | 2017-05-27 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 2639 | 1462 | 8.35 | Solar | 30W30 | 2017-03-30 | 2017-04-04 | 4 |  | 4 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2638 | 1420 | 8.35 | Solar | 31W37 | 2017-03-30 | 2017-04-04 | 4 |  | 4 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2636 | 1420 | 396 | Solar | 50W51 | 2017-05-26 | 2017-06-30 | 25 |  | 25 | 2017-06-30 | 2017-08-04 | 25 |  | 25 | 2017-08-14 | 2017-09-15 | 24 |  | 24 | [15 empty] | 2017-09-15 |  | 2017-07-15 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 2635 | 1431 | 4.15 | Solar | 39W19 | 2017-03-29 | 2017-04-04 | 5 | 3 | 2 | 2017-04-13 | 2017-05-30 | 32 |  | 32 | [20 empty] | 2017-05-30 |  | 2017-06-28 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2634 | 1469 | 10.95 | Solar | 15W16 | 2017-03-28 | 2017-05-02 | 25 |  | 25 | 2017-05-15 | 2017-06-19 | 25 |  | 25 | [20 empty] | 2017-06-20 |  | 2017-05-01 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2632 | 1420 | 10.95 | Solar | 11W11 | 2017-03-27 | 2017-03-31 | 5 |  | 5 | 2017-04-28 | 2017-06-02 | 25 |  | 25 | [20 empty] | 2017-06-16 |  |  | YES | Expedited | [8 empty] | 2017-11-08 | Not In Service | Res | Y
Fitchburg | Ashby | 2631 | 1431 | 8.35 | Solar | 39W19 | 2017-03-29 | 2017-04-11 | 10 |  | 10 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-04-27 | NO | Expedited | [8 empty] | 2017-07-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2628 | 1420 | 3.8 | Solar | 01W04 | 2017-03-24 | 2017-03-29 | 4 |  | 4 | 2017-04-05 | 2017-05-05 | 22 |  | 22 | [20 empty] | 2017-05-05 |  | 2017-06-24 | NO | Expedited | [8 empty] | 2017-08-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 2627 | 1420 | 12 | Solar | 01W04 | 2017-03-23 | 2017-03-27 | 3 |  | 3 | 2017-04-05 | 2017-05-05 | 22 |  | 22 | [20 empty] | 2017-05-05 |  | 2017-05-22 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2625 | 1420 | 10.95 | Solar | 01W04 | 2017-03-23 | 2017-03-29 | 5 |  | 5 | 2017-04-13 | 2017-05-08 | 17 |  | 17 | [20 empty] | 2017-05-08 |  |  | NO | Expedited | [8 empty] | 2017-07-06 | In Operation | Res | Y
Fitchburg | Ashby | 2623 | 1431 | 7.6 | Solar | 39W19 | 2017-03-22 | 2017-03-30 | 7 |  | 7 | 2017-04-17 | 2017-05-30 | 30 |  | 30 | [20 empty] | 2017-05-30 |  | 2017-05-22 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 2618 | 1462 | 6 | Solar | 30W30 | 2017-03-21 | 2017-03-27 | 5 |  | 5 | 2017-04-21 | 2017-05-30 | 27 |  | 27 | [20 empty] | 2017-05-30 |  | 2017-05-01 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2614 | 1420 | 3.8 | Solar | 20W22 | 2017-03-15 | 2017-03-21 | 4 |  | 4 | 2017-04-05 | 2017-05-04 | 21 |  | 21 | [20 empty] | 2017-05-05 |  | 2017-06-06 | NO | Expedited | [8 empty] | 2017-07-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2613 | 1462 | 10 | Solar | 31W37 | 2017-03-14 | 2017-03-29 | 11 | 4 | 7 | 2017-04-17 | 2017-05-30 | 30 |  | 30 | [20 empty] | 2017-05-30 |  | 2017-04-04 | NO | Expedited | [8 empty] | 2017-06-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2612 | 1462 | 10.95 | Solar | 30W30 | 2017-03-14 | 2017-03-27 | 9 |  | 9 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-04-15 | NO | Expedited | [8 empty] | 2017-06-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2611 | 1462 | 7.2 | Solar | 30W30 | 2017-03-13 | 2017-03-17 | 4 |  | 4 | 2017-05-11 | 2017-06-27 | 33 |  | 33 | [20 empty] | 2017-06-27 |  | 2017-05-13 | NO | Expedited | [8 empty] | 2017-09-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2610 | 1420 | 9 | Solar | 01W02 | 2017-03-13 | 2017-03-17 | 4 |  | 4 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-05-13 | NO | Expedited | [8 empty] | 2017-06-06 | In Operation | Res | Y
Fitchburg | Townsend | 2608 | 1469 | 10.95 | Solar | 39W18 | 2017-03-10 | 2017-03-15 | 4 |  | 4 | 2017-03-22 | 2017-05-01 | 28 |  | 28 | [20 empty] | 2017-05-05 |  | 2017-04-19 | NO | Expedited | [8 empty] | 2017-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2606 | 1462 | 5.45 | Solar | 30W31 | 2017-03-09 | 2017-03-10 | 2 |  | 2 | 2017-04-07 | 2017-05-04 | 19 |  | 19 | [20 empty] | 2017-05-08 |  |  | NO | Expedited | [8 empty] | 2017-06-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2605 | 1462 | 10.95 | Solar | 30W30 | 2017-03-09 | 2017-04-10 | 22 | 14 | 8 | 2017-04-19 | 2017-05-25 | 27 |  | 27 | [20 empty] | 2017-05-30 |  | 2017-04-19 | NO | Expedited | [8 empty] | 2017-09-18 | In Operation | Res | Y
Fitchburg | Ashby | 2604 | 1431 | 8.35 | Solar | 39W19 | 2017-03-07 | 2017-03-10 | 4 |  | 4 | 2017-03-24 | 2017-05-04 | 29 |  | 29 | [20 empty] | 2017-05-05 |  | 2017-05-08 | NO | Expedited | [8 empty] | 2017-08-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 2601 | 1420 | 9 | Solar | 01W04 | 2017-03-03 | 2017-03-08 | 4 |  | 4 | 2017-03-16 | 2017-04-26 | 28 |  | 28 | [20 empty] | 2017-04-28 |  | 2017-05-02 | NO | Expedited | [8 empty] | 2017-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2600 | 1420 | 3204 | Solar | 31W37 | 2017-04-03 | 2017-05-12 | 29 |  | 29 | [10 empty] | 2018-05-13 | 2018-05-13 | 0 |  | 0 | 2017-05-17 | 2017-09-08 | 80 |  | 80 | [5 empty] | 2017-10-28 | 2019-07-29 | 2018-06-01 | YES | Standard | [6 empty] | 2020-12-21 | 2020-12-21 | 2020-12-22 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2591 | 1462 | 23.04 | Solar | 31W38 | 2017-03-17 | 2017-04-03 | 11 |  | 11 | 2017-04-04 | 2017-04-13 | 8 |  | 8 | [20 empty] | 2017-11-22 |  | 2017-04-01 | NO | Expedited | [8 empty] | 2017-12-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2586 | 1420 | 8.35 | Solar | 20W22 | 2017-02-13 | 2017-02-20 | 5 |  | 5 | 2017-02-27 | 2017-03-30 | 22 |  | 22 | [20 empty] | 2017-08-11 |  | 2017-09-08 | YES | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2585 | 1462 | 7.6 | Solar | 30W30 | 2017-02-15 | 2017-02-17 | 3 |  | 3 | [27 empty] | 2017-04-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2584 | 1420 | 5.76 | Solar | 35W36 | 2017-02-23 | 2017-04-27 | 43 | 35 | 8 | 2017-06-19 | 2017-07-10 | 15 |  | 15 | [20 empty] | 2017-07-10 |  | 2017-01-20 | NO | Expedited | [8 empty] | 2017-08-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2580 | 1420 | 5 | Solar | 01W02 | 2017-02-14 | 2017-02-16 | 3 |  | 3 | 2017-03-20 | 2017-04-28 | 29 |  | 29 | [20 empty] | 2017-04-28 |  | 2017-03-17 | NO | Expedited | [8 empty] | 2017-06-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2577 | 1462 | 10.95 | Solar | 30W30 | 2017-02-14 | 2017-02-15 | 2 |  | 2 | 2017-03-15 | 2017-04-26 | 29 |  | 29 | [20 empty] | 2017-04-27 |  | 2017-04-14 | NO | Expedited | [8 empty] | 2017-07-14 | In Operation | Res | Y
Fitchburg | Townsend | 2575 | 1469 | 8.35 | Solar | 30W31 | 2017-02-13 | 2017-02-15 | 3 |  | 3 | 2017-03-15 | 2017-04-26 | 29 |  | 29 | [20 empty] | 2017-04-27 |  | 2017-04-10 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2570 | 1420 | 3.6 | Solar | 50W51 | 2017-02-10 | 2017-02-14 | 3 |  | 3 | 2017-03-23 | 2017-05-02 | 28 |  | 28 | [20 empty] | 2017-05-05 |  | 2017-04-10 | NO | Expedited | [8 empty] | 2017-07-13 | Cancelled | Res | Y
Fitchburg | Townsend | 2564 | 1469 | 7.6 | Solar | 15W16 | 2017-02-06 | 2017-02-08 | 3 |  | 3 | [25 empty] | 2017-03-31 |  |  |  | Expedited | [8 empty] | 2017-05-03 | In Operation |  | Y
Fitchburg | Fitchburg | 2562 | 1420 | 4.15 | Solar | 31W37 | 2017-01-31 | 2017-02-06 | 5 |  | 5 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-03-31 |  | 2017-03-31 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2561 | 1420 | 10.95 | Solar | 31W37 | 2017-02-03 | 2017-02-06 | 2 |  | 2 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-04-05 |  | 2017-08-09 | YES | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2559 | 1462 | 3.8 | Solar | 30W30 | 2017-01-31 | 2017-02-03 | 4 |  | 4 | 2017-03-09 | 2017-04-26 | 33 |  | 33 | [20 empty] | 2017-04-27 |  | 2017-03-31 | NO | Expedited | [8 empty] | 2017-05-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2558 | 1462 | 5.2 | Solar | 31W37 | 2017-01-31 | 2017-02-03 | 4 |  | 4 | 2017-02-27 | 2017-03-28 | 20 |  | 20 | [20 empty] | 2017-03-31 |  | 2017-03-31 | NO | Expedited | [8 empty] | 2017-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2556 | 1462 | 10.96 | Solar | 30W30 | 2017-01-30 | 2017-02-02 | 4 |  | 4 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-03-30 | NO | Expedited | [8 empty] | 2017-07-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2554 | 1462 | 21.3 | Solar | 30W30 | 2017-01-25 | 2017-03-01 | 24 | 15 | 9 | 2017-04-21 | 2017-05-16 | 18 |  | 18 | [22 empty] | 2016-12-29 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2553 | 1462 | 4.15 | Solar | 31W37 | 2017-01-25 | 2017-02-02 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-24 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2552 | 1642 | 4.15 | Solar | 31W38 | 2017-01-25 | 2017-02-03 | 8 |  | 8 | 2018-03-28 | 2018-04-05 | 7 |  | 7 | [20 empty] | 2018-04-09 |  | 2017-03-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2551 | 1462 | 8.35 | Solar | 31W38 | 2017-01-25 | 2017-02-03 | 8 |  | 8 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-04-12 |  | 2017-03-24 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2550 | 1420 | 8.35 | Solar | 35W36 | 2017-01-25 | 2017-02-02 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-24 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2545 | 1420 | 10.95 | Solar | 20W22 | 2017-01-23 | 2017-02-02 | 9 |  | 9 | 2017-02-27 | 2017-04-13 | 32 |  | 32 | [20 empty] | 2017-04-18 |  | 2017-08-09 | YES | Expedited | [8 empty] | 2017-09-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2542 | 1462 | 8.35 | Solar | 30W30 | 2017-01-17 | 2017-02-02 | 13 |  | 13 | 2017-02-27 | 2017-03-30 | 22 |  | 22 | [20 empty] | 2017-04-03 |  | 2017-03-17 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Ashby | 2541 | 1431 | 6 | Solar | 39W19 | 2017-01-18 | 2017-01-31 | 10 |  | 10 | 2017-02-06 | 2017-03-06 | 18 |  | 18 | [20 empty] | 2017-03-13 |  | 2017-01-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2540 | 1462 | 10 | Solar | 30W30 | 2017-01-12 | 2017-01-23 | 7 |  | 7 | 2017-01-27 | 2017-03-09 | 27 |  | 27 | [20 empty] | 2017-03-30 |  | 2017-06-30 | YES | Expedited | [8 empty] | 2017-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2539 | 1462 | 17 | Solar | 30W31 | 2017-01-18 | 2017-01-19 | 2 |  | 2 | 2017-01-19 | 2017-03-02 | 28 |  | 28 | [20 empty] | 2017-03-06 |  |  | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 2538 | 1462 | 8.35 | Solar | 30W30 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-01-30 | 2017-03-06 | 23 |  | 23 | [20 empty] | 2017-03-13 |  | 2017-03-11 | NO | Expedited | [8 empty] | 2017-05-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2534 | 1420 | 8.35 | Solar | 20W22 | 2017-01-06 | 2017-01-17 | 7 |  | 7 | 2017-03-24 | 2017-07-10 | 74 |  | 74 | [20 empty] | 2017-07-10 |  | 2017-03-06 | NO | Expedited | [8 empty] | 2017-09-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2533 | 1462 | 4.15 | Solar | 30W31 | 2017-01-06 | 2017-01-17 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-06 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2529 | 1462 | 5.2 | Solar | 30W31 | 2017-01-04 | 2017-01-13 | 8 |  | 8 | 2017-01-30 | 2017-02-21 | 15 |  | 15 | [20 empty] | 2017-02-22 |  | 2017-03-04 | NO | Expedited | [8 empty] | 2017-05-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2527 | 1462 | 10.95 | Solar | 30W31 | 2016-12-30 | 2017-01-10 | 8 |  | 8 | 2017-02-02 | 2017-03-06 | 20 |  | 20 | [20 empty] | 2017-03-06 |  | 2017-01-06 | NO | Expedited | [8 empty] | 2017-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2526 | 1462 | 6 | Solar | 30W30 | 2016-12-29 | 2017-01-11 | 10 | 2 | 8 | 2017-01-23 | 2017-02-24 | 23 |  | 23 | [20 empty] | 2017-03-01 |  | 2017-01-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2525 | 1462 | 6.6 | Solar | 30W30 | 2016-12-23 | 2017-01-06 | 11 |  | 11 | 2017-01-31 | 2017-02-21 | 14 |  | 14 | [20 empty] | 2017-02-22 |  | 2017-02-22 | NO | Expedited | [8 empty] | 2017-06-12 | In Operation | Res | Y
Fitchburg | Ashby | 2523 | 1431 | 7.5 | Solar | 39W19 | 2016-12-21 | 2017-01-05 | 12 |  | 12 | 2017-01-18 | 2017-02-07 | 15 |  | 15 | [20 empty] | 2017-02-10 |  | 2016-12-13 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2522 | 1462 | 8.35 | Solar | 30W31 | 2016-12-21 | 2017-01-10 | 15 |  | 15 | 2017-01-19 | 2017-02-21 | 22 |  | 22 | [20 empty] | 2017-02-22 |  | 2017-01-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2521 | 1462 | 7.36 | Solar | 30W30 | 2016-12-20 | 2017-01-09 | 15 |  | 15 | 2017-01-25 | 2017-02-27 | 22 |  | 22 | [20 empty] | 2017-03-06 |  | 2017-02-01 | NO | Expedited | [8 empty] | 2017-05-11 | In Operation | Res | Y
Fitchburg | Townsend | 2517 | 1469 | 296 | Solar | 15W16 | 2017-10-27 | 2017-11-07 | 7 |  | 7 | 2017-11-07 | 2017-12-06 | 21 |  | 21 | [20 empty] | 2017-12-06 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Ashby | 2512 | 1431 | 5 | Solar | 39W19 | 2016-12-15 | 2017-01-04 | 15 |  | 15 | 2017-01-18 | 2017-02-13 | 18 |  | 18 | [20 empty] | 2017-02-14 |  | 2016-12-27 | NO | Expedited | [8 empty] | 2017-04-25 | In Operation | Res | Y
Fitchburg | Ashby | 2509 | 1431 | 4.15 | Solar | 39W19 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-11 | 2017-02-07 | 19 |  | 19 | [20 empty] | 2017-02-10 |  | 2017-02-14 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2508 | 1420 | 4.15 | Solar | 31W37 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-16 | 2017-02-07 | 16 |  | 16 | [20 empty] | 2017-02-10 |  | 2017-02-14 | NO | Expedited | [8 empty] | 2017-06-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 2507 | 1420 | 6 | Solar | 01W02 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-02-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2505 | 1431 | 4.15 | Solar | 39W19 | 2016-12-13 | 2017-01-04 | 17 |  | 17 | 2017-01-31 | 2017-02-13 | 9 |  | 9 | [20 empty] | 2017-02-14 |  | 2017-02-13 | NO | Expedited | [8 empty] | 2017-06-12 | In Operation | Res | Y
Fitchburg | Townsend | 2502 | 1469 | 8.3 | Solar | 15W16 | 2016-12-07 | 2016-12-30 | 18 |  | 18 | 2017-01-23 | 2017-02-17 | 19 |  | 19 | [20 empty] | 2017-02-17 |  | 2017-02-07 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2501 | 1469 | 5.2 | Solar | 15W16 | 2016-12-06 | 2016-12-27 | 16 |  | 16 | 2017-01-23 | 2017-02-17 | 19 |  | 19 | [20 empty] | 2017-02-17 |  | 2017-02-06 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2496 | 1462 | 3.8 | Solar | 31W38 | 2016-12-02 | 2016-12-20 | 13 | 8 | 5 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-09-28 | NO | Expedited | [8 empty] | 2017-08-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2494 | 1462 | 4.15 | Solar | 30W30 | 2016-12-01 | 2016-12-20 | 14 |  | 14 | 2017-01-09 | 2017-01-30 | 15 |  | 15 | [20 empty] | 2017-01-31 |  | 2016-12-23 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Townsend | 2492 | 1469 | 8.35 | Solar | 15W16 | 2016-12-01 | 2016-12-20 | 14 |  | 14 | 2017-01-09 | 2017-02-03 | 19 |  | 19 | [20 empty] | 2017-02-09 |  | 2017-01-30 | NO | Expedited | [8 empty] | 2017-04-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2488 | 1420 | 7.6 | Solar | 35W36 | 2016-11-30 | 2016-12-13 | 10 |  | 10 | 2017-01-12 | 2017-02-03 | 16 |  | 16 | [20 empty] | 2017-02-06 |  | 2017-01-29 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Res | Y
Fitchburg | Ashby | 2486 | 1431 | 7.25 | Solar | 35W36 | 2016-11-28 | 2016-12-12 | 11 |  | 11 | 2016-12-20 | 2016-12-27 | 6 |  | 6 | [20 empty] | 2016-12-27 |  | 2017-01-27 | NO | Expedited | [8 empty] | 2017-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2484 | 1420 | 4.95 | Solar | 40W40 | 2016-11-28 | 2016-12-12 | 11 |  | 11 | 2017-01-03 | 2017-02-02 | 22 |  | 22 | [20 empty] | 2017-02-07 |  | 2016-11-08 | YES | Expedited | [8 empty] | 2017-03-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 2482 | 1462 | 3.8 | Solar | 30W31 | 2016-11-22 | 2016-12-08 | 12 | 3 | 9 | 2016-12-16 | 2017-01-06 | 16 |  | 16 | [20 empty] | 2017-01-09 |  | 2017-01-22 | NO | Expedited | [8 empty] | 2017-11-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2480 | 1462 | 8.35 | Solar | 30W31 | 2016-11-22 | 2016-12-08 | 12 |  | 12 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2017-01-22 | NO | Expedited | [8 empty] | 2017-07-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2479 | 1462 | 5.4 | Solar | 30W31 | 2016-11-22 | 2016-12-09 | 13 | 3 | 10 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-03-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2477 | 1462 | 10.95 | Solar | 30W30 | 2016-11-21 | 2016-12-06 | 11 | 2 | 9 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-14 |  | 2017-07-23 | YES | Expedited | [8 empty] | 2017-07-10 | In Operation | Res | Y
Fitchburg | Townsend | 2476 | 1469 | 4.15 | Solar | 30W31 | 2016-11-21 | 2016-12-06 | 11 |  | 11 | 2017-01-20 | 2017-01-20 | 1 |  | 1 | [20 empty] | 2017-01-24 |  | 2017-01-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2475 | 1431 | 10 | Solar | 39W19 | 2016-11-21 | 2016-12-07 | 12 |  | 12 | 2016-12-21 | 2017-01-17 | 19 |  | 19 | [20 empty] | 2017-01-23 |  |  |  | Expedited | [9 empty] | Cancelled |  | Y
Fitchburg | Townsend | 2474 | 1469 | 8.3 | Solar | 15W16 | 2016-11-21 | 2016-12-06 | 11 |  | 11 | 2016-12-16 | 2017-01-09 | 17 |  | 17 | [20 empty] | 2017-01-11 |  | 2017-01-18 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2473 | 1462 | 7.6 | Solar | 30W30 | 2016-11-18 | 2016-11-22 | 3 |  | 3 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2017-01-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2472 | 1469 | 3.8 | Solar | 15W17 | 2016-11-18 | 2016-11-22 | 3 |  | 3 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-18 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2468 | 1462 | 7.6 | Solar | 30W30 | 2016-11-16 | 2016-11-22 | 5 |  | 5 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2017-01-16 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2467 | 1462 | 5.45 | Solar | 30W31 | 2016-11-16 | 2016-11-22 | 5 |  | 5 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-27 |  | 2017-01-15 | YES | Expedited | [8 empty] | 2017-06-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 2466 | 1462 | 4.8 | Solar | 30W30 | 2016-11-16 | 2016-12-06 | 14 | 5 | 9 | 2017-01-03 | 2017-01-30 | 19 |  | 19 | [20 empty] | 2017-01-31 |  | 2016-12-23 | NO | Expedited | [8 empty] | 2017-03-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2464 | 1462 | 8.35 | Solar | 30W30 | 2016-11-15 | 2016-11-22 | 6 |  | 6 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-01-15 | NO | Expedited | [8 empty] | 2017-10-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2463 | 1420 | 8.35 | Solar | 40W40 | 2016-11-15 | 2016-11-17 | 3 |  | 3 | 2017-01-11 | 2017-02-02 | 16 | 2 | 14 | [20 empty] | 2017-02-07 |  | 2017-01-14 | NO | Expedited | [8 empty] | 2017-06-08 | In Operation | Res | Y
Fitchburg | Ashby | 2462 | 1431 | 10 | Solar | 39W19 | 2016-11-15 | 2016-11-29 | 10 |  | 10 | 2017-01-27 | 2017-02-14 | 12 |  | 12 | [20 empty] | 2017-02-14 |  | 2017-01-15 | NO | Expedited | [8 empty] | 2018-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 2459 | 1431 | 10 | Solar | 39W19 | 2016-11-14 | 2016-12-02 | 14 | 4 | 10 | 2016-12-16 | 2016-12-29 | 10 |  | 10 | [20 empty] | 2016-12-29 |  |  | NO | Expedited | [8 empty] | 2017-06-05 | In Operation | Res | Y
Fitchburg | Ashby | 2458 | 1431 | 2.75 | Solar | 39W19 | 2016-11-10 | 2016-12-05 | 16 | 10 | 6 | 2016-12-16 | 2016-12-28 | 9 |  | 9 | [20 empty] | 2016-12-28 |  |  | NO | Expedited | [8 empty] | 2017-01-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2455 | 1462 | 7.6 | Solar | 30W30 | 2016-11-10 | 2016-11-18 | 6 |  | 6 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-24 |  | 2017-01-09 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2454 | 1462 | 8.35 | Solar | 30W31 | 2016-11-08 | 2016-11-18 | 8 |  | 8 | 2017-01-03 | 2017-01-30 | 19 |  | 19 | [20 empty] | 2017-01-31 |  | 2017-01-08 | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2453 | 1420 | 5.4 | Solar | 01W02 | 2016-11-08 | 2016-11-18 | 8 |  | 8 | 2016-12-05 | 2016-12-21 | 13 |  | 13 | [20 empty] | 2016-12-27 |  | 2017-01-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2452 | 1420 | 4.15 | Solar | 11H10 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2017-01-11 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2451 | 1462 | 7.6 | Solar | 30W30 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-22 | 2017-01-20 | 21 |  | 21 | [20 empty] | 2017-01-23 |  | 2017-01-07 | NO | Expedited | [8 empty] | 2017-03-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2450 | 1462 | 10.95 | Solar | 30W30 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2016-12-27 |  | 2017-01-07 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2449 | 1420 | 8.35 | Solar | 25W27 | 2016-11-03 | 2016-11-10 | 6 |  | 6 | 2016-12-15 | 2016-12-15 | 1 |  | 1 | [20 empty] | 2016-12-15 |  | 2017-01-02 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2447 | 1462 | 12 | Solar | 30W31 | 2016-11-04 | 2016-11-17 | 9 |  | 9 | 2017-01-16 | 2017-01-20 | 4 |  | 4 | [20 empty] | 2017-02-10 |  | 2017-01-04 | NO | Expedited | [8 empty] | 2017-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2446 | 1462 | 8.35 | Solar | 30W30 | 2016-11-04 | 2016-11-17 | 9 |  | 9 | 2017-01-16 | 2017-01-17 | 1 |  | 1 | [20 empty] | 2017-02-10 |  | 2017-01-03 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2445 | 1420 | 7.6 | Solar | 01W02 | 2016-11-03 | 2016-11-17 | 10 |  | 10 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-24 |  | 2017-01-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2444 | 1462 | 10.95 | Solar | 30W30 | 2017-03-20 | 2017-03-20 | 1 |  | 1 | 2017-04-06 | 2017-05-05 | 21 |  | 21 | [20 empty] | 2017-05-05 |  | 2017-01-02 | NO | Expedited | [8 empty] | 2017-05-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2442 | 1420 | 7.6 | Solar | 35W36 | 2016-11-01 | 2016-11-17 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-31 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2441 | 1462 | 5.45 | Solar | 30W31 | 2016-10-31 | 2016-11-14 | 10 |  | 10 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-31 | NO | Expedited | [8 empty] | 2017-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2440 | 1462 | 10.95 | Solar | 30W30 | 2016-10-28 | 2016-11-14 | 11 |  | 11 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-28 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2439 | 1420 | 10.95 | Solar | 25W27 | 2016-10-27 | 2016-11-22 | 18 | 5 | 13 | 2016-12-08 | 2016-12-21 | 10 |  | 10 | [20 empty] | 2016-12-27 |  | 2016-12-27 | NO | Expedited | [8 empty] | 2017-02-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2438 | 1462 | 8.35 | Solar | 30W31 | 2016-10-27 | 2016-11-16 | 14 | 4 | 10 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2436 | 1462 | 8.35 | Solar | 31W38 | 2016-10-27 | 2016-11-14 | 12 |  | 12 | 2016-12-09 | 2016-12-21 | 9 |  | 9 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Townsend | 2435 | 1469 | 12.55 | Solar | 39W18 | 2016-10-27 | 2016-11-15 | 13 |  | 13 | 2017-01-26 | 2017-01-28 | 2 |  | 2 | [20 empty] | 2017-01-28 |  | 2016-12-26 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2434 | 1462 | 7.6 | Solar | 31W38 | 2016-10-26 | 2016-11-14 | 13 |  | 13 | 2016-12-20 | 2016-12-22 | 3 |  | 3 | [20 empty] | 2016-12-27 |  | 2016-12-26 | NO | Expedited | [8 empty] | 2017-02-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2433 | 1420 | 6 | Solar | 11W11 | 2016-10-26 | 2016-11-10 | 12 |  | 12 | 2016-12-15 | 2016-12-17 | 2 |  | 2 | [20 empty] | 2016-12-17 |  |  | YES | Expedited | [8 empty] | 2017-03-07 | In Operation | Res | Y
Fitchburg | Townsend | 2432 | 1474 | 4.15 | Solar | 39W18 | 2016-10-26 | 2016-11-10 | 12 |  | 12 | 2016-11-28 | 2016-12-22 | 19 |  | 19 | [20 empty] | 2016-12-27 |  | 2016-12-25 | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2431 | 1462 | 10.95 | Solar | 31W38 | 2016-10-25 | 2016-11-10 | 13 |  | 13 | 2016-12-20 | 2017-01-12 | 18 |  | 18 | [20 empty] | 2017-01-16 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 2429 | 1469 | 10 | Solar | 15W16 | 2016-10-25 | 2016-11-10 | 13 |  | 13 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-12-29 | In Operation | Res | Y
Fitchburg | Townsend | 2428 | 1469 | 5.45 | Solar | 39W18 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2427 | 1462 | 10.95 | Solar | 30W31 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2426 | 1420 | 7.6 | Solar | 31W37 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2017-01-12 | 2017-02-06 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2016-12-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2425 | 1462 | 8.25 | Solar | 30W31 | 2016-10-24 | 2016-11-15 | 16 | 6 | 10 | 2016-12-14 | 2016-12-22 | 7 |  | 7 | [20 empty] | 2016-12-27 |  | 2016-01-11 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2424 | 1420 | 3.5 | Solar | 20H22 | 2016-10-24 | 2016-11-09 | 13 |  | 13 | 2016-12-05 | 2016-12-20 | 12 |  | 12 | [20 empty] | 2016-12-27 |  | 2016-12-31 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2420 | 1462 | 9 | Solar | 30W30 | 2016-10-21 | 2016-11-09 | 14 |  | 14 | 2016-12-22 | 2017-01-23 | 22 |  | 22 | [20 empty] | 2017-01-23 |  | 2016-12-20 | NO | Expedited | [8 empty] | 2017-03-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2418 | 1462 | 10.95 | Solar | 30W30 | 2016-10-21 | 2016-11-07 | 12 |  | 12 | 2016-12-22 | 2017-01-24 | 23 |  | 23 | [20 empty] | 2017-01-24 |  | 2016-12-20 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2416 | 1420 | 4.75 | Solar | 11H10 | 2016-10-20 | 2016-11-03 | 11 |  | 11 | 2016-12-05 | 2016-12-22 | 14 |  | 14 | [20 empty] | 2017-01-11 |  | 2016-12-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2414 | 1462 | 8.35 | Solar | 30W31 | 2016-10-19 | 2016-11-02 | 11 |  | 11 | 2016-12-16 | 2016-12-29 | 10 |  | 10 | [20 empty] | 2016-12-29 |  | 2016-12-15 | NO | Expedited | [8 empty] | 2017-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2413 | 1420 | 4.73 | Solar | 01W04 | 2016-10-17 | 2016-10-28 | 10 |  | 10 | 2016-11-29 | 2016-12-21 | 17 |  | 17 | [20 empty] | 2016-12-22 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-04-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 2412 | 1420 | 7.88 | Solar | 35W36 | 2016-10-17 | 2016-11-15 | 21 |  | 21 | 2016-11-22 | 2016-12-22 | 22 |  | 22 | [20 empty] | 2016-12-22 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2409 | 1420 | 5.45 | Solar | 35W36 | 2016-10-13 | 2016-10-27 | 11 | 6 | 5 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2017-01-09 |  |  | NO | Expedited | [8 empty] | 2017-06-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2408 | 1462 | 8 | Solar | 31W37 | 2016-10-12 | 2016-10-27 | 12 |  | 12 | 2016-11-17 | 2016-11-29 | 8 |  | 8 | [20 empty] | 2016-11-30 |  | 2016-11-01 | NO | Expedited | [8 empty] | 2017-01-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2407 | 1420 | 6.6 | Solar | 25W27 | 2016-10-11 | 2016-10-26 | 12 | 10 | 2 | 2017-02-03 | 2017-02-07 | 3 |  | 3 | [20 empty] | 2017-02-09 |  | 2016-12-11 | NO | Expedited | [8 empty] | 2017-03-28 | In Operation | Res | Y
Fitchburg | Ashby | 2405 | 1431 | 8.35 | Solar | 39W19 | 2016-10-10 | 2016-10-26 | 12 |  | 12 | 2016-11-28 | 2016-12-28 | 23 |  | 23 | [20 empty] | 2016-12-28 |  | 2016-12-10 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2404 | 1420 | 5.45 | Solar | 31W37 | 2016-10-07 | 2016-10-25 | 12 |  | 12 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-11-01 | NO | Expedited | [8 empty] | 2017-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2402 | 1462 | 9 | Solar | 30W31 | 2016-10-07 | 2016-10-25 | 12 |  | 12 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-12-06 | NO | Expedited | [8 empty] | 2017-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 2401 | 1469 | 5.45 | Solar | 39W18 | 2016-10-06 | 2016-10-25 | 13 |  | 13 | 2016-11-14 | 2016-11-29 | 11 |  | 11 | [20 empty] | 2016-11-30 |  | 2016-11-30 | NO | Expedited | [8 empty] | 2017-03-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2397 | 1420 | 5.2 | Solar | 31W37 | 2016-10-05 | 2016-10-25 | 14 | 7 | 7 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-12-04 | NO | Expedited | [8 empty] | 2017-01-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2396 | 1462 | 5.45 | Solar | 30W31 | 2016-10-04 | 2016-10-25 | 15 | 6 | 9 | 2017-01-12 | 2017-02-06 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2016-12-04 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2395 | 1420 | 6.24 | Solar | 25W27 | 2016-10-04 | 2016-10-26 | 16 | 4 | 12 | 2016-12-12 | 2016-12-22 | 9 |  | 9 | [20 empty] | 2016-10-27 |  | 2016-06-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2394 | 1462 | 9 | Solar | 30W31 | 2016-10-04 | 2016-10-24 | 14 | 3 | 11 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-06 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-03-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2393 | 1462 | 5.2 | Solar | 30W30 | 2016-10-04 | 2016-10-24 | 14 | 6 | 8 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-02 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2391 | 1420 | 4.15 | Solar | 20W22 | 2016-10-04 | 2016-10-20 | 12 |  | 12 | 2016-11-04 | 2016-11-29 | 16 |  | 16 | [20 empty] | 2016-11-30 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2388 | 1462 | 10 | Solar | 30W31 | 2016-10-03 | 2016-10-20 | 13 |  | 13 | 2016-11-03 | 2016-11-03 | 1 |  | 1 | [20 empty] | 2016-11-07 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-02-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2387 | 1462 | 3.8 | Solar | 31W38 | 2016-09-29 | 2016-10-20 | 15 |  | 15 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2386 | 1420 | 3.8 | Solar | 40W40 | 2016-09-29 | 2016-10-20 | 15 |  | 15 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-01-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2385 | 1420 | 4000 | Solar + Energy Storage | 35W36 | 2017-02-16 | 2017-03-03 | 10 |  | 10 | [10 empty] | 2017-03-04 | 2017-04-01 | 19 | 11 | 8 | 2017-05-22 | 2017-09-08 | 77 | 35 | 42 | 2018-02-20 | 2018-03-13 | 12 |  | 12 | 2018-05-07 | 2018-11-28 | 2017-12-01 | YES | Standard | [6 empty] | 2020-03-17 | 2020-03-17 | 2020-03-18 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2381 | 1420 | 5.45 | Solar | 31W37 | 2016-09-29 | 2016-10-19 | 14 | 3 | 11 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2380 | 1420 | 8.96 | Solar | 31W37 | 2016-09-29 | 2016-10-19 | 14 | 3 | 11 | 2016-11-14 | 2016-11-29 | 11 |  | 11 | [20 empty] | 2016-11-30 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2016-12-21 | In Operation | Res | Y
Fitchburg | Ashby | 2379 | 1431 | 5.45 | Solar | 39W19 | 2016-09-28 | 2016-10-18 | 14 |  | 14 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-04 |  | 2016-10-15 | NO | Expedited | [8 empty] | 2016-12-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2378 | 1469 | 7.68 | Solar | 30W30 | 2016-09-29 | 2016-10-11 | 8 | 6 | 2 | 2016-10-28 | 2016-11-01 | 3 |  | 3 | [20 empty] | 2016-11-01 |  | 2016-09-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2377 | 1462 | 8.35 | Solar | 31W38 | 2016-09-30 | 2016-10-18 | 12 | 4 | 8 | 2016-10-31 | 2016-11-08 | 7 |  | 7 | [20 empty] | 2016-11-09 |  | 2016-11-28 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2375 | 1462 | 8.35 | Solar | 30W30 | 2016-09-27 | 2016-10-17 | 14 | 4 | 10 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-07 |  | 2016-11-27 | NO | Expedited | [6 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 2369 | 1420 | 9.45 | Solar | 35W36 | 2016-09-22 | 2016-11-16 | 38 | 24 | 14 | 2016-12-05 | 2016-12-21 | 13 | 6 | 7 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2368 | 1420 | 10.95 | Solar | 20H22 | 2016-09-22 | 2016-10-12 | 14 |  | 14 | [27 empty] | 2016-09-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2367 | 1431 | 15 | Solar | 39W19 | 2016-09-22 | 2016-10-06 | 11 | 2 | 9 | 2016-10-24 | 2016-11-03 | 9 |  | 9 | [20 empty] | 2016-11-04 |  |  | NO | Expedited | [8 empty] | 2016-11-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2364 | 1462 | 9 | Solar | 30W31 | 2016-09-21 | 2016-10-10 | 13 |  | 13 | [27 empty] | 2016-11-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2362 | 1431 | 8.35 | Solar | 39W19 | 2016-09-20 | 2016-10-10 | 14 |  | 14 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-04 |  | 2016-09-27 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2361 | 1469 | 6.6 | Solar | 15W17 | 2016-09-19 | 2016-10-10 | 15 |  | 15 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-11-19 | NO | Expedited | [8 empty] | 2017-02-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2359 | 1462 | 10.95 | Solar | 30W31 | 2016-09-19 | 2016-10-11 | 16 |  | 16 | 2016-11-22 | 2016-12-21 | 21 |  | 21 | [20 empty] | 2016-12-22 |  | 2016-11-17 | NO | Expedited | [8 empty] | 2017-09-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2357 | 1462 | 10.95 | Solar | 31W37 | 2016-09-19 | 2016-10-06 | 14 | 1 | 13 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-12-21 | NO | Expedited | [8 empty] | 2017-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2355 | 1420 | 3.8 | Solar | 01W02 | 2016-09-16 | 2016-10-05 | 14 |  | 14 | 2016-12-19 | 2016-12-22 | 4 |  | 4 | [20 empty] | 2016-12-27 |  | 2017-06-08 | NO | Expedited | [8 empty] | 2017-02-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2353 | 1462 | 8.35 | Solar | 31W38 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-11-03 | 2016-11-08 | 4 |  | 4 | [20 empty] | 2016-11-09 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-28 | In Operation | Res | Y
Fitchburg | Ashby | 2352 | 1431 | 8.35 | Solar | 39W19 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-10-18 | 2016-10-25 | 6 |  | 6 | [20 empty] | 2016-10-25 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2351 | 1420 | 8.35 | Solar | 25W27 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-10-18 | 2016-10-20 | 3 |  | 3 | [20 empty] | 2016-10-25 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2017-03-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2350 | 1462 | 5.8 | Solar | 30W30 | 2016-09-15 | 2016-10-03 | 13 |  | 13 | 2016-10-28 | 2016-10-28 | 1 |  | 1 | [20 empty] | 2016-11-01 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2348 | 1462 | 6.6 | Solar | 30W30 | 2016-09-13 | 2016-09-29 | 13 |  | 13 | 2016-11-08 | 2016-12-28 | 35 |  | 35 | [20 empty] | 2016-12-28 |  | 2016-11-13 | NO | Expedited | [8 empty] | 2017-03-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2346 | 1462 | 7.6 | Solar | 31W38 | 2016-09-12 | 2016-09-29 | 14 |  | 14 | [27 empty] | 2016-11-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2340 | 1431 | 12.75 | Solar | 39W19 | 2016-09-07 | 2016-09-21 | 11 |  | 11 | 2016-10-18 | 2016-10-19 | 2 |  | 2 | [20 empty] | 2016-10-21 |  |  | YES | Expedited | 2016-11-29 | 2016-11-16 | 2016-11-16 | 1 |  | 1 | 2017-04-07 | 2017-04-07 | 2017-04-11 | In Operation |  | Y
Fitchburg | Ashby | 2338 | 1431 | 8.35 | Solar | 39W19 | 2016-09-06 | 2016-09-21 | 12 | 2 | 10 | 2016-10-12 | 2016-10-12 | 1 |  | 1 | [20 empty] | 2016-10-20 |  | 2016-10-01 | NO | Expedited | [8 empty] | 2016-11-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 2337 | 1420 | 6.6 | Solar | 20W22 | 2016-09-06 | 2016-09-15 | 8 | 4 | 4 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-11-09 | NO | Expedited | [8 empty] | 2017-02-10 | In Operation | Res | Y
Fitchburg | Ashby | 2330 | 1431 | 6 | Solar | 39W19 | 2016-09-01 | 2016-09-16 | 11 | 1 | 10 | 2016-10-17 | 2016-10-19 | 3 |  | 3 | [20 empty] | 2016-10-20 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-11-17 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2321 | 1462 | 9 | Solar | 30W31 | 2016-08-29 | 2016-09-13 | 11 |  | 11 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-10-29 | NO | Expedited | [8 empty] | 2017-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2320 | 1462 | 12 | Solar | 30W31 | 2016-08-29 | 2016-09-13 | 11 |  | 11 | 2016-10-05 | 2016-10-12 | 5 |  | 5 | [20 empty] | 2016-10-18 |  | 2016-11-01 | YES | Expedited | [8 empty] | 2016-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2319 | 1469 | 4.15 | Solar | 30W31 | 2016-08-26 | 2016-09-13 | 12 |  | 12 | 2016-11-22 | 2016-12-01 | 7 |  | 7 | [20 empty] | 2016-12-06 |  | 2016-10-26 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2317 | 1462 | 5 | Solar | 30W31 | 2016-08-26 | 2016-09-12 | 11 |  | 11 | [25 empty] | 2016-09-22 |  | 2016-10-26 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2316 | 1469 | 6 | Solar | 39W18 | 2016-08-25 | 2016-09-12 | 12 | 4 | 8 | 2016-09-26 | 2016-09-30 | 5 |  | 5 | [20 empty] | 2016-10-07 |  | 2016-10-17 | NO | Expedited | [8 empty] | 2016-11-01 | In Operation | Res | Y
Fitchburg | Townsend | 2315 | 1469 | 5.25 | Solar | 15W16 | 2016-08-25 | 2016-09-07 | 9 |  | 9 | 2016-09-19 | 2016-10-07 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-09-28 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2313 | 1420 | 6.6 | Solar | 01W04 | 2016-08-24 | 2016-09-02 | 8 |  | 8 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-10-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2301 | 1462 | 5.2 | Solar | 31W37 | 2016-08-18 | 2016-08-31 | 10 |  | 10 | 2016-09-19 | 2016-10-07 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-10-17 | NO | Expedited | [8 empty] | 2016-11-16 | In Operation | Res | Y
Fitchburg | Townsend | 2292 | 1469 | 4.95 | Solar | 15W16 | 2016-08-12 | 2016-08-29 | 12 |  | 12 | 2016-09-09 | 2016-09-29 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-10-12 | NO | Expedited | [8 empty] | 2016-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2289 | 1420 | 7.6 | Solar | 25W27 | 2016-08-11 | 2016-08-25 | 11 |  | 11 | 2016-09-16 | 2016-09-30 | 11 |  | 11 | [20 empty] | 2016-10-07 |  | 2016-05-19 | NO | Expedited | [8 empty] | 2016-11-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2284 | 1462 | 8 | Solar | 30W30 | 2016-08-09 | 2016-08-23 | 11 | 2 | 9 | 2016-09-27 | 2016-10-07 | 9 |  | 9 | [20 empty] | 2016-10-07 |  |  | NO | Expedited | [8 empty] | 2017-05-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2283 | 1420 | 6.67 | Solar | 31W37 | 2016-08-08 | 2016-08-24 | 13 | 1 | 12 | 2016-09-23 | 2016-10-07 | 11 |  | 11 | [20 empty] | 2016-10-07 |  | 2016-08-17 | NO | Expedited | [8 empty] | 2016-11-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 2282 | 1420 | 4 | Solar | 01W02 | 2016-08-09 | 2016-08-23 | 11 |  | 11 | 2016-09-06 | 2016-09-28 | 17 |  | 17 | [20 empty] | 2016-10-05 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-10-26 | In Operation | Res | Y
Fitchburg | Ashby | 2281 | 1431 | 8.35 | Solar | 39W19 | 2016-08-05 | 2016-08-23 | 13 | 1 | 12 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | [20 empty] | 2016-10-07 |  |  | NO | Expedited | [8 empty] | 2016-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2280 | 1420 | 7.6 | Solar | 40W40 | 2016-08-05 | 2016-08-22 | 12 |  | 12 | 2016-09-12 | 2016-10-11 | 21 |  | 21 | [20 empty] | 2016-10-18 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2278 | 1420 | 4.25 | Solar | 20W22 | 2016-08-03 | 2016-08-22 | 14 |  | 14 | 2016-09-13 | 2016-10-05 | 17 |  | 17 | [20 empty] | 2016-10-12 |  | 2016-09-08 | YES | Expedited |  | 2016-12-15 | 2016-12-15 | 1 |  | 1 |  |  | 2016-12-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2274 | 1462 | 8.35 | Solar | 31W38 | 2016-08-02 | 2016-08-16 | 11 |  | 11 | 2016-09-12 | 2016-09-30 | 15 |  | 15 | [20 empty] | 2016-09-30 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2273 | 1420 | 4.15 | Solar | 20H22 | 2016-08-01 | 2016-08-11 | 9 |  | 9 | 2016-08-19 | 2016-09-26 | 26 |  | 26 | [20 empty] | 2016-09-26 |  | 2016-10-01 | YES | Expedited |  | 2016-12-15 | 2016-12-15 | 1 |  | 1 |  |  |  | Cancelled | Res | Y
Fitchburg | Lunenburg | 2268 | 1462 | 32 | Solar | 30W31 | 2016-07-29 | 2016-08-16 | 13 |  | 13 | 2016-08-17 | 2016-09-20 | 24 | 15 | 9 | [20 empty] | 2016-09-29 |  | 2016-10-01 | YES | Expedited | [6 empty] | 2017-02-21 | 2017-02-21 | 2017-02-21 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2267 | 1462 | 262 | Solar | 30W31 | 2016-08-15 | 2016-08-17 | 3 |  | 3 | 2016-08-18 | 2016-09-21 | 24 | 20 | 4 | [20 empty] | 2016-10-13 |  | 2016-10-01 | YES | Expedited | [8 empty] | 2017-06-01 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2263 | 1462 | 8 | Solar | 30W31 | 2016-07-25 | 2016-08-04 | 9 |  | 9 | 2016-09-20 | 2016-09-20 | 1 |  | 1 | [20 empty] | 2016-09-22 |  | 2016-10-01 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 2260 | 1462 | 10.95 | Solar | 31W37 | 2016-07-22 | 2016-08-04 | 10 |  | 10 | 2016-09-14 | 2016-09-29 | 12 |  | 12 | [20 empty] | 2016-10-07 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2259 | 1420 | 2.7 | Solar | 31W34 | 2016-07-21 | 2016-08-04 | 11 |  | 11 | 2016-08-26 | 2016-09-15 | 14 |  | 14 | [20 empty] | 2016-08-26 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-08-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 2256 | 1420 | 5.4 | Solar | 01W02 | 2016-07-19 | 2016-08-02 | 11 |  | 11 | 2016-08-22 | 2016-09-15 | 18 |  | 18 | [20 empty] | 2016-09-21 |  | 2016-09-19 | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2255 | 1420 | 4.15 | Solar | 20H22 | 2016-07-19 | 2016-08-01 | 10 |  | 10 | 2016-08-19 | 2016-09-13 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-09-19 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2253 | 1431 | 5.45 | Solar | 39W19 | 2016-07-19 | 2016-08-03 | 12 | 2 | 10 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  |  | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2251 | 1420 | 8.35 | Solar | 11H10 | 2016-07-19 | 2016-07-29 | 9 |  | 9 | [27 empty] | 2016-09-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2244 | 1420 | 17.2 | Solar | 20H22 | 2016-08-24 | 2016-08-31 | 6 |  | 6 | [25 empty] | 2016-09-27 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2240 | 1469 | 10.95 | Solar | 15W16 | 2016-07-11 | 2016-07-25 | 11 |  | 11 | 2016-08-15 | 2016-09-15 | 23 |  | 23 | [20 empty] | 2016-09-08 |  | 2016-09-11 | NO | Expedited | [8 empty] | 2016-11-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2239 | 1420 | 4.15 | Solar | 31W34 | 2016-07-11 | 2016-07-25 | 11 | 5 | 6 | 2016-08-05 | 2016-08-05 | 1 |  | 1 | [20 empty] | 2016-08-26 |  | 2016-09-11 | NO | Expedited | [8 empty] | 2017-02-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2237 | 1420 | 9 | Solar | 01W02 | 2016-07-11 | 2016-07-25 | 11 |  | 11 | 2016-09-30 | 2016-09-30 | 1 |  | 1 | [20 empty] | 2016-10-07 |  | 2016-08-31 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2230 | 1420 | 7.25 | Solar | 25W27 | 2016-07-06 | 2016-07-19 | 10 |  | 10 | 2016-08-09 | 2016-08-25 | 13 |  | 13 | [20 empty] | 2016-09-01 |  | 2016-08-08 | NO | Expedited | [7 empty] | 2016-10-26 | 2016-10-28 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2229 | 1420 | 8.88 | Solar | 35W36 | 2016-07-05 | 2016-07-15 | 9 |  | 9 | 2016-08-08 | 2016-08-22 | 11 |  | 11 | [20 empty] | 2016-08-26 |  | 2016-09-05 | NO | Expedited | [8 empty] | 2016-11-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2228 | 1462 | 4.15 | Solar | 30W30 | 2016-07-05 | 2016-07-15 | 9 |  | 9 | 2016-08-08 | 2016-08-19 | 10 |  | 10 | [20 empty] | 2016-08-22 |  |  | NO | Expedited | [8 empty] | 2016-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 2225 | 1420 | 4.15 | Solar | 31W37 | 2016-07-01 | 2016-07-15 | 10 |  | 10 | 2016-08-08 | 2016-08-23 | 12 |  | 12 | [20 empty] | 2016-08-26 |  | 2016-09-01 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2219 | 1462 | 6.76 | Solar | 31W38 | 2016-06-30 | 2016-07-13 | 9 | 2 | 7 | 2016-07-19 | 2016-08-19 | 24 |  | 24 | [20 empty] | 2016-08-18 |  |  | NO | Expedited | [8 empty] | 2016-09-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2215 | 1420 | 4.15 | Solar | 35W36 | 2016-06-28 | 2016-07-12 | 10 |  | 10 | 2016-07-22 | 2016-08-05 | 11 |  | 11 | [20 empty] | 2016-08-05 |  | 2016-08-27 | NO | Expedited | [8 empty] | 2016-10-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2210 | 1420 | 7.25 | Solar | 31W37 | 2016-06-27 | 2016-07-11 | 10 |  | 10 | 2016-07-26 | 2016-08-19 | 19 |  | 19 | [20 empty] | 2016-08-22 |  | 2016-07-30 | NO | Expedited | [8 empty] | 2016-09-09 | In Operation | Res | Y
Fitchburg | Townsend | 2205 | 1469 | 5.75 | Solar | 15W17 | 2016-06-23 | 2016-07-07 | 10 |  | 10 | 2016-07-22 | 2016-08-25 | 25 |  | 25 | [20 empty] | 2016-09-01 |  | 2016-07-26 | NO | Expedited | [8 empty] | 2016-11-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2199 | 1462 | 239 | Solar | 30W30 | 2016-07-25 | 2016-08-05 | 10 |  | 10 | 2016-08-05 | 2016-09-26 | 36 |  | 36 | [20 empty] | 2016-09-26 |  |  | YES | Expedited | [6 empty] | 2017-01-06 | 2017-01-06 | 2017-01-06 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2195 | 1420 | 5 | Solar | 40W40 | 2016-06-20 | 2016-07-01 | 10 |  | 10 | 2016-09-16 | 2016-10-18 | 22 |  | 22 | [20 empty] | 2016-10-01 |  | 2016-07-31 | NO | Expedited | [8 empty] | 2016-12-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2193 | 1420 | 84 | Solar | 50W56 | 2016-06-20 | 2016-07-01 | 10 |  | 10 | 2016-07-17 | 2016-07-29 | 10 |  | 10 | [20 empty] | 2016-08-02 |  | 2016-07-20 | NO | Expedited | [8 empty] | 2016-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2192 | 1420 | 8.35 | Solar | 01W02 | 2016-06-16 | 2016-07-01 | 11 | 8 | 3 | 2016-08-15 | 2016-08-29 | 11 |  | 11 | [20 empty] | 2016-09-01 |  | 2017-03-26 | NO | Expedited | [8 empty] | 2016-11-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2188 | 1462 | 18.15 | Solar | 31W38 | 2016-06-16 | 2016-06-30 | 10 |  | 10 | 2016-07-19 | 2016-08-17 | 22 |  | 22 | [20 empty] | 2016-08-18 |  | 2016-08-15 | NO | Expedited | [8 empty] | 2017-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2185 | 1420 | 4.15 | Solar | 35W36 | 2016-06-15 | 2016-06-23 | 6 |  | 6 | 2016-07-19 | 2016-08-05 | 14 |  | 14 | [20 empty] | 2016-08-05 |  | 2016-08-15 | NO | Expedited | [8 empty] | 2016-10-12 | In Operation | Res | Y
Fitchburg | Townsend | 2183 | 1469 | 6.72 | Solar | 15W16 | 2016-06-15 | 2016-06-22 | 5 |  | 5 | 2016-07-19 | 2016-08-05 | 14 |  | 14 | [20 empty] | 2016-08-05 |  | 2016-08-20 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2182 | 1462 | 9.92 | Solar | 31W37 | 2016-06-15 | 2016-06-22 | 5 | 2 | 3 | 2016-07-22 | 2016-08-19 | 21 |  | 21 | [20 empty] | 2016-08-22 |  | 2016-10-31 | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2179 | 1420 | 195 | Solar | 25W27 | 2016-06-13 | 2016-08-24 | 51 | 47 | 4 | 2016-08-25 | 2016-09-19 | 17 |  | 17 | [20 empty] | 2016-09-22 |  | 2016-09-01 | YES | Expedited | 2016-11-08 | 2016-11-10 | 2016-11-10 | 1 |  | 1 | 2017-02-17 | 2017-02-23 | 2017-02-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2178 | 1420 | 288 | Solar | 01W04 | 2016-06-13 | 2016-06-23 | 8 |  | 8 | 2016-06-24 | 2016-07-26 | 22 |  | 22 | [20 empty] | 2016-07-28 |  | 2016-09-01 | YES | Expedited | [8 empty] | 2017-06-19 | In Operation | Res | Y
Fitchburg | Ashby | 2177 | 1431 | 5.45 | Solar | 35W36 | 2016-06-13 | 2016-06-17 | 4 |  | 4 | 2016-08-05 | 2016-08-05 | 1 |  | 1 | [20 empty] | 2016-08-09 |  | 2016-08-13 | YES | Expedited | [8 empty] | 2016-11-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2175 | 1420 | 5.75 | Solar | 01W02 | 2016-06-10 | 2016-06-16 | 5 |  | 5 | 2016-07-05 | 2016-08-03 | 22 |  | 22 | [20 empty] | 2016-08-08 |  | 2016-07-14 | NO | Expedited | [8 empty] | 2016-09-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 2174 | 1420 | 6 | Solar | 20W22 | 2016-06-10 | 2016-06-16 | 5 |  | 5 | [25 empty] | 2016-09-09 |  |  | YES | Expedited | [8 empty] | 2016-09-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2173 | 1420 | 3.3 | Solar | 31W34 | 2016-06-09 | 2016-06-16 | 6 | 1 | 5 | 2016-07-30 | 2016-08-05 | 5 |  | 5 | [20 empty] | 2016-08-05 |  | 2016-08-01 | NO | Expedited | [8 empty] | 2016-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2170 | 1420 | 4.15 | Solar | 31W34 | 2016-06-07 | 2016-06-15 | 7 |  | 7 | 2016-07-06 | 2016-07-06 | 1 |  | 1 | [20 empty] | 2016-08-05 |  | 2016-08-07 | NO | Expedited | [8 empty] | 2016-11-16 | Cancelled | Res | Y
Fitchburg | Townsend | 2168 | 1469 | 7 | Solar | 15W16 | 2016-06-06 | 2016-06-13 | 6 |  | 6 | 2016-06-27 | 2016-07-28 | 23 |  | 23 | [20 empty] | 2016-07-28 |  | 2016-07-12 | NO | Expedited | [8 empty] | 2016-08-25 | In Operation | Com | Y
Fitchburg | Townsend | 2167 | 1469 | 10.5 | Solar | 15W16 | 2016-05-25 | 2016-06-09 | 12 | 1 | 11 | 2016-06-24 | 2016-06-24 | 1 |  | 1 | [20 empty] | 2016-07-28 |  | 2016-07-27 | NO | Expedited | [8 empty] | 2016-08-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2165 | 1420 | 7.5 | Solar | 20W22 | 2016-06-03 | 2016-07-06 | 22 | 6 | 16 | 2016-08-05 | 2016-08-23 | 13 |  | 13 | [20 empty] | 2016-08-25 |  | 2016-08-03 | YES | Expedited | [8 empty] | 2016-11-15 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2160 | 1420 | 5 | Solar | 40W40 | 2016-05-31 | 2016-08-25 | 61 | 55 | 6 | 2016-09-10 | 2016-09-29 | 14 |  | 14 | [20 empty] | 2016-09-29 |  | 2016-08-01 | NO | Expedited | [8 empty] | 2016-11-21 | In Operation | Res | Y
Fitchburg | Ashby | 2157 | 1431 | 10 | Solar | 39W19 | 2016-05-27 | 2016-06-09 | 10 |  | 10 | 2016-06-22 | 2016-06-22 | 1 |  | 1 | [20 empty] | 2016-06-22 |  |  | NO | Expedited | [8 empty] | 2016-11-10 | In Operation | Res | Y
Fitchburg | Ashby | 2148 | 1431 | 6.25 | Solar | 39W19 | 2016-05-24 | 2016-08-11 | 56 | 42 | 14 | 2016-08-22 | 2016-09-06 | 11 |  | 11 | [20 empty] | 2016-09-09 |  |  | NO | Expedited | [8 empty] | 2016-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2147 | 1420 | 3.5 | Solar | 31W34 | 2016-05-24 | 2016-06-06 | 10 |  | 10 | 2016-06-27 | 2016-07-28 | 23 |  | 23 | [20 empty] | 2016-07-28 |  | 2016-06-14 | NO | Expedited | [8 empty] | 2016-08-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2129 | 1462 | 12 | Solar | 31W37 | 2016-05-13 | 2016-06-01 | 13 |  | 13 | 2016-06-28 | 2016-07-28 | 22 |  | 22 | [20 empty] | 2016-07-28 |  | 2016-07-12 | NO | Expedited | [8 empty] | 2016-11-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2128 | 1420 | 3.5 | Solar | 35W36 | 2016-05-13 | 2016-06-01 | 13 |  | 13 | 2016-06-27 | 2018-06-27 | 497 |  | 497 | [20 empty] | 2016-07-28 |  | 2016-06-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2110 | 1462 | 5.5 | Solar | 31W37 | 2016-05-04 | 2016-06-02 | 21 |  | 21 | 2016-06-27 | 2016-06-27 | 1 |  | 1 | [20 empty] | 2016-07-28 |  | 2016-06-01 | NO | Expedited | [8 empty] | 2016-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2109 | 1462 | 4990 | Solar | 31W37 | 2017-02-16 | 2017-03-03 | 10 |  | 10 | [10 empty] | 2017-03-05 | 2017-03-31 | 19 | 3 | 16 | 2017-05-22 | 2017-09-08 | 77 | 32 | 45 | [5 empty] | 2017-10-28 | 2019-02-18 | 2017-12-01 | YES | Standard | [6 empty] | 2020-11-19 | 2020-11-19 | 2020-12-22 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2103 | 1420 | 4.15 | Solar | 31W37 | 2016-05-03 | 2016-05-20 | 14 |  | 14 | 2016-06-26 | 2016-07-29 | 24 |  | 24 | [20 empty] | 2016-07-29 |  | 2016-07-02 | NO | Expedited | [8 empty] | 2016-11-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2098 | 1420 | 6 | Solar | 25W27 | 2016-04-28 | 2016-06-08 | 29 |  | 29 | 2016-06-29 | 2016-07-28 | 21 |  | 21 | [20 empty] | 2016-07-28 |  | 2016-06-27 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Comm | Y
Fitchburg | Ashby | 2061 | 1431 | 8 | Solar | 39W19 | 2016-04-12 | 2016-07-28 | 74 | 52 | 22 | 2016-08-19 | 2018-09-14 | 514 |  | 514 | [20 empty] | 2016-09-16 |  |  | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2032 | 1420 | 22.5 | Solar | 11W11 | 2016-04-05 | 2016-04-08 | 4 |  | 4 | 2016-04-09 | 2016-04-12 | 2 |  | 2 | [20 empty] | 2016-04-13 |  |  | YES | Expedited | [6 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | In Operation | Res | Y
Fitchburg | Ashby | 2007 | 1431 | 3.25 | Solar | 39W19 | 2016-03-22 | 2016-08-16 | 102 |  | 102 | 2016-08-20 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-09-05 | NO | Expedited | [8 empty] | 2016-11-16 | In Operation | Res | Y
Fitchburg | Ashby | 2000 | 1431 | 8.75 | Solar | 39W19 | 2016-03-24 | 2016-08-10 | 96 |  | 96 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-08-31 | YES | Expedited | [8 empty] | 2016-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 1984 | 1469 | 10 | Solar | 15W16 | 2016-03-14 | 2016-03-17 | 3 |  | 3 | 2016-12-09 | 2016-12-27 | 13 |  | 13 | [20 empty] | 2016-03-18 |  | 2016-12-25 | NO | Expedited | [8 empty] | 2017-09-18 | In Operation | Res | Y
Fitchburg | Ashby | 1961 | 1431 | 2 | Solar | 39W19 | 2016-08-22 | 2016-08-24 | 3 | 96 | -93 | 2016-08-23 | 2016-09-07 | 11 | 6 | 5 | [20 empty] | 2016-09-09 |  |  | NO | Expedited | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-23 | Cancelled | Res | Y
Fitchburg | Townsend | 1938 | 1469 | 20.5 | Solar | 15W16 | 2016-03-01 | 2016-03-09 | 7 |  | 7 | 2016-03-10 | 2016-03-15 | 4 |  | 4 | [20 empty] | 2016-03-18 |  | 2016-03-29 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 1665 | 1420 | 200 | Solar | 50W56 | 2015-12-16 | 2015-12-29 | 9 |  | 9 | 2015-12-30 | 2016-01-26 | 18 |  | 18 | [20 empty] | 2016-01-26 |  | 2016-02-15 | YES | Expedited | [6 empty] | 2016-06-21 | 2016-07-05 | 2016-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 1540 | 1420 | 488 | Solar | 50W56 | 2015-11-16 | 2016-02-23 | 67 |  | 67 | [25 empty] | 2016-04-06 |  | 2016-01-05 | YES | Standard | [8 empty] | 2017-06-08 | In Operation |  | Y
Fitchburg | Townsend | 1531 | 1453 | 750 | Solar | 39W18 | 2016-05-02 | 2017-01-04 | 171 | 42 | 129 | [25 empty] | 2017-06-08 |  | 2017-09-01 | YES | Standard | [9 empty] | Cancelled | comm
Fitchburg | Fitchburg | 1464 | 1420 | 151.2 | Solar | 01W02 | 2016-03-18 | 2016-04-12 | 18 | 2 | 16 | [14 empty] | 0 | 2016-05-04 | 2016-07-20 | 53 |  | 53 | [5 empty] | 2016-07-22 |  |  | NO | Standard | [8 empty] | 2017-11-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 1320 | 1462 | 20.35 | Solar | 39W18 | 2015-09-18 | 2015-10-07 | 14 | 3 | 11 | 2015-10-07 | 2015-10-29 | 16 |  | 16 | [20 empty] | 2015-12-03 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 1314 | 1462 | 21 | Solar | 31W38 | 2015-10-09 | 2015-10-22 | 9 |  | 9 | [25 empty] | 2015-11-17 |  | 2015-11-01 | NO | Expedited | [8 empty] | 2016-02-01 | In Operation | Res | Y
Fitchburg | Townsend | 1239 | 1469 | 360 | Solar | 39W18 | 2016-03-21 | 2016-05-16 | 40 |  | 40 | 2016-05-16 | 2016-05-18 | 3 |  | 3 | [22 empty] | 06/31/2016 | NO | Expedited | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 1235 | 1420 | 19.3 | Solar | 40W40 | 2015-08-13 | 2015-08-31 | 13 |  | 13 | [15 empty] | 2015-10-02 | 2015-10-08 | 5 |  | 5 | [5 empty] | 2015-10-02 |  | 2015-10-13 | NO | Expedited | [8 empty] | 2016-03-21 | In Operation | Res | Y
Fitchburg | Ashby | 1219 | 1431 | 18 | Solar | 39W19 | 2015-08-19 | 2015-09-03 | 12 |  | 12 | 2015-09-04 | 2015-09-23 | 13 |  | 13 | [20 empty] | 2015-09-30 |  | 2015-10-13 | YES | Expedited |  | 2015-12-01 | 2015-12-01 | 1 |  | 1 | 2016-04-20 | 2016-04-20 | 2016-04-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 1218 | 1420 | 42 | Solar | 40W39 | 2015-08-14 | 2015-09-03 | 15 |  | 15 | [15 empty] | 2015-09-30 | 2015-10-09 | 8 |  | 8 | [5 empty] | 2015-10-14 |  | 2015-10-01 | NO | Expedited | [6 empty] | 2015-12-21 | 2015-12-21 | 2015-12-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 1206 | 1420 | 45 | Solar | 40W40 | 2015-08-19 | 2015-09-03 | 12 |  | 12 | 2015-09-04 | 2015-09-23 | 13 |  | 13 | [20 empty] | 2015-09-30 |  | 2015-11-30 | YES | Expedited |  | 2015-11-02 | 2015-12-04 | 23 |  | 23 | 2015-12-30 | 2015-12-30 | 2015-12-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 1192 | 1420 | 16.95 | Solar | 25W27 | 2015-08-13 | 2015-08-28 | 12 |  | 12 | 2018-08-29 | 2018-08-29 | 1 |  | 1 | [10 empty] | 2015-10-02 | 2015-11-24 | 36 |  | 36 | [5 empty] | 2015-10-02 |  |  | YES | Expedited | [8 empty] | 2016-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 1191 | 1420 | 720 | Solar | 31W37 | 2015-08-05 | 2015-10-08 | 46 | 27 | 19 | 2015-10-08 | 2015-10-08 | 1 |  | 1 | [22 empty] | 2015-10-31 | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 1126 | 1420 | 500 | Solar | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1125 | 1420 | 500 | Solar | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1124 | 1420 | 500 | Solar | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1123 | 1420 | 500 | Solar | 50W56 | 2016-01-21 | 2016-03-31 | 49 | 29 | 20 | 2016-03-31 | 2016-05-05 | 25 |  | 25 | [10 empty] | 2016-04-15 | 2016-05-31 | 31 |  | 31 | [7 empty] | 2016-09-14 | NO | Expedited | [9 empty] | Cancelled | Comm | Y
Fitchburg | Ashby | 964 | 1431 | 414 | Solar | 39W19 | 2015-05-11 | 2015-06-24 | 31 | 22 | 9 | 2015-06-24 | 2015-07-23 | 22 |  | 22 | [22 empty] | 2015-08-01 | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 952 | 1420 | 400 | Solar | 01W01 | 2015-05-12 | 2015-05-21 | 8 |  | 8 | [14 empty] | 0 | 2015-05-26 | 2015-06-05 | 9 |  | 9 | [5 empty] | 2015-12-04 |  | 2015-09-15 | NO | Standard | [8 empty] | 2015-12-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 932 | 1462 | 15.2 | Solar | 31W38 | 2015-04-20 | 2015-05-06 | 12 | 2 | 10 | [5 empty] | 2015-05-19 | 2015-06-15 | 19 |  | 19 | [5 empty] | 2015-06-15 | 2015-06-23 | 6 |  | 6 | [5 empty] | 2015-06-15 |  | 2015-06-30 | NO | Expedited | [8 empty] | 2015-09-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 895 | 1420 | 4608 | Solar | 20H22 | 2015-03-26 | 2015-04-09 | 11 |  | 11 | 2015-04-09 | 2015-04-09 | 1 |  | 1 | [22 empty] | 2015-08-01 | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 894 | 1420 | 480 | Solar | 20H22 | 2015-03-26 | 2015-04-09 | 11 |  | 11 | 2015-04-09 | 2015-04-24 | 11 |  | 11 | [10 empty] | 2015-06-04 | 2015-08-28 | 61 |  | 61 | [8 empty] | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 850 | 1420 | 984 | Solar | 35W36 | 2015-02-06 | 2015-03-17 | 26 | 19 | 7 | [10 empty] | 2015-03-19 | 2015-04-15 | 20 |  | 20 | 2015-05-21 | 2015-10-02 | 94 |  | 94 | 2016-02-22 | 2016-04-28 | 47 |  | 47 | 2016-06-03 | 2017-06-14 |  | YES | Standard |  | 2017-06-15 | 2018-06-04 | 239 | 120 | 119 | 2018-06-07 | 2018-06-07 | 2018-07-18 | In Operation | Comm | Y
Fitchburg | Fitchburg | 849 | 1420 | 864 | Solar | 35W36 | 2015-02-06 | 2015-03-01 | 15 | 15 | 0 | [10 empty] | 2015-03-08 | 2015-04-15 | 27 |  | 27 | 2015-05-21 | 2015-10-02 | 94 |  | 94 | 2016-02-22 | 2016-04-28 | 47 |  | 47 | 2016-06-03 | 2017-06-14 |  | YES | Standard |  | 2017-06-15 | 2018-06-04 | 239 | 120 | 119 | 2018-06-07 | 2018-06-07 | 2018-07-18 | In Operation | Comm | Y
Fitchburg | Lunenburg | 843 | 1462 | 2000 | Solar | 30W30 | 2015-03-19 | 2015-04-20 | 22 | 6 | 16 | 2015-04-20 | 2015-04-28 | 6 |  | 6 | [23 empty] | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Ashby | 841 | 1431 | 997.6 | Solar | 39W19 | 2015-01-27 | 2015-03-16 | 34 | 25 | 9 | 2015-03-16 | 2015-04-14 | 21 |  | 21 | [22 empty] | 2015-08-01 | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 808 | 1420 | 540 | Solar | 40W40 | 2015-05-11 | 2015-05-26 | 11 |  | 11 | [10 empty] | 2015-06-16 | 2015-07-13 | 19 | 4 | 15 | 2015-07-27 | 2015-10-06 | 51 |  | 51 | 2015-11-25 | 2016-01-08 | 30 |  | 30 | 2016-02-08 |  | 2015-09-01 | NO | Standard | [8 empty] | 2017-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 755 | 1462 | 170 | Solar | 31W37 | 2014-12-05 | 2014-12-17 | 9 |  | 9 | [5 empty] | 2015-02-12 | 2015-03-05 | 15 |  | 15 | [5 empty] | 2015-04-09 | 2015-05-12 | 23 |  | 23 | [5 empty] | 2015-03-31 |  | 2015-03-30 | NO | Standard | [6 empty] | 2015-12-04 | 2015-12-04 | 2015-12-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 750 | 1420 | 72 | Solar | 40W40 | 2014-12-03 | 2014-12-05 | 3 |  | 3 | 2014-12-05 | 2014-12-10 | 4 |  | 4 | [20 empty] | 2014-12-12 |  | 2015-01-31 | YES | Expedited | [6 empty] | 2015-03-11 | 2015-03-11 | 2015-03-11 | In Operation | Res | Y
Fitchburg | Ashby | 501 | 1431 | 1848 | Solar | 39W19 | 2014-12-15 | 2015-04-13 | 81 | 79 | 2 | [10 empty] | 2015-04-15 | 2015-04-22 | 5 |  | 5 | 2015-05-01 | 2015-09-04 | 89 | 5 | 84 | 2015-12-22 | 2016-02-08 | 32 |  | 32 | 2015-10-28 |  | 2015-06-01 | YES | Standard | 2017-11-08 | 2017-03-15 | 2017-10-04 | 141 |  | 141 |  |  | 2017-12-06 | In Operation | Comm | Y
Fitchburg | Townsend | 452 | 1420 | 17 | Solar | 15W16 | 2014-05-22 | 2014-06-23 | 21 | 10 | 11 | [14 empty] | 0 | [10 empty] | 2014-06-23 |  | 2014-07-19 | NO | Standard | [6 empty] | 2014-12-18 | 2014-12-18 | 2014-12-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 413 | 1462 | 72 | Solar | 30W30 | 2014-04-17 | 2014-04-24 | 5 | 1 | 4 | 2014-04-25 | 2014-05-19 | 17 |  | 17 | [20 empty] | 2014-05-20 |  | 2014-06-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 395 | 1469 | 36.765 | Solar | 15W16 | 2014-02-03 | 2014-02-07 | 5 |  | 5 | [14 empty] | 0 | 2014-04-30 | 2014-05-05 | 4 |  | 4 | [5 empty] | 2014-05-06 |  | 2014-02-17 | NO | Standard | [8 empty] | 2014-06-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 374 | 1462 | 72 | Solar | 30W30 | 2013-10-28 | 2013-11-01 | 5 |  | 5 | 2013-11-05 | 2013-12-02 | 18 |  | 18 | [20 empty] | 2013-12-10 |  | 2014-06-01 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 268 | 1462 | 300 | Solar | 31W37 | 2012-08-21 | 2012-09-03 | 9 |  | 9 | [14 empty] | 0 | [10 empty] | 2012-11-05 |  | 2012-11-01 | NO | Standard | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 258 | 1420 | 71.4 | Gas | 22W1 | 2012-07-13 | 2012-08-13 | 22 |  | 22 | [5 empty] | 2012-12-10 | 2013-03-04 | 57 |  | 57 |  |  |  |  | 0 | [10 empty] | 2013-04-11 |  | 2012-05-02 | NO | Standard | [8 empty] | 2014-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 238 | 1420 | 155 | Solar | 40W42 | 2012-05-17 | 2012-08-08 | 58 | 48 | 10 | [5 empty] | 2012-10-01 | 2012-11-26 | 39 |  | 39 |  |  |  |  | 0 | [10 empty] | 2012-11-26 |  | 2012-08-01 | NO | Standard | [6 empty] | 2013-01-08 | 2013-01-11 | 2013-01-11 | In Operation | Res | Y
Fitchburg | West Townsend | 230 | 1474 | 10 | Solar | 39W18 | 2012-04-11 | 2012-04-19 | 6 |  | 6 | [14 empty] | 0 | [10 empty] | 2012-05-22 |  | 2012-07-30 | NO | Standard | [6 empty] | 2012-07-18 | 2012-07-18 | 2012-07-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 206 | 1420 | 675 | Solar | 40W39 | 2012-03-29 | 2012-04-13 | 12 |  | 12 | [10 empty] | 2012-04-15 | 2012-04-27 | 9 |  | 9 | [5 empty] | 2012-05-08 | 2012-07-24 | 54 |  | 54 | 2012-10-25 |  | 2012-06-01 | YES | Standard |  | 2012-11-20 | 2013-05-31 | 132 |  | 132 | 2013-05-31 | 2013-05-31 | 2013-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 186 | 1420 | 190 | Solar | 22W1 | 2011-10-21 | 2011-11-01 | 8 |  | 8 | [14 empty] | 0 | [10 empty] | 2012-01-17 |  | 2011-12-01 | NO | Standard | [8 empty] | 2012-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 179 | 1420 | 2000 | Solar | 35W36 | 2011-08-26 | 2011-10-11 | 33 |  | 33 | [14 empty] | 0 | 2011-11-09 | 2012-11-01 | 250 | 210 | 40 | [7 empty] | 2012-07-01 | YES | Standard | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 178 | 1462 | 1000 | Solar | 31W38 | 2011-08-26 | 2011-09-26 | 22 |  | 22 | [10 empty] | 2011-10-12 | 2011-10-30 | 13 |  | 13 | 2011-11-09 | 2012-11-01 | 250 | 210 | 40 | [5 empty] | 2012-10-04 |  | 2012-07-01 | YES | Standard | [8 empty] | 2014-07-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 174 | 1462 | 2500 | Solar | 0 | 2011-07-28 | 2011-08-17 | 15 |  | 15 | [10 empty] | 2011-08-02 | 2011-10-18 | 56 | 28 | 28 | 2012-01-11 | 2012-05-02 | 78 | 9 | 69 | [7 empty] | 2012-03-01 | YES | Standard | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 173 | 1462 | 2500 | Solar | 30W31 | 2011-07-28 | 2011-08-17 | 15 |  | 15 | [10 empty] | 2011-08-02 | 2011-10-18 | 56 |  | 56 | 2012-01-11 | 2012-05-02 | 78 |  | 78 | [5 empty] | 2013-06-28 |  | 2013-06-28 | YES | Standard | [6 empty] | 2014-07-21 | 2014-07-21 | 2014-07-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 169 | 1852 | 1500 | Solar | 40W40 | 2011-07-28 | 2011-08-10 | 10 |  | 10 | [5 empty] | 2011-09-16 | 2011-10-13 | 20 |  | 20 |  |  |  |  | 0 | 2011-10-25 | 2012-01-22 | 63 | 45 | 18 | [7 empty] | 2011-12-31 | YES | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 139 | 1420 | 1800 | Gas | 40W38 | 2011-02-10 | 2011-04-19 | 49 | 41 | 8 | [14 empty] | 0 | 2011-06-01 | 2011-10-28 | 108 | 88 | 20 | [5 empty] | 2011-11-01 |  |  | YES | Standard | [8 empty] | 2012-04-13 | Not In Service | Res