## Sheet1
DG Interconnection Tracking and Reporting Template
Utility Timelines
Reporting Period: |  |  | from | 2025-10-01 | to | 2025-10-31
Date Filed: |  |  | 2025-11-12
Force Majeure Reporting |  |  |  | Start Date | End Date | Explanation
Enter Dates (inclusive) of Force Majeure Events with "Clock" Stoppage |  |  | Event #1
|  |  | Event #2 | [37 empty] | * added Complex
Event #3
Event #4
Total Workdays (calculated)
Application and Site Information | [6 empty] | Application Receipt |  |  |  |  | Screen Review |  |  |  |  | Supplemental Review |  |  |  |  | Standard Process Initial Review |  |  |  |  | Impact Study |  |  |  |  | Detailed Study |  |  |  |  | IA and Pre-Construction Information | [5 empty] | Construction |  |  |  |  | Witness Test |  | Authorization and Misc Information |  |  |  | Group Study Info
Company Name | City/Town | Facility ID (if any) | ZIP Code | Design Capacity (kW) | Fuel Type (Solar, Wind, etc) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Study Begun | Date Review of Screens Study Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/ Standard / Complex Project | Construction Timeline Commitment (Workdays) | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Status | Private/Gov't | Net Metered? (Y/N) | Impact_Group_Study_Name | Group_Name | ASO_Group_Name | Group_Study_Project_Status | Limiting Export Max Size kW | Substation_Name
WMECO | Springfield | 6S21-2009 | 1105 | 75 | Solar | 8C14 | 2009-03-30 | 2009-04-13 | 11 |  | 11 | [25 empty] | 2009-04-24 |  | 07/2009 | No | Expedited | [8 empty] | 2009-07-23 | Online
WMECO | Savoy | 6B44-2009 | 1256 | 10000 | Wind | 18C1 | 2009-06-26 | [31 empty] | 2010-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A82-2009 | 1002 | 39 | Solar | 17K2 | 2009-06-29 | 2009-07-24 | 20 |  | 20 | [25 empty] | 2009-07-30 |  | 08/2009 | No | Expedited | [8 empty] | 2009-08-10 | Online
WMECO | Leverett | 6A91-2009 | 1054 | 13.8 | Solar | 18G7 | 2009-07-28 | 2009-09-14 | 35 |  | 35 | [25 empty] | 2009-09-17 |  | 08/2009 or 09/2009 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B46-2009 | 1201 | 86 | Solar | 15E3 | 2009-07-29 | 2009-09-29 | 45 |  | 45 | [25 empty] | 2009-09-30 |  | 11/2009 | No | Expedited | [8 empty] | 2010-01-14 | Online
WMECO | Pittsfield | 6B47-2009 | 1201 | 95 | Solar | 19A5 | 2009-07-29 | 2009-09-15 | 35 |  | 35 | [25 empty] | 2009-09-16 |  | 11/2009 | No | Expedited | [8 empty] | 2009-11-10 | Online
WMECO | Lee | 6B55-2009 | 1238 | 125 | Solar | 16B5 | 2009-11-05 | [31 empty] | 2009-11-15 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S34-2009 | 1104 | 50 | Solar | 5J13 | 2009-11-13 | [31 empty] | 2009-11-15 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B59-2009 | 1201 | 126.9 | Solar | 19A2 | 2009-12-01 | [31 empty] | 2009-12-31 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S35-2009 | 1105 | 30 | Solar | 8C26 | 2009-12-01 | 2009-12-30 | 22 |  | 22 | [25 empty] | 2010-01-11 |  | 2009-12-30 | No | Expedited | [8 empty] | 2010-02-12 | Online
WMECO | Lee | 6B60-2009 | 1238 | 125 | Solar | 16B5 | 2009-12-09 | 2009-12-16 | 6 |  | 6 | [25 empty] | 2009-12-24 |  | 2009-12-31 | No | Expedited | [8 empty] | 2009-12-30 | Online
WMECO | Springfield | 6S36-2009 | 1111 | 87 | Solar | 5J14 | 2009-12-24 | 2010-01-29 | 27 |  | 27 | [25 empty] | 2010-02-08 |  | 2010-03-26 | No | Expedited | [8 empty] | 2010-08-11 | Online
WMECO | Hancock | 6B62-2009 | 1237 | 81.2 | Solar | 30B7 | 2009-12-28 | [31 empty] | 2009-12-31 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S37-2009 | 1104 | 95 | Solar | 5J14 | 2009-12-28 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A104-2009 | 1002 | 2000 | Natural Gas / Fuel Oil | 18G2 | 2009-12-30 | 2010-02-17 | 36 |  | 36 | [15 empty] | 2010-07-19 |  | -28841 | [7 empty] | 2011-02-22 |  | 09/2010 | Yes | Standard | [8 empty] | 2011-03-01 | Online
WMECO | Springfield | 6S38-2010 | 1104 | 38.07 | Solar | 5J13 | 2010-01-05 | 2010-01-29 | 19 |  | 19 | [25 empty] | 2010-02-02 |  | 2010-01-15 | No | Expedited | [8 empty] | 2010-02-19 | Online
WMECO | Hancock | 6B63-2010 | 1237 | 81.2 | Solar | 30B7 | 2010-01-12 | 2010-02-08 | 20 |  | 20 | [25 empty] | 2010-02-19 |  | 2009-12-31 | No | Expedited | [8 empty] | 2010-03-09 | Online
WMECO | Pittsfield | 6B64-2010 | 1201 | 126.91 | Solar | 19A2 | 2010-01-12 | 2010-01-28 | 13 |  | 13 | [25 empty] | 2010-02-09 |  | 2009-12-31 | No | Expedited | [8 empty] | 2010-02-25 | Online
WMECO | Springfield | 6S39-2010 | 1104 | 95 | Solar | 5J14 | 2010-02-03 | 2010-03-05 | 23 |  | 23 | [25 empty] | 2010-04-05 |  | 2010-03-15 | No | Expedited | [8 empty] | 2010-10-13 | Online
WMECO | Leverett | 6A107-2010 | 1054 | 13.795 | Solar | 18G7 | 2010-02-05 | 2010-02-11 | 5 |  | 5 | [25 empty] | 2010-02-12 |  | 2010-02-01 | Yes | Expedited | [8 empty] | 2010-02-18 | Online
WMECO | Amherst | 6A110-2010 | 1002 | 14.7 | Solar | 17K3 | 2010-04-01 | 2010-04-12 | 8 |  | 8 | [25 empty] | 2010-05-18 |  | 5/2010 | Yes | Expedited | [8 empty] | 2010-06-23 | Online
WMECO | Shelburne | 6F155-2010 | 1370 | 24.2 | Solar | 22B5 | 2010-04-06 | 2010-04-22 | 13 |  | 13 | [25 empty] | 2010-04-27 |  | 5/2010 | Yes | Expedited | [8 empty] | 2010-05-21 | Online
WMECO | Whately | 6AF157-2010 | 1093 | 20 | Solar | 18G8 | 2010-04-21 | [31 empty] | 7/2010 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Northfield | 6F158-2010 | 1360 | 65.4 | Solar | 21B8 | 2010-04-21 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Whately | 6AF160-2010 | 1093 | 15.6 | Solar | 18G8 | 2010-06-01 | 2010-06-18 | 14 |  | 14 | [25 empty] | 2010-06-28 |  | 7/2010 | Yes | Expedited | [8 empty] | 2010-07-09 | Online
WMECO | Pittsfield | 6B71-2010 | 1201 | 36 | Solar | 30B4 | 2010-06-01 | 2010-08-23 | 60 |  | 60 | [25 empty] | 2010-10-04 |  | 2010-09-13 | No | Expedited | [8 empty] | 2010-12-22 | Online
WMECO | Greenfield | 6F161-2010 | 1301 | 2000 | Solar | 22B3 | 2010-06-03 | 2011-01-05 | 154 |  | 154 | [15 empty] | 2010-07-20 | 2011-01-28 | 138 |  | 138 | [5 empty] | 2011-01-28 |  | 2011-03-04 | Yes | Standard | [8 empty] | 2012-06-20 | Online
WMECO | Pittsfield | 6B72-2010 | 1201 | 1800 | Solar | 30B3 | 2010-06-11 | [31 empty] | 11/2010 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B74-2010 | 1201 | 1800 | Solar | 30B2 | 2010-06-24 | [31 empty] | 11/2010 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B75-2010 | 1201 | 62 | Hydro | 19A7 | 2010-07-01 | 2011-02-14 | 162 |  | 162 | [15 empty] | 2010-09-30 |  | -28894 | [7 empty] | 2011-04-07 |  | 2010-11-15 | No | Standard | [8 empty] | 2011-06-16 | Online
WMECO | Pittsfield | 6B77-2010 | 1201 | 1500 | Solar | 30B3 | 2010-07-30 | 2011-02-02 | 133 |  | 133 | [15 empty] | 2010-08-20 |  | -28865 | [7 empty] | 2011-03-24 |  | 2010-12-10 | Yes | Standard | [7 empty] | 2012-02-01 | 2012-02-01 | Online
WMECO | Greenfield | 6F171-2010 | 1301 | 50 | Solar | 22B7 | 2010-08-03 | 2011-01-11 | 115 |  | 115 | [25 empty] | 2011-01-12 |  | 2010-10-20 | No | Expedited | [8 empty] | 2011-02-10 | Online
WMECO | Springfield | 6S46-2010 | 1118 | 26.4 | Solar | 22H16 | 2010-08-03 | 2010-09-18 | 34 |  | 34 | [25 empty] | 2010-10-20 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-11-03 | Online
WMECO | Hadley | 6A134-2010 | 1035 | 30.3 | Solar | 17K5 | 2010-08-20 | 2010-09-03 | 11 |  | 11 | [25 empty] | 2010-09-21 |  | 2010-09-20 | Yes | Expedited | [8 empty] | 2010-11-10 | Online
WMECO | Amherst | 6A136-2010 | 1002 | 39.6 | Solar | 19B15 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-01 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-10-15 | Online
WMECO | Deerfield | 6F175-2010 | 1343 | 50 | Solar | 22B3 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-26 |  | 2010-09-01 | No | Expedited | [8 empty] | 2010-12-17 | Online
WMECO | Lee | 6B78S-2010 | 1238 | 30 | Solar | 17G3 | 2010-09-17 | 2011-03-01 | 117 |  | 117 | [25 empty] | 2011-06-01 |  | 2010-10-01 | Yes | Expedited | [8 empty] | 2011-12-01 | Online
WMECO | Hadley | 6A138-2010 | 1035 | 25.5 | Solar | 18G5 | 2010-09-21 | 2010-10-22 | 24 |  | 24 | [25 empty] | 2010-11-30 |  | 2010-11-01 | Yes | Expedited | [8 empty] | 2011-02-23 | Online
WMECO | Ashfield | 6F192-2010 | 1330 | 41.385 | Solar | 38A1 | 2010-12-03 | 2011-01-28 | 41 |  | 41 | [25 empty] | 2011-01-28 |  | 2010-01-01 | Yes | Expedited | [8 empty] | 2011-04-19 | Online
WMECO | West Springfield | 6S52-2010 | 1089 | 50 | Solar | 16C14 | 2010-12-07 | 2011-01-25 | 36 |  | 36 | [25 empty] | 2011-03-02 |  | 2011-02-01 | No | Expedited | [8 empty] | 2011-03-29 | Online
WMECO | Pittsfield | 6B82-2010 | 1201 | 195 | Digester Gas | 30B3 | 2010-12-09 | 2011-08-18 | 181 |  | 181 | [25 empty] | 2011-09-27 |  | 2011-01-01 | No | Standard | [8 empty] | 2012-02-10 | Online
WMECO | Pittsfield | 6B86-2010 | 1201 | 387.2 | Solar | 30B7 | 2010-12-15 | 2011-06-17 | 133 |  | 133 | [25 empty] | 2011-06-17 |  | 2011-01-01 | No | Expedited | [8 empty] | 2011-07-27 | Online
WMECO | Hadley | 6A149-2011 | 1035 | 450 | Biogas | 19B15 | 2011-01-04 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Greenfield | 6F194-2011 | 1301 | 83 | Solar | 22B7 | 2011-01-04 | 2011-07-08 | 134 |  | 134 | [25 empty] | 2011-12-13 |  | 2011-03-01 | No | Expedited | [8 empty] | 2012-02-06 | Online
WMECO | Deerfield | 6F195-2011 | 1342 | 450 | Biogas | 22B1 | 2011-01-04 | [31 empty] | 2011-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Easthampton | 6A151-2011 | 1027 | 2000 | Solar | 15A3 | 2011-01-27 | 2011-03-16 | 35 |  | 35 | [15 empty] | 2011-03-21 | 2011-06-29 | 73 |  | 73 | 2011-07-06 |  | -29092 |  |  | 2011-10-21 |  | 2011-11-19 | Yes | Standard | [8 empty] | 2012-06-01 | Online
WMECO | Hadley | 6A156-2011 | 1035 | 450 | Biogas | 19B15 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B92-2011 | 1201 | 2000 | Solar | 19A3 | 2011-02-23 | [19 empty] | 2011-05-26 |  | -29063 | [9 empty] | 2011-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Deerfield | 6F201-2011 | 1373 | 450 | Biogas | 22B1 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Sandisfield | 6B93-2011 | 1255 | 14 | Solar | 19J4 | 2011-03-03 | 2011-03-28 | 18 |  | 18 | [25 empty] | 2011-04-27 |  | 2011-06-01 | No | Expedited | [8 empty] | 2011-12-05 | Online
WMECO | Greenfield | 6F203-2011 | 1301 | 100 | Solar | 22B4 | 2011-03-04 | 2011-12-07 | 199 |  | 199 | [25 empty] | 2012-03-26 |  | 2011-07-01 | No | Expedited | [8 empty] | 2012-05-07 | Online
WMECO | Springfield | 6S56-2011 | 1107 | 120.4 | Solar | 21S7 | 2011-03-17 | 2012-01-06 | 211 |  | 211 | [25 empty] | 2012-01-30 |  | 2011-05-01 | No | Standard | [8 empty] | 2012-03-12 | Online
WMECO | Westfield | 6A164-2011 | 1085 | 250 | Solar | 19J2 | 2011-04-07 | [31 empty] | 2011-07-31 | TBD | Standard | [9 empty] | Withdrawn
WMECO | Northfield | 6F215-2011 | 1360 | 2000 | Solar | 21B8 | 2011-04-07 | 2011-08-18 | 96 |  | 96 | [15 empty] | 2011-07-13 | 2011-12-13 | 110 |  | 110 | 2011-11-28 |  | -29195 |  |  | 2012-02-07 |  | 2011-08-01 | Yes | Standard | [8 empty] | 2012-03-30 | Online
WMECO | Agawam | 6S57-2011 | 1001 | 1500 | Solar | 30A6 | 2011-04-19 | 2011-05-26 | 28 |  | 28 | [15 empty] | 2011-06-09 | 2011-10-21 | 97 |  | 97 | 2011-11-14 |  | -29185 |  |  | 2012-04-27 |  | 2011-09-01 | Yes | Standard | [6 empty] | 2013-03-11 | 2013-03-13 | 2013-03-13 | Online
WMECO | Westfield | 6A168-2011 | 1085 | 1000 | Solar | 19J2 | 2011-05-17 | 2011-07-20 | 47 |  | 47 | [27 empty] | 2011-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A170-2011 | 1373 | 1500 | Solar | 18G8 | 2011-05-19 | 2011-07-21 | 46 |  | 46 | [15 empty] | 2011-07-08 | 2011-12-28 | 124 |  | 124 | 2011-12-21 |  | -29212 |  |  | 2012-04-03 |  | 2011-09-01 | Yes | Standard | [6 empty] | 2013-01-29 | 2013-02-01 | 2013-03-11 | Online
WMECO | Greenfield | 6F230-2011 | 1301 | 34.2 | Solar | 22B4 | 2011-06-14 | [31 empty] | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Dalton | 6B105-2011 | 1226 | 224 | Steam | 19A6 | 2011-06-20 | 2012-01-11 | 147 |  | 147 | [15 empty] | 2011-10-20 |  | -29168 | [7 empty] | 2012-01-11 |  | 2011-11-11 | No | Standard | [8 empty] | 2012-01-24 | Online
WMECO | Dalton | 6B106-2011 | 1226 | 250 | Hydro | 19A6 | 2011-06-20 | 2012-05-29 | 242 |  | 242 | [15 empty] | 2012-07-16 | 2012-12-19 | 108 |  | 108 | [5 empty] | 2013-04-30 |  | 2012-04-01 | Yes | Standard | [6 empty] | 2013-09-27 | 2013-10-03 | 2013-10-03 | Online
WMECO | Greenfield | 6F235-2011 | 1301 | 34.2 | Solar | 22B4 | 2011-06-24 | 2011-07-15 | 16 |  | 16 | [25 empty] | 2011-07-20 |  | 2011-07-21 | No | Expedited | [8 empty] | 2011-08-05 | Online
WMECO | Agawam | 6S60-2011 | 1001 | 1500 | Solar | 16C16 | 2011-07-07 | 2011-08-03 | 20 |  | 20 | [15 empty] | 2011-09-01 | 2011-12-29 | 86 |  | 86 | 2011-12-21 |  | -29212 |  |  | 2012-04-13 |  | 2011-12-01 | Yes | Standard | [6 empty] | 2013-02-06 | 2013-02-22 | 2013-03-11 | Online
WMECO | Chesterfield | 6F243-2011 | 1012 | 12 | Solar | 18K3 | 2011-07-25 | 2011-08-22 | 21 |  | 21 | [25 empty] | 2011-08-23 |  | 2011-08-01 | No | Expedited | [8 empty] | 2011-09-15 | Online
WMECO | Amherst | 6A183-2011 | 1002 | 60 | Solar | 19B16 | 2011-07-28 | 2011-09-22 | 41 |  | 41 | [25 empty] | 2011-10-17 |  | 2011-11-01 | No | Expedited | [8 empty] | 2011-11-18 | Online
WMECO | Conway | 6F248-2011 | 1341 | 22.8 | Solar | 38A1 | 2011-08-12 | 2011-10-26 | 54 |  | 54 | [25 empty] | 2011-11-17 |  | 2011-09-10 | Yes | Expedited | [8 empty] | 2012-02-27 | Online
WMECO | Whately | 6F251-2011 | 1373 | 100 | Solar | 18G8 | 2011-08-18 | 2011-10-13 | 41 |  | 41 | [25 empty] | 2011-10-18 |  | not supplied | No | Expedited | [8 empty] | 2011-12-28 | Online
WMECO | Hadley | 6A196-2011 | 1035 | 95 | Solar | 18G4 | 2011-09-01 | 2011-10-25 | 39 |  | 39 | [25 empty] | 2011-11-30 |  | 2011-11-01 | Yes | Expedited | [8 empty] | 2012-03-30 | Online
WMECO | Pittsfield | 6B111-2011 | 1201 | 300 | Solar | 30B4 | 2011-09-02 | 2011-10-05 | 24 |  | 24 | [25 empty] | 2012-02-07 |  | 2011-10-01 | No | Expedited | [8 empty] | 2012-06-01 | Online
WMECO | Springfield | 6S68-2011 | 1111 | 208 | Solar | 5J14 | 2011-09-12 | 2011-11-17 | 49 |  | 49 | [25 empty] | 2011-11-30 |  | 2011-10-15 | No | Expedited | [8 empty] | 2012-01-24 | Online
WMECO | Deerfield | 6F264-2011 | 1342 | 30 | Solar | 22B7 | 2011-09-16 | 2011-10-19 | 24 |  | 24 | [25 empty] | 2011-11-07 |  | 2011-10-31 | No | Expedited | [8 empty] | 2012-02-03 | Online
WMECO | Hadley | 6A209-2011 | 1035 | 300 | Biogas | 19B15 | 2011-09-21 | 2013-10-18 | 522 |  | 522 | 2013-10-21 |  | -29669 | [22 empty] | 2013-12-19 |  | 2012-04-01 | Yes | Standard | [8 empty] | 2013-12-31 | Online
WMECO | Deerfield | 6F265-2011 | 1372 | 600 | Biogas | 22B1 | 2011-09-21 | [31 empty] | 2012-04-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B116-2011 | 1238 | 295 | Solar | 16B5 | 2011-10-21 | [31 empty] | Q2 2012 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Colrain | 6F274-2011 | 1340 | 15.36 | Solar | 29R2 | 2011-10-24 | 2012-01-12 | 58 |  | 58 | [25 empty] | 2012-02-07 |  | 2011-11-30 | Yes | Expedited | [8 empty] | 2012-05-23 | Online
WMECO | Whately | 6A225-2011 | 1093 | 260 | Solar | 18G8 | 2011-11-07 | [31 empty] | 2012-03-16 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A228-2011 | 1035 | 17.995 | Solar | 18G5 | 2011-11-09 | 2011-12-20 | 30 |  | 30 | [25 empty] | 2011-12-21 |  | 2011-11-28 | No | Expedited | [8 empty] | 2012-01-19 | Online
WMECO | Pittsfield | 6B117-2011 | 1201 | 100 | Solar | 30B3 | 2011-11-09 | 2012-01-18 | 49 |  | 49 | [5 empty] | 2011-12-12 |  | -29205 | [17 empty] | 2012-03-02 |  | 2011-12-15 | Yes | Expedited | [8 empty] | 2012-05-03 | Online
WMECO | Springfield | 6S74-2011 | 1104 | 60 | Solar | 21S7 | 2011-11-15 | 2012-04-10 | 103 |  | 103 | [25 empty] | 2012-04-10 |  | 2012-03-01 | No | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S75-2011 | 1104 | 95 | Solar | 21S7 | 2011-11-15 | 2012-04-09 | 102 |  | 102 | 2011-12-20 |  | -29211 | [22 empty] | 2012-04-19 |  | 2012-03-01 | No | Expedited | [6 empty] | 2014-04-30 | 2014-05-05 | 2014-05-05 | Online
WMECO | Dalton | 6B120-2011 | 1226 | 13 | Solar | 19A2 | 2011-11-23 | [31 empty] | 2011-12-22 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Buckland | 6F286-2011 | 1338 | 57 | Solar | 22B5 | 2011-12-07 | 2012-02-22 | 53 |  | 53 | [25 empty] | 2012-03-12 |  | 2012-01-01 | Yes | Expedited | [8 empty] | 2012-05-01 | Online
WMECO | Greenfield | 6F290-2011 | 1301 | 14.7 | Solar | 21C4 | 2011-12-14 | 2012-01-26 | 30 |  | 30 | [25 empty] | 2012-02-08 |  | 2012-01-01 | No | Expedited | [8 empty] | 2012-03-19 | Online
WMECO | Whately | 6A239-2011 | 1093 | 260 | Solar | 18G8 | 2011-12-16 | 2012-04-13 | 83 |  | 83 | [25 empty] | 2012-04-19 |  | 2012-03-16 | No | Expedited | [8 empty] | 2012-05-01 | Online
WMECO | Easthampton | 6A241-2011 | 1027 | 3.3 | Wind | 15A5 | 2011-12-22 | 2012-01-04 | 9 |  | 9 | [25 empty] | 2012-01-12 |  | not supplied | No | Expedited | [8 empty] | 2012-02-13 | Online
WMECO | Hadley | 6A242-2011 | 1035 | 2000 | Solar | 18G4 | 2011-12-27 | 2012-02-16 | 36 |  | 36 | [15 empty] | 2012-04-02 | 2013-07-09 | 316 | 0 | 316 | 2013-05-03 | 2013-09-12 | 91 | 51 | 40 | 2013-10-04 |  | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A247-2012 | 1093 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A250-2012 | 1039 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6BA253-2012 | 1008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6BA254-2012 | 1008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Turners Falls | 6F295-2012 | 1376 | 370 | Hydro | 21C6 | 2012-01-10 | 2012-03-05 | 38 |  | 38 | [15 empty] | 2012-03-20 |  | -29273 | [7 empty] | 2013-03-27 |  | not supplied | No | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B125-2012 | 1634 | 3500 | Solar | 19J4 | 2012-01-25 | 2013-01-31 | 255 | 0 | 255 | [15 empty] | 2012-06-18 | 2013-06-07 | 243 | 0 | 243 | 2013-07-31 | 2013-09-06 | 27 |  | 27 | 2013-09-06 |  | 2012-09-25 | Yes | Complex | [6 empty] | 2014-09-25 | 2014-10-03 | 2014-10-03 | Online
WMECO | Tolland | 6B126-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29335 | [9 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B127-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29335 | [9 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Tolland | 6B128-2012 | 1634 | 1000 | Solar | 19J4 | 2012-01-25 | [31 empty] | 2012-09-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S90-2012 | 1089 | 110 | Solar | 21N5 | 2012-02-01 | 2012-03-02 | 22 |  | 22 | [5 empty] | 2012-02-29 |  | -29259 | [17 empty] | 2012-05-24 |  | not supplied | No | Expedited | [8 empty] | 2012-07-12 | Online
WMECO | Pittsfield | 6B130-2012 | 1201 | 2000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B131-2012 | 1201 | 3000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Ludlow | 6S91-2012 | 1056 | 3000 | Solar | 19S3 | 2012-02-03 | [31 empty] | 2012-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A262-2012 | 1038 | 45.6 | Solar | 18G5 | 2012-02-06 | 2012-04-11 | 47 |  | 47 | [25 empty] | 2012-05-02 |  | not supplied | Yes | Expedited | [6 empty] | 2012-08-24 | 2012-08-28 | 2012-08-28 | Online
WMECO | Shutesbury | 6A263-2012 | 1072 | 11.4 | Solar | 18G7 | 2012-02-07 | 2012-05-01 | 59 |  | 59 | [25 empty] | 2012-05-25 |  | 2/2012 | No | Expedited | [8 empty] | 2012-06-13 | Online
WMECO | Deerfield | 6F303-2012 | 1342 | 22.8 | Solar | 22B4 | 2012-02-07 | 2012-05-07 | 63 |  | 63 | [5 empty] | 2012-04-17 |  | -29292 | [17 empty] | 2012-05-10 |  | 2012-04-01 | Yes | Expedited | [8 empty] | 2012-09-12 | Online
WMECO | Southampton | 6A266-2012 | 1073 | 11.18 | Solar | 15A1 | 2012-02-17 | 2012-04-04 | 33 |  | 33 | [25 empty] | 2012-06-18 |  | 2012-04-25 | No | Expedited | [8 empty] | 2012-08-06 | Online
WMECO | Whately | 6A267-2012 | 1373 | 2000 | Solar | 18G8 | 2012-02-17 | 2012-04-10 | 37 |  | 37 | [15 empty] | 2012-05-17 | 2012-11-07 | 121 | 0 | 121 | 2012-09-12 | 2013-01-22 | 88 | 0 | 88 | 2013-02-26 |  | 2012-09-01 | Yes | Standard | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-06-25 | Online
WMECO | Blandford | 6B133-2012 | 1008 | 2000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B134-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B135-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B136-2012 | 1008 | 4000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B137-2012 | 1008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Ludlow | 6S96-2012 | 1056 | 2000 | Solar | 27A5 | 2012-02-23 | 2012-06-29 | 90 |  | 90 | [15 empty] | 2012-08-02 | 2012-10-22 | 56 |  | 56 | 2012-12-26 | 2013-03-08 | 50 | 0 | 50 | 2013-03-14 |  | 2012-09-30 | Yes | Standard | 2013-07-31 |  | 2013-07-30 |  |  |  | 2013-08-02 | 2013-08-07 | 2013-08-26 | Online
WMECO | Ludlow | 6S97-2012 | 1056 | 1000 | Solar | 19S3 | 2012-02-23 | [31 empty] | 2012-09-30 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A271-2012 | 1038 | 2000 | Solar | 18G6 | 2012-02-24 | 2012-07-19 | 102 |  | 102 | [15 empty] | 2012-04-30 | 2012-11-01 | 130 | 0 | 130 | 2012-10-10 | 2012-10-17 | 6 | 0 | 6 | 2013-02-13 |  | 2012-11-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B139-2012 | 1201 | 2000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B140-2012 | 1201 | 1000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Agawam | 6S98-2012 | 1001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Agawam | 6S99-2012 | 1001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Easthampton | 6A273-2012 | 1027 | 11 | Solar | 15A5 | 2012-03-01 | [31 empty] | 2012-03-20 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Lee | 6B141-2012 | 1238 | 295 | Solar | 16B5 | 2012-03-01 | 2012-06-11 | 71 |  | 71 | [25 empty] | 2012-06-14 |  | Q2 2012 | No | Expedited | [8 empty] | 2012-08-10 | Online
WMECO | Easthampton | 6A275-2012 | 1027 | 26.4 | Solar | 15A3 | 2012-03-02 | 2012-05-11 | 50 |  | 50 | [25 empty] | 2012-09-12 |  | 2012-04-15 | No | Expedited | [8 empty] | 2012-10-04 | Online
WMECO | Hadley | 6A277-2012 | 1035 | 1000 | Solar | 17K1 | 2012-03-12 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A278-2012 | 1035 | 2500 | Solar | 17K1 | 2012-03-12 | 2012-07-18 | 90 |  | 90 | [15 empty] | 2012-08-29 | 2013-06-07 | 192 | 0 | 192 | 2013-05-31 | 2013-07-23 | 36 | 18 | 18 | 2013-07-30 |  | 2012-10-12 | Yes | Standard | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-07-02 | Online
WMECO | Longmeadow | 6S102-2012 | 1106 | 45.6 | Solar | 22H11 | 2012-03-14 | 2012-05-03 | 36 |  | 36 | [25 empty] | 2012-06-11 |  | 2012-07-01 | No | Expedited | [8 empty] | 2012-08-15 | Online
WMECO | Lenoxdale | 6B142-2012 | 1242 | 780 | Solar | 17G3 | 2012-03-19 | 2013-03-27 | 256 |  | 256 |  |  |  | 0 | [11 empty] | 2012-12-17 | 2013-07-08 | 138 | 29 | 109 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B143-2012 | 1238 | 500 | Solar | 17G7 | 2012-03-19 | 2013-03-27 | 256 |  | 256 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 29 | 94 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-12 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B144-2012 | 1238 | 750 | Solar | 16B5 | 2012-03-19 | 2013-03-27 | 256 |  | 256 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B145-2012 | 1238 | 750 | Solar | 16B5 | 2012-03-21 | 2013-03-27 | 254 |  | 254 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B146-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B147-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B148-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B149-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lee | 6B150-2012 | 1238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A286-2012 | 1002 | 3750 | Solar | 17K2 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Whately | 6A287-2012 | 1373 | 1000 | Solar | 18G8 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Middlefield | 6B156-2012 | 1243 | 12.04 | Solar | 18C2 | 2012-03-29 | 2012-06-18 | 56 |  | 56 | [25 empty] | 2012-07-17 |  | 2012-04-24 | No | Expedited | [7 empty] | 2012-09-13 | 2012-09-13 | Online
WMECO | Whately | 6A289-2012 | 1373 | 1000 | Solar | 18G8 | 2012-04-03 | [31 empty] | 2012-01-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A290-2012 | 1038 | 44.4 | Solar | 18G5 | 2012-04-06 | 2012-06-08 | 44 |  | 44 | [25 empty] | 2012-06-29 |  | 2012-04-30 | No | Expedited | [8 empty] | 2012-07-27 | Online
WMECO | Hadley | 6A291-2012 | 1035 | 1000 | Solar | 17K1 | 2012-04-06 | 2012-06-29 | 59 |  | 59 | [15 empty] | 2012-08-29 |  | -29386 | [9 empty] | 2012-10-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Blandford | 6B159-2012 | 1008 | 125 | Solar | 19J4 | 2012-04-09 | [31 empty] | 2012-05-25 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A294-2012 | 1088 | 67.5 | Solar | 18G5 | 2012-04-10 | 2012-10-09 | 126 |  | 126 | [25 empty] | 2012-10-10 |  | 2012-10-31 | No | Expedited | [8 empty] | 2012-11-13 | Online
WMECO | Chesterfield | 6F316-2012 | 1012 | 60 | Solar | 18K3 | 2012-04-11 | 2012-05-18 | 27 |  | 27 | [5 empty] | 2012-07-12 |  | -29352 | [17 empty] | 2012-05-31 |  | 2012-05-01 | No | Expedited | [8 empty] | 2012-09-25 | Online
WMECO | Turners Falls | 6F319-2012 | 1376 | 8.6 | Solar | 21C2 | 2012-04-23 | 2012-07-18 | 61 |  | 61 | [25 empty] | 2012-07-25 |  | 2012-04-30 | No | Expedited | [8 empty] | 2012-09-18 | Online
WMECO | Cummington | 6F322-2012 | 1026 | 12.255 | Solar | 18K3 | 2012-05-14 | [31 empty] | 2012-05-25 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Hadley | 6A312-2012 | 1035 | 95 | Solar | 17K6 | 2012-05-17 | 2012-07-05 | 34 |  | 34 | [25 empty] | 2012-09-25 |  | 2012-07-13 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-28 | Online
WMECO | West Springfield | 6S112-2012 | 1089 | 333 | Solar | 21N8 | 2012-05-18 | 2012-08-15 | 62 |  | 62 | [25 empty] | 2012-08-17 |  | 2012-10-29 | No | Expedited | [9 empty] | Withdrawn
WMECO | Turners Falls | 6F325-2012 | 1376 | 500 | Solar | 21C3 | 2012-05-29 | [31 empty] | 2012-11-01 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Easthampton | 6A316-2012 | 1027 | 298 | Solar | 15A3 | 2012-05-30 | 2013-08-27 | 311 |  | 311 | 2013-08-28 | 2013-12-10 | 70 | 58 | 12 | 2013-12-10 |  | -29702 | 52 | [18 empty] | 2012-08-10 |  | Expedited | [9 empty] | Withdrawn
WMECO | Easthampton | 6A317-2012 | 1027 | 120 | Solar | 15A2 | 2012-05-30 | 2013-08-06 | 296 | 297 | -1 | 2013-08-07 | 2013-09-11 | 25 | 5 | 20 | 2014-04-29 | 2014-05-20 | 16 | 0 | 16 | [15 empty] | 2014-07-31 |  | 2012-08-10 | TBD | Expedited | [6 empty] | 2015-06-26 | 2015-06-26 | 2015-07-10 | Online
WMECO | Deerfield | 6F328-2012 | 1342 | 19.99 | Solar | 22B1 | 2012-06-04 | 2012-08-14 | 51 |  | 51 | [25 empty] | 2012-08-29 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-11-01 | 2012-11-07 | 2012-11-08 | Online
WMECO | Springfield | 6S115-2012 | 1104 | 500 | Solar | 5J15 | 2012-06-04 | 2012-10-18 | 96 |  | 96 | [25 empty] | 2013-02-21 |  | Q4 2012 | No | Expedited | [6 empty] | 2013-05-20 | 2013-05-21 | 2013-05-30 | Online
WMECO | Hatfield | 6A320-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A321-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hatfield | 6A322-2012 | 1038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hinsdale | 6B169-2012 | 1235 | 23.995 | Solar | 18C2 | 2012-06-27 | 2012-08-03 | 27 |  | 27 | [25 empty] | 2012-08-10 |  | 2012-08-01 | Yes | Expedited | [7 empty] | 2012-09-28 | 2012-09-28 | Online
WMECO | Shelburne Falls | 6F338-2012 | 1370 | 82 | Solar | 29R1 | 2012-06-28 | 2012-10-07 | 70 |  | 70 | [25 empty] | 2012-10-22 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-11-28 | 2012-12-05 | 2012-12-06 | Online
WMECO | Easthampton | 6A332-2012 | 1027 | 14 | Solar | 15A5 | 2012-07-13 | 2012-11-02 | 79 |  | 79 | 2012-11-05 | 2012-11-16 | 9 | 0 | 9 | [20 empty] | 2012-11-20 |  | 2012-09-01 | No | Expedited | [6 empty] | 2012-12-14 | 2012-12-20 | 2012-12-20 | Online
WMECO | Springfield | 6S123-2012 | 1104 | 142 | Solar | 5J9 | 2012-07-16 | 2012-10-23 | 70 |  | 70 | [25 empty] | 2013-03-13 |  | not supplied | No | Expedited | [6 empty] | 2012-04-10 | 2013-04-11 | 2013-04-23 | Online
WMECO | Springfield | 6S124-2012 | 1104 | 266 | Solar | 5J18 | 2012-07-16 | 2012-08-30 | 34 |  | 34 | [25 empty] | 2013-04-16 |  | 2012-10-30 | No | Expedited | [6 empty] | 2013-05-30 | 2013-05-31 | 2013-05-31 | Online
WMECO | Southwick | 6S126-2012 | 1077 | 1500 | Solar | 29A1 | 2012-07-17 | 2012-10-18 | 66 | 65 | 1 | [10 empty] | 2012-10-19 | 2013-03-05 | 91 | 89 | 2 | 2013-04-16 | 2013-09-20 | 110 | 0 | 110 | 2014-03-31 | 2014-08-20 | 99 | 99 | 0 | 2013-12-16 |  | Q4 2012 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A336-2012 | 1002 | 11.4 | Solar | 19B16 | 2012-07-24 | 2012-09-28 | 48 |  | 48 | [25 empty] | 2012-10-11 |  | 2012-08-01 | No | Expedited | [6 empty] | 2012-11-15 | 2012-11-16 | 2012-11-16 | Online
WMECO | Hatfield | 6A339-2012 | 1038 | 175 | Solar | 18G5 | 2012-07-27 | 2012-08-31 | 26 |  | 26 | [25 empty] | 2012-10-09 |  | not supplied | No | Expedited | [6 empty] | 2012-11-29 | 2012-12-03 | 2012-12-01 | Online
WMECO | Amherst | 6A341-2012 | 1002 | 34.2 | Solar | 17K2 | 2012-07-30 | 2012-11-29 | 84 |  | 84 | 2012-11-30 | 2012-12-04 | 3 | 0 | 3 | [20 empty] | 2012-12-05 |  | 2012-09-12 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-31 | Online
WMECO | Amherst | 6A343-2012 | 1027 | 57 | Solar | 17K8 | 2012-07-31 | 2012-12-10 | 90 |  | 90 | 2012-12-11 | 2013-01-08 | 19 | 0 | 19 | [20 empty] | 2013-01-10 |  | 2012-09-01 | No | Expedited | [6 empty] | 2013-02-26 | 2013-02-28 | 2013-02-28 | Online
WMECO | Amherst | 6A344-2012 | 1002 | 29.985 | Solar | 17K7 | 2012-08-01 | 2012-10-03 | 45 |  | 45 | [25 empty] | 2012-11-20 |  | not supplied | No | Expedited | [6 empty] | 2012-12-18 | 2012-12-19 | 2012-12-19 | Online
WMECO | Greenfield | 6F354-2012 | 1301 | 135 | Solar | 21C1 | 2012-08-17 | 2012-10-29 | 50 |  | 50 | [25 empty] | 2012-11-20 |  | not supplied | No | Expedited | [6 empty] | 2012-12-10 | 2012-12-12 | 2012-12-12 | Online
WMECO | Gill | 6F355-2012 | 1354 | 1250 | Diesel | 21B8 | 2012-08-20 | 2012-09-12 | 17 |  | 17 | [15 empty] | 2012-12-14 | 2013-08-21 | 171 | 17 | 154 | [5 empty] | 2013-12-12 |  | 2012-11-25 | TBD | Standard | [6 empty] | 2017-08-10 | 2017-05-19 | 2017-08-21 | Online
WMECO | Springfield | 6S136-2012 | 1119 | 333 | Solar | 20A33 | 2012-08-20 | 2012-10-05 | 34 |  | 34 | [25 empty] | 2012-12-21 |  | 2012-11-01 | No | Expedited | [6 empty] | 2012-12-27 | 2012-12-31 | 2012-12-31 | Online
WMECO | Tolland | 6B180-2012 | 1034 | 136.8 | Solar | 19J4 | 2012-08-22 | [31 empty] | 2013-01-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Amherst | 6A347-2012 | 1002 | 14 | Solar | 17K8 | 2012-08-24 | 2012-11-26 | 62 |  | 62 | 2012-11-27 | 2012-11-29 | 3 | 0 | 3 | [20 empty] | 2012-11-30 |  | 2012-12-01 | Yes | Expedited |  | 2012-12-06 | 2012-12-06 | 1 | 0 | 1 | 2012-12-14 | 2012-12-17 | 2012-12-17 | Online
WMECO | Leyden | 6F358-2012 | 1337 | 38 | Solar | 22B7 | 2012-08-28 | 2012-09-07 | 8 |  | 8 | [25 empty] | 2012-11-06 |  | 2012-12-01 | Yes | Expedited | [6 empty] | 2013-05-17 | 2013-05-22 | 2013-05-22 | Online
WMECO | Easthampton | 6A349-2012 | 1027 | 83 | Solar | 15A2 | 2012-08-29 | 2012-09-26 | 20 |  | 20 | [25 empty] | 2013-01-16 |  | 2012-11-12 | No | Expedited | [6 empty] | 2013-03-29 | 2013-04-02 | 2013-04-02 | Online
WMECO | Greenfield | 6F360-2012 | 1301 | 3.4 | Solar | 28WNW_1 | 2012-08-29 | 2012-09-20 | 16 |  | 16 | [25 empty] | 2013-01-15 |  | 2012-09-30 | No | Standard | [6 empty] | 2013-04-22 | 2013-04-23 | 2013-04-23 | Online
WMECO | Hancock | 6B183-2012 | 1237 | 6000 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hancock | 6B184-2012 | 1237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hancock | 6B185-2012 | 1237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Deerfield | 6F368-2012 | 1342 | 34.83 | Solar | 22B1 | 2012-09-06 | 2012-11-09 | 46 |  | 46 | 2012-11-12 | 2012-11-19 | 5 | 0 | 5 | [20 empty] | 2012-11-26 |  | not supplied | No | Expedited | [6 empty] | 2012-12-14 | 2013-01-03 | 2013-01-03 | Online
WMECO | Russell | 6A357-2012 | 1071 | 125 | Solar | 19J2 | 2012-09-17 | 2012-10-04 | 14 | 2 | 12 | 2012-11-05 | 2012-11-06 | 2 | 0 | 2 | [10 empty] | 2013-03-18 | 2013-09-03 | 117 | 0 | 117 | 2013-09-18 | 2013-10-10 | 17 | 0 | 17 | 2013-12-10 |  | 2012-11-08 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Middlefield | 6B190-2012 | 1243 | 10.965 | Solar | 18C2 | 2012-09-24 | 2012-10-17 | 17 | 0 | 17 | [25 empty] | 2013-01-24 |  | 2012-11-24 | No | Expedited | [6 empty] | 2013-06-18 | 2013-06-20 | 2013-06-20 | Online
WMECO | Westhampton | 6A363-2012 | 1027 | 12.9 | Solar | 15A3 | 2012-10-01 | 2012-10-01 | 1 |  | 1 | [25 empty] | 2012-11-27 |  | 2012-09-28 | No | Expedited | [6 empty] | 2012-12-26 | 2012-12-31 | 2012-12-31 | Online
WMECO | Pittsfield | 6B194-2012 | 1201 | 23.22 | Solar | 30B4 | 2012-10-02 | 2012-11-15 | 31 |  | 31 | 2012-11-16 |  | -29440 | [22 empty] | 2013-04-11 |  | not supplied | No | Expedited | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Online
WMECO | Pittsfield | 6B195-2012 | 1201 | 18.06 | Solar | 30B4 | 2012-10-02 | 2012-11-13 | 29 |  | 29 | 2012-11-14 |  | -29438 | [22 empty] | 2013-04-11 |  | not supplied | No | Expedited | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Online
WMECO | Ludlow | 6S144-2012 | 1056 | 600 | Diesel | 27A4 | 2012-10-19 | 2012-11-15 | 19 | 0 | 19 | 2012-11-27 | 2013-06-21 | 142 | 40 | 102 | [20 empty] | 2013-07-03 |  | 2012-11-12 | No | Expedited | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-08-01 | Online
WMECO | Pittsfield | 6B225-2012 | 1201 | 23.22 | Solar | 30BNW_1 | 2012-10-23 | 2012-11-07 | 12 |  | 12 | 2012-11-08 |  | -29435 | [22 empty] | 2013-03-21 |  | not supplied | No | Expedited | [6 empty] | 2013-04-01 | 2013-04-05 | 2013-04-05 | Online
WMECO | Pittsfield | 6B234-2012 | 1201 | 19.78 | Solar | 30B7 | 2012-11-16 | 2013-02-21 | 64 | 28 | 36 | 2013-02-22 | 2013-02-22 | 1 | 0 | 1 | [20 empty] | 2013-04-08 |  | 2013-01-21 | No | Expedited | [6 empty] | 2014-03-03 | 2014-03-05 | 2014-03-05 | Online
WMECO | Hadley | 6A381-2012 | 1035 | 760 | Solar | 17K5 | 2012-11-21 | 2013-07-30 | 170 | 2 | 168 | 2012-11-30 | 2013-09-10 | 194 | 153 | 41 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | 2013-10-08 | 2013-11-25 | 33 | 2 | 31 | [7 empty] | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A382-2012 | 1035 | 760 | Solar | 17K5 | 2012-11-21 | 2012-11-29 | 5 | 2 | 3 | 2012-11-30 | 2013-01-31 | 42 | 0 | 42 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | [12 empty] | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Lanesborough | 6B236-2012 | 1237 | 20.2 | Solar | 15E1 | 2012-11-21 | 2012-12-03 | 7 | 0 | 7 | 2012-11-22 | 2012-11-22 | 0 | 0 | [23 empty] | 2013-02-07 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Springfield | 6S149-2012 | 1105 | 5000 | Natural Gas / Diesel | 21S3 | 2012-11-26 |  |  | 208 | [28 empty] | 2012-10-15 | TBD | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B238-2012 | 1201 | 45.795 | Solar | 30B4 | 2012-11-27 | 2012-12-03 | 5 |  | 5 | 2012-12-04 | 2013-06-27 | 141 | 46 | 95 | [20 empty] | 2013-08-19 |  | 2012-11-30 | TBD | Expedited | [6 empty] | 2013-09-29 | 2013-09-30 | 2013-09-30 | Online
WMECO | Southampton | 6A384-2012 | 1073 | 600 | Diesel | 15A1 | 2012-12-04 | 2012-12-07 | 4 | 0 | 4 | 2013-06-10 | 2013-06-21 | 9 | 8 | 1 | [20 empty] | 2013-07-03 |  | 2012-12-31 | TBD | Expedited | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-07-30 | Online
WMECO | Pittsfield | 6B240-2012 | 1201 | 11.4 | Solar | 30B3 | 2012-12-05 | 2013-03-13 | 67 | 33 | 34 | 2013-03-14 | 2013-04-08 | 18 | 0 | 18 | [20 empty] | 2013-04-09 |  | 2013-01-21 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Montague | 6F410-2012 | 1351 | 11.4 | Solar | 21C7 | 2012-12-13 | 2013-02-12 | 41 |  | 41 | 2013-02-12 | 2013-02-12 | 1 | 0 | 1 | [20 empty] | 2013-03-19 |  | 2013-02-01 | No | Expedited | [6 empty] | 2013-04-30 | 2013-05-03 | 2013-05-03 | Online
WMECO | Amherst | 6A385-2012 | 1002 | 19.35 | Solar | 17K2 | 2012-12-17 | 2013-02-05 | 34 |  | 34 | 2013-02-05 | 2013-02-12 | 6 | 0 | 6 | [20 empty] | 2013-02-14 |  | not supplied | No | Expedited | [6 empty] | 2013-03-29 | 2013-04-01 | 2013-04-01 | Online
WMECO | Springfield | 6S154-2012 | 1111 | 5000 | Diesel | 5J14 | 2012-12-17 | 2013-04-19 | 85 | 0 | 85 | 2013-05-13 | 2013-10-28 | 116 | 45 | 71 | [5 empty] | 2013-04-22 | 2013-04-22 | 1 | 0 | 1 | 2013-10-28 | 2013-11-13 | 12 | 0 | 12 | [5 empty] | 2014-01-09 |  | not supplied | TBD | Standard | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Online
WMECO | Amherst | 6A387-2012 | 1059 | 3000 | Solar | 18G7 | 2012-12-26 |  |  | 148 | [28 empty] | 2013-07-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Richmond | 6B254-2013 | 1254 | 11.2 | Solar | 30B7 | 2013-01-08 | 2013-02-20 | 30 | 2 | 28 | 2013-02-21 | 2013-03-11 | 13 | 0 | 13 | [20 empty] | 2013-03-14 |  | 2013-03-13 | No | Expedited | [9 empty] | Withdrawn
WMECO | West Springfield | 6S155-2013 | 1089 | 16.985 | Solar | 21N9 | 2013-01-10 | 2013-03-06 | 38 | 1 | 37 | 2013-03-07 | 2013-03-07 | 1 | 0 | 1 | [20 empty] | 2013-04-01 |  | 2013-01-01 | No | Expedited | [6 empty] | 2013-05-08 | 2013-05-09 | 2013-05-09 | Online
WMECO | Pittsfield | 6B257-2013 | 1201 | 21.93 | Solar | 30B4 | 2013-01-16 | 2013-01-23 | 5 | 0 | 5 | 2013-01-24 | 2013-01-24 | 1 | 0 | 1 | [20 empty] | 2013-07-08 |  | not supplied | TBD | Expedited | [6 empty] | 2013-10-09 | 2013-10-10 | 2013-10-10 | Online
WMECO | Bernardston | 6F432-2013 | 1337 | 31.39 | Solar | 21B8 | 2013-02-01 | 2013-03-18 | 31 | 4 | 27 | 2013-03-19 | 2013-04-03 | 12 | 5 | 7 | [20 empty] | 2013-04-08 |  | 2013-05-01 | Yes | Expedited | [6 empty] | 2013-05-31 | 2013-06-05 | 2013-06-05 | Online
WMECO | Hadley | 6A405-2013 | 1035 | 833 | Solar | 18G4 | 2013-02-11 | 2013-06-19 | 89 | 26 | 63 | 2013-07-09 | 2013-07-12 | 4 | 0 | 4 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | [5 empty] | 2013-12-23 |  | 2013-12-15 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Hadley | 6A408-2013 | 1035 | 2730 | Solar | 17K1 | 2013-02-14 | 2013-03-29 | 31 | 1 | 30 | 2013-04-01 |  | -29530 | 93 | [23 empty] | 2013-10-13 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Sunderland | 6A411-2013 | 1375 | 300 | Solar | 18G3 | 2013-02-27 | 2013-04-03 | 26 | 18 | 8 | 2013-04-04 | 2013-09-11 | 110 | 84 | 26 | 2013-09-20 | 2013-10-11 | 16 | 0 | 16 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | Expedited | [9 empty] | Withdrawn
WMECO | Sunderland | 6A412-2013 | 1375 | 349.5 | Solar | 18G3 | 2013-02-27 | 2013-04-01 | 24 | 16 | 8 | 2013-04-02 | 2013-09-11 | 112 | 85 | 27 | 2013-10-15 | 2013-11-12 | 20 | 0 | 20 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B265-2013 | 1201 | 9.89 | Solar | 30BNW_1 | 2013-03-14 | 2013-03-28 | 11 | 0 | 11 | 2013-03-29 | 2013-07-02 | 65 | 8 | 57 | [20 empty] | 2013-08-01 |  | 2013-05-09 | TBD | Standard | [8 empty] | 2013-10-25 | Online
WMECO | Hadley | 6A415-2013 | 1035 | 833 | Solar | 18G4 | 2013-03-18 | 2013-06-18 | 64 | 21 | 43 | 2013-07-11 | 2013-07-12 | 2 | 0 | 2 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | 2014-03-04 | 2014-04-14 | 29 | 3 | 26 | 2014-05-07 |  | 2013-10-15 | Yes | Standard | 2014-09-15 | 2014-09-15 |  | -29891 |  |  | 2014-10-21 | 2014-10-30 | 2014-10-30 | Online
WMECO | West Springfield | 6S165-2013 | 1089 | 79.8 | Solar | 21N5 | 2013-03-18 | 2013-04-25 | 28 | 22 | 6 | 2013-04-26 |  | -29548 | 38 | [21 empty] | 2013-08-06 |  | 2013-04-25 | TBD | Expedited | [6 empty] | 2013-11-13 | 2013-12-10 | 2013-12-10 | Online
WMECO | Hadley | 6A418-2013 | 1035 | 57.405 | Solar | 17K5 | 2013-04-09 | 2013-06-12 | 45 | 37 | 8 | 2013-06-13 | 2013-08-06 | 37 | 28 | 9 | [20 empty] | 2013-08-09 |  | 2013-07-22 | TBD | Expedited | [6 empty] | 2013-11-13 | 2013-12-12 | 2013-12-31 | Online
WMECO | Greenfield | 6F447-2013 | 1301 | 300 | Solar | 21C1 | 2013-04-09 | 2013-05-07 | 20 |  | 20 | 2013-05-08 | 2013-05-23 | 12 |  | 12 | 2013-06-03 | 2013-06-26 | 17 | 0 | 17 | [15 empty] | 2013-07-15 |  | not supplied | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Amherst | 6A419-2013 | 1002 | 100 | Solar | 18G4 | 2013-04-16 | 2013-04-30 | 11 |  | 11 | 2013-05-01 | 2013-06-06 | 26 | 2 | 24 | [20 empty] | 2013-06-06 |  | 2013-05-01 | TBD | Expedited | [6 empty] | 2013-10-15 | 2013-10-22 | 2013-10-22 | Online
WMECO | Otis | 6B269-2013 | 1253 | 1800 | Wind | 19J6 | 2013-04-19 | 2013-05-02 | 10 | 0 | 10 | [10 empty] | 2013-05-03 | 2014-02-18 | 196 | 166 | 30 | 2014-04-10 | 2014-07-01 | 56 | 3 | 53 | [7 empty] | 2013-11-13 | Yes | Complex | [9 empty] | Withdrawn
WMECO | Peru | 6B277-2013 | 1235 | 16500 | Wind | 18C2 | 2013-05-06 | 2013-05-23 | 14 | 2 | 12 | [10 empty] | 2013-05-24 | 2013-09-06 | 72 | 47 | 25 |  |  |  | 29 | [8 empty] | not supplied | Yes | Complex | [9 empty] | Withdrawn
WMECO | Lanesborough | 6B280-2013 | 1237 | 20.21 | Solar | 15E1 | 2013-05-13 | 2013-11-12 | 126 | 120 | 6 | 2013-10-29 | 2013-10-29 | 1 | 0 | 1 | [20 empty] | 2013-11-12 |  | 2013-07-10 | TBD | Expedited | [6 empty] | 2014-03-28 | 2014-04-01 | 2014-04-01 | Online
WMECO | Amherst | 6A449-2013 | 1002 | 19.99 | Solar | 17K7 | 2013-06-26 | 2013-07-03 | 6 | 0 | 6 | 2013-07-05 | 2013-09-05 | 44 | 21 | 23 | [20 empty] | 2013-10-07 |  | 2013-09-01 | TBD | Expedited | [6 empty] | 2013-10-28 | 2013-10-29 | 2013-11-18 | Online
WMECO | Southwick | 6S195-2013 | 1077 | 40 | Hydro | 29A5 | 2013-07-09 | 2013-07-30 | 16 | 8 | 8 | 2013-07-31 |  | -29613 | 17 | [23 empty] | 2013-11-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Conway | 6F473-2013 | 1341 | 19.99 | Solar | 38A1 | 2013-07-15 | 2013-07-24 | 8 | 0 | 8 | 2013-07-25 | 2013-09-19 | 40 | 9 | 31 | 2013-09-26 | 2013-11-04 | 27 | 0 | 27 | [15 empty] | 2013-11-15 |  | 2013-08-01 |  | Expedited | [6 empty] | 2013-12-10 | 2013-12-13 | 2013-12-20 | Online
WMECO | Southwick | 6S200-2013 | 1077 | 3340 | Solar | 29A1 | 2013-07-18 | 2013-08-07 | 15 | 9 | 6 | [10 empty] | 2013-08-08 | 2013-10-15 | 47 | 27 | 20 | 2013-12-13 | 2014-05-01 | 94 | 0 | 94 | 2014-05-05 | 2014-11-05 | 128 | 12 | 116 | 2014-05-01 |  | 2014-08-01 |  | Standard |  | 2015-03-09 | 2015-03-20 | 9 |  | 9 | 2015-03-09 | 2015-03-30 | 2015-03-30 | Online
WMECO | Richmond | 6B301-2013 | 1254 | 18 | Solar | 30B7 | 2013-08-28 | 2013-10-07 | 28 | 20 | 8 | 2013-10-08 | 2013-11-20 | 30 | 19 | 11 | [20 empty] | 2013-11-20 |  | 2013-09-01 |  | Expedited | [6 empty] | 2013-12-13 | 2013-12-18 | 2013-12-31 | Online
WMECO | Springfield | 6S208-2013 | 1129 | 333 | Solar | 20A35 | 2013-08-29 | 2013-09-20 | 16 | 12 | 4 | 2013-10-31 | 2013-10-31 | 1 | 0 | 1 | 2013-12-02 | 2014-01-06 | 24 | 0 | 24 | [15 empty] | 2014-02-06 |  | 2014-06-30 | TBD | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B316-2013 | 1201 | 600 | Diesel | 30B4 | 2013-10-01 | 2013-11-05 | 25 | 13 | 12 | 2013-11-05 | 2014-01-13 | 45 | 45 | 0 | 2014-01-17 | 2014-04-11 | 58 | 44 | 14 | [15 empty] | 2014-05-20 |  | 2013-10-24 |  | Expedited | [8 empty] | 2018-04-25 | Online
WMECO | Southwick | 6S217-2013 | 1077 | 40 | Hydro | 29A2 | 2013-10-21 | 2013-11-05 | 12 | 1 | 11 | 2013-11-06 | 2013-12-04 | 18 | 2 | 16 | 2013-12-09 | 2014-01-30 | 36 | 20 | 16 | [15 empty] | 2014-02-06 |  | 2014-03-28 |  | Expedited | [6 empty] | 2015-11-16 | 2015-11-30 | 2015-11-30 | Online
WMECO | Greenfield | 6F508-2013 | 1301 | 29.985 | Solar | 22B2 | 2013-10-25 | 2013-11-05 | 8 | 0 | 8 | 2013-11-05 | 2013-11-05 | 1 | 0 | 1 | [20 empty] | 2014-01-03 |  | ASAP |  | Expedited | [6 empty] | 2014-04-14 | 2014-04-15 | 2014-04-15 | Online
WMECO | Hadley | 6A496-2013 | 1305 | 1950 | Solar | 17K1 | 2013-10-28 | 2014-01-17 | 55 | 10 | 45 | [10 empty] | 2014-01-21 | 2014-03-10 | 34 | 21 | 13 | 2014-04-09 | 2014-06-30 | 56 | 0 | 56 | 2014-12-09 | 2015-05-27 | 115 | 97 | 18 | 2015-07-21 |  |  |  | Standard | [7 empty] | 2016-10-20 | 2016-10-25 | Online
WMECO | Greenfield | 6F513-2013 | 1301 | 16 | Solar | 22B7 | 2013-10-29 | 2013-11-05 | 6 | 3 | 3 | 2013-11-07 | 2013-11-12 | 3 | 0 | 3 | [20 empty] | 2013-11-18 |  | 2013-11-10 |  | Expedited | [6 empty] | 2013-12-18 | 2013-12-23 | 2014-01-17 | Online
WMECO | Dalton | 6B345-2013 | 1226 | 1650 | Solar | 19A3 | 2013-12-03 | 2014-02-28 | 60 | 57 | 3 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | 2014-05-12 |  | -29805 | 11 | [10 empty] | Standard | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B359-2014 | 1201 | 16.5 | Solar | 30B7 | 2014-01-06 | 2014-02-12 | 27 | 15 | 12 | 2014-02-12 | 2014-02-12 | 1 | 0 | 1 | [20 empty] | 2014-02-18 |  | 2014-02-04 |  | Expedited | [6 empty] | 2014-04-17 | 2014-04-18 | 2014-04-18 | Online
WMECO | Dalton | 6B364-2014 | 1226 | 1250 | Solar | 19A3 | 2014-01-14 | 2014-02-28 | 32 | 16 | 16 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | [14 empty] | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S240-2014 | 1089 | 1950 | Solar | 16C12 | 2014-01-17 | 2014-03-12 | 37 | 22 | 15 | [10 empty] | 2014-03-13 | 2014-06-12 | 63 | 56 | 7 | 2014-07-18 | 2014-12-05 | 97 | 90 | 7 | 2015-04-21 | 2015-11-20 | 148 | 70 | 78 | 2015-11-30 |  | 2014-10-01 |  | Complex | [6 empty] | 2017-03-14 | 2017-03-22 | 2017-03-30 | Online
WMECO | Springfield | 6S244-2014 | 1111 | 4000 | Diesel | 5J14 | 2014-02-04 | 2014-02-24 | 14 | 13 | 1 | 2014-02-25 | 2014-03-19 | 16 | 0 | 16 | 2014-04-22 | 2014-05-12 | 15 | 10 | 5 | [15 empty] | 2014-07-02 |  | 2014-06-01 |  | Expedited | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Online
WMECO | Lee | 6B369-2014 | 1238 | 15.265 | Solar | 16B5 | 2014-02-05 | 2014-02-19 | 10 | 6 | 4 | 2014-02-20 |  | -29750 | 25 | [23 empty] | 2014-03-28 |  | Expedited | [9 empty] | Withdrawn
WMECO | Lee | 6B370-2014 | 1238 | 17.325 | Solar | 16B5 | 2014-02-05 | 2014-02-25 | 14 | 10 | 4 | 2014-02-26 | 2014-06-23 | 80 | 71 | 9 | [20 empty] | 2014-08-05 |  | 2014-01-24 |  | Expedited | [6 empty] | 2016-02-10 | 2016-02-16 | 2016-02-16 | Online
WMECO | Conway | 6F542-2014 | 1341 | 16.125 | Solar | 38A1 | 2014-02-24 | 2014-04-10 | 33 | 25 | 8 | 2014-04-11 | 2014-04-15 | 3 | 1 | 2 | [20 empty] | 2014-04-15 |  | 2014-03-21 |  | Expedited | [6 empty] | 2014-04-22 | 2014-04-24 | 2014-04-24 | Online
WMECO | Amherst | 6A540-2014 | 1002 | 24 | Solar | 17K6 | 2014-02-28 | 2014-03-12 | 9 | 8 | 1 | 2014-03-13 | 2014-05-01 | 34 | 14 | 20 | [20 empty] | 2014-05-07 |  | 2014-04-01 |  | Expedited | [6 empty] | 2014-05-30 | 2014-06-04 | 2014-06-04 | Online
WMECO | Lee | 6B383-2014 | 1238 | 19.8 | Solar | 16B5 | 2014-03-03 | 2014-03-19 | 12 | 7 | 5 | 2014-03-20 | 2014-05-20 | 43 | 6 | 37 | [20 empty] | 2014-06-10 |  | 2014-04-15 |  | Expedited | [6 empty] | 2014-09-12 | 2014-09-15 | 2014-09-30 | Online
WMECO | West Hatfield | 6A543-2014 | 1088 | 500 | Solar | 18G5 | 2014-03-06 | [31 empty] | 2014-06-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Longmeadow | 6S254-2014 | 1106 | 12 | Solar | 22H12 | 2014-03-11 | [31 empty] | 2014-05-30 |  | Expedited | [9 empty] | Withdrawn
WMECO | Whately | 6A564-2014 | 1093 | 22.8 | Solar | 18G6 | 2014-04-14 | 2014-04-23 | 7 | 0 | 7 | 2014-05-05 | 2014-05-21 | 13 | 7 | 6 | [20 empty] | 2014-05-21 |  | 2014-05-01 |  | Expedited | [6 empty] | 2014-08-05 | 2014-08-06 | 2014-08-06 | Online
WMECO | Springfield | 6S312-2014 | 1119 | 336 | Solar | 20A33 | 2014-06-11 | 2014-07-03 | 16 | 6 | 10 | 2014-07-07 | 2015-01-20 | 135 | 134 | 1 | 2015-01-21 | 2015-02-11 | 16 | 0 | 16 | [15 empty] | 2015-03-27 |  | 2014-11-17 |  | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B409-2014 | 1201 | 266 | Solar | 15E2 | 2014-06-23 | 2014-07-22 | 21 | 18 | 3 | 2014-07-23 | 2015-05-06 | 196 | 192 | 4 | 2015-05-21 | 2015-06-17 | 18 | 0 | 18 | [15 empty] | 2015-08-14 |  | 2014-08-25 |  | Expedited | [6 empty] | 2015-12-17 | 2016-04-21 | 2016-04-21 | Online
WMECO | Springfield | 6S334-2014 | 1129 | 278.4 | Solar | 20A35 | 2014-06-23 | [31 empty] | 2014-10-31 |  | Expedited | [9 empty] | Withdrawn
WMECO | Windsor | 6B413-2014 | 1270 | 24 | Solar | 18C1 | 2014-07-10 | 2014-07-22 | 9 | 2 | 7 | 2014-08-21 | 2014-09-03 | 9 | 8 | 1 | [20 empty] | 2014-09-05 |  | 2014-11-01 |  | Expedited | [6 empty] | 2014-12-09 | 2014-12-16 | 2014-12-16 | Online
WMECO | Russell | 6A681-2014 | 1071 | 49 | Solar | 19J2 | 2014-07-16 | 2014-09-05 | 37 | 30 | 7 | 2014-09-12 | 2014-12-03 | 56 | 50 | 6 | [20 empty] | 2014-12-16 |  | 2014-09-26 |  | Expedited | [6 empty] | 2015-10-02 | 2015-10-06 | 2015-10-06 | Online
WMECO | Hadley | 6A682-2014 | 1035 | 24.98 | Solar | 18G4 | 2014-07-16 | 2014-08-26 | 30 | 26 | 4 | 2014-08-27 | 2014-09-04 | 6 | 2 | 4 | [20 empty] | 2014-09-04 |  | not supplied |  | Expedited | [6 empty] | 2014-12-22 | 2014-12-22 | 2014-12-22 | Online
WMECO | Greenfield | 6F594-2014 | 1301 | 600 | Diesel | 22B7 | 2014-07-24 | 2014-08-26 | 24 | 23 | 1 | 2014-08-26 | 2014-12-03 | 68 | 54 | 14 | 2014-12-03 | 2014-12-29 | 18 | 0 | 18 | [15 empty] | 2015-01-07 |  | not supplied |  | Expedited | [8 empty] | 2018-04-25 | Online
WMECO | Springfield | 6S386-2014 | 1103 | 42 | Solar | 8CNW_1 | 2014-08-04 | 2014-08-25 | 16 | 15 | 1 | 2014-08-26 | 2014-09-29 | 24 | 22 | 2 |  |  |  | 17 | [18 empty] | 2014-08-01 |  | Standard | [9 empty] | Withdrawn
WMECO | West Springfield | 6S468-2014 | 1089 | 200 | Solar | 16C12 | 2014-08-25 |  |  | 165 | [28 empty] | 2014-08-01 |  | Expedited | [9 empty] | Withdrawn
WMECO | Pittsfield | 6B427-2014 | 1201 | 30.25 | Solar | 30B4 | 2014-08-26 | 2014-09-18 | 17 | 14 | 3 | 2014-09-19 | 2014-09-22 | 2 | 1 | 1 | [20 empty] | 2014-09-22 |  | 2014-12-01 |  | Expedited | [6 empty] | 2015-01-29 | 2015-02-04 | 2015-02-04 | Online
WMECO | Chesterfield | 6F652-2014 | 1012 | 22 | Solar | 18K3 | 2014-09-15 | 2014-10-15 | 22 | 20 | 2 | 2014-10-16 | 2014-11-05 | 15 | 8 | 7 | [20 empty] | 2014-11-12 |  | Q4 2014 |  | Expedited | [6 empty] | 2015-01-21 | 2015-01-26 | 2015-01-26 | Online
WMECO | Pittsfield | 6B436-2014 | 1201 | 499 | Solar | 30B2 | 2014-09-25 | 2014-10-09 | 11 | 5 | 6 | 2014-10-09 | 2014-10-15 | 4 | 3 | 1 | 2014-10-16 | 2014-11-07 | 17 | 0 | 17 | [15 empty] | 2014-12-02 |  | 2014-12-14 |  | Expedited | 2014-12-27 | 2014-12-30 | 2014-12-30 | 1 |  | 1 | 2014-12-26 | 2014-12-31 | 2015-01-12 | Online
WMECO | Springfield | 6S530-2014 | 1109 | 44.55 | Solar | 5JNW_1 | 2014-09-29 |  |  | 14 | [28 empty] | 2014-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S531-2014 | 1109 | 44.55 | Solar | 5J9 | 2014-09-29 | 2014-10-28 | 21 | 20 | 1 | 2014-10-29 | 2014-11-18 | 14 | 3 | 11 | [20 empty] | 2014-11-24 |  | 2014-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2015-02-18 | Online
WMECO | Indian Orchard | 6S532-2014 | 1151 | 180 | Solar | 27A13 | 2014-09-29 | 2014-10-14 | 11 | 10 | 1 | 2014-10-15 | 2014-11-26 | 30 | 9 | 21 | [20 empty] | 2014-12-05 |  | 2014-11-30 |  | Expedited |  |  |  | 0 |  |  | 2015-08-28 | 2015-09-02 | 2015-09-02 | Online
WMECO | Easthampton | 6A880-2014 | 1027 | 98 | Solar | 15A2 | 2014-10-06 | 2014-11-26 | 36 | 34 | 2 | 2014-11-28 | 2015-02-19 | 56 | 35 | 21 | [20 empty] | 2015-04-15 |  | 2014-12-01 |  | Expedited |  |  |  | 0 |  |  | 2016-03-03 | 2016-03-10 | 2016-03-10 | Online
WMECO | Pittsfield | 6B446-2014 | 1201 | 234 | Solar | 19A5 | 2014-10-15 | 2014-10-28 | 10 | 3 | 7 | 2014-10-29 | 2014-12-10 | 29 | 13 | 16 | 2014-12-11 | 2016-02-19 | 295 | 262 | 33 | [15 empty] | 2016-02-22 |  | 2014-12-31 |  | Expedited |  |  |  | 0 |  |  | 2016-03-17 | 2016-03-23 | 2016-03-23 | Online
WMECO | Pittsfield | 6B447-2014 | 1201 | 168 | Solar | 30B2 | 2014-10-24 | 2014-10-29 | 4 | 0 | 4 | 2014-10-30 | 2014-11-18 | 13 | 12 | 1 | [20 empty] | 2014-12-09 |  | 2014-12-12 |  | Expedited |  |  |  | 0 |  |  | 2015-01-21 | 2015-01-22 | 2015-01-22 | Online
WMECO | Amherst | 6A919-2014 | 1002 | 57.75 | Solar | 17K8 | 2014-11-05 | 2014-11-25 | 14 | 6 | 8 | 2014-11-26 | 2015-03-02 | 64 | 33 | 31 | [20 empty] | 2015-03-04 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-06-12 | 2015-06-15 | 2015-06-15 | Online
WMECO | Hatfield | 6A935-2014 | 1038 | 3300 | Solar | 18G5 | 2014-11-13 | 2015-03-04 | 75 | 69 | 6 | [10 empty] | 2015-03-05 | 2015-06-06 | 64 | 61 | 3 | 2015-05-29 | 2015-11-05 | 111 | 12 | 99 | 2016-04-12 |  | -30281 |  |  |  |  | 2015-10-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S672-2014 | 1056 | 998 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S673-2014 | 1056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S674-2014 | 1056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S689-2014 | 1104 | 150 | Solar | 21S7 | 2014-11-25 | 2015-07-30 | 168 | 163 | 5 | 2015-07-31 | 2016-05-05 | 190 | 31 | 159 | [10 empty] | 2016-05-06 | 2016-09-26 | 98 | 46 | 52 | [5 empty] | 2016-09-26 |  | 12/2014 |  | Standard |  |  |  | 0 |  |  | 2017-08-24 | 2017-08-25 | 2017-08-25 | Online
WMECO | Otis | 6B458-2014 | 1029 | 1500 | Wind | 19J6 | 2014-12-01 | 2014-12-17 | 13 | 12 | 1 | [10 empty] | 2014-12-18 | 2015-03-26 | 66 | 63 | 3 | 2015-03-27 | 2015-07-23 | 81 | 17 | 64 | 2016-02-23 |  | -30247 | 144 |  | 2015-07-27 |  | 2015-06-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-03-09 | Online
WMECO | Otis | 6B459-2014 | 1253 | 960 | Solar | 19J4 | 2014-12-02 | 2015-01-19 | 32 | 27 | 5 | 2015-01-20 | 2015-06-15 | 101 | 44 | 57 | [10 empty] | 2015-08-03 | 2016-01-04 | 105 | 41 | 64 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A962-2014 | 1375 | 22.8 | Solar | 18G3 | 2014-12-03 | 2014-12-30 | 19 | 9 | 10 | 2014-12-31 | 2015-02-27 | 40 | 36 | 4 | [20 empty] | 2015-03-06 |  | 2015-02-01 |  | Expedited |  |  |  | 0 |  |  | 2015-04-15 | 2015-04-16 | 2015-04-16 | Online
WMECO | Pittsfield | 6B462-2014 | 1201 | 3300 | Solar | 15E2 | 2014-12-08 | 2014-12-15 | 6 | 2 | 4 | [10 empty] | 2014-12-16 | 2015-02-17 | 42 | 26 | 16 | 2015-03-16 | 2015-08-24 | 111 | 33 | 78 | 2015-08-11 | 2015-10-22 | 51 | 30 | 21 | 2015-10-23 |  | 2015-08-27 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-04-13 | Online
WMECO | Otis | 6B463-2014 | 1253 | 960 | Solar | 19J4 | 2014-12-08 | 2015-01-19 | 28 | 24 | 4 | 2015-01-20 | 2015-06-15 | 101 | 44 | 57 | [10 empty] | 2015-08-03 | 2016-01-04 | 105 | 41 | 64 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S708-2014 | 1106 | 16.35 | Solar | 22H12 | 2014-12-09 | 2014-12-15 | 5 | 0 | 5 | 2014-12-16 | 2015-01-23 | 26 | 11 | 15 | [20 empty] | 2015-02-03 |  | 2015-02-09 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F724-2014 | 1301 | 48 | Solar | 21C1 | 2014-12-12 | 2014-12-30 | 12 | 10 | 2 | 2014-12-31 | 2015-03-09 | 46 | 38 | 8 | [20 empty] | 2015-03-25 |  | 2015-02-15 |  | Expedited |  |  |  | 0 |  |  | 2015-06-04 | 2015-06-08 | 2015-06-08 | Online
WMECO | Deerfield | 6F725-2014 | 1342 | 4500 | Solar | 22B4 | 2014-12-12 | 2015-01-29 | 32 | 23 | 9 | [10 empty] | 2015-01-30 | 2015-03-17 | 31 | 16 | 15 | 2015-03-18 | 2015-11-30 | 176 | 38 | 138 | 2016-03-18 |  | -30264 |  |  | 2015-12-07 |  | Q3/4 2015 |  | Complex |  |  |  | 0 |  |  | 2017-10-11 | 2017-10-18 | 2017-12-08 | Online
WMECO | Greenfield | 6F736-2014 | 1301 | 24 | Solar | 21C4 | 2014-12-26 | 2015-01-22 | 18 | 13 | 5 | 2015-01-23 | 2015-03-12 | 34 | 23 | 11 | [22 empty] | Feb 2015 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S764-2015 | 1108 | 37.8 | Solar | 22H16 | 2015-01-06 | 2015-01-30 | 18 | 17 | 1 | 2015-02-02 | 2015-03-06 | 24 | 15 | 9 | 2015-03-09 | 2015-04-03 | 19 | 1 | 18 | [15 empty] | 2015-04-20 |  | 2015-01-22 |  | Expedited |  |  |  | 0 |  |  | 2015-08-10 | 2015-08-12 | 2015-08-13 | Online
WMECO | Pittsfield | 6B474-2015 | 1201 | 36 | Solar | 15E3 | 2015-01-07 | 2015-02-11 | 25 | 9 | 16 | 2015-02-12 | 2015-04-08 | 38 | 37 | 1 | 2015-04-28 | 2015-05-18 | 15 | 14 | 1 | [15 empty] | 2015-07-08 |  | 2015-08-01 |  | Expedited |  |  |  | 0 |  |  | 2015-11-10 | 2015-11-13 | 2015-11-13 | Online
WMECO | Deerfield | 6F749-2015 | 1342 | 40 | Solar | 22B1 | 2015-01-07 | 2015-02-04 | 20 | 15 | 5 | 2015-02-05 | 2015-09-18 | 155 | 111 | 44 | [20 empty] | 2015-09-18 |  | 2015-02-01 |  | Expedited |  |  |  | 0 |  |  | 2015-11-05 | 2015-11-12 | 2016-02-03 | Online
WMECO | Hadley | 6A1005-2015 | 1035 | 253 | Solar | 17K6 | 2015-01-09 | 2015-01-23 | 10 | 5 | 5 | 2015-01-26 | 2015-03-02 | 25 | 15 | 10 | 2015-03-05 | 2015-03-27 | 16 | 0 | 16 | [15 empty] | 2015-04-03 |  | 2015-05-05 |  | Expedited |  |  |  | 0 |  |  | 2015-06-24 | 2015-07-01 | 2015-07-23 | Online
WMECO | Lanesborough | 6B479-2015 | 1237 | 368 | Solar | 15E2 | 2015-01-21 | 2015-02-04 | 11 | 6 | 5 | 2015-02-05 | 2015-03-03 | 18 | 12 | 6 | 2015-03-04 | 2017-01-08 | 459 | 435 | 24 | [15 empty] | 2017-01-10 |  | 2015-05-05 |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-12-22 | Online
WMECO | Becket | 6B481-2015 | 1223 | 24 | Solar | 16B1 | 2015-01-23 | 2015-01-26 | 2 | 1 | 1 | 2015-01-27 | 2015-03-06 | 28 | 16 | 12 | [20 empty] | 2015-03-10 |  | Spring 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-10-05 | 2015-10-07 | 2015-10-09 | Online
WMECO | Whately | 6A1047-2015 | 1093 | 20 | Solar | 18G8 | 2015-02-02 | 2015-02-19 | 13 | 5 | 8 | 2015-02-19 | 2015-02-20 | 2 | 0 | 2 | [20 empty] | 2015-02-20 |  | Q1 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-07-03 | 2015-07-07 | 2015-07-07 | Online
WMECO | Hatfield | 6A1053-2015 | 1038 | 1890 | Solar | 18G6 | 2015-02-09 | 2015-05-15 | 67 | 65 | 2 | 2015-05-18 | 2015-10-29 | 114 | 76 | 38 | [10 empty] | 2015-10-30 | 2016-02-12 | 71 | 2 | 69 | 2016-03-07 |  | -30256 |  |  | 2016-02-12 |  | Sept 2015 |  | Complex |  |  |  | 0 |  |  | 2017-07-03 | 2017-07-10 | 2017-09-07 | Online
WMECO | Whately | 6A1062-2015 | 1093 | 19.3 | Solar | 18G6 | 2015-02-19 | 2015-04-22 | 43 | 41 | 2 | 2015-04-23 | 2015-07-10 | 54 | 47 | 7 | [20 empty] | 2015-07-10 |  | 2015-04-06 |  | Expedited |  |  |  | 0 |  |  | 2016-01-29 | 2016-02-02 | 2016-02-02 | Online
WMECO | Becket | 6B483-2015 | 1223 | 17.5 | Solar | 19J6 | 2015-02-23 | 2015-04-16 | 38 | 18 | 20 | 2015-04-17 | 2015-04-30 | 9 | 8 | 1 | [20 empty] | 2015-05-18 |  | 2015-05-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2015-11-04 | Online
WMECO | South Deerfield | 6F801-2015 | 1342 | 500 | Biogas | 22B1 | 2015-02-24 | 2015-04-15 | 36 | 34 | 2 | 2015-04-16 | 2015-05-22 | 26 | 16 | 10 | [22 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F802-2015 | 1373 | 18 | Solar | 18G3 | 2015-02-24 | 2015-03-05 | 8 | 0 | 8 | 2015-03-06 | 2015-03-13 | 6 | 4 | 2 | [20 empty] | 2015-03-24 |  | March 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-05-19 | 2015-05-21 | 2015-05-21 | Online
WMECO | Greenfield | 6F815-2015 | 1301 | 56 | Solar | 21C1 | 2015-03-05 | 2015-03-31 | 18 | 15 | 3 | 2015-04-01 | 2015-04-13 | 9 | 2 | 7 | [20 empty] | 2015-04-15 |  | 2015-05-01 |  | Expedited |  |  |  | 0 |  |  | 2017-04-19 | 2017-04-20 | 2017-04-20 | Online
WMECO | Lee | 6B490-2015 | 1238 | 1904 | Solar | 17G7 | 2015-03-12 | 2015-03-20 | 6 | 2 | 4 | [10 empty] | 2015-03-23 | 2015-04-30 | 28 | 23 | 5 | 2015-05-15 | 2015-08-12 | 61 | 3 | 58 | 2015-08-20 |  | -30122 |  |  | 2015-08-27 |  | 2015-09-30 |  | Standard |  |  |  | 0 |  |  | 2017-03-28 | 2015-04-11 | 2017-04-11 | Online
WMECO | Pittsfield | 6B497-2015 | 1201 | 2340 | Solar | 19A3 | 2015-03-24 | 2015-03-31 | 6 | 2 | 4 | [10 empty] | 2015-04-01 | 2015-06-04 | 45 | 30 | 15 | 2015-06-05 | 2015-11-06 | 107 | 0 | 107 | 2015-11-24 | 2016-09-21 | 206 | 0 | 206 | 2015-11-09 |  | Fall 2015 |  | Complex |  |  |  | 0 |  |  | 2017-01-18 | 2017-01-20 | 2017-01-31 | Online
WMECO | Greenfield | 6F836-2015 | 1301 | 19.3 | Solar | 21C4 | 2015-03-27 | 2015-04-20 | 16 | 8 | 8 | 2015-04-21 | 2015-04-21 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2015-04-22 |  | 2015-04-01 |  | Expedited |  |  |  | 0 |  |  | 2015-05-15 | 2015-05-19 | 2015-05-19 | Online
WMECO | Granville | 6S941-2015 | 1034 | 24.99 | Solar | 29A5 | 2015-04-06 | 2015-04-16 | 9 | 6 | 3 | 2015-04-16 | 2015-04-16 | 1 | 0 | 1 | 2015-04-21 | 2015-05-06 | 12 | 0 | 12 |  |  | 0 | [12 empty] | 2015-05-07 |  | 2015-06-01 |  | Expedited |  |  |  | 0 |  |  | 2015-07-30 | 2015-07-31 | 2015-07-31 | Online
WMECO | Sunderland | 6A1124-2015 | 1375 | 44 | Solar | 18G3 | 2015-04-17 | 2015-05-12 | 17 | 11 | 6 | 2015-05-13 | 2015-06-18 | 25 | 0 | 25 | 2015-06-22 | 2015-06-30 | 7 | 0 | 7 |  |  | 0 | [12 empty] | 2015-06-30 |  | July 2015 |  | Expedited |  |  | 2015-09-25 | 30147 |  | 30147 | 2015-09-24 | 2015-09-30 | 2015-09-30 | Online
WMECO | Northfield | 6F857-2015 | 1360 | 56 | Solar | 21B8 | 2015-04-17 | 2015-05-12 | 17 | 6 | 11 | 2015-05-13 | 2015-05-27 | 10 | 0 | 10 | 2015-06-17 | 2015-07-20 | 22 | 17 | 5 |  |  | 0 | [12 empty] | 2015-07-31 |  | 7/2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-02 | 2016-02-03 | 2016-02-03 | Online
WMECO | Southwick | 6S959-2015 | 1077 | 1316 | Solar | 29A5 | 2015-04-17 | 2015-04-22 | 3 | 0 | 3 | 2015-04-23 | 2015-09-21 | 104 | 93 | 11 | [7 empty] | 0 |  |  | 2015-09-22 | 2015-12-11 | 56 | 0 | 56 | 2016-01-11 |  | -30218 |  |  | 2016-01-26 |  | 2015-12-01 |  | Complex |  |  |  | 0 |  |  |  | 2016-12-06 | 2016-12-14 | Online
WMECO | Shelburne Falls | 6F872-2015 | 1370 | 39.6 | Solar | 22B5 | 2015-04-23 | [16 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A1145-2015 | 1038 | 18.5 | Solar | 18G6 | 2015-04-27 | 2015-06-02 | 26 | 20 | 6 | 2015-06-03 | 2015-07-02 | 21 | 4 | 17 | [7 empty] | 0 | [12 empty] | 2015-07-10 |  | June 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-08-11 | 2015-08-17 | 2015-08-17 | Online
WMECO | South Deerfield | 6F881-2015 | 1373 | 16.7 | Solar | 22B1 | 2015-04-27 | 2015-05-18 | 16 | 13 | 3 | 2015-05-19 | 2015-05-27 | 6 | 3 | 3 | [7 empty] | 0 | [12 empty] | 2015-05-29 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-02-02 | 2016-02-03 | 2016-02-03 | Online
WMECO | Amherst | 6A1148-2015 | 1002 | 54 | Solar | 19B16 | 2015-04-29 | 2015-07-16 | 54 | 40 | 14 | 2015-07-17 | 2015-11-18 | 86 | 18 | 68 | [7 empty] | 0 | [12 empty] | 2015-11-18 |  | July 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-09-01 | 2016-09-07 | 2016-09-07 | Online
WMECO | Ashfield | 6F890-2015 | 1330 | 1995 | Biogas | 38A1 | 2015-05-01 | 2015-11-02 | 127 | 63 | 64 | 2015-11-03 | 2016-02-17 | 71 | 30 | 41 | [7 empty] | 0 |  |  | 2016-02-18 | 2016-08-15 | 123 | 54 | 69 | 2016-08-16 | 2017-10-05 | 286 | 34 | 252 | 2017-10-10 |  | 2016-01-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Richmond | 6B516-2015 | 1254 | 18 | Solar | 30B2 | 2015-05-04 | 2015-08-10 | 68 | 55 | 13 | 2015-08-11 | 2015-10-14 | 45 | 5 | 40 | 2015-10-15 | 2016-01-29 | 72 | 44 | 28 |  |  | 0 | [12 empty] | 2016-02-02 |  | 2015-06-01 |  | Expedited |  |  |  | 0 |  |  | 2016-09-21 | 2016-09-26 | 2016-10-18 | Online
WMECO | Pittsfield | 6B521-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-01 | 16 | 8 | 8 | 2015-06-02 | 2015-12-30 | 145 | 44 | 101 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B522-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 27 | 111 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B523-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 32 | 106 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | Pittsfield | 6B525-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 23 | 8 | 15 | 2015-06-11 | 2015-12-30 | 138 | 27 | 111 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-10-30 | Online
WMECO | West Springfield | 6S1051-2015 | 1089 | 180 | Solar | 16C12 | 2015-05-08 | 2015-06-25 | 33 | 20 | 13 | 2015-06-26 |  | -30084 | [9 empty] | 0 | [14 empty] | 2015-11-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1169-2015 | 1035 | 140 | Solar | 18G5 | 2015-05-12 | 2015-06-11 | 22 | 10 | 12 | 2015-06-12 | 2015-11-16 | 107 | 105 | 2 | [7 empty] | 0 |  |  | 2015-11-16 | 2016-02-11 | 60 | 5 | 55 | [5 empty] | 2016-02-12 |  | 2015-08-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2016-09-27 | Online
WMECO | Pittsfield | 6B529-2015 | 1201 | 499 | Solar | 30B5 | 2015-05-12 | 2015-07-06 | 37 | 10 | 27 | 2015-07-07 | 2015-12-30 | 122 | 32 | 90 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-04-19 | 74 | 26 | 48 | 2016-06-13 |  | -30323 |  |  | 2016-05-09 |  | 2015-06-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-10-24 | Online
WMECO | Ludlow | 6S1070-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 52 | 51 | 1 | 2015-07-31 | 2016-02-18 | 137 | 43 | 94 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-01-03 | Online
WMECO | Ludlow | 6S1071-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 52 | 51 | 1 | 2015-07-31 | 2016-02-18 | 137 | 43 | 94 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-12-21 | Online
WMECO | Shelburne Falls | 6F914-2015 | 1370 | 25 | Solar | 29R2 | 2015-05-19 | 2015-07-10 | 36 | 16 | 20 | 2015-07-13 | 2015-07-14 | 2 | 0 | 2 | [7 empty] | 0 | [12 empty] | 2015-07-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-08-24 | 2015-08-25 | 2015-08-25 | Online
WMECO | Pittsfield | 6B537-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 30 | 57 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Pittsfield | 6B538-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 29 | 58 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Pittsfield | 6B539-2015 | 1201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 18 | 3 | 15 | 2015-06-16 | 2015-10-20 | 87 | 29 | 58 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-10-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-02-09 | Online
WMECO | Greenfield | 6F915-2015 | 1301 | 480 | Solar | 21C1 | 2015-05-21 | 2015-07-09 | 33 | 7 | 26 | 2015-07-10 | 2016-01-07 | 124 | 43 | 81 | [7 empty] | 0 |  |  | 2016-01-08 | 2016-05-13 | 87 | 29 | 58 | [7 empty] | 2015-07-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6F917-2015 | 1026 | 499 | Solar | 18K3 | 2015-05-21 | 2015-07-30 | 48 | 47 | 1 | 2015-07-31 | 2015-12-30 | 104 | 33 | 71 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | Oct 2015 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-08-09 | Online
WMECO | Ludlow | 6S1096-2015 | 1056 | 1095.8 | Solar | 19S2 | 2015-05-21 | 2015-06-24 | 23 | 17 | 6 | 2015-06-25 | 2016-02-18 | 162 | 43 | 119 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | 2016-06-09 |  | -30321 |  |  | 2016-05-11 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-01-03 | Online
WMECO | Amherst | 6A1199-2015 | 1002 | 2002 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 39 | 14 | 25 | 2015-07-21 | 2015-11-04 | 75 | 53 | 22 | [7 empty] | 0 |  |  | 2015-11-05 | 2016-03-03 | 80 | 13 | 67 | 2016-05-17 |  | -30305 |  |  | 2016-03-04 |  | 2015-12-31 |  | Complex |  |  |  | 0 |  |  | 2017-05-08 | 2017-05-11 | 2017-05-12 | Online
WMECO | Amherst | 6A1200-2015 | 1002 | 1728 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 39 | 14 | 25 | 2015-07-21 | 2015-11-04 | 75 | 53 | 22 | [7 empty] | 0 |  |  | 2015-11-05 | 2016-03-03 | 80 | 13 | 67 | 2016-05-17 |  | -30305 |  |  | 2016-03-04 |  | 2015-12-31 |  | Complex |  |  |  | 0 |  |  | 2017-11-22 | 2017-11-28 | 2017-12-27 | Online
WMECO | Cummington | 6F920-2015 | 1026 | 840 | Solar | 18K3 | 2015-05-22 | 2015-07-30 | 47 | 46 | 1 | 2015-07-31 | 2015-12-30 | 104 | 33 | 71 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-06-15 | 114 | 0 | 114 | [7 empty] | Oct 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F921-2015 | 1342 | 19.3 | Solar | 22B7 | 2015-05-26 | 2015-07-06 | 28 | 4 | 24 | 2015-07-07 | 2015-07-22 | 12 | 1 | 11 | [7 empty] | 0 | [12 empty] | 2015-08-14 |  | Aug 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-04 | 2016-02-08 | 2016-02-08 | Online
WMECO | Amherst | 6A1211-2015 | 1002 | 192 | Solar | 18G2 | 2015-05-29 | 2015-07-06 | 25 | 9 | 16 | 2015-07-07 | 2015-10-08 | 67 | 37 | 30 | [7 empty] | 0 | [12 empty] | 2015-10-23 |  | 2015-09-01 |  | Expedited |  |  |  | 0 |  |  | 2016-02-11 | 2016-02-18 | 2016-02-18 | Online
WMECO | Plainfield | 6F926-2015 | 1070 | 331 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 43 | 6 | 37 | 2015-07-31 | 2015-11-05 | 68 |  | 68 | [7 empty] | 0 | [14 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F927-2015 | 1070 | 499 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 43 | 6 | 37 | 2015-07-31 | 2015-11-05 | 68 |  | 68 | [7 empty] | 0 | [14 empty] | 2015-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1217-2015 | 1002 | 15 | Solar | 17K8 | 2015-06-01 | 2015-07-06 | 24 | 1 | 23 | 2015-07-07 | 2015-07-23 | 13 | 1 | 12 | [7 empty] | 0 | [12 empty] | 2015-08-14 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-09-01 | 2015-09-11 | 2015-09-11 | Online
WMECO | Turners Falls | 6F939-2015 | 1376 | 1774 | Solar | 21C3 | 2015-06-05 | 2015-10-05 | 84 | 1 | 83 | 2015-10-06 |  | -30154 | [9 empty] | 0 | [14 empty] | 2015-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B553-2015 | 1201 | 1480 | Solar | 30B7 | 2015-06-08 | 2015-07-22 | 31 | 17 | 14 | 2015-07-23 | 2015-10-20 | 62 | 29 | 33 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | 2015-07-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2017-12-21 | Online
WMECO | Pittsfield | 6B554-2015 | 1201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 64 | 44 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 2015-07-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B555-2015 | 1201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 64 | 44 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 1901-12-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne Falls | 6F953-2015 | 1370 | 40 | Solar | 22B5 | 2015-06-10 | 2015-07-17 | 26 | 9 | 17 | 2015-07-20 | 2015-08-10 | 16 | 15 | 1 | 2015-08-20 | 2015-10-05 | 32 | 22 | 10 |  |  | 0 | [12 empty] | 2015-10-07 |  | 2015-08-01 |  | Expedited |  |  |  | 0 |  |  | 2015-12-23 | 2015-12-30 | 2015-12-30 | Online
WMECO | Easthampton | 6A1251-2015 | 1027 | 244 | Solar | 15A3 | 2015-06-15 | 2015-09-28 | 73 | 12 | 61 | 2015-09-29 |  | -30149 | 117 | [8 empty] | 0 | [14 empty] | 2015-07-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1252-2015 | 1093 | 496 | Solar | 18G8 | 2015-06-15 | 2015-07-17 | 23 | 18 | 5 | 2015-07-20 | 2015-11-02 | 74 | 21 | 53 | [7 empty] | 0 |  |  | 2015-11-03 | 2016-01-27 | 57 | 3 | 54 | 2016-03-09 |  | -30258 | 0 |  | 2016-02-04 |  | not supplied |  | Standard |  |  |  | 0 |  |  | 2017-02-28 | 2017-03-01 | 2017-03-02 | Online
WMECO | Springfield | 6S1174-2015 | 1104 | 150 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 59 | 40 | 19 | 2015-09-09 | 2016-06-01 | 181 | 95 | 86 | [7 empty] | 0 |  |  | 2016-06-02 | 2016-08-23 | 57 | 0 | 57 | 2016-09-14 |  | -30387 |  |  | 2016-09-14 |  | 2015-07-31 |  | Standard |  |  |  | 0 |  |  | 2017-10-05 | 2017-10-11 | 2017-10-26 | Online
WMECO | Springfield | 6S1175-2015 | 1104 | 284 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 59 | 40 | 19 | 2015-09-09 | 2016-06-01 | 181 | 95 | 86 | [7 empty] | 0 |  |  | 2016-06-02 | 2016-08-23 | 57 | 0 | 57 | 2016-09-14 |  | -30387 |  |  | 2016-09-14 |  | 1901-12-31 |  | Standard |  |  |  | 0 |  |  | 2018-01-17 | 2018-01-24 | 2018-01-30 | Online
WMECO | Pittsfield | 6B569-2015 | 1201 | 408 | Solar | 19A8 | 2015-06-18 | 2015-09-29 | 72 | 25 | 47 | 2015-09-30 |  | -30150 | [9 empty] | 0 | [14 empty] | 2015-07-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B571-2015 | 1223 | 10 | Solar | 19J6 | 2015-06-18 | 2015-07-22 | 24 | 23 | 1 | 2015-07-23 | 2015-08-20 | 21 | 2 | 19 | [7 empty] | 0 | [12 empty] | 2015-08-20 |  | 08-2015 |  | Expedited |  |  |  | 0 |  |  | 2016-01-25 | 2016-01-25 | 2016-01-25 | Online
WMECO | Shelburne | 6F969-2015 | 1370 | 16.7 | Solar | 22B6 | 2015-06-18 | 2015-07-30 | 30 | 13 | 17 | 2015-07-31 |  | -30108 | [9 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F970-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-10-06 | 77 | 1 | 76 | 2015-10-07 | 2015-12-30 | 57 | 33 | 24 | [7 empty] | 0 |  |  | 2015-12-31 |  | -30212 | [9 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F971-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 72 | 1 | 71 | 2015-09-30 | 2015-12-30 | 62 | 33 | 29 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | 2015-10-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chesterfield | 6F972-2015 | 1012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 72 | 1 | 71 | 2015-09-30 | 2015-12-30 | 62 | 33 | 29 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-09-26 |  | 2015-10-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1270-2015 | 1027 | 27 | Solar | 15A3 | 2015-06-19 | 2015-08-10 | 36 | 23 | 13 | 2015-08-11 | 2015-11-10 | 64 | 0 | 64 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-17 | 2015-12-18 | Online
WMECO | Blandford | 6B572-2015 | 1008 | 499 | Solar | 19J2 | 2015-06-19 | 2015-09-28 | 70 | 4 | 66 | 2015-09-29 |  | -30149 | [9 empty] | 0 | [14 empty] | Winter 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B579-2015 | 1201 | 170 | Solar | 30B2 | 2015-06-23 | 2015-09-08 | 54 | 34 | 20 | 2015-09-09 |  | -30135 | [9 empty] | 0 | [14 empty] | 2015-07-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F980-2015 | 1301 | 450 | Diesel | 21C4 | 2015-06-23 | 2015-09-29 | 69 | 17 | 52 | 2015-09-30 | 2016-02-23 | 98 | 18 | 80 | 2016-02-23 | 2016-10-05 | 156 | 5 | 151 |  |  | 0 | [12 empty] | 2016-10-06 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-12-07 | 2016-12-18 | 2016-12-19 | Online
WMECO | Plainfield | 6F986-2015 | 1070 | 392 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 65 | 0 | 65 | 2015-09-30 | 2015-11-05 | 26 |  | 26 | [7 empty] | 0 | [14 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F987-2015 | 1070 | 499 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 65 | 0 | 65 | 2015-09-30 | 2015-11-05 | 26 |  | 26 | [7 empty] | 0 | [14 empty] | 2015-10-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1298-2015 | 1375 | 242 | Solar | 18G3 | 2015-07-02 | 2015-12-21 | 118 | 30 | 88 | 2015-12-22 | 2016-01-28 | 25 | 9 | 16 | [7 empty] | 0 |  |  | 2016-01-28 | 2016-04-28 | 63 | 0 | 63 | [5 empty] | 2016-05-03 |  | winter 2015 |  | Standard |  |  |  | 0 |  |  | 2016-12-27 | 2016-12-28 | 2016-12-30 | Online
WMECO | Sunderland | 6A1309-2015 | 1375 | 160 | Solar | 18G3 | 2015-07-10 | 2015-12-21 | 113 | 25 | 88 | 2015-12-22 | 2016-01-28 | 25 | 9 | 16 | [7 empty] | 0 |  |  | 2016-01-28 | 2016-04-28 | 63 | 0 | 63 | [7 empty] | winter 2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6F1012-2015 | 1341 | 19.8 | Solar | 38A1 | 2015-07-14 | 2015-08-07 | 19 | 6 | 13 | 2015-08-10 | 2015-11-03 | 60 | 11 | 49 | 2015-11-12 | 2015-11-30 | 12 | 0 | 12 |  |  | 0 | [12 empty] | 2015-12-07 |  | 2015-09-01 |  | Expedited |  |  |  | 0 |  |  | 2016-03-04 | 2016-03-08 | 2016-03-08 | Online
WMECO | Easthampton | 6A1329-2015 | 1027 | 20.5 | Solar | 15A5 | 2015-07-15 | 2015-08-10 | 19 | 18 | 1 | 2015-08-11 | 2015-10-15 | 46 | 0 | 46 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | 2015-10-05 |  | Expedited |  |  |  | 0 |  |  | 2015-12-18 | 2015-12-22 | 2015-12-22 | Online
WMECO | Bernardston | 6F1028-2015 | 1337 | 36 | Solar | 21C1 | 2015-07-27 | 2015-09-23 | 42 | 5 | 37 | 2015-09-24 | 2015-10-13 | 13 | 3 | 10 | [7 empty] | 0 | [12 empty] | 2015-10-13 |  | Sept 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-17 | 2015-12-18 | Online
WMECO | Easthampton | 6A1343-2015 | 1027 | 1980 | Solar | 15A2 | 2015-07-30 | 2015-12-09 | 91 | 26 | 65 | 2015-12-10 |  | -30198 | [9 empty] | 0 | [14 empty] | 2016-05-28 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B624-2015 | 1201 | 995 | Solar | 30B7 | 2015-07-31 | 2015-08-06 | 5 | 3 | 2 | 2015-08-07 |  | -30113 | [9 empty] | 0 | [14 empty] | 10/1/2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B625-2015 | 1201 | 870 | Solar | 30B3 | 2015-08-03 | 2015-10-06 | 46 | 13 | 33 | 2015-10-07 | 2016-05-02 | 140 | 92 | 48 | [7 empty] | 0 |  |  | 2016-05-03 | 2016-07-19 | 53 | 32 | 21 | [7 empty] | 12/1/2015 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S1388-2015 | 1089 | 30 | Solar | 21N6 | 2015-08-03 | 2015-09-23 | 37 | 19 | 18 | 2015-09-24 | 2015-11-10 | 33 | 9 | 24 | [7 empty] | 0 | [12 empty] | 2015-11-16 |  | Q3 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-02-11 | 2016-02-17 | 2016-02-17 | Online
WMECO | Whately | 6A1350-2015 | 1093 | 1115 | Solar | 18G8 | 2015-08-04 | 2015-11-20 | 76 | 11 | 65 | 2015-11-23 | 2016-04-28 | 107 | 51 | 56 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 | 1 | 85 | 2016-10-31 |  | -30419 |  |  | 2016-10-03 |  | 2/28/16 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-10-01 | Online
WMECO | Hinsdale | 6B635-2015 | 1235 | 1484 | Solar | 18C2 | 2015-08-11 | [16 empty] | 0 | [14 empty] | 2015-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1366-2015 | 1035 | 32 | Solar | 17K5 | 2015-08-12 | 2015-10-22 | 50 | 39 | 11 | 2015-10-23 | 2015-11-03 | 8 | 0 | 8 | [7 empty] | 0 | [12 empty] | 2015-11-10 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-01-27 | 2016-01-29 | 2016-01-29 | Online
WMECO | Pittsfield | 6B640-2015 | 1201 | 54 | Solar | 30B2 | 2015-08-12 | 2015-09-23 | 30 | 5 | 25 | 2015-09-24 | 2015-12-29 | 65 | 47 | 18 | [7 empty] | 0 | [12 empty] | 2015-12-30 |  | 2015-07-01 |  | Expedited |  |  |  | 0 |  |  | 2016-05-13 | 2016-05-13 | 2016-05-13 | Online
WMECO | Springfield | 6S1435-2015 | 1104 | 140 | Solar | 5J16 | 2015-08-13 | 2015-09-24 | 30 | 5 | 25 | 2015-09-25 | 2016-02-05 | 90 | 19 | 71 | [7 empty] | 0 |  |  | 2016-02-08 | 2016-05-05 | 61 | 0 | 61 | 2016-10-06 |  | -30403 |  |  | 2016-05-05 |  | 2015-10-23 |  | Standard |  |  |  | 0 |  |  | 2017-09-20 | 2017-09-26 | 2017-10-06 | Online
WMECO | Sandisfield | 6B641-2015 | 1255 | 21.91 | Solar | 19J4 | 2015-08-14 | 2015-09-24 | 29 | 27 | 2 | 2015-09-25 |  | -30147 | [9 empty] | 0 | [14 empty] | 2015-10-13 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B655-2015 | 1201 | 1.8 | Solar | 30B7 | 2015-08-14 | 2015-09-23 | 28 | 21 | 7 | 2015-09-23 | 2016-04-08 | 135 | 105 | 30 | [7 empty] | 0 | [12 empty] | 2016-04-11 |  | 09302015 |  | Expedited |  |  |  | 0 |  |  | 2017-05-16 | 2017-05-30 | 2017-05-30 | Online
WMECO | Hatfield | 6A1390-2015 | 1066 | 584 | Solar | 18G6 | 2015-08-20 | 2015-11-17 | 61 | 4 | 57 | 2015-11-18 | 2016-02-16 | 60 | 28 | 32 | [7 empty] | 0 |  |  | 2016-02-17 |  | -30243 | [9 empty] | 2015-05-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sandisfield | 6B651-2015 | 1255 | 16.4 | Solar | 19J4 | 2015-08-21 | 2015-10-27 | 46 | 41 | 5 | 2015-10-28 | 2015-11-04 | 6 | 0 | 6 | 2015-12-02 | 2015-12-03 | 2 | 0 | 2 |  |  | 0 | [12 empty] | 2015-12-04 |  | Sept 2015 |  | Expedited |  |  |  | 0 |  |  | 2015-12-22 | 2015-12-24 | 2015-12-24 | Online
WMECO | Plainfield | 6F1072-2015 | 1070 | 1050 | Solar | 18K3 | 2015-08-24 | [16 empty] | 0 | [14 empty] | 2016-06-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S1476-2015 | 1077 | 18.4 | Solar | 29A5 | 2015-08-24 | 2015-10-02 | 29 | 12 | 17 | 2015-10-05 | 2016-03-24 | 116 | 95 | 21 | 2016-03-25 |  | -30269 |  |  |  |  | 0 | [14 empty] | 2015-10-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1481-2015 | 1030 | 17.25 | Solar | 16C17 | 2015-08-25 | 2015-10-22 | 41 | 30 | 11 | 2015-10-23 | 2015-10-28 | 4 | 0 | 4 | [7 empty] | 0 | [12 empty] | 2015-10-30 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-11 | 2015-12-14 | 2015-12-14 | Online
WMECO | West Hatfield | 6A1403-2015 | 1088 | 22.5 | Solar | 18G5 | 2015-08-28 | 2015-10-22 | 38 | 27 | 11 | 2015-10-22 | 2015-10-28 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2015-10-30 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2015-12-15 | 2015-12-16 | 2015-12-16 | Online
WMECO | Dalton | 6B667-2015 | 1226 | 25 | Solar | 18C1 | 2015-09-02 | 2015-11-05 | 45 | 33 | 12 | 2015-11-06 | 2016-01-06 | 40 | 22 | 18 | 2016-01-07 | 2016-01-13 | 5 | 2 | 3 |  |  | 0 | [12 empty] | 2016-01-13 |  | 2015-09-25 |  | Expedited |  |  |  | 0 |  |  | 2016-06-27 | 2016-06-29 | 2016-06-29 | Online
WMECO | Easthampton | 6A1411-2015 | 1027 | 2100 | Solar | 15A5 | 2015-09-03 | [16 empty] | 0 | [14 empty] | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1520-2015 | 1030 | 5440 | Solar | 30A6 | 2015-09-03 | [16 empty] | 0 | [14 empty] | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B670-2015 | 1201 | 1380 | Solar | 30B7 | 2015-09-04 | 2015-09-17 | 9 | 2 | 7 | 2015-09-17 | 2015-10-20 | 23 | 22 | 1 | [7 empty] | 0 |  |  | 2015-10-21 | 2016-03-30 | 109 | 0 | 109 | 2016-04-14 |  | -30283 |  |  | 2016-04-25 |  | July 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-04-17 | Online
WMECO | Springfield | 6S1550-2015 | 1109 | 1980 | Solar | 5J18 | 2015-09-04 | [16 empty] | 0 | [14 empty] | 2015-05-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1417-2015 | 1073 | 2000 | Solar | 15A1 | 2015-09-08 | 2015-11-09 | 44 | 35 | 9 | 2015-11-10 | 2016-02-05 | 59 | 14 | 45 | [7 empty] | 0 |  |  | 2016-02-05 | 2016-07-19 | 112 | 54 | 58 | 2016-07-20 | 2017-04-21 | 189 | 145 | 44 | 2017-04-28 |  | 2016-08-15 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-20 | Online
WMECO | Savoy | 6B673-2015 | 1256 | 2000 | Solar | 18C1 | 2015-09-08 | 2015-11-09 | 44 | 17 | 27 | 2015-11-10 | 2016-02-11 | 63 | 20 | 43 | [7 empty] | 0 |  |  | 2016-02-12 | 2016-07-15 | 105 | 50 | 55 | 2016-07-18 | 2017-04-20 | 190 | 145 | 45 | 2017-05-10 |  | 8/15/2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-12-19 | Online
WMECO | Hinsdale | 6B674-2015 | 1235 | 1000 | Solar | 18C2 | 2015-09-08 | 2015-11-16 | 48 | 27 | 21 | 2015-11-17 |  | -30182 | [9 empty] | 0 | [14 empty] | 8/15/2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1098-2015 | 1301 | 2000 | Solar | 21C1 | 2015-09-08 | 2015-11-13 | 47 | 36 | 11 | 2015-11-16 | 2016-01-07 | 36 | 22 | 14 | [7 empty] | 0 |  |  | 2016-01-08 | 2016-05-13 | 87 | 29 | 58 | 2016-10-31 |  | -30419 |  |  | 2017-05-22 |  | 2016-08-15 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-01-25 | Online
WMECO | Otis | 6B685-2015 | 1253 | 76.65 | Solar | 19J4 | 2015-09-14 | 2015-10-22 | 28 | 20 | 8 | 2015-10-23 | 2015-11-09 | 12 | 0 | 12 | [7 empty] | 0 | [14 empty] | 2015-10-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B689-2015 | 1235 | 2000 | Solar | 18C2 | 2015-09-15 | 2015-11-16 | 43 | 27 | 16 | 2015-11-17 | 2016-08-30 | 196 | 152 | 44 | [7 empty] | 0 |  |  | 2016-08-31 | 2017-03-08 | 128 | 40 | 88 | 2017-03-09 |  | -30506 |  |  | 2017-04-12 |  | 2016-08-15 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-19 | Online
WMECO | Springfield | 6S1577-2015 | 1119 | 16.7 | Solar | 20A12 | 2015-09-18 | 2015-11-20 | 44 | 18 | 26 | 2015-11-23 | 2015-12-21 | 20 | 17 | 3 | 2015-12-22 | 2016-01-14 | 16 | 0 | 16 |  |  | 0 | [12 empty] | 2016-01-25 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-04-21 | 2016-04-27 | 2016-04-27 | Online
WMECO | Springfield | 6S1588-2015 | 1107 | 5300 | Natural Gas | 21S8 | 2015-09-22 | 2015-12-01 | 48 | 10 | 38 | 2015-12-02 | 2016-02-22 | 55 | 18 | 37 | 2016-02-23 | 2016-04-27 | 45 | 11 | 34 |  |  | 0 | [12 empty] | 2016-04-29 |  | June 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-06 | Online
WMECO | Southampton | 6A1443-2015 | 1073 | 49.55 | Solar | 15A1 | 2015-09-23 | 2015-11-03 | 29 | 20 | 9 | 2015-11-04 | 2015-12-24 | 35 | 22 | 13 | 2015-12-28 | 2016-02-29 | 43 | 3 | 40 |  |  | 0 | [12 empty] | 2016-03-01 |  | 2015-10-12 |  | Expedited |  |  |  | 0 |  |  | 2016-09-09 | 2016-09-14 | 2016-09-14 | Online
WMECO | Lenox | 6B702-2015 | 1201 | 448 | Solar | 17G3 | 2015-09-23 | 2015-11-02 | 28 | 3 | 25 | 2015-11-03 | 2015-12-23 | 35 | 25 | 10 | [7 empty] | 0 |  |  | 2015-12-24 | 2016-02-11 | 33 | 4 | 29 | 2016-02-18 |  | -30244 |  |  | 2016-02-11 |  | 2016-03-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2017-04-12 | Online
WMECO | Southwick | 6S1590-2015 | 1077 | 500 | Solar | 29A5 | 2015-09-23 | 2015-12-01 | 47 | 7 | 40 | 2015-12-02 | 2016-03-18 | 73 | 42 | 31 | [7 empty] | 0 |  |  | 2016-03-21 | 2016-08-22 | 107 | 0 | 107 | [5 empty] | 2016-08-22 |  | 12/1/2015 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6F1134-2015 | 1354 | 1992 | Solar | 21B8 | 2015-09-24 | 2015-11-04 | 29 | 3 | 26 | 2015-11-05 | 2016-02-18 | 70 | 9 | 61 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-04-27 | 47 | 9 | 38 | 2016-05-06 |  | -30298 |  |  | 2016-04-27 |  | 2016-03-01 |  | Complex |  |  |  | 0 |  |  | 2017-12-29 | 2017-12-05 | 2018-01-18 | Online
WMECO | Greenfield | 6F1135-2015 | 1301 | 43.8 | Solar | 22B7 | 2015-09-25 | 2015-10-08 | 10 | 5 | 5 | 2015-10-09 | 2016-02-04 | 79 | 50 | 29 | 2016-02-04 | 2016-02-17 | 9 | 1 | 8 |  |  | 0 | [12 empty] | 2016-02-17 |  | Jan 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S1604-2015 | 1077 | 2000 | Solar | 29A5 | 2015-09-25 | 2015-12-04 | 48 | 26 | 22 | 2015-12-07 |  | -30195 | [9 empty] | 0 | [14 empty] | 8/15/2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S1610-2015 | 1089 | 112 | Solar | 21N5 | 2015-09-28 | 2015-12-17 | 56 | 49 | 7 | 2015-12-18 |  | -30204 | [9 empty] | 0 | [14 empty] | Nov 31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1149-2016 | 1070 | 499 | Solar | 18K3 | 2015-10-02 | 2015-10-22 | 14 | 5 | 9 | 2015-10-23 | 2015-11-05 | 10 |  | 10 | [7 empty] | 0 | [14 empty] | 2016-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1150-2015 | 1070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 56 | 33 | 23 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  |  |  | 2016-04-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1151-2015 | 1070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 56 | 33 | 23 | [7 empty] | 0 |  |  | 2015-12-31 | 2016-09-09 | 173 | 59 | 114 | 2016-09-12 |  | -30385 |  |  | 2016-12-22 |  | 2016-04-30 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-15 | Online
WMECO | Amherst | 6A1467-2015 | 1002 | 15.3 | Solar | 17K2 | 2015-10-06 | 2015-11-23 | 33 | 5 | 28 | 2015-11-24 | 2016-03-02 | 67 | 52 | 15 | 2016-03-03 |  | -30254 | 9 |  |  |  | 0 | [14 empty] | 2015-12-05 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A1468-2015 | 1038 | 900 | Solar | 18G5 | 2015-10-06 | 2016-01-13 | 67 | 24 | 43 | 2016-01-14 |  | -30221 | [9 empty] | 0 | [14 empty] | 2015-11-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1673-2015 | 1102 | 1000 | Diesel | 21S3 | 2015-10-09 | 2016-02-23 | 91 | 51 | 40 | 2016-02-24 | 2016-04-04 | 28 | 17 | 11 | 2016-04-05 | 2016-04-12 | 6 | 0 | 6 |  |  | 0 | [12 empty] | 2016-04-13 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1481-2015 | 1093 | 2000 | Solar | 18G8 | 2015-10-15 | 2015-12-11 | 40 | 5 | 35 | 2015-12-14 |  | -30200 | [9 empty] | 0 | [14 empty] | Summer 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1680-2015 | 1128 | 600 | Diesel | 20A34 | 2015-10-15 | 2016-01-20 | 65 | 11 | 54 | 2016-01-21 | 2016-04-14 | 59 | 49 | 10 | 2016-04-15 | 2016-09-08 | 100 | 10 | 90 |  |  | 0 | [12 empty] | 2016-09-09 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-25 | Online
WMECO | Agawam | 6S1687-2015 | 1001 | 999 | Solar | 30A3 | 2015-10-19 | 2015-12-07 | 34 | 2 | 32 | 2015-12-08 |  | -30196 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S1697-2015 | 1001 | 500 | Solar | 16C16 | 2015-10-21 | 2015-12-22 | 43 | 41 | 2 | 2015-12-23 | 2016-04-22 | 82 | 40 | 42 | [7 empty] | 0 |  |  | 2016-04-25 | 2016-08-15 | 78 | 0 | 78 | [7 empty] | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S1698-2015 | 1056 | 311 | Solar | 19S2 | 2015-10-21 | 2015-12-02 | 29 | 5 | 24 | 2015-12-03 | 2016-02-18 | 52 | 43 | 9 | [7 empty] | 0 |  |  | 2016-02-19 | 2016-05-11 | 57 | 0 | 57 | [5 empty] | 2016-05-11 |  | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S1699-2015 | 1001 | 500 | Solar | 16C16 | 2015-10-21 | 2016-01-20 | 61 | 1 | 60 | 2016-01-21 | 2016-04-22 | 64 | 40 | 24 | [7 empty] | 0 |  |  | 2016-04-25 | 2016-08-15 | 78 | 0 | 78 | [7 empty] | 2016-08-11 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S1797-2015 | 1056 | 16.7 | Solar | 19S1 | 2015-10-27 | [16 empty] | 0 | [14 empty] | 2015-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Buckland | 6F1201-2015 | 1338 | 16.7 | Solar | 38A1 | 2015-10-28 | 2015-11-30 | 22 | 18 | 4 | 2015-12-01 | 2015-12-15 | 11 | 5 | 6 | [7 empty] | 0 | [12 empty] | 2015-12-15 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-03-07 | 2016-03-09 | 2016-03-09 | Online
WMECO | Montague | 6F1203-2015 | 1351 | 408 | Solar | 21C3 | 2015-10-28 | 2016-01-27 | 61 | 3 | 58 | 2016-01-28 | 2016-06-10 | 93 | 35 | 58 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 |  | 51 | [7 empty] | June 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1730-2015 | 1108 | 299.16 | Solar | 22H17 | 2015-10-29 | 2016-03-08 | 88 | 28 | 60 | 2016-03-09 |  | -30258 | [9 empty] | 0 | [14 empty] | 2015-03-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1208-2015 | 1351 | 1992 | Solar | 21C3 | 2015-10-30 | 2016-01-27 | 59 | 1 | 58 | 2016-01-28 | 2016-06-10 | 93 | 35 | 58 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 | 0 | 51 | [7 empty] | June 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1209-2015 | 1351 | 4176 | Solar | 21C2 | 2015-10-30 | 2016-02-16 | 72 | 11 | 61 | 2016-02-17 | 2016-06-10 | 80 | 35 | 45 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-24 | 51 | 0 | 51 | 2016-11-08 |  | -30425 |  |  | 2016-09-23 |  | June 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-09-24 | Online
WMECO | Ashfield | 6F1210-2015 | 1330 | 45.6 | Solar | 38A1 | 2015-11-02 | 2015-11-19 | 13 | 7 | 6 | 2015-11-20 | 2016-01-19 | 39 | 17 | 22 | 2016-01-20 | 2016-01-29 | 8 | 0 | 8 |  |  | 0 | [12 empty] | 2016-02-03 |  | Nov 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-05-26 | 2016-05-27 | 2016-05-27 | Online
WMECO | Longmeadow | 6S1804-2015 | 1106 | 18 | Solar | 22H17 | 2015-11-03 | 2015-12-15 | 29 | 12 | 17 | 2015-12-15 | 2015-12-17 | 3 | 2 | 1 | [7 empty] | 0 | [12 empty] | 2015-12-17 |  | 2015-12-26 |  | Expedited |  |  |  | 0 |  |  | 2016-06-20 | 2016-06-27 | 2016-06-27 | Online
WMECO | Southwick | 6S1756-2015 | 1077 | 478 | Solar | 29A5 | 2015-11-06 | 2016-01-20 | 49 | 21 | 28 | 2016-01-20 | 2016-03-18 | 41 | 40 | 1 | [7 empty] | 0 |  |  | 2016-03-21 | 2016-08-22 | 107 | 0 | 107 | [5 empty] | 2016-08-22 |  | 2016-02-03 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Hatfield | 6A1528-2015 | 1088 | 292 | Solar | 18G5 | 2015-11-09 | 2015-12-22 | 30 | 12 | 18 | 2015-12-23 |  | -30207 | [9 empty] | 0 | [14 empty] | 2015-03-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6F1233-2015 | 1070 | 22.8 | Solar | 18K3 | 2015-11-10 | 2015-11-23 | 9 | 4 | 5 | 2015-11-24 | 2015-12-15 | 15 | 4 | 11 | [7 empty] | 0 | [12 empty] | 2015-12-15 |  | Nov 2015 |  | Expedited |  |  |  | 0 |  |  | 2016-04-01 | 2016-04-05 | 2016-04-05 | Online
WMECO | Otis | 6B789-2015 | 1253 | 2000 | Solar | 19J4 | 2015-11-13 | 2016-02-02 | 54 | 7 | 47 | 2016-02-03 |  | -30234 | [9 empty] | 0 | [14 empty] | 2016-07-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1795-2015 | 1030 | 15.3 | Solar | 16C17 | 2015-11-13 | 2015-12-04 | 15 | 8 | 7 | 2015-12-07 | 2015-12-10 | 4 | 0 | 4 | [7 empty] | 0 | [12 empty] | 2016-01-08 |  | 2016-01-13 |  | Expedited |  |  |  | 0 |  |  | 2016-03-23 | 2016-04-11 | 2016-04-11 | Online
WMECO | South Deerfield | 6F1241-2015 | 1373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 20 | 1 | 19 | 2015-12-15 |  | -30201 | [9 empty] | 0 | [14 empty] | Spring 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6F1242-2015 | 1373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 20 | 1 | 19 | 2015-12-15 |  | -30201 | [9 empty] | 0 | [14 empty] | Spring 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1796-2015 | 1104 | 1985 | Solar | 5J18 | 2015-11-16 | 2015-12-21 | 25 | 1 | 24 | 2015-12-22 | 2016-02-23 | 42 | 17 | 25 | [7 empty] | 0 |  |  | 2016-02-24 | 2016-05-02 | 47 | 0 | 47 | 2016-05-12 |  | -30302 | 7 |  | 2016-05-02 |  | 2016-05-31 |  | Standard |  |  |  | 0 |  |  | 2017-06-19 | 2017-06-26 | 2017-06-26 | Online
WMECO | Hadley | 6A1553-2015 | 1035 | 570 | Biogas | 19B15 | 2015-11-20 | 2016-02-24 | 64 | 63 | 1 | 2016-02-25 | 2016-04-20 | 38 | 36 | 2 | [7 empty] | 0 |  |  | 2016-04-21 | 2016-07-11 | 55 | 45 | 10 | 2016-08-22 |  | -30371 |  |  | 2016-08-17 |  | 4/30/2016 |  | Standard |  |  |  | 0 |  |  | 2017-06-30 | 2017-07-13 | 2017-07-13 | Online
WMECO | Whately | 6A1560-2015 | 1093 | 504 | Solar | 18G8 | 2015-11-24 | 2015-12-16 | 16 | 3 | 13 | 2015-12-17 | 2016-04-28 | 90 | 51 | 39 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 |  | 86 | [7 empty] | March 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B807-2015 | 1201 | 72 | Solar | 19A7 | 2015-12-01 | 2016-01-06 | 25 | 5 | 20 | 2016-01-07 | 2016-02-10 | 24 | 11 | 13 | [7 empty] | 0 | [12 empty] | 2016-02-10 |  | 1st qtr 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-05-20 | 2016-05-24 | 2016-05-24 | Online
WMECO | Whately | 6A1570-2015 | 1093 | 2000 | Solar | 18G8 | 2015-12-02 | 2015-12-11 | 8 | 0 | 8 | 2015-12-14 | 2016-04-28 | 93 | 51 | 42 | [7 empty] | 0 |  |  | 2016-04-29 | 2016-08-31 | 86 | 7 | 79 | 2016-10-31 |  | -30419 |  |  | 2016-10-03 |  | Sept 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-20 | Online
WMECO | Lee | 6B809-2015 | 1238 | 2000 | Solar | 16B5 | 2015-12-03 | 2016-02-11 | 48 | 9 | 39 | 2016-02-12 | 2016-04-04 | 35 | 12 | 23 | [7 empty] | 0 |  |  | 2016-04-05 | 2016-08-05 | 85 | 73 | 12 | [7 empty] | 2016-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6F1262-2015 | 1373 | 452 | Solar | 15E1 | 2015-12-04 | 2016-02-02 | 40 | 2 | 38 | 2016-02-03 |  | -30234 | [9 empty] | 0 | [14 empty] | 2016-03-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1578-2015 | 1027 | 496 | Solar | 15A2 | 2015-12-09 | 2016-01-28 | 34 | 25 | 9 | 2016-01-29 | 2016-06-03 | 87 | 49 | 38 | [7 empty] | 0 |  |  | 2016-06-06 | 2016-09-23 | 77 | 0 | 77 | [5 empty] | 2016-09-23 |  | June 2016 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Indian Orchard | 6S1915-2015 | 1151 | 1931.4 | Solar | 27A12 | 2015-12-15 | 2016-02-10 | 39 | 18 | 21 | 2016-02-11 | 2016-03-17 | 24 | 12 | 12 | [7 empty] | 0 |  |  | 2016-03-18 | 2016-08-08 | 98 | 17 | 81 | [5 empty] | 2016-08-12 |  | 2015-08-01 |  | Standard |  |  |  | 0 |  |  | 2017-02-10 | 2017-02-16 | 2017-02-16 | Online
WMECO | Hadley | 6A1588-2015 | 1035 | 1995.4 | Solar | 17K6 | 2015-12-16 | 2016-04-15 | 83 | 42 | 41 | 2016-04-19 | 2016-08-12 | 81 | 51 | 30 | [7 empty] | 0 |  |  | 2016-08-15 | 2016-12-01 | 75 | 0 | 75 | 2017-01-05 |  | -30463 |  |  | 2017-04-14 |  | Sept 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-01-16 | Online
WMECO | Hadley | 6A1589-2015 | 1035 | 1995.4 | Solar | 17K1 | 2015-12-16 | 2016-04-15 | 83 | 42 | 41 | 2016-04-19 | 2016-08-12 | 81 | 51 | 30 | [7 empty] | 0 |  |  | 2016-08-15 | 2017-01-27 | 113 | 24 | 89 | 2017-02-21 |  | -30494 |  |  | 2017-04-14 |  | Sept 2016 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-01-16 | Online
WMECO | Amherst | 6A1599-2015 | 1002 | 19.3 | Solar | 17K8 | 2015-12-16 | 2016-01-21 | 24 | 13 | 11 | 2016-01-21 | 2016-02-08 | 13 | 9 | 4 | [7 empty] | 0 | [12 empty] | 2016-02-08 |  | 02/16/2016 |  | Expedited |  |  |  | 0 |  |  | 2016-11-30 | 2016-12-01 | 2016-12-01 | Online
WMECO | Hinsdale | 6B826-2015 | 1235 | 1988 | Solar | 18C2 | 2015-12-16 | 2016-02-23 | 46 | 16 | 30 | 2016-02-24 | 2016-06-10 | 75 | 37 | 38 | [7 empty] | 0 |  |  | 2016-06-13 | 2016-08-10 | 41 | 0 | 41 | 2016-09-09 |  | -30384 |  |  | 2016-08-19 |  | 2015-09-01 |  | Standard |  |  |  | 0 |  |  | 2017-11-17 | 2017-11-20 | 2017-11-21 | Online
WMECO | Amherst | 6A1600-2015 | 1006 | 16.7 | Solar | 18G7 | 2015-12-18 | 2016-01-07 | 13 | 8 | 5 | 2016-01-08 | 2016-02-10 | 23 | 21 | 2 | 2016-02-11 | 2016-02-28 | 11 | 0 | 11 |  |  | 0 | [12 empty] | 2016-02-29 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1953-2015 | 1030 | 16.4 | Solar | 16C17 | 2015-12-23 | 2016-01-06 | 9 | 1 | 8 | 2016-01-06 | 2016-01-06 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-02-01 |  | 2016-02-16 |  | Expedited |  |  |  | 0 |  |  | 2016-08-15 | 2016-08-23 | 2016-08-23 | Online
WMECO | Middlefield | 6F1294-2015 | 1243 | 32.85 | Solar | 18C2 | 2015-12-24 | 2016-01-19 | 16 | 7 | 9 | 2016-01-19 | 2016-07-15 | 123 | 98 | 25 | [7 empty] | 0 | [12 empty] | 2016-07-15 |  | 2015-12-31 |  | Expedited |  |  |  | 0 |  |  | 2016-09-07 | 2016-09-13 | 2016-09-13 | Online
WMECO | Amherst | 6A1612-2015 | 1003 | 154 | Solar | 18G2 | 2015-12-28 | 2016-01-12 | 11 | 6 | 5 | 2016-01-13 | 2016-03-02 | 34 | 33 | 1 | 2016-03-03 | 2016-04-21 | 34 | 2 | 32 |  |  | 0 | [12 empty] | 2016-04-22 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S1979-2015 | 1129 | 343 | Solar | 20A23 | 2015-12-28 | 2016-01-28 | 22 | 20 | 2 | 2016-01-29 |  | -30231 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S1978-2015 | 1030 | 20.925 | Solar | 16C17 | 2015-12-29 | 2016-01-20 | 15 | 9 | 6 | 2016-01-21 | 2016-02-17 | 19 | 17 | 2 | 2016-02-18 |  | -30244 |  |  |  |  | 0 | [16 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B851-2016 | 1201 | 1000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Hancock | 6B852-2016 | 1237 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Hancock | 6B853-2016 | 1201 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 71 | 38 | 33 | 2016-04-15 | 2016-05-16 | 21 | 13 | 8 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-15 |  | not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2017-11-20 | Online
WMECO | Southwick | 6S1998-2016 | 1077 | 16.7 | Solar | 29A5 | 2016-01-05 | 2016-01-08 | 4 | 2 | 2 | 2016-01-08 |  | -30217 | [9 empty] | 0 | [14 empty] | 2016-03-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1621-2016 | 1002 | 17 | Solar | 19B16 | 2016-01-07 | 2016-01-22 | 11 | 6 | 5 | 2016-01-23 | 2016-02-09 | 12 | 0 | 12 | [7 empty] | 0 | [12 empty] | 2016-02-10 |  | 2016-05-01 |  | Expedited |  |  |  | 0 |  |  | 2016-06-23 | 2016-06-27 | 2016-06-27 | Online
WMECO | Amherst | 6A1622-2016 | 1002 | 27 | Solar | 17K5 | 2016-01-07 | 2016-03-02 | 38 | 19 | 19 | 2016-03-02 | 2016-06-13 | 71 | 63 | 8 | [7 empty] | 0 | [12 empty] | 2016-06-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-09-08 | 2016-09-21 | 2016-09-21 | Online
WMECO | West Springfield | 6S2018-2016 | 1089 | 24 | Solar | 21N9 | 2016-01-08 | 2016-01-14 | 5 | 1 | 4 | 2016-01-14 | 2016-04-04 | 55 | 54 | 1 | 2016-04-05 | 2016-07-19 | 72 | 0 | 72 |  |  | 0 | [12 empty] | 2016-08-04 |  | 2016-03-07 |  | Expedited |  |  |  | 0 |  |  | 2017-01-04 | 2017-01-06 | 2017-01-06 | Online
WMECO | Whately | 6A1625-2016 | 1093 | 16.7 | Solar | 18G8 | 2016-01-12 | 2016-01-20 | 6 | 1 | 5 | 2016-01-20 | 2016-02-09 | 15 | 9 | 6 | [7 empty] | 0 | [12 empty] | 2016-02-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B864-2016 | 1226 | 495.28 | Solar | 19A3 | 2016-01-12 | 2016-07-01 | 118 | 92 | 26 | 2016-07-05 |  | -30337 | [9 empty] | 0 | [14 empty] | 2016-09-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2043-2016 | 1109 | 16.7 | Solar | 20A32 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-29 | 14 | 10 | 4 | [7 empty] | 0 | [12 empty] | 2016-03-18 |  | 2016-02-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2044-2016 | 1118 | 14.35 | Solar | 20A32 | 2016-01-19 | [16 empty] | 0 | [14 empty] | 2016-02-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S2053-2016 | 1106 | 16.7 | Solar | 22H12 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-17 | 6 | 5 | 1 | [7 empty] | 0 | [12 empty] | 2016-02-19 |  | 2016-02-04 |  | Expedited |  |  |  | 0 |  |  | 2016-04-21 | 2016-04-25 | 2016-04-25 | Online
WMECO | Amherst | 6A1637-2016 | 1002 | 99 | Solar | 19B15 | 2016-01-20 | 2016-01-27 | 6 | 4 | 2 | 2016-01-28 | 2016-02-23 | 18 | 0 | 18 | [7 empty] | 0 | [12 empty] | 2016-02-23 |  | Feb 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-06-15 | 2016-06-16 | 2016-06-16 | Online
WMECO | Agawam | 6S2068-2016 | 1001 | 45 | Solar | 16C16 | 2016-01-22 | 2016-02-11 | 15 | 9 | 6 | 2016-02-11 | 2016-02-18 | 5 | 3 | 2 | [7 empty] | 0 | [12 empty] | 2016-02-22 |  | 2016-03-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2016-09-20 | Online
WMECO | Whately | 6A1647-2016 | 1093 | 1992 | Solar | 18G8 | 2016-01-27 | 2016-02-04 | 7 | 1 | 6 | 2016-02-05 |  | -30236 | [9 empty] | 0 | [14 empty] | Summer 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1652-2016 | 1093 | 1548 | Solar | 18G8 | 2016-01-29 | [16 empty] | 0 | [14 empty] | Summer 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2094-2016 | 1104 | 140 | Solar | 5J11 | 2016-02-02 | 2017-02-13 | 257 | 223 | 34 | 2017-02-14 |  | -30490 | [9 empty] | 0 | [14 empty] | 3/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2095-2016 | 1001 | 250 | Solar | 30A6 | 2016-02-02 | 2016-09-08 | 151 | 149 | 2 | 2016-09-09 | 2017-01-27 | 95 | 88 | 7 | 2017-01-30 | 2017-03-01 | 22 | 0 | 22 |  |  | 0 | [14 empty] | 3/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B887-2016 | 1201 | 625.8 | Solar | 30B7 | 2016-02-03 | 2016-03-08 | 24 | 9 | 15 | 2016-03-09 | 2016-05-16 | 47 | 13 | 34 | [7 empty] | 0 |  |  | 2016-05-17 | 2016-08-10 | 59 | 0 | 59 | 2016-08-31 |  | -30378 |  |  | 2016-08-16 |  | 2016-04-01 |  | Standard |  |  |  | 0 |  |  | 2017-11-28 | 2017-12-01 | 2017-12-18 | Online
WMECO | Westhampton | 6A1661-2016 | 1027 | 566.1 | Solar | 15A3 | 2016-02-04 | 2016-04-05 | 42 | 21 | 21 | 2016-04-06 | 2016-07-22 | 74 | 71 | 3 | [7 empty] | 0 |  |  | 2016-07-25 | 2016-10-07 | 54 |  | 54 | [7 empty] | 2016-04-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A1662-2016 | 1093 | 8.35 | Solar | 18G6 | 2016-02-04 | 2016-04-11 | 46 | 44 | 2 | 2016-04-11 | 2016-05-04 | 17 | 16 | 1 | 2016-05-05 |  | -30297 |  |  |  |  | 0 | [14 empty] | 2016-04-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B896-2016 | 1201 | 390 | Solar | 19A7 | 2016-02-10 | 2016-05-03 | 57 | 23 | 34 | 2016-05-04 |  | -30296 | [9 empty] | 0 | [14 empty] | not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1697-2015 | 1002 | 22.7 | Solar | 18G7 | 2016-02-22 | 2016-03-10 | 14 | 10 | 4 | 2016-03-10 |  | -30259 | [9 empty] | 0 | [14 empty] | 2016-03-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1704-2016 | 1375 | 288 | Solar | 18G3 | 2016-02-23 | 2016-05-04 | 50 | 44 | 6 | 2016-05-05 |  | -30297 | [9 empty] | 0 | [14 empty] | 2016-05-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Sunderland | 6A1708-2016 | 1375 | 22.5 | Solar | 18G8 | 2016-02-23 | 2016-04-13 | 36 | 6 | 30 | 2016-04-13 | 2016-04-14 | 2 | 1 | 1 | [7 empty] | 0 | [12 empty] | 2016-04-15 |  | not supplied |  | Expedited |  |  |  | 0 |  |  | 2016-06-08 | 2016-06-09 | 2016-06-09 | Online
WMECO | South Deerfield | 6F1389-2016 | 1373 | 1000 | Biogas | 22B1 | 2016-02-25 | 2016-04-13 | 34 | 12 | 22 | 2016-04-14 | 2016-07-01 | 54 | 20 | 34 | [7 empty] | 0 |  |  | 2016-07-05 | 2016-10-06 | 67 | 0 | 67 | 2016-10-19 |  | -30411 |  |  | 2016-10-12 |  | 6/20/16 |  | Complex |  |  |  | 0 |  |  | 2017-12-06 | 2017-12-11 | 2017-12-11 | Online
WMECO | Otis | 6B923-2016 | 1253 | 40.75 | Solar | 19J4 | 2016-03-01 | [16 empty] | 0 | [14 empty] | 2016-05-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A1736-2016 | 1035 | 16.4 | Solar | 18G4 | 2016-03-03 | 2016-03-10 | 6 | 2 | 4 | 2016-03-10 |  | -30259 | [9 empty] | 0 | [14 empty] | 2016-05-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Buckland | 6F1417-2016 | 1338 | 25.425 | Solar | 38A1 | 2016-03-04 | 2016-06-27 | 78 | 74 | 4 | 2016-06-27 |  | -30332 | [9 empty] | 0 | [14 empty] | 2016-04-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2185-2016 | 1001 | 22.95 | Solar | 16C17 | 2016-03-04 | 2016-03-21 | 11 | 3 | 8 | 2016-03-21 | 2016-03-28 | 6 | 5 | 1 | 2016-03-29 |  | -30271 |  |  |  |  | 0 | [14 empty] | 2016-04-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A1743-2016 | 1002 | 19.75 | Solar | 18G4 | 2016-03-07 | 2016-03-14 | 6 | 5 | 1 | 2016-03-15 |  | -30262 | 15 | [8 empty] | 0 | [14 empty] | Q2 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2199-2016 | 1001 | 22.95 | Solar | 16C17 | 2016-03-08 | [16 empty] | 0 | [14 empty] | 2016-04-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A1754-2016 | 1027 | 180 | Solar | 15A2 | 2016-03-09 | 2016-04-15 | 27 | 0 | 27 | 2016-04-19 | 2016-06-03 | 33 | 25 | 8 | [7 empty] | 0 |  |  | 2016-06-06 | 2016-09-23 | 77 | 0 | 77 | [5 empty] | 2016-09-23 |  | 5/2016 |  | Standard |  |  |  | 0 |  |  | 2017-03-28 | 2017-04-04 | 2017-04-04 | Online
WMECO | Amherst | 6A1755-2016 | 1002 | 60 | Solar | 17K4 | 2016-03-09 | 2016-04-06 | 20 | 11 | 9 | 2016-04-06 | 2016-04-12 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2016-04-13 |  | May 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-10-04 | 2016-10-06 | 2016-10-06 | Online
WMECO | Hadley | 6A1766-2016 | 1035 | 84 | Solar | 18G5 | 2016-03-11 | 2016-03-21 | 6 | 0 | 6 | 2016-03-21 | 2016-06-20 | 63 | 62 | 1 | 2016-06-21 | 2016-07-18 | 19 | 0 | 19 |  |  | 0 | [12 empty] | 2016-07-19 |  | 3/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-03-21 | 2017-03-22 | 2017-03-22 | Online
WMECO | Southampton | 6A1767-2016 | 1073 | 23.45 | Solar | 15A1 | 2016-03-11 | 2016-04-11 | 21 | 17 | 4 | 2016-04-11 |  | -30280 | [9 empty] | 0 | [14 empty] | 5/10/16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F1439-2016 | 1342 | 75 | Solar | 22B3 | 2016-03-11 | 2016-08-10 | 104 | 90 | 14 | 2016-08-10 | 2016-11-30 | 77 | 68 | 9 | [7 empty] | 0 | [12 empty] | 2016-12-05 |  | 5/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-12-12 | 2017-12-13 | 2018-04-23 | Online
WMECO | Turners Falls | 6F1440-2016 | 1376 | 19.3 | Solar | 21C6 | 2016-03-14 | 2016-03-25 | 9 | 8 | 1 | 2016-03-25 | 2016-03-31 | 5 | 4 | 1 | [7 empty] | 0 | [12 empty] | 2016-03-31 |  | 2015-11-09 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hancock | 6B939-2016 | 1237 | 42.25 | Solar | 30B7 | 2016-03-17 | [16 empty] | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6F1449-2016 | 1342 | 64 | Solar | 22B3 | 2016-03-17 | 2016-06-27 | 69 | 56 | 13 | 2016-06-28 | 2016-08-11 | 32 | 26 | 6 | [7 empty] | 0 | [12 empty] | 2016-08-11 |  | 6/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-09-22 | 2017-10-04 | 2018-04-25 | Online
WMECO | Springfield | 6S2233-2016 | 1105 | 16.95 | Solar | 21S11 | 2016-03-17 | 2016-07-26 | 89 | 80 | 9 | 2016-07-26 | 2016-09-16 | 38 | 37 | 1 | 2016-09-19 |  | -30390 |  |  |  |  | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cheshire | 6B947-2016 | 1225 | 16.7 | Solar | 19A5 | 2016-03-18 | 2016-03-30 | 9 | 7 | 2 | 2016-03-30 |  | -30272 | [9 empty] | 0 | [14 empty] | 2016-04-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2236-2016 | 1077 | 21.9 | Solar | 29A5 | 2016-03-22 | 2016-04-07 | 13 | 12 | 1 | 2016-04-07 | 2016-04-28 | 15 | 14 | 1 | 2016-04-29 | 2016-05-20 | 16 | 0 | 16 |  |  | 0 | [12 empty] | 2016-05-26 |  | 2016-06-17 |  | Expedited |  |  |  | 0 |  |  | 2017-03-06 | 2017-03-09 | 2017-03-09 | Online
WMECO | Springfield | 6S2248-2016 | 1109 | 72 | Solar | 5J15 | 2016-03-24 | 2016-04-05 | 9 | 7 | 2 | 2016-04-05 | 2016-05-30 | 38 | 30 | 8 | [7 empty] | 0 | [12 empty] | 2016-06-01 |  | July 2015 |  | Expedited |  |  |  | 0 |  |  | 2017-03-31 | 2017-04-05 | 2017-04-05 | Online
WMECO | West Springfield | 6S2264-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-03-29 | 2016-04-07 | 8 | 7 | 1 | 2016-04-07 |  | -30278 | [9 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B960-2016 | 1201 | 21.9 | Solar | 15E2 | 2016-04-05 | 2016-05-03 | 20 | 18 | 2 | 2016-05-03 | 2016-07-12 | 48 | 39 | 9 | 2016-07-13 |  | -30343 |  |  |  |  | 0 | [14 empty] | 2016-04-23 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B973-2016 | 1237 | 16.4 | Solar | 15E1 | 2016-04-11 | 2016-04-19 | 6 | 5 | 1 | 2016-04-19 | 2016-05-09 | 15 | 14 | 1 | 2016-05-10 | 2016-05-10 | 1 | 0 | 1 |  |  | 0 | [12 empty] | 2016-05-16 |  | 2016-05-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2294-2016 | 1001 | 45.9 | Solar | 16C17 | 2016-04-11 | 2016-05-03 | 16 | 13 | 3 | 2016-05-03 | 2016-05-11 | 7 | 6 | 1 | 2016-05-12 | 2016-05-18 | 5 | 0 | 5 |  |  | 0 | [12 empty] | 2016-05-27 |  | 2016-05-28 |  | Expedited |  |  |  | 0 |  |  |  |  | 2016-07-27 | Online
WMECO | Agawam | 6S2295-2016 | 1001 | 46.8 | Solar | 16C18 | 2016-04-11 | 2016-05-03 | 16 | 14 | 2 | 2016-05-03 | 2016-05-03 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-05-05 |  | 2016-05-28 |  | Expedited |  |  |  | 0 |  |  | 2016-08-09 | 2016-08-11 | 2016-08-11 | Online
WMECO | Montague | 6F1484-2016 | 1351 | 18 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 9 | 8 | 1 | 2016-04-25 |  | -30289 | [9 empty] | 0 | [14 empty] | July 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1485-2016 | 1351 | 56.35 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 9 | 8 | 1 | 2016-04-25 | 2016-05-20 | 20 | 18 | 2 | [7 empty] | 0 | [12 empty] | 2016-05-26 |  | July 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-01-18 | 2017-01-26 | 2017-01-26 | Online
WMECO | Southwick | 6S2301-2016 | 1077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 34 | 23 | 11 | 2016-06-02 | 2017-05-03 | 229 | 217 | 12 | [7 empty] | 0 |  |  | 2017-05-04 | 2017-09-19 | 96 | 15 | 81 | 2017-10-28 |  | -30667 |  |  | 2017-10-05 |  | Spring 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-12-20 | Online
WMECO | Southwick | 6S2303-2016 | 1077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 34 | 23 | 11 | 2016-06-02 | 2017-05-03 | 229 | 217 | 12 | [7 empty] | 0 |  |  | 2017-05-04 | 2017-09-19 | 96 | 15 | 81 | 2017-10-28 |  | -30667 |  |  | 2017-10-05 |  | Spring 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-20 | Online
WMECO | West Springfield | 6S2305-2016 | 1089 | 12 | Solar | 21N6 | 2016-04-14 | 2016-04-20 | 4 | 3 | 1 | 2016-04-20 |  | -30286 | [9 empty] | 0 | [14 empty] | 2016-08-07 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2314-2016 | 1056 | 16.7 | Solar | 19S3 | 2016-04-18 | 2016-05-09 | 15 | 14 | 1 | 2016-05-09 |  | -30299 | [9 empty] | 0 | [14 empty] | 2016-06-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2347-2016 | 1056 | 12 | Solar | 19S1 | 2016-04-28 | [16 empty] | 0 | [14 empty] | 2016-05-25 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B996-2016 | 1201 | 1476 | Solar | 30B7 | 2016-05-02 | 2016-05-24 | 17 | 6 | 11 | 2016-05-25 |  | -30311 | [9 empty] | 0 | [14 empty] | 2016-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2367-2016 | 1077 | 16.7 | Solar | 29A5 | 2016-05-04 | 2016-05-16 | 9 | 8 | 1 | 2016-05-16 | 2016-06-15 | 22 | 21 | 1 | 2016-06-16 | 2016-06-22 | 4 | 0 | 4 |  |  | 0 | [12 empty] | 2016-06-23 |  | 2016-03-04 |  | Expedited |  |  |  | 0 |  |  | 2016-11-08 | 2016-11-14 | 2016-11-14 | Online
WMECO | Springfield | 6S2368-2016 | 1119 | 152 | Solar | 27A7 | 2016-05-04 | 2016-05-16 | 9 | 1 | 8 | 2016-05-17 | 2016-07-07 | 35 | 18 | 17 | 2016-07-08 | 2016-08-02 | 18 | 0 | 18 |  |  | 0 | [12 empty] | 2016-08-09 |  | Aug 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-02-07 | 2017-02-10 | 2017-02-10 | Online
WMECO | Hancock | 6B1002-2016 | 1237 | 42.25 | Solar | 30B7 | 2016-05-05 | 2016-09-15 | 92 | 77 | 15 | 2016-09-15 |  | #VALUE! | 42 | #VALUE! | [7 empty] | 0 | [14 empty] | 2016-05-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1014-2016 | 1226 | 16.15 | Solar | 18C1 | 2016-05-10 | 2016-05-19 | 8 | 3 | 5 | 2016-05-19 | 2016-06-09 | 15 | 14 | 1 | 2016-06-10 | 2016-07-13 | 22 | 0 | 22 |  |  | 0 | [12 empty] | 2016-07-14 |  | 2016-07-03 |  | Expedited |  |  |  | 0 |  |  | 2016-12-07 | 2016-12-13 | 2016-12-13 | Online
WMECO | Montague | 6F1500-2016 | 1351 | 36 | Solar | 21C7 | 2016-05-10 | 2016-06-15 | 26 | 22 | 4 | 2016-06-15 | 2016-07-11 | 17 | 16 | 1 | 2016-07-12 | 2016-09-26 | 54 | 17 | 37 |  |  | 0 | [12 empty] | 2016-09-29 |  | 2016-08-01 |  | Expedited |  |  |  | 0 |  |  | 2017-06-09 | 2017-06-21 | 2017-11-10 | Online
WMECO | Plainfield | 6F1513-2016 | 1070 | 17.5 | Solar | 18K3 | 2016-05-25 | [16 empty] | 0 | [14 empty] | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1034-2016 | 1238 | 36 | Solar | 16B5 | 2016-05-26 | 2016-08-05 | 49 | 48 | 1 | 2016-08-05 | 2016-08-29 | 17 | 7 | 10 | [7 empty] | 0 | [12 empty] | 2016-08-30 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2017-01-17 | 2017-01-19 | 2017-01-20 | Online
WMECO | Turners Falls | 6F1515-2016 | 1376 | 1160 | Solar | 21C8 | 2016-05-27 | 2016-06-28 | 21 | 15 | 6 | 2016-06-29 | 2016-07-22 | 17 | 6 | 11 | [7 empty] | 0 |  |  | 2016-07-25 | 2016-10-06 | 53 | 0 | 53 | [7 empty] | 2016-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S2463-2016 | 1077 | 15.75 | Solar | 29A5 | 2016-05-31 | 2016-06-23 | 17 | 14 | 3 | 2016-06-23 | 2016-07-07 | 10 | 9 | 1 | [7 empty] | 0 | [12 empty] | 2016-07-14 |  | 2016-06-15 |  | Expedited |  |  |  | 0 |  |  | 2016-11-28 | 2016-11-29 | 2016-11-29 | Online
WMECO | Pittsfield | 6B1040-2016 | 1201 | 60 | Solar | 30B7 | 2016-06-01 | 2016-07-20 | 34 | 32 | 2 | 2016-07-20 | 2016-11-02 | 74 | 48 | 26 | [7 empty] | 0 | [12 empty] | 2016-11-02 |  | Sept 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-04-04 | 2017-04-06 | 2017-04-06 | Online
WMECO | Pittsfield | 6B1047-2016 | 1201 | 166.5 | Solar | 30B3 | 2016-06-08 | 2016-06-30 | 16 | 14 | 2 | 2016-06-30 | 2016-07-19 | 13 | 12 | 1 | 2016-07-19 | 2018-07-13 | 496 | 236 | 260 |  |  | 0 | [12 empty] | 2018-07-17 |  | Oct 2016 |  | Standard |  |  |  | 0 |  |  | 2018-08-30 | 2018-08-31 | 2018-09-04 | Online
WMECO | Amherst | 6A1948-2016 | 1002 | 86.995 | Solar | 18G4 | 2016-06-10 | 2016-06-21 | 7 | 5 | 2 | 2016-06-21 |  | -30328 | [9 empty] | 0 | [14 empty] | Sept 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1052-2016 | 1238 | 3328 | Natural Gas | 16B3 | 2016-06-10 | 2016-07-12 | 21 | 6 | 15 | 2016-07-13 | 2016-09-21 | 50 | 37 | 13 | [7 empty] | 0 |  |  | 2016-09-22 | 2017-03-13 | 116 | 78 | 38 | [7 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1053-2016 | 1201 | 460 | Solar | 19A5 | 2016-06-10 | 2017-01-11 | 146 | 137 | 9 | 2017-01-12 | 2017-03-10 | 40 | 38 | 2 | [7 empty] | 0 |  |  | 2017-03-13 | 2017-05-18 | 48 | 0 | 48 | [7 empty] | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1949-2016 | 1073 | 18 | Solar | 15A1 | 2016-06-13 | 2016-07-12 | 20 | 15 | 5 | 2016-07-13 | 2016-09-06 | 39 | 37 | 2 | [7 empty] | 0 | [12 empty] | 2016-09-13 |  | 8/12 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A1953-2016 | 1002 | 19.3 | Solar | 17K2 | 2016-06-15 | 2016-07-28 | 30 | 26 | 4 | 2016-07-28 | 2016-08-23 | 19 | 18 | 1 | [7 empty] | 0 | [12 empty] | 2016-08-29 |  | 2016-08-14 |  | Expedited |  |  |  | 0 |  |  | 2017-03-02 | 2017-03-07 | 2017-03-07 | Online
WMECO | West Springfield | 6S2516-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-06-22 | 2016-07-18 | 18 | 12 | 6 | 2016-07-18 | 2016-09-02 | 35 | 34 | 1 | 2016-09-06 |  | -30381 |  |  |  |  | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A1971-2016 | 1073 | 21.9 | Solar | 15A1 | 2016-06-23 | 2016-06-29 | 5 | 2 | 3 | 2016-06-29 | 2016-07-19 | 14 | 13 | 1 | 2016-07-20 |  | -30348 | 2 |  |  |  | 0 | [14 empty] | 2016-07-04 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S2539-2016 | 1089 | 16.4 | Solar | 21N4 | 2016-06-29 | [16 empty] | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2573-2016 | 1056 | 396 | Solar | 27A5 | 2016-07-11 | 2016-08-09 | 22 | 19 | 3 | 2016-08-12 |  | -30365 | [9 empty] | 0 | [14 empty] | 2016-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A2007-2016 | 1073 | 23.4 | Solar | 15A1 | 2016-07-26 | [16 empty] | 0 | [14 empty] | 2016-05-26 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1113-2016 | 1253 | 67.6 | Solar | 19J4 | 2016-07-26 | 2016-09-23 | 43 | 38 | 5 | 2016-09-26 | 2016-10-07 | 10 | 8 | 2 | 2016-10-11 |  | -30405 |  |  |  |  | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1127-2016 | 1201 | 1476 | Solar | 30B7 | 2016-08-04 | 2016-08-31 | 20 | 15 | 5 | 2016-09-01 |  | -30379 | [9 empty] | 0 | [14 empty] | 2016-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6F1588-2016 | 1337 | 42 | Solar | 21C1 | 2016-08-08 | 2016-08-15 | 6 | 5 | 1 | 2016-08-15 |  | -30366 | [9 empty] | 0 | [14 empty] | Nov 2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1590-2016 | 1301 | 50 | Solar | 21C1 | 2016-08-08 | [16 empty] | 0 | [14 empty] | August |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A2032-2016 | 1035 | 25 | Solar | 18G6 | 2016-08-12 | 2016-09-13 | 22 | 12 | 10 | 2016-08-31 |  | -30378 | [9 empty] | 0 | [14 empty] | 2016-10-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1134-2016 | 1201 | 16.75 | Solar | 19A1 | 2016-08-12 | 2016-09-27 | 32 | 13 | 19 | 2016-09-28 | 2016-09-28 | 1 | 0 | 1 | [7 empty] | 0 | [12 empty] | 2016-09-29 |  | 2016-08-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2045-2016 | 1002 | 86.995 | Solar | 18G4 | 2016-08-17 | 2016-09-27 | 29 | 18 | 11 | 2016-09-28 | 2016-11-03 | 26 | 11 | 15 | [7 empty] | 0 | [12 empty] | 2016-11-03 |  | Sept 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-03-15 | 2017-03-21 | 2017-03-21 | Online
WMECO | Pittsfield | 6B1139-2016 | 1201 | 240 | Solar | 19A7 | 2016-08-17 | 2016-09-01 | 12 | 10 | 2 | 2016-09-02 |  | -30380 | 44 | [8 empty] | 0 | [14 empty] | 2016-11-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2702-2016 | 1104 | 420 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 19 | 14 | 5 | 2016-09-15 |  | -30388 | [9 empty] | 0 | [14 empty] | 2016-12-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2703-2016 | 1104 | 300 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 19 | 14 | 5 | 2016-09-15 |  | -30388 | [9 empty] | 0 | [14 empty] | 2016-12-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2720-2016 | 1104 | 796 | Solar | 5J13 | 2016-08-23 | 2016-09-13 | 15 | 9 | 6 | 2016-09-14 | 2016-11-29 | 52 | 32 | 20 | [7 empty] | 0 |  |  | 2016-11-30 | 2017-01-27 | 40 | 0 | 40 | 2017-03-30 |  | -30521 |  |  | 2017-03-21 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A2060-2016 | 1027 | 16.7 | Solar | 15A3 | 2016-08-24 | [16 empty] | 0 | [14 empty] | 2016-10-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S2770-2016 | 1056 | 16.7 | Solar | 19S3 | 2016-09-13 | 2016-10-24 | 29 | 19 | 10 | 2016-10-24 |  | -30414 | [9 empty] | 0 | [14 empty] | 2016-06-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A2086-2016 | 1035 | 399.6 | Solar | 18G5 | 2016-09-14 | 2016-09-27 | 10 | 5 | 5 | 2016-09-28 | 2016-11-10 | 31 | 19 | 12 | [7 empty] | 0 |  |  | 2016-11-14 | 2017-04-19 | 107 | 56 | 51 | 2017-04-20 | 2017-08-10 | 79 | 21 | 58 | 2017-08-23 |  | Nov 2016 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-06-20 | Online
WMECO | Worthington | 6F1646-2016 | 1098 | 13.5 | Solar | 18K3 | 2016-09-15 | [16 empty] | 0 | [14 empty] | 2016-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Middlefield | 6F1675-2016 | 1243 | 41.5 | Solar | 18C2 | 2016-10-03 | 2016-10-17 | 10 | 8 | 2 | 2016-10-17 | 2016-11-07 | 16 | 0 | 16 | [7 empty] | 0 | [12 empty] | 2016-11-07 |  | 2016-12-01 |  | Expedited |  |  |  | 0 |  |  | 2017-06-01 | 2017-06-05 | 2017-06-06 | Online
WMECO | Northfield | 6F1684-2016 | 1360 | 21.9 | Solar | 21B8 | 2016-10-06 | 2016-11-23 | 33 | 32 | 1 | 2016-11-25 |  | -30436 | [9 empty] | 0 | [14 empty] | 2017-01-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6F1694-2016 | 1098 | 13.5 | Solar | 18K3 | 2016-10-11 | [16 empty] | 0 | [14 empty] | 2016-12-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2863-2016 | 1109 | 16.7 | Solar | 20A32 | 2016-10-11 | 2016-12-05 | 38 | 33 | 5 | 2016-12-05 | 2016-12-12 | 6 | 1 | 5 | [7 empty] | 0 | [12 empty] | 2016-12-12 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-02-21 | Online
WMECO | Greenfield | 6F1707-2016 | 1301 | 1200 | Solar | 21C1 | 2016-10-18 | 2016-10-31 | 10 | 7 | 3 | 2016-11-01 | 2016-11-17 | 12 | 10 | 2 | [7 empty] | 0 |  |  | 2016-11-18 | 2017-01-27 | 47 | 0 | 47 | 2017-02-21 |  | -30494 |  |  | 2017-03-10 |  | 2017-09-21 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-12-23 | Online
WMECO | Pittsfield | 6B1240-2016 | 1201 | 1320 | Solar | 15E3 | 2016-10-25 | 2016-11-23 | 21 | 9 | 12 | 2016-11-25 |  | -30436 | [9 empty] | 0 | [14 empty] | May 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2924-2016 | 1104 | 37.8 | Solar | 5J15 | 2016-10-26 | 2016-11-01 | 5 | 3 | 2 | 2016-11-01 | 2016-12-07 | 25 | 18 | 7 | [7 empty] | 0 | [12 empty] | 2016-12-07 |  | 2016-12-05 |  | Expedited |  |  |  | 0 |  |  | 2017-05-24 | 2017-05-26 | 2017-05-26 | Online
WMECO | Amherst | 6A2150-2016 | 1002 | 19.8 | Solar | 18G4 | 2016-10-27 | [16 empty] | 0 | [14 empty] | 11/30/2016 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S2929-2016 | 1104 | 252 | Solar | 21S6 | 2016-10-27 | 2016-11-08 | 9 | 6 | 3 | 2016-11-09 | 2016-12-05 | 17 | 15 | 2 | 2016-12-06 | 2016-12-29 | 17 | 6 | 11 |  |  | 0 | [12 empty] | 2017-03-15 |  | May 2016 |  | Expedited |  |  |  | 0 |  |  | 2017-11-15 | 2017-12-07 | 2017-12-07 | Online
WMECO | Dalton | 6B1258-2016 | 1226 | 27.5 | Solar | 18C1 | 2016-11-03 | 2016-12-13 | 27 | 25 | 2 | 2016-12-13 | 2017-01-20 | 26 | 3 | 23 | [7 empty] | 0 | [12 empty] | 2017-01-24 |  | Q4 2016 |  | Expedited |  |  |  | 0 |  |  | 2016-09-22 | 2016-09-27 | 2017-09-27 | Online
WMECO | Springfield | 6S2985-2016 | 1118 | 149.9 | Solar | 20A22 | 2016-11-14 | 2016-12-01 | 13 | 10 | 3 | 2016-12-01 | 2016-12-07 | 5 | 2 | 3 | [7 empty] | 0 | [12 empty] | 2016-12-07 |  | 1/4/2017 |  | Expedited |  |  |  | 0 |  |  | 2018-01-08 | 2018-01-11 | 2018-01-11 | Online
WMECO | Becket | 6B1277-2016 | 1223 | 4950 | Solar | 19J6 | 2016-11-15 | 2016-12-19 | 24 | 21 | 3 | 2016-12-19 |  | -30452 | [9 empty] | 0 | [14 empty] | 2017-10-18 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B1278-2016 | 1223 | 4950 | Solar | 16B1 | 2016-11-15 | 2016-12-01 | 12 | 9 | 3 | 2016-12-02 | 2017-01-25 | 36 | 29 | 7 | [7 empty] | 0 |  |  | 2017-01-26 | 2017-03-30 | 45 | 0 | 45 | 2017-04-20 |  | -30535 |  |  | 2017-04-19 |  | 2017-10-18 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-11-15 | Online
WMECO | Lee | 6B1279-2016 | 1238 | 1860 | Solar | 16B1 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-24 | 2017-03-22 | 41 | 3 | 38 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-24 | 85 | 17 | 68 | 2017-07-25 | 2017-11-03 | 72 | 0 | 72 | 2017-11-03 |  | Sept 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-08-24 | Online
WMECO | Lanesborough | 6B1280-2016 | 1237 | 4491 | Solar | 15E1 | 2016-11-15 | 2017-02-13 | 61 | 58 | 3 | 2017-02-14 | 2017-03-22 | 26 | 21 | 5 | [7 empty] | 0 |  |  | 2017-03-23 |  | -30516 | [9 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1281-2016 | 1201 | 1500 | Solar | 15E2 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-04 |  | -30462 | [9 empty] | 0 | [14 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6F1738-2016 | 1351 | 4080 | Solar | 21C8 | 2016-11-15 | 2017-02-17 | 65 | 64 | 1 | 2017-02-21 | 2017-03-22 | 22 | 16 | 6 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-28 | 89 | 16 | 73 | 2017-07-31 | 2017-10-02 | 45 | 0 | 45 | 2017-10-19 |  | Sept 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-10-12 | Online
WMECO | Ludlow | 6S2989-2016 | 1056 | 1860 | Solar | 19S1 | 2016-11-15 | 2017-01-23 | 46 | 39 | 7 | 2017-01-24 | 2017-03-02 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-06-12 | 70 | 20 | 50 | 2017-06-13 | 2017-10-03 | 79 | 0 | 79 | 2017-10-17 |  | Sept 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-08-29 | Online
WMECO | Agawam | 6S2990-2016 | 1030 | 4140 | Solar | 30A6 | 2016-11-15 | 2017-01-23 | 46 | 42 | 4 | 2017-01-24 | 2017-03-02 | 27 | 13 | 14 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-05-12 | 50 | 0 | 50 | [7 empty] | Sept 2017 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S2996-2016 | 1001 | 95.4 | Solar | 16C16 | 2016-11-15 | 2016-12-05 | 14 | 11 | 3 | 2016-12-05 | 2016-12-15 | 9 | 6 | 3 | [7 empty] | 0 | [12 empty] | 2016-12-15 |  | 12/23/2016 |  | Expedited |  |  |  | 0 |  |  | 2017-07-10 | 2017-07-12 | 2017-07-18 | Online
WMECO | Pittsfield | 6B1282-2016 | 1201 | 1590 | Solar | 30B7 | 2016-11-16 | 2016-12-01 | 11 | 6 | 5 | 2016-12-02 | 2016-12-19 | 12 | 4 | 8 | 2016-12-20 | 2017-02-08 | 34 | 15 | 19 |  |  | 0 |  |  | 2017-02-09 | 2017-04-11 | 43 | 0 | 43 | 2017-04-21 |  | -30536 |  |  | 2017-04-26 |  | 12/2016 |  | Standard |  |  |  | 0 |  |  |  | 2018-08-10 | 2018-09-10 | Online
WMECO | Hadley | 6A2172-2016 | 1035 | 1630 | Solar | 19B15 | 2016-11-21 | 2017-01-23 | 42 | 35 | 7 | 2017-01-24 | 2017-03-02 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2017-03-03 | 2017-05-19 | 55 | 0 | 55 | [7 empty] | 2017-09-28 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1290-2016 | 1238 | 999 | Solar | 16B1 | 2016-11-21 | 2016-12-01 | 8 | 7 | 1 | 2016-12-02 |  | -30441 | [9 empty] | 0 | [14 empty] | 5/1/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3021-2016 | 1030 | 849.7 | Solar | 30A6 | 2016-11-21 | 2017-02-28 | 67 | 65 | 2 | 2017-03-01 | 2017-03-22 | 16 | 10 | 6 | [7 empty] | 0 |  |  | 2017-03-23 |  | -30516 | 24 | [8 empty] | 9/28/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A2182-2016 | 1351 | 450 | Solar | 21C8 | 2016-11-22 | 2017-01-03 | 28 | 27 | 1 | 2017-01-04 | 2017-04-05 | 64 | 60 | 4 | [7 empty] | 0 |  |  | 2017-04-06 | 2018-02-23 | 221 | 179 | 42 | [5 empty] | 2018-02-28 |  | Dec 2016 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3052-2016 | 1118 | 266.4 | Solar | 20A32 | 2016-12-02 | 2017-04-03 | 83 | 81 | 2 | 2017-04-04 |  | -30524 | [9 empty] | 0 | [14 empty] | 2017-06-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3100-2016 | 1001 | 129.6 | Solar | 30A2 | 2016-12-21 | [16 empty] | 0 | [14 empty] | 2017-01-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3147-2017 | 1103 | 1023.24 | Solar | 08C32 | 2017-01-03 | 2017-02-14 | 30 | 23 | 7 | 2017-02-15 |  | -30491 | [9 empty] | 0 | [14 empty] | 2017-10-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S3151-2017 | 1034 | 475 | Biogas | 29A5 | 2017-01-03 | 2017-02-16 | 32 | 28 | 4 | 2017-02-17 | 2017-04-27 | 48 | 46 | 2 | [7 empty] | 0 |  |  | 2017-04-28 | 2017-07-20 | 58 | 11 | 47 | 2017-07-21 | 2017-10-03 | 52 | 0 | 52 | 2017-10-19 |  | 2017-10-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-05-16 | Online
WMECO | Hatfield | 6A2232-2017 | 1088 | 334.42 | Solar | 18G5 | 2017-01-09 | 2017-03-20 | 49 | 46 | 3 | 2017-03-21 |  | -30514 | [9 empty] | 0 | [14 empty] | 9/1/2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1329-2017 | 1201 | 725 | Natural Gas | 30B1 | 2017-01-10 | 2017-02-13 | 24 | 22 | 2 | 2017-02-14 | 2017-04-21 | 47 | 36 | 11 | 2017-04-24 | 2017-07-13 | 57 | 40 | 17 |  |  | 0 | [12 empty] | 2017-07-24 |  | 11/1/2017 |  | Expedited |  |  |  | 0 |  |  | 2018-05-14 | 2018-05-23 | 2018-06-07 | Online
WMECO | Erving | 6F1795-2017 | 1344 | 210 | Solar | 21B9 | 2017-01-11 | 2017-03-15 | 44 | 40 | 4 | 2017-03-16 |  | -30511 | [9 empty] | 0 | [14 empty] | 2017-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Chicopee | 6S3180-2017 | 1013 | 2535 | Solar | 21N7 | 2017-01-18 | 2017-02-14 | 20 | 8 | 12 | 2017-02-15 | 2017-03-09 | 16 | 12 | 4 | [7 empty] | 0 |  |  | 2017-03-10 | 2017-06-15 | 68 | 3 | 65 | [5 empty] | 2017-06-30 |  | 2017-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3184-2017 | 1103 | 6250 | Diesel | 8C31 | 2017-01-19 | 2017-02-17 | 22 | 12 | 10 | 2017-02-21 | 2017-05-08 | 54 | 18 | 36 | [7 empty] | 0 |  |  | 2017-05-09 | 2017-08-04 | 62 | 55 | 7 | [5 empty] | 2017-08-24 |  | Not supplied |  | Standard |  |  |  | 0 |  |  | 2017-09-15 | 2017-09-18 | 2017-09-25 | Online
WMECO | Greenfield | 6F1810-2017 | 1301 | 250 | Solar | 22B7 | 2017-01-24 | 2017-03-01 | 26 | 12 | 14 | 2017-03-01 |  | -30500 | [9 empty] | 0 | [14 empty] | 2017-05-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6F1809-2017 | 1301 | 294 | Solar | 22B7 | 2017-01-25 | 2017-03-01 | 25 | 12 | 13 | 2017-03-01 |  | -30500 | [9 empty] | 0 | [14 empty] | 2017-05-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Savoy | 6B1350-2017 | 1256 | 7500 | Wind | 18C1 | 2017-02-01 | 2017-02-23 | 16 | 12 | 4 | 2017-02-24 | 2017-03-28 | 23 | 15 | 8 | [7 empty] | 0 |  |  | 2017-03-29 | 2018-02-22 | 226 | 106 | 120 | 2018-02-23 |  | -30746 |  |  |  |  | Sept 2018 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3221-2017 | 1001 | 1252 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 | 2017-06-12 | 76 | 52 | 24 | [7 empty] | 0 |  |  | 2017-06-13 |  | -30572 |  |  | 2017-08-17 |  | -30618 |  |  |  |  | May 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3222-2017 | 1001 | 167 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 |  | -30496 | [9 empty] | 0 | [14 empty] | May 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3223-2017 | 1001 | 72 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 12 | 4 | 8 | 2017-02-23 |  | -30496 | [9 empty] | 0 | [14 empty] | May 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3230-2017 | 1103 | 16.2 | Solar | 8CNW_1 | 2017-02-08 | 2017-03-16 | 26 | 19 | 7 | 2017-03-17 | 2017-04-13 | 20 |  | 20 | [7 empty] | 0 | [14 empty] | 2017-04-10 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2263-2017 | 1002 | 3120 | Solar | 18G4 | 2017-02-09 | 2017-02-15 | 5 | 4 | 1 | 2017-02-16 | 2017-05-04 | 54 | 44 | 10 | [7 empty] | 0 |  |  | 2017-05-05 | 2017-08-04 | 64 | 15 | 49 | 2017-08-07 |  | -30610 |  |  | 2017-08-23 |  | 2017-12-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-20 | Online
WMECO | Worthington | 6A2274-2017 | 1098 | 5000 | Solar | 18K3 | 2017-02-13 | 2017-03-01 | 12 | 10 | 2 | 2017-03-02 |  | -30501 | [9 empty] | 0 | [14 empty] | 2018-01-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1362-2017 | 1008 | 1000 | Solar | 19J2 | 2017-02-13 | 2017-02-27 | 10 | 7 | 3 | 2017-02-28 | 2017-04-14 | 34 | 20 | 14 | [7 empty] | 0 |  |  | 2017-04-17 | 2017-08-08 | 79 | 38 | 41 | 2017-08-09 | 2017-11-17 | 70 | 4 | 66 | 2017-11-17 |  | Dec 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-11-15 | Online
WMECO | Hinsdale | 6B1363-2017 | 1235 | 5000 | Solar | 18C2 | 2017-02-13 | 2017-03-16 | 23 | 21 | 2 | 2017-03-17 |  | -30512 | [9 empty] | 0 | [14 empty] | Dec 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1365-2017 | 1201 | 499.5 | Solar | 30B5 | 2017-02-15 | 2017-03-29 | 30 | 20 | 10 | 2017-03-30 |  | -30521 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1366-2017 | 1226 | 499.5 | Solar | 19A3 | 2017-02-15 | 2017-03-29 | 30 | 20 | 10 | 2017-03-30 | 2017-05-05 | 26 | 22 | 4 | [7 empty] | 0 |  |  | 2017-05-08 | 2017-08-14 | 69 | 26 | 43 | 2017-08-24 |  | -30623 |  |  | 2017-08-14 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-28 | Online
WMECO | Cummington | 6A2290-2017 | 1026 | 10.95 | Solar | 18K3 | 2017-02-23 | 2017-03-06 | 8 | 4 | 4 | 2017-03-06 | 2017-04-28 | 39 | 24 | 15 | [7 empty] | 0 | [12 empty] | 2017-04-28 |  | 2017-05-15 |  | Expedited |  |  |  | 0 |  |  | 2017-06-26 | 2017-06-30 | 2017-06-30 | Online
WMECO | Pittsfield | 6B1375-2017 | 1201 | 1160 | Solar | 15E2 | 2017-02-27 | 2017-03-08 | 8 | 6 | 2 | 2017-03-08 | 2017-03-22 | 11 | 8 | 3 | [7 empty] | 0 |  |  | 2017-03-23 | 2017-07-28 | 89 | 16 | 73 | 2017-07-31 | 2017-09-29 | 44 | 9 | 35 | 2017-10-06 |  | 2017-09-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-08-17 | Online
WMECO | Lanesborough | 6B1377-2017 | 1237 | 1998 | Solar | 15E1 | 2017-02-28 | 2017-04-11 | 31 | 28 | 3 | 2017-04-12 |  | -30530 | 9 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1378-2017 | 1201 | 27.44 | Solar | 19A7 | 2017-02-28 | 2017-03-29 | 22 | 21 | 1 | 2017-03-29 | 2017-04-20 | 16 | 15 | 1 | 2017-04-21 | 2017-07-14 | 59 | 0 | 59 |  |  | 0 | [12 empty] | 2017-07-14 |  | Aug 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-03-21 | 2018-03-21 | 2018-03-23 | Online
WMECO | Greenfield | 6A2305-2017 | 1337 | 995 | Biogas | 22B7 | 2017-03-06 | 2017-03-20 | 11 | 9 | 2 | 2017-03-21 |  | -30514 | 30 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A2316-2017 | 1098 | 21.9 | Solar | 18K3 | 2017-03-09 | 2017-03-30 | 16 | 14 | 2 | 2017-03-30 |  | -30521 | [9 empty] | 0 | [14 empty] | 2017-06-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1399-2017 | 1237 | 1998 | Solar | 15E1 | 2017-03-20 | [16 empty] | 0 | [14 empty] | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A2364-2017 | 1354 | 4998.4 | Solar | 21C5 | 2017-03-29 | 2017-04-17 | 13 | 7 | 6 | 2017-04-18 | 2017-07-24 | 68 | 29 | 39 | [7 empty] | 0 |  |  | 2017-07-25 | 2017-12-18 | 101 | 18 | 83 | [7 empty] | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S3353-2017 | 1106 | 86.4 | Solar | 22H15 | 2017-04-07 | [16 empty] | 0 | [14 empty] | 5/7 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2398-2017 | 1059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 |  | -30576 | [9 empty] | 0 | [14 empty] | 2017-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2399-2017 | 1059 | 4980 | Battery | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 | 2017-08-08 | 36 | 28 | 8 | [7 empty] | 0 |  |  | 2017-08-09 | 2017-10-17 | 48 | 0 | 48 | 2017-12-15 |  | -30700 |  |  | 2017-10-30 |  | 2017-12-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Amherst | 6A2400-2017 | 1059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 46 | 41 | 5 | 2017-06-19 |  | -30576 | [9 empty] | 0 | [14 empty] | 2017-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3370-2017 | 1089 | 300 | Natural Gas | 21N5 | 2017-04-13 | 2017-07-20 | 68 | 67 | 1 | 2017-07-21 | 2017-10-10 | 56 | 49 | 7 | [7 empty] | 0 |  |  | 2017-10-11 | 2017-11-10 | 22 | 0 | 22 | [7 empty] | 2/2018 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S3392-2017 | 1118 | 165 | Solar | 20A32 | 2017-04-21 | 2017-05-01 | 7 | 5 | 2 | 2017-05-01 | 2017-05-08 | 6 | 3 | 3 | 2017-05-09 | 2017-08-31 | 81 | 43 | 38 |  |  | 0 |  |  | 2017-09-01 | 2017-11-28 | 59 | 7 | 52 | [5 empty] | 2017-11-28 |  | 2017-06-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1444-2017 | 1201 | 240 | Solar | 15E2 | 2017-04-25 | 2017-05-15 | 15 | 13 | 2 | 2017-05-16 | 2017-06-23 | 28 | 3 | 25 |  | 2017-07-06 | [5 empty] | 0 |  |  | 2017-06-23 | 2017-10-04 | 72 | 64 | 8 | 2017-10-05 | 2017-12-21 | 53 | 0 | 53 | 2017-12-21 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A2448-2017 | 1038 | 15.36 | Solar | 18G6 | 2017-05-01 | 2017-05-12 | 10 | 7 | 3 | 2017-05-12 |  | -30551 | [9 empty] | 0 | [14 empty] | 2017-05-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1446-2017 | 1237 | 2597.4 | Solar | 15E2 | 2017-05-04 | 2017-05-18 | 11 | 2 | 9 | 2017-05-19 |  | -30556 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1447-2017 | 1201 | 1998 | Solar | 19A4 | 2017-05-05 | 2017-05-18 | 10 | 3 | 7 | 2017-05-19 | 2017-06-02 | 10 | 6 | 4 | [7 empty] | 0 |  |  | 2017-06-05 | 2017-08-23 | 57 | 4 | 53 | 2017-08-24 |  | -30623 |  |  | 2017-08-30 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2018-12-21 | Online
WMECO | Blandford | 6B1451-2017 | 1008 | 4700 | Solar | 19J4 | 2017-05-08 | 2017-08-18 | 73 | 60 | 13 | 2017-08-21 | 2017-09-14 | 18 | 11 | 7 | [7 empty] | 0 |  |  | 2017-09-15 | 2017-12-04 | 54 | 10 | 44 | 2017-12-19 |  | -30702 |  |  | 2017-12-04 |  | 2018-09-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-06-30 | Online
WMECO | Springfield | 6S3435-2017 | 1104 | 1440 | Solar | 5J11 | 2017-05-08 | 2017-06-01 | 18 | 9 | 9 | 2017-06-02 | 2017-07-19 | 33 | 30 | 3 | [7 empty] | 0 |  |  | 2017-07-20 | 2017-11-02 | 74 | 17 | 57 | 2017-11-10 |  | -30676 |  |  | 2017-12-11 |  | Nov 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-10-17 | Online
WMECO | Pittsfield | 6B1454-2017 | 1201 | 1556 | Solar | 30B5 | 2017-05-11 | 2017-06-19 | 27 | 21 | 6 | 2017-06-20 |  | -30577 | [9 empty] | 0 | [14 empty] | 2018-01-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2489-2017 | 1026 | 480 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 17 | 13 | 4 | 2017-06-07 | 2017-07-17 | 28 | 22 | 6 | [7 empty] | 0 |  |  | 2017-07-18 | 2017-09-28 | 52 | 0 | 52 | [7 empty] | 2018-02-15 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2491-2017 | 1026 | 240 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 17 | 13 | 4 | 2017-06-07 |  | -30568 | 111 | [8 empty] | 0 | [14 empty] | 2018-02-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A2495-2017 | 1370 | 60 | Solar | 29R2 | 2017-05-17 | 2017-05-25 | 7 | 2 | 5 | 2017-05-25 | 2017-06-05 | 7 | 5 | 2 | [7 empty] | 0 | [12 empty] | 2017-06-09 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2018-01-31 | 2018-02-02 | 2018-02-02 | Online
WMECO | Easthampton | 6A2529-2017 | 1027 | 1095.8 | Solar | 15A5 | 2017-05-25 | 2017-08-17 | 59 | 51 | 8 | 2017-08-18 | 2017-10-27 | 49 | 37 | 12 | [7 empty] | 0 |  |  | 2017-10-30 | 2018-03-15 | 93 | 21 | 72 | 2018-03-16 | 2018-06-26 | 70 | 11 | 59 | 2018-06-29 |  | 2018-04-15 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A2524-2017 | 1342 | 72 | Solar | 22B1 | 2017-05-30 | 2017-06-08 | 8 | 5 | 3 | 2017-06-09 | 2017-06-22 | 10 | 2 | 8 | [7 empty] | 0 | [12 empty] | 2017-06-22 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2017-12-26 | 2017-12-17 | 2018-01-12 | Online
WMECO | Dalton | 6B1482-2017 | 1226 | 4980 | Solar | 29M1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30575 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1483-2017 | 1237 | 4980 | Solar | 15E2 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30575 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S3507-2017 | 1077 | 4980 | Solar | 29A1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 | 2017-09-01 | 55 | 48 | 7 | [7 empty] | 0 |  |  | 2017-09-05 | 2017-10-20 | 33 | 0 | 33 | 2017-10-31 |  | -30669 |  |  | 2017-10-30 |  | 1905-07-09 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-02-01 | Online
WMECO | Greenfield | 6A2544-2017 | 1301 | 380 | Solar | 22B2 | 2017-06-06 | 2017-06-20 | 11 | 4 | 7 | 2017-06-21 | 2017-09-25 | 67 | 30 | 37 | 2017-09-26 | 2017-12-28 | 64 | 41 | 23 |  |  | 0 |  |  | 2017-12-29 | 2018-02-02 | 24 | 8 | 16 | [5 empty] | 2018-02-07 |  | 10-17 |  | Standard |  |  |  | 0 |  |  |  | 2018-04-27 | 2018-04-30 | Online
WMECO | Hatfield | 6A2545-2017 | 1038 | 380 | Biogas | 18G6 | 2017-06-06 | 2017-06-30 | 19 | 10 | 9 | 2017-07-03 | 2017-07-27 | 18 | 8 | 10 | [7 empty] | 0 |  |  | 2017-07-28 | 2017-11-03 | 69 | 1 | 68 | 2018-01-19 |  | -30722 |  |  | 2017-11-10 |  | 6/2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-05-21 | Online
WMECO | Springfield | 6S3522-2017 | 1151 | 3500 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 74 | 35 | 39 | 2017-09-25 | 2017-12-06 | 50 | 45 | 5 | [7 empty] | 0 |  |  | 2017-12-07 | 2018-03-19 | 68 | 10 | 58 | 2018-04-03 |  | -30772 |  |  | 2018-04-10 |  | 2018-06-07 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-27 | Online
WMECO | Springfield | 6S3523-2017 | 1151 | 2000 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 74 | 33 | 41 | 2017-09-25 | 2018-02-13 | 96 | 92 | 4 | [7 empty] | 0 |  |  | 2018-02-14 | 2018-09-04 | 139 |  | 139 | [5 empty] | 2018-08-15 |  | 2018-06-07 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S3529-2017 | 1106 | 16 | Solar | 22H12 | 2017-06-12 | 2017-06-22 | 9 | 3 | 6 | 2017-06-22 | 2017-06-26 | 3 | 0 | 3 | [7 empty] | 0 | [12 empty] | 2017-06-30 |  | 2017-07-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2017-11-08 | Online
WMECO | Pittsfield | 6B1488-2017 | 1201 | 33.3 | Solar | 30B5 | 2017-06-14 | 2017-07-13 | 21 | 13 | 8 | 2017-07-13 | 2017-08-25 | 32 | 15 | 17 | [7 empty] | 0 | [12 empty] | 2017-09-17 |  | 2017-08-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-08-04 | Online
WMECO | Sunderland | 6A2588-2017 | 1375 | 1084 | Solar | 18G3 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-24 | 41 | 30 | 11 | [7 empty] | 0 |  |  | 2017-08-24 | 2017-10-19 | 39 | 0 | 39 | 2017-11-10 |  | -30676 |  |  | 2017-10-30 |  | DEC 2017 |  | Standard |  |  |  | 0 |  |  |  |  | 2018-09-21 | Online
WMECO | Pittsfield | 6B1490-2017 | 1201 | 499.5 | Solar | 30B1 | 2017-06-15 | 2017-07-05 | 14 | 3 | 11 | 2017-07-06 |  | -30588 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1491-2017 | 1201 | 765.9 | Solar | 30B1 | 2017-06-15 | 2017-07-03 | 13 | 3 | 10 | 2017-07-05 | 2017-12-18 | 115 | 93 | 22 | [7 empty] | 0 |  |  | 2017-12-19 | 2018-03-21 | 62 |  | 62 | [7 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3543-2017 | 1001 | 4989.8 | Solar | 30A3 | 2017-06-15 | 2017-06-28 | 10 | 6 | 4 | 2017-06-29 |  | -30584 | [9 empty] | 0 | [14 empty] | Fall 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3544-2017 | 1001 | 4990 | Solar | 30A3 | 2017-06-15 | 2017-06-30 | 12 | 6 | 6 | 2017-07-03 | 2017-08-01 | 21 | 14 | 7 | [7 empty] | 0 |  |  | 2017-08-02 | 2017-12-14 | 93 | 36 | 57 | 2017-12-15 | 2018-03-15 | 61 | 12 | 49 | 2018-03-16 |  | Fall 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-11 | Online
WMECO | Springfield | 6S3549-2017 | 1104 | 4000 | Solar | 5J18 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-23 | 40 | 32 | 8 | [7 empty] | 0 |  |  | 2017-08-24 | 2017-11-28 | 65 | 0 | 65 | 2017-12-06 |  | -30693 |  |  | 2017-12-05 |  | DEC 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2019-02-01 | Online
WMECO | Amherst | 6A2594-2017 | 1002 | 3875 | Solar | 17K8 | 2017-06-19 | 2017-06-29 | 9 | 7 | 2 | 2017-06-30 | 2017-08-29 | 42 | 31 | 11 | [7 empty] | 0 |  |  | 2017-08-30 | 2017-11-01 | 44 |  | 44 | [5 empty] | 2017-12-05 |  | 7/18 |  | Complex |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Hinsdale | 6B1495-2017 | 1235 | 999 | Solar | 18C2 | 2017-06-19 | 2017-07-05 | 12 | 5 | 7 | 2017-07-06 | 2017-08-18 | 32 | 23 | 9 | [7 empty] | 0 |  |  | 2017-08-21 | 2017-10-24 | 45 | 0 | 45 | 2017-11-29 |  | -30688 |  |  | 2017-11-02 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-10-30 | Online
WMECO | Feeding Hills | 6S3555-2017 | 1030 | 18.88 | Solar | 16C17 | 2017-06-19 | 2017-07-07 | 14 | 6 | 8 | 2017-07-07 |  | -30589 | [9 empty] | 0 | [14 empty] | 2017-07-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1497-2017 | 1237 | 499.5 | Solar | 15E1 | 2017-06-21 | 2017-07-07 | 12 | 6 | 6 | 2017-07-10 | 2017-10-04 | 62 | 55 | 7 | [7 empty] | 0 |  |  | 2017-10-05 | 2017-12-14 | 48 | 0 | 48 | 2018-01-26 |  | -30727 |  |  | 2017-12-18 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-07-25 | Online
WMECO | Southwick | 6S3566-2017 | 1077 | 2000 | Solar | 29A1 | 2017-06-21 | 2017-08-07 | 33 | 16 | 17 | 2017-08-08 |  | -30611 | 37 | [8 empty] | 0 | [5 empty] | 11 | [8 empty] | Sept 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2609-2017 | 1027 | 32.85 | Solar | 15A5 | 2017-06-22 | 2017-06-28 | 5 | 0 | 5 | 2017-06-28 | 2017-08-10 | 31 | 31 | 0 | 2017-08-11 | 2017-08-25 | 11 | 0 | 11 |  |  | 0 | [12 empty] | 2017-08-28 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-08-30 | 2018-08-31 | 2018-08-31 | Online
WMECO | Agawam | 6S3582-2017 | 1001 | 2330 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 106 | 99 | 7 | 2017-12-01 |  | -30690 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3583-2017 | 1001 | 5555 | Solar | 30A4 | 2017-06-29 | 2017-12-14 | 116 | 112 | 4 | 2017-12-14 | 2017-12-14 | 1 |  | 1 | [7 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3584-2017 | 1001 | 5500 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 106 | 99 | 7 | 2017-12-01 |  | -30690 | [9 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S3585-2017 | 1001 | 2330 | Solar | 30A4 | 2017-06-29 | [16 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1522-2017 | 1008 | 4920 | Solar | 19J2 | 2017-07-17 | 2017-07-20 | 4 | 1 | 3 | 2017-07-21 | 2017-11-10 | 78 | 31 | 47 | [7 empty] | 0 |  |  | 2017-11-13 | 2018-03-13 | 82 | 7 | 75 | 2018-06-29 |  | -30833 |  |  | 2018-05-07 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2019-12-27 | Online
WMECO | Hatfield | 6A2693-2017 | 1038 | 3600 | Solar | 18G5 | 2017-07-24 | 2017-07-27 | 4 | 0 | 4 | 2017-07-27 | 2017-09-27 | 44 | 20 | 24 | [7 empty] | 0 |  |  | 2017-09-28 | 2017-11-16 | 34 | 0 | 34 | 2017-11-28 |  | -30687 |  |  | 2017-11-27 |  | Nov 2017 |  | Complex |  |  |  | 0 |  |  |  |  | 2018-11-02 | Online
WMECO | Amherst | 6A2698-2017 | 1002 | 98.5 | Solar | 18G4 | 2017-07-26 | 2017-09-22 | 42 | 33 | 9 | 2017-09-25 | 2017-10-20 | 19 | 8 | 11 | [7 empty] | 0 | [12 empty] | 2017-10-27 |  | 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-03-30 | Online
WMECO | Pittsfield | 6B1539-2017 | 1201 | 4980 | Solar | 15E2 | 2017-07-28 | 2017-09-11 | 31 | 22 | 9 | 2017-09-12 |  | -30635 | 44 | [8 empty] | 0 | [14 empty] | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A2710-2017 | 1342 | 2200 | Solar | 22B4 | 2017-07-31 | 2017-08-09 | 8 | 1 | 7 | 2017-08-10 | 2017-08-28 | 13 | 6 | 7 | [7 empty] | 0 |  |  | 2017-08-29 | 2018-02-26 | 122 | 11 | 111 | [5 empty] | 2018-06-20 |  | 2018-03-02 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2718-2017 | 1027 | 2200 | Solar | 15A2 | 2017-08-02 | 2017-08-28 | 19 | 15 | 4 | 2017-08-28 | 2017-09-22 | 19 | 18 | 1 | [7 empty] | 0 |  |  | 2017-09-25 | 2017-12-07 | 51 | 17 | 34 | 2017-12-08 | 2018-03-23 | 71 | 21 | 50 | 2018-04-02 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2774-2017 | 1002 | 233.1 | Solar | 17K8 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 |  | -30625 | [9 empty] | 0 | [14 empty] | 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2776-2017 | 1002 | 233.1 | Solar | 17K2 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 | 2017-09-28 | 23 | 20 | 3 | [7 empty] | 0 |  |  | 2017-09-29 | 2017-10-31 | 22 | 0 | 22 | [7 empty] | 2017 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1571-2017 | 1238 | 4993 | Solar | 16B1 | 2017-08-24 | 2017-09-26 | 23 | 15 | 8 | 2017-09-27 | 2018-06-20 | 181 | 62 | 119 | [7 empty] | 0 |  |  | 2018-06-21 | 2018-11-05 | 95 |  | 95 | [5 empty] | 2018-11-09 |  |  |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3712-2017 | 1089 | 20 | Solar | 21N4 | 2017-08-24 | 2017-09-19 | 18 | 4 | 14 | 2017-09-20 | 2017-10-16 | 18 | 0 | 18 | [7 empty] | 0 | [12 empty] | 2017-10-16 |  | 2017 |  | Expedited |  |  |  | 0 |  |  | 2017-12-18 | 2017-12-21 | 2017-12-28 | Online
WMECO | Greenfield | 6A2815-2017 | 1301 | 7190 | Solar | 21C1 | 2017-08-29 | 2017-09-21 | 17 | 4 | 13 | 2017-09-22 |  | -30643 | [9 empty] | 0 | [14 empty] | 2018-08-18 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A2826-2017 | 1344 | 990 | Solar | 21B8 | 2017-09-01 | 2017-10-12 | 28 | 20 | 8 | 2017-10-13 | 2018-02-09 | 81 | 47 | 34 | [7 empty] | 0 |  |  | 2018-02-09 | 2018-07-19 | 110 | 32 | 78 | 2018-07-20 |  | -30847 |  |  | 2018-08-15 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2020-09-11 | Online
WMECO | Springfield | 6S3764-2017 | 1105 | 72 | Solar | 5J16 | 2017-09-08 | 2017-09-21 | 10 | 7 | 3 | 2017-09-22 | 2017-12-07 | 52 | 33 | 19 | [7 empty] | 0 | [12 empty] | 2017-12-08 |  | 11/17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cummington | 6A2837-2017 | 1026 | 999 | Solar | 18K3 | 2017-09-11 | 2017-10-12 | 23 | 16 | 7 | 2017-10-13 |  | -30657 | [9 empty] | 0 | [14 empty] | Fall 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Leverett | 6A2858-2017 | 1054 | 366.3 | Solar | 18G7 | 2017-09-14 | 2017-09-27 | 10 | 9 | 1 | 2017-09-28 | 2017-11-02 | 25 | 7 | 18 | [7 empty] | 0 |  |  | 2017-11-03 | 2018-01-23 | 53 | 0 | 53 | [5 empty] | 2018-02-01 |  | 2018-01-20 |  | Standard |  |  |  | 0 |  |  |  |  | 2019-02-14 | Online
WMECO | Springfield | 6S3788-2017 | 1105 | 57.6 | Solar | 8C26 | 2017-09-19 | 2017-09-28 | 8 | 7 | 1 | 2017-09-29 | 2018-01-22 | 76 | 53 | 23 | [7 empty] | 0 | [12 empty] | 2018-01-22 |  | 2018-10-26 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-04-26 | Online
WMECO | Springfield | 6S3797-2017 | 1103 | 450 | Natural Gas | 8C31 | 2017-09-20 | 2017-11-06 | 33 | 24 | 9 | 2017-11-07 | 2017-12-05 | 19 | 6 | 13 | 2017-12-06 | 2018-02-26 | 55 | 40 | 15 |  |  | 0 | [12 empty] | 2018-03-06 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A2885-2017 | 1002 | 2000 | Diesel | 17K5 | 2017-09-21 | 2017-10-18 | 19 | 13 | 6 | 2017-10-19 | 2018-02-28 | 89 | 26 | 63 | [7 empty] | 0 | [12 empty] | 2018-04-10 |  | Sept 2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-11-20 | Online
WMECO | South Deerfield | 6A2888-2017 | 1373 | 57.5 | Solar | 22B1 | 2017-09-22 | 2017-10-05 | 10 | 5 | 5 | 2017-10-06 | 2017-11-07 | 22 | 21 | 1 | 2017-11-08 | 2017-11-14 | 4 | 0 | 4 |  |  | 0 | [12 empty] | 2017-11-28 |  | Nov 2017 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-04-20 | Online
WMECO | South Deerfield | 6A2889-2017 | 1373 | 57 | Solar | 22B1 | 2017-09-22 | [16 empty] | 0 | [14 empty] | Nov 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1612-2017 | 1201 | 22.8 | Solar | 30B3 | 2017-09-22 | 2017-10-10 | 12 | 9 | 3 | 2017-10-11 |  | -30655 | [9 empty] | 0 | [14 empty] | 12/17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1616-2017 | 1253 | 24 | Solar | 19J4 | 2017-09-26 | 2017-10-04 | 7 | 5 | 2 | 2017-10-05 | 2018-09-24 | 241 |  | 241 | 2018-09-25 | 2018-10-23 | 20 |  | 20 |  |  | 0 | [12 empty] | 2018-10-23 |  | 2017-11-22 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Southwick | 6S3810-2017 | 1077 | 4980 | Solar | 29A5 | 2017-09-27 | 2017-09-29 | 3 | 0 | 3 | 2017-10-02 |  | -30649 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A2904-2017 | 1027 | 2460 | Solar | 15A2 | 2017-09-28 | 2017-09-29 | 2 | 0 | 2 | 2017-10-02 | 2017-11-21 | 35 | 10 | 25 | [7 empty] | 0 |  |  | 2017-11-22 | 2018-02-09 | 54 | 0 | 54 | 2018-02-12 |  | -30738 |  |  | 2018-02-20 |  | Q4 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-09-22 | Online
WMECO | Shelburne Falls | 6A2914-2017 | 1370 | 60 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 13 | 11 | 2 | 2017-10-18 | 2017-10-27 | 8 | 4 | 4 | 2017-10-27 | 2017-12-06 | 27 | 3 | 24 |  |  | 0 | [12 empty] | 2017-12-14 |  | Nov 2017 |  | Expedited |  |  |  | 0 |  |  | 2018-05-15 | 2018-05-17 | 2018-05-17 | Online
WMECO | Shelburne Falls | 6A2915-2017 | 1370 | 50 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 13 | 11 | 2 | 2017-10-18 |  | -30660 | [9 empty] | 0 | [14 empty] | Nov 2017 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Dalton | 6B1618-2017 | 1226 | 9.28 | Solar | 19A2 | 2017-09-28 | [16 empty] | 0 | [14 empty] | 2017-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1620-2017 | 1235 | 3000 | Solar | 18C2 | 2017-09-28 | 2017-10-04 | 5 | 2 | 3 | 2017-10-05 | 2017-10-24 | 13 | 4 | 9 | [7 empty] | 0 |  |  | 2017-10-25 | 2018-02-27 | 84 | 0 | 84 | 2018-02-28 |  | -30749 |  |  | 2018-02-27 |  | 12.18 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-10-15 | Online
WMECO | Otis | 6B1625-2017 | 1253 | 24 | Solar | 19J4 | 2017-09-29 | 2017-10-04 | 4 | 2 | 2 | 2017-10-05 | 2018-09-24 | 241 |  | 241 | 2018-09-25 | 2018-10-23 | 20 |  | 20 |  |  | 0 | [12 empty] | 2018-10-23 |  | Nov 22 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-10 | Online
WMECO | Hinsdale | 6B1626-2017 | 1235 | 2200 | Solar | 18C2 | 2017-09-29 | 2017-10-05 | 5 | 3 | 2 | 2017-10-06 |  | -30653 | [9 empty] | 0 | [14 empty] | 2018-08-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S3822-2017 | 1089 | 46.8 | Solar | 16C15 | 2017-10-02 | 2017-11-10 | 28 | 26 | 2 | 2017-11-13 | 2018-01-26 | 51 | 40 | 11 | [7 empty] | 0 | [12 empty] | 2018-01-26 |  | 2017-11-01 |  | Expedited |  |  |  | 0 |  |  | 2018-04-02 | 2018-04-10 | 2018-04-13 | Online
WMECO | Russell | 6A2932-2017 | 1071 | 2988 | Solar | 19J2 | 2017-10-04 | 2017-10-17 | 9 | 8 | 1 | 2017-10-18 | 2017-11-27 | 27 | 3 | 24 | [7 empty] | 0 |  |  | 2017-11-28 | 2018-05-24 | 122 | 60 | 62 | 2018-06-06 |  | -30816 |  |  | 2018-06-01 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-10-26 | Online
WMECO | Tolland | 6B1628-2017 | 1034 | 4980 | Solar | 19J4 | 2017-10-04 | 2017-10-17 | 9 | 7 | 2 | 2017-10-18 | 2017-12-11 | 37 | 16 | 21 | [7 empty] | 0 |  |  | 2017-12-12 | 2018-02-20 | 47 | 0 | 47 | 2018-03-01 |  | -30750 |  |  | 2018-02-27 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2020-12-28 | Online
WMECO | Pittsfield | 6B1632-2017 | 1201 | 4987 | Solar | 15E2 | 2017-10-06 | 2017-10-17 | 7 | 4 | 3 | 2017-10-18 |  | -30660 | [9 empty] | 0 | [14 empty] | Summer 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A2951-2017 | 1349 | 800 | Solar | 21C2 | 2017-10-11 | 2017-12-15 | 46 | 45 | 1 | 2017-12-18 | 2018-02-21 | 44 | 28 | 16 | [7 empty] | 0 |  |  | 2018-02-22 | 2018-05-08 | 52 | 22 | 30 | 2018-05-09 |  | -30797 |  |  | 2018-07-19 |  | 6/31/2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-31 | Online
WMECO | Windsor | 6B1641-2017 | 1270 | 999 | Solar | 18C1 | 2017-10-12 | 2017-11-16 | 25 | 19 | 6 | 2017-11-17 | 2017-12-27 | 27 | 24 | 3 | [7 empty] | 0 |  |  | 2017-12-28 | 2018-04-27 | 82 | 42 | 40 | [5 empty] | 2018-10-26 |  | Fall 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-29 | Online
WMECO | Springfield | 6S3848-2017 | 1119 | 600 | Diesel | 20A14 | 2017-10-12 | 2017-11-06 | 18 | 13 | 5 | 2017-11-07 | 2018-01-23 | 51 | 35 | 16 | 2018-01-24 | 2018-04-02 | 47 | 41 | 6 |  |  | 0 | [12 empty] | 2018-04-18 |  | 2017-12-15 |  | Expedited |  |  |  | 0 |  |  | 2018-04-25 | 2018-06-07 | 2018-06-07 | Online
WMECO | Springfield | 6S3870-2017 | 1103 | 1140 | Solar | 8C31 | 2017-10-18 | 2017-11-06 | 14 | 12 | 2 | 2017-11-07 | 2018-04-20 | 111 | 71 | 40 | [7 empty] | 0 | [12 empty] | 2018-04-26 |  | 2018-11-30 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-07-22 | Online
WMECO | Turners Falls | 6A2995-2017 | 1349 | 996 | Solar | 21C2 | 2017-10-30 | 2017-11-16 | 13 | 8 | 5 | 2017-11-17 | 2018-01-08 | 34 | 26 | 8 | [7 empty] | 0 |  |  | 2018-01-05 | 2018-06-11 | 107 | 94 | 13 | [5 empty] | 2018-09-20 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2019-12-24 | Online
WMECO | Westhampton | 6A3031-2017 | 1027 | 4980 | Solar | 15A3 | 2017-11-13 | 2017-12-15 | 24 | 22 | 2 | 2017-12-18 | 2018-01-08 | 14 | 2 | 12 | [7 empty] | 0 |  |  | 2018-01-09 | 2018-04-02 | 57 | 11 | 46 | 2018-04-05 |  | -30774 |  |  | 2018-04-13 |  | 2019 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-01-26 | Online
WMECO | Agawam | 6S3940-2017 | 1001 | 366.3 | Solar | 16C16 | 2017-11-20 | 2017-12-15 | 19 | 17 | 2 | 2017-12-18 | 2018-02-28 | 49 | 44 | 5 | 2018-03-01 | 2018-03-14 | 10 | 8 | 2 |  |  | 0 | [12 empty] | 2018-03-29 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  | 2018-10-03 | 2018-10-03 | 2018-10-05 | Online
WMECO | Lanesborough | 6B1701-2017 | 1237 | 4536 | Solar | 15E2 | 2017-11-21 | 2017-12-22 | 23 | 16 | 7 | 2017-12-22 | 2018-03-12 | 53 | 36 | 17 | [7 empty] | 0 |  |  | 2018-03-13 | 2018-06-15 | 66 | 4 | 62 | 2018-07-26 |  | -30851 |  |  | 2018-06-28 |  | asap |  | Complex |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Lanesborough | 6B1702-2017 | 1237 | 3600 | Solar | 15E1 | 2017-11-21 | 2017-12-22 | 23 | 16 | 7 | 2017-12-22 | 2018-03-12 | 53 | 51 | 2 | [7 empty] | 0 |  |  | 2018-03-13 | 2018-06-15 | 66 | 4 | 62 | 2018-07-18 |  | -30845 |  |  | 2018-06-28 |  | asap |  | Standard |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Hadley | 6A3069-2017 | 1035 | 2990 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3073-2017 | 1035 | 2000 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1708-2017 | 1027 | 2573 | Solar | 18C1 | 2017-11-27 | 2017-12-15 | 15 | 13 | 2 | 2017-12-15 |  | -30700 | [9 empty] | 0 | [14 empty] | 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A3081-2017 | 1376 | 3770 | Solar | 21C2 | 2017-11-29 | 2018-02-28 | 62 | 37 | 25 | 2018-03-01 | 2018-06-11 | 70 | 63 | 7 | [7 empty] | 0 |  |  | 2018-06-12 | 2018-10-31 | 99 |  | 99 | [5 empty] | 2018-10-29 |  | August 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-11-23 | Online
WMECO | Worthington | 6A3090-2017 | 1098 | 8300 | Solar | 18K3 | 2017-12-01 | 2017-12-18 | 12 | 9 | 3 | 2017-12-19 |  | -30702 | [9 empty] | 0 | [14 empty] | 2018-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3094-2017 | 1301 | 1000 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 89 | 70 | 19 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-09-17 | 94 |  | 94 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | Complex |  |  |  | 0 | [5 empty] | In Queue
WMECO | Chesterfield | 6A3095-2017 | 1012 | 500 | Solar | 18K3 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3096-2017 | 1301 | 500 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3097-2017 | 1360 | 1000 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 89 | 65 | 24 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-10-19 | 117 |  | 117 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3098-2017 | 1360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3099-2017 | 1360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30705 | [9 empty] | 0 | [14 empty] | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1724-2017 | 1201 | 1380 | Solar | 30B5 | 2017-12-05 | 2018-01-16 | 28 | 23 | 5 | 2018-01-17 | 2018-02-28 | 30 | 24 | 6 | [7 empty] | 0 |  |  | 2018-03-01 | 2018-07-16 | 94 | 40 | 54 | 2018-07-17 |  | -30844 |  |  | 2018-07-16 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2020-12-30 | Online
WMECO | Ludlow | 6S3969-2017 | 1056 | 3969 | Solar | 27A5 | 2017-12-05 | 2018-02-08 | 45 | 30 | 15 | 2018-02-09 | 2018-04-27 | 53 | 29 | 24 | [7 empty] | 0 |  |  | 2018-04-30 | 2018-10-15 | 117 |  | 117 | [5 empty] | 2018-10-27 |  | 2018 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-01-29 | Online
WMECO | Lanesborough | 6B1728-2017 | 1237 | 3000 | Solar | 15E1 | 2017-12-07 | [16 empty] | 0 | [14 empty] | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3130-2017 | 1301 | 4500 | Solar | 21C1 | 2017-12-14 | 2017-12-27 | 9 | 2 | 7 | 2017-12-28 | 2018-02-14 | 33 | 7 | 26 | [7 empty] | 0 |  |  | 2018-02-15 | 2018-07-25 | 110 | 42 | 68 | 2018-07-26 |  | -30851 |  |  | 2020-03-23 |  | 2018-12-21 |  | Standard |  |  |  | 0 |  |  |  |  | 2024-07-23 | Online
WMECO | Lanesborough | 6B1736-2017 | 1237 | 4536 | Solar | 15E1 | 2017-12-14 | 2017-12-22 | 7 | 0 | 7 | 2017-12-22 | 2018-05-31 | 108 | 106 | 2 | [7 empty] | 0 |  |  | 2018-06-01 | 2018-08-27 | 61 |  | 61 | [5 empty] | 2018-09-25 |  | ASAP |  | Standard |  |  |  | 0 |  |  |  |  | 2022-12-09 | Online
WMECO | Lanesborough | 6B1737-2017 | 1237 | 3000 | Solar | 15E1 | 2017-12-14 | 2017-12-15 | 2 | 0 | 2 | 2017-12-18 | 2018-01-16 | 19 | 11 | 8 | [7 empty] | 0 |  |  | 2018-09-20 | 2018-10-16 | 18 |  | 18 | [5 empty] | 2019-05-21 |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A3136-2017 | 1027 | 4998 | Solar | 15A3 | 2017-12-15 | 2018-01-02 | 11 | 5 | 6 | 2018-01-03 | 2018-06-05 | 105 | 97 | 8 | [7 empty] | 0 |  |  | 2018-06-06 | 2018-10-22 | 96 |  | 96 | [5 empty] | 2018-10-18 |  | 2019-01-14 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-11-30 | Online
WMECO | Pittsfield | 6B1741-2017 | 1201 | 5000 | Solar | 30B2 | 2017-12-18 | 2017-12-27 | 7 | 1 | 6 | 2017-12-28 | 2018-02-28 | 42 | 12 | 30 | [7 empty] | 0 |  |  | 2018-03-01 | 2018-09-24 | 143 |  | 143 | [5 empty] | 2018-10-05 |  | 2019-01-14 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S4000-2017 | 1089 | 180 | Solar | 16C12 | 2017-12-18 | 2018-02-02 | 32 | 6 | 26 | 2018-02-05 | 2018-03-12 | 25 | 7 | 18 | [7 empty] | 0 | [12 empty] | 2018-03-15 |  | 2018-03-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6A3138-2017 | 1341 | 2178 | Solar | 22B1 | 2017-12-19 | 2018-01-10 | 15 | 13 | 2 | 2018-01-11 |  | -30717 | [9 empty] | 0 | [14 empty] | Dec 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4010-2017 | 1118 | 99.9 | Solar | 20A32 | 2017-12-20 | 2018-01-10 | 14 | 9 | 5 | 2018-01-11 | 2018-02-09 | 21 | 2 | 19 | [7 empty] | 0 | [12 empty] | 2018-02-09 |  | 2018-05-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-10-03 | Online
WMECO | Southwick | 6S4042-2018 | 1077 | 9950 | Solar | 29A1 | 2018-01-03 | 2018-02-08 | 26 | 21 | 5 | 2018-02-09 |  | -30737 | [9 empty] | 0 | [14 empty] | 2018-12-10 |  | Standard |  |  |  | 0 | [5 empty] | In Queue
WMECO | Hatfield | 6A3180-2018 | 1038 | 500 | Solar | 18G5 | 2018-01-08 | 2018-01-31 | 17 | 1 | 16 | 2018-02-01 |  | -30731 | 11 | [8 empty] | 0 | [14 empty] | 2018-04-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B1756-2018 | 1223 | 33.3 | Solar | 19J6 | 2018-01-12 | 2018-01-22 | 6 | 4 | 2 | 2018-01-23 | 2018-02-28 | 26 | 0 | 26 | [7 empty] | 0 | [12 empty] | 2018-02-02 |  | 2018-05-01 |  | Expedited |  |  |  | 0 |  |  | 2018-07-11 | 2018-07-17 | 2018-07-18 | Online
WMECO | Deerfield | 6A3216-2018 | 1373 | 500 | Solar | 22B3 | 2018-01-16 | 2018-01-31 | 12 | 5 | 7 | 2018-02-01 | 2018-03-13 | 28 | 22 | 6 | [7 empty] | 0 |  |  | 2018-03-14 | 2018-04-30 | 32 | 2 | 30 | [7 empty] | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1761-2018 | 1008 | 4450 | Solar | 19J6 | 2018-01-17 | 2018-01-29 | 9 | 1 | 8 | 2018-01-30 |  | -30729 | [9 empty] | 0 | [16 empty] | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A3219-2018 | 1344 | 4980 | Solar | 21C8 | 2018-01-18 | 2018-01-31 | 10 | 1 | 9 | 2018-02-01 | 2018-05-03 | 63 | 43 | 20 | [7 empty] | 0 |  |  | 2018-05-04 | 2018-08-03 | 64 | 8 | 56 | [5 empty] | 2018-08-10 |  | Summer 2018 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-11-25 | Online
WMECO | Deerfield | 6A3221-2018 | 1373 | 1000 | Solar | 22B3 | 2018-01-18 | 2018-01-30 | 9 | 3 | 6 | 2018-01-31 | 2018-02-06 | 5 |  | 5 | [7 empty] | 0 | [14 empty] | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Peru | 6B1762-2018 | 1235 | 3320 | Solar | 18C2 | 2018-01-18 | 2018-01-30 | 9 | 2 | 7 | 2018-01-31 | 2018-03-09 | 27 | 21 | 6 | [7 empty] | 0 |  |  | 2018-03-12 | 2018-05-11 | 43 | 0 | 43 | 2018-05-16 |  | -30802 |  |  | 2018-05-18 |  | Q4 2018 |  | Standard |  |  |  | 0 |  |  |  |  | 2020-11-18 | Online
WMECO | Northfield | 6A3238-2018 | 1360 | 5000 | Solar | 21B8 | 2018-01-30 | 2018-02-21 | 16 | 7 | 9 | 2018-02-22 | 2018-10-26 | 171 | 165 | 6 | [7 empty] | 0 |  |  | 2018-10-29 |  | -30916 |  |  |  |  | 0 |  |  | 2018-11-30 |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1777-2018 | 1270 | 20 | Solar | 18C1 | 2018-01-31 | 2018-02-08 | 7 | 5 | 2 | 2018-02-09 | 2018-04-17 | 45 | 24 | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-17 |  | 2018-03-15 |  | Expedited |  |  |  | 0 |  |  | 2018-06-12 | 2018-06-15 | 2018-06-18 | Online
WMECO | Leverett | 6A3271-2018 | 1054 | 3120 | Solar | 18G7 | 2018-02-09 | 2018-02-21 | 8 | 6 | 2 | 2018-02-22 | 2018-04-04 | 29 | 28 | 1 | [7 empty] | 0 |  |  | 2018-04-05 | 2018-05-24 | 35 | 0 | 35 |  |  | 0 |  |  | 2018-06-28 |  | 2018-12-01 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1787-2018 | 1201 | 2574 | Solar | 30B2 | 2018-02-09 | 2018-03-05 | 16 | 4 | 12 | 2018-03-06 | 2018-03-14 | 7 |  | 7 | [7 empty] | 0 |  |  | 2019-04-05 | 2019-11-22 | 160 |  | 160 |  |  | 0 |  |  | 2020-03-23 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3277-2018 | 1360 | 3575 | Solar | 21B8 | 2018-02-12 | 2018-03-09 | 19 | 12 | 7 | 2018-03-12 | 2018-03-19 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-03-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3279-2018 | 1093 | 5225 | Solar | 18G8 | 2018-02-12 | 2018-02-22 | 8 | 0 | 8 | 2018-02-23 | 2018-05-10 | 53 | 46 | 7 | [7 empty] | 0 |  |  | 2018-05-11 | 2018-10-11 | 106 |  | 106 |  |  | 0 |  |  |  |  | 2018-08-30 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3280-2018 | 1337 | 1410 | Solar | 21C1 | 2018-02-12 | 2018-02-22 | 8 | 0 | 8 | 2018-02-23 | 2018-05-11 | 54 | 48 | 6 | [7 empty] | 0 |  |  | 2018-05-14 | 2018-11-14 | 128 |  | 128 |  |  | 0 |  |  | 2018-11-28 |  | 2018-08-30 |  | Standard |  |  |  | 0 |  |  |  |  | 2022-10-31 | Online
WMECO | Westhampton | 6A3288-2018 | 1027 | 22.8 | Solar | 15A3 | 2018-02-14 | 2018-02-22 | 6 | 4 | 2 | 2018-02-23 | 2018-03-05 | 7 | 3 | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-03-07 |  | 2018-03-15 |  | Expedited |  |  |  | 0 |  |  | 2018-05-30 | 2018-06-13 | 2018-06-13 | Online
WMECO | Whately | 6A3295-2018 | 1093 | 1000 | Solar | 18G8 | 2018-02-16 | 2018-02-22 | 4 | 3 | 1 | 2018-02-23 | 2018-07-31 | 109 | 105 | 4 | [7 empty] | 0 |  |  | 2018-08-01 | 2018-11-18 | 75 |  | 75 |  |  | 0 |  |  |  |  | 2018-12-31 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1793-2018 | 1008 | 4998 | Solar | 19J4 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-03-08 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S4145-2018 | 1089 | 19.3 | Solar | 16C14 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-03-06 | 8 | 4 | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-03-07 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4152-2018 | 1056 | 4998 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 | 2018-06-20 | 81 | 67 | 14 | [7 empty] | 0 |  |  | 2018-06-21 | 2018-10-02 | 72 |  | 72 |  |  | 0 |  |  | 2018-11-12 |  | 2019-10-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-12-16 | Online
WMECO | Ludlow | 6S4153-2018 | 1056 | 5000 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 4 | 2 | 2 | 2018-02-23 |  | -30746 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3297-2018 | 1373 | 1925 | Solar | 18G8 | 2018-02-20 | 2018-03-09 | 14 | 9 | 5 | 2018-03-12 | 2018-03-15 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Cheshire | 6B1794-2018 | 1225 | 1650 | Solar | 19A5 | 2018-02-20 | 2018-03-05 | 10 | 7 | 3 | 2018-03-06 |  | -30753 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1795-2018 | 1235 | 2200 | Solar | 18C2 | 2018-02-22 | 2018-03-14 | 15 | 11 | 4 | 2018-03-15 |  | -30760 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3302-2018 | 1337 | 4160 | Solar | 21C1 | 2018-02-23 | 2018-03-14 | 14 | 10 | 4 | 2018-03-15 | 2018-03-16 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-03-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1798-2018 | 1201 | 3250 | Solar | 30B5 | 2018-02-26 | 2018-03-28 | 22 | 19 | 3 | 2018-03-29 | 2018-05-14 | 32 | 17 | 15 | [7 empty] | 0 |  |  | 2018-05-15 | 2018-10-23 | 112 | 37 | 75 |  |  | 0 |  |  | 2018-11-23 |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4177-2018 | 1077 | 248 | Solar | 29A1 | 2018-02-28 | 2018-03-29 | 21 | 19 | 2 | 2018-04-02 | 2018-04-23 | 15 | 4 | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-23 |  | 5/2018 |  | Expedited |  |  |  | 0 |  |  | 2018-10-02 | 2018-10-02 | 2018-10-02 | Online
WMECO | Amherst | 6A3310-2018 | 1002 | 32.95 | Solar | 17K3 | 2018-03-01 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | March 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3312-2018 | 1002 | 99.9 | Solar | 17K5 | 2018-03-02 | 2018-03-14 | 9 | 8 | 1 | 2018-03-15 | 2018-08-06 | 99 | 48 | 51 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-08-06 |  | 2018-06-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-01-10 | Online
WMECO | Shelburne Falls | 6A3316-2018 | 1370 | 900 | Solar | 22B5 | 2018-03-05 | 2018-06-20 | 75 | 72 | 3 | 2018-06-21 | 2018-06-21 | 1 |  | 1 | [7 empty] | 0 |  |  | 2018-10-09 | 2019-03-13 | 105 |  | 105 |  |  | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A3317-2018 | 1050 | 900 | Solar | 19J5 | 2018-03-05 | 2018-06-20 | 75 | 72 | 3 | 2018-06-21 | 2018-06-26 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A3322-2018 | 1027 | 2500 | Solar | 15A3 | 2018-03-06 | 2018-04-18 | 30 | 23 | 7 | 2018-04-19 | 2018-10-19 | 128 | 126 | 2 | [7 empty] | 0 |  |  | 2018-10-19 | 2018-12-18 | 41 |  | 41 |  |  | 0 |  |  | 2019-01-27 |  | 2019-04-30 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4201-2018 | 1118 | 15.68 | Solar | 20A32 | 2018-03-13 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-04-05 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3340-2018 | 1070 | 495 | Solar | 19J5 | 2018-03-14 | 2018-06-13 | 63 | 55 | 8 | 2018-06-14 | 2018-06-22 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6A3341-2018 | 1373 | 2000 | Solar | 18G8 | 2018-03-15 | 2018-03-28 | 9 | 4 | 5 | 2018-03-29 |  | -30769 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Conway | 6A3350-2018 | 1341 | 4400 | Solar | 38A1 | 2018-03-16 | 2018-04-18 | 22 | 17 | 5 | 2018-04-19 | 2018-05-11 | 17 | 11 | 6 | [7 empty] | 0 |  |  | 2018-05-14 | 2018-09-25 | 94 |  | 94 |  |  | 0 |  |  | 2019-02-22 |  | 2018-12-01 |  | Complex |  |  |  | 0 |  |  |  |  | 2021-07-28 | Online
WMECO | Pittsfield | 6B1811-2018 | 1201 | 4890 | Solar | 30B5 | 2018-03-16 | 2018-04-06 | 15 | 9 | 6 | 2018-04-09 | 2018-08-03 | 82 | 17 | 65 | [7 empty] | 0 |  |  | 2018-08-06 | 2018-11-16 | 72 |  | 72 |  |  | 0 |  |  |  |  | 2018-12-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1817-2018 | 1201 | 187 | Solar | 30B5 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-27 | 17 | 15 | 2 | 2018-04-30 | 2018-07-20 | 58 | 22 | 36 |  |  | 0 | [9 empty] | 0 |  |  | 2018-09-17 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Pittsfield | 6B1818-2018 | 1201 | 191 | Solar | 30B4 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-13 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1819-2018 | 1201 | 249 | Solar | 30B7 | 2018-03-21 | 2018-04-04 | 11 | 5 | 6 | 2018-04-05 | 2018-05-24 | 35 | 22 | 13 | 2018-05-25 | 2018-09-17 | 79 |  | 79 |  |  | 0 | [9 empty] | 0 |  |  | 2018-10-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-14 | Online
WMECO | Dalton | 6B1825-2018 | 1226 | 4400 | Solar | 18C1 | 2018-03-21 | 2018-04-19 | 21 | 18 | 3 | 2018-04-20 | 2018-08-03 | 74 | 48 | 26 | [7 empty] | 0 |  |  | 2018-08-06 | 2018-11-29 | 80 |  | 80 |  |  | 0 |  |  | 2018-11-30 |  | 2018-12-01 |  | Standard |  |  |  | 0 |  |  |  |  | 2021-05-25 | Online
WMECO | Springfield | 6S4229-2018 | 1119 | 14.4 | Solar | 20A35 | 2018-03-21 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-04-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1824-2018 | 1201 | 480 | Solar | 30B5 | 2018-03-22 | 2018-04-03 | 9 | 2 | 7 | 2018-04-04 | 2021-04-23 | 758 |  | 758 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Richmond | 6B1826-2018 | 1254 | 97.75 | Solar | 30B7 | 2018-03-22 | 2018-03-29 | 6 | 1 | 5 | 2018-04-02 | 2018-04-20 | 14 | 6 | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-04-20 |  | 6/2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-08-28 | Online
WMECO | Pittsfield | 6B1831-2018 | 1201 | 350 | Solar | 19A5 | 2018-03-26 | 2018-07-03 | 70 | 60 | 10 | 2018-07-05 | 2019-07-01 | 246 |  | 246 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4247-2018 | 1034 | 4455 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-06-11 | 41 | 32 | 9 | [7 empty] | 0 |  |  | 2018-06-12 | 2018-10-29 | 97 |  | 97 |  |  | 0 |  |  | 2018-11-06 |  | Not supplied |  | Complex |  |  |  | 0 |  |  |  |  | 2022-05-31 | Online
WMECO | Granville | 6S4248-2018 | 1034 | 996 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-10-29 | 138 |  | 138 | [7 empty] | 0 |  |  | 2018-10-29 | 2019-02-14 | 73 |  | 73 |  |  | 0 |  |  | 2019-04-19 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A3370-2018 | 1543 | 4890 | Solar | 17K2 | 2018-03-28 | 2019-02-05 | 214 |  | 214 | 2019-02-05 | 2019-03-22 | 32 |  | 32 | [7 empty] | 0 |  |  | 2019-10-16 | 2020-01-07 | 55 |  | 55 |  |  | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A3396-2018 | 1070 | 4998 | Solar | 18K3 | 2018-04-06 | 2018-07-05 | 62 | 60 | 2 | 2018-07-06 | 2018-07-30 | 17 |  | 17 | [7 empty] | 0 |  |  | 2019-01-18 | 2019-04-25 | 66 |  | 66 |  |  | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B1847-2018 | 1235 | 4998 | Solar | 18C2 | 2018-04-09 | 2018-05-07 | 20 | 15 | 5 | 2018-05-08 |  | -30796 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-10-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4298-2018 | 1104 | 500 | Solar | 21S6 | 2018-04-09 | 2018-05-02 | 17 | 14 | 3 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | 2018-05-17 | 2018-06-07 | 15 |  | 15 |  |  | 0 |  |  | 2018-05-16 |  | -30802 |  |  |  |  | 0 |  |  | 2018-11-26 |  | 2018-06-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4299-2018 | 1001 | 576.6 | Solar | 16C16 | 2018-04-09 | 2018-05-02 | 17 | 14 | 3 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | [7 empty] | 0 |  |  | 2018-05-16 | 2018-09-29 | 95 |  | 95 |  |  | 0 |  |  |  |  | 2018-06-15 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1854-2018 | 1253 | 1375 | Solar | 19J4 | 2018-04-16 | 2018-05-07 | 15 | 5 | 10 | 2018-05-08 | 2018-05-10 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | April 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3441-2018 | 1360 | 4988 | Solar | 21B8 | 2018-04-23 | 2018-05-14 | 16 | 6 | 10 | 2019-02-06 |  | -30982 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1868-2018 | 1237 | 15.12 | Solar | 15E2 | 2018-04-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-21 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4359-2018 | 1129 | 12.32 | Solar | 20A34 | 2018-04-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4367-2018 | 1104 | 800 | Solar | 5J15 | 2018-05-01 | 2018-06-05 | 25 | 17 | 8 | 2018-06-06 | 2018-07-18 | 30 |  | 30 | [7 empty] | 0 |  |  | 2018-09-26 | 2018-11-19 | 37 |  | 37 |  |  | 0 |  |  | 2018-11-21 |  | 2018-08-31 |  | Standard |  |  |  | 0 |  |  |  |  | 2022-08-16 | Online
WMECO | Gill | 6A3473-2018 | 1354 | 132 | Solar | 21B8 | 2018-05-07 | 2018-06-11 | 25 | 20 | 5 | 2018-06-12 | 2018-06-19 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A3474-2018 | 1354 | 2310 | Solar | 21B8 | 2018-05-08 | 2018-05-29 | 15 | 9 | 6 | 2018-05-30 | 2018-05-31 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A3478-2018 | 1070 | 990 | Solar | 18K3 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A3480-2018 | 1050 | 900 | Solar | 29R2 | 2018-05-09 | 2018-06-21 | 31 | 23 | 8 | 2018-06-22 | 2018-08-01 | 28 |  | 28 | [7 empty] | 0 |  |  | 2018-12-04 | 2019-05-17 | 112 |  | 112 |  |  | 0 |  |  | 2019-06-26 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1875-2018 | 1237 | 990 | Solar | 15E2 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-05 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4395-2018 | 1034 | 990 | Solar | 29A5 | 2018-05-09 | 2018-06-20 | 30 | 22 | 8 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B1876-2018 | 1270 | 990 | Solar | 18C1 | 2018-05-10 | 2018-06-20 | 29 | 21 | 8 | 2018-06-21 | 2018-07-23 | 22 |  | 22 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A3483-2018 | 1038 | 249.8 | Solar | 18G5 | 2018-05-14 | 2018-06-06 | 17 | 5 | 12 | 2018-06-07 | 2018-08-15 | 49 |  | 49 | [7 empty] | 0 |  |  | 2018-12-02 | 2018-12-03 | 1 |  | 1 |  |  | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3484-2018 | 1035 | 499.9 | Solar | 17K5 | 2018-05-14 | 2018-06-06 | 17 | 6 | 11 | 2018-06-07 | 2018-08-06 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4407-2018 | 1107 | 240 | Solar | 21S6 | 2018-05-14 | 2018-05-31 | 13 | 5 | 8 | 2018-06-01 | 2018-06-14 | 10 | 8 | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-06-28 |  | 2018-08-17 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-12-12 | Online
WMECO | Springfield | 6S4409-2018 | 1104 | 199.8 | Solar | 5J13 | 2018-05-14 | 2018-06-13 | 22 | 14 | 8 | 2018-06-14 | 2018-10-23 | 91 |  | 91 | 2018-10-24 |  | -30913 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-27 |  | 2018-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-04 | Online
WMECO | Conway | 6A3492-2018 | 1341 | 900 | Solar | 38A1 | 2018-05-15 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2018-07-06 | 11 |  | 11 | [7 empty] | 0 |  |  | 2018-12-04 | 2019-05-17 | 112 |  | 112 |  |  | 0 |  |  | 2019-06-13 |  | Not supplied |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A3493-2018 | 1098 | 990 | Solar | 18K3 | 2018-05-15 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2018-07-06 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1881-2018 | 1201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 91 | 0 | 91 | 2018-09-21 | 2018-11-19 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1882-2018 | 1201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 91 | 0 | 91 | 2018-09-21 | 2018-11-19 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A3497-2018 | 1370 | 990 | Solar | 22B5 | 2018-05-16 | 2018-06-20 | 25 | 21 | 4 | 2018-06-21 | 2019-03-29 | 191 |  | 191 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A3498-2018 | 1098 | 990 | Solar | 18K3 | 2018-05-16 | 2018-06-20 | 25 | 21 | 4 | 2018-06-21 | 2018-07-27 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1887-2018 | 1238 | 480 | Solar | 16B1 | 2018-05-17 | 2018-09-19 | 87 | 0 | 87 | 2018-09-19 | 2018-11-05 | 33 |  | 33 | [7 empty] | 0 |  |  | 2018-11-14 |  | -30927 |  |  |  |  | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4424-2018 | 1119 | 19.2 | Solar | 20A33 | 2018-05-17 | 2018-11-08 | 122 |  | 122 | 2018-11-08 |  | -30924 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-07-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3509-2018 | 1330 | 4980 | Solar | 38A1 | 2018-05-21 | 2018-06-21 | 23 | 19 | 4 | 2018-06-22 | 2018-07-31 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A3510-2018 | 1050 | 4980 | Solar | 19J5 | 2018-05-21 | 2018-06-21 | 23 | 19 | 4 | 2018-06-22 | 2018-07-31 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3512-2018 | 1342 | 2000 | Solar | 22B3 | 2018-05-22 | 2018-06-05 | 10 | 9 | 1 | 2018-06-06 | 2018-07-16 | 28 | 17 | 11 | [7 empty] | 0 |  |  | 2018-07-17 | 2018-11-02 | 77 |  | 77 |  |  | 0 |  |  | 2018-11-29 |  | 2019-01-31 |  | Complex |  |  |  | 0 |  |  |  |  | 2022-09-20 | Online
WMECO | Granville | 6S4443-2018 | 1034 | 4980 | Solar | 29A5 | 2018-05-23 | 2018-06-21 | 21 | 17 | 4 | 2018-06-22 | 2018-07-30 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3523-2018 | 1342 | 72 | Solar | 22B1 | 2018-05-24 | 2018-06-20 | 19 | 13 | 6 | 2018-06-21 | 2018-07-16 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-08-30 |  | 2018-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-10-02 | Online
WMECO | Springfield | 6S4457-2018 | 1104 | 975 | Solar | 5J9 | 2018-05-25 | 2018-06-11 | 11 | 8 | 3 | 2018-06-12 | 2018-09-20 | 71 |  | 71 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-02-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4459-2018 | 1129 | 333.3 | Solar | 20A23 | 2018-05-25 | 2018-06-20 | 18 | 5 | 13 | 2018-06-21 | 2018-06-22 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-07 |  | 2018-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A3534-2018 | 1073 | 5000 | Solar | 15A1 | 2018-05-30 | 2018-08-02 | 46 | 39 | 7 | 2018-08-03 | 2018-09-11 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-11-01 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1906-2018 | 1201 | 2656 | Solar | 30B2 | 2018-05-30 | 2018-07-31 | 44 | 34 | 10 | 2018-08-01 | 2020-03-18 | 403 |  | 403 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B1907-2018 | 1008 | 4980 | Solar | 19J2 | 2018-05-30 | 2018-09-12 | 74 | 49 | 25 | 2018-09-13 |  | -30885 | [9 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4467-2018 | 1104 | 210 | Solar | 21S7 | 2018-05-31 | 2018-06-27 | 20 | 3 | 17 | 2018-06-28 | 2018-08-08 | 29 |  | 29 | 2018-11-13 | 2018-11-20 | 6 |  | 6 |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-21 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4468-2018 | 1034 | 594 | Solar | 29A5 | 2018-05-31 | 2018-06-25 | 18 | 14 | 4 | 2018-06-26 | 2018-07-31 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4469-2018 | 1034 | 1992 | Solar | 29A5 | 2018-05-31 | 2018-07-31 | 43 | 33 | 10 | 2018-08-01 | 2018-08-20 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A3550-2018 | 1344 | 2000 | Solar | 21C5 | 2018-06-05 | 2018-06-28 | 18 | 14 | 4 | 2018-06-29 | 2018-08-01 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A3553-2018 | 1027 | 27 | Solar | 15A3 | 2018-06-07 | 2018-06-20 | 10 | 2 | 8 | 2018-06-21 |  | -30827 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4501-2018 | 1104 | 999 | Solar | 5J13 | 2018-06-07 | 2018-07-12 | 25 | 17 | 8 | 2018-07-13 | 2018-08-24 | 31 |  | 31 | [7 empty] | 0 |  |  | 2018-12-31 | 2019-05-16 | 94 |  | 94 |  |  | 0 |  |  | 2019-12-20 |  | Not supplied |  | Standard |  |  |  | 0 |  |  |  |  | 2024-07-23 | Online
WMECO | Amherst | 6A3567-2018 | 1002 | 433.3 | Solar | 17K8 | 2018-06-12 | 2018-06-20 | 7 | 0 | 7 | 2018-06-21 | 2018-09-18 | 62 |  | 62 | 2018-09-19 | 2018-11-02 | 32 |  | 32 |  |  | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  | 2018 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4517-2018 | 1105 | 2500 | Diesel | 8CNW_1 | 2018-06-14 | 2019-02-05 | 160 | 158 | 2 | 2019-02-05 | 2020-01-14 | 234 |  | 234 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2023-06-14 |  | 2012 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Hadley | 6A3587-2018 | 1035 | 133.2 | Solar | 17K5 | 2018-06-20 | 2018-08-01 | 30 | 24 | 6 | 2018-08-02 | 2018-09-05 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-12-07 |  | September 2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-04-25 | Online
WMECO | Lee | 6B1926-2018 | 1238 | 2000 | Solar | 17G3 | 2018-06-20 | 2018-07-16 | 18 | 6 | 12 | 2018-07-17 | 2018-08-27 | 30 |  | 30 | [7 empty] | 0 |  |  | 2018-11-23 | 2019-12-10 | 260 |  | 260 |  |  | 0 |  |  | 2020-03-24 |  | 2019-01-20 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3593-2018 | 1002 | 2000 | Battery | 18G7 | 2018-06-22 | 2019-01-17 | 142 |  | 142 | 2019-01-17 | 2019-05-31 | 92 |  | 92 | [7 empty] | 0 |  |  | 2019-06-10 | 2019-07-31 | 37 |  | 37 |  |  | 0 |  |  | 2019-09-04 |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Blandford | 6B1932-2018 | 1008 | 4450 | Solar | 19J2 | 2018-06-26 | 2018-08-01 | 26 | 13 | 13 | 2018-08-02 | 2018-10-10 | 48 |  | 48 | [7 empty] | 0 |  |  | 2019-02-07 | 2019-07-19 | 112 |  | 112 |  |  | 0 |  |  | 2019-08-05 |  | 2019-09-30 |  | Complex |  |  |  | 0 | [5 empty] | customer hold
WMECO | Longmeadow | 6S4578-2018 | 1106 | 600 | Diesel | 22H12 | 2018-06-28 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-10-26 | Online
WMECO | Pittsfield | 6B1937-2018 | 1201 | 1850 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 23 | 19 | 4 | 2018-08-02 |  | -30856 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1938-2018 | 1201 | 4998 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 23 | 18 | 5 | 2018-08-02 | 2018-08-29 | 20 |  | 20 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-12-31 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A3610-2018 | 1340 | 3300 | Solar | 29R2 | 2018-07-03 | 2018-07-17 | 10 | 4 | 6 | 2018-07-18 | 2018-08-15 | 21 |  | 21 | [7 empty] | 0 |  |  | 2019-08-13 |  | -31111 |  |  |  |  | 0 |  |  |  |  | 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S4596-2018 | 1034 | 40 | Solar | 29A5 | 2018-07-03 | 2018-07-24 | 15 | 6 | 9 | 2018-07-25 | 2018-10-22 | 62 |  | 62 | 2018-10-22 |  | -30911 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2018-11-29 |  | 2018-08-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-11-24 | Online
WMECO | Greenfield | 6A3611-2018 | 1301 | 4998 | Solar | 22B7 | 2018-07-05 | 2018-07-24 | 14 | 7 | 7 | 2018-07-25 |  | -30850 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q2 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A3612-2018 | 1373 | 4998 | Solar | 18G6 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-28 | 25 |  | 25 | [7 empty] | 0 |  |  | 2018-11-20 | 2019-04-16 | 98 |  | 98 |  |  | 0 |  |  | 2019-05-15 |  | Q2 2019 |  | Complex |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A3615-2018 | 1337 | 180 | Solar | 21C1 | 2018-07-05 | 2018-08-01 | 20 | 17 | 3 | 2018-08-02 | 2018-09-05 | 24 |  | 24 |  | 2019-10-09 | [5 empty] | 0 | [9 empty] | 0 |  |  | 2019-10-09 |  | 2018-12-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-22 | Online
WMECO | Tolland | 6B1941-2018 | 1034 | 4998 | Solar | 19J4 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-15 | 16 |  | 16 | [7 empty] | 0 |  |  | 2019-05-07 |  | -31043 |  |  |  |  | 0 |  |  |  |  | Q2 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4610-2018 | 1056 | 14.08 | Solar | 19S1 | 2018-07-06 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-08-02 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3626-2018 | 1035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 58 |  | 58 | 2018-09-28 | 2019-04-18 | 135 |  | 135 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3627-2018 | 1035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 58 |  | 58 | 2018-10-02 | 2018-10-31 | 21 |  | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3631-2018 | 1071 | 13.688 | Solar | 19J2 | 2018-07-11 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-05-28 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S4648-2018 | 1030 | 15.36 | Solar | 16C17 | 2018-07-13 | 2018-10-18 | 68 | 31 | 37 | 2018-10-18 | 2019-01-17 | 61 |  | 61 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-28 |  | 2018-09-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-19 | Online
WMECO | Gill | 6A3641-2018 | 1354 | 4950 | Solar | 21C5 | 2018-07-17 | 2018-08-02 | 13 | 0 | 13 | 2018-08-03 | 2018-09-10 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-02-25 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4645-2018 | 1108 | 37.6 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-08-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-05-03 | Online
WMECO | Springfield | 6S4646-2018 | 1108 | 37.9 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 24 |  | 24 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-20 |  | 2018-08-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-05-03 | Online
WMECO | Russell | 6A3655-2018 | 1071 | 13.928 | Solar | 19J2 | 2018-07-24 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-09-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B1959-2018 | 1237 | 4890 | Solar | 15E1 | 2018-07-24 | 2018-08-31 | 29 | 11 | 18 | 2018-09-04 | 2019-04-01 | 141 |  | 141 | [7 empty] | 0 |  |  | 2019-05-30 | 2022-06-13 | 760 |  | 760 |  |  | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4675-2018 | 1001 | 4890 | Solar | 30A3 | 2018-07-24 | 2018-08-13 | 15 | 13 | 2 | 2018-08-14 | 2019-03-29 | 154 |  | 154 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Standard |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4685-2018 | 1077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 128 |  | 128 | 2019-01-29 | 2019-05-07 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4686-2018 | 1077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 128 |  | 128 | 2019-01-29 | 2019-05-07 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4747-2018 | 1106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-26 | 33 | 0 | 33 | 2018-09-27 |  | -30895 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-08 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4748-2018 | 1104 | 209.8 | Solar | 5J14 | 2018-08-10 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4750-2018 | 1106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-21 | 30 | 0 | 30 | 2018-10-12 | 2018-11-21 | 28 |  | 28 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-25 |  | 2018-11-08 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4751-2018 | 1104 | 209.8 | Solar | 5J14 | 2018-08-10 | 2018-10-12 | 44 | 0 | 44 | 2018-10-12 | 2018-11-20 | 27 |  | 27 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4753-2018 | 1001 | 286.4 | Solar | 30A3 | 2018-08-10 | 2018-10-01 | 36 | 0 | 36 | 2018-10-01 | 2018-11-20 | 35 |  | 35 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-25 |  | 2018-11-06 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4754-2018 | 1106 | 66.6 | Solar | 22H12 | 2018-08-10 | 2018-10-03 | 38 | 0 | 38 | 2018-10-03 | 2018-11-26 | 36 |  | 36 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-11-06 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-01 | Online
WMECO | Northfield | 6A3710-2018 | 1360 | 4950 | Solar | 21B8 | 2018-08-14 | 2018-09-12 | 21 | 1 | 20 | 2018-09-13 | 2019-08-16 | 230 |  | 230 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-02-15 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4780-2018 | 1106 | 163.3 | Solar | 22H16 | 2018-08-16 | 2018-10-12 | 40 | 0 | 40 | 2018-10-12 | 2018-11-26 | 30 |  | 30 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2018-11-26 |  | 2018-11-12 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3737-2018 | 1071 | 4998 | Solar | 19J2 | 2018-08-21 | 2018-10-29 | 48 |  | 48 | 2018-10-30 | 2019-04-01 | 102 |  | 102 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Erving | 6A3738-2018 | 1344 | 4494.4 | Solar | 21B9 | 2018-08-21 | 2019-01-03 | 91 |  | 91 | 2019-01-03 | 2019-03-28 | 58 |  | 58 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B1993-2018 | 1253 | 4998 | Solar | 19J4 | 2018-08-21 | 2018-12-11 | 77 | 71 | 6 | 2018-12-11 | 2019-04-01 | 74 |  | 74 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lee | 6B1994-2018 | 1238 | 120 | Solar | 17G3 | 2018-08-23 | 2018-10-09 | 32 | 0 | 32 | 2018-10-10 | 2019-01-15 | 65 |  | 65 | 2019-03-26 | 2019-04-30 | 25 |  | 25 |  |  | 0 | [9 empty] | 0 |  |  | 2019-05-13 |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B1997-2018 | 1201 | 253.1 | Solar | 30B2 | 2018-08-27 | 2018-09-20 | 18 | 0 | 18 | 2018-09-20 | 2018-12-12 | 57 |  | 57 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-25 |  | 2018-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S4816-2018 | 1030 | 250 | Solar | 16C17 | 2018-08-28 | 2018-10-24 | 40 | 0 | 40 | 2018-10-25 | 2018-12-12 | 33 |  | 33 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 11/31/18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2002-2018 | 1201 | 1450 | Solar | 19A5 | 2018-08-29 | 2018-11-28 | 62 | 0 | 62 | 2018-11-28 | 2019-03-05 | 65 |  | 65 | [7 empty] | 0 |  |  | 2019-05-21 | 2019-08-19 | 63 |  | 63 |  |  | 0 |  |  | 2019-08-19 |  | 2018-09-01 |  | Standard |  |  |  | 0 | [5 empty] | customer hold
WMECO | Chesterfield | 6A3750-2018 | 1026 | 3500 | Solar | 18K3 | 2018-08-30 | 2018-09-25 | 18 | 0 | 18 | 2018-09-26 |  | -30894 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 3/15/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S4833-2018 | 1056 | 2772 | Solar | 19S1 | 2018-08-31 | 2018-11-28 | 60 | 0 | 60 | 2018-11-28 |  | -30936 | [9 empty] | 0 |  |  | 2019-07-25 | 2020-03-09 | 154 |  | 154 |  |  | 0 |  |  | 2020-03-25 |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Sandisfield | 6B2011-2018 | 1255 | 400 | Solar | 19J4 | 2018-09-06 | 2018-09-21 | 12 | 0 | 12 | 2018-09-24 | 2018-11-25 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-08-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S4841-2018 | 1104 | 450 | Solar | 5J9 | 2018-09-06 | 2018-11-29 | 58 | 0 | 58 | 2018-11-29 | 2018-12-12 | 10 |  | 10 | [7 empty] | 0 |  |  | 2018-12-18 | 2018-12-19 | 2 |  | 2 |  |  | 0 |  |  |  |  | 2018-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S4842-2018 | 1001 | 580 | Solar | 16C16 | 2018-09-10 | 2018-10-09 | 21 | 0 | 21 | 2018-10-10 | 2020-08-06 | 453 |  | 453 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-29 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3767-2018 | 1330 | 4450 | Solar | 38A1 | 2018-09-11 | 2018-11-30 | 56 | 0 | 56 | 2018-12-03 | 2019-02-22 | 55 |  | 55 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 10/1/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S4890-2018 | 1106 | 16.24 | Solar | 22H12 | 2018-09-19 | 2018-10-24 | 25 | 0 | 25 | 2018-10-25 | 2018-11-21 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-23 |  | 2018-09-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2018-11-26 | Online
WMECO | Agawam | 6S4959-2018 | 1001 | 366.3 | Solar | 30A3 | 2018-10-05 | 2018-10-30 | 17 |  | 17 | 2018-10-31 | 2019-01-17 | 52 |  | 52 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-30 |  | 2018-11-26 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A3820-2018 | 1071 | 5000 | Solar | 19J2 | 2018-10-08 | 2018-12-19 | 50 |  | 50 | 2018-12-19 | 2019-05-07 | 93 |  | 93 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2036-2018 | 1201 | 1000 | Solar | 30B3 | 2018-10-12 | 2019-01-14 | 62 |  | 62 | 2019-01-14 | 2019-02-04 | 15 |  | 15 | [7 empty] | 0 |  |  | 2019-12-09 | 2020-03-13 | 65 |  | 65 |  |  | 0 |  |  | 2020-04-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3840-2018 | 1002 | 250 | Solar | 19B16 | 2018-10-15 | 2018-11-06 | 17 |  | 17 | 2018-11-06 | 2019-01-10 | 43 |  | 43 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3841-2018 | 1002 | 1000 | Solar | 19B16 | 2018-10-15 | 2018-11-20 | 26 |  | 26 | 2018-11-20 | 2019-01-28 | 45 |  | 45 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S4998-2018 | 1077 | 18872 | Solar | 29A5 | 2018-10-18 | [16 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S5004-2018 | 1077 | 150 | Solar | 29A5 | 2018-10-22 | 2018-10-24 | 3 | 0 | 3 | 2018-10-25 | 2019-01-11 | 52 |  | 52 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5005-2018 | 1108 | 99.9 | Solar | 21S12 | 2018-10-22 | 2018-10-25 | 4 | 0 | 4 | 2018-10-26 |  | -30915 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2019-01-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2044-2018 | 1008 | 18872 | Solar | 19J2 | 2018-10-23 | 2019-01-14 | 55 |  | 55 | 2019-01-14 | 2019-02-13 | 22 |  | 22 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S5010-2018 | 1077 | 4400 | Solar | 29A5 | 2018-10-23 | 2019-02-07 | 72 |  | 72 | 2019-02-07 | 2019-03-28 | 34 |  | 34 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3861-2018 | 1373 | 4885 | Solar | 18G6 | 2018-10-26 | 2019-01-14 | 52 |  | 52 | 2019-01-14 | 2019-04-17 | 64 |  | 64 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Whately | 6A3868-2018 | 1373 | 999 | Solar | 18G8 | 2018-10-30 | 2019-01-17 | 53 | 50 | 3 | 2019-01-17 | 2019-03-29 | 49 |  | 49 | [7 empty] | 0 |  |  |  | 2023-11-09 | [5 empty] | 0 |  |  | 2023-11-10 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Ludlow | 6S5036-2018 | 1056 | 5550 | Solar | 19S1 | 2018-10-30 | 2019-01-17 | 53 |  | 53 | 2019-01-17 | 2019-03-22 | 44 |  | 44 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3871-2018 | 1002 | 36.496 | Solar | 17K4 | 2018-11-01 | 2018-11-05 | 3 |  | 3 | 2018-11-05 | 2019-01-29 | 56 |  | 56 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southampton | 6A3880-2018 | 1073 | 3180 | solar | 15A1 | 2018-11-02 | 2019-01-30 | 58 |  | 58 | 2019-01-30 | 2019-03-29 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne Falls | 6A3884-2018 | 1370 | 250 | Solar | 29R2 | 2018-11-05 | 2018-12-06 | 22 |  | 22 | 2018-12-06 | 2018-12-19 | 10 |  | 10 | 2019-10-25 | 2019-11-22 | 20 |  | 20 |  |  | 0 | [9 empty] | 0 |  |  | 2019-11-26 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-07-21 | Online
WMECO | Ludlow | 6S5054-2018 | 1056 | 4400 | Solar | 19S3 | 2018-11-05 | 2018-12-06 | 22 |  | 22 | 2018-12-06 | 2019-01-03 | 18 |  | 18 | [7 empty] | 0 |  |  | 2019-03-05 | 2019-07-25 | 99 |  | 99 |  |  | 0 |  |  | 2020-03-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6A3888-2018 | 1235 | 39600 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 | 2019-03-22 | 46 |  | 46 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6A3889-2018 | 1235 | 14400 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 |  | -30967 | [9 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2053-2018 | 1201 | 4347.65 | Solar | 15E2 | 2018-11-08 | 2019-01-15 | 44 |  | 44 | 2019-01-15 | 2019-02-13 | 21 |  | 21 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A3896-2018 | 1360 | 2104 | Solar | 21B8 | 2018-11-13 | 2019-03-19 | 84 |  | 84 | 2019-03-19 | 2019-03-28 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A3901-2018 | 1035 | 518.4 | Solar | 17K5 | 2018-11-15 | 2018-12-06 | 15 |  | 15 | 2018-12-06 | 2018-12-26 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3916-2018 | 1002 | 3000 | Battery | 18G4 | 2018-11-19 | 2019-02-04 | 51 |  | 51 | 2019-02-04 | 2019-05-08 | 65 |  | 65 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2020-03-26 |  | 4/5/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-01-09 | Online
WMECO | Springfield | 6S5117-2018 | 1103 | 32.83 | Solar | 8CNW_1 | 2018-11-20 | 2019-01-18 | 40 |  | 40 | 2019-01-18 | 2019-04-10 | 56 |  | 56 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5103-2018 | 1104 | 532.8 | Solar | 5J9 | 2018-11-21 | 2018-11-26 | 3 |  | 3 | 2018-11-26 | 2019-01-17 | 36 |  | 36 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Nov 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2062-2018 | 1201 | 463.01 | Solar | 19A5 | 2018-11-26 | 2019-01-24 | 40 |  | 40 | 2019-01-24 |  | -30973 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A3912-2018 | 1373 | 15.78 | Solar | 22B1 | 2018-11-28 | 2018-12-03 | 4 |  | 4 | 2018-12-03 | 2018-12-24 | 15 |  | 15 | [7 empty] | 0 |  |  | 2018-12-03 |  | -30939 |  |  |  |  | 0 |  |  | 2019-03-08 |  | 12/2018 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-17 | Online
WMECO | Agawam | 6S5118-2018 | 1001 | 4950 | Solar | 16C16 | 2018-11-30 | 2019-01-15 | 30 |  | 30 | 2019-01-28 | 2019-03-28 | 42 |  | 42 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2018-12-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3920-2018 | 1002 | 2500 | Solar | 17K2 | 2018-12-04 | 2019-01-24 | 34 |  | 34 | 2019-01-24 | 2019-03-22 | 40 |  | 40 | [7 empty] | 0 |  |  | 2019-04-24 | 2019-11-27 | 151 |  | 151 |  |  | 0 |  |  | 2020-03-27 |  | 10/1/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-08-23 | Online
WMECO | Lanesborough | 6B2072-2018 | 1237 | 4540 | Solar | 15E1 | 2018-12-11 | 2019-01-15 | 23 |  | 23 | 2019-01-15 | 2019-03-22 | 46 |  | 46 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Fall 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5140-2018 | 1109 | 24 | Solar | 5J17 | 2018-12-11 | 2019-01-17 | 25 |  | 25 | 2019-01-17 | 2019-04-02 | 51 |  | 51 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-03-18 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-16 | Online
WMECO | Greenfield | 6A3934-2018 | 1301 | 41.47 | Solar | 22B2 | 2018-12-14 | 2019-01-31 | 31 |  | 31 | 2019-01-31 | 2019-03-22 | 35 |  | 35 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3935-2018 | 1301 | 96 | Solar | 21C4 | 2018-12-14 | 2019-01-23 | 25 |  | 25 | 2019-01-23 | 2019-03-22 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3936-2018 | 1301 | 101.38 | Solar | 22B3 | 2018-12-14 | 2019-02-07 | 36 |  | 36 | 2019-02-07 | 2019-03-22 | 30 |  | 30 | 2019-06-19 |  | -31073 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3937-2018 | 1301 | 36 | Solar | 22B2 | 2018-12-14 | 2019-01-23 | 25 |  | 25 | 2019-01-23 | 2019-03-22 | 41 |  | 41 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-06-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3938-2018 | 1301 | 88.13 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 26 |  | 26 | 2019-01-24 | 2019-03-22 | 40 |  | 40 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-06-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A3939-2018 | 1301 | 194 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 26 |  | 26 | 2019-01-24 | 2019-04-02 | 47 |  | 47 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A3949-2018 | 1002 | 3182.224 | Solar | 18G7 | 2018-12-19 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S5163-2018 | 1089 | 228 | Solar | 16C15 | 2018-12-20 | 2019-01-03 | 8 |  | 8 | 2019-01-03 | 2019-01-17 | 11 |  | 11 | [7 empty] | 0 |  |  | 2019-01-03 |  | -30959 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ashfield | 6A3958-2018 | 1330 | 4998 | Solar | 38A1 | 2018-12-24 | 2019-02-04 | 27 |  | 27 | 2019-02-04 | 2019-03-28 | 37 |  | 37 | [7 empty] | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | 6A4077-2019 | 1035 | 1000 | Battery | 17K6 | 2019-01-03 | 2019-05-06 | 84 |  | 84 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2019-12-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-05-09 | Online
WMECO | Hadley | 6A4078-2019 | 1035 | 1000 | Battery | 17K1 | 2019-01-03 | 2019-05-06 | 84 |  | 84 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-25 | 68 |  | 68 |  |  | 0 |  |  | 2019-12-18 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-03-26 | Online
WMECO | Plainfield | 6A3984-2019 | 1070 | 1000 | Battery | 18K3 | 2019-01-22 | 2019-02-07 | 13 |  | 13 | 2019-02-07 | 2019-03-22 | 30 |  | 30 | [7 empty] | 0 |  |  | 2019-07-22 | 2019-10-16 | 61 |  | 61 |  |  | 0 |  |  | 2020-03-27 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-01-24 | Online
WMECO | Hatfied | 6A4031-2019 | 1038 | 232 | Solar | 18G5 | 2019-02-14 | 2019-03-19 | 22 |  | 22 | 2019-03-19 | 2019-04-02 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-05-24 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-07-21 | Online
WMECO | Leyden | 6A4033-2019 | 1301 | 4980 | Solar | 22B7 | 2019-02-14 | 2019-02-22 | 6 |  | 6 | 2019-02-22 | 2019-04-18 | 38 |  | 38 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4034-2019 | 1340 | 1980 | Solar | 29R2 | 2019-02-14 | 2019-02-22 | 6 |  | 6 | 2019-02-22 | 2019-03-19 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4045-2019 | 1360 | 3000 | Solar | 21B8 | 2019-02-20 | 2019-04-01 | 28 | 27 | 1 | 2019-04-01 | 2019-04-18 | 13 |  | 13 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Northfield | 6A4048-2019 | 1360 | 2000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 52 | 47 | 5 | 2019-05-06 | 2019-06-07 | 24 |  | 24 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Northfield | 6A4049-2019 | 1360 | 1000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 52 | 42 | 10 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 |  |  | 2020-08-04 | 2022-12-14 | 598 |  | 598 |  |  | 0 |  |  | 2023-02-27 |  | 2020-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Ashfield | 6A4068-2019 | 1330 | 4950 | Solar |  | 2019-03-06 | 2019-05-08 | 44 |  | 44 | [12 empty] | 0 | [9 empty] | 0 |  |  |  |  | 4/4/2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5364-2019 | 1056 | 212 | Solar | 27A5 | 2019-03-13 | 2019-05-14 | 43 |  | 43 | 2019-05-14 | 2019-06-28 | 33 |  | 33 | 2020-04-15 | 2020-09-16 | 107 |  | 107 |  |  | 0 | [9 empty] | 0 |  |  | 2020-09-16 |  | 2019-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-07-10 | Online
WMECO | Whately | 6A4126-2019 | 1093 | 1000 | Battery | 18G8 | 2019-03-18 | 2019-04-22 | 24 |  | 24 | 2019-04-22 | 2019-05-08 | 13 |  | 13 | [7 empty] | 0 |  |  |  | 2020-01-16 | [5 empty] | 0 |  |  | 2020-03-23 |  | 3/1/2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5370-2019 | 1056 | 136 | Solar | 19S3 | 2019-03-19 | 2019-04-30 | 30 |  | 30 | 2019-04-30 | 2019-05-13 | 10 |  | 10 | 2019-06-04 | 2019-07-30 | 40 |  | 40 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-22 |  | Q3 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5376-2019 | 1001 | 15.08 | Solar | 30A5 | 2019-03-19 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-03-03 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A4093-2019 | 1342 | 72 | Solar | 22B1 | 2019-03-25 | 2019-05-07 | 31 |  | 31 | 2019-05-07 | 2019-09-05 | 85 |  | 85 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-09-26 |  | 5/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-04-21 | Online
WMECO | Springfield | 6S5394-2019 | 1104 | 80 | Solar | 5J16 | 2019-03-27 | 2019-04-03 | 6 |  | 6 | 2019-04-03 | 2019-04-11 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | ASAP |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4098-2019 | 1360 | 1000 | Solar | 21B8 | 2019-03-29 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5405-2019 | 1001 | 4990 | Solar | 30A3 | 2019-04-03 | 2019-05-06 | 23 |  | 23 | 2019-05-06 | 2019-05-23 | 14 |  | 14 | [7 empty] | 0 |  |  |  | 2019-06-24 | [5 empty] | 0 |  |  |  |  | Summer 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Deerfield | 6A4131-2019 | 1342 | 25.3 | Solar | 22B7 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-06-03 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-08-15 |  | 6/12/2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-12-11 | Online
WMECO | Lanesborough | 6B2129-2019 | 1237 | 3960 | Solar | 15E1 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2130-2019 | 1237 | 4990 | Solar | 15E2 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2131-2019 | 1237 | 4990 | Solar | 15E1 | 2019-04-17 | 2019-05-06 | 14 |  | 14 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Spring 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5434-2019 | 1229 | 200 | Solar | 27A13 | 2019-04-17 | 2019-05-08 | 16 |  | 16 | 2019-05-08 | 2019-05-23 | 12 |  | 12 | 2019-09-25 | 2020-06-23 | 184 |  | 184 |  |  | 0 | [9 empty] | 0 |  |  | 2020-06-23 |  | 2020-03-24 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-09-21 | Online
WMECO | Colrain | 6A4169-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 7/30/2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4199-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4200-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Colrain | 6A4201-2019 | 1340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 26 |  | 26 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-07-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A4175-2019 | 1002 | 3778 | Solar | 18G7 | 2019-05-13 | [16 empty] | 0 | [9 empty] | 0 |  |  | 2019-09-11 |  | Oct 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2019-07-30 | Online
WMECO | Tolland | 6B2161-2019 | 1034 | 5000 | Solar | 19J4 | 2019-06-11 | 2019-06-20 | 8 | 6 | 2 | 2019-06-20 | 2019-06-21 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Q4 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Plainfield / Blandford Group Study
WMECO | Whately | 6A4237-2019 | 1093 | 1000 | Solar | 18G8 | 2019-06-13 | 2019-06-20 | 6 |  | 6 | 2019-06-20 | 2019-06-26 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S5606-2019 | 1001 | 4975 | Solar | 30A1 | 2019-06-14 | 2019-06-20 | 5 |  | 5 | 2019-06-20 | 2019-06-24 | 3 |  | 3 | [7 empty] | 0 |  |  | 2019-12-02 | 2020-02-19 | 53 |  | 53 |  |  | 0 |  |  | 2020-04-03 |  | 2018-12-14 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-16 | Online
WMECO | Westhampton | 6A4242-2019 | 1027 | 34 | Solar | 15A3 | 2019-06-17 | 2019-09-11 | 61 |  | 61 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | 2019-10-17 | 2020-02-05 | 74 |  | 74 |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-12 |  | Not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-08-17 | Online
WMECO | Greenfield | 6A4259-2019 | 1301 | 20 | Solar | 21C4 | 2019-06-21 | 2019-08-27 | 47 |  | 47 | 2019-08-27 | 2019-10-11 | 33 |  | 33 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-03 |  | 2019-08-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-16 | Online
WMECO | Turners Falls | 6A4261-2019 | 1376 | 460 | Solar | 21C2 | 2019-06-25 | 2019-06-26 | 2 |  | 2 | 2019-06-26 | 2019-07-01 | 4 |  | 4 | 2019-09-10 | 2019-10-22 | 30 |  | 30 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-24 |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Huntington | 6A4268-2019 | 1050 | 21.54 | Solar | 19J5 | 2019-06-25 | 2019-09-09 | 53 |  | 53 | 2019-09-09 | 2019-08-14 | -18 |  |  | 2019-09-12 | 2019-10-25 | 31 |  | 31 |  |  | 0 | [9 empty] | 0 |  |  | 2019-10-30 |  | Fall 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-08-20 | Online
WMECO | Springfield | 6S5635-2019 | 1102 | 1875 | Diesel | 5J13 | 2019-07-02 | 2019-09-09 | 48 |  | 48 | 2019-09-09 | 2019-12-11 | 65 |  | 65 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-08-11 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-15 | Online
WMECO | Ashfield | 6A4287-2019 | 1330 | 25 | Solar | 22B5 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 |  | -31087 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A4288-2019 | 1370 | 25 | Solar | 38A1 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 | 2019-08-06 | 20 |  | 20 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S5659-2019 | 1089 | 233.3 | Solar | 21N5 | 2019-07-12 | 2019-07-18 | 5 |  | 5 | 2019-07-18 | 2019-07-29 | 8 |  | 8 | 2020-02-19 |  | -31238 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2020-07-01 |  | 2019-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pelham | 6A4306-2019 | 1002 | 4400 | Solar | 17K2 | 2019-07-15 | 2019-09-26 | 53 | 52 | 1 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-06-29 | 391 |  | 391 |  |  | 0 |  |  |  |  | 1/1/21 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Amherst | 6A4309-2019 | 1002 | 4400 | Solar | 17K7 | 2019-07-15 | 2019-09-26 | 53 | 51 | 2 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-05-13 | 358 |  | 358 |  |  | 0 |  |  | 2023-01-20 |  | 2021-01-21 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Easthampton | 6A4329-2019 | 1027 | 1000 | Solar | 15A3 | 2019-07-19 | 2019-07-31 | 9 | 9 | 0 | 2019-07-31 | 2019-08-21 | 16 |  | 16 | [7 empty] | 0 |  |  | 2021-03-01 |  | -31493 |  |  |  |  | 0 |  |  |  |  | 2020-07-10 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | South Deerfield | 6A4414-2019 | 1773 | 25 | Solar | 22B3 | 2019-08-28 | 2019-09-03 | 4 |  | 4 | 2019-09-03 | 2019-09-03 | 1 |  | 1 | 2019-09-24 |  | -31140 |  |  |  |  | 0 | [9 empty] | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Gill | 6A4433-2019 | 1354 | 17.6 | Solar | 21C5 | 2019-09-03 | 2019-09-06 | 4 |  | 4 | 2019-09-06 | 2019-10-10 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-03 |  | 2019-10-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-03-31 | Online
WMECO | Lanesborough | 6B2239-2019 | 1237 | 34.2 | Solar | 15E1 | 2019-09-03 | 2019-10-02 | 22 |  | 22 | 2019-10-02 | 2019-10-10 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-30 |  | Nov 2019 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A4430-2019 | 1301 | 25 | Solar | 22B4 | 2019-09-05 | 2019-09-13 | 7 |  | 7 | 2019-09-13 | 2019-09-17 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-11-13 |  | Nov 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-02-07 | Online
WMECO | Windsor | 6B2245-2019 | 1270 | 6 | Solar | 18C1 | 2019-09-05 | 2019-10-30 | 39 |  | 39 | 2019-10-31 | 2019-10-31 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S5825-2019 | 1128 | 72 | Battery | 20A21 | 2019-09-12 | 2019-10-07 | 18 |  | 18 | 2019-10-07 | 2019-10-15 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-30 |  | 2019-12-30 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-08-27 | Online
WMECO | Northfield | 6A4475-2019 | 1360 | 25 | Solar | 21B8 | 2019-09-20 | 2019-10-01 | 8 |  | 8 | 2019-10-01 | 2019-10-08 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2019-11-30 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2269-2019 | 1008 | 4998 | Solar | 19J2 | 2019-10-01 | 2019-10-07 | 5 | 3 | 2 | 2019-10-07 | 2019-10-16 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Indian Orchard | 6S5881-2019 | 1151 | 6780 | Solar | 27A11 | 2019-10-01 | 2019-10-01 | 1 |  | 1 | 2019-10-01 | 2020-01-09 | 67 |  | 67 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-04-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S5908-2019 | 1056 | 3.8 | Solar | 27A4 | 2019-10-09 | 2019-10-28 | 13 |  | 13 | 2019-10-29 | 2019-11-01 | 4 |  | 4 | 2020-05-19 | 2020-05-20 | 2 |  | 2 |  |  | 0 | [9 empty] | 0 |  |  | 2020-05-21 |  | 2019-11-08 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-15 | Online
WMECO | Amherst | 6A4520-2019 | 1002 | 20 | Solar | 17K8 | 2019-10-10 | 2019-10-15 | 3 |  | 3 | 2019-10-15 | 2019-10-21 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-11-06 |  | Dec 2019 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-02-13 | Online
WMECO | Greenfield | 6A4584-2019 | 1301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 4 |  | 4 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  | 5/2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-30 | Online
WMECO | Greenfield | 6A4585-2019 | 1301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 4 |  | 4 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2019-12-04 |  | 5/2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-30 | Online
WMECO | Deerfield | 6A4600-2019 | 1373 | 2250 | Solar | 22B1 | 2019-11-14 | 2019-11-20 | 5 | 3 | 2 | 2019-11-20 | 2019-12-02 | 8 |  | 8 | [7 empty] | 0 |  |  | 2021-02-26 | 2023-11-07 | 693 |  | 693 |  |  | 0 |  |  | 2023-11-10 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Pelham | 6A4622-2019 | 1002 | 17.6 | Solar | 17K2 | 2019-11-21 | 2020-01-30 | 46 |  | 46 | 2020-01-30 | 2020-02-04 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-30 |  | 2019-12-17 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-14 | Online
WMECO | Tyringham | 6B2332-2019 | 1264 | 26.25 | Solar | 16B1 | 2019-11-27 | 2019-12-17 | 14 |  | 14 | 2019-12-17 | 2020-01-22 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Greenfield | 6A4674-2019 | 1301 | 23.4 | Solar | 22B7 | 2019-12-31 | 2020-01-10 | 8 |  | 8 | 2020-01-13 | 2020-01-31 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-24 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Russell | 6A4686-2020 | 1071 | 2750 | Solar | 19J2 | 2020-01-13 | 2020-01-15 | 3 | 2 | 1 | 2020-01-16 | 2020-02-10 | 17 |  | 17 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-09-30 |  | Expedited |  |  |  | 0 | [5 empty] | Plainfield / Blandford Group Study
WMECO | Greenfield | 6A4689-2020 | 1301 | 23.4 | Solar | 28WNW_1 | 2020-01-13 | 2020-01-28 | 11 |  | 11 | 2020-01-28 | 2020-01-30 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-06-01 |  | 2020-03-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-08 | Online
WMECO | Windsor | 6B2367-2020 | 1270 | 6 | Solar | 18C1 | 2020-01-16 | 2020-02-28 | 30 |  | 30 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-03-13 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-01-08 | Online
WMECO | Chesterfield | 6A4702-2020 | 1012 | 17 | Solar | 18K3 | 2020-01-22 | 2020-01-24 | 3 |  | 3 | 2020-01-28 | 2020-01-28 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | March 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A4735-2020 | 1370 | 240 | Solar | 29R2 | 2020-02-19 | 2020-02-26 | 6 |  | 6 | 2020-02-27 | 2020-03-09 | 8 |  | 8 | 2020-04-07 | 2020-07-09 | 65 |  | 65 |  |  | 0 | [9 empty] | 0 |  |  | 2020-07-09 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-10-07 | Online
WMECO | Conway | 6A4737-2020 | 1341 | 17.6 | Solar | 38A1 | 2020-02-19 | 2020-02-28 | 8 |  | 8 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-04-07 |  | 2020-04-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-22 | Online
WMECO | Easthampton | 6A4739-2020 | 1027 | 133 | Solar | 15A3 | 2020-02-21 | 2020-02-28 | 6 |  | 6 | 2020-02-28 | 2020-03-13 | 11 |  | 11 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-08-27 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-09-05 | Online
WMECO | Greenfield | 6A4743-2020 | 1301 | 498 | Solar | 22B7 | 2020-02-25 | 2020-03-09 | 10 | 10 | 0 | 2020-03-09 | 2020-03-17 | 6 |  | 6 | 2020-09-15 | 2020-10-30 | 33 |  | 33 |  |  | 0 |  |  | 2021-01-09 | 2022-11-14 | 468 | 109 | 359 |  |  | 0 |  |  | 2023-01-12 |  | 1905-07-12 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Easthampton | 6A4745-2020 | 1027 | 500 | Solar | 15A3 | 2020-02-26 | 2020-02-28 | 3 |  | 3 | 2020-02-28 | 2020-03-17 | 12 |  | 12 | 2020-06-08 | 2020-08-17 | 50 |  | 50 |  |  | 0 | [9 empty] | 0 |  |  | 2020-08-18 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-15 | Online
WMECO | Haldle | 6A4756-2020 | 1035 | 18 | Solar | 18G5 | 2020-02-27 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4755-2020 | 1360 | 2000 | Solar | 21B8 | 2020-03-02 | 2020-06-24 | 80 | 80 | 0 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 | 2022-12-14 | 532 |  | 532 |  |  | 0 |  |  | 2023-02-27 |  | 2021-01-29 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Shelburne Falls | 6A4759-2020 | 1370 | 60 | Solar | 29R2 | 2020-03-03 | 2020-03-09 | 5 |  | 5 | 2020-03-09 | 2020-03-12 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-27 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-01-20 | Online
WMECO | Erving | 6A4764-2020 | 1344 | 43.2 | Solar | 21B8 | 2020-03-09 | 2020-03-11 | 3 |  | 3 | 2020-03-12 | 2020-03-31 | 13 |  | 13 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-04 |  | 2020-02-27 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-12-01 | Online
WMECO | Amherst | 6A4781-2020 | 1002 | 17 | Solar | 17K2 | 2020-03-17 | 2020-04-02 | 12 |  | 12 | 2020-04-02 | 2020-04-06 | 3 |  | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-28 |  | 2020-04-25 |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-10-15 | Online
WMECO | Springfield | 6S6248-2020 | 1105 | 292 | Solar | 21S4 | 2020-03-18 | 2020-04-21 | 24 |  | 24 | 2020-04-21 | 2020-04-27 | 5 |  | 5 | 2021-01-19 | 2021-02-04 | 12 |  | 12 |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | Nov 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2024-05-07 | Online
WMECO | Bernardston | 6A4815-2020 | 1337 | 996 | Solar | 21B8 | 2020-04-06 | 2020-11-03 | 147 | 0 | 147 | 2020-11-04 | 2020-11-09 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | July 2021 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Hatfield | 6A4825-2020 | 1038 | 2750 | Solar | 18G6 | 2020-04-13 | 2020-04-15 | 3 | 2 | 1 | 2020-04-16 | 2020-04-22 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-09-30 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Huntington | 6A4832-2020 | 1050 | 20 | Solar | 19J5 | 2020-04-17 | 2020-04-27 | 6 |  | 6 | 2020-04-28 | 2020-05-01 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-12 |  | Not Supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2020-09-11 | Online
WMECO | South Deerfield | 6A4834-2020 | 1373 | 10 | Battery | 22B1 | 2020-04-20 | 2020-04-27 | 5 |  | 5 | 2020-04-28 | 2020-05-05 | 6 |  | 6 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-05-15 |  | asap |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-03-10 | Online
WMECO | Northfield | 6A4835-2020 | 1360 | 2250 | Solar | 21B8 | 2020-04-20 | 2020-06-24 | 46 | 45 | 1 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-13 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Northfield | 6A4838-2020 | 1360 | 2000 | Solar | 21B8 | 2020-04-22 | 2020-06-24 | 45 | 43 | 2 | 2020-06-25 | 2020-07-23 | 20 |  | 20 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A4839-2020 | 1360 | 2000 | Solar | 21B8 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 |  |  | 2020-11-06 |  | -31419 |  |  |  |  | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Plainfield | 6A4840-2020 | 1070 | 3300 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 46 |  | 46 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Plainfield | 6A4841-2020 | 1070 | 3000 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 46 |  | 46 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4842-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-08-06 | 29 |  | 29 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Bernardston | 6A4843-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4844-2020 | 1337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4845-2020 | 1337 | 1570 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B2431-2020 | 1223 | 3640 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-23 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-23 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Becket | 6B2432-2020 | 1223 | 7860 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 45 | 44 | 1 | 2020-06-26 | 2020-07-23 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-05-23 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Dalton | 6B2451-2020 | 1226 | 16 | Solar | 19A1 | 2020-05-05 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2020-06-29 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Tolland | 6B2464-2020 | 1034 | 30.36 | Solar | 19J4 | 2020-05-21 | [16 empty] | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A4896-2020 | 1002 | 10 | Battery | 17K4 | 2020-06-05 | 2020-07-14 | 27 |  | 27 | 2020-07-15 | 2020-08-19 | 26 |  | 26 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-09-28 |  | July 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-22 | Online
WMECO | Tolland | 6B2480-2020 | 1034 | 30.36 | Solar | 19J4 | 2020-06-09 | 2020-08-18 | 50 | 49 | 1 | 2020-08-19 | 2020-09-03 | 12 |  | 12 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-10-21 |  | 2020-08-09 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-16 | Online
WMECO | Springfield | 6S6361-2020 | 1104 | 1669 | Solar | 5J13 | 2020-06-11 | 2020-06-25 | 11 | 11 | 0 | 2020-06-26 | 2020-07-30 | 24 |  | 24 | [7 empty] | 0 |  |  | 2020-12-04 | 2022-09-09 | 445 |  | 445 |  |  | 0 |  |  | 2022-09-19 |  | 2020-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Lee | 6B2503-2020 | 1238 | 4000 | Solar | 16B1 | 2020-06-15 | 2020-07-09 | 18 |  | 18 | 2020-07-10 | 2020-10-15 | 68 |  | 68 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A4913-2020 | 1337 | 4500 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Greenfield | 6A4914-2020 | 1301 | 1300 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [7 empty] | 0 |  |  | 2020-12-08 | 2022-12-30 | 523 | 18 | 505 |  |  | 0 |  |  | 2023-01-12 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6392-2020 | 1034 | 6750 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6393-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6394-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 12 | 0 | 2020-07-13 | 2020-09-25 | 54 |  | 54 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2021-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Granville | 6S6395-2020 | 1034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 12 | 13 | -1 | 2020-07-13 | 2020-10-05 | 60 |  | 60 | [7 empty] | 0 |  |  | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 |  |  | 0 |  |  | 2023-03-07 |  | 2020-07-18 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Dalton | 6B2502-2020 | 1226 | 499 | Solar | 19A3 | 2020-07-06 | 2020-08-05 | 23 | 22 | 1 | 2020-08-05 | 2020-08-14 | 8 | 34 | -26 |  |  |  | 0 |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-12 |  | Dec 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-29 | Online
WMECO | Feeding Hills | 6S6432-2020 | 1030 | 10 | Battery | 30A1 | 2020-07-13 | 2020-08-31 | 36 |  | 36 |  | 2020-09-23 | [10 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-02 |  | summer 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-03-15 | Online
WMECO | Agawam | 6S6455-2020 | 1001 | 50 | Solar | 30A3 | 2020-07-22 | 2020-10-23 | 66 |  | 66 | 2020-10-26 | 2020-11-19 | 19 |  | 19 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-12-16 |  | 2020-09-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-05-20 | Online
WMECO | Tyringham | 6B2524-2020 | 1264 | 9.6 | Battery | 16B1 | 2020-07-24 | 2020-08-31 | 27 |  | 27 | 2020-08-31 | 2020-09-09 | 7 |  | 7 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-15 |  | Summer 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-08-03 | Online
WMECO | Hatfield | 6A4961-2020 | 1038 | 20 | Solar | 18G6 | 2020-07-28 | 2020-09-09 | 31 |  | 31 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-10-05 |  | Autumn |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-02-10 | Online
WMECO | Deerfield | 6A4968-2020 | 1342 | 900 | Solar | 22B1 | 2020-08-04 | 2020-09-09 | 26 | 24 | 2 | 2020-09-09 | 2020-09-28 | 14 |  | 14 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | April 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6539-2020 | 1034 | 436 | Biogas | 29A5 | 2020-08-17 | 2020-09-16 | 22 | 20 | 2 | 2020-09-16 | 2020-10-21 | 25 |  | 25 | 2020-11-23 | 2021-01-25 | 40 |  | 40 |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-01-15 |  | Expedited |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Springfield | 6S6574-2020 | 1103 | 30 | Diesel | 8C24 | 2020-08-28 | 2020-09-22 | 17 | 15 | 2 | 2020-09-23 | 2020-10-27 | 24 | 21 | 3 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-03-11 |  | Dec 2020 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-06-23 | Online
WMECO | Springfield | 6S6575-2020 | 1103 | 75 | Diesel | 8C24 | 2020-08-28 | 2020-09-09 | 8 | 6 | 2 | 2020-09-10 | 2020-10-28 | 34 |  | 34 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Dec 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6576-2020 | 1103 | 35 | Diesel | 8C23 | 2020-08-28 | 2020-09-23 | 18 | 16 | 2 | 2020-09-24 | 2020-10-27 | 23 |  | 23 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | Dec 2020 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Shelburne | 6A5004-2020 | 1370 | 499 | Solar | 22B5 | 2020-09-03 | 2020-10-20 | 32 | 30 | 2 | 2020-10-21 | 2020-11-03 | 10 |  | 10 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2023-09-07 |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement
WMECO | Hadley | 6A5016-2020 | 1035 | 5000 | Solar | 18G4 | 2020-09-09 | 2020-09-09 | 1 | 0 | 1 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [7 empty] | 0 |  |  | 2021-04-21 | 2022-10-19 | 383 | 49 | 334 |  |  | 0 |  |  | 2023-01-12 |  | 2020-12-15 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Amherst | 6A5034-2020 | 1002 | 14.64 | Solar | 17K2 | 2020-09-17 | 2020-11-19 | 45 |  | 45 | 2020-11-20 | 2020-11-25 | 4 |  | 4 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2020-11-25 |  | 2020-11-17 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Granville | 6S6623-2020 | 1034 | 15.36 | Solar | 29A5 | 2020-09-17 | 2021-09-03 | 239 | 237 | 2 | 2021-09-03 | 2021-09-27 | 16 | 0 | 16 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-10-01 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-04-18 | Online
WMECO | Pittsfield | 6B2615-2020 | 1201 | 2490 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 17 | 11 | 6 | 2020-10-21 | 2020-11-09 | 14 |  | 14 | [7 empty] | 0 |  |  | 2021-02-22 | 2022-01-20 | 229 | 17 | 212 |  |  | 0 |  |  | 2023-01-13 |  | 2021-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Pittsfield | 6B2616-2020 | 1201 | 996 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 17 | 11 | 6 | 2020-10-21 | 2020-10-23 | 3 |  | 3 | [7 empty] | 0 |  |  | 2021-02-22 | 2022-01-20 | 229 | 17 | 212 |  |  | 0 |  |  | 2022-09-09 |  | 2021-10-01 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Amherst | 6A5066-2020 | 1002 | 20 | Solar | 17K2 | 2020-10-06 | 2020-11-02 | 19 | 15 | 4 | 2020-11-03 | 2020-11-03 | 1 |  | 1 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-06-03 |  | 2020-11-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-26 | Online
WMECO | Ludlow | 6S6730-2020 | 1056 | 990 | Solar | 19S1 | 2020-10-19 | 2020-11-02 | 11 | 7 | 4 | 2020-11-03 | 2021-01-05 | 42 |  | 42 | [7 empty] | 0 |  |  | 2021-05-11 | 2022-10-07 | 361 | 22 | 339 |  |  | 0 |  |  | 2022-11-09 |  | 2022-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Longmeadow | 6S6731-2020 | 1106 | 20 | Solar | 22H12 | 2020-10-20 | 2020-11-03 | 11 | 8 | 3 | 2020-11-04 | 2020-11-24 | 15 |  | 15 | [7 empty] | 0 | [9 empty] | 0 |  |  | 2021-06-15 |  | 2020-12-20 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-04-12 | Online
WMECO | Greenfield | 6A5099-2020 | 1301 | 4990 | Battery | 21C1 | 2020-10-27 | 2020-11-05 | 8 |  | 8 | 2020-11-06 | 2020-11-09 | 2 |  | 2 | [7 empty] | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6762-2020 | 1109 | 130.9 | Solar | 5J17 | 2020-10-27 | 2020-11-09 | 10 | 4 | 6 | 2020-11-10 | 2020-12-21 | 29 | 0 | 29 | 2021-01-15 | 2021-02-17 | 21 | 15 | 6 |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-02 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | West Springfield | 6S6770-2020 | 1089 | 20 | Solar | 21N4 | 2020-10-30 | 2020-12-08 | 27 | 23 | 4 | 2020-12-09 | 2021-04-05 | 77 | 0 | 77 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-04-05 |  | 2020-11-03 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-02-25 | Online
WMECO | Greenfield | 6A5102-2020 | 1301 | 4990 | Solar | 22B3 | 2020-11-05 | 2020-11-12 | 6 | 0 | 6 | 2020-11-12 | 2020-11-19 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | -31544 |  |  |  |  | 0 |  |  |  |  | 2022-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6773-2020 | 1104 | 25 | Solar | 5J16 | 2020-11-05 | 2020-11-23 | 13 |  | 13 | 2020-11-24 | 2021-01-22 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-25 |  | 2021-01-31 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-01-24 | Online
WMECO | Plainfield | 6A5104-2020 | 1070 | 10 | Battery | 18K3 | 2020-11-09 | 2020-11-23 | 11 |  | 11 | 2020-11-24 | 2020-12-29 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-01-20 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-16 | Online
WMECO | Pittsfield | 6B2658-2020 | 1201 | 2495 | Battery |  | 2020-11-12 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6B2659-2020 | 1270 | 2495 | Battery |  | 2020-11-12 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-11-20 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6772-2020 | 1001 | 15.2 | Solar | 16C17 | 2020-11-12 | 2020-11-16 | 3 |  | 3 | 2020-11-16 | 2020-12-03 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | 2021-01-11 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-03 | Online
WMECO | Southwick | 6S6774-2020 | 1077 | 10 | Solar | 29A5 | 2020-11-13 | 2021-02-16 | 61 |  | 61 | 2021-02-16 | 2021-03-05 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-05 |  | 2021-01-13 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-11-08 | Online
WMECO | Lee | 6B2660-2020 | 1240 | 3625 | Solar | 16B5 | 2020-11-16 | 2020-11-23 | 6 | 2 | 4 | 2020-11-23 | 2020-11-30 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | Q 4 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A5103-2020 | 1002 | 2840 | Solar |  | 2020-11-18 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A5105-2020 | 1029 | 125 | Solar | 15A2 | 2020-11-24 | 2020-12-09 | 11 |  | 11 | 2020-12-10 | 2021-02-08 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-08 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-06-28 | Online
WMECO | Amherst | 6A5106-2020 | 1002 | 20 | Solar | 19B16 | 2020-12-03 | 2021-01-19 | 30 | 28 | 2 | 2021-01-19 | 2021-04-05 | 52 | 0 | 52 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-04-05 |  | 2021-01-24 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-02 | Online
WMECO | Deerfield | 6A5118-2020 | 1342 | 17.6 | Solar | 22B1 | 2020-12-10 | 2021-01-19 | 25 |  | 25 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-24 |  | 2021-02-07 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-01-11 | Online
WMECO | Amherst | 6A5119-2020 | 1002 | 20 | Solar | 17K5 | 2020-12-10 | 2021-01-19 | 25 |  | 25 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-24 |  | 2021-02-10 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-01-03 | Online
WMECO | South Deerfield | 6A5107-2020 | 1373 | 4980 | Solar |  | 2020-12-14 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | Not Supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westhampton | 6A5111-2020 | 1027 | 22.8 | Solar | 15A3 | 2020-12-16 | 2021-02-01 | 29 | 26 | 3 | 2021-02-01 | 2021-03-10 | 27 | 0 | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-16 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-10-19 | Online
WMECO | Ludlow | 6S6775-2020 | 1056 | 133.2 | Solar | 27A6 | 2020-12-16 | 2020-12-24 | 6 |  | 6 | 2020-12-24 | 2021-02-05 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-05 |  | 2021-04-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A5108-2020 | 1376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Montague | 6A5109-2020 | 1376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A5110-2020 | 1360 | 4500 | Battery | 21B8 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Worthington | 6A5112-2020 | 1098 | 1990 | Solar | 18K3 | 2020-12-22 | 2020-12-24 | 2 |  | 2 | 2020-12-24 | 2021-01-11 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-04-20 |  | -31527 |  |  |  |  | 0 |  |  |  |  | 2022-01-16 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Feeding Hills | 6S6776-2020 | 1030 | 7.6 | Solar | 16C17 | 2020-12-22 | 2021-01-21 | 18 |  | 18 | 2021-01-21 | 2021-02-16 | 18 | 0 | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-16 |  | 2020-12-21 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-07-19 | Online
WMECO | Shelburne | 6A5113-2020 | 1370 | 10 | Solar | 22B5 | 2020-12-23 | 2021-01-05 | 7 |  | 7 | 2021-01-05 | 2021-02-16 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-02-16 |  | May |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-12-20 | Online
WMECO | Feeding Hills | 6S6777-2020 | 1030 | 17.6 | Solar | 16C17 | 2020-12-23 | 2021-03-04 | 46 |  | 46 | 2021-03-04 | 2021-03-12 | 7 | 0 | 7 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-19 |  | 2021-02-22 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-07-19 | Online
WMECO | Cummington | 6A5114-2020 | 1026 | 4990 | Battery | 18K3 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-01-27 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-22 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Amherst | 6A5115-2020 | 1002 | 4990 | Battery | 18G3 | 2020-12-28 | 2021-01-11 | 10 |  | 10 | 2021-01-11 | 2021-01-29 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-22 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B2662-2020 | 1235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-02-10 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hinsdale | 6B2663-2020 | 1235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 13 |  | 13 | 2021-01-14 | 2021-02-10 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Otis | 6B2664-2020 | 1253 | 4990 | Battery | 19J4 | 2020-12-28 | 2021-01-11 | 10 |  | 10 | 2021-01-11 | 2021-02-02 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-18 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Bernardston | 6A5116-2020 | 1337 | 4990 | Battery | 21C1 | 2020-12-29 | 2021-01-19 | 14 |  | 14 | 2021-01-19 | 2021-01-27 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6778-2020 | 1119 | 4.8 | Solar | 20A33 | 2020-12-29 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2021-01-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Ludlow | 6S6779-2020 | 1056 | 5000 | Battery |  | 2020-12-29 | 2021-01-19 | 14 |  | 14 | 2021-01-19 | 2021-02-19 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-01-14 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Easthampton | 6A5120-2021 | 1027 | 120 | Solar | 15A2 | 2021-01-08 | 2021-01-19 | 7 |  | 7 | 2021-01-19 | 2021-02-22 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-01 |  | 2021-06-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2021-09-29 | Online
WMECO | Easthampton | 6A5121-2021 | 1027 | 16.86 | Battery | 15A5 | 2021-01-08 | 2021-02-01 | 15 |  | 15 | 2021-02-01 | 2021-03-12 | 29 |  | 29 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-10 |  | March 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Windsor | 6A5117-2021 | 1270 | 10 | Battery | 18K3 | 2021-01-11 | 2021-02-01 | 14 |  | 14 | 2021-02-01 | 2021-03-10 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Lanesborough | 6B2665-2021 | 1224 | 4990 | Solar | 19A5 | 2021-01-14 | 2021-02-22 | 25 |  | 25 | 2021-02-22 | 2021-03-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-20 |  | -31549 |  |  |  |  | 0 |  |  |  |  | ASAP |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Westfield | 6S6780-2021 | 1085 | 2000 | Hydro | 18F1 | 2021-01-19 | 2021-02-01 | 9 | 4 | 5 | 2021-02-01 | 2021-04-26 | 58 | 0 | 58 |  |  | 0 | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2023-12-01 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Becket | 6B2666-2021 | 1223 | 10 | Solar | 19J6 | 2021-01-21 | 2021-02-22 | 22 |  | 22 | 2021-02-22 | 2021-03-24 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-25 |  | Spring 2021 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-10-05 | Online
WMECO | Ludlow | 6S6781-2021 | 1056 | 990 | Solar | 19S1 | 2021-01-26 | 2021-02-02 | 6 |  | 6 | 2021-02-02 | 2021-02-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  |  | 2022-07-01 |  | Expedited |  |  |  | 0 | [5 empty] | Impact Study
WMECO | Easthampton | 6A5123-2021 | 1027 | 450 | Solar | 15A2 | 2021-01-29 | 2021-02-22 | 16 | 4 | 12 | 2021-02-22 | 2021-03-15 | 16 | 0 | 16 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-01 | 2022-06-14 | 139 | 8 | 131 |  |  | 0 |  |  | 2022-08-08 |  | 2021-09-01 |  | Expedited |  |  |  | 0 |  |  |  |  | 2023-12-19 | Online
WMECO | Amherst | 6A5122-2021 | 1002 | 25 | Solar | 18G7 | 2021-02-01 | 2021-02-22 | 15 |  | 15 | 2021-02-22 | 2021-03-24 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-03-26 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-26 | Online
WMECO | Dalton | 6B2667-2021 | 1226 | 25 | Solar | 19A2 | 2021-02-03 | 2021-02-22 | 13 |  | 13 | 2021-02-22 | 2021-04-05 | 30 | 0 | 30 |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  | 2021-05-12 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Southwick | 6S6782-2021 | 1077 | 4600 | Solar | 29A1 | 2021-02-10 | 2021-02-22 | 8 |  | 8 | 2021-02-22 | 2021-03-22 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-21 | 2022-11-29 | 307 |  | 307 |  |  | 0 |  |  | 2022-12-08 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Dalton | 6B2669-2021 | 1226 | 2660 | Solar | 18C1 | 2021-02-15 | 2021-02-22 | 5 | 3 | 2 | 2021-02-22 | 2021-03-04 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-19 | 2022-08-23 | 322 | 38 | 284 |  |  | 0 |  |  | 2023-01-11 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Pittsfield | 6B2668-2021 | 1201 | 86.4 | Solar | 30B7 | 2021-02-16 | 2021-03-25 | 27 | 27 | 0 | 2021-03-25 | 2021-04-26 | 22 | 0 | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | 2021-06-15 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-06-30 | Online
WMECO | Hadley | 6A5124-2021 | 1035 | 20 | Battery | 17K5 | 2021-02-18 | 2021-03-03 | 10 | 9 | 1 | 2021-03-03 | 2021-04-05 | 23 | 0 | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-04-05 |  | March 2021 |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-04-15 | Online
WMECO | Springfield | 6S6783-2021 | 1119 | 4.8 | Solar | 20A33 | 2021-02-18 | 2021-02-22 | 3 | 2 | 1 | 2021-02-22 | 2021-03-08 | 11 | 0 | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-03-11 |  | 2021-01-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Blandford | 6B2670-2021 | 1008 | 1000 | Solar | 19J2 | 2021-02-26 | 2021-03-25 | 19 | 19 | 0 | 2021-03-25 | 2021-04-23 | 21 | 6 | 15 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | Jan 2022 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hatfield | 6A5125-2021 | 1038 | 250 | Biogas | 18G6 | 2021-03-01 | 2021-05-19 | 56 | 56 | 0 | 2021-05-19 | 2021-06-14 | 18 | 0 | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2021-08-30 |  | Expedited |  |  |  | 0 | [5 empty] | System Impact Study
WMECO | Easthampton | 6A5126-2021 | 1027 | 17.6 | Solar | 15A5 | 2021-03-09 | 2021-03-29 | 14 | 6 | 8 | 2021-03-29 | 2021-05-03 | 25 | 2 | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-26 |  | not supplied |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6784-2021 | 1001 | 360 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 12 | 4 | 8 | 2021-03-25 | 2021-04-22 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-22 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Agawam | 6S6785-2021 | 1001 | 499.9 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 12 | 4 | 8 | 2021-03-25 | 2021-04-29 | 25 | 0 | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-22 |  | 2021-12-31 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Pittsfield | 6B2671-2021 | 1201 | 166.6 | Solar | 30B4 | 2021-03-12 | 2021-03-29 | 11 | 9 | 2 | 2021-03-29 | 2021-04-26 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | 2021-09-01 |  | Expedited |  |  |  | 0 | [5 empty] | customer hold
WMECO | Lanesborough | 6B2672-2021 | 1237 | 16 | Solar | 15E1 | 2021-03-16 | 2021-03-29 | 9 | 6 | 3 | 2021-03-29 | 2021-04-26 | 20 | 0 | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-13 |  | not supplied |  | Expedited |  |  |  | 0 |  |  |  |  | 2022-05-13 | Online
WMECO | Springfield | 6S6786-2021 | 1128 | 500 | Solar |  | 2021-03-18 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | Oct 2021 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Springfield | 6S6787-2021 | 1129 | 500 | Solar |  | 2021-03-18 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Northfield | 6A5127-2021 | 1360 | 1500 | Solar | 21B8 | 2021-03-26 | 2021-04-09 | 11 | 0 | 11 | 2021-04-09 | 2021-04-19 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2022-04-24 |  | Expedited |  |  |  | 0 | [5 empty] | Withdrawn
WMECO | Hadley | ESMAEX-00037 | 1035 | 25 | Solar & Battery | 18G4 | 2021-04-08 | 2021-05-03 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-06 | [7 empty] | 0 |  |  |  |  | 2022-02-11 | Online | [7 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-00043 | 1077 | 8.7 | Solar & Battery | 29A1 | 2021-04-14 | 2021-05-18 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-07 | [7 empty] | 0 |  |  |  |  | 2021-12-16 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Indian Orchard | ESMAEX-00045 | 1151 | 2040 | Solar |  | 2021-05-28 | 2021-06-21 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-06 | [7 empty] | 0 |  |  |  |  | 2025-09-26 | Online |  |  |  |  | 2023 ASO Batch 1
WMECO | West Springfield | ESMAEX-00061 | 1089 | 21.4 | Solar & Battery | 21N9 | 2021-04-19 | 2021-05-18 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-05-24 | [7 empty] | 0 |  |  |  |  | 2022-01-18 | Online | [6 empty] | 11.4 | 21N PIPER
WMECO | Ludlow | ESMAEX-00069 | 1056 | 19.8 | Solar | 27A6 | 2021-04-22 | 2021-05-18 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-21 | [7 empty] | 0 |  |  |  |  | 2021-11-02 | Online | [6 empty] | 9.8 | 27A ORCHARD
WMECO | Amherst | ESMAEX-00170 | 1002 | 66.6 | Solar | 17K4 | 2022-02-11 | 2021-06-21 | -164 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-02-11 | [7 empty] | 0 |  |  |  |  | 2023-01-11 | Online | [7 empty] | 17K AMHERST
WMECO | Huntington | ESMAEX-00294 | 1050 | 20 | Solar | 19J5 | 2021-08-11 | 2021-08-23 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-21 | [7 empty] | 0 |  |  |  |  | 2022-06-28 | Online | [6 empty] | 0
WMECO | Chicopee | ESMAEX-00185 | 1013 | 4999 | Battery | 21N7 | 2021-06-15 | 2024-10-23 | 870 |  | 870 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-27 | [7 empty] | 0 | [5 empty] | Technical Review |  |  |  |  | 2023 ASO Batch 1 |  | 4999 | 21N PIPER
WMECO | Greenfield | ESMAEX-00134 | 1301 | 15 | Solar | 22B7 | 2021-05-18 | 2021-06-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-14 | [7 empty] | 0 |  |  |  |  | 2021-10-26 | Online | [6 empty] | 0 | 22B CUMBERLAND
WMECO | New Ashford | ESMAEX-00146 | 1237 | 10 | Solar & Battery | 15E1 | 2021-05-24 | 2021-06-21 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-06-24 | [7 empty] | 0 |  |  |  |  | 2022-10-03 | Online
WMECO | Huntington | ESMAEX-00150 | 1050 | 18 | Solar & Battery | 19J5 | 2021-05-26 | 2021-06-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-03 | [7 empty] | 0 |  |  |  |  | 2021-11-15 | Online | [6 empty] | 7.68
WMECO | Colrain | ESMAEX-00162 | 1340 | 22.8 | Solar | 29R2 | 2021-06-02 | 2021-06-21 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-02 | [7 empty] | 0 |  |  |  |  | 2021-12-02 | Online | [7 empty] | 29R SHELBURNE
WMECO | Springfield | ESMAEX-00165 | 1109 | 7.5 | Solar | 5J17 | 2021-06-03 | 2021-06-21 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-12 | [7 empty] | 0 |  |  |  |  | 2021-12-10 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Hadley | ESMAEX-00177 | 1035 | 375 | Solar | 18G5 | 2021-06-09 | 2021-06-21 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-19 | [7 empty] | 0 |  |  |  |  | 2024-06-14 | Online | [7 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-00366 | 1001 | 17.6 | Solar & Battery | 16C16 | 2021-08-27 | 2021-09-30 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-10-26 | [7 empty] | 0 |  |  |  |  | 2022-05-13 | Online | [7 empty] | 16C AGAWAM
WMECO | Agawam | ESMAEX-00187 | 1001 | 22 | Solar | 16C16 | 2021-06-15 | 2021-07-16 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-07-20 | [7 empty] | 0 |  |  |  |  | 2021-10-13 | Online | [6 empty] | 12 | 16C AGAWAM
WMECO | Hadley | ESMAEX-00212 | 1035 | 10.44 | Solar | 19B15 | 2021-06-25 | 2021-07-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-03 | [7 empty] | 0 |  |  |  |  | 2021-10-26 | Online | [7 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-00205 | 1201 | 60 | Internal Combustion Engine | 30B2 | 2021-06-23 | 2021-07-16 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-21 | [7 empty] | 0 |  |  |  |  | 2025-07-28 | Online | [7 empty] | 30B OSWALD
WMECO | Southampton | ESMAEX-00220 | 1073 | 996 | Solar & Battery | 15A1 | 2021-10-20 | 2021-10-26 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-02 | [7 empty] | 0 | [5 empty] | ISA Agreement | [6 empty] | 2000 | 15A GUNN
WMECO | Greenfield | ESMAEX-00256 | 1301 | 100.8 | Solar | 21C1 | 2021-07-21 | 2021-08-06 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-25 | [7 empty] | 0 |  |  |  |  | 2023-09-14 | Online | [7 empty] | 21C MONTAGUE
WMECO | Tyringham | ESMAEX-00233 | 1264 | 22.8 | Solar | 16B1 | 2021-07-12 | 2021-08-23 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-17 | [7 empty] | 0 |  |  |  |  | 2022-04-11 | Online | [7 empty] | 16B PLEASANT
WMECO | Westhampton | ESMAEX-00728 | 1027 | 30 | Battery | 15A3 | 2022-01-13 | 2022-01-26 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-28 | [7 empty] | 0 |  |  |  |  | 2022-07-27 | Online | [7 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-00242 | 1030 | 8 | Solar | 30A1 | 2021-07-16 | 2021-08-06 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-08-09 | [7 empty] | 0 |  |  |  |  | 2021-10-07 | Online | [7 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00290 | 1103 | 150 | Internal Combustion Engine | 8C24 | 2022-01-20 | 2022-02-10 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-18 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [6 empty] | 0 | 8C WEST SPRINGFIELD
WMECO | Easthampton | ESMAEX-00295 | 1027 | 9.8 | Solar | 15A1 | 2021-08-10 | 2021-10-12 | 44 |  | 44 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-10-26 | [7 empty] | 0 |  |  |  |  | 2022-01-31 | Online | [7 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-00296 | 1129 | 17.6 | Solar | 20A23 | 2021-08-10 | 2021-10-21 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-01 | [7 empty] | 0 |  |  |  |  | 2022-05-10 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Springfield | ESMAEX-00332 | 1105 | 60 | Internal Combustion Engine | 21S5 | 2021-08-19 | 2021-10-22 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-01 | [7 empty] | 0 |  |  |  |  | 2022-05-06 | Online | [7 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-00369 | 1035 | 45.6 | Solar | 18G4 | 2021-08-30 | 2021-08-30 | 1 |  | 1 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-05 | [7 empty] | 0 |  |  |  |  | 2023-10-24 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00383 | 1109 | 17.5 | Battery | 5J17 | 2021-09-03 | 2021-10-26 | 36 |  | 36 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-02 | [7 empty] | 0 |  |  |  |  | 2021-12-01 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-00370 | 1109 | 15.8 | Solar | 20A31 | 2021-08-30 | 2021-09-20 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-28 | [7 empty] | 0 |  |  |  |  | 2022-01-27 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00401 | 1077 | 18 | Solar | 29A1 | 2021-09-10 | 2021-09-28 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-09-28 | [7 empty] | 0 |  |  |  |  | 2023-02-07 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-00475 | 1056 | 2000 | Solar & Battery | 27A5 | 2021-10-06 | 2021-10-12 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-17 | [7 empty] | 0 | [5 empty] | ISA Agreement |  |  |  |  | 2023 ASO Batch 1 |  |  | 27A ORCHARD
WMECO | West Springfield | ESMAEX-00456 | 1089 | 16.225 | Solar | 21N9 | 2021-09-29 | 2021-10-26 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-02 | [7 empty] | 0 |  |  |  |  | 2023-10-11 | Online | [7 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-00459 | 1027 | 9.735 | Solar & Battery | 15A3 | 2021-09-30 | 2021-10-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2022-05-24 | Online | [7 empty] | GUNN
WMECO | Longmeadow | ESMAEX-00471 | 1106 | 15.2 | Solar | 22H11 | 2021-10-04 | 2021-11-08 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-29 | [7 empty] | 0 |  |  |  |  | 2022-09-12 | Online | [7 empty] | 22H FRANCONIA
WMECO | Springfield | ESMAEX-00491 | 1107 | 3000 | Internal Combustion Engine | 21S8 | 2021-10-12 | 2021-11-09 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-11 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [7 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-00483 | 1375 | 60 | Solar | 18G3 | 2021-10-08 | 2021-10-26 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00501 | 1104 | 108 | Solar | 5J9 | 2021-10-14 | 2021-10-26 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-06 | [7 empty] | 0 |  |  |  |  | 2023-08-31 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Bernardston | ESMAEX-00657 | 1337 | 2200 | Solar & Battery | 21B8 | 2021-12-13 | 2021-12-14 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval |  | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-00503 | 1201 | 4990 | Battery | 19A1 | 2022-02-23 | 2022-03-17 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-02 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 19A DOREEN
WMECO | Colrain | ESMAEX-00550 | 1340 | 10 | Battery | 29R2 | 2021-10-27 | 2021-11-08 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-12-01 | [7 empty] | 0 |  |  |  |  | 2023-03-07 | Online | [7 empty] | 29R SHELBURNE
WMECO | Hinsdale | ESMAEX-00541 | 1235 | 20 | Solar | 18C2 | 2021-10-25 | 2021-11-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2021-11-30 | [7 empty] | 0 |  |  |  |  | 2022-09-14 | Online | [7 empty] | BERKSHIRE
WMECO | Agawam | ESMAEX-00578 | 1001 | 4990 | Battery | 30A6 | 2022-01-12 | 2022-01-20 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-05 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  |  | 2023 ASO Batch 1 |  |  | 30A SILVER
WMECO | Chicopee | ESMAEX-00750 | 1013 | 4100 | Fuel Cell | 21N7 | 2022-01-21 | 2022-02-10 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-07 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  |  | 2023 ASO Batch 1 |  |  | 21N PIPER
WMECO | Hinsdale | ESMAEX-00608 | 1235 | 19.52 | Solar | 18C2 | 2021-11-19 | 2021-12-12 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-10 | [7 empty] | 0 |  |  |  |  | 2022-03-29 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Dalton | ESMAEX-00846 | 1226 | 42.6 | Solar |  | 2022-02-22 | 2022-03-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-10 | [7 empty] | 0 |  |  |  |  | 2022-08-02 | Online
WMECO | Springfield | ESMAEX-00618 | 1128 | 9.92 | Solar & Battery | 20A34 | 2021-11-23 | 2021-12-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-11 | [7 empty] | 0 |  |  |  |  | 2022-03-22 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Montague | ESMAEX-00653 | 1351 | 5 | Battery | 21C2 | 2021-12-10 | 2021-12-16 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-18 | [7 empty] | 0 |  |  |  |  | 2022-11-23 | Online |  |  |  | Gill-Montague |  |  | 14 | 21C MONTAGUE
WMECO | Southwick | ESMAEX-00695 | 1077 | 3984 | Solar | 29A3 | 2022-01-31 | 2022-02-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Southwick | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Buckland | ESMAEX-00739 | 1338 | 24 | Solar | 38A1 | 2022-01-19 | 2022-01-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-31 | [7 empty] | 0 |  |  |  |  | 2023-03-02 | Online | [7 empty] | 38A ASHFIELD
WMECO | Erving | ESMAEX-00810 | 1344 | 2600 | Battery | 21C8 | 2022-02-04 | 2022-02-28 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  |  | 2023 ASO Batch 1 |  |  | 21C MONTAGUE
WMECO | Lee | ESMAEX-00749 | 1238 | 9.49 | Solar & Battery | 16B5 | 2022-01-21 | 2022-01-24 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-02 | [7 empty] | 0 |  |  |  |  | 2023-04-03 | Online | [7 empty] | 16B PLEASANT
WMECO | Northfield | ESMAEX-00836 | 1360 | 40 | Battery |  | 2022-02-16 | 2022-03-10 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-15 | [7 empty] | 0 |  |  |  |  | 2022-07-01 | Online
WMECO | Whately | ESMAEX-00756 | 1093 | 6.4 | Battery | 18G6 | 2022-01-25 | 2022-01-28 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-01-28 | [7 empty] | 0 |  |  |  |  | 2022-06-15 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00823 | 1105 | 46.4 | Solar | 21S4 | 2022-02-09 | 2022-02-18 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-01 | [7 empty] | 0 |  |  |  |  | 2023-01-10 | Online | [7 empty] | CLINTON
WMECO | Longmeadow | ESMAEX-00766 | 1106 | 7.09 | Solar & Battery | 22H11 | 2022-01-29 | 2022-02-22 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-09 | [7 empty] | 0 |  |  |  |  | 2022-04-21 | Online | [7 empty] | 22H FRANCONIA
WMECO | Lee | ESMAEX-00806 | 1238 | 7.6 | Solar & Battery | 16B5 | 2022-02-03 | 2022-04-06 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-12 | [7 empty] | 0 |  |  |  |  | 2022-09-08 | Online | [7 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00914 | 1201 | 440 | Solar | 19A3 | 2022-04-07 | 2022-04-19 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-06 | [7 empty] | 0 |  |  |  |  | 2024-09-12 | Online | [7 empty] | 19A DOREEN
WMECO | Lee | ESMAEX-00855 | 1238 | 19.8 | Solar & Battery | 16B1 | 2022-02-24 | 2022-03-02 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-05 | [7 empty] | 0 |  |  |  |  | 2023-01-09 | Online | [7 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00854 | 1201 | 15.2 | Solar & Battery | 30B7 | 2022-02-24 | 2022-04-06 | 30 |  | 30 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-12 | [7 empty] | 0 |  |  |  |  | 2023-09-14 | Online | [7 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-00868 | 1089 | 5 | Battery | 21N4 | 2022-03-01 | 2022-03-29 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-02 | [7 empty] | 0 |  |  |  |  | 2022-09-01 | Online | [6 empty] | 14 | 21N PIPER
WMECO | Feeding Hills | ESMAEX-00898 | 1030 | 15.2 | Solar | 30A6 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-22 | [7 empty] | 0 |  |  |  |  | 2022-12-21 | Online | [7 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00942 | 1108 | 13.6 | Solar | 22H16 | 2022-03-17 | 2022-03-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-02 | [7 empty] | 0 |  |  |  |  | 2022-10-17 | Online | [7 empty] | 22H FRANCONIA
WMECO | Ludlow | ESMAEX-00910 | 1056 | 9.8 | Solar | 27A5 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-03-28 | [7 empty] | 0 |  |  |  |  | 2022-09-19 | Online | [7 empty] | 27A ORCHARD
WMECO | Agawam | ESMAEX-00944 | 1001 | 149.1 | Solar | 30A3 | 2022-03-18 | 2022-03-28 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-15 | [7 empty] | 0 |  |  |  |  | 2023-09-12 | Online | [7 empty] | SILVER
WMECO | Southwick | ESMAEX-00933 | 1077 | 15.2 | Solar | 29A5 | 2022-03-16 | 2022-04-12 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2023-01-05 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Pittsfield | ESMAEX-00941 | 1201 | 10 | Solar | 30B7 | 2022-03-17 | 2022-04-07 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-04-21 | [7 empty] | 0 |  |  |  |  | 2022-08-05 | Online | [7 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-00957 | 1095 | 240 | Solar | 20A35 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-11 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00958 | 1077 | 240 | Solar | 29A5 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-20 | [7 empty] | 0 |  |  |  |  | 2024-12-30 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Montague | ESMAEX-00988 | 1376 | 11000 | Battery | 21C6 | 2023-01-20 | 2023-01-23 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval | 4990 | 21C MONTAGUE
WMECO | Granville | ESMAEX-01120 | 1034 | 15.2 | Solar & Battery | 29A5 | 2022-04-27 | 2022-05-09 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-10 | [7 empty] | 0 |  |  |  |  | 2022-11-14 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Dalton | ESMAEX-01075 | 1226 | 20 | Solar | 18C1 | 2022-04-12 | 2022-04-26 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2022-08-08 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Northfield | ESMAEX-01087 | 1360 | 10 | Battery | 21B8 | 2022-04-16 | 2022-05-16 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-16 | [7 empty] | 0 |  |  |  |  | 2022-11-23 | Online |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Huntington | ESMAEX-01102 | 1050 | 4999 | Solar | 19J5 | 2022-05-12 | 2022-05-26 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-01110 | 1237 | 3.54 | Solar & Battery | 15E1 | 2022-04-25 | 2022-05-04 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-26 | [7 empty] | 0 |  |  |  |  | 2022-09-14 | Online
WMECO | Westhampton | ESMAEX-01141 | 1027 | 3.8 | Solar & Battery | 15A3 | 2022-05-03 | 2022-05-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-25 | [7 empty] | 0 |  |  |  |  | 2024-09-24 | Online | [7 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-01146 | 1089 | 3.8 | Solar & Battery | 21N4 | 2022-05-04 | 2022-05-18 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-24 | [7 empty] | 0 |  |  |  |  | 2023-03-09 | Online | [7 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01148 | 1104 | 400 | Solar & Battery | 5J9 | 2022-06-14 | 2022-06-30 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-14 | [7 empty] | 0 | [5 empty] | Construction Stage | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Greenfield | ESMAEX-01159 | 1301 | 996 | Solar & Battery | 22B7 | 2022-10-10 | 2022-10-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-28 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 22B CUMBERLAND
WMECO | Agawam | ESMAEX-01547 | 1001 | 117.3 | Solar | 30A2 | 2022-09-06 | 2022-09-13 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-13 | [7 empty] | 0 |  |  |  |  | 2023-10-06 | Online | [7 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-01165 | 1106 | 10 | Solar & Battery | 22H17 | 2022-05-10 | 2022-05-18 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-05-20 | [7 empty] | 0 |  |  |  |  | 2022-08-22 | Online | [7 empty] | 22H FRANCONIA
WMECO | Plainfield | ESMAEX-01166 | 1070 | 4980 | Solar & Battery | 18K3 | 2023-03-24 | 2023-05-05 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Complex |  |  |  | 0 | [5 empty] | Compliances Documents | [6 empty] | 4980 | 18K PLAINFIELD
WMECO | Westhampton | ESMAEX-01182 | 1027 | 15.2 | Solar & Battery | 15A3 | 2022-05-16 | 2022-06-09 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-26 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [7 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-01230 | 1109 | 791.5 | Solar & Battery | 21S4 | 2022-07-28 | 2022-08-04 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-20 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 21S CLINTON
WMECO | Bernardston | ESMAEX-01240 | 1337 | 15.2 | Solar | 21C5 | 2022-06-01 | 2022-06-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-07 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-01249 | 1089 | 10 | Battery | 21N4 | 2022-06-02 | 2022-06-09 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-11 | [7 empty] | 0 |  |  |  |  | 2023-07-05 | Online | [7 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01251 | 1103 | 990 | Solar & Battery | 5J13 | 2023-08-02 | 2023-08-11 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Supplemental Designer Review | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-01257 | 1129 | 6 | Solar | 20A14 | 2022-06-06 | 2022-06-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-06-17 | [7 empty] | 0 |  |  |  |  | 2022-09-19 | Online | [6 empty] | 6 | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-01410 | 1002 | 50 | Solar | 17K5 | 2022-07-25 | 2022-08-04 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-14 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online | [7 empty] | 17K AMHERST
WMECO | Easthampton | ESMAEX-01308 | 1027 | 10 | Solar | 15A1 | 2022-06-17 | 2022-06-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-26 | [7 empty] | 0 |  |  |  |  | 2022-10-12 | Online | [6 empty] | 10 | 15A GUNN
WMECO | Feeding Hills | ESMAEX-01317 | 1030 | 15.2 | Solar | 30A6 | 2022-06-22 | 2022-06-30 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-09 | [7 empty] | 0 |  |  |  |  | 2023-04-13 | Online | [6 empty] | 16 | 30A SILVER
WMECO | Easthampton | ESMAEX-01326 | 1027 | 17.6 | Battery |  | 2022-06-27 | 2022-07-01 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-07-26 | [7 empty] | 0 |  |  |  |  | 2023-10-02 | Online
WMECO | Whately | ESMAEX-01352 | 1093 | 10 | Battery | 18G8 | 2022-07-07 | 2022-07-29 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2023-02-02 | Online | [7 empty] | 18G PODICK
WMECO | Greenfield | ESMAEX-01376 | 1301 | 15.2 | Solar | 22B7 | 2022-07-13 | 2022-08-04 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2022-11-22 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Lanesborough | ESMAEX-01480 | 1224 | 17.6 | Solar & Battery | 19A5 | 2022-08-17 | 2022-09-07 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-28 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [7 empty] | 19A DOREEN
WMECO | Southampton | ESMAEX-01350 | 1073 | 17.68 | Solar & Battery | 15A1 | 2022-07-06 | 2022-08-04 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-23 | [7 empty] | 0 |  |  |  |  | 2023-01-05 | Online | [6 empty] | 7.68 | 15A GUNN
WMECO | Springfield | ESMAEX-01356 | 1107 | 2000 | Battery | 21S10 | 2022-10-18 | 2022-12-05 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-26 | [7 empty] | 0 |  |  |  |  | 2025-01-08 | Online |  |  |  |  | 2023 ASO Batch 1 |  | 0 | 21S CLINTON
WMECO | Springfield | ESMAEX-01384 | 1109 | 2549.99 | Solar & Battery | 20A33 | 2023-01-13 | 2023-02-02 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review |  |  |  |  | 2023 ASO Batch 1 |  |  | 20A BRECKWOOD
WMECO | Longmeadow | ESMAEX-01501 | 1106 | 15.2 | Solar & Battery | 22H11 | 2022-08-23 | 2022-09-23 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-03 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online | [7 empty] | 22H FRANCONIA
WMECO | Cheshire | ESMAEX-01421 | 1225 | 3800 | Solar & Battery | 19A5 | 2022-08-15 | 2022-09-07 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-13 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  |  | 2023 ASO Batch 1 |  | 3800 | 19A DOREEN
WMECO | Southwick | ESMAEX-01444 | 1077 | 15.2 | Solar & Battery |  | 2022-08-08 | 2022-08-24 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-08-24 | [7 empty] | 0 |  |  |  |  | 2023-01-31 | Online
WMECO | Granville | ESMAEX-01439 | 1034 | 3000 | Solar & Battery | 29A5 | 2022-09-07 | 2022-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Southwick | 2023 ASO Batch 1 | Phase 1 - Pending CIP Approval | 3000 | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01445 | 1002 | 69.2 | Solar | 17K4 | 2022-08-08 | 2022-08-16 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-09 | [7 empty] | 0 |  |  |  |  | 2024-02-14 | Online | [7 empty] | 17K AMHERST
WMECO | Ludlow | ESMAEX-01447 | 1056 | 20 | Solar |  | 2022-08-08 | 2022-12-16 | 95 |  | 95 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-30 | [7 empty] | 0 |  |  |  |  | 2024-05-01 | Online
WMECO | Springfield | ESMAEX-01448 | 1109 | 1683 | Solar & Battery | 20A14 | 2023-01-17 | 2023-02-02 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review |  |  |  |  | 2023 ASO Batch 1 |  |  | 20A BRECKWOOD
WMECO | Savoy | ESMAEX-02010 | 1256 | 15.2 | Solar & Battery | 18K4 | 2023-01-12 | 2023-01-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-03 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Blandford | ESMAEX-01479 | 1008 | 4998 | Solar & Battery | 19J5 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 4998 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-01489 | 1201 | 240 | Solar |  | 2023-01-12 | 2022-09-07 | -92 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-05 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online
WMECO | Springfield | ESMAEX-01502 | 1108 | 3 | Solar & Battery | 22H15 | 2022-08-23 | 2022-09-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-06 | [7 empty] | 0 |  |  |  |  | 2023-04-12 | Online | [6 empty] | 14 | 22H FRANCONIA
WMECO | Otis | ESMAEX-01512 | 1253 | 20 | Solar | 19J4 | 2022-08-25 | 2022-09-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-12 | [7 empty] | 0 | [5 empty] | Construction Stage |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Shelburne Falls | ESMAEX-01514 | 1370 | 20 | Solar | 22B5 | 2022-08-25 | 2022-09-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-25 | [7 empty] | 0 |  |  |  |  | 2024-11-22 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Hadley | ESMAEX-01515 | 1035 | 15.6 | Solar & Battery | 18G5 | 2022-08-26 | 2022-09-07 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-04 | [7 empty] | 0 |  |  |  |  | 2023-02-08 | Online | [7 empty] | 18G PODICK
WMECO | Amherst | ESMAEX-01522 | 1002 | 4990 | Battery | 18G6 | 2022-08-29 | 2022-09-14 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | 4990 | 18G PODICK
WMECO | Agawam | ESMAEX-01527 | 1001 | 960 | Solar | 30A3 | 2022-09-19 | 2022-09-23 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-08 | [7 empty] | 0 |  |  |  |  | 2025-02-14 | Online | [7 empty] | 30A SILVER
WMECO | Hatfield | ESMAEX-01533 | 1038 | 20 | Solar | 18G6 | 2022-09-01 | 2022-09-13 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-04 | [7 empty] | 0 |  |  |  |  | 2022-12-21 | Online | [7 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-01539 | 1375 | 10 | Solar & Battery | 18G8 | 2022-09-02 | 2022-09-21 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-05 | [7 empty] | 0 |  |  |  |  | 2023-03-06 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01563 | 1109 | 60 | Solar | 20A33 | 2022-09-11 | 2022-09-23 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-22 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-01581 | 1077 | 4999 | Battery | 29A3 | 2023-03-20 | 2023-04-19 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01582 | 1077 | 6700 | Solar & Battery | 29A3 | 2023-03-20 | 2023-03-22 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01586 | 1002 | 3830 | Solar & Battery | 17K8 | 2022-09-14 | 2022-09-15 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-11 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 3830 | 17K AMHERST
WMECO | Lanesborough | ESMAEX-01590 | 1237 | 16.4 | Solar | 15E1 | 2022-09-14 | 2022-09-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-09-27 | [7 empty] | 0 |  |  |  |  | 2023-07-06 | Online | [7 empty] | PARTRIDGE
WMECO | Buckland | ESMAEX-01594 | 1338 | 250 | Solar | 29R1 | 2022-10-07 | 2022-10-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-02 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online | [7 empty] | 29R SHELBURNE
WMECO | Worthington | ESMAEX-01622 | 1098 | 3000 | Solar & Battery | 18K3 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 3000 | 18K PLAINFIELD
WMECO | Blandford | ESMAEX-01635 | 1008 | 2000 | Solar | 19J2 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 2000 | 19J BLANDFORD
WMECO | Cummington | ESMAEX-01631 | 1026 | 5 | Solar | 18C1 | 2022-09-26 | 2022-10-05 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-02 | [7 empty] | 0 |  |  |  |  | 2023-02-24 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Hatfield | ESMAEX-01733 | 1038 | 7.6 | Solar & Battery | 18G5 | 2022-10-27 | 2023-01-11 | 55 |  | 55 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-18 | [7 empty] | 0 |  |  |  |  | 2023-06-15 | Online | [7 empty] | 18G PODICK
WMECO | Longmeadow | ESMAEX-01682 | 1106 | 10.752 | Solar & Battery | 22H11 | 2022-10-13 | 2022-11-21 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-15 | [7 empty] | 0 |  |  |  |  | 2023-04-27 | Online | [7 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-01647 | 1254 | 22.8 | Solar & Battery | 30B7 | 2022-09-30 | 2022-12-01 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-07 | [7 empty] | 0 |  |  |  |  | 2024-10-11 | Online | [7 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-01645 | 1109 | 12.6 | Solar & Battery | 5J17 | 2022-09-29 | 2022-10-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-21 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Amherst | ESMAEX-01862 | 1002 | 60 | Solar | 17K6 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-07 | [7 empty] | 0 |  |  |  |  | 2024-08-05 | Online | [7 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-01852 | 1223 | 2490 | Solar | 19J6 | 2022-11-28 | 2022-12-05 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study |  |  |  | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-01748 | 1330 | 10 | Solar | 38A1 | 2022-11-01 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-03 | [7 empty] | 0 |  |  |  |  | 2023-04-25 | Online | [6 empty] | 0 | 38A ASHFIELD
WMECO | Whately | ESMAEX-01677 | 1093 | 400 | Solar | 18G8 | 2023-02-16 | 2023-02-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-01715 | 1077 | 10 | Solar & Battery | 29A5 | 2022-10-25 | 2022-10-28 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-10-31 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online |  |  |  | Southwick |  |  | 7 | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-01813 | 1056 | 17.6 | Solar & Battery | 19S1 | 2022-11-15 | 2023-01-23 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-31 | [7 empty] | 0 |  |  |  |  | 2023-05-30 | Online | [6 empty] | 17.6 | 19S LUDLOW
WMECO | West Springfield | ESMAEX-01719 | 1089 | 225 | Solar | 21N5 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-30 | [7 empty] | 0 |  |  |  |  | 2024-10-24 | Online | [7 empty] | 21N PIPER
WMECO | Granville | ESMAEX-01695 | 1034 | 17.1 | Solar | 29A5 | 2022-10-19 | 2022-10-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-23 | [7 empty] | 0 |  |  |  |  | 2023-04-20 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-01708 | 1237 | 3800 | Solar & Battery | 30B5 | 2023-01-10 | 2024-07-29 | 405 |  | 405 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | 2800 | 30B OSWALD
WMECO | Conway | ESMAEX-01702 | 1341 | 12.6 | Solar | 38A1 | 2022-10-21 | 2022-11-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-12 | [7 empty] | 0 |  |  |  |  | 2023-02-09 | Online | [7 empty] | 38A ASHFIELD
WMECO | Blandford | ESMAEX-01704 | 1008 | 4998 | Solar & Battery | 19J2 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Blandford | 2023 ASO Batch 1 | Phase 2 - In Process | 4998 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-01713 | 1027 | 15.2 | Solar & Battery | 15A2 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-12 | [7 empty] | 0 |  |  |  |  | 2023-04-13 | Online | [7 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-01764 | 1002 | 10 | Battery | 17K8 | 2022-11-03 | 2022-12-07 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-18 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online | [7 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-01830 | 1077 | 15.93 | Solar | 29A1 | 2022-11-17 | 2022-12-05 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-05 | [7 empty] | 0 |  |  |  |  | 2023-08-29 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01769 | 1077 | 10 | Solar & Battery | 29A5 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-16 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online |  |  |  | Southwick |  |  | 7 | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-01754 | 1035 | 10 | Solar | 18G4 | 2022-11-02 | 2022-11-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-14 | [7 empty] | 0 |  |  |  |  | 2023-06-06 | Online | [7 empty] | 18G PODICK
WMECO | Washington | ESMAEX-01766 | 1223 | 5 | Solar & Battery | 19J6 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-18 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [6 empty] | 0
WMECO | Bernardston | ESMAEX-01755 | 1337 | 4700 | Solar & Battery | 21C1 | 2023-09-21 | 2023-09-29 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4700 | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-01802 | 1030 | 10 | Solar | 30A1 | 2022-11-11 | 2022-11-16 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-11-21 | [7 empty] | 0 |  |  |  |  | 2023-04-07 | Online | [6 empty] | 7 | 30A SILVER
WMECO | Ludlow | ESMAEX-01826 | 1056 | 14.7 | Solar | 27A5 | 2022-11-17 | 2022-12-21 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2022-12-23 | [7 empty] | 0 |  |  |  |  | 2023-04-06 | Online | [7 empty] | 27A ORCHARD
WMECO | Conway | ESMAEX-01828 | 1341 | 4200 | Solar & Battery | 22B1 | 2023-01-25 | 2023-02-01 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | 4200 | 22B CUMBERLAND
WMECO | Whately | ESMAEX-01872 | 1093 | 20 | Solar | 18G6 | 2022-11-30 | 2022-12-05 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-25 | [7 empty] | 0 |  |  |  |  | 2023-05-12 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01869 | 1118 | 15.2 | Solar & Battery | 20A32 | 2022-11-29 | 2022-12-14 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-01-03 | [7 empty] | 0 |  |  |  |  | 2025-07-02 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Whately | ESMAEX-02067 | 1093 | 5 | Battery | 18G8 | 2023-01-25 | 2023-02-21 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-09 | [7 empty] | 0 |  |  |  |  | 2024-06-17 | Online | [7 empty] | 18G PODICK
WMECO | Otis | ESMAEX-02145 | 1253 | 15.2 | Solar & Battery | 19J4 | 2023-02-09 | 2023-02-24 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-10-23 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-02059 | 1330 | 20 | Solar | 38A1 | 2023-01-23 | 2023-02-01 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-20 | [7 empty] | 0 |  |  |  |  | 2023-06-12 | Online | [7 empty] | 38A ASHFIELD
WMECO | Whately | ESMAEX-01991 | 1093 | 15.2 | Solar | 18G6 | 2023-01-10 | 2023-01-23 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-15 | [7 empty] | 0 |  |  |  |  | 2024-02-08 | Online | [7 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-01968 | 1056 | 240 | Solar |  | 2023-01-05 | 2023-02-01 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-03 | [7 empty] | 0 | [5 empty] | Compliances Documents
WMECO | Longmeadow | ESMAEX-02008 | 1106 | 20 | Solar | 22H13 | 2023-01-12 | 2023-02-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-15 | [7 empty] | 0 |  |  |  |  | 2023-05-23 | Online | [7 empty] | 22H FRANCONIA
WMECO | Feeding Hills | ESMAEX-02090 | 1030 | 10.62 | Solar & Battery | 30A1 | 2023-01-30 | 2023-03-31 | 45 |  | 45 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-03 | [7 empty] | 0 |  |  |  |  | 2023-08-04 | Online | [7 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-02073 | 1002 | 15.2 | Solar | 18G7 | 2023-01-25 | 2023-02-08 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-09 | [7 empty] | 0 |  |  |  |  | 2023-09-05 | Online | [7 empty] | 18G PODICK
WMECO | Feeding Hills | ESMAEX-02040 | 1030 | 15.2 | Solar | 16C17 | 2023-01-19 | 2023-02-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-28 | [7 empty] | 0 |  |  |  |  | 2023-08-04 | Online | [6 empty] | 17.4 | 16C AGAWAM
WMECO | Deerfield | ESMAEX-02052 | 1342 | 480 | Solar | 22B3 | 2023-02-17 | 2023-03-03 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22B CUMBERLAND
WMECO | Longmeadow | ESMAEX-02128 | 1106 | 10 | Battery | 22H13 | 2023-02-06 | 2023-02-24 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-01 | [7 empty] | 0 |  |  |  |  | 2024-01-25 | Online | [7 empty] | 22H FRANCONIA
WMECO | Agawam | ESMAEX-02138 | 1030 | 15.2 | Solar & Battery | 16C17 | 2023-02-07 | 2023-02-17 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-17 | [7 empty] | 0 |  |  |  |  | 2023-09-07 | Online | [7 empty] | 16C AGAWAM
WMECO | Feeding Hills | ESMAEX-02074 | 1030 | 15.2 | Solar | 30A1 | 2023-01-26 | 2023-02-08 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-08 | [7 empty] | 0 |  |  |  |  | 2023-05-11 | Online | [7 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-02093 | 1106 | 20.56 | Solar & Battery | 22H13 | 2023-01-31 | 2023-02-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-15 | [7 empty] | 0 |  |  |  |  | 2023-07-07 | Online | [7 empty] | 22H FRANCONIA
WMECO | Pelham | ESMAEX-02103 | 1002 | 13.26 | Solar & Battery | 17K2 | 2023-02-02 | 2023-03-31 | 42 |  | 42 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-13 | [7 empty] | 0 |  |  |  |  | 2023-08-07 | Online | [7 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-02155 | 1035 | 2000 | Solar | 17K5 | 2023-02-13 | 2023-02-15 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-11 | [7 empty] | 0 | [5 empty] | ISA Agreement | [6 empty] | 2000 | 17K AMHERST
WMECO | Colrain | ESMAEX-02141 | 1340 | 18.24 | Solar & Battery | 29R2 | 2023-02-08 | 2023-02-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-02-27 | [7 empty] | 0 |  |  |  |  | 2023-12-08 | Online | [7 empty] | 29R SHELBURNE
WMECO | Agawam | ESMAEX-02252 | 1001 | 15.2 | Solar | 30A5 | 2023-03-09 | 2023-03-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-23 | [7 empty] | 0 |  |  |  |  | 2023-08-14 | Online | [7 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-02230 | 1108 | 15.2 | Solar | 22H15 | 2023-03-03 | 2023-03-08 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-24 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online | [7 empty] | 22H FRANCONIA
WMECO | Longmeadow | ESMAEX-02189 | 1106 | 15.2 | Solar & Battery | 22H13 | 2023-02-22 | 2023-03-03 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online | [7 empty] | 22H FRANCONIA
WMECO | Southampton | ESMAEX-02171 | 1073 | 4980 | Solar & Battery | 15A1 | 2023-03-27 | 2023-06-02 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Transmission Study | [6 empty] | 4980 | 15A GUNN
WMECO | Lanesborough | ESMAEX-02210 | 1237 | 7.6 | Solar & Battery | 15E1 | 2023-02-28 | 2023-03-03 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [6 empty] | 14
WMECO | West Hatfield | ESMAEX-02405 | 1088 | 125 | Solar | 18G5 | 2023-04-21 | 2023-04-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2024-08-23 | Online | [7 empty] | 18G PODICK
WMECO | Blandford | ESMAEX-02238 | 1008 | 17.4 | Solar | 29A5 | 2023-03-06 | 2023-03-17 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-17 | [7 empty] | 0 |  |  |  |  | 2023-05-23 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Lee | ESMAEX-02279 | 1238 | 20.736 | Solar | 16B5 | 2023-03-17 | 2023-03-31 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-09-08 | Online | [7 empty] | 16B PLEASANT
WMECO | Longmeadow | ESMAEX-02289 | 1106 | 15.2 | Solar & Battery | 22H12 | 2023-03-21 | 2023-03-31 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-03 | [7 empty] | 0 |  |  |  |  | 2023-09-08 | Online | [7 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-02258 | 1201 | 12.98 | Solar | 19A7 | 2023-03-10 | 2023-03-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-28 | [7 empty] | 0 |  |  |  |  | 2023-07-20 | Online | [7 empty] | 19A DOREEN
WMECO | Amherst | ESMAEX-02259 | 1002 | 84.672 | Solar |  | 2023-03-10 | 2024-03-27 | 274 |  | 274 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-07 | [7 empty] | 0 |  |  |  |  | 2025-05-09 | Online
WMECO | Springfield | ESMAEX-02264 | 1108 | 8.26 | Solar & Battery | 21S12 | 2023-03-14 | 2023-03-20 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-03-21 | [7 empty] | 0 |  |  |  |  | 2023-05-03 | Online | [7 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-02288 | 1035 | 17.6 | Solar | 18G4 | 2023-03-20 | 2023-03-31 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-12 | [7 empty] | 0 |  |  |  |  | 2023-08-10 | Online | [7 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02312 | 1254 | 15.2 | Solar & Battery | 30B2 | 2023-03-27 | 2023-04-26 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-09-26 | Online | [7 empty] | 30B OSWALD
WMECO | Bernardston | ESMAEX-02295 | 1337 | 15.2 | Solar |  | 2023-03-22 | 2023-05-17 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online
WMECO | Cummington | ESMAEX-02311 | 1026 | 10 | Solar & Battery | 18C1 | 2023-03-27 | 2023-05-01 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-06 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-02314 | 1077 | 2000 | Solar | 29A5 | 2023-07-27 | 2023-08-02 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study |  |  |  | Southwick |  | Phase 1 - Pending CIP Approval | 2000 | 29A SOUTHWICK
WMECO | Becket | ESMAEX-02317 | 1223 | 9.3 | Solar | 19J6 | 2023-03-28 | 2023-04-07 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2023-08-03 | Online
WMECO | Springfield | ESMAEX-02322 | 1109 | 999 | Solar & Battery | 20A21 | 2023-05-09 | 2023-06-09 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-18 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-02326 | 1002 | 10 | Solar | 19B16 | 2023-03-30 | 2023-04-12 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-16 | [7 empty] | 0 |  |  |  |  | 2023-09-21 | Online | [7 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-02362 | 1201 | 60 | Solar | 19A7 | 2023-04-10 | 2023-04-26 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-02 | [7 empty] | 0 |  |  |  |  | 2024-01-18 | Online | [7 empty] | DOREEN
WMECO | Hadley | ESMAEX-02350 | 1035 | 15.2 | Solar | 19B15 | 2023-04-06 | 2023-04-26 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-26 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online | [6 empty] | 15.2 | 19B MIDWAY
WMECO | Southampton | ESMAEX-02348 | 1073 | 6 | Solar | 15A1 | 2023-04-05 | 2023-04-26 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-26 | [7 empty] | 0 |  |  |  |  | 2023-06-26 | Online | [6 empty] | 6 | 15A GUNN
WMECO | Southampton | ESMAEX-02396 | 1073 | 6 | Solar | 15A3 | 2023-04-20 | 2023-05-05 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2023-08-31 | Online | [6 empty] | 6 | 15A GUNN
WMECO | Peru | ESMAEX-02361 | 1235 | 10 | Battery |  | 2023-04-10 | 2023-05-17 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-26 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online
WMECO | Longmeadow | ESMAEX-02370 | 1106 | 15.2 | Solar & Battery | 22H17 | 2023-04-11 | 2023-04-26 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-04-28 | [7 empty] | 0 |  |  |  |  | 2023-09-21 | Online | [7 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-02475 | 1254 | 50 | Solar | 30B7 | 2023-05-15 | 2023-05-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2025-01-31 | Online | [7 empty] | 30B OSWALD
WMECO | Greenfield | ESMAEX-02459 | 1301 | 25 | Solar | 22B7 | 2023-05-08 | 2023-05-12 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-23 | [7 empty] | 0 |  |  |  |  | 2023-12-27 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02394 | 1105 | 100 | Solar | 5J16 | 2023-04-19 | 2023-06-08 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-08 | [7 empty] | 0 |  |  |  |  | 2025-09-29 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-02390 | 1253 | 20 | Solar | 19J4 | 2023-04-19 | 2023-05-15 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-26 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Shelburne Falls | ESMAEX-02408 | 1370 | 250 | Solar |  | 2023-04-21 |  | -32042 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Application Review
WMECO | Southwick | ESMAEX-02540 | 1077 | 16.52 | Solar | 29A5 | 2023-05-30 | 2023-07-07 | 29 |  | 29 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-02541 | 1073 | 15.2 | Solar & Battery | 15A1 | 2023-05-31 | 2023-06-16 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-09-03 | Online | [7 empty] | 15A GUNN
WMECO | Worthington | ESMAEX-02438 | 1098 | 2000 | Solar & Battery | 18K3 | 2023-05-26 | 2023-06-02 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 2000 | 18K PLAINFIELD
WMECO | Longmeadow | ESMAEX-02482 | 1106 | 21 | Solar | 22H11 | 2023-05-16 | 2023-05-31 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-31 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online | [7 empty] | FRANCONIA
WMECO | Amherst | ESMAEX-02471 | 1002 | 7.8 | Solar & Battery | 17K2 | 2023-05-11 | 2023-05-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-12-21 | Online | [7 empty] | 17K AMHERST
WMECO | Southampton | ESMAEX-02462 | 1073 | 10 | Solar | 15A3 | 2023-05-08 | 2023-05-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-09-05 | Online | [6 empty] | 10 | 15A GUNN
WMECO | Longmeadow | ESMAEX-02470 | 1106 | 15.2 | Solar & Battery | 22H13 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-05-25 | [7 empty] | 0 |  |  |  |  | 2023-09-12 | Online | [7 empty] | 22H FRANCONIA
WMECO | Sunderland | ESMAEX-02492 | 1375 | 25 | Solar |  | 2023-05-18 | 2023-05-24 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-02 | [7 empty] | 0 |  |  |  |  | 2023-08-02 | Online
WMECO | Montague | ESMAEX-02511 | 1376 | 4000 | Battery | 21C5 | 2023-05-23 | 2023-06-06 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4000 | 21C MONTAGUE
WMECO | Amherst | ESMAEX-02473 | 1002 | 15.2 | Solar & Battery | 19B16 | 2023-05-11 | 2023-07-06 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2023-10-17 | Online | [7 empty] | 19B MIDWAY
WMECO | Feeding Hills | ESMAEX-02493 | 1030 | 15.2 | Solar | 30A6 | 2023-05-18 | 2023-06-02 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-05 | [7 empty] | 0 |  |  |  |  | 2023-08-10 | Online | [7 empty] | 30A SILVER
WMECO | Worthington | ESMAEX-02520 | 1098 | 23.6 | Solar & Battery | 18C2 | 2023-05-25 | 2023-06-09 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-22 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Becket | ESMAEX-02484 | 1223 | 15.2 | Solar & Battery | 19J6 | 2023-05-16 | 2023-05-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-27 | [7 empty] | 0 |  |  |  |  | 2023-11-09 | Online
WMECO | Deerfield | ESMAEX-02485 | 1342 | 15.2 | Solar & Battery | 22B1 | 2023-05-16 | 2023-06-06 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-06 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Ludlow | ESMAEX-02496 | 1056 | 14 | Battery | 27A6 | 2023-05-19 | 2023-10-13 | 106 |  | 106 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Becket | ESMAEX-02501 | 1223 | 4999 | Solar & Battery | 16B1 | 2023-05-22 | 2023-05-31 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-04 | [7 empty] | 0 | [5 empty] | ISA Agreement | [6 empty] | 4999 | 16B PLEASANT
WMECO | Southwick | ESMAEX-02529 | 1077 | 15.2 | Solar |  | 2023-05-26 | 2023-06-19 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-06-19 | [7 empty] | 0 |  |  |  |  | 2024-04-30 | Online
WMECO | Springfield | ESMAEX-02508 | 1109 | 14 | Battery | 5J14 | 2023-05-22 | 2023-07-31 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-10 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Blandford | ESMAEX-02512 | 1008 | 2656 | Solar & Battery | 19J2 | 2023-07-05 | 2023-07-13 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study |  |  |  | Blandford |  | Phase 2 - In Process |  | 19J BLANDFORD
WMECO | Sunderland | ESMAEX-02515 | 1375 | 15.2 | Solar & Battery | 18G3 | 2023-05-24 | 2023-06-09 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-10-23 | Online | [7 empty] | 18G PODICK
WMECO | Montague | ESMAEX-02552 | 1376 | 4999 | Battery | 21C2 | 2023-07-20 | 2023-08-03 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague |  | Phase X - Pending CIP Approval |  | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-02604 | 1030 | 15.2 | Solar | 16C17 | 2023-06-22 | 2023-07-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-11-17 | Online | [7 empty] | 16C AGAWAM
WMECO | West Hatfield | ESMAEX-02557 | 1088 | 15.2 | Solar | 18G5 | 2023-06-06 | 2023-06-27 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-01-05 | Online | [7 empty] | 18G PODICK
WMECO | Russell | ESMAEX-02599 | 1071 | 5 | Battery | 19J2 | 2023-06-21 | 2023-07-07 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-13 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Agawam | ESMAEX-02606 | 1001 | 996 | Solar | 30A3 | 2023-08-15 | 2023-08-17 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-02613 | 1235 | 19 | Solar | 18C2 | 2023-06-23 | 2023-07-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-02 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | South Deerfield | ESMAEX-02623 | 1373 | 20 | Solar | 22B3 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-14 | [7 empty] | 0 |  |  |  |  | 2023-12-18 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02625 | 1104 | 6 | Solar | 5J15 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-07-07 | [7 empty] | 0 |  |  |  |  | 2023-09-26 | Online | [6 empty] | 6 | 5J EAST SPRINGFIELD
WMECO | Tolland | ESMAEX-02715 | 1034 | 6 | Solar & Battery | 19J4 | 2023-07-26 | 2023-08-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-24 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Amherst | ESMAEX-02641 | 1002 | 18.048 | Solar | 17K8 | 2023-07-06 | 2023-08-30 | 40 |  | 40 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-03 | [7 empty] | 0 |  |  |  |  | 2023-11-13 | Online | [7 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-02695 | 1238 | 110 | Solar |  | 2023-07-20 | 2023-08-01 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-02 | [7 empty] | 0 |  |  |  |  | 2024-06-20 | Online
WMECO | Southwick | ESMAEX-02662 | 1077 | 4998 | Solar & Battery | 29A1 | 2023-08-08 | 2023-08-09 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  |  | Southwick |  | Phase 1 - Pending CIP Approval |  | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-02696 | 1243 | 17.28 | Solar | 18C2 | 2023-07-21 | 2023-08-08 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-08 | [7 empty] | 0 |  |  |  |  | 2024-03-22 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Pittsfield | ESMAEX-02692 | 1201 | 22.8 | Solar & Battery | 30B4 | 2023-07-19 | 2023-08-03 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-06 | [7 empty] | 0 |  |  |  |  | 2024-04-04 | Online | [7 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-02764 | 1104 | 15.2 | Solar | 5J10 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-28 | [7 empty] | 0 |  |  |  |  | 2024-05-23 | Online | [6 empty] | 0 | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-02682 | 1027 | 15.2 | Solar & Battery | 15A5 | 2023-07-18 | 2023-12-15 | 109 |  | 109 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [7 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-02685 | 1054 | 15.2 | Solar & Battery | 21C7 | 2023-07-18 | 2023-09-06 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-25 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-02702 | 1089 | 11.21 | Solar & Battery | 21N4 | 2023-07-21 | 2023-08-07 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-07 | [7 empty] | 0 |  |  |  |  | 2023-10-12 | Online | [7 empty] | 21N PIPER
WMECO | Middlefield | ESMAEX-02742 | 1243 | 10 | Battery | 18C2 | 2023-08-01 | 2023-09-05 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-02 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-02710 | 1073 | 15.2 | Solar & Battery |  | 2023-07-25 | 2023-08-03 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-12 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Amherst | ESMAEX-02721 | 1002 | 20 | Solar | 17K2 | 2023-07-28 | 2023-08-11 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-22 | [7 empty] | 0 |  |  |  |  | 2023-11-13 | Online | [7 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-02741 | 1201 | 120 | Solar | 30B4 | 2023-10-19 | 2023-11-06 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-11-14 | Online | [7 empty] | 30B OSWALD
WMECO | Leverett | ESMAEX-02743 | 1054 | 15.2 | Solar & Battery | 18G7 | 2023-08-01 | 2023-08-15 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-18 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online | [7 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02753 | 1254 | 24.4 | Solar | 30B7 | 2023-08-04 | 2023-08-11 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-15 | [7 empty] | 0 |  |  |  |  | 2025-09-09 | Online | [7 empty] | 30B OSWALD
WMECO | Agawam | ESMAEX-02765 | 1001 | 200 | Solar | 16C16 | 2023-08-29 | 2023-08-11 | -13 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-02 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 16C AGAWAM
WMECO | Easthampton | ESMAEX-02766 | 1027 | 10 | Solar | 15A3 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2023-12-18 | Online | [7 empty] | 15A GUNN
WMECO | Becket | ESMAEX-02759 | 1223 | 13.12 | Solar & Battery | 19J6 | 2023-08-04 | 2023-08-30 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-02 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Southampton | ESMAEX-02782 | 1073 | 15.2 | Solar & Battery | 15A1 | 2023-08-09 | 2023-08-17 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-09-18 | [7 empty] | 0 |  |  |  |  | 2024-01-03 | Online | [7 empty] | 15A GUNN
WMECO | Hinsdale | ESMAEX-02797 | 1235 | 4950 | Solar & Battery | 18C2 | 2023-12-07 | 2023-12-12 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Berkshire | Berkshire |  | Phase 1 - Executed ISA |  | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-02897 | 1070 | 5 | Solar & Battery | 18K4 | 2023-09-07 | 2023-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-18 | [7 empty] | 0 |  |  |  |  | 2024-05-07 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-02846 | 1075 | 4980 | Solar & Battery | 18K3 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 4980 | 18K PLAINFIELD
WMECO | Lanesborough | ESMAEX-02849 | 1237 | 4980 | Solar & Battery | 15E1 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 15E PARTRIDGE
WMECO | Agawam | ESMAEX-02855 | 1001 | 16 | Solar | 30A3 | 2023-08-23 | 2023-08-30 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-08-31 | [7 empty] | 0 |  |  |  |  | 2024-03-01 | Online | [6 empty] | 16 | SILVER
WMECO | Indian Orchard | ESMAEX-02866 | 1151 | 6 | Solar | 27A13 | 2023-08-25 | 2023-08-30 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-03 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online | [6 empty] | 0 | 27A ORCHARD
WMECO | Northfield | ESMAEX-03085 | 1360 | 10 | Solar | 21B8 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-04 | [7 empty] | 0 |  |  |  |  | 2024-05-14 | Online |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Russell | ESMAEX-02942 | 1071 | 25 | Solar | 19J2 | 2023-09-21 | 2023-10-04 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-05-29 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-02907 | 1027 | 21.25 | Solar & Battery | 15A2 | 2023-09-11 | 2023-09-19 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-01 | [7 empty] | 0 |  |  |  |  | 2024-03-11 | Online | [7 empty] | 15A GUNN
WMECO | Dalton | ESMAEX-02940 | 1226 | 22.8 | Solar | 19A2 | 2023-09-21 | 2023-10-12 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-09-20 | Online | [7 empty] | 19A DOREEN
WMECO | Springfield | ESMAEX-02924 | 1108 | 10 | Battery | 22H15 | 2023-09-15 | 2023-10-12 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-06-21 | Online | [7 empty] | 22H FRANCONIA
WMECO | Tyringham | ESMAEX-02990 | 1264 | 15.2 | Solar & Battery |  | 2023-09-29 | 2023-10-05 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-12 | [7 empty] | 0 |  |  |  |  | 2024-04-02 | Online
WMECO | Dalton | ESMAEX-03002 | 1226 | 15.2 | Solar | 18C1 | 2023-10-02 | 2023-10-12 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-06-19 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Richmond | ESMAEX-03008 | 1254 | 15.2 | Solar | 30B2 | 2023-10-03 | 2023-10-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-10-13 | [7 empty] | 0 |  |  |  |  | 2024-04-16 | Online | [7 empty] | 30B OSWALD
WMECO | Hatfield | ESMAEX-03011 | 1038 | 1992 | Solar & Battery | 18G6 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03039 | 1056 | 20 | Solar | 19S3 | 2023-10-12 | 2023-11-06 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-06 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [7 empty] | 19S LUDLOW
WMECO | Pittsfield | ESMAEX-03068 | 1201 | 30 | Solar | 30B2 | 2023-10-19 | 2024-09-16 | 238 |  | 238 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-08 | [7 empty] | 0 | [5 empty] | Meter | [7 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-03047 | 1107 | 6 | Solar | 21S6 | 2023-10-13 | 2023-10-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-06 | [7 empty] | 0 |  |  |  |  | 2024-02-07 | Online | [6 empty] | 6 | 21S CLINTON
WMECO | Ludlow | ESMAEX-03087 | 1056 | 17.28 | Solar | 19S1 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-09 | [7 empty] | 0 |  |  |  |  | 2024-02-08 | Online | [7 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-03121 | 1035 | 16 | Solar & Battery | 19B15 | 2023-11-06 | 2023-12-07 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-03-05 | Online | [7 empty] | 19B MIDWAY
WMECO | Dalton | ESMAEX-03120 | 1226 | 15.2 | Solar & Battery |  | 2023-11-06 | 2023-11-16 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-11-22 | [7 empty] | 0 |  |  |  |  | 2024-06-21 | Online
WMECO | Agawam | ESMAEX-03118 | 1001 | 14.79 | Solar | 30A1 | 2023-11-03 | 2023-11-16 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-08 | [7 empty] | 0 |  |  |  |  | 2024-05-20 | Online | [7 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-03125 | 1002 | 15 | Battery |  | 2023-11-07 | 2024-02-27 | 81 |  | 81 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-10-22 | Online
WMECO | Springfield | ESMAEX-03156 | 1118 | 7.6 | Solar & Battery | 20A32 | 2023-11-15 | 2023-11-20 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-12 | [7 empty] | 0 |  |  |  |  | 2024-11-22 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Deerfield | ESMAEX-03331 | 1342 | 10 | Battery | 22B7 | 2024-01-04 | 2024-03-13 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-25 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 22B CUMBERLAND
WMECO | Hatfield | ESMAEX-03241 | 1088 | 20 | Solar & Battery | 18G5 | 2023-12-06 | 2023-12-28 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-01 | [7 empty] | 0 |  |  |  |  | 2024-09-11 | Online | [7 empty] | 18G PODICK
WMECO | Westhampton | ESMAEX-03179 | 1027 | 15.2 | Solar | 15A3 | 2023-11-20 | 2023-11-29 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-13 | [7 empty] | 0 |  |  |  |  | 2024-06-12 | Online | [7 empty] | 15A GUNN
WMECO | Tolland | ESMAEX-03176 | 1034 | 2988 | Solar & Battery | 19J4 | 2023-11-20 | 2023-12-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Blandford |  | Hold In Queue | 2988 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-03184 | 1027 | 100 | Solar | 15A2 | 2023-11-21 | 2023-11-22 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-08 | [7 empty] | 0 |  |  |  |  | 2024-01-24 | Online | [7 empty] | 15A GUNN
WMECO | Plainfield | ESMAEX-03192 | 1070 | 3820 | Solar & Battery | 18K3 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [6 empty] | 3820 | 18K PLAINFIELD
WMECO | Hadley | ESMAEX-03228 | 1035 | 499 | Solar | 18G6 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-24 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 499 | 18G PODICK
WMECO | Hadley | ESMAEX-03229 | 1035 | 499 | Solar | 18G5 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-02 | [7 empty] | 0 | [5 empty] | Technical Review | [6 empty] | 499 | 18G PODICK
WMECO | Whately | ESMAEX-03396 | 1093 | 84.6 | Solar & Battery | 18G8 | 2024-01-30 | 2024-02-22 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-16 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-03234 | 1027 | 15.2 | Solar | 15A3 | 2023-12-06 | 2023-12-22 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2023-12-29 | [7 empty] | 0 |  |  |  |  | 2024-06-18 | Online | [7 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03323 | 1027 | 15.36 | Solar & Battery | 15A3 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [7 empty] | 15A GUNN
WMECO | Ashfield | ESMAEX-03516 | 1330 | 10 | Solar & Battery | 38A1 | 2024-03-08 | 2024-03-19 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-26 | [7 empty] | 0 |  |  |  |  | 2024-08-06 | Online | [6 empty] | 10 | 38A ASHFIELD
WMECO | Richmond | ESMAEX-03326 | 1254 | 15.36 | Solar & Battery | 30B2 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-13 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online | [7 empty] | 30B OSWALD
WMECO | Hadley | ESMAEX-03306 | 1035 | 10 | Solar | 18G4 | 2023-12-21 | 2024-01-04 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-23 | Online | [7 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03290 | 1056 | 7.6 | Battery | 27A4 | 2023-12-19 | 2024-01-17 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-15 | [7 empty] | 0 |  |  |  |  | 2024-11-19 | Online | [7 empty] | 27A ORCHARD
WMECO | Easthampton | ESMAEX-03304 | 1027 | 18 | Solar | 15A5 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-05 | [7 empty] | 0 |  |  |  |  | 2024-09-19 | Online | [7 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03309 | 1027 | 22.8 | Solar | 15A2 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-05-15 | Online | [7 empty] | 15A GUNN
WMECO | Longmeadow | ESMAEX-03380 | 1106 | 15.2 | Solar & Battery |  | 2024-01-24 | 2024-02-01 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-26 | [7 empty] | 0 |  |  |  |  | 2024-10-28 | Online
WMECO | Buckland | ESMAEX-03311 | 1338 | 37.5 | Solar | 22B5 | 2023-12-22 | 2024-01-09 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-13 | [7 empty] | 0 |  |  |  |  | 2025-01-21 | Online | [7 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03327 | 1089 | 15.2 | Solar | 16C11 | 2024-01-03 | 2024-01-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-24 | [7 empty] | 0 |  |  |  |  | 2024-03-05 | Online | [6 empty] | 15.2 | 16C AGAWAM
WMECO | Westhampton | ESMAEX-03330 | 1027 | 15.2 | Solar & Battery | 15A3 | 2024-01-04 | 2024-01-17 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-08-29 | Online | [7 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-03343 | 1002 | 16.5 | Solar | 18G4 | 2024-01-09 | 2024-01-17 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-01-30 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [6 empty] | 15.95 | 18G PODICK
WMECO | Conway | ESMAEX-03473 | 1341 | 20 | Battery | 38A1 | 2024-02-22 | 2024-02-28 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-08-30 | Online | [6 empty] | 10 | 38A ASHFIELD
WMECO | Greenfield | ESMAEX-03367 | 1301 | 999 | Solar & Battery | 22B2 | 2025-04-25 | 2025-05-08 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 999 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-03638 | 1027 | 17.6 | Solar | 15A3 | 2024-04-08 | 2024-04-18 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-28 | [7 empty] | 0 |  |  |  |  | 2025-01-16 | Online | [7 empty] | 15A GUNN
WMECO | Greenfield | ESMAEX-03857 | 1301 | 30 | Solar | 22B4 | 2024-06-24 | 2024-07-25 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 |  |  |  |  | 2025-03-20 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Hancock | ESMAEX-04296 | 1237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 2000 | 30B OSWALD
WMECO | Tolland | ESMAEX-03388 | 1034 | 9.9 | Solar & Battery | 19J4 | 2024-01-26 | 2024-02-09 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-13 | [7 empty] | 0 |  |  |  |  | 2024-05-20 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Hancock | ESMAEX-04297 | 1237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 2000 | 30B OSWALD
WMECO | Pittsfield | ESMAEX-04298 | 1201 | 1000 | Solar | 30B7 | 2024-11-22 | 2025-01-22 | 44 |  | 44 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-16 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 1000 | 30B OSWALD
WMECO | South Deerfield | ESMAEX-03438 | 1373 | 10 | Battery | 18G3 | 2024-02-14 | 2024-03-18 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [7 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-03394 | 1035 | 15.2 | Solar | 17K5 | 2024-01-29 | 2024-02-01 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-12 | [7 empty] | 0 |  |  |  |  | 2024-09-13 | Online | [7 empty] | 17K AMHERST
WMECO | Lanesborough | ESMAEX-03409 | 1237 | 1992 | Solar & Battery | 30B5 | 2024-02-29 | 2024-03-06 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | 30B OSWALD
WMECO | Greenfield | ESMAEX-03468 | 1301 | 100 | Solar | 21C4 | 2024-02-21 | 2024-05-02 | 52 |  | 52 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-22 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Springfield | ESMAEX-03437 | 1118 | 5 | Solar & Battery | 20A21 | 2024-02-14 | 2024-02-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-02-26 | [7 empty] | 0 |  |  |  |  | 2024-07-16 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Plainfield | ESMAEX-03434 | 1070 | 24 | Solar | 18C1 | 2024-02-13 | 2024-04-23 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-04 | [7 empty] | 0 |  |  |  |  | 2024-10-06 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Turners Falls | ESMAEX-03587 | 1376 | 40 | Solar | 21C6 | 2024-03-28 | 2024-05-09 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-11 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Agawam | ESMAEX-03455 | 1001 | 1500 | Solar | 30A3 | 2024-05-06 | 2024-06-06 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | 30A SILVER
WMECO | West Springfield | ESMAEX-03502 | 1089 | 250 | Solar | 21N8 | 2024-03-01 | 2024-04-03 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-24 | [7 empty] | 0 |  |  |  |  | 2025-09-05 | Online | [7 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-03541 | 1103 | 700 | Fuel Cell | 8C13 | 2024-03-19 | 2024-04-03 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 8C WEST SPRINGFIELD
WMECO | Erving | ESMAEX-03495 | 1360 | 4980 | Solar & Battery | 21B8 | 2024-02-29 | 2024-03-18 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Whatley-Deerfield | Gill-Montague |  | Phase 1 - Pending CIP Approval | 4980 | 21B FRENCH KING
WMECO | Worthington | ESMAEX-03482 | 1098 | 15.2 | Solar | 18C2 | 2024-02-27 | 2024-03-06 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-09-24 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Lenox Dale | ESMAEX-03488 | 1242 | 13.6 | Solar & Battery | 17G3 | 2024-02-28 | 2024-03-06 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-03-06 | [7 empty] | 0 |  |  |  |  | 2025-01-31 | Online | [7 empty] | 17G WOODLAND RD
WMECO | Worthington | ESMAEX-03492 | 1098 | 20 | Solar | 18C2 | 2024-02-29 | 2024-03-06 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-10-04 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03550 | 1104 | 32.83 | Solar | 5J13 | 2024-03-19 | 2024-05-13 | 40 |  | 40 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-22 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-03531 | 1253 | 70 | Solar | 19J4 | 2024-03-12 | 2024-04-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-24 | [7 empty] | 0 | [5 empty] | Construction Stage |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Lee | ESMAEX-03528 | 1238 | 10 | Solar & Battery | 16B5 | 2024-03-11 | 2024-03-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-25 | [7 empty] | 0 |  |  |  |  | 2024-08-09 | Online | [7 empty] | 16B PLEASANT
WMECO | Turners Falls | ESMAEX-03511 | 1376 | 990 | Battery | 21C8 | 2024-07-24 | 2024-09-16 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-25 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Hadley | ESMAEX-03526 | 1035 | 498 | Solar | 18G4 | 2024-06-11 | 2024-06-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Worthington | ESMAEX-03537 | 1098 | 16.8 | Solar | 18C2 | 2024-03-14 | 2024-03-21 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-05 | [7 empty] | 0 |  |  |  |  | 2024-08-29 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03563 | 1027 | 15.2 | Solar & Battery | 15A5 | 2024-03-21 | 2024-03-27 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-01 | [7 empty] | 0 |  |  |  |  | 2024-08-08 | Online | [7 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04793 | 1077 | 10 | Solar & Battery | 29A1 | 2025-04-15 | 2025-04-29 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-03579 | 1243 | 10 | Solar & Battery | 18C2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-31 | [7 empty] | 0 |  |  |  |  | 2025-01-24 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Peru | ESMAEX-03573 | 1235 | 4999.8 | Solar & Battery | 18C2 | 2024-03-25 | 2024-05-15 | 38 |  | 38 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Berkshire | Berkshire |  | Phase 1 - Executed ISA | 4999.8 | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03576 | 1027 | 15.2 | Solar | 15A2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-15 | [7 empty] | 0 |  |  |  |  | 2024-09-12 | Online | [7 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-03620 | 1089 | 50 | Solar |  | 2024-04-03 | 2024-05-15 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-28 | [7 empty] | 0 |  |  |  |  | 2025-01-22 | Online
WMECO | Deerfield | ESMAEX-03581 | 1342 | 46 | Solar & Battery | 22B4 | 2024-03-27 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-21 | [7 empty] | 0 |  |  |  |  | 2024-10-28 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-03600 | 1118 | 15.2 | Solar | 20A32 | 2024-04-01 | 2024-04-12 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-28 | [7 empty] | 0 |  |  |  |  | 2025-02-26 | Online | [7 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-03626 | 1002 | 20 | Solar | 18G3 | 2024-04-03 | 2024-06-05 | 46 |  | 46 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-11-07 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03681 | 1108 | 10 | Battery | 22H16 | 2024-04-18 | 2024-04-24 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-04-26 | [7 empty] | 0 |  |  |  |  | 2024-09-25 | Online | [7 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-03648 | 1002 | 15.2 | Solar | 18G7 | 2024-04-09 | 2024-05-21 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [7 empty] | 18G PODICK
WMECO | Lanesborough | ESMAEX-03699 | 1237 | 9.9 | Solar & Battery | 15E1 | 2024-04-22 | 2024-05-13 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-10 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [6 empty] | 9.75
WMECO | Ludlow | ESMAEX-03662 | 1056 | 3.8 | Solar | 27A4 | 2024-04-12 | 2024-05-28 | 33 |  | 33 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-30 | [7 empty] | 0 |  |  |  |  | 2024-09-16 | Online | [7 empty] | 27A ORCHARD
WMECO | Pittsfield | ESMAEX-03669 | 1201 | 7.6 | Solar | 19A1 | 2024-04-15 | 2024-06-06 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-09-17 | Online | [7 empty] | 19A DOREEN
WMECO | Savoy | ESMAEX-03695 | 1256 | 10 | Battery | 18K4 | 2024-04-22 | 2024-05-14 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-05-22 | [7 empty] | 0 |  |  |  |  | 2024-08-28 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Amherst | ESMAEX-03769 | 1002 | 100 | Solar | 17K7 | 2024-05-15 | 2024-05-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | Meter | [7 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-03737 | 1238 | 100 | Solar | 16B5 | 2024-05-07 | 2024-05-28 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 16B PLEASANT
WMECO | Shutesbury | ESMAEX-03732 | 1072 | 11.5 | Solar & Battery | 18G7 | 2024-05-03 | 2024-05-14 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-18 | [7 empty] | 0 |  |  |  |  | 2024-10-07 | Online | [7 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03727 | 1056 | 15.2 | Solar |  | 2024-05-02 | 2024-05-31 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-17 | [7 empty] | 0 |  |  |  |  | 2024-12-17 | Online
WMECO | Sunderland | ESMAEX-03718 | 1375 | 10 | Solar | 18G6 | 2024-04-30 | 2024-06-06 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-30 | [7 empty] | 0 |  |  |  |  | 2025-01-14 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03739 | 1108 | 240 | Solar | 22H17 | 2024-05-08 | 2024-05-16 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-26 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 22H FRANCONIA
WMECO | Hatfield | ESMAEX-03738 | 1038 | 15 | Solar | 18G6 | 2024-05-08 | 2024-05-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2024-12-02 | Online | [7 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-03748 | 1001 | 9 | Solar | 30A5 | 2024-05-10 | 2024-07-09 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-12 | [7 empty] | 0 |  |  |  |  | 2024-09-03 | Online | [7 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-03822 | 1235 | 4999.8 | Solar & Battery | 18C2 | 2024-06-10 | 2024-06-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study |  |  | Berkshire | Berkshire |  | Phase 1 - Executed ISA | 4999.8 | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03751 | 1108 | 15.2 | Solar | 21S11 | 2024-05-10 | 2024-05-30 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-06-15 | [7 empty] | 0 |  |  |  |  | 2024-10-30 | Online | [7 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-03764 | 1375 | 20 | Solar | 18G6 | 2024-05-14 | 2024-06-06 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-23 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03772 | 1107 | 20 | Solar | 21S10 | 2024-05-15 | 2024-06-21 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-01-10 | [7 empty] | 0 |  |  |  |  | 2025-06-12 | Online | [7 empty] | 21S CLINTON
WMECO | Turners Falls | ESMAEX-03804 | 1376 | 600 | Internal Combustion Engine | 21C2 | 2024-05-30 | 2024-06-21 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Gill-Montague |  |  | 0 | 21C MONTAGUE
WMECO | Montgomery | ESMAEX-03811 | 1085 | 15.2 | Solar | 19J5 | 2024-06-04 | 2024-07-01 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2024-12-20 | Online |  |  |  | Blandford
WMECO | Bernardston | ESMAEX-03896 | 1337 | 200 | Solar | 21B8 | 2024-07-12 | 2024-07-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Bernardston | ESMAEX-03897 | 1337 | 240 | Solar | 21B8 | 2024-07-12 | 2024-07-22 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-03 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Greenfield | ESMAEX-03922 | 1301 | 240 | Solar | 22B2 | 2024-07-24 | 2024-08-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-15 | [7 empty] | 0 | [5 empty] | Construction Stage | [7 empty] | 22B CUMBERLAND
WMECO | Greenfield | ESMAEX-03928 | 1301 | 240 | Solar | 22B7 | 2024-07-26 | 2024-08-06 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 22B CUMBERLAND
WMECO | Hatfield | ESMAEX-03820 | 1038 | 750 | Solar | 18G5 | 2024-10-24 | 2024-11-01 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-03843 | 1375 | 20 | Solar | 18G3 | 2024-06-14 | 2024-08-05 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [7 empty] | 18G PODICK
WMECO | Leyden | ESMAEX-03827 | 1337 | 10 | Solar | 22B7 | 2024-06-12 | 2024-07-08 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-07 | [7 empty] | 0 |  |  |  |  | 2025-01-02 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Colrain | ESMAEX-03862 | 1340 | 20 | Solar & Battery | 29R2 | 2024-06-25 | 2024-07-23 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-28 | [7 empty] | 0 |  |  |  |  | 2025-01-02 | Online | [7 empty] | 29R SHELBURNE
WMECO | South Deerfield | ESMAEX-03855 | 1373 | 15.2 | Solar | 22B1 | 2024-06-24 | 2024-07-05 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-08 | [7 empty] | 0 |  |  |  |  | 2024-11-26 | Online | [7 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03872 | 1089 | 20 | Solar | 21N9 | 2024-06-29 | 2024-07-23 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-07-29 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [7 empty] | 21N PIPER
WMECO | Ludlow | ESMAEX-03876 | 1056 | 23 | Solar & Battery | 19S3 | 2024-07-01 | 2024-07-09 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-02-14 | Online | [7 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-03880 | 1002 | 23 | Solar | 19B16 | 2024-07-02 | 2024-08-07 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2024-12-24 | Online | [7 empty] | 19B MIDWAY
WMECO | East Otis | ESMAEX-03888 | 1029 | 20 | Solar | 19J4 | 2024-07-10 | 2024-08-06 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-06 | [7 empty] | 0 |  |  |  |  | 2025-01-10 | Online |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-03925 | 1201 | 3500 | Solar & Battery | 15E2 | 2024-07-25 | 2024-08-06 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Impact Study | [7 empty] | 15E PARTRIDGE
WMECO | Lee | ESMAEX-03914 | 1238 | 4999 | Other | 16B5 | 2025-02-04 | 2025-02-11 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Standard |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 4999 | 16B PLEASANT
WMECO | Huntington | ESMAEX-03924 | 1050 | 23 | Solar & Battery | 19J5 | 2024-07-25 | 2024-08-20 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online
WMECO | Feeding Hills | ESMAEX-03937 | 1030 | 15.2 | Solar | 30A6 | 2024-07-30 | 2024-09-13 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-16 | [7 empty] | 0 |  |  |  |  | 2025-01-06 | Online | [7 empty] | 30A SILVER
WMECO | Tyringham | ESMAEX-03966 | 1264 | 23 | Solar | 16B1 | 2024-08-14 | 2024-08-28 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-08-30 | [7 empty] | 0 |  |  |  |  | 2025-01-14 | Online | [7 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-03954 | 1201 | 180 | Solar | 30B2 | 2024-09-06 | 2024-11-08 | 46 |  | 46 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-17 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-03961 | 1106 | 15.36 | Solar | 22H13 | 2024-08-12 | 2024-08-14 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-16 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [7 empty] | 22H FRANCONIA
WMECO | Lee | ESMAEX-03957 | 1238 | 15.2 | Solar | 16B5 | 2024-08-09 | 2024-09-11 | 24 |  | 24 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-06 | [7 empty] | 0 |  |  |  |  | 2025-02-12 | Online | [7 empty] | 16B PLEASANT
WMECO | Montague | ESMAEX-03967 | 1351 | 20 | Battery | 21C7 | 2024-08-14 | 2024-09-11 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-16 | [7 empty] | 0 |  |  |  |  | 2024-12-30 | Online |  |  |  | Gill-Montague |  |  | 10 | 21C MONTAGUE
WMECO | West Hatfield | ESMAEX-03989 | 1088 | 9.57 | Solar | 18G5 | 2024-08-22 | 2024-08-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-23 | [7 empty] | 0 |  |  |  |  | 2024-12-13 | Online | [7 empty] | 18G PODICK
WMECO | Whately | ESMAEX-03978 | 1093 | 23 | Solar & Battery | 18G8 | 2024-08-18 | 2024-08-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-25 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 18G PODICK
WMECO | Otis | ESMAEX-03984 | 1253 | 5000 | Solar & Battery | 19J4 | 2024-09-09 | 2024-09-13 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Blandford |  | Hold In Queue |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-04002 | 1237 | 16.9 | Battery | 15E1 | 2024-08-27 | 2024-09-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-09-17 | [7 empty] | 0 | [5 empty] | Compliances Documents | [6 empty] | 6.9
WMECO | Southampton | ESMAEX-04025 | 1073 | 23 | Solar & Battery | 15A3 | 2024-09-04 | 2024-09-26 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-02-24 | Online | [7 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-04054 | 1002 | 30 | Solar | 18G7 | 2024-09-12 | 2024-09-20 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-29 | [7 empty] | 0 |  |  |  |  | 2025-01-24 | Online | [7 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-04039 | 1035 | 999 | Solar | 17K5 | 2024-11-19 | 2025-01-28 | 51 |  | 51 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [6 empty] | 999 | 17K AMHERST
WMECO | Hadley | ESMAEX-04202 | 1035 | 625 | Solar | 17K5 | 2024-10-24 | 2024-11-18 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 17K AMHERST
WMECO | Deerfield | ESMAEX-04030 | 1342 | 2500 | Solar | 22B4 | 2024-12-13 |  | -32472 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22B CUMBERLAND
WMECO | Lee | ESMAEX-04068 | 1238 | 15.2 | Solar |  | 2024-09-18 | 2024-10-22 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-10-24 | [7 empty] | 0 |  |  |  |  | 2025-04-07 | Online
WMECO | Hadley | ESMAEX-04056 | 1035 | 240 | Solar | 17K1 | 2024-09-13 | 2024-09-19 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-03 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-04115 | 1077 | 7.6 | Solar | 29A1 | 2024-09-26 | 2024-10-17 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-28 | [7 empty] | 0 |  |  |  |  | 2025-07-17 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-04155 | 1073 | 15.2 | Solar | 15A1 | 2024-10-08 | 2024-10-28 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-03 | [7 empty] | 0 |  |  |  |  | 2025-03-12 | Online | [7 empty] | 15A GUNN
WMECO | North Hatfield | ESMAEX-04157 | 1066 | 17.16 | Solar | 18G6 | 2024-10-09 | 2024-10-18 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-12-09 | [7 empty] | 0 |  |  |  |  | 2025-04-08 | Online | [7 empty] | 18G PODICK
WMECO | Dalton | ESMAEX-04162 | 1226 | 3000 | Solar & Battery | 18C1 | 2024-11-01 | 2024-11-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 | [5 empty] | Technical Review |  |  |  | Berkshire |  | Hold In Queue |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-04166 | 1073 | 3000 | Solar & Battery | 15A1 | 2024-11-06 | 2024-11-18 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Impact Study | [7 empty] | 15A GUNN
WMECO | Ludlow | ESMAEX-04200 | 1056 | 7.6 | Solar | 19S3 | 2024-10-22 | 2024-11-08 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-18 | [7 empty] | 0 |  |  |  |  | 2025-03-25 | Online | [7 empty] | 19S LUDLOW
WMECO | Richmond | ESMAEX-04237 | 1254 | 10 | Solar & Battery | 30B7 | 2024-11-04 | 2024-11-12 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 | [7 empty] | 0 | [5 empty] | Technical Review | [7 empty] | 30B OSWALD
WMECO | Easthampton | ESMAEX-04203 | 1027 | 11.5 | Battery | 15A2 | 2024-10-24 |  | -32436 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-06-13 | Online | [7 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04231 | 1077 | 15 | Battery | 29A5 | 2024-11-01 | 2024-11-19 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-03 | [7 empty] | 0 |  |  |  |  | 2025-07-18 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-04607 | 1035 | 480 | Solar | 17K1 | 2025-03-07 | 2025-06-10 | 68 |  | 68 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 17K AMHERST
WMECO | Dalton | ESMAEX-04224 | 1226 | 24 | Solar | 19A2 | 2024-10-29 | 2024-11-06 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2024-11-06 | [7 empty] | 0 |  |  |  |  | 2025-02-27 | Online | [7 empty] | 19A DOREEN
WMECO | Hinsdale | ESMAEX-04230 | 1235 | 13.8 | Solar | 18C2 | 2024-11-01 | 2025-01-08 | 49 |  | 49 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-06 | [7 empty] | 0 | [5 empty] | Compliances Documents |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-04274 | 1077 | 11.5 | Battery | 29A5 | 2024-11-13 |  | -32450 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-27 | [7 empty] | 0 |  |  |  |  | 2025-06-13 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-04280 | 1002 | 300 | Solar | 17K5 | 2025-02-14 | 2025-02-24 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-04356 | 1035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-05 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04357 | 1035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-10 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 19B MIDWAY
WMECO | West Springfield | ESMAEX-04335 | 1089 | 11.5 | Battery | 16C11 | 2024-12-05 | 2025-01-24 | 37 |  | 37 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-06 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 16C AGAWAM
WMECO | Blandford | ESMAEX-04291 | 1008 | 1999 | Solar & Battery | 19J2 | 2024-11-21 | 2024-12-05 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Blandford |  | Hold In Queue | 1999 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-04288 | 1201 | 46 | Solar & Battery |  | 2024-11-20 | 2024-11-26 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 | [7 empty] | 0 |  |  |  |  | 2025-07-16 | Online
WMECO | West Springfield | ESMAEX-04318 | 1089 | 22.77 | Solar |  | 2024-12-03 | 2024-12-18 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-14 | [7 empty] | 0 |  |  |  |  | 2025-09-17 | Online
WMECO | Feeding Hills | ESMAEX-04359 | 1030 | 15.2 | Solar | 30A1 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-18 | [7 empty] | 0 |  |  |  |  | 2025-10-20 | Online | [7 empty] | 30A SILVER
WMECO | Deerfield | ESMAEX-04370 | 1342 | 4999 | Solar & Battery | 22B7 | 2024-12-13 |  | -32472 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22B CUMBERLAND
WMECO | Erving | ESMAEX-04365 | 1344 | 200 | Solar | 21C8 | 2024-12-17 | 2025-01-28 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Amherst | ESMAEX-04361 | 1002 | 15.2 | Solar | 19B16 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-07 | [7 empty] | 0 |  |  |  |  | 2025-04-29 | Online | [7 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04385 | 1035 | 67.3 | Solar | 18G4 | 2024-12-16 | 2025-01-21 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-09-29 | Online | [7 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04467 | 1089 | 240 | Solar | 21N5 | 2025-06-17 | 2025-06-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-04403 | 1027 | 15.2 | Solar | 15A3 | 2024-12-23 | 2025-01-22 | 23 |  | 23 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-06-17 | Online | [7 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-04412 | 1109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04476 | 1201 | 120 | Solar | 30B2 | 2025-01-29 | 2025-02-11 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04431 | 1093 | 11.4 | Solar | 18G8 | 2025-01-14 | 2025-01-30 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-12 | [7 empty] | 0 |  |  |  |  | 2025-06-16 | Online | [7 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-04459 | 1027 | 15.2 | Solar | 15A5 | 2025-01-22 | 2025-02-07 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-17 | [7 empty] | 0 |  |  |  |  | 2025-06-18 | Online | [7 empty] | 15A GUNN
WMECO | Pittsfield | ESMAEX-04680 | 1201 | 1999 | Other | 30B3 | 2025-03-24 | 2025-04-16 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 30B OSWALD
WMECO | Hadley | ESMAEX-04586 | 1035 | 15.2 | Battery | 18G4 | 2025-03-04 | 2025-03-10 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-13 | Online | [6 empty] | 13.8 | 18G PODICK
WMECO | Pittsfield | ESMAEX-04470 | 1201 | 120 | Solar | 30B2 | 2025-01-28 | 2025-02-11 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 30B OSWALD
WMECO | Chesterfield | ESMAEX-04473 | 1012 | 30 | Solar & Battery |  | 2025-01-29 | 2025-02-26 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-05 | [7 empty] | 0 | [5 empty] | Construction Stage
WMECO | Hadley | ESMAEX-04478 | 1035 | 225 | Solar | 18G4 | 2025-01-31 | 2025-02-11 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Review | [7 empty] | 18G PODICK
WMECO | Westhampton | ESMAEX-04474 | 1027 | 15.2 | Solar | 15A3 | 2025-01-29 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 | [7 empty] | 0 |  |  |  |  | 2025-06-17 | Online | [7 empty] | 15A GUNN
WMECO | Conway | ESMAEX-04480 | 1341 | 18.48 | Solar | 38A1 | 2025-02-13 | 2025-02-26 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-26 | [7 empty] | 0 | [5 empty] | Compliances Documents | [7 empty] | 38A ASHFIELD
WMECO | Lee | ESMAEX-04484 | 1238 | 51.9 | Solar | 16B5 | 2025-02-04 | 2025-02-19 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-02-21 | [7 empty] | 0 |  |  |  |  | 2025-10-03 | Online | [7 empty] | 16B PLEASANT
WMECO | Hatfield | ESMAEX-04498 | 1038 | 9 | Solar | 18G5 | 2025-02-07 | 2025-03-21 | 31 |  | 31 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 0 |  |  |  |  | 2025-10-09 | Online | [6 empty] | 9 | 18G PODICK
WMECO | Leyden | ESMAEX-04516 | 1301 | 23 | Solar & Battery | 22B7 | 2025-02-24 | 2025-03-10 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-29 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-10 | Online | [6 empty] | 15 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-04497 | 1027 | 10.56 | Solar | 15A3 | 2025-02-07 | 2025-02-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-31 | [7 empty] | 0 |  |  |  |  | 2025-07-17 | Online | [7 empty] | 15A GUNN
WMECO | Hadley | ESMAEX-04495 | 1035 | 450 | Solar | 18G5 | 2025-03-10 | 2025-04-16 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Hinsdale | ESMAEX-04505 | 1235 | 4999 | Solar & Battery | 18C2 | 2025-02-10 | 2025-04-07 | 41 |  | 41 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Berkshire |  | Hold In Queue | 4999 | 18C BERKSHIRE
WMECO | Ludlow | ESMAEX-04504 | 1056 | 5.76 | Solar | 19S3 | 2025-02-10 | 2025-03-03 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-15 | [7 empty] | 0 | [5 empty] | Construction Stage | [7 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-04513 | 1002 | 15.744 | Solar | 17K8 | 2025-02-12 | 2025-02-25 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 | [7 empty] | 0 |  |  |  |  | 2025-10-08 | Online | [7 empty] | 17K AMHERST
WMECO | Conway | ESMAEX-04521 | 1341 | 11.5 | Solar & Battery | 38A1 | 2025-02-14 | 2025-03-24 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-30 | [7 empty] | 0 | [5 empty] | ISA Agreement | [7 empty] | 38A ASHFIELD
WMECO | Greenfield | ESMAEX-04532 | 1301 | 999.45 | Solar & Battery | 22B3 | 2025-03-27 | 2025-04-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 999.45 | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-04542 | 1073 | 20 | Solar | 15A1 | 2025-02-19 | 2025-03-10 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-08-26 | Online | [7 empty] | 15A GUNN
WMECO | Southampton | ESMAEX-04557 | 1073 | 10 | Solar | 15A1 | 2025-02-21 | 2025-03-10 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 | [7 empty] | 0 |  |  |  |  | 2025-09-18 | Online | [7 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-04568 | 1054 | 11.4 | Solar | 18G7 | 2025-02-25 | 2025-03-03 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-29 | Online | [7 empty] | 18G PODICK
WMECO | Pittsfield | ESMAEX-04562 | 1201 | 21.4 | Solar | 15E2 | 2025-03-03 | 2025-03-17 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-17 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-17 | Online
WMECO | Amherst | ESMAEX-04600 | 1002 | 7.6 | Solar | 18G7 | 2025-03-06 | 2025-03-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-17 | Online | [7 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04628 | 1089 | 50 | Solar | 21N5 | 2025-03-14 | 2025-04-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 21N PIPER
WMECO | Pittsfield | ESMAEX-04566 | 1201 | 4350 | Other | 15E2 | 2025-07-22 | 2025-08-13 | 17 |  | 17 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 4350 | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-04570 | 1056 | 8.36 | Solar & Battery | 19S2 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-12 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-26 | Online | [7 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-04573 | 1035 | 11.5 | Solar & Battery | 18G4 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-04578 | 1109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04602 | 1201 | 9.6 | Solar | 30B5 | 2025-03-05 | 2025-03-21 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-17 | Online | [7 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-04617 | 1106 | 5.76 | Solar | 22H11 | 2025-03-11 | 2025-03-17 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-03-27 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-12 | Online | [7 empty] | 22H FRANCONIA
WMECO | Hadley | ESMAEX-04633 | 1035 | 15.2 | Solar | 19B15 | 2025-03-14 | 2025-03-25 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-23 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-08-05 | Online | [7 empty] | 19B MIDWAY
WMECO | Springfield | ESMAEX-04651 | 1129 | 990 | Solar | 27A7 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-04657 | 1035 | 990 | Solar | 17K5 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 17K AMHERST
WMECO | Longmeadow | ESMAEX-04661 | 1106 | 240 | Solar | 22H12 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22H FRANCONIA
WMECO | Savoy | ESMAEX-04663 | 1256 | 5.76 | Solar | 18K4 | 2025-03-19 | 2025-04-09 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-15 | Online |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-04670 | 1027 | 17.6 | Solar & Battery |  | 2025-03-19 | 2025-04-29 | 30 |  | 30 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-20 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | New Ashford | ESMAEX-04682 | 1237 | 9.3 | Solar | 15E1 | 2025-03-24 | 2025-03-31 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-04-02 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Partridge |  |  |  | 15E PARTRIDGE
WMECO | Blandford | ESMAEX-04687 | 1008 | 498 | Solar | 19J2 | 2025-04-01 | 2025-04-16 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Designer Review | [7 empty] | 19J BLANDFORD
WMECO | Hadley | ESMAEX-04703 | 1035 | 22.8 | Solar | 18G5 | 2025-03-28 | 2025-04-15 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-15 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-29 | Online | [7 empty] | 18G PODICK
WMECO | Shelburne Falls | ESMAEX-04706 | 1370 | 498 | Solar | 29R2 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-03 |  |  |  | Complex |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 29R SHELBURNE
WMECO | Deerfield | ESMAEX-04917 | 1342 | 95 | Solar | 22B1 | 2025-05-14 | 2025-07-01 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-04725 | 1027 | 498 | Solar | 15A3 | 2025-07-01 | 2025-08-22 | 39 |  | 39 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Designer Review | [7 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-04764 | 1054 | 13.8 | Solar | 18G7 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [7 empty] | 18G PODICK
WMECO | Southampton | ESMAEX-04748 | 1073 | 1500 | Solar | 15A1 | 2025-04-07 | 2025-04-24 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 15A GUNN
WMECO | South Deerfield | ESMAEX-04749 | 1373 | 15.2 | Solar | 22B1 | 2025-04-07 | 2025-04-15 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-03 | Online | [7 empty] | 22B CUMBERLAND
WMECO | Buckland | ESMAEX-04755 | 1370 | 498 | Solar | 38A1 | 2025-04-23 | 2025-05-08 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 38A ASHFIELD
WMECO | Springfield | ESMAEX-05060 | 1105 | 161 | Solar | 21S12 | 2025-06-13 | 2025-07-02 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-04767 | 1375 | 7.6 | Solar | 18G6 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-19 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-30 | Online | [7 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-04769 | 1077 | 20 | Solar | 29A5 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Northfield | ESMAEX-04863 | 1360 | 11.5 | Solar & Battery | 21B8 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-11 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-02 | Online |  |  |  | Gill-Montague |  |  | 10 | 21B FRENCH KING
WMECO | Hinsdale | ESMAEX-04784 | 1235 | 4999 | Solar & Battery | 18C2 | 2025-04-10 | 2025-04-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Berkshire |  | Hold In Queue | 4999 | 18C BERKSHIRE
WMECO | Lee | ESMAEX-04791 | 1238 | 23 | Solar & Battery | 16B5 | 2025-04-14 | 2025-04-23 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-02 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-28 | Online | [6 empty] | 8 | 16B PLEASANT
WMECO | Easthampton | ESMAEX-04803 | 1027 | 11.5 | Other | 15A2 | 2025-04-17 | 2025-04-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-05 | Online | [7 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-04833 | 1030 | 4.22 | Solar & Battery | 16C17 | 2025-05-01 | 2025-05-12 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 16C AGAWAM
WMECO | Springfield | ESMAEX-04814 | 1105 | 99.9 | Solar |  | 2025-04-18 | 2025-06-30 | 52 |  | 52 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [6 empty] | 100
WMECO | Lanesborough | ESMAEX-04806 | 1237 | 5.76 | Solar | 30B5 | 2025-04-17 | 2025-05-01 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-05 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-08 | Online | [7 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04816 | 1093 | 498 | Solar | 18G8 | 2025-05-12 | 2025-06-01 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Granville | ESMAEX-04868 | 1034 | 7.6 | Solar | 29A5 | 2025-05-02 | 2025-05-20 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-23 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-06-20 | Online |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Agawam | ESMAEX-04834 | 1001 | 15.18 | Solar | 30A1 | 2025-04-25 | 2025-05-14 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-22 | Online | [7 empty] | 30A SILVER
WMECO | Otis | ESMAEX-04873 | 1253 | 16.2 | Solar | 19J4 | 2025-05-05 | 2025-06-11 | 28 |  | 28 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-24 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Hadley | ESMAEX-05100 | 1035 | 20 | Solar | 18G4 | 2025-06-24 | 2025-07-07 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 18G PODICK
WMECO | Cummington | ESMAEX-04865 | 1026 | 24.42 | Solar | 18C1 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-04 | Online |  |  |  | Plainfield |  |  |  | 18C BERKSHIRE
WMECO | Leverett | ESMAEX-04895 | 1054 | 15.2 | Solar | 18G7 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-29 | Online | [7 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-04957 | 1373 | 250 | Solar | 22B3 | 2025-05-20 | 2025-06-01 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-04900 | 1002 | 10 | Solar | 19B16 | 2025-05-12 | 2025-05-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04867 | 1035 | 499 | Solar | 19B15 | 2025-05-16 | 2025-08-22 | 71 |  | 71 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 19B MIDWAY
WMECO | Ashfield | ESMAEX-04941 | 1330 | 10 | Solar | 38A1 | 2025-05-16 | 2025-06-02 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 38A ASHFIELD
WMECO | West Springfield | ESMAEX-05066 | 1089 | 80 | Solar |  | 2025-06-16 |  | -32603 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review
WMECO | Hadley | ESMAEX-05059 | 1035 | 100 | Solar | 17K5 | 2025-06-13 | 2025-06-30 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 17K AMHERST
WMECO | Longmeadow | ESMAEX-04880 | 1106 | 15.2 | Solar | 22H12 | 2025-05-06 | 2025-05-30 | 19 |  | 19 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-03 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-10 | Online | [7 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-04891 | 1002 | 10 | Solar | 19B16 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-27 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [7 empty] | 19B MIDWAY
WMECO | Otis | ESMAEX-04888 | 1253 | 20 | Solar | 19J4 | 2025-05-06 | 2025-06-23 | 35 |  | 35 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Greenfield | ESMAEX-04959 | 1301 | 22.8 | Solar | 22B4 | 2025-05-20 | 2025-06-10 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 22B CUMBERLAND
WMECO | Conway | ESMAEX-04906 | 1341 | 15 | Solar | 38A1 | 2025-05-13 | 2025-05-21 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-07 | Online | [7 empty] | 38A ASHFIELD
WMECO | Bernardston | ESMAEX-04910 | 1337 | 15.2 | Solar | 21C1 | 2025-05-13 | 2025-06-10 | 21 |  | 21 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Pittsfield | ESMAEX-04946 | 1201 | 15.18 | Solar | 19A1 | 2025-05-18 | 2025-06-01 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-07-25 | Online | [7 empty] | 19A DOREEN
WMECO | Hinsdale | ESMAEX-04934 | 1235 | 15.2 | Solar | 18C2 | 2025-05-15 | 2025-06-01 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Dalton-Hinsdale |  |  |  | 18C BERKSHIRE
WMECO | Hadley | ESMAEX-04936 | 1035 | 499 | Other | 17K5 | 2025-08-01 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 499 | 17K AMHERST
WMECO | Ashfield | ESMAEX-04962 | 1330 | 50 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 38A ASHFIELD
WMECO | Ashfield | ESMAEX-04963 | 1330 | 120 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 38A ASHFIELD
WMECO | Pittsfield | ESMAEX-04950 | 1201 | 15.2 | Solar | 30B7 | 2025-05-19 | 2025-06-06 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 30B OSWALD
WMECO | Huntington | ESMAEX-05030 | 1050 | 10 | Solar | 19J5 | 2025-06-09 | 2025-06-26 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-28 | Online
WMECO | West Springfield | ESMAEX-04964 | 1089 | 15.2 | Solar | 16C11 | 2025-05-21 | 2025-06-04 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-11 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-24 | Online | [7 empty] | 16C AGAWAM
WMECO | Lee | ESMAEX-04965 | 1238 | 7.6 | Solar | 16B5 | 2025-05-21 | 2025-06-10 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-18 | Online | [7 empty] | 16B PLEASANT
WMECO | Southampton | ESMAEX-04983 | 1073 | 19 | Solar | 15A1 | 2025-05-27 | 2025-06-05 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [7 empty] | 15A GUNN
WMECO | Granville | ESMAEX-05010 | 1034 | 498 | Solar | 29A5 | 2025-06-26 | 2025-07-11 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Feeding Hills | ESMAEX-05012 | 1030 | 5.76 | Solar | 30A6 | 2025-06-04 | 2025-07-10 | 27 |  | 27 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-31 | Online | [7 empty] | 30A SILVER
WMECO | Hadley | ESMAEX-05024 | 1035 | 225 | Solar | 18G4 | 2025-06-06 | 2025-06-17 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-11 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Pittsfield | ESMAEX-05016 | 1201 | 5.76 | Solar | 30B5 | 2025-06-05 | 2025-06-23 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-11 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 30B OSWALD
WMECO | Southwick | ESMAEX-05043 | 1077 | 15.76 | Solar | 29A1 | 2025-06-10 | 2025-06-24 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-06-27 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Southwick |  |  |  | 29A SOUTHWICK
WMECO | Springfield | ESMAEX-05072 | 1104 | 250 | Solar | 5J9 | 2025-06-19 | 2025-06-30 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [7 empty] | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-05056 | 1027 | 7.6 | Solar | 15A5 | 2025-06-13 | 2025-06-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 15A GUNN
WMECO | Montgomery | ESMAEX-05069 | 1085 | 20 | Solar | 19J5 | 2025-06-16 | 2025-07-01 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | West Springfield | ESMAEX-05093 | 1089 | 160 | Solar |  | 2025-06-20 | 2025-07-25 | 26 |  | 26 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 21N PIPER
WMECO | Hatfield | ESMAEX-05096 | 1038 | 10 | Solar | 18G5 | 2025-06-20 | 2025-07-03 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-05106 | 1035 | 999 | Solar | 18G4 | 2025-09-26 |  | -32677 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [6 empty] | 999 | 18G PODICK
WMECO | Ludlow | ESMAEX-05166 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05168 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05169 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05170 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05171 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05172 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05173 | 1056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-07 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05202 | 1056 | 100 | Solar | 27A6 | 2025-07-15 | 2025-07-25 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-05109 | 1035 | 1750 | Solar | 18G4 | 2025-08-05 | 2025-08-22 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-05102 | 1035 | 499 | Solar | 19B15 | 2025-07-21 | 2025-08-13 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-05107 | 1201 | 11.5 | Solar & Battery | 30B7 | 2025-06-23 | 2025-07-10 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-31 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 30B OSWALD
WMECO | Westhampton | ESMAEX-05132 | 1027 | 50 | Solar |  | 2025-06-26 | 2025-07-16 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Erving | ESMAEX-05120 | 1344 | 5.76 | Solar | 21C8 | 2025-06-25 | 2025-07-10 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage |  |  |  | Gill-Montague |  |  |  | 21C MONTAGUE
WMECO | Lanesborough | ESMAEX-05162 | 1237 | 6.9 | Solar | 15E1 | 2025-07-07 | 2025-07-21 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-22 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage
WMECO | Conway | ESMAEX-05133 | 1341 | 28.33 | Solar | 38A1 | 2025-06-26 | 2025-08-22 | 42 |  | 42 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 38A ASHFIELD
WMECO | Longmeadow | ESMAEX-05136 | 1106 | 22.8 | Solar | 22H13 | 2025-06-27 | 2025-07-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 22H FRANCONIA
WMECO | West Springfield | ESMAEX-05140 | 1089 | 7.6 | Solar | 16C11 | 2025-06-27 | 2025-07-18 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 16C AGAWAM
WMECO | Westhampton | ESMAEX-05160 | 1027 | 498 | Solar | 15A3 | 2025-07-21 | 2025-08-13 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 15A GUNN
WMECO | Colrain | ESMAEX-05161 | 1340 | 15.2 | Solar | 29R2 | 2025-07-07 | 2025-07-18 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-10-10 | Online | [7 empty] | 29R SHELBURNE
WMECO | Hadley | ESMAEX-05179 | 1035 | 7.6 | Solar | 17K5 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-05197 | 1077 | 3340 | Solar | 29A1 | 2025-09-24 | 2025-10-15 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 29A SOUTHWICK
WMECO | Turners Falls | ESMAEX-05407 | 1376 | 483 | Solar | 21C2 | 2025-09-02 | 2025-09-29 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 21C MONTAGUE
WMECO | Russell | ESMAEX-05189 | 1071 | 15.2 | Solar | 19J2 | 2025-07-10 | 2025-07-14 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-05194 | 1201 | 10.89 | Solar | 30B7 | 2025-07-11 | 2025-07-24 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-12 | Online | [7 empty] | 30B OSWALD
WMECO | Huntington | ESMAEX-05195 | 1050 | 20.736 | Solar | 19J5 | 2025-07-11 | 2025-07-22 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Amherst | ESMAEX-05190 | 1002 | 5.76 | Solar | 17K1 | 2025-07-10 | 2025-07-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-13 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-05198 | 1201 | 400 | Solar | 19A8 | 2025-08-08 | 2025-08-22 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 19A DOREEN
WMECO | Agawam | ESMAEX-05206 | 1001 | 7.6 | Solar | 30A3 | 2025-07-15 | 2025-07-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-10 | Online | [7 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05282 | 1002 | 37.3 | Solar | 17K2 | 2025-08-05 | 2025-09-08 | 25 |  | 25 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-05235 | 1035 | 5.76 | Solar | 18G4 | 2025-07-28 | 2025-07-29 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-05214 | 1373 | 19 | Solar | 22B3 | 2025-07-18 | 2025-07-18 | 1 |  | 1 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-07-21 |  |  |  | Expedited |  |  |  | 0 |  |  |  |  | 2025-09-05 | Online | [6 empty] | 19 | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-05221 | 1002 | 19.032 | Solar | 18G7 | 2025-07-22 | 2025-07-29 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Meter | [7 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-05215 | 1056 | 11 | Solar | 19S3 | 2025-07-18 |  | -32627 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 19S LUDLOW
WMECO | Granville | ESMAEX-05260 | 1034 | 11.5 | Other | 29A5 | 2025-07-31 | 2025-08-25 | 18 |  | 18 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [6 empty] | 0 | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-05251 | 1035 | 7.6 | Solar | 19B15 | 2025-07-29 | 2025-08-04 | 5 |  | 5 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 19B MIDWAY
WMECO | Northfield | ESMAEX-05292 | 1360 | 11.4 | Solar | 21B8 | 2025-08-07 | 2025-08-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold |  |  |  | Gill-Montague |  |  | 9 | 21B FRENCH KING
WMECO | Ludlow | ESMAEX-05272 | 1056 | 4988 | Solar & Battery | 19S3 | 2025-08-04 | 2025-08-22 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 4988 | 19S LUDLOW
WMECO | Amherst | ESMAEX-05291 | 1002 | 15.2 | Solar | 17K8 | 2025-08-07 | 2025-08-20 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 17K AMHERST
WMECO | Worthington | ESMAEX-05332 | 1098 | 7.6 | Solar & Battery | 18C2 | 2025-08-18 | 2025-08-26 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-26 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 18C BERKSHIRE
WMECO | Deerfield | ESMAEX-05268 | 1342 | 498 | Solar | 18G3 | 2025-08-13 | 2025-09-03 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 18G PODICK
WMECO | Whately | ESMAEX-05270 | 1093 | 166 | Solar | 18G8 | 2025-08-15 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 18G PODICK
WMECO | Plainfield | ESMAEX-05280 | 1070 | 4950 | Solar | 18K3 | 2025-10-02 | 2025-10-21 | 14 |  | 14 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 18K PLAINFIELD
WMECO | Greenfield | ESMAEX-05511 | 1301 | 67.3 | Solar | 22B8 | 2025-09-29 | 2025-10-08 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-05297 | 1073 | 11.4 | Solar | 15A1 | 2025-08-08 | 2025-09-04 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 15A GUNN
WMECO | Whately | ESMAEX-05315 | 1093 | 250 | Solar | 18G6 | 2025-10-08 | 2025-10-21 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 18G PODICK
WMECO | Otis | ESMAEX-05411 | 1253 | 25 | Solar | 19J4 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement |  |  |  | Blandford |  |  | 20 | 19J BLANDFORD
WMECO | Springfield | ESMAEX-05318 | 1101 | 11.5 | Other | 22H15 | 2025-08-14 | 2025-08-26 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 22H FRANCONIA
WMECO | West Springfield | ESMAEX-05357 | 1089 | 5.376 | Battery | 16C11 | 2025-08-22 | 2025-09-18 | 20 |  | 20 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [7 empty] | 16C AGAWAM
WMECO | Greenfield | ESMAEX-05340 | 1301 | 240 | Solar | 22B7 | 2025-08-27 | 2025-09-12 | 13 |  | 13 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-05510 | 1105 | 50 | Solar |  | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Bernardston | ESMAEX-05356 | 1337 | 10 | Solar | 21B8 | 2025-08-22 | 2025-09-03 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-05361 | 1201 | 15.2 | Solar | 19A7 | 2025-08-25 | 2025-08-26 | 2 |  | 2 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-28 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 19A DOREEN
WMECO | Chicopee | ESMAEX-05362 | 1013 | 980 | Solar | 21N7 | 2025-10-31 |  | -32702 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 21N PIPER
WMECO | Agawam | ESMAEX-05364 | 1001 | 480 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 30A SILVER
WMECO | Bernardston | ESMAEX-05375 | 1337 | 499 | Solar | 21C1 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 21C MONTAGUE
WMECO | Southwick | ESMAEX-05377 | 1077 | 23 | Battery | 29A5 | 2025-08-26 | 2025-09-03 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold |  |  |  | Southwick |  |  | 13.4 | 29A SOUTHWICK
WMECO | Savoy | ESMAEX-05391 | 1256 | 4980 | Solar & Battery | 18C1 | 2025-09-25 | 2025-10-15 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 18C BERKSHIRE
WMECO | Sunderland | ESMAEX-05409 | 1375 | 11.5 | Other | 18G6 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents | [6 empty] | 20 | 18G PODICK
WMECO | Montague | ESMAEX-05600 | 1351 | 21.4 | Solar |  | 2025-10-17 | 2025-10-28 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Longmeadow | ESMAEX-05437 | 1106 | 15.2 | Solar | 22H11 | 2025-09-10 | 2025-09-22 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 22H FRANCONIA
WMECO | Greenfield | ESMAEX-05464 | 1301 | 150 | Solar | 22B6 | 2025-09-16 |  | -32669 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 22B CUMBERLAND
WMECO | Middlefield | ESMAEX-05454 | 1243 | 22.8 | Solar | 18C2 | 2025-09-15 | 2025-09-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Construction Stage | [7 empty] | 18C BERKSHIRE
WMECO | Northfield | ESMAEX-05455 | 1360 | 15.76 | Solar | 21B8 | 2025-09-15 | 2025-09-29 | 11 |  | 11 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold |  |  |  | Gill-Montague |  |  |  | 21B FRENCH KING
WMECO | Easthampton | ESMAEX-05559 | 1027 | 50 | Solar |  | 2025-10-09 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Longmeadow | ESMAEX-05468 | 1106 | 15.2 | Solar | 22H18 | 2025-09-17 | 2025-09-29 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-05474 | 1201 | 400 | Solar | 15E2 | 2025-10-15 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-05477 | 1056 | 20 | Solar & Battery | 19S1 | 2025-09-17 | 2025-09-25 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-31 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [6 empty] | 20 | 19S LUDLOW
WMECO | Longmeadow | ESMAEX-05480 | 1106 | 21.25 | Solar | 22H13 | 2025-09-17 | 2025-09-30 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement | [7 empty] | 22H FRANCONIA
WMECO | Southwick | ESMAEX-05487 | 1077 | 450 | Solar | 29A1 | 2025-10-24 |  | -32697 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-05493 | 1237 | 23 | Other | 30B5 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-05513 | 1089 | 30 | Solar |  | 2025-09-25 | 2025-10-16 | 16 |  | 16 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review
WMECO | Southwick | ESMAEX-05501 | 1077 | 160 | Solar |  | 2025-09-23 | 2025-10-08 | 12 |  | 12 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold
WMECO | Easthampton | ESMAEX-05523 | 1027 | 11.5 | Solar & Battery | 15A1 | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 15A GUNN
WMECO | Lanesborough | ESMAEX-05508 | 1237 | 6 | Solar | 15E1 | 2025-09-24 | 2025-10-14 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Exhibit D Agreement
WMECO | Easthampton | ESMAEX-05524 | 1027 | 11.5 | Solar & Battery | 15A5 | 2025-09-29 | 2025-10-02 | 4 |  | 4 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 15A GUNN
WMECO | Hatfield | ESMAEX-05525 | 1038 | 19.8 | Solar |  | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | Compliances Documents
WMECO | Bernardston | ESMAEX-05531 | 1337 | 15.2 | Solar | 21C1 | 2025-10-01 |  | -32680 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | 21C MONTAGUE
WMECO | Amherst | ESMAEX-05535 | 1002 | 240 | Solar | 17K3 | 2025-10-02 | 2025-10-15 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-05536 | 1238 | 249 | Solar | 16B5 | 2025-10-03 | 2025-10-14 | 8 |  | 8 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 16B PLEASANT
WMECO | Agawam | ESMAEX-05539 | 1001 | 70 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 2025-11-06 |  |  |  | Expedited |  |  |  | 0 | [5 empty] | ISA Agreement | [7 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05613 | 1002 | 18.666 | Solar | 17K2 | 2025-10-23 |  | -32696 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-05552 | 1223 | 4999 | Solar | 16B1 | 2025-10-06 | 2025-10-24 | 15 |  | 15 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Complex |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 4999 | 16B PLEASANT
WMECO | Otis | ESMAEX-05624 | 1253 | 11.52 | Solar | 19J4 | 2025-10-23 | 2025-11-05 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Otis | ESMAEX-05593 | 1253 | 13.2 | Solar | 19J4 | 2025-10-16 | 2025-10-28 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review |  |  |  | Blandford |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-05631 | 1201 | 23 | Solar | 30B7 | 2025-10-24 | 2025-11-06 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [6 empty] | 20 | 30B OSWALD
WMECO | South Deerfield | ESMAEX-05590 | 1373 | 17.16 | Solar | 18G3 | 2025-10-15 | 2025-10-22 | 6 |  | 6 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Supplemental Review | [7 empty] | 18G PODICK
WMECO | Greenfield | ESMAEX-05596 | 1301 | 50 | Solar |  | 2025-10-16 | 2025-10-28 | 9 |  | 9 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold
WMECO | Deerfield | ESMAEX-05662 | 1342 | 80 | Solar | 22B3 | 2025-10-31 |  | -32702 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Application Review | [7 empty] | 22B CUMBERLAND
WMECO | Southwick | ESMAEX-05612 | 1077 | 22.8 | Solar | 29A5 | 2025-10-23 |  | -32696 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | 29A SOUTHWICK
WMECO | Pittsfield | ESMAEX-05603 | 1201 | 15.2 | Solar | 19A1 | 2025-10-20 | 2025-10-31 | 10 |  | 10 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 19A DOREEN
WMECO | Gill | ESMAEX-05628 | 1354 | 17.6 | Solar | 21B8 | 2025-10-24 |  | -32697 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | CIP On Hold | [7 empty] | 21B FRENCH KING
WMECO | Pittsfield | ESMAEX-05629 | 1201 | 5.76 | Solar | 30B1 | 2025-10-24 | 2025-10-28 | 3 |  | 3 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | Expedited |  |  |  | 0 | [5 empty] | Technical Review | [7 empty] | 30B OSWALD
Note on AC63: Renata J Peloquin: Check and Study were NOT stamped with date received.

## Holidays
2012-01-02
2012-01-16
2012-02-20
2012-03-17
2012-04-16
2012-05-28
2012-06-17
2012-07-04
2012-09-03
2012-10-08
2012-11-12
2012-11-22
2012-11-23
2012-12-25
2013-01-01
2013-01-21
2013-02-18
2013-03-17
2013-04-15
2013-05-27
2013-06-17
2013-07-04
2013-09-02
2013-10-14
2013-11-11
2013-11-28
2013-11-29
2013-12-25
2014-01-01
2014-01-20
2014-02-17
2014-03-17
2014-04-21
2014-05-26
2014-06-17
2014-07-04
2014-09-01
2014-10-13
2014-11-11
2014-11-27
2014-12-25
2015-01-01
2015-01-19
2015-02-16
2015-03-17
2015-04-20
2015-05-25
2015-06-17
2015-07-03
2015-09-07
2015-10-12
2015-11-11
2015-11-26
2015-12-25
2016-01-01
2016-01-18
2016-02-15
2016-03-17
2016-04-18
2016-05-30
2016-06-17
2016-07-04
2016-09-05
2016-10-10
2016-11-11
2016-11-24
2016-12-26
2017-01-02
2017-01-16
2017-02-20
2017-04-17
2017-05-29
2017-07-04
2017-09-04
2017-10-09
2017-11-10
2017-11-23
2017-12-25
2018-01-01
2018-01-15
2018-02-19
2018-03-16
2018-04-16
2018-05-28
2018-07-04
2018-09-03
2018-10-08
2018-11-12
2018-11-22
2018-12-24
2018-12-25
2019-01-01
2019-01-21
2019-02-18
2019-03-18
2019-04-15
2019-05-27
2019-07-04
2019-09-02
2019-10-14
2019-11-11
2019-11-28
2019-12-24
2019-12-25
2020-01-01
2020-01-20
2020-02-17
2020-03-17
2020-04-20
2020-05-25
2020-07-03
2020-09-07
2020-10-12
2010-11-11
2020-11-26
2020-12-24
2020-12-25
2021-01-01
2021-01-18
2021-01-20
2021-02-15
2021-03-17
2021-04-19
2021-05-31
2021-06-18
2021-07-05
2021-09-06
2021-10-11
2021-11-11
2021-11-25
2021-12-24